## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
January 14, 2021

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2020 Results
    2020 Releases
    2020 Project Spending
  2021 Release Targets
  ESR and DGR Pre-Passport Projects
  Passport Impacts 2021–2024
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2020 December Release – R6 – 12/8/2020 – 12/10/2020 Complete
  SCR806 – Adding QSE and DME Information to Disclosure Reports
  NPRR978(b) – Alignment with Amendments to PUCT Substantive Rule 25.505
    Non-Forecast Zone scope
2021 January Release – Off-Cycle – 1/1/2021 Complete
  NPRR1055 – Market Notice and ERCOT Discretion re Late-Filed NOIE Eligibility Attestations for PTP Obligations with Links to an Option Bid Awards
MMS/OS Tech Refresh go-live still TBD In Flight
2021 February Release – R1 – 2/4/2020 – 2/6/2020 In Flight
  NPRR902(a) – ERCOT Critical Energy Infrastructure Information
    New MPIM Market Participant role for ECEII
  NPRR974 – Capacity Insufficiency Operating Condition Notice (OCN) Transparency
  NPRR978(c) – Alignment with Amendments to PUCT Substantive Rule 25.505
    Forecast Zone scope
  NOGRR195 – Generator Voltage Control Tolerance Band
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2020 Releases – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/4 – 2/6 | April 3/31 – 4/2 | May 5/26 – 5/29 | August 8/4 – 8/6 | October 10/13 – 10/15 | December 12/8 – 12/10
NPRR873 SCR797 NPRR877 Ph2 NPRR968 NPRR943 EMIL Web Interface NPRR863 FFR NPRR960 NOGRR187 OBDRR011 | SCR802 NPRR928 NPRR929 NPRR978(a) NPRR988 NPRR953 | NPRR856 NPRR884 OBDRR006 SCR803 NPRR887 NPRR907 NPRR985 RMGRR163 NPRR837 NPRR930(a) NPRR933 RRGRR021 | NPRR935(a) NPRR951 NPRR977 NPRR955 NOGRR183 SCR781(a) RRGRR016 RRGRR019 | MIS Go-Live RIOO R2 MMS/OS Refresh | SCR806 NPRR978(b)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
3/1
NPRR930(a) – O&M portion
NPRR935(a) – Sections 4.2.2 (1) (6), 4.2.5
NPRR935(b) – Sections 2.1, 2.2, 4.2.3
NPRR978(a) – Initial report decommissions
NPRR978(b) – Non-Forecast Zone scope
PGRR070(b) – Remaining PGRR language
SCR781(a) – View / Edit capability
MMS/OS Upgrade “Chill”
MMS/OS Upgrade “Freeze”
ü
ü
ü
December
Off-Cycle
1/1
1/19
E
ü
ü
ü
CMM Release 2a
1/30
8/1
November
RIOO – 9/3
RARF Go-Live - View/Update
ü
ü
ü
ü
ü
ü
ü
ü
ü
5/1
ü
7/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
10/1
ü
ü
ü
ü
ü
ü

## Slide 5: 2020 Project Spending
2020 PPL Budget = $29.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 6: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/2 – 2/4 | April 3/30 – 4/1 | May 5/25 – 5/27 | July 7/27 – 7/29 | October 10/5 – 10/7 | December 12/7 – 12/9
NPRR902(a) NPRR974 NPRR978(c) NOGRR195 NPRR1055 | NPRR902(b) NPRR905 NPRR971 NPRR974 NPRR978(c) NPRR986 NPRR998 NPRR1043 | NPRR904 NPRR905 NPRR1006 NPRR930 NPRR998 NPRR1019 OBDRR009 | NPRR867 | NPRR484 NPRR829 SCR781(b) | FFR Advancement (NPRR863 FFR) NPRR1015 NPRR863 ECRS NPRR1015
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR902(a) – ECEII Market Participant MPIM role
NPRR902(b) – MIS links updated for ECEII reports
NPRR978(c) – Forecast Zone scope
SCR781(b) – “Add” capability
TBD Items | 2018 | 2019 / 2020 / 2021
 | NPRR825(b), NPRR867, NPRR841 | NPRRs: 826, 857, 879, 885, 918, 935(b), 936, 939, 941, 962, 965, 1020, 1030, PGRR066, SCR799, SCR800, SCR805
E
E
P
E
P
I
I
P
E
E
E
E
E
E
On Hold
2024 Go-Lives
RIOO – Q4 2021
RARF Add Functionality Go-Live
TBD Go-Live
E
SCR804
Go-Live – 3/18/2021
TO training in Feb.
P
I
Impacts of the MMS/OS Tech Refresh delay on other projects is being evaluated
ECMS – May
Market Info & Grid Info to new platform
Improved dashboards and displays
Replace NoticeBuilder
ECMS – Dec.
Combine ERCOT.com and MIS
Improved search
New navigation
TBD Go-Lives Due to MMS/OS Delay
NPRR904 / NPRR1006 / OBDRR009
NPRR930
NPRR1019
Risk of Delay to R3
NPRR986 / NPRR971 / NPR1043
1/1
ü
June
P

## Slide 7: ESR and DGR Pre-Passport Projects
On 10/16/2020, ERCOT initiated 2 projects to deliver several Revision Requests relating to ESR and DGR
  PR353-01 BES Combo Model Implementation (now in Planning phase)
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NOGRR204 – Related to NPRR989, BESTF-1
    NOGRR208 – Related to NPRR1002, BESTF-5
    OBDRR017 – Related to NPRR987, BESTF-3
    PGRR081 – Related to NPRR1026, BESTF-7
    RRGRR023 – Related to NPRR1002, BESTF-5
  PR354-01 DGR/DESR Implementation (now in Planning phase)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources (DESRs)
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995 Implementation
    NOGRR212 – Related to NPRR1016
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process *
    RRGRR026 – Related to NPRR1016, Clarify Requirements for DGRs and DESRs
Since these projects are merging multiple RRs, it will take a few months before target go-live dates are established for these two projects (gate to Execution target is February 2021)
BES: Battery Energy Storage
DGR: Distributed Generation Resource
ESR: Energy Storage Resource
Red text = New addition since last report

## Slide 8: Passport Impacts 2021–2024
RTC NPRRs were approved by the Board in December 2020
  RTC is the largest component of the Passport program
Impact Analysis postings will begin reporting potential Passport impacts
  Passport Schedule Risk Assessment
    Risk to Passport project if Revision Request is implemented in 2021-2024
    IA will report one of three risk conclusions
      No risk to Passport schedule
      Potential risk to Passport schedule
      Significant risk to Passport schedule
  Passport Cost Impact (optional analysis from Passport Program)
    Additional cost if implemented in current systems AND in Passport systems under development
Passport assessment of “Not Started” Revision Requests
  Passport requirements are in progress
  Teams need to understand which “Not Started” RRs need to be included in requirements
  ERCOT is working on a recommendation for the sequencing of these items
  Results to be brought to an upcoming PRS meeting (target = February 2021)

## Slide 9: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR995 | RTF-6 Create Definition and Terms for Settlement Only Energy Storage |  |  | $800k-$1.2M, 20-30 months Impact Areas: RIOO, S&B, MMS, EMS, NMMS, Reporting Risk to Passport schedule due to resource requirements
NPRR1024 | Determination of Significance with Respect to Price Correction | N/A | N/A | <$5k O&M, 1-2 months Impact Areas: Reporting
NPRR1034 | Frequency-Based Limits on DC Tie Imports or Exports | 2021 | 3280 | $50k–$70k, 5–7 months Impact Areas: Grid Displays, MMS, NoticeBuilder, Reporting Add to end of 2021 list (funded by Southern Cross – work into the plan at a time consistent with conditions outlined in the IA [similar to NPRR857])
NPRR1040 | Compliance Metrics for Ancillary Service Supply Responsibility | 2021 | 3290 | $20k-$30k, 3-5 months Impact Areas: Reporting Add to end of 2021 list – Work into plan without disrupting other projects
NPRR1054 | Removal of Oklaunion Exemption Language | 2021 | 3300 | $10k-$15k, 3-4 months Impact Areas: S&B, Integration Add to end of 2021 list – Work into plan without disrupting other projects
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3280
Next available Rank in Regulatory = 320
Options for…
Recommend tabling
See ERCOT Comments