## Slide 1
Passport Update
Matt Mereness
ERCOT Compliance Director
TAC
January 27, 2021

## Slide 2: Passport Update
Scope of Passport
Passport Sequence of Milestones through 2024
Passport Near-Term Milestones through 2021
Current Status
Future NPRR consideration

## Slide 3: Passport Scope and Delivery
EMS Technology Foundation Upgrade
2019
2020
2024
2021
2022
2023
Real-Time Co-optimization
RTC
Key Principles
RTC
NPRR review
Battery Energy Storage Resources
BES Key Topic Concepts
BES
NPRR review
Distribution Generation Resources
DGR Workshops
DGR
NPRR review
“Pre-Passport” deliveries before 2024:
DGR enhancements to re-open registration
Battery storage functionality enhancements
ERCOT Contingency Reserve Service
New 10-minute Ancillary Service product defined in NPRR863

## Slide 4: Real-Time Co-optimization Scope
Real-Time Market will be expanded to clear Energy and Ancillary Services (AS) every five minutes
  Already in place at most ISOs; ERCOT currently co-optimizes in Day-Ahead Market
RTC design also creates benefits and changes:
  Provides ability for ERCOT to select and dispatch full capability of Resources (previously AS capacity was managed by MPs based on their Day-Ahead Market awards).
  Retires an adjustment period AS market
  Reliability Unit Commitment will also co-optimize the full capability of Resources
  Day-Ahead Market will allow virtual AS Offers
Operating Reserve Demand Curve (ORDC) price adders will be discontinued, and replaced by converting ORDC into AS Demand Curves for each AS and reflected in real-time energy and AS prices.

## Slide 5: Passport Storage and Distribution Level Scope
Modeling and Dispatching Battery Energy Storage as a single device
  Same device can be a Load when charging and a Generator when discharging.
Distribution-level Generator or Energy Storage
  Device can be within Distribution system and still be dispatched by ERCOT with improved mapping techniques.

## Slide 6: Passport Protocol Scope
Design | Revision Requests*
Real-Time Co-optimization | NPRR1007 – 1013
Battery Energy Storage Resources | NPRR1014 & 1029
Distribution Generation Resources | NPRR1016 (mapping improvements only)
ERCOT Contingency Reserve Service | NPRR863 (ECRS only)
  Merging these requirements into design scenarios, for example:
  SCED is being re-developed to economically co-optimize and award all Ancillary Services (an RTC requirement), including the clearing of a new ESR type (Battery Energy Storage Resource requirement where a single model Resource can inject or withdraw), and the ESR is within the Distribution system (per Distribution Generation Resource requirement), and can be awarded a new 10-minute Ancillary Service (ECRS requirement).
*Additional supporting Market Guide changes are also within Passport scope.

## Slide 7: Passport Sequence of Milestones through 2024
Unit/Functional testing
Pre-Passport
Last major release date for EMS/MMS/S&B projects
EMS Upgrade
Convert Gen/SCADA to C++
EMS/MMS CIM16 Network Model Go-Live
Last date for Go/No-Go for Combined Passport EMS Upgrade
Other EMS Subsystem Dev and Customs
Snapshot of EMS Upgrade Codestream without Passport
Passport Market Design
Core - EMS/MMS/SB
Support- OS/Reg…
Report- EIS/MIS
Core Business Reqts
Support Business Reqts
Report Business Reqts
Design/Development/UnitTest
Design/Development/UnitTest
Design/Development/UnitTest
Integration Testing
Begin Early SCED Testing (EMS/MMS)
Begin iTest EMS/MMS/S&B
Begin End-to-end Testing
Market
Trials
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Market Readiness & Go-Live
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Develop/Publish MP Specifications
Develop Market Trials Plans
Passport Cutover/Go-Live
Deliver Market Training
Market Readiness Metrics
Passport Implementation Task Force
Pre-Passport Deliveries into production before Passport
Planned milestone
Estimated milestone

## Slide 8: Passport Sequence of Milestones through 2024
Unit/Functional testing
Pre-Passport
Last major release date for EMS/MMS/S&B projects
EMS Upgrade
Convert Gen/SCADA to C++
EMS/MMS CIM16 Network Model Go-Live
Last date for Go/No-Go for Combined Passport EMS Upgrade
Other EMS Subsystem Dev and Customs
Snapshot of EMS Upgrade Codestream without Passport
Passport Market Design
Core - EMS/MMS/SB
Support- OS/Reg…
Report- EIS/MIS
Core Business Reqts
Support Business Reqts
Report Business Reqts
Design/Development/UnitTest
Design/Development/UnitTest
Design/Development/UnitTest
Integration Testing
Begin Early SCED Testing (EMS/MMS)
Begin iTest EMS/MMS/S&B
Begin End-to-end Testing
Market
Trials
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Market Readiness & Go-Live
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Develop/Publish MP Specifications
Develop Market Trials Plans
Passport Cutover/Go-Live
Deliver Market Training
Market Readiness Metrics
Passport Implementation Task Force
Pre-Passport Deliveries into production before Passport
Planned milestone
Estimated milestone
Software Development
&
Unit Testing
Market Trials
&
Go-Live
Cutover
Business Requirements
&
Design
Integration
&
End-to-End Testing

## Slide 9: Passport Near-Term Milestones through 2021
GridOps
Package
EMS/OTS Business Reqts
NMMS/RIOO Business Reqts
PI and Operator Display Business Reqts
1Q2021
Jan
Feb
Mar
2Q2021
Apr
May
Jun
3Q2021
Jul
Aug
Sep
4Q2021
Oct
Nov
Dec
MarketOps
Package
MMS/PVT Business Reqts
SupportOps
Package
S&B/DataAgg/CSI-S&B Business Reqts
CMM / CMM-CSI Business Reqts
Siebel Business Reqts
Report/Data Package
DAIP/Cognos CDR/ EIS/ISM Business Reqts
TIBCO Business Reqts
MIS/Dashboards/ERCOT.com Business Reqts
EMS Upgrade
Convert Gen/SCADA to C++
EMS/MMS CIM16 Network Model Go-Live
Other EMS Subsystem Dev and Customs
Market Readiness & Go-Live
Develop and Publish MP Specifications
Potentially Begin Passport Implementation Task Force
Outage Scheduler Business Reqts

## Slide 10: Passport Current Status
Business Requirements for core Passport systems are in-flight
  Market Management System (MMS) and Settlements & Billing (S&B) Business Requirements are slightly ahead of schedule.
  Energy Management System (EMS) Business Requirements have resource constraints, but are currently recoverable.
EMS Upgrade
  Vendor has been delivering software releases on-schedule
  ERCOT EMS Upgrade team is on-schedule
Budget
  More details in February 2021 Board F&A Report

## Slide 11: Future NPRR consideration
Limited resources and project funding for initiatives beyond the large projects identified below until 2024.
  FFR Advancement BES Pre-Passport Project
  DGR Pre-Passport Passport Program
Strict controls are needed to ensure delivery of these large projects on time and within budget.
ERCOT wants to partner with PRS and TAC on most effective approach for managing the current and future NPRRs.

## Slide 12: Future NPRR consideration
ERCOT recommends the following control for TAC and PRS consideration
  Going forward, ERCOT will file comments on stakeholder Revision Requests identifying high-level assessment of impacts and risks to Passport Program delivery.
  ERCOT comments will provide a recommendation for “before or after” Passport Program delivery.
  If impact to Passport Program delivery, Sponsor can decide next step for the Revision Request – withdraw or pursue.
  If pursue, then PRS may recommend approval and/or tabling of the Revision Request. If approved by PRS, ERCOT will file additional comments indicating that Impact Analysis will not be completed until ERCOT has bandwidth to consider post-Passport Program efforts.
Benefits and Exceptions on next page….

## Slide 13: Future NPRR consideration
Benefits of this recommendation:
  Allows continued discussion of future policy changes with some direction of regulatory certainty with PRS approval.
  Prevents gray-boxes within gray-boxes in Protocols and reduces administrative or substantive clean-up Revision Requests in the future.
  Avoids outdated Impact Analyses which can create risk to future resource and budget issues.
  Helps manage Project Priority List (PPL) more effectively with post-Passport Program changes.
Most Likely Exceptions to this recommendation:
  Revision Requests that are critical to reliability or instructed by PUCT.
Additional recommended control for TAC consideration:
  Be cognizant of workshops or other focused initiatives on Passport related systems (EMS, MMS and S&B) that rely heavy on ERCOT SMEs.
ERCOT welcomes feedback from TAC and PRS on these recommendations or alternatives.

## Slide 14: Wrap-up and Questions
ERCOT plans to present Board updates related to Passport at TAC meetings prior to Board meetings
ERCOT will start working with TAC leadership on Passport Implementation Working Task Force
ERCOT will continue work to evaluate delivery sequences of approved NPRRs and processes for future NPRRs that overlap with Passport scope or resources
Final questions?