## Contents
This data file was used to create the Feburary 2021 SAWG meeting GINR Analysis presentation.
http://www.ercot.com/calendar/2021/2/5/220195-SAWG
Table of Contents
Tab | Notes
Planned Projects View 1 | Planned projects listed in recent summer final SARA reports. Includes a retrospective analysis on which projects come online as expected by their projected in-service date.
Planned Projects View 2 | Planned projects listed in recent CDR and summer final SARA reports. Includes a retrospective analysis on which projects come online as expected by their projected in-service date.
Summer 2020 COD Delays | Shows the Projected Commercial Operations Date (COD) delays faced by summer 2020 SARA planned projects over the course of the Summer 2020 season.
COD Forecast Issues | Data for the various issues with trying to forecast planned project COD delays.
Notable 2020 Queue Trends | Data for the various queue trends during 2020 highlighted in the presentation.

## Planned Projects View 1
REPORT ID | FULL REPORT NAME | ORDER ID | UNIT NAME | INR | UNIT CODE | COUNTY | FUEL | ZONE | START YEAR | SUMMER NAMEPLATE CAPACITY (MW) | SUMMER CAPACITY CONTRIBUTION % | SUMMER CONTRIBUTION MW | PROJECTED COD (FROM REPORT) | ACTUAL IN-SERVICE DATE (as of 1/1/21) | CURRENT PROJECT STATUS (as of 1/1/21) | APPROVED FOR SYNCHRONIZATION (as of 1/1/21) | WAS IN-SERVICE BEFORE START OF SUMMER? | SUMMER CUTOFF DATE | NOTES ID | NOTES
1 | Final Summer 2017 SARA | 1 | COLORADO BEND II | 17INR0007 |  | WHARTON | GAS | SOUTH | 2017 | 1088 | 100% | 1088 | 2017-06-01 | 2017-06-23 | OPERATIONAL | 2017-02-10 | No | 2017-06-01 | O2 | operational by July 1st
1 | Final Summer 2017 SARA | 2 | PHR PEAKERS [BAC_CTG1-6] | 14INR0038 |  | GALVESTON | GAS | HOUSTON | 2017 | 324 | 100% | 324 | 2017-03-31 | 2018-07-11 | OPERATIONAL | 2017-03-22 | No | 2017-06-01 | O4 | operational after August 1st
1 | Final Summer 2017 SARA | 3 | WOLF HOLLOW 2 | 17INR0009 |  | HOOD | GAS | NORTH | 2017 | 1069 | 100% | 1069 | 2017-05-01 | 2017-05-02 | OPERATIONAL | 2017-01-05 | Yes | 2017-06-01 | O1 | operational by June 1st
1 | Final Summer 2017 SARA | 4 | SALT FORK WIND | 14INR0062 |  | GRAY | WIND | PANHANDLE | 2017 | 174 | 14% | 24.36 | 2017-04-01 | 2017-06-13 | OPERATIONAL | 2016-11-07 | No | 2017-06-01 | O2 | operational by July 1st
1 | Final Summer 2017 SARA | 5 | FALVEZ ASTRA W | 15INR0074 |  | DEAF SMITH | WIND | PANHANDLE | 2017 | 163.2 | 14% | 22.848 | 2017-05-04 | 2017-05-24 | OPERATIONAL | 2017-03-01 | Yes | 2017-06-01 | O1 | operational by June 1st
1 | Final Summer 2017 SARA | 6 | CHAPMAN RANCH WIND I | 16INR0055 |  | NUECES | WIND-C | COASTAL | 2017 | 250 | 58% | 145 | 2017-05-31 | 2017-10-27 | OPERATIONAL | 2017-07-11 | No | 2017-06-01 | O4 | operational after August 1st
1 | Final Summer 2017 SARA | 7 | FS BARILLA SOLAR 1B [HOVEY_UNIT2] | 12INR0059b |  | PECOS | SOLAR | WEST | 2017 | 7.4 | 77% | 5.698 | 2017-04-15 | N/A | PLANNED | N/A | No | 2017-06-01 | P2 | COD delays without part 2 approval
1 | Final Summer 2017 SARA | 8 | OCI ALAMO 6 (WEST TEXAS PHASE II) | 15INR0070_1b |  | PECOS | SOLAR | WEST | 2017 | 49 | 77% | 37.73 | 2017-04-28 | 2017-10-05 | OPERATIONAL | 2017-08-24 | No | 2017-06-01 | O4 | operational after August 1st
1 | Final Summer 2017 SARA | 9 | BNB LAMESA SOLAR | 16INR0023 |  | DAWSON | SOLAR | WEST | 2017 | 101.6 | 77% | 78.232 | 2017-04-15 | 2018-02-21 | OPERATIONAL | 2017-02-14 | No | 2017-06-01 | O4 | operational after August 1st
1 | Final Summer 2017 SARA | 10 | SOLAIREHOLMAN 1 | 15INR0061 |  | BREWSTER | SOLAR | WEST | 2017 | 50 | 77% | 38.5 | 2017-04-25 | 2018-05-24 | OPERATIONAL | 2017-03-30 | No | 2017-06-01 | O4 | operational after August 1st
2 | Final Summer 2018 SARA | 11 | DENTON ENERGY CENTER | 18INR0013 |  | DENTON | GAS | NORTH | 2018 | 226 | 100% | 226 | 2018-06-22 | 2018-07-11 | OPERATIONAL | 2018-04-16 | No | 2018-06-01 | O3 | operational by August 1st
2 | Final Summer 2018 SARA | 12 | FRIENDSWOOD G | 13INR0049 |  | HARRIS | GAS | HOUSTON | 2018 | 119 | 100% | 119 | 2018-05-30 | 2018-11-08 | OPERATIONAL | 2018-05-09 | No | 2018-06-01 | O4 | operational after August 1st
2 | Final Summer 2018 SARA | 13 | FLAT TOP WIND I | 15INR0082 |  | COMANCHE | WIND | NORTH | 2018 | 200 | 14% | 28 | 2018-04-30 | 2018-09-07 | OPERATIONAL | 2018-01-18 | No | 2018-06-01 | O4 | operational after August 1st
2 | Final Summer 2018 SARA | 14 | HICKMAN (SANTA RITA WIND) | 16INR0091 |  | REAGAN | WIND | WEST | 2018 | 300 | 14% | 42 | 2018-05-30 | 2018-05-09 | OPERATIONAL | 2017-12-19 | Yes | 2018-06-01 | O1 | operational by June 1st
2 | Final Summer 2018 SARA | 15 | RTS WIND | 16INR0087 |  | MCCULLOCH | WIND | SOUTH | 2018 | 160 | 14% | 22.4 | 2018-05-30 | 2018-09-07 | OPERATIONAL | 2018-03-08 | No | 2018-06-01 | O4 | operational after August 1st
2 | Final Summer 2018 SARA | 16 | CASTLE GAP SOLAR | 16INR0065 |  | UPTON | SOLAR | WEST | 2018 | 180 | 75% | 135 | 2018-06-01 | 2018-05-31 | OPERATIONAL | 2018-03-16 | Yes | 2018-06-01 | O1 | operational by June 1st
2 | Final Summer 2018 SARA | 17 | FS BARILLA SOLAR 1B [HOVEY_UNIT2] | 12INR0059b |  | PECOS | SOLAR | WEST | 2018 | 7.4 | 75% | 5.55 | 2018-05-30 | N/A | PLANNED | N/A | No | 2018-06-01 | P2 | COD delays without part 2 approval
2 | Final Summer 2018 SARA | 18 | RIGGINS (SE BUCKTHORN WESTEX SOLAR) | 15INR0045 |  | PECOS | SOLAR | WEST | 2018 | 150 | 75% | 112.5 | 2018-04-20 | 2018-06-15 | OPERATIONAL | 2018-04-02 | No | 2018-06-01 | O2 | operational by July 1st
2 | Final Summer 2018 SARA | 19 | SOLAIREHOLMAN 1 | 15INR0061 |  | BREWSTER | SOLAR | WEST | 2018 | 50 | 75% | 37.5 | 2018-06-01 | 2018-05-24 | OPERATIONAL | 2017-03-30 | Yes | 2018-06-01 | O1 | operational by June 1st
3 | Final Summer 2019 SARA | 20 | HUDSON (BRAZORIA ENERGY G) | 16INR0076 |  | BRAZORIA | GAS | COASTAL | 2019 | 90 | 100% | 90 | 2019-05-01 | 2020-07-17 | OPERATIONAL | 2019-08-16 | No | 2019-06-01 | O4 | operational after August 1st
3 | Final Summer 2019 SARA | 21 | MIRAGE | 17INR0022 |  | HARRIS | GAS | HOUSTON | 2019 | 11 | 100% | 11 | 2019-02-18 | N/A | PLANNED | N/A | No | 2019-06-01 | P2 | COD delays without part 2 approval
3 | Final Summer 2019 SARA | 22 | VICTORIA PORT (VICTPORT) | 17INR0045 |  | CALHOUN | GAS | COASTAL | 2019 | 100 | 100% | 100 | 2019-05-03 | 2019-09-30 | OPERATIONAL | 2019-06-19 | No | 2019-06-01 | O4 | operational after August 1st
3 | Final Summer 2019 SARA | 23 | BLUE SUMMIT II | 18INR0070 |  | WILBARGER | WIND | WEST | 2019 | 102 | 15% | 15.3 | 2019-04-15 | 2020-04-06 | OPERATIONAL | 2019-01-10 | No | 2019-06-01 | O4 | operational after August 1st
3 | Final Summer 2019 SARA | 24 | CABEZON WIND (RIO BRAVO I WIND) | 17INR0005 |  | STARR | WIND | SOUTH | 2019 | 237.6 | 15% | 35.64 | 2019-05-31 | 2019-12-17 | OPERATIONAL | 2019-03-14 | No | 2019-06-01 | O4 | operational after August 1st
3 | Final Summer 2019 SARA | 25 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND | WEST | 2019 | 148.4 | 15% | 22.26 | 2019-04-29 | N/A | PLANNED | 2018-06-11 | No | 2019-06-01 | P1 | COD delays but received part 2 approval
3 | Final Summer 2019 SARA | 26 | S_HILLS WIND (LITTLE MOUNTAIN WIND) | 12INR0055 |  | BAYLOR | WIND | WEST | 2019 | 30.2 | 15% | 4.53 | 2019-05-30 | 2019-08-07 | OPERATIONAL | 2019-04-19 | No | 2019-06-01 | O4 | operational after August 1st
3 | Final Summer 2019 SARA | 27 | TORRECILLAS WIND | 14INR0045 |  | WEBB | WIND | SOUTH | 2019 | 300.5 | 15% | 45.075 | 2019-04-15 | 2019-11-07 | OPERATIONAL | 2019-02-26 | No | 2019-06-01 | O4 | operational after August 1st
3 | Final Summer 2019 SARA | 28 | WILSON RANCH (INFINITY LIVE OAK WIND) | 12INR0060 |  | SCHLEICHER | WIND | WEST | 2019 | 199.5 | 15% | 29.925 | 2019-05-31 | 2020-04-17 | OPERATIONAL | 2018-11-29 | No | 2019-06-01 | O4 | operational after August 1st
3 | Final Summer 2019 SARA | 29 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 162.9 | 58% | 94.482 | 2019-04-05 | 2019-08-15 | OPERATIONAL | 2018-12-04 | No | 2019-06-01 | O4 | operational after August 1st
3 | Final Summer 2019 SARA | 30 | SHAFFER (PATRIOT WIND/PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2019 | 226 | 58% | 131.08 | 2019-05-22 | N/A | PLANNED | 2019-04-05 | No | 2019-06-01 | P1 | COD delays but received part 2 approval
3 | Final Summer 2019 SARA | 31 | BLUEBELL SOLAR (CAPRICORN RIDGE SOLAR) | 16INR0019 |  | COKE | SOLAR | WEST | 2019 | 30 | 74% | 22.2 | 2019-04-15 | 2019-11-07 | OPERATIONAL | 2018-10-25 | No | 2019-06-01 | O4 | operational after August 1st
3 | Final Summer 2019 SARA | 32 | HOVEY (BARILLA SOLAR 1B) | 12INR0059b |  | PECOS | SOLAR | WEST | 2019 | 7.4 | 74% | 5.476 | 2019-02-28 | N/A | PLANNED | N/A | No | 2019-06-01 | P2 | COD delays without part 2 approval
4 | Final Summer 2020 SARA | 37 | BLUE SUMMIT WIND 3 | 19INR0182 |  | WILBARGER | WIND-O | WEST | 2020 | 200 | 16% | 32 | 2020-06-30 | 2020-05-19 | OPERATIONAL | 2019-12-11 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Final Summer 2020 SARA | 47 | HOLSTEIN SOLAR | 19INR0009 |  | NOLAN | SOLAR | WEST | 2020 | 204.5 | 76% | 155.42 | 2020-06-01 | 2020-05-28 | OPERATIONAL | 2020-01-16 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Final Summer 2020 SARA | 56 | FLAT TOP BATTERY |  | FLTBES_BESS1 | REEVES | STORAGE | WEST | 2019 | 9.9 | 0% | 0 | 2019-09-01 | 2020-05-22 | OPERATIONAL | 2020-05-05 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Final Summer 2020 SARA | 35 | PEYTON CREEK WIND | 18INR0018 |  | MATAGORDA | WIND-C | COASTAL | 2020 | 151.2 | 63% | 95.256 | 2020-04-30 | 2020-06-04 | OPERATIONAL | 2019-11-14 | No | 2020-06-01 | O2 | operational by July 1st
4 | Final Summer 2020 SARA | 48 | LAPETUS SOLAR | 19INR0185 |  | ANDREWS | SOLAR | WEST | 2020 | 100 | 76% | 76 | 2020-05-01 | 2020-06-24 | OPERATIONAL | 2019-12-06 | No | 2020-06-01 | O2 | operational by July 1st
4 | Final Summer 2020 SARA | 52 | PROSPERO SOLAR | 19INR0092 |  | ANDREWS | SOLAR | WEST | 2020 | 300 | 76% | 228 | 2020-06-30 | 2020-06-30 | OPERATIONAL | 2020-04-24 | No | 2020-06-01 | O2 | operational by July 1st
4 | Final Summer 2020 SARA | 33 | HUDSON (BRAZORIA ENERGY G) | 16INR0076 |  | BRAZORIA | GAS | COASTAL | 2020 | 90 | 100% | 90 | 2020-05-31 | 2020-07-17 | OPERATIONAL | 2019-08-16 | No | 2020-06-01 | O3 | operational by August 1st
4 | Final Summer 2020 SARA | 50 | OBERON SOLAR | 19INR0083 |  | ECTOR | SOLAR | WEST | 2020 | 180 | 76% | 136.8 | 2020-05-26 | 2020-07-13 | OPERATIONAL | 2020-04-08 | No | 2020-06-01 | O3 | operational by August 1st
4 | Final Summer 2020 SARA | 55 | COMMERCE ST ESS |  | X443ESS1_SWRI | BEXAR | STORAGE | SOUTH | 2019 | 10 | 0% | 0 | 2019-06-01 | 2020-10-06 | OPERATIONAL | 2019-11-26 | No | 2020-06-01 | O4 | operational after August 1st
4 | Final Summer 2020 SARA | 54 | RAMBLER SOLAR | 19INR0114 |  | TOM GREEN | SOLAR | WEST | 2020 | 200 | 76% | 152 | 2020-07-01 | 2020-10-01 | OPERATIONAL | 2020-04-01 | No | 2020-06-01 | O4 | operational after August 1st
4 | Final Summer 2020 SARA | 53 | QUEEN SOLAR PHASE II | 20INR0298 |  | UPTON | SOLAR | WEST | 2020 | 200 | 76% | 152 | 2020-04-30 | 2020-08-28 | OPERATIONAL | 2020-04-10 | No | 2020-06-01 | O4 | operational after August 1st
4 | Final Summer 2020 SARA | 39 | HIDALGO II WIND | 19INR0053 |  | HIDALGO | WIND-O | SOUTH | 2020 | 51 | 16% | 8.16 | 2020-03-17 | N/A | PLANNED | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 34 | PALMAS ALTAS WIND | 17INR0037 |  | CAMERON | WIND-C | COASTAL | 2020 | 144.9 | 63% | 91.287 | 2020-04-24 | 2020-11-12 | OPERATIONAL | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 43 | OVEJA WIND | 18INR0033 |  | IRION | WIND-O | WEST | 2020 | 300 | 16% | 48 | 2020-04-30 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 46 | WHITEHORSE WIND | 19INR0080 |  | FISHER | WIND-O | WEST | 2020 | 418.9 | 16% | 67.024 | 2020-04-30 | N/A | PLANNED | 2019-12-27 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 36 | BARROW RANCH (JUMBO HILL WIND) | 18INR0038 |  | ANDREWS | WIND-O | WEST | 2020 | 160 | 16% | 25.6 | 2020-04-30 | N/A | PLANNED | 2020-02-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 51 | OXY SOLAR | 19INR0184 |  | ECTOR | SOLAR | WEST | 2020 | 16.2 | 76% | 12.312 | 2020-05-15 | N/A | PLANNED | 2019-07-31 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 40 | HIGH LONESOME W | 19INR0038 |  | CROCKETT | WIND-O | WEST | 2020 | 449.5 | 16% | 71.92 | 2020-05-15 | N/A | PLANNED | 2019-11-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 45 | SAGE DRAW WIND | 19INR0163 |  | LYNN | WIND-O | WEST | 2020 | 338 | 16% | 54.08 | 2020-05-15 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 49 | MISAE SOLAR | 18INR0045 |  | CHILDRESS | SOLAR | PANHANDLE | 2020 | 240.8 | 76% | 183.008 | 2020-05-15 | N/A | PLANNED | 2020-01-16 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 41 | HIGH LONESOME WIND PHASE II | 20INR0262 |  | CROCKETT | WIND-O | WEST | 2020 | 50.6 | 16% | 8.096 | 2020-05-15 | N/A | PLANNED | 2020-02-28 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 42 | MESTENO WIND | 16INR0081 |  | STARR | WIND-O | SOUTH | 2020 | 201.6 | 16% | 32.256 | 2020-06-01 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 38 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND-O | WEST | 2020 | 148.4 | 16% | 23.744 | 2020-06-30 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Final Summer 2020 SARA | 44 | RTS 2 WIND (HEART OF TEXAS WIND) | 18INR0016 |  | MCCULLOCH | WIND-O | SOUTH | 2020 | 179.91 | 16% | 28.7856 | 2020-07-29 | N/A | PLANNED | 2020-04-29 | No | 2020-06-01 | P1 | COD delays but received part 2 approval

## Planned Projects View 2
REPORT ID | FULL REPORT NAME | ORDER ID | UNIT NAME | INR | UNIT CODE | COUNTY | FUEL | ZONE | START YEAR | SUMMER NAMEPLATE CAPACITY (MW) | SUMMER CAPACITY CONTRIBUTION % | SUMMER CONTRIBUTION MW | PROJECTED COD (FROM REPORT) | CURRENT PROJECT STATUS (as of 1/1/21) | CURRENT PROJECT STATUS | APPROVED FOR SYNCHRONIZATION (as of 1/1/21) | WAS IN-SERVICE BEFORE START OF SUMMER? | SUMMER CUTOFF DATE | NOTES ID | NOTES
12 | Final Summer 2020 SARA | 1 | FRIENDSWOOD II | 19INR0180 |  | BRAZORIA | GAS | COASTAL | 2021 | 0 | 100% | 0 | 2021-02-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
12 | Final Summer 2020 SARA | 2 | GIBBONS CREEK TEERP | 20INR0308 |  | GRIMES | COAL | NORTH | 2020 | 0 | 100% | 0 | 2020-07-27 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
12 | Final Summer 2020 SARA | 3 | HUDSON (BRAZORIA ENERGY G) | 16INR0076 |  | BRAZORIA | GAS | COASTAL | 2020 | 90 | 100% | 90 | 2020-05-31 | 2020-07-17 | OPERATIONAL | 2019-08-16 | No | 2020-06-01 | O3 | operational by August 1st
12 | Final Summer 2020 SARA | 4 | MIRAGE | 17INR0022 |  | HARRIS | GAS | HOUSTON | 2020 | 0 | 100% | 0 | 2020-10-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 5 | PES1 | 20INR0206 |  | HARRIS | GAS | HOUSTON | 2020 | 0 | 100% | 0 | 2020-12-01 | N/A | PLANNED | 2020-12-17 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 6 | CHALUPA WIND | 20INR0042 |  | CAMERON | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-12-21 | N/A | PLANNED | 2020-08-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 7 | CHOCOLATE BAYOU W | 16INR0074 |  | BRAZORIA | WIND-C | COASTAL | 2021 | 0 | 63% | 0 | 2021-05-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
12 | Final Summer 2020 SARA | 8 | CRANEL WIND | 19INR0112 |  | REFUGIO | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-07-16 | N/A | PLANNED | 2020-05-19 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 9 | EAST RAYMOND WIND | 18INR0059 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-09-30 | N/A | PLANNED | 2020-10-06 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 10 | EL ALGODON ALTO W | 15INR0034 |  | SAN PATRICIO | WIND-C | COASTAL | 2021 | 0 | 63% | 0 | 2021-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 11 | ESPIRITU WIND | 17INR0031 |  | CAMERON | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-12-21 | N/A | PLANNED | 2020-08-10 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 12 | LAS MAJADAS WIND | 17INR0035 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-10-29 | N/A | PLANNED | 2020-10-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 13 | MONTE ALTO I | 19INR0022 |  | WILLACY | WIND-C | COASTAL | 2021 | 0 | 63% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 14 | PALMAS ALTAS WIND | 17INR0037 |  | CAMERON | WIND-C | COASTAL | 2020 | 144.9 | 63% | 91.287 | 2020-04-24 | 2020-11-12 | OPERATIONAL | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 15 | PEYTON CREEK WIND | 18INR0018 |  | MATAGORDA | WIND-C | COASTAL | 2020 | 151.2 | 63% | 95.256 | 2020-04-30 | 2020-06-04 | OPERATIONAL | 2019-11-14 | No | 2020-06-01 | O2 | operational by July 1st
12 | Final Summer 2020 SARA | 16 | SHAFFER (PATRIOT WIND/PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-08-28 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 17 | WEST RAYMOND (EL TRUENO) WIND | 20INR0088 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 18 | GOODNIGHT WIND | 14INR0033 |  | ARMSTRONG | WIND-P | PANHANDLE | 2021 | 0 | 29% | 0 | 2021-12-30 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
12 | Final Summer 2020 SARA | 19 | HART WIND | 16INR0033 |  | CASTRO | WIND-P | PANHANDLE | 2021 | 0 | 29% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 20 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND-P | PANHANDLE | 2020 | 0 | 29% | 0 | 2020-12-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
12 | Final Summer 2020 SARA | 21 | APOGEE WIND | 21INR0467 |  | HASKELL | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 22 | AVIATOR WIND | 19INR0156 |  | COKE | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-10-01 | N/A | PLANNED | 2020-06-24 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 23 | BAIRD NORTH WIND | 20INR0083 |  | CALLAHAN | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-06-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 24 | BARROW RANCH (JUMBO HILL WIND) | 18INR0038 |  | ANDREWS | WIND-O | WEST | 2020 | 160 | 16% | 25.6 | 2020-04-30 | N/A | PLANNED | 2020-02-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 25 | BIG SAMPSON WIND | 16INR0104 |  | CROCKETT | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-09-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 26 | BLACKJACK CREEK WIND | 20INR0068 |  | BEE | WIND-O | SOUTH | 2021 | 0 | 16% | 0 | 2021-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 27 | BLUE SUMMIT WIND 3 | 19INR0182 |  | WILBARGER | WIND-O | WEST | 2020 | 200 | 16% | 32 | 2020-06-30 | 2020-05-19 | OPERATIONAL | 2019-12-11 | Yes | 2020-06-01 | O1 | operational by June 1st
12 | Final Summer 2020 SARA | 28 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND-O | WEST | 2020 | 148.4 | 16% | 23.744 | 2020-06-30 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 29 | CANYON WIND | 18INR0030 |  | SCURRY | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-03-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 30 | COYOTE WIND | 17INR0027b |  | SCURRY | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-10-29 | N/A | PLANNED | 2020-11-25 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 31 | EDMONDSON RANCH WIND | 18INR0043 |  | GLASSCOCK | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-12-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 32 | GRIFFIN TRAIL WIND | 20INR0052 |  | KNOX | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-09-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 33 | HARALD (BEARKAT WIND B) | 15INR0064b |  | GLASSCOCK | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-07-07 | N/A | PLANNED | 2020-05-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 34 | HIDALGO II WIND | 19INR0053 |  | HIDALGO | WIND-O | SOUTH | 2020 | 51 | 16% | 8.16 | 2020-03-17 | N/A | PLANNED | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 35 | HIGH LONESOME W | 19INR0038 |  | CROCKETT | WIND-O | WEST | 2020 | 449.5 | 16% | 71.92 | 2020-05-15 | N/A | PLANNED | 2019-11-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 36 | HIGH LONESOME WIND PHASE II | 20INR0262 |  | CROCKETT | WIND-O | WEST | 2020 | 50.6 | 16% | 8.096 | 2020-05-15 | N/A | PLANNED | 2020-02-28 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 37 | KAISER CREEK WIND | 18INR0042 |  | CALLAHAN | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-11-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 38 | KONTIKI 1 WIND (ERIK) | 19INR0099a |  | GLASSCOCK | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 39 | KONTIKI 2 WIND (ERNEST) | 19INR0099b |  | GLASSCOCK | WIND-O | WEST | 2022 | 0 | 16% | 0 | 2022-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 40 | LAS LOMAS WIND | 16INR0111 |  | STARR | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-12-01 | N/A | PLANNED | 2020-12-08 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 41 | LORAINE WINDPARK PHASE III | 18INR0068 |  | MITCHELL | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 42 | MARYNEAL WINDPOWER | 18INR0031 |  | NOLAN | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-02-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 43 | MAVERICK CREEK I | 20INR0045 |  | CONCHO | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-12-04 | N/A | PLANNED | 2020-09-01 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 44 | MAVERICK CREEK II | 20INR0046 |  | CONCHO | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-12-15 | N/A | PLANNED | 2020-11-02 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 45 | MESTENO WIND | 16INR0081 |  | STARR | WIND-O | SOUTH | 2020 | 201.6 | 16% | 32.256 | 2020-06-01 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 46 | OVEJA WIND | 18INR0033 |  | IRION | WIND-O | WEST | 2020 | 300 | 16% | 48 | 2020-04-30 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 47 | PRAIRIE HILL WIND | 19INR0100 |  | MCLENNAN | WIND-O | NORTH | 2020 | 0 | 16% | 0 | 2020-10-30 | N/A | PLANNED | 2020-11-12 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 48 | RELOJ DEL SOL WIND | 17INR0025 |  | ZAPATA | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-12-01 | N/A | PLANNED | 2020-12-29 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 49 | ROADRUNNER CROSSING WIND 1 | 19INR0117 |  | EASTLAND | WIND-O | NORTH | 2021 | 0 | 16% | 0 | 2021-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 50 | RTS 2 WIND (HEART OF TEXAS WIND) | 18INR0016 |  | MCCULLOCH | WIND-O | SOUTH | 2020 | 179.91 | 16% | 28.7856 | 2020-07-29 | N/A | PLANNED | 2020-04-29 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 51 | SAGE DRAW WIND | 19INR0163 |  | LYNN | WIND-O | WEST | 2020 | 338 | 16% | 54.08 | 2020-05-15 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 52 | TG EAST WIND | 19INR0052 |  | KNOX | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 53 | VERA WIND | 19INR0051 |  | KNOX | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-07-01 | N/A | PLANNED | 2020-07-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 54 | VERA WIND V110 | 20INR0305 |  | KNOX | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-07-01 | N/A | PLANNED | 2020-07-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 55 | WHITE MESA WIND | 19INR0128 |  | CROCKETT | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-09-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 56 | WHITEHORSE WIND | 19INR0080 |  | FISHER | WIND-O | WEST | 2020 | 418.9 | 16% | 67.024 | 2020-04-30 | N/A | PLANNED | 2019-12-27 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 57 | WILDWIND | 20INR0033 |  | COOKE | WIND-O | NORTH | 2020 | 0 | 16% | 0 | 2020-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 58 | WKN AMADEUS WIND | 14INR0009 |  | FISHER | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-10-30 | N/A | PLANNED | 2020-10-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 59 | ANSON SOLAR | 19INR0081 |  | JONES | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | 2020-12-30 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 60 | ARAGORN SOLAR | 19INR0088 |  | CULBERSON | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 61 | AZURE SKY SOLAR | 21INR0477 |  | HASKELL | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 62 | BLUEBELL SOLAR II | 20INR0204 |  | STERLING | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | 2020-11-12 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 63 | BRAVEPOST SOLAR | 20INR0053 |  | TOM GREEN | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 64 | CONIGLIO SOLAR | 20INR0037 |  | FANNIN | SOLAR | NORTH | 2021 | 0 | 76% | 0 | 2021-03-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 65 | CORAZON SOLAR | 15INR0044 |  | WEBB | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 66 | COTTONWOOD BAYOU | 19INR0134 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 67 | CROWDED STAR SOLAR | 20INR0241 |  | JONES | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-07-02 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 68 | CROWDED STAR SOLAR II | 22INR0274 |  | JONES | SOLAR | WEST | 2022 | 0 | 76% | 0 | 2022-05-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 69 | DANCIGER SOLAR | 20INR0098 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 70 | DANISH FIELDS SOLAR I | 20INR0069 |  | WHARTON | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 71 | DANISH FIELDS SOLAR II | 21INR0016 |  | WHARTON | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 72 | DANISH FIELDS SOLAR III | 21INR0017 |  | WHARTON | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 73 | ELARA SOLAR | 21INR0276 |  | FRIO | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-05-11 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 74 | EMERALD GROVE SOLAR (PECOS SOLAR POWER I) | 15INR0059 |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-04-10 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 75 | EUNICE SOLAR | 20INR0219 |  | ANDREWS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | 2020-12-01 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 76 | FORT BEND SOLAR | 18INR0053 |  | FORT BEND | SOLAR | HOUSTON | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 77 | FOWLER RANCH | 18INR0039 |  | CRANE | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-08-07 | 2020-08-28 | OPERATIONAL | 2020-06-16 | No | 2020-06-01 | O4 | operational after August 1st
12 | Final Summer 2020 SARA | 78 | GALLOWAY 1 SOLAR | 19INR0121 |  | CONCHO | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-08 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 79 | GALLOWAY 2 SOLAR | 21INR0431 |  | CONCHO | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-08 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 80 | GREASEWOOD SOLAR | 19INR0034 |  | PECOS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-11-30 | N/A | PLANNED | 2020-10-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 81 | HOLSTEIN SOLAR | 19INR0009 |  | NOLAN | SOLAR | WEST | 2020 | 204.5 | 76% | 155.42 | 2020-06-01 | 2020-05-28 | OPERATIONAL | 2020-01-16 | Yes | 2020-06-01 | O1 | operational by June 1st
12 | Final Summer 2020 SARA | 82 | HORIZON SOLAR | 21INR0261 |  | FRIO | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 83 | IMPACT SOLAR | 19INR0151 |  | LAMAR | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-12-23 | N/A | PLANNED | 2020-09-02 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 84 | IP TITAN | 20INR0032 |  | CULBERSON | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 85 | JUNO SOLAR PHASE I | 21INR0026 |  | BORDEN | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 86 | JUNO SOLAR PHASE II | 21INR0501 |  | BORDEN | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-08-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 87 | KELLAM SOLAR | 20INR0261 |  | VAN ZANDT | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-12-01 | 2020-12-24 | OPERATIONAL | 2020-11-17 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 88 | LAPETUS SOLAR | 19INR0185 |  | ANDREWS | SOLAR | WEST | 2020 | 100 | 76% | 76 | 2020-05-01 | 2020-06-24 | OPERATIONAL | 2019-12-06 | No | 2020-06-01 | O2 | operational by July 1st
12 | Final Summer 2020 SARA | 89 | LILY SOLAR | 19INR0044 |  | KAUFMAN | SOLAR | NORTH | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 90 | LONG DRAW SOLAR | 18INR0055 |  | BORDEN | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-08-31 | N/A | PLANNED | 2020-11-20 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 91 | LONG POINT SOLAR | 19INR0042 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-12-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 92 | MISAE SOLAR | 18INR0045 |  | CHILDRESS | SOLAR | PANHANDLE | 2020 | 240.8 | 76% | 183.008 | 2020-05-15 | N/A | PLANNED | 2020-01-16 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 93 | MISAE SOLAR II | 20INR0091 |  | CHILDRESS | SOLAR | PANHANDLE | 2022 | 0 | 76% | 0 | 2022-12-20 | N/A | INACTIVE | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 94 | MORROW LAKE SOLAR | 19INR0155 |  | FRIO | SOLAR | SOUTH | 2022 | 0 | 76% | 0 | 2022-04-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 95 | MUSTANG CREEK SOLAR | 18INR0050 |  | JACKSON | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 96 | MYRTLE SOLAR | 19INR0041 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 97 | NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2022 | 0 | 76% | 0 | 2022-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 98 | NORTON SOLAR | 19INR0035 |  | RUNNELS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-09-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 99 | OBERON SOLAR | 19INR0083 |  | ECTOR | SOLAR | WEST | 2020 | 180 | 76% | 136.8 | 2020-05-26 | 2020-07-13 | OPERATIONAL | 2020-04-08 | No | 2020-06-01 | O3 | operational by August 1st
12 | Final Summer 2020 SARA | 100 | OLD 300 SOLAR CENTER | 21INR0406 |  | FORT BEND | SOLAR | HOUSTON | 2021 | 0 | 76% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 101 | OXY SOLAR | 19INR0184 |  | ECTOR | SOLAR | WEST | 2020 | 16.2 | 76% | 12.312 | 2020-05-15 | N/A | PLANNED | 2019-07-31 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 102 | PFLUGERVILLE SOLAR | 15INR0090 |  | TRAVIS | SOLAR | SOUTH | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 103 | PHOENIX SOLAR | 19INR0091 |  | FANNIN | SOLAR | NORTH | 2021 | 0 | 76% | 0 | 2021-04-23 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 104 | PROSPERO SOLAR | 19INR0092 |  | ANDREWS | SOLAR | WEST | 2020 | 300 | 76% | 228 | 2020-06-30 | 2020-06-30 | OPERATIONAL | 2020-04-24 | No | 2020-06-01 | O2 | operational by July 1st
12 | Final Summer 2020 SARA | 105 | PROSPERO SOLAR II | 21INR0229 |  | ANDREWS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-07-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 106 | QUEEN SOLAR PHASE II | 20INR0298 |  | UPTON | SOLAR | WEST | 2020 | 200 | 76% | 152 | 2020-04-30 | 2020-08-28 | OPERATIONAL | 2020-04-10 | No | 2020-06-01 | O4 | operational after August 1st
12 | Final Summer 2020 SARA | 107 | RAMBLER SOLAR | 19INR0114 |  | TOM GREEN | SOLAR | WEST | 2020 | 200 | 76% | 152 | 2020-07-01 | 2020-10-01 | OPERATIONAL | 2020-04-01 | No | 2020-06-01 | O4 | operational after August 1st
12 | Final Summer 2020 SARA | 108 | RAYOS DEL SOL | 19INR0045 |  | CAMERON | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-08-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 109 | RE MAPLEWOOD 2A SOLAR | 17INR0020a |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-04-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 110 | RE MAPLEWOOD 2B SOLAR | 17INR0020b |  | PECOS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 111 | RE MAPLEWOOD 2C SOLAR | 17INR0020c |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-30 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
12 | Final Summer 2020 SARA | 112 | RIPPEY SOLAR | 20INR0031 |  | COOKE | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-12-31 | 2020-12-30 | OPERATIONAL | 2020-11-20 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 113 | RODEO SOLAR | 19INR0103 |  | ANDREWS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 114 | SHAKES SOLAR | 19INR0073 |  | ZAVALA | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-02-12 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 115 | SODA LAKE SOLAR 1 | 18INR0040 |  | CRANE | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
12 | Final Summer 2020 SARA | 116 | SODA LAKE SOLAR 2 | 20INR0143 |  | CRANE | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 117 | STRATEGIC ENERGY | 20INR0081 |  | ELLIS | SOLAR | NORTH | 2021 | 0 | 76% | 0 | 2021-10-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 118 | TAYGETE II SOLAR | 21INR0233 |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 119 | TAYGETE SOLAR | 20INR0054 |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-02-02 | N/A | PLANNED | 2020-12-07 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 120 | TEXAS SOLAR NOVA | 19INR0001 |  | KENT | SOLAR | WEST | 2022 | 0 | 76% | 0 | 2022-01-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 121 | TIMBERWOLF POI A | 20INR0226 |  | UPTON | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 122 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-09-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 123 | WAGYU SOLAR | 18INR0062 |  | BRAZORIA | SOLAR | COASTAL | 2020 | 0 | 76% | 0 | 2020-06-03 | N/A | PLANNED | 2020-05-22 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
12 | Final Summer 2020 SARA | 124 | WESTORIA SOLAR | 20INR0101 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 125 | AZURE SKY BESS | 21INR0476 |  | HASKELL | STORAGE | WEST | 2021 | 0 | 0% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 126 | BAT CAVE | 21INR0365 |  | MASON | STORAGE | SOUTH | 2021 | 0 | 0% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 127 | CHISHOLM GRID | 20INR0089 |  | TARRANT | STORAGE | NORTH | 2021 | 0 | 0% | 0 | 2021-05-07 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 128 | EUNICE STORAGE | 20INR0220 |  | ANDREWS | STORAGE | WEST | 2020 | 0 | 0% | 0 | 2020-12-31 | N/A | PLANNED | 2020-12-01 | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 129 | MADERO GRID | 21INR0244 |  | HIDALGO | STORAGE | SOUTH | 2021 | 0 | 0% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 130 | NORTH FORK | 20INR0276 |  | WILLIAMSON | STORAGE | SOUTH | 2021 | 0 | 0% | 0 | 2021-05-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 131 | SILICON HILL STORAGE | 20INR0291 |  | TRAVIS | STORAGE | SOUTH | 2021 | 0 | 0% | 0 | 2021-09-27 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 136 | BRP HEIGHTS |  | BRHEIGHT_UNIT1 | GALVESTON | STORAGE | HOUSTON | 2020 | 0 | 0% | 0 | 2020-09-01 | N/A | PLANNED | #N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 134 | BRP BRAZORIA |  | BRP_BRAZ_UNIT1 | BRAZORIA | STORAGE | COASTAL | 2020 | 0 | 0% | 0 | 2020-09-01 | N/A | PLANNED | #N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 135 | BRP DICKINSON |  | BRP_DIKN_UNIT1 | GALVESTON | STORAGE | HOUSTON | 2020 | 0 | 0% | 0 | 2020-09-01 | N/A | PLANNED | #N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 132 | BRP ALVIN |  | BRPALVIN_UNIT1 | BRAZORIA | STORAGE | COASTAL | 2020 | 0 | 0% | 0 | 2020-08-01 | 2020-09-16 | OPERATIONAL | #N/A | No | 2020-06-01 | O4 | operational after August 1st
12 | Final Summer 2020 SARA | 133 | BRP ANGELTON |  | BRPANGLE_UNIT1 | BRAZORIA | STORAGE | COASTAL | 2020 | 0 | 0% | 0 | 2020-09-01 | N/A | PLANNED | #N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 137 | BRP MAGNOLIA |  | BRPMAGNO_UNIT1 | GALVESTON | STORAGE | HOUSTON | 2020 | 0 | 0% | 0 | 2020-09-01 | N/A | PLANNED | #N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
12 | Final Summer 2020 SARA | 138 | BRP ODESSA SW |  | BRPODESA_UNIT1 | ECTOR | STORAGE | WEST | 2020 | 0 | 0% | 0 | 2020-08-01 | 2020-08-21 | OPERATIONAL | #N/A | No | 2020-06-01 | O4 | operational after August 1st
9 | May 2019 CDR | 502 | CASTLE GAP BATTERY |  | CASL_GAP_BATTERY1 | UPTON | OTHER | WEST | 2018 | 9.9 | 0% | 0 | 2018-12-31 | 2019-06-11 | OPERATIONAL | #N/A | Yes | 2020-06-01 | O1 | operational by June 1st
12 | Final Summer 2020 SARA | 140 | FLAT TOP BATTERY |  | FLTBES_BESS1 | REEVES | STORAGE | WEST | 2019 | 9.9 | 0% | 0 | 2019-09-01 | 2020-05-22 | OPERATIONAL | 2020-05-05 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 267 | FLAT TOP BATTERY |  | FLTBES_BESS1 | REEVES | STORAGE | WEST | 2019 | 9.9 | 0% | 0 | 2019-09-01 | 2020-05-22 | OPERATIONAL | 2020-05-05 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 142 | FRIENDSWOOD II | 19INR0180 |  | BRAZORIA | GAS | COASTAL | 2021 | 0 | 100% | 0 | 2021-02-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
11 | Preliminary Summer 2020 SARA | 143 | HALYARD WHARTON ENERGY CENTER | 16INR0044 |  | WHARTON | GAS | SOUTH | 2021 | 0 | 100% | 0 | 2021-06-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 144 | HUDSON (BRAZORIA ENERGY G) | 16INR0076 |  | BRAZORIA | GAS | COASTAL | 2020 | 90 | 100% | 90 | 2020-03-31 | 2020-07-17 | OPERATIONAL | 2019-08-16 | No | 2020-06-01 | O3 | operational by August 1st
11 | Preliminary Summer 2020 SARA | 145 | MIRAGE | 17INR0022 |  | HARRIS | GAS | HOUSTON | 2020 | 11 | 100% | 11 | 2020-05-04 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 146 | PES1 | 20INR0206 |  | HARRIS | GAS | HOUSTON | 2020 | 0 | 100% | 0 | 2020-12-01 | N/A | PLANNED | 2020-12-17 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 147 | CHALUPA WIND | 20INR0042 |  | CAMERON | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-12-21 | N/A | PLANNED | 2020-08-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 148 | CHOCOLATE BAYOU W | 16INR0074 |  | BRAZORIA | WIND-C | COASTAL | 2021 | 0 | 63% | 0 | 2021-05-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 149 | CRANEL WIND | 19INR0112 |  | REFUGIO | WIND-C | COASTAL | 2020 | 220 | 63% | 138.6 | 2020-05-15 | N/A | PLANNED | 2020-05-19 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 150 | EAST RAYMOND WIND | 18INR0059 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-06-30 | N/A | PLANNED | 2020-10-06 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 151 | ESPIRITU WIND | 17INR0031 |  | CAMERON | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-12-21 | N/A | PLANNED | 2020-08-10 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 152 | LAS MAJADAS WIND | 17INR0035 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-10-29 | N/A | PLANNED | 2020-10-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 153 | MONTE ALTO I | 19INR0022 |  | WILLACY | WIND-C | COASTAL | 2021 | 0 | 63% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 154 | PALMAS ALTAS WIND | 17INR0037 |  | CAMERON | WIND-C | COASTAL | 2020 | 144.9 | 63% | 91.287 | 2020-01-31 | 2020-11-12 | OPERATIONAL | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 155 | PEYTON CREEK WIND | 18INR0018 |  | MATAGORDA | WIND-C | COASTAL | 2020 | 151.2 | 63% | 95.256 | 2020-04-01 | 2020-06-04 | OPERATIONAL | 2019-11-14 | No | 2020-06-01 | O2 | operational by July 1st
11 | Preliminary Summer 2020 SARA | 156 | SHAFFER (PATRIOT WIND/PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2020 | 226 | 63% | 142.38 | 2020-01-31 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 157 | WEST RAYMOND (EL TRUENO) WIND | 20INR0088 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 158 | GOODNIGHT WIND | 14INR0033 |  | ARMSTRONG | WIND-P | PANHANDLE | 2020 | 0 | 29% | 0 | 2020-12-12 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 159 | HART WIND | 16INR0033 |  | CASTRO | WIND-P | PANHANDLE | 2021 | 0 | 29% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 160 | MARIAH DEL ESTE | 13INR0010a |  | PARMER | WIND-P | PANHANDLE | 2020 | 0 | 29% | 0 | 2020-10-30 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 161 | NORTHDRAW WIND | 13INR0025 |  | RANDALL | WIND-P | PANHANDLE | 2020 | 0 | 29% | 0 | 2020-08-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 162 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND-P | PANHANDLE | 2022 | 0 | 29% | 0 | 2022-12-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 163 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND-P | PANHANDLE | 2020 | 0 | 29% | 0 | 2020-12-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
11 | Preliminary Summer 2020 SARA | 164 | WILDROSE WIND (SWISHER WIND) | 13INR0038 |  | SWISHER | WIND-P | PANHANDLE | 2021 | 0 | 29% | 0 | 2021-12-30 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 165 | AVIATOR WIND | 19INR0156 |  | COKE | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-10-01 | N/A | PLANNED | 2020-06-24 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 166 | BAIRD NORTH WIND | 20INR0083 |  | CALLAHAN | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-06-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 167 | BARROW RANCH (JUMBO HILL WIND) | 18INR0038 |  | ANDREWS | WIND-O | WEST | 2020 | 160 | 16% | 25.6 | 2020-04-15 | N/A | PLANNED | 2020-02-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 168 | BIG SAMPSON WIND | 16INR0104 |  | CROCKETT | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-09-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 169 | BLACKJACK CREEK WIND | 20INR0068 |  | BEE | WIND-O | SOUTH | 2021 | 0 | 16% | 0 | 2021-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 170 | BLUE SUMMIT WIND 2 | 18INR0070 |  | WILBARGER | WIND-O | WEST | 2020 | 102 | 16% | 16.32 | 2020-06-30 | 2020-04-06 | OPERATIONAL | 2019-01-10 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 171 | BLUE SUMMIT WIND 3 | 19INR0182 |  | WILBARGER | WIND-O | WEST | 2020 | 200 | 16% | 32 | 2020-06-30 | 2020-05-19 | OPERATIONAL | 2019-12-11 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 172 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND-O | WEST | 2020 | 148.4 | 16% | 23.744 | 2020-06-30 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 173 | CANYON WIND | 18INR0030 |  | SCURRY | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-03-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 174 | COYOTE WIND | 17INR0027b |  | SCURRY | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-10-29 | N/A | PLANNED | 2020-11-25 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 175 | EDMONDSON RANCH WIND | 18INR0043 |  | GLASSCOCK | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-12-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 176 | GOPHER CREEK WIND | 18INR0067 |  | BORDEN | WIND-O | WEST | 2020 | 158 | 16% | 25.28 | 2020-01-31 | 2020-03-09 | OPERATIONAL | 2019-05-30 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 177 | GRIFFIN TRAIL WIND | 20INR0052 |  | KNOX | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-09-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 178 | HARALD (BEARKAT WIND B) | 15INR0064b |  | GLASSCOCK | WIND-O | WEST | 2020 | 162.1 | 16% | 25.936 | 2020-04-16 | N/A | PLANNED | 2020-05-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 179 | HIDALGO II WIND | 19INR0053 |  | HIDALGO | WIND-O | SOUTH | 2020 | 51 | 16% | 8.16 | 2020-02-25 | N/A | PLANNED | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 180 | HIGH LONESOME W | 19INR0038 |  | CROCKETT | WIND-O | WEST | 2019 | 449.5 | 16% | 71.92 | 2019-12-20 | N/A | PLANNED | 2019-11-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 181 | HIGH LONESOME WIND PHASE II | 20INR0262 |  | CROCKETT | WIND-O | WEST | 2020 | 50.6 | 16% | 8.096 | 2020-01-30 | N/A | PLANNED | 2020-02-28 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 182 | KAISER CREEK WIND | 18INR0042 |  | CALLAHAN | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-12-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 183 | KONTIKI 1 WIND (ERIK) | 19INR0099a |  | GLASSCOCK | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 184 | KONTIKI 2 WIND (ERNEST) | 19INR0099b |  | GLASSCOCK | WIND-O | WEST | 2022 | 0 | 16% | 0 | 2022-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 185 | LAS LOMAS WIND | 16INR0111 |  | STARR | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-12-01 | N/A | PLANNED | 2020-12-08 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 186 | LOMA PINTA WIND | 16INR0112 |  | LA SALLE | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-05-31 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 187 | LORAINE WINDPARK PHASE III | 18INR0068 |  | MITCHELL | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 188 | MARYNEAL WINDPOWER | 18INR0031 |  | NOLAN | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-02-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 189 | MAVERICK CREEK I | 20INR0045 |  | CONCHO | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-09-01 | N/A | PLANNED | 2020-09-01 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 190 | MAVERICK CREEK II | 20INR0046 |  | CONCHO | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-11-11 | N/A | PLANNED | 2020-11-02 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 191 | MESTENO WIND | 16INR0081 |  | STARR | WIND-O | SOUTH | 2020 | 201.6 | 16% | 32.256 | 2020-04-01 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 192 | OVEJA WIND | 18INR0033 |  | IRION | WIND-O | WEST | 2020 | 300 | 16% | 48 | 2020-02-28 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 193 | PRAIRIE HILL WIND | 19INR0100 |  | MCLENNAN | WIND-O | NORTH | 2020 | 0 | 16% | 0 | 2020-09-01 | N/A | PLANNED | 2020-11-12 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 194 | RANCHERO WIND | 20INR0011 |  | CROCKETT | WIND-O | WEST | 2020 | 300 | 16% | 48 | 2020-03-31 | 2020-05-04 | OPERATIONAL | 2019-09-04 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 195 | RELOJ DEL SOL WIND | 17INR0025 |  | ZAPATA | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-10-31 | N/A | PLANNED | 2020-12-29 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 196 | RTS 2 WIND (HEART OF TEXAS WIND) | 18INR0016 |  | MCCULLOCH | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-08-06 | N/A | PLANNED | 2020-04-29 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 197 | SAGE DRAW WIND | 19INR0163 |  | LYNN | WIND-O | WEST | 2020 | 338 | 16% | 54.08 | 2020-03-31 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 198 | TG EAST WIND | 19INR0052 |  | KNOX | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 199 | VERA WIND | 19INR0051 |  | KNOX | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-07-01 | N/A | PLANNED | 2020-07-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 200 | WHITE MESA WIND | 19INR0128 |  | CROCKETT | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 201 | WHITEHORSE WIND | 19INR0080 |  | FISHER | WIND-O | WEST | 2020 | 418.9 | 16% | 67.024 | 2020-03-09 | N/A | PLANNED | 2019-12-27 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 202 | WILSON RANCH (INFINITY LIVE OAK WIND) | 12INR0060 |  | SCHLEICHER | WIND-O | WEST | 2020 | 199.5 | 16% | 31.92 | 2020-02-28 | 2020-04-17 | OPERATIONAL | 2018-11-29 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 203 | WKN AMADEUS WIND | 14INR0009 |  | FISHER | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-10-30 | N/A | PLANNED | 2020-10-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 204 | AGATE SOLAR | 20INR0023 |  | ELLIS | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-08-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 205 | ANSON SOLAR | 19INR0081 |  | JONES | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | 2020-12-30 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 206 | ARAGORN SOLAR | 19INR0088 |  | CULBERSON | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 207 | BRAVEPOST SOLAR | 20INR0053 |  | TOM GREEN | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 208 | CORAZON SOLAR | 15INR0044 |  | WEBB | SOLAR | SOUTH | 2020 | 0 | 76% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 209 | COTTONWOOD BAYOU | 19INR0134 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 210 | CROWDED STAR SOLAR | 20INR0241 |  | JONES | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-07-02 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 211 | ELARA SOLAR | 21INR0276 |  | FRIO | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-04-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 212 | EMERALD GROVE SOLAR (PECOS SOLAR POWER I) | 15INR0059 |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-04-10 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 213 | EUNICE SOLAR | 20INR0219 |  | ANDREWS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | 2020-12-01 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 214 | FORT BEND SOLAR | 18INR0053 |  | FORT BEND | SOLAR | HOUSTON | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 215 | FOWLER RANCH | 18INR0039 |  | CRANE | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-06-03 | 2020-08-28 | OPERATIONAL | 2020-06-16 | No | 2020-06-01 | O4 | operational after August 1st
11 | Preliminary Summer 2020 SARA | 216 | GALLOWAY 1 SOLAR | 19INR0121 |  | CONCHO | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 217 | GALLOWAY 2 SOLAR | 21INR0431 |  | CONCHO | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 218 | GARNET SOLAR | 20INR0021 |  | WILLIAMSON | SOLAR | SOUTH | 2020 | 0 | 76% | 0 | 2020-12-18 | N/A | INACTIVE | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 219 | GREASEWOOD SOLAR | 19INR0034 |  | PECOS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-11-30 | N/A | PLANNED | 2020-10-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 220 | HOLSTEIN SOLAR | 19INR0009 |  | NOLAN | SOLAR | WEST | 2020 | 204.5 | 76% | 155.42 | 2020-06-01 | 2020-05-28 | OPERATIONAL | 2020-01-16 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 221 | HORIZON SOLAR | 21INR0261 |  | FRIO | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 222 | HOVEY (BARILLA SOLAR 1B) | 12INR0059b |  | PECOS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-04-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 223 | IMPACT SOLAR | 19INR0151 |  | LAMAR | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-12-15 | N/A | PLANNED | 2020-09-02 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 224 | IP TITAN | 20INR0032 |  | CULBERSON | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 225 | JUNO SOLAR | 21INR0026 |  | BORDEN | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 226 | KELLAM SOLAR | 20INR0261 |  | VAN ZANDT | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-12-11 | 2020-12-24 | OPERATIONAL | 2020-11-17 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 227 | LAPETUS SOLAR | 19INR0185 |  | ANDREWS | SOLAR | WEST | 2020 | 100 | 76% | 76 | 2020-03-01 | 2020-06-24 | OPERATIONAL | 2019-12-06 | No | 2020-06-01 | O2 | operational by July 1st
11 | Preliminary Summer 2020 SARA | 228 | LILY SOLAR | 19INR0044 |  | KAUFMAN | SOLAR | NORTH | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 229 | LONG DRAW SOLAR | 18INR0055 |  | BORDEN | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-07-31 | N/A | PLANNED | 2020-11-20 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 230 | LONG POINT SOLAR | 19INR0042 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-12-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 231 | MISAE SOLAR | 18INR0045 |  | CHILDRESS | SOLAR | PANHANDLE | 2020 | 240.8 | 76% | 183.008 | 2020-02-28 | N/A | PLANNED | 2020-01-16 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 232 | MISAE SOLAR II | 20INR0091 |  | CHILDRESS | SOLAR | PANHANDLE | 2021 | 0 | 76% | 0 | 2021-06-21 | N/A | INACTIVE | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 233 | MORROW LAKE SOLAR | 19INR0155 |  | FRIO | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-04-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 234 | MURPHY LAKE SOLAR | 19INR0033 |  | KAUFMAN | SOLAR | NORTH | 2021 | 0 | 76% | 0 | 2021-03-15 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
11 | Preliminary Summer 2020 SARA | 235 | MUSTANG CREEK SOLAR | 18INR0050 |  | JACKSON | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 236 | MYRTLE SOLAR | 19INR0041 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 237 | NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2022 | 0 | 76% | 0 | 2022-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 238 | NORTON SOLAR | 19INR0035 |  | RUNNELS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 239 | OBERON SOLAR | 19INR0083 |  | ECTOR | SOLAR | WEST | 2020 | 180 | 76% | 136.8 | 2020-04-29 | 2020-07-13 | OPERATIONAL | 2020-04-08 | No | 2020-06-01 | O3 | operational by August 1st
11 | Preliminary Summer 2020 SARA | 240 | OXY SOLAR | 19INR0184 |  | ECTOR | SOLAR | WEST | 2020 | 16.2 | 76% | 12.312 | 2020-05-15 | N/A | PLANNED | 2019-07-31 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 241 | PFLUGERVILLE SOLAR | 15INR0090 |  | TRAVIS | SOLAR | SOUTH | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 242 | PHOENIX SOLAR | 19INR0091 |  | FANNIN | SOLAR | NORTH | 2021 | 0 | 76% | 0 | 2021-04-23 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 243 | PROSPERO SOLAR | 19INR0092 |  | ANDREWS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-06-30 | 2020-06-30 | OPERATIONAL | 2020-04-24 | No | 2020-06-01 | O2 | operational by July 1st
11 | Preliminary Summer 2020 SARA | 244 | PROSPERO SOLAR II | 21INR0229 |  | ANDREWS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-07-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 245 | QUEEN SOLAR | 19INR0102 |  | UPTON | SOLAR | WEST | 2019 | 200 | 76% | 152 | 2019-12-20 | 2020-05-04 | OPERATIONAL | 2019-12-12 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 246 | QUEEN SOLAR PHASE II | 20INR0298 |  | UPTON | SOLAR | WEST | 2020 | 200 | 76% | 152 | 2020-04-30 | 2020-08-28 | OPERATIONAL | 2020-04-10 | No | 2020-06-01 | O4 | operational after August 1st
11 | Preliminary Summer 2020 SARA | 247 | RAMBLER SOLAR | 19INR0114 |  | TOM GREEN | SOLAR | WEST | 2020 | 200 | 76% | 152 | 2020-05-31 | 2020-10-01 | OPERATIONAL | 2020-04-01 | No | 2020-06-01 | O4 | operational after August 1st
11 | Preliminary Summer 2020 SARA | 248 | RAYOS DEL SOL | 19INR0045 |  | CAMERON | SOLAR | COASTAL | 2020 | 0 | 76% | 0 | 2020-10-22 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 249 | RE MAPLEWOOD 2A SOLAR | 17INR0020a |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-04-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 250 | RE MAPLEWOOD 2B SOLAR | 17INR0020b |  | PECOS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 251 | RE MAPLEWOOD 2C SOLAR | 17INR0020c |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-30 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
11 | Preliminary Summer 2020 SARA | 252 | RIPPEY SOLAR | 20INR0031 |  | COOKE | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-12-31 | 2020-12-30 | OPERATIONAL | 2020-11-20 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 253 | RODEO SOLAR | 19INR0103 |  | ANDREWS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 254 | SHAKES SOLAR | 19INR0073 |  | ZAVALA | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-02-12 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 255 | SODA LAKE SOLAR 1 | 18INR0040 |  | CRANE | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
11 | Preliminary Summer 2020 SARA | 256 | SODA LAKE SOLAR 2 | 20INR0143 |  | CRANE | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 257 | SPINEL SOLAR | 20INR0025 |  | MEDINA | SOLAR | SOUTH | 2020 | 0 | 76% | 0 | 2020-12-17 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
11 | Preliminary Summer 2020 SARA | 258 | TAYGETE II SOLAR | 21INR0233 |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 259 | TAYGETE SOLAR | 20INR0054 |  | PECOS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-01 | N/A | PLANNED | 2020-12-07 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 260 | TEXAS SOLAR NOVA | 19INR0001 |  | KENT | SOLAR | WEST | 2022 | 0 | 76% | 0 | 2022-01-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 261 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-09-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 262 | WAGYU SOLAR | 18INR0062 |  | BRAZORIA | SOLAR | COASTAL | 2020 | 120 | 76% | 91.2 | 2020-06-01 | N/A | PLANNED | 2020-05-22 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
11 | Preliminary Summer 2020 SARA | 263 | CHISHOLM GRID | 20INR0089 |  | TARRANT | STORAGE | NORTH | 2020 | 0 | 0% | 0 | 2020-11-20 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 264 | EUNICE STORAGE | 20INR0220 |  | ANDREWS | STORAGE | WEST | 2020 | 0 | 0% | 0 | 2020-12-31 | N/A | PLANNED | 2020-12-01 | No | 2020-06-01 | P2 | COD delays without part 2 approval
11 | Preliminary Summer 2020 SARA | 265 | MADERO GRID | 21INR0244 |  | HIDALGO | STORAGE | SOUTH | 2021 | 0 | 0% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 392 | FLAT TOP BATTERY |  | FLTBES_BESS1 | REEVES | STORAGE | WEST | 2019 | 9.9 | 0% | 0 | 2019-09-01 | 2020-05-22 | OPERATIONAL | 2020-05-05 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 268 | JOHNSON CITY BESS |  | JC_BAT | BLANCO | STORAGE | SOUTH | 2020 | 2.3 | 0% | 0 | 2020-02-01 | 2020-10-12 | OPERATIONAL | #N/A | No | 2020-06-01 | O4 | operational after August 1st
10 | Dec 2019 CDR | 393 | JOHNSON CITY BESS |  | JC_BAT | BLANCO | STORAGE | SOUTH | 2020 | 2.3 | 0% | 0 | 2020-02-01 | 2020-10-12 | OPERATIONAL | #N/A | No | 2020-06-01 | O4 | operational after August 1st
9 | May 2019 CDR | 504 | JOHNSON CITY BESS |  | JC_BAT | BLANCO | OTHER | SOUTH | 2019 | 2.25 | 0% | 0 | 2019-11-06 | 2020-10-12 | OPERATIONAL | #N/A | No | 2020-06-01 | O4 | operational after August 1st
12 | Final Summer 2020 SARA | 141 | JOHNSON CITY BESS |  | JC_BAT_UNIT_1 | BLANCO | STORAGE | SOUTH | 2020 | 0 | 0% | 0 | 2020-02-01 | 2020-10-12 | OPERATIONAL | #N/A | No | 2020-06-01 | O4 | operational after August 1st
10 | Dec 2019 CDR | 271 | FRIENDSWOOD II | 19INR0180 |  | BRAZORIA | GAS | COASTAL | 2021 | 0 | 100% | 0 | 2021-02-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
10 | Dec 2019 CDR | 272 | HALYARD WHARTON ENERGY CENTER | 16INR0044 |  | WHARTON | GAS | SOUTH | 2021 | 0 | 100% | 0 | 2021-06-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 273 | HUDSON (BRAZORIA ENERGY G) | 16INR0076 |  | BRAZORIA | GAS | COASTAL | 2019 | 90 | 100% | 90 | 2019-12-31 | 2020-07-17 | OPERATIONAL | 2019-08-16 | No | 2020-06-01 | O3 | operational by August 1st
10 | Dec 2019 CDR | 274 | LEVEE (FREEPORT LNG) | 16INR0003 |  | BRAZORIA | GAS | COASTAL | 2019 | 11 | 100% | 11 | 2019-12-15 | 2019-12-04 | OPERATIONAL | 2019-09-04 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 275 | MIRAGE | 17INR0022 |  | HARRIS | GAS | HOUSTON | 2020 | 11 | 100% | 11 | 2020-02-07 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 276 | VICTORIA CITY (CITYVICT) | 18INR0035 |  | REFUGIO | GAS | COASTAL | 2019 | 100 | 100% | 100 | 2019-12-31 | 2020-02-06 | OPERATIONAL | 2019-12-17 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 277 | CHALUPA WIND | 20INR0042 |  | CAMERON | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-12-21 | N/A | PLANNED | 2020-08-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 278 | CHOCOLATE BAYOU W | 16INR0074 |  | BRAZORIA | WIND-C | COASTAL | 2021 | 0 | 63% | 0 | 2021-05-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 279 | CRANEL WIND | 19INR0112 |  | REFUGIO | WIND-C | COASTAL | 2020 | 220 | 63% | 138.6 | 2020-04-10 | N/A | PLANNED | 2020-05-19 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 280 | EAST RAYMOND WIND | 18INR0059 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-06-30 | N/A | PLANNED | 2020-10-06 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 281 | KARANKAWA WIND | 18INR0014 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 206.6 | 63% | 130.158 | 2019-12-06 | 2019-12-30 | OPERATIONAL | 2019-11-07 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 282 | KARANKAWA WIND 2 | 19INR0074 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 101 | 63% | 63.63 | 2019-11-26 | 2019-12-30 | OPERATIONAL | 2019-11-05 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 283 | LAS MAJADAS WIND | 17INR0035 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-10-29 | N/A | PLANNED | 2020-10-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 284 | PALMAS ALTAS WIND | 17INR0037 |  | CAMERON | WIND-C | COASTAL | 2019 | 144.9 | 63% | 91.287 | 2019-12-31 | 2020-11-12 | OPERATIONAL | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 285 | PEYTON CREEK WIND | 18INR0018 |  | MATAGORDA | WIND-C | COASTAL | 2019 | 151.2 | 63% | 95.256 | 2020-02-28 | 2020-06-04 | OPERATIONAL | 2019-11-14 | No | 2020-06-01 | O2 | operational by July 1st
10 | Dec 2019 CDR | 286 | SHAFFER (PATRIOT WIND/PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2019 | 226 | 63% | 142.38 | 2019-12-20 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 287 | WEST RAYMOND (EL TRUENO) WIND | 20INR0088 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 63% | 0 | 2020-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 288 | ARMSTRONG WIND | 18INR0029 |  | ARMSTRONG | WIND-P | PANHANDLE | 2020 | 253 | 29% | 73.37 | 2020-03-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
10 | Dec 2019 CDR | 289 | CANADIAN BREAKS WIND | 13INR0026 |  | OLDHAM | WIND-P | PANHANDLE | 2019 | 210 | 29% | 60.9 | 2019-10-31 | 2019-12-17 | OPERATIONAL | 2019-07-18 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 290 | GOODNIGHT WIND | 14INR0033 |  | ARMSTRONG | WIND-P | PANHANDLE | 2020 | 0 | 29% | 0 | 2020-12-12 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 291 | HART WIND | 16INR0033 |  | CASTRO | WIND-P | PANHANDLE | 2021 | 0 | 29% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 292 | MARIAH DEL ESTE | 13INR0010a |  | PARMER | WIND-P | PANHANDLE | 2020 | 0 | 29% | 0 | 2020-10-30 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 293 | NORTHDRAW WIND | 13INR0025 |  | RANDALL | WIND-P | PANHANDLE | 2020 | 0 | 29% | 0 | 2020-08-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 294 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND-P | PANHANDLE | 2022 | 0 | 29% | 0 | 2022-12-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 295 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND-P | PANHANDLE | 2020 | 0 | 29% | 0 | 2020-12-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
10 | Dec 2019 CDR | 296 | WILDROSE WIND (SWISHER WIND) | 13INR0038 |  | SWISHER | WIND-P | PANHANDLE | 2021 | 0 | 29% | 0 | 2021-12-30 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 297 | AVIATOR WIND | 19INR0156 |  | COKE | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-10-01 | N/A | PLANNED | 2020-06-24 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 298 | BAIRD NORTH WIND | 20INR0083 |  | CALLAHAN | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-06-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 299 | BARROW RANCH (JUMBO HILL WIND) | 18INR0038 |  | ANDREWS | WIND-O | WEST | 2020 | 160 | 16% | 25.6 | 2020-03-23 | N/A | PLANNED | 2020-02-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 300 | BIG SAMPSON WIND | 16INR0104 |  | CROCKETT | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-09-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 301 | BLACKJACK CREEK WIND | 20INR0068 |  | BEE | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 302 | BLUE SUMMIT WIND 2 | 18INR0070 |  | WILBARGER | WIND-O | WEST | 2019 | 102 | 16% | 16.32 | 2020-06-30 | 2020-04-06 | OPERATIONAL | 2019-01-10 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 303 | BLUE SUMMIT WIND 3 | 19INR0182 |  | WILBARGER | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-06-30 | 2020-05-19 | OPERATIONAL | 2019-12-11 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 304 | CABEZON WIND (RIO BRAVO I WIND) | 17INR0005 |  | STARR | WIND-O | SOUTH | 2019 | 237.6 | 16% | 38.016 | 2019-12-11 | 2019-12-17 | OPERATIONAL | 2019-03-14 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 305 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND-O | WEST | 2019 | 148.4 | 16% | 23.744 | 2019-12-15 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 306 | CANYON WIND | 18INR0030 |  | SCURRY | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-03-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 307 | COYOTE WIND | 17INR0027b |  | SCURRY | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-10-29 | N/A | PLANNED | 2020-11-25 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 308 | EDMONDSON RANCH WIND | 18INR0043 |  | GLASSCOCK | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-09-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 309 | FOARD CITY WIND | 19INR0019 |  | FOARD | WIND-O | WEST | 2019 | 350 | 16% | 56 | 2019-10-30 | 2019-12-05 | OPERATIONAL | 2019-08-20 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 310 | GOPHER CREEK WIND | 18INR0067 |  | BORDEN | WIND-O | WEST | 2019 | 158 | 16% | 25.28 | 2019-11-15 | 2020-03-09 | OPERATIONAL | 2019-05-30 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 311 | GRIFFIN TRAIL WIND | 20INR0052 |  | KNOX | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-09-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 312 | HARALD (BEARKAT WIND B) | 15INR0064b |  | GLASSCOCK | WIND-O | WEST | 2020 | 162.1 | 16% | 25.936 | 2020-03-20 | N/A | PLANNED | 2020-05-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 313 | HIDALGO II WIND | 19INR0053 |  | HIDALGO | WIND-O | SOUTH | 2019 | 51 | 16% | 8.16 | 2019-12-16 | N/A | PLANNED | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 314 | HIGH LONESOME W | 19INR0038 |  | CROCKETT | WIND-O | WEST | 2019 | 449.5 | 16% | 71.92 | 2019-12-20 | N/A | PLANNED | 2019-11-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 315 | HIGH LONESOME WIND PHASE II | 20INR0262 |  | CROCKETT | WIND-O | WEST | 2020 | 50.6 | 16% | 8.096 | 2020-01-30 | N/A | PLANNED | 2020-02-28 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 316 | KAISER CREEK WIND | 18INR0042 |  | CALLAHAN | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-12-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 317 | KONTIKI 1 WIND (ERIK) | 19INR0099a |  | GLASSCOCK | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 318 | KONTIKI 2 WIND (ERNEST) | 19INR0099b |  | GLASSCOCK | WIND-O | WEST | 2022 | 0 | 16% | 0 | 2022-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 319 | LAS LOMAS WIND | 16INR0111 |  | STARR | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-12-01 | N/A | PLANNED | 2020-12-08 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 320 | LOMA PINTA WIND | 16INR0112 |  | LA SALLE | WIND-O | SOUTH | 2020 | 200 | 16% | 32 | 2020-05-31 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 321 | LORAINE WINDPARK PHASE III | 18INR0068 |  | MITCHELL | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 322 | MAVERICK CREEK I | 20INR0045 |  | CONCHO | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-09-01 | N/A | PLANNED | 2020-09-01 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 323 | MAVERICK CREEK II | 20INR0046 |  | CONCHO | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-11-11 | N/A | PLANNED | 2020-11-02 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 324 | MESTENO WIND | 16INR0081 |  | STARR | WIND-O | SOUTH | 2020 | 201.6 | 16% | 32.256 | 2020-03-01 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 325 | OVEJA WIND | 18INR0033 |  | IRION | WIND-O | WEST | 2019 | 300 | 16% | 48 | 2019-10-31 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 326 | PRAIRIE HILL WIND | 19INR0100 |  | MCLENNAN | WIND-O | NORTH | 2020 | 0 | 16% | 0 | 2020-09-01 | N/A | PLANNED | 2020-11-12 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 327 | RANCHERO WIND | 20INR0011 |  | CROCKETT | WIND-O | WEST | 2019 | 300 | 16% | 48 | 2019-09-30 | 2020-05-04 | OPERATIONAL | 2019-09-04 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 328 | RELOJ DEL SOL WIND | 17INR0025 |  | ZAPATA | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-10-31 | N/A | PLANNED | 2020-12-29 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 329 | RTS 2 WIND (HEART OF TEXAS WIND) | 18INR0016 |  | MCCULLOCH | WIND-O | SOUTH | 2020 | 0 | 16% | 0 | 2020-07-10 | N/A | PLANNED | 2020-04-29 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 330 | SAGE DRAW WIND | 19INR0163 |  | LYNN | WIND-O | WEST | 2020 | 338 | 16% | 54.08 | 2020-03-31 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 331 | TG EAST WIND | 19INR0052 |  | KNOX | WIND-O | WEST | 2021 | 0 | 16% | 0 | 2021-12-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 332 | VERA WIND | 19INR0051 |  | KNOX | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-07-01 | N/A | PLANNED | 2020-07-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 333 | WHITE MESA WIND | 19INR0128 |  | CROCKETT | WIND-O | WEST | 2020 | 0 | 16% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 334 | WHITEHORSE WIND | 19INR0080 |  | FISHER | WIND-O | WEST | 2020 | 418.9 | 16% | 67.024 | 2020-03-09 | N/A | PLANNED | 2019-12-27 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 335 | WILSON RANCH (INFINITY LIVE OAK WIND) | 12INR0060 |  | SCHLEICHER | WIND-O | WEST | 2020 | 199.5 | 16% | 31.92 | 2020-01-15 | 2020-04-17 | OPERATIONAL | 2018-11-29 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 336 | WKN AMADEUS WIND | 14INR0009 |  | FISHER | WIND-O | WEST | 2020 | 250.1 | 16% | 40.016 | 2020-05-19 | N/A | PLANNED | 2020-10-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 337 | AGATE SOLAR | 20INR0023 |  | ELLIS | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-08-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 338 | ANSON SOLAR | 19INR0081 |  | JONES | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | 2020-12-30 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 339 | ARAGORN SOLAR | 19INR0088 |  | CULBERSON | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 340 | BRAVEPOST SOLAR | 20INR0053 |  | TOM GREEN | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 341 | COTTONWOOD BAYOU | 19INR0134 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 342 | ELARA SOLAR | 21INR0276 |  | FRIO | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-04-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 343 | EMERALD GROVE SOLAR (PECOS SOLAR POWER I) | 15INR0059 |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-04-10 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 344 | FORT BEND SOLAR | 18INR0053 |  | FORT BEND | SOLAR | HOUSTON | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 345 | FOWLER RANCH | 18INR0039 |  | CRANE | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-06-03 | 2020-08-28 | OPERATIONAL | 2020-06-16 | No | 2020-06-01 | O4 | operational after August 1st
10 | Dec 2019 CDR | 346 | GALLOWAY SOLAR | 19INR0121 |  | CONCHO | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 347 | GARNET SOLAR | 20INR0021 |  | WILLIAMSON | SOLAR | SOUTH | 2020 | 0 | 76% | 0 | 2020-12-18 | N/A | INACTIVE | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 348 | GREASEWOOD SOLAR | 19INR0034 |  | PECOS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-09-30 | N/A | PLANNED | 2020-10-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 349 | HOLSTEIN SOLAR | 19INR0009 |  | NOLAN | SOLAR | WEST | 2020 | 204.5 | 76% | 155.42 | 2020-06-01 | 2020-05-28 | OPERATIONAL | 2020-01-16 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 350 | HORIZON SOLAR | 21INR0261 |  | FRIO | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 351 | HOVEY (BARILLA SOLAR 1B) | 12INR0059b |  | PECOS | SOLAR | WEST | 2019 | 7.4 | 76% | 5.624 | 2019-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 352 | IMPACT SOLAR | 19INR0151 |  | LAMAR | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-12-15 | N/A | PLANNED | 2020-09-02 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 353 | IP TITAN | 20INR0032 |  | CULBERSON | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 354 | JUNO SOLAR | 21INR0026 |  | BORDEN | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 355 | KELLAM SOLAR | 20INR0261 |  | VAN ZANDT | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-06-15 | 2020-12-24 | OPERATIONAL | 2020-11-17 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 356 | LAPETUS SOLAR | 19INR0185 |  | ANDREWS | SOLAR | WEST | 2019 | 100 | 76% | 76 | 2019-12-31 | 2020-06-24 | OPERATIONAL | 2019-12-06 | No | 2020-06-01 | O2 | operational by July 1st
10 | Dec 2019 CDR | 357 | LILY SOLAR | 19INR0044 |  | KAUFMAN | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-12-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 358 | LONG DRAW SOLAR | 18INR0055 |  | BORDEN | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-06-29 | N/A | PLANNED | 2020-11-20 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 359 | LONG POINT SOLAR | 19INR0042 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-12-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 360 | MISAE SOLAR | 18INR0045 |  | CHILDRESS | SOLAR | PANHANDLE | 2019 | 240.8 | 76% | 183.008 | 2019-12-27 | N/A | PLANNED | 2020-01-16 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 361 | MISAE SOLAR II | 20INR0091 |  | CHILDRESS | SOLAR | PANHANDLE | 2021 | 0 | 76% | 0 | 2021-06-21 | N/A | INACTIVE | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 362 | MORROW LAKE SOLAR | 19INR0155 |  | FRIO | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-04-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 363 | MUSTANG CREEK SOLAR | 18INR0050 |  | JACKSON | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 364 | MYRTLE SOLAR | 19INR0041 |  | BRAZORIA | SOLAR | COASTAL | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 365 | NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 366 | NORTON SOLAR | 19INR0035 |  | RUNNELS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 367 | OBERON SOLAR | 19INR0083 |  | ECTOR | SOLAR | WEST | 2020 | 180 | 76% | 136.8 | 2020-03-09 | 2020-07-13 | OPERATIONAL | 2020-04-08 | No | 2020-06-01 | O3 | operational by August 1st
10 | Dec 2019 CDR | 368 | OXY SOLAR | 19INR0184 |  | ECTOR | SOLAR | WEST | 2020 | 16.2 | 76% | 12.312 | 2020-05-15 | N/A | PLANNED | 2019-07-31 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 369 | PFLUGERVILLE SOLAR | 15INR0090 |  | TRAVIS | SOLAR | SOUTH | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 370 | PHOENIX SOLAR | 19INR0091 |  | FANNIN | SOLAR | NORTH | 2021 | 0 | 76% | 0 | 2021-04-23 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 371 | PROSPERO SOLAR | 19INR0092 |  | ANDREWS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-06-30 | 2020-06-30 | OPERATIONAL | 2020-04-24 | No | 2020-06-01 | O2 | operational by July 1st
10 | Dec 2019 CDR | 372 | QUEEN SOLAR | 19INR0102 |  | UPTON | SOLAR | WEST | 2019 | 400 | 76% | 304 | 2019-12-20 | 2020-05-04 | OPERATIONAL | 2019-12-12 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 373 | RAMBLER SOLAR | 19INR0114 |  | TOM GREEN | SOLAR | WEST | 2020 | 200 | 76% | 152 | 2020-05-31 | 2020-10-01 | OPERATIONAL | 2020-04-01 | No | 2020-06-01 | O4 | operational after August 1st
10 | Dec 2019 CDR | 374 | RAYOS DEL SOL | 19INR0045 |  | CAMERON | SOLAR | COASTAL | 2020 | 0 | 76% | 0 | 2020-10-22 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 375 | RE MAPLEWOOD 2A SOLAR | 17INR0020a |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-04-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 376 | RE MAPLEWOOD 2B SOLAR | 17INR0020b |  | PECOS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 377 | RE MAPLEWOOD 2C SOLAR | 17INR0020c |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-30 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
10 | Dec 2019 CDR | 378 | RIPPEY SOLAR | 20INR0031 |  | COOKE | SOLAR | NORTH | 2020 | 0 | 76% | 0 | 2020-12-31 | 2020-12-30 | OPERATIONAL | 2020-11-20 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 379 | RODEO SOLAR | 19INR0103 |  | ANDREWS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 380 | SHAKES SOLAR | 19INR0073 |  | ZAVALA | SOLAR | SOUTH | 2021 | 0 | 76% | 0 | 2021-02-12 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 381 | SODA LAKE SOLAR 1 | 18INR0040 |  | CRANE | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
10 | Dec 2019 CDR | 382 | SODA LAKE SOLAR 2 | 20INR0143 |  | CRANE | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 383 | SPINEL SOLAR | 20INR0025 |  | MEDINA | SOLAR | SOUTH | 2020 | 0 | 76% | 0 | 2020-12-17 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
10 | Dec 2019 CDR | 384 | TAYGETE II SOLAR | 21INR0233 |  | PECOS | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 385 | TAYGETE SOLAR | 20INR0054 |  | PECOS | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-12-01 | N/A | PLANNED | 2020-12-07 | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 386 | TEXAS SOLAR NOVA | 19INR0001 |  | KENT | SOLAR | WEST | 2021 | 0 | 76% | 0 | 2021-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 387 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2020 | 0 | 76% | 0 | 2020-09-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 388 | WAGYU SOLAR | 18INR0062 |  | BRAZORIA | SOLAR | COASTAL | 2020 | 120 | 76% | 91.2 | 2020-06-01 | N/A | PLANNED | 2020-05-22 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
10 | Dec 2019 CDR | 389 | WEST OF PECOS SOLAR | 14INR0044 |  | REEVES | SOLAR | WEST | 2019 | 100 | 76% | 76 | 2019-12-20 | 2019-12-20 | OPERATIONAL | 2019-10-08 | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 390 | CHISHOLM GRID | 20INR0089 |  | TARRANT | STORAGE | NORTH | 2020 | 200 | 0% | 0 | 2020-11-20 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
10 | Dec 2019 CDR | 394 | PORT LAVACA BATTERY |  | PTLBES_BESS1 | CALHOUN | STORAGE | SOUTH | 2019 | 9.9 | 0% | 0 | 2019-11-15 | 2020-01-29 | OPERATIONAL | #N/A | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 506 | RABBIT HILL ENERGY STORAGE PROJECT |  | RHESS | WILLIAMSON | OTHER | SOUTH | 2019 | 9.9 | 0% | 0 | 2019-05-25 | 2020-03-06 | OPERATIONAL | #N/A | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 269 | RABBIT HILL ENERGY STORAGE PROJECT |  | RHESS2_ESS_1 | WILLIAMSON | STORAGE | SOUTH | 2019 | 9.9 | 0% | 0 | 2019-07-01 | 2020-03-06 | OPERATIONAL | #N/A | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 396 | RABBIT HILL ENERGY STORAGE PROJECT |  | RHESS2_ESS_1 | WILLIAMSON | STORAGE | SOUTH | 2019 | 9.9 | 0% | 0 | 2019-07-01 | 2020-03-06 | OPERATIONAL | #N/A | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 395 | PROSPECT STORAGE |  | WCOLLDG_BSS_U1 | BRAZORIA | STORAGE | HOUSTON | 2019 | 9.9 | 0% | 0 | 2019-08-02 | 2020-01-17 | OPERATIONAL | #N/A | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 270 | WORSHAM BATTERY |  | WRSBES_BESS1 | REEVES | STORAGE | WEST | 2019 | 9.9 | 0% | 0 | 2019-08-28 | 2020-04-07 | OPERATIONAL | #N/A | Yes | 2020-06-01 | O1 | operational by June 1st
10 | Dec 2019 CDR | 397 | WORSHAM BATTERY |  | WRSBES_BESS1 | REEVES | STORAGE | WEST | 2019 | 9.9 | 0% | 0 | 2019-08-28 | 2020-04-07 | OPERATIONAL | #N/A | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 398 | FGE TEXAS I PROJECT | 16INR0010 |  | MITCHELL | GAS | WEST | 2021 | 0 | 100% | 0 | 2021-04-30 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
9 | May 2019 CDR | 399 | HALYARD HENDERSON | 16INR0045 |  | HENDERSON | GAS | NORTH | 2021 | 0 | 100% | 0 | 2021-05-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
9 | May 2019 CDR | 400 | HALYARD WHARTON ENERGY CENTER | 16INR0044 |  | WHARTON | GAS | SOUTH | 2021 | 0 | 100% | 0 | 2021-06-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
9 | May 2019 CDR | 401 | HUDSON (BRAZORIA ENERGY G) | 16INR0076 |  | BRAZORIA | GAS | COASTAL | 2019 | 90 | 100% | 90 | 2019-05-01 | 2020-07-17 | OPERATIONAL | 2019-08-16 | No | 2020-06-01 | O3 | operational by August 1st
9 | May 2019 CDR | 402 | MIRAGE | 17INR0022 |  | HARRIS | GAS | HOUSTON | 2019 | 11 | 100% | 11 | 2019-02-18 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 403 | VICTORIA CITY (CITYVICT) | 18INR0035 |  | REFUGIO | GAS | COASTAL | 2019 | 100 | 100% | 100 | 2019-11-01 | 2020-02-06 | OPERATIONAL | 2019-12-17 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 404 | VICTORIA PORT (VICTPORT) | 17INR0045 |  | CALHOUN | GAS | COASTAL | 2019 | 100 | 100% | 100 | 2019-05-03 | 2019-09-30 | OPERATIONAL | 2019-06-19 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 405 | ARMSTRONG WIND | 18INR0029 |  | ARMSTRONG | WIND | PANHANDLE | 2020 | 253 | 15% | 37.95 | 2020-03-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
9 | May 2019 CDR | 406 | BARROW RANCH (JUMBO HILL WIND) | 18INR0038 |  | ANDREWS | WIND | WEST | 2019 | 160 | 15% | 24 | 2019-12-01 | N/A | PLANNED | 2020-02-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 407 | BLUE SUMMIT II | 18INR0070 |  | WILBARGER | WIND | WEST | 2019 | 102 | 15% | 15.3 | 2019-04-15 | 2020-04-06 | OPERATIONAL | 2019-01-10 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 408 | BLUE SUMMIT WIND III | 19INR0182 |  | WILBARGER | WIND | WEST | 2019 | 200 | 15% | 30 | 2019-11-01 | 2020-05-19 | OPERATIONAL | 2019-12-11 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 409 | CABEZON WIND (RIO BRAVO I WIND) | 17INR0005 |  | STARR | WIND | SOUTH | 2019 | 237.6 | 15% | 35.64 | 2019-05-31 | 2019-12-17 | OPERATIONAL | 2019-03-14 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 410 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND | WEST | 2019 | 148.4 | 15% | 22.26 | 2019-04-29 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 411 | CANADIAN BREAKS WIND | 13INR0026 |  | OLDHAM | WIND | PANHANDLE | 2019 | 210 | 15% | 31.5 | 2019-09-13 | 2019-12-17 | OPERATIONAL | 2019-07-18 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 412 | CANYON WIND | 18INR0030 |  | SCURRY | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 413 | COYOTE WIND | 17INR0027b |  | SCURRY | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-06-03 | N/A | PLANNED | 2020-11-25 | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 414 | DARMSTADT | 18INR0023 |  | SCHLEICHER | WIND | WEST | 2019 | 200.9 | 15% | 30.135 | 2019-12-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
9 | May 2019 CDR | 415 | EASTER WIND | 15INR0063 |  | CASTRO | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2020-10-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
9 | May 2019 CDR | 416 | EDMONDSON RANCH WIND | 18INR0043 |  | GLASSCOCK | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-06-26 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 417 | FOARD CITY WIND | 19INR0019 |  | FOARD | WIND | WEST | 2019 | 350 | 15% | 52.5 | 2019-09-24 | 2019-12-05 | OPERATIONAL | 2019-08-20 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 418 | GOODNIGHT WIND | 14INR0033 |  | ARMSTRONG | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2020-08-15 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
9 | May 2019 CDR | 419 | GOPHER CREEK WIND | 18INR0067 |  | BORDEN | WIND | WEST | 2019 | 158 | 15% | 23.7 | 2019-07-31 | 2020-03-09 | OPERATIONAL | 2019-05-30 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 420 | GRAPE CREEK WIND | 19INR0156 |  | COKE | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-10-01 | N/A | PLANNED | 2020-06-24 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 421 | GRIFFIN TRAIL WIND | 20INR0052 |  | KNOX | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-09-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 422 | HARALD (BEARKAT WIND B) | 15INR0064b |  | GLASSCOCK | WIND | WEST | 2019 | 162.1 | 15% | 24.315 | 2019-12-13 | N/A | PLANNED | 2020-05-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 423 | HART WIND | 16INR0033 |  | CASTRO | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 424 | HIDALGO II WIND | 19INR0053 |  | HIDALGO | WIND | SOUTH | 2019 | 51 | 15% | 7.65 | 2019-11-15 | N/A | PLANNED | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 425 | HIGH LONESOME W | 19INR0038 |  | CROCKETT | WIND | WEST | 2019 | 449.5 | 15% | 67.425 | 2019-12-31 | N/A | PLANNED | 2019-11-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 426 | KONTIKI 1 WIND (ERIK) | 19INR0099a |  | GLASSCOCK | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 427 | KONTIKI 2 WIND (ERNEST) | 19INR0099b |  | GLASSCOCK | WIND | WEST | 2021 | 0 | 15% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 428 | LAS LOMAS WIND | 16INR0111 |  | STARR | WIND | SOUTH | 2019 | 200 | 15% | 30 | 2019-12-31 | N/A | PLANNED | 2020-12-08 | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 429 | LOCKETT WIND FARM | 16INR0062b |  | WILBARGER | WIND | WEST | 2019 | 184 | 15% | 27.6 | 2019-09-30 | 2019-09-19 | OPERATIONAL | 2019-05-31 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 430 | LOMA PINTA WIND | 16INR0112 |  | LA SALLE | WIND | SOUTH | 2019 | 200 | 15% | 30 | 2019-11-30 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
9 | May 2019 CDR | 431 | LORAINE WINDPARK PHASE III | 18INR0068 |  | MITCHELL | WIND | WEST | 2020 | 100 | 15% | 15 | 2020-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 432 | MARIAH DEL ESTE | 13INR0010a |  | PARMER | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2020-10-30 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
9 | May 2019 CDR | 433 | MAVERICK CREEK I | 20INR0045 |  | CONCHO | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-09-01 | N/A | PLANNED | 2020-09-01 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 434 | MAVERICK CREEK II | 20INR0046 |  | CONCHO | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-09-01 | N/A | PLANNED | 2020-11-02 | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 435 | MESTENO WIND | 16INR0081 |  | STARR | WIND | SOUTH | 2020 | 201.6 | 15% | 30.24 | 2020-03-01 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 436 | NORTHDRAW WIND | 13INR0025 |  | RANDALL | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2020-08-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
9 | May 2019 CDR | 437 | OVEJA WIND | 18INR0033 |  | IRION | WIND | WEST | 2019 | 300 | 15% | 45 | 2019-06-30 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 438 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2020-12-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
9 | May 2019 CDR | 439 | PRAIRIE HILL WIND | 19INR0100 |  | MCLENNAN | WIND | NORTH | 2020 | 300 | 15% | 45 | 2020-06-01 | N/A | PLANNED | 2020-11-12 | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 440 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2020-12-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
9 | May 2019 CDR | 441 | RANCHERO WIND | 20INR0011 |  | CROCKETT | WIND | WEST | 2019 | 300 | 15% | 45 | 2019-09-30 | 2020-05-04 | OPERATIONAL | 2019-09-04 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 442 | RELOJ DEL SOL WIND | 17INR0025 |  | ZAPATA | WIND | SOUTH | 2020 | 0 | 15% | 0 | 2020-10-31 | N/A | PLANNED | 2020-12-29 | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 443 | RTS 2 WIND (HEART OF TEXAS WIND) | 18INR0016 |  | MCCULLOCH | WIND | SOUTH | 2020 | 0 | 15% | 0 | 2020-06-30 | N/A | PLANNED | 2020-04-29 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 444 | S_HILLS WIND (LITTLE MOUNTAIN WIND) | 12INR0055 |  | BAYLOR | WIND | WEST | 2019 | 30.2 | 15% | 4.53 | 2019-05-30 | 2019-08-07 | OPERATIONAL | 2019-04-19 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 445 | SAGE DRAW WIND | 19INR0163 |  | LYNN | WIND | WEST | 2020 | 338 | 15% | 50.7 | 2020-03-31 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 446 | TG EAST WIND | 19INR0052 |  | KNOX | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-10-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 447 | TORRECILLAS WIND | 14INR0045 |  | WEBB | WIND | SOUTH | 2019 | 300.5 | 15% | 45.075 | 2019-04-15 | 2019-11-07 | OPERATIONAL | 2019-02-26 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 448 | VERA WIND | 19INR0051 |  | KNOX | WIND | WEST | 2020 | 242.8 | 15% | 36.42 | 2020-06-01 | N/A | PLANNED | 2020-07-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 449 | WHITE MESA WIND | 19INR0128 |  | CROCKETT | WIND | WEST | 2020 | 0 | 15% | 0 | 2020-09-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 450 | WHITEHORSE WIND | 19INR0080 |  | FISHER | WIND | WEST | 2019 | 418.9 | 15% | 62.835 | 2019-12-15 | N/A | PLANNED | 2019-12-27 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 451 | WILDROSE WIND (SWISHER WIND) | 13INR0038 |  | SWISHER | WIND | PANHANDLE | 2021 | 0 | 15% | 0 | 2021-12-30 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
9 | May 2019 CDR | 452 | WILSON RANCH (INFINITY LIVE OAK WIND) | 12INR0060 |  | SCHLEICHER | WIND | WEST | 2019 | 199.5 | 15% | 29.925 | 2019-05-31 | 2020-04-17 | OPERATIONAL | 2018-11-29 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 453 | WKN AMADEUS WIND | 14INR0009 |  | FISHER | WIND | WEST | 2020 | 245.9 | 15% | 36.885 | 2020-05-15 | N/A | PLANNED | 2020-10-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 454 | CHALUPA WIND | 20INR0042 |  | CAMERON | WIND-C | COASTAL | 2020 | 0 | 58% | 0 | 2020-12-21 | N/A | PLANNED | 2020-08-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 455 | CRANEL WIND | 19INR0112 |  | REFUGIO | WIND-C | COASTAL | 2019 | 220 | 58% | 127.6 | 2019-12-31 | N/A | PLANNED | 2020-05-19 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 456 | KARANKAWA 2 WIND FARM | 19INR0074 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 101 | 58% | 58.58 | 2019-12-31 | 2019-12-30 | OPERATIONAL | 2019-11-05 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 457 | KARANKAWA WIND ALT A | 18INR0014 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 206.6 | 58% | 119.828 | 2019-12-31 | 2019-12-30 | OPERATIONAL | 2019-11-07 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 458 | LAS MAJADAS WIND | 17INR0035 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 58% | 0 | 2020-10-01 | N/A | PLANNED | 2020-10-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 459 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 162.9 | 58% | 94.482 | 2019-04-05 | 2019-08-15 | OPERATIONAL | 2018-12-04 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 460 | PALMAS ALTAS WIND | 17INR0037 |  | CAMERON | WIND-C | COASTAL | 2020 | 144.9 | 58% | 84.042 | 2020-01-10 | 2020-11-12 | OPERATIONAL | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 461 | SHAFFER (PATRIOT WIND/PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2019 | 226 | 58% | 131.08 | 2019-05-22 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 462 | PEYTON CREEK WIND | 18INR0018 |  | MATAGORDA | WIND-C | COASTAL | 2019 | 151.2 | 58% | 87.696 | 2019-12-01 | 2020-06-04 | OPERATIONAL | 2019-11-14 | No | 2020-06-01 | O2 | operational by July 1st
9 | May 2019 CDR | 463 | EAST RAYMOND WIND | 18INR0059 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 58% | 0 | 2020-09-15 | N/A | PLANNED | 2020-10-06 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 464 | AGATE SOLAR | 20INR0023 |  | ELLIS | SOLAR | NORTH | 2020 | 0 | 74% | 0 | 2020-08-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
9 | May 2019 CDR | 465 | ARAGORN SOLAR | 19INR0088 |  | CULBERSON | SOLAR | WEST | 2021 | 0 | 74% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 466 | BLUEBELL SOLAR (CAPRICORN RIDGE SOLAR) | 16INR0019 |  | COKE | SOLAR | WEST | 2019 | 30 | 74% | 22.2 | 2019-04-15 | 2019-11-07 | OPERATIONAL | 2018-10-25 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 467 | EMERALD GROVE SOLAR (PECOS SOLAR POWER I) | 15INR0059 |  | PECOS | SOLAR | WEST | 2020 | 108 | 74% | 79.92 | 2020-04-10 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 468 | FOWLER RANCH | 18INR0039 |  | CRANE | SOLAR | WEST | 2020 | 150 | 74% | 111 | 2020-04-30 | 2020-08-28 | OPERATIONAL | 2020-06-16 | No | 2020-06-01 | O4 | operational after August 1st
9 | May 2019 CDR | 469 | GALLOWAY SOLAR | 19INR0121 |  | CONCHO | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2020-12-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 470 | GARNET SOLAR | 20INR0021 |  | WILLIAMSON | SOLAR | SOUTH | 2020 | 0 | 74% | 0 | 2020-07-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 471 | GREASEWOOD SOLAR | 19INR0034 |  | PECOS | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2020-09-30 | N/A | PLANNED | 2020-10-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 472 | HOLSTEIN SOLAR | 19INR0009 |  | NOLAN | SOLAR | WEST | 2020 | 204 | 74% | 150.96 | 2020-04-01 | 2020-05-28 | OPERATIONAL | 2020-01-16 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 473 | HOVEY (BARILLA SOLAR 1B) | 12INR0059b |  | PECOS | SOLAR | WEST | 2019 | 7.4 | 74% | 5.476 | 2019-02-28 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 474 | IP TITAN | 20INR0032 |  | CULBERSON | SOLAR | WEST | 2021 | 0 | 74% | 0 | 2021-06-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 475 | JUNO SOLAR | 21INR0026 |  | BORDEN | SOLAR | WEST | 2021 | 0 | 74% | 0 | 2021-05-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 476 | LAPETUS SOLAR 2 | 19INR0185 |  | ANDREWS | SOLAR | WEST | 2019 | 100 | 74% | 74 | 2019-12-31 | 2020-06-24 | OPERATIONAL | 2019-12-06 | No | 2020-06-01 | O2 | operational by July 1st
9 | May 2019 CDR | 477 | LILY SOLAR | 19INR0044 |  | KAUFMAN | SOLAR | NORTH | 2020 | 150 | 74% | 111 | 2020-06-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 478 | LONG DRAW SOLAR | 18INR0055 |  | BORDEN | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2020-06-30 | N/A | PLANNED | 2020-11-20 | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 479 | MISAE SOLAR | 18INR0045 |  | CHILDRESS | SOLAR | PANHANDLE | 2019 | 240.8 | 74% | 178.192 | 2019-11-29 | N/A | PLANNED | 2020-01-16 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 480 | MISAE SOLAR II | 20INR0091 |  | CHILDRESS | SOLAR | PANHANDLE | 2020 | 0 | 74% | 0 | 2020-12-31 | N/A | INACTIVE | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 481 | MUSTANG CREEK SOLAR | 18INR0050 |  | JACKSON | SOLAR | SOUTH | 2020 | 150 | 74% | 111 | 2020-04-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 482 | NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2021 | 0 | 74% | 0 | 2021-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 483 | OBERON SOLAR | 19INR0083 |  | ECTOR | SOLAR | WEST | 2019 | 180 | 74% | 133.2 | 2019-12-15 | 2020-07-13 | OPERATIONAL | 2020-04-08 | No | 2020-06-01 | O3 | operational by August 1st
9 | May 2019 CDR | 484 | OXY SOLAR | 19INR0184 |  | ECTOR | SOLAR | WEST | 2019 | 16.2 | 74% | 11.988 | 2019-07-15 | N/A | PLANNED | 2019-07-31 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
9 | May 2019 CDR | 485 | PFLUGERVILLE SOLAR | 15INR0090 |  | TRAVIS | SOLAR | SOUTH | 2020 | 0 | 74% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 486 | PHOEBE SOLAR | 19INR0029 |  | WINKLER | SOLAR | WEST | 2019 | 250 | 74% | 185 | 2019-09-01 | 2019-11-26 | OPERATIONAL | 2019-06-05 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 487 | PROSPERO SOLAR | 19INR0092 |  | ANDREWS | SOLAR | WEST | 2020 | 300 | 74% | 222 | 2020-06-01 | 2020-06-30 | OPERATIONAL | 2020-04-24 | No | 2020-06-01 | O2 | operational by July 1st
9 | May 2019 CDR | 488 | QUEEN SOLAR | 19INR0102 |  | UPTON | SOLAR | WEST | 2019 | 400 | 74% | 296 | 2019-12-31 | 2020-05-04 | OPERATIONAL | 2019-12-12 | Yes | 2020-06-01 | O1 | operational by June 1st
9 | May 2019 CDR | 489 | RAMBLER SOLAR | 19INR0114 |  | TOM GREEN | SOLAR | WEST | 2019 | 150 | 74% | 111 | 2020-05-31 | 2020-10-01 | OPERATIONAL | 2020-04-01 | No | 2020-06-01 | O4 | operational after August 1st
9 | May 2019 CDR | 490 | RAYOS DEL SOL | 19INR0045 |  | CAMERON | SOLAR | COASTAL | 2020 | 0 | 74% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 491 | RE MAPLEWOOD 2A SOLAR | 17INR0020a |  | PECOS | SOLAR | WEST | 2020 | 222 | 74% | 164.28 | 2020-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 492 | RE MAPLEWOOD 2B SOLAR | 17INR0020b |  | PECOS | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 493 | RE MAPLEWOOD 2C SOLAR | 17INR0020c |  | PECOS | SOLAR | WEST | 2021 | 0 | 74% | 0 | 2021-06-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
9 | May 2019 CDR | 494 | SHAKES SOLAR | 19INR0073 |  | ZAVALA | SOLAR | SOUTH | 2020 | 206 | 74% | 152.44 | 2020-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 495 | SODA LAKE SOLAR 1 | 18INR0040 |  | CRANE | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2020-12-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
9 | May 2019 CDR | 496 | SODA LAKE SOLAR 2 | 20INR0143 |  | CRANE | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2020-12-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 497 | SPINEL SOLAR | 20INR0025 |  | MEDINA | SOLAR | SOUTH | 2020 | 0 | 74% | 0 | 2020-08-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
9 | May 2019 CDR | 498 | TAYGETE SOLAR | 20INR0054 |  | PECOS | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2020-12-01 | N/A | PLANNED | 2020-12-07 | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 499 | TAYGETE II SOLAR | 21INR0233 |  | PECOS | SOLAR | WEST | 2021 | 0 | 74% | 0 | 2021-02-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 500 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2020 | 104.6 | 74% | 77.404 | 2020-05-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
9 | May 2019 CDR | 501 | WEST OF PECOS SOLAR | 14INR0044 |  | REEVES | SOLAR | WEST | 2019 | 100 | 74% | 74 | 2019-12-15 | 2019-12-20 | OPERATIONAL | 2019-10-08 | Yes | 2020-06-01 | O1 | operational by June 1st
11 | Preliminary Summer 2020 SARA | 266 | COMMERCE ST ESS |  | X443ESS1 | BEXAR | STORAGE | SOUTH | 2019 | 10 | 0% | 0 | 2020-02-01 | 2020-10-06 | OPERATIONAL | 2019-11-26 | No | 2020-06-01 | O4 | operational after August 1st
10 | Dec 2019 CDR | 391 | COMMERCE ST ESS |  | X443ESS1 | BEXAR | STORAGE | SOUTH | 2020 | 10 | 0% | 0 | 2020-02-01 | 2020-10-06 | OPERATIONAL | 2019-11-26 | No | 2020-06-01 | O4 | operational after August 1st
9 | May 2019 CDR | 503 | COMMERCE ST ESS |  | X443ESS1 | BEXAR | OTHER | SOUTH | 2019 | 10 | 0% | 0 | 2019-06-01 | 2020-10-06 | OPERATIONAL | 2019-11-26 | No | 2020-06-01 | O4 | operational after August 1st
9 | May 2019 CDR | 505 | JUNO STORAGE | 21INR0032 |  | BORDEN | OTHER | WEST | 2021 | 0 | 0% | 0 | 2021-05-15 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
12 | Final Summer 2020 SARA | 139 | COMMERCE ST ESS |  | X443ESS1_SWRI | BEXAR | STORAGE | SOUTH | 2019 | 10 | 0% | 0 | 2019-06-01 | 2020-10-06 | OPERATIONAL | 2019-11-26 | No | 2020-06-01 | O4 | operational after August 1st
8 | Dec 2018 CDR | 507 | FGE TEXAS I PROJECT | 16INR0010 |  | MITCHELL | GAS | WEST | 2021 | 0 | 100% | 0 | 2019-05-26 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 508 | HALYARD HENDERSON | 16INR0045 |  | HENDERSON | GAS | NORTH | 2021 | 0 | 100% | 0 | 2019-05-27 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 509 | HALYARD WHARTON ENERGY CENTER | 16INR0044 |  | WHARTON | GAS | SOUTH | 2021 | 0 | 100% | 0 | 2019-05-28 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
8 | Dec 2018 CDR | 510 | HUDSON (BRAZORIA ENERGY G) | 16INR0076 |  | BRAZORIA | GAS | COASTAL | 2019 | 90 | 100% | 90 | 2019-05-29 | 2020-07-17 | OPERATIONAL | 2019-08-16 | No | 2020-06-01 | O3 | operational by August 1st
8 | Dec 2018 CDR | 511 | MIRAGE | 17INR0022 |  | HARRIS | GAS | HOUSTON | 2019 | 11 | 100% | 11 | 2019-05-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 512 | VICTORIA CITY (CITYVICT) | 18INR0035 |  | REFUGIO | GAS | COASTAL | 2019 | 100 | 100% | 100 | 2019-05-31 | 2020-02-06 | OPERATIONAL | 2019-12-17 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 513 | VICTORIA PORT (VICTPORT) | 17INR0045 |  | CALHOUN | GAS | COASTAL | 2019 | 100 | 100% | 100 | 2019-06-01 | 2019-09-30 | OPERATIONAL | 2019-06-19 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 514 | ARMSTRONG WIND | 18INR0029 |  | ARMSTRONG | WIND | PANHANDLE | 2020 | 253 | 15% | 37.95 | 2019-06-05 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 515 | BARROW RANCH (JUMBO HILL WIND) | 18INR0038 |  | ANDREWS | WIND | WEST | 2019 | 160 | 15% | 24 | 2019-06-06 | N/A | PLANNED | 2020-02-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 516 | BLUE SUMMIT II | 18INR0070 |  | WILBARGER | WIND | WEST | 2019 | 102 | 15% | 15.3 | 2019-06-07 | 2020-04-06 | OPERATIONAL | 2019-01-10 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 517 | CABEZON WIND (RIO BRAVO I WIND) | 17INR0005 |  | STARR | WIND | SOUTH | 2019 | 237.6 | 15% | 35.64 | 2019-06-08 | 2019-12-17 | OPERATIONAL | 2019-03-14 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 518 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND | WEST | 2018 | 148.4 | 15% | 22.26 | 2019-06-09 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 519 | CANADIAN BREAKS WIND | 13INR0026 |  | OLDHAM | WIND | PANHANDLE | 2019 | 210 | 15% | 31.5 | 2019-06-10 | 2019-12-17 | OPERATIONAL | 2019-07-18 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 520 | CANYON WIND | 18INR0030 |  | SCURRY | WIND | WEST | 2020 | 0 | 15% | 0 | 2019-06-11 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 521 | COMANCHE RUN WIND | 12INR0029 |  | SWISHER | WIND | PANHANDLE | 2019 | 500 | 15% | 75 | 2019-06-12 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 522 | COYOTE WIND | 17INR0027b |  | SCURRY | WIND | WEST | 2019 | 242.5 | 15% | 36.375 | 2019-06-13 | N/A | PLANNED | 2020-11-25 | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 523 | DARMSTADT | 18INR0023 |  | SCHLEICHER | WIND | WEST | 2019 | 200.9 | 15% | 30.135 | 2019-06-14 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 524 | EASTER WIND | 15INR0063 |  | CASTRO | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2019-06-15 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 525 | EDMONDSON RANCH WIND | 18INR0043 |  | GLASSCOCK | WIND | WEST | 2020 | 0 | 15% | 0 | 2019-06-16 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 526 | FOARD CITY WIND | 19INR0019 |  | FOARD | WIND | WEST | 2019 | 350 | 15% | 52.5 | 2019-06-17 | 2019-12-05 | OPERATIONAL | 2019-08-20 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 527 | GOODNIGHT WIND | 14INR0033 |  | ARMSTRONG | WIND | PANHANDLE | 2019 | 496.8 | 15% | 74.52 | 2019-06-18 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
8 | Dec 2018 CDR | 528 | GOPHER CREEK WIND | 18INR0067 |  | SCURRY | WIND | WEST | 2019 | 158 | 15% | 23.7 | 2019-06-19 | 2020-03-09 | OPERATIONAL | 2019-05-30 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 529 | HARALD (BEARKAT WIND B) | 15INR0064b |  | GLASSCOCK | WIND | WEST | 2019 | 162.1 | 15% | 24.315 | 2019-06-20 | N/A | PLANNED | 2020-05-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 530 | HART WIND | 16INR0033 |  | CASTRO | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2019-06-21 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 531 | HIGH LONESOME W | 19INR0038 |  | CROCKETT | WIND | WEST | 2019 | 449.5 | 15% | 67.425 | 2019-06-22 | N/A | PLANNED | 2019-11-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 532 | KONTIKI 1 WIND | 19INR0099a |  | GLASSCOCK | WIND | WEST | 2019 | 255.3 | 15% | 38.295 | 2019-06-23 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 533 | KONTIKI 2 WIND | 19INR0099b |  | GLASSCOCK | WIND | WEST | 2020 | 0 | 15% | 0 | 2019-06-24 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 534 | LOCKETT WIND FARM | 16INR0062b |  | WILBARGER | WIND | WEST | 2019 | 184 | 15% | 27.6 | 2019-06-25 | 2019-09-19 | OPERATIONAL | 2019-05-31 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 535 | LOMA PINTA WIND | 16INR0112 |  | LA SALLE | WIND | SOUTH | 2019 | 200 | 15% | 30 | 2019-06-26 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
8 | Dec 2018 CDR | 536 | LORAINE WINDPARK PHASE III | 18INR0068 |  | MITCHELL | WIND | WEST | 2018 | 100 | 15% | 15 | 2019-06-27 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 537 | MARIAH DEL ESTE | 13INR0010a |  | PARMER | WIND | PANHANDLE | 2018 | 152.5 | 15% | 22.875 | 2019-06-28 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
8 | Dec 2018 CDR | 538 | MAVERICK CREEK I | 20INR0045 |  | CONCHO | WIND | WEST | 2020 | 0 | 15% | 0 | 2019-06-29 | N/A | PLANNED | 2020-09-01 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 539 | MAVERICK CREEK II | 20INR0046 |  | CONCHO | WIND | WEST | 2020 | 0 | 15% | 0 | 2019-06-30 | N/A | PLANNED | 2020-11-02 | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 540 | MESTENO WIND | 16INR0081 |  | STARR | WIND | SOUTH | 2019 | 201.6 | 15% | 30.24 | 2019-07-01 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 541 | NORTHDRAW WIND | 13INR0025 |  | RANDALL | WIND | PANHANDLE | 2019 | 150 | 15% | 22.5 | 2019-07-02 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
8 | Dec 2018 CDR | 542 | OVEJA WIND | 18INR0033 |  | IRION | WIND | WEST | 2019 | 300 | 15% | 45 | 2019-07-03 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 543 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2019-07-04 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
8 | Dec 2018 CDR | 544 | PRAIRIE HILL WIND | 19INR0100 |  | LIMESTONE | WIND | NORTH | 2020 | 300 | 15% | 45 | 2019-07-05 | N/A | PLANNED | 2020-11-12 | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 545 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND | PANHANDLE | 2019 | 280.9 | 15% | 42.135 | 2019-07-06 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 546 | RANCHERO WIND | 20INR0011 |  | CROCKETT | WIND | WEST | 2019 | 300 | 15% | 45 | 2019-07-07 | 2020-05-04 | OPERATIONAL | 2019-09-04 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 547 | RTS 2 WIND (HEART OF TEXAS WIND) | 18INR0016 |  | MCCULLOCH | WIND | SOUTH | 2019 | 179.8 | 15% | 26.97 | 2019-07-08 | N/A | PLANNED | 2020-04-29 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 548 | S_HILLS WIND (LITTLE MOUNTAIN WIND) | 12INR0055 |  | BAYLOR | WIND | WEST | 2019 | 30.2 | 15% | 4.53 | 2019-07-09 | 2019-08-07 | OPERATIONAL | 2019-04-19 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 549 | SAGE DRAW WIND | 19INR0163 |  | LYNN | WIND | WEST | 2019 | 300 | 15% | 45 | 2019-07-10 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 550 | SCANDIA WIND DEF | 13INR0010def |  | PARMER | WIND | PANHANDLE | 2019 | 600.3 | 15% | 90.045 | 2019-07-11 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 551 | SILVER CANYON WIND A | 12INR0002a |  | BRISCOE | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2019-07-12 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 552 | TAHOKA WIND (STAKED PLAINS WIND 1) | 18INR0025 |  | LYNN | WIND | WEST | 2019 | 300 | 15% | 45 | 2019-07-13 | 2019-03-01 | OPERATIONAL | 2018-11-09 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 553 | TG EAST WIND | 19INR0052 |  | KNOX | WIND | WEST | 2019 | 275.6 | 15% | 41.34 | 2019-07-14 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 554 | TORRECILLAS WIND | 14INR0045 |  | WEBB | WIND | SOUTH | 2018 | 300.5 | 15% | 45.075 | 2019-07-15 | 2019-11-07 | OPERATIONAL | 2019-02-26 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 555 | VERA WIND | 19INR0051 |  | KNOX | WIND | WEST | 2019 | 242.8 | 15% | 36.42 | 2019-07-16 | N/A | PLANNED | 2020-07-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 556 | WILDROSE WIND (SWISHER WIND) | 13INR0038 |  | SWISHER | WIND | PANHANDLE | 2020 | 0 | 15% | 0 | 2019-07-17 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
8 | Dec 2018 CDR | 557 | WILSON RANCH (INFINITY LIVE OAK WIND) | 12INR0060 |  | SCHLEICHER | WIND | WEST | 2019 | 199.5 | 15% | 29.925 | 2019-07-18 | 2020-04-17 | OPERATIONAL | 2018-11-29 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 558 | WKN AMADEUS WIND | 14INR0009 |  | KENT | WIND | WEST | 2019 | 245.9 | 15% | 36.885 | 2019-07-19 | N/A | PLANNED | 2020-10-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 559 | CHALUPA WIND | 20INR0042 |  | CAMERON | WIND-C | COASTAL | 2020 | 0 | 58% | 0 | 2019-07-20 | N/A | PLANNED | 2020-08-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 560 | CRANEL WIND | 19INR0112 |  | REFUGIO | WIND-C | COASTAL | 2019 | 220 | 58% | 127.6 | 2019-07-21 | N/A | PLANNED | 2020-05-19 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 561 | KARANKAWA 2 WIND FARM | 19INR0074 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 200 | 58% | 116 | 2019-07-22 | 2019-12-30 | OPERATIONAL | 2019-11-05 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 562 | KARANKAWA WIND ALT A | 18INR0014 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 200 | 58% | 116 | 2019-07-23 | 2019-12-30 | OPERATIONAL | 2019-11-07 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 563 | LAS MAJADAS WIND | 17INR0035 |  | WILLACY | WIND-C | COASTAL | 2020 | 0 | 58% | 0 | 2019-07-24 | N/A | PLANNED | 2020-10-21 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 564 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2018 | 162.9 | 58% | 94.482 | 2019-07-25 | 2019-08-15 | OPERATIONAL | 2018-12-04 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 565 | PALMAS ALTAS WIND | 17INR0037 |  | CAMERON | WIND-C | COASTAL | 2019 | 144.9 | 58% | 84.042 | 2019-07-26 | 2020-11-12 | OPERATIONAL | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 566 | SHAFFER (PATRIOT WIND/PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2019 | 226 | 58% | 131.08 | 2019-07-27 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 567 | PEYTON CREEK WIND | 18INR0018 |  | MATAGORDA | WIND-C | COASTAL | 2019 | 151.2 | 58% | 87.696 | 2019-07-28 | 2020-06-04 | OPERATIONAL | 2019-11-14 | No | 2020-06-01 | O2 | operational by July 1st
8 | Dec 2018 CDR | 568 | RAYMOND WIND | 18INR0059 |  | WILLACY | WIND-C | COASTAL | 2019 | 201.6 | 58% | 116.928 | 2019-07-29 | N/A | PLANNED | 2020-10-06 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 569 | STELLA 1 WIND | 15INR0035 |  | KENEDY | WIND-C | COASTAL | 2018 | 201 | 58% | 116.58 | 2019-07-30 | 2018-12-19 | OPERATIONAL | 2018-10-24 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 570 | ARAGORN SOLAR | 19INR0088 |  | CULBERSON | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2019-08-09 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 571 | BLUEBELL SOLAR (CAPRICORN RIDGE SOLAR) | 16INR0019 |  | COKE | SOLAR | WEST | 2018 | 30 | 74% | 22.2 | 2019-08-10 | 2019-11-07 | OPERATIONAL | 2018-10-25 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 572 | EMERALD GROVE SOLAR (PECOS SOLAR POWER I) | 15INR0059 |  | PECOS | SOLAR | WEST | 2019 | 108 | 74% | 79.92 | 2019-08-11 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 573 | FS BARILLA SOLAR 1B [HOVEY_UNIT2] | 12INR0059b |  | PECOS | SOLAR | WEST | 2019 | 7.4 | 74% | 5.476 | 2019-08-12 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 574 | HOLSTEIN SOLAR | 19INR0009 |  | NOLAN | SOLAR | WEST | 2020 | 204 | 74% | 150.96 | 2019-08-13 | 2020-05-28 | OPERATIONAL | 2020-01-16 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 575 | LAMESA SOLAR (PHASE II) | 16INR0023b |  | DAWSON | SOLAR | WEST | 2018 | 50 | 74% | 37 | 2019-08-14 | 2018-12-19 | OPERATIONAL | 2018-10-04 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 576 | LONG DRAW SOLAR | 18INR0055 |  | BORDEN | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2019-08-15 | N/A | PLANNED | 2020-11-20 | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 577 | MISAE SOLAR | 18INR0045 |  | CHILDRESS | SOLAR | PANHANDLE | 2019 | 240.8 | 74% | 178.192 | 2019-08-16 | N/A | PLANNED | 2020-01-16 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
8 | Dec 2018 CDR | 578 | NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2020 | 201 | 74% | 148.74 | 2019-08-17 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 579 | OBERON SOLAR | 19INR0083 |  | ECTOR | SOLAR | WEST | 2019 | 180 | 74% | 133.2 | 2019-08-18 | 2020-07-13 | OPERATIONAL | 2020-04-08 | No | 2020-06-01 | O3 | operational by August 1st
8 | Dec 2018 CDR | 580 | PFLUGERVILLE SOLAR | 15INR0090 |  | TRAVIS | SOLAR | SOUTH | 2019 | 144 | 74% | 106.56 | 2019-08-19 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 581 | PHOEBE SOLAR | 19INR0029 |  | WINKLER | SOLAR | WEST | 2019 | 250 | 74% | 185 | 2019-08-20 | 2019-11-26 | OPERATIONAL | 2019-06-05 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 582 | PROSPERO SOLAR | 19INR0092 |  | ANDREWS | SOLAR | WEST | 2019 | 300 | 74% | 222 | 2019-08-21 | 2020-06-30 | OPERATIONAL | 2020-04-24 | No | 2020-06-01 | O2 | operational by July 1st
8 | Dec 2018 CDR | 583 | QUEEN SOLAR | 19INR0102 |  | UPTON | SOLAR | WEST | 2019 | 400 | 74% | 296 | 2019-08-22 | 2020-05-04 | OPERATIONAL | 2019-12-12 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 584 | RAMBLER SOLAR | 19INR0114 |  | TOM GREEN | SOLAR | WEST | 2019 | 150 | 74% | 111 | 2019-08-23 | 2020-10-01 | OPERATIONAL | 2020-04-01 | No | 2020-06-01 | O4 | operational after August 1st
8 | Dec 2018 CDR | 585 | RE MAPLEWOOD 2A SOLAR | 17INR0020a |  | PECOS | SOLAR | WEST | 2019 | 100 | 74% | 74 | 2019-08-24 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 586 | RE MAPLEWOOD 2B SOLAR | 17INR0020b |  | PECOS | SOLAR | WEST | 2019 | 100 | 74% | 74 | 2019-08-25 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 587 | RE MAPLEWOOD 2C SOLAR | 17INR0020c |  | PECOS | SOLAR | WEST | 2019 | 100 | 74% | 74 | 2019-08-26 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 588 | RE MAPLEWOOD 2D SOLAR | 17INR0020d |  | PECOS | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2019-08-27 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 589 | RE MAPLEWOOD 2E SOLAR | 17INR0020e |  | PECOS | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2019-08-28 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 590 | SODA LAKE SOLAR 1 | 18INR0040 |  | CRANE | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2019-08-29 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
8 | Dec 2018 CDR | 591 | SODA LAKE SOLAR 2 | 20INR0143 |  | CRANE | SOLAR | WEST | 2020 | 0 | 74% | 0 | 2019-08-30 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 592 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2019 | 102 | 74% | 75.48 | 2019-08-31 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
8 | Dec 2018 CDR | 593 | WAYMARK SOLAR | 16INR0115 |  | PECOS | SOLAR | WEST | 2018 | 182 | 74% | 134.68 | 2019-09-01 | 2018-12-20 | OPERATIONAL | 2018-10-17 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 594 | WEST OF PECOS SOLAR | 14INR0044 |  | REEVES | SOLAR | WEST | 2019 | 100 | 74% | 74 | 2019-09-02 | 2019-12-20 | OPERATIONAL | 2019-10-08 | Yes | 2020-06-01 | O1 | operational by June 1st
8 | Dec 2018 CDR | 595 | WINKLER SOLAR (RES WINK SOLAR) | 18INR0022 |  | WINKLER | SOLAR | WEST | 2019 | 150 | 74% | 111 | 2019-09-03 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 596 | PHR PEAKERS [BAC_CTG1-6] | 14INR0038 |  | GALVESTON | GAS | HOUSTON | 2018 | 324 | 100% | 324 | 2019-09-04 | 2018-07-11 | OPERATIONAL | 2017-03-22 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 597 | BETHEL CAES PROJECT | 15INR0013 |  | ANDERSON | GAS | NORTH | 2020 | 0 | 100% | 0 | 2019-09-05 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 598 | DENTON ENERGY CENTER | 18INR0013 |  | DENTON | GAS | NORTH | 2018 | 225.8 | 100% | 225.8 | 2019-09-06 | 2018-07-11 | OPERATIONAL | 2018-04-16 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 599 | FGE TEXAS I PROJECT | 16INR0010 |  | MITCHELL | GAS | WEST | 2020 | 0 | 100% | 0 | 2019-09-07 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 600 | FRIENDSWOOD G | 13INR0049 |  | HARRIS | GAS | HOUSTON | 2018 | 119 | 100% | 119 | 2019-09-08 | 2018-11-08 | OPERATIONAL | 2018-05-09 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 601 | HALYARD HENDERSON | 16INR0045 |  | HENDERSON | GAS | NORTH | 2020 | 432 | 100% | 432 | 2019-09-09 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 602 | HALYARD WHARTON ENERGY CENTER | 16INR0044 |  | WHARTON | GAS | SOUTH | 2019 | 419 | 100% | 419 | 2019-09-10 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
7 | May 2018 CDR | 603 | HUDSON (BRAZORIA ENERGY G) | 16INR0076 |  | BRAZORIA | GAS | COASTAL | 2019 | 90 | 100% | 90 | 2019-09-11 | 2020-07-17 | OPERATIONAL | 2019-08-16 | No | 2020-06-01 | O3 | operational by August 1st
7 | May 2018 CDR | 604 | INDECK WHARTON ENERGY CENTER | 15INR0023 |  | WHARTON | GAS | SOUTH | 2021 | 0 | 100% | 0 | 2019-09-12 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 605 | MIRAGE | 17INR0022 |  | HARRIS | GAS | HOUSTON | 2018 | 11 | 100% | 11 | 2019-09-13 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 606 | PINECREST ENERGY CENTER PROJECT | 16INR0006 |  | ANGELINA | GAS | NORTH | 2020 | 785 | 100% | 785 | 2019-09-14 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 607 | VICTORIA CITY (CITYVICT) | 18INR0035 |  | VICTORIA | GAS | SOUTH | 2018 | 100 | 100% | 100 | 2019-09-15 | 2020-02-06 | OPERATIONAL | 2019-12-17 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 608 | CABEZON WIND (RIO BRAVO I WIND) | 17INR0005 |  | STARR | WIND | SOUTH | 2019 | 237.6 | 14% | 33.264 | 2019-09-19 | 2019-12-17 | OPERATIONAL | 2019-03-14 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 609 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND | WEST | 2018 | 148.4 | 14% | 20.776 | 2019-09-20 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
7 | May 2018 CDR | 610 | CANADIAN BREAKS WIND | 13INR0026 |  | OLDHAM | WIND | PANHANDLE | 2019 | 210 | 14% | 29.4 | 2019-09-21 | 2019-12-17 | OPERATIONAL | 2019-07-18 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 611 | COMANCHE RUN WIND | 12INR0029 |  | SWISHER | WIND | PANHANDLE | 2019 | 500 | 14% | 70 | 2019-09-22 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 612 | COYOTE WIND | 17INR0027b |  | SCURRY | WIND | WEST | 2019 | 242.5 | 14% | 33.95 | 2019-09-23 | N/A | PLANNED | 2020-11-25 | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 613 | EDMONDSON RANCH WIND | 18INR0043 |  | GLASSCOCK | WIND | WEST | 2019 | 292.5 | 14% | 40.95 | 2019-09-24 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 614 | FLAT TOP WIND I | 15INR0082 |  | COMANCHE | WIND | NORTH | 2018 | 200 | 14% | 28 | 2019-09-25 | 2018-09-07 | OPERATIONAL | 2018-01-18 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 615 | FOARD CITY WIND | 19INR0019 |  | FOARD | WIND | WEST | 2019 | 350 | 14% | 49 | 2019-09-26 | 2019-12-05 | OPERATIONAL | 2019-08-20 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 616 | GOODNIGHT WIND | 14INR0033 |  | ARMSTRONG | WIND | PANHANDLE | 2019 | 496.8 | 14% | 69.552 | 2019-09-27 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
7 | May 2018 CDR | 617 | GOPHER CREEK WIND | 18INR0067 |  | SCURRY | WIND | WEST | 2019 | 158 | 14% | 22.12 | 2019-09-28 | 2020-03-09 | OPERATIONAL | 2019-05-30 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 618 | GRANDVIEW WIND 3 (CONWAY) | 13INR0005c |  | CARSON | WIND | PANHANDLE | 2019 | 187.5 | 14% | 26.25 | 2019-09-29 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 619 | HARALD (BEARKAT WIND B) | 15INR0064b |  | GLASSCOCK | WIND | WEST | 2019 | 162.1 | 14% | 22.694 | 2019-09-30 | N/A | PLANNED | 2020-05-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
7 | May 2018 CDR | 620 | HEART OF TEXAS WIND | 18INR0016 |  | MCCULLOCH | WIND | SOUTH | 2018 | 150 | 14% | 21 | 2019-10-01 | N/A | PLANNED | 2020-04-29 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
7 | May 2018 CDR | 621 | HICKMAN (SANTA RITA WIND) | 16INR0091 |  | REAGAN | WIND | WEST | 2018 | 300 | 14% | 42 | 2019-10-02 | 2018-05-09 | OPERATIONAL | 2017-12-19 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 622 | HIGH LONESOME W | 19INR0038 |  | CROCKETT | WIND | WEST | 2019 | 500 | 14% | 70 | 2019-10-03 | N/A | PLANNED | 2019-11-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
7 | May 2018 CDR | 623 | INFINITY LIVE OAK WIND | 12INR0060 |  | SCHLEICHER | WIND | WEST | 2018 | 199.5 | 14% | 27.93 | 2019-10-04 | 2020-04-17 | OPERATIONAL | 2018-11-29 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 624 | KARANKAWA 2 WIND FARM | 19INR0074 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 200 | 59% | 118 | 2019-10-05 | 2019-12-30 | OPERATIONAL | 2019-11-05 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 625 | KARANKAWA WIND ALT A | 18INR0014 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 200 | 59% | 118 | 2019-10-06 | 2019-12-30 | OPERATIONAL | 2019-11-07 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 626 | LITTLE MOUNTAIN WIND | 12INR0055 |  | BAYLOR | WIND | WEST | 2019 | 80 | 14% | 11.2 | 2019-10-07 | 2019-08-07 | OPERATIONAL | 2019-04-19 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 627 | LOCKETT WIND FARM | 16INR0062b |  | WILBARGER | WIND | WEST | 2019 | 184 | 14% | 25.76 | 2019-10-08 | 2019-09-19 | OPERATIONAL | 2019-05-31 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 628 | LOMA PINTA WIND | 16INR0112 |  | LA SALLE | WIND | SOUTH | 2018 | 200 | 14% | 28 | 2019-10-09 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
7 | May 2018 CDR | 629 | LONGHORN SOUTH | 20INR0058 |  | BRISCOE | WIND | PANHANDLE | 2020 | 0 | 14% | 0 | 2019-10-10 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 630 | LORAINE WINDPARK PHASE III | 18INR0068 |  | MITCHELL | WIND | WEST | 2018 | 100 | 14% | 14 | 2019-10-11 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 631 | MARIAH DEL ESTE | 13INR0010a |  | PARMER | WIND | PANHANDLE | 2018 | 152.5 | 14% | 21.35 | 2019-10-12 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
7 | May 2018 CDR | 632 | MARIAH DEL SUR | 13INR0010c |  | PARMER | WIND | PANHANDLE | 2018 | 217.5 | 14% | 30.45 | 2019-10-13 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 633 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2018 | 162.9 | 59% | 96.111 | 2019-10-14 | 2019-08-15 | OPERATIONAL | 2018-12-04 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 634 | PALMAS ALTAS WIND | 17INR0037 |  | CAMERON | WIND-C | COASTAL | 2019 | 144.9 | 59% | 85.491 | 2019-10-15 | 2020-11-12 | OPERATIONAL | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
7 | May 2018 CDR | 635 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND | PANHANDLE | 2020 | 0 | 14% | 0 | 2019-10-16 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
7 | May 2018 CDR | 636 | PATRIOT WIND (PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2019 | 239 | 59% | 141.01 | 2019-10-17 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
7 | May 2018 CDR | 637 | PEYTON CREEK WIND | 18INR0018 |  | MATAGORDA | WIND-C | COASTAL | 2020 | 0 | 59% | 0 | 2019-10-18 | 2020-06-04 | OPERATIONAL | 2019-11-14 | No | 2020-06-01 | O2 | operational by July 1st
7 | May 2018 CDR | 638 | PULLMAN ROAD WIND | 15INR0079 |  | RANDALL | WIND | PANHANDLE | 2019 | 300 | 14% | 42 | 2019-10-19 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 639 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND | PANHANDLE | 2019 | 280.9 | 14% | 39.326 | 2019-10-20 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 640 | RTS WIND | 16INR0087 |  | MCCULLOCH | WIND | SOUTH | 2018 | 160 | 14% | 22.4 | 2019-10-21 | 2018-09-07 | OPERATIONAL | 2018-03-08 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 641 | SAGE DRAW WIND | 19INR0163 |  | LYNN | WIND | WEST | 2019 | 300 | 14% | 42 | 2019-10-22 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
7 | May 2018 CDR | 642 | SCANDIA WIND DEF | 13INR0010def |  | PARMER | WIND | PANHANDLE | 2019 | 600.3 | 14% | 84.042 | 2019-10-23 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 643 | SILVER CANYON WIND A | 12INR0002a |  | BRISCOE | WIND | PANHANDLE | 2019 | 200 | 14% | 28 | 2019-10-24 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 644 | STELLA 1 WIND | 15INR0035 |  | KENEDY | WIND-C | COASTAL | 2018 | 201 | 59% | 118.59 | 2019-10-25 | 2018-12-19 | OPERATIONAL | 2018-10-24 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 645 | TAHOKA WIND (STAKED PLAINS WIND 1) | 18INR0025 |  | LYNN | WIND | WEST | 2018 | 300 | 14% | 42 | 2019-10-26 | 2019-03-01 | OPERATIONAL | 2018-11-09 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 646 | TORRECILLAS WIND | 14INR0045 |  | WEBB | WIND | SOUTH | 2018 | 300.5 | 14% | 42.07 | 2019-10-27 | 2019-11-07 | OPERATIONAL | 2019-02-26 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 647 | UNITY WIND | 15INR0050 |  | DEAF SMITH | WIND | PANHANDLE | 2019 | 203 | 14% | 28.42 | 2019-10-28 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 648 | WILDROSE WIND (SWISHER WIND) | 13INR0038 |  | SWISHER | WIND | PANHANDLE | 2019 | 211.9 | 14% | 29.666 | 2019-10-29 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
7 | May 2018 CDR | 649 | WKN AMADEUS WIND | 14INR0009 |  | KENT | WIND | WEST | 2019 | 245.9 | 14% | 34.426 | 2019-10-30 | N/A | PLANNED | 2020-10-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
7 | May 2018 CDR | 650 | BLUEBELL SOLAR (CAPRICORN RIDGE SOLAR) | 16INR0019 |  | COKE | SOLAR | WEST | 2018 | 30 | 75% | 22.5 | 2019-11-09 | 2019-11-07 | OPERATIONAL | 2018-10-25 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 651 | CASTLE GAP SOLAR | 16INR0065 |  | UPTON | SOLAR | WEST | 2018 | 180 | 75% | 135 | 2019-11-10 | 2018-05-31 | OPERATIONAL | 2018-03-16 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 652 | FS BARILLA SOLAR 1B [HOVEY_UNIT2] | 12INR0059b |  | PECOS | SOLAR | WEST | 2018 | 7.4 | 75% | 5.55 | 2019-11-11 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 653 | LAMESA SOLAR (PHASE II) | 16INR0023b |  | DAWSON | SOLAR | WEST | 2018 | 50 | 75% | 37.5 | 2019-11-12 | 2018-12-19 | OPERATIONAL | 2018-10-04 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 654 | NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2019 | 201 | 75% | 150.75 | 2019-11-13 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 655 | PECOS SOLAR POWER I | 15INR0059 |  | PECOS | SOLAR | WEST | 2019 | 108 | 75% | 81 | 2019-11-14 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 656 | PFLUGERVILLE SOLAR | 15INR0090 |  | TRAVIS | SOLAR | SOUTH | 2019 | 144 | 75% | 108 | 2019-11-15 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 657 | PROSPERO SOLAR | 19INR0092 |  | ANDREWS | SOLAR | WEST | 2019 | 300 | 75% | 225 | 2019-11-16 | 2020-06-30 | OPERATIONAL | 2020-04-24 | No | 2020-06-01 | O2 | operational by July 1st
7 | May 2018 CDR | 658 | RES WINK SOLAR | 18INR0022 |  | WINKLER | SOLAR | WEST | 2019 | 150 | 75% | 112.5 | 2019-11-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 659 | RE MAPLEWOOD 2A SOLAR | 17INR0020a |  | PECOS | SOLAR | WEST | 2019 | 100 | 75% | 75 | 2019-11-18 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 660 | RE MAPLEWOOD 2B SOLAR | 17INR0020b |  | PECOS | SOLAR | WEST | 2019 | 100 | 75% | 75 | 2019-11-19 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 661 | RE MAPLEWOOD 2C SOLAR | 17INR0020c |  | PECOS | SOLAR | WEST | 2019 | 100 | 75% | 75 | 2019-11-20 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 662 | RE MAPLEWOOD 2D SOLAR | 17INR0020d |  | PECOS | SOLAR | WEST | 2020 | 0 | 75% | 0 | 2019-11-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 663 | RE MAPLEWOOD 2E SOLAR | 17INR0020e |  | PECOS | SOLAR | WEST | 2020 | 0 | 75% | 0 | 2019-11-22 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
7 | May 2018 CDR | 664 | RIGGINS (SE BUCKTHORN WESTEX SOLAR) | 15INR0045 |  | PECOS | SOLAR | WEST | 2018 | 150 | 75% | 112.5 | 2019-11-23 | 2018-06-15 | OPERATIONAL | 2018-04-02 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 665 | SOLAIREHOLMAN 1 | 15INR0061 |  | BREWSTER | SOLAR | WEST | 2018 | 50 | 75% | 37.5 | 2019-11-24 | 2018-05-24 | OPERATIONAL | 2017-03-30 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 666 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2019 | 102 | 75% | 76.5 | 2019-11-25 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
7 | May 2018 CDR | 667 | WAYMARK SOLAR | 16INR0115 |  | PECOS | SOLAR | WEST | 2018 | 182 | 75% | 136.5 | 2019-11-26 | 2018-12-20 | OPERATIONAL | 2018-10-17 | Yes | 2020-06-01 | O1 | operational by June 1st
7 | May 2018 CDR | 668 | WEST OF PECOS SOLAR | 14INR0044 |  | REEVES | SOLAR | WEST | 2019 | 100 | 75% | 75 | 2019-11-27 | 2019-12-20 | OPERATIONAL | 2019-10-08 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 669 | DENTON ENERGY CENTER | 18INR0013 |  | DENTON | GAS | NORTH | 2018 | 225.8 | 100% | 225.8 | 2019-11-28 | 2018-07-11 | OPERATIONAL | 2018-04-16 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 670 | FGE TEXAS I PROJECT | 16INR0010 |  | MITCHELL | GAS | WEST | 2019 | 720 | 100% | 720 | 2019-11-29 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 671 | PHR PEAKERS [BAC_CTG1-6] | 14INR0038 |  | GALVESTON | GAS | HOUSTON | 2017 | 324 | 100% | 324 | 2019-11-30 | 2018-07-11 | OPERATIONAL | 2017-03-22 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 672 | INDECK WHARTON ENERGY CENTER | 15INR0023 |  | WHARTON | GAS | SOUTH | 2019 | 654 | 100% | 654 | 2019-12-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 673 | PINECREST ENERGY CENTER PROJECT | 16INR0006 |  | ANGELINA | GAS | NORTH | 2020 | 785 | 100% | 785 | 2019-12-02 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 674 | FRIENDSWOOD G | 13INR0049 |  | HARRIS | GAS | HOUSTON | 2017 | 119 | 100% | 119 | 2019-12-03 | 2018-11-08 | OPERATIONAL | 2018-05-09 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 675 | BETHEL CAES PROJECT | 15INR0013 |  | ANDERSON | GAS | NORTH | 2020 | 0 | 100% | 0 | 2019-12-04 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 676 | HALYARD HENDERSON | 16INR0045 |  | HENDERSON | GAS | NORTH | 2019 | 450 | 100% | 450 | 2019-12-05 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 677 | HALYARD WHARTON ENERGY CENTER | 16INR0044 |  | WHARTON | GAS | SOUTH | 2019 | 419 | 100% | 419 | 2019-12-06 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
6 | Dec 2017 CDR | 678 | MIRAGE | 17INR0022 |  | HARRIS | GAS | HOUSTON | 2018 | 11 | 100% | 11 | 2019-12-07 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 679 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2019 | 162.9 | 59% | 96.111 | 2019-12-11 | 2019-08-15 | OPERATIONAL | 2018-12-04 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 680 | LONGHORN WIND SOUTH | 14INR0023b |  | BRISCOE | WIND | PANHANDLE | 2018 | 160 | 14% | 22.4 | 2019-12-12 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 681 | MARIAH DEL ESTE | 13INR0010a |  | PARMER | WIND | PANHANDLE | 2018 | 152.5 | 14% | 21.35 | 2019-12-13 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
6 | Dec 2017 CDR | 682 | MARIAH DEL SUR | 13INR0010c |  | PARMER | WIND | PANHANDLE | 2018 | 217.5 | 14% | 30.45 | 2019-12-14 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 683 | PATRIOT WIND (PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2019 | 180 | 59% | 106.2 | 2019-12-15 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
6 | Dec 2017 CDR | 684 | COMANCHE RUN WIND | 12INR0029 |  | SWISHER | WIND | PANHANDLE | 2019 | 500 | 14% | 70 | 2019-12-16 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 685 | GRANDVIEW WIND 3 (CONWAY) | 13INR0005c |  | CARSON | WIND | PANHANDLE | 2019 | 187.5 | 14% | 26.25 | 2019-12-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 686 | SCANDIA WIND DEF | 13INR0010def |  | PARMER | WIND | PANHANDLE | 2019 | 600.3 | 14% | 84.042 | 2019-12-18 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 687 | PULLMAN ROAD WIND | 15INR0079 |  | RANDALL | WIND | PANHANDLE | 2019 | 300 | 14% | 42 | 2019-12-19 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 688 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND | PANHANDLE | 2018 | 248 | 14% | 34.72 | 2019-12-20 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
6 | Dec 2017 CDR | 689 | UNITY WIND | 15INR0050 |  | DEAF SMITH | WIND | PANHANDLE | 2019 | 203 | 14% | 28.42 | 2019-12-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 690 | TORRECILLAS WIND A | 14INR0045a |  | WEBB | WIND | SOUTH | 2019 | 200 | 14% | 28 | 2019-12-22 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 691 | TORRECILLAS WIND B | 14INR0045b |  | WEBB | WIND | SOUTH | 2019 | 200 | 14% | 28 | 2019-12-23 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 692 | LOCKETT WIND FARM | 16INR0062b |  | WILBARGER | WIND | WEST | 2019 | 184 | 14% | 25.76 | 2019-12-24 | 2019-09-19 | OPERATIONAL | 2019-05-31 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 693 | WILLOW SPRINGS WIND | 14INR0060b |  | HASKELL | WIND | WEST | 2017 | 230 | 14% | 32.2 | 2019-12-25 | 2017-12-29 | OPERATIONAL | 2017-10-18 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 694 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND | PANHANDLE | 2018 | 280.9 | 14% | 39.326 | 2019-12-26 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 695 | BRUENNING'S BREEZE | 14INR0041a |  | WILLACY | WIND-C | COASTAL | 2017 | 228 | 59% | 134.52 | 2019-12-27 | 2017-12-21 | OPERATIONAL | 2017-10-30 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 696 | SANTA RITA WIND | 16INR0091 |  | REAGAN | WIND | WEST | 2017 | 300 | 14% | 42 | 2019-12-28 | 2018-05-09 | OPERATIONAL | 2017-12-19 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 697 | SWISHER WIND | 13INR0038 |  | SWISHER | WIND | PANHANDLE | 2019 | 211.9 | 14% | 29.666 | 2019-12-29 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
6 | Dec 2017 CDR | 698 | RTS WIND | 16INR0087 |  | MCCULLOCH | WIND | SOUTH | 2018 | 160 | 14% | 22.4 | 2019-12-30 | 2018-09-07 | OPERATIONAL | 2018-03-08 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 699 | SILVER CANYON WIND A | 12INR0002a |  | BRISCOE | WIND | PANHANDLE | 2019 | 200 | 14% | 28 | 2019-12-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 700 | FLAT TOP WIND I | 15INR0082 |  | COMANCHE | WIND | NORTH | 2018 | 200 | 14% | 28 | 2020-01-01 | 2018-09-07 | OPERATIONAL | 2018-01-18 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 701 | CANADIAN BREAKS WIND | 13INR0026 |  | OLDHAM | WIND | PANHANDLE | 2019 | 210 | 14% | 29.4 | 2020-01-02 | 2019-12-17 | OPERATIONAL | 2019-07-18 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 702 | SALT FORK WIND EXPANSION | 16INR0121 |  | CARSON | WIND | PANHANDLE | 2018 | 54 | 14% | 7.56 | 2020-01-03 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 703 | CHOCOLATE BAYOU | 16INR0074 |  | BRAZORIA | WIND-C | COASTAL | 2019 | 150 | 59% | 88.5 | 2020-01-04 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
6 | Dec 2017 CDR | 704 | GOODNIGHT WIND | 14INR0033 |  | ARMSTRONG | WIND | PANHANDLE | 2018 | 496.8 | 14% | 69.552 | 2020-01-05 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
6 | Dec 2017 CDR | 705 | COYOTE WIND | 17INR0027b |  | SCURRY | WIND | WEST | 2019 | 242.5 | 14% | 33.95 | 2020-01-06 | N/A | PLANNED | 2020-11-25 | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 706 | BEARKAT WIND A | 15INR0064 |  | GLASSCOCK | WIND | WEST | 2017 | 197 | 14% | 27.58 | 2020-01-07 | 2018-02-14 | OPERATIONAL | 2017-12-15 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 707 | BEARKAT WIND B | 15INR0064b |  | GLASSCOCK | WIND | WEST | 2018 | 162.1 | 14% | 22.694 | 2020-01-08 | N/A | PLANNED | 2020-05-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
6 | Dec 2017 CDR | 708 | INFINITY LIVE OAK WIND | 12INR0060 |  | SCHLEICHER | WIND | WEST | 2019 | 199.5 | 14% | 27.93 | 2020-01-09 | 2020-04-17 | OPERATIONAL | 2018-11-29 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 709 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND | WEST | 2018 | 150 | 14% | 21 | 2020-01-10 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
6 | Dec 2017 CDR | 710 | STAKED PLAINS WIND 1 | 18INR0025 |  | LYNN | WIND | WEST | 2018 | 505 | 14% | 70.7 | 2020-01-11 | 2019-03-01 | OPERATIONAL | 2018-11-09 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 711 | STELLA 1 WIND | 15INR0035 |  | KENEDY | WIND-C | COASTAL | 2018 | 201 | 59% | 118.59 | 2020-01-12 | 2018-12-19 | OPERATIONAL | 2018-10-24 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 712 | RIO BRAVO I WIND | 17INR0005 |  | STARR | WIND | SOUTH | 2018 | 237.6 | 14% | 33.264 | 2020-01-13 | 2019-12-17 | OPERATIONAL | 2019-03-14 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 713 | EDMONDSON RANCH WIND | 18INR0043 |  | GLASSCOCK | WIND | WEST | 2019 | 292.5 | 14% | 40.95 | 2020-01-14 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 714 | HEART OF TEXAS WIND | 18INR0016 |  | MCCULLOCH | WIND | SOUTH | 2018 | 150 | 14% | 21 | 2020-01-15 | N/A | PLANNED | 2020-04-29 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
6 | Dec 2017 CDR | 715 | FS BARILLA SOLAR 1B [HOVEY_UNIT2] | 12INR0059b |  | PECOS | SOLAR | WEST | 2017 | 7.4 | 75% | 5.55 | 2020-01-25 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 716 | SE BUCKTHORN WESTEX SOLAR (RIGGINS SOLAR) | 15INR0045 |  | PECOS | SOLAR | WEST | 2018 | 150 | 75% | 112.5 | 2020-01-26 | 2018-06-15 | OPERATIONAL | 2018-04-02 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 717 | NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2019 | 201 | 75% | 150.75 | 2020-01-27 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 718 | PECOS SOLAR POWER I | 15INR0059 |  | PECOS | SOLAR | WEST | 2019 | 108 | 75% | 81 | 2020-01-28 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 719 | BNB LAMESA SOLAR (PHASE I) | 16INR0023 |  | DAWSON | SOLAR | WEST | 2017 | 101.6 | 75% | 76.2 | 2020-01-29 | 2018-02-21 | OPERATIONAL | 2017-02-14 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 720 | LAMESA SOLAR (PHASE II) | 16INR0023b |  | DAWSON | SOLAR | WEST | 2018 | 50 | 75% | 37.5 | 2020-01-30 | 2018-12-19 | OPERATIONAL | 2018-10-04 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 721 | CAPRICORN RIDGE SOLAR | 16INR0019 |  | COKE | SOLAR | WEST | 2018 | 100 | 75% | 75 | 2020-01-31 | 2019-11-07 | OPERATIONAL | 2018-10-25 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 722 | CASTLE GAP SOLAR | 16INR0065 |  | UPTON | SOLAR | WEST | 2018 | 180 | 75% | 135 | 2020-02-01 | 2018-05-31 | OPERATIONAL | 2018-03-16 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 723 | SOLAIREHOLMAN 1 | 15INR0061 |  | BREWSTER | SOLAR | WEST | 2018 | 50 | 75% | 37.5 | 2020-02-02 | 2018-05-24 | OPERATIONAL | 2017-03-30 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 724 | RE MAPLEWOOD 2A SOLAR | 17INR0020a |  | PECOS | SOLAR | WEST | 2018 | 100 | 75% | 75 | 2020-02-03 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 725 | RE MAPLEWOOD 2B SOLAR | 17INR0020b |  | PECOS | SOLAR | WEST | 2019 | 100 | 75% | 75 | 2020-02-04 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 726 | RE MAPLEWOOD 2C SOLAR | 17INR0020c |  | PECOS | SOLAR | WEST | 2019 | 100 | 75% | 75 | 2020-02-05 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 727 | RE MAPLEWOOD 2D SOLAR | 17INR0020d |  | PECOS | SOLAR | WEST | 2020 | 0 | 75% | 0 | 2020-02-06 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 728 | RE MAPLEWOOD 2E SOLAR | 17INR0020e |  | PECOS | SOLAR | WEST | 2020 | 0 | 75% | 0 | 2020-02-07 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
6 | Dec 2017 CDR | 729 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2018 | 102 | 75% | 76.5 | 2020-02-08 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 730 | WEST OF PECOS SOLAR | 14INR0044 |  | REEVES | SOLAR | WEST | 2018 | 100 | 75% | 75 | 2020-02-09 | 2019-12-20 | OPERATIONAL | 2019-10-08 | Yes | 2020-06-01 | O1 | operational by June 1st
6 | Dec 2017 CDR | 731 | PFLUGERVILLE SOLAR | 15INR0090 |  | TRAVIS | SOLAR | SOUTH | 2018 | 120 | 75% | 90 | 2020-02-10 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
6 | Dec 2017 CDR | 732 | WAYMARK SOLAR | 16INR0115 |  | PECOS | SOLAR | WEST | 2018 | 182 | 75% | 136.5 | 2020-02-11 | 2018-12-20 | OPERATIONAL | 2018-10-17 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 733 | BLUE SUMMIT BATTERY | 16INR0122 |  | WILBARGER | STORAGE | WEST | 2017 | 0 | 0% | 0 | 2020-02-12 | 2017-08-11 | OPERATIONAL | 2017-06-23 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 734 | COLORADO BEND II | 17INR0007 |  | WHARTON | GAS | SOUTH | 2017 | 1088 | 100% | 1088 | 2020-02-13 | 2017-06-23 | OPERATIONAL | 2017-02-10 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 735 | TEXAS CLEAN ENERGY PROJECT | 13INR0023 |  | ECTOR | COAL | WEST | 2019 | 240 | 100% | 240 | 2020-02-14 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 736 | FGE TEXAS I PROJECT | 16INR0010 |  | MITCHELL | GAS | WEST | 2019 | 720 | 100% | 720 | 2020-02-15 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 737 | PHR PEAKERS [BAC_CTG1-6] | 14INR0038 |  | GALVESTON | GAS | HOUSTON | 2017 | 324 | 100% | 324 | 2020-02-16 | 2018-07-11 | OPERATIONAL | 2017-03-22 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 738 | INDECK WHARTON ENERGY CENTER | 15INR0023 |  | WHARTON | GAS | SOUTH | 2019 | 654 | 100% | 654 | 2020-02-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 739 | PINECREST ENERGY CENTER PROJECT | 16INR0006 |  | ANGELINA | GAS | NORTH | 2020 | 785 | 100% | 785 | 2020-02-18 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 740 | WOLF HOLLOW 2 | 17INR0009 |  | HOOD | GAS | NORTH | 2017 | 1069 | 100% | 1069 | 2020-02-19 | 2017-05-02 | OPERATIONAL | 2017-01-05 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 741 | FRIENDSWOOD G | 13INR0049 |  | HARRIS | GAS | HOUSTON | 2017 | 119 | 100% | 119 | 2020-02-20 | 2018-11-08 | OPERATIONAL | 2018-05-09 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 742 | BETHEL CAES PROJECT | 15INR0013 |  | ANDERSON | GAS | NORTH | 2020 | 0 | 100% | 0 | 2020-02-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 743 | HALYARD HENDERSON | 16INR0045 |  | HENDERSON | GAS | NORTH | 2018 | 450 | 100% | 450 | 2020-02-22 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 744 | HALYARD WHARTON ENERGY CENTER | 16INR0044 |  | WHARTON | GAS | SOUTH | 2018 | 419 | 100% | 419 | 2020-02-23 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
5 | May 2017 CDR | 745 | CASTLEMAN CHAMON | 17INR0042 |  | HARRIS | GAS | HOUSTON | 2017 | 88 | 100% | 88 | 2020-02-24 | 2017-10-24 | OPERATIONAL | 2017-09-28 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 746 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2017 | 161 | 58% | 93.38 | 2020-02-28 | 2019-08-15 | OPERATIONAL | 2018-12-04 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 747 | LONGHORN WIND SOUTH | 14INR0023b |  | BRISCOE | WIND | PANHANDLE | 2017 | 160 | 14% | 22.4 | 2020-02-29 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 748 | MARIAH WIND A | 13INR0010a |  | PARMER | WIND | PANHANDLE | 2018 | 139.2 | 14% | 19.488 | 2020-03-01 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
5 | May 2017 CDR | 749 | MARIAH DEL SUR | 13INR0010c |  | PARMER | WIND | PANHANDLE | 2018 | 230.4 | 14% | 32.256 | 2020-03-02 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 750 | RATTLESNAKE DEN WIND 2 | 13INR0020b |  | GLASSCOCK | WIND | WEST | 2020 | 158 | 14% | 22.12 | 2020-03-03 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 751 | PATRIOT WIND (PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2018 | 180 | 58% | 104.4 | 2020-03-04 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
5 | May 2017 CDR | 752 | COMANCHE RUN WIND | 12INR0029 |  | SWISHER | WIND | PANHANDLE | 2018 | 500 | 14% | 70 | 2020-03-05 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 753 | PAMPA WIND | 12INR0018 |  | GRAY | WIND | PANHANDLE | 2018 | 500 | 14% | 70 | 2020-03-06 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 754 | GRANDVIEW WIND 3 (CONWAY) | 13INR0005c |  | CARSON | WIND | PANHANDLE | 2017 | 187.5 | 14% | 26.25 | 2020-03-07 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 755 | SCANDIA WIND DEF | 13INR0010def |  | PARMER | WIND | PANHANDLE | 2018 | 600.3 | 14% | 84.042 | 2020-03-08 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 756 | PULLMAN ROAD WIND | 15INR0079 |  | RANDALL | WIND | PANHANDLE | 2018 | 300 | 14% | 42 | 2020-03-09 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 757 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND | PANHANDLE | 2017 | 248 | 14% | 34.72 | 2020-03-10 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
5 | May 2017 CDR | 758 | SALT FORK WIND | 14INR0062 |  | GRAY | WIND | PANHANDLE | 2017 | 174 | 14% | 24.36 | 2020-03-11 | 2017-06-13 | OPERATIONAL | 2016-11-07 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 759 | PALO DURO WIND | 15INR0050 |  | DEAF SMITH | WIND | PANHANDLE | 2018 | 203 | 14% | 28.42 | 2020-03-12 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 760 | CAPROCK WIND | 10INR0009 |  | CASTRO | WIND | PANHANDLE | 2018 | 300 | 14% | 42 | 2020-03-13 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 761 | TORRECILLAS WIND A | 14INR0045a |  | WEBB | WIND | SOUTH | 2017 | 200 | 14% | 28 | 2020-03-14 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 762 | TORRECILLAS WIND B | 14INR0045b |  | WEBB | WIND | SOUTH | 2017 | 200 | 14% | 28 | 2020-03-15 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 763 | CHANGING WINDS | 13INR0045 |  | CASTRO | WIND | PANHANDLE | 2018 | 288 | 14% | 40.32 | 2020-03-16 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 764 | LOCKETT WIND FARM | 16INR0062b |  | WILBARGER | WIND | WEST | 2017 | 184 | 14% | 25.76 | 2020-03-17 | 2019-09-19 | OPERATIONAL | 2019-05-31 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 765 | WILLOW SPRINGS WIND | 14INR0060b |  | HASKELL | WIND | WEST | 2017 | 230 | 14% | 32.2 | 2020-03-18 | 2017-12-29 | OPERATIONAL | 2017-10-18 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 766 | FALVEZ ASTRA W | 15INR0074 |  | DEAF SMITH | WIND | PANHANDLE | 2017 | 163.2 | 14% | 22.848 | 2020-03-19 | 2017-05-24 | OPERATIONAL | 2017-03-01 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 767 | CHAPMAN RANCH WIND I | 16INR0055 |  | NUECES | WIND-C | COASTAL | 2017 | 250 | 58% | 145 | 2020-03-20 | 2017-10-27 | OPERATIONAL | 2017-07-11 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 768 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND | PANHANDLE | 2019 | 280.9 | 14% | 39.326 | 2020-03-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 769 | ROCK SPRINGS VAL VERDE WIND | 11INR0082a |  | VAL VERDE | WIND | WEST | 2017 | 149.3 | 14% | 20.902 | 2020-03-22 | 2017-10-26 | OPERATIONAL | 2017-06-20 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 770 | MAGIC VALLEY WIND II (REDFISH 2A and 2B) | 14INR0041a |  | WILLACY | WIND-C | COASTAL | 2017 | 228 | 58% | 132.24 | 2020-03-23 | 2017-12-21 | OPERATIONAL | 2017-10-30 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 771 | SANTA RITA WIND | 16INR0091 |  | REAGAN | WIND | WEST | 2017 | 300 | 14% | 42 | 2020-03-24 | 2018-05-09 | OPERATIONAL | 2017-12-19 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 772 | SWISHER WIND | 13INR0038 |  | SWISHER | WIND | PANHANDLE | 2017 | 300 | 14% | 42 | 2020-03-25 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
5 | May 2017 CDR | 773 | BUCKTHORN WIND 1 | 14INR0057 |  | ERATH | WIND | NORTH | 2017 | 100.7 | 14% | 14.098 | 2020-03-26 | 2017-12-12 | OPERATIONAL | 2017-08-01 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 774 | FLUVANNA RENEWABLE 1 | 13INR0056 |  | SCURRY | WIND | WEST | 2017 | 155.4 | 14% | 21.756 | 2020-03-27 | 2017-11-20 | OPERATIONAL | 2017-07-28 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 775 | RTS WIND | 16INR0087 |  | MCCULLOCH | WIND | SOUTH | 2018 | 160 | 14% | 22.4 | 2020-03-28 | 2018-09-07 | OPERATIONAL | 2018-03-08 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 776 | SILVER CANYON WIND A | 12INR0002a |  | BRISCOE | WIND | PANHANDLE | 2017 | 200 | 14% | 28 | 2020-03-29 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 777 | LOGAN'S GAP WIND II | 15INR0082 |  | COMANCHE | WIND | NORTH | 2017 | 200 | 14% | 28 | 2020-03-30 | 2018-09-07 | OPERATIONAL | 2018-01-18 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 778 | CANADIAN BREAKS WIND | 13INR0026 |  | OLDHAM | WIND | PANHANDLE | 2018 | 201 | 14% | 28.14 | 2020-03-31 | 2019-12-17 | OPERATIONAL | 2019-07-18 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 779 | SALT FORK WIND EXPANSION | 16INR0121 |  | CARSON | WIND | PANHANDLE | 2017 | 24 | 14% | 3.36 | 2020-04-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 780 | CHOCOLATE BAYOU | 16INR0074 |  | BRAZORIA | WIND-C | COASTAL | 2018 | 150 | 58% | 87 | 2020-04-02 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
5 | May 2017 CDR | 781 | GOODNIGHT WIND | 14INR0033 |  | ARMSTRONG | WIND | PANHANDLE | 2018 | 500 | 14% | 70 | 2020-04-03 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
5 | May 2017 CDR | 782 | DERMOTT WIND 1 | 17INR0027 |  | SCURRY | WIND | WEST | 2017 | 253 | 14% | 35.42 | 2020-04-04 | 2017-08-01 | OPERATIONAL | 2017-06-09 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 783 | COYOTE WIND | 17INR0027b |  | SCURRY | WIND | WEST | 2018 | 250 | 14% | 35 | 2020-04-05 | N/A | PLANNED | 2020-11-25 | No | 2020-06-01 | P2 | COD delays without part 2 approval
5 | May 2017 CDR | 784 | BEARKAT WIND A | 15INR0064 |  | GLASSCOCK | WIND | WEST | 2017 | 197 | 14% | 27.58 | 2020-04-06 | 2018-02-14 | OPERATIONAL | 2017-12-15 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 785 | BEARKAT WIND B | 15INR0064b |  | GLASSCOCK | WIND | WEST | 2018 | 163 | 14% | 22.82 | 2020-04-07 | N/A | PLANNED | 2020-05-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
5 | May 2017 CDR | 786 | INFINITY LIVE OAK WIND | 12INR0060 |  | SCHLEICHER | WIND | WEST | 2017 | 200.6 | 14% | 28.084 | 2020-04-08 | 2020-04-17 | OPERATIONAL | 2018-11-29 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 787 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND | WEST | 2018 | 150 | 14% | 21 | 2020-04-09 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
5 | May 2017 CDR | 788 | FS BARILLA SOLAR 1B [HOVEY_UNIT2] | 12INR0059b |  | PECOS | SOLAR | WEST | 2017 | 7.4 | 77% | 5.698 | 2020-04-19 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
5 | May 2017 CDR | 789 | OCI ALAMO 6 (SIRIUS, WEST TEXAS PHASE II) | 15INR0070_1b |  | PECOS | SOLAR | WEST | 2017 | 49 | 77% | 37.73 | 2020-04-20 | 2017-10-05 | OPERATIONAL | 2017-08-24 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 790 | SE BUCKTHORN WESTEX SOLAR (RIGGINS SOLAR) | 15INR0045 |  | PECOS | SOLAR | WEST | 2017 | 150 | 77% | 115.5 | 2020-04-21 | 2018-06-15 | OPERATIONAL | 2018-04-02 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 791 | LC NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2017 | 201 | 77% | 154.77 | 2020-04-22 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
5 | May 2017 CDR | 792 | PECOS SOLAR POWER I | 15INR0059 |  | PECOS | SOLAR | WEST | 2019 | 108 | 77% | 83.16 | 2020-04-23 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
5 | May 2017 CDR | 793 | BNB LAMESA SOLAR | 16INR0023 |  | DAWSON | SOLAR | WEST | 2017 | 101.6 | 77% | 78.232 | 2020-04-24 | 2018-02-21 | OPERATIONAL | 2017-02-14 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 794 | BNB LAMESA SOLAR B | 16INR0023b |  | DAWSON | SOLAR | WEST | 2018 | 97.5 | 77% | 75.075 | 2020-04-25 | 2018-12-19 | OPERATIONAL | 2018-10-04 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 795 | CAPRICORN RIDGE SOLAR | 16INR0019 |  | COKE | SOLAR | WEST | 2017 | 100 | 77% | 77 | 2020-04-26 | 2019-11-07 | OPERATIONAL | 2018-10-25 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 796 | UPCO POWER 1 (SP-TX-12) | 16INR0065 |  | UPTON | SOLAR | WEST | 2019 | 117 | 77% | 90.09 | 2020-04-27 | 2018-05-31 | OPERATIONAL | 2018-03-16 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 797 | CASTLE GAP SOLAR 2 | 16INR0065a |  | UPTON | SOLAR | WEST | 2020 | 30 | 77% | 23.1 | 2020-04-28 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 798 | SP-TX-12-PHASE B | 16INR0065b |  | UPTON | SOLAR | WEST | 2017 | 120 | 77% | 92.4 | 2020-04-29 | 2017-08-25 | OPERATIONAL | 2017-06-30 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 799 | SOLAIREHOLMAN 1 | 15INR0061 |  | BREWSTER | SOLAR | WEST | 2017 | 50 | 77% | 38.5 | 2020-04-30 | 2018-05-24 | OPERATIONAL | 2017-03-30 | Yes | 2020-06-01 | O1 | operational by June 1st
5 | May 2017 CDR | 800 | RE MAPLEWOOD 2A SOLAR | 17INR0020a |  | PECOS | SOLAR | WEST | 2018 | 100 | 77% | 77 | 2020-05-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
5 | May 2017 CDR | 801 | RE MAPLEWOOD 2B SOLAR | 17INR0020b |  | PECOS | SOLAR | WEST | 2019 | 100 | 77% | 77 | 2020-05-02 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
5 | May 2017 CDR | 802 | RE MAPLEWOOD 2C SOLAR | 17INR0020c |  | PECOS | SOLAR | WEST | 2019 | 100 | 77% | 77 | 2020-05-03 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 803 | RE MAPLEWOOD 2D SOLAR | 17INR0020d |  | PECOS | SOLAR | WEST | 2020 | 0 | 77% | 0 | 2020-05-04 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 804 | RE MAPLEWOOD 2E SOLAR | 17INR0020e |  | PECOS | SOLAR | WEST | 2020 | 0 | 77% | 0 | 2020-05-05 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
5 | May 2017 CDR | 805 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2018 | 102 | 77% | 78.54 | 2020-05-06 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
5 | May 2017 CDR | 806 | WEST OF PECOS SOLAR | 14INR0044 |  | REEVES | SOLAR | WEST | 2017 | 100 | 77% | 77 | 2020-05-07 | 2019-12-20 | OPERATIONAL | 2019-10-08 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 807 | COLORADO BEND II | 17INR0007 |  | WHARTON | GAS | SOUTH | 2017 | 1088 | 100% | 1088 | 2020-05-08 | 2017-06-23 | OPERATIONAL | 2017-02-10 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 808 | TEXAS CLEAN ENERGY PROJECT | 13INR0023 |  | ECTOR | COAL | WEST | 2019 | 240 | 100% | 240 | 2020-05-09 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 809 | FGE TEXAS I PROJECT | 16INR0010 |  | MITCHELL | GAS | WEST | 2019 | 720 | 100% | 720 | 2020-05-10 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 810 | LA PALOMA ENERGY CENTER PROJECT | 16INR0004 |  | CAMERON | GAS | COASTAL | 2019 | 730 | 100% | 730 | 2020-05-11 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 811 | INDECK WHARTON ENERGY CENTER | 15INR0023 |  | WHARTON | GAS | SOUTH | 2019 | 654 | 100% | 654 | 2020-05-12 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 812 | PHR PEAKERS [BACLIFF] | 14INR0038 |  | GALVESTON | GAS | HOUSTON | 2016 | 388 | 100% | 388 | 2020-05-13 | 2018-07-11 | OPERATIONAL | 2017-03-22 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 813 | PINECREST ENERGY CENTER PROJECT | 16INR0006 |  | ANGELINA | GAS | NORTH | 2017 | 785 | 100% | 785 | 2020-05-14 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 814 | WOLF HOLLOW 2 | 17INR0009 |  | HOOD | GAS | NORTH | 2017 | 1069 | 100% | 1069 | 2020-05-15 | 2017-05-02 | OPERATIONAL | 2017-01-05 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 815 | FRIENDSWOOD G | 13INR0049 |  | HARRIS | GAS | HOUSTON | 2017 | 115 | 100% | 115 | 2020-05-16 | 2018-11-08 | OPERATIONAL | 2018-05-09 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 816 | BETHEL CAES PROJECT | 15INR0013 |  | ANDERSON | STORAGE | NORTH | 2018 | 0 | 100% | 0 | 2020-05-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 817 | HALYARD HENDERSON | 16INR0045 |  | HENDERSON | GAS | NORTH | 2018 | 450 | 100% | 450 | 2020-05-18 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 818 | HALYARD WHARTON ENERGY CENTER | 16INR0044 |  | WHARTON | GAS | SOUTH | 2018 | 419 | 100% | 419 | 2020-05-19 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
4 | Dec 2016 CDR | 819 | ALBERCAS WIND | 15INR0049 |  | ZAPATA | WIND | SOUTH | 2016 | 200 | 14% | 28 | 2020-05-23 | 2017-02-03 | OPERATIONAL | 2016-10-28 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 820 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2017 | 161 | 58% | 93.38 | 2020-05-24 | 2019-08-15 | OPERATIONAL | 2018-12-04 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 821 | LONGHORN WIND SOUTH | 14INR0023b |  | BRISCOE | WIND | PANHANDLE | 2017 | 160 | 14% | 22.4 | 2020-05-25 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 822 | MARIAH WIND A | 13INR0010a |  | PARMER | WIND | PANHANDLE | 2018 | 139.2 | 14% | 19.488 | 2020-05-26 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
4 | Dec 2016 CDR | 823 | MARIAH WIND B | 13INR0010b |  | PARMER | WIND | PANHANDLE | 2016 | 230.4 | 14% | 32.256 | 2020-05-27 | 2017-03-08 | OPERATIONAL | 2016-10-13 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 824 | MARIAH DEL SUR | 13INR0010c |  | PARMER | WIND | PANHANDLE | 2018 | 230.4 | 14% | 32.256 | 2020-05-28 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 825 | RATTLESNAKE DEN WIND 2 | 13INR0020b |  | GLASSCOCK | WIND | WEST | 2019 | 158 | 14% | 22.12 | 2020-05-29 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 826 | PATRIOT WIND (PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2017 | 180 | 58% | 104.4 | 2020-05-30 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
4 | Dec 2016 CDR | 827 | COMANCHE RUN WIND | 12INR0029 |  | SWISHER | WIND | PANHANDLE | 2018 | 500 | 14% | 70 | 2020-05-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 828 | PAMPA WIND | 12INR0018 |  | GRAY | WIND | PANHANDLE | 2018 | 500 | 14% | 70 | 2020-06-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 829 | GRANDVIEW WIND 3 (CONWAY) | 13INR0005c |  | CARSON | WIND | PANHANDLE | 2017 | 187.5 | 14% | 26.25 | 2020-06-02 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 830 | SCANDIA WIND DEF | 13INR0010def |  | PARMER | WIND | PANHANDLE | 2017 | 600.3 | 14% | 84.042 | 2020-06-03 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 831 | PULLMAN ROAD WIND | 15INR0079 |  | RANDALL | WIND | PANHANDLE | 2018 | 300 | 14% | 42 | 2020-06-04 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 832 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND | PANHANDLE | 2017 | 248 | 14% | 34.72 | 2020-06-05 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
4 | Dec 2016 CDR | 833 | SALT FORK WIND | 14INR0062 |  | GRAY | WIND | PANHANDLE | 2016 | 200 | 14% | 28 | 2020-06-06 | 2017-06-13 | OPERATIONAL | 2016-11-07 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 834 | PALO DURO (UNITY) WIND | 15INR0050 |  | DEAF SMITH | WIND | PANHANDLE | 2018 | 203 | 14% | 28.42 | 2020-06-07 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 835 | CAPROCK WIND | 10INR0009 |  | CASTRO | WIND | PANHANDLE | 2017 | 300 | 14% | 42 | 2020-06-08 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 836 | SAN ROMAN WIND | 14INR0013 |  | CAMERON | WIND-C | COASTAL | 2016 | 94 | 58% | 54.52 | 2020-06-09 | 2017-02-21 | OPERATIONAL | 2016-08-25 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 837 | TORRECILLAS WIND A | 14INR0045a |  | WEBB | WIND | SOUTH | 2017 | 200 | 14% | 28 | 2020-06-10 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 838 | TORRECILLAS WIND B | 14INR0045b |  | WEBB | WIND | SOUTH | 2017 | 200 | 14% | 28 | 2020-06-11 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 839 | CHANGING WINDS | 13INR0045 |  | CASTRO | WIND | PANHANDLE | 2017 | 288 | 14% | 40.32 | 2020-06-12 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 840 | ELECTRA WIND | 16INR0062a |  | WILBARGER | WIND | WEST | 2016 | 230 | 14% | 32.2 | 2020-06-13 | 2017-01-31 | OPERATIONAL | 2016-10-17 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 841 | LOCKETT WIND FARM | 16INR0062b |  | WILBARGER | WIND | WEST | 2017 | 184 | 14% | 25.76 | 2020-06-14 | 2019-09-19 | OPERATIONAL | 2019-05-31 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 842 | HORSE CREEK WIND | 14INR0060 |  | HASKELL | WIND | WEST | 2016 | 230 | 14% | 32.2 | 2020-06-15 | 2017-01-23 | OPERATIONAL | 2016-09-29 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 843 | WILLOW SPRINGS WIND | 14INR0060b |  | HASKELL | WIND | WEST | 2017 | 230 | 14% | 32.2 | 2020-06-16 | 2017-12-29 | OPERATIONAL | 2017-10-18 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 844 | MUENSTER WIND | 15INR0085 |  | COOKE | WIND | NORTH | 2016 | 125.6 | 14% | 17.584 | 2020-06-17 | 2017-04-13 | OPERATIONAL | 2016-10-18 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 845 | FALVEZ ASTRA W | 15INR0074 |  | DEAF SMITH | WIND | PANHANDLE | 2017 | 163.2 | 14% | 22.848 | 2020-06-18 | 2017-05-24 | OPERATIONAL | 2017-03-01 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 846 | CHAPMAN RANCH WIND I | 16INR0055 |  | NUECES | WIND-C | COASTAL | 2017 | 250 | 58% | 145 | 2020-06-19 | 2017-10-27 | OPERATIONAL | 2017-07-11 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 847 | HIDALGO & STARR WIND | 16INR0024 |  | HIDALGO | WIND | SOUTH | 2016 | 250 | 14% | 35 | 2020-06-20 | 2016-12-15 | OPERATIONAL | 2016-10-13 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 848 | BLANCO CANYON WIND (COTTON PLAINS) | 16INR0037 |  | FLOYD | WIND | PANHANDLE | 2016 | 50 | 14% | 7 | 2020-06-21 | 2017-04-20 | OPERATIONAL | 2017-01-12 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 849 | BLANCO CANYON WIND (OLD SETTLER) | 16INR0037b |  | FLOYD | WIND | PANHANDLE | 2017 | 150 | 14% | 21 | 2020-06-22 | 2017-04-20 | OPERATIONAL | 2017-01-12 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 850 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND | PANHANDLE | 2019 | 200 | 14% | 28 | 2020-06-23 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 851 | ROCK SPRINGS VAL VERDE WIND | 11INR0082a |  | VAL VERDE | WIND | WEST | 2017 | 149.3 | 14% | 20.902 | 2020-06-24 | 2017-10-26 | OPERATIONAL | 2017-06-20 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 852 | MAGIC VALLEY WIND II (REDFISH 2A and 2B) | 14INR0041a |  | WILLACY | WIND-C | COASTAL | 2017 | 230 | 58% | 133.4 | 2020-06-25 | 2017-12-21 | OPERATIONAL | 2017-10-30 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 853 | SALT FORK WIND 2 | 16INR0082 |  | CARSON | WIND | PANHANDLE | 2017 | 200 | 14% | 28 | 2020-06-26 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 854 | SANTA RITA WIND | 16INR0091 |  | REAGAN | WIND | WEST | 2017 | 300 | 14% | 42 | 2020-06-27 | 2018-05-09 | OPERATIONAL | 2017-12-19 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 855 | SWISHER WIND | 13INR0038 |  | SWISHER | WIND | PANHANDLE | 2017 | 300 | 14% | 42 | 2020-06-28 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
4 | Dec 2016 CDR | 856 | BUCKTHORN WIND 1 | 14INR0057 |  | ERATH | WIND | NORTH | 2017 | 96 | 14% | 13.44 | 2020-06-29 | 2017-12-12 | OPERATIONAL | 2017-08-01 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 857 | FLUVANNA RENEWABLE 1 | 13INR0056 |  | SCURRY | WIND | WEST | 2017 | 155.4 | 14% | 21.756 | 2020-06-30 | 2017-11-20 | OPERATIONAL | 2017-07-28 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 858 | RTS WIND | 16INR0087 |  | MCCULLOCH | WIND | SOUTH | 2017 | 160 | 14% | 22.4 | 2020-07-01 | 2018-09-07 | OPERATIONAL | 2018-03-08 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 859 | SILVER CANYON WIND A | 12INR0002a |  | BRISCOE | WIND | PANHANDLE | 2017 | 200 | 14% | 28 | 2020-07-02 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 860 | LOGAN'S GAP WIND II (FLAT TOP) | 15INR0082 |  | COMANCHE | WIND | NORTH | 2017 | 200 | 14% | 28 | 2020-07-03 | 2018-09-07 | OPERATIONAL | 2018-01-18 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 861 | CANADIAN BREAKS WIND | 13INR0026 |  | OLDHAM | WIND | PANHANDLE | 2017 | 201 | 14% | 28.14 | 2020-07-04 | 2019-12-17 | OPERATIONAL | 2019-07-18 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 862 | SALT FORK WIND EXPANSION | 16INR0121 |  | CARSON | WIND | PANHANDLE | 2017 | 24 | 14% | 3.36 | 2020-07-05 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 863 | CHOCOLATE BAYOU | 16INR0074 |  | BRAZORIA | WIND-C | COASTAL | 2018 | 150 | 58% | 87 | 2020-07-06 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
4 | Dec 2016 CDR | 864 | GOODNIGHT WIND | 14INR0033 |  | ARMSTRONG | WIND | PANHANDLE | 2018 | 500 | 14% | 70 | 2020-07-07 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
4 | Dec 2016 CDR | 865 | DERMOTT WIND 1 | 17INR0027 |  | SCURRY | WIND | WEST | 2017 | 250 | 14% | 35 | 2020-07-08 | 2017-08-01 | OPERATIONAL | 2017-06-09 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 866 | COYOTE WIND | 17INR0027b |  | SCURRY | WIND | WEST | 2018 | 250 | 14% | 35 | 2020-07-09 | N/A | PLANNED | 2020-11-25 | No | 2020-06-01 | P2 | COD delays without part 2 approval
4 | Dec 2016 CDR | 867 | BEARKAT WIND A | 15INR0064 |  | GLASSCOCK | WIND | WEST | 2017 | 197 | 14% | 27.58 | 2020-07-10 | 2018-02-14 | OPERATIONAL | 2017-12-15 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 868 | INFINITY LIVE OAK WIND | 12INR0060 |  | SCHLEICHER | WIND | WEST | 2017 | 200.6 | 14% | 28.084 | 2020-07-11 | 2020-04-17 | OPERATIONAL | 2018-11-29 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 869 | FS BARILLA SOLAR 1B [HOVEY_UNIT2] | 12INR0059b |  | PECOS | SOLAR | WEST | 2016 | 7.4 | 77% | 5.698 | 2020-07-21 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
4 | Dec 2016 CDR | 870 | FS BARILLA SOLAR 2 | 12INR0059c |  | PECOS | SOLAR | WEST | 2017 | 21 | 77% | 16.17 | 2020-07-22 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 871 | OCI ALAMO 6 (WEST TEXAS) | 15INR0070_1 |  | PECOS | SOLAR | WEST | 2017 | 110 | 77% | 84.7 | 2020-07-23 | 2017-03-16 | OPERATIONAL | 2016-06-06 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 872 | OCI ALAMO 6 (WEST TEXAS PHASE II) | 15INR0070_1b |  | PECOS | SOLAR | WEST | 2017 | 50 | 77% | 38.5 | 2020-07-24 | 2017-10-05 | OPERATIONAL | 2017-08-24 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 873 | SE BUCKTHORN WESTEX SOLAR (RIGGINS SOLAR) | 15INR0045 |  | PECOS | SOLAR | WEST | 2017 | 150 | 77% | 115.5 | 2020-07-25 | 2018-06-15 | OPERATIONAL | 2018-04-02 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 874 | FS EAST PECOS SOLAR | 16INR0073 |  | PECOS | SOLAR | WEST | 2016 | 120 | 77% | 92.4 | 2020-07-26 | 2017-04-07 | OPERATIONAL | 2017-01-25 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 875 | LC NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2017 | 201 | 77% | 154.77 | 2020-07-27 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
4 | Dec 2016 CDR | 876 | PECOS SOLAR POWER I | 15INR0059 |  | PECOS | SOLAR | WEST | 2019 | 108 | 77% | 83.16 | 2020-07-28 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
4 | Dec 2016 CDR | 877 | BNB LAMESA SOLAR | 16INR0023 |  | DAWSON | SOLAR | WEST | 2017 | 101.6 | 77% | 78.232 | 2020-07-29 | 2018-02-21 | OPERATIONAL | 2017-02-14 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 878 | BNB LAMESA SOLAR B | 16INR0023b |  | DAWSON | SOLAR | WEST | 2018 | 97.5 | 77% | 75.075 | 2020-07-30 | 2018-12-19 | OPERATIONAL | 2018-10-04 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 879 | CAPRICORN RIDGE SOLAR | 16INR0019 |  | COKE | SOLAR | WEST | 2017 | 100 | 77% | 77 | 2020-07-31 | 2019-11-07 | OPERATIONAL | 2018-10-25 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 880 | UPCO POWER 1 (SP-TX-12) | 16INR0065 |  | UPTON | SOLAR | WEST | 2017 | 117 | 77% | 90.09 | 2020-08-01 | 2018-05-31 | OPERATIONAL | 2018-03-16 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 881 | CASTLE GAP SOLAR 2 | 16INR0065a |  | UPTON | SOLAR | WEST | 2017 | 63 | 77% | 48.51 | 2020-08-02 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 882 | SP-TX-12-PHASE B | 16INR0065b |  | UPTON | SOLAR | WEST | 2017 | 120 | 77% | 92.4 | 2020-08-03 | 2017-08-25 | OPERATIONAL | 2017-06-30 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 883 | SOLAIREHOLMAN 1 | 15INR0061 |  | BREWSTER | SOLAR | WEST | 2017 | 50 | 77% | 38.5 | 2020-08-04 | 2018-05-24 | OPERATIONAL | 2017-03-30 | Yes | 2020-06-01 | O1 | operational by June 1st
4 | Dec 2016 CDR | 884 | RE MAPLEWOOD 2A SOLAR | 17INR0020a |  | PECOS | SOLAR | WEST | 2018 | 100 | 77% | 77 | 2020-08-05 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
4 | Dec 2016 CDR | 885 | RE MAPLEWOOD 2B SOLAR | 17INR0020b |  | PECOS | SOLAR | WEST | 2019 | 200 | 77% | 154 | 2020-08-06 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
4 | Dec 2016 CDR | 886 | RE MAPLEWOOD 2C SOLAR | 17INR0020c |  | PECOS | SOLAR | WEST | 2020 | 100 | 77% | 77 | 2020-08-07 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 887 | RE MAPLEWOOD 2D SOLAR | 17INR0020d |  | PECOS | SOLAR | WEST | 2020 | 0 | 77% | 0 | 2020-08-08 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
4 | Dec 2016 CDR | 888 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2018 | 102 | 77% | 78.54 | 2020-08-09 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
3 | May 2016 CDR | 889 | COLORADO BEND II | 17INR0007 |  | WHARTON | GAS | SOUTH | 2017 | 1088 | 100% | 1088 | 2020-08-10 | 2017-06-23 | OPERATIONAL | 2017-02-10 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 890 | TEXAS CLEAN ENERGY PROJECT | 13INR0023 |  | ECTOR | COAL | WEST | 2019 | 240 | 100% | 240 | 2020-08-11 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 891 | FGE TEXAS I PROJECT | 16INR0010 |  | MITCHELL | GAS | WEST | 2018 | 703 | 100% | 703 | 2020-08-12 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 892 | ANTELOPE 1-3 IC & ELK CTG 1 (SWITCHABLE) | 13INR0028 |  | HALE | GAS | PANHANDLE | 2016 | 0 | 100% | 0 | 2020-08-13 | 2016-06-07 | OPERATIONAL | 2016-04-12 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 893 | LA PALOMA ENERGY CENTER PROJECT | 16INR0004 |  | CAMERON | GAS | COASTAL | 2018 | 730 | 100% | 730 | 2020-08-14 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 894 | PHR PEAKERS [BAC_CTG1-6] | 14INR0038 |  | GALVESTON | GAS | HOUSTON | 2016 | 388 | 100% | 388 | 2020-08-15 | 2018-07-11 | OPERATIONAL | 2017-03-22 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 895 | SKY GLOBAL POWER ONE | 16INR0057 |  | COLORADO | GAS | SOUTH | 2016 | 51.4 | 100% | 51.4 | 2020-08-16 | 2016-08-12 | OPERATIONAL | 2016-02-10 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 896 | INDECK WHARTON ENERGY CENTER PROJECT | 15INR0023 |  | WHARTON | GAS | SOUTH | 2019 | 654 | 100% | 654 | 2020-08-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 897 | PINECREST ENERGY CENTER PROJECT | 16INR0006 |  | ANGELINA | GAS | NORTH | 2017 | 785 | 100% | 785 | 2020-08-18 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 898 | RED GATE IC PLANT [REDGATE_AGR_A-D] | 14INR0040 |  | HIDALGO | GAS | SOUTH | 2016 | 225 | 100% | 225 | 2020-08-19 | 2016-12-13 | OPERATIONAL | 2016-08-10 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 899 | ELK STATION CTG 2 (SWITCHABLE) | 15INR0032 |  | HALE | GAS | PANHANDLE | 2016 | 0 | 100% | 0 | 2020-08-20 | 2016-06-07 | OPERATIONAL | 2016-04-14 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 900 | ELK STATION CTG 3 | 15INR0033 |  | HALE | GAS | PANHANDLE | 2016 | 202 | 100% | 202 | 2020-08-21 | 2016-06-07 | OPERATIONAL | 2016-04-18 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 901 | WOLF HOLLOW 2 | 17INR0009 |  | HOOD | GAS | NORTH | 2017 | 1069 | 100% | 1069 | 2020-08-22 | 2017-05-02 | OPERATIONAL | 2017-01-05 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 902 | FRIENDSWOOD G | 13INR0049 |  | HARRIS | GAS | HOUSTON | 2017 | 115 | 100% | 115 | 2020-08-23 | 2018-11-08 | OPERATIONAL | 2018-05-09 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 903 | BETHEL CAES PROJECT | 15INR0013 |  | ANDERSON | STORAGE | NORTH | 2018 | 324 | 100% | 324 | 2020-08-24 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 904 | HALYARD HENDERSON | 16INR0045 |  | HENDERSON | GAS | NORTH | 2018 | 432 | 100% | 432 | 2020-08-25 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 905 | HALYARD WHARTON ENERGY CENTER | 16INR0044 |  | WHARTON | GAS | SOUTH | 2017 | 419 | 100% | 419 | 2020-08-26 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
3 | May 2016 CDR | 906 | ALBERCAS WIND | 15INR0049 |  | ZAPATA | WIND | SOUTH | 2016 | 250 | 12% | 30 | 2020-08-30 | 2017-02-03 | OPERATIONAL | 2016-10-28 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 907 | GUNSIGHT MOUNTAIN WIND | 08INR0018 |  | HOWARD | WIND | WEST | 2016 | 120 | 12% | 14.4 | 2020-08-31 | 2016-09-28 | OPERATIONAL | 2016-05-13 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 908 | BAFFIN WIND [BAFFIN_UNIT1-2] | 06INR0022c |  | KENEDY | WIND-C | COASTAL | 2016 | 202 | 55% | 111.1 | 2020-09-01 | 2016-06-24 | OPERATIONAL | 2015-02-09 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 909 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2017 | 161 | 55% | 88.55 | 2020-09-02 | 2019-08-15 | OPERATIONAL | 2018-12-04 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 910 | LONGHORN WIND SOUTH | 14INR0023b |  | BRISCOE | WIND | PANHANDLE | 2017 | 160 | 12% | 19.2 | 2020-09-03 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 911 | MARIAH WIND A | 13INR0010a |  | PARMER | WIND | PANHANDLE | 2017 | 139.2 | 12% | 16.704 | 2020-09-04 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
3 | May 2016 CDR | 912 | MARIAH WIND B | 13INR0010b |  | PARMER | WIND | PANHANDLE | 2016 | 230.4 | 12% | 27.648 | 2020-09-05 | 2017-03-08 | OPERATIONAL | 2016-10-13 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 913 | MARIAH DEL SUR | 13INR0010c |  | PARMER | WIND | PANHANDLE | 2017 | 230.4 | 12% | 27.648 | 2020-09-06 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 914 | RATTLESNAKE DEN WIND 2 | 13INR0020b |  | GLASSCOCK | WIND | WEST | 2017 | 158 | 12% | 18.96 | 2020-09-07 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 915 | PATRIOT WIND (PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2017 | 180 | 55% | 99 | 2020-09-08 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
3 | May 2016 CDR | 916 | COMANCHE RUN WIND | 12INR0029 |  | SWISHER | WIND | PANHANDLE | 2018 | 500 | 12% | 60 | 2020-09-09 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 917 | PAMPA WIND | 12INR0018 |  | GRAY | WIND | PANHANDLE | 2017 | 500 | 12% | 60 | 2020-09-10 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 918 | SOUTH PLAINS WIND II | 14INR0025b |  | FLOYD | WIND | PANHANDLE | 2016 | 151.8 | 12% | 18.216 | 2020-09-11 | 2016-06-08 | OPERATIONAL | 2016-03-05 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 919 | SOUTH PLAINS WIND III | 14INR0025c |  | FLOYD | WIND | PANHANDLE | 2016 | 148.5 | 12% | 17.82 | 2020-09-12 | 2016-06-08 | OPERATIONAL | 2016-03-05 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 920 | WAKE WIND | 14INR0047 |  | DICKENS | WIND | PANHANDLE | 2016 | 257.3 | 12% | 30.876 | 2020-09-13 | 2016-10-28 | OPERATIONAL | 2016-07-12 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 921 | DOUG COLBECK'S CORNER (CONWAY) | 13INR0005b |  | CARSON | WIND | PANHANDLE | 2016 | 200.5 | 12% | 24.06 | 2020-09-14 | 2016-05-18 | OPERATIONAL | 2016-03-15 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 922 | GRANDVIEW WIND 3 (CONWAY) | 13INR0005c |  | CARSON | WIND | PANHANDLE | 2016 | 187.5 | 12% | 22.5 | 2020-09-15 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 923 | SCANDIA WIND DEF | 13INR0010def |  | PARMER | WIND | PANHANDLE | 2017 | 600.3 | 12% | 72.036 | 2020-09-16 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 924 | PULLMAN ROAD WIND | 15INR0079 |  | RANDALL | WIND | PANHANDLE | 2016 | 300 | 12% | 36 | 2020-09-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 925 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND | PANHANDLE | 2016 | 248 | 12% | 29.76 | 2020-09-18 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
3 | May 2016 CDR | 926 | SALT FORK WIND | 14INR0062 |  | GRAY | WIND | PANHANDLE | 2016 | 200 | 12% | 24 | 2020-09-19 | 2017-06-13 | OPERATIONAL | 2016-11-07 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 927 | LOS VIENTOS IV WIND | 15INR0037 |  | STARR | WIND | SOUTH | 2016 | 200 | 12% | 24 | 2020-09-20 | 2016-12-01 | OPERATIONAL | 2016-06-06 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 928 | LOS VIENTOS V WIND [LV5_UNIT_1] | 15INR0021 |  | STARR | WIND | SOUTH | 2016 | 110 | 12% | 13.2 | 2020-09-21 | 2016-09-01 | OPERATIONAL | 2015-11-25 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 929 | PALO DURO WIND | 15INR0050 |  | DEAF SMITH | WIND | PANHANDLE | 2018 | 203 | 12% | 24.36 | 2020-09-22 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 930 | CAPROCK WIND | 10INR0009 |  | CASTRO | WIND | PANHANDLE | 2017 | 300 | 12% | 36 | 2020-09-23 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 931 | SAN ROMAN WIND | 14INR0013 |  | CAMERON | WIND-C | COASTAL | 2016 | 103 | 55% | 56.65 | 2020-09-24 | 2017-02-21 | OPERATIONAL | 2016-08-25 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 932 | TORRECILLAS WIND A | 14INR0045a |  | WEBB | WIND | SOUTH | 2016 | 200 | 12% | 24 | 2020-09-25 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 933 | TORRECILLAS WIND B | 14INR0045b |  | WEBB | WIND | SOUTH | 2016 | 200 | 12% | 24 | 2020-09-26 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 934 | CHANGING WINDS | 13INR0045 |  | CASTRO | WIND | PANHANDLE | 2017 | 288 | 12% | 34.56 | 2020-09-27 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 935 | ELECTRA WIND | 16INR0062a |  | WILBARGER | WIND | WEST | 2016 | 230 | 12% | 27.6 | 2020-09-28 | 2017-01-31 | OPERATIONAL | 2016-10-17 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 936 | LOCKETT WIND FARM | 16INR0062b |  | WILBARGER | WIND | WEST | 2017 | 184 | 12% | 22.08 | 2020-09-29 | 2019-09-19 | OPERATIONAL | 2019-05-31 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 937 | HORSE CREEK WIND | 14INR0060 |  | HASKELL | WIND | WEST | 2016 | 230 | 12% | 27.6 | 2020-09-30 | 2017-01-23 | OPERATIONAL | 2016-09-29 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 938 | WILLOW SPRINGS WIND | 14INR0060b |  | HASKELL | WIND | WEST | 2016 | 230 | 12% | 27.6 | 2020-10-01 | 2017-12-29 | OPERATIONAL | 2017-10-18 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 939 | MUENSTER WIND | 15INR0085 |  | COOKE | WIND | NORTH | 2016 | 118.3 | 12% | 14.196 | 2020-10-02 | 2017-04-13 | OPERATIONAL | 2016-10-18 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 940 | HAPPY WHITEFACE WIND | 15INR0074 |  | DEAF SMITH | WIND | PANHANDLE | 2016 | 157 | 12% | 18.84 | 2020-10-03 | 2017-05-24 | OPERATIONAL | 2017-03-01 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 941 | CHAPMAN RANCH WIND I | 16INR0055 |  | NUECES | WIND-C | COASTAL | 2017 | 250 | 55% | 137.5 | 2020-10-04 | 2017-10-27 | OPERATIONAL | 2017-07-11 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 942 | HIDALGO & STARR WIND | 16INR0024 |  | HIDALGO | WIND | SOUTH | 2016 | 250 | 12% | 30 | 2020-10-05 | 2016-12-15 | OPERATIONAL | 2016-10-13 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 943 | BLANCO CANYON WIND (COTTON PLAINS) | 16INR0037 |  | FLOYD | WIND | PANHANDLE | 2016 | 50 | 12% | 6 | 2020-10-06 | 2017-04-20 | OPERATIONAL | 2017-01-12 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 944 | BLANCO CANYON WIND (OLD SETTLER) | 16INR0037b |  | FLOYD | WIND | PANHANDLE | 2017 | 150 | 12% | 18 | 2020-10-07 | 2017-04-20 | OPERATIONAL | 2017-01-12 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 945 | PUMPKIN FARM WIND | 16INR0037c |  | FLOYD | WIND | PANHANDLE | 2017 | 200 | 12% | 24 | 2020-10-08 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 946 | ROCK SPRINGS VAL VERDE WIND | 11INR0082a |  | VAL VERDE | WIND | WEST | 2016 | 149.3 | 12% | 17.916 | 2020-10-09 | 2017-10-26 | OPERATIONAL | 2017-06-20 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 947 | MAGIC VALLEY WIND II (REDFISH 2A and 2B) | 14INR0041a |  | WILLACY | WIND-C | COASTAL | 2017 | 230 | 55% | 126.5 | 2020-10-10 | 2017-12-21 | OPERATIONAL | 2017-10-30 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 948 | SALT FORK WIND 2 | 16INR0082 |  | CARSON | WIND | PANHANDLE | 2017 | 200 | 12% | 24 | 2020-10-11 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 949 | SANTA RITA WIND | 16INR0091 |  | REAGAN | WIND | WEST | 2016 | 300 | 12% | 36 | 2020-10-12 | 2018-05-09 | OPERATIONAL | 2017-12-19 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 950 | SWISHER WIND | 13INR0038 |  | SWISHER | WIND | PANHANDLE | 2017 | 300 | 12% | 36 | 2020-10-13 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
3 | May 2016 CDR | 951 | BUCKTHORN WIND 1 | 14INR0057 |  | ERATH | WIND | NORTH | 2016 | 96 | 12% | 11.52 | 2020-10-14 | 2017-12-12 | OPERATIONAL | 2017-08-01 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 952 | FLUVANNA RENEWABLE 1 | 13INR0056 |  | SCURRY | WIND | WEST | 2017 | 240 | 12% | 28.8 | 2020-10-15 | 2017-11-20 | OPERATIONAL | 2017-07-28 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 953 | RTS WIND | 16INR0087 |  | MCCULLOCH | WIND | SOUTH | 2016 | 160 | 12% | 19.2 | 2020-10-16 | 2018-09-07 | OPERATIONAL | 2018-03-08 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 954 | SILVER CANYON WIND A | 12INR0002a |  | BRISCOE | WIND | PANHANDLE | 2017 | 200 | 12% | 24 | 2020-10-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 955 | LOGAN'S GAP WIND II | 15INR0082 |  | COMANCHE | WIND | NORTH | 2017 | 200 | 12% | 24 | 2020-10-18 | 2018-09-07 | OPERATIONAL | 2018-01-18 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 956 | FS BARILLA SOLAR 1B [HOVEY_UNIT2] | 12INR0059b |  | PECOS | SOLAR | WEST | 2016 | 7.4 | 80% | 5.92 | 2020-10-28 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
3 | May 2016 CDR | 957 | FS BARILLA SOLAR 2 | 12INR0059c |  | PECOS | SOLAR | WEST | 2017 | 21 | 80% | 16.8 | 2020-10-29 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 958 | RE ROSEROCK SOLAR | 16INR0048 |  | PECOS | SOLAR | WEST | 2016 | 160 | 80% | 128 | 2020-10-30 | 2016-11-23 | OPERATIONAL | 2016-06-13 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 959 | OCI ALAMO 6 (WEST TEXAS) | 15INR0070_1 |  | PECOS | SOLAR | WEST | 2016 | 110 | 80% | 88 | 2020-10-31 | 2017-03-16 | OPERATIONAL | 2016-06-06 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 960 | OCI ALAMO 6 (WEST TEXAS PHASE II) | 15INR0070_1b |  | PECOS | SOLAR | WEST | 2016 | 50 | 80% | 40 | 2020-11-01 | 2017-10-05 | OPERATIONAL | 2017-08-24 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 961 | SE BUCKTHORN WESTEX SOLAR (RIGGINS SOLAR) | 15INR0045 |  | PECOS | SOLAR | WEST | 2016 | 150 | 80% | 120 | 2020-11-02 | 2018-06-15 | OPERATIONAL | 2018-04-02 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 962 | FS EAST PECOS SOLAR | 16INR0073 |  | PECOS | SOLAR | WEST | 2016 | 100 | 80% | 80 | 2020-11-03 | 2017-04-07 | OPERATIONAL | 2017-01-25 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 963 | OCI ALAMO 7 (PAINT CREEK) | 16INR0052 |  | HASKELL | SOLAR | WEST | 2016 | 106 | 80% | 84.8 | 2020-11-04 | 2016-09-23 | OPERATIONAL | 2016-07-29 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 964 | LC NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2016 | 201 | 80% | 160.8 | 2020-11-05 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
3 | May 2016 CDR | 965 | PECOS SOLAR POWER I | 15INR0059 |  | PECOS | SOLAR | WEST | 2017 | 108 | 80% | 86.4 | 2020-11-06 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
3 | May 2016 CDR | 966 | BNB LAMESA SOLAR | 16INR0023 |  | DAWSON | SOLAR | WEST | 2016 | 200 | 80% | 160 | 2020-11-07 | 2018-02-21 | OPERATIONAL | 2017-02-14 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 967 | CAPRICORN RIDGE SOLAR | 16INR0019 |  | COKE | SOLAR | WEST | 2016 | 100 | 80% | 80 | 2020-11-08 | 2019-11-07 | OPERATIONAL | 2018-10-25 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 968 | UPCO POWER 1 (SP-TX-12) | 16INR0065 |  | UPTON | SOLAR | WEST | 2017 | 117 | 80% | 93.6 | 2020-11-09 | 2018-05-31 | OPERATIONAL | 2018-03-16 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 969 | CASTLE GAP SOLAR 2 | 16INR0065a |  | UPTON | SOLAR | WEST | 2017 | 63 | 80% | 50.4 | 2020-11-10 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
3 | May 2016 CDR | 970 | SP-TX-12-PHASE B | 16INR0065B |  | UPTON | SOLAR | WEST | 2016 | 120 | 80% | 96 | 2020-11-11 | 2017-08-25 | OPERATIONAL | 2017-06-30 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 971 | SOLAIREHOLMAN 1 | 15INR0061 |  | BREWSTER | SOLAR | WEST | 2017 | 50 | 80% | 40 | 2020-11-12 | 2018-05-24 | OPERATIONAL | 2017-03-30 | Yes | 2020-06-01 | O1 | operational by June 1st
3 | May 2016 CDR | 972 | UPTON SOLAR | 16INR0114 |  | UPTON | SOLAR | WEST | 2017 | 102 | 80% | 81.6 | 2020-11-13 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
2 | Dec 2015 CDR | 973 | TEXAS CLEAN ENERGY PROJECT | 13INR0023 |  | ECTOR | COAL | WEST | 2018 | 240 | 100% | 240 | 2020-11-14 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 974 | FGE TEXAS I PROJECT | 16INR0010 |  | MITCHELL | GAS | WEST | 2018 | 703 | 100% | 703 | 2020-11-15 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 975 | ANTELOPE 1-3 IC & ELK CTG 1 (SWITCHABLE) | 13INR0028 |  | HALE | GAS | PANHANDLE | 2016 | 0 | 100% | 0 | 2020-11-16 | 2016-06-07 | OPERATIONAL | 2016-04-12 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 976 | LA PALOMA ENERGY CENTER PROJECT | 16INR0004 |  | CAMERON | GAS | COASTAL | 2018 | 730 | 100% | 730 | 2020-11-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 977 | PHR PEAKERS [BAC_CTG1-6] | 14INR0038 |  | GALVESTON | GAS | HOUSTON | 2016 | 388 | 100% | 388 | 2020-11-18 | 2018-07-11 | OPERATIONAL | 2017-03-22 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 978 | SKY GLOBAL POWER ONE | 16INR0057 |  | COLORADO | GAS | SOUTH | 2016 | 51.4 | 100% | 51.4 | 2020-11-19 | 2016-08-12 | OPERATIONAL | 2016-02-10 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 979 | INDECK WHARTON ENERGY CENTER PROJECT | 15INR0023 |  | WHARTON | GAS | SOUTH | 2017 | 700 | 100% | 700 | 2020-11-20 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 980 | PONDERA KING PROJECT | 10INR0022 |  | HARRIS | GAS | HOUSTON | 2017 | 881.7 | 100% | 881.7 | 2020-11-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 981 | PINECREST ENERGY CENTER PROJECT | 16INR0006 |  | ANGELINA | GAS | NORTH | 2017 | 785 | 100% | 785 | 2020-11-22 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 982 | RED GATE IC PLANT [REDGATE_AGR_A-D] | 14INR0040 |  | HIDALGO | GAS | SOUTH | 2016 | 225 | 100% | 225 | 2020-11-23 | 2016-12-13 | OPERATIONAL | 2016-08-10 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 983 | ELK STATION CTG 2 (SWITCHABLE) | 15INR0032 |  | HALE | GAS | PANHANDLE | 2016 | 0 | 100% | 0 | 2020-11-24 | 2016-06-07 | OPERATIONAL | 2016-04-14 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 984 | ELK STATION CTG 3 | 15INR0033 |  | HALE | GAS | PANHANDLE | 2016 | 202 | 100% | 202 | 2020-11-25 | 2016-06-07 | OPERATIONAL | 2016-04-18 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 985 | WOLF HOLLOW 2 | 17INR0009 |  | HOOD | GAS | NORTH | 2017 | 1077 | 100% | 1077 | 2020-11-26 | 2017-05-02 | OPERATIONAL | 2017-01-05 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 986 | FRIENDSWOOD G | 13INR0049 |  | HARRIS | GAS | HOUSTON | 2017 | 115 | 100% | 115 | 2020-11-27 | 2018-11-08 | OPERATIONAL | 2018-05-09 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 987 | BETHEL CAES PROJECT | 15INR0013 |  | ANDERSON | STORAGE | NORTH | 2018 | 324 | 100% | 324 | 2020-11-28 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 988 | GUNSIGHT MOUNTAIN WIND | 08INR0018 |  | HOWARD | WIND | WEST | 2016 | 120 | 12% | 14.4 | 2020-12-02 | 2016-09-28 | OPERATIONAL | 2016-05-13 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 989 | BAFFIN WIND [BAFFIN_UNIT1-2] | 06INR0022c |  | KENEDY | WIND-C | COASTAL | 2015 | 202 | 55% | 111.1 | 2020-12-03 | 2016-06-24 | OPERATIONAL | 2015-02-09 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 990 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2016 | 161 | 55% | 88.55 | 2020-12-04 | 2019-08-15 | OPERATIONAL | 2018-12-04 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 991 | LONGHORN WIND SOUTH | 14INR0023b |  | BRISCOE | WIND | PANHANDLE | 2016 | 160 | 12% | 19.2 | 2020-12-05 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 992 | MARIAH WIND A | 13INR0010a |  | PARMER | WIND | PANHANDLE | 2016 | 232 | 12% | 27.84 | 2020-12-06 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
2 | Dec 2015 CDR | 993 | MARIAH WIND B | 13INR0010b |  | PARMER | WIND | PANHANDLE | 2016 | 230 | 12% | 27.6 | 2020-12-07 | 2017-03-08 | OPERATIONAL | 2016-10-13 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 994 | MIAMI WIND 1B | 14INR0012b |  | GRAY | WIND | PANHANDLE | 2016 | 111 | 12% | 13.32 | 2020-12-08 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 995 | SHANNON WIND [SHANNONW_UNIT_1] | 11INR0079a |  | CLAY | WIND | WEST | 2015 | 200 | 12% | 24 | 2020-12-09 | 2015-12-23 | OPERATIONAL | 2015-10-14 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 996 | SENDERO WIND ENERGY [EXGNSND_WIND_1] | 12INR0068 |  | JIM HOGG | WIND | SOUTH | 2015 | 78 | 12% | 9.36 | 2020-12-10 | 2015-12-22 | OPERATIONAL | 2015-11-13 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 997 | RATTLESNAKE DEN WIND 2 | 13INR0020b |  | GLASSCOCK | WIND | WEST | 2017 | 158 | 12% | 18.96 | 2020-12-11 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 998 | PATRIOT WIND (PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2016 | 180 | 55% | 99 | 2020-12-12 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
2 | Dec 2015 CDR | 999 | COMANCHE RUN WIND | 12INR0029 |  | SWISHER | WIND | PANHANDLE | 2016 | 500 | 12% | 60 | 2020-12-13 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1000 | CAMERON COUNTY WIND [CAMWIND_UNIT1] | 11INR0057 |  | CAMERON | WIND-C | COASTAL | 2015 | 165 | 55% | 90.75 | 2020-12-14 | 2016-01-27 | OPERATIONAL | 2015-10-31 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1001 | LOS VIENTOS III WIND [LV3_UNIT_1] | 13INR0052 |  | STARR | WIND | SOUTH | 2015 | 200 | 12% | 24 | 2020-12-15 | 2015-12-28 | OPERATIONAL | 2015-01-29 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1002 | PAMPA WIND | 12INR0018 |  | GRAY | WIND | PANHANDLE | 2017 | 500 | 12% | 60 | 2020-12-16 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1003 | SOUTH PLAINS WIND II | 14INR0025b |  | FLOYD | WIND | PANHANDLE | 2016 | 151.8 | 12% | 18.216 | 2020-12-17 | 2016-06-08 | OPERATIONAL | 2016-03-05 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1004 | SOUTH PLAINS WIND III | 14INR0025c |  | FLOYD | WIND | PANHANDLE | 2016 | 148.5 | 12% | 17.82 | 2020-12-18 | 2016-06-08 | OPERATIONAL | 2016-03-05 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1005 | WAKE WIND | 14INR0047 |  | DICKENS | WIND | PANHANDLE | 2016 | 300 | 12% | 36 | 2020-12-19 | 2016-10-28 | OPERATIONAL | 2016-07-12 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1006 | DOUG COLBECK'S CORNER (CONWAY) | 13INR0005b |  | CARSON | WIND | PANHANDLE | 2016 | 200.5 | 12% | 24.06 | 2020-12-20 | 2016-05-18 | OPERATIONAL | 2016-03-15 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1007 | GRANDVIEW WIND 3 (CONWAY) | 13INR0005c |  | CARSON | WIND | PANHANDLE | 2016 | 187.5 | 12% | 22.5 | 2020-12-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1008 | SCANDIA WIND D | 13INR0010d |  | PARMER | WIND | PANHANDLE | 2017 | 200 | 12% | 24 | 2020-12-22 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1009 | SCANDIA WIND E | 13INR0010e |  | PARMER | WIND | PANHANDLE | 2017 | 200 | 12% | 24 | 2020-12-23 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1010 | SCANDIA WIND F | 13INR0010f |  | PARMER | WIND | PANHANDLE | 2017 | 200 | 12% | 24 | 2020-12-24 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1011 | PULLMAN ROAD WIND | 15INR0079 |  | RANDALL | WIND | PANHANDLE | 2016 | 300 | 12% | 36 | 2020-12-25 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1012 | PANHANDLE WIND 3 | 14INR0030c |  | CARSON | WIND | PANHANDLE | 2016 | 248 | 12% | 29.76 | 2020-12-26 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
2 | Dec 2015 CDR | 1013 | SALT FORK WIND | 14INR0062 |  | GRAY | WIND | PANHANDLE | 2016 | 200 | 12% | 24 | 2020-12-27 | 2017-06-13 | OPERATIONAL | 2016-11-07 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1014 | LOS VIENTOS IV WIND | 15INR0037 |  | STARR | WIND | SOUTH | 2016 | 200 | 12% | 24 | 2020-12-28 | 2016-12-01 | OPERATIONAL | 2016-06-06 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1015 | LOS VIENTOS V WIND [LV5_UNIT_1] | 15INR0021 |  | STARR | WIND | SOUTH | 2015 | 110 | 12% | 13.2 | 2020-12-29 | 2016-09-01 | OPERATIONAL | 2015-11-25 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1016 | PALO DURO WIND | 15INR0050 |  | DEAF SMITH | WIND | PANHANDLE | 2016 | 203 | 12% | 24.36 | 2020-12-30 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1017 | JAVELINA WIND [BORDAS_JAVEL18 & 20] | 13INR0055 |  | ZAPATA | WIND | SOUTH | 2015 | 250 | 12% | 30 | 2020-12-31 | 2015-12-23 | OPERATIONAL | 2015-10-28 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1018 | CAPROCK WIND | 10INR0009 |  | CASTRO | WIND | PANHANDLE | 2017 | 300 | 12% | 36 | 2021-01-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1019 | SAN ROMAN WIND | 14INR0013 |  | CAMERON | WIND-C | COASTAL | 2016 | 103 | 55% | 56.65 | 2021-01-02 | 2017-02-21 | OPERATIONAL | 2016-08-25 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1020 | TORRECILLAS WIND A | 14INR0045a |  | WEBB | WIND | SOUTH | 2016 | 200 | 12% | 24 | 2021-01-03 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1021 | TORRECILLAS WIND B | 14INR0045b |  | WEBB | WIND | SOUTH | 2016 | 200 | 12% | 24 | 2021-01-04 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1022 | CHANGING WINDS | 13INR0045 |  | CASTRO | WIND | PANHANDLE | 2017 | 288 | 12% | 34.56 | 2021-01-05 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1023 | ELECTRA WIND | 16INR0062 |  | WILBARGER | WIND | WEST | 2016 | 360 | 12% | 43.2 | 2021-01-06 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1024 | HORSE CREEK WIND | 14INR0060 |  | HASKELL | WIND | WEST | 2016 | 200 | 12% | 24 | 2021-01-07 | 2017-01-23 | OPERATIONAL | 2016-09-29 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1025 | WILLOW SPRINGS WIND | 14INR0060b |  | HASKELL | WIND | WEST | 2016 | 200 | 12% | 24 | 2021-01-08 | 2017-12-29 | OPERATIONAL | 2017-10-18 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1026 | MUENSTER WIND | 15INR0085 |  | COOKE | WIND | NORTH | 2016 | 118.3 | 12% | 14.196 | 2021-01-09 | 2017-04-13 | OPERATIONAL | 2016-10-18 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1027 | HAPPY WHITEFACE WIND | 15INR0074 |  | DEAF SMITH | WIND | PANHANDLE | 2016 | 157 | 12% | 18.84 | 2021-01-10 | 2017-05-24 | OPERATIONAL | 2017-03-01 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1028 | CHAPMAN RANCH WIND I | 16INR0055 |  | NUECES | WIND-C | COASTAL | 2016 | 250 | 55% | 137.5 | 2021-01-11 | 2017-10-27 | OPERATIONAL | 2017-07-11 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1029 | HIDALGO & STARR WIND | 16INR0024 |  | HIDALGO | WIND | SOUTH | 2016 | 250 | 12% | 30 | 2021-01-12 | 2016-12-15 | OPERATIONAL | 2016-10-13 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1030 | BLANCO CANYON WIND (COTTON PLAINS) | 16INR0037 |  | FLOYD | WIND | PANHANDLE | 2016 | 50 | 12% | 6 | 2021-01-13 | 2017-04-20 | OPERATIONAL | 2017-01-12 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1031 | BLANCO CANYON WIND (OLD SETTLER) | 16INR0037b |  | FLOYD | WIND | PANHANDLE | 2016 | 150 | 12% | 18 | 2021-01-14 | 2017-04-20 | OPERATIONAL | 2017-01-12 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1032 | ROCK SPRINGS VAL VERDE WIND | 11INR0082a |  | VAL VERDE | WIND | WEST | 2016 | 180 | 12% | 21.6 | 2021-01-15 | 2017-10-26 | OPERATIONAL | 2017-06-20 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1033 | MAGIC VALLEY WIND II (REDFISH 2A) | 14INR0041a |  | WILLACY | WIND-C | COASTAL | 2016 | 115 | 55% | 63.25 | 2021-01-16 | 2017-12-21 | OPERATIONAL | 2017-10-30 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1034 | MAGIC VALLEY WIND II (REDFISH 2B) | 14INR0041b |  | WILLACY | WIND-C | COASTAL | 2016 | 115 | 55% | 63.25 | 2021-01-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1035 | SALT FORK WIND 2 | 16INR0082 |  | CARSON | WIND | PANHANDLE | 2016 | 200 | 12% | 24 | 2021-01-18 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1036 | SWISHER WIND | 13INR0038 |  | SWISHER | WIND | PANHANDLE | 2016 | 300 | 12% | 36 | 2021-01-19 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
2 | Dec 2015 CDR | 1037 | BUCKTHORN WIND 1 | 14INR0057 |  | ERATH | WIND | NORTH | 2016 | 96 | 12% | 11.52 | 2021-01-20 | 2017-12-12 | OPERATIONAL | 2017-08-01 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1038 | FLUVANNA RENEWABLE 1 | 13INR0056 |  | SCURRY | WIND | WEST | 2017 | 240 | 12% | 28.8 | 2021-01-21 | 2017-11-20 | OPERATIONAL | 2017-07-28 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1039 | RTS WIND | 16INR0087 |  | MCCULLOCH | WIND | SOUTH | 2016 | 200 | 12% | 24 | 2021-01-22 | 2018-09-07 | OPERATIONAL | 2018-03-08 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1040 | FS BARILLA SOLAR 1B [HOVEY_UNIT2] | 12INR0059b |  | PECOS | SOLAR | WEST | 2015 | 7.4 | 100% | 7.4 | 2021-02-01 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
2 | Dec 2015 CDR | 1041 | FS BARILLA SOLAR 2 | 12INR0059c |  | PECOS | SOLAR | WEST | 2016 | 21 | 100% | 21 | 2021-02-02 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
2 | Dec 2015 CDR | 1042 | OCI ALAMO 5 (DOWNIE RANCH) [HELIOS_UNIT1] | 15INR0036 |  | UVALDE | SOLAR | SOUTH | 2015 | 95 | 100% | 95 | 2021-02-03 | 2015-12-22 | OPERATIONAL | 2015-08-18 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1043 | RE ROSEROCK SOLAR | 16INR0048 |  | PECOS | SOLAR | WEST | 2016 | 150 | 100% | 150 | 2021-02-04 | 2016-11-23 | OPERATIONAL | 2016-06-13 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1044 | OCI ALAMO 6 (WEST TEXAS) | 15INR0070_1 |  | PECOS | SOLAR | WEST | 2016 | 110 | 100% | 110 | 2021-02-05 | 2017-03-16 | OPERATIONAL | 2016-06-06 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1045 | OCI ALAMO 6 (WEST TEXAS PHASE II) | 15INR0070_1b |  | PECOS | SOLAR | WEST | 2016 | 52.3 | 100% | 52.3 | 2021-02-06 | 2017-10-05 | OPERATIONAL | 2017-08-24 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1046 | SE BUCKTHORN WESTEX SOLAR (OAK) | 15INR0045 |  | PECOS | SOLAR | WEST | 2017 | 100 | 100% | 100 | 2021-02-07 | 2018-06-15 | OPERATIONAL | 2018-04-02 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1047 | FS EAST PECOS SOLAR | 16INR0073 |  | PECOS | SOLAR | WEST | 2016 | 100 | 100% | 100 | 2021-02-08 | 2017-04-07 | OPERATIONAL | 2017-01-25 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1048 | OCI ALAMO 7 (PAINT CREEK) | 16INR0052 |  | HASKELL | SOLAR | WEST | 2016 | 110 | 100% | 110 | 2021-02-09 | 2016-09-23 | OPERATIONAL | 2016-07-29 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1049 | LC NAZARETH SOLAR | 16INR0049 |  | CASTRO | SOLAR | PANHANDLE | 2016 | 201 | 100% | 201 | 2021-02-10 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
2 | Dec 2015 CDR | 1050 | PECOS SOLAR POWER I | 15INR0059 |  | PECOS | SOLAR | WEST | 2017 | 108 | 100% | 108 | 2021-02-11 | N/A | PLANNED | N/A | No | 2020-06-01 | P2 | COD delays without part 2 approval
2 | Dec 2015 CDR | 1051 | BNB LAMESA SOLAR | 16INR0023 |  | DAWSON | SOLAR | WEST | 2016 | 200 | 100% | 200 | 2021-02-12 | 2018-02-21 | OPERATIONAL | 2017-02-14 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1052 | CAPRICORN RIDGE SOLAR | 16INR0019 |  | COKE | SOLAR | WEST | 2016 | 100 | 100% | 100 | 2021-02-13 | 2019-11-07 | OPERATIONAL | 2018-10-25 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1053 | UPCO POWER 1 (SP-TX-12) | 16INR0065 |  | UPTON | SOLAR | WEST | 2016 | 180 | 100% | 180 | 2021-02-14 | 2018-05-31 | OPERATIONAL | 2018-03-16 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1054 | SP-TX-12-PHASE B | 16INR0065B |  | UPTON | SOLAR | WEST | 2016 | 120 | 100% | 120 | 2021-02-15 | 2017-08-25 | OPERATIONAL | 2017-06-30 | Yes | 2020-06-01 | O1 | operational by June 1st
2 | Dec 2015 CDR | 1055 | SOLAIREHOLMAN 1 | 15INR0061 |  | BREWSTER | SOLAR | WEST | 2016 | 50 | 100% | 50 | 2021-02-16 | 2018-05-24 | OPERATIONAL | 2017-03-30 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1056 | TEXAS CLEAN ENERGY PROJECT | 13INR0023 |  | ECTOR | COAL | WEST | 2018 | 240 | 100% | 240 | 2021-02-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1057 | PANDA TEMPLE II CTG1 | 10INR0020b |  | BELL | GAS | NORTH | 2015 | 191.2 | 100% | 191.2 | 2021-02-18 | 2015-05-07 | OPERATIONAL | 2015-03-06 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1058 | PANDA TEMPLE II CTG2 | 10INR0020b |  | BELL | GAS | NORTH | 2015 | 191.2 | 100% | 191.2 | 2021-02-19 | 2015-05-07 | OPERATIONAL | 2015-03-06 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1059 | PANDA TEMPLE II STG | 10INR0020b |  | BELL | GAS | NORTH | 2015 | 334.7 | 100% | 334.7 | 2021-02-20 | 2015-05-07 | OPERATIONAL | 2015-03-06 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1060 | FGE TEXAS I | 16INR0010 |  | MITCHELL | GAS | WEST | 2017 | 703 | 100% | 703 | 2021-02-21 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1061 | ANTELOPE STATION IC & CTG | 13INR0028 |  | HALE | GAS | PANHANDLE | 2016 | 0 | 100% | 0 | 2021-02-22 | 2016-06-07 | OPERATIONAL | 2016-04-12 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1062 | ECTOR COUNTY ENERGY [ECEC_G1-2] | 14INR0039 |  | ECTOR | GAS | WEST | 2015 | 294 | 100% | 294 | 2021-02-23 | 2015-09-28 | OPERATIONAL | 2015-07-25 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1063 | LA PALOMA ENERGY CENTER | 16INR0004 |  | CAMERON | GAS | COASTAL | 2017 | 730 | 100% | 730 | 2021-02-24 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1064 | PHR PEAKERS [BAC_CTG1-6] | 14INR0038 |  | GALVESTON | GAS | HOUSTON | 2016 | 388 | 100% | 388 | 2021-02-25 | 2018-07-11 | OPERATIONAL | 2017-03-22 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1065 | SKY GLOBAL POWER ONE | 16INR0057 |  | COLORADO | GAS | SOUTH | 2016 | 51 | 100% | 51 | 2021-02-26 | 2016-08-12 | OPERATIONAL | 2016-02-10 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1066 | INDECK WHARTON ENERGY CENTER | 15INR0023 |  | WHARTON | GAS | SOUTH | 2017 | 700 | 100% | 700 | 2021-02-27 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1067 | PONDERA KING PROJECT | 10INR0022 |  | HARRIS | GAS | HOUSTON | 2017 | 881.7 | 100% | 881.7 | 2021-02-28 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1068 | PINECREST ENERGY CENTER | 16INR0006 |  | ANGELINA | GAS | NORTH | 2017 | 785 | 100% | 785 | 2021-03-01 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1069 | STEC RED GATE IC PLANT | 14INR0040 |  | HIDALGO | GAS | SOUTH | 2016 | 225 | 100% | 225 | 2021-03-02 | 2016-12-13 | OPERATIONAL | 2016-08-10 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1070 | OCI ALAMO 5 SOLAR (DOWNIE RANCH) [HELIOS_UNIT1] | 15INR0036 |  | UVALDE | SOLAR | SOUTH | 2015 | 105 | 100% | 105 | 2021-03-03 | 2015-12-22 | OPERATIONAL | 2015-08-18 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1071 | EAST PECOS SOLAR | 16INR0073 |  | PECOS | SOLAR | WEST | 2016 | 100 | 100% | 100 | 2021-03-04 | 2017-04-07 | OPERATIONAL | 2017-01-25 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1072 | OCI ALAMO 6 SOLAR | 15INR0070_1 |  | PECOS | SOLAR | WEST | 2016 | 110 | 100% | 110 | 2021-03-05 | 2017-03-16 | OPERATIONAL | 2016-06-06 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1073 | RE ROSEROCK SOLAR | 16INR0048 |  | PECOS | SOLAR | WEST | 2016 | 150 | 100% | 150 | 2021-03-06 | 2016-11-23 | OPERATIONAL | 2016-06-13 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1074 | SUNEDISON BUCKTHORN WESTEX (OAK SOLAR) | 15INR0045 |  | PECOS | SOLAR | WEST | 2017 | 100 | 100% | 100 | 2021-03-07 | 2018-06-15 | OPERATIONAL | 2018-04-02 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1075 | STEPHENS RANCH PH 2 [SRWE1_SRWE2] | 12INR0034b |  | BORDEN | WIND | WEST | 2015 | 165 | 12% | 19.8 | 2021-03-11 | 2015-05-21 | OPERATIONAL | 2015-04-17 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1076 | MARIAH WIND PH a | 13INR0010a |  | PARMER | WIND | PANHANDLE | 2016 | 232 | 12% | 27.84 | 2021-03-12 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
1 | May 2015 CDR | 1077 | MARIAH WIND PH b | 13INR0010b |  | PARMER | WIND | PANHANDLE | 2017 | 232 | 12% | 27.84 | 2021-03-13 | 2017-03-08 | OPERATIONAL | 2016-10-13 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1078 | MIDWAY FARMS WIND | 11INR0054 |  | SAN PATRICIO | WIND-C | COASTAL | 2016 | 161 | 56% | 90.16 | 2021-03-14 | 2019-08-15 | OPERATIONAL | 2018-12-04 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1079 | LONGHORN ENERGY NORTH [LHORN_N_UNIT1-2] | 14INR0023 |  | BRISCOE | WIND | PANHANDLE | 2015 | 200 | 12% | 24 | 2021-03-15 | 2015-09-21 | OPERATIONAL | 2015-01-19 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1080 | LONGHORN ENERGY SOUTH | 14INR0023b |  | BRISCOE | WIND | PANHANDLE | 2016 | 160 | 12% | 19.2 | 2021-03-16 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1081 | GRANDVIEW PHASE 2 (CONWAY) | 13INR0005b |  | CARSON | WIND | PANHANDLE | 2016 | 389 | 12% | 46.68 | 2021-03-17 | 2016-05-18 | OPERATIONAL | 2016-03-15 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1082 | SHANNON WIND [SHANNONW_UNIT_1] | 11INR0079a |  | CLAY | WIND | WEST | 2015 | 200 | 12% | 24 | 2021-03-18 | 2015-12-23 | OPERATIONAL | 2015-10-14 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1083 | BAFFIN WIND (PENASCAL 3) [BAFFIN_UNIT1-2] | 06INR0022c |  | KENEDY | WIND-C | COASTAL | 2015 | 202 | 56% | 113.12 | 2021-03-19 | 2016-06-24 | OPERATIONAL | 2015-02-09 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1084 | GUNSIGHT MOUNTAIN WIND | 08INR0018 |  | HOWARD | WIND | WEST | 2015 | 120 | 12% | 14.4 | 2021-03-20 | 2016-09-28 | OPERATIONAL | 2016-05-13 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1085 | BRISCOE WIND FARM | 14INR0072 |  | BRISCOE | WIND | PANHANDLE | 2015 | 150 | 12% | 18 | 2021-03-21 | 2015-11-13 | OPERATIONAL | 2015-10-02 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1086 | CAMERON COUNTY WIND | 11INR0057 |  | CAMERON | WIND-C | COASTAL | 2015 | 165 | 56% | 92.4 | 2021-03-22 | 2016-01-27 | OPERATIONAL | 2015-10-31 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1087 | COMANCHE RUN WIND | 12INR0029 |  | SWISHER | WIND | PANHANDLE | 2016 | 500 | 12% | 60 | 2021-03-23 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1088 | CPV RATTLESNAKE DEN PH 1 [RSNAKE_G1-2] | 13INR0020a |  | GLASSCOCK | WIND | WEST | 2015 | 211 | 12% | 25.32 | 2021-03-24 | 2015-09-21 | OPERATIONAL | 2015-06-10 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1089 | CPV RATTLESNAKE DEN PH 2 | 13INR0020b |  | GLASSCOCK | WIND | WEST | 2016 | 158 | 12% | 18.96 | 2021-03-25 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1090 | GREEN PASTURES WIND I [GPASTURE_WIND_I & II] | 12INR0070 |  | BAYLOR | WIND | WEST | 2015 | 300 | 12% | 36 | 2021-03-26 | 2015-11-17 | OPERATIONAL | 2015-01-26 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1091 | HEREFORD WIND [HRFDWIND_WIND_G & V] | 13INR0059a |  | CASTRO | WIND | PANHANDLE | 2015 | 200 | 12% | 24 | 2021-03-27 | 2015-05-20 | OPERATIONAL | 2014-10-23 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1092 | LOGANS GAP WIND I [LGW_UNIT1-2] | 13INR0050 |  | COMANCHE | WIND | NORTH | 2015 | 200 | 12% | 24 | 2021-03-28 | 2015-09-30 | OPERATIONAL | 2015-05-27 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1093 | LOS VIENTOS III WIND [LV3_UNIT_1] | 13INR0052 |  | STARR | WIND | SOUTH | 2015 | 200 | 12% | 24 | 2021-03-29 | 2015-12-28 | OPERATIONAL | 2015-01-29 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1094 | MIAMI WIND 1b | 14INR0012b |  | GRAY | WIND | PANHANDLE | 2016 | 111 | 12% | 13.32 | 2021-03-30 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1095 | PAMPA WIND | 12INR0018 |  | GRAY | WIND | PANHANDLE | 2017 | 500 | 12% | 60 | 2021-03-31 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1096 | PATRIOT WIND (PETRONILLA) | 11INR0062 |  | NUECES | WIND-C | COASTAL | 2016 | 180 | 56% | 100.8 | 2021-04-01 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval
1 | May 2015 CDR | 1097 | ROUTE 66 WIND [ROUTE_66_WIND1] | 14INR0032a |  | RANDALL | WIND | PANHANDLE | 2015 | 150 | 12% | 18 | 2021-04-02 | 2015-08-11 | OPERATIONAL | 2015-04-28 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1098 | SENDERO WIND ENERGY | 12INR0068 |  | JIM HOGG | WIND | SOUTH | 2015 | 78 | 12% | 9.36 | 2021-04-03 | 2015-12-22 | OPERATIONAL | 2015-11-13 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1099 | SOUTH PLAINS WIND I [SPLAIN1_WIND1-2] | 14INR0025a |  | FLOYD | WIND | PANHANDLE | 2015 | 200 | 12% | 24 | 2021-04-04 | 2015-11-13 | OPERATIONAL | 2015-09-04 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1100 | SOUTH PLAINS WIND II | 14INR0025b |  | FLOYD | WIND | PANHANDLE | 2016 | 150 | 12% | 18 | 2021-04-05 | 2016-06-08 | OPERATIONAL | 2016-03-05 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1101 | SPINNING SPUR 3 [SSPURTWO_SS3WIND1-2] | 14INR0053 |  | OLDHAM | WIND | PANHANDLE | 2015 | 194 | 12% | 23.28 | 2021-04-06 | 2015-10-13 | OPERATIONAL | 2015-09-02 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1102 | WAKE WIND ENERGY | 14INR0047 |  | DICKENS | WIND | PANHANDLE | 2015 | 299 | 12% | 35.88 | 2021-04-07 | 2016-10-28 | OPERATIONAL | 2016-07-12 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1103 | CAPROCK WIND | 10INR0009 |  | CASTRO | WIND | PANHANDLE | 2017 | 300 | 12% | 36 | 2021-04-08 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1104 | JAVELINA WIND ENERGY | 13INR0055 |  | ZAPATA | WIND | SOUTH | 2015 | 250 | 12% | 30 | 2021-04-09 | 2015-12-23 | OPERATIONAL | 2015-10-28 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1105 | LOS VIENTOS IV WIND | 15INR0037 |  | STARR | WIND | SOUTH | 2016 | 200 | 12% | 24 | 2021-04-10 | 2016-12-01 | OPERATIONAL | 2016-06-06 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1106 | LOS VIENTOS V WIND | 15INR0021 |  | STARR | WIND | SOUTH | 2015 | 200 | 12% | 24 | 2021-04-11 | 2016-09-01 | OPERATIONAL | 2015-11-25 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1107 | PALO DURO WIND | 15INR0050 |  | DEAF SMITH | WIND | PANHANDLE | 2016 | 203 | 12% | 24.36 | 2021-04-12 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1108 | PANHANDLE WIND PH 3 | 14INR0030c |  | CARSON | WIND | PANHANDLE | 2016 | 248 | 12% | 29.76 | 2021-04-13 | N/A | INACTIVE | N/A | No | 2020-06-01 | P3 | projects that went inactive
1 | May 2015 CDR | 1109 | PULLMAN ROAD WIND | 15INR0079 |  | RANDALL | WIND | PANHANDLE | 2016 | 300 | 12% | 36 | 2021-04-14 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1110 | SALT FORK WIND | 14INR0062 |  | GRAY | WIND | PANHANDLE | 2016 | 200 | 12% | 24 | 2021-04-15 | 2017-06-13 | OPERATIONAL | 2016-11-07 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1111 | SCANDIA WIND PH d | 13INR0010d |  | PARMER | WIND | PANHANDLE | 2016 | 200 | 12% | 24 | 2021-04-16 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1112 | SCANDIA WIND PH e | 13INR0010e |  | PARMER | WIND | PANHANDLE | 2016 | 200 | 12% | 24 | 2021-04-17 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1113 | SCANDIA WIND PH f | 13INR0010f |  | PARMER | WIND | PANHANDLE | 2016 | 200 | 12% | 24 | 2021-04-18 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1114 | SAN ROMAN WIND | 14INR0013 |  | CAMERON | WIND-C | COASTAL | 2016 | 103 | 56% | 57.68 | 2021-04-19 | 2017-02-21 | OPERATIONAL | 2016-08-25 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1115 | CHANGING WINDS | 13INR0045 |  | CASTRO | WIND | PANHANDLE | 2016 | 288 | 12% | 34.56 | 2021-04-20 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1116 | ELECTRA WIND | 16INR0062 |  | WILBARGER | WIND | WEST | 2016 | 360 | 12% | 43.2 | 2021-04-21 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1117 | SOUTH PLAINS WIND III | 14INR0025c |  | FLOYD | WIND | PANHANDLE | 2016 | 150 | 12% | 18 | 2021-04-22 | 2016-06-08 | OPERATIONAL | 2016-03-05 | Yes | 2020-06-01 | O1 | operational by June 1st
1 | May 2015 CDR | 1118 | TORRECILLAS WIND A | 14INR0045a |  | WEBB | WIND | SOUTH | 2016 | 250 | 12% | 30 | 2021-04-23 | N/A | CANCELLED | #N/A | No | 2020-06-01 | P4 | projects that were cancelled
1 | May 2015 CDR | 1119 | TORRECILLAS WIND B | 14INR0045b |  | WEBB | WIND | SOUTH | 2016 | 250 | 12% | 30 | 2021-04-24 | N/A | CANCELLED | N/A | No | 2020-06-01 | P4 | projects that were cancelled

## Summer 2020 COD Delays
REPORT ID | FULL REPORT NAME | Order ID | UNIT NAME | INR | UNIT CODE | COUNTY | FUEL | ZONE | START YEAR | SUMMER NAMEPLATE CAPACITY (MW) | SUMMER CAPACITY CONTRIBUTION % | SUMMER CONTRIBUTION MW | PROJECTED COD (FROM REPORT) | ACTUAL IN-SERVICE DATE (as of 1/1/21) | CURRENT PROJECT STATUS (as of 1/1/21) | APPROVED FOR SYNCHRONIZATION (as of 1/1/21) | WAS IN-SERVICE BEFORE START OF SUMMER? | SUMMER CUTOFF DATE | NOTES ID | NOTES | PROJECTED COD (AS OF 6/1/20) | PROJECTED COD (AS OF 7/1/20) | PROJECTED COD (AS OF 8/1/20) | PROJECTED COD (AS OF 9/1/20) | PROJECTED COD (AS OF 10/1/20) | COD DELAY DAYS (FROM REPORT RELEASE TO END OF MAY) | COD DELAY DAYS (FROM REPORT RELEASE TO END OF JUNE) | COD DELAY DAYS (FROM REPORT RELEASE TO END OF JULY) | COD DELAY DAYS (FROM REPORT RELEASE TO END OF AUGUST) | COD DELAY DAYS (FROM REPORT RELEASE TO END OF SEPTEMBER)
4 | Final Summer 2020 SARA | 38 | CACTUS FLATS WIND | 16INR0086 |  | CONCHO | WIND-O | WEST | 2020 | 148.4 | 0.16 | 23.744 | 2020-06-30 | N/A | PLANNED | 2018-06-11 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2020-11-30 | 92 | 92 | 92 | 92 | 153
4 | Final Summer 2020 SARA | 42 | MESTENO WIND | 16INR0081 |  | STARR | WIND-O | SOUTH | 2020 | 201.6 | 0.16 | 32.256 | 2020-06-01 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-06-01 | 2020-08-01 | 2020-08-01 | 2020-10-31 | 2020-10-31 | 0 | 61 | 61 | 152 | 152
4 | Final Summer 2020 SARA | 40 | HIGH LONESOME W | 19INR0038 |  | CROCKETT | WIND-O | WEST | 2020 | 449.5 | 0.16 | 71.92 | 2020-05-15 | N/A | PLANNED | 2019-11-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-05-15 | 2020-05-15 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 0 | 153 | 153 | 153
4 | Final Summer 2020 SARA | 41 | HIGH LONESOME WIND PHASE II | 20INR0262 |  | CROCKETT | WIND-O | WEST | 2020 | 50.6 | 0.16 | 8.096 | 2020-05-15 | N/A | PLANNED | 2020-02-28 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-05-15 | 2020-05-15 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 0 | 0 | 153 | 153 | 153
4 | Final Summer 2020 SARA | 44 | RTS 2 WIND (HEART OF TEXAS WIND) | 18INR0016 |  | MCCULLOCH | WIND-O | SOUTH | 2020 | 179.91 | 0.16 | 28.7856 | 2020-07-29 | N/A | PLANNED | 2020-04-29 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-07-29 | 2020-07-29 | 2020-07-29 | 2020-07-29 | 2020-10-08 | 0 | 0 | 0 | 0 | 71
4 | Final Summer 2020 SARA | 49 | MISAE SOLAR | 18INR0045 |  | CHILDRESS | SOLAR | PANHANDLE | 2020 | 240.8 | 0.76 | 183.008 | 2020-05-15 | N/A | PLANNED | 2020-01-16 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-05-29 | 2020-06-19 | 2020-07-31 | 2020-08-19 | 2020-10-01 | 14 | 35 | 77 | 96 | 139
4 | Final Summer 2020 SARA | 51 | OXY SOLAR | 19INR0184 |  | ECTOR | SOLAR | WEST | 2020 | 16.2 | 0.76 | 12.312 | 2020-05-15 | N/A | PLANNED | 2019-07-31 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-05-29 | 2020-07-17 | 2020-07-17 | 2020-09-11 | 2020-09-30 | 14 | 63 | 63 | 119 | 138
4 | Final Summer 2020 SARA | 34 | PALMAS ALTAS WIND | 17INR0037 |  | CAMERON | WIND-C | COASTAL | 2020 | 144.9 | 0.63 | 91.287 | 2020-04-24 | N/A | PLANNED | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-05-31 | 2020-05-31 | 2020-07-31 | 2020-07-31 | 2020-09-30 | 37 | 37 | 98 | 98 | 159
4 | Final Summer 2020 SARA | 39 | HIDALGO II WIND | 19INR0053 |  | HIDALGO | WIND-O | SOUTH | 2020 | 51 | 0.16 | 8.16 | 2020-03-17 | N/A | PLANNED | 2019-12-10 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-06-01 | 2020-06-01 | 2020-08-03 | 2020-08-31 | 2020-09-30 | 76 | 76 | 139 | 167 | 197
4 | Final Summer 2020 SARA | 46 | WHITEHORSE WIND | 19INR0080 |  | FISHER | WIND-O | WEST | 2020 | 418.9 | 0.16 | 67.024 | 2020-04-30 | N/A | PLANNED | 2019-12-27 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-04-30 | 2020-04-30 | 2020-08-05 | 2020-08-05 | 2020-09-30 | 0 | 0 | 97 | 97 | 153
4 | Final Summer 2020 SARA | 37 | BLUE SUMMIT WIND 3 | 19INR0182 |  | WILBARGER | WIND-O | WEST | 2020 | 200 | 0.16 | 32 | 2020-06-30 | 2020-05-19 | OPERATIONAL | 2019-12-11 | Yes | 2020-06-01 | O1 | operational by June 1st | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 92 | 92 | 92 | 92 | 92
4 | Final Summer 2020 SARA | 54 | RAMBLER SOLAR | 19INR0114 |  | TOM GREEN | SOLAR | WEST | 2020 | 200 | 0.76 | 152 | 2020-07-01 | 2020-10-01 | OPERATIONAL | 2020-04-01 | No | 2020-06-01 | O4 | operational after August 1st | 2020-07-01 | 2020-08-14 | 2020-09-02 | 2020-09-18 | 2020-09-18 | 0 | 44 | 63 | 79 | 79
4 | Final Summer 2020 SARA | 45 | SAGE DRAW WIND | 19INR0163 |  | LYNN | WIND-O | WEST | 2020 | 338 | 0.16 | 54.08 | 2020-05-15 | N/A | PLANNED | 2019-12-12 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-05-29 | 2020-05-29 | 2020-08-21 | 2020-09-13 | 2020-09-13 | 14 | 14 | 98 | 121 | 121
4 | Final Summer 2020 SARA | 43 | OVEJA WIND | 18INR0033 |  | IRION | WIND-O | WEST | 2020 | 300 | 0.16 | 48 | 2020-04-30 | N/A | PLANNED | 2019-04-05 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-06-30 | 2020-06-30 | 2020-08-30 | 2020-08-30 | 2020-08-30 | 61 | 61 | 122 | 122 | 122
4 | Final Summer 2020 SARA | 53 | QUEEN SOLAR PHASE II | 20INR0298 |  | UPTON | SOLAR | WEST | 2020 | 200 | 0.76 | 152 | 2020-04-30 | 2020-08-28 | OPERATIONAL | 2020-04-10 | No | 2020-06-01 | O4 | operational after August 1st | 2020-04-30 | 2020-04-30 | 2020-08-21 | 2020-08-21 | 2020-08-21 | 0 | 0 | 113 | 113 | 113
4 | Final Summer 2020 SARA | 33 | HUDSON (BRAZORIA ENERGY G) | 16INR0076 |  | BRAZORIA | GAS | COASTAL | 2020 | 90 | 1 | 90 | 2020-05-31 | 2020-07-17 | OPERATIONAL | 2019-08-16 | No | 2020-06-01 | O3 | operational by August 1st | 2020-05-31 | 2020-06-30 | 2020-08-03 | 2020-08-03 | 2020-08-03 | 0 | 30 | 64 | 64 | 64
4 | Final Summer 2020 SARA | 36 | BARROW RANCH (JUMBO HILL WIND) | 18INR0038 |  | ANDREWS | WIND-O | WEST | 2020 | 160 | 0.16 | 25.6 | 2020-04-30 | N/A | PLANNED | 2020-02-26 | No | 2020-06-01 | P1 | COD delays but received part 2 approval | 2020-04-30 | 2020-04-30 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 0 | 0 | 92 | 92 | 92
4 | Final Summer 2020 SARA | 50 | OBERON SOLAR | 19INR0083 |  | ECTOR | SOLAR | WEST | 2020 | 180 | 0.76 | 136.8 | 2020-05-26 | 2020-07-13 | OPERATIONAL | 2020-04-08 | No | 2020-06-01 | O3 | operational by August 1st | 2020-06-26 | 2020-07-06 | 2020-07-14 | 2020-07-14 | 2020-07-14 | 31 | 41 | 49 | 49 | 49
4 | Final Summer 2020 SARA | 52 | PROSPERO SOLAR | 19INR0092 |  | ANDREWS | SOLAR | WEST | 2020 | 300 | 0.76 | 228 | 2020-06-30 | 2020-06-30 | OPERATIONAL | 2020-04-24 | No | 2020-06-01 | O2 | operational by July 1st | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-06-30 | 0 | 0 | 0 | 0 | 0
4 | Final Summer 2020 SARA | 48 | LAPETUS SOLAR | 19INR0185 |  | ANDREWS | SOLAR | WEST | 2020 | 100 | 0.76 | 76 | 2020-05-01 | 2020-06-24 | OPERATIONAL | 2019-12-06 | No | 2020-06-01 | O2 | operational by July 1st | 2020-05-01 | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-06-25 | 0 | 55 | 55 | 55 | 55
4 | Final Summer 2020 SARA | 47 | HOLSTEIN SOLAR | 19INR0009 |  | NOLAN | SOLAR | WEST | 2020 | 204.5 | 0.76 | 155.42 | 2020-06-01 | 2020-05-28 | OPERATIONAL | 2020-01-16 | Yes | 2020-06-01 | O1 | operational by June 1st | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 | 0 | 0 | 0 | 0 | 0
4 | Final Summer 2020 SARA | 35 | PEYTON CREEK WIND | 18INR0018 |  | MATAGORDA | WIND-C | COASTAL | 2020 | 151.2 | 0.63 | 95.256 | 2020-04-30 | 2020-06-04 | OPERATIONAL | 2019-11-14 | No | 2020-06-01 | O2 | operational by July 1st | 2020-05-15 | 2020-05-15 | 2020-05-15 | 2020-05-15 | 2020-05-15 | 15 | 15 | 15 | 15 | 15
4 | Final Summer 2020 SARA | 56 | FLAT TOP BATTERY | FLTBES_BESS1 | FLTBES_BESS1 | REEVES | STORAGE | WEST | 2019 | 9.9 | 0 | 0 | 2019-09-01 | 2020-05-22 | OPERATIONAL | 2020-05-05 | Yes | 2020-06-01 | O1 | operational by June 1st | 2019-09-01 | 2019-09-01 | 2019-09-01 | 2019-09-01 | 2019-09-01 | 0 | 0 | 0 | 0 | 0
4 | Final Summer 2020 SARA | 55 | COMMERCE ST ESS | X443ESS1_SWRI | X443ESS1_SWRI | BEXAR | STORAGE | SOUTH | 2019 | 10 | 0 | 0 | 2019-06-01 | 2020-10-16 | OPERATIONAL | 2019-11-26 | No | 2020-06-01 | O4 | operational after August 1st | 2019-06-01 | 2019-06-01 | 2019-06-01 | 2019-06-01 | 2019-06-01 | 0 | 0 | 0 | 0 | 0

## COD Forecast Issues
Other Significant issues in trying to forecast planned project COD delays
Commentary: Trying to forecast future delays for solar and storage projects using historical queue information dominated by wind could cause a selection bias.
Stacked bar chart based on recent December GIS report, summary tabs.
GIS report | Queue Snapshot | Total | Gas | Wind | Solar | Storage | Other
Dec 2017 GIS | 2017-12-31 | 68320 | 13969 | 30198 | 24123 | 30 | 0
Dec 2018 GIS | 2018-12-31 | 91921.16 | 9249.4 | 39596.45 | 40732.49 | 2342.82 | 0
Dec 2019 GIS | 2019-12-31 | 111742.19 | 5607 | 30173.96 | 67807.94 | 7790.29 | 363
Dec 2020 GIS | 2020-12-31 | 142743 | 7179 | 23620 | 88032 | 23550 | 362
Commentary: The development cycle for solar is noticeably shorter compared to wind and gas projects.
The chart shows the distribution of project lifespan in the queue since 2013 by fuel type. Lifespan is defined as the length between request date and commercial operations approval.
Fuel | Group | project lifespan (from request to commerical approval)
Solar | Lower quartile + (1.5*IRQ) | 1.31
Solar | Lower quartile | 2.62
Solar | Median | 3.19
Solar | Upper quartile | 3.87
Solar | Upper quartile + (1.5*IRQ) | 4.71
Wind | Lower quartile + (1.5*IRQ) | 1.73
Wind | Lower quartile | 2.87
Wind | Median | 4.03
Wind | Upper quartile | 5.72
Wind | Upper quartile + (1.5*IRQ) | 9.45
Gas | Lower quartile + (1.5*IRQ) | 1.57
Gas | Lower quartile | 2.98
Gas | Median | 3.61
Gas | Upper quartile | 5.72
Gas | Upper quartile + (1.5*IRQ) | 7.98
Commentary: Delays to projects are frequent and take several days to several weeks for developers to communicate with ERCOT.
Heat map of number of COD delays to projects in RIOO-IS system by Month and Year
Year | Month | Number of COD delays to projects in RIOO-IS
2018 | 9 | 61
2018 | 10 | 46
2018 | 11 | 62
2018 | 12 | 119
2019 | 1 | 89
2019 | 2 | 66
2019 | 3 | 96
2019 | 4 | 127
2019 | 5 | 85
2019 | 6 | 95
2019 | 7 | 110
2019 | 8 | 125
2019 | 9 | 124
2019 | 10 | 99
2019 | 11 | 92
2019 | 12 | 93
2020 | 1 | 85
2020 | 2 | 74
2020 | 3 | 112
2020 | 4 | 124
2020 | 5 | 94
2020 | 6 | 133
2020 | 7 | 132
2020 | 8 | 120
2020 | 9 | 170
2020 | 10 | 117
2020 | 11 | 118
2020 | 12 | 116

## Notable 2020 Queue Trends
Notable Queue Trends during 2020
Commentary: The projected CODs of planned solar projects in the queue highlights the quick development cycle of these resources.
Area chart based of projected COD of planned solar projects from recent GIS reports.
GIS report | snapshot | COD Year | Capacity to Grid (MW)
DEC. 2017 GIS | 2017-12-31 | 2018 | 200
DEC. 2017 GIS | 2017-12-31 | 2019 | 10085
DEC. 2017 GIS | 2017-12-31 | 2020 | 2414
DEC. 2017 GIS | 2017-12-31 | 2021 | 200
DEC. 2018 GIS | 2018-12-31 | 2019 | 4161.1
DEC. 2018 GIS | 2018-12-31 | 2020 | 16667.23
DEC. 2018 GIS | 2018-12-31 | 2021 | 7360.33
DEC. 2018 GIS | 2018-12-31 | 2022 | 600
DEC. 2019 GIS | 2019-12-31 | 2019 | 540.8
DEC. 2019 GIS | 2019-12-31 | 2020 | 6495.45
DEC. 2019 GIS | 2019-12-31 | 2021 | 35991.38
DEC. 2019 GIS | 2019-12-31 | 2022 | 9255.9
DEC. 2019 GIS | 2019-12-31 | 2023 | 1248.2
DEC. 2020 GIS | 2020-12-31 | 2020 | 143.6
DEC. 2020 GIS | 2020-12-31 | 2021 | 11465.73
DEC. 2020 GIS | 2020-12-31 | 2022 | 31074.47
DEC. 2020 GIS | 2020-12-31 | 2023 | 21094.44
DEC. 2020 GIS | 2020-12-31 | 2024 | 1649.51
DEC. 2020 GIS | 2020-12-31 | 2025 | 203.39
Commentary: The December 2020 COVID-19 relief bill provided a 2-year extension to the Investment Tax Credit (ITC) phase-out schedule, allowing solar and co-located solar/battery energy storage projects more headroom to qualify the 26% ITC value.
highlight table
https://www.powermag.com/wind-and-solar-tax-credits-extended/
Snapshot | Year | ITC Value
before Dec. 2020 stimulus bill | 2019 | 30%
before Dec. 2020 stimulus bill | 2020 | 26%
before Dec. 2020 stimulus bill | 2021 | 22%
before Dec. 2020 stimulus bill | 2022 | 10%
before Dec. 2020 stimulus bill | 2023 | 10%
before Dec. 2020 stimulus bill | 2024 | 10%
after Dec. 2020 stimulus bill | 2020 | 26%
after Dec. 2020 stimulus bill | 2021 | 26%
after Dec. 2020 stimulus bill | 2022 | 26%
after Dec. 2020 stimulus bill | 2023 | 22%
after Dec. 2020 stimulus bill | 2024 | 10%
Commentary: Cancelation Trends in ERCOT Queue since August 2018
Confounding factors associated with project cancelations make it hard to find any meaningful high-level trends.
Diverging stacked bar chart based on recent GIS reports.
Year | Month | Number of Cancelled Projects | Number of Requested Projects | Number of Operational Projects
2018 | 8 | 11 | 16 | 0
2018 | 9 | 15 | 23 | 2
2018 | 10 | 4 | 7 | 0
2018 | 11 | 7 | 23 | 1
2018 | 12 | 9 | 31 | 3
2019 | 1 | 20 | 40 | 0
2019 | 2 | 12 | 19 | 0
2019 | 3 | 18 | 27 | 1
2019 | 4 | 9 | 27 | 0
2019 | 5 | 11 | 46 | 0
2019 | 6 | 19 | 26 | 2
2019 | 7 | 11 | 28 | 0
2019 | 8 | 12 | 32 | 2
2019 | 9 | 15 | 13 | 2
2019 | 10 | 16 | 15 | 0
2019 | 11 | 11 | 28 | 4
2019 | 12 | 19 | 42 | 7
2020 | 1 | 3 | 31 | 2
2020 | 2 | 1 | 12 | 1
2020 | 3 | 21 | 15 | 1
2020 | 4 | 6 | 9 | 3
2020 | 5 | 40 | 24 | 4
2020 | 6 | 20 | 36 | 4
2020 | 7 | 9 | 20 | 2
2020 | 8 | 5 | 31 | 2
2020 | 9 | 37 | 29 | 0
2020 | 10 | 3 | 34 | 1
2020 | 11 | 5 | 19 | 1
2020 | 12 | 10 | 42 | 2
Commentary: In 2020, solar developers increasingly sought projects outside of the West CDR zone
Small multiple line charts
Zone | Request Year | Request Month | Capacity to Grid (MW)
WEST | 2018 | 1 | 564
WEST | 2018 | 2 | 505.07
WEST | 2018 | 3 | 205
WEST | 2018 | 4 | 2014
WEST | 2018 | 5 | 641
WEST | 2018 | 6 | 325
WEST | 2018 | 7 | 789.8
WEST | 2018 | 8 | 166.12
WEST | 2018 | 9 | 1663.6
WEST | 2018 | 10 | 115
WEST | 2018 | 11 | 1122.5
WEST | 2018 | 12 | 1896.21
WEST | 2019 | 1 | 1899.8
WEST | 2019 | 2 | 958.09
WEST | 2019 | 3 | 1365.01
WEST | 2019 | 4 | 1656.73
WEST | 2019 | 5 | 790.57
WEST | 2019 | 6 | 1826.96
WEST | 2019 | 7 | 637.69
WEST | 2019 | 8 | 880.5
WEST | 2019 | 9 | 767
WEST | 2019 | 10 | 517.27
WEST | 2019 | 11 | 516
WEST | 2019 | 12 | 3287.22
WEST | 2020 | 1 | 1312.5
WEST | 2020 | 2 | 65
WEST | 2020 | 3 | 382.09
WEST | 2020 | 4 | 374.4
WEST | 2020 | 5 | 350
WEST | 2020 | 6 | 1210.18
WEST | 2020 | 7 | 200
WEST | 2020 | 8 | 350
WEST | 2020 | 9 | 1333.39
WEST | 2020 | 10 | 330
WEST | 2020 | 12 | 995.73
PANHANDLE | 2018 | 2 | 222.95
PANHANDLE | 2018 | 4 | 250
PANHANDLE | 2018 | 5 | 1017.35
PANHANDLE | 2019 | 2 | 1218.41
PANHANDLE | 2019 | 3 | 223.2
PANHANDLE | 2019 | 5 | 151.69
PANHANDLE | 2019 | 8 | 714
PANHANDLE | 2019 | 12 | 480
PANHANDLE | 2020 | 2 | 848.21
PANHANDLE | 2020 | 7 | 405.74
PANHANDLE | 2020 | 10 | 204.2
PANHANDLE | 2020 | 12 | 511.63
SOUTH | 2018 | 3 | 769
SOUTH | 2018 | 4 | 201
SOUTH | 2018 | 5 | 862
SOUTH | 2018 | 6 | 253.3
SOUTH | 2018 | 7 | 414
SOUTH | 2018 | 8 | 50
SOUTH | 2018 | 9 | 502.8
SOUTH | 2018 | 10 | 752.89
SOUTH | 2018 | 11 | 635.99
SOUTH | 2018 | 12 | 1370.84
SOUTH | 2019 | 1 | 858.74
SOUTH | 2019 | 2 | 172.83
SOUTH | 2019 | 3 | 438.49
SOUTH | 2019 | 4 | 1096.3
SOUTH | 2019 | 5 | 2889.5
SOUTH | 2019 | 6 | 460
SOUTH | 2019 | 7 | 1332.88
SOUTH | 2019 | 8 | 440.49
SOUTH | 2019 | 9 | 110.69
SOUTH | 2019 | 10 | 500
SOUTH | 2019 | 11 | 937.43
SOUTH | 2019 | 12 | 2849.69
SOUTH | 2020 | 1 | 1061.15
SOUTH | 2020 | 2 | 685.58
SOUTH | 2020 | 4 | 204.65
SOUTH | 2020 | 5 | 984.94
SOUTH | 2020 | 6 | 1425.6
SOUTH | 2020 | 7 | 287.5
SOUTH | 2020 | 8 | 230
SOUTH | 2020 | 9 | 1052.53
SOUTH | 2020 | 10 | 1510
SOUTH | 2020 | 11 | 910.95
SOUTH | 2020 | 12 | 902.97
NORTH | 2018 | 3 | 522.2
NORTH | 2018 | 4 | 516.09
NORTH | 2018 | 5 | 125
NORTH | 2018 | 6 | 715
NORTH | 2018 | 8 | 175
NORTH | 2018 | 9 | 776
NORTH | 2018 | 10 | 284.29
NORTH | 2018 | 11 | 2709
NORTH | 2018 | 12 | 251
NORTH | 2019 | 1 | 1150
NORTH | 2019 | 2 | 401.6
NORTH | 2019 | 3 | 339.8
NORTH | 2019 | 4 | 1332
NORTH | 2019 | 5 | 1395.41
NORTH | 2019 | 6 | 716.38
NORTH | 2019 | 7 | 1486.72
NORTH | 2019 | 8 | 795.11
NORTH | 2019 | 9 | 503.1
NORTH | 2019 | 10 | 120
NORTH | 2019 | 11 | 864.85
NORTH | 2019 | 12 | 610
NORTH | 2020 | 1 | 1813.59
NORTH | 2020 | 2 | 1245.62
NORTH | 2020 | 3 | 500
NORTH | 2020 | 4 | 204.47
NORTH | 2020 | 5 | 1182.2
NORTH | 2020 | 6 | 2064.8
NORTH | 2020 | 7 | 1350.6
NORTH | 2020 | 8 | 961.75
NORTH | 2020 | 9 | 852.5
NORTH | 2020 | 10 | 1640.95
NORTH | 2020 | 11 | 1085.85
NORTH | 2020 | 12 | 3725.13
COASTAL | 2018 | 4 | 120
COASTAL | 2018 | 5 | 180
COASTAL | 2018 | 6 | 506.55
COASTAL | 2018 | 7 | 201.7
COASTAL | 2018 | 11 | 45.73
COASTAL | 2018 | 12 | 450
COASTAL | 2019 | 1 | 234
COASTAL | 2019 | 2 | 509.88
COASTAL | 2019 | 3 | 695
COASTAL | 2019 | 4 | 719.91
COASTAL | 2019 | 5 | 150
COASTAL | 2019 | 6 | 186.5
COASTAL | 2019 | 7 | 120
COASTAL | 2019 | 8 | 261.63
COASTAL | 2019 | 10 | 170
COASTAL | 2020 | 1 | 494.17
COASTAL | 2020 | 3 | 300
COASTAL | 2020 | 4 | 200
COASTAL | 2020 | 5 | 1087.9
COASTAL | 2020 | 6 | 407.84
COASTAL | 2020 | 7 | 400
COASTAL | 2020 | 8 | 509.67
COASTAL | 2020 | 9 | 790.8
COASTAL | 2020 | 10 | 415.26
COASTAL | 2020 | 11 | 201.5
COASTAL | 2020 | 12 | 350
HOUSTON | 2018 | 12 | 254.94
HOUSTON | 2019 | 2 | 100
HOUSTON | 2019 | 3 | 356.55
HOUSTON | 2019 | 7 | 310
HOUSTON | 2019 | 8 | 438.75
HOUSTON | 2019 | 9 | 300
HOUSTON | 2020 | 1 | 161.34
HOUSTON | 2020 | 6 | 458
HOUSTON | 2020 | 8 | 60
HOUSTON | 2020 | 10 | 447.5
HOUSTON | 2020 | 12 | 200.33