## Slide 1
Challenges building resources near series capacitors
- An Update to the 2017 and 2019 presentations -
ERCOT System Planning
Resource Integration Working Group
February 10, 2020

## Slide 2: Recap
In 2017 and 2019 ERCOT presented observations and challenges connecting near series capacitors
Since then,
  More resources are connecting closer to series capacitors
  More challenges have been observed, some causing delays

## Slide 3: Why is it so challenging to connect near series caps?

## Slide 4: Technical Challenges – Connecting Near Series Capacitors
Compensation level seen by IRR can be >100%
Potential Challenges:
  More SSR risk
  VRT / tripping issues
  “Energy accumulation” and inverter saturation
  Voltage Profile
  Voltage Control
  Transformer oscillations

## Slide 5: SSR Studies can identify non-SSR problems that still need to be resolved
Although the study purpose is to identify SSR vulnerability between gens and series capacitors, additional issues may be identified. Examples:
  Transient Voltage
  Tripping (VRT non-compliance)
  Transformer oscillations
If the addition of a new Resource creates SSR issues involving neighboring existing resources:
  Finding a solution may require substantial time
  Obstacles such as confidentiality restrictions on information sharing and coordination and tuning difficulties
  Expectation is for new resources to resolve problems created by their addition

## Slide 6: Timing Challenges
ERCOT has in the past worked with stakeholders to provide more flexibility for SSR studies
  PGRR043 decoupled SSR from FIS
  NPRR926 removed the mandatory 90 day window
Per Protocols, ERCOT has up to 30 days to review SSR studies. If the study is updated, ERCOT has another 30 days to review.
Most SSR studies are being completed only few weeks prior to planned synchronization date
For projects identified with SSR vulnerability, based on ERCOT’s observation, it typically takes months to resolve the issues and could impact the synchronization date.
ERCOT is receiving increased requests from the IEs for special rushed reviews of SSR studies and synchronization approvals
  Study is complex; requires sufficient time to review the report and often require additional information and data if SSR vulnerability was identified.

## Slide 7: Takeaways
For resources planning to connect close to series capacitors:
  Could present very complex technical challenges
  May require extensive engagement of various entities (manufactures, TSPs, and potential neighboring REs)
  Takes time
These issues can only be identified after the completion of the SSR study.
  Study timeline not considering these potential challenges could impact the planned interconnection schedule, like synchronization date.
To ensure each project is thoroughly and equitably vetted, it is necessary to retain the 30 day review period

## Slide 8: Questions?
  As always, please reach out to your Resource Integration engineer if regarding a specific project