## Slide 1
Passport Update
Future NPRR Consideration
Matt Mereness
Passport Program Director
PRS
February 11, 2021

## Slide 2: Passport Update
Passport Sequence of Milestones through 2024
Future NPRR consideration

## Slide 3: Passport Scope and Delivery
EMS Technology Foundation Upgrade
2019
2020
2024
2021
2022
2023
Real-Time Co-optimization
RTC
Key Principles
RTC
NPRR review
Battery Energy Storage Resources
BES Key Topic Concepts
BES
NPRR review
Distribution Generation Resources
DGR Workshops
DGR
NPRR review
On-going deliveries before Passport 2024:
DGR enhancements to re-open registration
Battery storage functionality enhancements
FFR Advancement
ERCOT Contingency Reserve Service
New 10-minute Ancillary Service product defined in NPRR863

## Slide 4: Passport Protocol Scope
Design | Revision Requests*
Real-Time Co-optimization | NPRR1007 – 1013
Battery Energy Storage Resources | NPRR1014 & 1029
Distribution Generation Resources | NPRR1016 (mapping improvements only)
ERCOT Contingency Reserve Service | NPRR863 (ECRS only)
*Additional supporting Market Guide changes are also within Passport scope.
May require clarifying NPRRs during Business Requirements development.
Over 900 pages of protocol/NPRR changes.

## Slide 5: Passport Sequence of Milestones through 2024
Unit/Functional testing
Pre-Passport
Last major release date for EMS/MMS/S&B projects
EMS Upgrade
Convert Gen/SCADA to C++
EMS/MMS CIM16 Network Model Go-Live
Last date for Go/No-Go for Combined Passport EMS Upgrade
Other EMS Subsystem Dev and Customs
Snapshot of EMS Upgrade Codestream without Passport
Passport Market Design
Core - EMS/MMS/SB
Support- OS/Reg…
Report- EIS/MIS
Core Business Reqts
Support Business Reqts
Report Business Reqts
Design/Development/UnitTest
Design/Development/UnitTest
Design/Development/UnitTest
Integration Testing
Begin Early SCED Testing (EMS/MMS)
Begin iTest EMS/MMS/S&B
Begin End-to-end Testing
Market
Trials
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Market Readiness & Go-Live
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Develop/Publish MP Specifications
Develop Market Trials Plans
Passport Cutover/Go-Live
Deliver Market Training
Market Readiness Metrics
Passport Implementation Task Force
Pre-Passport Deliveries into production before Passport
Planned milestone
Estimated milestone
Software Development
&
Unit Testing
Market Trials
&
Go-Live
Cutover
Business Requirements
&
Design
Integration
&
End-to-End Testing

## Slide 6: Future NPRR consideration
Limited resources and project funding for initiatives beyond the large projects identified below until 2024.
  FFR Advancement BES Pre-Passport Project
  DGR Pre-Passport Passport Program
Strict controls are needed to ensure delivery of these large projects on time and within budget.
ERCOT wants to partner with PRS and TAC on most effective approach for managing the current and future NPRRs.

## Slide 7: Future NPRR consideration
ERCOT recommends the following control for TAC & PRS consideration
  Going forward, ERCOT will file comments on stakeholder Revision Requests identifying high-level assessment of impacts and risks to Passport Program delivery.
  ERCOT comments will also provide a recommendation for “before or after” Passport Program delivery.
  If impact to Passport Program delivery, Sponsor can decide next step for the Revision Request – withdraw or pursue.
  If pursue, then PRS may recommend approval and/or tabling of the Revision Request. If approved by PRS, ERCOT will have option to file additional comments indicating that an Impact Analysis will not be completed until ERCOT has bandwidth to consider post-Passport Program efforts.
    Per Section 21.4, without an Impact Analysis the NPRR would remain tabled at PRS.
    ERCOT will continue be engaged at PRS to coordinate the potential timing of Impact Analysis work as resources become available.
Benefits and Exceptions on next page.

## Slide 8: Future NPRR consideration
Benefits of this recommendation:
  Allows continued discussion of future policy changes with some direction of regulatory certainty with PRS approval.
  Prevents gray-boxes within gray-boxes in Protocols and reduces administrative or substantive clean-up Revision Requests in the future.
  Avoids outdated Impact Analyses which can create risk to future resource and budget issues.
  Helps manage Project Priority List (PPL) more effectively with post-Passport Program changes.
Most Likely Exceptions to this recommendation:
  Revision Requests that are critical to reliability or instructed by PUCT.
Additional recommended control for TAC consideration:
  Be cognizant of workshops or other focused initiatives on Passport related systems (EMS, MMS and S&B) that rely heavy on ERCOT SMEs.
ERCOT welcomes feedback from TAC and PRS on these recommendations or alternatives.