## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
March 11, 2021

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Highlights
  2021 Release Targets
  ESR and DGR Pre-Passport Projects
  Passport Impacts 2021–2024
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2021 January Release – Off-Cycle – 1/1/2021 Complete
  NPRR1055 – Market Notice and ERCOT Discretion re Late-Filed NOIE Eligibility Attestations for PTP Obligations with Links to an Option Bid Awards
2021 February Release – R1 – 2/4/2020 – 2/6/2020 Complete
  NPRR902(a) – ERCOT Critical Energy Infrastructure Information
    New MPIM Market Participant role for ECEII
  NOGRR195 – Generator Voltage Control Tolerance Band
MMS/OS Tech Refresh Go-Live – 2/11/2021 – 3/4/2021 Complete
ERCOT decommissions old Market Information System (MIS) portlet site Complete
Date changed to 2/24/2021
NPRR902 – ERCOT Critical Energy Infrastructure Information workshop canceled
Reschedule date TBD
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/2 – 2/4 | April 3/30 – 4/1 | May 5/25 – 5/27 | July 7/27 – 7/29 | October 10/5 – 10/7 | December 12/7 – 12/9
NPRR902(a) NOGRR195 NPRR1055 OBDRR023(a) NPRR1020 | NPRR902(b) NPRR971 NPRR974 NPRR978(c) NPRR986 NPRR998 NPRR1043 VCMRR027 NPRR974 NPRR978(c) | NPRR905 SCR811 | NPRR867 | NPRR484 NPRR829 OBDRR023(b) SCR781(b) | FFR Advancement (NPRR863 FFR) NPRR1015 NPRR863 ECRS NPRR1015
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR902(a) – ECEII Market Participant MPIM role
NPRR902(b) – MIS links updated for ECEII reports
NPRR978(c) – Forecast Zone scope
SCR781(b) – “Add” capability
OBDRR023(a) – ERS Expenditure Limit
OBDRR023(b) – 4 Standard Contract Terms/Year
TBD Items | NPRRs: 825(b), 826, 841, 857, 879, 885, 918, 935(b), 936, 939, 941, 945, 962, 965, 1020, 1030, 1032, 1034, 1040, 1051 SCRs: 789 P, 799, 800, 805, 809, 812 Others: PGRR066
E
P
E
E
E
E
E
E
E
E
2024 Go-Lives
RIOO – Q4 2021
RARF Add Functionality Go-Live
TBD Go-Live
E
SCR804
Go-Live – April 2021
TO training in March
P
I
ECMS – May
Market Info & Grid Info to new platform
Improved dashboards and displays
Replace NoticeBuilder
ECMS – Dec.
Combine ERCOT.com and MIS
Improved search
New navigation
TBD Go-Lives Due to MMS/OS Delay
NPRR904, NPRR1006, OBDRR009
NPRR930
NPRR1019
1/1
ü
June
P
ü
ü
2/1
10/1
4/29
3/15
ü

## Slide 5: ESR and DGR Pre-Passport Projects
On 10/16/2020, ERCOT initiated 2 projects to deliver several Revision Requests relating to ESR and DGR
  PR353-01 BES Combo Model Implementation (gate to Execution phase in May 2021)
      Target go-live TBD
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NOGRR204 – Related to NPRR989, BESTF-1
    NOGRR208 – Related to NPRR1002, BESTF-5
    OBDRR017 – Related to NPRR987, BESTF-3
    PGRR081 – Related to NPRR1026, BESTF-7
    RRGRR023 – Related to NPRR1002, BESTF-5
  PR354-01 DGR/DESR Implementation (gate to Execution phase in late April 2021)
      Target go-live 2021-R5 (to be confirmed at gate to Execution)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources (DESRs)
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995 Implementation
    NOGRR212 – Related to NPRR1016
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    RRGRR026 – Related to NPRR1016
ESR: Energy Storage Resource
BES: Battery Energy Storage
DGR: Distributed Generation Resource
Red text = New addition since last report

## Slide 6: Passport Impacts 2021–2024
Impact Analysis postings will begin reporting potential Passport impacts
  Passport Schedule Risk Assessment
    Risk to Passport project if Revision Request is implemented in 2021-2024
    IA will report one of three risk conclusions
      No risk to Passport schedule
      Potential risk to Passport schedule
      Significant risk to Passport schedule
  Passport Cost Impact (optional analysis from Passport Program)
    Additional cost if implemented in current systems AND in Passport systems under development
Passport assessment of “Not Started” Revision Requests
  Passport requirements are in progress
  Teams need to understand which “Not Started” RRs need to be included in requirements
  ERCOT is working on a recommendation for the sequencing of these items
  Results to be brought to an upcoming PRS meeting (target = March TBD)

## Slide 7: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1023 | Change to CRR Repossession Process | 2022 | 3500 | $250k-$350k, 10-14 months Impact Area: CRR Target 2022 start due to conflicts with in-flight projects No impact to Passport
NPRR1060 | Improvements to ERS Testing Requirements and Other ERS Items | N/A | N/A | <$5k O&M Impact Area: Reporting No project required
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3310
Next available Rank in Regulatory = 320
Options for…