## Slide 1
Passport Update
Matt Mereness
Passport Director
TAC
March 24, 2021

## Slide 2: Passport Update
Scope of Passport
Milestones for Passport
Current Status
Future NPRR consideration
Passport stakeholder meetings and future actions
Appendix:
  Passport Scope Details
  Detailed Passport Milestones (2021-2024)
  RTCTF Items for Future Consideration by TAC

## Slide 3: Passport Scope and Delivery
EMS Technology Foundation Upgrade
2019
2020
2024
2021
2022
2023
Real-Time Co-optimization
RTC
Key Principles
RTC
NPRR review
Battery Energy Storage Resources
BES Key Topic Concepts
BES
NPRR review
Distribution Generation Resources
DGR Workshops
DGR
NPRR review
“Pre-Passport” deliveries before 2024:
FFR advancement
DGR enhancements to re-open registration
Battery storage functionality enhancements
ERCOT Contingency Reserve Service
New 10-minute Ancillary Service product defined in NPRR863

## Slide 4: Passport Protocol Scope
Design | Revision Requests*
Real-Time Co-optimization | NPRR1007 – 1013
Battery Energy Storage Resources | NPRR1014 & 1029
Distribution Generation Resources | NPRR1016 (mapping improvements only)
ERCOT Contingency Reserve Service | NPRR863 (ECRS only)
*Additional supporting Market Guide changes are also within Passport scope.

## Slide 5: Passport Sequence of Milestones through 2024
Unit/Functional testing
Pre-Passport
Last major release date for EMS/MMS/S&B projects
EMS Upgrade
Convert Gen/SCADA to C++
EMS/MMS CIM16 Network Model Go-Live
Last date for Go/No-Go for Combined Passport EMS Upgrade
Other EMS Subsystem Dev and Customs
Snapshot of EMS Upgrade Codestream without Passport
Passport Market Design
Core - EMS/MMS/SB
Support- OS/Reg…
Report- EIS/MIS
Core Business Reqts
Support Business Reqts
Report Business Reqts
Design/Development/UnitTest
Design/Development/UnitTest
Design/Development/UnitTest
Integration Testing
Begin Early SCED Testing (EMS/MMS)
Begin iTest EMS/MMS/S&B
Begin End-to-end Testing
Market
Trials
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Market Readiness & Go-Live
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Develop/Publish MP Specifications
Develop Market Trials Plans
Passport Cutover/Go-Live
Deliver Market Training
Market Readiness Metrics
Passport Implementation Task Force
Pre-Passport Deliveries into production before Passport
Planned milestone
Estimated milestone
Software Development
&
Unit Testing
Market Trials
&
Go-Live
Cutover
Business Requirements
&
Design
Integration
&
End-to-End Testing

## Slide 6: Passport Current Status
Key Passport Activities and Risks
  2021 Program objectives
    Upgrade EMS to new version for Passport development to be built upon
    Develop and integrate the EMS, MMS, S&B Business Requirements in first half of year to then develop supporting system requirements in second half of year
    Passport scope and shared staff resources with FFR, pre-Passport BES and DGR.
  Challenges and Risks
    Passport planning has aggressive EMS upgrade schedule as well as supporting key Pre-Passport projects (risk connected to a go/no-go milestone).
    MMS/OS Tech project went live three-months late affecting EMS-IT resources and other planned project work.
    Winter event impacts to staffing resources and recognition of potential policy-driven system changes.
  Currently the Market Management System (MMS) and Settlements & Billing (S&B) Business Requirements are on schedule.
  The Energy Management System (EMS) Upgrade and EMS Passport Business Requirements have staffing constraints that are being evaluated.
  No change in combined $85.5M budget
Budget
  More budget details in April 2021 Board F&A Report
(Dollars in millions)

## Slide 7: Future NPRR consideration
Reminder that Passport program is engaged with Protocol and Impact Analysis to file comments on stakeholder Revision Requests identifying high-level assessment of impacts and risks to Passport Program delivery.
ERCOT feedback through comments or the Impact Analysis will provide a recommendation for “before or after” Passport Program delivery.
If impact to Passport Program delivery, Sponsor can decide next step for the Revision Request – withdraw or pursue.
If pursue, then PRS may recommend approval and/or tabling of the Revision Request. If approved by PRS, ERCOT will file additional comments indicating that Impact Analysis will not be completed until ERCOT has bandwidth to consider post-Passport Program efforts.
Exceptions to this recommendation:
  Revision Requests that are critical to reliability or instructed by PUCT (would include any Revision Requests from February 2021 Extreme Winter Weather Event).

## Slide 8: Passport stakeholder meetings and future actions
Reminder of recommendation for TAC to sunset the RTCTF.
  Development of RTC Principles and RTC Protocols completed.
Recommendation that TAC consider ownership and assignments of the RTCTF-identified items that will require stakeholder engagement prior to 2024 Passport implementation (details in Appendix).
  Policy items- Potentially to WMS
  Analysis items- Potentially to WMS
  Supporting details- Future implementation working group / task force
  Market Participant needs- Future implementation working group / task force
ERCOT proposes working with TAC leadership to develop a Passport Implementation Working Group or Task Force in the coming months.

## Slide 9: Wrap-up and Questions
ERCOT is continuing work on Passport efforts.
ERCOT acknowledges there is risk to Passport and will keep stakeholders (PUCT staff, TAC, and Board) updated on the risks.
ERCOT will continue work to evaluate NPRRs that overlap with Passport scope or resources.
ERCOT willing to support next steps on transitioning stakeholder processes to support Passport implementation effort in coming months.
Questions?

## Slide 10: Appendix
Passport Scope Details
Detailed Passport Milestones (2021-2024)
RTCTF Items for Future Consideration by TAC

## Slide 11: Real-Time Co-optimization Scope
Real-Time Market will be expanded to clear Energy and Ancillary Services (AS) every five minutes
  Already in place at most ISOs; ERCOT currently co-optimizes in Day-Ahead Market
RTC design also creates benefits and changes:
  Provides ability for ERCOT to select and dispatch full capability of Resources (previously AS capacity was managed by MPs based on their Day-Ahead Market awards).
  Retires an adjustment period AS market
  Reliability Unit Commitment will also co-optimize the full capability of Resources
  Day-Ahead Market will allow virtual AS Offers
Operating Reserve Demand Curve (ORDC) price adders will be discontinued, and replaced by converting ORDC into AS Demand Curves for each AS and reflected in real-time energy and AS prices.

## Slide 12: Passport Storage and Distribution Level Scope
Modeling and Dispatching Battery Energy Storage as a single device
  Same device can be a Load when charging and a Generator when discharging.
Distribution-level Generator or Energy Storage
  Device can be within Distribution system and still be dispatched by ERCOT with improved mapping techniques.

## Slide 13: Passport Near-Term Milestones through 2021
GridOps
Package
EMS/OTS Business Reqts
NMMS/RIOO Business Reqts
PI and Operator Display Business Reqts
1Q2021
Jan
Feb
Mar
2Q2021
Apr
May
Jun
3Q2021
Jul
Aug
Sep
4Q2021
Oct
Nov
Dec
MarketOps
Package
MMS/PVT Business Reqts
SupportOps
Package
S&B/DataAgg/CSI-S&B Business Reqts
CMM / CMM-CSI Business Reqts
Siebel Business Reqts
Report/Data Package
DAIP/Cognos CDR/ EIS/ISM Business Reqts
TIBCO Business Reqts
MIS/Dashboards/ERCOT.com Business Reqts
EMS Upgrade
Convert Gen/SCADA to C++
EMS/MMS CIM16 Network Model Go-Live
Other EMS Subsystem Dev and Customs
Market Readiness & Go-Live
Develop and Publish MP Specifications
Potentially Begin Passport Implementation Task Force
Outage Scheduler Business Reqts

## Slide 14: Passport Sequence of Milestones through 2024
Unit/Functional testing
Pre-Passport
Last major release date for EMS/MMS/S&B projects
EMS Upgrade
Convert Gen/SCADA to C++
EMS/MMS CIM16 Network Model Go-Live
Last date for Go/No-Go for Combined Passport EMS Upgrade
Other EMS Subsystem Dev and Customs
Snapshot of EMS Upgrade Codestream without Passport
Passport Market Design
Core - EMS/MMS/SB
Support- OS/Reg…
Report- EIS/MIS
Core Business Reqts
Support Business Reqts
Report Business Reqts
Design/Development/UnitTest
Design/Development/UnitTest
Design/Development/UnitTest
Integration Testing
Begin Early SCED Testing (EMS/MMS)
Begin iTest EMS/MMS/S&B
Begin End-to-end Testing
Market
Trials
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Market Readiness & Go-Live
Market Connectivity
SCED/Control Tests
DAM, S&B reports
Develop/Publish MP Specifications
Develop Market Trials Plans
Passport Cutover/Go-Live
Deliver Market Training
Market Readiness Metrics
Passport Implementation Task Force
Pre-Passport Deliveries into production before Passport
Planned milestone
Estimated milestone

## Slide 15: RTCTF Items for Future Consideration
POLICY - Open policy discussion items:
  Parameters for Ancillary Service proxy offers
  Ancillary Service Demand Curves (ASDCs) for use in Reliability Unit Commitment (RUC) studies
  Any needed discussion on triggers for initiating off-cycle Security-Constrained Economic Dispatch (SCED) executions
    Largely driven by ERCOT Operator desk procedures and discretion today
  Consideration of NPRR for allowing real-time updates to offers in current Real-Time Market and future with RTC.
ANALYSIS - Requested analysis going forward:
  Framework for periodic analysis comparing RTC and the current Operating Reserve Demand Curve (ORDC) design – Key Principle 1.1(8)

## Slide 16: RTCTF Items for Future Consideration (continued)
SUPPORTING DETAILS - Other documentation that may need review:
  Verifiable Cost Manual (Change for on-line hydro Resources per Key Principle 1.3(3))
  Additional review of transmission constraint max. shadow price values
  Operation Procedures (e.g., removing SASM and HASL/LASL)
  Business Practice Manuals (e.g., changes to COP and telemetry)
MARKET PARTICIPANT NEEDS - Market needs for the transition and implementation:
  Mapping of bill determinants to extracts and reporting for developing shadow settlement
  Changes to Inter-Control Center Communications Protocol (ICCP) handbook, and documentation for non-ICCP market submissions
  Market trials/training/annual seminar engagement
  Any details MPs need for designing their control systems