## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
April 15, 2021

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Highlights
  2021 Release Targets
  ESR and DGR Pre-Passport Projects
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
MMS/OS Tech Refresh Go-Live – 3/4/2021 Complete
2021 March Release – Off-Cycle – 3/15/2021 Complete
  NPRR1020 – Allow Some Integrated Energy Storage Designs to Calculate Internal Loads
2021 April Release – R2 – 3/30/2021 – 4/1/2021 Complete
  NPRR971 – Replacing the Real-Time Average Incremental Energy Cost
  NPRR986 – BESTF-2 Energy Storage Resource Energy Offer Curves, Pricing, Dispatch, & Mitigation
  NPRR998 – ERS Deployment and Recall Messages
  NPRR1024 – Determination of Significance with Respect to Price Correction
  NPRR1043 – Clarification of NPRR986 Language Related to Wholesale Storage Load
  NOGRR213 – Alignment Changes for May 1, 2020 Nodal Operating Guide – NPRR998
  VCMRR027 – Related to NPRR986, BESTF-2 ESR Energy Offer Curves, Pricing, Dispatch, & Mitigation
2021 April Release – Off-Cycle – 4/22/2021 In Flight
  SCR804 – ERCOT GridGeo Access for Transmission Operators
2021 May Release – Off-Cycle – 5/1/2021 In Flight
  NPRR974 – Capacity Insufficiency Operating Condition Notice (OCN) Transparency
  NPRR978(c) – Alignment with Amendments to PUCT Substantive Rule 25.505
2021 May Release – R3 – 5/25/2021 – 5/27/2021 In Flight
  SCR811 – Addition of Intra-Hour PhotoVoltaic Power Forecast to GTBD Calculation
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/2 – 2/4 | April 3/30 – 4/1 | May 5/25 – 5/27 | July 7/27 – 7/29 | October 10/5 – 10/7 | December 12/7 – 12/9
NPRR902(a) NOGRR195 NPRR1055 OBDRR023(a) NPRR1020 | NPRR902(b) NPRR971 NPRR986 NPRR998 NPRR1024 NPRR1043 NOGRR213 VCMRR027 NPRR974 NPRR978(c) | NPRR905 SCR811 | NPRR902(b) NPRR905 SCR789 NPRR867 | NPRR484 NPRR829 OBDRR023(b) SCR781(b) | FFR Advancement (NPRR863 FFR) NPRR1015 NPRR863 ECRS NPRR1015
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR902(a) – ECEII Market Participant MPIM role
NPRR902(b) – MIS links updated for ECEII reports
NPRR978(c) – Forecast Zone scope
SCR781(b) – “Add” capability
OBDRR023(a) – ERS Expenditure Limit
OBDRR023(b) – 4 Standard Contract Terms/Year
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 867, 879, 885, 918, 935(b), 936, 939, 941, 945, 962, 965, 1030, 1032, 1034, 1040, 1051 SCRs: 789, 799, 800, 805, 809, 812 Market Guides: PGRR066
E
E
E
2024 Go-Lives
RIOO – Q4 2021
RARF Add Functionality Go-Live
TBD Go-Live
E
SCR804
Go-Live – 4/22/2021
TO training in April
ECMS – May
Market Info & Grid Info to new platform
Improved dashboards and displays
Replace NoticeBuilder
ECMS – Nov.
Combine ERCOT.com and MIS
Improved search
New navigation
TBD Go-Lives Due to MMS/OS Delay
NPRR904, NPRR1006, OBDRR009
NPRR930
NPRR1019
1/1
ü
June
ü
ü
2/1
10/1
5/1
3/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
E

## Slide 5: ESR and DGR Pre-Passport Projects
On 10/16/2020, ERCOT initiated 2 projects to deliver several Revision Requests relating to ESR and DGR
  PR353-01 BES Combo Model Implementation
      Target go-live TBD – potential for multiple go-lives
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NOGRR204 – Related to NPRR989, BESTF-1
    NOGRR208 – Related to NPRR1002, BESTF-5
    OBDRR017 – Related to NPRR987, BESTF-3
    PGRR081 – Related to NPRR1026, BESTF-7
    RRGRR023 – Related to NPRR1002, BESTF-5
  PR354-01 DGR/DESR Implementation (scheduled for gate to Execution phase in May 2021)
      Target go-live TBD
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources (DESRs)
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995 Implementation
    NOGRR212 – Related to NPRR1016
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    RRGRR026 – Related to NPRR1016
ESR: Energy Storage Resource
BES: Battery Energy Storage
DGR: Distributed Generation Resource
Red text = New addition since last report

## Slide 6: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1062 | Modify IDR Meter Requirement and Eliminate IDR Meter Requirement Report | N/A | N/A | <$10k O&M Impact Area: Data Access & Transparency No project required
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3310
Next available Rank in Regulatory = 320
Options for…