## Slide 1
Resource Integration Topics
Jay Teixeira
ERCOT
Resource Integration Working Group
April 20, 2021

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
TSAT Model Required – If PSSE model is UDM, then TSAT model should be UDM by November 1, 2021.

## Slide 4: GINR Time Line (Fastest)

## Slide 5: Self-Limiting Facilities in the INR Process
Unknown if Passport dates will slip due to Feb 2021 storm aftermath
Will wait a couple of months to see if schedule slips
Pause accepting SLF projects in RIOO until then
For any projects already submitted
  SLF Facilities in the INR process must have PLD after January 1, 2023 some future date TBD.
  If system changes delayed, part of the SLF may be allowed to proceed to PLD prior to 2023 this future date if configuration and MW output was specifically studied in FIS.

## Slide 6: New PGRR to create 60 day deadline to have FIS Applications Approved
Revision Description:
This Planning Guide Revision Request (PGRR) establishes a 60 day limit for an application to request a Full Interconnection Study (FIS) in the Generation Interconnection or Change Request (GINR) process to be completed by the Interconnecting Entity (IE) and approved by ERCOT.
Business Case:
This PGRR will establish a limit of 60 days from submittal for an IE to complete an application to request an FIS . This will allow an FIS request to be cancelled if not completed within 60 days. Data extracted from RIOO-IS from January 1, 2020 to March 11, 2020 shows that 78% of FIS requests are completed within 60 days. Section 5.3, Full Interconnection Study Request, lists several items that an IE is required to submit for ERCOT to approve an FIS request.

## Slide 7: New PGRR to create 60 day deadline to have FIS Applications Approved
The IE should be ready with all the required items prior to submitting an FIS request and should not be making an FIS request just to avoid being cancelled for not making the FIS request within 180 days of receiving the screening study results (see paragraph (5) of Section 5.4.1, Security Screening Study),

## Slide 8: Active PGRR’s
RRGRR028, submitted by John Karlik on behalf of the SPWG on December 23, 2020, Transformer Impedance Clarifications. Comments submitted by SPWG and ERCOT. ROS approval of comments needed to complete Impact Analysis. Tabled at ROS until next month.

## Slide 9: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department
Mailing List
  RESOURCE_INTEGRATION@LISTS.ERCOT.COM

## Slide 10: Questions?
Thank you!