## Slide 1: 2021 Update on ETT CREZ Outages
CMWG Meeting April 19, 2021
Kip Fox
President, ETT

## Slide 2: Agenda
Brief Timeline of Winter Storm Uri ETT Outages
Current CREZ Outage Schedule
Current Productivity
Other Discussion Items
Questions

## Slide 3: Timeline of ETT Asset Outages All 345kV lines returned to service prior to Feb 11th
ERCOT DECLARES EMERGENCY OPERATIONS LEVEL 3
1:20 am
Trip: Clear Crossing – Dermott (Oncor) 345 kV
8:05 am (15 min)
11th
18th
12th & 13th
14th
15th
16th
17th
Trip: Lytle – Lytle (CPS) 138 kV CPS outage
14th 1:17 pm (1.2 hrs)
Trip: Hamilton Road SVC2 138 kV
14th 9:12 pm (2.8 days)
Trip: Barney Davis – Nelson Sharpe 138 kV
14th 10:22 pm (13 hours)
Trip: N. Edinburg – Palmito (Sharyland outage) 345 kV
14th 11:35 pm (13.6 hours)
Trip: Razorback – Castroville (CPS outage) 138 kV
15th 12:36 am (6.5 hours)
Trip: Laredo VFT (CFE outage)
Trip: Lytle – Lytle (CPS outage) 138 kV
16th 11:55 pm (8.5 hours)
Trip: Nelson Sharpe – Santa Cruz 138 kV
17th 1:44 am (7.7 hours)
Trip: Rocksprings (Pedernales Interconnection, LCRA and AEP Texas outages)
17th 11:23 am (2.3 days)
Trip: Big Hill – Wilson Ranch Wind Interconnection
17th 11:39 am (Developer outage with ETT support)
Trip: LCRA Big Hill – LCRA Kendall
14th 9:02 am (LCRA)
19th
AEP WINTER STORM WARNING THROUGH 12th FOR NORTH TEXAS
Midnight on 10th
NORMAL CONDITIONS
10:35 am
AEP WINTER STORM WARNING THROUGH 15th FOR ENTIRE ETT TERRITORY
Midnight
15th 7:48 AM (3.5 days)
AEP WINTER STORM WARNING THROUGH 18th FOR CENTRAL AND WEST TEXAS
3:00 am

## Slide 5: Current Schedule
CC – Clear Crossing
WS – West Shakelford
EC – Edith Clarke
T – Tesla
*Edith Clarke – Clear Crossing outages are bifurcated to allow generation output during inspections
Thanksgiving
In-service
In-service

## Slide 6: Current Productivity
Chart: Edith Clark - Cottonwood Outage: Overall Availability OCT 23, 2020 - MAY 16, 2021
| 44127 | 44134 | 44141 | 44148 | 44155 | 44162 | 44169 | 44176 | 44183 | 44190 | 44197 | 44204 | 44211 | 44218 | 44225 | 44232 | 44239 | 44246 | 44253 | 44260 | 44267 | 44274 | 44281 | 44288 | 44295 | 44302 | 44309 | 44316 | 44323 | 44330 | 44337
available working days/wk | 1 | 6 | 6 | 6 | 6 | 4 | 5 | 6 | 6 | 4 | 0 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 1
worked days/wk | 0 | 1 | 7 | 5 | 4.395 | 2.604 | 3.207 | 7 | 5.541 | 3.437 | 0 | 3.02 | 2.604 | 5.333 | 5.166 | 4.146 | 1 | 0 | 4 | 3.999 | 3.207 | 1.621 | 1.301 | 1.446
weekly availability | 0 | 0.16667 | 1.1667 | 0.83333 | 0.7325 | 0.651 | 0.6414 | 1.1667 | 0.9235 | 0.85925 | 0 | 0.604 | 0.434 | 0.88883 | 0.861 | 0.691 | 0.16667 | 0 | 0.66667 | 0.6665 | 0.5345 | 0.27017 | 0.21683 | 0.2892
cumulative availability | 0 | 0.14286 | 0.61538 | 0.68421 | 0.6958 | 0.68962 | 0.68253 | 0.75515 | 0.77711 | 0.78368 | 0.78368 | 0.76735 | 0.73456 | 0.74837 | 0.75763 | 0.75257 | 0.71121 | 0.66432 | 0.66446 | 0.66458 | 0.65742 | 0.63722 | 0.61637 | 0.60339
Winter Storm Uri
New Year
Break

## Slide 7: Other Discussion Items
2022 and Beyond Tentative Plan
Additional Capacity Efforts
  Network upgrades for GTC’s (all economic)
  New technology to reduce impedance, congestion, other issues
Accountability issues to address in Texas
  Winterization certification/planning/additional work
  Storm quick response performance plan
  Transmission line availability (99.95%)
    1.00 –[(hours out x miles) / (1852 circuit miles x 8760 hrs)]