## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2021-03-25
Agenda Item: | Decision / Resolution | Action Items :
January Call Notes
| No changes were made. | The TX SET Vice Chair will have the notes posted.
The Texas SET Chair provided the Retail Market Subcommittee (RMS) Update on the following topics.
Winter Storm | The Texas SET Chair conducted a discussion related to the notes provided by the RMS Chair from the March RMS and TAC meetings. The Texas SET Chair stated that he believes that RMS will give direction at a later time but is reviewing the list of lessons learned created by the RMS chair to let the Texas SET meeting attendees know what has been discussed in case they were not able to be on those calls where this subject is being discussed. ERCOT Listserv was down. What can be done to have a backup if this happens in the future? RMS is considering creating a task force to address the issue. Types of communication from TDUs. The RMS Chair stated that they believe there is a PUCT Project, 51889: Review of Communiations for the Electric Market. Also noted was PUCT Project 51888: Review of Critical Load Standards and Processes that has been opened to discuss Communications processes which may include the TDU outages. Also noted was PUCT Project 51888: Review of Critical Load Standards and Processes that will be discussed as well. Types of communication from ERCOT. The RMS Chair stated that this is one of the items that may have to be handed down from above. Meter Data Expectations. Default, Acquisitions and Uplift Clarifications. ERCOT Website Display, develop and improve the conditions on the grid numbers. The Supply/Demand chart was not helpful because it was not accurate. Current system conditions and forecasts are not clear. The RMS Chair stated that this subject falls under the PUCT Project to review communications during an event like this. Winter Weather Preparations--have RMS preparations discussions twice a year to cover summer and winter. | The Texas SET Chair stated that Texas SET will wait for direction from RMS.
ERCOT Discussion Items
Flight Update | The Texas SET chair presented the update as provided by ERCOT. ERCOT noted that the 0221 Flight used the NAESB TLS v1.2.
Mass Transition Testing Discussion | The Texas SET chair provided an update from the March RMS meeting and Requested the RMS Leadership to provide any updates. The RMS Chair stated that they reached out to PUCT Staff to see how they expect any testing that may be required. He has not heard back. ERCOT stated that they have not heard anything either, but believes that the real Transitions that occurred in February were complex enough to analyze to determine if a Summer Readiness test is needed.
Discussion Items
Texas SET Enhancement Matrix
Outstanding Change Controls
CSA CC: Review Change Control Update | The Texas SET Chair conducted a review of the Change Control and made changes where needed. A question was asked to see what ERCOT would do when the CSA end date expires and there is no other CSA. ERCOT stated that they would remove the flag if the expiration date passed and there was no other adds. It was also noted that an add would always trump an existing CSA. | The Texas SET Chair will submit the change control to ERCOT for the next Change Control call.
2020 Issue I150 A13 Reject Codes Update | ERCOT conducted a discussion of the Change Control and made changes where needed. | ERCOT will submit the Change Control for the next Change Control call.
Premise Type CC: Update | Centerpoint conducted a discussion of the Change Control and made changes where needed. It was noted that there is interest in having this code displayed on the ERCOT MIS for each ESI ID and will be discussed later. | Centerpoint will submit the Change Control to ERCOT for the next Change Control call.
IAS Solution Update | Centerpoint conducted a discussion of the Change Control and made changes where needed | AEP will submit the Change Control to ERCOT for the next Change Control call.
Final 5.0 CC Timeline | Texas SET will have a Change Control Call at the April Meeting
Retail Market Guide Impacts | This discussion for this topic will be delayed until the April Meeting.
Protocol Impacts | This discussion for this topic will be delayed until the April Meeting.
System Change Request (SCR) | This discussion for this topic will be delayed until the April Meeting.
ERCOT Additional Changes | ERCOT would like to use the SNP (Safety Net Pending) reject code on Acquisition Transfers like it is on the Mass Transition.
TNMP Additional Un-executable code 814_28 IBO function from 814_04 | TNMP explained a scenario of accepting a backdated MVI and sending the 814_04 scheduling transaction; then realizing there was no back up to justify the backdated MVI. The request was to determine if we need a new un-executable code in the 814_28 to mirror the 814_04 IBO, Backdated request not part of a coordinated back-office clean up to allow these to be canceled. Also, it was noted that the reference to ERCOT MIMO rules in the 814_04 IBO Reject code should be removed. ERCOT stated that they already put the change to remove the ERCOT reference in changes they were submitting. | TNMP will request the other TDSPs' feedback offline; then let the others know if a change is needed prior to the next meeting for the new 814_28 Un-executable code.
Centerpoint additional discussion | Texas SET reviewed the extra documents Centerpoint Energy provided. Additional TX SET 5.0 Enhancements Requested by CNP 03_25_21
| 1. Add CW1 Reject code logic on 814_12/814_13 • Scenario 1: CNP would like to reject 814_12 with CW1 if it is received on the initial transaction (Move In and Move out) schedule date. • Scenario 2: CNP would like to reject 814_12 with CW1 if it is received after the initial transaction (Move In and Move out) schedule date. • 03/25/21 Consensus of TX SET: Agreed that change was needed to remove/delete graybox verbiage Used by ERCOT only from the 814_13 transaction in the REF~7G Reject Reason, therefore, CW1 Reject Code would be available for use by both ERCOT and TDSP. | It was noted that ERCOT already completed the redlined changes which will be included on the April 22, 2021 Change Control Call.
| 2. Add CW1 Reject code logic on 814_08/814_09 RD cancel (B40, A13) • Scenario 1: CNP would like to reject 814_08 RD cancel (B40, A13) with CW1 if it is received on the initial transaction (Move In, Move out and Switch) schedule date. • Scenario 2: CNP would like to reject 814_08 RD cancel (B40, A13) with CW1 if it is received after the initial transaction (Move In, Move out and Switch) schedule date. • 03/21/21 Consensus of TX SET: Agreed that change was needed to remove/delete graybox verbiage Used by ERCOT only from the 814_09 transaction in the REF~7G Reject Reason, therefore, CW1 Reject Code would be available for use by both ERCOT and TDSP: | It was noted that ERCOT already completed the redlined changes which will be included on the April 22, 2021 Change Control Call.
3. Add New Code to 814_24 (MVO) REF~1P that could be used by the REP of Record that would bypass the CSA agreement at ERCOT when one exists. •This new code could be used the same as a REP~1P = B44 instead of TDSP removing meter and drops it would allow TDSPs to only deenergize and obtain a final reading for invoicing that could be done via AMS/MDM systems, no special crews required for field execution(s) for meter and drops removal if that is necessary. •This new code would address the 2W issue going away for non-CSA CRs with the implementation of TX SET 5.0. However, there are circumstances where the REP of Record would want their MVO completed as requested by their Customer if the CSA MVI is rejected or completed un-executable by the TDSP. •03/25/21 Consensus of TX SET: No new code should be created for this scenario due to the volume of ESI IDs impacted and the infrequency of the event. In the future the process to resolve 814_24 MVO’s impacted ESI IDs involved into a CSA CR Default scenario may be resolved by one of these two options: •Option 1 Prior to TX SET v5.0: 814_24 will include REF~2W (MVO CSA De-energized) data element until TX SET v5.0 is implemented where ERCOT will start rejecting the 814_24 REF~2W coding if MVO CR is not CSA of Record. •Option 2 Only Option after TX SET v5.0: If MVO CR transactional processes doesn’t support including the REF~2W and/or after the implementation of TX SET v5.0 then the only remaining option post TX SET v5.0 option would be that the MVO CR would send the 814_24 transaction with the REF~1P = B44:
| 4. On March 3, 2021 ERCOT transmitted (503) 814_03’s that only included a comma in the EDI field for the customer name. CNP generated 814_04’s for these but they failed TX SET validation because none generated with a name. CNP manually worked to get them corrected and 814_04’s generated. We did complete the switches and sent 867_04’s for them. •Question: Should these have failed validation at ERCOT for not having a name? •ERCOT noted that they do not currently fail these as they are considered alphanumeric and would require a Texas SET guide change to have them validated. •03/25/21 Consensus of TX SET: Agreed that only a comma in the PER~IC PER02 Name field isn’t acceptable, but at this point TX SET is unable to determine what would be the best recourse for this data field since it is Free-form Alphanureric with a minimum of 1 and maximum of 60 characters. | Follow-up discussions at TX SET will be conducted to determine if there is a transactional solution.
| 5. Need new Reject or Complete Unexecutable code for situations when 814_01/814_03 Switch transaction is received by the TDSP on an address/premise where MVO is completed, and Meter has been removed by the TDSP. • Reject/Unexecutable code would provide CR specific response that MVI is required to get new meter installed and services turned back on with some exceptions where MVI may require permit to energize premise based upon city ordinances. • 03/25/21 Consensus of TX SET: Agreed that change control was needed to include reject code for Switch transaction reject since MVI is needed. | It was noted that ERCOT already completed the redlined changes needed in Section 11, Solution to Staking, of the Retail Market Guide. Also, ERCOT will include a new Reject Code in the list of Reject Codes for the Switch transaction since an 814_16 MVI transaction would be required. Change Control should be available for the April 22, 2021 TX SET Change Control Conference Call.
| 6. A Mass Transition (Default) population of 3 ESI IDs need to be discussed concerning what is the appropriate number of ESI IDs where all the notifications and Mass Transition processes should be initiated, hopefully it isn’t 3 ESI IDs in the future? • 03/25/21 Consensus of TX SET: After TX SET discussed with Dave Michelsen (ERCOT), Dave thought that revisions could be made to the Retail Market Guide Section 7.11 “Mass Transitions” to give ERCOT flexibility/discretion when assigning a small number of ESI IDs that would only go to the VREP(s) wouldn’t necessitate all the normally required email and market notifications. The information would only be provided to impacted TDSPs and VREPs involved into completing the transition of ESI IDs from the Defaulting CR. | Vistra took the action item to draft the required changes to the Retail Market Guide Section 7.11 for Mass Transition Roles and Responsibilities of ERCOT.
| 7. Competitive Retailer(s) CBCI File(s) data content unreliable, which isn’t identifiable until the critical reason this file is being provided to ERCOT is for a Mass Transition event. • 03/25/21 Consensus of TX SET: Agreed this item will require more discussion to determine what would be the best recourse long term. | Texas SET will discuss at the next meeting.
Other Business
Issues--No new Issues were discussed this month. | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | Still on Hold
Next Meeting--WebEx Only | 2021-04-22
Attendees F-T-F
Attendees Webex
Kyle Patrick NRG | Kathy Scott Centerpoint Energy
Jordan Troublefield ERCOT | Stephen Wilson TXUE
Diana Rehfeldt TNMP | Lauren Damen NRG
Deb Belin MarkeWise | Kim Wall Hansen Technologies
Kathryn Thurman ERCOT | Frank Nunes EC Infosystems
Sam Pak ONCOR | Dave Michelsen ERCOT
Jeff Chen Centerpoint Energy | Jim Lee AEP
John Schatz Vistra | Sheri Wiegand TXUE
Eric Blakey Just Energy