## Slide 1
Passport Program Update
Matt Mereness
Passport Director
TAC
April 28, 2021

## Slide 2: Passport Update
Scope of Passport
Bifurcation of EMS Upgrade and RTC
Reason for EMS/Passport Separation
Next Steps
Appendix:
  Passport Scope Details
  RTCTF Items for Future Consideration by TAC

## Slide 3: Passport Scope and Delivery
EMS Technology Foundation Upgrade
2019
2020
2024
2021
2022
2023
Real-Time Co-optimization
RTC
Key Principles
RTC
NPRR review
Battery Energy Storage Resources
BES Key Topic Concepts
BES
NPRR review
Distribution Generation Resources
DGR Workshops
DGR
NPRR review
“Pre-Passport” deliveries before 2024:
FFR advancement
DGR enhancements to re-open registration
Battery storage functionality enhancements
ERCOT Contingency Reserve Service
New 10-minute Ancillary Service product defined in NPRR863

## Slide 4: ERCOT Bifurcation of EMS Upgrade and RTC
EMS Upgrade
2019
2020
2024
2021
2022
2023
Passport/RTC Stakeholder Work
Passport NPRR Review
2025
2026
Original Passport
Implementation with EMS Upgrade
Real-Time Co-optimization (RTC)
Implementation after EMS Upgrade
Stabilization
Stabilization
Stabilization
Initial estimate that RTC go-live will be 18-months after EMS Upgrade.
Integration Testing,
Operating Day & Closed Loop Testing, Market Trials

## Slide 5: Reason for EMS/Passport Separation
Summary of Key Activities
  2021 Program objectives
    Upgrade EMS version for Passport development to be built upon (last upgrade was 2016)
    Develop and integrate the EMS, MMS, S&B Business Requirements in first half of year to then develop supporting system requirements in second half of year
    Passport scope and staff shared with other 2021 efforts (FFR, pre-Passport BES & DGR).
  1Q2021 Challenges
    Passport planning had an aggressive EMS upgrade schedule, with plan to upgrade portions of EMS software in 2021 to new language and then build Passport on top of new EMS.
    MMS/OS Tech project delay affected EMS-IT resources and other planned project work.
    Winter event impacts to staffing resources and recognition of potential policy-driven system changes.
  The Energy Management System (EMS) Upgrade and EMS Passport Business Requirements staffing constraints were not resolvable, and led to the decision to accelerate the go/no-go decision of separating the EMS Upgrade from the Passport Program.

## Slide 6: Next Steps
Step 1- ERCOT needs time to develop an updated delivery schedule for EMS Upgrade without Passport scope.
Step 2- Based on updated EMS Upgrade and staffing plans, ERCOT will analyze delivery sequence alternatives for strategic efforts.
  Work continues for planning FFR, Pre-Passport DGR, and Pre-Passport BES.
  ERCOT will re-evaluate options on delivery for RTC, ECRS, BES, and DGR changes.
In parallel, ERCOT will support Revision Requests from February 2021 Extreme Winter Weather Event and other policy decisions with Impact Analysis efforts.
However, as this program delay is based in resource constraints, ERCOT still reserves the right to defer significant Impact Analysis work for large design changes until staff are available to support the effort (especially in the areas of EMS, MMS, S&B/Credit).

## Slide 7: Wrap-up
ERCOT is working on re-planning EMS Upgrade and Passport efforts.
ERCOT will continue monthly update at TAC meetings.
ERCOT recommends delaying plans for establishing an Implementation Working Group.
Questions?

## Slide 8: Appendix
Passport Scope Details
RTCTF Items for Future Consideration by TAC

## Slide 9: Passport Protocol Scope
Design | Revision Requests*
Real-Time Co-optimization | NPRR1007 – 1013
Battery Energy Storage Resources | NPRR1014 & 1029
Distribution Generation Resources | NPRR1016 (mapping improvements only)
ERCOT Contingency Reserve Service | NPRR863 (ECRS only)
*Additional supporting Market Guide changes are also within Passport scope.

## Slide 10: Real-Time Co-optimization Scope
Real-Time Market will be expanded to clear Energy and Ancillary Services (AS) every five minutes
  Already in place at most ISOs; ERCOT currently co-optimizes in Day-Ahead Market
RTC design also creates benefits and changes:
  Provides ability for ERCOT to select and dispatch full capability of Resources (previously AS capacity was managed by MPs based on their Day-Ahead Market awards).
  Retires an adjustment period AS market
  Reliability Unit Commitment will also co-optimize the full capability of Resources
  Day-Ahead Market will allow virtual AS Offers
Operating Reserve Demand Curve (ORDC) price adders will be discontinued, and replaced by converting ORDC into AS Demand Curves for each AS and reflected in real-time energy and AS prices.

## Slide 11: Passport Storage and Distribution Level Scope
Modeling and Dispatching Battery Energy Storage as a single device
  Same device can be a Load when charging and a Generator when discharging.
Distribution-level Generator or Energy Storage
  Device can be within Distribution system and still be dispatched by ERCOT with improved mapping techniques.

## Slide 12: RTCTF Items for Future Consideration
POLICY - Open policy discussion items:
  Parameters for Ancillary Service proxy offers
  Ancillary Service Demand Curves (ASDCs) for use in Reliability Unit Commitment (RUC) studies
  Any needed discussion on triggers for initiating off-cycle Security-Constrained Economic Dispatch (SCED) executions
    Largely driven by ERCOT Operator desk procedures and discretion today
  Consideration of NPRR for allowing real-time updates to offers in current Real-Time Market and future with RTC.
ANALYSIS - Requested analysis going forward:
  Framework for periodic analysis comparing RTC and the current Operating Reserve Demand Curve (ORDC) design – Key Principle 1.1(8)

## Slide 13: RTCTF Items for Future Consideration (continued)
SUPPORTING DETAILS - Other documentation that may need review:
  Verifiable Cost Manual (Change for on-line hydro Resources per Key Principle 1.3(3))
  Additional review of transmission constraint max. shadow price values
  Operation Procedures (e.g., removing SASM and HASL/LASL)
  Business Practice Manuals (e.g., changes to COP and telemetry)
MARKET PARTICIPANT NEEDS - Market needs for the transition and implementation:
  Mapping of bill determinants to extracts and reporting for developing shadow settlement
  Changes to Inter-Control Center Communications Protocol (ICCP) handbook, and documentation for non-ICCP market submissions
  Market trials/training/annual seminar engagement
  Any details MPs need for designing their control systems