## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
May 13, 2021

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Highlights
  2021 Release Targets
  ESR and DGR Pre-Passport Projects
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2021 April Release – Off-Cycle – 4/22/2021 Complete
  SCR804 – ERCOT GridGeo Access for Transmission Operators
2021 May Release – Off-Cycle – 5/1/2021 Complete
  PGRR070 – Revised Responsibilities for Performing GMD Vulnerability Assessments
    Section 3.1.8 (8) – …implement process for obtaining GIC monitor data and geomagnetic field data…
2021 May Release – R3 – 5/25/2021 – 5/27/2021 In Flight
  NPRR974 – Capacity Insufficiency Operating Condition Notice (OCN) Transparency
  NPRR978(c) – Alignment with Amendments to PUCT Substantive Rule 25.505
  NPRR1048 – Clarification on NPRR978 Short-Term Adequacy Reports
  NPRR1051 – Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices
  SCR811 – Addition of Intra-Hour PhotoVoltaic Power Forecast to GTBD Calculation
2021 June Release Off-Cycle – 6/1/2021 In Flight
  NPRR902(b) – ERCOT Critical Energy Infrastructure Information
2021 June Release Off-Cycle – 6/11/2021 In Flight
  ECMS – Enterprise Content Management System
    Market Info & Grid Info to new platform, improved dashboards and displays, replace NoticeBuilder
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/2 – 2/4 | April 3/30 – 4/1 | May 5/25 – 5/27 | July 7/27 – 7/29 | October 10/5 – 10/7 | December 12/7 – 12/9
NPRR902(a) NOGRR195 NPRR1055 OBDRR023(a) NPRR1020 SCR804 | NPRR971 NPRR986 NPRR998 NPRR1024 NPRR1043 NOGRR213 VCMRR027 NPRR974 NPRR978(c) PGRR070 | NPRR974 NPRR978(c) NPRR1048 NPRR1051 SCR811 NPRR902(b) | NPRR902(b) NPRR905 SCR789 ECMS | OBDRR023(b) SCR781(b) | FFR Advancement (NPRR863 FFR) NPRR1015 DGR/DESR (See next slide) FFR Advancement (NPRR863 FFR) NPRR863 ECRS NPRR1015
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR902(a) – ECEII Market Participant MPIM role
NPRR902(b) – MIS links updated for ECEII reports
NPRR978(c) – Forecast Zone scope
SCR781(b) – “Add” capability
OBDRR023(a) – ERS Expenditure Limit
OBDRR023(b) – 4 Standard Contract Terms/Year
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 867, 879, 885, 918, 935(b), 936, 939, 941, 945, 962, 965, 1023, 1030, 1032, 1034, 1040, 1051, 1057 SCRs: 799, 800, 805, 809, 812 Market Guides: PGRR066
E
E
E
E
E
E
TBD Go-Live
E
Market Info & Grid Info to new platform
Improved dashboards and displays
Replace NoticeBuilder
ECMS – Nov.
Combine ERCOT.com and MIS
Improved search
New navigation
TBD Go-Lives Due to MMS/OS Delay
NPRR904, NPRR1006, OBDRR009
NPRR930
NPRR1019
1/1
ü
ü
ü
2/1
10/1
5/1
3/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
4/22
ü
6/1
ü
P
P
P
RIOO – Q4 2021
RARF Add Functionality Go-Live
6/11

## Slide 5: ESR and DGR Pre-Passport Projects
On 10/16/2020, ERCOT initiated 2 projects to deliver several Revision Requests relating to ESR and DGR
  PR353-01 BES Combo Model Implementation – potential for multiple go-lives
      Target go-live TBD – the team is still working to set release targets
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
  PR354-01 DGR/DESR Implementation (scheduled for gate to Execution phase on 6/5/2021)
      Target go-live 2021-R6 (December 2021) or 2022-R1 (February 2022)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources (DESRs)
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995 Implementation
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
ESR: Energy Storage Resource
BES: Battery Energy Storage
DGR: Distributed Generation Resource
Red text = New addition/edit since last report
ERCOT is working to define the timing to lift the DGR moratorium based on the target go-live that will be determined over the next few weeks

## Slide 6: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
LPGRR068 | Add BUSLRG and BUSLRGDG Profile Types | 2021 | 3320 | $20k-$40k, 3-6 months Impact Area: Reporting Target late 2021 start for completion after the 2/1/2022 “no earlier than” date Worked with RMS on Priority/Rank No impact to Passport
PGRR088 | Include Financial Security Amount in the Monthly Generator Interconnection Status Report | 2022 | 3510 | $20k-$40k, 3-5 months Impact Area: RIOO (Resource Integration and Ongoing Operations), Reporting Add functionality to RIOO after current effort to include “add” capability is complete Worked with ROS on Priority/Rank No impact to Passport
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3320
Next available Rank in Regulatory = 320
Options for…