## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2021-04-22
Agenda Item: | Decision / Resolution | Action Items :
March Call Notes
| No Changes were made. | The Texas SET Chair will have the notes posted to the March meeting page.
The Texas SET Chair provided the Retail Market Subcommittee (RMS) Update on the following topics.
ERCOT Extended Outage 2 PM May 1 through Midnight May 3. | The Texas SET Chair stated that ERCOT's extended outage for their release that starts May 1 at 2 PM through midnight Monday Morning May 3rd was discussed and the TDSP's offered information about how they will work Move Ins during the 2 PM to 7 PM timeframe on May 1. Centerpoint stated that they are only accepting Move Ins from May 1 2PM through 7PM. TNMP also stated that their REP portal will only process those Safety Net Move Ins for that same timeframe.
Winter Storm Update | It was mentioned that the communications issue for the ERCOT list serves was assigned to the Texas Data Transport and MarkeTrak Systems (TDTMS) working group.
ERCOT Discussion Items
Flight Update | ERCOT noted that it will be a big flight in June similar to the February Flight, but no other information is available at this time.
Texas SET Change Control Call at 10:00 AM
Change Control 2020-827: Allow Competitive Retailer to provide customer's email to TDSP. | Texas SET reached consensus to endorse this Change Control and request that the Retail Market Subcommittee (RMS) approve for a future release. | ERCOT will present this Change Control at RMS for a vote.
Change Control 2021-828: Add DTM Start and End segments to the 814_18 Establish/Delete CSA Request and the 814_19 Establish/Delete CSA Response. | Texas SET reached consensus to endorse this Change Control and request that the Retail Market Subcommittee (RMS) approve for a future release. | ERCOT will present this Change Control at RMS for a vote.
Change Control 2021-829: Add indicator for Inadvertent and Right of Rescission. | Texas SET reached consensus to endorse this Change Control and request that the Retail Market Subcommittee (RMS) approve for a future release. | ERCOT will present this Change Control at RMS for a vote.
Change Control 2021-830: Add additional Reject Codes and Reject Reasons to provide more descriptive rejects | Texas SET reached consensus to endorse this Change Control and request that the Retail Market Subcommittee (RMS) approve for a future release. | ERCOT will present this Change Control at RMS for a vote.
Change Control 2021-831: Add new REF segment in order to provide Meter Service Type | Texas SET reached consensus to endorse this Change Control and request that the Retail Market Subcommittee (RMS) approve for a future release. | ERCOT will present this Change Control at RMS for a vote.
ERCOT requested clarification for how these Change Controls will be presented to RMS. | Texas SET agreed that these Change Controls will be presented to RMS to be approved for a future release; then Texas SET will return with the Revision Requests that are needed to assign them to Version 5.0.
Discussion Items
Texas SET Enhancement Matrix | The Texas SET Chair conducted a review of the matrix and made changes where needed. The review included determining if the list needs a Retail Market Guide REvision Request (RMGRR) and/or a Nodal Protocol Revision Request (NPRR). All assignments to draft NPRRs and RMGRRs will be completed; then incorporated into one NPRR or RMGRR for submission.
Outstanding Change Controls
Final 5.0 CC Timeline | No changes were made to the existing timeline. | This will continue to be discussed at the next meeting
Centerpoint additional discussion: Additional TX SET 5.0 Enhancements Requested by CNP 03_25_21 | Texas SET continued to review the items left on the Centerpoint Energy provided document from the March meeting and made assignments as needed.
| 4. On March 3, 2021 ERCOT transmitted (503) 814_03’s that only included a comma in the EDI field for the customer name. CNP generated 814_04’s for these but they failed TX SET validation because none generated with a name. CNP manually worked to get them corrected and 814_04’s generated. We did complete the switches and sent 867_04’s for them. •Question: Should these have failed validation at ERCOT for not having a name? •ERCOT noted that they do not currently fail these as they are considered alphanumeric and would require a Texas SET guide change to have them validated. •03/25/21 Consensus of TX SET: Agreed that only a comma in the PER~IC PER02 Name field isn’t acceptable, but at this point TX SET is unable to determine what would be the best recourse for this data field since it is Free-form Alphanureric with a minimum of 1 and maximum of 60 characters. | The Texas SET members will review the requirements for the CBCI file and the Retail Market Guide (RMG); then bring suggestions back to the next meeting.
| 6. A Mass Transition (Default) population of 3 ESI IDs need to be discussed concerning what is the appropriate number of ESI IDs where all the notifications and Mass Transition processes should be initiated, hopefully it isn’t 3 ESI IDs in the future? • 03/25/21 Consensus of TX SET: After TX SET discussed with Dave Michelsen (ERCOT), Dave thought that revisions could be made to the Retail Market Guide Section 7.11 “Mass Transitions” to give ERCOT flexibility/discretion when assigning a small number of ESI IDs that would only go to the VREP(s) wouldn’t necessitate all the normally required email and market notifications. The information would only be provided to impacted TDSPs and VREPs involved into completing the transition of ESI IDs from the Defaulting CR • 04/22/21 The Texas SET members reviewed the Retail Market Guide Revision Request (RMGRR) written by Vistra; then made changes as needed. | Texas SET Leadership will send the RMGRR to ERCOT for review and feedback to be provided at the next meeting.
| 7. Competitive Retailer(s) CBCI File(s) data content unreliable, which isn’t identifiable until the critical reason this file is being provided to ERCOT is for a Mass Transition event. • 03/25/21 Consensus of TX SET: Agreed this item will require more discussion to determine what would be the best recourse long term. • 04/22/2021 Texas SET continued to review the issue requested the meeting attendees incorporate suggestions in assignment as #4 above. | The Texas SET members will review the requirements for the CBCI file and the Retail Market Guide (RMG); then bring suggestions back to the next meeting. This will be included in the suggestions for #4.
Other Business
Issues--No new Issues were discussed this month. | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | Still on Hold
Next Meeting--WebEx Only | 2021-05-19
Attendees F-T-F
Attendees Webex
Kyle Patrick NRG | Mary Do Agility CIS
Jordan Troublefield ERCOT | Angela Ghormley Calpine Corporation
Diana Rehfeldt TNMP | Carolyn Reed Centerpoint Energy
Kathryn Thurman ERCOT | Deb Belin MarketWise
Kathy Scott Centerpoint Energy | Dave Michelsen ERCOT
Jim Lee AEP | Steve Pliler TXU Energy
Sam Pak ONCOR | Jeff Chen Centerpoint Energy
Stephen Wilson TXU Energy | Sheri Wiegand TXU Energy
Lauren Damen NRG | Kim Wall Hansen Technologies
Michael Heselton Intelometry | Frank Nunes EC Infosystems
Jesse Macias AEP