## Wind Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 19INR0080 | Whitehorse Wind | Fisher | 2020-09-30 | 2018-12-05 | 2019-12-27 | Wind | WT | 418.9 | 2020 | Yes
[7 empty] | 19INR0156 | Aviator Wind | Coke | 2020-10-01 | 2019-02-14 | 2020-06-24 | Wind | WT | 525 | 2020 | Yes
[7 empty] | 19INR0163 | Sage Draw Wind | Lynn | 2020-12-31 | 2018-01-03 | 2019-12-12 | Wind | WT | 338 | 2020 | Yes
[7 empty] | 19INR0174 | Elbow Creek repower | Howard | 2021-02-12 | 2007-11-30 | 2019-06-27 | Wind | WT | 0 | 2021 | No
[7 empty] | 18INR0033 | Oveja Wind | Irion | 2021-03-01 | 2018-07-24 | 2019-04-05 | Wind | WT | 300 | 2021 | Yes
[7 empty] | 17INR0035 | Las Majadas Wind | Willacy | 2021-04-23 | 2018-04-13 | 2020-10-21 | Wind | WT | 272.6 | 2021 | Yes
[7 empty] | 19INR0038 | High Lonesome Wind | Crockett | 2021-04-29 | 2018-04-17 | 2019-11-26 | Wind | WT | 449.5 | 2021 | Yes
[7 empty] | 17INR0031 | Espiritu Wind | Cameron | 2021-04-30 | 2020-01-29 | 2020-08-10 | Wind | WT | 25.2 | 2021 | Yes
[7 empty] | 18INR0038 | Barrow Ranch Wind | Andrews | 2021-04-30 | 2018-06-26 | 2020-02-26 | Wind | WT | 160 | 2021 | Yes
[7 empty] | 20INR0042 | Chalupa Wind | Cameron | 2021-04-30 | 2018-09-28 | 2020-08-10 | Wind | WT | 174 | 2021 | Yes
[7 empty] | 20INR0262 | High Lonesome Wind Phase II | Crockett | 2021-04-30 | 2019-07-22 | 2020-02-28 | Wind | WT | 50.6 | 2021 | Yes
[7 empty] | 17INR0027b | Coyote Wind | Scurry | 2021-05-07 | 2016-08-09 | 2020-11-25 | Wind | WT | 242.6 | 2021 | Yes
[7 empty] | 18INR0059 | East Raymond Wind (El Rayo) | Willacy | 2021-05-27 | 2018-09-18 | 2020-10-06 | Wind | WT | 201.6 | 2021 | Yes
[7 empty] | 18INR0064 | Silver Star repower | Eastland | 2021-05-28 | 2018-10-16 | 2020-07-28 | Wind | WT | -7.2 | 2021 | Yes
[7 empty] | 19INR0120 | Sherbino II Wind repower | Pecos | 2021-05-28 | 2008-02-28 | 2020-06-09 | Wind | WT | -18 | 2021 | Yes
[7 empty] | 16INR0111 | Venado Wind | Starr | 2021-05-31 | 2018-12-22 | 2020-12-08 | Wind | WT | 201.6 | 2021 | Yes
[7 empty] | 17INR0025 | Reloj Del Sol Wind | Zapata | 2021-05-31 | 2018-12-21 | 2020-12-29 | Wind | WT | 209.4 | 2021 | Yes
[7 empty] | 19INR0053 | Hidalgo II Wind | Hidalgo | 2021-05-31 | 2019-04-25 | 2019-12-10 | Wind | WT | 51 | 2021 | Yes
[7 empty] | 20INR0019 | Trinity Hills Wind repower | Young | 2021-06-16 | 2018-10-17 | 2020-05-22 | Wind | WT | -27 | 2021 | No
[7 empty] | 20INR0033 | WILDWIND | Cooke | 2021-06-18 | 2020-02-21 | 2021-02-10 | Wind | WT | 180.08 | 2021 | Yes
[7 empty] | 19INR0112 | Cranel Wind | Refugio | 2021-06-21 | 2018-10-12 | 2020-05-19 | Wind | WT | 220 | 2021 | Yes
[7 empty] | 11INR0062 | Shaffer Wind | Nueces | 2021-06-30 | 2013-07-02 | 2019-04-05 | Wind | WT | 226 | 2021 | Yes
[7 empty] | 17INR0069 | Trent repower | Nolan | 2021-06-30 | 2018-10-19 | 2019-05-09 | Wind | WT | 6.4 | 2021 | No
[7 empty] | 17INR0070 | Desert Sky repower | Pecos | 2021-06-30 | 2018-10-18 | 2019-09-06 | Wind | WT | 7.2 | 2021 | Yes
[7 empty] | 16INR0081 | Mesteno Wind | Starr | 2021-07-01 | 2018-04-25 | 2019-12-12 | Wind | WT | 201.6 | 2021 | Yes
[7 empty] | 20INR0052 | Griffin Trail Wind | Knox | 2021-07-01 | 2019-03-04 |  | Wind | WT | 225.6 | 2021 | Yes
[7 empty] | 21INR0449 | Panther Creek III Repower | Howard | 2021-07-01 | 2009-03-19 | 2021-04-07 | Wind | WT | 15.96 | 2021 | No
[7 empty] | 19INR0100 | Prairie Hill Wind | McLennan | 2021-07-30 | 2018-09-17 | 2020-11-12 | Wind | WT | 300 | 2021 | Yes
[7 empty] | 19INR0128 | White Mesa Wind | Crockett | 2021-07-30 | 2018-12-13 | 2021-05-12 | Wind | WT | 152.3 | 2021 | Yes
[7 empty] | 20INR0088 | West Raymond (El Trueno) Wind | Willacy | 2021-07-30 | 2019-05-20 | 2021-01-20 | Wind | WT | 239.8 | 2021 | Yes
[7 empty] | 16INR0086 | Cactus Flats Wind | Concho | 2021-07-31 | 2017-03-15 | 2018-06-11 | Wind | WT | 148.4 | 2021 | Yes
[7 empty] | 17INR0068 | Sweetwater 2 repower | Nolan | 2021-07-31 | 2003-06-27 | 2017-12-20 | Wind | WT | 7.3 | 2021 | No
[7 empty] | 18INR0073 | Sweetwater 1 repower | Nolan | 2021-07-31 | 2002-10-23 |  | Wind | WT | 3 | 2021 | No
[7 empty] | 15INR0064b | Harald (BearKat Wind B) | Glasscock | 2021-08-03 | 2018-05-30 | 2020-05-12 | Wind | WT | 162.1 | 2021 | Yes
[7 empty] | 20INR0142 | Ajax Wind | Wilbarger | 2021-08-13 | 2020-07-14 |  | Wind | WT | 366.6 | 2021 | Yes
[7 empty] | 20INR0045 | Maverick Creek I Wind | Concho | 2021-09-30 | 2018-07-30 | 2020-09-01 | Wind | WT | 373.2 | 2021 | Yes
[7 empty] | 20INR0046 | Maverick Creek II Wind | Concho | 2021-09-30 | 2018-07-30 | 2020-11-02 | Wind | WT | 118.8 | 2021 | Yes
[7 empty] | 20INR0068 | Blackjack Creek Wind | Bee | 2021-09-30 | 2019-10-24 |  | Wind | WT | 240.5 | 2021 | Yes
[7 empty] | 20INR0083 | Baird North Wind | Callahan | 2021-09-30 | 2019-05-31 |  | Wind | WT | 350 | 2021 | Yes
[7 empty] | 18INR0031 | Maryneal Wind | Nolan | 2021-10-01 | 2020-01-31 | 2021-04-23 | Wind | WT | 182.4 | 2021 | Yes
[7 empty] | 19INR0145 | Aquilla Lake Wind | Hill | 2021-11-12 | 2020-06-30 |  | Wind | WT | 202 | 2021 | Yes
[7 empty] | 20INR0256 | Aquilla Lake 2 Wind | Hill | 2021-11-12 | 2020-06-30 |  | Wind | WT | 100 | 2021 | Yes
[7 empty] | 16INR0085 | Priddy Wind | Mills | 2021-11-30 | 2020-08-13 |  | Wind | WT | 302.4 | 2021 | Yes
[7 empty] | 17INR0052 | Horse13 CallD repower | Taylor | 2021-11-30 | 2019-05-22 | 2021-03-16 | Wind | WT | 44 | 2021 | Yes
[7 empty] | 21INR0521 | White Mesa 2 Wind | Coke | 2021-11-30 | 2018-12-13 |  | Wind | WT | 348 | 2021 | Yes
[7 empty] | 15INR0034 | El Algodon Alto W | San Patricio | 2021-12-15 | 2020-04-02 |  | Wind | WT | 201 | 2021 | Yes
[7 empty] | 19INR0052 | TG East Wind | Knox | 2021-12-15 | 2018-10-22 |  | Wind | WT | 336 | 2021 | Yes
[7 empty] | 21INR0387 | Anchor Wind | Eastland | 2021-12-24 | 2020-11-30 |  | Wind | WT | 114.9 | 2021 | Yes
[7 empty] | 21INR0539 | Anchor Wind II | Eastland | 2021-12-24 | 2020-11-30 |  | Wind | WT | 148.02 | 2021 | Yes
[7 empty] | 17INR0054 | Capricorn I & III repower | Sterling | 2021-12-31 | 2006-11-14 | 2021-03-04 | Wind | WT | 32 | 2021 | No
[7 empty] | 17INR0061 | Capricorn IV repower | Sterling | 2021-12-31 | 2008-01-15 | 2020-08-19 | Wind | WT | 9 | 2021 | No
[7 empty] | 18INR0069 | Indian Mesa repower | Pecos | 2021-12-31 | 2018-12-04 | 2018-11-02 | Wind | WT | 0 | 2021 | No
[7 empty] | 18INR0079 | Woodward I repower | Pecos | 2021-12-31 | 2018-12-12 | 2019-11-13 | Wind | WT | 0 | 2021 | Yes
[7 empty] | 18INR0080 | Woodward 2 repower | Pecos | 2021-12-31 | 2018-12-18 | 2018-12-19 | Wind | WT | 0 | 2021 | Yes
[7 empty] | 20INR0120 | Vortex Wind | Throckmorton | 2021-12-31 | 2020-12-01 |  | Wind | WT | 350.15 | 2021 | Yes
[7 empty] | 21INR0263 | Monarch Creek Wind | Throckmorton | 2021-12-31 | 2020-08-24 |  | Wind | WT | 209 | 2021 | No
[7 empty] | 21INR0467 | Apogee Wind | Haskell | 2021-12-31 | 2020-03-10 |  | Wind | WT | 393.24 | 2021 | Yes
[7 empty] | 20INR0129 | Foxtrot Wind | Bee | 2022-04-01 | 2020-05-05 |  | Wind | WT | 268.2 | 2022 | Yes
[7 empty] | 20INR0217 | CAROL wind | Potter | 2022-05-30 | 2020-09-11 |  | Wind | WT | 169.2 | 2022 | No
[7 empty] | 18INR0030 | Canyon Wind | Scurry | 2022-06-01 | 2018-09-20 |  | Wind | WT | 201.8 | 2022 | Yes
[7 empty] | 14INR0033 | Goodnight Wind | Armstrong | 2022-07-23 | 2018-03-07 |  | Wind | WT | 506.6 | 2022 | No
[7 empty] | 16INR0112 | Loma Pinta Wind | La Salle | 2022-09-01 | 2017-12-13 |  | Wind | WT | 200 | 2022 | No
[7 empty] | 20INR0097 | El Suaz Ranch | Willacy | 2022-09-30 | 2021-01-27 |  | Wind | WT | 301.74 | 2022 | Yes
[7 empty] | 18INR0043 | Edmondson Ranch Wind | Glasscock | 2022-10-31 | 2017-09-28 |  | Wind | WT | 293.28 | 2022 | Yes
[7 empty] | 21INR0005 | Hutt Wind | Midland | 2022-11-16 | 2020-05-26 |  | Wind | WT | 336 | 2022 | No
[7 empty] | 19INR0117 | Roadrunner Crossing Wind | Eastland | 2022-12-15 | 2020-04-17 |  | Wind | WT | 200.2 | 2022 | Yes
[7 empty] | 16INR0033 | Hart Wind | Castro | 2022-12-31 | 2018-08-06 |  | Wind | WT | 151.5 | 2022 | No
[7 empty] | 19INR0022 | Monte Alto I | Willacy | 2022-12-31 | 2020-02-13 |  | Wind | WT | 223.8 | 2022 | No
[7 empty] | 22INR0326 | Inertia Wind | Haskell | 2022-12-31 | 2021-05-04 |  | Wind | WT | 350 | 2022 | No
[7 empty] | 19INR0099a | Kontiki 1 Wind (ERIK) | Glasscock | 2023-03-01 | 2018-05-07 |  | Wind | WT | 250.1 | 2023 | Yes
[7 empty] | 19INR0099b | Kontiki 2 Wind (ERNEST) | Glasscock | 2023-03-01 | 2018-05-07 |  | Wind | WT | 250.1 | 2023 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | 20INR0249 | Appaloosa Run Wind_ | Upton | 2023-03-01 | 2021-04-12 |  | Wind | WT | 175 | 2023 | Yes
2000 | 160.37 | 160.37 | 0 | 0 | 0 | 0 | 18INR0068 | Loraine Windpark Phase III | Mitchell | 2023-05-10 | 2018-04-10 |  | Wind | WT | 100 | 2023 | Yes
2001 | 859.29 | 859.29 | 0 | 0 | 0 | 0
2002 | 1019.79 | 1019.79 | 0 | 0 | 0 | 0
2003 | 1217.29 | 1217.29 | 0 | 0 | 0 | 0
2004 | 1325.29 | 1325.29 | 0 | 0 | 0 | 0
2005 | 1902.69 | 1902.69 | 0 | 0 | 0 | 0
2006 | 2633.39 | 2633.39 | 0 | 0 | 0 | 0
2007 | 4203.41 | 4203.41 | 0 | 0 | 0 | 0
2008 | 8101.01 | 8101.01 | 0 | 0 | 0 | 0
2009 | 9007.57 | 9007.57 | 0 | 0 | 0 | 0
2010 | 9458.49 | 9458.49 | 0 | 0 | 0 | 0
2011 | 9603.49 | 9603.49 | 0 | 0 | 0 | 0
2012 | 10698.35 | 10698.35 | 0 | 0 | 0 | 0
2013 | 11100.05 | 11100.05 | 0 | 0 | 0 | 0
2014 | 12728.93 | 12728.93 | 0 | 0 | 0 | 0
2015 | 15857.48 | 15857.48 | 0 | 0 | 0 | 0
2016 | 17662.45 | 17662.45 | 0 | 0 | 0 | 0
2017 | 20697.84 | 20697.84 | 0 | 0 | 0 | 0
2018 | 21777 | 21777 | 0 | 0 | 0 | 0
2019 | 23860 | 23860 | 0 | 0 | 0 | 0
2020 | 25121 | 25121 | 0 | 0 | 0 | 0
2021 | 35726.28 | 25642.28 | 6194 | 3678 | 212 | 0
2022 | 38929.35 | 25642.28 | 6194.34 | 4943.63 | 2149.1 | 0
2023 | 39704.55 | 25642.28 | 6194.34 | 5718.83 | 2149.1 | 0

## Solar Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 20INR0219 | Eunice Solar | Andrews | 2021-03-08 | 2019-12-11 | 2020-12-01 | Solar | PV | 426.7 | 2021 | Yes
[7 empty] | 18INR0062 | Wagyu Solar | Brazoria | 2021-04-01 | 2019-06-03 | 2020-05-22 | Solar | PV | 120 | 2021 | Yes
[7 empty] | 18INR0045 | Misae Solar | Childress | 2021-05-14 | 2018-07-18 | 2020-01-16 | Solar | PV | 240.8 | 2021 | Yes
[7 empty] | 18INR0055 | Long Draw Solar | Borden | 2021-05-31 | 2018-08-16 | 2020-11-20 | Solar | PV | 226.73 | 2021 | Yes
[7 empty] | 19INR0081 | Anson Solar 1 | Jones | 2021-05-31 | 2019-06-05 | 2020-12-30 | Solar | PV | 201.53 | 2021 | Yes
[7 empty] | 19INR0151 | Impact Solar | Lamar | 2021-05-31 | 2019-07-02 | 2020-09-02 | Solar | PV | 198.55 | 2021 | Yes
[7 empty] | 20INR0054 | Taygete Solar | Pecos | 2021-06-04 | 2018-10-26 | 2020-12-07 | Solar | PV | 255.07 | 2021 | Yes
[7 empty] | 20INR0037 | Coniglio Solar | Fannin | 2021-06-15 | 2019-08-03 |  | Solar | PV | 125.68 | 2021 | Yes
[7 empty] | 21INR0229 | Prospero Solar II | Andrews | 2021-06-28 | 2020-01-17 | 2021-04-16 | Solar | PV | 250 | 2021 | Yes
[7 empty] | 15INR0044 | Corazon Solar | Webb | 2021-06-30 | 2020-01-09 |  | Solar | PV | 202.64 | 2021 | Yes
[7 empty] | 19INR0044 | Lily Solar | Kaufman | 2021-06-30 | 2019-03-29 | 2021-04-26 | Solar | PV | 147.63 | 2021 | Yes
[7 empty] | 19INR0088 | Aragorn Solar | Culberson | 2021-06-30 | 2018-05-31 |  | Solar | PV | 187.2 | 2021 | Yes
[7 empty] | 20INR0032 | Titan Solar | Culberson | 2021-06-30 | 2019-02-04 | 2021-03-18 | Solar | PV | 270 | 2021 | Yes
[7 empty] | 15INR0090 | East Blackland Solar | Travis | 2021-07-15 | 2017-06-13 | 2021-04-13 | Solar | PV | 144 | 2021 | Yes
[7 empty] | 21INR0501 | Juno Solar (Phase II) | Borden | 2021-07-15 | 2018-12-22 | 2021-05-25 | Solar | PV | 147.09 | 2021 | Yes
[7 empty] | 17INR0020b | RE Maplewood 2b Solar | Pecos | 2021-07-29 | 2019-05-06 | 2021-03-29 | Solar | PV | 28 | 2021 | Yes
[7 empty] | 18INR0060 | Brightside Solar | Bee | 2021-07-30 | 2020-06-11 |  | Solar | PV | 50 | 2021 | Yes
[7 empty] | 19INR0091 | Phoenix Solar | Fannin | 2021-08-10 | 2019-10-22 | 2021-04-13 | Solar | PV | 82.3 | 2021 | Yes
[7 empty] | 17INR0020a | RE Maplewood 2a Solar | Pecos | 2021-08-16 | 2019-05-06 | 2021-04-16 | Solar | PV | 222 | 2021 | Yes
[7 empty] | 21INR0477 | Azure Sky Solar | Haskell | 2021-08-20 | 2020-04-01 |  | Solar | PV | 228.4 | 2021 | Yes
[7 empty] | 20INR0130 | Plainview Solar | Wharton | 2021-09-02 | 2020-05-29 |  | Solar | PV | 514 | 2021 | Yes
[7 empty] | 21INR0233 | Taygete II Solar | Pecos | 2021-09-23 | 2019-03-27 |  | Solar | PV | 203.8 | 2021 | Yes
[7 empty] | 19INR0121 | Galloway Solar | Concho | 2021-10-10 | 2019-12-20 | 2021-05-25 | Solar | PV | 250 | 2021 | Yes
[7 empty] | 20INR0081 | Strategic Solar 1 | Ellis | 2021-11-05 | 2020-01-13 |  | Solar | PV | 136.85 | 2021 | Yes
[7 empty] | 20INR0082 | Vision Solar 1 | Navarro | 2021-11-09 | 2020-01-13 |  | Solar | PV | 129.24 | 2021 | Yes
[7 empty] | 21INR0031 | Indigo Solar | Fisher | 2021-12-15 | 2020-10-15 |  | Solar | PV | 125 | 2021 | No
[7 empty] | 20INR0255 | Dawn Solar | Deaf Smith | 2021-12-21 | 2021-01-04 |  | Solar | PV | 515.66 | 2021 | No
[7 empty] | 21INR0276 | Elara Solar | Frio | 2021-12-27 | 2019-07-12 |  | Solar | PV | 132.4 | 2021 | Yes
[7 empty] | 19INR0045 | Rayos Del Sol | Cameron | 2021-12-31 | 2018-11-06 |  | Solar | PV | 137.45 | 2021 | Yes
[7 empty] | 20INR0101 | Westoria Solar | Brazoria | 2021-12-31 | 2020-03-20 |  | Solar | PV | 203.35 | 2021 | Yes
[7 empty] | 21INR0213 | Vancourt Solar | Cameron | 2021-12-31 | 2020-06-11 |  | Solar | PV | 45.73 | 2021 | Yes
[7 empty] | 15INR0059 | Emerald Grove Solar | Pecos | 2022-01-29 | 2017-12-04 |  | Solar | PV | 108 | 2022 | Yes
[7 empty] | 19INR0103 | Rodeo Solar | Andrews | 2022-01-30 | 2019-08-20 |  | Solar | PV | 200 | 2022 | Yes
[7 empty] | 19INR0001 | Texas Solar Nova | Kent | 2022-01-31 | 2019-07-01 |  | Solar | PV | 252.2 | 2022 | Yes
[7 empty] | 19INR0085 | Blue Jay Solar | Grimes | 2022-01-31 | 2020-10-26 |  | Solar | PV | 141.05 | 2022 | Yes
[7 empty] | 21INR0538 | Blue Jay Solar II | Grimes | 2022-01-31 | 2020-10-26 |  | Solar | PV | 68.95 | 2022 | Yes
[7 empty] | 21INR0384 | Concho Valley Solar | Tom Green | 2022-03-01 | 2020-09-28 |  | Solar | PV | 159.8 | 2022 | Yes
[7 empty] | 21INR0406 | Old 300 Solar Center | Fort Bend | 2022-03-15 | 2020-04-16 |  | Solar | PV | 438.75 | 2022 | Yes
[7 empty] | 21INR0221 | Samson Solar 1 | Lamar | 2022-03-31 | 2020-08-26 |  | Solar | PV | 250 | 2022 | Yes
[7 empty] | 21INR0413 | Big Star Solar | Bastrop | 2022-03-31 | 2020-10-02 |  | Solar | PV | 220.61 | 2022 | Yes
[7 empty] | 21INR0491 | Samson Solar 3 | Lamar | 2022-03-31 | 2020-08-27 |  | Solar | PV | 250 | 2022 | Yes
[7 empty] | 19INR0035 | Norton Solar | Runnels | 2022-04-01 | 2019-06-20 |  | Solar | PV | 125 | 2022 | Yes
[7 empty] | 21INR0431 | Galloway 2 Solar | Concho | 2022-04-01 | 2019-12-20 |  | Solar | PV | 110 | 2022 | Yes
[7 empty] | 22INR0205 | Sbranch Solar | Wharton | 2022-04-01 | 2020-07-26 |  | Solar | PV | 230 | 2022 | Yes
[7 empty] | 18INR0053 | Fort Bend Solar | Fort Bend | 2022-04-26 | 2019-06-30 |  | Solar | PV | 240 | 2022 | Yes
[7 empty] | 20INR0026 | Longbow Solar | Brazoria | 2022-05-01 | 2021-01-06 |  | Solar | PV | 80 | 2022 | Yes
[7 empty] | 20INR0248 | Second Division Solar | Brazoria | 2022-05-01 | 2020-10-14 |  | Solar | PV | 100 | 2022 | No
[7 empty] | 22INR0352 | Sparta Solar | Bee | 2022-05-02 | 2020-08-14 |  | Solar | PV | 256 | 2022 | Yes
[7 empty] | 21INR0341 | Space City Solar | Wharton | 2022-05-06 | 2021-01-06 |  | Solar | PV | 609.74 | 2022 | Yes
[7 empty] | 20INR0266 | Tres Bahias Solar | Calhoun | 2022-05-21 | 2020-08-07 |  | Solar | PV | 195 | 2022 | Yes
[7 empty] | 21INR0019 | Zier Solar | Kinney | 2022-05-25 | 2020-10-22 |  | Solar | PV | 160 | 2022 | No
[7 empty] | 20INR0208 | Signal Solar | Hunt | 2022-05-30 | 2020-10-23 |  | Solar | PV | 50 | 2022 | No
[7 empty] | 20INR0214 | Noble Solar | Denton | 2022-05-30 | 2020-10-10 |  | Solar | PV | 279 | 2022 | No
[7 empty] | 21INR0274 | Carol Solar | Potter | 2022-05-30 | 2020-09-11 |  | Solar | PV | 223.2 | 2022 | No
[7 empty] | 20INR0222 | Tyson Nick Solar | Lamar | 2022-05-31 | 2020-08-28 |  | Solar | PV | 90 | 2022 | No
[7 empty] | 21INR0389 | Red-tailed Hawk Solar | Wharton | 2022-05-31 | 2020-08-28 |  | Solar | PV | 355.27 | 2022 | Yes
[7 empty] | 22INR0257 | Corazon Solar Phase II | Webb | 2022-05-31 | 2020-08-04 |  | Solar | PV | 203.9 | 2022 | No
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | 19INR0042 | Long Point Solar | Brazoria | 2022-06-01 | 2019-10-24 |  | Solar | PV | 101.25 | 2022 | No
2010 | 15 | 15 | 0 | 0 | 0 | 0 | 20INR0098 | Danciger Solar | Brazoria | 2022-06-01 | 2020-03-20 |  | Solar | PV | 203.2 | 2022 | Yes
2011 | 15 | 15 | 0 | 0 | 0 | 0 | 21INR0278 | Fighting Jays Solar | Fort Bend | 2022-06-01 | 2020-06-22 |  | Solar | PV | 351.29 | 2022 | Yes
2012 | 72.3 | 72.3 | 0 | 0 | 0 | 0 | 22INR0202 | Delilah Solar 1 | Lamar | 2022-06-01 | 2020-12-22 |  | Solar | PV | 300 | 2022 | Yes
2013 | 121.2 | 121.2 | 0 | 0 | 0 | 0 | 18INR0050 | Mustang Creek Solar | Jackson | 2022-06-30 | 2019-01-04 |  | Solar | PV | 152.25 | 2022 | Yes
2014 | 168.7 | 168.7 | 0 | 0 | 0 | 0 | 19INR0155 | Morrow Lake Solar | Frio | 2022-06-30 | 2019-08-29 |  | Solar | PV | 204 | 2022 | Yes
2015 | 289.28 | 289.28 | 0 | 0 | 0 | 0 | 21INR0428 | Nabatoto Solar North | Leon | 2022-06-30 | 2021-02-26 |  | Solar | PV | 400 | 2022 | No
2016 | 565.78 | 565.78 | 0 | 0 | 0 | 0 | 20INR0205 | Roseland Solar | Falls | 2022-07-14 | 2020-12-10 |  | Solar | PV | 513 | 2022 | No
2017 | 1067.78 | 1067.78 | 0 | 0 | 0 | 0 | 20INR0203 | Pine Forest Solar | Hopkins | 2022-07-31 | 2020-07-29 |  | Solar | PV | 284.29 | 2022 | No
2018 | 1856.78 | 1856.78 | 0 | 0 | 0 | 0 | 19INR0073 | Shakes Solar | Zavala | 2022-08-01 | 2018-10-26 |  | Solar | PV | 206 | 2022 | Yes
2019 | 2281.38 | 2281.38 | 0 | 0 | 0 | 0 | 19INR0131 | Cutlass Solar | Fort Bend | 2022-08-01 | 2020-09-23 |  | Solar | PV | 300 | 2022 | No
2020 | 3973.5 | 3973.5 | 0 | 0 | 0 | 0 | 20INR0050 | Castro Solar | Castro | 2022-09-15 | 2020-11-30 |  | Solar | PV | 222.95 | 2022 | No
2021 | 10542.65 | 4394.51 | 3210.4 | 2296.74 | 641 | 0 | 20INR0080 | Frye Solar | Swisher | 2022-09-30 | 2021-02-06 |  | Solar | PV | 500 | 2022 | No
2022 | 22674.59 | 4394.51 | 3210.4 | 9453 | 5616.68 | 0 | 21INR0205 | Radian Solar | Brown | 2022-11-30 | 2021-01-08 |  | Solar | PV | 374.4 | 2022 | Yes
2023 | 28394.82 | 4394.51 | 3210.4 | 11985.91 | 8804 | 0 | 19INR0041 | Myrtle Solar | Brazoria | 2022-12-15 | 2019-11-13 |  | Solar | PV | 240 | 2022 | Yes
[7 empty] | 20INR0263 | Myrtle Solar II | Brazoria | 2022-12-15 | 2021-02-01 |  | Solar | PV | 100 | 2022 | No
[7 empty] | 22INR0242 | Bright Arrow Solar | Hopkins | 2022-12-15 | 2021-02-18 |  | Solar | PV | 324.72 | 2022 | Yes
[7 empty] | 19INR0169 | Sun Valley Solar | Hill | 2022-12-29 | 2020-03-15 |  | Solar | PV | 252 | 2022 | No
[7 empty] | 20INR0210 | Hopkins Solar | Hopkins | 2022-12-29 | 2020-09-25 |  | Solar | PV | 252 | 2022 | No
[7 empty] | 20INR0216 | Starr Solar Ranch | Starr | 2022-12-30 | 2020-10-01 |  | Solar | PV | 135.99 | 2022 | Yes
[7 empty] | 21INR0391 | Grandslam Solar | Atascosa | 2022-12-30 | 2021-01-29 |  | Solar | PV | 228.23 | 2022 | No
[7 empty] | 21INR0421 | Armadillo Solar | Navarro | 2022-12-31 | 2021-02-02 |  | Solar | PV | 204 | 2022 | No
[7 empty] | 22INR0254 | Pisgah Ridge Solar | Navarro | 2022-12-31 | 2021-01-27 |  | Solar | PV | 253.85 | 2022 | No
[7 empty] | 22INR0360 | Jade Solar | Scurry | 2022-12-31 | 2021-01-22 |  | Solar | PV | 374.4 | 2022 | Yes
[7 empty] | 22INR0374 | Inertia Solar | Haskell | 2022-12-31 | 2021-05-04 |  | Solar | PV | 258.35 | 2022 | No
[7 empty] | 19INR0134 | Cottonwood Bayou Solar | Brazoria | 2023-01-01 | 2019-11-13 |  | Solar | PV | 150 | 2023 | No
[7 empty] | 21INR0228 | Cottonwood Bayou Solar II | Brazoria | 2023-01-01 | 2021-03-25 |  | Solar | PV | 200 | 2023 | No
[7 empty] | 19INR0093 | Solemio | Hopkins | 2023-01-10 | 2020-10-22 |  | Solar | PV | 81.4 | 2023 | No
[7 empty] | 21INR0323 | Spanish Crown | Falls | 2023-02-10 | 2021-01-13 |  | Solar | PV | 103.1 | 2023 | Yes
[7 empty] | 21INR0434 | Golinda Solar | Falls | 2023-02-10 | 2021-03-21 |  | Solar | PV | 103.1 | 2023 | Yes
[7 empty] | 21INR0021 | Green Holly Solar | Dawson | 2023-03-31 | 2020-05-19 |  | Solar | PV | 413.6 | 2023 | No
[7 empty] | 21INR0351 | 7V Solar | Fayette | 2023-03-31 | 2020-09-01 |  | Solar | PV | 246.3 | 2023 | No
[7 empty] | 22INR0223 | Eiffel Solar | Lamar | 2023-03-31 | 2021-03-19 |  | Solar | PV | 200 | 2023 | No
[7 empty] | 22INR0412 | Andromeda Solar | Scurry | 2023-03-31 | 2021-04-01 |  | Solar | PV | 374.4 | 2023 | No
[7 empty] | 20INR0053 | Bravepost Solar | Tom Green | 2023-05-31 | 2019-10-30 |  | Solar | PV | 200 | 2023 | Yes
[7 empty] | 20INR0143 | Soda Lake Solar 2 | Crane | 2023-05-31 | 2018-08-20 |  | Solar | PV | 202.99 | 2023 | No
[7 empty] | 20INR0236 | Old Hickory Solar | Jackson | 2023-05-31 | 2020-06-30 |  | Solar | PV | 206 | 2023 | Yes
[7 empty] | 16INR0049 | Nazareth Solar | Castro | 2023-06-01 | 2018-05-10 |  | Solar | PV | 201 | 2023 | No
[7 empty] | 21INR0220 | Maleza Solar | Wharton | 2023-06-01 | 2021-01-27 |  | Solar | PV | 254.94 | 2023 | No
[7 empty] | 20INR0069 | Danish Fields Solar | Wharton | 2023-06-15 | 2020-02-24 |  | Solar | PV | 201 | 2023 | Yes
[7 empty] | 21INR0016 | Danish Fields II Solar | Wharton | 2023-06-15 | 2020-02-24 |  | Solar | PV | 201 | 2023 | Yes
[7 empty] | 21INR0017 | Danish Fields III Solar | Wharton | 2023-06-15 | 2020-02-24 |  | Solar | PV | 201 | 2023 | Yes
[7 empty] | 21INR0226 | Equinox Solar 1 | Starr | 2023-06-30 | 2021-01-28 |  | Solar | PV | 200 | 2023 | No
[7 empty] | 21INR0490 | Samson Solar 2 | Lamar | 2023-06-30 | 2020-08-27 |  | Solar | PV | 200 | 2023 | Yes
[7 empty] | 22INR0203 | Delilah Solar 2 | Lamar | 2023-06-30 | 2020-12-22 |  | Solar | PV | 310 | 2023 | Yes
[7 empty] | 23INR0042 | Delilah Solar 3 | Lamar | 2023-06-30 | 2020-12-22 |  | Solar | PV | 200 | 2023 | Yes
[7 empty] | 23INR0060 | Delilah Solar 4 | Lamar | 2023-06-30 | 2020-12-22 |  | Solar | PV | 90 | 2023 | Yes
[7 empty] | 20INR0091 | Misae Solar II | Childress | 2023-07-31 | 2019-02-21 |  | Solar | PV | 517.35 | 2023 | Yes
[7 empty] | 21INR0022 | Red Holly Solar | Dawson | 2023-08-01 | 2020-10-19 |  | Solar | PV | 260 | 2023 | No
[7 empty] | 20INR0241 | Crowded Star Solar | Jones | 2023-10-23 | 2019-12-17 |  | Solar | PV | 217.6 | 2023 | No
[7 empty] | 22INR0274 | Crowded Star Solar II | Jones | 2023-10-23 | 2019-12-17 |  | Solar | PV | 185 | 2023 | No

## Battery Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 20INR0220 | Eunice Storage | Andrews | 2021-03-08 | 2019-12-11 | 2020-12-01 | Battery | BA | 40.26 | 2021 | Yes
[7 empty] | 21INR0364 | Gambit Batt | Brazoria | 2021-06-01 | 2020-05-28 | 2021-04-12 | Battery | BA | 102.4 | 2021 | Yes
[7 empty] | 21INR0476 | Azure Sky BESS | Haskell | 2021-06-01 | 2020-04-01 |  | Battery | BA | 77.6 | 2021 | Yes
[7 empty] | 21INR0365 | Bat Cave Energy Storage | Mason | 2021-06-18 | 2020-02-21 |  | Battery | BA | 100.49 | 2021 | Yes
[7 empty] | 20INR0276 | North Fork Energy Storage | Williamson | 2021-06-25 | 2020-04-28 | 2021-04-16 | Battery | BA | 100.49 | 2021 | Yes
[7 empty] | 20INR0294 | Lily Storage | Kaufman | 2021-06-30 | 2020-07-14 | 2021-04-30 | Battery | BA | 51.74 | 2021 | Yes
[7 empty] | 19INR0176 | Roughneck Storage | Brazoria | 2021-07-01 | 2020-05-13 |  | Battery | BA | 50 | 2021 | Yes
[7 empty] | 20INR0089 | Chisholm Grid | Tarrant | 2021-07-23 | 2019-08-16 |  | Battery | BA | 101.7 | 2021 | Yes
[7 empty] | 21INR0496 | Flower Valley II Batt | Reeves | 2021-08-01 | 2021-01-12 |  | Battery | BA | 100.98 | 2021 | Yes
[7 empty] | 21INR0497 | Swoose II | Ward | 2021-08-01 | 2021-01-12 |  | Battery | BA | 100.98 | 2021 | Yes
[7 empty] | 21INR0510 | Crossett Power Batt | Crane | 2021-08-01 | 2020-08-05 |  | Battery | BA | 203 | 2021 | Yes
[7 empty] | 21INR0357 | SP TX-12B BESS | Upton | 2021-09-01 | 2020-05-01 |  | Battery | BA | 25.12 | 2021 | Yes
[7 empty] | 20INR0291 | Silicon Hill Storage | Travis | 2021-09-09 | 2020-03-27 |  | Battery | BA | 104.62 | 2021 | Yes
[7 empty] | 21INR0460 | Republic Road Storage | Robertson | 2021-10-29 | 2020-10-29 |  | Battery | BA | 51.75 | 2021 | Yes
[7 empty] | 21INR0474 | Anchor BESS | Eastland | 2021-12-24 | 2021-03-15 |  | Battery | BA | 71.45 | 2021 | Yes
[7 empty] | 21INR0473 | Vortex BESS | Throckmorton | 2021-12-31 | 2021-04-23 |  | Battery | BA | 121.83 | 2021 | Yes
[7 empty] | 21INR0244 | Madero Grid | Hidalgo | 2022-01-13 | 2019-12-06 |  | Battery | BA | 101.52 | 2022 | Yes
[7 empty] | 21INR0479 | Endurance Park Storage | Scurry | 2022-01-17 | 2021-02-13 |  | Battery | BA | 52.25 | 2022 | No
[7 empty] | 21INR0522 | Ignacio Grid | Hidalgo | 2022-03-03 | 2020-10-27 |  | Battery | BA | 101.52 | 2022 | Yes
[7 empty] | 20INR0281 | Queen BESS | Upton | 2022-05-06 | 2020-08-06 |  | Battery | BA | 51.06 | 2022 | No
[7 empty] | 22INR0325 | BRP Dickens BESS | Dickens | 2022-05-30 | 2020-11-03 |  | Battery | BA | 202.33 | 2022 | Yes
[7 empty] | 20INR0280 | High Lonesome BESS | Crockett | 2022-06-01 | 2020-08-26 |  | Battery | BA | 51.06 | 2022 | No
[7 empty] | 21INR0281 | Byrd Ranch Storage | Brazoria | 2022-06-01 | 2020-12-14 |  | Battery | BA | 50 | 2022 | No
[7 empty] | 22INR0322 | BRP Paleo BESS | Hale | 2022-09-30 | 2021-02-05 |  | Battery | BA | 202.36 | 2022 | Yes
[7 empty] | 22INR0372 | BRP Hydra BESS | Pecos | 2022-10-30 | 2021-05-08 |  | Battery | BA | 202.46 | 2022 | Yes
[7 empty] | 22INR0328 | Inertia BESS | Haskell | 2022-12-31 | 2021-05-04 |  | Battery | BA | 121.45 | 2022 | No
[7 empty] | 22INR0375 | Inertia BESS 2 | Haskell | 2022-12-31 | 2021-05-04 |  | Battery | BA | 100.77 | 2022 | No
[7 empty] | 20INR0246 | Ryan Energy Storage | Coryell | 2023-01-09 | 2021-02-18 |  | Battery | BA | 50 | 2023 | No
[7 empty] | 21INR0029 | Green Holly Storage | Dawson | 2023-08-01 | 2020-10-19 |  | Battery | BA | 50 | 2023 | No
[7 empty] | 21INR0033 | Red Holly Storage | Dawson | 2023-08-01 | 2020-10-19 |  | Battery | BA | 50 | 2023 | No
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
2012 | 36 | 36 | 0 | 0 | 0 | 0
2013 | 36 | 36 | 0 | 0 | 0 | 0
2014 | 36 | 36 | 0 | 0 | 0 | 0
2015 | 38 | 38 | 0 | 0 | 0 | 0
2016 | 39 | 39 | 0 | 0 | 0 | 0
2017 | 72.5 | 72.5 | 0 | 0 | 0 | 0
2018 | 93.8 | 93.8 | 0 | 0 | 0 | 0
2019 | 103.7 | 103.7 | 0 | 0 | 0 | 0
2020 | 225.4 | 225.4 | 0 | 0 | 0 | 0
2021 | 1770.72 | 257.2 | 294.89 | 1110 | 0 | 108.63
2022 | 3007.72 | 257.2 | 294.89 | 1920 | 427 | 108.63
2023 | 3157.72 | 257.2 | 294.89 | 1920 | 577 | 108.63

## Gas-Combined Cycle Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 20INR0286 | Wise County Power Repower (CT1, CT2) | Wise | 2020-12-01 | 2001-03-19 |  | Gas | CC | 21 | 2020 | Yes
[7 empty] | 20INR0282 | Odessa-Ector Unit 2 (Block 2) Uprate Repower | Ector | 2020-12-31 | 2019-11-01 |  | Gas | CC | 83 | 2020 | Yes
[7 empty] | 20INR0312 | Barney Davis IPAC #4 repower | Nueces | 2021-05-01 | 2008-06-18 |  | Gas | CC | 48 | 2021 | No
[7 empty] | 21INR0202 | R Massengale | Lubbock | 2021-07-20 | 2020-10-30 |  | Gas | CC | 58 | 2021 | Yes
[7 empty] | 16INR0054 | NASA | Harris | 2021-09-01 | 2016-10-27 | 2017-11-27 | Gas | CC | 12 | 2021 | Yes
[7 empty] | 18INR0077 | Colorado Bend 2 repower | Wharton | 2021-09-30 | 2015-12-17 | 2019-06-19 | Gas | CC | 45 | 2021 | No
[7 empty] | 19INR0014 | Formosa Increase | Calhoun | 2021-09-30 | 2019-04-30 | 2020-03-04 | Gas | CC | 240 | 2021 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
1999 | 2867 | 2867 | 0 | 0 | 0 | 0
2000 | 7851 | 7851 | 0 | 0 | 0 | 0
2001 | 14437 | 14437 | 0 | 0 | 0 | 0
2002 | 18913 | 18913 | 0 | 0 | 0 | 0
2003 | 24611 | 24611 | 0 | 0 | 0 | 0
2004 | 26111 | 26111 | 0 | 0 | 0 | 0
2005 | 26009 | 26009 | 0 | 0 | 0 | 0
2006 | 26728 | 26728 | 0 | 0 | 0 | 0
2007 | 27285 | 27285 | 0 | 0 | 0 | 0
2008 | 27846 | 27846 | 0 | 0 | 0 | 0
2009 | 28779 | 28779 | 0 | 0 | 0 | 0
2010 | 30240 | 30240 | 0 | 0 | 0 | 0
2011 | 30958 | 30958 | 0 | 0 | 0 | 0
2012 | 30958 | 30958 | 0 | 0 | 0 | 0
2013 | 31008 | 31008 | 0 | 0 | 0 | 0
2014 | 33550 | 33550 | 0 | 0 | 0 | 0
2015 | 34367 | 34367 | 0 | 0 | 0 | 0
2016 | 33968 | 33968 | 0 | 0 | 0 | 0
2017 | 36429 | 36429 | 0 | 0 | 0 | 0
2018 | 36429 | 36429 | 0 | 0 | 0 | 0
2019 | 36429 | 36429 | 0 | 0 | 0 | 0
2020 | 36429 | 36429 | 0 | 0 | 0 | 0
2021 | 36936 | 36429 | 297 | 162 | 48 | 0

## Gas-Other Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 20INR0104 | GoodAlta GT | Navarro | 2021-04-01 | 2020-03-16 |  | Gas | GT | 150 | 2021 | No
[7 empty] | 22INR0371 | PES 2 Power Station | Harris | 2021-07-01 | 2019-12-17 |  | Gas | GT | 102 | 2021 | Yes
[7 empty] | 19INR0057 | Old Bloomington Road | Victoria | 2021-07-15 | 2020-05-20 |  | Gas | GT | 100 | 2021 | Yes
[7 empty] | 20INR0231 | Topaz Power Plant | Galveston | 2021-07-15 | 2020-04-28 |  | Gas | GT | 510 | 2021 | Yes
[7 empty] | 21INR0201 | Brandon | Lubbock | 2021-07-26 | 2020-10-30 |  | Gas | GT | 21 | 2021 | Yes
[7 empty] | 21INR0506 | Ty Cooke | Lubbock | 2021-07-27 | 2020-10-30 |  | Gas | GT | 33 | 2021 | Yes
[7 empty] | 19INR0056 | Chamon 2 | Harris | 2021-10-01 | 2019-09-20 |  | Gas | GT | 100 | 2021 | Yes
[7 empty] | 17INR0022 | MIRAGE | Harris | 2022-02-07 | 2016-08-31 |  | Gas | GT | 11 | 2022 | Yes
[7 empty] | 20INR0221 | Braes Power Plant | Fort Bend | 2022-03-07 | 2020-11-18 |  | Gas | GT | 408 | 2022 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | Cumulative MW Synchronized | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned
1999 | 33796.03 | 33796.03 | 0 | 0 | 0 | 0
2000 | 33796.03 | 33796.03 | 0 | 0 | 0 | 0
2001 | 34262.59 | 34262.59 | 0 | 0 | 0 | 0
2002 | 34262.59 | 34262.59 | 0 | 0 | 0 | 0
2003 | 34210.59 | 34210.59 | 0 | 0 | 0 | 0
2004 | 32708.69 | 32708.69 | 0 | 0 | 0 | 0
2005 | 30818 | 30818 | 0 | 0 | 0 | 0
2006 | 30375 | 30375 | 0 | 0 | 0 | 0
2007 | 28649 | 28649 | 0 | 0 | 0 | 0
2008 | 28282 | 28282 | 0 | 0 | 0 | 0
2009 | 23743.29 | 23743.29 | 0 | 0 | 0 | 0
2010 | 21030.17 | 21030.17 | 0 | 0 | 0 | 0
2011 | 20673.47 | 20673.47 | 0 | 0 | 0 | 0
2012 | 20649.47 | 20649.47 | 0 | 0 | 0 | 0
2013 | 20124.47 | 20124.47 | 0 | 0 | 0 | 0
2014 | 20015.47 | 20015.47 | 0 | 0 | 0 | 0
2015 | 18636.67 | 18636.67 | 0 | 0 | 0 | 0
2016 | 19677.05 | 19677.05 | 0 | 0 | 0 | 0
2017 | 18984.19 | 18984.19 | 0 | 0 | 0 | 0
2018 | 19803.35 | 19803.35 | 0 | 0 | 0 | 0
2019 | 19577.05 | 19577.05 | 0 | 0 | 0 | 0
2020 | 19322.4 | 19322.4 | 0 | 0 | 0 | 0
2021 | 20703.74 | 19687.74 | 0 | 866 | 150 | 0
2022 | 21122.74 | 19687.74 | 0 | 1285 | 150 | 0