## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
June 10, 2021

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Highlights
  2021 Release Targets
  ESR and DGR Pre-Passport Projects
  Impact Analysis Change and PPL Posting Question
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2021 May Release – R3 – 5/25/2021 – 5/27/2021 Complete
  NPRR974 – Capacity Insufficiency Operating Condition Notice (OCN) Transparency *
  NPRR978(c) – Alignment with Amendments to PUCT Substantive Rule 25.505 *
  NPRR1048 – Clarification on NPRR978 Short-Term Adequacy Reports
  NPRR1051 – Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices
  SCR811 – Addition of Intra-Hour PhotoVoltaic Power Forecast to GTBD Calculation
  ECMS – Replaced NoticeBuilder (now called “GCC Notices”) [Grid Condition Communication]
  ECMS – Partial Deployment: Market Info & Grid Info to new platform, improved dashboards and displays
2021 June Release Off-Cycle – 6/1/2021 Delayed until August
  NPRR902(b) – ERCOT Critical Energy Infrastructure Information
2021 June Release Off-Cycle – 6/22/2021 In Flight
  ECMS – Enterprise Content Management System
    New public version of ERCOT.com
2021 July Release – R4 – 7/27/2021 – 7/29/2021 In Flight
  NPRR905 – CRR Balancing Account Resettlement
  SCR789 – Update NMMS Topology Processor to PSSE 34 Capability
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.
Note: Several of these items have effective dates between 5/29/2021 and 6/3/2021
* Issue resolution in progress for ST System Adequacy Report postings

## Slide 4: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/2 – 2/4 | April 3/30 – 4/1 | May 5/25 – 5/27 | July 7/27 – 7/29 | October 10/5 – 10/7 | December 12/7 – 12/9
NPRR902(a) NOGRR195 NPRR1055 OBDRR023(a) NPRR1020 SCR804 | NPRR971 NPRR986 NPRR998 NPRR1024 NPRR1043 NOGRR213 VCMRR027 PGRR070 | NPRR974 NPRR978(c) NPRR1048 NPRR1051 SCR811 ECMS NPRR902(b) NPRR1060 ECMS | NPRR905 SCR789 NPRR902(b) | OBDRR023(b) SCR781(b) | FFR Advancement (NPRR863 FFR) NPRR1015 DGR/DESR (See next slide)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR902(a) – ECEII Market Participant MPIM role
NPRR902(b) – MIS links updated for ECEII reports
NPRR978(c) – Forecast Zone scope
SCR781(b) – “Add” capability
OBDRR023(a) – ERS Expenditure Limit
OBDRR023(b) – 4 Standard Contract Terms/Year
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 867, 879, 885, 918, 935(b), 936, 939, 941, 945, 962, 965, 1023, 1030, 1032, 1034, 1040, 1057 SCRs: 799, 800, 805, 809, 812 Market Guides: PGRR066
E
Replace NoticeBuilder
ECMS – Nov.
Combine ERCOT.com and MIS
Improved search
New navigation
TBD Go-Lives Due to MMS/OS Delay
NPRR904, NPRR1006, OBDRR009
NPRR930
NPRR1019
1/1
ü
ü
ü
2/1
10/1
5/1
3/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
4/22
ü
6/1
ü
P
P
P
RIOO – Q4 2021
RARF Add Functionality Go-Live
6/22
ü
ü
ü
ü
ü
ü
ü
August
E
New public version of ERCOT.com
E

## Slide 5: ESR and DGR Pre-Passport Projects
On 10/16/2020, ERCOT initiated 2 projects to deliver several Revision Requests relating to ESR and DGR
  PR353-01 BES Combo Model Implementation – potential for multiple go-lives
      Target go-live TBD – the team is still working to set release targets
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
  PR354-01 DGR/DESR Implementation (gating to Execution phase on 6/23/2021)
      Target go-live 2021-R6 (December 2021) or 2022-R1 (February 2022)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources (DESRs)
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995 Implementation
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
ESR: Energy Storage Resource
BES: Battery Energy Storage
DGR: Distributed Generation Resource
Red text = New addition/edit since last report
ERCOT is working to define the timing to lift the DGR moratorium based on the target go-live that will be determined over the next few weeks

## Slide 6: Impact Analysis Change and PPL Posting Question
ERCOT Project Management and Portfolio Management are completing the implementation of an enterprise Project and Portfolio Management (PPM) system
  There will be some minor changes appearing in project reporting and the Impact Analysis template
    Primarily, an effort to standardize our internal roadmap reporting will change some of the language in the “Impacted Systems” section of the IA
    Example in the NPRR1063 IA (on the 6/10/2021 PRS agenda)
For many years, ERCOT has posted a redacted version of the PPL to ERCOT.com
  Approximately once per month at the following link:
    http://www.ercot.com/services/projects/index
Question: Are Market Participants loading the posted PPL Excel file into their systems?
  The answer to this question will determine our approach to transitioning the monthly PPL posting
    i.e. Do we need to maintain the same column order, tab names, etc.?
  If not, the format of the posted PPL will change as we switch over to the new system
System Impact | Former System Impacts Category | New Category
New MIS Link | Data Access & Transparency | ERCOT Website and MIS Systems

## Slide 7: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR995 | RTF-6 Create Definition and Terms for Settlement Only Energy Storage | 2025 | 4500 | $800k-$1.2M, 20-30 months Impacted Systems: RIOO, S&B, EMS, NMMS, Registration, Reporting, Integration Impact to Passport
NPRR1063 | Dynamic Rating Transparency | 2021 | 3330 | $15k-$25k, 3-4 months Impacted Systems: ERCOT Website and MIS Work into project plan in 2021
RRGRR028 | Transformer Impedance Clarifications | 2022 | 3520 | $100k-$150k, 7-10 months Impact Area: RIOO (Resource Integration and Ongoing Operations), Reporting Add functionality to RIOO after current effort to include “add” capability is complete Worked with ROS on Priority/Rank
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3330
Next available Rank in Regulatory = 320
Options for…