## Slide 1
Passport Program Update
Matt Mereness
Passport Director
TAC
June 23, 2021

## Slide 2: Passport Update
Pre-Passport Update
Re-Assessing Delivery Sequence
Passport Next Steps
Appendix:
  Passport Scope Details
  RTCTF Items for Future Consideration by TAC

## Slide 3: In-Flight Pre-Passport Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on June 22, 2021)
    Planned go-live for December 2021
    NPRR863, NPRR1015, NOGRR187
  PR354-01 DGR/DESR Implementation (Gate to Execution phase June 2021)
    Target go-live 2021-R6 (December 2021) or 2022-R1 (February 2022)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
  PR353-01 BES Combo Model Implementation – potential for multiple go-lives
    Target go-live TBD (the team is still working to set release targets)
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
ESR: Energy Storage Resource
BES: Battery Energy Storage
DGR: Distributed Generation Resource
ERCOT is working to define the timing to lift the DGR moratorium based on the target go-live that will be determined over the next few weeks

## Slide 4: Re-Assessing Delivery Sequence (not delivery dates)
EMS Technology Foundation Upgrade
2020
2021
2025
2022
2023
2024
Real-Time Co-optimization (RTC)
NPRR1007-1013
Single Model Energy Storage Resources (NPRR1014)
DC Coupled Resources (NPRR1029)
DGR enhancements for
Single Model Energy Storage Resources
ERCOT Contingency
Reserve Service (NPRR863-ECRS)
LONGER-TERM PLANS
BEING DEVELOPED

## Slide 5: Next Steps on Longer-Term Plans
Based on updated EMS Upgrade and staffing plans, ERCOT analyzing delivery sequence alternatives for strategic efforts.
  Work is already in-flight for FFR, Pre-Passport DGR, and Pre-Passport BES.
  ERCOT re-evaluating options on delivery for RTC, ECRS, and other strategic changes.
In parallel, ERCOT will support Revision Requests from February 2021 Extreme Winter Weather Event and other reliability/policy decisions with Impact Analysis efforts.
Reminder as program delays are based in resource constraints, ERCOT still reserves the right to defer significant Impact Analysis work for large design changes until staff are available to support the effort (especially in the areas of EMS, MMS, S&B/Credit).

## Slide 6: Wrap-up
ERCOT is working on re-planning sequence of Passport scope (more details at July TAC meeting).
ERCOT will continue to provide monthly updates at TAC meetings.
Questions?

## Slide 7: Appendix
Passport Scope Details
RTCTF Items for Future Consideration by TAC

## Slide 8: Passport Protocol Scope
Design | Revision Requests*
Real-Time Co-optimization | NPRR1007 – 1013
Battery Energy Storage Resources | NPRR1014 & 1029
Distribution Generation Resources | DGR changes for single model DESR
ERCOT Contingency Reserve Service | NPRR863 (ECRS only)
*Additional supporting Market Guide changes are also within Passport scope.

## Slide 9: RTCTF Items for Future Consideration
POLICY - Open policy discussion items:
  Parameters for Ancillary Service proxy offers
  Ancillary Service Demand Curves (ASDCs) for use in Reliability Unit Commitment (RUC) studies
  Any needed discussion on triggers for initiating off-cycle Security-Constrained Economic Dispatch (SCED) executions
    Largely driven by ERCOT Operator desk procedures and discretion today
  Consideration of NPRR for allowing real-time updates to offers in current Real-Time Market and future with RTC.
ANALYSIS - Requested analysis going forward:
  Framework for periodic analysis comparing RTC and the current Operating Reserve Demand Curve (ORDC) design – Key Principle 1.1(8)

## Slide 10: RTCTF Items for Future Consideration (continued)
SUPPORTING DETAILS - Other documentation that may need review:
  Verifiable Cost Manual (Change for on-line hydro Resources per Key Principle 1.3(3))
  Additional review of transmission constraint max. shadow price values
  Operation Procedures (e.g., removing SASM and HASL/LASL)
  Business Practice Manuals (e.g., changes to COP and telemetry)
MARKET PARTICIPANT NEEDS - Market needs for the transition and implementation:
  Mapping of bill determinants to extracts and reporting for developing shadow settlement
  Changes to Inter-Control Center Communications Protocol (ICCP) handbook, and documentation for non-ICCP market submissions
  Market trials/training/annual seminar engagement
  Any details MPs need for designing their control systems