## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
July 15, 2021

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Highlights
  2021 Release Targets
  ESR and DGR Pre-Passport Projects
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2021 June Release Off-Cycle – 6/25/2021 Complete
  ECMS – Enterprise Content Management System
    New public version of ERCOT.com homepage
2021 July Release Off-Cycle – 7/1/2021 Complete
  NPRR1080 – Limiting Ancillary Service Price to System-Wide Offer Cap
  OBDRR030 – Related to NPRR1080, Limiting Ancillary Service Price to System-Wide Offer Cap
  NPRR1081 – Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed
2021 July Release Off-Cycle – 7/23/2021 In Flight
  NPRR1062 – Modify IDR Meter Requirement and Eliminate IDR Meter Requirement Report
  RMGRR164 – Related to NPRR1062
2021 July Release – R4 – 7/27/2021 – 7/29/2021 In Flight
  NPRR902(b) – ERCOT Critical Energy Infrastructure Information
  NPRR905 – CRR Balancing Account Resettlement
  SCR789 – Update NMMS Topology Processor to PSSE 34 Capability
2021 September Release Off-Cycle – 9/10/2021 In Flight
  NPRR867 – Revisions to CRR Auction Credit Lock Amount to Reduce Excess Collateral
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/2 – 2/4 | April 3/30 – 4/1 | May 5/25 – 5/27 | July 7/27 – 7/29 | October 10/5 – 10/7 | December 12/7 – 12/9
NPRR902(a) NOGRR195 NPRR1055 OBDRR023(a) NPRR1020 SCR804 | NPRR971 NPRR986 NPRR998 NPRR1024 NPRR1043 NOGRR213 VCMRR027 PGRR070 NPRR1060 | NPRR974 NPRR978(c) NPRR1048 NPRR1051 SCR811 ECMS ECMS NPRR1080 OBDRR030 NPRR1081 | NPRR902(b) NPRR905 SCR789 NPRR1062 RMGRR164 NPRR902(b) NPRR867 | OBDRR023(b) SCR781(b) | FFR Advancement (NPRR863 FFR) NPRR1015 DGR/DESR (See next slide)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR902(a) – ECEII Market Participant MPIM role
NPRR902(b) – MIS links updated for ECEII reports
NPRR978(c) – Forecast Zone scope
SCR781(b) – “Add” capability
OBDRR023(a) – ERS Expenditure Limit
OBDRR023(b) – 4 Standard Contract Terms/Year
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 867, 879, 885, 904, 918, 930, 935(b), 936, 939, 941, 945, 962, 965, 1006, 1019, 1023, 1030, 1032, 1034, 1040, 1057 SCRs: 799, 800, 805, 809, 812 Market Guides: PGRR066, PGRR076 Other Binding Docs: OBDRR009
E
Replace NoticeBuilder
ECMS – Nov.
Combine ERCOT.com and MIS
Improved search
New navigation
1/1
ü
ü
ü
2/1
10/1
5/1
3/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
E
E
E
4/22
ü
6/1
ü
E
E
P
RIOO – Q4 2021
RARF Add Functionality Go-Live
6/25
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
August
New public version of ERCOT.com homepage
ü
7/1
9/10
7/23
E
2022 R1 (Feb.)

## Slide 5: In-Flight Pre-Passport Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on 6/22/2021)
    Planned go-live for December 2021
    NPRR863, NPRR1015, NOGRR187
  PR354-01 DGR/DESR Implementation (Gating to Execution phase in late July 2021)
    Target go-live 2022-R1 (February 2022)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
  PR353-01 BES Combo Model Implementation – potential for multiple go-lives
    Target go-live TBD (the team is still working to set release targets)
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
ESR: Energy Storage Resource
BES: Battery Energy Storage
DGR: Distributed Generation Resource
ERCOT is working to define the timing to lift the DGR moratorium based on the target go-live that will be determined over the next few weeks
Green text: ERCOT considering removing from project for earlier delivery

## Slide 6: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
None |  |  |  | 
PPL Rank Information
Next available 2021 Rank in Business Strategy = 3340
Next available Rank in Regulatory = 320
Options for…