## Slide 1
Passport Program Update
Matt Mereness
Passport Director
TAC
July 28, 2021

## Slide 2: Passport Update
Pre-Passport Update
Re-Assessing Delivery Sequence
Passport Next Steps
Appendix:
  Passport Scope Details
  RTCTF Items for Future Consideration by TAC

## Slide 3: In-Flight Pre-Passport Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on 6/22/2021)
    Planned go-live for December 2021
    NPRR863, NPRR1015, NOGRR187
  PR354-01 DGR/DESR Implementation (Gating to Execution phase in late July 2021)
    Target go-live 2022-R1 (February 2022)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
  PR353-01 BES Combo Model Implementation – potential for multiple go-lives
    Target go-live TBD (the team is still working to set release targets)
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
ESR: Energy Storage Resource
BES: Battery Energy Storage
DGR: Distributed Generation Resource
ERCOT is working to define the timing to lift the DGR moratorium based on the target go-live that will be determined over the next few weeks

## Slide 4: New delivery “sequence” for de-coupled Passport scope
EMS Technology Upgrade
2021
2022
2026
2023
2024
2025
  Real-Time Co-optimization (RTC)
  - NPRR1007-1013
  - 3.5 year project
  Energy Storage Resources
  - Single Model ESR/DESR (NPRR1014)
  - DC Coupled (NPRR1029)
ECRS
New 10-minute AS product NPRR863
FFR Advancement
DGR/DESR Implementation
BES Combo Model Implementation
At least
12-month delay
At least 18-months needed between EMS and RTC go-live
Deliver ECRS as soon as possible after EMS

## Slide 5: Delivery Sequence priorities
Continue work on FFR, DGR/DESR, BES Combo Model, and work to deliver EMS Upgrade by July 2024
Expedite ECRS:
De-couple ECRS project from Passport/RTC
Deliver as separate project as soon as possible after EMS upgrade
Place remaining Passport scope on-hold for future consideration:
Remaining scope is RTC, single-model ESR, and DC-Coupled single-model ESR
Placing program on-hold for at least 1-year (hibernation)
  ERCOT has already begun to place sub-projects “on-hold”.
Allows room for other work (such as Securitization) to proceed and for longer-term policy decisions to be made before potentially resuming work in 2022.

## Slide 6: Next Steps
At August TAC meeting, ERCOT will propose that TAC retire RTCTF
  Chartered deliverables were completed in December 2020 related to RTC Protocols.
  As with other retired task forces, the RTCTF webpage will remain available.
ERCOT proposes discontinuing Passport updates after the August 10, 2021 Board and August 25, 2021 TAC meetings.
ERCOT has appreciated the time, expertise, and collaboration from the PUCT, IMM, and Market Participants on this effort and will stand ready as needed.
Questions?

## Slide 7: Appendix
Passport Scope Details
RTCTF Items for Future Consideration by TAC

## Slide 8: Passport Protocol Scope
Design | Revision Requests*
Real-Time Co-optimization | NPRR1007 – 1013
Battery Energy Storage Resources | NPRR1014 & 1029
Distribution Generation Resources | DGR changes for single model DESR
ERCOT Contingency Reserve Service | NPRR863 (ECRS only)
*Additional supporting Market Guide changes are also within Passport scope.

## Slide 9: RTCTF Items for Future Consideration
POLICY - Open policy discussion items:
  Parameters for Ancillary Service proxy offers
  Ancillary Service Demand Curves (ASDCs) for use in Reliability Unit Commitment (RUC) studies
  Any needed discussion on triggers for initiating off-cycle Security-Constrained Economic Dispatch (SCED) executions
    Largely driven by ERCOT Operator desk procedures and discretion today
  Consideration of NPRR for allowing real-time updates to offers in current Real-Time Market and future with RTC.
ANALYSIS - Requested analysis going forward:
  Framework for periodic analysis comparing RTC and the current Operating Reserve Demand Curve (ORDC) design – Key Principle 1.1(8)

## Slide 10: RTCTF Items for Future Consideration (continued)
SUPPORTING DETAILS - Other documentation that may need review:
  Verifiable Cost Manual (Change for on-line hydro Resources per Key Principle 1.3(3))
  Additional review of transmission constraint max. shadow price values
  Operation Procedures (e.g., removing SASM and HASL/LASL)
  Business Practice Manuals (e.g., changes to COP and telemetry)
MARKET PARTICIPANT NEEDS - Market needs for the transition and implementation:
  Mapping of bill determinants to extracts and reporting for developing shadow settlement
  Changes to Inter-Control Center Communications Protocol (ICCP) handbook, and documentation for non-ICCP market submissions
  Market trials/training/annual seminar engagement
  Any details MPs need for designing their control systems