## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2021-06-16
Agenda Item: | Decision / Resolution | Action Items :
May Call Notes
| No changes. | The Texas SET Vice Chair will have the notes posted to the May meeting page.
The Texas SET Chair provided the Retail Market Subcommittee (RMS) Update on the following topics.
ERCOT provided an update on the Listservs | ERCOT is planning to bring the software inhouse to allow backups to use when outages occur.
RECTF Leadership provided an update.
RMS approved the RMGRR166 with the PUCT comments that added OPUC to those notified of a potential a Mass Transition.
ERCOT Discussion Items
Market Test Flight 0621 Update | The ERCOT Flight Administrator presented the update.
Discussion Items
Texas SET Enhancement Matrix
Final 5.0 CC Timeline | This topic is delayed to a future meeting.
NPRRs & RMGRRs for v5.0
IAS Enhancements
Draft RMGRR - TXSET5.0 IAS Enhancements_JointTDSP_20210614 | AEP conducted a review of the proposed language changes and made additional changes as needed. | 1. TDSP API users to check how Cancel with Approvals are handled, manual or automated kick back; then provide feedback at the next meeting. 2. AEP will send the updated RMGRR to Texas SET Leadership to be distributed to the Texas SET email distribution list.
Draft Change Control for 814_04 and 814_05 IAS Valid Reject Reasons | The Texas SET Chair conducted a review of the reject codes and made changes where needed. | Centerpoint will make the updates to the Change Controls; then submit to ERCOT for the official Change Control Call at the next meeting.
Meter Service Type/County for MIS | No further discussion was needed for this change today.
CBCI File | Discussions were delayed to a future meeting.
CSA Bypass
ChangeControl2012-798-05_ApprovedFuture | The Texas SET Chair conducted a review of the already approved Change Control to determine if any additional language is needed for the NPRR that was written.
CSA Start/End Dates
TXSETChangeControl for 814_19 ERCOT CSA Rejects 06_04_21_KT | Centerpoint Energy Chair conducted a review of the reject/un-executable codes and made changes where needed. | Centerpoint will make the updates to the Change Controls; then submit to ERCOT for the official Change Control Call at the next meeting.
Additional CCs
TXSETChangeControl for 650s and 814_28 DG Unexecutables 06_04_21 | Centerpoint Energy Chair conducted a review of the reject/un-executable codes and made changes where needed. | Centerpoint will make the updates to the Change Controls; then submit to ERCOT for the official Change Control Call at the next meeting.
Other Business
Retail Emergency Conditions Task Force (RECTF) Referral
Mass Transition expectations and scenarios for customers **Stacking Logic** | TXU Energy provided the update stating that the language of First Available Switch Date (FASD) is contained in the PUCT substantive rule and that no changes should be made in conflict to this without speaking with the PUCT. Centerpoint stated that the language referenced was under the CR's responsibilities and not ERCOT's. | Centerpoint will send documentation to TXU Energy; then Texas SET will review the issue at the next meeting.
Issues--No new Issues were discussed this month. | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | Still on Hold
Next Meeting--WebEx Only | 2021-06-16
Attendees F-T-F
Attendees Webex
Kyle Patrick NRG | Paul Yockey ERCOT
Jordon Troublefield ERCOT | Deb Belin MarketWise
Diana Rehfeldt TNMP | Mark Pepdjonovic ESG
Kathy Scott Centerpoint Energy | Jeff Chen Centerpoint Energy
Kathryn Thurman ERCOT | Kim Wall Hansen Technologies
Jim Lee AEP | Carolyn Reed Centerpoint Energy
Sam Pak ONCOR | Tyler Krueger BDE
Mary Do Agility CIS | Frank Nunes EC InfoSystems
Norman Levine DE / NRG | Sheri Weigand TXU Energy
Stephen Wilson TXU Energy