## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2021-07-21
Agenda Item: | Decision / Resolution | Action Items :
Minutes:
Meeting minutes were considered approved by the WG
RMS update
No action items for TEXAS SET from RMS. Patrick brought up that at RMS it was announced that in person meetings would be allowed at ERCOT after 9/1/2021. |  | RMS leadership to organize a call with working group and task force leadership to discuss the announcement that in person meetings
ERCOT Update
Flight administrator gave update on 0621. Presentation posted to meeting link for reference. |  | Flight 2022 Schedule to be brought next month.
RECTF
Wilson present the draft RMGRR: ERCOT Responsibilities During the Mass Transition to Texas SET. No comments or revisions to the document. |  | Texas SET to submit to RMS for September RMS meeting.
CBCI File: Scott expressed concerns over the "," being used in transactions that were received during MT. ERCOT suggested that the issues of data in transactions vs CBCI file needed to be separated and the team agreed. Thurman is going to see if ERCOT could informally review validation for "," and if the WG submitted a CC would that be enough to effectuate change. Thurman unsure, but stated she would see what she could do regarding this issue. The CBCI file was discussed and NRG and Vistra agreed to look at market guide language to determine if any refinement to language would be beneficial at changing behaviors. |  | RMG to reviewed by Vistra and NRG and discussed at next TEXAS SET meeting.
Change Control Call
Change Control 2021-832: To support Change Control 2021-829 for Inadvertent Gain/Loss or Customer Rescission this change control adds 2 new rejection reasons. TEXAS SET agreed to send it to RMS with no edits. |  | Referred to RMS for approval
Change Control 2021-833: Add new Reject codes to the 814_19 for support of the new CSA Start and End dates added in Change Control 2021-828. TEXAS SET agreed to send it to RMS with no edits. |  | Referred to RMS for approval
Change Control 2021-834: Add specific Unexecutable codes to provide detailed explanations rather than just "T018" for turndowns associated with unapproved Distributed Generation equipment or Auto Transfer Switch and/or no signed Interconnection Agreement received by TDSP. TEXAS SET agreed to send it to RMS with no edits. |  | Referred to RMS for approval
TEXAS SET 5.0 Matrix
Timeline Discussion: Patrick reviewed timeline for TDTMS SCR, TEXAS SET NPRR, and TEXAS SET RMGRR to be submitted and move throughout ERCOT stakeholder process. Timeline will be posted to ERCOT.com as a meeting document.
Review Draft Nodal Protocol Revision Requests | Patrick reviewed the NPRR with TEXAS SET. No edits were made and the NPRR is ready for submission. | NPRR to be submitted
o Meter Service Type/County for MIS
o CSA Bypass
o CSA Start/End Dates
Review Draft Retail Market Guide Revision Requests | Scott presented the RMGRR with new language describing rejection process for IAS trxs over 150 days. No additional comments from TEXAS SET. Patrick and Thurman will work on language for the CSA enhancements to add to the Solution to Stacking section and then the RMGRR will be ready for submission. | Patrick and Thurman to write up CSA language in solution to stacking section 11 for review at Aug TEXAS SET
o IAS Enhancements
Parking Lot
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | Still on Hold
Next Meeting--WebEx Only
Attendees F-T-F
Attendees Webex
Kyle Patrick NRG | Paul Yockey ERCOT
Jordon Troublefield ERCOT | Deb Belin MarketWise
Melinda Earnest AEP | Mark Pepdjonovic ESG
Kathy Scott Centerpoint Energy | Jeff Chen Centerpoint Energy
Kathryn Thurman ERCOT | Kim Wall Hansen Technologies
Jim Lee AEP | Carolyn Reed Centerpoint Energy
Sam Pak ONCOR
Mary Do Agility CIS | Frank Nunes EC InfoSystems
Norman Levine DE / NRG | Sheri Weigand TXU Energy
Stephen Wilson TXU Energy | Dave Michelsen ERCOT

## Sheet2
Antitrust Admonition
Minutes: June
RMS update
ERCOT Update
Flight Update
RECTF
· RMGRR: ERCOT Responsibilities During the Mass Transition
· CBCI File Discussion
TEXAS SET 5.0 Matrix
Timeline Discussion
Review Draft Nodal Protocol Revision Requests
o Meter Service Type/County for MIS
o CSA Bypass
o CSA Start/End Dates
Review Draft Retail Market Guide Revision Requests
o IAS Enhancements