## Slide 1
Resource Integration Topics
Jay Teixeira
ERCOT
Resource Integration Working Group
August 24, 2021

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
PSCAD Model Quality Test and Unit Model Validation required for November 1, 2021 QSA
TSAT Model Required – If PSSE model is UDM, then TSAT model should be UDM by November 1, 2021.

## Slide 4: GINR Time Line (Fastest)

## Slide 5: Active RR’s
RRGRR028, submitted by John Karlik on behalf of the SPWG on December 23, 2020, Transformer Impedance Clarifications. Language active 9/1.
PGRR091, FIS Application Completion 60-Day Limit. Approved by BOD 8/10/2021. PUCT consideration.
NOGRR223, Add Phasor Measurement Recording Equipment Requirement to Modified Generating Facilities in Interconnection Process. ROS approved 8/5/2021, IA at ROS 9/2/2021.
NOGRR227, Add Phasor Measurement Recording Equipment Location for Main Power Transformer for Intermittent Renewable Resource (IRR). ROS approved 8/5/2021. Next at TAC.

## Slide 6: New AVR Template

## Slide 7: DGR Workshop XII
September 16, 2021 after PRS meeting
Topics for Discussion (tentative)
  Unboxing PGRR82 language
  Timeline for lifting moratorium
  What will RE’s need to have ready for January 4, 2022

## Slide 8: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department
Mailing List
  RESOURCE_INTEGRATION@LISTS.ERCOT.COM

## Slide 9: Questions?
Thank you!