## ImprovementCostSummary09012012
PRIVILEGED AND CONFIDENTIAL, DO NOT release outside of ERCOT Staff or Transmission Providers organization. Contains critical cost information that can affect bids for projects.
| Project Cost | [5 empty] | Circuit Miles |  |  |  |  | XFMR MVA
| Project Cost | [5 empty] | XFMR MVA
| 345 | 138 | 69 | total |  |  | 345 | 138 | 69 | total
2010 | 527016732 | 393661395 | 79708160 | 1000386287 |  | 2010 | 5957 | 758 | 0 | 6715
2011 | 648929545 | 325895515 | 204249547 | 1179074607 |  | 2011 | 5422 | 983 | 0 | 6405 |  | For ROS and BOD reports
2012 | 566729909 | 514133445 | 277949104 | 1358812458 | 3538273352 | 2012 | 3800 | 827 | 0 | 4627 | 17747
2013 | 5395055242 | 485287904 | 136476527 | 6016819673 |  | 2013 | 2078 | 75 | 0 | 2153 |  | ·All Projects (in engineering, routing, licensing and construction) (sum of F13, E16) |  |  |  | 9681444466
2014 | 179011257 | 413684068 | 89050137 | 681745462 |  | 2014 | 2200 | 745 | 150 | 3095
2015 | 201432065 | 339977931 | 21920000 | 563329996 |  | 2015 | 1800 | 190 | 0 | 1990 |  | ·Transmission Projects Energized in 2012 (E15) |  |  |  | 732159946
2016 | 618884000 | 144636396 | 91111100 | 854631496 |  | 2016 | 450 | 0 | 0 | 450
2017 | 109240549 | 77214000 | 0 | 186454549 |  | 2017 | 0 | 40 | 0 | 40
2018+ | 343819538 | 363780697 | 44210543 | 751810778 | 9054791954 | 2018+ | 5504 | 420 | 60 | 5984 | 13712
2012COM | 237128512 | 316170484 | 178860950 | 732159946 |  | 2012COM | 2600 | 510 | 0 | 3110
2012PLAN | 329601397 | 197962961 | 99088154 | 626652512 |  | 2012PLAN | 1200 | 317 | 0 | 1517
2010-2018+ | 8590118837 | 3058271351 | 944675118 | 12593065306 |  | 2010-2018+ | 27211 | 4038 | 210 | 31459
2010-2012 | 1742676186 | 1233690355 | 561906811 | 3538273352 |  | 2010-2012 | 15179 | 2568 | 0 | 17747
2013-2018+ | 6847442651 | 1824580996 | 382768307 | 9054791954 |  | 2013-2018+ | 12032 | 1470 | 210 | 13712
| Circuit Miles New | [5 empty] | Circuit Miles Rebuilt, Reconductored or Upgraded |  |  |  |  | TOTAL
| 345 | 138 | 69 | total |  |  | 345 | 138 | 69 | total |  | 345 | 138 | 69 | total
2010 | 380.5 | 108.1 | 27.5 | 516.1 |  | 2010 | 115.5 | 284.9 | 52.6 | 453 |  | 496 | 393 | 80.1 | 969.1
2011 | 624.3 | 61.2 | 3.6 | 689.1 |  | 2011 | 12.9 | 313.1 | 284.7 | 610.7 |  | 637.2 | 374.3 | 288.3 | 1299.8
2012 | 473.8 | 111.8 | 60 | 645.6 | 1850.8 | 2012 | 16.4 | 370 | 249.2 | 635.6 | 1699.3 | 490.2 | 481.8 | 309.2 | 1281.2
2013 | 3903.1 | 143.6 | 0 | 4046.7 |  | 2013 | 66.7 | 393.6 | 98.3 | 558.6 |  | 3969.8 | 537.2 | 98.3 | 4605.3
2014 | 6.9 | 89.8 | 0 | 96.7 |  | 2014 | 70.4 | 293.6 | 120.7 | 484.7 |  | 77.3 | 383.4 | 120.7 | 581.4
2015 | 30 | 130.3 | 0 | 160.3 |  | 2015 | 122.9 | 211.7 | 27.8 | 362.4 |  | 152.9 | 342 | 27.8 | 522.7
2016 | 288.5 | 26.8 | 7.7 | 323 |  | 2016 | 72.8 | 112.5 | 52.3 | 237.6 |  | 361.3 | 139.3 | 60 | 560.6
2017 | 13.5 | 20.6 | 0 | 34.1 |  | 2017 | 0 | 16.2 | 0 | 16.2 |  | 13.5 | 36.8 | 0 | 50.3
2018+ | 72.3 | 180 | 11 | 263.3 | 4924.1 | 2018+ | 70.6 | 200 | 56.6 | 327.2 | 1986.7 | 142.9 | 380 | 67.6 | 590.5
2012COM | 192.4 | 30.2 | 60 | 282.6 |  | 2012COM | 15.2 | 285.9 | 118.5 | 419.6 |  | 207.6 | 316.1 | 178.5 | 702.2
2012PLAN | 281.4 | 81.6 | 0 | 363 |  | 2012PLAN | 1.2 | 84.1 | 130.7 | 216 |  | 282.6 | 165.7 | 130.7 | 579
2010-2018+ | 5792.9 | 872.2 | 109.8 | 6774.9 |  | 2010-2018+ | 548.2 | 2195.6 | 942.2 | 3686 |  | 6341.1 | 3067.8 | 1052 | 10460.9
2010-2012 | 1478.6 | 281.1 | 91.1 | 1850.8 |  | 2010-2012 | 144.8 | 968 | 586.5 | 1699.3 |  | 1623.4 | 1249.1 | 677.6 | 3550.1
2013-2018+ | 4314.3 | 591.1 | 18.7 | 4924.1 |  | 2013-2018+ | 403.4 | 1227.6 | 355.7 | 1986.7 |  | 4717.7 | 1818.7 | 374.4 | 6910.8

## FutureTPIT09012012NoCost
SEPTEMBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS As Of 09/01/2012
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional)
12TPIT0152 | Louise Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-09-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | WHARTON |  | Tier 4 |  |  |  | 5528 | Y | N
12TPIT0213 | Odessa North - Holt Switch 69 kV line | Upgrade terminal equipment |  | Odessa North | Holt Switch | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2012-09-01 |  | 69 | 0 | 0 | 0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 1123, 1142 | Y | N
12TPIT0209 | Lewisville Switch - Jones St 138 kV line | Increase rating of line |  | Lewisville Switch | Jones St | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2012-09-01 |  | 138 | 0 | 0.3 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  |  | 645, 1972 | Y | N
12TPIT0210 | Lakepointe - Jones St 138 kV line | Increase rating of line |  | Lakepointe | Jones St | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2012-09-01 |  | 138 | 0 | 5.02 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  |  | 37010, 1972 | Y | N
12TPIT0212 | Moss - Westover 138 kV line | Upgrade terminal equipment |  | Moss | Westover | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2012-09-01 |  | 138 | 0 | 0 | 0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 1019, 1129 | Y | N
12TPIT0214 | Odessa North 138/69 kV autotransformer | Increase rating of autotransformer |  |  |  | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2012-09-01 |  | 138 | 0 | 0 | 99 | 0 | ECTOR |  | Tier 4 |  |  |  | 1123, 1122 | Y | N
12TPIT0216 | Judkins Substation switches | Upgrade switches |  |  |  | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2012-09-01 |  | 138 | 0 | 0 | 0 | 0 | ECTOR |  | Tier 4 |  |  |  | 1102 | Y | N
12TPIT0073 | Nordheim West - New Substation (Formerly FM 239) | Construct a new 69/138-26.18-KV, 12/16/20 MVA substation |  | Nordheim West | Nordheim/Yorktown | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2012-09-10 |  | 69 | 0 | 0 | 0.0 | 0 | DEWITT |  | Tier 4 |  |  |  | See Project Title | Y | N
12TPIT0175 | Switch Station Entergy Tie | Build a tranmission tie between COCS Switch Station and Entergy Switch Station for emergency tie per a PUCT order. |  | 138 kV Switch S1617ETI | 138 kV Switch 26421 | Planned |  | COCS | Tony Michalsky 979- 764-3438 tmichalsky@cstx.gov |  | 2012-09-12 |  | 138 | 0 | 0 | 0.0 | 0 | BRAZOS |  | Tier 4 |  |  |  | 32000 | N | N
12TPIT0188 | Mayo: Construct 138 kV Station | Mayo Sub-Construct new distribution station on Gila to Whitepoint 138kV line. | Change Status | Gila | Whitepoint | Under Construction | 562-0730 | AEP/TCC | Frank Pritzlaff 918-599-2653 | 3440 | 2012-09-14 |  | 138 | 0 | 0 | 0 | 0 | SAN PATRICIO |  | Tier 4 |  |  |  | 80258 | N | N
13TPIT0101 | Winchester Terminal Equipment Upgrade | Upgrade three switches and jumpers to 2000 A at the Winchester Substation (7306). |  | Winchester | Winchester | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2012-09-17 |  | 138 | 0 | 0 | 0.0 | 0 | FAYETTE |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
12TPIT0170 | Airline - White Oak Ckt. 21 | Upgrade 138kV Ckt. 21 Airline to White Oak to increase thermal ratings. | Change in project schedule. | Airline | White Oak | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-09-30 |  | 138 | 0 | 3.03 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 45630, 46610 | Y | N
12TPIT0148 | Olivia Capacitor | Add 4.8 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-10-01 |  | 69 | 0 | 0 | 0.0 | 4.8 | CALHOUN |  | Tier 4 |  |  |  | 5576 | Y | N
12TPIT0158 | Permian Basin terminal equipment | Upgrade terminal equipment at Permian Basin in the Permian Basin - Wickett 69 kV line |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8052-WAC | 2012-10-01 |  | 69 | 0 | 0 | 0.0 | 0 | WARD |  | Tier 4 |  |  |  | 1015 | Y | N
12TPIT0162 | Line Ratings Project - Grandview substation equipment upgrade | Upgrade substation equipment at Grandview and Laredo to remove existing MLSE on the Grandview to Highlands and Grandview to Tenth St. 138kV line |  | Grandview | Highland Hills/Tenth St | Planned |  | CPS | Dieckrow, Robert | S-0704 | 2012-10-01 |  | 138 | 0 | 0 | 0.0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5175 5205 5420 | Y | N |  | There are no transformers associated with this project
12TPIT0195 | 1360 East Midland Substation | Transfer 1360 East Midland Substation into ERCOT | New | Oncor Stanton East Substation | Oncor Midland East Substation | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2012-10-01 |  | 138 | 0 | 0 | 0 | 0 | MIDLAND |  | Tier 4 |  |  | n/a |  | N | N |  | This project has been completed and compiling accounting data for costs.
12TPIT0176 | Odlaw | Construct the new Odlaw (7425) substation on the LCRA TSC 138 kV transmission line T-464 from AEP Hamilton Road (8255) - Uvalde (8234) |  | Odlaw | Hamilton Road/Uvalde | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2012-10-01 |  | 138 | 0 | 0 | 0.0 | 0 | KINNEY |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N | Generation Interconnection -Coordinate with AEP
12TPIT0160 | Clear Creek Substation terminal equipment | Upgrade terminal equipment at Clear Creek Substation in the Killeen Switch - Lampasas 138 kV line |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R760A, B & C-WAC | 2012-10-01 |  | 138 | 0 | 0 | 0.0 | 0 | BELL |  | Tier 4 |  |  |  | 3628 | Y | N
12TPIT0115 | Bullick Hollow Substation (7535) | Construct a new 4 breaker ring-bus to serve load at Austin Energy's WTP#4. New substation will be constructed approximately 3.7 miles north of Marshall Ford Substation on T-325. |  | Bullick Hollow | Marshall Ford/Balcones | Planned |  | PEC | Randy Buchanan (830) 868-6058 |  | 2012-10-10 |  | 138 | 0 | 2.3 | 0.0 | 0 | WILLIAMSON | WILLIAMSON | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
12TPIT0028 | Twin Buttes to Big Hill | Construct a new double circuit capable 345 kV transmission line (approximately 31 miles) between the existing LCRA TSC Twin Buttes (76009) and new Big Hill station (76003). The new transmission line will consist of Cumberland conductor to provide a thermal rating of 2988 MVA. |  | Twin Buttes | Big Hill | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2012-10-12 |  | 345 | 31 | 0 | 0.0 | 0 | TOM GREEN | SCHLEICHER | CREZ |  |  |  | SEE PROJECT DESCRIPTION | Y | N
12TPIT0087 | Wilson Substation | Add T2, 138kV-13.09x26.18 dual kV, 40 MVA PWT w/associated bus, structures, panels, etc | [5 empty] | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2012-10-18 |  | 138 | 0 | 0 | 0.0 | 0 | WILSON |  | Tier 4 |  |  |  | See Project Title | N | N
15TPIT0012 | Petteway to Ben Hur | Rebuild Petteway to Ben Hur 69 kV line with 795 ACSR |  | Petteway | Ben Hur | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10046 | 2012-10-25 |  | 69 | 0 | 23.59 | 0.0 | 0 | ROBERTSON | LIMESTONE | Tier 4 |  |  |  | 93, 85, 99 | Y | N
12TPIT0102 | Lone Tree: Construct 69 kV Station | Lone Tree Station: Construct New Distribution Substation in the Victoria to Leary Lane 69 kV transmission line. | Changed Status | Lone Tree |  | Under Construction | 555 - 0496 | AEP/TCC | Dave Goetz 918-599-2653 | 2555 | 2012-10-30 |  | 69 | 0 | 0 | 0 | 0 | VICTORIA |  | Tier 4 |  |  |  | 88179 | Y | N
12TPIT0137 | New Barksdale: Construct new 69 kV Substation including box bay structure interconnection | Add new 69 kV New Barksdale Substation for PEC distribution interconnection |  | New Barksdale |  | Under Construction | 469 - 0671 | AEP/ETT | Eric Scott 918-599-2653 | 3343 | 2012-10-31 |  | 69 | 0 | 0 | 0 | 0 | EDWARDS | EDWARDS | Tier 4 |  |  |  | 8365 | Y | N | 8365
12TPIT0187 | La Quinta: Add 138 kV breaker terminal for WF interconnect | Construct a 138 kV breaker terminal at La Quinta for the Whitetail WF Interconnect | Update In-Service Date | LaQuinta |  | Under Construction | 574-0751 | AEP/ETT | Kenneth 'Rich' Haley 918-599-2653 | 3456 | 2012-10-31 |  | 138 | 0 | 0 | 0 | 0 | WEBB | 0 | TIER 4 | 0 | 0 | 0 | 80439 | Y | N | 0 | 0
12TPIT0208 | Goldsmith Gulf Substation Conversion | Convert service to substation to 138 kV |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8049-E | 2012-11-01 |  | 138 | 0 | 0 | 0 | 0 | ECTOR |  | Tier 4 |  |  |  | 1260 | Y | N
12TPIT0215 | Odessa North 138/69 kV autotransformer | Replace existing autotransformer with a larger autotransformer |  |  |  | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8110-E | 2012-11-01 |  | 138 | 0 | 0 | 125 | 0 | ECTOR |  | Tier 4 |  |  |  | 1123, 1122 | Y | N
12TPIT0201 | Highlands - West rebuild | Rebuild Highlands - West 138 kV transmission line with 795 ACSS conductor. |  | Highlands | West | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE08312 | 2012-11-02 |  | 138 | 0 | 1.6 | 0.0 | 0 | Denton | Denton | Tier 4 |  |  |  | 37050, 37060 | Y | N
13TPIT0172 | Highlands Switching Station upgrade | Upgrade the Highlands 138 kV Switching Station to 3000 Amp. |  | Highlands |  | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE08412 | 2012-11-02 |  | 138 | 0 | 0 | 0.0 | 0 | Denton |  | Tier 4 |  |  |  | 37050 | Y | N
12TPIT0068 | South Bend Switch to Morris Sheppard Rebuild | Rebuild South Bend Switch to Morris Sheppard 69 kV line |  | South Bend Switch | Morris Sheppard | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 09008 | 2012-11-15 |  | 138 | 0 | 18.2 | 0.0 | 0 | YOUNG | PALO PINTO | Tier 4 |  |  |  | 795, 343 | Y | N
10TPIT0080 | Olney to South Bend Switch Rebuild | Rebuild Olney to South Bend Switch with 959ACSS |  | Olney | South Bend Switch | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 08011 | 2012-11-29 |  | 69 | 0 | 24 | 0.0 | 0 | YOUNG | YOUNG | Tier 4 |  |  |  | 788, 795 | Y | N
12TPIT0095b | South Lane - West Columbia Ckts. 04 & 60 | Upgrade 138kV Ckt.04 TXGULF - West Columbia to increase thermal ratings. | Delay as a result of ERCOT outage approval | TXGULF | West Columbia | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-11-30 |  | 138 | 0 | 27.53 | 0.0 | 0 | WHARTON | BRAZORIA | Tier 3 | 2011-02-02 | 2011-02-24 | N/A | 43340, 43011, 43120, 43380 | Y | N | See project 12TPIT0095a for total project cost estimate | Project is part of the 2011 ERCOT 5-Year Plan.
12TPIT0095d | South Lane - West Columbia Ckts. 04 & 60 | Upgrade substation equipment at TXGULF and West Columbia to increase thermal ratings. |  | TXGULF | West Columbia | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-11-30 |  | 138 | 0 | 0 | 0.0 | 0 | WHARTON | BRAZORIA | Tier 3 | 2011-02-02 | 2011-02-24 | N/A | 43340, 43011, 43120, 43380 | Y | N | See project 12TPIT0095a for total project cost estimate | Project is part of the 2011 ERCOT 5-Year Plan.
12TPIT0165 | Fairbanks - White Oak Ckt. 81 | Upgrade 138kV Ckt. 81 Fairbanks to Deihl to increase thermal ratings. | Change in project schedule | Fairbanks | Deihl | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-11-30 |  | 138 | 0 | 3.59 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 45760, 45730 | Y | N
12TPIT0165a | Fairbanks - White Oak Ckt. 81 | Upgrade 138kV Ckt. 81 Deihl to White Oak to increase thermal ratings. | Change in project schedule | Deihl | White Oak | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-11-30 |  | 138 | 0 | 4.05 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 45730, 46610 | Y | N | Cost included in main project
12TPIT0168 | WINFRE 138kV Substation | Construct service to new 138kV WINFRE customer-owned substation. Loop through Ckt. 86 Cities - Brine. |  | WINFRE | CITIES/ BRINE | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-11-30 |  | 138 | 0 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 4 |  |  |  | 40340, 40764, 40220 | Y | N
12TPIT0171 | HO Clarke - Knight Ckt. 08 | Upgrade 138kV Ckt.08 HO Clarke to Knight to increase thermal ratings. |  | HO Clarke | Knight | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-11-30 |  | 138 | 0 | 3.94 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 47150, 47331 | Y | N
14TPIT0058m | Mont Belvieu Area Upgrades | Install 73.3MVAR capacitor bank at Mont Belvieu substation. | Change in project schedule. | Mont Belvieu |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-11-30 |  | 138 | 0 | 0 | 0.0 | 73.3 | CHAMBERS |  | Tier 4 | 2012-02-03 | 2012-03-05 | N/A | 41111 | Y | N
12TPIT0205 | McCampbell: New substation Cut In | Customer construct 138kV substation. 138kV Cut-In on substation. | Changed to TCC asset | Dupont SS | Whitepoint SS | Planned | 561-0729 | AEP/TCC | Paul Hassink 918-599-2653 | 3435 | 2012-11-30 |  | 138 | 0 | 0 | 0 | 0 | SAN PATRICIO | 0 | Tier 4 | 0 | 0 | 0 | 0 | Y | N | 0 | 0
12TPIT0186 | Musquiz: Build new Switch Tap | Construct new Musquiz station along the Barrilla Junction to Permian Basin 138 kV line | Contact Update | Barrilla Junction | Permian Basin | Under Construction | 509 - 0723 | AEP/TNC | Michael Tallon 918-599-2653 | 2503 | 2012-11-30 |  | 138 | 0 | 0 | 0 | 0 | REEVES |  | Tier 4 |  |  |  |  | Y | N
12TPIT0203 | Musquiz: Build 138 kV point of delivery for Patriot Resources | Build 138 kV point of delivery from AEP's Musquiz tap to serve customer load. |  | Musquiz | Wolf Bone Tap | Planned | 12TPIT0186 | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE08812 | 2012-11-30 |  | 138 | 0 | 0 | 0.0 | 0 | Pecos |  | Tier 4 |  |  |  | 6673, 38300 | Y | N
11TPIT0110b | Valverde-AEP Weslaco Switch | Rebuild 4.5 Miles of 138kV line from Alberta Switch to Valverde Substation to AEP Weslaco Switch | Project Speedup due to delay with Alberta Switch-Doedyns | Weslaco Switch | Valverde | Planned | 07TPIT7777 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-12-01 |  | 138 | 0 | 4.5 | 0.0 | 0 | HIDALGO | HIDALGO | Tier 4 |  |  |  | 8759-8769-8354 | Y | N |  | Divided Project into two projects. Associated with Alberta Switch to Valverde
07TPIT0024 | Lytle: Add 138/69 kV Auto | Add CPS Lytle to ETT Lytle 795 ACSR 138 kV line and 93 MVA 69/138 kV autotransformer at Lytle |  | Lytle |  | Under Construction | 028 - 0028 | AEP/ETT | Terry Weeks (AEP) 918-599-2653 | 3373 | 2012-12-01 |  | 138 | 0 | 0 | 93 | 0 | MEDINA |  | Tier 4 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8962, 8622 | Y | N
11TPIT0040 | Uvalde 138 kV Substation Upgrade | Construct Uvalde to CPS Castroville 138 kV line with 2x795 ACSR utilizing open circuit for existing 69kV circuits in ROW |  | Uvalde |  | Under Construction | 291 - 0046 | AEP/TCC | Terry Weeks (AEP) 918-599-2653 | 1525 | 2012-12-01 |  | 138 | 0 | 0 | 0 | 0 | UVALDE |  | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 |  | Y | N
09TPIT0121 | Sun Switch - Sacroc 138 kV line | Rebuild 138 kV line |  | Sun Switch | Sacroc | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R812-WAC | 2012-12-01 |  | 138 | 0 | 1.8 | 0.0 | 0 | SCURRY | SCURRY | Tier 4 |  |  |  | 1064, 1311 | Y | N
12TPIT0121 | Oran 138/69 kV autotransformer | Install second 138/69 kV autotransformer |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R598-WAC | 2012-12-01 |  | 138 | 0 | 0 | 50.0 | 0 | PALO PINTO |  | Tier 4 |  |  |  | 1571, 1572 | Y | N
12TPIT0159 | Windthorst 138 kV Switching Station | Build new switching station |  |  |  | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R911-WAC | 2012-12-01 |  | 138 | 0 | 0 | 0.0 | 0 | ARCHER |  | Tier 4 |  |  |  | 1475 | Y | N
10TPIT0125 | Killeen Switch | Install circuit breakers and second 345/138 kV autotransformer |  |  |  | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C006-WA | 2012-12-01 |  | 345 | 0 | 0 | 600.0 | 0 | BELL |  | CREZ |  |  |  | 3422, 3423 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. The autotransformer was placed in service in 12/2010.
11TPIT0059 | Odessa EHV Switch #2 | Build new switching station adjacent to existing switching station |  |  |  | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C1010-E | 2012-12-01 |  | 345 | 0 | 0 | 0.0 | 0 | ECTOR |  | CREZ |  |  |  | 11028 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
12TPIT0036 | Brown - Newton 345 kV line | Construct double-circuit 345 kV line with one circuit |  | Brown | Newton | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C048-E | 2012-12-01 |  | 345 | 96 | 0 | 0.0 | 0 | BROWN | LAMPASAS | CREZ |  |  |  | 1444, 3690 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
12TPIT0037 | Newton - Killeen Switch 345 kV line | Construct double-circuit 345 kV line with one circuit. |  | Newton | Killeen Switch | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C049-E & C006B-E | 2012-12-01 |  | 345 | 27.9 | 0 | 0.0 | 0 | LAMPASAS | BELL | CREZ |  |  |  | 3690, 3422 | Y | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
12TPIT0038 | Brown - Killeen Switch 345 kV line | Add 345 kV circuit to the structures of the Brown - Newton - Killeen Switch line |  | Brown | Killeen Switch | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C048-E & C049-E | 2012-12-01 |  | 345 | 126.5 | 0 | 0.0 | 0 | BROWN | BELL | CREZ |  |  |  | 1444, 3691, 3422 | Y | Y | 2007-E7f | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. Cost estimate is included in the estimate for Brown - Newton - Killeen Switch 345 kV line.
12TPIT0039 | Newton Relay Booster Station | Construct a relay booster station |  |  |  | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C023-E | 2012-12-01 |  | 345 | 0 | 0 | 0.0 | 0 | LAMPASAS |  | CREZ |  |  |  |  | N | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
14TPIT0037 | Mount Enterprise Switching Station and 345 kV line | Reconfigure switching station and 345 kV lines from Martin Lake and Trinidad |  | Martin Lake | Mount Enterprise | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R6006-WAC | 2012-12-01 |  | 345 | 0 | 1.2 | 0.0 | 0 | GREGG |  | Tier 2 | 2010-11-01 | 2010-12-01 |  | 3116 | Y | N
12TPIT0093 | Switch Station Transformer Addition | Add 40 MVA Power Transformer. |  | 138 kV Switch S10009A | 138 kV Switch S12009A | Planned |  | COCS | Tony Michalsky 979- 764-3438 tmichalsky@cstx.gov |  | 2012-12-12 |  | 138 | 0 | 0 | 0.0 | 0 | BRAZOS |  | Tier 4 |  |  |  | 32000 | Y | N
11TPIT0026 | Cagnon - Install a Third 345kV Autotransformer | Install one 600 MVA autotransformer. | [5 empty] | CPS | Blake Williams |  | 2012-12-12 |  | 345 | 0 | 0 | 600.0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5055 5056 | Y | N |  | There are no transmission line additions associated with this project
11TPTI0173 | Substation CIP Security Project | Install physical and cyber security measures at each of TMPA's critical substations | Changes in CIP compliance timeframe for TMPA | Gibbons Creek, Shelby, Interchange | Gibbons Creek, Shelby, Interchange | Under Construction |  | TMPA | Eric Schroeder 936-873-1124 eschroeder@texasmpa.org | T11004 | 2012-12-12 |  | 345 | 0 | 0 | 0.0 | 0 | Grimes, Hunt |  | Tier 4 |  |  |  |  | N | N
09TPIT0060 | Buda-Turnersville | Replace under-rated limiting line terminal equipment at Buda to increase Buda (7498)-Turnersville (7500) to the conductor's rating. |  | Buda | Turnersville | Planned |  | PEC | Randy Buchanan (830) 868-6058 |  | 2012-12-16 |  | 138 | 0 | 0 | 0.0 | 0 | HAYS | HAYS | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
10TPIT0073 | Buda-Rutherford | Replace under-rated limiting line terminal equipment at Buda to increase Buda (7498)-Rutherford (7509) to the conductor's rating. |  | Buda | Rutherford | Planned |  | PEC | Randy Buchanan (830) 868-6058 |  | 2012-12-16 |  | 138 | 0 | 0 | 0.0 | 0 | HAYS |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
10TPIT0074 | Buttercup-Whitestone | Replace under-rated limiting line terminal equipment at Buttercup and Whitestone to increase Buttercup (7531)-Whitestone (7529) to the conductor's rating. |  | Buttercup | Whitestone | Planned |  | PEC | Randy Buchanan (830) 868-6058 |  | 2012-12-16 |  | 138 | 0 | 0 | 0.0 | 0 | WILLIAMSON | WILLIAMSON | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
10TPIT0082 | Carlton Switch to Mountary Rebuild | Rebuild Carlton Switch to Mountary with 959ACSS |  | Carlton | Mountary | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 08051 | 2012-12-21 |  | 69 | 0 | 9.6 | 0.0 | 0 | ERATH | COMANCHE | Tier 4 |  |  |  | 297, 294 | Y | N
10TPIT0012 | Barclay to Silver City Rebuild | Rebuild existing Barclay to Silver City 69kv line |  | Barclay | Silver City | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 05009 | 2012-12-26 |  | 69 | 0 | 17 | 0.0 | 0 | FALLS | MILAM | Tier 4 |  |  |  | 69,65 | Y | N
12TPIT0126 | Pyote cap bank | Install 10 MVAR, 69kV cap bank at Pyote Substation |  | Pyote |  | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE072AB | 2012-12-30 |  | 69 | 0 | 0 | 0.0 | 10 | Ward |  | Tier 4 |  |  |  | 38000 | Y | N
12TPIT0199 | Pecos cap bank | Install 10 MVAR, 69kV cap bank at Pecos Substation |  | Pecos |  | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE03812 | 2012-12-30 |  | 69 | 0 | 0 | 0.0 | 10 | Reeves |  | Tier 4 |  |  |  | 38090 | Y | N
12TPIT0200 | Hico cap bank | Install 6.6 MVAR, 69kV cap bank at Hico Substation |  | Hico |  | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE03212 | 2012-12-30 |  | 69 | 0 | 0 | 0.0 | 6.6 | Hamilton |  | Tier 4 |  |  |  | 37750 | Y | N
12TPIT0194 | Castroville Switch to Quihi | Rebuild the existing Castroville Switch to Quihi Sw 69 kV line with 795 ACSR at the same time AEP is constructing Uvalde to CPS Castroville 138 kV line with 2x795 ACSR. Utilizes open circuit for existing 69kV circuits in same ROW. Also removes the pole mounted switches that are Quihi Switch. |  | Castroville Switch | Quihi | Planned | 08TPIT0018 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-12-31 |  | 69 | 0 | 7.38 | 0 | 0 | MEDINA | MEDINA | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 5805, 5807, 5821 | Y | N |  | The cost for this project appears low, but the cost of the towers is in the associated separate project.
12TPIT0183 | Gonzales: Add terminal position and rebuild 2.2.mile 69 kV line to Acacia Solar Farm | Interconnect Acacia Solar Farm into the Gonzales 69 kV station, rebuild 69 kV line with 477 ACSR | Contact Update | Gonzales |  | Under Construction | 513 - 0710 | AEP/ETT | Frank Pritzlaff 918-599-2653 | 2568 | 2012-12-31 |  | 69 | 0 | 2.2 | 0 | 0 | PRESIDIO | PRESIDIO | Tier 4 |  |  |  |  | Y | N
12TPIT0099 | Knippa to Sabinal 69 kV line, transfer to new 138/69 double circuit line | Construct Uvalde to CPS Castroville 138 kV line with 2x795 ACSR utilizing open circuit for existing 69kV circuits in ROW |  | Knippa | Sabinal | Under Constuction | 291 - 0046 | AEP/TCC | Terry Weeks (AEP) 918-599-2653 | 1521 | 2012-12-31 |  | 69 | 0 | 8.5 | 0 | 0 | UVALDE | MEDINA | Tier 4 |  |  |  |  | Y | N
12TPIT0100 | Uvalde to Knippa 69 kV line, tranfer to new 138/69 double circuit line | Construct Uvalde to CPS Castroville 138 kV line with 2x795 ACSR utilizing open circuit for existing 69kV circuits in ROW |  | Uvalde | Knippa | Under Constuction | 291 - 0046 | AEP/TCC | Terry Weeks AEP) 918-599-2653 | 1520 | 2012-12-31 |  | 69 | 0 | 4.5 | 0 | 0 | UVALDE | MEDINA | Tier 4 |  |  |  |  | Y | N
12TPIT0108 | Wolfgang, Build new Switch Tap | Interconnect Mozart Wind Farm at Wolfgang to connect Mozart to the Jayton to Rotan 69 kV line |  | Jayton | Rotan | Planned | 493 - 695 | AEP/TNC | Dave Goetz 918-599-2653 | 2441 | 2012-12-31 |  | 69 | 0 | 0 | 0 | 0 | KENT | FISHER | Tier 4 |  |  |  |  | Y | N
15TPIT0014 | Wink-Cochise-Pecos 69kV rebuild | Rebuild the Oncor Wink - TNMP Wink and TNMP Wink - Cochise - Pecos 69 kV lines with 795 ACSR conductor. Upgrade terminal equipment at TNMP Wink, Cochise, and Pecos stations. |  | Wink | Pecos | Under Construction |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE08711 | 2012-12-31 |  | 69 | 0 | 33.12 | 0.0 | 0 | Reeves | Winkler | Tier 3 | 2011-07-08 | 2011-08-24 | N/A | 1075, 37921, 37922, 38160, 38090 | Y | N |  | Rebuild of all three line sections was completed in May 2012. Terminal equipment upgrades at TNMP Wink, Cochise, and Pecos should be completed by the end of 2012.
11TPIT0174 | Nall to Briarcrest Upgrade | Upgrade 0.82 miles of conductor from 2/0 ACSR to 795 ACSR and replace transmission poles as needed. |  | Nall Lane Substation | Briarcrest Substation | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2012-12-31 |  | 69 | 0 | 0.82 | 0.0 | 0 | BRAZOS | BRAZOS | Tier 4 |  |  |  |  | N | N
12TPIT0095c | South Lane - West Columbia Ckts. 04 & 60 | Upgrade substation equipment at South Lane and TXGULF to increase thermal ratings. |  | South Lane | TXGULF | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-12-31 |  | 138 | 0 | 0 | 0.0 | 0 | WHARTON | WHARTON | Tier 3 | 2011-02-02 | 2011-02-24 | N/A | 43190, 43012, 43340 | Y | N | See project 12TPIT0095a for total project cost estimate | Project is part of the 2011 ERCOT 5-Year Plan.
12TPIT0129 | Industrial Substation Conversion | Convert Industrial substation from double-tap to 138kV loop service Ckt. 84. | Change in project schedule. | Industrial | Haden/Port | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-12-31 |  | 138 | 0 | 0.1 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 40841, 40842 | Y | N
12TPIT0130 | Oates Substation Conversion | Convert Oates substation from double-tap to 138kV loop service Ckt. 08. |  | Oates | Anbush/Greens Bayou | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-12-31 |  | 138 | 0 | 0.1 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 41191, 41192 | Y | N
12TPIT0167 | Crockett - Hardy Ckt. 91 | Upgrade 138kV Ckt. 91 Crockett - Northside tap to increase thermal ratings. |  | Crockett | Northside | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-12-31 |  | 138 | 0 | 2.53 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 47570, 47711 | Y | N
12TPIT0169 | Bellaire - Ulrich Ckt. 35 | Upgrade 138kV Ckt. 35 Bellaire to Ulrich to increase thermal ratings. |  | Bellaire | Ulrich | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-12-31 |  | 138 | 0 | 3.39 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 47011, 47441 | Y | N
12TPIT0178 | LaMarque 69kV Substation Removal | Convert LaMarque Sub from 69kV to 138kV and remove 69kV facilities |  | EXTER | HASTINGS | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-12-31 |  | 138 | 0.1 | 0 | 0.0 | 0 | HARRIS | BRAZORIA | Tier 4 |  |  |  | 42600, 42860, 42820 | Y | N
14TPIT0030 | Bellaire - HO Clarke Ckt. 09 | Upgrade substation equipment to increase thermal ratings. |  |  |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-12-31 |  | 138 | 0 | 0 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 47010, 47050, 47150 | Y | N
08TPIT0018 | Uvalde to Castroville, build 138 kV line, double circuit capable | Construct Uvalde to CPS Castroville 138 kV line with 2x795 ACSR utilizing open circuit for existing 69kV circuits in ROW |  | Uvalde | Castroville | Under Construction | 291 - 0046 | AEP/ETT | Terry Weeks (AEP) 918-599-2653 Hector Torres (CPS) 210-353-2404 | 1522 | 2012-12-31 |  | 138 | 77.5 | 0 | 0 | 0 | UVALDE | MEDINA | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 5430, 8234 | Y | N
12TPIT0189 | Orlando: Build new Tap | Interconnect Blue Summit Wind Farm at Orlando to connect Blue Summit to the Lake Pauline to Vernon Main 138 kV line |  | Lake Pauline | Vernon Main | Planned | 506 - 0717 | AEP/ETT | Dave Goetz 918-599-2653 | 2512 | 2012-12-31 |  | 138 | 0 | 0 | 0 | 0 | WILBARGER |  | Tier 4 |  |  |  |  | Y | N
07TPIT0027 | CPS Lytle to ETT Lytle: Build 138 kV Line and CPS Lytle Substation Upgrades | Add CPS Lytle to ETT Lytle 795 ACSR 138 kV line and 93 MVA 69/138 kV autotransformer at Lytle |  | CPS Lytle | ETT Lytle | Under Construction | 028 - 0028 | AEP/ETT/CPS | Terry Weeks (AEP) 918-599-2653 Hector Torres (CPS) 210-353-2404 | 21 | 2012-12-31 |  | 138 | 4 | 0 | 0 | 0 | BEXAR | MEDINA | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 5290, 8962 | Y | N |  | There are no transformers associated with this project
12TPIT0104 | Rio Hondo: Add 138 kV double breaker terminal for WF Interconnect | Construct a 138 kV double breakered terminal at Rio Hondo for the Los Vientos WF Interconnect | Updated 'Other' Field | Rio Hondo |  | Under Construction | 487 - 0689 | AEP/TCC | Rich Haley 918-599-2653 | 3365 | 2012-12-31 |  | 138 | 0 | 0 | 0 | 0 | CAMERON |  | Tier 4 |  |  |  | 8319 | Y | N |  | Backfeed anticipated in Oct, 2012
12TPIT0204 | Construct: Catarina 138 kV station | Contruct new Catarina station on Asherton to North Laredo 138 kV line | Corrected Associated Projects Number | Catarina |  | Planned | 590-0760 | AEP/TCC | Paul Hassink 918-599-2655 | 3455 | 2012-12-31 |  | 138 | 0 | 0 | 0 | 0 | DIMMIT |  | Tier 4 |  |  |  | 8970 | Y | N
12TPIT0190 | Boots: Build 138 kV Box Bay Structure with three breakers | Interconnect White Camp Solar Farm at Boots to connect White Camp to the Spur to Sun 138 kV line | Transmission Status Update | Spur | Sun | Under Construction | 507 - 0718 | AEP/TNC | Eric Scott 918-599-2653 | 2502 | 2012-12-31 |  | 138 | 0 | 0 | 0 | 0 | KENT |  | Tier 4 |  |  |  |  | Y | N
13TPIT0079 | Alvin-North Alvin rebuild | Rebuild Alvin to North Alvin 138 kV transmission line with 795 ACSS conductor. Upgrade terminal equipment at Alvin Substation. |  | Alvin | North Alvin | Under Construction |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | STE07211 | 2012-12-31 |  | 138 | 0 | 2.08 | 0.0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 39015, 39030 | Y | N |  | Line rebuild completed on June 1, 2012. Terminal equipment upgrades at Alvin Substation should be completed by the end of 2012.
12TPIT0153 | Cotulla Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-01-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | LA SALLE |  | Tier 4 |  |  |  | 5876 | Y | N
11TPIT0162 | Cordele 69 kV Substation | Construct new 69 kV load serving substation in the line between Edna and Ganado Switch |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-01-01 |  | 69 | 0 | 0 | 0.0 | 0 | JACKSON |  | Tier 4 |  |  |  | 5524 | Y | N
13TPIT0132 | Freer Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-01-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | WEBB |  | Tier 4 |  |  |  | 5880 | Y | N
12TPIT0097 | Cross substation | Construct new 138 kV load serving substation in San Miguel to Pearsall line. |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-01-01 |  | 138 | 0 | 0 | 0.0 | 0 | ATASCOSA |  | Tier 4 |  |  |  | 5707 | Y | N
13TPIT0066 | E C Mornhinweg | Construct a new 138 kV 959 ACSS transmission line between the GPI switching station (7459) and the new E C Mornhinweg substation (7463). |  | GPI | EC Mornhinweg | Planned |  | NBU | Greg Baumbach (830) 629-8441 gbaumbach@nbutexas.com |  | 2013-01-01 |  | 138 | 2.7 | 0 | 0.0 | 0 | COMAL | COMAL | Tier 2 | 2009-02-06 | 2009-06-01 | N/A | SEE PROJECT DESCRIPTION | Y | N
13TPIT0071 | Bullick Hollow 138kV Substation | Establish a new substation with (2) 50MVA unit transformers to serve the Water Treatment Plant |  | Bullick Hollow Substation | Bullick Hollow Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P070 PLAN_117_P355 | 2013-01-01 |  | 138 | 0 | 0 | 0.0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9162 | Y | N |  | Will add idev file to the cases
13TPIT0207 | Texas City Main Cap Bank | Install a New 25 MVAR 69 kV Cap Bank at Texas City Main Station and Retire the 14.4 MVAR Cap Bank at Amoco 69kV Bus |  | Texas City Main |  | Planned |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com |  | 2013-01-09 |  | 69 | 0 | 0 | 0 | 25 | GALVESTON |  | Tier 4 |  |  |  | 38650, 39140 | Y | N |  | Retired 14.4 MVAR 69kV Cap Bank at Amoco Station
12TPIT0202 | West Substation upgrade | Upgrade the 138 kV portion of the West substation to 3000 Amp. |  | West |  | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE03612 | 2013-01-23 |  | 138 | 0 | 0 | 0.0 | 0 | Denton |  | Tier 4 |  |  |  | 37060 | Y | N
12TPIT0132 | BARNES 138kV Substation | Construct service to new 138kV BARNES customer-owned substation. Loop through Ckt.88 SRB - ROHMAS |  | BARNES | SR Bertron/ROHMAS | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-01-30 |  | 138 | 0.1 | 0.4 | 0.0 | 0 | HARRIS |  | Tier 4 |  |  |  | 41355 | Y | N
13TPIT0118 | EL Campo: Add 138kV bay and breaker | EL Campo add 138kV bay: Add 138kV breaker and associated protection to accomodate LCRA's upgrade of the EL Campo-Altair 69kV line to 138kV. | Change Status | EL Campo |  | Under Construction | 560-0728 | AEP/TCC | Paul Hassink 918-599-2653 | 3434 | 2013-01-30 |  | 138 | 0 | 0 | 0 | 0 | WHARTON |  | Tier 4 |  |  |  | 8102 | N | N |  | No topology changes
13TPIT0144 | Central Dawson 69 kV POI/South Lamesa Sub | Tap the 69 kV Lamesa/Ackerly Line where the line intersects Dawson Co. Road 22 and construct a 10 MVA substation to replace a distribution metering point |  |  |  | Under Construction |  | Golden Spread/Lyntegar EC | Chris Koenig 806-349-5201 ckoenig@gsec.coop |  | 2013-02-01 |  | 69 | 0 | 0 | 0.0 | 0 | DAWSON | DAWSON | Tier 4 |  |  |  | 9413 | Y | N
12TPIT0149 | Cordele Capacitor | Add 19.2 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-02-01 |  | 69 | 0 | 0 | 0 | 19.2 | JACKSON |  | Tier 4 |  |  |  | 5524 | Y | N
13TPIT0185 | Fashing Capacitor | Add two 9.6 MVAR capacitors |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-02-01 |  | 69 | 0 | 0 | 0.0 | 19.2 | ATASCOSA |  | Tier 2 | 2011-12-16 | 2012-04-25 | N/A | 5716 | Y | N
13TPIT0165 | 1775 Driver Substation | Constuct new 2-30 MVA substation with ring bus to feed new and existing load | New | 1881 Skywest Breaker Yard | 0566 Midkiff Substation | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-02-01 |  | 138 | 0 | 0 | 0 | 0 | MIDLAND |  | Tier 4 | 2012-08-17 | on-going | N/A |  | N | N
13TPIT0166 | 1881 Skywest Breaker Yard | Construct new 1881 Skywest Breaker Station in conjuction with LCRA for new and existiong load moving to ERCOT, 1775 Driver Substation, 0566 Midkiff Substation, and 2058 Pembrook Substation | New | 1956 Substation | 1775 Driver Substation | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-02-01 |  | 138 | 0 | 0 | 0 | 0 | MIDLAND | UPTON | Tier 4 | 2012-08-17 | on-going | N/A |  | N | N
13TPIT0167 | Skywest Breaker Yard to Driver Substation 8175 Transmission Line | Construct 4 miles of new 138 Kv transmission line in an existing transmission line for 1775 Driver Substation | New | 1881 Skywest Breaker Yard | 1775 Driver Substation | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-02-01 |  | 138 | 2 | 0 | 0 | 0 | MIDLAND | MIDLAND | Tier 4 | 2012-08-17 | on-going | N/A |  | N | N
13TPIT0168 | Driver Substation to Midkiff Substation 7566 Transmission Line | Construct 4 miles of new 138 Kv transmission line in an existing transmission line for 1775 Driver Substation | New | 1775 Driver Substation | 0566 Midkiff Substation | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-02-01 |  | 138 | 2 | 0 | 0 | 0 | MIDLAND | REAGAN | Tier 4 | 2012-08-17 | on-going | N/A |  | N | N
13TPIT0200 | Lewisville Switch - Jones St 138 kV line | Increase rating of line |  | Lewisville Switch | Jones St | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2013-02-01 |  | 138 | 0 | 0.3 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  |  | 645, 1972 | Y | N
13TPIT0206 | Bone Springs 69 kV Tap | This project will tap TNMP's Wink to Cochise 69kV line to serve the Bone Springs customer load. |  | Wink | Bone Springs Tap | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com |  | 2013-02-20 |  | 69 | 0 | 0 | 0 | 0 | WARD | WARD | Tier 4 |  |  |  | 38170, 38175 | Y | N |  | Bone Springs Tap will be Approximately 3.48 Miles from Cochise.
13TPIT0117 | Sunniland 69 kV substation: STEC Interconnect | Sunniland 69 kV STEC Interconnection: Construct 69 kV Substation Including Motor Operated Switches with Interconnection on Pleasanton - Three Rivers 69kV line. | Changed Status | Sunniland |  | Under Construction | 556-0716 | AEP/TCC | Kenneth Haley 918-599-2653 | 3431 | 2013-02-25 |  | 69 | 0 | 0 | 0 | 0 | LIVE OAK |  | Tier 4 |  |  |  | 8406 | Y | N
12TPIT0098 | Bruni relay upgrade | Additional relays will be installed to allow the autotransformer to be normally closed. |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-02-28 |  | 138 | 0 | 0 | 0.0 | 0 | WEBB |  | Tier 4 |  |  |  | 5887, 5888 | Y | N
12TPIT0157 | West Sinton Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-03-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | SAN PATRICIO |  | Tier 4 |  |  |  | 5622 | Y | N
13TPIT0184 | Poteet Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-03-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | ATASCOSA |  | Tier 2 | 2011-12-16 | 2012-04-25 | N/A | 5710 | Y | N |  | This location was chosen for a capcitor bank because there is not room for a capacitor bank at Pleasanton unless more land is purchased.
13TPIT0197 | Pleasanton Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-03-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | ATASCOSA |  | Tier 2 | 2011-12-16 | 2012-04-25 | N/A | 5714 | Y | N
12TPIT0172 | Western Dawson 138 kV POI/Patricia Sub | Tap the 138 kV Andrews/Lamesa Line where the line intersects FM 829. Build 7.5 miles of 138 kV transmission south to new Patricia Sub, which will be loaded approximately 5 MVA when energized. |  |  |  | Under Construction |  | Golden Spread/Lyntegar EC | Chris Koenig 806-349-5201 ckoenig@gsec.coop |  | 2013-03-01 |  | 138 | 7.5 | 0 | 0.0 | 0 | DAWSON | DAWSON | Tier 4 |  |  |  | 9418 | Y | N
12TPIT0196 | 0274 Gardendale Substation | Transfer 0274 Gardendale Substation into ERCOT | New | Oncor Moss 138 KV | Oncor Midland East 138 KV | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-03-01 |  | 138 | 0 | 0 | 0 | 0 | MIDLAND |  | Tier 4 |  |  | n/a |  | N | N
13TPIT0139 | Greenville 138kV Line Rebuild Olinger to Interchange to Shelby Tap | Replace wooden transmission structures and install new conductor on approximately 25 miles of line |  | Olinger | Greenville Interchange | Planned |  | TMPA | Eric Schroeder 936-873-1124 eschroeder@texasmpa.org |  | 2013-03-01 |  | 138 | 0 | 25 | 0.0 | 0 | Hunt |  | Tier 4 |  |  |  |  | N | N
12TPIT0135 | Spring to Bridgeport Switch | Rebuild 30.3 miles of line with 959 ACSS |  | Spring | Bridgeport Switch | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 11008 | 2013-03-01 |  | 138 | 0 | 33.3 | 0.0 | 0 | COOKE | WISE | Tier 4 |  |  |  | 684, 587, 634, 992 | Y | N
13TPIT0048 | Scurry County (Central A) - West Shackelford (Central C) | CREZ Assigned Project to build West Shackelford (Central C) substation in Shackelford county and double ckt 345 kV lines from Scurry County sub (Oncor Central A facility) to West Shackelford substation utilizing 2-1590 ACSS/TW "Falcon" conductor; Approximate route distance is 103 miles. Two 100 MVAR (2 x -100) shunt reactors will be placed on the line terminals to Sam Switch and Navarro at West Shackelford (one on each circuit). |  | Scurry County South | West Shackelford | under construction |  | Lone Star Transmission, LLC | Shirley Mathew 512-236-3144 shirley.mathew@lonestar-transmission.com |  | 2013-03-01 |  | 345 | 206.2 | 0 | 0.0 | -200 | SCURRY | SHACKELFORD | CREZ | N/A | N/A | N/A | West Shackelford 68000 | Y | N
13TPIT0049 | West Shackelford (Central C) - Sam Switch/Navarro | CREZ Assigned Project to build double ckt 345 kV lines from S West Shackelford -Romney-Kopperl-Sam Switch and Shackelford -Romney-Kopperl-Navarro transmission lines utilizing 2-1590 ACSS/TW "Falcon" conductor; Approximate route distance is 190 miles between West Shackleford and Sam Switch and 225 miles between West Shackleford and Navarro stations. Series compensators will be installed at Romney and Kopperl substations, in addition to 4 - 4x50 MVAr reactor banks at Romney substation. |  | West Shackelford | Circuit 1 - Sam Switch Circuit 2 - Navarro | under construction |  | Lone Star Transmission, LLC | Shirley Mathew 512-236-3144 shirley.mathew@lonestar-transmission.com |  | 2013-03-01 |  | 345 | 414.1 | 0 | 0.0 | -200 | SHACKELFORD | HILL / NAVARRO | CREZ | N/A | N/A | N/A | Romney 1 W 68010 Romney 2 W 68050 Romney 1 E 68020 Romney 2 E 68060 Kopperl 1 W 68030 Kopperl 2 W 68070 Kopperl 1 E 68040 Kopperl 2 E 68080 Sam Switch 68090 Navarro 68091 Sam Reactr 68005 Nav Reactr 68006 | Y | N | Revised as of 3/7/2012 - LST plans to cut-in and energize Navarro and Sam Switch and Navarro switchyards (only) on existing Oncor lines according to the following schedule: • Navarro (first set of lines) - October 1 - 15, 2012 (Navarro is energized after this outage concludes) • Navarro (second set of lines) - October 16 - November 2, 2012 (Navarro fully operational) • Sam Switch - November 3 - 17, 2012 (Sam Switch fully operational) (Above schedule subject to ERCOT approvals to be confirmed mid-July) | Project scope also include two series capacitor bank stations (Kopperl, Romney) equally spaced between West Shackelford and Sam Switch consisting of two series capacitor banks rated at 683 MVAR and 817 MVAR, with associated switches and line terminals and associated components at both Sam Switch and Navarro substations. There will be 4 x 50 MVAR shunt reactor banks at Romney, 2 x 50 MVAR on the east side of the series capacitors and 2 x 50 MVAR on the west side.
12TPIT0049 | LS04 Silverton to Cottonwood | Construct a new 345kV double circuit line from Silverton switching station to WETT's Cottonwod switching station | New | Cottonwood | Silverton | Planned | 12TPIT0050 | SU | Mark Caskey, (214) 978-8243, mcaskey@sharyland.com |  | 2013-03-01 |  | 345 | 64.5 | 0 | 0.0 | 0 | BRISCOE | DICKENS | CREZ |  |  |  | 99103-99104 | Y | N |  | Per one year compliance filing under PUC Docket # 37858
12TPIT0050 | Silverton Collection Station | Construct the new 345 kV Silverton switching station.Initial build is 14 element folded breaker and one half bus arrangement. | New |  |  | Planned | 12TPIT0049 | SU | Mark Caskey, (214) 978-8243, mcaskey@sharyland.com |  | 2013-03-01 |  | 345 | 0 | 0 | 0.0 | 100 -50 | BRISCOE |  | CREZ |  |  |  | 99103 | Y | N |  | Per one year compliance filing under PUC Docket # 37858
13TPIT0143 | El Campo - Ricebird - Nada Transmission Line Upgrade and Substation Addition | Construct a new 138 kV Ricebird Substation (78104) and terminate the 138 kV transmission lines from El Campo (8102) and Nada (78103) at the Ricebird Substation. Install a new 60MVA 138/69kV autotransformer at the Nada substation. |  | El Campo Substation | Nada Substation | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-03-04 |  | 138 | 0 | 17.5 | 60.0 | 0 | COLORADO | WHARTON | Tier 3 | 2011-10-14 | 2011-11-09 | N/A | SEE PROJECT DESCRIPTION | Y | N |  | Coordinate this project with STEC
13TPIT0051 | Gray to Tesla, build double circuit 345 kV line | Build new Gray Substation (Panhandle B-B) including 150 to 200 MVAR of reactive compensation and 345 kV double circuit line from Gray to Tesla | Updated Project Cost based on Approved CCN and revised bus numbers | Gray | Tesla | Planned |  | CTT | Tim Cook 636-534-3310 Tcook@LSPower.com |  | 2013-03-09 |  | 345 | 218 | 0 | 0.0 | 0 | GRAY | CHILDRESS | CREZ |  |  |  | 79000-60501, CKT 1 & 79000-60501, CKT 2 | Y | Y
13TPIT0052 | Gray Substation (Panhandle B-B), build new collector substation | Build new Gray Substation (Panhandle B-B) including 150 to 200 MVAR of reactive compensation and 345 kV double circuit line from Gray to Tesla | Updated Project Cost. | - | - | Planned |  | CTT | Tim Cook 636-534-3310 Tcook@LSPower.com |  | 2013-03-09 |  | 345 | 0 | 0 | 0.0 | 0 | GRAY | - | CREZ |  |  |  | 79000 | Y | N
13TPIT0053 | Gray Substation (Panhandle B-B), build 150 to 200 MVAR of Reactive Compensation | Build new Gray Substation (Panhandle B-B) including 150 to 200 MVAR of reactive compensation and 345 kV double circuit line from Gray to Tesla | Updated Project Cost. | - | - | Planned |  | CTT | Tim Cook 636-534-3310 Tcook@LSPower.com |  | 2013-03-09 |  | 345 | 0 | 0 | 0.0 | -200 | GRAY | - | CREZ |  |  |  | 79000 | Y | N
10TPIT0070 | Magruder to North Victoria: Rebuild 69 kV Line | Reconductor Magruder to North Victoria 69 kV line to 795 ACSS. Install 138/69 kV, 187 MVA, autotransformer at Magruder on the Victoria to Thomaston 138kV line. | Changed Status | Magruder | North Victoria | Under Construction | 389 - 0567 | AEP/TCC | Dave Goetz 918-599-2653 | 3261 | 2013-03-13 |  | 69 | 0 | 3.7 | 0 | 0 | VICTORIA | VICTORIA | Tier 4 |  |  |  |  | Y | N
07TPIT0250 | Lone Tree: Install 1-14.4 MVAR 69 kV Cap Banks | Add capacitors in Victoria area at the McGruder Victoria plant and Lone Tree | Date Change | Lone Tree |  | Planned | 389 - 0667 | AEP/TCC | Dave Goetz 918-599-2653 | 2047 | 2013-03-13 |  | 69 | 0 | 0 | 0 | 14.4 | VICTORIA |  | Tier 4 |  |  |  |  | Y | N
13TPIT0202 | Barstow Tap cap bank | Install 10 MVAR, 69kV cap bank at Barstow Tap Substation |  | Barstow Tap |  | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com |  | 2013-03-13 |  | 69 | 0 | 0 | 0.0 | 10 | REEVES |  | Tier 4 |  |  |  | 38150 | Y | N
11TPIT0076 | Cottonwood 345 kV Station and Cotttonwood to Dermott 345 kV line | Establish new 345 kV Cottonwood station and construct a new double circuit 345 kV transmission line WETT new Cottonwood and Oncor's Dermott 345 kV stations. Includes 2x50 MVAR shunt reactor banks at Cottonwood. |  | Cottonwood | Dermott | Planned |  | Wind Energy Transmission Texas (WETT) | Julius Horvath (512) 279-7377 julius.horvath@windenergyoftexas.com |  | 2013-03-13 |  | 345 | 74.2 | 0 | 0.0 | 2 x -50 | DICKENS | SCURRY | CREZ |  |  |  | 59904 | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases
12TPIT0056 | Grelton 345 kV Station and Grelton to Long Draw 345 kV line | Establish new 345 kV Grelton station and construct a new single circuit, double circuit capable 345 kV transmission line between new Grelton and new Long Draw 345 kV stations. Includes 1x50 MVAR shunt capacitor bank at Grelton. |  | Grelton | Long Draw | Planned |  | Wind Energy Transmission Texas (WETT) | Julius Horvath (512) 279-7377 julius.horvath@windenergyoftexas.com |  | 2013-03-14 |  | 345 | 55.4 | 0 | 0.0 | 50 | MARTIN | BORDEN | CREZ |  |  |  | 59901 | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases
12TPIT0057 | Grelton to Odessa 345 kV line | Construct a new single circuit, double circuit capable 345 kV transmission line between WETT's new Grelton and Oncor's existing Odessa 345 kV stations. |  | Grelton | Odessa | Planned |  | Wind Energy Transmission Texas (WETT) | Julius Horvath (512) 279-7377 julius.horvath@windenergyoftexas.com |  | 2013-03-15 |  | 345 | 49.9 | 0 | 0.0 | 0 | MARTIN | SCURRY | CREZ |  |  |  |  | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases
12TPIT0058 | Long Draw 345 kV Station and Long Draw to Scurry County South 345 kV line | Establish new 345 kV Long Draw station and construct a new double circuit 345 kV transmission line between WETT's new Long Draw and Oncor's Scurry County South 345 kV stations. |  | Long Draw | Scurry | Planned |  | Wind Energy Transmission Texas (WETT) | Julius Horvath (512) 279-7377 julius.horvath@windenergyoftexas.com |  | 2013-03-16 |  | 345 | 50.7 | 0 | 0.0 | 0 | BORDEN | SCURRY | CREZ |  |  |  | 59900 | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases
13TPIT0205 | Barilla Draw 69 kV Tap | This project will tap TNMP's IH20 to Flattop 69kV line to serve the Barilla Draw Field customer load and Install a 15 MVAR 69 kV Cap Bank at Barilla Draw Station |  | IH20 | Barilla Draw Tap | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com |  | 2013-03-20 |  | 69 | 0 | 0 | 0 | 15 | REEVES | REEVES | Tier 4 |  |  |  | 38060 | Y | N |  | Barilla Draw Tap will be Approximately 11.57 Miles from IH20
13TPIT0019 | Riley to Edith Clarke double circuit 345kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis |  | Riley | Edith Clarke | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2381 | 2013-03-25 |  | 345 | 86.6 | 0 | 0 | 0 | WILBARGER | COTTLE | CREZ |  |  |  |  | Y | N
13TPIT0023 | Edith Clarke 345kV station | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis |  | Edith Clarke |  | Under Construction | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2387 | 2013-03-25 |  | 345 | 0 | 0 | 0 | 0 | COTTLE |  | CREZ |  |  |  |  | Y | N
13TPIT0020 | Tesla to Edith Clarke double circuit 345kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis |  | Tesla | Edith Clarke | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2382 | 2013-03-27 |  | 345 | 110.4 | 0 | 0 | 0 | COTTLE | COTTLE | CREZ |  |  |  |  | Y | N
13TPIT0140 | Smiley Substation Addition | Replace existing station, add 138x69kV-13.09x26.18 dual kV, 12/16/20 MVA PWT w/associated structures, bus, panels, etc | [5 empty] | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2013-03-28 |  | 69 | 0 | 0 | 0.0 | 0 | GONZALES |  | Tier 4 |  |  |  | See Project Title | N | N
13TPIT0120 | Ricebird Station and autotransformer. | Construct 69 kV Ricebird station, install 150 MVA autotransformer, tie into El Campo to Round Mott Switch 69 kV line and connect 69 kV line from Nada at Ricebird. |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-03-31 |  | 69 | 0 | 0 | 150.0 | 0 | WHARTON |  | Tier 3 | 2011-10-14 | 2011-11-09 | N/A | 5535, 78104 | Y | N |  | Coordinated project with LCRA
11TPIT0111 | Snook to Koppe Bridge Transmission Line | Build 13 miles of 1033ACSR transmission line (operated at 138 kV) to Koppe Bridge substation. | The Thompson Creek to Koppe Bridge Line is now broken into two segments with different completion dates. | Snook Substation | Koppe Bridge | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2013-03-31 |  | 138 | 13 | 0 | 0.0 | 0 | BURLESON | BRAZOS | Tier 4 |  |  |  | 32863 32860 | Y | N
13TPIT0026 | Tesla 345kv Switching Station | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis **Complete but Not in Service** | Project Description Update | Tesla |  | Under Construction | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2393 | 2013-03-31 |  | 345 | 0 | 0 | 0 | 0 | COTTLE |  | CREZ |  |  |  |  | Y | N
13TPIT0028 | Tesla, add four 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis **Complete but Not in Service** | Project Description & Status Update | Tesla |  | Under Construction | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2395 | 2013-03-31 |  | 345 | 0 | 0 | 0 | -200 | COTTLE |  | CREZ |  |  |  |  | Y | N
13TPIT0024 | Edith Clarke, add two 130.9 MVar capacitors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Edith Clarke |  | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2389 | 2013-03-31 |  | 345 | 0 | 0 | 0 | +261.8 | COTTLE |  | CREZ |  |  |  |  | Y | N
13TPIT0025 | Edith Clarke, add four 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Edith Clarke |  | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2390 | 2013-03-31 |  | 345 | 0 | 0 | 0 | -200 | COTTLE |  | CREZ |  |  |  |  | Y | N
13TPIT0027 | Tesla, add two 130.9 MVar capacitors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Tesla |  | Under Construction | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2394 | 2013-03-31 |  | 345 | 0 | 0 | 0 | +261.8 | COTTLE |  | CREZ |  |  |  |  | Y | N
13TPIT0183 | Coy City Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-04-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | KARNES |  | Tier 2 | 2011-12-16 | 2012-04-25 | N/A | 5720 | Y | N |  | This location was chosen for 9.6 MVAR instead of having all 19.2 MVAR at Kenedy.
13TPIT0177 | Colorado - Nada Transmission Line Upgrade | Upgrade the 20 mile Colorado (7636) - Nada (5536) 69-kV transmission line to 795 ACSR 69-kV, 111 MVA. |  | Colorado | Nada | Planned |  | LCRA TSC/STEC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-04-01 |  | 69 | 0 | 20 | 0.0 | 0 | COLORADO | COLORADO | Tier 2 | 2012-02-01 |  |  | SEE PROJECT DESCRIPTION | Y | N
12TPIT0198 | 3852Colorado City Temp Interconnect | Temporary interconnect of 3852 Colorado City Substation to the Oncor transmission in ERCOT for load transfer | New | Big Spring Switch Yard | Oncor China Grove | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-04-01 |  | 138 | 0 | 0 | 0 | 0 | MARTIN |  | Tier 4 |  |  | n/a |  | N | N
11TPIT0085 | Doedyns-Sioux 138kV Line | Build New 138kV Line from Doedyns-Sioux Substations | Delays due to Right of Way process | Doedyns | Sioux | Planned | 06TPIT0166 | STEC | Doug Evans 361-485-6459 devans@stec.org | 789640 | 2013-04-01 |  | 138 | 5.5 | 0 | 0.0 | 0 | HIDALGO | HIDALGO | Tier 2 | 2005-02-01 | 2005-04-20 |  | 8753-8792 | Y | N
13TPIT0146 | Central Avenue Sub- 138kV Breaker Addition | Install 138kV Breakers |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-04-13 |  | 138 | 0 | 0 | 0.0 | 0 | CAMERON |  | Tier 4 |  |  |  | 8766 | Y | N
12TPIT0128 | WA Parish - Sienna Ckt. 02 | Upgrade 138 kV Ckt. 02 WA Parish to Sienna to increase thermal ratings. | Change in project scope | WA Parish | Sienna | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-04-30 |  | 138 | 0 | 4.2 | 0.0 | 0 | FORT BEND | FORT BEND | Tier 4 |  |  |  | 44651, 44010 | Y | N
13TPIT0141 | NORTON 138kV Substation | Construct service to new 138kV NORTON customer-owned substation. Loop through Ckt. 86 HACHER - ENPROD. |  | NORTON | HACHER/ ENPROD | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-04-30 |  | 138 | 1.98 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 4 |  |  |  | 40770, 40760, 40510 | Y | N
13TPIT0122 | Choate Station and Autotransformer | Build new Choate substation where Pawnee to Four Corners 138 kV and Kenedy to Charco 69 kV lines cross and add a 150 MVA 139/69 kV autotransformer |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-04-30 |  | 138 | 0 | 0 | 150.0 | 0 | KARNES |  | Tier 2 | 2011-12-16 | 2012-04-25 | N/A | 5728, 5729 | Y | N
12TPIT0109 | Laguna to Naval Base | Upgrade the 3.09-mile Laguna (8494)-Naval Base (8495) 69 kV transmission line to 69kV 959.6 ACSS , 194.71 MVA with 138 kV capable structures. |  | Laguna | Naval Base | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-05-01 |  | 69 | 0 | 3.09 | 0.0 | 0 | NUECES | NUECES | Tier 4 | 2012-07-06 | on-going | N/A | SEE PROJECT DESCRIPTION | Y | N
13TPIT0199 | Burrows 69 kV Capacitors | Install shunt capacitors |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R513-E | 2013-05-01 |  | 69 | 0 | 0 | 0 | 18.4 | HUNT |  | Tier 4 |  |  |  | 1829 | Y | N
11TPIT0024 | TCC - 138kV Line Reroutes | The following 138kV lines will be rerouted: Cagnon - AMDTP - AMD becomes Cagnon - AMD Cagnon - AMDTP - Pinn becomes Cagnon - Pinn Pinn - SWRI becomes Pinn - Westside Construct a new 138kV line from TCC - SWRI Cagnon - AMD line upgrade to 1590AAC |  | Cagnon Cagnon Pinn Rd TCC | AMD Pinn Rd Westside SWRI | Planned | S-0384 | CPS | T: Kevin Phillips | T-0106 | 2013-05-01 |  | 138 | 5.8 | 0 | 0.0 | 0 | BEXAR | BEXAR | Tier 2 | 2012-08-07 | on-going | N/A | 5423 5419 5345 5002 5004 5490 | Y | N |  | There are no transformers associated with this project
13TPIT0170 | 2570 East Stiles Substation | Construct new 2570 East Stiles Substaion, 30MVA | New | 2372 St. Lawerence Substation | 2168 Stiles Substation | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-05-01 |  | 138 | 2 | 0 | 0 | 0 | REAGAN |  | Tier 4 |  |  | n/a |  | N | N
13TPIT0127 | Tilden 138 kV Substation | Convert Tilden from 69 kV to 138 kV and connect to new 138 kV line from Tilden to George West. |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-05-01 |  | 138 | 0 | 0 | 0.0 | 0 | MCMULLEN |  | Tier 4 |  |  |  | 5701 | Y | N
13TPIT0129 | George West to Tilden Rebuild | Rebuild 4/0 ACSR 69 kV to double circuit 138 kV capable 795 ACSR. One circuit will be operated at 69 kV from George West to Choke Canyon Prison Sub. The other will be 138 kV from George West to Tilden |  | George West | Tilden | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-05-01 |  | 138 | 20.6 | 8.4 | 0.0 | 0 | MCMULLEN | LIVE OAK | Tier 4 |  |  |  | 5688, 5701 | Y | N
13TPIT0163 | Payne Switch | Upgrade 138 kV switching station |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4106-E | 2013-05-01 |  | 138 | 0.25 | 0 | 0.0 | 0 | GRAYSON |  | Tier 4 |  |  |  | 1758 | Y | N
12TPIT0051 | LS01 Silverton to Nazareth | Construct a new 345kV single circuit line from Silverton switching station to Nazareth switching station. | New | Silverton | Nazareth | Planned | 12TPIT0053 | SU | Mark Caskey, (214) 978-8243, mcaskey@sharyland.com |  | 2013-05-01 |  | 345 | 46 | 0 | 0.0 | 0 | BRISCOE | CASTRO | CREZ |  |  |  | 99103-99101 | Y | N |  | Per 6 month compliance filing under PUC Docket # 37858
12TPIT0053 | Nazareth Collection Station | Construct the new 345 kV Nazareth switching station.Initial build is 7 element ring bus arrangement. | New |  |  | Planned | 12TPIT0051 | SU | Mark Caskey, (214) 978-8243, mcaskey@sharyland.com |  | 2013-05-01 |  | 345 | 0 | 0 | 0.0 | -50 | CASTRO |  | CREZ |  |  |  | 99101 | Y | N |  | Per 6 month compliance filing under PUC Docket # 37858
13TPIT0091 | Big Hill Reactive Devices | Install two each 50 MVAR Reactor Banks and two each 72 MVAR Capacitor Banks at the Big Hill station (76003). | [5 empty] | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-05-01 |  | 345 | 0 | 0 | 0.0 | -100, 144 | SCHLEICHER |  | CREZ |  |  |  | SEE PROJECT DESCRIPTION | Y | N |  | Cost is included in the 12TPIT0028 project
13TPIT0186 | Trinidad second 345/138 kV autotransformer | Install 345/138 kV autotransformer |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R6015-E | 2013-05-01 |  | 345 | 0 | 0 | 450.0 | 0 | HENDERSON |  | Tier 4 |  |  |  | 3124, 3127 | Y | N
13TPIT0178 | Skywest | Cut in the new Skywest (71210) substation on the LCRA TSC Midkiff (1210) - Sprayberry (1329) 138kV transmission line. |  | Skywest | Midkiff/Sprayberry | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-05-02 |  | 138 | 0 | 0 | 0.0 | 0 | MIDLAND |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
13TPIT0077 | Kendall to Miller Creek to Paleface | Upgrade existing Kendall (7152) to Miller Creek (7148)line to 1433 ACSS/TW (Merrimack) and Miller (7148) Creek to Paleface (7476) line to 795 ACSR (Drake). |  | Kendall | Paleface | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-05-02 |  | 138 | 0 | 56.88 | 0.0 | 0 | KENDALL | BURNET | CREZ |  |  |  | SEE PROJECT DESCRIPTION | Y | N
11TPIT0038 | CSU Northgate Substation | Install (3) Breaker ring to include (2) 138 lines and tap to College Station Utilities | Name changed back to Northgate (from Finfeather) at CSU's request | CSU Northgate | CSU Northgate | planned |  | BTU/CSU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2013-05-06 |  | 138 | 0 | 0 | 0.0 | 0 | BRAZOS |  | Tier 4 |  |  |  |  | Y | N
12TPIT0111 | Kimbro | Cut in the new Kimbro (7337) substation on the LCRA TSC Gilleland Creek (7336) - Elgin (3650) 138kV transmission line. |  | Kimbro | Gilleland Creek/Elgin | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-05-23 |  | 138 | 0 | 0 | 0.0 | 0 | TRAVIS |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
13TPIT0115 | Barnhart SWTEC: Add 3.6 Mvar capacitor bank | Add 3.6 Mvar capacitor bank at Barnhart SWTEC and add 10 MVA DRCS with 7.2 Mvar capacitor bank at Yucca | Transmission Status Update | Barnhart |  | Planned | 558 - 0721 | AEP/TNC | Michael Tallon 918-599-2653 | 2560 | 2013-05-31 |  | 69 | 0 | 0 | 0 | +3.6 | IRION |  | Tier 4 |  |  |  |  | Y | N
13TPIT0156 | Katemcy: Add 7.2 Mvar capacitor bank | Add two 7.2 Mvar capacitor banks at North Brady and add 7.2 Mvar capacitor bank at Katemcy | Transmission Status Update | Katemcy |  | Planned | 559 - 0722 | AEP/TNC | Paul Hassink 918-599-2656 | 2562 | 2013-05-31 |  | 69 | 0 | 0 | 0 | +7.2 | MCCULLOCH | 0 | Tier 4 | 0 | 0 | 0 | 0 | Y | N | 0 | 0
12TPIT0081 | 36th St - New 138kV Substation | Loop new 138kV substation into existing 138kV Merida to Medina Base line and replace exiting Kelly Field #3 138kV substation | Delayed due to Budget Constraints | Merida | Medina Base | Planned | T-0161 | CPS | PM: Hector Torres | S-0578 | 2013-05-31 |  | 138 | 0.1 | 0 | 0.0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5427 5245 5305 5310 | Y | N |  | There are no transformers associated with this project
13TPIT0188 | Crabb River Road Substation Reconfiguration | Reconfigure 138kV Crabb River Road substation from loop to double tap. Tap Ckt.80 between WA Parish and Imperial. |  | Crabb River Road | WA Parish/Imperial | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-05-31 |  | 138 | 0.2 | 0 | 0.0 | 0 | FORT BEND | FORT BEND | Tier 4 |  |  |  | 44010, 44171, 44172, 44341, 44170 | Y | N |  | Part of Fort Bend Area Upgrades.
13TPIT0191 | Southwyck Cap Bank | Install 28.8MVAR capacitor bank at Southwyck substation. |  | Southwyck |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-05-31 |  | 138 | 0 | 0 | 0 | 28.8 | BRAZORIA |  | Tier 4 |  |  |  | 43260 | Y | N
13TPIT0192 | Lockwood Cap Bank | Install 14.4MVAR capacitor bank at Lockwood substation. |  | Lockwood |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-05-31 |  | 138 | 0 | 0 | 0 | 14.4 | HARRIS |  | Tier 4 |  |  |  | 46032 | Y | N
13TPIT0182 | Comanche cap bank | Install a 30 MVAR, 138 kV capacitor bank at Comanche Switching Station. |  | Comanche |  | Planned |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com |  | 2013-05-31 |  | 138 | 0 | 0 | 0.0 | 30 | Galveston |  | Tier 4 |  |  |  | 38560 | Y | N
10TPIT0048 | Koppe Bridge Substation | Install (4) Breaker ring to include (2) 138 lines and (1) 138/12.5 transformer |  | Koppe Bridge | Koppe Bridge | under construction | 10TPIT0049 | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2013-05-31 |  | 138 | 0 | 0 | 0.0 | 0 | BRAZOS |  | Tier 4 |  |  |  | 32860 | Y | N
13TPIT0083 | Snook Substation | Install (3) Breaker ring to include (2) 138 lines and (1) 138/69 auto transformer relocated from Thompson Creek. |  | Snook Substation | Snook Substation | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2013-05-31 |  | 138 | 0 | 0 | 0.0 | 0 | BURLESON |  | Tier 4 |  |  |  | 32857 32865 | Y | N
12TPIT0059 | Sand Bluff 345 kV Station and Sand Bluff to Divide 345 kV line | Establish new 345 kV Sand Bluff station and construct a new single circuit, double circuit capable 345 kV transmission line between WETT's new Sand Bluff and LCRA TSC's Divide 345 kV stations. |  | Sand Bluff | Divide | Planned |  | Wind Energy Transmission Texas (WETT) | Julius Horvath (512) 279-7377 julius.horvath@windenergyoftexas.com |  | 2013-05-31 |  | 345 | 37 | 0 | 0.0 | 0 | GLASSCOCK | COKE | CREZ |  |  |  | 59902 | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases
12TPIT0060 | Bearkat 345 kV Station and Bearkat to Sand Bluff 345 kV line | Establish new 345 kV Bearkat station and construct a new single circuit, double circuit capable 345 kV transmission line between WETT's new Sand Bluff and new Bearkat 345 kV stations. |  | Bearkat | Sandbluff | Planned |  | Wind Energy Transmission Texas (WETT) | Julius Horvath (512) 279-7377 julius.horvath@windenergyoftexas.com |  | 2013-05-31 |  | 345 | 28.9 | 0 | 0.0 | 0 | GLASSCOCK | STERLING | CREZ |  |  |  | 59903 | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases
12TPIT0061 | Sand Bluff to Long Draw 345 kV line | Construct a new single circuit, double circuit capable 345 kV transmission line between WETT's new Sand Bluff and new Long Draw 345 kV stations. |  | Sand Bluff | Long Draw | Planned |  | Wind Energy Transmission Texas (WETT) | Julius Horvath (512) 279-7377 julius.horvath@windenergyoftexas.com |  | 2013-05-31 |  | 345 | 77.4 | 0 | 0.0 | 0 | GLASSCOCK | BORDEN | CREZ |  |  |  |  | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases
13TPIT0102 | Greens Bayou Autotransformer Upgrade | Replace existing 400MVA Greens Bayou autotransformer A2 with 800MVA autotransformer. |  |  |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-05-31 |  | 345/138 | 0 | 0 | 400.0 | 0 | HARRIS |  | Tier 4 |  |  |  | 40700, 40716, 49019 | Y | N
13TPIT0103 | Obrien Autotransformer Upgrade | Replace existing 400MVA Obrien autotransformer A3 with 800MVA autotransformer. |  |  |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-05-31 |  | 345/138 | 0 | 0 | 400.0 | 0 | FORT BEND |  | Tier 4 |  |  |  | 44500, 44510, 49063 | Y | N
12TPIT0142 | Choate to Fashing Rebuild | Rebuild 4/0 ACSR 69 kV to 138 capable 795 ACSR. | The Fashing to Coy City line section is now needed due to newest load forecast. Changes prior quarter comment. | Choate | Coy City | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-06-01 |  | 69 | 0 | 30 | 0.0 | 0 | ATASCOSA | KARNES | Tier 2 | 2011-12-16 | 2012-04-25 | N/A | 5729, 5722, 5720 | Y | N
12TPIT0140 | South Batesville breaker addition | Adds breakers to South Batesville to allow closing of normally open South Batesville to Frio Town. Creates 3- terminal switching station |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-06-01 |  | 69 | 0 | 0 | 0.0 | 0 | ZAVALA |  | Tier 4 |  |  |  | 5848 | Y | N
13TPIT0164 | Big Oak 69 kV Substation | Build new load serving station in the 69 kV line between Beeville and Goliad Switch. |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-06-01 |  | 69 | 0 | 0 | 0.0 | 0 | GOLIAD |  | Tier 4 | 2012-08-31 | on-going | N/A | 5675 | Y | N
13TPIT0069 | Panther Springs - New 138kV Substation | Loop new 138kV substation into existing 138kV Hill Country to Stonegate circuit #1 line |  | Panther Springs | Hill Country/Stonegate | Planned | T-0172 | CPS | PM: Don Stanton | S-0616 | 2013-06-01 |  | 138 | 0.1 | 0 | 0.0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5331 5210 5415 | Y | N |  | There are no transformers associated with this project
15TPIT0006 | Bandera to Broadview - 138kV substation equipment upgrade | Upgrade substation equipment at Broadview to remove existing MLSE on the Bandera to Broadview 138kV line |  | Bandera | Broadview | Planned |  | CPS | PM: Ulrich Skerhut | S-0603 | 2013-06-01 |  | 138 | 0 | 0 | 0.0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5020 5040 | Y | N |  | There are no transformers associated with this project
13TPIT0187 | Harlandale to Sommers - 138 kV Transmission Line Rebuild | Rebuild approximately 40 circuit miles of 138 kV transmission from Harlandale to Sommers |  | Harlandale | Sommers | Conceptual | S-0732 | CPS | Blake Williams | T-0192 | 2013-06-01 |  | 138 | 0.1 | 40 | 0 | 0 | BEXAR | BEXAR | Tier 3 |  |  |  | 5190 5395 | Y | N |  | There are no transformers associated with this project
14TPIT0035 | Northgate Substaton Addition | Build new distibution substation in BTU transmission line from TAMU Substation to Atkins Substation |  | BTU Adkins 138 kV Line Switch 8027 | BTU Switch 8011 & BTU Switch 8042 @ TAMU 138 kV Substation (ring bus) | Planned |  | COCS/BTU | Tony Michalsky 979- 764-3438 tmichalsky@cstx.gov |  | 2013-06-01 |  | 138 | 0 | 0 | 0.0 | 0 | BRAZOS |  | Tier 4 |  |  |  | 32006 | Y | N
11TPIT0114 | Alberta Switch-Doedyns 138kV Line | Rebuild 3.1 Miles of 138kV line from Alberta Switch to Doedyns Substation | Delay Engineering Design | Alberta Switch | Doedyns | Planned | 07TPIT7777 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-06-01 |  | 138 | 0 | 3.1 | 0.0 | 0 | HIDALGO | HIDALGO | Tier 4 |  |  |  | 8753 - 8759 | Y | N
13TPIT0046 | Flatonia-Yoakum Gartner Road | Upgrade and convert the 27.7 mile Flatonia (7248)-Moulton (7236)-Henkhaus (7237)-Shiner (7238)-Yoakum Gartner Road (7242) 2/0 ACSR 69 kV transmission line to 795 ACSR 138 kV. |  | Flatonia | Yoakum Gartner Road | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-06-01 |  | 138 | 0 | 27.7 | 0.0 | 0 | FAYETTE | DEWITT | Tier 3 |  | 2009-03-01 |  | SEE PROJECT DESCRIPTION | Y | N
13TPIT0179 | McCarty Lane Terminal Equipment Upgrade | Upgrade the jumper continuous ratings to minimum 2000 Amps on Zorn - McCarty Lane line at the McCarty Lane (7182) substation. |  | McCarty Lane |  | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-06-01 |  | 138 | 0 | 0 | 0.0 | 0 | HAYS |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
11TPIT0134 | Dye Mound Capacitor Bank | Install 25 MVAR at Dye Mound substation |  | Dye Mound |  | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10026 | 2013-06-01 |  | 138 | 0 | 0 | 0 | 25 | MONTAGUE |  | Tier 4 |  |  |  | 741 | Y | N
13TPIT0092 | Killeen Switch - Killeen Elms Road - Harker Heights 138 kV line | Upgrade existing 138 kV line |  | Killeen Switch | Harker Heights | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R777-E | 2013-06-01 |  | 138 | 0 | 14.8 | 0.0 | 0 | BELL | BELL | CREZ |  |  |  | 3423, 3633 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0135 | Holt Switch - Goldsmith - Goldsmith South 138 kV line | Rebuild existing 69 kV line to create a double-circuit line with 69 kV and 138 kV circuits and convert Goldsmith South to 138 kV. | Construction schedule change | Holt Switch | Goldsmith South Substation | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8050A-E | 2013-06-01 |  | 138 | 9 | 0 | 0.0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 1141, 11256, 11250 | Y | N |  | Goldsmith - Goldsmith South section completed in 3/2013
13TPIT0201 | Goldsmith South - Goldsmith Junction 138 kV line | Rebuild existing 69 kV line to create a double-circuit line with 69 kV and 138 kV circuits and connect the 138 kV circuit to an existing Moss - Ector County North 138 kV line. |  | Goldsmith South Substation | Goldsmith Junction | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8120-E | 2013-06-01 |  | 138 | 5.54 | 5.5 | 0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 11250 | Y | N
13TPIT0180 | Salem Autotransformer Replacement | Replace failed autotransformer at the Salem substation | A spare autotransformer will be in service at Salem temporarily until the replacement is installed. The in-service date for the spare is June 15, 2012 |  |  | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-06-01 |  | 345 | 0 | 0 | 600.0 | 0 | WASHINGTON |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N |  | Cost will be determined during the September TPIT.
13TPIT0181 | Gilleland Creek Autotransformer Replacement | Replace failed autotransformer at the Gilleland Creek substation | No autotransformer will be in service at Gilleland Creek until the replacement is installed |  |  | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-06-01 |  | 345 | 0 | 0 | 672.0 | 0 | TRAVIS |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N |  | Cost will be determined during the September TPIT.
10TPIT0031 | Dunlap 138/345kV Autotransformer Project | Install a 138/345 672 MVA autoxfmr at Dunlap, configuring a Dunlap to Lost Pines 345 kV circuit, add a new 345kV line from Dunlap to Austrop and merge 138kv Dunlap to Decker and Decker to Techridge into one single circuit bypassing Decker. Re-terminate the WebberSolar Tap into the vacant Austrop 138kV position. | As part of the project, the existing Webber Solar Tap will be removed and the solar plant will be connected to the existing vacant position at Austrop substation. | Dunlap Substation | Dunlap Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P132 | 2013-06-01 |  | 345 | 0 | 0 | 672.0 | 0 | TRAVIS | TRAVIS | Tier 3 | 2010-04-01 | 2010-06-01 | N/A | 9044, 9045 | Y | N
11TPIT0078 | Riley, add four 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Riley |  | Planned | 467 - 0668 | AEP/ETT | Paul Hassink 918-599-2653 | 2380 | 2013-06-01 |  | 345 | 0 | 0 | 0 | -200 | WILBARGER |  | CREZ Modified |  |  |  |  | Y | N
11TPIT0079 | Riley, Expand 345 kV switch station for the additon of the West Krum to Riley 345 kV double circuit | Build new Riley 345 kV switch station, cut in the existing and future 345 kV lines as described in ERCOT CREZ Scenario 2 |  | Riley |  | Planned | 467 - 0668 | AEP/ETT | Paul Hassink 918-599-2653 | 2435 | 2013-06-01 |  | 345 | 0 | 0 | 0 | 0 | WILBARGER |  | CREZ Modified |  |  |  |  | Y | N
13TPIT0022 | Gray to Oklaunion double circuit 345kV line (Tesla to Riley portion) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis |  | Tesla | Riley | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2384 | 2013-06-01 |  | 345 | 131.2 | 0 | 0 | 0 | GRAY | WILBARGER | CREZ |  |  |  |  | Y | N
13TPIT0036 | Krum West - Riley (Oklaunion) 345 kV line (Oncor Electric Delivery portion) | Construct double-circuit 345 kV line |  | Krum West | Riley | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C050-E | 2013-06-01 |  | 345 | 326.2 | 0 | 0.0 | 0 | DENTON | WILBARGER | CREZ |  |  |  | 1730, 6101 | Y | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0037 | Krum West Switch | Construct 345 kV switching station |  |  |  | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C017-E | 2013-06-01 |  | 345 | 0 | 0 | 0.0 | 0 | DENTON |  | CREZ |  |  |  | 1730 | Y | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0038 | Hicks Switch | Construct 345 kV switching station |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C030-E | 2013-06-01 |  | 345 | 0 | 0 | 0.0 | 0 | TARRANT |  | CREZ |  |  |  | 2081 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0039 | Willow Creek - Hicks Switch 345 kV line | Construct double-circuit 345 kV line |  | Hicks Switch | Willow Creek | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C061-E | 2013-06-01 |  | 345 | 80.4 | 0 | 0.0 | 0 | TARRANT | WISE | CREZ |  |  |  | 2081, 1421 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0040 | Willow Creek Switch circuit breakers | Install 345 kV circuit breakers. |  |  |  | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C012B-E | 2013-06-01 |  | 345 | 0 | 0 | 0.0 | 0 | WISE |  | CREZ |  |  |  | 1421 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0093 | Willow Valley Switch | Install 345/138 kV autotransformer |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8029-E | 2013-06-01 |  | 345 | 0 | 0 | 600.0 | 0 | BORDEN |  | Tier 2 | 2011-03-01 | 2011-04-01 |  | 1301 | Y | N
13TPIT0096 | Krum West Switch reactors | Install shunt reactors |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C085R-E | 2013-06-01 |  | 345 | 0 | 0 | 0.0 | -100 | DENTON |  | CREZ |  |  |  | 2373 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0150 | Glidden to Colorado Transmission upgrade | Rebuild entire line from Glidden to Colorado substation to 795 MCM 138 Kv insulation | ERCOT approval through RPG review process was granted March 27,2012 | Glidden | Colorado | Under construction |  | SBEC | Don Roberts | WO#12-6056 WO#12-6057 WO#12-6058 WO#12-5315 WO#12-5316 WO#12-5317 | 2013-06-01 |  | insulated at 138 operated at 69 | 0 | 27 | 0.0 | 0 | Colorado | Colorado | Tier 3 | 2012-02-27 | 2012-03-27 | N/A | SEE PROJECT DESCRIPTION | N | N
15TPIT0013 | Seymour to Lake Kemp Switch | Rebuild Seymour to Lake Kemp Switch 69 kV line with 795 ACSR |  | Seymour | Lake Kemp Switch | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10047 | 2013-06-20 |  | 69 | 0 | 6.9 | 0.0 | 0 | BAYLOR | BAYLOR | Tier 4 |  |  |  | 779, 782 | Y | N
13TPIT0012 | Zorn Autotransformer Addition | Add a new 345-138 kV 478 MVA autotransformer at the Zorn substation (7042). | [5 empty] | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-06-27 |  | 345 | 0 | 0 | 478 | 0 | GUADALUPE |  | Tier 3 | 2008-01-30 | 2008-06-10 | N/A | SEE PROJECT DESCRIPTION | Y | N
13TPIT0176 | Wormser Road: Install Capacitor Bank | Install one (1) - 14.4 MVAR Capacitor Bank at Wormser Road substation. |  | Wormser |  | Planned | 563-0731 | AEP/TCC | Paul Hassink 918-599-2653 | 3457 | 2013-06-30 |  | 69 | 0 | 0 | 0 | 0 | VAL VERDE | 0 | Tier 4 | 0 | 0 | 0 | 0 | N | N | 0 | 0
13TPIT0189 | Brazos Valley to Fort Bend Ckt.09 | Upgrade 138kV Ckt. 09 Brazos Valley to Fort Bend to increase thermal ratings. |  | Brazos Valley | Fort Bend | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-06-30 |  | 138 | 0 | 5.62 | 0.0 | 0 | FORT BEND | FORT BEND | Tier 4 |  |  |  | 44100, 44280 | Y | N |  | Part of Fort Bend Area Upgrades.
13TPIT0196 | MILLER 138kV Substation | Construct service to new 138kV MILLER customer-owned substation. Loop through Ckt.88 BARNES to SR Bertron. | Change in project schedule | MILLER | BARNES/SR Bertron | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-06-30 |  | 138 | 0.2 | 0.3 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 41355, 41420, 41405 | Y | N
13TPIT0098 | Faraday Switch | Establish new 345 kV Faraday station in WETT's Long Draw-S. Scurry 345 kV line. |  |  |  | Planned |  | Wind Energy Transmission Texas (WETT) | Julius Horvath (512) 279-7377 julius.horvath@windenergyoftexas.com |  | 2013-06-30 |  | 345 | 0 | 0 | 0.0 | 0 | BORDEN |  | Tier 2 | 2011-03-18 | 2011-04-18 | N/A | 59905 | Y | N |  | Project is shown in the DSB 2013 and later (2014, 2015, etc) cases
11TPIT0077 | Riley, Add two 130.9 MVar capacitors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Riley |  | Under Construction | 467 - 0668 | AEP/ETT | Paul Hassink 918-599-2653 | 2379 | 2013-06-30 |  | 345 | 0 | 0 | 0 | +261.8 | WILBARGER |  | CREZ Modified |  |  |  |  | Y | N
13TPIT0109 | Ajo to Rio Hondo: Reconductor 345kV line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Reconfigure Series Capacitors at North Edinburg and Rio Hondo |  | Ajo | Rio Hondo | Planned | 071 - 0281 | AEP/ETT/TCC | Paul Hassink 918-599-2653 | 3182 | 2013-06-30 |  | 345 | 0 | 66.708 | 0 | 0 | KENEDY | CAMERON | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 80076, 8318 | Y | N
10TPIT0095 | VH Braunig - Grandview 138kV Line Reroute | Reroute VH Braunig - Grandview to become VH Braunig - Coliseum Rd | Delayed due to Rail Road permit | VH Braunig | Grandview | Planned | S-0554 | CPS | PM: Ulrich Skerhut | T-0130 | 2013-07-01 |  | 138 | 2.1 | 0 | 0.0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5030 5095 5175 | Y | N |  | There are no transformers associated with this project
12TPIT0048 | Hereford Collection Station | Construct the new 345 kV Hereford switching station.Initial build is 7 element folded breaker and one half bus arrangement | New |  |  | Planned | 13TPIT0042, 13TPIT0043 | SU | Mark Caskey, (214) 978-8243, mcaskey@sharyland.com |  | 2013-07-01 |  | 345 | 0 | 0 | 0.0 | -200 | DEAF SMITH |  | CREZ |  |  |  | 99102 | Y | N |  | Per one year compliance filing under PUC Docket # 37858
12TPIT0052 | LS02 Nazareth to Hereford | Construct a new 345kV single circuit line from Nazareth Switching to Hereford switching station | New | Nazareth | Hereford | Planned |  | SU | Mark Caskey, (214) 978-8243, mcaskey@sharyland.com |  | 2013-07-01 |  | 345 | 25.5 | 0 | 0.0 | 0 | CASTRO | DEAF SMITH | CREZ |  |  |  | 99101-99102 | Y | N |  | Per 6 month compliance filing under PUC Docket # 37858
05TPIT0072 | Mountain Top-Blanco-Devil's Hill | Close the 69-kV switch (SW 458) at the Blanco substation(7482) to loop the load located at the Blanco substation. Upgrade the capacity of the 138-69-kV auto-transformer (T2) at the Devil’s Hill substation(7493) from 20-MVA to 45-MVA. | Devil's Hill Auto Installed. Construction for Blanco bus to close Loop not scheduled to complete until July 2013. | Mountain Top | Devil's Hill | Under Construction |  | PEC | Randy Buchanan (830) 868-6058 | 1005443 | 2013-07-13 |  | 138 | 0 | 0 | 45.0 | 0 | BLANCO | COMAL | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
12TPIT0022 | North McCamey Autotransformer Addition | Add two new 345-138 kV 800 MVA autotransformer at the North McCamey substation (76595). | [5 empty] | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-07-17 |  | 345 | 0 | 0 | 1600 | 0 | UPTON |  | CREZ |  |  |  | SEE PROJECT DESCRIPTION | Y | N |  | CREZ Default project assigned to LCRA TSC
10TPIT0049 | Koppe Bridge to Wellborn Transmission | Build (5.8) miles of 138 kV line(s) to serve station |  | Koppe Bridge | Wellborn | planned | 10TPIT0048 | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2013-07-31 |  | 138 | 6.2 | 0 | 0.0 | 0 | BRAZOS | BRAZOS | Tier 4 |  |  |  | 32860 32895 | Y | N
13TPIT0015 | Wellborn Switching Sub | Install (3) Breaker ring to include (2) 138 lines and (1) 138/69 auto transformer relocated from Greens Prairie |  | Wellborn | Wellborn | planned | 10TPIT0049 | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2013-07-31 |  | 138 | 0 | 0 | 20.0 | 0 | BRAZOS |  | Tier 4 |  |  |  | 32895 (138) 32898 (69) | Y | N
13TPIT0016 | Greens Prairie to Wellborn Transmission | ReBuild-Reconductor (3.75) miles of 69kV line converting to 138 kV to serve Wellborn |  | Greens Prairie | Wellborn | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2013-07-31 |  | 138 | 0 | 3.82 | 0.0 | 0 | BRAZOS | BRAZOS | Tier 4 |  |  |  | 32878 32895 | Y | N
13TPIT0017 | Greens Prairie Substation | Install (1) Breaker in existing ring bus for a 138 line from Wellborn/Millican Substation(s) |  | Greens Prairie | Greens Prairie | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2013-07-31 |  | 138 | 0 | 0 | 0.0 | 0 | BRAZOS |  | Tier 4 |  |  |  | 32878 | Y | N
12TPIT0156 | Brundage Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-08-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | DIMMIT |  | Tier 4 |  |  |  | 5870 | Y | N
13TPIT0018 | McCamey C to McCamey D (Bakersfield to Big Hill) | Construct new 113 miles 1590 ACSR 345 kV line from Bakersfiled to Big Hill (McCamey C to McCamey D). |  | Bakersfield | Big Hill | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-08-01 |  | 345 | 112 | 0 | 0.0 | 0 | PECOS | SCHLEICHER | CREZ |  |  |  | 76002-76003 | Y | N
13TPIT0147 | Carrizo Springs Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-09-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | DIMMIT |  | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5872 | Y | N
13TPIT0148 | Cotulla Autotransformer | Expand Cotulla station to have 138 kV and add a 150 MVA 138/69 kV autotransformer at Cotulla. |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-09-01 |  | 69 | 0 | 0 | 150.0 | 0 | LA SALLE |  | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5875 , 5876 | Y | N
13TPIT0042 | LS03 White Deer to Hereford | Construct a new 345kV single circuit line from White Deer switching station to Hereford switching station | New | White Deer | Hereford | Planned | 12TPIT0048, 13TPIT0043 | SU | Mark Caskey, (214) 978-8243, mcaskey@sharyland.com |  | 2013-09-01 |  | 345 | 91.2 | 0 | 0.0 | 0 | CARSON | DEAF SMITH | CREZ |  |  |  | 99201-99102 | Y | N |  | Per one year compliance filing under PUC Docket # 37858
13TPIT0043 | White Deer Collection Station | Construct the new 345 kV White Deer switching station.Initial build is 10 element folded breaker and one half bus arrangement. | New |  |  | Planned | 12TPIT0048, 13TPIT0042 | SU | Mark Caskey, (214) 978-8243, mcaskey@sharyland.com |  | 2013-09-01 |  | 345 | 0 | 0 | 0.0 | -100 | CARSON |  | CREZ |  |  |  | 99201 | Y | N |  | Per one year compliance filing under PUC Docket # 37858
13TPIT0151 | Gibbons Creek Reactive Support | Install transmission capacitors, reactors and associated switching devices and replace existing T1 autotransformer |  | Gibbons Creek | Gibbons Creek | Conceptual |  | TMPA | Eric Schroeder 936-873-1124 eschroeder@texasmpa.org |  | 2013-09-01 |  | 345 | 0 | 0 | 600.0 | +130/-135 | Grimes |  | Tier 3 |  |  |  |  | N | N
13TPIT0054 | Gray to White Deer, build double circuit 345 kV line | Build 345 kV double circuit line from Gray to White Deer | Updated Circuit Miles | Gray | White Deer | Planned |  | CTT | Tim Cook 636-534-3310 Tcook@LSPower.com |  | 2013-09-12 |  | 345 | 83 | 0 | 0.0 | 0 | GRAY | CARSON | CREZ |  |  |  | 79000-79500,CKT 1 & 79000-79500,CKT 2 | Y | N
13TPIT0055 | Silverton to Tesla, build double circuit 345 kV line | Build 345 kV double circuit line from Silverton to Tesla | Updated Circuit Miles | Silverton | Tesla | Planned |  | CTT | Tim Cook 636-534-3310 Tcook@LSPower.com |  | 2013-09-12 |  | 345 | 172 | 0 | 0.0 | 0 | BRISCOE | CHILDRESS | CREZ |  |  |  | 79503-79001, 79002-60501 & 79503-79003, 79004-60501 | Y | Y
13TPIT0056 | Silverton to Tesla, build series compensation | Add series compenstion to both circuit of the 345 kV double circuit line from Silverton to Tesla | Updated Project Cost. | - | - | Planned |  | CTT | Tim Cook 636-534-3310 Tcook@LSPower.com |  | 2013-09-12 |  | 345 | 0 | 0 | 0.0 | 0 | Hall | - | CREZ |  |  |  | 79001-79002 & 79003-79004 | Y | N
11TPIT0133 | Bowie to Montague Rebuild | Rebuild Bowie to Montague 69kV line with 959 ACSS |  | Bowie | Montague | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10015 | 2013-09-20 |  | 69 | 0 | 11 | 0.0 | 0 | MONTAGUE | MONTAGUE | Tier 4 |  |  |  | 621, 632, 633 | Y | N
11TPIT0108 | Penascal Wind Phases 3 Generation Interconnect | Penascal Wind Phases 2 and 3 (Added Terminal From) |  | Penascal |  | Under Construction | 489 - 0690 | AEP/ETT/TCC | John Pulay 918-599-2653 | 3370 | 2013-09-21 |  | 345 | 0 | 0 | 0 | 0 | KENNEDY |  | Tier 4 |  |  |  |  | Y | N
13TPIT0105 | Silver City to Calvert Switch | Install additional poles and modify existing structures to raise normal operating temperature to 100° C |  | Silver City | Calvert Switch | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 11051 | 2013-09-24 |  | 69 | 0 | 7.95 | 0.0 | 0 | MILAM | MILAM | Tier 4 |  |  |  | 65, 73 | Y | N
13TPIT0032 | Edith Clarke to West Shackelford double circuit 345kV line (Edith Clarke to Clear Crossing portion) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis |  | Edith Clarke | Clear Crossing | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2385 | 2013-09-25 |  | 345 | 158.4 | 0 | 0 | 0 | COTTLE | SHACKELFORD | CREZ |  |  |  |  | Y | N
13TPIT0175 | Wormser Road: Install DRCS | Relocate DRCS from Hamilton Road to Wormser Road. | Update In-Service Date and TSPs | Wormser |  | Planned | 563-0731 | AEP/TCC/ETT | Paul Hassink 918-599-2653 | 3441 | 2013-09-30 |  | 69 | 0 | 0 | 0 | 0 | VAL VERDE | 0 | Tier 4 | 0 | 0 | 0 | 0 | N | N | 0 | 0
13TPIT0174 | Piloncillo 138 kV Station: Install breaker ring bus | Construct 4 CB ring bus at new Piloncillo station on Asherton to North Laredo 138 kV line | Change Status and dollars | Piloncillo |  | Planned | 600-762 | AEP/TCC | Paul Hassink 918-599-2655 | 3469 | 2013-09-30 |  | 138 | 0 | 0 | 0 | 0 | DIMMIT |  | Tier 4 |  |  |  | 89630 | Y | N
13TPIT0050 | LS05 Silverton to White Deer | Construct a new 345kV double circuit line from Silverton switching station to White Deer switching station | New | Silverton | White Deer | Planned |  | SU | Mark Caskey, (214) 978-8243, mcaskey@sharyland.com |  | 2013-09-30 |  | 345 | 68.2 | 0 | 0.0 | 0 | BRISCOE | CARSON | CREZ |  |  |  | 99103-99201 | Y | N |  | Per one year compliance filing under PUC Docket # 37858
13TPIT0030 | Dermott to Willow Creek (Dermott to Clear Crossing portion) double circuit 345kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis |  | Dermott | Clear Crossing | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2391 | 2013-09-30 |  | 345 | 180.6 | 0 | 0 | 0 | SCURRY | HASKELL | CREZ |  |  |  |  | Y | N
13TPIT0033 | Edith Clarke to West Shackelford double circuit 345kV line (Clear Crossing to West Shackelford portion) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis |  | Clear Crossing | West Shackleford | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2386 | 2013-09-30 |  | 345 | 67.6 | 0 | 0 | 0 | COTTLE | SHACKELFORD | CREZ |  |  |  |  | Y | N
13TPIT0085 | Clear Crossing 345 kV station | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT |  | Clear Crossing |  | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2486 | 2013-09-30 |  | 345 | 0 | 0 | 0 | 0 | HASKELL |  | CREZ |  |  |  |  | Y | N
13TPIT0088 | Clear Crossing add six 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Clear Crossing |  | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2489 | 2013-09-30 |  | 345 | 0 | 0 | 0 | -300 | HASKELL |  | CREZ |  |  |  |  | Y | N
12TPIT0181 | Lon Hill to Calallen: Rebuild 69kV line | Rebuild Lon Hill - Calallan 69kV Line | Description, date, and dollars changed | Lon Hill | Calallan | Conceptual | 581-0736 | AEP/TCC | Paul Hassink 918-599-2658 | 3461 | 2013-10-01 |  | 69 | 0 | 2.1 | 0 | 0 | SAN PATRICIO | SAN PATRICIO | Tier 4 |  |  |  | 5626, 8448 | Y | N |  | 0
13TPIT0169 | Eiland Substation | Construct new 2257 Eiland Substation, 30 MVA, with bi-directional interconnection to Oncor's Spraberry to Morgan Creek 138 Kv transmission line to transfer new and existing load into ERCOT, 2372 St LawerenceSubstation, 2168 Stiles Substaion, New 2570 East Stiles Substation | New | Oncor Spraberry Switch Yard | Oncor Morgan Creek Switch Yard | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-10-01 |  | 138 | 2 | 0 | 0 | 0 | GLASSCOCK |  | Tier 4 |  |  | n/a |  | N | N
13TPIT0021 | Cottonwood to Edith Clarke double circuit 345kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis |  | Cottonwood | Edith Clarke | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2383 | 2013-10-01 |  | 345 | 178 | 0 | 0 | 0 | DICKENS | COTTLE | CREZ |  |  |  |  | Y | N
13TPIT0162 | Mitchell County 138 Kv Transmission Line | Construct 2.1 miles of new 138 Kv transmission line between 3852 Colorado City Substation and new Oncor Ring Bus Breaker Station between Morgan Creek and China Grove and transfer remaining substations into ERCOT, 1440 Salem, 2254 South Midland, 2478 Vealmoor, 2664 Fairview, 2850 Elbow, and 1548 Greenwood Substations | New | 3852 Colorado City Substation | New Oncor Breaker Station | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-10-13 |  | 138 | 2.1 | 0 | 0.0 | 0 | MITCHELL | MITCHELL | Tier 4 | 2011-01-01 | 2011-05-24 | n/a | 1189, 79605 | Y | N |  | Docket #37090
12TPIT0192 | Triangle Switch Yard | Construct a four position breaker station with a 30 MVA transformer | New | Oncor Stanton East | Oncor Midland East | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2013-10-13 |  | 138 | 0 | 0 | 0.0 | 0 | MARTIN |  | Tier 4 | 2011-01-01 | 2011-05-24 | n/a | 79619, 79609 | Y | N |  | Docket #37090
13TPIT0145 | Rangerville Sub- 138kV Breaker Addition | Install 138kV Breakers |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-10-13 |  | 138 | 0 | 0 | 0.0 | 0 | CAMERON |  | Tier 4 |  |  |  | 8747 | Y | N
13TPIT0116 | North Brady: Add two 7.2 Mvar capacitor banks | Add two 7.2 Mvar capacitor banks at North Brady and add 7.2 Mvar capacitor bank at Katemcy | Status, Contact & Schedule Update | North Brady |  | Planned | 559 - 0722 | AEP/TNC | Paul Hassink 918-599-2653 | 2561 | 2013-10-31 |  | 69 | 0 | 0 | 0 | +14.4 | MCCULLOCH |  | Tier 4 |  |  |  |  | Y | N
12TPIT0174 | Pointer, Build new three breaker ring bus | Construct new Pointer station along the Munday to Rule 69 kV line | Transmission Status Update | Munday | Rule | Under Construction | 504 - 0715 | AEP/TNC | Terry Weeks 918-599-2653 | 2496 | 2013-10-31 |  | 69 | 0 | 0 | 0 | 0 | KNOX |  | Tier 4 |  |  |  |  | Y | N
13TPIT0190 | Busch Substation Conversion | Convert Busch substation from double-tap to 138kV loop service Ckt. 08. |  | Busch | Anbush/Clinton | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-10-31 |  | 138 | 0 | 0.2 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 40100, 40230, 40351 | Y | N
13TPIT0158 | Bruni to MEC Bruni: Rebuild 138 kV line | Reterminate MEC Bruni tap into Bruni sub-station and upgrade sub-station to 4 breaker ring bus |  | Bruni | MEC Bruni | Under Construction | 572-0749 | AEP/TCC | Michael Tallon 918-599-2653 | 3450 | 2013-10-31 |  | 138 | 0.5 | 0.1 | 0 | 0 | WEBB | WEBB | TIER 4 | 0 |  |  | 8297, 8958 | Y | N
13TPIT0159 | Bruni 138 kV station: Install 138 kV breakers ring bus | Reterminate MEC Bruni tap into Bruni sub-station and upgrade sub-station to 4 breaker ring bus |  | Bruni |  | Under Construction | 572-0749 | AEP/TCC | Michael Tallon 918-599-2653 | 3453 | 2013-10-31 |  | 138 | 0 | 0 | 0 | 0 | WEBB | 0 | TIER 4 |  |  |  | 8297 | N | N
13TPIT0089 | Tesla, add dynamic reactive compensation | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Tesla |  | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2491 | 2013-10-31 |  | 345 | 0 | 0 | 0 | +300 / -100 | COTTLE |  | CREZ |  |  |  |  | Y | N
13TPIT0090 | Hamilton Road, add dynamic reactive compensation | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Hamilton Road |  | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2492 | 2013-10-31 |  | 345 | 0 | 0 | 0 | +200 / -50 | VALVERDE |  | CREZ Modified |  |  |  |  | Y | N
14TPIT0048 | Maxwell Substation (aka Clear Fork) | Construct 69kV/12.5kV distribution substation Maxwell (7195) on T-519 between Reedville and Lockhart. |  | Maxwell | Reedville/Lockhart | Planned |  | BBEC | Thomas Ellis |  | 2013-11-01 |  | 69 | 0 | 0 | 0 | 0 | CALDWELL |  | Tier 4 |  |  |  | see project description | Y | N
07TPIT0050 | Decker to Techridge 138kV Circuit Relocation/Reconductor | This project will reroute existing Ckt 975 (Decker to Techridge) from Yager corner to Techridge substation. The reroute will adopt 3000 Amps bundled 795 ACSS Drake. |  | Decker Switchyard | Techridge Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P071 | 2013-11-01 |  | 138 | 0 | 4.5 | 0.0 | 0 | TRAVIS | TRAVIS | Tier 2 | 2009-01-26 | 2009-06-01 | N/A | 9195, 9190 | Y | N
12TPIT0029 | Big Hill to Kendall | Construct a new double circuit 345 kV transmission line (approximately 137 miles) between the new Big Hill (76003) and the existing Kendall station (7046). The new transmission lines will consist of Cumberland conductor to provide a thermal rating of 2988 MVA each. |  | Big Hill | Kendall | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2013-11-01 |  | 345 | 274 | 0 | 0.0 | 0 | SCHLEICHER | KENDALL | CREZ |  |  |  | SEE PROJECT DESCRIPTION | Y | N
12TPIT0075 | Knob Creek 345 kV Switching Station Phase I | Construct 345 kV switching station |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R749A-E | 2013-11-01 |  | 345 | 0 | 0 | 0 | 0 | BELL |  | Tier 4 |  |  |  | 13413 | Y | N
13TPIT0070 | Nash Creek Substation | Replace existing PWT with new 138x69kV-13.09x26.18 dual kV, 12/16/20 MVA PWT w/associated CSW, structures, bus, panels, etc | [5 empty] | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2013-11-29 |  | 69 | 0 | 0 | 0.0 | 0 | GUADALUPE |  | Tier 4 |  |  |  | See Project Title | N | N
13TPIT0193 | Tomball Reactor | Install 50MVAR reactor at Tomball substation. |  | Tomball |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-11-30 |  | 138 | 0 | 0 | 0 | -50 | HARRIS |  | Tier 4 |  |  |  | 46510 | Y | N
13TPIT0195 | Arcola Substation Conversion | Convert Arcola substation from double-tap to 138kV loop service Ckt.82. |  | Arcola | Thompsons/Karsten | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-11-30 |  | 138 | 0 | 0.2 | 0.0 | 0 | FORT BEND |  | Tier 4 |  |  |  | 44722, 44032, 44390 | Y | N
13TPIT0119 | Vanderbilt to El Campo rebuild | Rebuild 4/0 ACSR 69 kV to 795 ACSR double circuit 138 kV structures with one side operated at 69 kV. Includes building new load serving station with a 2 mile double circuit that loops into the 138 kV line near the Cordele substation. |  | Vanderbilt | Ricebird | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-11-30 |  | 138 | 52 | 48 | 0.0 | 0 | JACKSON | WHARTON | Tier 2 | 2011-10-07 | 2012-01-26 | N/A | 5584, 5523, 78104 | Y | N
13TPIT0099 | League City-Magnolia rebuild | Rebuild League City to Magnolia 138 kV transmission line with 795 ACSS conductor. |  | League City | Magnolia | Planned |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com |  | 2013-11-30 |  | 138 | 0 | 3.62 | 0.0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 38920, 38930, 38950 | Y | N
09TPIT0039 | Woodrow to Kings Row 69kV Transmission Line Reconstruction | Reconstruct 4.2 miles of existing 69V transmission line | On schedule | Woodrow Substation PSS/E Bus 901 | Kings Row Substation PSS/E Bus 909 | Planned | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 600483 | 2013-12-01 |  | 69 | 0 | 4 | 0.0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 901, 909 | Y | N
07TPIT0078 | Devine to Lytle: Rebuild 69 kV Line | Add CPS Lytle to ETT Lytle 795 ACSR 138 kV line and 93 MVA 69/138 kV autotransformer at Lytle |  | Devine | Lytle | Under Construction | 028 - 0028 | AEP/ETT | Terry Weeks (AEP) 918-599-2653 | 1778 | 2013-12-01 |  | 69 | 0 | 7 | 0 | 0 | MEDINA | MEDINA | Tier 4 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8223, 8622 | Y | N
13TPIT0126 | Hindes 138 kV Substation | Build new load serving station in the 138 kV line between CR343 and Pearsall. |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-12-01 |  | 138 | 0 | 0 | 0.0 | 0 | ATASCOSA |  | Tier 4 |  |  |  | 5899 | Y | N
13TPIT0198 | Seawillow Substation | Construct 138kV/12.5kV distribution substation Seawillow (7559) on T-184 Lockhart and Luling. |  | Seawillow | Luling/Lockhart | Planned |  | BBEC | Thomas Ellis |  | 2013-12-01 |  | 138 | 0 | 0 | 0 | 0 | CALDWELL |  | Tier 4 |  |  |  | see project description | N | N
13TPIT0134 | Cumby Switch | Replace existing 138/69 kV autotransformer |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R908-E | 2013-12-01 |  | 138 | 0 | 0 | 50.0 | 0 | DELTA |  | Tier 4 |  |  |  | 1815, 1812 | Y | N
13TPIT0154 | Barber Lake 138 kV Switching Station | Construct new switching station |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8060-E | 2013-12-01 |  | 138 | 0 | 0 | 0.0 | 0 | MITCHELL |  | Tier 4 |  |  |  | 1189 | Y | N
14TPIT0088 | Moss - Holt Switch 138 kV line | Upgrade existing line |  | Moss | Holt Switch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8065B-E | 2013-12-01 |  | 138 | 0 | 18 | 0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 11140, 1141 | Y | N
10TPIT0020 | Anna Switch - Krum W. Switch 345 kV line | Construct a double-circuit 345 kV line |  | Anna Switch | Krum W. Switch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C060-E | 2013-12-01 |  | 345 | 140 | 0 | 0.0 | 0 | DENTON | COLLIN | CREZ |  |  |  | 1730, 2373 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0035 | Willow Creek - Clear Crossing - Dermott Switch (Central B) 345 kV line (Oncor Electric Delivery section) | Construct double-circuit 345 kV line |  | Willow Creek | Dermott Switch | Under Construction |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C054-E | 2013-12-01 |  | 345 | 220 | 0 | 0.0 | 0 | WISE | HASKELL | CREZ |  |  |  | 1421 | Y | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0041 | Anna Switch circuit breakers | Install 345 kV circuit breakers |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C015-E | 2013-12-01 |  | 345 | 0 | 0 | 0.0 | 0 | COLLIN |  | CREZ |  |  |  | 1730 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0072 | Scurry County South Switch (Central A) | Install shunt capacitor |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | RC0088-E | 2013-12-01 |  | 345 | 0 | 0 | 0.0 | 160 | SCURRY |  | CREZ |  |  |  | 11318 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0073 | Killeen Switch | Install shunt capacitors |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | RC0089-E | 2013-12-01 |  | 345 | 0 | 0 | 0.0 | 160 | BELL |  | CREZ |  |  |  | 3422 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0074 | Willow Creek Switch | Install shunt reactors. |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C054B-E | 2013-12-01 |  | 345 | 0 | 0 | 0.0 | -100 | WISE |  | CREZ |  |  |  | 1421 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0075 | Graham Switching Station | Install shunt reactor |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | RC083-E | 2013-12-01 |  | 345 | 0 | 0 | 0.0 | -200 | YOUNG |  | CREZ |  |  |  | 1430 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0076 | Parker Switching Station | Install a dynamic reactive device |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | RC087-E | 2013-12-01 |  | 345 | 0 | 0 | 0.0 | 300 -265 | PARKER |  | CREZ |  |  |  | 1436 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0081 | Brown Switch capacitors | Install shunt capacitors |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | RC082-E | 2013-12-01 |  | 345 | 0 | 0 | 0.0 | 240 | BROWN |  | CREZ |  |  |  | 1444 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. The estimated cost is included in the estimated cost of Brown Switch (12TPIT0045).
13TPIT0082 | Brown Switch dynamic reactive device | Install two dynamic reactive devices |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | RC086-E | 2013-12-01 |  | 345 | 0 | 0 | 0.0 | 600, -530 | BROWN |  | CREZ |  |  |  | 1444 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. The estimated cost is included in the estimated cost of Brown Switch (12TPIT0045).
13TPIT0095 | Krum West Switch capacitors | Install shunt capacitors |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C085-E | 2013-12-01 |  | 345 | 0 | 0 | 0.0 | 80 | DENTON |  | CREZ |  |  |  | 2373 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
13TPIT0029 | Big Hill to Kendall Series Compensation (Edison) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Edison | Edison | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2398 | 2013-12-09 |  | 345 | 0 | 0 | 0 | +933 | SCHLEICHER | KENDALL | CREZ |  |  |  |  | Y | N
13TPIT0031 | Dermott to Clear Crossing Series Compensation (Kirchoff) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Kirchoff | Kirchoff | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2392 | 2013-12-09 |  | 345 | 0 | 0 | 0 | +737 | SCURRY | HASKELL | CREZ |  |  |  |  | Y | N
13TPIT0034 | Edith Clarke to West Shackelford Series Compensation (Gauss) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Gauss | Gauss | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2388 | 2013-12-09 |  | 345 | 0 | 0 | 0 | +737 | COTTLE | COTTLE | CREZ |  |  |  |  | Y | N
07TPIT0096 | Pockrus Substation - Reconstruct 138kV Section of the Station | Reconstruct the 138kV section of the station to install transmission circuit breakers in a ring bus configuration | On schedule |  |  | Planned | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 600852 | 2013-12-12 |  | 138 | 0 | 0 | 0.0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 917 | Y | N
12TPIT0090 | Whitney 2nd Auto | Replace 60 MVA, 138/69 kV auto with 75 MVA auto |  | Whitney |  | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10048 | 2013-12-12 |  | 138 | 0 | 0 | 75 | 0 | BOSQUE |  | Tier 4 |  |  |  | 241, 243 | Y | N
13TPIT0204 | Wink Substation Ring Bus | Build ring bus for 69 kV system in TNMP's Wink Substation |  | Wink |  | Conceptual |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE03313 | 2013-12-13 |  | 69 | 0 | 0 | 0 | 0 | WINKLER |  | Tier 4 |  |  |  |  | N | N
13TPIT0106 | Killeen SS to Ding Dong | Install additional poles and modify existing structures to raise normal operating temperature to 100° C |  | Killeen SS | Ding Dong | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 11037 | 2013-12-20 |  | 138 | 0 | 23.8 | 0.0 | 0 | BELL | BELL | Tier 4 |  |  |  | 3423, 136, 117, 115 | Y | N
12TPIT0083 | Firewheel-Lookout 138 kV line | Line upgrade | On Hold For Funding | Switch 8512 at Firewheel | A new switch at new Lookout | Planned |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2013-12-27 |  | 138 | 0 | 1.3 | 0.0 | 0 | DALLAS |  | Tier 4 |  |  |  | 821, 828 | Y | N |  | This project is a line reconductor for solving overload
12TPIT0084 | Lookout 138 kV new substation | New load serving | On Hold For Funding |  |  | Planned |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2013-12-27 |  | 138 | 0 | 0 | 0.0 | 0 | DALLAS |  | Tier 4 |  |  |  | 828 | Y | N |  | This project is a line reconductor for solving overload
12TPIT0085 | Apollo-Lookout 138 kV line | Line upgrade | On Hold For Funding | Switch 8622 at Apollo | A new switch at new Lookout | Planned |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2013-12-27 |  | 138 | 0 | 2.8 | 0.0 | 0 | DALLAS |  | Tier 4 |  |  |  | 802, 828 | Y | N |  | This project is a line reconductor for solving overload
12TPIT0008 | Kings Row to Denton North 69kV Transmission Line Reconstruction | Reconstruct 1.91 miles of existing 69V transmission line | On schedule | Kings Row Substation PSS/E Bus 909 | Denton North Interchange PSS/E Bus 912 | Planned | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 602674 | 2013-12-31 |  | 69 | 0 | 2 | 0.0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 909, 912 | Y | N
12TPIT0088 | Kings Row Substation Reconstruction | Completely reconstruct the Kings Row Substation | On schedule |  |  | Planned | 09TPIT0039 12TPIT0008 | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 602931 | 2013-12-31 |  | 69 | 0 | 0 | 0.0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 909 | Y | N
11TPIT0107 | Happy Valley: Tie 69 kV tap into Steamboat | Happy Valley: Tie 69 kV tap into Steamboat | Schedule Update | Happy Valley | Happy Valley | Planned | 341 - 0515 | AEP/ETT | Teresa Trotman 918-599-2653 | 2092 | 2013-12-31 |  | 69 | 0 | 0.6 | 0 | 0 | TAYLOR | TAYLOR | Tier 4 |  |  |  |  | Y | N
13TPIT0114 | Silver to Silver Tap 1: Reterminate the 69 kV line into the Cedar Hill 69 kV station and add 7.2 Mvar capacitor bank at Silver | Reterminate Silver Tap 1 to Silver with 795 ACSR and add 7.2 Mvar capacitor bank at Silver | Status, Contact & Schedule Update | Cedar Hill | Silver Tap 1 | Planned | 557 - 0719 | AEP/TNC | Paul Hassink 918-599-2653 | 2559 | 2013-12-31 |  | 69 | 0.02 | 0 | 0 | +7.2 | COKE | COKE | Tier 4 |  |  |  |  | Y | N
13TPIT0155 | Yucca: Add 10 MVA DRCS with 7.2 Mvar capacitor bank | Add 3.6 Mvar capacitor bank at Barnhart SWTEC and add 10 MVA DRCS with 7.2 Mvar capacitor bank at Yucca | Transmission Status Update | Yucca |  | Planned | 558 - 0721 | AEP/TNC | Michael Tallon 918-599-2653 | 2563 | 2013-12-31 |  | 69 | 0 | 0 | 0 | +17.2 / -10 | IRION | 0 | Tier 4 | 0 | 0 | 0 | 0 | Y | N | 0 | 0
13TPIT0173 | Friend Ranch: Remove 10 MVA DRCS | Add 3.6 Mvar capacitor bank at Barnhart SWTEC and add 10 MVA DRCS with 7.2 Mvar capacitor bank at Yucca | Transmission Status Update | Friend Ranch |  | Planned | 558 - 0721 | AEP/TNC | Michael Tallon 918-599-2653 | 2564 | 2013-12-31 |  | 69 | 0 | 0 | 0 | 0 | IRION | 0 | Tier 4 | 0 | 0 | 0 | 0 | Y | N | 0 | 0
14TPIT0058k | Mont Belvieu Area Upgrades | Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. |  | BENDER | DUNCAN | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-12-31 |  | 138 | 0 | 1.91 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 4 | 2012-02-03 | 2012-03-05 | N/A | 40155, 40360 | Y | N |  | Cost included in main project
14TPIT0058l | Mont Belvieu Area Upgrades | Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. |  | CROSBY | BENDER | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-12-31 |  | 138 | 0 | 7.89 | 0.0 | 0 | HARRIS | CHAMBERS | Tier 4 | 2012-02-03 | 2012-03-05 | N/A | 40390, 40155 | Y | N |  | Cost included in main project
13TPIT0194 | Cardiff Substation Conversion | Convert Cardiff substation from double-tap to 138kV loop service Ckt. 96. |  | Cardiff | South/Deer Park | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-12-31 |  | 138 | 0 | 0.2 | 0.0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 43250, 42241, 40442 | Y | N
13TPIT0160 | Whitepoint: Add 138 kV breaker terminal for WF interconnect | Construct a 138 kV breaker terminal at Whitepoint for the Midway WF Interconnect |  | Whitepoint |  | Planned | 573-0750 | AEP/TCC | Frank Pritzlaff (AEP) 918-599-2653 | 3454 | 2013-12-31 |  | 138 | 0 | 0 | 0 | 0 | SAN PATRICIO |  | TIER 4 |  |  |  | 8961 | Y | N
13TPIT0100 | Westminster Substation and transmission line | Build Westminster 138 kV Substation and transmission line tap from Oncor's Anna Switch - Van Alstyne 138 kV line. |  |  |  | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE076AB | 2013-12-31 |  | 138 | 0 | 0 | 0.0 | 0 | COLLIN |  | Tier 4 |  |  |  | 37270 | Y | N
15TPIT0015 | Hastings-Friendswood rebuild | Rebuild Hastings to Friendswood 138 kV transmission line with 795 ACSS conductor. Upgrade terminal equipment at Friendswood Substation. |  | Hastings | Friendswood | Planned |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | STE08112 | 2013-12-31 |  | 138 | 0 | 7.3 | 0.0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 38980, 39010 | Y | N
13TPIT0203 | Blossom - New Substation | Build Blossom 138-22 kV substation to serve new load and relieve Oncor Deport Substation |  | Blossom |  | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com |  | 2013-12-31 |  | 138 | 0 | 0 | 0 | 0 | LAMAR |  | Tier 4 |  |  |  | 11687 | Y | N
13TPIT0111 | WA Parish Split Bus | Split WA Parish 345kV Bus 44000 |  |  |  | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2013-12-31 |  | 345 | 0 | 0 | 0.0 | 0 | FORT BEND |  | Tier 2 | 2011-02-08 | 2011-09-22 | N/A | 44000, 44005 | Y | N
12TPIT0026 | North McCamey (76000) to Odessa EHV (11028) | Construct a new double circuit capable 345 kV transmission line (approximately 50 miles) between the existing LCRA TSC North McCamey (McCamey A) and the existing Oncor Odessa EHV stations. The new transmission line will consist of 2x1590 ACSR Falcon conductor to provide a thermal rating of 1678 MVA. | Project reassigned by PUCT to STEC from LCRA. | Odessa | North McCamey | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-12-31 |  | 345 | 59.6 | 0 | 0.0 | 0 | UPTON | ECTOR | CREZ |  |  |  | 76000-11028 | Y | N |  | Cost estimates for this project include TPIT project # 12TPIT0027. Both projects will be filed in one PUCT Project # in 2011.
12TPIT0027 | North McCamey (76000) to Bakersfield (76002) | Construct a new double circuit capable 345 kV transmission line (approximately 12 miles) between the LCRA TSC North McCamey (76000) and Bakersfield (76002) stations. The new transmission line will consist of 2x1590 ACSR Falcon conductor to provide a thermal rating of 1678 MVA | Project reassigned by PUCT to STEC from LCRA. | Bakersfield | North McCamey | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2013-12-31 |  | 345 | 15.9 | 0 | 0.0 | 0 | UPTON | PECOS | CREZ |  |  |  | 76000-76002 | Y | N |  | Cost estimates for this project have been included with TPIT project # 12TPIT0026. Both projects will be filed in one PUCT Project # in 2011.
13TPIT0084 | Big Hill to Kendall Series Compensation (Orsted) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Orsted |  | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2485 | 2013-12-31 |  | 345 | 0 | 0 | 0 | +933 | KENDALL |  | CREZ |  |  |  |  | Y | N
13TPIT0086 | Edison, add two 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Edison |  | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2487 | 2013-12-31 |  | 345 | 0 | 0 | 0 | -100 | KENDALL |  | CREZ |  |  |  |  | Y | N
13TPIT0087 | Orsted, add two 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Orsted |  | Planned | 478 - 0680 | AEP/ETT | Paul Hassink 918-599-2653 | 2488 | 2013-12-31 |  | 345 | 0 | 0 | 0 | -100 | KENDALL |  | CREZ |  |  |  |  | Y | N
13TPIT0142 | Broadview 72 MVAR Capacitor Bank | Install 72 MVAR capacitor bank on the East bus and remove both back-to-back capacitor banks from the West bus | [5 empty] | CPS | PM: Hector Torres | S-0395 | 2014-01-31 |  | 138 | 0 | 0 | 0.0 | 72 | BEXAR | BEXAR | Tier 4 |  |  |  | 5040 | Y | N |  | There are no transformers associated with this project
13TPIT0011 | Palo Alto - New 138kV Substation | Loop new 138kV substation into the existing 138kV Leon Creek to Chavaneaux line |  | Palo Alto | Leon Creek/Chavaneaus | Conceptual |  | CPS | Blake Williams | S-0527 | 2014-01-31 |  | 138 | 0.1 | 0 | 0.0 | 0 | BEXAR | BEXAR | Tier 4 | 2011-02-08 | 2011-09-22 | N/A | 5330 | Y | N |  | There are no transformers associated with this project
09TPIT0032 | Williamson 31.2 Mvar Capacitor bank | Install one 31.2 Mvar capacitor bank at Williamson substation. |  | Williamson Substation | Williamson Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P063 | 2014-02-01 |  | 138 | 0 | 0 | 0.0 | 31.2 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9295 | Y | N
13TPIT0108 | Nelson Sharpe to Ajo: Reconductor 345kV line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Reconfigure Series Capacitors at North Edinburg and Rio Hondo |  | Nelson Sharpe | Ajo | Planned | 071 - 0281 | AEP/ETT/TCC | Paul Hassink 918-599-2653 | 3181 | 2014-02-28 |  | 345 | 0 | 37.044 | 0 | 0 | KLEBERG | KENEDY | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 85000, 80076 | Y | N
13TPIT0013 | Perry to Midway Rebuild | Rebuild Perry to Midway with 959ACSS |  | Perry | Midway | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 08050 | 2014-03-28 |  | 69 | 0 | 12.4 | 0.0 | 0 | FALLS | FALLS | Tier 4 |  |  |  | 92185 | Y | N
14TPIT0058c | Mont Belvieu Area Upgrades | Build new circuit out of JORDAN substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new JORDAN - BARHIL circuit. |  | JORDAN | BARHIL | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 138 | 0.87 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40855, 40150 | Y | N |  | Cost included in main project
14TPIT0058d | Mont Belvieu Area Upgrades | Build new circuit out of JORDAN substation and reconnect portion of existing ENPROD - HACHER circuit to create new JORDAN - NORTON circuit. |  | JORDAN | NORTON | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 138 | 0.87 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40855, 40760 | Y | N |  | Cost included in main project
14TPIT0058e | Mont Belvieu Area Upgrades | Loop existing Ckt.86 DUNCAN - BENDER into new JORDAN substation to create new circuit JORDAN - DUNCAN. |  | JORDAN | DUNCAN | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 138 | 0 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40855, 40360 | Y | N |  | Cost included in main project
14TPIT0058f | Mont Belvieu Area Upgrades | Loop existing Ckt.86 DUNCAN - BENDER into new JORDAN substation to create new circuit JORDAN - BENDER. |  | JORDAN | BENDER | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 138 | 0 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40855, 40155 | Y | N |  | Cost included in main project
14TPIT0058g | Mont Belvieu Area Upgrades | Loop existing Ckt.86 ENPROD - CITIES into new JORDAN substation to create new circuit JORDAN - ENPROD. |  | JORDAN | ENPROD | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 138 | 0 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40855, 40510 | Y | N |  | Cost included in main project
14TPIT0058h | Mont Belvieu Area Upgrades | Loop existing Ckt.86 ENPROD - CITIES into new JORDAN substation to create new circuit JORDAN - CITIES. |  | JORDAN | CITIES | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 138 | 0 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40855, 40340 | Y | N |  | Cost included in main project
14TPIT0058i | Mont Belvieu Area Upgrades | Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new circuit DUNCAN - ENPROD. |  | DUNCAN | ENPROD | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 138 | 0 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40360, 40510 | Y | N |  | Cost included in main project
14TPIT0058a | Mont Belvieu Area Upgrades | Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. |  | JORDAN | Cedar Bayou | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 345 | 0 | 0 | 0.0 | 0 | CHAMBERS | CHAMBERS | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40850, 40000 | Y | N |  | Cost included in main project
14TPIT0058b | Mont Belvieu Area Upgrades | Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. |  | JORDAN | Northbelt | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 345 | 0 | 0 | 0 | 0 | CHAMBERS | CHAMBERS | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40850, 46100 | Y | N |  | Cost included in main project
13TPIT0110 | Rio Hondo: Reconfigure 345 kV Series Capacitors | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Reconfigure Series Capacitors at North Edinburg and Rio Hondo | Schedule Update | Rio Hondo |  | Planned | 071 - 0281 | AEP/TCC | Paul Hassink 918-599-2653 | 3185 | 2014-03-31 |  | 345 | 0 | 0 | 0 | 0 | CAMERON |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8318 | Y | N
14TPIT0058 | Mont Belvieu Area Upgrades | Build new 345/138kV JORDAN substation. Install new 800 MVA autotransformer. |  |  |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-03-31 |  | 345/138 | 0 | 0 | 800 | 0 | CHAMBERS |  | Tier 3 | 2012-02-03 | 2012-03-05 | N/A | 40850, 40855, 49077 | Y | N
07TPIT0077 | Big Foot to Devine: Rebuild 69 kV Line | Add CPS Lytle to ETT Lytle 795 ACSR 138 kV line and 93 MVA 69/138 kV autotransformer at Lytle |  | Big Foot | Devine | Under Construction | 028 - 0028 | AEP/ETT | Terry Weeks (AEP) 918-599-2653 | 1777 | 2014-05-01 |  | 69 | 0 | 6.1 | 0 | 0 | FRIO | MEDINA | Tier 4 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8218, 8223 | Y | Y
07TPIT0116 | Handley - Duval 69 kV line | Upgrade existing 69 kV line |  | Handley | Duval | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5116-E | 2014-05-01 |  | 69 | 0 | 5.4 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 1952, 2158 | Y | N
07TPIT0210 | Hilltop - White Settlement 69 kV line | Rebuild 4/0 ACSR section of line | Studies indicate timing of project should be changed | Hilltop | White Settlement | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5135-E | 2014-05-01 |  | 69 | 0 | 14.33 | 0 | 0 | PARKER | TARRANT | Tier 4 |  |  |  | 502, 1588, 2089 | Y | N
14TPIT0083 | Electra 69 kV capacitors | Install capacitors |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R561-E | 2014-05-01 |  | 69 | 0 | 0 | 0 | 9.2 | WICHITA |  | Tier 4 |  |  |  | 1538 | Y | N
14TPIT0060 | Arco Station Upgrade | Upgrade Krugerville line terminal and station transfer bus equipment and associated relay and SCADA systems |  | Arco | Arco | Planned |  | TMPA | Eric Schroeder 936-873-1124 eschroeder@texasmpa.org | T12002 | 2014-05-01 |  | 138 | 0 | 0 | 0 | 0 | Denton |  | Tier 4 |  |  |  |  | N | N
14TPIT0049 | Big Foot SW Station: Install 138 kV Ring Bus | Add CPS Lytle to ETT Lytle 795 ACSR 138 kV line and 93 MVA 69/138 kV autotransformer at Lytle |  | Big Foot |  | Under Construction | 028 - 0028 | AEP/TCC | Terri Weeks 918-599-2653 | 1786 | 2014-05-01 |  | 138 | 0 | 0 | 0 | 0 | FRIO | FRIO | Tier 4 |  |  |  | 8218 | N | N
07TPIT0017 | Handley - Hurst 138 kV line | Reconductor existing 138 kV line | Construction schedule change | Handley | Hurst | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M572-WAC | 2014-05-01 |  | 138 | 0 | 18.7 | 0.0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 1950, 2110, 2109, 1951 | Y | N |  | Interim rating increase was implemented in May 2012.
08TPIT0109 | Payne - Collin Switching Station 138 kV line | Rebuild existing 138 kV line |  | Payne | Collin Switching Station | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R519-E | 2014-05-01 |  | 138 | 0 | 31.75 | 0 | 0 | GRAYSON | COLLIN | Tier 3 |  |  |  | 1758, 1757, 2350, 2366, 2349, 2364, 2370 | N | N | 2009-R12
08TPIT0153 | Elkton - Athens 138 kV line | Upgrade existing 138 kV line |  | Elkton | Athens | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R651-E | 2014-05-01 |  | 138 | 0 | 29.1 | 0 | 0 | HENDERSON | HENDERSON | Tier 4 | 2007-11-26 |  |  | 3177, 3178, 3172, 3131 | Y | N
09TPIT0044 | E. Richardson - Apollo 138 kV line (Oncor Electric Delivery section) | Upgrade existing 138 kV line |  | E. Richardson | Apollo | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3033-WA | 2014-05-01 |  | 138 | 0 | 2.32 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 802, 2690 | N | N
13TPIT0060 | Cedar Hill Switch - Mountain Creek 138 kV line | Upgrade existing line |  | Cedar Hill Switch | Mountain Creek | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4068-E | 2014-05-01 |  | 138 | 0 | 11.4 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2422, 2421, 2412, 2411 | Y | N
13TPIT0094 | Lamesa - Ackerly Vealmoor 138 kV line | Add second circuit to existing line |  | Lamesa | Ackerly Vealmoor | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8032-E | 2014-05-01 |  | 138 | 21.5 | 0 | 0 | 0 | DAWSON | HOWARD | Tier 2 | 2008-10-01 | 2011-01-01 |  | 1355, 1163 | Y | N
13TPIT0136 | Odessa North 138 kV Switching Station | Construction 138 kV switching station |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8050B-E | 2014-05-01 |  | 138 | 0 | 0 | 0 | 0 | ECTOR |  | Tier 4 |  |  |  | 1122, 1123 | Y | N
13TPIT0152 | Wink Switch - Loving - El Mar - Mason 138 kV line | Upgrade existing 138 kV line |  | Wink Switch | Mason | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8066-E | 2014-05-01 |  | 138 | 0 | 40 | 0 | 0 | WINKLER | REEVES | Tier 3 | 2012-05-02 | 2012-06-06 | N/A | 1092, 1074, 1093, 1094 | Y | N |  | Wink - Loving complete in 5/2013, Loving - El Mar complete in 12/2013 and El Mar - Mason complete in 5/2014
13TPIT0153 | Moss - Odessa EHV 138 kV line | Upgrade existing 138 kV line |  | Moss | Odessa EHV | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8064-E | 2014-05-01 |  | 138 | 0 | 14.2 | 0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 1019, 1027 | Y | N
14TPIT0015 | Troup - Walnut Grove - Whitehouse - Tyler Grande 138 kV line | Upgrade existing line | Construction schedule change | Troup | Tyler Grande | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R6002-WAC | 2014-05-01 |  | 138 | 0 | 13.34 | 0.0 | 0 | CHEROKEE | SMITH | Tier 4 |  |  |  | 3147, 3227, 3156 | Y | N |  | A SPS has been modified to manage flow on this line.
14TPIT0052 | Stanton East - Triangle (SU) 138 kV line | Upgrade existing line | Project scope change | Triangle (SU) | Stanton East | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8025-E | 2014-05-01 |  | 138 | 0 | 4.1 | 0 | 0 | MARTIN | MARTIN | Tier 4 |  |  |  | 1326, 79549 | Y | N
14TPIT0053 | Moss - Westover 138 kV line | Upgrade existing line |  | Moss | Westover | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8016-E | 2014-05-01 |  | 138 | 0 | 3.4 | 0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 1019, 1129 | Y | N
14TPIT0084 | Ackerly Vealmoor 138 kV Switching Station | Install 138 kV circuit breakers |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8034-E | 2014-05-01 |  | 138 | 0 | 0 | 0 | 0 | DAWSON |  | Tier 4 |  |  |  | 1355 | Y | N
14TPIT0085 | Lamesa Switching Station | Install 138 kV circuit breakers |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8033-E | 2014-05-01 |  | 138 | 0 | 0 | 0 | 0 | HOWARD |  | Tier 4 |  |  |  | 1163 | Y | N
14TPIT0086 | Allen Switch - Parker Maxwell Creek - Ben Davis 138 kV line | Upgrade existing line |  | Allen Switch | Ben Davis Switch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4102-E | 2014-05-01 |  | 138 | 0 | 9.4 | 0 | 0 | COLLIN | COLLIN | Tier 4 |  |  |  | 12509, 2477, 968 | Y | N
14TPIT0089 | North Main Switch third transmission source | Construct a third 138 kV line into North Main Switch |  | North Main Tap | North Main Switch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5161-E | 2014-05-01 |  | 138 | 4.4 | 4.4 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 1961 | Y | N
07TPIT0126 | Tri Corner - Seagoville Switch 345 kV line | Upgrade existing 345 kV line |  | Tri Corner | Seagoville Switch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4044-E | 2014-05-01 |  | 345 | 0 | 9.4 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2432, 2433 | Y | N
09TPIT0042 | Collin 345/138 kV autotransformer | Install second 345/138 kV autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M318-E | 2014-05-01 |  | 345 | 0 | 0 | 600 | 0 | COLLIN |  | Tier 4 |  |  |  | 2370, 2372 | N | N | 2009-R15
14TPIT0091 | Riley (Oklaunion) - Fisher Road 345 kV line relocation | Relocate 345 kV line |  | Oklaunion | Fisher Road | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R921-E | 2014-05-01 |  | 345 | 6.91 | 0 | 0 | 0 | WILBARGER | WICHITA | Tier 4 |  |  |  | 6101, 1425 | Y | N
14TPIT0092 | Temple Switch - Bell County East 345 kV line | Upgrade existing 345 kV line |  | Temple Switch | Bell County East | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R764-E | 2014-05-01 |  | 345 | 0 | 24 | 0 | 0 | BELL | BELL | Tier 4 |  |  |  | 3687, 3414 | Y | N
10TPIT0010 | Coppell to Roanoke Reconductor | Reconductor existing Coppell to Roanoke 138kv line with 959ACSS conductor |  | Coppell | Roanoke | planned | 12TPIT0079 | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 02005 | 2014-05-27 |  | 138 | 0 | 17 | 0.0 | 0 | TARRANT | DALLAS | Tier 4 |  |  |  | 1852, 661, 556, 555, 648 | Y | N |  | construction by Oncor
13TPIT0157 | Cactus to Ft. Lancaster: Rebuild 69 kV line | Rebuild Cactus to Ft. Lancaster 69 kV line with 795 ACSS | Transmission Status & Contact Update | Cactus | Ft. Lancaster | Planned | 569 - 0743 | AEP/TNC | Paul Hassink 918-599-2653 | 2573 | 2014-05-31 |  | 69 | 0 | 9.28 | 0 | 0 | CROCKETT | PECOS | Tier 4 |  |  |  |  | Y | N
14TPIT0076 | Fry Road 138kV Substation | Build new 138kV Fry Road distribution substation. Double tap off Ckt.09 Zenith - Gertie tap and Ckt.76 Zenith - Gertie tap. |  | Fry Road | Zenith/Gertie | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-05-31 |  | 138 | 0.1 | 0 | 0 | 0 | HARRIS |  | Tier 4 |  |  |  | 44910, 45811, 45801, 45812, 45802 | Y | N
14TPIT0058j | Mont Belvieu Area Upgrades | Remove BRINE substation from CNP transmission service |  | BRINE |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-05-31 |  | 138 | 0 | 0 | 0 | 0 | CHAMBERS |  | Tier 4 | 2012-02-03 | 2012-03-05 | N/A | 40220 | Y | N |  | Cost included in main project
10TPIT0148 | Las Pulgas Tap - Renamed from Willacy Tap Switch 138kV | Move normally open 138kV connection to the AEP Raymondville #2 bus and add breakers at Las Pulgas to serve E Raymondville and La Sara from Las Pulgas. |  |  |  | Planned | 12TPIT0103 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2014-05-31 |  | 138 | 0 | 0 | 0.0 | 0 | WILLACY | WILLACY | Tier 4 |  |  |  | 80309 | N | N
14TPIT0072 | Las Pulgas: Complete Ringbus, Add Breakers, Terminate STEC East Raymondville 138 kV Line | Loop STEC radial 138 kV Raymondville #2 to East Raymondville line into Las Pulgas | Updated 'TSP/Company Contact' Field | Las Pulgas |  | Conceptual |  | AEP/TCC | Paul Hassink (AEP) 918-599-2653 Doug Evans (STEC) 361-485-6459 |  | 2014-05-31 |  | 138 | 0 | 0 | 0 | 0 | WILLACY |  | Tier 4 |  |  |  | 80309 | N | N
14TPIT0065 | Concho: Replace 138/69 kV autotransformer & build four breaker ring bus | Rebuild new Concho station and replace 138/69 kV autotransformer | Project Title, Description, Status & Contact Update | Concho |  | Planned | 567 - 0741 | AEP/TNC | Paul Hassink 918-599-2653 | 2571 | 2014-05-31 |  | 138 | 0 | 0 | 90 | 0 | TOM GREEN |  | Tier 4 |  |  |  |  | Y | N
13TPIT0171 | Farmersville West - New Substation | Build a new 138-12.47 kV substation to accommodate load growth in Farmersville. Cut Oncor's Princeton - Royce City 138 kV line into the new substation. |  |  |  | Planned | 16TPIT0005 | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com |  | 2014-05-31 |  | 138 | 0 | 0 | 0 | 0 | Collin |  | Tier 4 |  |  |  | 12527, 37291 | Y | N
14TPIT0074 | Thompson Creek to Snook Transmission Line | Build 6 miles of 1033ACSR transmission line (operated at 138 kV) to Snook substation. | The Thompson Creek to Koppe Bridge Line is now broken into two segments with different completion dates. | Thompson Creek | Snook Substation | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2014-05-31 |  | 138 | 2.4 | 3.6 | 0 | 0 | BRAZOS | BURLESON | Tier 4 |  |  |  |  | Y | N
14TPIT0066 | Treece: Build new three breaker ring bus | Interconnect Blue Summit Wind Farm at Treece to connect Blue Summit to the Riley to Tesla 345 kV line |  | Riley | Tesla | Planned | 512 - 0724 | AEP/ETT | Dave Goetz 918-599-2653 | 2515 | 2014-05-31 |  | 345 | 0 | 0 | 0 | 0 | WILBARGER |  | Tier 4 |  |  |  |  | Y | N
14TPIT0077 | PH Robinson Autotransformer Upgrade | Replace existing 400MVA PH Robinson autotransformer A1 with 800MVA autotransformer. |  | PH Robinson |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-05-31 |  | 345/138 | 0 | 0 | 400.0 | 0 | GALVESTON |  | Tier 4 |  |  |  | 42000, 42015, 49026 | Y | N
12TPIT0143 | Danevang Switch to El Campo Rebuild | Rebuild 4/0 ACSR 69 kV to 138 capable 795 ACSR. |  | Danevang Switch | El Campo | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2014-06-01 |  | 69 | 0 | 12.75 | 0.0 | 0 | WHARTON | WHARTON | Tier 4 |  |  |  | 5544, 5540 5543, 5538 | Y | N
13TPIT0128 | Danevang Switch to Danevang Substaton Rebuild | Rebuild 4/0 ACSR 69 kV to 138 capable 795 ACSR. |  | Danevang Switch | Danevang Substation | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2014-06-01 |  | 69 | 0 | 2.2 | 0.0 | 0 | WHARTON | WHARTON | Tier 4 |  |  |  | 5544, 5548 | Y | N
12TPIT0182 | Crystal City - Turtle Creek: Reconductor 69kV Line | Reconductor Crystal City - Turtle Creek 69kV Line | Change Status | Crystal City | Turtle Creek | Planned | 591-0745 | AEP/TCC | Paul Hassink 918-599-2660 | 0 | 2014-06-01 |  | 69 | 0 | 3.3 | 0 | 0 | ZAVALA | ZAVALA | Tier 4 |  |  |  | 8242, 8243 | Y | N |  | 0
12TPIT0180 | Lon Hill to City of Robstown: Rebuild 69kV line | Rebuild Lon Hill - City of Robstown 69kV Line | Description changed | Lon Hill | City of Robstown | Conceptual | 582-0735 | AEP/TCC | Paul Hassink 918-599-2657 | 3460 | 2014-06-01 |  | 69 | 0 | 4.6 | 0 | 0 | SAN PATRICIO | SAN PATRICIO | Tier 4 |  |  |  | 8448, 8884 | Y | N |  | 0
12TPIT0123 | Braunig West Bus - 138 kV Substation Equipment Upgrade | Upgrade Terminals at Braunig West for Valley Rd., Mauermann Rd., Streich Rd. circuits and upgrade terminals at remote ends to ensure a 2420 A rating and remove the existing MLSE on the 138kV transmission lines |  | Braunig_W | Valley Rd Mauermann Streich Rd | Planned | T-0181 | CPS | Blake Williams | S-0658 | 2014-06-01 |  | 138 | 0 | 0 | 0.0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5025 5465 5297 5417 | Y | N |  | There are no transformers associated with this project
14TPIT0042 | Five Points to Broadview - 138 kV Transmission Line Rebuild | Rebuild 9.4 miles of 138 kV transmission line from Five Points to Broadview and ensure a minimum conductor rating of 331 MVA |  | Five Points | Broadview | Conceptual |  | CPS | Blake Williams | T-0208 | 2014-06-01 |  | 138 | 0 | 9.4 | 0 | 0 | BEXAR | BEXAR | Tier 3 |  |  |  | 5025 5428 | Y | N |  | There are no transformers associated with this project
14TPIT0044 | Helotes to Hill Country - 138 kV Substation Equipment Upgrade | Upgrade terminals at Helotes and Hill Country to ensure a 2420 A rating and remove existing MLSE on Helotes to Hill Country 138 kV transmission line |  | Helotes | Hill Country | Conceptual |  | CPS | Blake Williams | S-0651 | 2014-06-01 |  | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5200 5210 | Y | N |  | There are no transformers associated with this project
14TPIT0045 | Anderson to Cagnon - 138 kV Substation Equipment Upgrade | Upgrade terminals at Anderson and Cagnon to ensure at 2420 A rating and remove the existing MLSE on Anderson to Cagnon 138kV transmission line |  | Anderson | Cagnon | Conceptual |  | CPS | Blake Williams | S-0479 | 2014-06-01 |  | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5054 5003 | Y | N |  | There are no transformers associated with this project
14TPIT0046 | Hill Country to La Sierra - 138 kV Substation Equipment Upgrade | Upgrade termainls at Hill Country and La Sierrra to ensure a 2420 A rating and remove the existing MLSE on Hill Country to La Sierra 138kV transmission line |  | Hill Country | La Sierra | Conceptual |  | CPS | Blake Williams | S-0485 | 2014-06-01 |  | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5209 5257 | Y | N |  | There are no transformers associated with this project
10TPIT0038 | College-Brand 138 kV line | Line reconductor | On Hold For Funding | Switch 8832 at College | Switch 1364 at Brand | Planned |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2014-06-01 |  | 138 | 0 | 4.2 | 0 | 0 | DALLAS |  | Tier 4 |  |  |  | 829, 827 | Y | N |  | This project is a line reconductor for solving overload
13TPIT0130 | San Miguel to Fashing Conversion | Convert 69 kV line to 138 kV line. The line was originally built for 138 kV operation | Likely to be sped up with new load forecast | San Miguel | Fashing | Planned | 13TPIT0123 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2014-06-01 |  | 138 | 0 | 23.05 | 0 | 0 | ATASCOSA | ATASCOSA | Tier 3 | 2012-09-12 | on-going |  | 5706, 5715 | Y | N
13TPIT0123 | Fashing Autotransformer | Expand Fashing station to have 138 kV and add a 150 MVA 138/69 kV autotransformer at Fashing. | Likely to be sped up with new load forecast |  |  | Planned | 13TPIT0130 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2014-06-01 |  | 138 | 0 | 0 | 150 | 0 | ATASCOSA |  | Tier 3 | 2012-09-12 | on-going |  | 5715, 5716 | Y | N
11TPIT0009 | Dunlap 138kV substation | Install one 30MVA Transformer at Dunlap Substation |  | Dunlap Substation | Dunlap Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | 3230_117_2930 3230_117_2933 3240_117_4930 3240_117_4933 | 2014-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9045 | Y | N
13TPIT0058 | Circuit 941 Summit - Williamson Reconductor | Reconductor the 3.54 miles circuit from single 795 ACSR to single 795 ACSS Drake conductor. |  | Summit Substation | Williamson Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_079 | 2014-06-01 |  | 138 | 0 | 3.54 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9279, 9295 | Y | N
10TPIT0013 | Apollo to East Richardson | BEPC's portion of the line. | Oncor to rebuild BEPC's portion of the line | Apollo | East Richardson | planned | 09TPIT0044 | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 05010 | 2014-06-01 |  | 138 | 0 | 1.4 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 802, 2690 | Y | N |  | mileage shown is for Bepc portion of line
12TPIT0184 | Lon Hill: Replace 138/69kV Autotransformers #1 and #2 | Upgrade Both 138/69kV Autotransformers at Lon Hill to 240MVA | Change Status | Lon Hill |  | Planned | 580-0734 | AEP/TCC | Paul Hassink 918-599-2656 | 3463 | 2014-06-01 |  | 138 | 0 | 0 | 240 | 0 | SAN PATRICIO |  | Tier 4 |  |  |  | 8452, 8448 | Y | N |  | 0
12TPIT0185 | Airline to Westside: Add 138kV Circuit | Add a Second 138kV Circuit between Airline and Westside |  | Airline | Cabaniss | Conceptual | 584-0747 | AEP/TCC | Paul Hassink 918-599-2662 | 3464 | 2014-06-01 |  | 138 | 0 | 5.5 | 0 | 0 | NUECES | NUECES | Tier 4 |  |  |  | 8490, 8485 | Y | N |  | 0
14TPIT0043 | Tri-County - New 138kV Substation | Loop new 138kV substation into the existing Skyline to Wiederstein transmission line |  | Skyline | Tri_Conty/Wiederstein | Conceptual | T-0191 | CPS | Blake Williams | S-0620 | 2014-06-06 |  | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5370 5445 7461 | Y | N |  | There are no transformers associated with this project
14TPIT0032 | Downing to Mountary | Existing 69 kV line. |  | Downing | Mountary | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10044 | 2014-06-15 |  | 69 | 0 | 15 | 0 | 0 | COMANCHE | COMANCHE | Tier 4 |  |  |  | 281, 294 | Y | N | 2009-R29
14TPIT0069 | Expansion of 138kV Palo Alto station | Add one more bay position to existing 138kV Palo Alto station | New | Palo Alto |  | Planned |  | SU | Bill Bojorquez 512-771-0965 BBojorquez@hunttransmission.com |  | 2014-06-16 |  | 138 | 0 | 0 | 0 | 0 | Cameron |  | Tier 1 | 2011-05-03 | 2011-12-19 | 2012-01-17 |  | N | N
14TPIT0070 | New 138kV line from LaPalma to Palo Alto | Construct new La Palma – Palo Alto 138 kV line (~12 mi) and station upgrades | New Changed Dollars to include the station costs associated with the project (Approved by RPG, see comments for breakout) | LaPalma | Palo Alto | Planned |  | SU/TCC | Bill Bojorquez (SU) 512-771-0965 Paul Hassink (AEP) 918-599-2656 |  | 2014-06-16 |  | 138 | 12 | 0 | 0 | 0 | Cameron | Cameron | Tier 1 | 2011-05-03 | 2011-12-19 | 2012-01-17 |  | N | N
14TPIT0040 | Springwoods 138kV Substation | Build new 138kV Springwoods distribution substation. Loop through Ckt.66 Rayford to Westfield. |  | Springwoods | Rayford/ Louetta | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2014-06-29 |  | 138 | 6.2 | 0 | 0 | 0 | HARRIS |  | Tier 4 |  |  |  | 46270, 46295, 46051 | Y | N
14TPIT0004 | Cushman-Highway 123 | Construct a new 6.2 mile single 795 ACSR 138 kV transmission line (rated 220 MVA) from the new Highway 123 substation (7221) located near the intersection of State Highway 123 and the GVEC Hickory Forest (7225)-New Berlin (7612) 138 kV (T–529) transmission line to the LCRA TSC Cushman substation (7226). |  | Highway 123 | Cushman/New Berlin/Hickory Forrest | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2014-06-30 |  | 138 | 6.2 | 0 | 0 | 0 | GUADALUPE |  | Tier 2 | 2009-02-06 | 2009-06-01 | N/A | SEE PROJECT DESCRIPTION | Y | N
05TPIT0065 | Highway 32-Wimberley | Construct a new 795 ACSR (220-MVA) 138-kV double circuit transmission line (approximately four miles) between the Highway 32(7546) and Wimberley(7496) substations. |  | Highway 32 | Wimberley | Planned |  | PEC | Randy Buchanan (830) 868-6058 |  | 2014-06-30 |  | 138 | 4 | 0 | 0 | 0 | HAYS | HAYS | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | N | N
14TPIT0021 | Buttercup-Whitestone Upgrade | Upgrade the 2.3-mile Buttercup (7531)-Whitestone (7529) 795 ACSR (220-MVA) 138-kV transmission line to bundled 795 ACSR (440MVA). |  | Buttercup Substation | Whitestone Substation | Planned |  | PEC | Randy Buchanan (830) 868-6058 |  | 2014-06-30 |  | 138 | 0 | 2.3 | 0 | 0 | WILLIAMSON | WILLIAMSON | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
14TPIT0073 | Kokernut Substation | Build a 138x69-26.18 kV 12/16/20 MVA substation on the GVEC Gonzales-GVEC Shiner 69 kV transmission line |  | Kokernut | Gonzales/Shiner | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2014-07-30 |  | 69 | 0 | 0 | 0 | 0 | GONZALES |  | Tier 4 |  |  |  |  | N | N
14TPIT0062 | Kurten Substation Upgrage | Install (3) Breaker ring to support (2) existing 138 lines and (1) existing 138/12.5 transformer |  | Kurten Substation | Kurten Substation | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2014-08-30 |  | 138 | 0 | 0 | 0 | 0 | BRAZOS |  | Tier 4 |  |  |  |  | N | N
13TPIT0161 | Rojo Springs: Build new three breaker ring bus | Interconnect Baker Ranch Wind Farm at Rojo Springs to connect Baker Ranch to the Mulberry Creek to Oklaunion 345 kV line |  | Mulberry Creek | Oklaunion | Planned | 408 - 0597 | AEP/ETT | Dave Goetz 918-599-2653 | 3132 | 2014-08-31 |  | 345 | 0 | 0 | 0 | 0 | HASKELL |  | Tier 4 |  |  |  |  | Y | N
14TPIT0061 | Atkins to Briarcrest Upgrade | Upgrade to 795 ACSR to alleviate overload during double contingency situations. Add OPGW. Add new poles/structures. |  | Atkins Substation | Briarcrest Substation | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2014-09-30 |  | 138 | 0 | 3.4 | 0 | 0 | BRAZOS | BRAZOS | Tier 4 |  |  |  |  | N | N
12TPIT0007 | FM-725 - New Substation | Build a 138-26.18 kV, 40 MVA substation on the GVEC McQueeney(7606) - Schumansville(7609) 138 kV transmission line |  | FM 725 | McQueeney/Schumansville | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2014-10-30 |  | 138 | 0 | 0 | 0 | 0 | GUADALUPE |  | Tier 4 |  |  |  | See Project Title | N | N
11TPIT0012 | Euless - Grapevine Ball Street 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Euless | Grapevine Ball Street | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5131-E | 2014-11-01 |  | 138 | 0 | 5.9 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 2016, 2021 | Y | N |  | Euless - Highway 360 Substation section by 5/2014
13TPIT0137 | Odessa North - Goldsmith Junction 138 kV line | Rebuild existing 69 kV line to create a double-circuit line with 69 kV and 138 kV circuits | Construction schedule change | Odessa North Switch | Goldsmith Junction | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8050C-E | 2014-11-01 |  | 138 | 13.3 | 0 | 0 | 0 | ECTOR | ECTOR | Tier 3 |  |  |  | 11256, 1123 | Y | N
14TPIT0054 | Odessa - Odessa North 138 kV line | Upgrade existing line | Construction schedule change | Odessa | Odessa North | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8019-E | 2014-11-01 |  | 138 | 0 | 7.2 | 0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 1126, 1122 | N | N
14TPIT0090 | Monticello shunt reactors | Install shunt reactors |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R919-E | 2014-11-01 |  | 345 | 0 | 0 | 0 | -100 | TITUS |  | Tier 4 |  |  |  | 1695 | Y | N
14TPIT0093 | Paris Switch shunt reactor | Install shunt reactor |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R920-E | 2014-11-01 |  | 345 | 0 | 0 | 0 | -100 | LAMAR |  | Tier 4 |  |  |  | 1692 | Y | N
14TPIT0071 | Princeton South - New Substation | Build a new 138-12.47 kV substation to accommodate load growth in Princeton. |  |  |  | Planned | 16TPIT0005 | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com |  | 2014-11-29 |  | 138 | 0 | 0 | 0 | 0 | Collin |  | Tier 4 |  |  |  | 37295 | Y | N
16TPIT0005 | Farmersville West to Princeton South - new 138 kV line. | Build approximately 7.5 miles of 138 kV transmission line from Farmersville West Substation to Princeton South Substation. |  | Farmersville West | Princeton South | Planned | New projects added on rows 18 and 19. Please add TPIT numbers here after they have been assigned. | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE07213 | 2014-11-30 |  | 138 | 7.5 | 0 | 0 | 0 | COLLIN | COLLIN | Tier 4 |  |  |  | 37291, 37295 | Y | N
15TPIT0026 | Wellborn to Millican Upgrade | ReBuild-Reconductor (3.6) miles of 69kV line converting to 138 kV as part of 138 kV BEC Roans Prairie Project |  | Wellborn Susbstation | Millican Substation | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2014-11-30 |  | 138 | 0 | 3.6 | 0 | 0 | BRAZOS | BRAZOS | Tier 4 |  |  |  |  | N | N
15TPIT0027 | Millican Substation Upgrade | Install (3) Breaker ring to support (2) 138kV lines and (1) 138/69 auto-transformer |  | Millican Substation | Millican Substation | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2014-11-30 |  | 138 | 0 | 0 | 0 | 0 | BRAZOS |  | Tier 4 |  |  |  |  | N | N
14TPIT0075 | Millican to BEC HWY 6Line | Build(6) miles of new 1033 ACSR energized at 138 kV to planned BEC HWY 6 substation as part of Dobbin Project |  | Millican Substation | BEC HWY 6 Substation | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2014-11-30 |  | 138 | 6 | 0 | 0 | 0 | BRAZOS | BRAZOS | Tier 4 |  |  |  |  | N | N
14TPIT0059 | Bevo Station and Autotransformer | Build new Bevo substation west of Cotulla where 138 and 69 kV lines cross and add a 150 MVA 139/69 kV autotransformer |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2014-12-01 |  | 69 | 0 | 0 | 150 | 0 | DIMMIT |  | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5871, 78280 | Y | N
14TPIT0068 | North Lakes Substation to Bonnie Brae Substation 69kV Transmission Line Reconstruction | Reconstruct approximately 1.2 miles of existing 69V transmission line | New Project | North Lakes Substation PSS/E Bus 915 | Bonnie Brae Substation PSS/E Bus 905 | Planned | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 602946 | 2014-12-01 |  | 69 | 0 | 1.2 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 915, 905 | Y | N
14TPIT0078 | Advance Capacitor Bank | Install 15 MVAR at Advance substation |  | Advance | Advance | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 12011 | 2014-12-01 |  | 69 | 0 | 0 | 0 | 15 | PARKER |  | Tier 4 |  |  |  | 518 | Y | N
14TPIT0081 | Perch Hill Capacitor Bank | Install 15 MVAR at Perch Hill substation |  | Perch Hill | Perch Hill | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 12012 | 2014-12-01 |  | 138 | 0 | 0 | 25 | 0 | WISE |  | Tier 4 |  |  |  | 590 | Y | N
14TPIT0079 | Glen Rose to Meridian Rebuild | Rebuild Glen Rose to Meridian with 959 ACSS, 138 kV construction (operate at 69 kV) |  | Glen Rose | Meridian | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 12044 | 2014-12-02 |  | 69 | 0 | 18.18 | 0 | 0 | SOMERVELL | BOSQUE | Tier 4 |  |  |  | 315, 319 | Y | N
14TPIT0080 | Oran to Advance Rebuild | Rebuild Oran to Advance with 959 ACSS, 138 kV construction (operate at 69 kV) |  | Oran | Advance | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 12010 | 2014-12-03 |  | 69 | 0 | 13.7 | 0 | 0 | PALO PINTO | PARKER | Tier 4 |  |  |  | 518, 519, 785 | Y | N
09TPIT0073 | Jupiter-Apollo 69 kV line | Line reconductor | On Hold For Funding | Switch 1377 at Jupiter | Switch 6612 at Apollo | Planned |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2014-12-28 |  | 138 | 0 | 2 | 0 | 0 | DALLAS |  | Tier 4 |  |  |  | 806, 802 | Y | N |  | This project is a line reconductor for solving overload
09TPIT0074 | Jupiter-Lawler 69 kV line | Line reconductor | On Hold For Funding | Switch 1378 at Jupiter | Switch 931 at Lawler Tap | Planned |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2014-12-28 |  | 138 | 0 | 1.5 | 0 | 0 | DALLAS |  | Tier 4 |  |  |  | 806, 815, 820 | Y | N |  | This project is a line reconductor for solving overload
09TPIT0076 | Lawler-College 69 kV line | Line reconductor | On Hold For Funding | Switch 932 at Lawler Tap | Switch 6832 at College | Planned |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2014-12-28 |  | 138 | 0 | 2 | 0 | 0 | DALLAS |  | Tier 4 |  |  |  | 803, 815, 820 | Y | N |  | This project is a line reconductor for solving overload
14TPIT0064 | West Yates to Air Products: Rebuild 69 kV line | Rebuild West Yates to Air Products 69 kV line with 795 ACSS | Transmission Status & Contact Update | West Yates | Air Products | Planned | 570 - 0744 | AEP/TNC | Paul Hassink 918-599-2653 | 2574 | 2014-12-31 |  | 69 | 0 | 2.28 | 0 | 0 | PECOS | CROCKETT | Tier 4 |  |  |  |  | Y | N
14TPIT0094 | Pecos Substation Ring Bus | Build ring bus for 69 kV system in TNMP's Pecos Substation |  | Pecos |  | Conceptual |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE03414 | 2014-12-31 |  | 69 | 0 | 0 | 0 | 0 | REEVES |  | Tier 4 |  |  |  |  | N | N
12TPIT0015 | Barney Davis to Laguna: Construct 138 kV transmission line | Construct new 138 kV line and add tranformation at Laguna to remove contingency overloads during off-peak maintenance |  | Barney Davis | Laguna | Planned | 400 - 0648 | AEP/ETT | Michael Glueck 918-599-2653 | 3302 | 2014-12-31 |  | 138 | 4.2 | 0 | 0 | 0 | NUECES | NUECES | Tier 1 | 2009-03-26 | 2009-10-09 | 2009-12-01 |  | Y | N
12TPIT0014 | Laguna: Add 138/69 kV Auto | Construct new 138 kV line and add tranformation at Laguna to remove contingency overloads during off-peak maintenance |  | Laguna |  | Planned | 400 - 0648 | AEP/ETT/TCC | Michael Glueck 918-599-2653 | 3307 | 2014-12-31 |  | 138 | 0 | 0 | 240 | 0 | NUECES |  | Tier 1 | 2009-03-24 | 2009-10-09 | 2009-12-01 |  | Y | N
14TPIT0082 | Kenedy - Pettus: Build 138 kV line | Rebuild Kenedy - Pettus 69 kV line with 69/138 kV double circuit line | NEW | Kenedy | Pettus | Planned | 603 - 0765 | AEP/TCC | Paul Hassink 918-599-2653 | 3473 | 2014-12-31 |  | 138 | 0 | 15.9 | 0 | 0 | Karnes | Bee | Tier 3 |  |  |  | 8184, 8186, 8188, 8590 | Y | N
14TPIT0067 | San Angelo Area: Replace both 345/138 kV autotransformers | Add 345/138 kV autotransformer capacity at Red Creek or build new 345/138 kV station | Transmission Status & Contact Update | Red Creek |  | Planned | 566 - 0740 | AEP/TNC | Paul Hassink 918-599-2653 | 2570 | 2014-12-31 |  | 345 | 0 | 0 | 800 | 0 | TOM GREEN |  | Tier 3 |  |  |  |  | Y | N
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2015-01-01 |  | 69 | 0 | 0 | 0 | 0 | VICTORIA |  | Tier 4 |  |  |  | 5601 | Y | N
15TPIT0018 | Kerrville Stadium to Raymond F. Barker | Upgrade the 10.1-mile Kerrville Stadium (7136) – Kerrville Travis (7162) – Kerrville Legion (7160) - Raymond F. Barker (7159) 69 kV transmission lines to 795 ACSR, 138 kV (220 MVA / 920 Amperes) and OPGW. |  | Kerrville Stadium | Raymond F Barker | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2015-01-06 |  | 138 | 0 | 10.1 | 0 | 0 | KERR | KERR | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
07TPIT0252 | Greta: Install 1-7.2 MVAR 69 kV Cap Bank | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138/69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. | Change Status | Greta |  | Conceptual | 100 - 0100 | AEP/TCC | Paul Hassink 918-599-2653 | 2045 | 2015-03-31 |  | 69 | 0 | 0 | 0 | 7.2 | REFUGIO |  | Tier 4 |  |  |  |  | Y | N
08TPIT0131 | Melon Creek: Install 138/69 KV Auto | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138/69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. | Change Status | Melon Creek |  | Conceptual | 100 - 0100 | AEP/TCC | Paul Hassink 918-599-2653 | 2021 | 2015-03-31 |  | 138 | 0 | 0 | 50 | 0 | REFUGIO |  | Tier 4 |  |  |  |  | Y | N
07TPIT0236 | N. Terrell Tap - Rose Hill 138 kV line | Rebuild existing line | Studies indicate timing of project should be changed | N. Terrell Tap | Rose Hill | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3059-E | 2015-05-01 |  | 138 | 0 | 8.68 | 0 | 0 | KAUFMAN | KAUFMAN | Tier 4 |  |  |  | 2715, 2717, 2714, 2723, 2719 | Y | N
08TPIT0172 | Gunsight 138 kV Switching Station | Construct new switching station to connect a new wind farm | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R829-WA | 2015-05-01 |  | 138 | 0 | 0 | 0.0 | 0 | HOWARD |  | Tier 4 |  |  |  | 1360 | Y | N
09TPIT0117 | Stryker Creek - Dialville 138 kV line | Upgrade existing 138 kV line | Construction schedule change | Stryker Creek | Dialville | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R664-E | 2015-05-01 |  | 138 | 0 | 15.2 | 0 | 0 | CHEROKEE | CHEROKEE | Tier 4 |  |  |  | 3110, 3160 | Y | N
10TPIT0017 | Allen Switch - Plano Custer - Collin Junction 138 kV line | Upgrade existing double-circuit 138 kV line | Studies indicate timing of project should be changed | Allen Switch | Collin Junction | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3047-E | 2015-05-01 |  | 138 | 0 | 9 | 0 | 0 | COLLIN | COLLIN | Tier 4 |  |  |  | 2509, 2525, 2510,2526,2524 | Y | N
11TPIT0015 | Sherry - Park Row - Grand Prairie 138 kV line | Upgrade existing 138 kV line |  | Sherry | Grand Prairie | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5121-E | 2015-05-01 |  | 138 | 0 | 11.4 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 1919, 1920, 2257, 2258 | Y | N
11TPIT0032 | NW Carrollton - Collin second 138 kV circuit | Rebuild existing 138 kV line for double-circuit operation. | Construction schedule change | NW Carrollton | Collin | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M368-E | 2015-05-01 |  | 138 | 16.93 | 16.93 | 0 | 0 | DALLAS | COLLIN | Tier 4 |  |  |  | 2363, 2370 | Y | N | 2009-R13
11TPIT0050 | Roanoke Switch - Elizabeth Creek 138 kV line | Construct new line. |  | Roanoke Switch | Elizabeth Creek | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M509-E | 2015-05-01 |  | 138 | 3.75 | 0 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 1850, 1852, 1866, 1867 | Y | N
11TPIT0179 | Hicks Switch - Elizabeth Creek 138 kV line | Construct new 138 kV line |  | Hicks Switch | Elizabeth Creek | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M523-E | 2015-05-01 |  | 138 | 10 | 0 | 0 | 0 | TARRANT | TARRANT | Tier 2 |  |  |  | 1866, 1867, | Y | N
13TPIT0061 | Terrell Switch - North Terrell Tap 138 kV line | Upgrade existing line |  | Terrell Switch | North Terrell Tap | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M363-E | 2015-05-01 |  | 138 | 0 | 7.9 | 0 | 0 | KAUFMAN | KAUFMAN | Tier 4 |  |  |  | 2718, 2715, 2721 | Y | N
14TPIT0016 | West Mesquite - Prairie Creek 138 kV line | Upgrade existing line | Construction schedule change | West Mesquite | Prairie Creek | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4069-E | 2015-05-01 |  | 138 | 0 | 2.8 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2754, 2441 | Y | N | 2009-R19
14TPIT0055 | Seagoville - Wilmer 138 kV line | Upgrade existing line | Construction schedule change | Seagoville | Wilmer | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4081-E | 2015-05-01 |  | 138 | 0 | 10.9 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 3076, 3083 | Y | N
14TPIT0057 | Cedar Hill - Mayfield Tap North 138 kV line | Upgrade existing line | Construction schedule change | Cedar Hill Switch | Mayfield Tap North | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5041-E | 2015-05-01 |  | 138 | 0 | 4.3 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2422, 2421, 1912 | Y | N
15TPIT0038 | Venus Switch terminal equipment | Upgrade terminal equipment |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R912-E | 2015-05-01 |  | 138 | 0 | 0 | 0 | 0 | ELLIS |  | Tier 4 |  |  |  | 1909 | Y | N
15TPIT0039 | Plano Tennyson Road - Preston Meadows | Upgrade 138 kV line |  | Plano Tennyson Road | Preston Meadows | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4103-E | 2015-05-01 |  | 138 | 0 | 2.6 | 0 | 0 | COLLIN | COLLIN | Tier 4 |  |  |  | 2523, 10010 | Y | N
12TPIT0080 | Forney Sw. Sta. Second 600 MVA, 345/138 kV Autotransformer | Add second 345/138 autotransformer | Construction schedule change |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4037 | 2015-05-01 |  | 345 | 0 | 0 | 600 | 0 | KAUFMAN |  | Tier 4 | 2008-06-01 | 2008-07-01 |  | 2437, 2438 | Y | N | 2007-R2
13TPIT0113 | Renner | Replace existing 345/138 kV autotransformer with larger autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3099-E | 2015-05-01 |  | 345 | 0 | 0 | 600 | 0 | COLLIN |  | Tier 4 |  |  |  | 2355, 2354, 2355 | Y | N
16TPIT0018 | Hicks Switch Autotransformer | Install 345/138 kV autotransformer |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5145-E | 2015-05-01 |  | 345 | 0 | 0 | 600 | 0 | TARRANT |  | Tier 4 |  |  |  | 2081 | Y | N
15TPIT0040 | Temple Switch 345/138 kV autotransformer | Replace existing autotransformer |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R758-E | 2015-05-01 |  | 345 | 0 | 0 | 600 | 0 | BELL |  | Tier 4 |  |  |  | 3414, 3415 | Y | N
15TPIT0041 | Knob Creek 345 kV Switching Station Phase II | Expand 345 kV switching station |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R749B-E | 2015-05-01 |  | 345 | 0 | 0 | 0 | 0 | BELL |  | Tier 4 |  |  |  | 13413 | Y | N
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Convert to 138kV and upgrade Ckt. 47 Velasco to Freeport |  | Velasco | Freeport | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 4.5 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 43370, 42640, 43360, 46640 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades
15TPIT0034a | Freeport Area Upgrades and Conversion to 138kV | Convert to 138kV and upgrade Ckt. 47 Freeport to Quintana |  | Freeport | Quintana | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 0 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 42640, 43135, 46640, 46135 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost included in main project.
15TPIT0034b | Freeport Area Upgrades and Conversion to 138kV | Convert to 138kV Ckt. 47 Freeport to Bryan |  | Freeport | Bryan | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 2.4 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 42640, 42200, 46640, 45200 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost included in main project.
15TPIT0034C | Freeport Area Upgrades and Conversion to 138kV | Convert to 138kV and upgrade Ckt. 47 Surfside to Quintana |  | Surfside | Quintana | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 2.1 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 43135, 43310, 46135, 46310 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost included in main project.
15TPIT0034d | Freeport Area Upgrades and Conversion to 138kV | Convert to 138kV and upgrade Ckt. 10 Velasco to Surfside |  | Velasco | Surfside | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 2.5 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 43310, 43370, 46310, 43360 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost included in main project.
15TPIT0035 | Velasco to West Columbia Upgrades and Conversion to 138kV | Convert Retrieve substation to 138kV and energize with existing Ckt. 02 Lake Jackson to West Columbia. Upgrade Ckt. 02 Lake Jackson to Retrieve and parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. |  | Lake Jackson | Retrieve | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 5.34 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 42880, 43145 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades
15TPIT0035a | Velasco to West Columbia Upgrades and Conversion to 138kV | Upgrade Ckt. 02 Retrieve to West Columbia. Parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. |  | Retrieve | West Columbia | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 11.9 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 43145, 43380 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost included in main project.
15TPIT0035b | Velasco to West Columbia Upgrades and Conversion to 138kV | Parallel bundle a portion of Ckt. 02 Hofman to Lake Jackson with converted 69kV Ckt.47 Velasco to West Columbia. |  | Hofman | Lake Jackson | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 3.9 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 42810, 42880 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost included in main project.
15TPIT0035c | Velasco to West Columbia Upgrades and Conversion to 138kV | Parallel bundle a portion of Ckt. 02 BASF to Hofman with converted 69kV Ckt.47 Velasco to West Columbia. |  | BASF | Hofman | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 0.84 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 42150, 42810 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost included in main project.
15TPIT0035d | Velasco to West Columbia Upgrades and Conversion to 138kV | Parallel bundle a portion of Ckt. 02 Brazosport to Velasco with converted 69kV Ckt.47 Velasco to West Columbia. |  | Brazosport | Velasco | Planned |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2015-05-31 |  | 138 | 0 | 1.32 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 3 | 2012-06-14 | 2012-07-24 | N/A | 42210, 43360 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost included in main project.
16TPIT0020 | Rio Bravo 138 kV Station: Add 138 kV Terminal | Construct 345 kV circuit from Lobo to Rio Bravo energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Rio Bravo 138kV stations. | Update In-Service Date | Rio Bravo |  | Planned | 206 - 0288 | AEP/TCC | Bill Eakin 918-599-2653 | 900 | 2015-05-31 |  | 138 | 0 | 0 | 0 | 0 | WEBB | 0 | Tier 1 | 2012-03-12 | 2012-04-02 | 2012-04-27 |  | Y | N
12TPIT0062 | UTMB - New Substation | Build a new 138-12.47 kV substation to serve proposed UTMB Medical Center at Victory Lakes in League City. |  |  |  | Planned |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | STE04512 | 2015-05-31 |  | 138 | 0 | 0 | 0 | 0 | GALVESTON |  | Tier 4 |  |  |  | 38930 | Y | N |  | Project pushed out based on revised load forecast from UTMB.
15TPIT0030 | Mainland - New Substation | Build a new 138-12.47 kV substation to accommodate load growth along I45 between Texas City and Dickinson. Cut TNMP's Freeway Park - Alvin 138 kV line into the new substation. |  | Mainland |  | Planned |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com |  | 2015-05-31 |  | 138 | 0 | 0 | 0 | 0 | Galveston |  | Tier 4 |  |  |  | 38830 | Y | N
16TPIT0019 | Lobo 138 kV station: install 2 additional CB | Construct 345 kV circuit from Lobo to Rio Bravo energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Rio Bravo 138kV stations. | Update In-Service Date | Lobo |  | Planned | 206 - 0288 | AEP/ETT | Bill Eakin 918-599-2653 | 634 | 2015-05-31 |  | 345 | 0 | 0 | 0 | 0 | WEBB | 0 | Tier 1 | 2012-03-12 | 2012-04-02 | 2012-04-27 |  | Y | N
11TPIT0001 | Lobo to Rio Bravo, build 345 kV circuit energized at 138kV | Construct 345 kV circuit from Lobo to Rio Bravo energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Rio Bravo 138kV stations. | Update In-Service Date | Lobo | Rio Bravo | Planned | 206 - 0288 | AEP/ETT | Bill Eakin 918-599-2653 | 880 | 2015-05-31 |  | 345 | 30 | 0 | 0 | 0 | WEBB | WEBB | Tier 1 | 2012-03-12 | 2012-04-02 | 2012-04-27 |  | Y | N
15TPIT0002 | Hickory Substation to Locust Substation 69kV Transmission Line Reconstruction | Reconstruct 2.5 miles of existing 69V transmission line | On schedule | Hickory Substation, 910 | Locust Substation, 914 | Planned | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 602949 | 2015-06-01 |  | 69 | 0 | 2.5 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 910, 914 | N | N
15TPIT0011 | Shannon to Montague | Rebuild Shannon to Montague 69 kV line with 959 ACSS. |  | Shannon | Montague | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10045 | 2015-06-01 |  | 69 | 0 | 23.36 | 0 | 0 | CLAY | MONTAGUE | Tier 4 |  |  |  | 772, 769, 768, 633 | Y | N
09TPIT0037 | Blossom - New 138 kV Substation | Loop new 138 kV substation into the existing 138kV Harmony Hills to Skyline line | Delayed due to budget constraint | Blossom | Harmony Hills/Skyline | Planned | T-0178 | CPS | PM: Ulrich Skerhut | S-0602b | 2015-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5022 | N | N |  | There are no transformers associated with this project
14TPIT0003 | Ranchtown - New 138 kV Substation | Loop new 138kV substation into the existing 138kV Helotes to Menger Creek line |  | Ranchtown | Helotes/Menger Creek | Conceptual | T-0175 | CPS | Blake Williams | S-0567 | 2015-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5200 5358 7663 | Y | N |  | There are no transformers associated with this project. There is no transmission line additions associated with this project
15TPIT0007 | Green Mountain to Stonegate - 138kV 2nd Circuit | Build second 138kV transmission line from Green Mountain to Stonegate on existing transmission structures |  | Green Mountain | Stonegate | Conceptual | S-0608 | CPS | Blake Williams | T-0179 | 2015-06-01 |  | 138 | 11.5 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5180 5415 | Y | N |  | There are no transformers associated with this project
10TPIT0001 | Trumbo - New 138 kV Substation | Loop new 138 kV substation into the existing 138kV Leon Creek to Pleasanton Rd line | Accelarated by Disribution Planning | Trumbo | Leon Creek/Pleasanton Rd | Conceptual | T-0082 | CPS | Blake Williams | S-0181 | 2015-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5429 | Y | N |  | There are no transformers associated with this project
15TPIT0031 | Brooks to Chavaneaux - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from Brooks to Chavaneaux |  | Brooks | Chavaneaux | Conceptual | S-0733 | CPS | Blake Williams | T-0207 | 2015-06-01 |  | 138 | 0.1 | 4 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5045 5085 | Y | N |  | There are no transformers associated with this project
13TPIT0149 | Oaks to Loxley | Build new 138 kV 795 ACSR circuit from Oaks to a new AEP switching station Loxley in the Leon Creek to Pleasanton line |  | Oaks | Loxley | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2015-06-01 |  | 138 | 6 | 0 | 0 | 0 | ATASCOSA | ATASCOSA | Tier 2 | 2011-12-16 | 2012-04-25 | N/A | 5713, 80491 | Y | N
15TPIT0019 | Blockhouse (7527) | Add a 31.2 MVAR Capacitor Bank at the Blockhouse (7527) substation | [5 empty] | PEC | Randy Buchanan (830) 868-6058 |  | 2015-06-01 |  | 138 | 0 | 0 | 0 | 31.2 | WILLIAMSON |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | N | N
14TPIT0020 | Spencer Interchange to Pockrus 138kV Transmission Line New Construction | Construct 3.25 miles of new 138V transmission line | On schedule | Spencer Interchange PSS/E Bus 982 | Pockrus Substation PSS/E Bus 917 | Planned | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 600755 | 2015-06-01 |  | 138 | 3.25 | 0 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 982, 917 | N | N
10TPIT0083 | Mustang Capacitor Bank | Install 100mvar capacitors at future Mustang substation |  | Mustang |  | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 08052 | 2015-06-01 |  | 138 | 0 | 0 | 0 | 100 | DENTON |  | Tier 4 |  |  |  | 654 | Y | N
15TPIT0023 | Seaton Auto | Upgrade 138/69 kV auto to 100 MVA |  | Seaton | Seaton | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 11036 | 2015-06-01 |  | 138 | 0 | 0 | 100 | 0 | BELL |  | Tier 4 |  |  |  | 130, 131 | Y | N
15TPIT0037 | Rhome to Rhome | Loop Oncor's Rhome to Decatur Line into BEPC's Rome switching station |  | Rhome | Decatur | conceptual |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 12015 | 2015-06-01 |  | 138 | 4 | 0 | 0 | 0 | WISE | WISE | Tier 4 |  |  |  | 576, 1570, 1594 | Y | N
13TPIT0121 | Tilden to Reveille 138 kV line | Construct a new 138 kV double circuit capable line from Tilden to Reveille. For new Eagleford shale oil and gas needs. |  | Tilden | Reveille | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2015-06-30 |  | 138 | 47 | 0 | 0 | 0 | MCMULLEN | LA SALLE | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5701, 8612 | Y | N
10TPIT0063 | Geronimo(7604)-CMC Tap-McQueeney T-Line | Rebuild 5.5 miles of existing 69kV t-line to 138 kV, 1192 ACSR between Geronimo and McQueeny substations on existing right-of-way |  | Geronimo | McQueeney | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2015-08-31 |  | 138 | 0 | 5.5 | 0 | 0 | GUADALUPE | GUADALUPE | Tier 4 |  |  |  | See Project Title | N | N
16TPIT0003 | Longneck to Princeton South - new 138 kV line | Build 3.5 miles of 138kV transmission line from Longneck Substation to Princeton South Substation. |  | Longneck | Princeton South | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE07314 | 2015-08-31 |  | 138 | 3.5 | 0 | 0 | 0 | COLLIN | COLLIN | Tier 4 |  |  |  | 37295, 37250 | Y | N
14TPIT0050 | Lon Hill to North Edinburg: Reconductor 345kV line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Reconfigure Series Capacitors at North Edinburg and Rio Hondo |  | Lon Hill | North Edinburg | Planned | 071 - 0281 | AEP/TCC | Paul Hassink 918-599-2653 | 3183 | 2015-09-30 |  | 345 | 0 | 122.94 | 0 | 0 | NUECES | HIDALGO | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8455, 8383 | Y | N
14TPIT0051 | North Edinburg: Reconfigure 345 kV Series Capacitors and Terminate 345 kV Lobo Line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Reconfigure Series Capacitors at North Edinburg and Rio Hondo |  | North Edinburg |  | Planned | 071 - 0281 | AEP/TCC | Paul Hassink 918-599-2653 | 3184 | 2015-09-30 |  | 345 | 0 | 0 | 0 | 0 | HIDALGO |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8455 | Y | N
06TPIT0043 | Sherry - Liggett 138 kV line & Liggett - International Airport 138 kV line | Upgrade 138 kV line | Construction schedule change | Sherry | Liggett | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5042-WA | 2015-11-01 |  | 138 | 0 | 13 | 0 | 0 | TARRANT | DALLAS | Tier 4 |  |  |  | 1920, 2140, 1922, 2124, 2128, 2133, 2137 | Y | N |  | Sherry - GM section was completed in 2009.
08TPIT0104 | Elgin Switching Station - Elgin 69 kV line conversion to 138 kV | Rebuild existing 69 kV line and convert to 138 kV operation | Studies indicate timing of project should be changed | Elgin Switching Station | Elgin | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R471-E | 2015-11-01 |  | 138 | 0 | 5.9 | 0 | 0 | WILLIAMSON | BASTROP | Tier 4 |  |  |  | 3655, 3650 | Y | N
13TPIT0063 | Salado 138 kV Switch | Construct 138 kV switching station | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R445B-E | 2015-11-01 |  | 138 | 0 | 0 | 0 | 0 | BELL |  | Tier 4 |  |  |  | 13640 | Y | N
15TPIT0025 | Monticello SES - Monticello Tap 138 kV line | Upgrade existing line | Construction schedule change | Monticello SES | Monticello Tap | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R906-E | 2015-11-01 |  | 138 | 0 | 20.1 | 0 | 0 | TITUS | FRANKLIN | Tier 4 |  |  |  | 1795, 1994 | Y | N
15TPIT0028 | Spencer Switch to Locust Substation 69kV Transmission Line Reconductor | Reconductor approximately 1.91 miles of existing 69V transmission line to increase capacity | New Project | Spencer Switch PSS/E Bus 908 | Locust Substation PSS/E Bus 914 | Planned | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 602948 | 2015-12-01 |  | 69 | 0 | 1.91 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 908, 914 | Y | N
15TPIT0020 | Braunig to Highland Hills/Brooks - 138 kV Substation Equipment Upgrade | Replace Line and Bus Switches at Brooks and ensure a 1385 A rating and remove existing MLSE on the Braunig to Brooks 138 kV transmission line |  | Braunig_W | Highland Hills/Brooks | Conceptual | T-0194 | CPS | Blake Williams | S-0669 | 2015-12-01 |  | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 3 |  |  |  | 5025 5045 5205 | Y | N |  | There are no transformers associated with this project
15TPIT0032 | Fort Sam to Tenth Street - 138 kV Transmission Line Rebuild | Rebuild approximately five circuit miles of 138 kV transmission from Ft. Sam to Tenth Street |  | Fort Sam | Tenth St | Conceptual |  | CPS | Blake Williams | T-0188 | 2015-12-01 |  | 138 | 0 | 5 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5160 5420 | Y | N |  | There are no transformers associated with this project
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and/or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle/Weiderstein | Conceptual |  | CPS | Blake Williams | S-0645b | 2015-12-01 |  | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5360 5435 7461 | Y | N |  | There are no transformers associated with this project
13TPIT0047 | Parkway to EC Mornhinweg | Construct a new 138 kV 795 ACSR transmission line between the new EC Mornhinweg substation (7463) and the Parkway substation (7611). |  | Parkway | EC Mornhinweg | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2015-12-01 |  | 138 | 8 | 0 | 0 | 0 | COMAL | GUADALUPE | Tier 2 | 2009-02-06 | 2009-06-01 | N/A | SEE PROJECT DESCRIPTION | Y | N
15TPIT0036 | Bethel Area Improvements | Build Bethel Switching Station, Rebuild Sardis to Reqgor Springs with 959 ACSS and 138 kV construction. Relocate Auto from Sardis to Bethel Switching Station. Connect Bethel Switching Station to Oncor's 138 kV system in the area (Ennis to Waxahachie 138 kV line. |  | Multiple | Multiple | conceptual |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 12016 | 2015-12-01 |  | 138 | 14 | 4 | 40 | 0 | ELLIS | ELLIS | Tier 4 |  |  |  | 202, 203, 204, 205, 210, 2241, 2321 | Y | N | load serving project: improvments are requires to serve furture Enterprise pipleline pumping stations
12TPIT0079 | Roanoke Switch - Southlake - Grapevine Junction - Coppell 138 kV line (See comments in Other Column.) | Rebuild 138 kV line | Construction schedule change | Roanoke Switch | Coppell | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5118 | 2015-12-01 |  | 138 | 0 | 19.63 | 0 | 0 | Denton | Tarrant | Tier 4 |  |  |  | 1852, 2018, 2020 | Y | N | 2007-R4 | Interim rating increase for Coppell - Grapevine Junction section was implemented in May 2012, and an interim rating increase for the Roanoke Switch - Roanoke West line section was implemented in July 2012. Grapevine Junction - Coppell section will be completed by 5/2014, Roanoke Switch - Southlake section will be completed by 12/2014 and Southlake - Grapevine Junction will be completed by 12/2015.
13TPIT0064 | Rocky Mound Switching Station series capacitors | Install series capacitors for Willow Creek - Clear Crossing - Dermott Switch (Central B) 345 kV line (Oncor Electric Delivery part) | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C079-E | 2015-12-01 |  | 345 | 0 | 0 | 0.0 | 0 | HASKELL |  | CREZ |  |  |  |  | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
15TPIT0029 | CMC Tap to CMC (SMI) 138 kV Transmission Line | Build 2 miles of new double ckt 138 kV t-line loop, 1192 ACSR between CMC Tap and CMC (SMI) substation |  | CMC Tap | CMC (SMI) | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2015-12-18 |  | 138 | 2 | 0 | 0 | 0 | GUADALUPE | GUADALUPE | Tier 4 |  |  |  | See Project Title | N | N
08TPIT0132 | Melon Creek to Tatton: Build 69 KV Line & Tatton Substation Upgrades | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138/69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. | Change Status | Melon Creek | Tatton | Conceptual | 100 - 0100 | AEP/TCC | Paul Hassink 918-599-2653 | 2028 | 2016-03-31 |  | 69 | 7.7 | 0 | 0 | 0 | REFUGIO | ARANSAS | Tier 2 |  |  |  |  | Y | N
14TPIT0063 | Munday to BEC Munday: Rebuild 69 kV line | Rebuild Munday to BEC Munday 69 kV line with 795 ACSR | Transmission Status & Contact Update | Munday | BEC Munday | Planned | 568 - 0742 | AEP/TNC | Paul Hassink 918-599-2653 | 2572 | 2016-03-31 |  | 69 | 0 | 3.57 | 0 | 0 | KNOX | KNOX | Tier 4 |  |  |  |  | Y | N
15TPIT0024 | Lon Hill to Nelson Sharpe: Reconductor 345kV line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Reconfigure Series Capacitors at North Edinburg and Rio Hondo |  | Lon Hill | Nelson Sharpe | Planned | 071 - 0281 | AEP/TCC | Paul Hassink 918-599-2653 | 3180 | 2016-04-30 |  | 345 | 0 | 20.81 | 0 | 0 | NUECES | KLEBERG | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8455, 85000 | Y | N
14TPIT0047 | Denton 138kV System Upgrades | Proposed reliability projects necessary for the Denton area. Reconductoring 138kV loop line segments, adding second circuits, substation expansions, etc. |  | West Denton, North Denton, Jim Cristal, Arco, Pockrus, Teasley, Industrial | West Denton, North Denton, Jim Cristal, Arco, Pockrus, Teasley, Industrial | Under Construction |  | TMPA | Eric Schroeder 936-873-1124 eschroeder@texasmpa.org | T12001 | 2016-05-01 |  | 138 | 19.1 | 26.3 | 0 | 0 | Denton | Denton | Tier 3 | 2012-02-09 | 2012-04-20 | N/A |  | Y | N
15TPIT0021 | PH Robinson-South Shore rebuild | Rebuild PH Robinson to South Shore 138 kV transmission line with 795 ACSS conductor. |  | PH Robinson | South Shore | Planned |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | STE08410 | 2016-05-30 |  | 138 | 0 | 5.6 | 0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 38890, 42015 | Y | N
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into existing 138kV Deely to Skyline line |  | Converse | Deely/Skyline | Conceptual | T-0177 | CPS | Blake Williams | S-0601 | 2016-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5098 5110 5370 | Y | N |  | There are no transformers associated with this project
16TPIT0011 | JT Deely to Streich - 138 kV Substation Equipment Upgrade | Upgrade terminals at JT Deely and Streich Rd. to ensure a 2420 A rating and remove existing MLSE on JT Deely to Streich 138 kV transmission line |  | JT Deely | Streich Rd | Conceptual |  | CPS | Blake Williams | S-0674 | 2016-06-01 |  | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5110 5417 | Y | N |  | There are no transformers associated with this project
16TPIT0012 | Encino to Skyline - 138 kV Substation Equipment Upgrade | Upgrade terminals at Encino and Skyline to ensure a 2420 A rating and remove existing MLSE on Encino to Skyline 138 kV transmission line |  | Encino | Skyline | Conceptual |  | CPS | Blake Williams | S-0671 | 2016-06-01 |  | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5140 5369 | Y | N |  | There are no transformers associated with this project
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 2000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | NEW | 2016-06-01 |  | 138 | 0 | 4.11 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case
07TPIT0060 | Howard Lane to Techridge Reconductor | The project re-conductors Circuit 1004 (Techridge to Howard Lane) using 795 ACSS Drake conductors to increase the capacity to 3000 Amp. |  | Howard Lane Substation | Techridge Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P067 PLAN_117_P194 | 2016-06-01 |  | 138 | 0 | 1.72 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9190, 9217 | Y | N
10TPIT0025 | Rinard Creek 138kV substation | Establish 138kV Rinard Ck substation with (2) 30MVA transformers and will cut into existing Ckt 987 (Lytton Springs to Slaughter Lane). |  | Rinard Creek substation | Rinard Creek Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P151 PLAN_117_P152 | 2016-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9262 | Y | N
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures |  | McNeil Substation | Mag Plant Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | P396 | 2016-06-01 |  | 138 | 0 | 3.24 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9077, 9238 | Y | N |  | Will add the ptoject to the base case.
09TPIT0012 | Hill Country to Skyline - 345 kV 2nd Circuit | Build second 345 kV line from Hillcountry to Skyline. The second circuit will be installed on existing transmission structures |  | Hill Country | Skyline | Conceptual | S-0470 | CPS | Blake Williams | T-0052 | 2016-06-01 |  | 345 | 11 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5211 5371 | N | N |  | There are no transformers associated with this project
16TPIT0013 | Skyline to Spruce - 345 kV Substation Equipment Upgrade | Replace the Line MDS at Skyline and Spruce (both circuits) and ensure all terminals have a 2420 A rating and remove existing MLSE on Skyline to Spruce 345 kV transmission lines (both circuits) |  | Skyline | Spruce | Conceptual |  | CPS | Blake Williams | S-0468 | 2016-06-01 |  | 345 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5371 5400 | Y | N |  | There are no transformers associated with this project
08TPIT0033 | Gilleland to Techridge 138kV Circuit | Establish a new 138kV circuit from Gilleland to Techridge and maintain a normally close tie between AEN and LCRA's switchyard at Gilleland. |  | Gilleland Substation | Techridge Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_4276 PLAN_117_P207 | 2016-06-01 |  | 345 | 8 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 1 |  |  | 2004-12-01 | 9053, 9054 | Y | N
15TPIT0000 | Bird Pond Substation | Install (3) Breaker ring to include (2) 138 lines and (1) 138/12.5 transformer |  | Bird Pond | Bird Pond | planned |  | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2016-06-11 |  | 138 | 0 | 0 | 0 | 0 | BRAZOS |  | Tier 4 |  |  |  |  | N | N
16TPIT0026 | Lon Hill to Smith: Rebuild 69kV line | Rebuild Lon Hill - Smith 69kV Line | Description changed. | Lon Hill | Smith | Conceptual | 583-0739 | AEP/TCC | Paul Hassink 918-599-2661 | 3462 | 2016-06-14 |  | 69 | 0 | 3.1 | 0 | 0 | HIDALGO | HIDALGO | Tier 4 |  |  |  | 8448, 8866 | Y | N |  | 0
16TPIT0023 | South McAllen - Stewart Road: Rebuild 138kV Line | Rebuild South McAllen - Stewart Road 138kV Line | Changed Status | South McAllen | Stewart Road | Planned | 601-0738 | AEP/TCC | Paul Hassink 918-599-2659 | 0 | 2016-06-14 |  | 138 | 0 | 9.8 | 0 | 0 | HIDALGO | HIDALGO | Tier 4 |  |  |  | 8371, 8758, 8951 | Y | N |  | 0
16TPIT0024 | Hamilton Road to Escondido: Rebuild 138kV Line | Rebuild the Hamilton Road to Escondido 138kV line |  | Hamilton Road | Uvalde | Conceptual | 602-0746 | AEP/TCC | Paul Hassink 918-599-2662 | 0 | 2016-06-14 |  | 138 | 0 | 53.7 | 0 | 0 | VAL VERDE | MAVERICK | Tier 3 |  |  |  | 8255, 8692, 8263, 8260 | Y | N |  | 0
16TPIT0029 | New 345kV Loma Alta Station | Construct a new 345 kV Loma Alta station with one 345/138kV 450 MVA auto with 345 kV line terminal | New | Loma Alta |  | Planned |  | SU | Bill Bojorquez 512-771-0965 BBojorquez@hunttransmission.com |  | 2016-06-16 |  | 345 | 0 | 0 | 450 | 0 | Cameron |  | Tier 1 | 2011-05-03 | 2011-12-19 | 2012-01-17 |  | N | N
16TPIT0030 | New 345kV line from Loma Alta to N Edinburgh | Construct a new 345 kV transmission line from N.Edinburg to Loma Alta (~106.5 mi) and station upgrades | New Changed Dollars to include the station costs associated with the project (Approved by RPG, see comments for breakout) | Loma Alta | N Edinburgh | Planned |  | SU/ETT | Bill Bojorquez (SU) 512-771-0965 Paul Hassink (AEP) 918-599-2656 |  | 2016-06-16 |  | 345 | 106.5 | 0 | 0 | 0 | Cameron | Hidalgo | Tier 1 | 2011-05-03 | 2011-12-19 | 2012-01-17 |  | N | N
16TPIT0027 | Beeville - Sinton: Rebuild 69kV Line | Rebuild Beeville - Sinton 69kV Line for future 138 kV operation | Change project Title and Description | Pettus | Sinton | Conceptual | 579-0737 | AEP/TCC | Paul Hassink 918-599-2662 | 3465 | 2016-06-30 |  | 69 | 0 | 29.5 | 0 | 0 | SAN PATRICIO | BEE | Tier 3 | 2012-08-31 | on-going | N/A | 8413, 8405, 8198 | Y | N |  | 0
11TPIT0084 | Hidden Lakes - New Substation | Build a new 138-12.47 kV substation to accommodate new subdivision growth along the FM 517 and FM 646 corridors in Dickinson, Texas |  | Leave blank | Leave blank | Planned |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | STE02411 | 2016-06-30 |  | 138 | 0 | 0 | 0 | 0 | GALVESTON |  | Tier 4 |  |  |  | 38900 | Y | N
16TPIT0006 | Climax to Longneck - Rebuild and conversion from 69 kV to 138 kV | Rebuild Climax to Longneck 69 kV transmission line and convert to 138 kV. |  | Climax | Longneck | Planned |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE07214 | 2016-06-30 |  | 138 | 7.5 | 4.2 | 0 | 0 | COLLIN | COLLIN | Tier 4 |  |  |  | 37250, 37260 | Y | N
16TPIT0000 | Del Sol : Add a 24 Ohm, 3600 A Series Capacitor | Construct 345 kV series compensated line from Lobo to Rio Bravo to Del Sol to North Edinburg | Schedule Update | Del Sol |  | Planned | 065 - 0273 | AEP/ETT | Paul Hassink 918-599-2653 | 629 | 2016-06-30 |  | 345 | 0 | 0 | 0 | +368.5 | HIDALGO |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80355 | Y | N
16TPIT0017 | Rio Bravo: Add a 24 Ohm, 3600 A Series Capacitor | Construct 345 kV series compensated line from Lobo to Rio Bravo to Del Sol to North Edinburg | Schedule Update | Rio Bravo |  | Planned | 065 - 0273 | AEP/ETT | Paul Hassink 918-599-2653 | 630 | 2016-06-30 |  | 345 | 0 | 0 | 0 | +368.5 | WEBB |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 80220 | Y | N
11TPIT0002 | Lobo to North Edinburg: Construct 345 kV line | Construct 345 kV series compensated line from Lobo to Rio Bravo to Del Sol to North Edinburg | Schedule Update | Lobo | North Edinburg | Planned | 065 - 0273 | AEP/ETT | Paul Hassink 918-599-2653 | 3421 | 2016-06-30 |  | 345 | 163 | 0 | 0 | 0 | WEBB | HIDALGO | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80219, 80220, 80355, 8383 | Y | N
16TPIT0014 | Fort Stockton to Sanderson rebuild | Rebuild the Fort Stockton to Sanderson 69 kV line. |  | Fort Stockton | Sanderson | Conceptual |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE075AA | 2016-08-31 |  | 69 | 0 | 0 | 0 | 0 | Pecos | TERRELL | Tier 3 |  |  |  |  | N | N
07TPIT0140 | Trinidad - Tri Corner - Watermill 345 kV line | Upgrade existing 345 kV line | Studies indicate timing of project should be changed | Trinidad | Watermill | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4045-E | 2016-11-01 |  | 345 | 0 | 52 | 0 | 0 | HENDERSON | DALLAS | Tier 3 |  |  |  | 2427, 3123 | Y | N
12TPIT0025 | Refugio - Tatton: Rebuild Irreparable 69 kV Line | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138/69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. | Change Status | Refugio | Tatton | Conceptual | 100 - 0100 | AEP/TCC | Paul Hassink 918-599-2653 | 2027 | 2016-12-01 |  | 69 | 0 | 13.9 | 0 | 0 | REFUGIO | ARANSAS | Tier 4 |  |  |  |  | Y | N
16TPIT0028 | Denton North Interchange to North Lakes Substation 69kV Transmission Line Recconstruction and Reconductor |  | New Project | Denton North Interchange PSS/E Bus 912 | Noth Lakes Substation PSS/E Bus 915 | Planned | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 602947 | 2016-12-01 |  | 70 | 0 | 2.25 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 912, 915 | Y | N
16TPIT0009 | Five Points to Westside - 138 kV Transmission Line Rebuild | Rebuild 3.8 miles of 138 kV transmission line from Five Points to Westside and ensure a minimum conductor rating of 331 MVA |  | Five Points | Westside | Conceptual |  | CPS | Blake Williams | T-0195 | 2016-12-01 |  | 138 | 0 | 3.8 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5150 5490 | Y | N |  | There are no transformers associated with this project
14TPIT0022 | Sand Dollar 345 kV: Construct GIS 4 Breaker Ring Bus | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Sand Dollar | 0 | Planned | 495 - 0698 | AEP/ETT | Larry Roberson 918-599-2653 | 3388 | 2017-01-31 |  | 345 | 0 | 0 | 0 | 0 | NUECES |  | Tier 3 |  |  |  |  | Y | N |  | 0
14TPIT0024 | Lon Hill to Sand Dollar 345 kV: Construct New 345 kV Transmission Line | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Lon Hill | Sand Dollar | Planned | 495 - 0698 | AEP/ETT | Larry Roberson 918-599-2653 | 3389 | 2017-01-31 |  | 345 | 11.5 | 0 | 0 | 0 | NUECES | NUECES | Tier 1 |  |  |  |  | Y | N |  | 0
14TPIT0026 | Sand Dollar to Las Brisas Energy Center #1 345 kV: Construct New 345 kV Transmission Line | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Sand Dollar | Las Brisas | Planned | 495 - 0698 | AEP/ETT | Larry Roberson 918-599-2653 | 3392 | 2017-01-31 |  | 345 | 2 | 0 | 0 | 0 | NUECES | NUECES | Tier 2 |  |  |  |  | Y | N |  | Backfeed 13 months prior to commercial operation date
16TPIT0010 | Bulverde - New 138kV Substation | Loop new 138kV substation into the existing Hill Country to Stonegate transmission line |  | Hill Country | Bulverde/Stonegate | Conceptual | T-0189 | CPS | Blake Williams | S-0665 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5210 5051 5415 | Y | N |  | There are no transformers associated with this project
11TPIT0008 | Rainey St 138kV substation | Establish a new 138kV Rainey St substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9261 | Y | N
17TPIT0003 | Breaker Replacement Program | Replace 36 aging and underrated circuit breakers and associated disconnect switches at both 345kV and 138kV |  | Gibbons Creek, Ben Davis, Spencer Steam, West Denton, North Denton, Dansby, Bryan East | Gibbons Creek, Ben Davis, Spencer Steam, West Denton, North Denton, Dansby, Bryan East | Conceptual |  | TMPA | Eric Schroeder 936-873-1124 eschroeder@texasmpa.org |  | 2017-09-02 |  | 345/138 | 0 | 0 | 0.0 | 0 | Grimes, Denton, Hunt, Dallas |  | Tier 4 |  |  |  |  | N | N
13TPIT0045 | Blumenthal | Construct a new 8.4-mile 138 kV transmission line from a tap point on the Kendall CTEC (7147) - Mountain Top (7148)138 kV transmission line to the new Blumenthal substation (7418). | Delayed from initial May 2013 in-service date | Blumenthal | Kendall CTEC/Mountain Top | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2017-11-16 |  | 138 | 8.4 | 0 | 0 | 0 | KENDALL |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
14TPIT0041 | Coliseum to Kirby - 138 kV Transmission Line Rebuild | Rebuild 4.2 miles of 138 kV transmission line from Coliseum to Holbrook to Kirby and ensure a minimum conductor rating of 331 MVA |  | Colesium | Kirby | Conceptual |  | CPS | Blake Williams | T-0164 | 2017-12-01 |  | 138 | 0 | 4.2 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5095 5218 5250 | Y | N |  | There are no transformers associated with this project
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Conceptual |  | CPS | Blake Williams | T-0196 | 2017-12-01 |  | 138 | 0 | 4 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5427 5310 | Y | N |  | There are no transformers associated with this project
17TPIT0002 | Hunt Lane to Pinn Road - 138 kV Transmission Line Rebuild | Rebuild approximately eight circuit miles of 138 kV transmission from Hunt Lane to Pinn Road |  | Hunt Lane | Pinn Rd | Conceptual |  | CPS | Blake Williams | T-0190 | 2017-12-01 |  | 138 | 0 | 8 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5234 5345 | Y | N |  | There are no transformers associated with this project
17TPIT0004 | Frisco to Krugerville Second Circuit | Add second circuit from Frisco to Krugerville |  | Frisco | Krugerville | conceptual |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 12042 | 2017-12-01 |  | 138 | 12 | 0 | 0 | 0 | COLLIN | DENTON | Tier 4 |  |  |  | 649, 662, 1993, 1994, 2370 | Y | N
17TPIT0005 | St. Jo Autos | Replace 40 MVA autos with 60 MVA autos |  | St. Jo | St. Jo | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 12005 | 2017-12-01 |  | 138 | 0 | 0 | 40 | 0 | COOKE |  | Tier 4 |  |  |  | 746, 750 | Y | N
14TPIT0023 | Nopalito 345 kV: Construct 5 Breaker Ring Bus | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Napalito |  | Planned | 495 - 0698 | AEP/ETT | Larry Roberson 918-599-2653 | 3390 | 2018-01-31 |  | 345 | 0 | 0 | 0 | 0 | SAN PATRICIO |  | Tier 3 |  |  |  |  | Y | N |  | 0
14TPIT0025 | Nopalito to Sand Dollar 345 kV: Construct New 345 kV Transmission Line | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Nopalito | Sand Dollar | Planned | 495 - 0698 | AEP/ETT | Larry Roberson 918-599-2653 | 3391 | 2018-01-31 |  | 345 | 14.5 | 0 | 0 | 0 | NUECES | SAN PATRICIO | Tier 2 |  |  |  |  | Y | N |  | 0
15TPIT0003 | Sand Dollar to Las Brisas Energy Center #2 345 kV: Construct New 345 kV Transmission Line | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Sand Dollar | Las Brisas | Planned | 495 - 0698 | AEP/ETT | Larry Roberson 918-599-2653 | 3393 | 2018-01-31 |  | 345 | 2 | 0 | 0 | 0 | NUECES | NUECES | Tier 2 |  |  |  |  | Y | N |  | Backfeed 13 months prior to commercial operation date
06TPIT0068 | Hamilton Road to Picacho, reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | Hamilton Road | Picacho | Conceptual | 301 - 0449 | AEP/TCC | Paul Hassink 918-599-2653 | 1544 | 2018-03-30 |  | 138 | 0 | 8.67 | 0 | 0 | VAL VERDE | VAL VERDE | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 |  | Y | N
06TPIT0084 | Hamilton Road to Del Rio reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | Hamilton Road | Del Rio | Conceptual | 301 - 0449 | AEP/TCC | Paul Hassink 918-599-2653 | 1545 | 2018-04-30 |  | 138 | 0 | 3 | 0 | 0 | VAL VERDE | VAL VERDE | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 |  | Y | N
10TPIT0027 | West Batesville, Install 138 kV ring bus | West Batesville: Construct bundled 2x795 ACSR 138 kV line, add 138 kV circuit breaker and convert to 4 breaker ring bus |  | West Batesville |  | Conceptual | 383 - 0560 | AEP/ETT | Paul Hassink 918-599-2653 | 2168 | 2018-05-01 |  | 138 | 0 | 0 | 0 | 0 | ZAVALA |  | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 |  | N | N
10TPIT0028 | Escondido to West Batesville, build 138 kV Line | West Batesville: Construct bundled 2x795 ACSR 138 kV line, add 138 kV circuit breaker and convert to 4 breaker ring bus |  | Escondido | West Batesville | Conceptual | 383 - 0560 | AEP/ETT | Paul Hassink 918-599-2653 | 2169 | 2018-05-01 |  | 138 | 46.2 | 0 | 0 | 0 | MAVERICK | ZAVALA | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 |  | N | Y
14TPIT0012 | Mountain Creek - Norwood 138 kV line | Upgrade existing line | Studies indicate timing of project should be changed | Mountain Creek | Norwood | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4074-E | 2018-05-01 |  | 138 | 0 | 7.2 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2412, 2804, 2805, 2407 | Y | N
06TPIT0083 | Del Rio to Buena Vista, reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | Del Rio | Buena Vista | Conceptual | 301 - 0449 | AEP/TCC | Paul Hassink 918-599-2653 | 1546 | 2018-05-30 |  | 138 | 0 | 3 | 0 | 0 | VAL VERDE | VAL VERDE | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 |  | Y | N
18TPIT0003 | Chorizo Crossing Station | Construct a 69 kV substation at the crossing of the AEP Carrizo – Crystal City 69 kV line and STEC Brundage – Carrizo Springs 69 kV line |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2018-06-01 |  | 69 | 0 | 0 | 0 | 0 | DIMMIT |  | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 8245 | Y | N
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Valley Rd line and the Cagnon to Howard line |  | Masterson Rd. | Cagnon/Valley/Howard | Planned | T-0910 | CPS | Blake Williams | S-0538 | 2018-06-01 |  | 138 | 20 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 2 |  |  |  | 5296 | Y | N |  | There are no transformers associated with this project
18TPIT0002 | Martinez - New 138kV Substation | Loop new 138kV substation into the existing 138kV Deely to Walzem line and the future 138kV Deely to Converse line |  | Deely | Walzem Converse | Conceptual |  | CPS | Blake Williams |  | 2018-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5110 5294 5485 5098 | Y | N |  | There are no transformers associated with this project
11TPIT0011 | Northeast 138kV Substation | Establish a 138kV substation with (2) 30MVA transformers and 4 distribution circuits with underground get-a-ways. The station will cut into existing Gilleland - Techridge line. | Original Project title is "East Substation" | Northeast Substation | Northeast Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P142 PLAN_117_P143 PLAN_117_P144 | 2018-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9195 | Y | N
15TPIT0022 | Dobbin to Sota | Build 23 miles of 138 kV transmission line with 959 ACSS |  | Dobbin | Highway 6 | planned | 13TPIT0107 15TPIT0022 16TPIT0016 | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 11047 | 2018-06-01 |  | 138 | 23 | 0 | 0 | 0 | MONTGOMERY | BRAZOS | Tier 1 | 2010-10-04 | 2010-12-20 | 2011-05-05 | 3, 5, 6 | Y | N
13TPIT0107 | Dobbin switching station | Construct 345/138 kV switching station in CNP's Roans Prairie to Kuykendahl line |  | Dobbin | Dobbin | planned | 13TPIT0107 15TPIT0022 16TPIT0016 | BRAZOS-CNP | Brion Ryan, 254-750-6353, Wayne E. Kemper 713 207 2192 | 11045 | 2018-06-01 |  | 345 | 0 | 0 | 700 | 0 | MONTGOMERY |  | Tier 1 | 2010-10-04 | 2010-12-20 | 2011-05-05 | 40630, 3 | Y | Y
16TPIT0016 | Dobbin to Fish Creek | Build 15.5 miles of 138 kV transmission line with 959 ACSS |  | Dobbin | Fish Creek | planned | 13TPIT0107 15TPIT0022 16TPIT0016 | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 11046 | 2018-06-02 |  | 138 | 15.5 | 0 | 0 | 0 | MONTGOMERY | MONTGOMERY | Tier 1 | 2010-10-04 | 2010-12-20 | 2011-05-05 | 3, 22, 23, 24 | Y | N
10TPIT0062 | Weil Road (Marion South) - New Substation | Build a 138-26.18 kV 40 MVA substation on the GVEC Marion(7178)-Cibolo(7608) 138 kV transmission line near the Marion Interchange |  | Weil Road | Marion/Cibolo | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2018-06-30 |  | 138 | 0 | 0 | 0 | 0 | GUADALUPE |  | Tier 4 |  |  |  | See Project Title | N | N
07TPIT0083 | Picacho to CFE, construct new 138 kV line | Convert Amistad to CFE Amistad 12.5 kV distribution to 138 kV line |  | Picacho | CFE | Conceptual | 301 - 0449 | AEP/ETT | Paul Hassink 918-599-2653 | 1548 | 2018-06-30 |  | 138 | 8.8 | 0 | 0 | 0 | VAL VERDE | VAL VERDE | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 |  | Y | Y
06TPIT0082 | Buena Vista to Picacho, reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | Buena Vista | Picacho | Conceptual | 301 - 0449 | AEP/TCC | Paul Hassink 918-599-2653 | 1547 | 2018-06-30 |  | 138 | 0 | 3 | 0 | 0 | VAL VERDE | VAL VERDE | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 |  | Y | N
18TPIT0001 | Wiederstein Substation | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer | [5 empty] | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2018-12-15 |  | 138 | 0 | 0 | 0 | 0 | GUADALUPE |  | Tier 4 |  |  |  | See Project Title | N | N
15TPIT0008 | Triple R - New Substation | Build a 138-26.18 kV, 40 MVA substation on the GVEC Wilson - Sutherland Springs (T549) 138 kV transmission line |  | Triple R | Wilson/Sutherland Springs | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2018-12-30 |  | 138 | 0 | 0 | 0 | 0 | WILSON |  | Tier 4 |  |  |  | See Project Title | N | N
13TPIT0125 | CR343 138 kV Substation | Build new load serving station in the 138 kV line between Cross and Pearsall. |  |  |  | Conceptual |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2019-02-01 |  | 138 | 0 | 0 | 0.0 | 0 | ATASCOSA |  | Tier 4 |  |  |  | 5897 | Y | N
12TPIT0141 | Dinero 138 kV Substation | Build new load serving station in the 138 kV line from Orange Grove to AEP's George West. |  |  |  | Conceptual |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2019-03-01 |  | 138 | 0.5 | 0 | 0.0 | 0 | LIVE OAK |  | Tier 4 |  |  |  | 5670 | Y | N
14TPIT0008 | Holt - Emma 69 Tap kV line | Upgrade existing line | Studies indicate timing of project should be changed | Holt | Emma | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8006-E | 2019-05-01 |  | 69 | 0 | 6.2 | 0 | 0 | ECTOR | ANDREWS | Tier 4 |  |  |  | 1262, 1142 | N | N | 2009-R5
14TPIT0000 | CSU Graham Rd Substation | Install (3) Breaker ring to include (2) 138 lines and tap to College Station Utilities |  | CSU Graham Rd | CSU Graham Rd | planned |  | BTU/CSU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2019-05-06 |  | 138 | 0 | 0 | 0 | 0 | BRAZOS | BRAZOS | Tier 4 |  |  |  |  | N | N
14TPIT0031 | Cagnon - Install a Fourth 345kV Autotransformer | Install one 600 MVA autotransformer. |  |  |  |  | T-0176 | CPS | Blake Williams | S-0588 | 2019-06-01 |  | 345 | 0 | 0 | 600 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5056 5055 | Y | N |  | There are no transmission line additions associated with this project
19TPIT0000 | Weser substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer | [5 empty] | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2019-06-15 |  | 69 | 0 | 0 | 0 | 0 | GOLIAD |  | Tier 4 |  |  |  | See Project Title | Y | N
13TPIT0131 | Oaks to Fashing Rebuild | Rebuild 4/0 ACSR 69 kV to 795 ACSR double circuit 138 kV structures with one side operated at 69 kV. |  | Oaks | Fashing | Conceptual |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2019-06-30 |  | 138 | 38 | 38 | 0 | 0 | ATASCOSA | ATASCOSA | Tier 3 |  |  |  | 5716, 5714, 5710, 5712, 5713 | N | N
11TPIT0037 | Santa Clara - New Substation | Build a new 138-26.18 kV 40 MVA substation on the GVEC McQueeney(7606)-Cibolo(7608) 138 kV transmission line |  | Santa Clara | McQueeney/Cibolo | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 | 0 | GUADALUPE |  | Tier 4 |  |  |  | See Project Title | N | N
13TPIT0133 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  |  |  | Conceptual |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2019-12-01 |  | 69 | 0 | 0 | 0.0 | 0 | Medina |  | Tier 4 |  |  |  | 5857 | Y | N
11TPIT0036 | Caddo - New Substation | Construct a new 69-13.09x26.18-KV, 10 MVA substation |  | Caddo | La Vernia/GVEC Nixon | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2019-12-31 |  | 138 | 0 | 0 | 0 | 0 | WILSON |  | Tier 4 |  |  |  | See Project Title | N | N
09TPIT0024 | Electra - KMA Tap 69 kV line | Upgrade existing 69 kV line |  | Electra | KMA Tap | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R185-E | 2020-05-01 |  | 69 | 0 | 9.9 | 0 | 0 | WICHITA | WICHITA | Tier 4 |  |  |  | 1538, 1536 | N | N
09TPIT0116 | Gatesville Tap - Gatesville TDC 69 kV line | Upgrade existing 69 kV line | Studies indicate timing of project should be changed | Gatesville Tap | Gatesville TDC | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R497-WA | 2020-05-01 |  | 69 | 0 | 4.4 | 0 | 0 | MCLENNAN | CORYELL | Tier 4 |  |  |  | 3587, 3583 | N | N
11TPIT0014 | Muenster - St. Jo (BEC) 69 kV line | Upgrade existing 69 kV line |  | Muenster | St. Jo | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R186B-E | 2020-05-01 |  | 69 | 0 | 7.8 | 0 | 0 | COOKE | COOKE | Tier 4 |  |  |  | 1712, 1716 | N | N
14TPIT0009 | Odessa North - North Cowden 69 kV line | Upgrade existing line |  | Odessa North | North Cowden | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8008-E | 2020-05-01 |  | 69 | 0 | 12.4 | 0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 1259, 1123 | N | N | 2009-R4
06TPIT0047 | Elkton - Tyler West 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Elkton | Tyler | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R323-E | 2020-05-01 |  | 138 | 0 | 4.98 | 0 | 0 | SMITH | SMITH | Tier 4 |  |  |  | 3106, 3139 | N | N
06TPIT0143 | Temple Switch - Temple SE 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Temple Switch | Temple SE | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R448-E | 2020-05-01 |  | 138 | 0 | 4.4 | 0 | 0 | BELL | BELL | Tier 4 |  |  |  | 3415, 3612, 3602, 3611 | N | N
07TPIT0014 | Plano West - Richardson Tap 138 kV line | Upgrade existing 138 kV line |  | Plano West | Richardson Tap | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M364-E | 2020-05-01 |  | 138 | 0 | 1.9 | 0 | 0 | COLLIN | DALLAS | Tier 4 |  |  |  | 2673, 2685 | N | N
09TPIT0047 | N. Waco - NE. Waco 138 kV line | Upgrade existing 138 kV line |  | N. Waco | NE. Waco | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R477-E | 2020-05-01 |  | 138 | 0 | 1.9 | 0 | 0 | MCLENNAN | MCLENNAN | Tier 4 |  |  |  | 3551, 3552 | N | N
09TPIT0118 | Fisher Road - Wichita Falls 138 kV line | Upgrade existing 138 kV line. |  | Fisher Road | Wichita Falls | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R191-E | 2020-05-01 |  | 138 | 0 | 1.45 | 0 | 0 | WICHITA | WICHITA | Tier 4 |  |  |  | 1427, 1448 | N | N
09TPIT0122 | Shamburger - Tyler NW 138 kV line | Upgrade existing 138 kV line |  | Shamburger | Tyler NW | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R6001-E | 2020-05-01 |  | 138 | 0 | 6.3 | 0 | 0 | SMITH | SMITH | Tier 4 |  |  |  | 3104, 3141 | N | N | 2009-E6
10TPIT0019 | Everman - Cleburne Switch 138 kV line sections | Upgrade existing 138 kV line |  | Everman | Cleburne Switch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3034-E | 2020-05-01 |  | 138 | 0 | 8.5 | 0 | 0 | TARRANT | JOHNSON | Tier 4 |  |  |  | 2279, 2210, 2209, 2208, 1883 | N | N
10TPIT0053 | Kaufman South 138 kV capacitors | Install 138 kV capacitors |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3064-E | 2020-05-01 |  | 138 | 0 | 0 | 0 | 55.2 | KAUFMAN |  | Tier 4 |  |  |  | 2728 | N | N
10TPIT0054 | Royse 138/69 kV autotransformer | Install larger autotransformer |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3065-E | 2020-05-01 |  | 138 | 0 | 0 | 120 | 0 | ROCKWALL |  | Tier 4 |  |  |  | 2462, 2463 | N | N
10TPIT0091 | Elm Mott - Waco Northcrest 138 kV line upgrade | Upgrade existing 138 kV line |  | Elm Mott | Waco Northcrest | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R714-E | 2020-05-01 |  | 138 | 0 | 3.6 | 0 | 0 | MCLENNAN | MCLENNAN | Tier 4 |  |  |  | 3407, 3575 | N | N
11TPIT0033 | Saginaw - American MFG Tap 138 kV line | Upgrade existing 138 kV line |  | Saginaw | American MFG Tap | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5070-E | 2020-05-01 |  | 138 | 0 | 1.37 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 2146, 1957 | N | N
13TPIT0059 | Cedar Crest - Industrial 138 kV line | Upgrade existing line |  | Cedar Crest | Industrial | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4072-E | 2020-05-01 |  | 138 | 0 | 3.2 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2494, 2981, 2976 | N | N | 2009-R23
13TPIT0112 | North Andrews | Install 138 kV capacitors |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8015-E | 2020-05-01 |  | 138 | 0 | 0 | 0 | 36.8 | ANDREWS |  | Tier 4 |  |  |  | 1159 | N | N
14TPIT0011 | Midland East - Windwood 138 kV line | Upgrade existing line |  | Midland East | Windwood | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8009-E | 2020-05-01 |  | 138 | 0 | 1.7 | 0 | 0 | MIDLAND | MIDLAND | Tier 4 |  |  |  | 1023, 1116 | N | N
14TPIT0014 | NW Carrollton - Lakepointe (TNMP) 138 kV line (Oncor Electric Delivery's section) | Upgrade existing line | Studies indicate timing of project should be changed | NW Carrollton | Lakepointe (TNMP) | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5156-E | 2020-05-01 |  | 138 | 0 | 2.1 | 0 | 0 | DALLAS | DENTON | Tier 4 |  |  |  | 2362, 37010 | N | N
14TPIT0056 | Northaven - Welch 138 kV line | Upgrade existing line | Studies indicate timing of project should be changed | Northaven | Welch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4088-E | 2020-05-01 |  | 138 | 0 | 6 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2657, 2658, 2660, 2661 | N | N
07TPIT0073 | Venus - Webb 345 kV line | Upgrade existing 345 kV line |  | Venus | Webb | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5098-E | 2020-05-01 |  | 345 | 0 | 11.3 | 0 | 0 | ELLIS | DALLAS | Tier 4 |  |  |  | 1906, 1904 | N | N
00TPITno07 | Loma Alta - Rio Hondo 345-kV line | Install 345-kV line from Loma Alta to Rio Hondo |  | Loma Alta Substation | Rio Hondo Substation | Conceptual |  | BPUB | Ramon Sanz, Jr. (956) 983-6203 rsanz@brownsville-pub.com |  | 2020-05-01 |  | 345 | 35 | 0 | 0 | 0 | CAMERON | CAMERON | Tier 2 |  |  |  |  | N | N
20TPIT0000 | Parkway Substation | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer | [5 empty] | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2020-05-15 |  | 138 | 0 | 0 | 0 | 0 | GUADALUPE |  | Tier 4 |  |  |  | See Project Title | N | N
13TPIT0104 | Jack County Auto | Install 345/138 kV, 700 MVA auto at Jack County |  | Jack County | Jack County | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 11038 | 2020-06-01 |  | 345 | 0 | 0 | 700 | 0 | JACK |  | Tier 4 |  |  |  | 575, 579 | Y | N
12TPIT0006 | Olmos(7613) - New Substation | Build a 138-13.09 kV 20 MVA substation on the Olmos switching station site |  | Olmos | Olmos Switching Station | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2020-11-30 |  | 138 | 0 | 0 | 0 | 0 | GUADALUPE |  | Tier 4 |  |  |  | See Project Title | Y | N
14TPIT0033 | Muenster to Red River | Add 60 MVA 138/69 kV auto at Munester. Build 11 miles of 795 ACSR line to Red River. |  | Muenster | Red River | conceptual |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 09033 | 2020-12-01 |  | 69 | 11 | 0 | 60 | 0 | COOKE | COOKE | Tier 2 |  |  |  | 694, 694, 735 | Y | N
08TPIT0097 | Rhome to Roanoke Rebuild | Rebuild existing Rhome to Roanoke |  | Rhome | Roanoke | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 06062 | 2020-12-31 |  | 138 | 0 | 16.6 | 0.0 | 0 | WISE | DENTON | Tier 4 |  |  |  | 602-640 640-1866-1852 | Y | N |  | 602-640 completed 4/19/2012 640-1852-1866 completed 12/31/2012
10TPIT0009 | Trinity Switch - Hurst 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Trinity Switch | Hurst | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5040-E | 2021-05-01 |  | 138 | 0 | 4 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 2096, 2115 | N | N
10TPIT0034 | Leon Switch #2 138/69 kV autotransformer replacement | Replace existing 138/69 kV autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R517-E | 2021-05-01 |  | 138 | 0 | 0 | 100 | 0 | EASTLAND |  | Tier 4 |  |  |  | 1624, 1626 | N | N
11TPIT0027 | East Richardson Switch - Ben Davis Switch (TMPA) 138 kV line | Create a new 138 kV line by reconfiguring existing lines | Studies indicate timing of project should be changed | East Richardson Switch | Ben Davis Switch | Conceptual | M375A | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M375D-E | 2021-05-01 |  | 138 | 0 | 0 | 0 | 0 | COLLIN | DALLAS | Tier 4 |  |  |  | 968, 2690 | N | N
11TPIT0028 | Allen Switch - West Plano Switch 138 kV line | Create a new 138 kV line by reconfiguring existing lines and adding circuit to existing structures | Studies indicate timing of project should be changed | Allen Switch | West Plano Switch | Conceptual | M375A | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M375C-E | 2021-05-01 |  | 138 | 3.5 | 0 | 0 | 0 | COLLIN | COLLIN | Tier 4 |  |  |  | 2510, 2691, 2673 | N | N
12TPIT0019 | Pleasant Valley second 138/69 kV autotransformer | Install second 138/69 kV autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R555-E | 2021-05-01 |  | 138 | 0 | 0 | 100 | 0 | WICHITA |  | Tier 4 |  |  |  | 1450, 1451 | N | N
14TPIT0029 | Lake Creek - Robinson 138 kV line | Rebuild 138 kV line | Studies indicate timing of project should be changed | Lake Creek | Robinson | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R476 | 2021-05-01 |  | 138 | 0 | 8.3 | 0 | 0 | MCLENNAN | MCLENNAN | Tier 4 |  |  |  | 3410, 3567 | N | N | 2007-R8
00TPIT0004 | DeCordova - Benbrook 345 kV line upgrade | Upgrade existing 345 kV line | Studies indicate timing of project should be changed | DeCordova | Benbrook | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5034-E | 2021-05-01 |  | 345 | 0 | 27 | 0 | 0 | HOOD | TARRANT | Tier 4 |  |  |  | 1873, 1890 | N | N
07TPIT0001 | Liggett - Trinity Switch 345 kV line | Construct Liggett - Trinity 345 kV line | Studies indicate timing of project should be changed | Liggett | Trinity Switch | Conceptual | M5014-E | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5015-E | 2021-05-01 |  | 345 | 12.8 | 0 | 0 | 0 | DALLAS | TARRANT | Tier 2 |  |  |  | 2095, 2097 | N | N
07TPIT0002 | Trinity Switch 345/138 kV autotransformer | Create Trinity Switch and install a 600 MVA 345/138 kV autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual | M5015-E | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5014-E | 2021-05-01 |  | 345 | 0 | 0 | 600 | 0 | TARRANT |  | Tier 4 |  |  |  | 2096, 2097 | N | N
07TPIT0118 | Lavon 345/138 kV Switching Station | Construct 345/138 kV switching station | Studies indicate timing of project should be changed |  |  | Conceptual | M375B, M375C | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M375A-E | 2021-05-01 |  | 345 | 0 | 0 | 600 | 0 | COLLIN |  | Tier 4 |  |  |  | 2475, 2476 | N | N
08TPIT0071 | North Lake 345/138 kV autotransformer | Install a 345/138 kV autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3020-E | 2021-05-01 |  | 345 | 0 | 0 | 600 | 0 | DALLAS |  | Tier 4 |  |  |  | 2334, 2333 | N | N
11TPIT0034 | Sargent Road 345/138 kV autotransformer | Install second 345/138 kV autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M486-E | 2021-05-01 |  | 345 | 0 | 0 | 600 | 0 | DALLAS |  | Tier 4 |  |  |  | 2946, 2949 | N | N
11TPIT0097 | Norwood Switch autotransformer | Replace #1 345/138 kV autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4070-E | 2021-05-01 |  | 345 | 0 | 0 | 600 | 0 | DALLAS |  | Tier 4 |  |  |  | 2405, 2406 | N | N
13TPIT0062 | Cedar Hill Switch second 345/138 kV autotransformer | Install autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4071-E | 2021-05-01 |  | 345 | 0 | 0 | 504 | 0 | DALLAS |  | Tier 4 |  |  |  | 2420, 2422, 2421 | N | N
06TPIT0092 | Wichita Falls Switch - Wichita Falls Basin 69 kV line | Upgrade existing 69 kV line | Studies indicate timing of project should be changed | Wichita Falls Switch | Wichita Falls Basin | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R168A-E | 2022-05-01 |  | 69 | 0 | 1 | 0 | 0 | ARCHER | WICHITA | Tier 4 |  |  |  | 1449, 1508 | N | N
08TPIT0110 | Temple - Little River 69 kV line | Rebuild existing 69 kV line | Studies indicate timing of project should be changed | Temple | Little River | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R097-E | 2022-05-01 |  | 69 | 0 | 7.4 | 0 | 0 | BELL | BELL | Tier 4 |  |  |  | 3645, 3644 | N | N
09TPIT0068 | W. Weatherford - Weatherford 69 kV line | Rebuild existing 69 kV line | Studies indicate timing of project should be changed | W. Weatherford | Weatherford | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R515-E | 2022-05-01 |  | 69 | 0 | 7.5 | 0 | 0 | PARKER | PARKER | Tier 4 |  |  |  | 1586, 1585 | N | N
07TPIT0069 | Sterrett - Sardis 138 kV line | Upgrade existing 138 kV line |  | Sterrett | Sardis | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M361-E | 2022-05-01 |  | 138 | 0 | 1.95 | 0 | 0 | ELLIS | ELLIS | Tier 4 |  |  |  | 2317, 203 | N | N
11TPIT0048 | Austin Ranch 138 kV capacitors | Install capacitors | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3074-E | 2022-05-01 |  | 138 | 0 | 0 | 0 | 55.2 | DENTON |  | Tier 4 |  |  |  | 2378, 2377 | N | N
14TPIT0010 | Handley - Pantego 138 kV line | Upgrade existing line | Studies indicate timing of project should be changed | Handley | Pantego | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5155-E | 2022-05-01 |  | 138 | 0 | 3.8 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 1950, 1951, 2247 | N | N
07TPIT0234 | Collin Switch - NW. Carrollton 345 kV line | Upgrade existing 345 kV line |  | Collin Switch | NW. Carrollton | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3061-E | 2022-05-01 |  | 345 | 0 | 19.3 | 0 | 0 | COLLIN | DALLAS | Tier 4 | 2006-10-01 | 2007-02-01 | N/A | 2372, 2361 | N | N |  | The ERCOT Staff determined this project is not economically justified in their February 2007 study.
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer | [5 empty] | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0 | GUADALUPE |  | Tier 4 |  |  |  | See Project Title | N | N
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers/Kirby | Conceptual |  | CPS | Blake Williams | S-0385 | 2022-06-01 |  | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5416 | Y | N |  | There are no transformers associated with this project
12TPIT0078 | Southeast Nacogdoches - Lufkin Switch 345 kV line | Construct new 345 kV line, add second circuit to existing structures and add 345 kV circuit breakers at existing switching stations |  | Southeast Nacogdoches | Lufkin Switch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R862 | 2022-12-01 |  | 345 | 8 | 13 | 0 | 0 | NACOGDOCHES | ANGELINA | Tier 2 | 2008-07-01 |  | 2008-09-01 | 3117, 3119 | N | N | 2007-E4
06TPIT0036 | Ennis Switch - Ennis 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Ennis Switch | Ennis | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M280-E | 2023-05-01 |  | 138 | 0 | 6.32 | 0 | 0 | ELLIS | ELLIS | Tier 4 |  |  |  | 2324, 2326 | N | N
06TPIT0042 | Lake Wichita Switch - Wichita Falls Switch 69 kV line | Upgrade existing 69 kV line | Studies indicate timing of project should be changed | Lake Wichita Switch | Wichitia Falls Switch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R168-E | 2023-05-01 |  | 138 | 0 | 6.3 | 0 | 0 | ARCHER | WICHITA | Tier 4 |  |  |  | 1447, 1449 | N | N
07TPIT0012 | Trinity Switch - Richland 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Trinity Switch | Richland | Conceptual | M5014-E | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5069-E | 2023-05-01 |  | 138 | 0 | 0.5 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 2096, 2100 | N | N
07TPIT0115 | Elgin Switch - Taylor 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Elgiin Switch | Taylor | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R026-E | 2023-05-01 |  | 138 | 0 | 11.4 | 0 | 0 | BASTROP | BASTROP | Tier 4 |  |  |  | 3650, 3658 | N | N
07TPIT0119 | Lavon Switch - Allen Switch 138 kV line | Create a new 138 kV line by reconfiguring existing lines and adding circuit to existing structures | Studies indicate timing of project should be changed | Lavon Switch | Allen Switch | Conceptual | M375A | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M375B-E | 2023-05-01 |  | 138 | 8.9 | 0 | 0 | 0 | COLLIN | COLLIN | Tier 4 |  |  |  | 2475, 2477, 2509 | N | N
07TPIT0122 | Royse - Dalrock 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Royse | Dalrock | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3035-E | 2023-05-01 |  | 138 | 0 | 6.8 | 0 | 0 | ROCKWALL | ROCKWALL | Tier 4 |  |  |  | 2472, 2733, 2735 | N | N
07TPIT0138 | Oates (GPL) - Garland Bobtown Tap 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Oats (GPL) | Garland Bobtown Tap | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M322-E | 2023-05-01 |  | 138 | 0 | 1.5 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 831, 2739 | N | N
08TPIT0007 | Austin Ranch - Hebron 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Austin Ranch | Hebron | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3002-E | 2024-05-01 |  | 138 | 0 | 0.7 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  |  | 2376, 2377 | N | N
08TPIT0069 | Lake Creek - East Waco 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Lake Creek | East Waco | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R470-E | 2024-05-01 |  | 138 | 0 | 10.5 | 0 | 0 | MCLENNAN | MCLENNAN | Tier 4 |  |  |  | 3410, 3452, 3438 | N | N
08TPIT0111 | Lufkin Switching Station - Texas Foundries Tap 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Lufkin Switching Station | Texas Foundries Tap | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R389-E | 2024-05-01 |  | 138 | 0 | 0.73 | 0 | 0 | ANGELINA | ANGELINA | Tier 4 |  |  |  | 3326, 3327, 3328 | N | N
09TPIT0043 | Coppell - North Lake 138 kV line | Construct 138 kV line | Studies indicate timing of project should be changed | Coppell | North Lake | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M549-E | 2024-05-01 |  | 138 | 4.8 | 0 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2015, 2386 | N | N
09TPIT0046 | N. Midlothian - Midlothian TXI Tap 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | N. Midlothian | Midlothian TXI Tap | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3031-E | 2024-05-01 |  | 138 | 0 | 6.2 | 0 | 0 | ELLIS | ELLIS | Tier 4 |  |  |  | 2310, 2311, 2313 | N | N
09TPIT0050 | Rowlett - Garland Bobtown Tap 138 kV line | Upgrade existing 138 kV line | Studies indicate timing of project should be changed | Rowlett | Garland Bobtown Tap | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3032-E | 2024-05-01 |  | 138 | 0 | 4.1 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2736, 2739 | N | N
09TPIT0051 | Salado Switch - Cedar Valley Switch (BEC) 138 kV line and switching stations | Establish two new 138 kV switching stations and connect them with a new 138 kV line | Studies indicate timing of project should be changed | Saldo Switch | Cedar Valley Switch | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R469-E | 2024-05-01 |  | 138 | 7 | 0 | 0 | 0 | BELL | BELL | Tier 2 |  |  |  | 117, 3640 | N | N
09TPIT0066 | Boggy Creek 138 kV Switching Station and associated line | Construct 138 kV switching station and add second circuit to a 138 kV line | Studies indicate timing of project should be changed | Boggy Creek | Little River | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R488-E | 2024-05-01 |  | 138 | 3.5 | 0 | 0 | 0 | BELL | BELL | Tier 4 |  |  |  | 3424, 3415, 3425, 13645 | N | N
09TPIT0067 | Bonham Switching Station 138/69 kV autotransformer replacement | Replace existing 138/69 kV autotransformer | Studies indicate timing of project should be changed |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R516-E | 2024-05-01 |  | 138 | 0 | 0 | 100 | 0 | FANNIN |  | Tier 4 |  |  |  | 1760, 1761 | N | N

## CompletedTPIT09012012NoCost
SEPTEMBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) COMPLETED PROJECTS As Of 09/01/2012.
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional)
08TPIT0156 | H.O. Clarke - Brays Ckt.09 | Raise conductors and upgrade limiting equipment at H.O. Clarke and Brays to increase thermal ratings. |  |  |  |  | 07TPIT0263 | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2009-12-31 | 2010-01-05 | 138 | 0 | 2.62 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 47150, 47050 | Y |  |  | 1) No transformer capacity to be added and no transmission circuits to be built, rebuilt or reconductored.
07TPIT0098 | Replace five poles, Hickory - Locust 69kV Transmission Line | Replace five poles in an existing 69kV transmission line | On Schedule |  |  | Complete | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 600774 | 2010-03-31 | 2010-01-10 | 69 | 0 | 0.25 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 910, 914 | Y
10TPIT0097 | Salt Creek Reactor | Install 25 MVAR reactor at Salt Creek | [5 empty] | BRAZOS | Dwight Beckmann, 254-750-6373, dbeckman@brazoselectric.com |  | 2010-06-01 | 2010-01-19 | 138 | 0 | 0 | 0 | -25 | KENT | KENT | Tier 4 |  |  |  | 743 | N
06TPIT0037 | Carrollton East - Renner 138 kV line | Upgrade existing 138 kV line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M448-WA | 2009-12-01 | 2010-01-19 | 138 | 0 | 6.9 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2356, 2611, 2578, 2582 | Y |  |  | Carrollton East - Farmers Branch Gillis Rd section will be completed in 12/2008.
06TPIT0080 | Medina Lake-CPS (Part 1) | Construct a new 138-kV 795 ACSR transmission line (approximately 20 miles in length) from the BEC Medina Lake substation (7432) to the future CPS Energy Talley Road substation (5422), then continuing on to the CPS Energy Texas Research Park substation (5430). | LCRA projected completion date is March 2010. CPS Energy completed on September 23, 2009. | Tally | Medina Lake |  | 07TPIT0034 CPS S-0275 | CPS / LCRA TSC | Stuart Nelson (512) 369-4526 Stuart.Nelson@lcra.org PM:Hector Torres (210) 353-2404 HVTorres@cpsenergy.com | CPS T-0049 | 2010-01-08 | 2010-01-21 | 138 | 20.7 | 0 | 0 | 0 | BANDERA | BEXAR | Tier 2 | 2007-10-03 | 2007-11-03 |  | 5430 7432 | Y | N |  | CPS and LCRA have filed update letter with ERCOT. BEC is proposing a new load serving substation between Medina Lake and CPS.
09TPIT0175 | Reconfigure Ckt.03 Lynch - Cedar Bayou. | Reconfigure Ckt.03 Lynch - Cedar Bayou substation to create two new circuits Ckt.03 Lynch - EXXON and Ckt.03 Baytown - Cedar Bayou substation per customers request. | [5 empty] | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-01-31 | 2010-01-22 | 138 | 0.7 | 0 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 41010, 40011, 40015, 40170, 40570 | Y |  |  | No transformer capacity to be added.
08TPIT0135 | Yellowjacket, Install 150 MVA Phase Shifting Transformer | Yellowjacket, Install 150 MVA 138 kV Phase Shifting Transformer on the SAPS 138 kV line | IN-SERVICE |  |  |  | AEP GROUP 354 | AEP/TNC | Brett Madison 918-599-2653 | 2219 | 2010-01-28 | 2010-01-28 | 138 | 0 | 0 | 150 | 0 | MENARD |  | Tier 4 |  |  |  |  | Y
09TPIT0127 | Menard to San Angelo Power Station 138 kV Hairpin into Yellowjacket | Yellowjacket, Build new 138 kV Switch Station Station: Five postion ring with 2-90 MVA Auto 138/69 (LTC), 138 KV 28.8 MVAR Capacitor and 1- 10 MVA distribution bank | IN-SERVICE |  |  |  | AEP GROUP 354 | AEP/TNC | Brett Madison 918-599-2653 | 2154 | 2010-01-28 | 2010-01-28 | 138 | 2 | 0 | 0 | 0 | MENARD | TOM GREEN | Tier 4 |  |  |  |  | Y
09TPIT0211 | San Angelo Power Station to Menard 138 kV line improvements | Rebuild part of SAPS to Menard 138 kV line by replacing structures and Move SAPS auto and add DCRS at North Brady | IN-SERVICE |  |  |  | AEP GROUP 472 | AEP/TNC | Brett Madison 918-599-2653 | 2359 | 2010-01-28 | 2010-01-28 | 138 | 0 | 0 | 0 | 0 | TOM GREEN | MENARD | Tier 4 |  |  |  |  | Y
10TPIT0134 | Gonzales, Build new 69 kV station | Add 2nd 138/69 kV autotransformer at Alamito Creek, and install a NaS Battery at Gonzales | IN-SERVICE |  |  |  | AEP GROUP 358 | AEP/ETT | Brett Madison 918-599-2653 | 1182 | 2010-02-01 | 2010-02-01 | 69 | 0 | 0 | 0 | 0 | PRESIDIO |  | Tier 4 |  |  |  |  | Y
10TPIT0153 | Graham terminal equipment | Upgrade terminal equipment on 345 kV line to Bowman | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C070-E | 2010-05-01 | 2010-02-01 | 345 | 0 | 0 | 0 | 0 | YOUNG |  | Tier 4 |  |  |  | 1430 | Y
06TPIT0247 | Salt Dome 69kV Substation | Construct a new Salt Dome substation in the STEC N. Clemville to S. Clemville circut. | Tie is delayed to verify load. Load customer delays and changing load level. Project scope may be reduced before actual construction. Name Changed from "United Brine" to "Salt Dome" |  |  |  |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2009-12-09 | 2010-02-10 | 69 | 0.1 | 0 | 0 | 0 | JACKSON |  | Tier 4 | 2006-03-23 | 2006-04-17 | N/A | 5551 | Y | N
08TPIT0167 | Friend Ranch, Add 2nd 138 kV 28.8 Mvar Shunt Capacitor | Reconfigure Rio Pecos to add SVC and 2nd 138/69 kV auto (available when needed) | IN-SERVICE |  |  |  | AEP GROUP 386 | AEP/TNC | Brett Madison 918-599-2653 | 2264 | 2010-02-28 | 2010-02-28 | 138 | 0 | 0 | 0 | 28.8 | CROCKETT |  | Tier 4 |  |  |  |  | Y
08TPIT0193 | Sonora to Hamilton 138 kV Line: Apply a dynamic rating with new structures | Raise necessary structures to increase MVA rating of Sonora to Hamilton 138 kV line | IN-SERVICE |  |  |  | AEP GROUP 386 | AEP/TNC/TCC | Brett Madison 918-599-2653 | 2231 | 2010-02-28 | 2010-02-28 | 138 | 0 | 0 | 0 | 0 | SUTTON | VAL VERDE | Tier 4 |  |  |  |  | Y
10TPIT0077 | Hamilton to Pancake Rebuild | Rebuild Hamilton to Pancake with 795ACSR, 138KV | [5 empty] | BRAZOS | Dwight Beckmann, 254-750-6373, dbeckman@brazoselectric.com |  | 2010-08-01 | 2010-03-01 | 69 | 0 | 21.9 | 0 | 0 | HAMILTON | CORYELL | Tier 4 |  |  |  | 158258 | Y
06TPIT0077 | Rim Rock-Jack Furman | Construct a new 336 ACSR 138 kV transmission line (approximately 7.5 miles) between the existing Rim Rock substation (7143) and a new 138 kV switching substation (Jack Furman)(7141). | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org | 1002912 | 2010-06-30 | 2010-03-01 | 138 | 7.5 | 0 | 0 | 0 | KERR |  | Tier 2 | 2005-09-01 | 2205-09-01 |  | SEE PROJECT DESCRIPTION | Y |  |  | The name of the new substation was changed from Goat Creek to Jack Furman.
09TPIT0178 | Fox to Granbury 138KV Conversion | Convert exisitng Fox to Granbury 69KV line to 138KV operation | [5 empty] | BRAZOS | Dwight Beckmann, 254-750-6373, dbeckman@brazoselectric.com |  | 2010-11-01 | 2010-03-04 | 138 | 3 | 0 | 0 | 0 | PARKER | HOOD | Tier 4 |  |  |  | 306487478 | Y
10TPIT0092 | Crockett Cap Bank | Increase reactive capacity to 107.2 MVAR at 138kV Crockett substation. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-03-31 | 2010-03-05 | 138 | 0 | 0 | 0 | 100 | HARRIS |  | Tier 4 |  |  |  | 47570, 47571 | Y |  |  | No transformer capacity to be added and no transmission circuits to be built, rebuilt or reconductored.
10TPIT0146 | Seward Junction-Leander | Relocate two (2) structures( #84 #85) for Hwy 183A Roadwork | [5 empty] | PEC | Randy Buchanan (830) 868-6058 |  | 2010-03-10 | 2010-03-05 | 138 | 0 | 0 | 0 | 0 | WILLIAMSON | WILLIAMSON | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | N
08TPIT0146 | Firerock, Add Phase Shifting Transformer | Firerock, Build new station and Add Phase Shifting Transformer East of Santa Anna on the Brownwood line | IN-SERVICE |  |  |  | AEP GROUP 391 | AEP/ETT | Ashley Beasley 918-599-2653 | 2269 | 2010-03-18 | 2010-03-07 | 138 | 0 | 0 | 150 | 0 | COLEMAN |  | Tier 4 |  |  |  |  | Y
09TPIT0004 | Laredo Plant to Lobo, rebuild 138 kV line | Construct new Laredo Lobo to San Miguel 345 kV line with Laredo Lobo 345/138 kV substation where the existing Falfurrias to Laredo 138 kV and the Freer to Laredo 69 kV transmission lines cross Highway 59, rebuild Laredo Lobo to Laredo 138 kV line and convert Lobo to Laredo 69 kV line section to 138 kV | IN-SERVICE |  |  |  | AEP GROUP 216 | AEP/ETT | Bill Eakin 918-599-2653 | 1304 | 2010-03-07 | 2010-03-07 | 138 | 0 | 15 | 0 | 0 | WEBB | WEBB | Tier 1 | 2003-09-15 | 2004-02-19 | 2004-03-08 |  | Y
10TPIT0002 | Lobo, build 345 kV for 675MVA autotransformer | Construct new Laredo Lobo to San Miguel 345 kV line with Laredo Lobo 345/138 kV substation where the existing Falfurrias to Laredo 138 kV and the Freer to Laredo 69 kV transmission lines cross Highway 59, rebuild Laredo Lobo to Laredo 138 kV line and convert Lobo to Laredo 69 kV line section to 138 kV | IN-SERVICE |  |  |  | AEP GROUP 216 | AEP/ETT | Bill Eakin 918-599-2653 | 1720 | 2010-03-07 | 2010-03-07 | 345 | 0 | 0 | 675 | 0 | WEBB |  | Tier 1 | 2003-09-15 | 2004-02-19 | 2004-03-08 |  | Y
09TPIT0003 | Lobo to San Miguel, build 345 kV line | Construct new Laredo Lobo to San Miguel 345 kV line with Laredo Lobo 345/138 kV substation where the existing Falfurrias to Laredo 138 kV and the Freer to Laredo 69 kV transmission lines cross Highway 59, rebuild Laredo Lobo to Laredo 138 kV line and con | IN-SERVICE |  |  |  | AEP GROUP 216 | AEP/ETT/TCC | Bill Eakin 918-599-2653 | 633 | 2010-03-07 | 2010-03-07 | 345 | 72 | 0 | 0 | 0 | WEBB | ATASCOSA | Tier 1 | 2003-09-15 | 2004-02-19 | 2004-03-08 |  | Y |  |  | Associated with STEC project 10TPIT0075
10TPIT0075 | San Miguel to Lobo 345 kV line | Construct a 113.8 miles 345 kV line from San Miguel to Lobo. Joint project with AEP. STEC portion 41.8 miles | Previous 2007 date entry was a typo. Work is planned for 2009. Changed responsibility to STEC and AEP |  |  |  | 09TPIT0003 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2010-03-01 | 2010-03-10 | 345 | 41.8 | 0 | 0 | 0 | ATASCOSA | WEBB | Tier 1 | 2009-10-03 | 2009-02-04 | 2009-03-04 | 5901-80219 | Y | N
07TPIT0248 | San Miguel 345 kV line terminal for San Miguel to Lobo 345 kV line | Breakers, bus, relaying for San Miguel to Lobo 345 kV line termination | Previous 2007 date entry was a typo. Work is planned for 2009. Changed responsibility to STEC and AEP |  |  |  | 09TPIT0003 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2010-03-01 | 2010-03-10 | 345 | 0 | 0 | 0 | 0 | ATASCOSA |  | Tier 4 |  |  |  | 5901 | Y | N
10TPIT0149 | Tomball - Tomball Tap Ckt.66 - Substation Equipment | Upgrade limiting equipment at Tomball substation to increase thermal ratings. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-03-31 | 2010-03-16 | 138 | 0 | 0 | 0 | 0 | HARRIS |  | Tier 4 |  |  |  | 46510, 46511 | Y |  |  | No transformer capacity to be added and no transmission circuits to be built, rebuilt or reconductored.
09TPIT0104 | Gonzales, add NaS Battery | Add 2nd 138/69 kV autotransformer at Alamito Creek, and install a Nas Battery at Gonzales | IN-SERVICE |  |  |  | AEP GROUP 358 | AEP/ETT | Brett Madison 918-599-2653 | 2281 | 2010-03-17 | 2010-03-17 | 69 | 0 | 0 | 0 | 0 | PRESIDIO |  | Tier 1 | 2008-03-21 | 2008-06-10 | 2008-07-15 |  | Y
08TPIT0086 | Exeter - New 138kV Substation | Construct new 138kV substation to replace Terrell Hills substation |  |  |  |  | T-0088 | CPS | PM: Ulrich Skerhut | S-0230 | 2010-03-02 | 2010-03-19 | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5143 | Y | N |  | There are no transformers associated with this project
10TPIT0111 | Sandow Switch - Sandow Third 138 kV line | Build new 138 kv line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R732-WACF | 2010-03-01 | 2010-03-20 | 138 | 1 | 0 | 0 | 0 | MILAM | MILAM | Tier 2 |  | 2009-03-01 |  | 13430, 3430, 13434 | Y
10TPIT0112 | Sandow Switch Third 345/138 kV autotransformer | Install third 345/138 kV autotransformer and remove small autotransformer from service. | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R736-WACF | 2010-03-01 | 2010-03-20 | 345 | 0 | 0 | 600 | 0 | MILAM |  | Tier 2 |  | 2009-03-01 |  | 3429, 13430 | Y
10TPIT0143 | Childress 20th St to Henry: Rebuild Dbl Ckt 138/69 kV Line | Rebuild Dbl Crkt 138/69 Line from West Chilldress to Childress 20th Street to connect BEC's Henry Substation (11/09) | IN-SERVICE |  |  |  | AEP GROUP 403 | AEP/BEC | John Pulay 918-599-2653 | 2279 | 2010-03-21 | 2010-03-21 | 69 | 1 | 0 | 0 | 0 | CHILDRESS | CHILDRESS | Tier 4 |  |  |  |  | Y
10TPIT0151 | Benbrook terminal equipment | Upgrade terminal equipment on 345 kV line to Parker | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5154-WACF | 2010-05-01 | 2010-03-21 | 345 | 0 | 0 | 0 | 0 | TARRANT |  | Tier 4 |  |  |  | 1873, 1869, 1870, 1436 | Y
10TPIT0152 | Parker terminal equipment | Upgrade terminal equipment on 345 kV line to Benbrook | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R586-WACF | 2010-05-01 | 2010-03-21 | 345 | 0 | 0 | 0 | 0 | PARKER |  | Tier 4 |  |  |  | 1436, 1873, 1869, 1870 | Y
10TPIT0071 | Rayford - Westfield Ckt.66 | Upgrade 138 kV Ckt.66 Rayford - Westfield to increase thermal ratings | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-03-31 | 2010-03-25 | 138 | 0 | 9.14 | 0 | 0 | MONTGOMERY | HARRIS | Tier 4 |  |  |  | 46261, 46051 | Y |  |  | No transformer capacity to be added. Energization dates for projects associated with Rothwood substation have been updated to match the current construction schedule.
09TPIT0084 | Tomball - Rothwood - Rayford Ckt.66 | Upgrade 138 kV Ckt.66 Tomball - Rothwood to increase thermal ratings | IN-SERVICE |  |  |  | 09TPIT0086 | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-03-31 | 2010-03-25 | 138 | 0 | 13 | 0 | 0 | HARRIS | MONTGOMERY | Tier 3 | 2008-03-26 | 2008-04-14 | 2008-05-20 | 46510, 46295, 46261 | Y |  | “Please see Requested Info in 09tpit0086” | Added as part of 2007 ERCOT 5 year plan projects. Energization dates for projects associated with Rothwood substation have been updated to match the current construction schedule.
10TPIT0093 | Tomball - Westfield Ckt.81 | Upgrade 138 kV Ckt.81 Tomball - Westfield to increase thermal ratings | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-03-31 | 2010-03-25 | 138 | 0 | 8.31 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 46510, 46512, 46052 | Y |  |  | No transformer capacity to be added and no transmission circuits to be built, rebuilt or reconductored. Energization dates for projects associated with Rothwood substation have been updated to match the current construction schedule.
09TPIT0085 | Convert Rayford 138 kV substation. | Convert Rayford from a double tap substation to a loop tap configuration substation. | IN-SERVICE |  |  |  | 09TPIT0086 | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-03-31 | 2010-03-25 | 138 | 0 | 0 | 0 | 0 | MONTGOMERY |  | Tier 3 | 2008-03-26 | 2008-04-14 | 2008-05-20 | 46261, 46262 | Y |  |  | Added as part of 2007 ERCOT 5 year plan projects. Energization dates for projects associated with Rothwood substation have been updated to match the current construction schedule.
09TPIT0086 | Rothwood 345/138 kV substation | Build a new 345/138 kV Rothwood substation. Loop Ckt.74 Kuykendahl to King and 138 kV Ckt.66 Rayford tap section into the new substation. Add one 800 MVA 345/138 kV autotransformer at Rothwood substation. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-03-31 | 2010-03-25 | 345 | 0.4 | 0 | 800 | 0 | HARRIS |  | Tier 3 | 2008-03-27 | 2008-04-14 | 2008-05-20 | 46290, 46295 | Y |  | (Q) I’ve been reviewing the SSWG cases and ERCOT’s 08/01/2008 TPIT to get a better understanding of the projects related to the new Rothwood 345/138 kV substation. In the 2010/2011 SSWG cases, as released, there are still significant overloads on the 138 kV branch from Rothwood to Rayford (46290-46261) for loss of branches 46512-46052 and 46570-45910. (A) Branches 46512-46052 and 46570-45910 do not share a common tower currently and will not share a common tower after the Rothwood project is complete; therefore, they are not included in the ERCOT contingency files posted with the SSWG cases. Furthermore, after the Rothwood project is finished, the circuit segment 46512-46052 will be part of a multi-section line with the circuit designation 46510-46570-&1 (Q) This overload is like the original 2009 overload of the Tomball – Rayford (46510-46261)138 kV line that results in unserved energy that this project is designed to fix. (A) The contingency that caused the unserved energy in the 5 year plan was the loss of the 345 kV double circuit line into Tomball overloading North Belt to Westfield (Q) The latest TPIT lists line upgrade projects on the 138 kV line from Tomball – Rothwood – Rayford going in in 2010. I do not believe that this project is captured in the 2010 or 2011 case. (A) It is captured in the cases; however, the scope of the upgrade had yet to be finalized; therefore, we only modeled bundling the Tomball to Rothwood to Rayford segments with 2-795ACSR. Our own studies on the 08DSB cases from June show a need to upgrade above this capacity because of single contingencies and the soon to be updated TPIT update will reflect these changes. (Q) Can any of you provide the ratings of the lines once the upgrades are complete? The current SSWG case currently has a ratings of 371/455/455 MVA for both 2010 and 2011 (A) The ckt 66 Tomball – Rothwood ratings are expected be 440/526/562. Ckt 66 Rothwood – Rayford ratings are expected to be at least 398/455/893. Final ratings on these segments are still to be determined. (Q) As a side note, the line upgrades associated with the branches from CWESFLD_ 138D – TRSWIG_138A and TRSWIG_138A – Humble__138F are not included in the case. We’ve already included those ratings in our cases though, I have no requests related to those branches. (Q) Additionally, there is an approximately 250% growth in load at Rayford, bus 46261, between 2009 and 2010. I just wanted to verify that this was correct. (A) The reason for the large increase in load is that with the Rothwood project Rayford is being converted from a double tap station to a loop-thru station. The model is adjusted accordingly by eliminating bus 46262 and moving its load (86.2 MW) to bus 46261 for a total of (67.5 + 86.2 MW). | Added as part of 2007 ERCOT 5 year plan projects. Energization dates for projects associated with Rothwood substation have been updated to match the current construction schedule.
08TPIT0079 | Steamboat, new 69 kV switching station | Build new Steamboat 69 kV switch station | IN-SERVICE |  |  |  | AEP GROUP 341 | AEP/TNC | Brett Madison 918-599-2653 | 2074 | 2010-03-31 | 2010-03-31 | 69 | 0 | 0 | 0 | 0 | TAYLOR |  | Tier 4 |  |  |  |  | Y
10TPIT0052 | Big Lake, Add 150 MVA Phase Shifting Transformer | Install a 138 kV Phase Shifting Transformer at Big Lake | IN-SERVICE |  |  |  | AEP GROUP 386 | AEP/TNC | Brett Madison 918-599-2653 | 2228 | 2010-03-31 | 2010-03-31 | 138 | 0 | 0 | 150 | 0 | REAGAN |  | Tier 4 |  |  |  |  | Y
10TPIT0058 | Lytton Springs Autotransformer Addition | Add a new 345-138 kV 478 MVA autotransformer at the Lytton Springs substation (9074). Terminate the Mendoza (7325) - Turnersville (7500) 138 kV transmission line (T-382) into the Lytton Springs substation 138 kV bus (9075), creating the new Turnersville (7500) - Lytton Springs (9075) and Mendoza (7325) - Lytton Springs (9075) 138 kV transmission lines. Upgrade the new Turnersville (7500) - Lytton Springs (9075) 138 kV transmission line from 795 ACSR (220MVA) to 1433 ACSS/TW (507 MVA). Upgrade the new Mendoza (7325) - Lytton Springs (9075) 138 kV transmission line from 795 ACSR (220 MVA) to bundled 795 ACSR (440 MVA). | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2010-05-11 | 2010-04-01 | 345 | 0 | 7 | 478 | 0 | CALDWELL |  | Tier 3 |  |  |  | SEE PROJECT DESCRIPTION | Y
10TPIT0121 | Lolita: Replace Limiting Switches and Jumpers on Formosa to Lolita 138 kV Line | Upgrade generator disturbance monitoring, metering, and communications at the Formosa 138 kV substation. Add generator monitoring, protection, and communications at the Formosa CFB Plant. | In-Service |  |  |  | AEP GROUP 437 | AEP/TCC | Paul Hassink 918-599-2653 | 3336 | 2010-04-09 | 2010-04-09 | 138 | 0 | 11.84 | 0 | 0 | CALHOUN | JACKSON | Tier 4 |  |  |  |  | Y
09TPIT0196 | Pearsall to Moore SS 138 kV Line | Upgrade 12 miles composite core 1020 ACCC-TW 138 kV line conductor from Pearsall to Moore Switching Station. | Upgrade 138 kV line for new generation at Pearsall |  |  |  |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2010-04-01 | 2010-04-10 | 138 | 0 | 12 | 0 | 0 | FRIO | FRIO | Tier 4 |  |  |  | 5895-5827 | Y | N
10TPIT0110 | Sandow Switch - Elgin Switch 138 kV line | Rebuild existing 138 kV line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R733-WACF | 2010-04-01 | 2010-04-17 | 138 | 0 | 21.8 | 0 | 0 | MILAM | WILLIAMSON | Tier 2 | 2008-07-07 | 2008-08-04 | 2009-03-31 | 13430, 3650 | Y
10TPIT0150 | Elgin Switch terminal equipment | Upgrade 138 kV terminal equipment on line to Gilleland | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R734-WACF | 2010-05-01 | 2010-04-17 | 138 | 0 | 0 | 0 | 0 | WILLIAMSON |  | Tier 4 |  |  |  | 3650 | Y
10TPIT0139 | Salado Switch | Add 345 kV breakers | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C007-WA | 2010-06-01 | 2010-04-17 | 345 | 0 | 0 | 0 | 0 | BELL |  | CREZ |  |  |  | 3699 | Y |  |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
08TPIT0158 | Baytown - Haney Ckt.66 | Reconductor and upgrade limiting equipment at Baytown to increase thermal ratings. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-04-30 | 2010-04-29 | 138 | 0 | 7.1 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 40170, 40172, 40790 | Y |  |  | No transformer capacity to be added.
06TPIT0198 | Hickory Substation 69kV Bay Addition | Construct new 69kV bays to allow tie in of the new Iron Horse to Hickory transmission line | On Schedule |  |  | Complete | 07TPIT0095 | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 600128 | 2010-06-01 | 2010-05-01 | 69 | 0 | 0 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 910 | Y
07TPIT0095 | RD Wells to Hickory 69kV Transmission Line | Construct 1.6 miles of new 138kV transmission line to be operated at 69kV | On schedule |  |  | Complete | 07TPIT0091, 0092, 0094, 0179 | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 600130 | 2010-04-10 | 2010-05-01 | 69 | 1.6 | 0 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 932, 910 | Y
07TPIT0097 | Reconstruct 1.2 miles - Hickory to North Lakes 69kV Transmission Line | Reconstruct 1.2 miles of existing 69V transmission line | On schedule |  |  | Complete | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 600775 | 2010-03-01 | 2010-05-01 | 69 | 0 | 1.2 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 910, 915 | Y
10TPIT0131 | Elgin-Gilleland Creek | Upgrade the conductor on the 12.9-mile Elgin (3650)-Gilleland Creek (7336) 138 kV transmission line from 795 ACSR (220 MVA) to 1433 ACSS/TW (507 MVA). | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2010-05-28 | 2010-05-01 | 138 | 0 | 12.9 | 0 | 0 | TRAVIS | WILLIAMSON | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y
10TPIT0099 | Goldthwaite to Evant | The existing LCRA TSC 138 kV transmission line (approximately 24 miles) between the LCRA TSC Goldthwaite (7070) and Evant (7068) stations will be rebuilt. The rebuilt transmission line will consist of 1X795 ACSR conductor to provide a thermal rating of 220 MVA. | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2010-05-30 | 2010-05-01 | 138 | 0 | 24 | 0 | 0 | MILLS | LAMPASAS | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y |  |  | CREZ Default project assigned to LCRA TSC
07TPIT0091 | RD Wells 138kV to 69kV Interchange | Construct a new 138kV to 69 kV 150MVA interchange | On schedule |  |  | Complete | 07TPIT0092, 0094,0095, 0179 | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 600005 | 2010-04-10 | 2010-05-01 | 138 | 0 | 0 | 168 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 930, 932 | Y
08TPIT0128 | Stanton East - Big Spring Switch 138 kV line and Stanton East 138/69 kV autotransformer | Rebuild and convert an existing 69 kV line to a 138 kV line and install a 138/69 kV autotransformer at Stanton East | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8002-WACF | 2010-05-01 | 2010-05-01 | 138 | 0 | 21.6 | 60 | 0 | MARTIN | HOWARD | Tier 4 | 2008-12-12 | 2009-03-27 | 2009-07-21 | 1229, 1326, 1322, 1323 | Y
10TPIT0124 | Port O'Conner to Seadrift 69 kV line | Construct new 12.4miles 795 MCM ACSR 69 kV line between the new Seadrift station and STEC's Port O'Connor substation. | In construction |  |  |  | 05TPIT0092 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2010-04-30 | 2010-05-10 | 69 | 12.4 | 0 | 0 | 0 | CALHOUN | CALHOUN | Tier 2 |  | 2001-06-22 | 2001-07-09 | 5596-5598 | Y | N
09TPIT0215 | Seadrift 69 kV substation | Construct new 69 kV substation connected to new line from Port O'Connor substation. Will tie to AEP Union Carbide in future. | Acquiring Right-Of-Way Easements |  |  |  | 05TPIT0092 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2010-04-30 | 2010-05-10 | 69 | 0 | 0 | 0 | 0 | CALHOUN |  | Tier 2 |  | 2001-06-22 | 2001-07-09 | 5598 | Y | N
08TPIT0116 | CenterPoint Energy/TNMP Alvin interconnection | Build a new 345 kV, 3 breaker ring bus Meadow substation looped into Ckt.99 P.H. Robinson - Oasis. Move 345/138 kV autotransformer from PH Robinson to new Meadow substation for interconnection with TNMP 138 kV North Alvin bus. | IN-SERVICE |  |  |  | 07TPIT0161 | CNP, TNMP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-06-30 | 2010-05-17 | 345 | 0.1 | 0 | 500 | 0 | BRAZORIA |  | Tier 4 | 2006-07-25 | 2006-11-06 | 2007-01-16 | 43030, 42000, 42015 | Y |  |  | 1)_TNMP and CenterPoint Energy jointly studied project. 2)_No transmission circuits to be built, rebuilt or reconductored. 3) See Project #07TPIT0161 for reason for delay. 4) Moving P.H. Robinson Auto #3 (500MVA) to Meadow Substation 5) Meadow substation was formerly known as South Alvin.
09TPIT0013 | Skyline - Install a Third 345kV Autotransformer | Install one 600 MVA autotransformer at Skyline. | [5 empty] | CPS | S: Joe Rodriguez | S-0182 | 2010-05-26 | 2010-05-25 | 345 | 0 | 0 | 600 | 0 | BEXAR | BEXAR | Tier 4 | 2007-03-29 | 2007-04-20 | N/A | 5370 5371 | Y | N |  | There is no transmission line additions associated with this project
10TPIT0130 | Hondo -138 kV Capacitor Bank | Install 18 MVAR Capacitor at the Hondo substation | [5 empty] | CPS | S: Thomas Fryer | S-0569 | 2010-05-28 | 2010-05-27 | 138 | 0 | 0 | 0 | 18 | BEXAR | BEXAR | Tier 4 |  |  |  | 5225 | Y | N |  | There are no transmission line additions associated with this project There are no transformers associated with this project
05TPIT0040 | Fairview to Aledo | Construct 138kv 795 line from Fairview to Aledo, rebuild Waples to Fairview radial | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2010-04-26 | 2010-05-27 | 138 | 32 | 5.8 | 0 | 0 | HOOD | PARKER | Tier 2 |  | 2002-09-01 | 2003-01-01 | 467, 470, 527, 526 | Y
07TPIT0161 | Centerpoint Energy/TNMP Alvin Interconnection Project | Install 138 kV switching station on Alvin-Hastings transmission line and interconnect with Centerpoint 345-138 kV auto-transformer near Alvin. | Difficulties in acquistion of land of switching station site has delayed the project. |  |  |  | 08TPIT0116 | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | GCEC 27517, 27519 | 2010-05-01 | 2010-05-31 | 138 | 0 | 0 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 4 | 2006-07-06 | 2006-11-06 | 2007-01-07 | 39015 | Y |  | Autotransformer for this project is being relocated from PH Robinson.
10TPIT0116 | North Brady, Move DRCS from Rio Pecos to N Brady | Rebuild part of SAPS to Menard 138 kV line by replacing structures and Move SAPS auto and add DCRS at North Brady | IN-SERVICE |  |  |  | AEP GROUP 472 | AEP/TNC | Rue Galyean 918-599-2653 | 2358 | 2010-06-01 | 2010-06-01 | 69 | 0 | 0 | 0 | 0 | MCCULLOCH | MCCULLOCH | Tier 4 |  |  |  |  | Y
10TPIT0127 | Austin to Tuttle - 138 kV Substation Equipment Upgrade | Replace Substation Equipment at Austin to remove MLSE on the Austin to Tuttle 138kV transmission lines |  | Austin | Tuttle |  |  | CPS | S: Keith Calle | S-0396 | 2010-06-01 | 2010-06-01 | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5005 5435 | Y | N |  | There are no transmission line additions associated with this project There are no transformers associated with this project
10TPIT0129 | Merida to Sommers - 138 kV Substation Equipment Upgrade | Replace Substation Equipment at Merida to remove MLSE on the Merida to Sommers 138kV transmission line |  | Merida | Sommers |  |  | CPS | S: David Riethmeyer | S-0565 | 2010-06-01 | 2010-06-01 | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5310 5395 | Y | N |  | There are no transmission line additions associated with this project There are no transformers associated with this project
10TPIT0107 | McNeil-Marshall Ford | Replace under-rated limiting line terminal equipment to increase McNeil (7334)-Marshall Ford (7356) to the conductor's rating. | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2010-06-30 | 2010-06-01 | 138 | 0 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y
10TPIT0072 | Fayetteville-Willow Springs-New Bremen-Bellville South | Rebuild the 28-mile Fayetteville (7286)-Willow Springs (7273)-New Bremen (7271)-Bellville South (7270) 138 kV transmission line (T-216). Upgrade the conductor along the entire line to 1433 ACSS (450 MVA). | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2010-06-01 | 2010-06-01 | 138 | 0 | 28.2 | 0 | 0 | FAYETTE | AUSTIN | Tier 3 |  |  |  | SEE PROJECT DESCRIPTION | Y
11TPIT0046 | Twin Buttes (76009) to Coleman/Brown County Line | Add the second 345 kV circuit (approximately 88 miles) to existing transmission line, double circuit capable structures, between the LCRA TSC Twin Buttes station (76009) and the Oncor Brown station (1444). Circuit ownership changes with Oncor at the Coleman/Brown County line. The new circuit will consist of Cumberland conductor to provide a thermal rating of 2988 MVA. | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2010-06-29 | 2010-06-01 | 345 | 88 | 0 | 0 | 0 | TOM GREEN | COLEMAN | Tier 3 |  |  |  | SEE PROJECT DESCRIPTION | N |  |  | CREZ Default project assigned to LCRA TSC
11TPIT0045 | Divide to Twin Buttes | Add the second 345 kV transmission line (approximately 31 miles) to existing double circuit capable structures between the LCRA TSC Divide (76090) and Twin Buttes (76009) stations. The new transmission line will consist of 2x1590 ACSR Falcon ACSS Merrimack conductor to provide a thermal rating of 1678 MVA. | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2010-06-04 | 2010-06-01 | 345 | 31 | 0 | 0 | 0 | COKE | TOM GREEN | Tier 3 |  |  |  | SEE PROJECT DESCRIPTION | Y |  |  | CREZ Default project assigned to LCRA TSC
09TPIT0124 | Jacksboro Switch - Willow Creek 345 kV line | Rebuild 345 kV line for double-circuit operation. | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C039-WA | 2010-06-01 | 2010-06-01 | 345 | 19.1 | 19.1 | 0 | 0 | JACK | WISE | CREZ |  |  |  | 1429, 1421 | Y |  |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. Cost is included in Willow Creek - Parker project.
10TPIT0102 | Bowman - Jacksboro Switch 345 kV line | Rebuild existing 345 kV line. | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C041-WA | 2010-06-01 | 2010-06-01 | 345 | 0 | 46.7 | 0 | 0 | ARCHER | JACK | CREZ |  |  |  | 1422, 1429 | Y |  |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
10TPIT0106 | Killeen Switch - Salado Switch 345 kV line | Construct 345 kV line on existing structures | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C036-WA | 2010-03-01 | 2010-06-01 | 345 | 15.7 | 0 | 0 | 0 | BELL | BELL | CREZ |  |  |  | 3422, 3699 | Y |  |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
10TPIT0156 | NW Carrollton Switch | Add 345 kV breaker. | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C0008E | 2010-06-01 | 2010-06-01 | 345 | 0 | 0 | 0 | 0 | DALLAS |  | CREZ |  |  |  | 1730 | Y |  |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
10TPIT0056 | Renner SVC Phase I | Install one static var compensator (+300 Mvar/-265 Mvar) | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4058-WA | 2010-06-02 | 2010-06-02 | 138 | 0 | 0 | 0 | 600 | DALLAS |  | Tier 1 | 2008-10-16 |  | 2009-02-01 | 12356, 12357 | Y |  |  | The first phase of the project was approved on 8/19/2008, and the second phase was approved on 2/2/2009. Phase I will go into service in May 2010, and Phase II will go into service in May 2011.
10TPIT0068 | Broadview to Fredericksburg Rd - 138kV line upgrade | Upgrade the existing Broadview to Fredericksburg Rd 138kV transmission line |  | Broadview | Fred Rd |  |  | CPS | PM: Ulrich Skerhut | T-0133 | 2010-06-07 | 2010-06-08 | 138 | 0 | 2.3 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5040 5170 | Y | N |  | There are no transformers associated with this project
11TPIT0025 | Anderson to Westover Hills - New 138kV Transmission Line | Build new 138kV line from Anderson - Westover Hills |  | Anderson | Westover Hills |  | S-0439 | CPS | T: LeeRoy Perez PM: Bruce Raney | T-0200 | 2010-06-01 | 2010-06-08 | 138 | 1.8 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 2 | 2008-08-01 | 2008-10-01 |  | 5003 5488 | Y | N |  | There are no transformers associated with this project
08TPIT0067 | Fort Worth Substation | Construct new 25MVA, 138kV to 13.2kV substation adjacent to TMPA's 138kV transmission line where it intersects US377 | On schedule |  |  | Complete | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 600821 | 2010-06-01 | 2010-06-10 | 138 | 0 | 4 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 919 | Y
06TPIT0010 | W. Levee - Norwood 345 kV line | Construct W. Levee - Norwood 345 kV line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M477-WAC | 2010-06-01 | 2010-06-10 | 345 | 6.5 | 0 | 0 | 0 | DALLAS | DALLAS | Tier 3 | 2003-10-01 | 2004-02-01 | 2004-04-01 | 2398, 2406 | Y
10TPIT0144 | Tombstone: Build new 138 kV Box Bay structure | Interconnect Occidental Petroleum into new Tombstone station | IN-SERVICE |  |  |  | AEP GROUP 473 | AEP/ETT | Brett Madison 918-599-2653 | 2360 | 2010-06-15 | 2010-06-15 | 138 | 0 | 0 | 0 | 0 | PECOS | PECOS | Tier 4 |  |  |  |  | Y
08TPIT0003 | Hutto Switch - Salado Switch 345 kV line | Construct Hutto Switch - Salado Switch 345 kV line and Salado 345 kV Switching Station |  |  |  |  | R456 | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R445-WA | 2010-06-01 | 2010-06-15 | 345 | 73.8 | 0 | 0 | 0 | WILLIAMSON | BELL | Tier 1 |  |  | 2004-12-18 | 3699, 3696 | Y
10TPIT0008 | Hutto Switch and 345/138 kV autotransformer | Create 345 kV switching station and install a 345/138 kV autotransformer |  |  |  |  | R445 | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R456-WA | 2010-06-01 | 2010-06-15 | 345 | 0 | 0 | 600 | 0 | WILLIAMSON |  | Tier 1 |  |  | 2004-12-18 | 3696, 3666 | Y
10TPIT0098 | Henderson Ranch Switching Station | Construct new switching station to connect a new power plant | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R580-WA | 2010-06-01 | 2010-06-17 | 345 | 0 | 0 | 0 | 0 | JACK |  | Tier 4 |  |  |  | 1443 | Y
10TPIT0042 | Ables Springs 138 kV line and point of interconnection (Oncor Electric Delivery portion only) | Construct 138 kV line and point of interconnection | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3055-WA | 2010-07-01 | 2010-06-21 | 138 | 15.67 | 4.97 | 0 | 0 | KAUFMAN | HUNT | Tier 2 | 2007-01-05 | 2007-05-01 | N/A | 12469, 12470 | Y |  |  | The point of interconnection and eastern line were placed into service in May 2010.
10TPIT0128 | Sommers to Kirby & Sommers to Beck to Kirby - 138 kV Substation Equipment Upgrade | Replace Substation Equipment at O.W. Sommers, Beck Rd. and Kirby to remove MLSE on the Sommers to Kirby & Sommers to Beck to Kirby 138kV transmission lines |  | Sommers | Kirby/Beck |  |  | CPS | S: Ricardo Renteria | S-0561 | 2010-06-30 | 2010-06-30 | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5395 5035 5250 | Y | N |  | There are no transmission line additions associated with this project There are no transformers associated with this project
07TPIT0047 | Centerville-Miller line 69 kV to 138 kV voltage conversion | Converts voltage for the line |  | Switch 1376 at Centerville | Switch 1418 at Miller | Completed |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2010-06-30 | 2010-06-30 | 138 | 0 | 2.68 | 0 | 0 | DALLAS | [5 empty] | 810, 824 | Y | N
07TPIT0046 | Newman-Miller line 69 kV to 138 kV voltage conversion | Converts voltage for the line |  | Switch 938 at Newman | Switch 1419 at Miller | Completed |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2010-06-30 | 2010-06-30 | 138 | 0 | 2.27 | 0 | 0 | DALLAS | [5 empty] | 814, 824 | Y | N
07TPIT0044 | Miller 69 kV to 138 kV voltage conversion | Converts voltage for the substation | [5 empty] | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2010-06-30 | 2010-06-30 | 138 | 0 | 0 | 0 | 0 | DALLAS | [5 empty] | 824 | Y
07TPIT0043 | Wynn Joyce-Miller line 69 kV to 138 kV voltage conversion | Converts voltage for the line |  | Switch 9122 at Wynn Joyce | Switch 1420 at Miller | Completed |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2010-06-30 | 2010-06-30 | 138 | 0 | 2.81 | 0 | 0 | DALLAS | [5 empty] | 811, 824 | Y | N
09TPIT0185 | Quanum to Airpro to Shell Ckt.85 | Upgrade limiting equipment at Airpro substation to increase thermal ratings. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-06-30 | 2010-06-30 | 138 | 0 | 0 | 0 | 0 | HARRIS |  | Tier 4 |  |  |  | 41330, 40070, 41450 | Y |  |  | No transformer capacity to be added and no transmission circuits to be built, rebuilt or reconductored.
10TPIT0145 | Pelican 138 kV: Add second tap for generation interconnect | Cotton Wind Farm Interconnect Facilities | IN SERVICE |  |  |  | AEP GROUP 397 | AEP/ETT | Tommy Vannoy 918-599-2653 |  | 2010-06-30 | 2010-06-30 | 138 | 0 | 0 | 0 | 0 | SAN PATRICIO |  | Tier 4 |  |  |  |  | Y
10TPIT0137 | Krum Tap 138 kV Switching Station | Construct 138 kV switching station |  |  |  |  | R510D-E | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R510C-WACF | 2010-06-01 | 2010-06-30 | 138 | 0 | 1 | 0 | 0 | DENTON |  | Tier 3 | 2008-01-14 | 2008-05-19 | N/A | 1582, 1568, 1987, 1990, 1986 | Y
10TPIT0138 | Krum Tap 138 kV line | Rebuild existing 138 kV line |  |  |  |  | R510C-E | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R510D-WA | 2010-06-01 | 2010-06-30 | 138 | 0 | 3.3 | 0 | 0 | DENTON | DENTON | Tier 3 | 2008-01-14 | 2008-05-19 | N/A | 1987, 1986 | Y
09TPIT0194 | Taylor Expansion | Close in 138kV ring bus at Taylor Substation | New |  |  |  |  | SU | Dwight Yarbrough, 956-687-5600, dyarbrough@sharylandUtilties.com | PR08.05149.CAP | 2010-07-01 | 2010-07-15 | 138 | 0.2 | 0 | 0 | 0 | HIDALGO |  | Tier 4 |  |  |  | 8821 | Y |  |  | CCN 30192
09TPIT0190 | Spunky to Georges Creek and New Hope Rebuilds | Rebuild Spunky to New Hope and Spunky to Georges Creek with 795 ACSR conductor | [5 empty] | BRAZOS | Dwight Beckmann, 254-750-6373, dbeckman@brazoselectric.com |  | 2010-09-15 | 2010-07-16 | 69 | 0 | 10.2 | 0 | 0 | JOHNSON | SOMERVELL | Tier 4 |  |  |  | 357384387 | Y
09TPIT0179 | SLU Taylor Road Substation: Loop station into line | Hairpin SLU Taylor Substation into South McAllen to Frontera 138kV Line | IN-SERVICE |  |  |  | AEP GROUP 458 | AEP/TCC/SLU | Rich Haley 918-599-2653 | 3326 | 2010-07-23 | 2010-07-23 | 138 | 0 | 0 | 0 | 0 | HIDALGO | HIDALGO | Tier 4 |  |  |  |  | Y
10TPIT0155 | Cedar Hill Switch 345/138 kV autotransformer | Replace failed autotransformer | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4083A-E | 2010-08-01 | 2010-08-01 | 345 | 0 | 0 | 600 | 0 | DALLAS |  | Tier 4 |  |  |  | 2420,2422, 2421 | Y
09TPIT0083 | P.H. Robinson - Oasis Ckt.99 | Raise conductors and upgrade in-series equipment at P.H. Robinson to increase thermal rating. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-06-30 | 2010-08-17 | 345 | 0 | 20.45 | 0 | 0 | GALVESTON | BRAZORIA | Tier 4 |  |  |  | 42000, 43035 | Y |  |  | No transformer capacity to be added and no transmission circuits to be built, rebuilt or reconductored.
10TPIT0117 | TECO Generation | Interconnect a new generation plant at TECO substation. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-09-30 | 2010-08-24 | 138 | 0 | 0 | 0 | 0 | HARRIS |  | Tier 4 |  |  |  | 48865, 47430 | Y |  |  | No transformer capacity to be added and no transmission circuits to be built, rebuilt or reconductored. Commercial operation scheduled for June 2010
05TPIT0092 | Seadrift to AEP Union Carbide 69 kV line | Construct new 12.4 miles 795 MCM ACSR 69 kV line between the AEP Union Carbide station and STEC's new Seadrift substation. | Construction delays- weather |  |  |  |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2010-09-01 | 2010-09-01 | 69 | 12.4 | 0 | 0 | 0 | CALHOUN | CALHOUN | Tier 2 |  | 2001-06-22 | 2001-07-09 | 5598-80135 | Y | N
10TPIT0140 | Second Hasse 138 / 69 Autotransformer | Install 40 MVA 138 / 69 kV autotransformer at Hasse | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2010-09-23 | 2010-09-22 | 138 | 0 | 0 | 40 | 0 | COMANCHE |  | Tier 4 |  |  |  | 277, 1649 | Y
10TPIT0135 | La Quinta: Temporary Connection into Falfurrias to Lobo 138kV Line | Construct new 138kV La Quinta Substation to directly interconnect 150MW Cedro Hill Wind Farm | IN SERVICE |  |  |  | AEP GROUP 398 | AEP/ETT | Tommy Vannoy 918-599-2653 | 3353 | 2010-09-27 | 2010-09-27 | 138 | 0 | 0 | 0 | 0 | WEBB | WEBB | Tier 4 |  |  |  |  | Y
09TPIT0133 | Jim Christal Substation 138kV Reconstruction | Reconstruct 138kV section of the station installing five 138kV circuit breakers to break the Denton West to Denton North transmission line into two sections | On schedule |  |  | Complete | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 602153 | 2010-11-01 | 2010-10-01 | 69 | 0 | 2 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 916 | Y
09TPIT0135 | CSU Dowling Road Substation | Install (3) Breaker ring to include (2) 138 lines and tap to College Station Utilities | [5 empty] | BTU/CSU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2010-09-01 | 2010-10-01 | 138 | 0 | 0 | 0 | 0 | BRAZOS |  | Tier 4 |  |  |  |  | Y
10TPIT0147 | San Miguel to Pawnee 138 kV reroute | Reroute San Miguel to Pawnee 138 kV circuit to parallel 345 kV circuit per PUCT order | [5 empty] | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2010-11-01 | 2010-10-10 | 138 | 0 | 11 | 0 | 0 | ATASCOSA | KARNES | Tier 4 |  |  |  | 5902-5727 | Y | N
10TPIT0100 | Tippett (76001) to North McCamey (76032) | Add the second 138 kV transmission line (approximately 15 miles) to existing double circuit capable structures between the LCRA TSC North McCamey station (76032) and the new Tippett station (76001). The new transmission line will consist of 2X795 ACSR conductor to provide a thermal rating of 448 MVA. | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2010-10-01 | 2010-10-10 | 138 | 15 | 0 | 0 | 0 | UPTON | UPTON | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y |  |  | CREZ Default project assigned to LCRA TSC
10TPIT0126 | Galveston Area 138kV Circuit Upgrades Phase One | Reconductor a portion of 138 kV Ckt. 93 PH Robinson - Alta Loma to increase thermal ratings. | [5 empty] | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-05-31 | 2010-10-15 | 138 | 0 | 5.34 | 0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 42015, 42061 | Y |  |  | No transformer capacity to be added. Project is part of the 2009 ERCOT 5-Year Plan.
10TPIT0113 | Odessa EHV Third 345/138 kV autotransformer | Install 345/138 kV autotransformer and tertiary shunt reactors | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8004-WA | 2010-12-15 | 2010-11-01 | 345 | 0 | 0 | 504 | -75 | ECTOR |  | Tier 4 |  |  | 2009-07-21 | 1027, 1028 | Y |  | 2009-R6 | ERCOT BOD approved this project as part of the RMR exit strategy for Permian Basin generation.
09TPIT0170 | Tyler Bullard Road terminal equipment | Replace terminal equipment | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R836-WA | 2010-10-01 | 2010-11-02 | 138 | 0 | 0 | 0 | 0 | SMITH |  | Tier 4 |  |  |  | 3219 | Y |  | 2009-R37
07TPIT0034 | Medina Lake-Pipe Creek Rebuild (formally (Medina Lake-CPS Cagnon (Part 2)) | Rebuild and upgrade the 7.8 mile Pipe Creek (7437) - Medina Lake (7432) 1/0 ACSR 69kV transmission line to 795 ACSR 138kV. |  | Pipe Creek Sub | Medina Lake Sub | Complete | 06TPIT0080 | Bandera Electric | Brian D. Bartos (830) 796-6074 b.bartos@banderaelectric.com | 57596 | 2010-11-10 | 2010-11-10 | 138 | 0 | 7.8 | 0 | 0 | BANDERA | BANDERA | Tier 4 | 2003-10-01 | 2003-11-01 |  | See Project Description | Y | N |  | This project was formally known as Medina Lake - CPS Cagnon (Part 2). Submissions to ERCOT RPG for review where concurrent with Medina Lake - CPS Cagnon (Part 1)
10TPIT0118 | Bandera-Verde Creek Rebuild | Rebuild and upgrade the 15 mile Bandera - Verde Creek 336 ACSR 138kV transmission line to 2- 795 ACSR 138kV. |  | Bandera Sub | Verde Creek Sub | Complete |  | Bandera Electric | Brian D. Bartos (830) 796-6074 b.bartos@banderaelectric.com | 134142 | 2010-11-10 | 2010-11-10 | 138 | 0 | 15 | 0 | 0 | BANDERA | KENDALL | CREZ |  |  |  |  | N | N |  | The project will now to bundle the 795 conductor per ERCOT recommendation.
10TPIT0119 | Add 2nd Autotransformer at Bandera | Install a second 24/32/40 MVA 138/69kV autotransformer at Bandera Substation. |  |  |  | Complete |  | Bandera Electric | Brian D. Bartos (830) 796-6074 b.bartos@banderaelectric.com | 151272 | 2010-11-10 | 2010-11-10 | 138 | 0 | 0 | 40 | 0 | BANDERA | BANDERA | CREZ |  |  |  |  | N | N
09TPIT0018 | Reagor Springs to India Rebuild/Upgrade | Upgrade/rebuild existing Reagor Springs. to India line | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2010-11-16 | 2010-11-11 | 69 | 0 | 17 | 0 | 0 | ELLIS | ELLIS | Tier 4 |  |  |  | 210, 214, 215 | Y |  |  | There are no circuit breakers, reactive capability or transformer capacity associated with this project
10TPIT0142 | Waples Capacitor | Install 36 MVA capacitor bank at Wapels 138 kV bus | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2010-12-05 | 2010-11-24 | 138 | 0 | 0 | 0 | 36 | HOOD |  | Tier 4 |  |  |  | 467 | Y
10TPIT0132 | Britmore - Addicks Ckt.09 Reconductor | Upgrade 138 kV Ckt.09 Britmore - Addicks to increase thermal ratings. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-12-31 | 2010-11-29 | 138 | 0 | 2.03 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 44120, 45610 | Y |  |  | No transformer capacity to be added.
11TPIT0095 | Renner SVC Phase II | Install one static var compensator (+300 Mvar/-265 Mvar) | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4058B-WA | 2010-12-01 | 2010-12-01 | 138 | 0 | 0 | 0 | 300 | DALLAS |  | Tier 1 | 2008-10-16 |  | 2009-02-01 | 12356, 12357 | Y |  |  | The first phase of the project was approved on 8/19/2008, and the second phase was approved on 2/2/2009. Phase I will go into service in May 2010, and Phase II will go into service in May 2011.
10TPIT0101 | Willow Creek - Parker 345 kV line | Rebuild 345 kV line for double-circuit operation. | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C040-WA | 2010-12-01 | 2010-12-01 | 345 | 22.25 | 22.25 | 0 | 0 | WISE | PARKER | CREZ |  |  |  | 1421, 1436 | Y |  |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. Cost covers entire Jacksboro Switch - Willow Creek - Parker 345 kV line.
10TPIT0154 | Penascal Wind Phases 2 Generation Interconnect | Penascal Wind Phases 2 and 3 Install ERCOT EPS Metering | IN-SERVICE |  |  |  | 038 - 0489 | AEP/ETT/TCC | John Pulay 918-599-2653 | 3381 | 2010-12-13 | 2010-12-13 | 345 | 0 | 0 | 0 | 0 | KENNEDY |  | Tier 4 |  |  |  |  | Y
10TPIT0157 | Relocation of Line 138-S for Road work on FM 524 | Relocate impacted 138kV transmission line segment for Farm to Market Road 524 work | [5 empty] | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | STE07310 | 2010-12-10 | 2010-12-17 | 138 | 0 | 0.75 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 4 |  |  |  |  | N
12TPIT0077 | Liggett 345/138 kV Autotransformer #1 | Replace 480 MVA Autotransformer | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5107-WAC | 2010-12-01 | 2010-12-17 | 345 | 0 | 0 | 600 | 0 | DALLAS |  | Tier 4 | 2008-06-01 | 2008-07-01 |  | 1923, 1926 | Y |  | 2007-R5
11TPIT0073 | Kirby - Garrott Ckt. 37 | Upgrade 138kV Ckt. 37 Kirby - Garrott to increase thermal ratings. | IN-SERVICE |  |  |  | 11TPIT0072 | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-12-31 | 2010-12-19 | 138 | 0 | 2.32 | 0 | 0 | HARRIS | HARRIS | Tier 3 | 2009-07-01 | 2009-07-01 | N/A | 47320, 47660 | Y |  |  | Part of Garrott - Midtown - Polk Ckt. 90 Upgrade
11TPIT0105 | La Palma to San Benito: Rebuild 0.2 miles | Construct a new 138/69 kV Switching Station near East Harrison substation and reconductor the 69 kV line from La Palma to San Benito | IN-SERVICE |  |  |  | 362 - 0537 | AEP/TCC | Rich Haley 918-599-2653 | 3368 | 2010-12-31 | 2010-12-22 | 138 | 0 | 0.2 | 0 | 0 | CAMERON | CAMERON | Tier 4 |  |  |  |  | Y
08TPIT0009 | Hutto Switch - Round Rock NE - Round Rock 138 kV line | Rebuild existing 138 kV single-circuit line from Hutto Switch to Round Rock with larger conductor and double-circuit structures and add a second circuit to structures to create a Hutto Switch - Round Rock circuit and a Hutto Switch - Gabriel (LCRA) circuit. |  |  |  |  | R456 | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R406-WAC | 2010-12-01 | 2010-12-22 | 138 | 8.4 | 8.9 | 0 | 0 | WILLIAMSON | WILLIAMSON | Tier 4 |  |  |  | 3666, 3670, 3667, 3669, 3668 | Y |  |  | Hutto Switch - Round Rock NE section will be completed in June 2010.
09TPIT0173 | Waco West - Waco Woodway - Waco Atco 138 kV line | Rebuild existing line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R409-WAC | 2010-12-01 | 2010-12-29 | 138 | 0 | 5.84 | 0 | 0 | MCLENNAN | MCLENNAN | Tier 4 | 2008-07-07 |  |  | 3436, 3591, 3592 | Y |  |  | Project submitted to RPG by Luminant.
09TPIT0077 | McCree-Shiloh 138 kV line | Line reconductor |  | Switch 1392 at McCree | Switch 8722 at Shiloh | Completed |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2010-12-31 | 2010-12-31 | 138 | 0 | 2.2 | 0 | 0 | DALLAS |  | Tier 4 |  |  |  | 830, 834 | Y | N
10TPIT0114 | Roanoke Tap to West Denton 345kV CREZ Circuit | Add 345kV circuit to vacant position of TMPA-owned double circuit line from Roanoke Tap over West Denton | Delayed due to coordination with Oncor construction schedule for remainder of line |  |  |  |  | TMPA | Eric Schroeder 936-873-1124 eschroeder@texasmpa.org | T09003 | 2010-12-31 | 2010-12-31 | 345 | 9.8 | 0 | 0 | 0 | DALLAS |  | CREZ |  |  |  | 988, 1730, 2361 | Y
06TPIT0167 | MVEC Merett-MVEC Pharr | Rebuild 138kV line from Merett to MVEC Pharr Substations | Clearance extended to 1-14-11 |  |  |  | 06TPIT0166 | STEC | Doug Evans 361-485-6459 devans@stec.org | 984505 | 2010-12-30 | 2011-01-01 | 138 | 0 | 2.2 | 0 | 0 | HIDALGO | HIDALGO | Tier 4 |  |  |  | 8752-8762 | Y | N
09TPIT0022 | Killeen Switch - S. Harker Heights 138 kV line | Upgrade existing 138 kV line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R410-WAC | 2011-01-01 | 2011-01-01 | 138 | 0 | 5.3 | 0 | 0 | BELL | BELL | Tier 4 |  |  |  | 3423, 3633 | Y
11TPIT0127 | Graham 345/138 kV autotransformer | Replace existing autotransformer | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R904A-WAC | 2011-05-01 | 2011-01-01 | 345 | 0 | 0 | 350 | 0 | YOUNG |  | Tier 4 |  |  |  | 1596, 1430 | Y
11TPIT0113 | Oasis - Meadow Ckt.99 | Upgrade 345kV Ckt. 99 Oasis to Meadow to increase thermal ratings. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2010-12-31 | 2011-01-07 | 345 | 0 | 3.91 | 0 | 0 | BRAZORIA | BRAZORIA | Tier 4 |  |  |  | 43035, 43030 | Y |  |  | 1) Identified by ERCOT as an Economic Project in 2009 5-Year Plan. Needed by summer peak 2011. 2) No transformer capacity to be added.
10TPIT0108 | Dowling Rd Substation Additions | Build new distibution substation in BTU transmission line from BTU South Switch to TAMU Substation | [5 empty] | COCS/BTU | Tony Michalsky 979- 764-3438 tmichalsky@cstx.gov |  | 2011-01-01 | 2011-01-11 | 138 | 0 | 0 | 0 | 0 | BRAZOS |  | Tier 4 |  |  |  |  | Y
08TPIT0032 | Gilleland 345/138kV autotransformer | Install a 672 MVA 345/138kV autotransformer at the new Gilleland switching substation | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2011-01-01 | 2011-01-11 | 345 | 0 | 0 | 672 | 0 | TRAVIS |  | Tier 4 |  |  |  | The 345kV bus is 7340 and the 138kV bus is 7336 | Y
08TPIT0042 | Seaton to Barclay Rebuild | Rebuild existing Seaton to Barclay with 1033 ACSR | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2010-12-23 | 2011-01-20 | 69 | 0 | 10.2 | 0 | 0 | BELL | FALLS | Tier 4 |  |  |  | 69131 | Y |  |  | There are no circuit breakers, reactive capability or transformer capacity associated with this project
09TPIT0119 | Whitesboro SE - Gordonville 138 kV tap line | Construct 138 kV line and convert existing 69 kV line and substations to 138 kV operation. | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R546-WAC | 2011-01-01 | 2011-01-25 | 138 | 0.9 | 7.9 | 0 | 0 | GRAYSON | GRAYSON | Tier 4 |  |  |  | 1744, 1725 | Y
08TPIT0020 | Zorn/Clear Springs-Gilleland Creek-Hutto Switch 345-kV line | Construct a 345 kV double circuit (bundled 959 ACSS) line between Zorn/Clear Springs and Hutto Switch and other ONCOR and AE projects. Upgrade the 7.5-mile McNeil (7334)-Gilleland(7336) 795 ACSR 138-kV transmission line to 1433 ACSS/TW. | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org | Not yet assigned | 2011-02-01 | 2011-02-01 | 345 | 165 | 7.5 | 0 | 0 | WILLIAMSON | GUADALUPE | Tier 1 | 2001-12-01 | 2001-12-01 | 2002-02-01 | 7042, 7050, 7340, 3696 | Y |  |  | Harris Branch substation replaced with Gilleland Creek substation as an in-line termination point for one of the
09TPIT0098 | Dilley, add 138 kV terminal | Construct 9 miles 795 ACSR 138 kV line from Palo Duro to Dilley | IN-SERVICE |  |  |  | 382 - 0559 | AEP/TCC | Brian Johnson 918-599-2653 | 3098 | 2011-02-17 | 2011-02-11 | 138 | 0 | 0 | 0 | 0 | FRIO | FRIO | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 |  | Y
11TPIT0126 | Cactus tap located on the Ft. Lancaster to West Yates 69 kV line | SouthWest Texas Electric Co-Op distribution station | IN-SERVICE |  |  |  | 491 - 0692 | AEP/TNC | Joe Gilbert 918-599-2653 | 2429 | 2011-02-16 | 2011-02-16 | 69 | 0 | 0 | 0 | 0 | CROCKETT | CROCKETT | Tier 4 |  |  |  |  | Y
07TPIT0055 | Frisco to Kruegerville Rebuild | Rebuild existing Frisco to Kruegerville with1590 or Acss conductor | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2011-04-08 | 2011-02-16 | 138 | 0 | 11.7 | 0 | 0 | COLLIN | DENTON | Tier 3 | 2009-10-13 | 2009-11-01 | N/A | 662, 1994, 681 | Y
08TPIT0094 | Palo Duro to AEP Dilley SS 138 kV Line | Construct 9 miles 795 ACSR 138 kV line from Palo Duro to AEP Dilley. | Changed responsibility to STEC |  |  |  |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-01-01 | 2011-02-17 | 138 | 9 | 0 | 0 | 0 | FRIO | FRIO | Tier 4 | 2006-02-01 | 2006-06-29 | 2006-08-01 | 5866-8212 | Y | N
08TPIT0085 | Palo Duro Switching Station | Construct a new Palo Duro switching substation in the 138 kV transmission line, from Pearsall to Batesville, at the point where the line changes from a north/south direction to an east/west direction, ties-in new 138 kV transmission line to AEP Dilley. | Negotiation of site is in progress. Acquiring Right-Of-Way Easements. |  |  |  |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-01-01 | 2011-02-17 | 138 | 0 | 0 | 0 | 0 | FRIO |  | Tier 4 | 2006-02-01 | 2006-06-29 | 2006-08-01 | 5866 | Y | N
09TPIT0189 | Pearsall to Dilley 69 kV Line | Upgrade 21.8 miles of 69 kV to 795 ACSR conductor from Pearsall to Derby to Dilley. | Upgrade 69 kV line for new generation at Pearsall |  |  |  |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-01-01 | 2011-02-25 | 69 | 0 | 21.8 | 0 | 0 | FRIO | FRIO | Tier 4 | 2006-02-01 | 2006-06-29 | 2006-08-01 | 5893-5842--5860 | Y | N
10TPIT0076 | Stephenville to Granbury 138KV Conversion | Convert exisitng Stephenville to Granbury 69KV line to 138KV operation | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2011-01-04 | 2011-02-25 | 138 | 0 | 27.81 | 0 | 0 | HOOD | ERATH | Tier 4 |  |  |  | 306, 307, 309, 306, 305, 304, 303, 299 | Y
10TPIT0050 | Rayburn Substation | Install (3) Breaker ring to include (2) 69 lines and (1) 69/12.5 transformer | [5 empty] | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2011-02-28 | 2011-03-01 | 69 | 0 | 0 | 0 | 0 | BRAZOS |  | Tier 4 |  |  |  |  | Y
11TPIT0088 | La Quinta: Configure station to 3 breaker ring bus | Construct new 138kV La Quinta Substation to directly interconnect 150MW Cedro Hill Wind Farm | Schedule Update |  |  |  | 398 - 0587 | AEP/ETT | Tommy Vannoy 918-599-2653 | 3351 | 2012-03-31 | 2011-03-01 | 138 | 0 | 0 | 0 | 0 | WEBB | WEBB | Tier 4 |  |  |  |  | Y
10TPIT0021 | Krum West Switch - NW Carrollton 345 kV circuit (Oncor Electric Delivery section) | Add second 345 kV circuit on existing structures . |  |  |  |  | C017 | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C037-WA | 2011-03-01 | 2011-03-01 | 345 | 37.2 | 0 | 0 | 0 | DENTON | DALLAS | CREZ |  |  |  | 988, 1730, 2361 | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
08TPIT0162 | Convert Alta Loma 69/138kV dual voltage substation to a 138kV substation. | Convert Alta Loma 69/138kV dual voltage double tap configuration substation to a 138kVsectionalizing substation looped into Ckt.93 PH Robinson to Hitchcock. | [5 empty] | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-03-31 | 2011-03-02 | 138 | 0 | 0.1 | 0 | 0 | GALVESTON |  | Tier 4 |  |  |  | 42061, 42062 | Y |  |  | No transformer capacity to be added and no transmission circuits to be built, rebuilt or reconductored.
12TPIT0055 | Hill Country to Stonegate - 138 kV 2nd Circuit | Build second 138kV transmission line from Hill Country to Stonegate on existing transmission structures |  | Hill Country | Stonegate |  | S-0580 | CPS | PM: Hector Torres | T-0163 | 2011-03-17 | 2011-03-08 | 138 | 10.01 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5209 5415 | Y | N |  | There are no transformers associated with this project
11TPIT0141 | Ft. Lancaster to Illinois #4, Rebuild 69 kV as 138 kV, energize at 69 kV | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE |  |  |  | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2437 | 2011-03-31 | 2011-03-09 | 69 | 0 | 17.21 | 0 | 0 | PECOS | CROCKETT | CREZ Modified |  |  |  |  | Y
11TPIT0119 | Texas Substation Conversion | Convert Texas substation from 69kV to 138kV service. | [5 empty] | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-04-30 | 2011-03-09 | 138 | 0.76 | 0 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 41550, 41540 | Y |  |  | No transformer capacity to be added.
11TPIT0148 | Ayers 138 kV terminal equipment | Upgrade terminal equipment on line from Handley to Hemphill | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5169-WAC | 2011-05-01 | 2011-03-11 | 138 | 0 | 0 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 1950, 2167, 2164 | Y
07TPIT0018 | Lewisville Switch (Brazos) - Highland (TNMP) 138 kV line (Oncor portion) | Upgrade existing 138 kV line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5067-WAC | 2011-05-01 | 2011-03-14 | 138 | 0 | 1.6 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | 2010-06-15 | 645, 1970 | Y
06TPIT9999 | Sioux-Gandy 138kV Line | Build New 138kV Line from Sioux-Gandy Substations | Acquiring Right-Of-Way Easements |  |  |  | 06TPIT0166 | STEC | Doug Evans 361-485-6459 devans@stec.org | 789640 | 2011-03-01 | 2011-03-16 | 138 | 4.5 | 0 | 0 | 0 | HIDALGO | HIDALGO | Tier 2 | 2005-02-01 | 2005-04-20 |  | 8792-8755 | Y | N
11TPIT0160 | Bruni auto upgrade | Upgrade the 18 MVA138/69 kV autotransformer. | [5 empty] | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-04-01 | 2011-03-16 | 138 | 0 | 0 | 37 | 0 | WEBB |  | Tier 4 |  |  |  | 5887, 5888 | Y | N
10TPIT0123 | Sioux 138 kV substation | Build New 138kV Sioux Substation in the Line from Doedyns-Gandy. | Acquiring Right-Of-Way Easements on Sioux-Gandy T/L |  |  |  | 06TPIT9999 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-03-01 | 2011-03-16 | 138 | 0 | 0 | 0 | 0 | HIDALGO |  | Tier 4 |  |  |  | 8792 | Y | N
08TPIT0068 | Collin - Frisco (Brazos) 138 kV line | Upgrade existing 138 kV line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M596-WAC | 2011-05-01 | 2011-03-18 | 138 | 0 | 1.7 | 0 | 0 | COLLIN | DENTON | Tier 4 |  |  | 2010-06-15 | 2370, 681 | Y |  | 2009-R14
11TPIT0137 | Hilltop Lakes Auto | Replace 40 MVA, 138/69 kV auto with 60 MVA auto | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2011-04-01 | 2011-03-21 | 138 | 0 | 0 | 60 | 0 | MADISON |  | Tier 4 |  |  |  | 47, 48 | Y
11TPIT0093 | Saginaw Switch capacitors | Install 138 kV capacitors | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5160-WAC | 2011-05-01 | 2011-03-29 | 138 | 0 | 0 | 0 | 55.2 | TARRANT |  | Tier 4 |  |  |  | 1957 | Y
11TPIT0178 | AGRI Substation Removal | Remove AGRI substation from CNP transmission service | IN-SERVICE | AGRI |  | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | N/A | 2011-03-31 | 69 | 0 | 0 | 0 | 0 | HARRIS |  | Tier 4 |  |  |  | 40051 | Y | N
11TPIT0116 | FM 237 Yorktown - New Substation | Construct a new 69-13.09x26.18-KV, 7.0 MVA substation | COMPLETED |  |  |  |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2011-04-11 | 2011-03-31 | 69 | 0 | 0 | 0 | 0 | DEWITT |  | Tier 4 |  |  |  | See Project Title | Y
11TPIT0161 | Pt Lavaca to Pt Oconnor | Upgrade miles of 69 kV from 4/0 to 795 ACSR conductor between Pt Lavaca and Pt Oconnor. | [5 empty] | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-04-01 | 2011-04-01 | 69 | 0 | 20.1 | 0 | 0 | CALHOUN | CALHOUN | Tier 4 |  |  |  | 5592-5596 | Y | N
11TPIT0053 | Gresham Road 138 kV Switching Station | Construction switching station to connect a new power plant | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R6000-WAC | 2011-06-01 | 2011-04-01 | 138 | 0 | 0 | 0 | 0 | NACOGDOCHES |  | Tier 4 |  |  |  | 3301 | Y
11TPIT0121 | Parker - Comanche Peak - Everman 345 kV line | Connect Parker - Everman 345 kV line into Comanche Peak | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2011-05-01 | 2011-04-01 | 345 | 0 | 0 | 0 | 0 | SOMERVELL |  | Tier 2 | 2009-07-01 | 2010-03-31 |  | 1900 | Y
09TPIT0105 | Rattlesnake Road Switch - Lake Creek 345 kV line | Upgrade existing 345 kV line |  |  |  |  | R499 | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R499A-E | 2011-09-01 | 2011-04-04 | 345 | 0 | 1.5 | 0 | 0 | MCLENNAN | MCLENNAN | Tier 4 |  |  |  | 3399, 3409 | Y
10TPIT0047 | Zenith 345kV Switching Station | Build a new 345 kV Zenith substation. Loop Ckt.99 Singleton - Obrien, Ckt.98 Singleton - T.H. Wharton, Ckt 98 T.H. Wharton - Obrien into the new substation. | [5 empty] | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-05-31 | 2011-04-06 | 345 | 1 | 0 | 0 | 0 | HARRIS |  | Tier 3 | 2007-04-28 | 2007-07-16 | 2007-08-21 | 44900 | Y |  |  | Added to Houston Area Constraint Mitigation Project, Phase II per discussion with ERCOT.
11TPIT0159 | AGRI 69kV Substation | Disconnect customer owned AGRI 69kV substation from CNP service. | [5 empty] | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-04-30 | 2011-04-20 | 69 | 0 | 0 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 40051 | Y
11TPIT0112 | Hockley - Peters Ckt.58 | Convert Hockley to Peters Ckt. 58 from 69kV to 138kV | [5 empty] | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-05-31 | 2011-04-20 | 138 | 0 | 28.5 | 0 | 0 | HARRIS | AUSTIN | Tier 4 |  |  |  | 45890, 46250, 46230 | Y |  |  | No transformer capacity to be added. After completion of conversion to 138kV, Ckt. 58 will become Ckt. 65.
10TPIT0044 | Marbach substation removal - Reconfigure 138kV lines at Marbach and Cagnon | Reroute the 138kV lines at Marbach and Cagnon. Due to removal of the Marbach substation. |  |  |  |  | S-0401 | CPS | T: Aaron Finley PM:Hector Torres | T-0129 | 2011-06-01 | 2011-04-21 | 138 | 0.3 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5295 | Y | N |  | There are no transformers associated with this project
11TPIT0051 | Riley, Build 345 kV switch station, cutting in the existing Oklaunion to Bowman 345 kV line | Build new Riley 345 kV switch station, cut in the existing and future 345 kV lines as described in ERCOT CREZ Scenario 2 | IN-SERVICE |  |  |  | 467 - 0668 | AEP/ETT | Tommy Vannoy 918-599-2653 | 2350 | 2011-05-27 | 2011-04-28 | 345 | 0 | 0 | 0 | 0 | WILBARGER | WILBARGER | CREZ Modified |  |  |  |  | Y
11TPIT0149 | Hemphill 138 kV terminal equipment | Upgrade terminal equipment on line to Randol Mill | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5167-WAC, M5167B-WAC & M5167C-WAC | 2011-05-01 | 2011-04-29 | 138 | 0 | 0 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 2164, 2105 | Y
11TPIT0150 | Hemphill 138 kV terminal equipment | Upgrade terminal equipment on line to Ayers | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5167D-E & M5167E-E | 2011-05-01 | 2011-04-29 | 138 | 0 | 0 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 2164, 2167 | Y
14TPIT0019 | Orange Grove Switch to Orange Grove Sub upgrade | Upgrade 0.21 miles of 69 kV circuit between Orange Grove Switch and Orange Grove Sub | [5 empty] | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-06-01 | 2011-05-01 | 69 | 0 | 0.21 | 0 | 0 | JIM WELLS | JIM WELLS | Tier 4 |  |  |  | 5658 - 5662 | Y | N
11TPIT0117 | Leakey | Remove a 15.6 MVAR Capacitor bank from the Bandera substation (7439) and add a 15.6 MVAR capacitor bank at the Leakey substation (7426) | [5 empty] | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2011-04-01 | 2011-05-01 | 69 | 0 | 0 | 0 | 0 | BANDERA | REAL | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y
11TPIT0166 | Alazan to Nelson Sharpe 138 kV line rebuild | Barney Davis to Nelson Sharpe 138 kV line rebuild 1st circuit on a double circuit capable structure | IN-SERVICE |  |  |  | 400 - 0647 | AEP/ETT/TCC | Michael Glueck 918-599-2653 | 3360 | 2011-06-01 | 2011-05-01 | 138 | 0 | 10.1 | 0 | 0 | NUECES | NUECES | Tier 1 |  |  |  |  | Y
11TPIT0054 | Abilene South - Leon 138 kV line (Oncor Electric Delivery's section) | Rebuild existing 69 kV line for 138 kV operation. | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C042-E | 2011-06-01 | 2011-05-01 | 138 | 0 | 8.4 | 0 | 0 | EASTLAND | EASTLAND | CREZ |  |  |  | 1624 | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0128 | Leon Switch | Install 138 kV breaker. | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C042-E | 2011-06-01 | 2011-05-01 | 138 | 0 | 0 | 0 | 0 | EASTLAND |  | CREZ |  |  |  | 1624 | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0152 | Randol Mill 138 kV terminal equipment | Upgrade terminal equipment on Hemphill - Randol Mill - Handley/Saginaw line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5168-WAC, M5168B-WAC, M5168C-WAC & M5168D-WAC | 2011-05-01 | 2011-05-01 | 138 | 0 | 0 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 2164, 2105, 2103, 2104, 2106 | Y
09TPIT0101 | Oleander, Construct 138/69 kV Substation | Construct a new 138/69 kV Switching Station near East Harrison substation and reconductor the 69 kV line from La Palma to San Benito | IN-SERVICE |  |  |  | 362 - 0537 | AEP/TCC | Rich Haley 918-599-2653 | 3101 | 2011-05-31 | 2011-05-02 | 138 | 0 | 0 | 130 | 0 | CAMERON | CAMERON | Tier 4 |  |  |  | 80023, 80022 | Y
11TPIT0094 | Venus Switch capacitors | Install 138 kV capacitors | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3096-WAC | 2011-05-01 | 2011-05-04 | 138 | 0 | 0 | 0 | 110.4 | ELLIS |  | Tier 4 |  |  |  | 1908 | Y
11TPIT0151 | Mesquite 138 kV terminal equipment | Upgrade terminal equipment on the E Mesquite - Mesquite - Seagoville Switch line | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4046-WAC | 2011-05-01 | 2011-05-05 | 138 | 0 | 0 | 0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2771, 2775, 2776 | Y
07TPIT7777 | MVEC Pharr-Alberta Switch | Rebuild 138kV line from Pharr to Alberta Switch Substations | Delay of Start of Construction to 1-17-11 |  |  |  | 06TPIT0166 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-05-01 | 2011-05-06 | 138 | 0 | 1.2 | 0 | 0 | HIDALGO | HIDALGO | Tier 4 |  |  |  | 8759-8762 | Y | N
11TPIT0056 | Cisco, Convert station to 138 kV | Build new 138 kV circuit from E. Abilene to Leon with 795 ACSS as alternative to CREZ project of upgrading Abilene S. to Leon 138 kV line | IN-SERVICE |  |  |  | 466 - 0666 | AEP/TNC | Dave Goetz 918-599-2653 | 2341 | 2011-06-30 | 2011-05-06 | 138 | 0 | 0 | 0 | 0 | EASTLAND |  | CREZ Modified |  |  |  |  | Y
11TPIT0090 | Benbrook Switch capacitors | Install 138 kV capacitors | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5158-WAC | 2011-05-01 | 2011-05-13 | 138 | 0 | 0 | 0 | 220.8 | TARRANT |  | Tier 4 |  |  |  | 1874, 1875 | Y
11TPIT0091 | Elkton Switch capacitors | Install 138 kV capacitors | [5 empty] | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R6003-WA | 2011-05-01 | 2011-05-13 | 138 | 0 | 0 | 0 | 110.4 | SMITH |  | Tier 4 |  |  |  | 3106 | Y
11TPIT0132 | Olney 2nd Auto | Add 60 MVA, 138/69 kV auto | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2011-05-09 | 2011-05-16 | 138 | 0 | 0 | 60 | 0 | YOUNG |  | Tier 4 |  |  |  | 787, 788 | Y
10TPIT0141 | Olney to Rice | Rebuild existin Olney to Rice 138 kV line | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2011-04-29 | 2011-05-16 | 138 | 0 | 17.1 | 0 | 0 | YOUNG | YOUNG | Tier 4 |  |  |  | 787, 1477 | Y |  |  | 2009-R10
10TPIT0069 | Thomaston: Install 138 kV PST, Add 3-28.8 MVAR Cap Banks, Reterminate 138 kV Line | Upgrade Thomaston substation to 3 breaker ring bus, install 180/200 MVA PST on Thomaston to LCRA Cuero 138 kV line. | IN-SERVICE |  |  |  | 402 - 0653 | AEP/ETT/TCC | Dave Goetz 918-599-2653 | 3264 | 2011-05-31 | 2011-05-19 | 138 | 0 | 0 | 150 | 86.4 | DEWITT |  | Tier 4 |  |  |  |  | Y
11TPIT0124 | Construct Service to Crystal Bay 138kV Substation | Serve substation by looping into Ckt.84 Borden to Dowlap. | [5 empty] | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-05-31 | 2011-05-20 | 138 | 0.2 | 0 | 0 | 0 | HARRIS |  | Tier 4 |  |  |  | 40290 | Y |  |  | No transformer capacity to be added.
11TPIT0005 | Talley Rd - New 138kV Substation | Loop new 138kV substation into future 138kV Medina Lake to CPS line (06TPIT0080) |  | Tally | Tx Research/Medina Lake |  | T-0160 | CPS | PM: Ulrich Skerhut | S-0383 | 2011-06-01 | 2011-05-26 | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5422 | Y | N |  | There are no transformers associated with this project
11TPIT0021 | Nassau Bay to Nassau Bay Sw. Rebuild | Rebuild existing 138 kV 4/0 line from Nassau Bay to Nassau Bay Sw. with 1033 double-circuit construction | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2011-05-03 | 2011-05-30 | 69 | 0 | 1.21 | 0 | 0 | HOOD | HOOD | Tier 4 |  |  |  | 364373451455 | Y
11TPIT0039 | Dresden to LA Heights - 138kV line upgrade | Upgrade the existing Dresden to LA Heights 138kV transmission line |  | Dresden | LA Heights |  | S-0308 | CPS | PM: Bruce Raney | T-0156 | 2011-06-01 | 2011-05-31 | 138 | 0 | 3.29 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5130 5285 5286 | Y | N |  | There are no transformers associated with this project
11TPIT0135 | Navo Capacitor Bank | Install additional 75 MVAR at Navo sub | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2011-04-15 | 2011-05-31 | 138 | 0 | 0 | 0 | 75 | DENTON |  | Tier 4 |  |  |  | 662 | Y
11TPIT0102 | Waples to Hood Conversion | Convert existing Waples to Hood line to 138 kV operation | [5 empty] | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2011-05-03 | 2011-05-31 | 138 | 0 | 7.25 | 0 | 0 | HOOD | HOOD | Tier 4 |  |  |  | 466, 373, 455, 451, 364 | Y
11TPIT0087 | Putnam, Recofigure Station | Build new 138 kV circuit from E. Abilene to Leon with 795 ACSS as alternative to CREZ project of upgrading Abilene S. to Leon 138 kV line | IN-SERVICE |  |  |  | 466 - 0666 | AEP/TNC | Dave Goetz 918-599-2653 | 2400 | 2011-05-31 | 2011-05-31 | 138 | 0 | 0 | 0 | 0 | CALLAHAN |  | CREZ Modified |  |  |  |  | Y
10TPIT0115 | Gibbons Creek Substation Upgrade Project | Install new control houses for both 138kV and 345kV systems. Upgrade all relays and SCADA devices and install new cabling for yard equipment. Install high-side load-break switches for autotransformers 1 and 2. | Revised due to coordination with generation plant outage schedule |  |  |  |  | TMPA | Eric Schroeder 936-873-1124 eschroeder@texasmpa.org | T09002 | 2011-05-01 | 2011-05-31 | 345 | 0 | 0 | 0 | 0 | GRIMES | GRIMES | Tier 4 |  |  |  |  | N
11TPIT0035 | McCree 69 kV, install 18.0 MVAR Cap Bank | Install 18 MVAR capacitor bank to support local low voltage problems | [5 empty] | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2011-06-01 | 2011-06-01 | 69 | 0 | 0 | 0 | 18 | DALLAS |  | Tier 4 |  |  |  | 832 | Y
11TPIT0044 | Highway 9 to Valero West 69 kV transmission line upgrades | Upgrade the Upriver to Highway 9 69 kV Loop and add transformation to remove contingency overloads during off-peak maintenance | IN-SERVICE | Highway 9 | Upriver | Under Construction | 399 - 0644 | AEP/ETT/TCC | Michael Glueck 918-599-2653 | 3280 | 2011-06-30 | 2011-06-01 | 69 | 0 | 3.96 | 0 | 0 | NUECES | NUECES | Tier 1 | 2009-03-18 | 2009-10-09 | 2009-12-01 |  | Y | N
11TPIT0075 | Kirby to Tuttle - 138 kV Circuit | Construct a 138 kV circuit between Kirby and Tuttle using existing ROW and install new substation terminal equipment |  | Kirby | Tuttle |  |  | CPS | PM: Bruce Raney | T-0206 | 2011-10-01 | 2011-06-01 | 138 | 6.475 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5250 5435 | Y | N |  | There are no transformers associated with this project
09TPIT0130 | Newman 138 kV, install 24.0 MVAR Cap Bank | Install 24 MVAR capacitor bank to support local low voltage problems | [5 empty] | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2011-05-02 | 2011-06-01 | 138 | 0 | 0 | 0 | 24 | DALLAS |  | Tier 4 |  |  |  | 849 | Y
05TPIT0068 | Marshall Ford-Buttercup | Upgrade the 9.8-mile Marshall Ford(7356)-Buttercup(7531) 795 ACSR (220-MVA) 138-kV transmission line to bundled 795 ACSR (440MVA). | Complete 6/1/11 |  |  |  |  | PEC | Randy Buchanan (830) 868-6058 |  | 2011-06-01 | 2011-06-01 | 138 | 0 | 9.8 | 0 | 0 | TRAVIS | WILLIAMSON | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y
11TPIT0080 | Killeen Switch - Killeen South - Killeen Fort Hood West Tap 138 kV line | Upgrade existing 138 kV line |  | Killeen Switch | Killeen Fort Hood West Tap | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R741-E | 2011-06-01 | 2011-06-01 | 138 | 0 | 7 | 0 | 0 | BELL | BELL | Tier 4 |  |  |  | 3423, 3428 | Y | N | 2009-R32
11TPIT0122 | Cedar Hill Switch 138 kV terminal equipment | Upgrade 138 kV terminal equipment used to connect the 345/138 kV autotransformer |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4083B-WAC | 2011-06-01 | 2011-06-01 | 138 | 0 | 0 | 0 | 0 | DALLAS |  | Tier 4 |  |  |  | 2421, 2422 | Y | N
11TPIT0145 | Goldsmith Tap - Goldsmith 138 kV Line | Rebuild existing 69 kV line as a double-circuit line with a 138 kV circuit and a 69 kV circuit and convert Goldsmith Substation to 138 kV. |  | Goldsmith Tap | Goldsmith | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8021-WAC | 2011-06-01 | 2011-06-01 | 138 | 3.3 | 3.3 | 0 | 0 | ECTOR | ECTOR | Tier 4 |  |  |  | 11256, 11250, 1141, 1145 | Y | N
11TPIT0172 | PH Robinson - Center Ckt. 97 | Upgrade substation equipment to increase thermal ratings. | [5 empty] | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-06-01 | 2011-06-01 | 345 | 0 | 0 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 42000, 40240 | Y
11TPIT0067 | Tonkawa Switch | Expand existing switching station |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C859-E | 2011-06-01 | 2011-06-01 | 345 | 0 | 0 | 0 | -100 | MITCHELL |  | CREZ |  |  |  | 11048 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0068 | Tonkawa - Sweetwater East 345 kV line | Construct double-circuit 345 kV line |  | Tonkawa | Sweetwater East | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C1007-E | 2011-06-01 | 2011-06-01 | 345 | 63.4 | 0 | 0 | 0 | MITCHELL | NOLAN | CREZ |  |  |  | 11048, 11420 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0069 | Sweetwater East Switch | Construct 345 kV switching station |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C858-E | 2011-06-01 | 2011-06-01 | 345 | 0 | 0 | 0 | -100 | NOLAN |  | CREZ |  |  |  | 11420 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
12TPIT0040 | Scurry County South Switch (Central A) | Construct 345 kV switching station with 345/138 kV autotransformers and shunt reactor |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C1004-E | 2011-06-01 | 2011-06-01 | 345 | 0 | 0 | 1200 | -150 | SCURRY |  | CREZ |  |  |  | 11318 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
12TPIT0041 | Dermott Switch (Central B) | Construct 345 kV switching station with 345/138 kV autotransformers and shunt reactor |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C1003-E | 2011-06-01 | 2011-06-01 | 345 | 0 | 0 | 1200 | -150 | SCURRY |  | CREZ |  |  |  | 11305 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
12TPIT0042 | Scurry County South Switch (Central A) - Tonkawa 345 kV line | Construct double-circuit 345 kV line |  | Scurry County South | Tonkawa | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C1008-E | 2011-06-01 | 2011-06-01 | 345 | 30.4 | 0 | 0 | 0 | SCURRY | MITCHELL | CREZ |  |  |  | 11318, 11048 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0118 | Cheapside - New Substation | Construct a new 138-13.09KV, 20 MVA x two, redundant backup substation | COMPLETED |  |  |  |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2011-06-03 | 2011-06-03 | 138 | 0 | 0 | 0 | 0 | GONZALES |  | Tier 4 |  |  |  | See Project Title | Y | N
08TPIT0080 | Abilene South to Tuscola, Rebuild 69 kV line | Re-Build Portions of the Ballinger to Abilene South 69 kV line with 795 ACSR | IN-SERVICE | Abilene South | Tuscola | Under Construction | 499 - 0704 | AEP/ETT | Teresa Trotman 918-599-2653 | 2455 | 2011-06-06 | 2011-06-06 | 69 | 0 | 11.4 | 0 | 0 | TAYLOR | TAYLOR | Tier 1 | 2008-06-20 | 2009-03-19 | 2009-08-06 |  | Y | N
11TPIT0139 | DUNCAN 138kV Substation | Serve DUNCAN substation by looping into Ckt.86 BENDER - BARHIL. | IN-SERVICE | DUNCAN | BENDER/ BARHIL |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-06-30 | 2011-06-06 | 138 | 0.3 | 0 | 0 | 0 | CHAMBERS | CHAMBERS | Tier 4 |  |  |  | 40360, 40150, 40155 | Y | N |  | No autotransformer capacity to be added.
10TPIT0087 | Putnam to Leon, Convert 69 kV line to 138 kV | Build new 138 kV circuit from E. Abilene to Leon with 795 ACSS as alternative to CREZ project of upgrading Abilene S. to Leon 138 kV line | IN-SERVICE | Putnam | Leon | Under Construction | 466 - 0666 | AEP/ETT/ONCOR | Larry Roberson 918-599-2653 | 2347 | 2011-06-30 | 2011-06-07 | 138 | 0 | 17.38 | 0 | 0 | NUECES | EASTLAND | CREZ Modified | 2008-06-20 | 2009-03-19 | 2009-08-06 |  | Y | Y
11TPIT0146 | Big Brown 345 kV terminal equipment | Upgrade terminal equipment on line to Venus |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R752-WAC | 2011-06-01 | 2011-06-08 | 345 | 0 | 0 | 0 | 0 | FREESTONE | FREESTONE | Tier 4 |  |  |  | 3380, 1906 | Y | N
11TPIT0125 | Teasley Substation - Add 28 MVA Transformer | Install an additional 138kV circuit breaker and a new 28 MVA tranformer in the existing Teasley Substation to accommodate additional load growth | On schedule |  |  | Complete | None | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 602766 | 2011-06-11 | 2011-06-11 | 138 | 0 | 0 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 918 | Y | N
11TPIT0030 | Thompson Creek Substation | Install (3) Breaker ring to include (1) 138 lines, and (1) 138/12.5 transformer |  | Thompson Creek | Thompson Creek | completed | 05TPIT0172 10TIPIT0065 | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2011-06-11 | 2011-06-11 | 138 | 0 | 0 | 14 | 0 | BRAZOS |  | Tier 4 |  |  |  |  | Y | N
10TPIT0065 | Dansby Substation | Install (1) Breaker in existing ring bus for a 138 lines to Thompson Creek Substation |  | Dansby | Dansby | completed | 05TPIT0172 11TIPIT0030 | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com |  | 2011-06-11 | 2011-06-11 | 138 | 0 | 0 | 0 | 0 | BRAZOS |  | Tier 4 |  |  |  | 32897 | Y | N
12TPIT0092 | OXY USA Collie Field 69kV Tap | This project will tap TNMP's Worsham to IH20 69kV line to serve the new Oxy Collie Filed station |  | Worhsam | IH20 | Completed |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | NTE07410 | 2012-02-28 | 2011-06-20 | 69 | 3.077 | 0 | 0 | 0 | WARD | REEVES | Tier 4 |  |  |  | 38020, 38040, 38041, 38042 | Y | N
05TPIT0172 | Thompson Creek to Dansby 138, New line construction | Build a 1033 ACSR 138 kV line |  | Thompson Creek | Dansby | completed | 10TPIT0065 11TPIT0030 | BTU | James Tanneberger, 979-821-5763, jtanneberger@btutilities.com Shawndra Green, 979-821-5744, sgreen@btutilities.com | 802 | 2011-06-20 | 2011-06-20 | 138 | 10.2 | 0 | 0 | 0 | BRAZOS | BRAZOS | Tier 4 |  |  |  | 32897, 32863 | Y | N
11TPIT0147 | Venus 345 kV terminal equipment | Upgrade terminal equipment on line to Big Brown |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3103-WAC & M3103B-WAC | 2011-06-01 | 2011-06-20 | 345 | 0 | 0 | 0 | 0 | ELLIS | ELLIS | Tier 4 |  |  |  | 3380, 1906 | Y | N
11TPIT0120 | Pegasus 138 kV Tap and Point of Interconnection | Convert the tap line to Pegasus and South Pegasus substations to 138 kV and connect to the Odesaa - Crane 138 kV line (Oncor portion) | Construction taking more time than expected | Pleasant Farms | Pagasus and South Pegasus | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8010-WAC | 2011-06-01 | 2011-06-23 | 138 | 0 | 11.4 | 0 | 0 | ECTOR | MIDLAND | Tier 4 |  |  |  | 1235, 1234 | Y | N | 2009-R2
12TPIT0066 | Laguna Vista 138 kV tap lines | Construct 138 kV tap lines to convert Laguna Vista Substation to 138 kV service. | Construction taking more time than expected | East Tap and West Tap | Laguna Vista | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R587-WAC | 2011-06-01 | 2011-06-23 | 138 | 10.4 | 10.4 | 0 | 0 | PARKER | PARKER | Tier 4 |  |  |  | 528, 1590, 529 | Y | N
11TPIT0074c | Galveston Area 138kV Circuit Upgrades Phase Two | Upgrade 138 kV Ckt. 01 Webster to Tiki Island to Galveston to increase thermal ratings. | IN-SERVICE | Webster | Galveston |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-06-30 | 2011-06-30 | 138 | 0 | 26.38 | 0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 43500, 42862, 43355, 42670 | Y | N | See project 11TPIT0074a for total project cost estimate | No transformer capacity to be added. Project is part of the 2009 ERCOT 5-Year Plan. Construction included in cancelled project 11TPIT0071 is now included in 11TPIT0074.
11TPIT0074b | Galveston Area 138kV Circuit Upgrades Phase Two | Upgrade 138kV Ckt. 93 Alta Loma to Hitchcock to West Galveston to increase thermal ratings. | IN-SERVICE | Alta Loma | West Galveston |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-06-30 | 2011-06-30 | 138 | 0 | 15.7 | 0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 42061, 42800, 43400 | Y | N | See project 11TPIT0074a for total project cost estimate | No transformer capacity to be added. Project is part of the 2009 ERCOT 5-Year Plan. Construction included in cancelled project 11TPIT0071 is now included in 11TPIT0074.
11TPIT0074a | Galveston Area 138kV Circuit Upgrades Phase Two | Upgrade 138 kV Ckt. 63 Webster to Stewart to increase thermal ratings. | IN-SERVICE | Webster | Stewart |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-06-30 | 2011-06-30 | 138 | 0 | 21.85 | 0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 43507, 42861, 43290 | Y | N |  | No transformer capacity to be added. Project is part of the 2009 ERCOT 5-Year Plan. Construction included in cancelled project 11TPIT0071 is now included in 11TPIT0074.
07TPIT0026 | Booneville to Hearne Southwest Rebuild | Rebuild existing Booneville - Hearne Southwest with 795 | row issues | Booneville | Hearne Southwest | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com |  | 2011-09-20 | 2011-07-07 | 69 | 0 | 22.2 | 0 | 0 | ROBERTSON | BRAZOS | Tier 4 |  |  |  | 38, 32870 | Y | N |  | There are no circuit breakers, reactive capability or transformer capacity associated with this project
07TPIT0086 | Circuit 978 (Seaholm to Warren) Reconductor | Reconductor the last span of the Ckt 978 (Seaholm to Warren) going into Warren substation with bundled 795 ACSR Drake conductor. | COMPLETE | Seaholm Substation | Warren Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P086 | 2011-08-01 | 2011-08-01 | 138 | 0 | 0.1 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9132, 9286 | Y | N
11TPIT0142 | Illinois #4 to Comstock, Rebuild 69 kV as 138 kV, energize at 69 kV | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE | Illinois #4 | Comstock | Under Construction | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2438 | 2011-08-02 | 2011-08-02 | 69 | 0 | 63.6 | 0 | 0 | CROCKETT | VALVERDE | CREZ Modified |  |  |  |  | Y | Y
11TPIT0177 | TRIBAY Substation Removal | Remove TRIBAY substation from CNP transmission service | IN-SERVICE | TRIBAY |  | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | N/A | 2011-09-22 | 138 | 0 | 0 | 0 | 0 | HARRIS |  | Tier 4 |  |  |  | 41600 | Y | N
11TPIT0136 | Bissett to Aspermont | Rebuild Bissett to Aspermont 69 kV line with 795 ACSR | construction delay due to high temps | Bissett | Aspermont | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10030 | 2011-09-15 | 2011-09-27 | 69 | 0 | 21.35 | 0 | 0 | STONEWALL | STONEWALL | Tier 4 |  |  |  | 753, 755, 6156 | Y | N
11TPIT0106 | Pelican 138 kV: Build 4 Breaker ring Bus | Pelican 138 kV Switching Station for ultimate interconnect of Papalote Creek and Cotton Windfarms | IN-SERVICE |  |  | In Service | 486 - 0688 | AEP/ETT/TCC | Tommy Vannoy 918-599-2653 | 3361 | 2011-09-28 | 2011-09-28 | 138 | 0 | 0 | 0 | 0 | SAN PATRICIO |  | Tier 4 |  |  |  |  | Y | N
11TPIT0171 | Hutto Switch shunt reactors | Install shunt reactors on the tertiary of the 345/138 kV autotransformer |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R755-WAC | 2011-10-01 | 2011-09-30 | 138 | 0 | 0 | 0 | -75 | WILLIAMSON |  | Tier 4 |  |  |  | 3666 | Y | N
10TPIT0026 | Mueller 138kV substation | Establish new 138kV Mueller substation with a 30MVA transformer and two underground feeders. The substation will cut into existing Ckt 938 (Kingsbery to Wheless Lane). | COMPLETE | Mueller Substation | Mueller Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | 3230_117_2793 3240_117_4793 3230_117_4229 | 2011-10-01 | 2011-10-01 | 138 | 1 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9342 | Y | N
10TPIT0022 | Ckt 918 Oak Hill to Brodie Lane Reconductor | Reconductor the last span of the Ckt 918 going into Oak Hill sub with bundled 795 ACSR Drake capable of 2000 Amperes | COMPLETE | Oak Hill Substation | Brodie Lane Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P080 | 2011-10-01 | 2011-10-01 | 138 | 0 | 0.1 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9169, 9247 | Y | N
11TPIT0169 | Graham 138 kV terminal equipment | Upgrade terminal equipment on 345/138 kV autotransformer |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R904A-WAC | 2011-12-01 | 2011-10-01 | 138 | 0 | 0 | 382 | 0 | YOUNG |  | Tier 4 |  |  |  | 1601 | Y | N
09TPIT0176 | Bertram-Andice | Close the normally open Bertram (7520)-Andice(7521) 69 kV transmission line. |  | Bertram | Andice |  |  | PEC | Randy Buchanan (830) 868-6058 |  | 2011-09-12 | 2011-10-10 | 69 | 0 | 0 | 0 | 0 | BURNET | WILLIAMSON | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
11TPIT0131 | Hearne Auto | Replace 60 MVA, 138/69 kV auto with 100 MVA auto |  | Hearne |  | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10067 | 2011-10-07 | 2011-10-11 | 138 | 0 | 0 | 100 | 0 | ROBERTSON |  | Tier 4 |  |  |  | 35, 36 | Y | N
11TPIT0143 | Comstock to Rough Canyon, Rebuild 69 kV as 138 kV, energize at 69 kV | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE | Comstock | Rough Canyon | In-Service | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2439 | 2011-10-12 | 2011-10-12 | 69 | 0 | 21.6 | 0 | 0 | VALVERDE | VALVERDE | CREZ Modified |  |  |  |  | Y | N
10TPIT0078 | Granbury to Glen Rose Rebuild | Rebuild Granbury to Geln Rose with 959ACSS |  | Granbury | Glen Rose | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 07017 | 2011-10-10 | 2011-10-17 | 69 | 0 | 14.2 | 0 | 0 | HOOD | SOMERVELL | Tier 4 |  |  |  | 315307 | Y | N
12TPIT0070 | Ballinger to Winters, Rebuild 69 kV line | Re-Build Portions of the Ballinger to Abilene South 69 kV line with 795 ACSR | IN-SERVICE | Ballinger | Winters | Under Construction | 499 - 0705 | AEP/ETT | Teresa Trotman 918-599-2653 | 2460 | 2011-10-22 | 2011-10-22 | 69 | 0 | 16.7 | 0 | 0 | TAYLOR | TAYLOR | Tier 1 | 2008-06-20 | 2009-03-19 | 2009-08-06 |  | Y | N
11TPIT0130 | Webberville Solar Project | A new 30MW solar plant operated at 138kV level and tapped into an existing Austrop to Decker Ckt 921. | COMPLETE | Webberville Solar Plant | Webberville Tap | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P311 | 2011-11-01 | 2011-11-01 | 138 | 0.91 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9030, 9185, 9289 | Y | N
12TPIT0119 | Forney - Hubbard 138 kV line | Replace terminal equipment |  | Forney | Hubbard | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4040A - WAC | 2011-12-01 | 2011-11-01 | 138 | 0 | 0 | 0 | 0 | KAUFMAN | DALLAS | Tier 4 |  |  |  | 2934, 2438, 2402 | Y | N
11TPIT0099 | Temple Switch circuit breaker | Install 345 kV circuit breaker on line to Salado Switch. |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R739-WAC | 2011-12-01 | 2011-11-01 | 345 | 0 | 0 | 0 | 0 | BELL |  | Tier 4 |  |  |  | 3414 | Y | N
11TPIT0092 | Handley SES capacitors | Install 138 kV capacitors |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5159-WAC | 2011-09-01 | 2011-11-05 | 138 | 0 | 0 | 0 | 110.4 | TARRANT |  | Tier 4 |  |  |  | 1951 | Y | N
11TPIT0153 | Colorado City 69 kV terminal equipment | Upgrade terminal equipment on line to Morgan Creek |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8026-WAC, R8026B-WAC, R8026C-WAC & R8026D-WAC | 2011-11-01 | 2011-11-09 | 69 | 0 | 0 | 0 | 0 | MITCHELL | MITCHELL | Tier 4 |  |  |  | 1378, 1033 | Y | N
09TPIT0103 | Alamito Creek, add 2nd 138/69 kV auto | Add 2nd 138/69 kV autotransformer at Alamito Creek, and install a NaS Battery at Gonzales | IN-SERVICE |  |  | In-Service | 358 - 0532 | AEP/TNC | Jim Eriksen 918-599-2653 | 1178 | 2011-11-10 | 2011-11-10 | 138 | 0 | 0 | 50 | 0 | PRESIDIO |  | Tier 1 | 2008-03-21 | 2008-06-10 | 2008-07-15 |  | Y | N
11TPIT0163 | Tres Palacious 69 kV Substation | Construct new 69 kV load serving substation in the line between N Clemville and Saltdome. |  |  |  | Under Construction |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-09-01 | 2011-11-11 | 69 | 0 | 0 | 0 | 0 | MATAGORDA |  | Tier 4 |  |  |  | 5553 | Y | N
11TPIT0104 | Move Hearn Rd to the Lon Hill to Upriver 69 kV line | Lon Hill to Upriver 69 kV Hairpin into Hearn Road and Upgrade Lon Hill to Hearn Road section | IN-SERVICE | Lon Hill & Upriver | Hearn Road | Under Construction | 399 - 0709 | AEP/ETT/TCC | Michael Glueck 918-599-2653 | 3279 | 2011-11-11 | 2011-11-11 | 69 | 0.5 | 0.5 | 0 | 0 | NUECES | NUECES | Tier 1 |  |  |  |  | Y | N
11TPIT0103 | Remove Hearn Rd from Lon Hill to Sinton 69 kV Line | Lon Hill to Upriver 69 kV Hairpin into Hearn Road and Upgrade Lon Hill to Hearn Road section | IN-SERVICE | Lon Hill | Sinton | Under Construction | 399 - 0709 | AEP/TCC | Michael Glueck 918-599-2653 | 3279 | 2011-11-11 | 2011-11-11 | 69 | 0 | 0.25 | 0 | 0 | NUECES | NUECES | Tier 1 |  |  |  |  | Y | N
11TPIT0156 | Bandera Sub 138kv switches | Upgrade 138kv switches and bus |  | Bandera Sub | Bandera Sub | Complete |  | Bandera Electric | David Baker 830-796-6084 | 182768 | 2011-10-30 | 2011-11-11 | 138 | 0 | 0 | 0 | 0 | Bandera |  | Tier 4 | N/A | N/A | N/A |  | N | N |  | Necessary to utilize full rating of the 2-795 circuit
11TPIT0157 | Verde Creek Sub 138kv switches | Upgrade 138kv switches |  | Verde Creek Sub | Verde Creek Sub | Complete |  | Bandera Electric | David Baker 830-796-6084 | 182769 | 2011-10-30 | 2011-11-11 | 138 | 0 | 0 | 0 | 0 | Kerr |  | Tier 4 | N/A | N/A | N/A |  | N | N |  | Necessary to utilize full rating of the 2-795 circuit
11TPIT0138 | Deer Park Area Reconfigurations | Reconfigure Ckt. 84 SOUTH - WABURN and Ckt. 96 CONIAL - Morgan's Point to create new Ckt. 96 SOUTH - Morgan's Point and Ckt. 84 WABURN - CONIAL. | IN-SERVICE |  |  |  |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-11-30 | 2011-11-16 | 138 | 0 | 0 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 43250, 41670, 40370, 41100, 40442, 40443, 42241 | Y | N |  | No autotransformer capacity to be added and no transmission circuits to be built, rebuilt or reconductored.
12TPIT0024 | Kendall Autotransformer Replacement | Replace the existing 345/138 kV 336 MVA autotransformer with an 800 MVA autotransformer at the Kendall Substation (7152). | [5 empty] | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2012-06-01 | 2011-11-17 | 345 | 0 | 0 | 800 | 0 | KENDALL |  | CREZ |  |  |  | SEE PROJECT DESCRIPTION | Y | N |  | CREZ Default project assigned to LCRA TSC
10TPIT0064 | Parkway(7611) - Schertz(7610) Transmission Line | Replace existing 795 "Drake" circuit with 680T19 ACCR composite conductor, new line rating = 1491 amps | COMPLETED | Parkway | Schertz | Complete |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2011-11-17 | 2011-11-18 | 138 | 2.8 | 0 | 0 | 0 | GUADALUPE | GUADALUPE | Tier 4 |  |  |  | See Project Title | ? | ?
11TPIT0042 | Gila to Highway 9 138kV, Re-connect existing Highway 9 to Nueces Bay into Gila, | Expand Nueces Bay 138 kV system for interconnection of 700 MW of new generation | IN-SERVICE | Highway 9 | Gila | Planned | 399 - 0649 | AEP/TCC | Michael Glueck 918-599-2653 | 3255 | 2011-11-18 | 2011-11-18 | 138 | 0 | 3.29 | 0 | 0 | NUECES | NUECES | Tier 1 | 2009-03-17 | 2009-10-09 | 2009-12-01 |  | Y | N |  | Comment: Distribution banks converted to 138kV
11TPIT0058 | Paducah Clare to Paducah City, Rebuild 69 kV line | Rebuild 69 kV line from Matador to Paducah Clare to Paducah City as 69/138 kV double circuit capable with 795 ACSS | IN-SERVICE | Paducah Clare | Paducah City | In-Service | 454 - 0652 | AEP/ETT | Eric Scott 918-599-2653 | 2378 | 2011-11-22 | 2011-11-22 | 69 | 0 | 0.68 | 0 | 0 | COTTLE | COTTLE | Tier 4 | 2010-05-03 |  |  |  | Y | N
11TPIT0165 | Wirtz (7107) - Johnson City (7516) | Rebuild Johnson City 69kV bus to single bus, replacing switches (512 and 542) with breakers (22150 and 22160). Move T-313 from Wirtz breaker (1430) to Wirtz breaker (1690). Close loop Wirtz (1690)-Johnson City(22150)-Mountain Top (1990). |  | Wirtz | Johnson City |  |  | PEC | Randy Buchanan (830) 868-6058 |  | 2011-10-30 | 2011-11-23 | 69 | 0 | 0 | 0 | 0 | BURNET | Blanco | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
12TPIT0089 | Knox to Knox | Rebuild Knox to Knox 69 kV line with 795 ACSR |  | Knox | Knox | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10032 | 2011-12-07 | 2011-11-30 | 69 | 0 | 3.67 | 0 | 0 | HASKELL | KNOX | Tier 4 |  |  |  | 765, 6114 | Y | N
11TPIT0052 | Riley, Build a new Riley to Oklaunion 345 kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis | IN-SERVICE | Riley | Oklaunion | Under Construction | 467 - 0668 | AEP/ETT | Paul Hassink 918-599-2653 | 2351 | 2011-11-30 | 2011-11-30 | 345 | 3.5 | 0 | 0 | 0 | WILBARGER | WILBARGER | CREZ Modified |  |  |  |  | Y | N
12TPIT0076 | Oklaunion, Expand 345 kV switch station for the addition of the new Oklaunion to Riley circuit #2 | Build new Riley 345 kV switch station, cut in the existing and future 345 kV lines as described in ERCOT CREZ Scenario 2 | IN-SERVICE |  |  | Under Construction | 501 - 0708 | AEP/ETT | Paul Hassink 918-599-2653 | 2452 | 2011-11-30 | 2011-11-30 | 345 | 0 | 0 | 0 | 0 | WILBARGER |  | CREZ Modified |  |  |  |  | Y | N
08TPIT0133 | Rocksprings Station: Install 69 KV Ring Bus | Rocksprings : Install 5-69 KV Breaker Ring Bus and 3.6 MVAR Cap Bank | IN-SERVICE (Updated TPIT after it was posted - 2/16 | Rocksprings |  | Under Constuction | 377 - 0552 | AEP/ETT | Eric Scott 918-599-2653 | 3019 | 2011-12-01 | 2011-12-01 | 69 | 0 | 0 | 0 | 3.6 | EDWARDS |  | Tier 4 |  |  |  |  | N | N
11TPIT0110a | Alberta Switch-Valverde | Rebuild 4.05 Miles of 138kV line from Alberta Switch to Valverde Substation to AEP Weslaco Switch | Project Speedup due to delay with Alberta Switch-Doedyns | Alberta Switch | Valverde | Planned | 07TPIT7777 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-12-31 | 2011-12-01 | 138 | 0 | 4.05 | 0 | 0 | HIDALGO | HIDALGO | Tier 4 |  |  |  | 8759-8769-8354 | Y | N |  | Divided Project into two projects. Associated with Valverde to AEP Weslaco Switch
09TPIT0214 | Alberta Switch 138kV Substation | Build new 138kV Switching Station |  |  |  | Under Construction | 07TPIT7777 | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2011-12-01 | 2011-12-01 | 138 | 0 | 0 | 0 | 0 | HIDALGO | HIDALGO | Tier 4 |  |  |  | 8759 | Y | N
10TPIT0103 | Bowman Switch terminal equipment | Replace terminal equipment on line to Fisher Road. |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C032-WA | 2011-12-01 | 2011-12-01 | 345 | 0 | 0 | 0 | 0 | ARCHER |  | CREZ |  |  |  | 1422, 1425 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
10TPIT0104 | Bowman Switch terminal equipment | Replace terminal equipment on line to Graham. |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C070-WA | 2011-12-01 | 2011-12-01 | 345 | 0 | 0 | 0 | 0 | ARCHER |  | CREZ |  |  |  | 1422, 1430 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0061 | Bowman - Riley (Oklaunion) 345 kV line (Oncor Electric Delivery portion) | Construct double-circuit 345 kV line |  | Bowman | Riley | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C073-E | 2011-12-01 | 2011-12-01 | 345 | 85.2 | 0 | 0 | 0 | WILBARGER | ARCHER | CREZ |  |  |  | 1422, 6101 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0062 | Sweetwater East - Central Bluff 345 kV line | Construct double-circuit 345 kV line |  | Sweetwater East | Central Bluff | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C058-E | 2011-12-01 | 2011-12-01 | 345 | 71.6 | 0 | 0 | 0 | NOLAN | NOLAN | CREZ |  |  |  | 11420, 11406 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0063 | Central Bluff Switch | Construct 345 kV switching station with 345/138 kV autotransformer |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C074-E | 2011-12-01 | 2011-12-01 | 345 | 0 | 0 | 1200 | -150 | NOLAN |  | CREZ |  |  |  | 11406 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0064 | Central Bluff - Bluff Creek 345 kV line | Construct double-circuit 345 kV line with one circuit |  | Central Bluff | Bluff Creek | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C075-E | 2011-12-01 | 2011-12-01 | 345 | 19 | 0 | 0 | 0 | NOLAN | TAYLOR | CREZ |  |  |  | 11406, 60040 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0070 | Dermott Switch (Central B) - Scurry County South Switch (Central A) 345 kV line | Construct double-circuit 345 kV line |  | Dermott Switch | Scurry County South Switch | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C1009-E | 2011-12-01 | 2011-12-01 | 345 | 65.4 | 0 | 0 | 0 | SCURRY | SCURRY | CREZ |  |  |  | 11305, 11318 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0098 | Bowman Switch | Rebuild switching station |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C009-E | 2011-12-01 | 2011-12-01 | 345 | 0 | 0 | 0 | 0 | ARCHER |  | CREZ |  |  |  | 1422 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0176 | TH Wharton - TH Wharton (tap) Ckt. 81 | Upgrade substation equipment at TH Wharton to increase thermal ratings. | IN-SERVICE |  |  | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-12-31 | 2011-12-03 | 138 | 0 | 0 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 45515, 45511 | Y | N
11TPIT0168 | Elroy | Add Elroy station (7209) to LCRA TSC's Colton (7208) to Wolf Lane (7212) 138 kV transmission line. |  | Elroy | Colton/Wolf Lane | Planned |  | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2012-03-01 | 2011-12-09 | 138 | 0 | 0 | 0 | 0 | TRAVIS |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
12TPIT0069 | Barney Davis to Alazan 138 kV line rebuild | Barney Davis to Nelson Sharpe 138 kV line rebuild 1st circuit on a double circuit capable structure | IN-SERVICE | Barney Davis | Alazan | Under Construction | 400 - 0647 | AEP/ETT/TCC | Michael Glueck 918-599-2653 | 3332 | 2011-12-09 | 2011-12-09 | 138 | 0 | 12.24 | 0 | 0 | NUECES | NUECES | Tier 1 |  |  |  |  | Y | N
12TPIT0032 | Fort Mason to Pitsburg | Rebuild and convert the capacity of the existing transmission line (approximately 31 miles) between the LCRA TSC Fort Mason (76390) and Pitsburg (7120) stations. The new transmission line will consist of 1x795 ACSR Drake conductor to provide a thermal rating of 220 MVA. |  | Fort Mason | Pitsburg | Under construction |  | LCRA TSC | Brad Woods (512) 369-4104 brad.woods@lcra.org |  | 2011-12-01 | 2011-12-14 | 138 | 0 | 31 | 0 | 0 | MASON | LLANO | CREZ |  |  |  | SEE PROJECT DESCRIPTION | Y | N
11TPIT0155 | Pearsall Capacitor Bank | Install 60 MVAR Capacitor and a new 138 kV circuit breaker at the Pearsall Substation. Replace Existing Substation Equipment at Pearsall to remove MLSE on the Leon Creek to Pearsall and the Medina Base to Pearsall 138kV transmission lines. | [5 empty] | CPS | S: Juan Salinas | S-0605 | 2011-12-15 | 2011-12-15 | 138 | 0 | 0 | 0 | 60 | BEXAR | BEXAR | Tier 4 |  |  |  | 5335 5260 5305 | Y | N |  | There are no transformers associated with this project
11TPIT0144 | Rough Canyon to Hamilton Road, Rebuild 69 kV as 138 kV, energize at 69 kV | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE | Rough Canyon | Hamilton Road | Planned | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2440 | 2011-12-20 | 2011-12-20 | 69 | 0 | 12.4 | 0 | 0 | VALVERDE | VALVERDE | CREZ Modified |  |  |  |  | Y | N
12TPIT0117 | Temple Switch shunt reactors | Install shunt reactors 345/138 kV autotransformer tertiary |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R756-WAC | 2011-12-01 | 2011-12-28 | 138 | 0 | 0 | 0 | -37.5 | BELL |  | Tier 4 |  |  |  | 3415 | Y | N
11TPIT0060 | Lamesa - Ackerly Vealmoor 69 kV line | Rebuild existing 69 kV line |  | Lamesa | Ackerly Vealmoor | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8005-WAC | 2011-12-01 | 2011-12-29 | 69 | 0 | 21.5 | 0 | 0 | DAWSON | HOWARD | Tier 4 |  |  | 2009-07-21 | 1164, 1364, 1362, 1363, 1356 | Y | N | 2009-R3 | ERCOT BOD approved this project as part of the RMR exit strategy for Permian Basin generation. Ackerly Vealmoor - Sparenburg section was completed in 5/2011, and Sparenburg - Lamesa section will be completed in 12/2011.
10TPIT0090 | Copperas Cove - Killeen Clark Road Tap - Killeen Fort Hood West 138 kV line upgrade | Upgrade existing 138 kV line |  | Copperas Cove | Killeen Fort Hood West | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R717-WAC | 2011-12-01 | 2011-12-29 | 138 | 0 | 5 | 0 | 0 | CORYELL | BELL | Tier 4 |  |  |  | 3630, 3620, 3629 | Y | N
12TPIT0122 | Killeen Switch Shunt Reactors | Install shunt reactors on the tertiary of the 345/138 kV autotransformer |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R757-WAC | 2012-01-01 | 2011-12-29 | 138 | 0 | 0 | 0 | -75.0 | BELL |  | Tier 4 |  |  |  | 3423 | Y | N
12TPIT0091 | Garvey Road 345 kV Switching Station | Construct new switching station |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R905-WAC | 2011-12-01 | 2011-12-29 | 345 | 0 | 0 | 0 | 0 | ARCHER | ARCHER | Tier 4 |  |  |  | 1702 | Y | N
10TPIT0037 | Bell County East - TNP One 345 kV line and Bell County East Switching Station (Oncor Electric Delivery part of project) | Install 345 kV switching station and construct a double-circuit 345 kV line |  | Bell County East | TNP One | Completed | R704A, R705 | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R494-WAC | 2011-12-01 | 2011-12-30 | 345 | 82.6 | 0 | 0 | 0 | ROBERTSON | BELL | Tier 1 | 2006-11-30 |  | 2007-07-01 | 39950, 3687 | Y | N |  | Bell County East Switching Station was completed in 5/2011.
11TPIT0175 | Rocksprings - PEC Rocksprings: Constrcut 69 kV line | Rocksprings : Install 5-69 KV Breaker Ring Bus and 3.6 MVAR Cap Bank | IN-SERVICE (Updated TPIT after it was posted - 2/16 | Rocksprings | PEC Rocksprings | Under Construction | 377 - 0552 | AEP/ETT | Eric Scott 918-599-2653 | 3203 | 2011-12-31 | 2011-12-31 | 69 | 0 | 0 | 0 | 0 | EDWARDS | EDWARDS | Tier 4 |  |  |  |  | Y | N
09TPIT0031 | Circuit 972 (McNeil to Howard Lane) Reconductor | Reconductor the last span of the Ckt 972 (McNeil to Howard Lane) going into McNeil substation with bundled 795 ACSR Drake conductor. | COMPLETE | McNeil Substation | Howard Lane Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P085 | 2012-01-01 | 2012-01-01 | 138 | 0 | 0.1 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9079, 9217 | Y | N
11TPIT0158 | Mason Creek Sub 138kv breakers | Add 138kv breakers |  | Mason Creek Sub | Mason Creek Sub | Complete |  | Bandera Electric | David Baker 830-796-6084 | 201491 | 2011-12-01 | 2012-01-12 | 138 | 0 | 0 | 0 | 0 | Bandera |  | Tier 4 | N/A | N/A | N/A |  | N | N |  | System reliability & Maintenance
10TPIT0088 | Ft. Lancaster to Illinois #4, Convert 69 KV to 138 kV | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE | Ft. Lancaster | Illinois #4 | Planned | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2363 | 2012-01-19 | 2012-01-19 | 138 | 0 | 17.21 | 0 | 0 | PECOS | CROCKETT | CREZ Modified |  |  |  |  | Y | N
10TPIT0089 | Illinois #4 to Hamilton Rd., Convert 69 kV to 138 kV | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE | Illinois #4 | Hamilton Road | Planned | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2364 | 2012-01-19 | 2012-01-19 | 138 | 0 | 97.63 | 0 | 0 | CROCKETT | VALVERDE | CREZ Modified |  |  |  |  | Y | Y
12TPIT0064 | Rough Canyon, Convert station to 138 kV | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE |  |  | Planned | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2433 | 2012-01-19 | 2012-01-19 | 138 | 0 | 0 | 0 | 0 | VALVERDE |  | CREZ Modified |  |  |  |  | Y | N
12TPIT0065 | Comstock, Convert station to 138 kV | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE |  |  | Planned | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2401 | 2012-01-19 | 2012-01-19 | 138 | 0 | 0 | 0 | 0 | VALVERDE |  | CREZ Modified |  |  |  |  | Y | N
12TPIT0034 | Illinois #4, Build new three breaker ring bus & add 138/69 kV auto | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE | Illinois #4 |  | Under Construction | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2365 | 2012-01-19 | 2012-01-19 | 138 | 0 | 0 | 83 | 0 | CROCKETT |  | CREZ Modified |  |  |  |  | Y | N
10TPIT0039 | East Bell County - TNP One 345 kV Line Project | Expansion of 345 kV Switchyard at TNP One associated with East Bell County TNP One 345 kV Line Project |  | TNP One | TNP One | Completed | 10TPIT0037 | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com |  | 2011-12-11 | 2012-01-20 | 345 | 0 | 0 | 0 | 0 | ROBERTSON | ROBERTSON | Tier 4 | 2006-11-30 | 2007-01-02 |  | 39950 | Y | N | See Oncor Electric Delivery Entry for this project, 10TPIT0037
11TPIT0154 | Montell: Construct 69 kV Substation Including Motor Operated Switches with Interrupters | Add new 69 kV Montell Substation for STEC distribution interconnection | IN-SERVICE |  |  | Under Constuction | 498 - 0703 | AEP/TCC | Kenneth 'Rich' Haley 918-599-2653 | 3419 | 2012-01-23 | 2012-01-23 | 69 | 0 | 0 | 0 | 0.0 | UVALDE |  | Tier 4 |  |  |  | 8230 | N | N
11TPIT0089 | Cottonwood Road 69 kV Switch | Construct new switching station |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R588-WAC | 2011-12-01 | 2012-01-30 | 69 | 0 | 0 | 0 | 0 | ARCHER |  | Tier 4 |  |  |  | 1605 | Y | N
09TPIT0054 | LA Heights - 138kV Breaker Installations | Install line breakers between LA Heights bus A & B. | Delayed due to Budget Constraints |  |  |  | T-0156 | CPS | PM: Bruce Raney | S-0308 | 2012-02-01 | 2012-02-01 | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5285 5286 | Y | N |  | This is a line terminal addition, there are no additional tranformer capacity or transmission circuit miles associated with this project
11TPIT0164 | McNeil 138kV Bus Upgrade | Upgrade the pin cap and bus support insulators for fault duty requirements. A minor topology change will be made within the station. | COMPLETE | McNeil Substation | McNeil Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | 1461 | 2012-03-01 | 2012-02-01 | 138 | 0 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9076, 9077, 9079 | N | N
14TPIT0018 | Upgrade North Alvin-Hastings | This project will rebuild North Alvin to Hastings transmission line |  | North Alvin | Hastings | Completed |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | STE07113 | 2012-05-31 | 2012-02-01 | 138 | 0 | 1.93 | 0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 39010, 39015 | Y | N
12TPIT0095a | South Lane - West Columbia Ckts. 04 & 60 | Upgrade 138kV Ckt.60 South Lane - TXGULF to increase thermal ratings. | IN-SERVICE | South Lane | TXGULF | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2011-07-31 | 2012-02-03 | 138 | 0 | 10.52 | 0 | 0 | WHARTON | WHARTON | Tier 3 | 2011-02-02 | 2011-02-24 | N/A | 43190, 43012, 43340 | Y | N |  | Project is part of the 2011 ERCOT 5-Year Plan.
11TPIT0086 | Bruni 138kV Station: Install breaker | Construct new 138kV La Quinta Substation to directly interconnect 150MW Cedro Hill Wind Farm | IN-SERVICE |  |  | Under Constuction | 398 - 0587 | AEP/TCC | Tommy Vannoy 918-599-2653 | 3354 | 2012-02-06 | 2012-02-06 | 138 | 0 | 0 | 0 | 0 | WEBB | WEBB | Tier 4 |  |  |  |  | Y | N
11TPIT0140 | Convert Kirby Substation into a double tap substation | Reconfigure Kirby substation. Kirby will loop through Ckt.37 (existing) and tap from Ckt.90 HOC to Garrott (new). | IN-SERVICE | Kirby | HO Clarke/ Garrott | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-06-30 | 2012-02-08 | 138 | 0 | 0 | 0 | 0 | HARRIS | HARRIS | Tier 4 |  |  |  | 47320, 47321, 47322 | Y | N |  | No autotransformer capacity to be added.
11TPIT0041 | Gila 138kV: Construct new 138 kV, 6 breaker Ring Bus | Expand Nueces Bay 138 kV system for interconnection of 700 MW of new generation | IN-SERVICE |  |  | Under Construction | 399 - 0650 | AEP/ETT/TCC | Michael Glueck 918-599-2653 | 3242 | 2012-02-10 | 2012-02-10 | 138 | 0 | 0 | 0 | 57.6 | NUECES |  | Tier 1 | 2009-03-16 | 2009-10-09 | 2009-12-01 |  | Y | N
08TPIT0092 | North Victoria to Victoria: Reconductor 69 kV Line | Reconductor Victoria to North Victoria and North Victoria to Magruder 69 kV line to 1590 ACSR. Install 138/69 kV, 187 MVA, autotransformer at Magruder on the Victoria to Thomaston 138kV line. | IN-SERVICE | North Victoria | Victoria Power Plant | Planned | 389 - 0567 | AEP/TCC | Dave Goetz 918-599-2653 | 15 | 2012-02-15 | 2012-02-15 | 69 | 0 | 3.1 | 0 | 0 | VICTORIA | VICTORIA | Tier 4 |  |  |  |  | Y | N
12TPIT0086 | Hamilton Road, expand station | Rebuild 69 kV line from Ft. Lancaster to Hamilton Rd. with 795 ACSS, double circuit capable as alternative to CREZ project of rebuilding Sonora to Hamilton 138 kV line | IN-SERVICE |  |  | Under Construction | 474 - 0676 | AEP/ETT | Larry Roberson 918-599-2653 | 2368 | 2012-02-16 | 2012-02-16 | 138 | 0 | 0 | 0 | 0 | VALVERDE |  | CREZ Modified |  |  |  |  | Y | N
05TPIT0079 | Port Aransas: add 3 breaker 69 kv bus and 1-14.4 MVAR 69 kV cap bank | Add 3 breaker 69 kV ring bus on high side and install 1-14.4 MVAR capacitor bank at Port Aransas substation | IN-SERVICE |  |  | Under Construction | 029 - 0123 | AEP/TCC/ETT/LCRA | Michael Glueck 918-599-2653 | 1136 | 2012-02-17 | 2012-02-17 | 69 | 0 | 0 | 0 | 14.4 | ARANSAS |  | Tier 4 |  |  |  |  | Y | N
10TPIT0045 | Mauermann Rd - New 138kV Substation | Loop new 138kV substation into the existing VH Braunig to Toyota line | Delayed due to resource allocation | VH Braunig | Toyota | Planned | T-0087 | CPS | PM: Hector Torres | S-0399 | 2012-02-28 | 2012-02-22 | 138 | 0.1 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5297 | Y | N |  | There are no transformers associated with this project
12TPIT0105 | Elroy 138kV Unit Transformer | Establish one 30MVA unit transformer at the LCRA owned 138kV Elroy substation | COMPLETE | Elroy Substation | Elroy Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | 3230_117_2943 3230_117_4943 | 2012-01-01 | 2012-02-23 | 138 | 0 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9198 | Y | N |  | Will add to the base case in this TPIT updates.
11TPIT0167 | Lyssy: Construct 138 kV Facilities | Construct Lyssy 138 kV Substation |  | Kenedy Switch Station | Pleasanton | Planned | 497 - 0702 | AEP/TCC/ STEC | Kenneth Haley 918-599-2653 | 3413 | 2012-02-28 | 2012-02-28 | 138 | 0 | 0 | 0 | 0 | KARNES |  | Tier 4 |  |  |  | 8193 | Y | N
12TPIT0101 | Knippa 69 kV Substation Upgrade | Construct Uvalde to CPS Castroville 138 kV line with 2x795 ACSR utilizing open circuit for existing 69kV circuits in ROW | IN-SERVICE | Uvalde | Sabinal | Under Constuction | 291 - 0046 | AEP/TCC | Terry Weeks (AEP) 918-599-2653 | 1523 | 2012-02-29 | 2012-02-29 | 69 | 0 | 0 | 0 | 0 | UVALDE | MEDINA | Tier 1 |  |  |  |  | Y | N
12TPIT0063 | Rebuild Heights-Lamarque 69kV line | This project will rebuild the 69 kV path from Heights to LaMarque. This includes lines 69-H1, 69-H2, and 69-J. Total length of line is approximately 2.8 miles. This project also will add to the system hardening efforts taken after Hurricane Ike in September of 2008. |  | Heights | LaMarque | Completed |  | TNMP | Rex McDaniel, 409-948-8451, Rex.McDaniel@tnmp.com | STE07610 | 2012-03-01 | 2012-03-01 | 69 | 0 | 2.8 | 0 | 0 | GALVESTON | GALVESTON | Tier 4 |  |  |  | 38770, 39280, 39310, 39340 | N | N
06TPIT0112 | Lakeway second circuit from LCRA tap to the substation. | Construct 0.88 mile long 138kV circuit from Lakeway substation to the LCRA tap between Marshall Ford and Bee Creek substation. | COMPLETE | Lakeway Substation | Lakeway Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | 3230_117_4255 | 2012-03-01 | 2012-03-01 | 138 | 0.88 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 7349, 9235 | Y | N
10TPIT0122 | Formosa: Interconnect New Generation at Formosa Substation | Interconnect Generation at Formosa Substation | IN-SERVICE | Formosa |  | Planned | 437 - 0645 | AEP/TCC | Dave Goetz 918-599-2653 | 3333 | 2012-03-01 | 2012-03-01 | 138 | 0 | 0 | 0 | 0 | CALHOUN | CALHOUN | Tier 4 |  |  |  |  | Y | N |  | Project schedule date delayed based on customer's input.
10TPIT0018 | Austin Ranch - Colony 138 kV line | Upgrade existing 138 kV line |  | Austin Ranch | Colony | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3004-WAC | 2012-05-01 | 2012-03-01 | 138 | 0 | 4.6 | 0 | 0 | DENTON | COLLIN | Tier 4 |  |  |  | 2518, 2378, 12518 | Y | N | 2009-R16
11TPIT0129 | Pilot Grove - New Substation | Construct a new 138-26.18KV, 40 MVA x two, redundant backup substation | COMPLETED | Pilot Grove | Sweet Home/Yoakum | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2012-03-06 | 2012-03-06 | 138 | 0 | 0 | 0 | 0 | LAVACA |  | Tier 4 |  |  |  | See Project Title | Y | N
12TPIT0133 | PH Robinson Autotransformer A3 | Install temporary 600MVA Autotransformer A3 at PH Robinson | IN-SERVICE |  |  | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-03-31 | 2012-03-18 | 345/138 | 0 | 0 | 600 | 0 | GALVESTON |  | Tier 4 |  |  |  | 42000, 42010, 49049 | Y | N |  | EPRI sponsored autotransformer project
10TPIT0011 | Olney to Lake Kemp Switch Rebuild | Rebuild existing Olney to Lake Kemp Switch 69kv line |  | Olney | Lake Kemp Switch | planned |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 05007 | 2012-03-20 | 2012-03-21 | 69 | 0 | 29 | 0 | 0 | YOUNG | BAYLOR | Tier 3 | 2011-11-11 | 2011-12-27 | N/A | 788781784782 | Y | N
11TPIT0096 | Elm Mott Switch circuit breaker | Install 345 kV circuit breaker on line to Tradinghouse |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R737-WAC | 2012-05-01 | 2012-04-01 | 345 | 0 | 0 | 0 | 0 | MCLENNAN |  | Tier 4 |  |  |  | 3406 | Y | N
11TPIT0072b | Garrott - Midtown - Polk Ckt. 90 | Upgrade 138 kV underground Ckt. 90 Midtown to Polk by building additional underground cable parallel to existing cable. | IN-SERVICE | Midtown | Polk | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-04-30 | 2012-04-03 | 138 | 0 | 1.04 | 0 | 0 | HARRIS | HARRIS | Tier 3 | 2009-07-01 | 2009-07-01 | N/A | 47705, 47730 | Y | N | See project 11TPIT0072a for total project cost estimate | No transformer capacity to be added.
12TPIT0103 | Las Pulgas: Construct 138 kV Tap Station for WF Interconnect | Construct a 138 kV tap substation for the Magic Valley WF Interconnect, cut the Raymondville to Rio Hondo 138 kV line into the tap station | *Added "Terminal From" information *IN-SERVICE *Updated Cost & Sched | Las Pulgas |  | INSV | 490 - 0691 | AEP/TCC | Teresa Trotman 918-599-2653 | 3371 | 2012-04-30 | 2012-04-10 | 138 | 0 | 0 | 0 | 0 | WILLACY |  | Tier 4 |  |  |  | 80309 | Y | N
12TPIT0116 | Scarsdale 138kV Substation | Build new 138kV Scarsdale customer-owned substation. Loop through Ckt.92 PH Robinson to Garden Villas. | IN-SERVICE | Scarscale | El Dorado/ South Houston | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-04-30 | 2012-04-20 | 138 | 0.9 | 0 | 0 | 0 | HARRIS |  | Tier 4 |  |  |  | 43610, 42652, 43173 | Y | N
10TPIT0084 | Magruder: Add 1-14.4 MVAR 69 kV Cap Bank | Add capacitors in Victoria area at the McGruder Victoria plant and Lone Tree | IN-SERVICE | Magruder |  | Planned | 389 - 0667 | AEP/ETT | Dave Goetz 918-599-2653 | 3374 | 2012-05-31 | 2012-04-23 | 69 | 0 | 0 | 0 | 14.4 | VICTORIA |  | Tier 4 | 0 | 0 |  |  | Y | N
06TPIT0057 | Magruder: Add 138/69 kV, 187 MVA, auto, 3 breaker 138 kV ringbus, 1 69 kV lowside breaker | Reconductor Victoria to North Victoria and North Victoria to Magruder 69 kV line to 1590 ACSR. Install 138/69 kV, 187 MVA, autotransformer at Magruder on the Victoria to Thomaston 138kV line. | IN-SERVICE | Magruder |  | Planned | 389 - 0567 | AEP/ETT/TCC | Dave Goetz 918-599-2653 | 3375 | 2012-05-31 | 2012-04-23 | 138 | 0 | 0 | 187 | 0 | VICTORIA |  | Tier 4 |  |  |  |  | Y | N
11TPIT0072a | Garrott - Midtown - Polk Ckt. 90 | Upgrade 138 kV underground Ckt. 90 Garrott to Midtown by building additional underground cable parallel to existing cable. | IN-SERVICE | Garrott | Midtown | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-04-30 | 2012-04-26 | 138 | 0 | 1.47 | 0 | 0 | HARRIS | HARRIS | Tier 3 | 2009-07-01 | 2009-07-01 | N/A | 47660, 47705 | Y | N |  | No transformer capacity to be added.
11TPIT0057 | Matador to Paducah Clare, Rebuild 69 kV line | Rebuild 69 kV line from Matador to Paducah Clare to Paducah City as 69/138 kV double circuit capable with 795 ACSS | IN-SERVICE | Matador | Paducah Clare | Under Construction | 454 - 0652 | AEP/ETT | Eric Scott 918-599-2653 | 2328 | 2012-04-30 | 2012-04-30 | 69 | 0 | 31.2 | 0 | 0 | MOTLEY | COTTLE | Tier 3 | 2010-05-01 | 2010-06-01 | N/A |  | Y | N
12TPIT0047a | Zenith - Kluge and Zenith - Addicks: Reconfigure and Upgrade Circuits 09, 21, & 76. | Reconfigure circuits to form Zenith to Gertie tap to Cy Fair tap to Kluge Ckt.09. | IN-SERVICE | ZENITH | KLUGE | COMPLETE | 12TPIT0046 | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-05-31 | 2012-04-30 | 138 | 0 | 0 | 0 | 0 | HARRIS | HARRIS | Tier 2 | 2009-02-06 | 2009-09-01 | N/A | 44910, 45801, 45711, 45952 | Y | N |  | Part of the 2012 Northwest Houston Reliability Project
12TPIT0047b | Zenith - Kluge and Zenith - Addicks: Reconfigure and Upgrade Circuits 09, 21, & 76. | Reconfigure circuits to form Zenith to Gertie tap to Satsuma tap to Addicks Ckt.76. Upgrade portion of Ckt.76 to increase thermal ratings. | IN-SERVICE | ZENITH | ADDICKS | COMPLETE | 12TPIT0046 | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-05-31 | 2012-04-30 | 138 | 0 | 1.49 | 0 | 0 | HARRIS | HARRIS | Tier 2 | 2009-02-06 | 2009-09-01 | N/A | 44910, 45802, 46302, 45610 | Y | N | Cost included in main project | Part of the 2012 Northwest Houston Reliability Project
12TPIT0047c | Zenith - Kluge and Zenith - Addicks: Reconfigure and Upgrade Circuits 09, 21, & 76. | Reconfigure circuits to form Camron to Cy Fair tap to Kluge Ckt.21. Upgrade portion of Ckt.21 to increase thermal ratings. | IN-SERVICE | CAMRON | KLUGE | COMPLETE | 12TPIT0046 | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-05-31 | 2012-04-30 | 138 | 0 | 4.62 | 0 | 0 | HARRIS | HARRIS | Tier 2 | 2009-02-06 | 2009-09-01 | N/A | 45700, 45712, 45952 | Y | N | Cost included in main project | Part of the 2012 Northwest Houston Reliability Project
12TPIT0166 | Aldine Cap Bank | Install 7.2MVAR capacitor bank at Aldine substation. | IN-SERVICE |  |  | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-05-31 | 2012-04-30 | 138 | 0 | 0 | 0 | 7.2 | HARRIS |  | Tier 4 |  |  |  | 45640 | Y | N
12TPIT0046 | Zenith 138kV | Expand Zenith substation with addition of 345/138kV 800MVA Autotransformer. Build a new 138kV double circuit line from Zenith to Gertie corner. | IN-SERVICE | ZENITH | Gertie | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-05-31 | 2012-04-30 | 345 | 10 | 0 | 800 | 0 | HARRIS | HARRIS | Tier 2 | 2009-02-06 | 2009-09-01 | N/A | 44900, 44910, 45801, 45802 | Y | N |  | Part of the 2012 Northwest Houston Reliability Project
08TPIT0034 | McNeil to Summit Reconductor | The proposal of adding the 2nd ckt from McNeil to Summit in not feasible due to right of way issues. New proposal calls for the upgrading of the original circuit to 3000Amp. | COMPLETE | McNeil Substation | Summit Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | PLAN_117_P351 PLAN_117_P372 PLAN_117_P373 | 2012-05-01 | 2012-05-01 | 138 | 2 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9079, 9279 | Y
10TPIT0024 | Stoney Ridge 138kV substation (original title is Linda Vista substation) | Establish new 138kV Stoney Ridge substation and install (2) 30MVA transformers. The substation will cut into Ckt 962 (Garfield to Onion Ck). | COMPLETE | Stoney Ridge Substation | Stoney Ridge Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | 3230_117_2894 3230_117_4894 | 2012-05-01 | 2012-05-01 | 138 | 0.1 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9237 | Y | N
09TPIT0120 | Sun Switch - Golden - Sacroc 138 kV line | Rebuild 138 kV line |  | Sun Switch | Sacroc | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R807-E | 2012-05-01 | 2012-05-01 | 138 | 0 | 12.8 | 0 | 0 | SCURRY | SCURRY | Tier 4 |  |  |  | 1064, 1067, 1311 | Y | N
12TPIT0118 | Elkton - Tyler Bullard Rd - S Tyler 138 kV line | Upgrade existing 138 kV line |  | Elkton | S Tyler | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R6008-WAC | 2012-05-01 | 2012-05-01 | 138 | 0 | 2.8 | 0 | 0 | SMITH | SMITH | Tier 4 |  |  |  | 3106, 3219,3218 | Y | N
12TPIT0161 | East Mesquite Switch terminal equipment | Upgrade terminal equipment at East Mesquite Switch in the East Mesquite Switch - Seagoville Switch 138 kV line |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4096A, B &C -WAC | 2012-05-01 | 2012-05-01 | 138 | 0 | 0 | 0 | 0 | DALLAS |  | Tier 4 |  |  |  | 2756 | Y | N
12TPIT0179 | Lake Hubbard capacitors | Install 138 kV capacitors |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4100-WAC | 2012-05-01 | 2012-05-01 | 138 | 0 | 0 | 0 | 36.8 | DALLAS |  | Tier 4 |  |  |  | 2401, 2402 | Y | N
12TPIT0207 | Handley - Hurst 138 kV line | Upgrade existing 138 kV line |  | Handley | Hurst | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2012-05-01 | 2012-05-01 | 138 | 0 | 18.7 | 0 | 0 | TARRANT | TARRANT | Tier 4 |  |  |  | 1950, 2110, 2109, 1951 | Y | N
10TPIT0109 | Burwick Switching Station | Construct new switching station to connect a new wind farm |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R583-WAC | 2012-05-01 | 2012-05-01 | 345 | 0 | 0 | 0 | 0 | JACK |  | Tier 4 |  |  |  | 1456 | Y | N
12TPIT0067 | Anna Switch 345/138 kV autotransformer replacement | Replace #1 autotransformer |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3085-WAC | 2012-05-01 | 2012-05-01 | 345 | 0 | 0 | 600 | 0 | COLLIN |  | Tier 4 |  |  |  | 2373, 2374 | Y | N
12TPIT0106 | Southeast Nacogdoches 345/138 kV autotransformer | Replace existing 345/138 kV autotransformer with larger autotransformer |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R6007-WAC | 2012-05-01 | 2012-05-01 | 345 | 0 | 0 | 600 | 0 | NACOGDOCHES |  | Tier 2 | 2010-11-01 | 2010-12-01 |  | 3119, 3120 | Y | N
07TPIT0251 | Victoria Power Plant: Install 1-28.8 MVAR 69 kV Cap Bank | Add capacitors in Victoria area at the McGruder Victoria plant and Lone Tree | IN-SERVICE | Victoria Power Plant |  | Planned | 389 - 0667 | AEP/TCC | Dave Goetz 918-599-2653 | 2243 | 2012-03-01 | 2012-05-04 | 69 | 0 | 0 | 0 | 28.8 | VICTORIA |  | Tier 4 |  |  |  |  | Y | N
12TPIT0173 | Austin to Kirby Rebuild - 138 kV Transmission Line | Remove the existing bifrucation line between Austin2 and Kirby2 and rebuild with a single 138 kV transmission line |  | Austin | Kirby |  |  | CPS | T: Adam Marin | T-0182 | 2012-05-04 | 2012-05-04 | 138 | 0 | 2.75 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5005 5006 5249 5250 | Y | N |  | There are no transformers associated with this project
09TPIT0132 | Bonnie Brae Substation Construction | Construct new 50MVA, 69kV to 13.2kV substation adjacent to DME's 69kV Hickory to North Lakes transmission line 1/4 mile south of US 380 | On schedule |  |  | Complete | 07TPIT0097 | DENTON | Chuck Sears, (940) 349-7111, cxsears@cityofdenton.com | 602099 | 2012-05-15 | 2012-05-12 | 69 | 0 | 0 | 0 | 0 | DENTON | DENTON | Tier 4 |  |  | NA | 905 | Y | N
12TPIT0163 | Line Ratings Project - Ball Park to Deely and Deely to Laredo - 138kV substation equipment upgrade | Upgrade substation equipment at Deely and Laredo to remove existing MLSE on the Deely to Laredo and the Ball Park to Laredo 138kV line |  | Deely | Ball Park/Laredo |  |  | CPS | Blake Williams | S-0700 | 2012-05-31 | 2012-05-17 | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5011 5110 | Y | N |  | There are no transformers associated with this project
12TPIT0177 | Wirtz Autotransformer Replacement | Replace the existing T-1 autotransformer (comprised of three single phase units) at the Wirtz Substation with a three phase 40 MVA 138/69-kV autotransformer (7104 - 7107 -7110) | [5 empty] | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2012-06-01 | 2012-05-18 | 138 | 0 | 0 | 40 | 0 | BURNET |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
10TPIT0079 | Morris Sheppard to Oran Rebuild | Rebuild Morris Sheppard to Oran with 959ACSS | row issues | Morris Sheppard | Oran | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 07018 | 2012-05-15 | 2012-05-21 | 69 | 0 | 18.4 | 0 | 0 | PALO PINTO | PALO PINTO | Tier 4 |  |  |  | 343785 | Y | N
12TPIT0096 | Pearsall auto upgrade | Upgrade the 50 MVA138/69 kV autotransformer. |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-10-01 | 2012-05-21 | 138 | 0 | 0 | 200 | 0 | FRIO |  | Tier 4 |  |  |  | 5893, 5895 | Y | N
12TPIT0113 | Mont - New Substation | Construct a new 138-26.18KV, 12/16/20 MVA on LCRA Hallettsville to Sweet Home 138 Transmission line | COMPLETED | Mont | Hallestville/Sweet Home | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2012-05-31 | 2012-05-31 | 138 | 0 | 0 | 0 | 0 | LAVACA |  | Tier 4 |  |  |  | See Project Title | N | N
12TPIT0018 | Bonham Switch 69 kV capacitors | Install 69 kV capacitors | Construction delays |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R556-WAC | 2012-06-18 | 2012-06-01 | 69 | 0 | 0 | 0.0 | 18.4 | FANNIN |  | Tier 4 |  |  |  | 1761 | Y | N
12TPIT0120 | Seymour 69 kV capacitors | Install 69 kV capacitors | Construction delays |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R599-WAC | 2012-06-27 | 2012-06-01 | 69 | 0 | 0 | 0.0 | 9.2 | BAYLOR |  | Tier 4 |  |  |  | 1532 | Y | N
12TPIT0125 | Westside MLSE Upgrade - 138 kV Substation Equipment Upgrade | Replace Existing Substation Equipment at Westside to remove MLSE on the Cagnon to Westside and SWRI to Westside 138kV transmission line |  | Cagnon | Westside |  |  | CPS | Blake Williams | S-0524 | 2012-06-01 | 2012-06-01 | 138 | 0 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5490 5419 5310 5150 5054 | Y | N |  | There are no transformers associated with this project
13TPIT0068 | Reconfigure Helotes to Bandera - 138kV Circuit | Reconfigure Helotes - Bandera to Helotes - Grissom 138 kV circuit |  | Helotes | Grissom | Planned |  | CPS | Ballard, Cathleen | T-0203 | 2012-06-08 | 2012-06-01 | 138 | 0.5 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 2 |  |  |  | 5200 5020 5185 | Y | N |  | There are no transformers associated with this project
12TPIT0131 | DEPOT 138kV Substation | Construct service to new 138kV DEPOT customer-owned substation. Loop through Ckt.84 Channelview - Jacintoport | IN-SERVICE | DEPOT | Channelview/EPOTH | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-06-30 | 2012-06-01 | 138 | 0.1 | 0 | 0.0 | 0 | HARRIS |  | Tier 4 |  |  |  | 40410 | Y | N
12TPIT0072 | Ferguson to Wirtz | Upgrade the 4.0 mile Ferguson (7126) -Wirtz (7104) 138kV transmission lines to 1433.6 ACSS/TW (2000 Amps) |  | Ferguson | Wirtz | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2012-06-01 | 2012-06-01 | 138 | 0 | 4 | 0 | 0 | BURNET | LLANO | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
12TPIT0107 | AMD to Pedernales New Circuit | First part of the project is to merge Circuit 1014 (Burleson to Pedernales) and Circuit 1017 (AMD to Burleson) into single 138kV circuit bypassing Burleson sub. Second part of the project is to relocate the Ckt 923 termination to the MB2. | COMPLETE | AMD Substation | Pedernales Substation | Planned |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com |  | 2012-06-01 | 2012-06-01 | 138 | 0 | 0 | 0 | 0 | TRAVIS | TRAVIS | Tier 4 |  |  |  | 9151, 9118 | Y | N
10TPIT0032 | Arco (TMPA) - Krugerville 138 kV line | Rebuild existing 138 kV line | Construction delays | Arco (TMPA) | Krugerville | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M5129-WAC | 2012-06-29 | 2012-06-01 | 138 | 0 | 5.6 | 0.0 | 0 | DENTON | DENTON | Tier 4 |  |  | 2010-06-15 | 1994, 1993 | Y | N
11TPIT0031 | Celina SE 138 kV capacitors | Install 138 kV capacitors | Construction delays |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M3066-WAC | 2012-05-21 | 2012-06-01 | 138 | 0 | 0 | 0.0 | 110.4 | COLLIN |  | Tier 4 |  |  |  | 2350 | Y | N
12TPIT0193 | Graham Switch 138 kV series reactor | Install 9-ohm series reactor on line to Barton Switch |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R911-WAC | 2012-06-27 | 2012-06-01 | 138 | 0 | 0 | 0.0 | 0 | YOUNG |  | Tier 4 |  |  |  | 1596 | Y | N | 2007- E7d
08TPIT0107 | Leon - Flat Creek 138 kV line | Rebuild existing 138 kV line | Construction delays | Leon | Flat Creek | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R520A-E | 2012-06-28 | 2012-06-01 | 138 | 0 | 19.5 | 0.0 | 0 | EASTLAND | ERATH | Tier 4 |  |  |  | 1624, 1640 | Y | N
11TPIT0065 | Ector County North Switch (West B) - Moss 138 kV line | Construct 138 kV line with one circuit in place. |  | Ector County North Switch | Moss | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C043-E | 2012-06-01 | 2012-06-01 | 138 | 20.1 | 0 | 0.0 | 0 | ECTOR | ECTOR | CREZ |  |  |  | 11140, 1019 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0066 | Ector County North Switch (West B) | Construct 138 kV switching station |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C016-E | 2012-06-01 | 2012-06-01 | 138 | 0 | 0 | 0.0 | 0 | ECTOR |  | CREZ |  |  |  | 11140 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0100 | Moss Switch | Install 138 kV circuit breakers |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C005-E | 2012-06-01 | 2012-06-01 | 138 | 0 | 0 | 0.0 | 0 | ECTOR |  | CREZ |  |  |  | 1019 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
12TPIT0124 | Skyline to Marion - 345 kV Substation Equipment Upgrade | Replace Metering CT at Skyline and ensure a 1800 A rating and remove the existing MLSE on Skyline to Marion 345kV transmission line |  | Skyline | Marion |  |  | CPS | Blake Williams | S-0467 | 2012-06-01 | 2012-06-01 | 345 | 0 | 0 | 0 | 0 | BEXAR | GUADALUPE | Tier 4 |  |  |  | 5371 7044 | Y | N |  | There are no transformers associated with this project
12TPIT0043 | Bluff Creek - Brown 345 kV line | Construct double-circuit 345 kV line with one circuit |  | Bluff Creek | Brown | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C076-E | 2012-06-01 | 2012-06-01 | 345 | 86.1 | 0 | 0.0 | 0 | TAYLOR | BROWN | CREZ |  |  |  | 60040, 1444 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
12TPIT0044 | Central Bluff - Brown 345 kV line | Construct double-circuit 345 kV line with one circuit |  | Central Bluff | Brown | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C075-E & C076-E | 2012-06-01 | 2012-06-01 | 345 | 96.1 | 0 | 0.0 | 0 | NOLAN | BROWN | CREZ |  |  |  | 11406, 11425, 1444 | Y | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
11TPIT0047 | Twin Buttes - Brown 345 kV line (Oncor Electric Delivery section) | Add second 345 kV circuit |  | Twin Buttes | Brown | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C038-E | 2012-06-01 | 2012-06-01 | 345 | 0.2 | 0 | 0.0 | 0 | BROWN | BROWN | CREZ |  |  |  | 76009 | Y | N | 2007-E7f | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
12TPIT0045 | Brown Switch | Construct 345 kV switching station with shunt reactors |  |  |  | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | C022-E | 2012-06-01 | 2012-06-01 | 345 | 0 | 0 | 0.0 | -250 | BROWN |  | CREZ |  |  |  | 1444 | Y | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report.
10TPIT0041 | Temple Switch - Salado Switch 345 kV line | Upgrade existing 345 kV line |  | Temple Switch | Salado Switch | Completed | R494 | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R705-WAC | 2012-06-18 | 2012-06-01 | 345 | 0 | 15.2 | 0.0 | 0 | BELL | BELL | Tier 1 | 2006-11-01 |  | 2007-07-01 | 3414, 3699 | Y | N
12TPIT0144 | Rayburn to Nursery Rebuild | Rebuild 4/0 ACSR 69 kV to 795 ACSR. |  | Rayburn | Nursery | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-06-10 | 2012-06-10 | 69 | 0 | 3.4 | 0.0 | 0 | VICTORIA | VICTORIA | Tier 4 |  |  |  | 5500, 5504 | Y | N
12TPIT0127 | Barstow Oncor POI | Create Tap for Oncor's new Barstow station; install 10 MVAR Capacitor Bank |  |  |  | Completed |  | TNMP | Allen Aars, 972-420-4189,Allen.Aars@tnmp.com | NTE087AA | 2012-06-01 | 2012-06-11 | 69 | 0 | 0 | 0.0 | 10 | Ward |  | Tier 4 |  |  |  | 38150, 1086 | Y | N
10TPIT0051 | Alamito Creek to Gonzales, Replace existing 69kV line with new 69kV line | Replace Alamito Creek to Gonzales line with 795 ACSR | IN-SERVICE | Alamito Creek | Gonzales | Under Construction | 438 - 0701 | AEP/ETT | Jim Eriksen 918-599-2653 | 2170 | 2012-06-12 | 2012-06-12 | 69 | 60 | 0 | 0 | 0 | PRESIDIO | PRESIDIO | Tier 1 | 2008-03-21 | 2008-06-10 | 2008-07-15 |  | Y | N
12TPIT0146 | Bonnieview Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-06-15 | 2012-06-15 | 69 | 0 | 0 | 0.0 | 9.6 | REFUGIO |  | Tier 4 |  |  |  | 5614 | Y | N
12TPIT0155 | Kenedy Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-06-15 | 2012-06-15 | 69 | 0 | 0 | 0.0 | 9.6 | KARNES |  | Tier 4 | 2011-12-16 | 2012-04-25 | N/A | 5722 | Y | N
12TPIT0139 | Gonzales, add 3.0 Mvar reactor and add 69 kV line | Replace Alamito Creek to Gonzales line with 795 ACSR | IN-SERVICE | Gonzales | 0 | Under Construction | 438 - 0701 | AEP/ETT | Jim Eriksen 918-599-2653 | 2451 | 2012-06-15 | 2012-06-15 | 69 | 0 | 0 | 0 | -3 | PRESIDIO |  | Tier 4 |  |  |  |  | Y | N
11TPIT0115 | Reagor Springs to Purdon Rebuild | Rebuild existing Reagor Springs to Purdon 69 kV line to serve new load at Emmett. |  | Reagor Springs | Purdon | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 10020 | 2012-06-15 | 2012-06-18 | 69 | 0 | 28.55 | 0.0 | 0 | ELLIS | NAVARRO | Tier 4 |  |  |  | 204, 210, 193, 194, 198 | Y | N |  | Load-serving project, necessitated by a large load addition at Emmett.
10TPIT0086 | East Abilene to Putnam, Add 138 kV to existing 69 kV line | Build new 138 kV circuit from E. Abilene to Leon with 795 ACSS as alternative to CREZ project of upgrading Abilene S. to Leon 138 kV line | IN-SERVICE | East Abilene | Putnam | Planned | 466 - 0666 | AEP/ETT | Larry Roberson 918-599-2653 | 2346 | 2012-06-19 | 2012-06-19 | 138 | 0 | 32 | 0 | 0 | NUECES | CALLAHAN | CREZ Modified |  |  |  |  | Y | N
11TPIT0016 | GPLTemp-Shiloh 69kV line and Shiloh 138kV substation rebuild and install a 138 kV/69 kV autotransformer (75 MVA) | Line upgrade and substation rebuild with installing a 138 kV/69 kV autotransformer (75 MVA) at Shiloh substation |  |  |  | Completed |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2012-06-20 | 2012-06-20 | 69 | 0 | 2 | 75.0 | 0 | DALLAS |  | Tier 4 |  |  |  | 808, 830, 854 | Y | N
12TPIT0136 | STEC Sioux - El Gato: Construct 138 kV Line | Construct El Gato 138 kV partial ringbus substation and build a new 138 kV transmission line from STEC Sioux to El Gato | IN-SERVICE | El Gato | Sioux | Under Construction | 255 - 0488 | AEP/TCC/STEC | Frank Pritzlaff (AEP) 918-599-2653 | 1328 | 2012-06-20 | 2012-06-20 | 138 | 5.43 | 0 | 0 | 0 | HIDALGO | HIDALGO | Tier 2 | 2005-02-11 | 2005-04-20 | Unknown | 85005, 8792 | Y | N
12TPIT0114 | Lost Creek - New Substation | Construct a new 69/138-4.16-KV, 12/16/20 MVA x two, redundant backup substation | COMPLETED | Lost Creek | FM237/Cuero Hydro | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2012-06-15 | 2012-06-26 | 69 | 0 | 0 | 0.0 | 0 | DEWITT |  | Tier 4 |  |  |  | See Project Title | N | N
13TPIT0044 | Hill Country - Install Fourth 345/138 kV Autotransformer | Install 600 MVA autotransformer at Hill Country | [5 empty] | CPS | Blake Williams |  | 2012-06-28 | 2012-06-28 | 345 | 0 | 0 | 600.0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5211 5210 | Y | N |  | There is no transmission line additions associated with this project
12TPIT0082 | Hotwells - New 138kV Substation | Loop new 138kV substation into existing 138kV Ball Park to Deely line |  | Hotwells | Ball Park/Deely |  | T-0168 | CPS | PM: Hector Torres | S-0615 | 2012-06-29 | 2012-06-29 | 138 | 0.1 | 0 | 0.0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5227 5255 5110 | Y | N |  | There are no transformers associated with this project
14TPIT0013 | Norwood - East Levee 138 kV line | Upgrade existing line and retire a section of the West Dallas Tap - East Levee 138 kV line |  | Norwood | East Levee | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | M4073-WAC | 2012-06-01 | 2012-07-01 | 138 | 0 | 6.6 | 0.0 | 0 | DALLAS | DALLAS | Tier 4 |  |  |  | 2481, 2405 | Y | N
12TPIT0211 | Wink - Loving 138 kV line | Increase line rating |  | Wink | Loving | Completed |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com |  | 2012-07-01 | 2012-07-01 | 138 | 0 | 16.59 | 0 | 0 | WINKLER | LOING | Tier 4 |  |  |  | 1092, 1074 | Y | N
11TPIT0101 | Reno to Rhome Rebuild | Rebuild existing Reno to Rhome 138 kV Line |  | Reno | Rhome | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 09010 | 2012-10-14 | 2012-07-02 | 138 | 0 | 13.85 | 0.0 | 0 | PARKER | WISE | Tier 4 |  |  |  | 541, 572, 576 | Y | N
11TPIT0081 | Plastipak-Shiloh 138 kV line | Line upgrade |  | Switch 7512 at Plastipak | Switch 8702 at Shiloh | Completed |  | GARLAND | Danh Huynh, 972-205-3826,Dhuynh@garlandpower-light.org |  | 2012-07-11 | 2012-07-11 | 138 | 0 | 1.5 | 0.0 | 0 | DALLAS |  | Tier 4 |  |  |  | 808, 830 | Y | N
09TPIT0125 | East Abilene, Build new 138 kV switch station, terminate new 138 kV Putnam line | Build new 138 kV circuit from E. Abilene to Leon with 795 ACSS as alternative to CREZ project of upgrading Abilene S. to Leon 138 kV line | IN-SERVICE | East Abilene | 0 | Planned | 479 - 0681 | AEP/ETT | Larry Roberson 918-599-2653 | 2272 | 2012-07-12 | 2012-07-12 | 138 | 0 | 0 | 0 | 0 | EASTLAND |  | CREZ Modified |  |  |  |  | Y | N
13TPIT0014 | East Bridgeport Capacitor Bank | Install 15mvar capacitor bank at East Bridgeport |  | East Bridgeport |  | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 08053 | 2012-07-11 | 2012-07-13 | 138 | 0 | 0 | 0.0 | 15 | WISE |  | Tier 4 |  |  |  | 601 | Y | N
12TPIT0110 | Hollmig | Cut in the new Hollmig (7145) substation on the LCRA TSC Fredericksburg-Kendall 138 kV transmission line |  | Hollmig | Fredricksburg/Kendall | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2012-07-01 | 2012-07-17 | 138 | 0 | 0 | 0.0 | 0 | GILLESPIE |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N
07TPIT0042 | 2nd Lewisville Auto | Install (2nd) 345/138 kV autotransformer at Lewisville station |  | Lewisville |  | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 02032 | 2012-06-28 | 2012-07-17 | 345 | 0 | 0 | 700.0 | 0 | DENTON |  | Tier 4 |  |  |  | 646, 645 | Y | N | 2009-R17
12TPIT0134 | St Jo to Capps Corner | Install additional poles and modify existing structures to raise normal operating temperature to 75° C |  | St Jo | Capps Corner | under construction |  | BRAZOS | Brion Ryan, 254-750-6353, bryan@brazoselectric.com | 11035 | 2012-07-06 | 2012-07-18 | 138 | 0 | 8.6 | 0.0 | 0 | MONTAGUE | MONTAGUE | Tier 4 |  |  |  | 750, 754 | Y | N
12TPIT0154 | Tilden Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-07-01 | 2012-08-01 | 69 | 0 | 0 | 0.0 | 9.6 | MCMULLEN |  | Tier 4 |  |  |  | 5700 | Y | N
12TPIT0147 | Salt Dome Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-08-01 | 2012-08-01 | 69 | 0 | 0 | 0.0 | 9.6 | MATAGORDA |  | Tier 4 |  |  |  | 5551 | Y | N
12TPIT0151 | Hillje Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-12-01 | 2012-08-01 | 69 | 0 | 0 | 0.0 | 9.6 | WHARTON |  | Tier 4 |  |  |  | 5532 | Y | N
12TPIT0094 | De-energization of Crosby - Mont Belvieu Ckt. 43 | De-energize Ckt. 43 Crosby - Mont Belvieu. Remove autotransformers from Crosby and Mont Belvieu. Move Highlands tap from Ckt. 43 to Ckt. 66 Haney - Baytown. | IN-SERVICE | CROSBY | MONT BELVIEU | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@ CenterPoint Energy.com 713 207 2192 |  | 2012-07-31 | 2012-08-13 | 138 | 0 | 0 | -158.0 | 0 | HARRIS | CHAMBERS | Tier 4 |  |  |  | 40391, 49010, 40380, 40812, 41112, 49023, 41111 | Y | N
12TPIT0164 | Lindenau - New Substation | Construct a new 138-26.18KV, 18/24/30 MVA on LCRA Cheapside to Cuero Hydro 138 Transmission line |  | Lindenau | Cheapside/Cuero Hydro | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org Barry Kremling bkremling@GVEC.org 830-857-1200 |  | 2012-08-24 | 2012-08-24 | 138 | 0 | 0 | 0.0 | 0 | DEWITT |  | Tier 4 |  |  |  | See Project Title | Y | N
13TPIT0078 | Kendall Autotransformer Addition | Replace the existing 345-138 kV 478MVA autotransformer with an 672 MVA autotransformer at the Kendall substation (7150). | [5 empty] | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2012-08-01 | 2012-08-24 | 345 | 0 | 0 | 672.0 | 0 | KENDALL |  | CREZ |  |  |  | SEE PROJECT DESCRIPTION | Y | N |  | CREZ Default project assigned to LCRA TSC
12TPIT0206 | Dewitt County Capacitor Bank Additions | Install one 7.8 MVAr cap bank at the Lost Creek substation (78188) and one 7.8 MVAr cap bank at the Nordheim West substation (78576) |  |  |  | Planned |  | LCRA TSC | Brad Woods (512) 578-4104 brad.woods@lcra.org |  | 2012-08-31 | 2012-08-31 | 69 | 0 | 0 | 0.0 | 15.6 | DEWITT |  | Tier 4 |  |  |  | SEE PROJECT DESCRIPTION | Y | N

## CancelledTPIT09012012NoCost
SEPTEMBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) CANCELLED PROJECTS As Of 09/01/2012
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) (only in completed tab) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location of Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional)
09TPIT0011 | Cagnon to Hill Country - 345kV 2nd Circuit | Build second 345 kV line from Cagnon to Hill Country. The circuit will be installed on existing transmission structures |  | Cagnon | Hill Country | Conceptual |  | CPS | Blake Williams | T-0053 | 2020-06-01 |  | 345 | 19.5 | 0 | 0 | 0 | BEXAR | BEXAR | Tier 4 |  |  |  | 5056 5211 | N | N |  | There are no transformers associated with this project
12TPIT0150 | Ganado Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans 361-485-6459 devans@stec.org |  | 2012-12-01 |  | 69 | 0 | 0 | 0.0 | 9.6 | JACKSON |  | Tier 4 |  |  |  | 5526 | Y | N
12TPIT0197 | Eiland Temporary Substation | Install temporary substation to serve new and existing load until permenant substation is constructed 2013 | New | Oncor Spraberry Switch Yard | Oncor Morgan Creek Switch Yard | Planned |  | SU | Dwight Yarbrough (956) 279-6902 dyarbrough@sharyland.com |  | 2012-08-01 |  | 138 | 0 | 0 | 0 | 0 | GLASSCOCK |  | Tier 4 |  |  | n/a |  | N | N
08TPIT0044 | Circuit 1013 Double Breaker at Decker Power Plant | Install one 138 kV, 3000 Amp, 63 kA circuit breaker and two switches to connect Ckt 1013 (Decker to McNeil) to the Decker MB2 Bus. | CANCELLED This project will not be in the PSSE base cases. |  |  |  |  | AUSTIN ENERGY | Biju Mathew (512) 322-6737 Biju.Mathew@austinenergy.com | [8 empty] | TRAVIS | TRAVIS
12TPIT0191 | Rojo Springs: Build new Tap | Interconnect Baker Ranch Wind Farm at Rojo Springs to connect Baker Ranch to the Mulberry Creek to Oklaunion 345 kV line | CANCELLED | Mulberry Creek | Oklaunion | Planned | 408 - 0597 | AEP/ETT | Paul Hassink 918-599-2655 | 2453 | 2012-12-31 |  | 345 | 0 | 0 | 0 | 0 | HASKELL | 0 | Tier 4 | 0 | 0 | 0 | 0 | Y | N | 0 | 0
14TPIT0087 | Ector County North Switch expansion | Connect Moss - Amoco North Cowden Tap - Holt Switch 138 kV line into Ector County North Switch |  |  |  | Conceptual |  | Oncor Electric Delivery | Michael Juricek, 214.743.6671, Michael.Juricek@oncor.com | R8065A-E | 2014-11-01 |  | 138 | 0.5 | 0 | 0 | 0 | ECTOR |  | Tier 4 |  |  |  | 11140 | Y | N

## TPIT5YearPlanProjects
Project Number | Project Name | Proposed in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2011-R1 | IH20 – Pecos– Lone Star Tap terminal equipment upgrades | 2012 |  |  | These upgrades are system protection equipment adjustments that are planned to be completed by the end of year 2012. | Planning Stage
2011-R2 | Odessa Area 138 kV line upgrades | 2016 | Planning Stage | 13TPIT0153 | Oncor Electric Delivery project | In RPG Process
2011-R3 | San Angelo Concho 138/69 kV autotransformer upgrade | 2014 | Conceptual | 14TPIT0065 |  | Canceled
2011-R4 | Load transfer from Morgan Creek 69 kV to 138 kV | 2016 | Planning Stage |  | Oncor Electric Delivery project | Design Stage
2011-R5 | A new (third) San Angelo Red Creek 345/138 kV autotransformer | 2014 | Conceptual | 14TPIT0067 |  | CCN
2011-R6 | A new Mason Switching Station – North Brady 69 kV line | 2014 |  |  | LCRA TSC is discussing this project with AEP to develop coordinated internal plans for addressing the needs. | In Service
2011-R7 | Lon Hill – Robstown Tap – City of Robstown 69 kV line upgrade | 2012 | Conceptual | 12TPIT0180 | City of Robstown
2011-R8 | Calallen Substation – Lon Hill 69 kV line upgrade | 2014 | Conceptual | 12TPIT0181 | Lon Hill - Calallen Rebuild 69kV line
2011-R9 | Lon Hill 138/69 kV autotransformers #1 and #2 upgrade | 2014 | Planning Stage | 12TPIT0184
2011-R10 | South McAllen – Las Milpas – Steward Road 138 kV upgrade | 2016 | Conceptual | 16TPIT0023 | Stewart Road
2011-R11 | Crystal City – Turtle Creek 69 kV upgrade | 2012 | Conceptual | 12TPIT0182 | Turtle Creek
2011-R12 | Open Raymondville #1 - Raymondville #2 69 kV line | 2016 |  |  | (Same as 2011-E3 Below - AEP will review and determine how/if to address.
2011-R13 | Kenedy Switching Station - Helena 69 kV line upgrade | 2016 | Project details being developed by LCRA TSC
2011-R14 | Nixon – Nixon South - Milton 69 kV line upgrade | 2014 | Project details being developed by LCRA TSC
2011-R15 | Rebuild Poteet – Oaks 69 kV & Poteet – Pearsall 69 kV line | 2014 |  | N/A | A cheaper alternative was chosen with a new line from Oaks to AEP's Leon Creek to Pleasanton line.
2011-R16 | Lost Creek Area 138/69 kV upgrade | 2014 | Capacitor bank addition planned by LCRA TSC | New project | GVEC
2011-R17 | Lago Vista – Marshal Ford 138 kV line upgrade | 2016 | Under study by LCRA TSC
2011-R18 | Jollyville – Avery Ranch 138 kV line upgrade | 2016 | Under study by LCRA TSC
2011-R19 | Taylor - Elgin 138 kV line upgrade | 2016 | Planning Stage | 07TPIT0115 | Oncor Electric Delivery project
2011-R20 | Lon Hill - Smith 69 kV line upgrade | 2016 | Conceptual | 16TPIT0026 | Smith
2011-R21 | Sinton – Skidmore - Beeville 69 kV line upgrade | 2016 | Conceptual | 16TPIT0027 | Beeville
2011-R22 | Seguin – Seguin West 138 kV line upgrade | 2016 | Under study by GVEC
2011-R23 | Laredo – Del Mar 138 kV line upgrade | 2014 |  |  | Not necessary Lobo to Rio Bravo will resolve this issue
2011-R24 | Danevang – Danevang Distribution Substation 69 kV line upgrade | 2016 |  | 13TPIT0128 | STEC
2011-R25 | Fort Bend - Brazos 138 kV line upgrade | 2016 | Planning Stage |  | CNP; Evaluating project alternatives
2011-R26 | Polk - Downtown 138 kV underground cable upgrade | 2016 | Planning Stage |  | CNP
2011-R27 | Brownsboro – Murchison 69 kV line closure | 2012 | Completed |  | Oncor Electric Delivery project Mitigation Plan to close 69 kV switch post-contingency was put in place in June 2012.
2011-R28 | Northaven – Welch Road 138 kV double circuit upgrade | 2016 | Planning Stage | 14TPIT0056 | Oncor Electric Delivery project Preliminary results of 2012 5 Year Plan indicate deferral of project.
2011-R29 | Denton Area 138 kV line upgrades | 2016 |  | 14TPIT0047 | TMPA
2011-R30 | Parker Maxwell Creek – Ben Davis 138 kV line upgrade | 2016 | Planning Stage |  | Oncor Electric Delivery project
2011-R31 | Allen Switch 345/138 kV Autotransformer #1 series reactor in service | 2014 | Planning Stage |  | Oncor Electric Delivery project
2011-R32 | St Jo – Capps Corner 69 kV line upgrade | 2014 |  | 12TPIT0134 | BRAZOS
2011-R33 | Hicks 138 kV project | 2016 | Planning Stage | 16TPIT0018, 11TPIT0117 and 11TPIT0050 | Oncor Electric Delivery project
2011-R34 | Munday – Munday 2 69 kV line upgrade | 2016 | Conceptual | 14TPIT0063 | BEC Munday
2011-R35 | Seymour – Lake Kemp 69 kV line upgrade | 2014 |  | 15TPIT0013 | BRAZOS
2011-E1 | Odessa Area 138 kV line upgrades | 2014 | Planning Stage | 14TPIT0053 | Oncor Electric Delivery project
2011-E2 | Uprate Rio Hondo – East Rio Hondo 138 kV line | 2014 | NOMCR and PMCR submitted | N/A
2011-E3 | Open Raymondville #1 – Raymondville #2 69 kV line | 2014 |  |  | (Same as 2011-R12 above - AEP will review and determine how/if to address.

## TransmissionOwnerProjContacts
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Bob Healey | bhealey@aep.com | Bob Healey: 918 599 2249 | Glen Reed; David Kidd; Brad Myers; Sugam Patel; Mabel See; Mike Forcum; Doug Lee; Daniel Lyons; Bob Lager | gareed@aep.com; dekidd@aep.com; rlbentz@aep.com; naward@aep.com; smdsouza@aep.com; camatthes@aep.com; blmyers@aep.com; pcbelkin@aep.com ; msee@aep.com; mlforcum@aep.com; dnlyons@aep.com; dlee@aep.com; rjlager@aep.com | David Kidd: 918 599 2637 Glen Reed: 918 599 2664 Brad Myers: 918 599 2690
AUSTIN ENERGY | Primary & Secondary | Biju Mathew | biju.mathew@austinenergy.com; | Biju: 512 322 6737 | Armke, James; Mathew, Biju; Ebrahimian, Reza; Hunt, Dandy; Ron Krautz | James.Armke@austinenergy.com; biju.mathew@austinenergy.com; reza.ebrahimian@austinenergy.com; dandy.hunt@austinenergy.com; ron.krautz@austinenergy.com | James:512 322 6705 Biju:512 322 6381 Reza:512 322 6740 Dandy:512 322 6748 Ron:512 322 6835
Bandera Electric | Primary | David Baker | d.baker@banderaelectric.com | David: 830-796-6084 | Brian Bartos | b.bartos@banderaelectric.com | Brian: 830 796 6074
BPUB | Primary | Ramon Sanz | rsanz@brownsville-pub.com; | Ramon: 956 983 6203 | James McCann | jmccann@brownsville-pub.com; | James: 956 983 6204
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Brion Ryan | bryan@brazoselectric.com | Brion: 254 750 6353 | David Albers; Dwight Beckman | dalbers@brazoselectric.com; dbeckman@brazoselectric.com | David: 254 750 6358 Dwight: 254 750 6373
BTU | Primary & Secondary | James Tanneberger | jtanneberger@btutilities.com | James: 979 821 5763 | Shawndra Green | sgreen@btutilities.com | Shawndra: 979 821 5744
CNP | Primary & Secondary | Wayne Kemper | wayne.kemper@centerpointenergy.com | Wayne: 713 207 2192 | Wesley Woitt; Cody Mann; Roy Palacios | wesley.woitt@centerpointenergy.com; Roy.Palacios@centerpointenergy.com cody.mann@centerpointenergy.com; | Wesley Woitt: 713-207-2760 Cody Mann: 713-207-3149
COCS | Primary | Tony Michalsky | tmichalsky@cstx.gov; | Tony: 979 764 3438 | Timothy Crabb; Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | Basileo Rocha, Mario De La Garza | bdrocha@cpsenergy.com; MADelagarza1@CPSEnergy.com | Basileo: 210 353 4933 | Kenneth Bowen Blake Williams | kbowen@cpsenergy.com; bawilliams@cpsenergy.com; | Kenneth: 210 353 4142 Blake: 210 353 3557
CTT (Cross Texas Transmission) | Primary & Secondary | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310 | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310
DENTON | Primary & Secondary | Chuck Sears | Chuck.Sears@cityofdenton.com; | Chuck: 940 349 7111 | Brent Heath | brent.heath@cityofdenton.com; | Brent: 940 349 7180
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@garlandpower-light.org | Danh: 972 205 3826 | Grubbs, David; Fred Sherman; Steve Zaragoza | Dgrubbs@garlandpower-light.org; FredS@gplops.org; stevez@gplops.org | David: 972 205 2664 Fred: 972 205 3184 Steve: 972-205-3098
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; PEC; SBEC; GVEC; City of Georgetown; BBEC,CTEC, NBU | Primary & Secondary | Brad Woods | brad.woods@lcra.org | Brad: 512 578 4104 | Sergio Garza, Christina Doerr, Ken Chui | sergio.garza@lcra.org; christina.doerr@lcra.org; ken.chui@lcra.org | Sergio: 512 578 4149 Christina: 512 578 4514 Ken: 512 578 4510
Lone Star | Primary & Secondary | Shirley Mathew | Shirley.mathew@lonestar-transmission.com | Shirley: 512 236 3144 | David Turner | david.turner@lonestar-transmission.com | David: 512-236-3146
Oncor | Primary & Secondary | Mike Juricek | Michael.Juricek@oncor.com; | Mike: 214 743 6671 | Jim Painter | jpainte1@oncor.com | Jim: 214 743 6779
Sharyland Utilities | Primary & Secondary | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243 | Michael Glass, Dwight Yarbrough, Miguel Alvarado | mglass@sharyland.com; dyarbrough@sharyland.com; malvarado@sharyland.com | Michael: (956) 687-5600, Dwight: (432) 684-0321, Miguel: (214) 855-6103
STEC | Primary & Secondary | Doug Evans | devans@stec.org | Doug: 361 485 6459 | Dotty DiSanto Loretta Gallaga | dottyd@stec.org; lgallaga@stec.org; | Dotty: 361 645 6146 Loretta: 956 377 7120
TMPA | Primary & Secondary | Eric Schroeder | eschroeder@texasmpa.org; | Eric: 936 873 1124 | Frank Owens | fowens@texasmpa.org; | Frank: 936 873 1120
TNMP | Primary & Secondary | Raja Sekhar Kakarla | raja.kakarla@tnmp.com | Raja: 281 581 4733 | Anthony, Hudson McDaniel, Rex Aars, Alton | Anthony.Hudson@tnmp.com; Rex.McDaniel@tnmp.com; Alton.Aars@tnmp.com; | Anthony: 281 581 4712 Rex:409 948 8451 X238 Alton:972 420 4189
Wind Energy Texas Transmission (WETT) | Primary | Julius Horvath | julius.horvath@windenergyoftexas.com | Julius: 512 279 7377; cell: 512 496 9186 | Christina Eckhoff | christina.eckhoff@windenergyoftexas.com | Christina: Christina: 512 279 7371