## ImprovementCostSummary10242018
| Project Cost |  |  |  |  | XFMR MVA
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total
2017 | 261296875 | 634706922 | 196889112 | 1092892909 | 2017 | 5627 | 777 | 134.8 | 6538.8 | For ROS and BOD Reports
2018 | 553842009 | 1344046578 | 416130781 | 2314019368 | 2018 | 5446 | 2300 | 0 | 7746 | ·All Projects (in engineering, routing, licensing and construction): |  |  |  | 6032611078
2019 | 269046469 | 1081180253 | 773918094 | 2124144816 | 2019 | 5328 | 820 | 200 | 6348 | ·Transmission Projects Energized in 2018: |  |  |  | 1441969065
2020 | 664055800 | 857477442 | 250469717 | 1772002959 | 2020 | 7944 | 265 | 0 | 8209
2021 | 461650000 | 281354000 | 74200000 | 817204000 | 2021 | 2508 | 105 | 0 | 2613
2022 | 62800000 | 60959000 | 6600000 | 130359000 | 2022 | 2686 | 0 | 0 | 2686
2023 | 71200000 | 84300000 | 1950000 | 157450000 | 2023 | 675 | 0 | 0 | 675
2024+ | 9000000 | 57900000 | 92500000 | 159400000 | 2024+ | 600 | 0 | 0 | 600
2018COM | 512433000 | 780962265 | 148573800 | 1441969065 | 2018COM | 5446 | 770 | 0 | 6216
2018PLAN | 41409009 | 563084313 | 267556981 | 872050303 | 2018PLAN | 0 | 1530 | 0 | 1530
2017-2024+ | 2352891153 | 4401924195 | 1812657704 | 8567473052 | 2017-2024+ | 30814 | 4267 | 334.8 | 35415.8
2017-2018 | 815138884 | 1978753500 | 613019893 | 3406912277 | 2017-2018 | 11073 | 3077 | 134.8 | 14284.8
2019-2024+ | 1537752269 | 2423170695 | 1199637811 | 5160560775 | 2019-2024+ | 19741 | 1190 | 200 | 21131
| Circuit Miles New |  |  |  | Circuit Miles Rebuilt, Reconductored or Upgraded |  |  |  |  | Total
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total | 345 | 138 | 69 | Total
2017 | 0 | 86.64 | 0.15 | 86.79 | 2017 | 6 | 298.71 | 181.34 | 486.05 | 6 | 385.35 | 181.49 | 572.84
2018 | 305 | 298.349 | 2.6 | 605.949 | 2018 | 135.14 | 798.096 | 389.21 | 1322.446 | 440.14 | 1096.445 | 391.81 | 1928.395
2019 | 25.53 | 158.58 | 33.11 | 217.22 | 2019 | 44.3 | 227.48 | 556.098 | 827.878 | 69.83 | 386.06 | 589.208 | 1045.098
2020 | 365.6 | 127.827 | 0 | 493.427 | 2020 | 186.65 | 552.72 | 215.873 | 955.243 | 552.25 | 680.547 | 215.873 | 1448.67
2021 | 164 | 86.8 | 0 | 250.8 | 2021 | 76.5 | 111.56 | 42.54 | 230.6 | 240.5 | 198.36 | 42.54 | 481.4
2022 | 0 | 11.7 | 61 | 72.7 | 2022 | 37.4 | 33.48 | 0 | 70.88 | 37.4 | 45.18 | 61 | 143.58
2023 | 0 | 0.1 | 0 | 0.1 | 2023 | 141.9 | 79.4 | 0 | 221.3 | 141.9 | 79.5 | 0 | 221.4
2024+ | 4 | 16.4 | 0 | 20.4 | 2024+ | 67.96 | 39.7 | 51.8 | 159.46 | 71.96 | 56.1 | 51.8 | 179.86
2018COM | 305 | 217.149 | 2.6 | 524.749 | 2018COM | 96 | 599.58 | 149.05 | 844.63 | 401 | 816.729 | 151.65 | 1369.379
2018PLAN | 0 | 81.2 | 0 | 81.2 | 2018PLAN | 39.14 | 198.516 | 240.16 | 477.816 | 39.14 | 279.716 | 240.16 | 559.016
2017-2024+ | 864.13 | 786.396 | 96.86 | 1747.386 | 2017-2024+ | 695.85 | 2141.146 | 1436.861 | 4273.857 | 1559.98 | 2927.542 | 1533.721 | 6021.243
2017-2018 | 305 | 384.989 | 2.75 | 692.739 | 2017-2018 | 141.14 | 1096.806 | 570.55 | 1808.496
2019-2024+ | 559.13 | 401.407 | 94.11 | 1054.647 | 2019-2024+ | 554.71 | 1044.34 | 866.311 | 2465.361

## FutureTPIT100118NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2018
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
44370 | Wingarten Substation Addition | Construct a 69-kV unbreakered substation between La Pryor and Turtle Creek on an AEP owned line. The substation will provide transmission service for a DSP load interconnection request. |  | La Pryor | Turtle Creek | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-10-12 |  | 69 | 0 | 0 | 0 |  | Zavala | Zavala | Tier 4 |  |  |  | 7867, 8243, 8672 | Y | N |  | 0 | 44371 | 44370
6104 | Refugio - Heard Tap 69 kV Line | Rehab Refugio - Heard Tap 69 kV Line |  | Refugio | Heard Tap | Under Construction | 834 - 1018 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3635 | 2018-10-14 |  | 69 | 0 | 2.36 | 0 |  | Refugio |  | Tier 4 |  |  |  | 8410, 8802 | Y | N |  |  | 13830 | 6104
5716 | GLOBAL - 138kV Substation | Build new 138kV ME Global customer-owned substation. Loop through Ckt.82 Oyster Creek to Velasco. |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-10-29 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 43345, 42190, 43335, 43337, 43336, 43361 | Y | N |  |  | 13457 | 5716
4703B | Bellaire to San Felipe Ckt.09 & Bellaire tap Ckt.24 | Upgrade Ckt.24 Bellaire to Bellaire tap |  | Bellaire | Bellaire | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1132 | 2018-10-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47010, 47012 | Y |  |  |  | 13603 | 4703
5150 | Southwest Vernon: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Southwest Vernon |  | Southwest Vernon |  | Planned | 741 - 0924 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2913 | 2018-10-30 |  | 138 | 0 | 0 | 130 |  | Wilbarger |  | Tier 4 |  |  |  | 6064, 6066 | Y | N |  |  | 12805 | 5150
5887A | RUSSEL 138kV Substation (ARITEK Substation Removal) | Remove ARITEK 138kV substation from CNP service |  | ARITEK | SR Bertron/CHORIN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-10-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40120, 40320, 41391 | Y | N |  |  | 13612 | 5887
6750 | Quihi: Build 138kV Tap | Quihi Temprary 138kV Hard Tap on Razorback to Castroville 138kV Line |  | Razorback |  | Planned | 899 - 1077 | AEP TCC/STEC | Daniel Lyons dnlyons@aep.com 918-599-2698 | 3683 | 2018-10-30 |  | 138 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 88248, 5083, 8241 | Y | Y |  |  | 14543 | 6750
3418 | Nelson Sharpe: Add 345 kV Terminal for WF Interconnect | Add a new 345 kV line terminal at Nelson Sharpe for the Patriot WF Interconnect | Schedule Update | Nelson Sharpe |  | Under Construction | 515 - 0756 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3474 | 2018-10-31 |  | 345 | 0 | 0 | 0 |  | Kleberg |  | Tier 4 |  |  |  | 85000 | Y | N |  |  | 10793 | 3418
3683 | Abilene South to Sawgrass: Rebuild 69 kV line | Rebuild Abilene South to Sawgrass 69 kV line | Schedule Update | Abilene South | Sawgrass | Under Construction | 651 - 0820 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 1815 | 2018-10-31 |  | 69 |  | 2.15 |  |  | Taylor | Taylor | Tier 4 |  |  |  | 6284, 60394, 6283, 6285, 6636 | Y | N |  |  | 12804 | 3683
4703A | Bellaire to San Felipe Ckt.09 & Bellaire tap Ckt.24 | Reconductor Ckt.09 Bellaire to San Felipe and upgrade substation equipment to increase thermal ratings. | Accelerated Project Schedule | Bellaire | San Felipe | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1132 | 2018-10-31 |  | 138 | 0 | 2 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47010, 47380 | Y | N |  |  | 12290 | 4703
5172 | Laredo: Add two 138 kV breakers | Add two 138 kV breakers to the STATCOM yard and rebuild the Laredo to Laredo STATCOM 138 kV tie with 1026 ACCC/TW |  | Laredo | Laredo | Under Construction | 744 - 0927 | AEP TCC | Rich Haley dnlyons@aep.com 918-599-2698 | 2918 | 2018-10-31 |  | 138 | 0 | 0.111 | 0 |  | Webb | Webb | Tier 4 |  |  |  | 8293, 80021 | Y | N |  |  | 12831 | 5172
5887B | RUSSEL 138kV Substation (ARITEK Substation Removal) | Install 138kV customer-owned RUSSEL substation (ARITEK substation replacement). Loop from Ckt.84 DOWLAP to Morgans Point. |  | RUSSEL | DOWLAP/Morgans Point | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40125, 40070, 40490, 41310, 41391, 41415, 41631, 41100, 41400, 41419, 41450, 42610 | Y | N |  |  | 13613 | 5887
5891B | LUBZOL Substation Removal and Substation PATRIK Addition | Install 138kV customer-owned PATRIK substation (LUBZOL substation replacement) |  | PATRIK | TIDAL/TRAVIS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-10-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40981, 41580, 41620 | Y | N |  |  | 13647 | 5891
5963 | Big Hill: Build 345 kV terminal | Interconnect Live Oak wind farm at Big Hill | Schedule Update | Big Hill |  | Under Construction | 844 - 1028 | ETT | Greg Crane mlforcum@aep.com 918-599-2674 | 2685 | 2018-10-31 |  | 345 | 0 | 0 | 0 |  | Schleicher |  | Tier 4 |  |  |  | 76003 | Y | N |  |  | 13678 | 5963
5977 | Mertzon (CVEC T) to Tankersley 69 kV line: Rbld 69 kV line | Rehab Mertzon (CVEC Tap) to Tankersley 69 kV line |  | Mertzon (CVEC Tap) | Tankersley | Planned | 786 - 0971 | AEP TNC | Bill Roberts mlforcum@aep.com 918-599-2674 | 2662 | 2018-10-31 |  | 69 | 0 | 13.2 | 0 |  | Irion | Irion | Tier 4 |  |  |  | 6526, 6528, 6529 | Y | N |  |  | 13692 | 5977
6009 | Kenedy Switch: Replace 138/69 kV autotransformer | Upgrade 138/69 kV autotransformer capacity at Kenedy Switch |  | Kenedy Switch |  | Planned | 837 - 1021 | AEP TCC | James Nivens dnlyons@aep.com 918-599-2698 | 3639 | 2018-10-31 |  | 138 | 0 | 0 | 130 |  | Karnes |  | Tier 4 |  |  |  | 8184, 8186 | Y | N |  |  | 13726 | 6009
6244 | Rio Pecos to Sun Valley 69 kV line: Rebuild 69 kV line | Rehab Rio Pecos to Sun Valley 69 kV line |  | Rio Pecos | Sun Valley | Planned | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2703 | 2018-10-31 |  | 69 | 0 | 9.4 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 6598, 6641 | Y | N |  |  | 13969 | 6244
6387E | Greenville Arera System Enhancements | [6 empty] | RYBRN | Charles Gibune 214-678-1192 |  | 2018-10-31 |  | 138 | 0 | 0 | 0 |  | Hunt |  | Tier 3 | 2015-12-15 | 2016-02-15 |  | 6750, 6879, 6882 | Y | N |  | 0 | 44055 | 6387
6581 | HUDSON (Brazoria Energy) - Generator Interconnection 138kV S | New 138kV HUDSON (Brazoria Energy) generator interconnection. Loop substation to create new Ckt.04 MONSAN to HUDSON to Mustang Bayou | - Accelerated project schedule | HUDSON | MONSAN/ Mustang Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-10-31 |  | 138 | 0.1 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 42100, 905111, 905118, 42090, 42652, 42940, 42960, 111321, 43500 | Y | N |  |  | 14334 | 6581
7077 | Horse Crossing - Rio Pecos Transmission Line Addition | Construct a new 138-kV transmission line to a new radially connected generator-serving substation called Horse Crossing from Rio Pecos using double 795 26/7 ACSR Drake OPGW static. The planned transmission circuit rating will be (MVA): Rate A=439, Rate B=448, Rate C=448. |  | Horse Crossing | Rio Pecos | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-10-31 |  | 138 | 0.9 | 0 | 0 |  | Crane | Crockett | Tier 4 |  |  |  | 76601, 76602, 6601 | Y | N |  |  | 14909 | 7077
5894 | Install Third Zenith 345/138kV 800MVA Transformer | Install a third 800MVA autotransformer at Zenith Substation. |  | Zenith |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-10-31 00:01 |  | 345 | 0 | 0 | 800 |  | Harris |  | Tier 4 |  |  |  | 49091, 44900, 44910 | Y | N |  |  | 13615 | 5894
6095 | South Channel to Jefferson Ckt.06 | Upgrades substation equipment at South Channel and/or Jefferson substation to increase thermal ratings. | - Delayed project schedule | South Channel | Jefferson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41370, 41371 | Y | N |  |  | 13820 | 6095
6889 | GSEC_6889_69kV_Add_Enterprise_Lake_Ivey_Sub | [6 empty] | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2018-11-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 9431, 6377 | Y |  |  |  | 14704 | 6889
5223A | 2015 RTP rebuild 4 sections from George West through Mathis | Rebuild 4/0 ACSR from George West Substation to Mathis with 795 ACSR that is 138 capable. 2015 RTP |  | GW Substation | Mathis | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-11-09 |  | 69 | 0 | 18.44 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  | 5668, 5684 | Y | N |  | 0 | 43339 | 43336
6110 | Blessing - Palacios 69 kV Line | Rehab Blessing - Palacios 69 kV Line |  | Blessing | Palacios | Planned | 817 - 1001 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3611 | 2018-11-26 |  | 69 | 0 | 9.27 | 0 |  | Matagorda |  | Tier 4 |  |  |  | 8119, 8131 | Y | N |  |  | 13836 | 6110
3897 | Add New Weltner Rd. Sub | Construct a new 138-kV Weltner Rd. (7758) substation, which will cut into the LCRA TSC Clear Springs (7680) to Freiheit (7462) 138-kV transmission line | Substation name change from FM758 to Weltner | Weltner Road | Freiheit Road / Clear Springs | Planned |  | LCRATSC/NBU | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015105 | 2018-11-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7758, 7462, 7680 | Y | N |  |  | 12022 | 3897
5493 | Hays Energy Substation Upgrade | Upgrade the Hays Energy 345-kV substation bus to a double bus double breaker configuration. |  | Hays Energy |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016230 | 2018-11-30 |  | 345 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  | 7043 | Y | N |  |  | 13231 | 5493
5794 | Mason to Fort Mason: Rebuild 69 kV line | Rebuild Mason to Fort Mason 69 kV line and convert to 138 kV | Schedule Update | Mason | Ft. Mason | Under Construction | 646 - 0815 | AEP TNC | Michael Richardson mlforcum@aep.com 918-599-2674 | 1810 | 2018-11-30 |  | 69 | 0 | 0.15 | 0 |  | Mason | Mason | Tier 4 |  |  |  | 6393, 60410, 76388, 76390 | Y | N |  |  | 13533 | 5794
5962 | Mason: Add new 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Mason | Schedule Update | Mason |  | Under Construction | 646 - 0815 | AEP TNC | Michael Richardson mlforcum@aep.com 918-599-2674 | 2687 | 2018-11-30 |  | 138 | 0 | 0 | 130 |  | Mason |  | Tier 4 |  |  |  | 60410, 6393 | Y | N |  |  | 13677 | 5962
5968 | Alpine to Alpine REA 69 kV line: Rebuild 69 kV line | Rehab Alpine to Alpine REA 69 kV line | Schedule Update | Alpine | Alpine REA | Planned | 786 - 0971 | AEP TNC | Guillermo Taylor mlforcum@aep.com 918-599-2674 | 2657 | 2018-11-30 |  | 69 | 0 | 8.82 | 0 |  | Brewster | Brewster | Tier 4 |  |  |  | 6665, 6666 | Y | N |  |  | 13683 | 5968
5993 | Owls: Build 138 kV station | Construct new 138 kV ring bus with a 138/69 kV autotransformer |  | Owls |  | Planned | 841 - 1025 | AEP TNC | Brad Duvall mlforcum@aep.com 918-599-2674 | 2681 | 2018-11-30 |  | 138 | 0 | 0 | 90 |  | Reagan |  | Tier 4 |  |  |  | 60413, 60414, 6536, 6544, 60361, 60396 | Y | N |  |  | 13709 | 5993
6001 | Goliad - Fannin 69 kV line | Rehab Goliad - Fannin 69 kV line |  | Goliad | Fannin | Planned | 809 - 0994 | AEP TCC | James Nivens dnlyons@aep.com 918-599-2698 | 3598 | 2018-11-30 |  | 69 | 0 | 5 | 0 |  | Goliad | Victoria | Tier 4 |  |  |  | 5736, 8587 | Y | N |  |  | 13718 | 6001
6079 | Childress to Kirkland 69 kV line: Rebuild 69 kV line | Rehab Childress to Kirkland 69 kV line | Cost Update | Childress | Kirkland | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2693 | 2018-11-30 |  | 69 | 0 | 5.61 | 0 |  | Childress | Childress | Tier 4 |  |  |  | 6032, 6053 | Y | N |  |  | 13803 | 6079
6241 | WINMIL 138kV Substation | Construct service to new 138kV WINMIL customer-owned substation. Loop through Ckt.26 Rosharon to Angleton | - Delay in project schedule | WINMIL | Rosharon/ Angleton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-11-30 |  | 138 | 0.6 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 44531, 42110, 44410, 42870, 44600 | Y | N |  |  | 13966 | 6241
6242 | Pinto Creek Substation Addition | Install a new motor operated 138-kV load serving substation on T464 between Brackettville and Hamilton Road. |  | Pinto Creek |  | Planned |  | LCRATSC/RGEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017994 | 2018-11-30 |  | 138 | 0 | 0 | 0 |  | Kinney |  | Tier 4 |  |  |  | 78255, 8252, 8255 | Y | N |  |  | 13967 | 6242
44404 | Jim Treece: Interconnect Blue Summit II | Interconnect Blue Summit II wind farm into Blue Summit station | NEW | Jim Treece |  | Planned | 932 - 1110 | AEP TNC | Dave Goetz mlforcum@aep.com 918-599-2674 | 2743 | 2018-11-30 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  | 61001 | Y | N |  | 0 | 44405 | 44404
18TPIT0002 | Martinez - New 138kV Substation | Loop new 138kV substation into the existing 138kV Deely to Skyline line |  | Deely | Skyline | Planned | S-0751 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0218 | 2018-12-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5294, 5110, 5368 | Y | N |  | There are no transformers associated with this project | 9511 | 2263
4711B | CORTEZ 138kV Substation | Add 138kV CORTEZ Load |  | CORTEZ |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 55 | 2018-12-01 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43440 | Y |  |  |  | 13648 | 4711
5634 | Rebuild Danevang to Clemville Sw 69 kV line | Rebuild the Danevang Sub to Clemville Switch 4/0 ACSR 69 kV line with 795 ACSR 138 capable. 2016 RTP |  | Danevang | Clemville | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-12-01 |  | 69 | 0 | 5.1 | 0 |  | Wharton | Matagorda | Tier 4 |  |  |  | 5548, 5550 | Y | N |  |  | 13368 | 5634
5943 | T-283 Prairie View to Sunnyside | Rebuild transmission line to 138-kV capable 959.6 ACSS-TW conductor due to maintenance on old 69 KV wood pole line and the future conversion to 138 KV. |  | Prairie View | Sunnyside | Under Construction |  | SBEC | Don Roberts droberts@sbec.org | WO# 17-6069 | 2018-12-01 |  | 69 | 0 | 13 | 0 |  | Waller | Waller | Tier 4 |  |  |  | 7664, 7666 | Y | N |  |  | 13654 | 5943
6105 | Heard Tap - Woodsboro 69 kV Line | Rehab Heard Tap - Woodsboro 69 kV line |  | Heard Tap | Woodsboro | Planned | 834 - 1018 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3636 | 2018-12-01 |  | 69 | 0 | 2.41 | 0 |  | Refugio |  | Tier 4 |  |  |  | 8802, 8804 | Y | N |  |  | 13831 | 6105
5926 | Kendall CTEC Circuit Breaker Addition | Add circuit breakers in a SB/SB arrangement at Kendall CTEC Tap (S343). |  | Kendall CTEC |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017390 | 2018-12-03 |  | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7147 | Y | N |  |  | 13634 | 5926
4537 | Add new line to connect Rocky Rd to Coates station (new) |  |  | Rocky Rd | Coates | Planned |  | CTT | Brad Schwarz 512-289-7425 |  | 2018-12-04 |  | 138 | 7 | 0 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 79563, 79614 | Y | N |  |  | 12114 | 4537
3276 | JT Deely to Martinez MLSE Upgrade | Upgrade terminal at JT Deely to ensure a rating of 2386 A (minimum). |  | JT Deely | Martinez | Planned | S-0759 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2018-12-10 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5294, 5110 | Y | N |  | There are no transformers associated with this project | 10627 | 3276
6122 | Sunniland - Three Rivers 69 kV Line | Rehab Sunniland - Three Rivers 69 kV Line |  | Sunniland | Three Rivers | Planned | 814 - 0998 | AEP TCC | James Nivens dnlyons@aep.com 918-599-2698 | 3606 | 2018-12-12 |  | 69 | 0 | 7.18 | 0 |  | Live Oak |  | Tier 4 |  |  |  | 8400, 8406 | Y | N |  |  | 13848 | 6122
6003 | Knippa - Uvalde 69 kV line | Rehab Knippa - Uvalde 69 kV line |  | Knippa | Uvalde | Planned | 811 - 0996 | AEP TCC | James Nivens dnlyons@aep.com 918-599-2698 | 3601 | 2018-12-13 |  | 69 | 0 | 4.62 | 0 |  | Uvalde |  | Tier 4 |  |  |  | 8231, 8628 | Y | N |  |  | 13720 | 6003
13TPIT0059 | Cedar Crest - Industrial 138 kV line | Upgrade existing line | Construction schedule change | Cedar Crest | Industrial | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4072-E | 2018-12-15 |  | 138 | 0 | 3.2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2494, 2976, 2981 | Y | N | 2009-R23 |  | 9775 | 2495
14TPIT0057 | Cedar Hill Switch - Liggett 138 kV line | Upgrade Cedar Hill Switch - Dalworth existing line section |  | Cedar HIll Switch | Dalworth | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5041-E | 2018-12-15 |  | 138 | 0 | 8.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 1912, 1922, 2265, 2270, 2271, 2274, 2422 | Y | N |  |  | 10276 | 2926
16TPIT0061 | Norwood - Record Crossing - East Levee 138 kV Line | Upgrade existing line | Construction schedule change | Norwood | East Levee | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4107-E | 2018-12-15 |  | 138 | 0 | 7.6 | 0 |  | Dallas | Dallas | Tier 4 |  | 2016-08-22 |  | 2405, 2407, 2482, 2811, 2812, 2813, 2815, 2816, 2814, 2819, 2823, 2824 | Y | N |  |  | 11846 | 3067
17TPIT0019 | Forney - Royse 138 kV Line | Upgrade existing line |  | Forney | Royse | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4111-E | 2018-12-15 |  | 138 | 0 | 18.32 | 0 |  | Kaufman | Rockwall | Tier 4 |  |  |  | 2438, 2471, 2709, 2710, 2711, 2712 | Y | N |  |  | 11839 | 3086
17TPIT0022 | Nacogdoches - Nacogdoches Southeast 138 kV Line | Upgrade existing Camino - Nacogdoches Southeast 138 kV line section |  | Camino | Nacogdoches Southeast | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6037-E | 2018-12-15 |  | 138 | 0 | 10.8 | 0 |  | Nacogdoches | Nacogdoches | Tier 4 |  |  |  | 3120, 3310, 3311, 13303 | Y | N |  |  | 14738 | 3152
06TPIT0042 | Lake Wichita Switch - Wichita Falls Switch 69 kV line | Upgrade existing 69 kV line |  | Lake Wichita Switch | Wichitia Falls Switch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R933-E | 2018-12-15 |  | 138 | 0 | 6.3 | 0 |  | Archer | Wichita | Tier 4 |  |  |  | 1446, 1447, 1448, 1449 | Y | N |  |  | 10565 | 3217
4527 | Fullerton Switching Station | Construct new switching station |  | Fullerton |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8277 | 2018-12-15 |  | 138 | 0 | 0 | 0 |  | Andrews |  | Tier 4 |  |  |  | 1272, 1275, 1271, 1274, 1284, 11274 | Y | N |  |  | 12102 | 4527
4549 | Yucca Drive - Barilla Junction (AEP) 138 kV Line | Rebuild Oncor's section of the existing line |  | Yucca Drive | Barilla Junction (AEP) | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8272 | 2018-12-15 |  | 138 | 0 | 15 | 0 |  | Ward | Pecos | Tier 3 | 2015-12-15 | 2016-09-21 | 2016-10-11 | 1009, 60397 | Y | N |  |  | 12126 | 4549
4837 | Everman - Cleburne Sw. Sta. 138 kV Line | Upgrade existing Everman - Burleson line section | Construction schedule change | Everman | Burleson | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5204 | 2018-12-15 |  | 138 | 0 | 16.6 | 0 |  | Tarrant | Johnson | Tier 4 |  |  |  | 1883, 2208, 2209 | Y | N |  |  | 12439 | 4837
4840 | Crockett 138 kV Sw. Sta | Upgrade existing station |  | Crockett |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6060 | 2018-12-15 |  | 138 | 0 | 0 | 0 |  | Houston |  | Tier 4 |  |  |  | 3351, 3354 | Y | N |  |  | 12442 | 4840
5427 | Holt-Andrews North-Andrews County South 138 kV DCKT Line | Upgrade existing line |  | Holt | Andrews North | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8352 | 2018-12-15 |  | 138 | 0 | 30 | 0 |  | Andrews | Ector | Tier 3 | 2016-02-01 | 2016-05-01 |  | 1262, 1263, 1141, 1142, 1159, 1157, 1267 | Y | N |  |  | 13112 | 5427
5434 | Littman - Fullerton 138 kV Line | Construct new 138 kV line |  | Littman | Fullerton | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8344 | 2018-12-15 |  | 138 | 10 | 5.5 | 0 |  | Andrews | Andrews | Tier 3 | 2016-08-24 | 2016-10-10 |  | 1273, 1134, 1275, 1274 | Y | N |  |  | 13137 | 5434
5484 | Royse-Terrell 138 kV Line | Upgrade existing Royse - Terrell 138 kV line |  | Royse | Terrell Sw | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4224 | 2018-12-15 |  | 138 | 0 | 28 | 0 |  | Rockwall | Kaufman | Tier 4 |  |  |  | 2715, 2472, 2713, 2717, 2718, 2719, 2721, 2723 | Y | N |  |  | 13222 | 5484
5485 | Nacogdoches Southeast Switching Station | Upgrade existing 138 kV switching station |  | Nacogdoches Southeast Sw. Sta. | Nacogdoches Southeast Sw. Sta. | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6068 | 2018-12-15 |  | 138 | 0 | 0 | 0 |  | Nacogdoches | Nacogdoches | Tier 4 |  |  |  | 3120, 3319 | Y | N |  |  | 13223 | 5485
5488 | Northwest Carrollton - LakePointe TNP 138 kV Line | Upgrade existing NW Carrollton - LakePointe 138 kV Line | Construction schedule change | Northwest Carrollton | LakePointe | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5156 | 2018-12-15 |  | 138 | 0 | 2.1 | 0 |  | Dallas | Denton | Tier 4 |  |  |  | 2362, 37010 | Y | N |  |  | 13226 | 5488
5532 | NW Paris 138 kV Sw. Sta. | Construct new 138/69 kV switching station | Construction schedule change | NW Paris | Paris | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4100 | 2018-12-15 |  | 138 | 0 | 3.5 | 100 |  | Lamar |  | Tier 4 |  |  |  | 1700, 1703, 1778, 1803, 1805, 1806, 6846, 11701, 11778, 1693, 1694, 1777, 1788, 1820, 1821 | Y | N |  |  | 13260 | 5532
5731B | Tri Corner 345 kV Sw Sta | Ultimate Configuration for Tri Corner |  | Tri Corner | Tri Corner | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4228 | 2018-12-15 |  | 345 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2432, 2428, 2433, 3102, 3124 | Y |  |  |  | 14311 | 5731
5800 | Hutto-Taylor 138 kV Line | Upgrade existing 138 kV Line |  | Hutto | Taylor | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R775 | 2018-12-15 |  | 138 | 0 | 15.6 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 3658, 3666, 3673 | Y | N |  |  | 13540 | 5800
5805 | Holland 69 kV Capacitors | Install 69 kV Capacitors |  | Holland | Holland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R772 | 2018-12-15 |  | 69 | 0 | 0 | 0 | 7.2,0 | Bell | Bell | Tier 4 |  |  |  | 3646 | Y | N |  |  | 13545 | 5805
5973 | Forest Hill 138 kV Switching Station | Rebuild existing Forest Hill 138 kV Switching Station |  | Forest Hill Sw. Sta. |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5268 | 2018-12-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  | 1883, 1967, 2194 | Y | N |  |  | 13688 | 5973
5996 | Corsicana 69 kV Switching Station | Corsicana 69 kV Switching Station |  | Corsicana | Corsicana | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2020 | 2018-12-15 |  | 138 | 0 | 0 | 100 |  | Navarro | Navarro | Tier 4 |  |  |  | 3466, 3467, 3469, 3480, 3127, 3128, 3455, 3468, 3478, 3479 | Y | N |  |  | 13713 | 5996
5997 | Temple - Belton 138 kV Line | Temple - Belton 138 kV Line |  | Temple | Belton | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R784 | 2018-12-15 |  | 138 | 0 | 10.9 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3415, 3602, 3610, 3611, 3612 | Y | N |  |  | 13714 | 5997
6035 | Liggett Sw. Sta. - Irving/Irving Grant 138 kV Double-circuit | Upgrade terminal equipment on Liggett Sw. Sta. - Irving/Irving Grant 138 kV Double-circuit Line section |  | Liggett | Irving Grant | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4164 | 2018-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 1922, 1924, 2053, 2055 | Y | N |  |  | 13754 | 6035
6038 | Irving - Norwood 138 kV Line Section | Upgrade terminal equipment on Pleasant Valley - Ceramic 138 kV Line |  | Irving | Norwood | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4166 | 2018-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2053, 2054, 2408 | Y | N |  |  | 13757 | 6038
6271 | Wichita Falls 138 kV Sw Sta Rebuild | Rebuild the existing 138 kV switching station and install a second 138/69 kV autotransformer |  | Wichita Falls Sw. Sta. |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R970 | 2018-12-15 |  | 138 | 0 | 0 | 150 |  | Wichita |  | Tier 4 |  |  |  | 11448, 1448, 1446, 1449 | Y |  |  |  | 14001 | 6271
6274 | Payne 138 kV Sw Sta | Rebuild the existing 138 kV Switching Station |  | Payne Sw. Sta |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R981 | 2018-12-15 |  | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  | 1758, 1839, 11760, 1699, 1704, 1713, 1732, 1746, 1753, 1763, 12468, 140002, 1759, 11759 | Y |  |  | 0 | 44079 | 6274
6275 | Everman 345/138 kV autotransformer | Replace the existing autotransformer #1 and remove autotransformer #2 |  | Everman Sw. Sta. |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5263 | 2018-12-15 |  | 138 | 0 | 0 | 600 |  | Tarrant |  | Tier 4 |  |  |  | 11883, 1886, 1884, 11882, 11886 | Y |  |  |  | 14005 | 6275
6276 | Northaven 138 kV Sw Sta | Rebuild the existing 138 kV Switching Station |  | Northaven Sw. Sta. |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4243 | 2018-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2597, 2652, 2657, 2658, 2659, 2661 | Y |  |  |  | 14006 | 6276
6779 | Wagley Robertson - Saginaw 138 kV Double-circuit Line | Upgrade existing line | Construction schedule changed | WAGLEY ROBERTSON | SAGINAW | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5250 | 2018-12-15 |  | 138 | 0 | 23 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 564, 1957, 2071, 2075, 2076, 2077 | Y | N |  |  | 14573 | 6779
7042 | White Settlement - Hilltop 69 kV Line | Convert 4.3-mile section of 69 kV Line out of White Settlement to 138 kV. Install 100 MVA 138/69 kV autotransformer at White Settlement. |  | White Settlement | White Settlement West | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5230 | 2018-12-15 |  | 138 | 3 | 4.3 | 100 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 506, 1953, 1954, 1975, 2085, 2086, 2087, 2088, 2089 | Y | N |  |  | 14864 | 7042
5431 | Holt 138 kV Switching Station | Expand existing 138 kV switching station |  | Holt |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8353 | 2018-12-15 12:00 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  | 1142, 1259, 1123, 1141, 1257 | Y | N |  |  | 13134 | 5431
44189 | Upgrade Wolf Holllow - Comanche Peak 345 kV Line |  |  | WOLF HOLLOW | COMANCHE PEAK | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 |  | 2018-12-15 12:00 |  | 345 | 0 | 7.8 | 0 |  | Hood | Somervell | Tier 4 |  |  |  | 1900, 1981 | Y | N |  | 0 | 44190 | 44189
4251 | Everman - Wedgwood 138 kV Line | Upgrade existing double-circuit line | Construction schedule change | Everman | Wedgwood | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5210 | 2018-12-16 |  | 138 | 0 | 18 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1883, 1967, 2184, 2185, 2190, 2191, 2192, 2193, 2194, 2195 | Y | N |  |  | 11797 | 4251
6562A | Crowley - Cresson 69 kV Line Conversion | Rebuild existing 69 kV line section from Crowley - Cresson |  | Crowley | Cresson | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5244 | 2018-12-18 |  | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2202, 2203, 1884, 1967, 2205 | Y | N |  |  | 14307 | 6562
5217 | Rebuild Cotulla to Big Wells 69 kV line | Rebuild 69 kV line with 138 kV capable 795 ACSR 2015- NERC assessment. |  | Cotulla | Big Wells | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-12-28 |  | 69 | 0 | 22.2 | 0 |  | La Salle | Dimmit | Tier 4 |  |  |  | 5868, 5876 | Y | N |  |  | 12882 | 5217
16TPIT0034 | Coleto Creek to Tuleta: New 138 kV Line | Build a double circuit capable 138 kV circuit from Coleto Creek station to new Tuleta station. |  | COLETO CREEK | TULETA | Under Construction | 606-0771 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3481 | 2018-12-30 |  | 138 | 56 | 0 | 0 |  | Goliad | Bee | Tier 1 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8595, 8162, 8590 | Y | N |  |  | 10877 | 3495
4065 | Add Graham Road Substation |  |  | BTU South | BTU Greens Prairie | Planned |  | COCS | Tony Mickalsky tmichalsky@cstx.gov 979-764-3438 |  | 2018-12-30 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32007, 32878, 32880 | Y |  |  |  | 11590 | 4065
5527 | Euler 138 kV Station: Construct a new station | Build a double circuit capable 138 kV circuit from Coleto Creek station to new Tuleta station. |  | Euler |  | Under Construction | 606-0771 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3481 | 2018-12-30 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 1 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8595, 5675 | Y | N |  |  | 13254 | 5527
5588 | La Palma Dynamic Reactive | Add +300/-300 MVAR Dynamic Reactive to La Palma 138 kV station |  | La Palma |  | Under Construction | 793 - 0978 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3583 | 2018-12-30 |  | 138 | 0 | 0 | 0 | 300300 | Cameron |  | Tier 1 | 2015-04-16 | 2016-05-19 | 2016-06-16 | 80319, 80320, 80322, 80323, 8314 | Y | N |  |  | 13318 | 5588
6082 | Basin: Build 138 kV station | Construct new 138 kV box bay on the Solstice to Permian Basin 138 kV line |  | Basin |  | Planned | 860 - 1038 | AEP TNC | Dave Baker mlforcum@aep.com 918-599-2674 | 2696 | 2018-12-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60415, 60392, 60397 | Y | N |  |  | 13806 | 6082
6312B | PH Robinson Autotransformer A3 800MVA Addition | Move PH Robinson 800MVA 345/138kV Auto A1 to North bus. | - Delayed project schedule | PH Robinson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-12-30 00:01 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 42000, 42010, 42015, 49026 | Y | N |  | 0 | 43465 | 6312
2979 | Melon Creek: Build new 138 kV station | Construct new Melon Creek station near Refugio, cut-in Airco to Rincon 138 kV line into Melon Creek, and cut-in Refugio to Tatton 69 kV line into Melon Creek. | Company Contact Update | Melon Creek |  | Under Construction | 100 - 0100 | AEP TCC | Wilburt Roberts dnlyons@aep.com 918-599-2698 | 2021 | 2018-12-31 |  | 138 | 3 | 0 |  |  | Refugio |  | Tier 3 | 2017-03-31 | 2017-04-21 | 2017-06-01 | 8144, 8437, 8800, 8811, 80065, 8410, 8412, 80066 | Y | N |  |  | 10323 | 2979
4716 | Tortuga: Build new 3 breaker 138 kV station | Construct new Tortuga 138 kV line and cut it into the Gila - Upriver (Koch) 138 kV line |  | Gila | Upriver (Koch) | Planned | 717 - 0899 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3553 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8168, 81680, 8467, 80136, 80260 | Y |  |  |  | 12389 | 4716
5017 | Lotebush: Build 138 kV station and add 2 capacitor banks | Construct new 138 kV station on the Barrilla Junction to Permian Basin Line and add two 28.8 Mvar capacitor banks | Cost Update | Lotebush |  | Under Construction | 736 - 0919 | AEP TNC | David Baker mlforcum@aep.com 918-599-2674 | 2616 | 2018-12-31 |  | 138 | 0 | 0 | 0 | 0,57.6 | Reeves |  | Tier 4 |  |  |  | 6656, 1009, 6657, 6673, 38370, 60392, 60397, 60393, 60415 | Y | N |  |  | 14994 | 5017
5199 | Vernon Main Street: Add 138 kV capacitor banks | Add two 14.4 Mvar capacitor banks at Vernon Main Street | Schedule Update | Vernon Main Street |  | Planned | 760 - 0944 | AEP TNC | Dave Goetz mlforcum@aep.com 918-599-2674 | 2635 | 2018-12-31 |  | 138 | 0 | 0 | 0 | 0,28.8 | Wilbarger |  | Tier 4 |  |  |  | 6060 | Y | N |  |  | 12858 | 5199
5257 | Solstice to Pig Creek: Rebuild 138 kV line | Rebuild Solstice to Yucca Drive 138 kV line and add dynamic reactive devices at Lotebush | Project Title, Schedule, and Cost Update | Solstice | Pig Creek | Planned | 713 - 0946 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2636 | 2018-12-31 |  | 138 | 0 | 13.285 | 0 |  | Pecos | Reeves | Tier 1 | 2015-12-15 | 2016-09-21 | 2016-10-26 | 60385, 60393 | Y | Y |  |  | 12932 | 5257
5596 | Pharr Dynamic Reactive | Add +300/-300 MVAR Dynamic Reactive to Pharr 138 kV station |  | Pharr |  | Planned | 794 - 0979 | AEP TCC | Rich Haley dnlyons@aep.com 918-599-2698 | 3584 | 2018-12-31 |  | 138 | 0 | 0 | 0 | 300300 | Hidalgo |  | Tier 1 | 2015-04-16 | 2016-05-19 | 2016-06-16 | 80372, 80373, 80375, 80376, 8372 | Y | N |  |  | 14072 | 5596
5715A | Red Bluff - 138kV Substation | Install temporary service for Red Bluff 138kV substation. Tap from Ckt.79 SEPTON to BAYWAY. |  | Red Bluff | Terminal/Bayway | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42931, 42170, 42955 | Y | N |  |  | 13454 | 5715
5831 | Rebuild Gustine to Energy SW | Rebuild Gustine (Bus #273) to Energy SW (Bus #265) per RTP study results |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 16013 | 2018-12-31 |  | 69 | 0 | 5.05 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  | 265, 273 | Y |  |  |  | 13573 | 5831
5951 | Bishop-Stratton: Rebuild 69 kV line | Rebuild Bishop - Stratton 69 kV line |  | Bishop | Stratton | Under Construction | 825 - 1009 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3624 | 2018-12-31 |  | 69 |  | 5 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8498, 8512 | Y | N |  |  | 13662 | 5951
5966 | College Hills to Grape Crk T 69 kV line: Rebuild 69 kV line | Rehab College Hills to Grape Creek Tap 69 kV line |  | College Hills | Burma | Planned | 786 - 0971 | AEP TNC | Guillermo Taylor mlforcum@aep.com 918-599-2674 | 2664 | 2018-12-31 |  | 69 | 0 | 10.45 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6468, 6416 | Y | N |  |  | 13681 | 5966
5972 | Benjamin Tap to Munday 69 kV line: Rebuild 69 kV line | Rehab Benjamin Tap to Munday 69 kV line |  | Benjamin Tap | Munday | Planned | 786 - 0971 | AEP TNC | Guillermo Taylor mlforcum@aep.com 918-599-2674 | 2661 | 2018-12-31 |  | 69 | 0 | 13.12 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 790, 6086, 6087, 6107 | Y | N |  |  | 13687 | 5972
5979 | Carver: Build new 138 kV station | Construct a new 138 kV ring bus station to replace the 138 kV portion of the Sonora 138/69 kV station | Schedule and Cost Update | Carver |  | Planned | 838 - 1022 | AEP TNC | Dave Baker mlforcum@aep.com 918-599-2674 | 2678 | 2018-12-31 |  | 138 | 0 | 0 | 90 |  | Sutton |  | Tier 4 |  |  |  | 60412, 60433, 6500, 6513, 6515, 6562, 8259 | Y | N |  |  | 13694 | 5979
5994 | Owls to Pwll Fld Jnctn T (Bison) 69 kV line: Rbld 69 kV line | Rehab Owls to Powell Field Junction Tap (Bison) 69 kV line |  | Owls | Bison | Planned | 786 - 0971 | AEP TNC | Michael Richardson mlforcum@aep.com 918-599-2674 | 2665 | 2018-12-31 |  | 69 | 0 | 11.53 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  | 6545, 60396, 60395, 60413 | Y | N |  |  | 13710 | 5994
5998 | Ganso: Build new 138 kV station | Build new three breaker ring in place of Eagle Pass Hydro Tap |  | Ganso |  | Planned | 835 - 1019 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3637 | 2018-12-31 |  | 138 | 0 | 0.3 | 0 |  | Maverick |  | Tier 4 |  |  |  | 8264, 8267, 8260, 8263, 8692 | Y | N |  |  | 13715 | 5998
6000 | Banquete - Calallen 69 kV line | Rehab Banquete - Calallen 69 kV line |  | Calallen | Banquete | Planned | 816 - 1000 | AEP TCC/STEC | Andrew Garlick dnlyons@aep.com 918-599-2698 | 3609 | 2018-12-31 |  | 69 | 0 | 12.7 | 0 |  | Nueces |  | Tier 4 |  |  |  | 5626, 8888 | Y | Y |  |  | 13717 | 6000
6078 | Bronte to Bronte Atlantic 69 kV line: Rebuild 69 kV line | Rehab Bronte to Bronte Atlantic 69 kV line | Cost Update | Bronte | Bronte Atlantic | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2692 | 2018-12-31 |  | 69 | 0 | 3.73 | 0 |  | Runnels | Coke | Tier 4 |  |  |  | 6414, 6418 | Y | N |  |  | 13802 | 6078
6080 | Concho to Christoval 69 kV line: Rebuild 69 kV line | Rehab Concho to Christoval 69 kV line |  | Concho | Christoval | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2694 | 2018-12-31 |  | 69 | 0 | 16.8 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6450, 6495, 6477, 6527 | Y | N |  |  | 13804 | 6080
6119 | Rockport - Fulton 69 kV Line | Rehab Rockport - Fulton 69 kV Line |  | Rockport | Fulton | Planned | 827 - 1011 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3628 | 2018-12-31 |  | 69 | 0 | 7.66 | 0 |  | San Patricio | Aransas | Tier 4 |  |  |  | 8431, 8432, 8841 | Y | N |  |  | 13845 | 6119
6260 | Install 3rd 120MVAR capacitor bank at Jones Creek substation | Install capacitor bank #3 at Jones Creek substation (120MVAR). |  | Jones Creek | Velasco | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 | 0,120 | Brazoria | Brazoria | Tier 4 |  |  |  | 42543, 42540, 43360 | Y | N |  |  | 13988 | 6260
6261 | Velasco Cap Bank #3 | Install capacitor bank #3 at Velasco substation (120MVAR). |  | Velasco | SURFSI | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 | 0,120 | Brazoria | Brazoria | Tier 4 |  |  |  | 43363, 43315, 43360 | Y | N |  |  | 13989 | 6261
6281 | CPSE_Harlandal_Sommers_MLSE | Upgrade terminals at Harlandale and Sommers Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0732 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 5190, 5395 | Y |  |  |  | 14013 | 6281
6636 | CELNES 138kV Substation | Install 138kV customer-owned CELWST substation. Loop from Ckt.94 BAYWAY to HIMONT |  | Himont | Bayway | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42250, 42170, 42790 | Y |  |  | 0 | 43475 | 6636
43284B | Baytown Area Upgrades | Upgrade equipment at EXXON substation to increase thermal ratings on Ckt.66 EXXON to Baytown |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40170, 40570 | Y |  |  | 0 | 43285 | 43284
43531 | PH Robinson - Replace Failed Auto A4 | Replace failed PH Robinson auto A4 (800MVA) |  | PH Robinson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-12-31 |  | 345 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 49047, 42000, 42010 | Y | N |  | 0 | 43532 | 43531
6328 | REED - Substation Removal | Remove 69kV REED substation from CNP transmission service |  | REED |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-12-31 00:01 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 41340, 40800, 41040 | Y |  |  |  | 14063 | 6328
6871 | FirewheelToLookoutLineUpgrade | Firewheel to Lookout 138kV line upgrade to Cumberland conductor |  | Lookout | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2018-12-31 23:00 |  | 138 | 0 | 1.18 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 821, 828 | Y | N |  |  | 14680 | 6871
44389 | Torrecillas POI | [6 empty] | ETT | Terry Weeks dnlyons@aep.com 918-599-2698 |  | 2019-01-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 80210, 80219, 161257 | Y |  |  | 0 | 44390 | 44389
5223B | 2015 RTP rebuild 4 sections from George West through Mathis | Rebuild 4/0 ACSR from George West Switching Station to Kittie West Substation with 795 ACSR that is 138 capable. Removes the GOAB at West George West Switch. 2015 RTP |  | George West Switching Station | Kittie West | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-01-18 |  | 69 | 0 | 4.25 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  | 5685, 5683, 5684, 5686 | Y | N |  | 0 | 43337 | 43336
4531 | Solstice to Clovis: Build 138 kV line | Interconnect Roserock solar farm with a new 138 kV line from Solstice to Clovis |  | Solstice | Clovis | Planned | 705 - 0875 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2811 | 2019-01-31 |  | 138 | 4.5 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 60383, 6630, 60385, 132331 | Y | N |  |  | 12106 | 4531
5205 | Carrizo Springs-Crystal City: 69 kVLine Rebuild | Rebuild 69 kV line from Carrizo Spring to Crystal City |  | Carrizo Springs | Crystal City | Under Construction | 761-0945 | AEP TCC | Jeremy Brazeal dnlyons@aep.com 918-599-2698 | 3569 | 2019-01-31 |  | 69 | 0 | 13.9 | 0 |  | Dimmit | Zavala | Tier 3 |  |  |  | 8244, 8242 | Y | N |  |  | 12864 | 5205
5533 | Lynx: Build a 138 kV station | Construct a new 138 kV ring bus near Woodward #1 Tap on the Fort Stockton to Rio Pecos Line and terminate Woodward 1 and 2 wind farms into Lynx |  | Lynx |  | Planned | 788 - 0973 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2647 | 2019-01-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6632, 60400, 6601, 6671, 38330, 130432, 130533, 130431 | Y | N |  |  | 13261 | 5533
5535 | Lynx to Rio Pecos: Rebuild 138 kV line | Rebuild Lynx to Rio Pecos 138 kV line |  | Lynx | Rio Pecos | Planned | 788 - 0973 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2648 | 2019-01-31 |  | 138 | 0 | 2.23 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 6601, 60400 | Y | N |  |  | 13263 | 5535
5555B | Clodine-Obrien Ckt25 & Ck73 Thermal Uprate | Upgrade Ckt.73 Clodine to Obrien to increase thermal ratings | Delay in project schedule | Clodine | Obrien | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1118 | 2019-01-31 |  | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  | 44140, 44512 | Y | N |  |  | 13284 | 5555
5555A | Clodine-Obrien Ckt25 & Ck73 Thermal Uprate | Upgrade Ckt.25 Clodine to Obrien to increase thermal ratings | Delay in project schedule | Clodine | Obrien | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1118 | 2019-01-31 |  | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  | 44145, 44511 | Y | N |  |  | 13283 | 5555
6203 | Premont - Falfurrias 69 kV Line | Rehab Premont - Falfurrias 69 kV Line |  | Premont | Falfurrias | Planned | 818 - 1002 | AEP TCC | Andrew Garlick dnlyons@aep.com 918-599-2698 | 3616 | 2019-01-31 |  | 69 | 0 | 12.25 | 0 |  | Jim Wells | Brooks | Tier 4 |  |  |  | 8508, 8894 | Y | N |  |  | 13928 | 6203
5763D | CHORIN to STRANG Ckt.87 | Upgrade STRANG and CHORIN to 4000 Amp equipment |  | STRANG | CHORIN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-02-01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40320, 41500 | Y | N |  | 0 | 44229 | 5763
6011 | Laredo Plant: Replace 138/69 kV autotransformer | Upgrade 138/69 kV autotransformer capacity at Laredo Plant |  | Laredo Plant |  | Planned | 806 - 0991 | AEP TCC | Randy Weaver dnlyons@aep.com 918-599-2698 | 3595 | 2019-02-04 |  | 138 | 0 | 0 | 180 |  | Webb |  | Tier 4 |  |  |  | 8530, 8290, 8642, 8293, 8298, 8303 | Y | N |  |  | 13728 | 6011
6120 | Sabinal - Knippa 69 kV line | Rehab Sabinal - Knippa 69 kV line |  | Sabinal | Knippa | Planned | 811 - 0996 | AEP TCC | James Nivens dnlyons@aep.com 918-599-2698 | 3602 | 2019-02-06 |  | 69 | 0 | 2.655 | 0 |  | Uvalde |  | Tier 4 |  |  |  | 8628, 8630 | Y | N |  |  | 13846 | 6120
10TPIT0062 | Marion Power Transformer Addition (Formerly Weil Road) | Expand the Marion substation 138-kV bus. Install a 138-26.18 kV 40 MVA power transformer at Marion 138 kV bus. | Delayed due to ERCOT outage restrictions | Marion |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org | 1015120 | 2019-02-15 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7178 | Y | N |  |  | 9648 | 2384
6123 | Turtle Creek - La Pryor 69 kV Line | Rehab Turtle Creek - La Pryor 69 kV Line |  | Turtle Creek | La Pryor | Planned | 810 - 0995 | AEP TCC | James Nivens dnlyons@aep.com 918-599-2698 | 3599 | 2019-02-18 |  | 69 | 0 | 14.603 | 0 |  | Zavala |  | Tier 4 |  |  |  | 8243, 8672 | Y | N |  |  | 13849 | 6123
5766A | Knight to BUNKER to HOC Ckt.08 Upgrades | Upgrade Ckt.08 Knight to BUNKER to increase thermal ratings |  | Knight | BUNKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-02-27 |  | 138 | 0 | 1.6 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47331, 47340 | Y | N |  |  | 13512 | 5766
5766B | Knight to BUNKER to HOC Ckt.08 Upgrades | Upgrade Ckt.08 HOC to BUNKER to increase thermal ratings |  | HO Clarke | BUNKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47150, 47340 | Y | N |  | Cost is Reflected in Phase A of TPIT Project 5766 | 13536 | 5766
5970 | Wolfgang to Rotan 69 kV line: Rebuild 69 kV line | Rehab Wolfgang to Rotan 69 kV line |  | Wolfgang | Rotan | Planned | 786 - 0971 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2659 | 2019-02-28 |  | 69 | 0 | 12.41 | 0 |  | Kent | Fisher | Tier 4 |  |  |  | 6162, 6196 | Y | N |  |  | 13685 | 5970
6081 | Chillicothe to Vernon Main 69 kV line: Rebuild 69 kV line | Rehab Chillicothe to Vernon Main 69 kV line | Contact and Schedule Update | Chillicothe | Vernon Main | Planned | 786 - 0971 | AEP TNC | Joseph Page mlforcum@aep.com 918-599-2674 | 2695 | 2019-02-28 |  | 69 | 0 | 14.17 | 0 |  | Hardeman | Wilbarger | Tier 4 |  |  |  | 6056, 6057, 6058 | Y | N |  |  | 13805 | 6081
6358 | Christoval to Arrott 69 kV line: Rebuild 69 kV line | Rehab Christoval to Arrott 69 kV line |  | Christoval | Arrott | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2721 | 2019-02-28 |  | 69 | 0 | 8.17 | 0 |  | Tom Green | Schleicher | Tier 4 |  |  |  | 6495, 6496 | Y | N |  |  | 14102 | 6358
5230 | Sonne Substation Addition | Provide transmission service for a generator off T554 radial 138-kV line between North McCamey and Tippet Substations. |  | North McCamey | Tippet | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015964 | 2019-03-01 |  | 138 | 0 | 0 | 0 |  | Upton | Pecos | Tier 4 |  |  |  | 76020, 76021, 76595 | Y | N |  |  | 12903 | 5230
6781 | Leakey - Utopia Transmission Line Overhaul | Rebuild T281 Leakey to Utopia to be 138 kV capable with a nominal conductor rating of 223 MVA at 138 kV (Single Drake) with ADSS and operated at 69 kV. | Accelerating Schedule | Leakey | Utopia | Planned |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-33726078 | 353985 | 2019-03-01 |  | 69 | 0 | 17.95 | 0 |  | Real | Bandera | Tier 3 |  |  |  | 7426, 7428, 7439, 7440 | Y | N |  |  | 14575 | 6781
5223C | 2015 RTP rebuild 4 sections from George West through Mathis | Rebuild 4/0 ACSR from Kittie West Substation to George West Substation to Mathis with 795 ACSR that is 138 capable. 2015 RTP |  | Kittie West | George West Substation | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-03-01 |  | 69 | 0 | 6.44 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  | 5684, 5683 | Y | N |  | 0 | 43338 | 43336
4577 | BRYN_4577_Dansby_Rebuild | Convert Dansby 69kV bus to Double Bus, Double Breaker configuration |  |  |  | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2019-03-02 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  | 32875, 32897 | Y |  |  |  | 12159 | 4577
5767 | TECO to Grant Ckt.37 | Upgrade Ckt.37 TECO to Grant to increase thermal ratings |  | TECO | Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-03-28 |  | 138 | 0 | 0.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47110, 47430 | Y | N |  |  | 13513 | 5767
4185 | HO Clarke Partial Load Conversion (TR1) | Convert HO Clarke TR1 load to 138kV. Tap off of Ckt.90 HO Clarke to Garrott | - Delayed project schedule | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1112 | 2019-03-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47155, 47160, 47150, 47322 | Y | N |  |  | 11715 | 4185
4487 | Nueces Area 69kV Reinforcement | Expand and add new 138/69kV Auto at Valero East 69kV substation. Add 5th breaker to Champlin 138kV substation. Construct Champlin to Valero East 138kV Line. |  | Champlin | Valero East | Planned | 709 - 0879 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2903 | 2019-03-30 |  | 138 | 1.6 | 0 | 200 |  | Nueces |  | Tier 4 |  |  |  | 8528, 8476, 8859 | Y | N |  |  | 13570 | 4487
4495 | AEP_4495_Champlin | Expand existing breaker configuration to a four (4) breaker ring bus expandable to a six (6) breaker ring bus configuration. |  | Champlin | Champlin | Planned | 694 - 0864 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3541 | 2019-03-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8476 | Y | N |  |  | 12064 | 4495
4996 | HO Clarke Load Conversion | Convert HO Clarke TR2 & TR3 to 138kV service. Tap off of Ckt.25 HO Clarke to Fondren. | - Delayed project schedule | HO Clarke | Fondren | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-03-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 47151, 47152, 47160, 47150, 47412 | Y |  |  |  | 12629 | 4996
5221 | Move Oaks load to 138 kV bus | Move the Oaks load from the 69 kV to the 138 kV instead of replacing auto. 2015 RTP |  | Oaks |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-03-30 |  | 138 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5713 | Y | N |  |  | 12888 | 5221
5242 | Clodine to Barker Ckt.73 Thermal Uprate | Upgrade Ckt.73 Clodine to Barker to increase thermal ratings | Delay in project schedule | Clodine | Barker | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2019-03-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44052, 44140 | Y | N |  |  | 12917 | 5242
6314A | BASF to HOFMAN to Lake Jackson Ckt.02 Upgrades | Upgrade 138kV Ckt.02 BASF to HOFMAN to increase thermal ratings. | - Delayed project schedule | BASF | HOFMAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-03-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 42150, 42810 | Y | N |  |  | 14047 | 6314
5024 | Crane Loop: Rebuild 69 kV line | Rebuild Crane Loop 69 kV line |  | Crane | Crane | Planned | 738 - 0921 | AEP TNC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | 2619 | 2019-03-31 |  | 69 | 0 | 8.05 | 0 |  | Crane | Crane | Tier 4 |  |  |  | 6600, 6603, 6607, 6609, 6606, 6608, 6613 | Y | N |  |  | 12661 | 5024
6064 | Anson to Exxon Hawley Tap 69 kV line: Rebuild 69 kV line | Rehab Anson to Exxon Hawley Tap 69 kV line |  | Anson | Exxon Hawley Tap | Planned | 786 - 0971 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2674 | 2019-03-31 |  | 69 | 0 | 10.39 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6175, 6176, 6238 | Y | N |  |  | 13784 | 6064
6165 | Whitepoint: Install 100 MVAR Reactor | Whitepoint: Install 100 MVAR Reactor |  | Whitepoint |  | Planned | 867 - 1045 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3654 | 2019-03-31 |  | 345 | 0 | 0 | 0 | 0,-100 | San Patricio |  | Tier 4 |  |  |  | 8956 | Y | N |  |  | 13890 | 6165
6166 | Carbide - Greenlake: Rebuild 69 kV Line | Carbide - Greenlake: Rebuild 69 kV Line |  | Carbide | Greenlake | Planned | 868 - 1046 | AEP TCC | Brad Duvall dnlyons@aep.com 918-599-2698 | 3655 | 2019-03-31 |  | 69 | 0 | 2.2 | 0 |  | Calhoun |  | Tier 4 |  |  |  | 8149, 8159 | Y | N |  |  | 13891 | 6166
6245 | Sun Valley to Masterson Field 69 kV line: Rebuild 69 kV line | Rehab Sun Valley to Masterson Field 69 kV line |  | Sun Valley | Masterson Field | Planned | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2702 | 2019-03-31 |  | 69 | 0 | 7.17 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 6641, 6642 | Y | N |  |  | 13973 | 6245
6314B | BASF to HOFMAN to Lake Jackson Ckt.02 Upgrades | Upgrade 138kV Ckt.02 HOFMAN to Lake Jackson to increase thermal ratings. | - Delayed project schedule | HOFMAN | Lake Jackson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-03-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 42810, 42880 | Y | N |  | Cost included in 18TPIT6314A | 14362 | 6314
6397 | Treadwell: Build new 138 kV station | Interconnect Cactus Flats wind farm on the SAPS to Yellowjacket 138 kV line | Contact, Schedule, and Cost Update | Treadwell |  | Planned | 875 - 1053 | AEP TNC | Tom Reynolds mlforcum@aep.com 918-599-2674 | 2727 | 2019-03-31 |  | 138 | 0 | 0 | 0 |  | Concho |  | Tier 4 |  |  |  | 60423, 6365, 6480 | Y | Y |  |  | 14156 | 6397
6715 | Noelke Substation Addition | Construct a new substation named Noelke off the Bakersfield to Schneeman Draw transmission line to support a generation interconnection request (20INR0011). |  | Bakersfield | Schneeman Draw | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1018746 | 2019-03-31 |  | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  | 7053, 76002, 76005 | Y | N |  |  | 14498 | 6715
6568 | SAPS: Replace the 138/69 kV autotransformer | Replace the 138/69 kV autotransformer at SAPS with a 130 MVA autotransformer | Schedule Update | SAPS |  | Planned | 839 - 1023 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2818 | 2019-04-01 |  | 138 | 0 | 0 | 130 |  | Tom Green |  | Tier 4 |  |  |  | 6480, 76320, 6478 | Y | N |  |  | 14319 | 6568
4454 | Henne to Comal Transmission Line Upgrade | Upgrade the 7.6 mile Henne (7174) - Comal (7176) 138-kV transmission line from 159 MVA to 380 MVA using single 959 ACSS Suwannee conductors. |  | Henne | Comal | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015116 | 2019-04-09 |  | 138 | 0 | 7.6 | 0 |  | Comal | Comal | Tier 4 |  |  |  | 7172, 7174, 7176 | Y | N |  |  | 12014 | 4454
5259 | Lotebush: Add dynamic reactive device | Rebuild Solstice to Yucca Drive 138 kV line and add dynamic reactive devices at Lotebush | Description Update | Lotebush |  | Planned | 713 - 0946 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2638 | 2019-04-30 |  | 138 | 0 | 0 | 0 | -100100 | Reeves |  | Tier 1 | 2015-12-15 | 2016-09-21 | 2016-10-26 | 60392, 60425 | Y | N |  |  | 14312 | 5259
5978 | Tankersley to Mathis Field 69 kV line: Rebuild 69 kV line | Rehab Tankersley to Mathis Field 69 kV line |  | Tankersley | Mathis Field | Planned | 786 - 0971 | AEP TNC | Bill Roberts mlforcum@aep.com 918-599-2674 | 2663 | 2019-04-30 |  | 69 | 0 | 9.99 | 0 |  | Irion | Tom Green | Tier 4 |  |  |  | 6477, 6528 | Y | N |  |  | 13693 | 5978
6021 | Haskell Tap 1 to Paint Creek 69 kV line: Rebuild 69 kV line | Rehab Haskell Tap 1 to Paint Creek 69 kV line |  | Haskell Tap 1 | Paint Creek | Planned | 786 - 0971 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2669 | 2019-04-30 |  | 69 | 0 | 14 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  | 6005, 6159, 6171, 6174 | Y | N |  |  | 13738 | 6021
6101 | Lon Hill: Replace 345/138 kV autotransformers | Replace 345/138 kV autotransformers at Lon Hill | Formerly TPIT project 6040 | Lon Hill |  | Planned | 829 - 1013 | AEP TCC | Bill Roberts dnlyons@aep.com 918-599-2698 | 3630 | 2019-04-30 |  | 345 | 0 | 0 | 1350 |  | Nueces |  | Tier 4 |  |  |  | 8455, 8452, 8499, 8502 | Y | N |  | Formerly TPIT project 6040 | 13826 | 6101
6202 | North Ella - Premont 69 kV Line | Rehab North Ella - Premont 69 kV Line |  | North Ella | Premont | Planned | 818 - 1002 | AEP TCC | Andrew Garlick dnlyons@aep.com 918-599-2698 | 3615 | 2019-04-30 |  | 69 | 0 | 10.7 | 0 |  | Jim Wells |  | Tier 4 |  |  |  | 8878, 8894 | Y | N |  |  | 13927 | 6202
6345 | Yellowjckt to Menard Phillips T 69 kV line: Rebld 69 kV line | Rehab Yellowjacket to Menard Phillips Tap 69 kV line |  | Yellowjacket | Menard Phillips Tap | Planned | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2711 | 2019-04-30 |  | 69 | 0 | 15.3 | 0 |  | Menard | Kimble | Tier 4 |  |  |  | 6363, 6401 | Y | N |  |  | 14089 | 6345
6353 | Kirkland to Acme Best Wall 69 kV line: Rebuild 69 kV line | Rehab Kirkland to Acme Best Wall 69 kV line |  | Kirkland | Acme Best Wall | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2717 | 2019-04-30 |  | 69 | 0 | 14.6 | 0 |  | Childress | Hardeman | Tier 4 |  |  |  | 6052, 6053 | Y | N |  |  | 14097 | 6353
6359 | Arrott to Pave Paws 69 kV line: Rebuild 69 kV line | Rehab Arrott to Pave Paws 69 kV line |  | Arrott | Pave Paws | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2722 | 2019-04-30 |  | 69 | 0 | 6.47 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  | 6494, 6496, 6497 | Y | N |  |  | 14103 | 6359
6579 | DALTON 138kV Substation | Construct service to new 138kV DALTON customer-owned substation. Loop through Ckt.86 CITIES to WINFRE. |  | DALTON | DALTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-04-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  | 40740, 40220, 40340, 40855, 40764, 40857 | Y |  |  | 0 | 43366 | 6579
6745 | Reading: New Distribution Station | Add New Reading Distribution Station |  | Uvalde | STEC Downie | Planned | 876 - 1054 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3663 | 2019-04-30 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 4 |  |  |  | 8024, 5885, 8234 | Y | N |  |  | 14538 | 6745
44385 | Victoria City | [6 empty] | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2019-04-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 8174, 8172, 111363 | Y |  |  | 0 | 44386 | 44385
4464B | Comal to Marion Transmission Line Upgrade | Upgrade/Replace underrated switches to 3000 Amp Switches. Replace and increase fault interrupting rating of breakers 430, 440, 3370, 3380, 5680, 5690, 5700, 2970, 5870 to 63kA. Replace and upgrade CS2965 and CS2975 to 3000 Amp 40kA. Replace and upgrade CS5395 and CS5405 to 40kA. | Switches may be dynamically rated during Winter peak conditions. | Comal | Marion | Planned |  | NBU | Gregory Thomas gthomas@nbutexas.com 830-608-8953 |  | 2019-05-01 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  | 7176, 7456, 7459 | Y | N |  |  | 12381 | 4464
4501 | Trading Post Circuit Breaker Addition | Install Line Breakers at Trading Post on the Trading Post to Marshall Ford and the Trading Post to Cedar Valley 138kV lines (T315). |  | Trading Post |  | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2019-05-01 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7505 | Y | N |  |  | 12073 | 4501
5048 | Falfurius: Upgrade | Replace DSTATCOM with SVC Plus at Falfurius station +/- 50 MVAR capability |  | Falfurrias |  | Under Construction | 873-1049 | ETT | Kenneth 'Rich' Haley 918-599-2664 dnlyons@aep.com | 3658 | 2019-05-01 |  | 69 | 0 | 0 | 0 |  | Brooks |  | Tier 4 |  |  |  | 88508, 8508 | Y | N |  |  | 12699 | 5048
6342 | Cross Plains to Santa Anna T 69 kV line: Rebuild 69 kV line | Rehab Cross Plains to Santa Anna Tap 69 kV line | Cost Update | Cross Plains | Santa Anna Tap | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2719 | 2019-05-01 |  | 69 | 0 | 14.72 | 0 |  | Callahan | Coleman | Tier 4 |  |  |  | 6352, 6356, 6357 | Y | N |  |  | 14086 | 6342
6785 | Leakey Substation Upgrade | Replace 69/25 kV and 69/12.5 kV Power Transformers with dual-rated 138-69/25-12.5 kV Power Transformers and add one 138 kV Circuit Breaker to be operated at 69 kV. | Accelerating Schedule | Leakey |  | Planned |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-33726078 | 353985 | 2019-05-01 |  | 69 | 0 | 0 | 0 |  | Bandera |  | Tier 4 |  |  |  | 7426 | Y | N |  |  | 14579 | 6785
6749 | Roasata: Build 138kV Substation | Build new Rosata 138kV POD Switch on Coleto Creek to Kenedy 138kV Line |  | Coleto Creek | Kenedy | Planned | 898 - 1076 | AEP TCC/GVEC | Daniel Lyons dnlyons@aep.com 918-599-2698 | 3682 | 2019-05-02 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  | 88153, 8162, 8186 | Y | Y |  |  | 14542 | 6749
6754 | Bunsen: Add Breakers | Add Breakers at Bunsen 138kV Substation for customer Interconnect. Build 0.75 mile of 138kV Line between Bunsen and Customer. |  | Bunsen |  | Planned | 902 - 1080 | AEP TCC | Daniel Lyons dnlyons@aep.com 918-599-2698 | 3686 | 2019-05-02 |  | 138 | 0.8 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8614, 8459 | Y | N |  |  | 14547 | 6754
4758 | Sand Lake 138 kV Switching Station | Construct new switching station |  | Sand Lake |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8340 | 2019-05-14 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 11097, 1086, 11086, 11104, 11197 | Y | N |  |  | 12353 | 4758
2941B | North Main Switch third transmission source |  |  | North Main Tap | North Main Sw | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5161-E | 2019-05-15 |  | 138 | 0 | 0.1 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2093, 2106 | Y | N |  |  | 14910 | 2941
16TPIT0050 | Northaven - Renner 138 kV Line | Upgrade existing line | Project Deferral | Northaven | Renner | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4108-E | 2019-05-15 |  | 138 | 0 | 8.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2356, 2357, 2596, 2597, 2613, 2614, 2615, 2616, 2657, 2659 | Y | N |  |  | 11845 | 3065
17TPIT0023 | Northwest Carrollton - Norwood 138 kV Line | Upgrade existing double-circuit Northwest Carrollton - Carrollton line section | Project Deferral | Northwest Carrollton | Carrollton | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4110-E | 2019-05-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 4 |  | 2017-01-11 |  | 2362, 2363, 2409, 2535, 2536, 2537, 2540, 2541, 2542, 2550, 2551, 2552, 12552 | Y | N |  |  | 10433 | 3089
17TPIT0024 | Payne - Anna Switch 138 kV Line | Upgrade existing line | Project Deferral | Payne | Anna Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R938-E | 2019-05-15 |  | 138 | 0 | 20.8 | 0 |  | Grayson | Collin | Tier 4 |  |  |  | 1713, 1748, 1754, 1839, 2374 | Y | N |  |  | 10561 | 3213
4274 | Navarro - Corsicana 69 kV Line | Upgrade existing line |  | Navarro | Corsicana | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R793 | 2019-05-15 |  | 69 | 0 | 12.5 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  | 3468, 3475, 3479, 3480, 13468 | Y | N |  |  | 11823 | 4274
4759 | Riverton - Sand Lake 138 kV Line | Construct new 138 kV line | Construction schedule change | Riverton | Sand Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8341 | 2019-05-15 |  | 138 | 25 | 0 | 0 |  | Reeves | Reeves | Tier 2 | 2016-02-01 | 2016-11-11 |  | 11083, 11097 | Y | N |  |  | 12354 | 4759
5312 | Mitchell Bend - Rocky Creek 345 kV line | Upgrade existing line | Project Deferral | Mitchell Bend | Rocky Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1736 | 2019-05-15 |  | 345 | 0 | 32.8 | 0 |  | Hood | Tarrant | Tier 4 |  | 2016-07-22 | 2016-08-22 | 1877, 1880 | Y |  |  |  | 12988 | 5312
5834 | Salt Creek to Cogdell | RPG Project for Salt Creek (Bus# 743) to Clairmont (Bus# 752) to ONCOR's Cogdell (Bus# 1402) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 14032 | 2019-05-15 |  | 138 | 20 | 0 | 0 |  | Kent | Scurry | Tier 2 | 2015-12-21 | 2016-06-27 |  | 752, 743, 6198 | Y |  |  |  | 13576 | 5834
5974 | Saginaw - Denton Ave/Springdale 138 kV DCKT Line | Rebuild existing 69 kV Lines | Construction schedule change | SAGINAW | DENTON AVE | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5245 | 2019-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1957, 2102, 2146, 2148, 2156, 2157 | Y | N |  |  | 13689 | 5974
6269 | Ennis Creek 138 kV Switching Station | Rebuild existing Ennis Creek 138 kV Switching Station |  | Ennis Creek |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9026 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Scurry |  | Tier 4 | 2015-12-21 | 2016-10-11 |  | 1410 | Y | N |  |  | 13999 | 6269
6759 | Ranger Gulf 69 kV Emergency Capacitors | Install 18.4 MVar Cap Bank at Ranger Gulf |  | Ranger Gulf | Ranger Gulf | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1746 | 2019-05-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Eastland | Eastland | Tier 4 |  |  |  | 1627 | Y | N |  |  | 14553 | 6759
6763 | Round Rock switching station | Reconfigure existing 138 kV Round Rock switching station |  | Round Rock | Round Rock | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R767 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | Y | N |  |  | 14557 | 6763
6764 | Round Rock Capacitors | Upgrade existing capacitor banks at Round Rock Switching Station |  | Round Rock | Round Rock | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R764 | 2019-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Williamson | Williamson | Tier 4 |  |  |  | 3668 | Y | N |  |  | 14558 | 6764
6778 | Tri Corner - Watermill 345 kV Line | Upgrade existing line |  | WATERMILL | TRI CORNER | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4226 | 2019-05-15 |  | 345 | 0 | 11.5 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2427, 2432, 3123 | Y | N |  |  | 14572 | 6778
6780 | Saginaw 138 kV Switching Station | Rebuild existing Saginaw 138 kV Switching Station |  | SAGINAW |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5277 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | Y | N |  |  | 14574 | 6780
7036 | Forest Grove Sw. Sta. to Mabank 138 kV line section | Rebuild the Forest Grove Sw. Sta. to Mabank 138 kV line section |  | Forest Grove Sw. Sta. | Mabank | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6014 | 2019-05-15 |  | 138 | 0 | 13.6 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  | 3131, 3173, 3176, 3177, 3175, 3178, 3179 | Y | N |  |  | 14858 | 7036
7092 | Moss Sw. Sta. 345/138 kV Autotransformer #2 | Moss Sw. Sta. 345/138 kV Autotransformer #2 |  | Moss |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8275 | 2019-05-15 |  | 345 | 0 | 0 | 600 |  | Ector |  | Tier 4 |  |  |  | 18526, 1018, 1019 | Y |  |  |  | 14926 | 7092
7099 | Yucca - Moss 138 kV Series Reactor | Yucca - Moss 138 kV Series Reactor |  | Yucca Dr | Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8447 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Ward | Ector | Tier 4 |  |  |  | 11015, 1009, 1019, 37980 | Y |  |  |  | 14933 | 7099
7100 | Wolf - General Tire 138 kV Series Reactor | Wolf - General Tire 138 kV Series Reactor |  | Wolf | General Tire | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8448 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Ward | Ector | Tier 4 |  |  |  | 11018, 1013, 1103 | Y |  |  |  | 14934 | 7100
7101 | Wink Sw. Sta. - No Trees Sw. Sta. 138 kV Line | Rebuild Wink Sw. Sta. - No Trees Sw. Sta. 138 kV Line |  | Wink | No Trees | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8406 | 2019-05-15 |  | 138 | 0 | 27.8 | 0 |  | Winkler | Winkler | Tier 3 |  |  |  | 1074, 1147, 131853 | Y |  |  |  | 14935 | 7101
7102 | Wink - Yukon 138 kV Second Circuit | Wink - Yukon 138 kV Second Circuit |  | Wink | Yukon | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8449 | 2019-05-15 |  | 138 | 26.6 | 9.4 | 0 |  | Winkler | Ector | Tier 4 |  |  |  | 1251, 1253, 1258, 1074, 1250, 1254, 11253 | Y |  |  |  | 14936 | 7102
7110 | Horseshoe Springs - Owl Hills 138 kV Line | Horseshoe Springs - Owl Hills 138 kV Line |  | Horseshoe Springs | Owl Hills | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8383 | 2019-05-15 |  | 138 | 10 | 0 | 0 |  | Culberson |  | Tier 4 |  |  |  | 11090, 11190 | Y |  |  |  | 14944 | 7110
7126 | Renner TPL 138 kV Capacitors | Upgrade existing capacitor banks |  | RENNER SWITCH | RENNER SWITCH | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3048 | 2019-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas | Dallas | Tier 4 |  |  |  | 2352, 2353 | Y | N |  |  | 14964 | 7126
7127 | East Levee 138 kV Emergency Capacitors | Upgrade East Levee 138 kV Emergency Capacitors |  | EAST LEVEE | EAST LEVEE | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4290 | 2019-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas | Dallas | Tier 4 |  |  |  | 2481, 2482 | Y | N |  |  | 14965 | 7127
7128 | Paris 138 kV Sw. Sta. | Rebuild existing switching station |  | PARIS |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4104 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Lamar |  | Tier 4 |  |  |  | 1693 | Y | N |  |  | 14966 | 7128
5499 | Everman - Cedar Hill Sw. Sta. 345 kV Line | Upgrade existing Everman - Cedar Hill Sw. Sta. 345 kV Line | Construction schedule change | Everman | Cedar Hill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5260 | 2019-05-15 11:52 |  | 345 | 0 | 39.14 | 0 |  | Tarrant | Dallas | Tier 4 | 2016-03-10 | 2016-07-22 |  | 1885, 1886, 1931, 1932, 2420 | Y | N |  |  | 13239 | 5499
6776 | Sherry - Brookhollow Tap 138 kV Line Upgrade | Upgrade existing line |  | SHERRY | BROOKHOLLOW TAP | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5247 | 2019-05-16 |  | 138 | 0 | 16 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1919, 2134, 2138, 2142, 2143 | Y | N |  |  | 14570 | 6776
6945 | Horseshoe Spring 138 kV Sw. Sta. | Horseshoe Spring 138 kV Sw. Sta. |  | Horseshoe Springs |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8408 | 2019-05-16 |  | 138 | 0 | 0 | 0 |  | Culberson |  | Tier 4 |  |  |  | 11190, 1096, 1097, 11079, 11103 | Y |  |  |  | 14767 | 6945
6946 | Add Horseshoe Draw 138 kV Dynamic Reactive Devices | Construct Horseshoe Draw 138 kV -250/+250 MVAR STATCOM |  | Horseshoe Spring | Horsehsoe Draw | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8418 | 2019-05-17 |  | 138 | 0 | 0 | 0 | 250250 | Culberson |  | Tier 1 | 2018-02-02 | 2018-05-22 |  | 11172, 11190 | Y |  |  |  | 14768 | 6946
7097 | Add Horseshoe Springs 138 kV Capacitors | Add 4 blocks of 36.8 MVAR capacitors at Horseshoe Springs Sw. Sta. |  | Horseshoe Springs |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8410 | 2019-05-18 |  | 138 | 0 | 0 | 0 | 0,147.2 | Culberson |  | Tier 1 | 2018-02-02 | 2018-05-22 |  | 11079, 11103, 11190 | Y |  |  |  | 14931 | 7097
6116 | Palacios - Carancahua 69 kV Line | Rehab Palacios - Carancahua 69 kV Line |  | Palacios | Carancahua | Planned | 817 - 1001 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3612 | 2019-05-22 |  | 69 | 0 | 13.36 | 0 |  | Matagorda | Jackson | Tier 4 |  |  |  | 8131, 8555 | Y | N |  |  | 13842 | 6116
6673A | Freeport - Bridge the Gap | Install capacitor bank #4 at Jones Creek substation (120MVAR). |  | Jones Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-29 |  | 138 | 0 | 0 | 0 | 0,120 | Brazoria |  | Tier 1 |  |  | 2017-12-12 | 42540 | Y | N |  |  | 14430 | 6673
6673C | Freeport - Bridge the Gap | Loop Ckt.27 STP-DOW into Jones Creek to create new Ckt.27 Jones Creek to STP |  | Jones Creek | STP | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-29 |  | 345 | 0.18 | 0 | 0 |  | Brazoria | Matagorda | Tier 1 |  |  | 2017-12-12 | 5915, 42500, 42530 | Y | N |  |  | 14443 | 6673
7007 | CNP_18TPIT7007_WAP_Reactor_Upgrades | Install (2) 5-Ohm Reactors at WA Parish as a fault duty upgrade |  | WAP | WAP | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-29 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44010, 44015, 44170, 44171, 44172, 44651, 44671, 110013, 110014 | Y |  |  |  | 14829 | 7007
4426B | Aritek to Chorin to SR Bertron Ckt. 87 Upgrades | Upgrade 138kV Ckt.87 Alexander Island to SR Bertron to increase thermal ratings. |  | Alexander Island | SRB | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40089, 40120, 40170, 40470, 40480, 41350, 41391, 41405, 41410, 41415, 41355, 41380, 41400, 41419, 41420, 41540 | Y | N |  | Cost Shown in TPIT Project 4426 Phase A | 13809 | 4426
5552A | North Belt to Greens to Lockwood Ckt.90 Thermal Uprate | Upgrade Ckt.90 North Belt to Greens Road to increase thermal ratings |  | North Belt | Greens Road | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1126 | 2019-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45822, 46112 | Y |  |  |  | 14476 | 5552
6109 | Stadium - Banquete 69 kV Line | Rehab Stadium - Banquete 69 kV Line |  | Stadium | Banquete | Planned | 816 - 1000 | AEP TCC | Andrew Garlick dnlyons@aep.com 918-599-2698 | 3610 | 2019-05-30 |  | 69 | 0 | 16.43 | 0 |  | Jim Wells | Nueces | Tier 4 |  |  |  | 8031, 8888, 8889 | Y | Y |  |  | 13835 | 6109
6673D | Freeport - Bridge the Gap | Loop Ckt.27 STP-DOW into Jones Creek to create new Ckt.27 Jones Creek to DOW |  | Jones Creek | DOW | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 |  |  | 2017-12-12 | 42500, 42530 | Y | N |  | Cost included in Phase C. | 14459 | 6673
6673B | Freeport - Bridge the Gap | Install 1st 138kV Automatically Switchable Capacitor Bank (Cap Bank #5 - 140 MVAR) at Jones Creek Substation |  | Jones Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-30 |  | 138 | 0 | 0 | 0 | 0,140 | Brazoria |  | Tier 1 |  |  | 2017-12-12 | 42535, 42540 | Y | N |  |  | 14431 | 6673
6696A | Nash 138kV Loop Conversion | Convert Nash Substation to 138kV loop service. Loop from Ckt.02 WA Parish to West Columbia. Reconductor the loop sections to Nash. |  | Nash | WA Parish/West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-30 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 42980, 42981, 43380, 44010 | Y | N |  |  | 14478 | 6696
7006B | CNP_18TPIT7006_HOC_Reactor_Upgrades | Install (1) 5-Ohm Reactor at HO Clarke as a fault duty upgrade |  | HOC | HOC | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47175, 42041, 47150, 47155, 47170, 47165, 49009 | Y |  |  |  | 14827 | 7006
3775 | Firewheel-WylieSW Line Upgrade | Firewheel to Wylie Switch 138 kV line upgrade to Cumberland conductor |  | Firewheel | WylieSW | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2019-05-31 |  | 138 | 0 | 17.77 | 0 |  | Dallas | Collin | Tier 4 |  |  |  | 821, 833 | Y | N |  |  | 11195 | 3775
4426A | Aritek to Chorin to SR Bertron Ckt. 87 Upgrades | Upgrade 138kV Ckt.87 ARITEK to CHORIN to increase thermal ratings. | Change in project schedule | ARITEK | CHORIN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40320, 41391 | Y | N |  |  | 11985 | 4426
4473 | Zorn to Marion 2nd 345-kV Transmission Line Addition | Add 345-kV Zorn (7042) to Marion (7044) 2nd circuit using bundled Suwannee. Portion of the CPS-Tie Project. |  | Zorn | Marion | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015208 | 2019-05-31 |  | 345 | 18 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 1 | 2014-06-29 | 2015-03-26 | 2015-04-14 | 7042, 7044 | Y | N |  |  | 12034 | 4473
4844 | 2nd Marion Autotransformer | Add a Second 345/138-kV Autotransformer at Marion. Part of the CPS Tie Project |  | Marion | Marion | Planned | 4473 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015208 | 2019-05-31 |  | 345 | 0 | 0 | 478 |  | Guadalupe | Guadalupe | Tier 1 | 2014-06-29 | 2015-03-26 | 2015-04-14 | 77044, 7044, 7178 | Y | N |  |  | 12446 | 4844
4871 | Webster Breaker Addition | Install breaker at Webster 138kV substation to connect ring buses | - Delay in project schedule | Webster |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1134 | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 43505, 42651, 42970, 43082, 43500, 43507 | Y | N |  |  | 12481 | 4871
5552B | North Belt to Greens to Lockwood Ckt.90 Thermal Uprate | Upgrade Ckt.90 Greens Road to Lockwood to increase thermal ratings |  | Greens Road | Lockwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1126 | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45822, 46031 | Y |  |  |  | 14477 | 5552
5715B | Red Bluff - 138kV Substation | Construct service to new 138kV Red Bluff distribution substation. Loop through Ckt.79 Terminal to Bayway |  | Red Bluff | Terminal/Bayway | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 1.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42930, 42931, 42170, 42955, 43225 | Y | N |  |  | 13455 | 5715
5763B | CHORIN to STRANG Ckt.87 | STRANG to Cedar Bayou Ckt.87 |  | STRANG | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40010, 41500 | Y | N |  | 0 | 44227 | 5763
5980 | Bison: Build 69 kV station | Construct new 69 kV ring bus at Powell Field Junction Tap | Schedule Update | Bison |  | Planned | 840 - 1024 | AEP TNC | Brad Duvall mlforcum@aep.com 918-599-2674 | 2680 | 2019-05-31 |  | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6548, 60395, 6545, 6547, 6549 | Y | N |  |  | 13695 | 5980
6065 | Abilene Northwest to Onyx 69 kV line: Rebuild 69 kV line | Rehab Abilene Northwest to Onyx 69 kV line |  | Abilene Northwest | Onyx | Under Construction | 786 - 0971 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2673 | 2019-05-31 |  | 69 | 0 | 3.61 | 0 |  | Taylor | Jones | Tier 4 |  |  |  | 6224, 6236 | Y | N |  |  | 13785 | 6065
6077 | Bronte Atlantic to Miles 69 kV line: Rebuild 69 kV line | Rehab Bronte Atlantic to Miles 69 kV line | Cost Update | Bronte Atlantic | Miles | Under Construction | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2691 | 2019-05-31 |  | 69 | 0 | 17.44 | 0 |  | Coke | Runnels | Tier 4 |  |  |  | 6410, 6418 | Y | N |  |  | 13800 | 6077
6640 | PARKES 138kV Substation | PARKES 138kV Substation for TDWP |  | Channel View | Haden | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40880, 40280, 40780 | Y |  |  |  | 14397 | 6640
6667 | Stewart and West Galveston 5MVAR Reactors | Remove existing 10MVAR reactor at Stewart 138kV substation and re-install 5MVAR reactor. Install 5MVAR reactor at West Galveston substation |  | Stewart & West Galveston |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 43290, 43400 | Y | N |  |  | 14451 | 6667
6673E | Freeport - Bridge the Gap | Install 2nd 138kV Automatically Switchable Capacitor Bank (Cap Bank #6 - 140 MVAR) at Jones Creek Substation |  | Jones Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 | 0,140 | Brazoria |  | Tier 1 |  |  | 2017-12-12 | 42536, 42540 | Y | N |  |  | 14432 | 6673
6673F | Freeport - Bridge the Gap | Install 3rd 800MVA autotransformer (A3) at Jones Creek substation |  | Jones Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 345 | 0 | 0 | 800 |  | Brazoria |  | Tier 1 |  |  | 2017-12-12 | 49038, 42530, 42540 | Y | N |  |  | 14444 | 6673
6673G | Freeport - Bridge the Gap | Install 7-Ohm in-series reactors at Jones Creek substation on Ckts.18 & 27 Jones Creek to STP |  | Jones Creek | STP | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Matagorda | Tier 1 |  |  | 2017-12-12 | 47531, 47532, 5915, 42530 | Y | N |  |  | 14445 | 6673
6696B | Nash 138kV Loop Conversion | Remove 69kV Nash tap from Ckt.45 Damon to West Columbia |  | Damon | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 69 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 42982, 42340, 43390 | Y | N |  | Cost included in Phase A | 14480 | 6696
6709 | Heines Substation Addition | Construct a new load-serving substation named Heines off the Airline to Naval Base (T476) transmission line. |  | Airline | Naval Base | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1018754 | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 78560, 8490, 8997 | Y | N |  |  | 14492 | 6709
6986A | Upton County Capacitor Bank Additions | Install one (1) 31.2 MVAR capacitor bank at Benedum Substation. |  | Benedum |  | Planned | 6717 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 | 0,31.2 | Upton |  | Tier 4 |  |  |  | 71213 | Y | N |  |  | 14803 | 6986
7006A | CNP_18TPIT7006_HOC_Reactor_Upgrades | Remove cap bank C1 from HOC Ckt.05 to WAP (position between HOC breakers H850 & H810) |  | HOC | HOC | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47171, 44081, 47170 | Y |  |  |  | 14828 | 7006
7013 | CNP_18TPIT_NASA_Sub_Upgrades | Upgrade NASA bus equipment to 4000A |  | NASA | NASA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42970 | Y |  |  |  | 14835 | 7013
7163 | T180 Lakeway - Marshall Ford MLSE Upgrade | Upgrade terminal equipment at Lakeway and Marshall Ford to achieve a planned static normal and emergency rating of 217 MVA on T180. |  | Lakeway | Marshall Ford | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 7356, 7538 | Y | N |  |  | 15004 | 7163
7164 | T195 Granite Mountain - Marble Falls MLSE Upgrade | Upgrade terminal equipment at Granite Mountain and Marble Falls to achieve a planned static normal and emergency rating of 221 MVA on T195. |  | Granite Mountain | Marble Falls | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  | 7348, 7474 | Y | N |  |  | 15005 | 7164
7165 | T505 Geronimo - Clear Springs MLSE Upgrade | Upgrade terminal equipment at Geronimo and Clear Springs to achieve a planned static normal and emergency rating of 493 MVA on T505. |  | Geronimo | Clear Springs | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7604, 7680 | Y | N |  |  | 15006 | 7165
7166 | T535 Plum - Piney Creek MLSE Upgrade | Upgrade terminal equipment at Plum and Piney Creek to achieve a planned static normal and emergency rating of 530 MVA on T535. |  | Plum | Piney Creek | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  | 7274, 7307 | Y | N |  |  | 15007 | 7166
43165 | Campbell138kVSwitchyardProjectAdded | Campbell138kVSwitchyardProjectAdded |  | Firewheel | Lookout | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2019-05-31 |  | 138 | 0 | 2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 838, 821, 828 | Y | N |  | 0 | 43166 | 43165
43452B | Angleton to MONSAN Ckt.04 Upgrades | Upgrade Ckt.04 Liverpool to PETSON to increase thermal limits |  | Liverpool | PETSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 5.06 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 42870, 43070 | Y |  |  | 0 | 43534 | 43452
43452C | Angleton to MONSAN Ckt.04 Upgrades | Upgrade Ckt.04 Angleton to Liverpool to increase thermal limits |  | Angleton | Liverpool | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 10.54 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 42110, 42870 | Y |  |  | 0 | 43535 | 43452
43452A | Angleton to MONSAN Ckt.04 Upgrades | Upgrade Ckt.04 PETSON to MONSAN to increase thermal limits |  | PETSON | MONSAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 0.93 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 42940, 43070 | Y |  |  | 0 | 43533 | 43452
44428 | Edith Clarke: Build 345 kV terminal | Interconnect Foard City wind farm at Edith Clarke | NEW | Edith Clarke |  | Planned | 934 - 1112 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 2747 | 2019-05-31 |  | 345 | 0 | 0 | 0 |  | Foard |  | Tier 4 |  |  |  | 60500 | Y | N |  | 0 | 44429 | 44428
44445 | Riley: Interconnect Electra Wind phase two | Interconnect Electra wind farm phase two, Lockett Station, into the Electra wind farm phase one, Digby substation | NEW | Riley |  | Planned | 935 - 1113 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 2748 | 2019-05-31 |  | 345 | 0 | 0 | 0 |  | Foard |  | Tier 4 |  |  |  | 6101 | Y | N |  | 0 | 44446 | 44445
44495 | Edith Clarke to Foard City: Build 345 kV line | Interconnect Foard City wind farm at Edith Clarke | NEW | Edith Clarke | Foard City | Planned | 934 - 1112 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 2746 | 2019-05-31 01:00 |  | 345 | 4 | 0 | 0 |  | Foard | Foard | Tier 4 |  |  |  | 142561, 60500 | Y | N |  | 0 | 44496 | 44495
08TPIT0033 | Gilleland to Techridge 138kV Circuit | Establish a new 138kV circuit from Gilleland to Techridge and maintain a normally close tie between AEN and LCRA's switchyard at Gilleland. |  | Gilleland Substation | Techridge Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_4276 PLAN_117_P207 | 2019-06-01 |  | 345 | 8 | 0 | 0 |  | Travis | Travis | Tier 2 |  | 2009-07-21 | 2009-07-21 | 9054, 9191, 7336, 9190 | Y | N |  |  | 8205 | 1029
11TPIT0084 | Hidden Lakes - New Substation | Build a new 138-12.47 kV substation to accommodate new subdivision growth along the FM 517 and FM 646 corridors in Dickinson, Texas. Project delayed until 2019 RMC. |  | Leave blank | Leave blank | Planned |  | TNMP | Anthony Hudson Anthony.Hudson@tnmp.com. 281-581-4712 | STE02416 | 2019-06-01 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38900, 38890, 42015 | Y | N |  |  | 8439 | 1261
4083 | CPSE_Merida to Westside Rebuild | Rebuild approximately four miles of 138 kV transmission circuit from Merida to Westside. |  | Merida | Westside | Planned | S-0773 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0235 | 2019-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5310, 5490 | Y | N |  |  | 11608 | 4083
4084 | Barton-Vega: Upgrade Ckt 928 | Reconductor to 2000 amps |  | Barton | Vega | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2019-06-01 |  | 138 | 0 | 4.05 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9158, 9285 | Y |  |  |  | 11609 | 4084
4323 | CPSE_Braunig to Brooks_MLSE | Upgrade terminal at Brooks and ensure a rating of 2000 A (minimum) at both Braunig and Brooks terminals |  | Braunig | Brooks | In-Service |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0669 | 2019-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5030, 5045 | Y | Y |  |  | 11875 | 4323
5144 | CPSE_Pleasanton Rd Transmission Rebuild | Rebuild approximately seven circuit miles of 138 kV transmission on Pleasanton Road from Loop 410 to Harlandale Tap. This project includes partial rebuild of the Sommers to Harlandale and Sommers to Merida 138 kV transmission circuits. |  | Sommers | Harlandale/Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0192 | 2019-06-01 |  | 138 | 0 | 7 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5190, 5310, 5395 | Y | N |  |  | 12797 | 5144
5218 | San Miguel 345/138 kV autotransformer replacements | Replace both existing 300 MVA autos with at least 600 MVA autos-2015 RTP |  | San Miguel |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-06-01 |  | 345 | 0 | 0 | 1200 |  | Atascosa |  | Tier 4 |  |  |  | 5908, 5909, 5901, 5902 | Y | N |  | Delayed from 2018 to 2019 in the 2016 RTP. | 12883 | 5218
5222 | Rebuild Dilley to Cotulla 69 kV line | Rebuild 4/0 ACSR 69 kV line with 138 kV capable 795 ACSR. 2015 RTP |  | Dilley | Cotulla | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-06-01 |  | 69 | 0 | 15.8 | 0 |  | La Salle | Frio | Tier 4 |  |  |  | 5863, 5876 | Y | N |  |  | 12889 | 5222
6742 | Heines Sub: New Distribution Station | Add New Heines Sub Distribution Station |  | Airline | Naval Base | Planned | 877 - 1055 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3664 | 2019-06-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8490, 8997, 78560 | Y | Y |  |  | 14535 | 6742
6773 | Callicaotte: Add New Distribution Station | Add New Callicaotte Distribution Station |  | Lon Hill | Haisley | Planned | 880 - 1058 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3667 | 2019-06-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8027, 8452, 8920 | Y | N |  |  | 14567 | 6773
6930 | New Paloma Substation | Adds new station and short line from Midstream |  | Midstream | Paloma | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-06-01 |  | 138 | 0.9 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 5644, 5643 | Y | N |  |  | 14749 | 6930
6746 | Valadez: Add New Distribution Station | Add New Valadez Distribution Station |  | Wooldridge | Barney Davis | Planned | 879 - 1057 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3666 | 2019-06-02 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8028, 8458, 8492 | Y | N |  |  | 14539 | 6746
6878 | AEN_New_AshtonW_138KV_SUB |  |  |  |  | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2019-06-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 9224, 9217, 9223 | Y |  |  |  | 14688 | 6878
6107 | Bonniview - Rincon 69 kV Line | Rehab Bonniview - Rincon 69 kV line |  | Bonniview | Rincon | Planned | 834 - 1018 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3641 | 2019-06-06 |  | 69 | 0 | 11.97 | 0 |  | Refugio | San Patricio | Tier 4 |  |  |  | 8416, 8805 | Y | N |  |  | 13833 | 6107
6427 | AEP_Refugio_Rincon | Upgrade line from Rincon - Refugio and terminal equipments at Rincon, Bonneview, Woodsboro, Heard, and Refugio |  | Refugio | Rincon | Under Construction |  | AEP TCC | Wilburt Robert dnlyons@aep.com 918-599-2698 |  | 2019-06-06 |  | 138 | 0 | 1 | 0 |  | San Patricio | Refugio | Tier 3 | 2017-03-28 | 2017-04-21 | 2017-05-08 | 8410, 8802, 8804, 8805, 8416 | Y | N |  |  | 14170 | 6427
6113 | Coy City Tap - Sunniland 69 kV Line | Rehab Coy City Tap - Sunniland 69 kV Line |  | Coy City Tap | Sunniland | Planned | 814 - 0998 | AEP TCC | James Nivens dnlyons@aep.com 918-599-2698 | 3605 | 2019-06-23 |  | 69 | 0 | 16.5 | 0 |  | Atascosa | Live Oak | Tier 4 |  |  |  | 8406, 8600 | Y | N |  |  | 13839 | 6113
17TPIT0008 | Marion to Cibolo T-Line (T-302) Circuit Addition | Add another 138 kV circuit, to existing Marion to Cibolo T-Line (T-302), 1192 ACSR, 4.81 miles; Replace 3-138 breakers to 63 kA rating at Marion; Add 138 terminal w 138 breaker and associated relaying at Cibolo sub | Construction Schedule | Marion | Cibolo | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2019-06-28 |  | 138 | 4.81 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7178, 7608 | Y | N |  |  | 10137 | 2792
5234 | Cibolo to Schertz T-Line (T303), Breaker upgrades | Add 138kV Breaker at Schertz, replace 138 breaker at Cibolo; upgrad associated 138 switches relaying to achieve 277 MVA rating on the Cibolo to Schertz Cirtcuit #2. | Construction Schedule | Cibolo | Schertz | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2019-06-28 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7608, 7610 | Y | N |  |  | 12907 | 5234
5915 | Cypress Creek Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Cypress Creek Substation (This is a two year project). |  | Cypress Creek |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017351 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7156 | Y | N |  |  | 13623 | 5915
5916 | Darst Creek Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Darst Creek Substation (138-kV capable). |  | Darst Creek |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017352 | 2019-06-30 |  | 69 | 0 | 0 | 0 |  |  | Guadalupe | Tier 4 |  |  |  | 78195 | Y | N |  |  | 13624 | 5916
5917 | Desert Mesa Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Desert Sky Tap #1 (S566). |  | Desert Sky Tap #1 |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017353 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 76022 | Y | N |  |  | 13625 | 5917
5920 | Fourmile Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Indian Mesa/Orion/NWP Tap (S564). |  | Indian Mesa/Orion/NWP Tap |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017380 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 76019 | Y | N |  |  | 13628 | 5920
5927 | King Mountain Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at King Mountain West Tap (S563). |  | King Mountain |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017391 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Crane |  | Tier 4 |  |  |  | 76635 | Y | N |  |  | 13635 | 5927
5930 | Robbins Switch Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Robbins Switch (S547). |  | Robbins Switch |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017400 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  | 76597 | Y | N |  |  | 13638 | 5930
5931 | Shiner Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Shiner (S183). |  | Shiner |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017402 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Lavaca |  | Tier 4 |  |  |  | 7238 | Y | N |  |  | 13639 | 5931
5934 | Warda Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Warda (S407). |  | Warda |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017411 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Fayette |  | Tier 4 |  |  |  | 7312 | Y | N |  |  | 13642 | 5934
6004 | Refugio - Melon Creek 69 kV line | Rehab Refugio - Melon Creek 69 kV line |  | Refugio | Melon Creek | Under Construction | 815 - 0999 | AEP TCC | Wilburt Roberts dnlyons@aep.com 918-599-2698 | 3607 | 2019-06-30 |  | 69 | 0 | 12.6 | 0 |  | Refugio | Calhoun | Tier 4 |  |  |  | 8410, 8800 | Y | N |  |  | 13721 | 6004
6115 | Melon Creek - Tatton 69 kV Line | Rehab Melon Creek - Tatton 69 kV Line |  | Melon Creek | Tatton | Under Construction | 815 - 0999 | AEP TCC | Bill Roberts dnlyons@aep.com 918-599-2698 | 3608 | 2019-06-30 |  | 69 | 0 | 7.75 | 0 |  | Refugio | Aransas | Tier 4 |  |  |  | 8410, 8800 | Y | N |  |  | 13841 | 6115
6246 | Masterson Fld to Pecos Valley 69 kV line: Rebuild 69 kV line | Rehab Masterson Field to Pecos Valley 69 kV line |  | Masterson Field | Pecos Valley | Planned | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2701 | 2019-06-30 |  | 69 | 0 | 8.84 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 6642, 6643 | Y | N |  |  | 13974 | 6246
6341 | Lake Pauline to Chillicothe 69 kV line: Rebuild 69 kV line | Rehab Lake Pauline to Chillicothe 69 kV line | Contact and Schedule Update | Lake Pauline | Chillicothe | Planned | 786 - 0971 | AEP TNC | Joseph Page mlforcum@aep.com 918-599-2674 | 2704 | 2019-06-30 |  | 69 | 0 | 9.4 | 0 |  | Hardeman | Hardeman | Tier 4 |  |  |  | 6048, 6057 | Y | N |  |  | 14085 | 6341
6377 | Pave Paws to Eldorado Live Oak 69 kV line: Rbld 69 kV line | Rehab Pave Paws to Eldorado Live Oak 69 kV line | Schedule Update | Pave Paws | Eldorado Live Oak | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2723 | 2019-06-30 |  | 69 | 0 | 7.71 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  | 6494, 6498 | Y | N |  |  | 14121 | 6377
6716 | Navigation Substation Addition | Construct a new load-serving substation named Navigation off the Citgo N. Oak Park to Valero (T436) transmission line. |  | Citgo N. Oak Park | Valero | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1019006 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 78460, 8426, 8466 | Y | N |  |  | 14499 | 6716
6717 | Roadrunner Substation Addition | Construct a new load-serving substation named Roadrunner off the Benedum to Midkiff (T611) transmission line. |  | Benedum | Midkiff (Oncor) | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1019008 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  | 71220, 1210, 71213 | Y | N |  |  | 14500 | 6717
6743 | Magellan Tank Farm: LCRA Interconnect | Add 138kV Tie Line between Navigation 138kV substation and Magellan¿s 138kV substation. Add Metering at Magellan's Substation. |  | Citgo N Oak |  | Conceptual | 905 - 1083 | AEP TCC/LCRA | Dan Lyons dnlyons@aep.com 918-599-2698 | 3689 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 78460 | Y | Y |  |  | 14536 | 6743
6580 | Clyde Magnolia Tap: Replace 69 kV capacitor bank | Replace 6 Mvar capacitor bank with a 7.2 Mvar capacitor bank at Clyde Magnolia Tap | Schedule Update | Clyde Magnolia Tap |  | Planned | 839 - 1023 | AEP TNC | Eric Johnson mlforcum@aep.com 918-599-2674 | 2819 | 2019-06-30 |  | 69 | 0 | 0 | 0 | 0,7.2 | Callahan |  | Tier 4 |  |  |  | 6302 | Y | N |  |  | 15003 | 7162
7172 | Refugio: Install 138/69 kV Auto | Install 90 MVA 138/69 kV autotransformer and a 138 kV breaker |  | Refugio |  | Under Construction | 100-0100 | AEP TCC | Wilburt Robert dnlyons@aep.com 918-599-2698 | 2021 | 2019-06-30 |  | 138 | 0 | 0 | 90 |  | Refugio |  | Tier 3 | 2017-03-31 | 2017-04-21 | 2017-06-01 | 8412, 89634, 8410 | Y | N |  |  | 15013 | 7172
43458 | Heights Cap Bank #1 | Relocate Harrisburg cap bank #1 to Heights substation and reduce size to 7.2 MVAR |  | Heights |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-06-30 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40800, 47680 | Y | N |  | 0 | 43459 | 43458
6387B | Greenville Arera System Enhancements |  |  |  |  | Planned |  | RYBRN | Charles Gibune 214-678-1192 |  | 2019-07-01 |  | 138 | 0 | 0 | 100 |  | Hunt | Hunt | Tier 3 | 2015-12-15 | 2016-02-15 |  | 837, 946 | Y | N |  | 0 | 44052 | 6387
6536 | T-283 Bellville South to Quanex Switch | Rebuild transmission line to 138-kV capable 959.6 ACSS-TW conductor due to maintenance on old 69 KV wood pole line and the future conversion to 138 KV. |  | Bellville South | Quanex Switch Structure | Planned |  | SBEC | Don Roberts droberts@sbec.org | WO# 17-6071 | 2019-07-01 |  | 69 | 0 | 3.33 | 0 |  | Austin | Austin | Tier 4 |  |  |  | 7269, 7660 | Y | N |  |  | 14276 | 6536
6986B | Upton County Capacitor Bank Additions | Install one (1) 31.2 MVAR capacitor bank at Roadrunner Substation. |  | Roadrunner |  | Planned | 6717 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-07-01 |  | 138 | 0 | 0 | 0 | 0,31.2 | Upton |  | Tier 4 |  |  |  | 71220 | Y | N |  |  | 14804 | 6986
43677 | Add 138kV MASCH Branch Substation | [5 empty] | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2019-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 934, 901, 916, 985 | Y | N | N/A | 0 | 43678 | 43677
44460 | Tesla: Build 345 kV terminal | Interconnect Misae Solar at Tesla | NEW | Tesla |  | Planned | 936 - 1114 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 2749 | 2019-07-31 |  | 345 | 0 | 0 | 0 |  | Foard |  | Tier 4 |  |  |  | 60501 | Y | N |  | 0 | 44461 | 44460
6741 | Closner: Add New Distribution Station | Add New Closner Distribution Station |  | Azteca | South East Edinburg | Planned | 883 - 1061 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3670 | 2019-08-01 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 8029, 8374, 8708 | Y | N |  |  | 14534 | 6741
44397 | Rebuild Continental | [6 empty] | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2019-08-02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 8799 | Y |  |  | 0 | 44398 | 44397
6834 | IH20 STATCOM RPG | IH20 STATCOM RPG Approved | Speedup project ISD to meet anticipated reactive support needs for West Texas system. | 38045 | 38046 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2019-08-15 |  | 138 | 0 | 0 | 0 | -190190 | Reeves | Reeves | Tier 1 | 2017-10-10 | 2017-12-06 |  | 38046, 38045 | Y |  |  | 0 | 44262 | 6834
6387D | Greenville Arera System Enhancements |  |  |  |  | Planned |  | RYBRN | Charles Gibune 214-678-1192 |  | 2019-08-30 |  | 138 | 5 | 0 | 0 |  | Hunt | Hunt | Tier 3 | 2015-12-15 | 2016-02-15 |  | 837, 6750 | Y | N |  | 0 | 44054 | 6387
4706E | HO Clarke to Webster Ckt.05 | Restore Southwyck to Friendswood Tap after upgrades |  | Southwyck | Friendswood Tap | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2019-08-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42651, 43262, 44361, 43500, 47150 | Y |  |  | 0 | 43257 | 4706
5195 | Rio Pecos: Build 138 kV terminal | Interconnect Pecos solar farm at Rio Pecos |  | Rio Pecos |  | Planned | 758 - 0942 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2633 | 2019-08-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6601 | Y | N |  |  | 12854 | 5195
7104 | Owl Hills - Tunstill POD 138 kV Line | Owl Hills - Tunstill POD 138 kV Line |  | Owl Hills | Tunstill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8428 | 2019-09-15 |  | 138 | 12 | 0 | 0 |  | Culberson | Reeves | Tier 1 | 2018-02-02 | 2018-05-22 |  | 11090, 11183 | Y |  |  |  | 14938 | 7104
3463 | Shady Bus Split | Reconfigure 69kV bus |  |  |  | Planned |  | BRYN | James Tanneberger 979-821-5763 |  | 2019-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 10843 | 3463
4504 | BRYN_4504_Rayburn_Rodgers_Upgrade | Reconductor Rayburn to Rodgers with 1033ACSR |  | 32861 | 32849 | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2019-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32861, 32849, 32872 | Y |  |  |  | 14761 | 4504
4575 | BRYN_4575_Steele_Store_138 | Construct Steele Store substation 138kV bus with 138/69kV auto. |  |  |  | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2019-09-30 |  | 138 | 0 | 0 | 0 |  | Burleson |  | Tier 4 | 2015-10-09 | 2015-11-06 |  | 32852, 32866, 32868 | Y |  |  |  | 12157 | 4575
5041 | BRYN_5041_Snook_to_Steele_Store | Construct 138kV line from Snook to Steele Store (Bundled 1033 ACSR - Curlew) as part of the reliability project to loop in Steele Store |  | 32857 | 32852 | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2019-09-30 |  | 138 | 9.2 | 0 | 0 |  | Burleson | Brazos | Tier 4 | 2015-10-09 | 2015-11-06 |  | 32852, 32857 | Y |  |  |  | 12690 | 5041
5045 | BRYN_5045_Rodgers_Sub | Construct new Rodgers Substation and remove Nall Lane Substation |  |  |  | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2019-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32849, 32872, 32874, 32877 | Y |  |  | 0 | 44459 | 5045
5885 | Tardis to Benjamin Tap: Rebuild 69 kV line | Construct new 138 kV ring bus Tardis on the Munday to Paducah 138 kV line, rebuild exiting Benjamin Tap to 138 kV, terminate into Tardis, convert Benjamin to 138 kV operation and build new 138 kV line from Benjamin to Katz (BEC) | Schedule Update | Benjamin | Tardis | Planned | 769 - 0954 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2656 | 2019-09-30 |  | 138 | 1.67 | 5.99 | 0 |  | Knox | Knox | Tier 2 | 2016-02-03 | 2016-05-01 | 2016-05-01 | 790, 6086, 6087, 6088, 6320, 6085, 6117, 6135, 6107 | Y | N |  |  | 13601 | 5885
5961 | Tardis: Build new 138 kV station | Construct new 138 kV ring bus Tardis on the Munday to Paducah 138 kV line, rebuild exiting Benjamin Tap to 138 kV, terminate into Tardis, convert Benjamin to 138 kV operation and build new 138 kV line from Benjamin to Katz (BEC) | Schedule Update | Tardis |  | Planned | 769 - 0954 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2683 | 2019-09-30 |  | 138 | 0 | 0 | 0 |  | Knox |  | Tier 2 | 2016-02-03 | 2016-05-01 | 2016-05-01 | 6320 | Y | N |  |  | 13676 | 5961
6387C | Greenville Arera System Enhancements |  |  |  |  | Planned |  | RYBRN | Charles Gibune 214-678-1192 |  | 2019-10-01 |  | 138 | 5 | 0 | 0 |  | Hunt | Hunt | Tier 3 | 2015-12-15 | 2016-02-15 |  | 837, 960 | Y | N |  | 0 | 44053 | 6387
7160 | Jackie Howard: Create Interconnection for Mesteno WF | Create interconnection for Mesteno windfarm by interconnecting the the Mesteno gen-tie line permanently to the last ETT transmission line deadend structure on the existing Del Sol - Jackie Howard line. Windfarm owner will own an interconnecting station named "Charlie Egner". |  | Del Sol | Jackie Howard | Planned | 924 - 1102 | ETT | Dan Lyons dnlyons@aep.com 918-599-2698 | 3701 | 2019-10-01 |  | 345 | 0 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  | 162101, 80355, 161553 | Y | N |  |  | 15001 | 7160
44352 | GreenvilleAreaProject | The project resolves for local voltage issues in Greenville area |  | Dent Road | Shelby | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2019-10-01 |  | 138 | 0 | 8.5 | 150 |  | Hunt | Hunt | Tier 4 |  |  |  | 837, 960, 6879, 946 | Y | N |  | 0 | 44353 | 44352
44379 | Raymond Wind | [6 empty] | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2019-10-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 8573, 8318, 8383 | Y |  |  | 0 | 44380 | 44379
5954 | Gillrina: Build new distribution station | Gillrina: Build new distribution station for STEC load |  | Banquette | Stadium | Planned | 805 - 0990 | AEP TCC/STEC | Bill Roberts dnlyons@aep.com 918-599-2698 | 3594 | 2019-10-30 |  | 69 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8031, 88031, 8888, 8889 | Y | Y |  |  | 13667 | 5954
6251 | Pecos Valley to TNMP Gomez 69 kV line: Rebuild 69 kV line | Rehab Pecos Valley to TNMP Gomez 69 kV line | Cost Update | Pecos Valley | Gomez | Planned | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2699 | 2019-10-31 |  | 69 | 0 | 14.2 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 6643, 38470 | Y | N |  |  | 13979 | 6251
6344 | Harriett to Miles 69 kV line: Rebuild 69 kV line | Rehab Harriett to Miles 69 kV line |  | Harriett | Miles | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2713 | 2019-10-31 |  | 69 | 0 | 5.71 | 0 |  | Tom Green | Runnels | Tier 4 |  |  |  | 6410, 6412 | Y | N |  |  | 14088 | 6344
7015 | CNP_18TPIT7015_Refuge_POI_Sub | Loop new 345kV REFUGE substation and install one generator lead for new generator interconnection to PEYTON substation (Peyton Creek Wind). (18INR0018) |  | STP | DOW | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-10-31 |  | 138 | 0 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  | 42400, 5915, 47532 | Y |  |  |  | 14837 | 7015
43536 | RIGBY (RIG) - New 138kV Substation | Construct service to new 138kV customer-owned RIGBY (RIG) substation. Loop through Ckt.86 Crosby to CONNOR |  | RIGBY | Crosby/ CONNOR | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-10-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  | 40670, 40390, 40665 | Y | N |  | 0 | 43537 | 43536
5558C | Proposed Substation |  |  |  |  | Planned |  | RYBRN | Charles Gibune 214-678-1192 |  | 2019-11-01 |  | 138 | 0 | 0 | 0 |  | Fannin |  | Tier 4 |  |  |  | 6817, 1807 | Y | N |  |  | 13289 | 5558
44391 | Victoria Port Temporary | [6 empty] | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2019-11-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 88142, 8143, 8172, 111343 | Y |  |  | 0 | 44392 | 44391
6784 | Schumansville T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Schumansville |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2019-11-22 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7609 | Y |  |  |  | 14578 | 6784
3754 | Heartland to Yellowjacket: Build 69 kV line | Build new 69 kV line from Heartland to Yellowjacket |  | Heartland | Yellowjacket | Planned | 637 - 0806 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2592 | 2019-11-30 |  | 69 | 32 | 0 | 0 |  | Mason | McCulloch | Tier 2 | 2014-01-23 | 2014-11-04 | 2014-11-17 | 6379, 60386, 6363, 6378, 6381, 6406 | Y | N |  |  | 12085 | 3754
4519 | Heartland: Build 69 kV station | Construct new 69 kV ring bus between MCEC Brady and Katemcy |  | Heartland |  | Planned | 637 - 0806 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2609 | 2019-11-30 |  | 69 | 0 | 0 | 0 |  | McCulloch |  | Tier 2 | 2014-01-23 | 2014-11-04 | 2014-11-17 | 60386 | Y | N |  |  | 12091 | 4519
4530 | Heartland to South Brady Tap: Rebuild existing & build new | Construct a new 69 kV line from Heartland to South Brady Tap and rebuild the existing line from Heartland to South Brady Tap |  | Heartland |  | Planned | 637 - 0806 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2610 | 2019-11-30 |  | 69 | 1.11 | 1.11 | 0 |  | McCulloch | McCulloch | Tier 2 | 2014-01-23 | 2014-11-04 | 2014-11-17 | 6379, 60386, 6378, 6381, 6406 | Y | N |  |  | 12105 | 4530
5914 | Crosswinds Substation Addition | LCRA TSC will construct a new three breaker ring bus substation to provide transmission service to PEC's planned distribution substation facility. |  | Turnersville | Goforth | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017349 | 2019-11-30 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  | 7503, 7500, 7501 | Y | N |  |  | 13622 | 5914
5932 | Jim Briley Substation Addition | Construct a motor operated load serving 138-kV substation off T499 between Geronimo and Seguin. | Substation name change from Strempel to Jim Briley | Seguin | Geronimo | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017707 | 2019-11-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7695, 7228, 7604 | Y | N |  |  | 13640 | 5932
6075 | Veribest T to Harriett 69 kV line: Rebuild 69 kV line | Rehab Veribest Tap to Harriett CVEC REA 69 kV line |  | Veribest Tap | Harriett CVEC REA | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2690 | 2019-11-30 |  | 69 | 0 | 8.4 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6409, 6412 | Y | N |  |  | 13797 | 6075
6354 | Acme Bestwall to Quanah 69 kV line: Rebuild 69 kV line | Rehab Acme Bestwall to Quanah 69 kV line | Cost Update | Acme Bestwall | Quanah | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2718 | 2019-11-30 |  | 69 | 0 | 5.72 | 0 |  | Hardeman | Hardeman | Tier 4 |  |  |  | 6051, 6052 | Y | N |  |  | 14098 | 6354
6823 | Goddard: Contruct a new 345 kV station | Interconnect Karankawa I Wind Farm at Goddard. Construct a three breaker ring in breaker and half configuration expandable to four rungs |  | Goddard |  | Under Construction |  | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 |  | 2019-11-30 |  | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8606, 5725, 8455 | Y | N |  |  | 14624 | 6823
7018 | Kleimann Substation Addition | Construct a 138-kV breakered substation, in a ring bus arrangement, between Columbus and Stafford Hill on circuit T544. The substation will provide transmission service to AEP load that will be transferred from Columbus Substation. Columbus Substation will be retired. |  | Columbus | Stafford Hill | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-11-30 |  | 138 | 0 | 0 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  | 78115, 78111, 78520 | Y | N |  |  | 14840 | 7018
7153 | Fort Stockton Plant to Solstice: Raise Structures on 138 kV | Raise Structures on the Fort Stockton Plant to Solstice 138 kV line | NEW | Fort Stockton Plant | Solstice | Planned | 923 - 1101 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2820 | 2019-11-30 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 6630, 60385 | Y | N |  |  | 14992 | 7153
05TPIT0065 | Highway 32-Wimberley | Upgrade and convert the Highway 32 (7546) to Wimberley (7496) transmission line to 138-kV and 795 ACSR (220-MVA). |  | Highway 32 | Wimberley | Planned |  | LST | Don Le Don.le@lonestar-transmission.com 512-236-3144 |  | 2019-12-01 |  | 138 | 0 | 4 | 0 |  | Hays | Hays | Tier 4 |  |  |  | 7496, 7545, 7546 | Y | N |  |  | 8173 | 997
3273 | Southton - New 138kV Substation | A new 138kV substation from 138kV Braunig to Brooks. |  | Southton | Braunig-Brooks | Planned | S-0750 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0217 | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5394, 5030, 5045 | Y | N |  | There are no transformers associated with this project | 10624 | 3273
5275 | Esperanza Substation Addition | Add a new load serving substation (ring bus) at Esperanza. The station will be built between Boerne an Fair Oaks Ranch off T503. |  | Boerne | Fair Oaks Ranch | Planned |  | LCRATSC/PEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016187 | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7710, 5470, 7168 | Y | N |  |  | 12951 | 5275
5491 | Whitestone - Leander 138kV Transmission Line Upgrade | Upgrade the Whitestone - Blockhouse (T469) and the Blockhouse - Leander (T326) 138kV Line to 441MVA. |  | Whitestone | Leander | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2019-12-01 |  | 138 | 0 | 5.4 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 7525, 7527, 7529 | Y | N |  |  | 13229 | 5491
5558D | Proposed Substation |  |  |  |  | Planned |  | RYBRN | Charles Gibune 214-678-1192 |  | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Fannin |  | Tier 4 |  |  |  | 6807, 1835 | Y | N |  |  | 13288 | 5558
5956 | Young: Build new distribution station | Young: Build new distribution station |  | Polk Avenue | Pharr | Planned | 804 - 0989 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 3593 | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 8030, 8372, 8373 | Y | N |  |  | 13669 | 5956
6537 | T-283 Quanex Switch Structure - Sunnyside | Rebuild transmission line to 138-kV capable 959.6 ACSS-TW conductor due to maintenance on old 69 KV wood pole line and the future conversion to 138 KV. |  | Quanex Switch Structure | Sunnyside | Planned |  | SBEC | Don Roberts droberts@sbec.org | WO# 17-6072 | 2019-12-01 |  | 69 | 0 | 9.75 | 0 |  | Austin | Austin | Tier 4 |  |  |  | 7660, 7664 | Y | N |  |  | 14277 | 6537
6755 | Stratton: Add Cap Bank | Add 14.4Mvar Cap Bank at Stratton 138kV Substation |  | Stratton |  | Planned | 903 - 1081 | AEP TCC | Daniel Lyons dnlyons@aep.com 918-599-2698 | 3687 | 2019-12-01 |  | 138 | 0 | 0 | 0 | 0,14.4 | Nueces |  | Tier 4 |  |  |  | 8514 | Y | N |  |  | 14548 | 6755
6787 | Utopia Susbtation Upgrade | Add two 138 kV Circuit Breakers to Line Terminals to be operated at 69 kV. | Accelerating Schedule | Utopia |  | Planned |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-33726078 | 353985 | 2019-12-01 |  | 69 | 0 | 0 | 0 |  | Bandera |  | Tier 4 |  |  |  | 7428, 7439, 7440 | Y | N |  |  | 14581 | 6787
6789 | Wirtz to Johnson City to Mountain Top Rebuild to 138kV | Rebuild the Wirtz to Johnson City to Mountain Top 69kV Line and convert to 138kV. Convert Johnson City Substation to 138kV. |  | Wirtz | Mountain Top | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2019-12-01 |  | 138 | 0 | 25 | 0 |  | Burnet | Blanco | Tier 4 | 2017-10-01 | 2017-12-01 |  | 7104, 7107, 7110, 7514, 7516, 7148, 7480 | Y | N |  |  | 14586 | 6789
6931 | New Cantu Substation | Adds new station and short line from W Edinburg-Alton line |  | West Edinburg | Alton | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-12-01 |  | 138 | 1.8 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 5770, 5771, 5772 | Y | N |  |  | 14750 | 6931
4275 | Hutto Switching Station 138 kV capacitors | Install shunt capacitors | Project Deferral | Hutto Switching Station |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R798 | 2019-12-15 |  | 138 | 0 | 0 | 0 | 0,220.8 | Williamson |  | Tier 4 |  |  |  | 3666 | Y | N |  |  | 11824 | 4275
4817 | TI Dallas - Kirkland Park/Coit Road 138 kV Line | Upgrade existing TI Dallas - Schroeder Road line section | Project Deferral | TI Dallas | Schroeder Road | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4202 | 2019-12-15 |  | 138 | 0 | 1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2607, 2633, 2636, 2637 | Y | N |  |  | 12423 | 4817
5500 | Lamar Blossom - Paris East Tap 138 kV Line | Construct new 138 kV line and ring bus | Project Deferral | Lamar Blossom | Paris East Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4103 | 2019-12-15 |  | 138 | 10 | 0 | 0 |  | Lamar | Lamar | Tier 4 |  |  |  | 1769, 1770, 1771 | Y | N |  |  | 13240 | 5500
6790 | Sargent Road-East Network 138 kV Line | Construct the new Sargent Road-East Network 138 kV Line | Project Deferral | Sargent Road | Oakland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4268 | 2019-12-15 |  | 138 | 2.5 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2905, 2949, 2969, 2970, 2971, 12447 | Y | N |  |  | 14588 | 6790
6833 | Grapevine 138 kV Switching Station | Establish new 138 kV switching station | Project Deferral | Grapevine Switch |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3211 | 2019-12-15 |  | 138 | 4.2 | 0 | 0 |  | Tarrant | Tarrant | Tier 2 |  |  |  | 2025, 555, 648, 2014, 2015, 2021, 2023, 2031, 12012, 12040 | Y | N |  |  | 14635 | 6833
7111 | Quarry Field 138 kV Sw. Sta. | Quarry Field 138 kV Sw. Sta. |  | Quarry Field |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8412 | 2019-12-15 |  | 138 | 0 | 0 | 0 |  | Loving |  | Tier 1 | 2018-02-02 | 2018-05-22 |  | 11189, 1093, 11091, 11094, 11100 | Y |  |  |  | 14946 | 7111
6111 | Carancahua - Point Comfort 69 kV Line | Rehab Carancahua - Point Comfort 69 kV Line |  | Carancahua | Point Comfort | Planned | 817 - 1001 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3613 | 2019-12-16 |  | 69 | 0 | 9.18 | 0 |  | Jackson | Calhoun | Tier 4 |  |  |  | 8132, 8555 | Y | N |  |  | 13837 | 6111
7114 | Rondo 138 kV Dynamic Reactive Devices | Rondo 138 kV Dynamic Reactive Devices |  | Quarry Field | Rondo | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8454 | 2019-12-17 |  | 138 | 0 | 0 | 0 | 250250 | Loving |  | Tier 1 | 2018-02-02 | 2018-05-22 |  | 11173, 11189 | Y |  |  |  | 14949 | 7114
7112 | Quarry Field 138 kV Capacitors | Quarry Field 138 kV Capacitors |  | Quarry Field |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8453 | 2019-12-18 |  | 138 | 0 | 0 | 0 | 0,147.2 | Loving |  | Tier 1 | 2018-02-02 | 2018-05-22 |  | 11189 | Y |  |  |  | 14947 | 7112
44381 | Causeway | [6 empty] | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2019-12-20 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 8744 | Y |  |  | 0 | 44382 | 44381
6002 | Gregory - Rincon 69 kV line | Rehab Gregory - Rincon 69 kV line |  | Gregory | Rincon | Planned | 833 - 1017 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3634 | 2019-12-26 |  | 69 | 0 | 4.34 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8416, 8421 | Y | N |  |  | 13719 | 6002
6872 | Support 69kV to 138kV Conversion Projects | Removing of Lawler substation from system to support 69kV to 138kV conversion projects |  |  |  | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2019-12-27 |  | 69 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 815, 820, 803, 806 | Y | N |  |  | 14681 | 6872
43456 | Greens Bayou 138kV Reconfigurations | Connect Greens Bayou 'East' and 'West' buses with (1) 8-Ohm Reactor. |  | Greens Bayou | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-29 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40710, 40715 | Y |  |  | 0 | 44326 | 43456
3776 | Big Lake to Powell Field Junction Tap: Rebuild 69 kV line | Rebuild Big Lake to Powell Field Junction Tap 69 kV line |  | Big Lake | Powell Field Junction Tap | Planned | 667 - 0836 | AEP TNC | Michael Richardson mlforcum@aep.com 918-599-2674 | 2593 | 2019-12-30 |  | 69 | 0 | 11.7 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  | 6533, 6546, 6547, 60395 | Y | N |  |  | 11196 | 3776
4186A | University Area 138kV Conversions | Convert University TR2 load to 138kV. |  | University | COUGAR | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2019-12-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47750, 47751, 47752, 47755, 47760, 47762, 47764, 42690, 47560, 47600, 47670, 47700, 49030 | Y | N |  |  | 14511 | 4186
6578A | Rebuild Ckt.66 Katy-Freeman-Betka-Hockley | Rebuild Ckt.66 Freeman-Betka-Hockley to address clearance issues (Phase 1 of overall Katy to Hockley upgrades) |  | Freeman | Hockley | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45675, 45880 | Y |  |  |  | 14822 | 6578
43456B | Greens Bayou 138kV Reconfigurations | Reposition Ckt.08F (GBY to Lychem) to connect to GBY 'West' bus |  | Greens Bayou | Uvalde | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40710, 40715, 41651 | Y |  |  | 0 | 44327 | 43456
3967 | Leander - Round Rock Transmission Line Addition | Construct a new 138kV transmission line from Leander to Ridgmar (new substation) to Spanish Oak (new substation) to Round Rock (approximately 13 miles) using bundled 795 ACSR Drake (446 MVA) conductor. | Substation name change from Hero Way to Ridgmar and Parmer to Spanish Oak | Leander | Round Rock | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014352 | 2019-12-31 |  | 138 | 13 | 0 | 0 |  | Williamson | Williamson | Tier 2 | 2013-12-10 | 2014-05-22 | 2014-06-10 | 7367, 7368, 3668, 7525 | Y | N |  |  | 11463 | 3967
4186B | University Area 138kV Conversions | Convert University TR3 load to 138kV. |  | University | Eastside | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47763, 47755, 47600, 47760 | Y | N |  | Cost included in 4186A | 14512 | 4186
5154 | Holford 138 kV new load substation and connections | Holford 138 kV new substation and its connections to CampbellSW and to Firewheel as well as some load growths at Holford |  | CampbellSW | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2019-12-31 |  | 138 | 0 | 1.5 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 835, 802, 821, 828, 838 | Y |  |  |  | 12810 | 5154
5165 | Borglum: Construct a new 138/69 kV station | Construct a new 138/69 kV Borglum station near Beeville | Schedule Update | Borglum |  | Planned | 742 - 0925 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2914 | 2019-12-31 |  | 138 | 0 | 0 | 130 |  | Bee |  | Tier 1 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8196, 8197, 8205, 8107, 8198, 8904 | Y | N |  |  | 13315 | 5165
5356 | Bakersfield: Build 345 kV terminal | Interconnect Maplewood solar farm at Bakersfield |  | Bakersfield | Red Barn | Under Construction | 780 - 0965 | ETT | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2640 | 2019-12-31 |  | 345 | 2.35 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 60420, 76002 | Y | N |  |  | 13042 | 5356
5836 | Rebuild Shady Grove to Advance | Rebuild Shady Grove (Bus #515) to Advance (Bus #518) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 16017 | 2019-12-31 |  | 69 | 0 | 11.34 | 0 |  | Parker | Parker | Tier 4 |  |  |  | 515, 518 | Y |  |  |  | 13578 | 5836
5838 | New Katz Auto to Benjamin 138 kV | Joint project with AEP to add autotransformer from Katz (bus# 774) to Katz8 (bus #798) and new line to Benjamin (bus # 6088) when AEP converts to 138 kV and builds line from the new Tardis switching station | [5 empty] | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 15016 | 2019-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | 2016-02-03 | 2016-05-30 |  | 790, 798, 33798, 745, 774, 6088, 6087 | Y |  |  |  | 14961 | 5838
5967 | Burma: Build new 69 kV station | Construct a new 69 kV station near the exsiting Grape Creek tap and reterminate the College Hills to Sterling City and Grape Creek to North San Angelo 69 kV lines into Burma | Cost Update | Burma |  | Planned | 845 - 1029 | AEP TNC | Guillermo Taylor mlforcum@aep.com 918-599-2674 | 2688 | 2019-12-31 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  | 6416, 60411, 6437, 6460, 6468 | Y | N |  |  | 13682 | 5967
5969 | Clairmont Tap to Wolfgang 69 kV line: Rebuild 69 kV line | Rehab Clairmont Tap to Wolfgang 69 kV line |  | Clairmont Tap | Wolfgang | Under Construction | 786 - 0971 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2658 | 2019-12-31 |  | 69 | 0 | 7.82 | 0 |  | Kent | Kent | Tier 4 |  |  |  | 6162, 6197 | Y | N |  |  | 13684 | 5969
6005 | Airline: Convert 69 kV Station | Upgrade Airline 69 kV station and lines to 138 kV |  | Airline | Naval Base | Planned | 808 - 0993 | AEP TCC/LCRA TSC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3597 | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8487, 8494, 8548, 8560, 8561, 8490, 8495, 8997, 8562, 8856 | Y | Y |  |  | 13771 | 6005
6041 | Ely Tap to Scott REA Tap 69 kV line: Rebuild 69 kV line | Rehab Ely Tap to Scott REA Tap 69 kV line | Cost Update | Ely Tap | Scott REA Tap | Planned | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2670 | 2019-12-31 |  | 69 | 0 | 8.79 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6242, 6246, 60405 | Y | N |  |  | 13760 | 6041
6042 | Scott REA Tap to Eskota 69 kV line: Rebuild 69 kV line | Rehab Scott REA Tap to Eskota 69 kV line |  | Scott REA Tap | Eskota | Planned | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2671 | 2019-12-31 |  | 69 | 0 | 11.73 | 0 |  | Taylor | Nolan | Tier 4 |  |  |  | 1340, 6246, 6247 | Y | N |  |  | 13761 | 6042
6044 | Big Lake to Barnhart 69 kV line: Rebuild 69 kV line | Rehab Big Lake to Barnhart 69 kV line |  | Big Lake | Barnhart | Planned | 786 - 0971 | AEP TNC | Randy Weaver mlforcum@aep.com 918-599-2674 | 2672 | 2019-12-31 |  | 69 | 0 | 17.71 | 0 |  | Reagan | Irion | Tier 4 |  |  |  | 6530, 6534 | Y | N |  |  | 13763 | 6044
6067 | Belknap to Rainey Crk 69 kV line: Rebld 69 kV line | Rehab Belknap to Rainey Creek 69 kV line |  | Belknap | Rainey Creek | Planned | 786 - 0971 | AEP TNC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | 2675 | 2019-12-31 |  | 69 | 0 | 8.33 | 0 |  | Jones | Taylor | Tier 4 |  |  |  | 6215, 6220, 6221, 60409 | Y | N |  |  | 13788 | 6067
6068 | Onyx to Nugent Tap 69 kV line: Rebuild 69 kV line | Rehab Onyx to Nugent Tap 69 kV line |  | Onyx | Nugent Tap | Planned | 786 - 0971 | AEP TNC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | 2676 | 2019-12-31 |  | 69 | 0 | 6.71 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6219, 6243, 6388 | Y | N |  |  | 13789 | 6068
6074 | Concho to Veribest Tap 69 kV line: Rebuild 69 kV line | Rehab Concho to Veribest Tap 69 kV line |  | Concho | Veribest Tap | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2689 | 2019-12-31 |  | 69 | 0 | 1.86 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6409, 6450 | Y | N |  |  | 13796 | 6074
6118 | Port Isabel - Causeway 138 kV Line | Rehab Port Isabel - Causeway 138 kV Line |  | Port Isabel | Causeway | Planned | 826 - 1010 | AEP TCC | Rich Haley dnlyons@aep.com 918-599-2698 | 3626 | 2019-12-31 |  | 138 | 0 | 6.74 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8338, 8744 | Y | N |  |  | 13844 | 6118
6121 | Sunchase - South Padre Island 138 kV Line | Rebuild Sunchase - South Padre Island 138 kV Line |  | Sunchase | South Padre Island | Planned | 826 - 1010 | AEP TCC | Rich Haley dnlyons@aep.com 918-599-2698 | 3625 | 2019-12-31 |  | 138 | 0 | 3.33 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8335, 8917 | Y | N |  |  | 13847 | 6121
6201 | Alice - North Ella 69 kV Line | Rehab Alice - North Ella 69 kV Line |  | Alice | North Ella | Planned | 818 - 1002 | AEP TCC | Andrew Garlick dnlyons@aep.com 918-599-2698 | 3614 | 2019-12-31 |  | 69 | 0 | 11.56 | 0 |  | Jim Wells |  | Tier 4 |  |  |  | 8500, 8878 | Y | N |  |  | 13926 | 6201
6254 | Gomez to Fort Stockton Switch 69 kV line: Rebuild 69 kV line | Rehab TNMP Gomez to Fort Stockton Switch 69 kV line |  | Gomez | Fort Stockton Switch | Planned | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2700 | 2019-12-31 |  | 69 | 0 | 4.77 | 0 |  | Pecos | Reeves | Tier 4 |  |  |  | 6645, 38470 | Y | N |  |  | 13982 | 6254
6343 | Dressy Tap to Santa Anna Tap 69 kV line: Rebuild 69 kV line | Rehab Dressy Tap to Santa Anna Tap 69 kV line |  | Dressy Tap | Santa Anna Tap | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2720 | 2019-12-31 |  | 69 | 0 | 13.6 | 0 |  | Callahan | Coleman | Tier 4 |  |  |  | 6352, 6356 | Y | N |  |  | 14087 | 6343
6346 | Menard Phillips T to Junction 69 kV line: Rbld 69 kV line | Rehab Menard Phillips Tap to Junction 69 kV line | Cost Update | Menard Phillips Tap | Junction | Planned | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2712 | 2019-12-31 |  | 69 | 0 | 12.2 | 0 |  | Kimble | Kimble | Tier 4 |  |  |  | 6400, 6401 | Y | N |  |  | 14090 | 6346
6355 | Robert Lee to Bronte 69 kV line: Rebuild 69 kV line | Rehab Robert Lee to Bronte 69 kV line |  | Robert Lee | Bronte | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2716 | 2019-12-31 |  | 69 | 0 | 8.72 | 0 |  | Coke | Coke | Tier 4 |  |  |  | 6414, 6419, 6420 | Y | N |  |  | 14099 | 6355
6357 | Spence Pump to Robert Lee 69 kV line: Rebuild 69 kV line | Rehab Spence Pump to Robert Lee 69 kV line | Cost Update | Spence Pump | Robert Lee | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2715 | 2019-12-31 |  | 69 | 0 | 8.55 | 0 |  | Coke | Coke | Tier 4 |  |  |  | 6420, 6421 | Y | N |  |  | 14101 | 6357
6569 | Aspermont: Replace the 138/69 kV autotransformer | Replace the 138/69 kV autotransformer at Aspermont with a 130 MVA autotransformer |  | Aspermont |  | Planned | 839 - 1023 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2817 | 2019-12-31 |  | 138 | 0 | 0 | 130 |  | Stonwall |  | Tier 4 |  |  |  | 6156, 6158 | Y | N |  |  | 14320 | 6569
6578B | Rebuild Ckt.66 Katy-Freeman-Betka-Hockley | Rebuild Ckt.66 Katy to Freeman to address clearance issues (Phase 2 of overall Katy to Hockley upgrades) |  | Katy | Freeman | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Waller | Tier 4 |  |  |  | 45770, 45675 | Y |  |  |  | 14823 | 6578
6687 | Rebuild Rio Hondo to East Rio Hondo | Rebuild the 138 kV line from Rio Hondo to East Rio Hondo. |  | Rio Hondo | East Rio Hondo | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-12-31 |  | 138 | 0 | 8.19 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  | 5764, 8319 | Y | N |  |  | 14458 | 6687
7004 | CNP_18TPIT7004_New_Garth_Distribution_Sub | Construct service to new 138kV Garth distribution substation. Loop through Ckt.66 Baytown to Highlands tap |  | Baytown | Highlands | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44630, 40172, 40812 | Y |  |  |  | 14825 | 7004
7005 | CNP_18TPIT_New_LakeHouston_Distribution_Sub | Construct service to new 138kV Lake Houston distribution substation. Loop through Ckt.66 Kingwood to Atascocita. |  | Kingwood | Atascocita | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40820, 40130, 40930 | Y |  |  |  | 14826 | 7005
7071 | West Columbia 138kV Load Conversion | Replace 69/12kV West Columbia power transformer with 138/12kV transformer |  | West Columbia |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43380, 43390 | Y |  |  |  | 14902 | 7071
43245 | HOPSON - New 138kV Substation | Construct service to new 138kV HOPSON customer-owned substation. Loop through Ckt.84 WARVUE to Cedar Bayou |  | HOPSON | WARVUE/ Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  | 41690, 40012, 41700 | Y |  |  |  | 43246 | 43245
43454 | Gable Street Reconfigurations | Add 69kV breaker at Gable Street to mitigate P2 contingency load loss |  | Gable Street | Gable Street | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47640 | Y |  |  | 0 | 43455 | 43454
43456C | Greens Bayou 138kV Reconfigurations | Upgrade Ckt.08E Greens Bayou to Oates to increase thermal ratings |  | Greens Bayou | Oates | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40715, 41191 | Y |  |  | 0 | 44328 | 43456
43462 | Add new distribution xfmr | [Northside] Distribution Substation Expansion - Install third new 138/12 kV, 100 MVA dstribution transformer |  | Northside | Northside | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47711, 47712 | Y |  |  | 0 | 43463 | 43462
44485 | Pig Creek: Build 138 kV terminal | Interconnect 138 kV line to Tar Bush | NEW | Pig Creek |  | Planned | 938 - 1116 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2751 | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60393 | Y | N |  | 0 | 44486 | 44485
6938 | Leonard Road Substation 69 | Construct Leonard Rd Substation with Dual Voltage Transformer. Will be served at 69kV until completion of Smetana to Leonard Rd 138kV line. | [5 empty] | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2020-01-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 32851, 32864, 32850 | Y |  |  |  | 14758 | 6938
4489 | Eagle Pass to Escondido: Rebuild 138kV line | Rebuild Eagle Pass to Escondido Circuit #1 |  | Eagle Pass | Escondido | Under Construction | 708 - 0878 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2664 | 2902 | 2020-01-01 21:00 |  | 138 | 0 | 1.5 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  | 8270, 8260 | Y | N |  |  | 12058 | 4489
07TPIT0060 | Howard Lane to Techridge Reconductor | The project re-conductors Circuit 1004 (Techridge to Howard Lane) using 795 ACSS Drake conductors to increase the capacity to 3000 Amp. |  | Howard Lane | Techridge | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P067 PLAN_117_P194 | 2020-01-03 |  | 138 | 0 | 1.72 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9191, 9217 | Y | N |  |  | 8204 | 1028
5648 | Hamilton Road to Picacho #1, rebuild 138 kV line | Rebuild Hamilton Road to Picacho 138 kV line ckt #1 |  | Hamilton Road | Del Rio | Under Construction | 869-1050 | AEP TCC | Jeremy Brazeal dnlyons@aep.com 918-599-2698 | 3659 | 2020-01-31 |  | 138 | 0 | 8.7 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  | 8255, 8584 | Y | N |  |  | 13382 | 5648
6352 | Crckett Hghts to Sonora Atlntic 69 kV line: Rbld 69 kV line | Rehab Crockett Heights to Sonora Atlantic 69 kV line | Cost Update | Crockett Heights | Sonora Atlantic | Planned | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2706 | 2020-01-31 |  | 69 | 0 | 16.8 | 0 |  | Crockett | Sutton | Tier 4 |  |  |  | 6511, 6552 | Y | N |  |  | 14096 | 6352
6822 | Figaro: Build new 345 kV station | Interconnect Amadeus wind farm on the Clear Crossing to Dermott 345 kV line |  | Figaro |  | Planned | 907 - 1085 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 2731 | 2020-01-31 |  | 345 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  | 60715, 11305, 60706, 60704 | Y | N |  |  | 14623 | 6822
6851 | Saragosa to Solstice: Rebuild 138 kV line | Build Saragosa to Solstice 138 kV line, retire existing Barrilla Junction to Saragosa 69 kV line, add new auto and capacitor bank at Saragosa. | Schedule and Cost Update | Saragosa | Solstice | Planned | 922 - 1100 | AEP TNC | Guillermo Taylor mlforcum@aep.com 918-599-2674 | 2736 | 2020-01-31 |  | 138 | 0 | 19 | 90 | 0,7.2 | Pecos | Ward | Tier 4 |  |  |  | 60716, 6650, 6652, 60385, 6653 | Y | N |  |  | 14659 | 6851
43485 | Cryo: Build 138 kV station | Build new Cryo 138 kV station, build Cryo to Saragosa new 138 kV line, add capacitor banks at Cryo | NEW | Cryo |  | Planned | 926 - 1104 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2740 | 2020-01-31 |  | 138 | 0 | 0 | 0 | 0,28.8 | Reeves |  | Tier 4 |  |  |  | 60721, 60716 | Y | N |  | 0 | 43486 | 43485
43487 | Cryo to Saragosa: Build 138 kV line | Build new Cryo 138 kV station, build Cryo to Saragosa new 138 kV line, add capacitor banks at Cryo | NEW | Cryo | Saragosa | Planned | 926 - 1104 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2739 | 2020-01-31 |  | 138 | 5 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  | 60721, 60716 | Y | N |  | 0 | 43488 | 43487
44056 | Coral to Cryo: Build 138 kV line | Build new Coral 138 kV station and build Coral to Cryo new 138 kV line | NEW | Coral | Cryo | Planned | 931 - 1109 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2741 | 2020-01-31 01:00 |  | 138 | 5.1 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  | 60434, 60721 | Y | N |  | 0 | 44057 | 44056
44058 | Coral: Build 138 kV station | Build new Coral 138 kV station and build Coral to Cryo new 138 kV line | NEW | Coral |  | Planned | 931 - 1109 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2742 | 2020-01-31 01:00 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60434, 60721 | Y | N |  | 0 | 44059 | 44058
07TPIT0050 | Dunlap to Techridge 138kV Circuit Relocation | This project will reroute the existing Ckt 975 Dunlap-Techridge from near the intersection of Howard Lane and Dessau Road to the Techridge substation. The reroute will use 3000 amp bundled 795 ACSS Drake conductor. |  | Dunlap Substation | Techridge Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P071 | 2020-02-01 |  | 138 | 0 | 2.7 | 0 |  | Travis | Travis | Tier 2 | 2009-01-26 | 2009-07-21 |  | 9045, 9190 | Y | N |  |  | 8189 | 1013
44181 | 138kV Cooper Creek - Arco Line Reconstruction |  |  |  |  | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-02-01 |  | 138 | 0 | 1.62 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 906, 923 | Y | N |  | Reconstruct 138kV Cooper Creek to Arco | 44182 | 44181
4505 | BRYN_4505_Smetana_Sub | Construction of a new Smetana Substation at 138kV |  |  |  | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2020-02-02 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32850, 32853, 32868, 32864 | Y |  |  |  | 12077 | 4505
4576 | BRYN_4576_Smetana_to_Steele_Store | Construct New 138kV line (Bundled 1033 ACSR - Curlew) to new Steele Store substation as part of the reliability project to loop in Steele Store |  | 32853 | 32852 | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2020-02-02 |  | 138 | 10 | 0 | 0 |  | Brazos | Burleson | Tier 4 | 2015-10-09 | 2015-11-06 |  | 32852, 32853 | Y |  |  |  | 12158 | 4576
6683 | Del Sol-Cabezon: Create Permanent Interconnection for Rio Br | Construct 2nd circuit on Cenizo-Del Sol 345 kV line from the Rio Bravo Windfarm Collector Station (Cabezon) to Del Sol. |  | Del Sol | Cabezon | Planned | 896 - 1074 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3680 | 2020-02-17 |  | 345 | 26.5 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  | 80380, 80307, 80355, 80225, 161851 | Y | N |  |  | 14453 | 6683
7159 | Ajo-Stella: Create Permanent Interconnection for Stella WF | Convert Stella Windfarm temporary tap interconnection to a permanent interconnection. ETT will construct an extension of the gen tie-line by adding a second circuit on the Ajo-Zorillo line, therefore creating a dedicated circuit terminating at the Ajo station. |  |  |  | Planned | 894 - 1072 | ETT | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3678 | 2020-02-17 |  | 345 | 0 | 7.85 | 0 |  | Kenedy | Kenedy | Tier 4 |  |  |  | 80070, 80071, 80076, 161591, 161953 | Y | N |  |  | 15000 | 7159
6106 | Woodsboro - Bonniview 69 kV Line | Rehab Woodsboro - Bonniview 69 kV line |  | Woodsboro | Bonniview | Planned | 834 - 1018 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3640 | 2020-02-28 |  | 69 | 0 | 5.37 | 0 |  | Refugio |  | Tier 4 |  |  |  | 8804, 8805 | Y | N |  |  | 13832 | 6106
6114 | La Pryor - Uvalde 69 kV Line | Rehab La Pryor - Uvalde 69 kV Line |  | La Pryor | Uvalde | Planned | 810 - 0995 | AEP TCC | James Nivens dnlyons@aep.com 918-599-2698 | 3600 | 2020-02-28 |  | 69 | 0 | 17.603 | 0 |  | Zavala | Uvalde | Tier 4 |  |  |  | 8231, 8672 | Y | N |  |  | 13840 | 6114
6022 | Stamford to Haskell Tap 1 69 kV line: Rebuild 69 kV line | Rehab Stamford to Haskell Tap 1 69 kV line |  | Stamford | Haskell Tap 1 | Planned | 786 - 0971 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2668 | 2020-02-29 |  | 69 | 0 | 12.22 | 0 |  | Jones | Haskell | Tier 4 |  |  |  | 6171, 6172 | Y | N |  |  | 13739 | 6022
44395 | Victoria Port Permanent | [6 empty] | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2020-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 8142, 8143, 8172, 111343 | Y |  |  | 0 | 44396 | 44395
6782 | Bandera Substation Upgrade | Remove one 138/69 kV Autotransformer rated for 44.8 MVA and remove one 138 kV Circuit Breaker and convert T281 Leakey to Utopia to 138 kV operation. |  | Bandera |  | Conceptual |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-33726078 | 353985 | 2020-03-17 |  | 138 | 0 | 0 | 0 |  | Bandera |  | Tier 4 |  |  |  | 7426 | N | N |  |  | 14576 | 6782
6083 | Wolfgang: Build 69 kV station | Construct new 69 kV ring bus at Wolfgang | Schedule and Contact Update | Wolfgang |  | Planned | 842 - 1026 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2682 | 2020-03-31 |  | 69 | 0 | 0 | 0 |  | Kent |  | Tier 4 |  |  |  | 6162 | Y | N |  |  | 13807 | 6083
6117 | Pleasanton - Coy City Tap 69 kV Line | Rehab Pleasanton - Coy City Tap 69 kV Line |  | Pleasanton | Coy City Tap | Planned | 814 - 0998 | AEP TCC | James Nivens dnlyons@aep.com 918-599-2698 | 3604 | 2020-03-31 |  | 69 | 0 | 16.79 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 8200, 8600 | Y | N |  |  | 13843 | 6117
7027 | Barrilla Junction to Ft. Stockton SW: Rebuild 69 kV line | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138, reterminate into Solstice, install series reactor at Solsctice, and build new Ft. Stockton 138 kV station | NEW | Solstice | Fort Stockton Switch | Planned | 908 - 1086 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2732 | 2020-03-31 |  | 138 | 0 | 16.3 | 0 |  | Pecos | Pecos | Tier 3 | 2017-12-22 | 2018-02-02 |  | 6645, 60717, 60385, 6653, 38350, 38470 | Y | N |  |  | 14849 | 7027
7028 | Ft. Stockton SW to Rio Pecos: Rebuild 69 kV line | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138, reterminate into Solstice, install series reactor at Solsctice, and build new Ft. Stockton 138 kV station | Cost Update | Fort Stockton Switch | Rio Pecos | Planned | 908 - 1086 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2733 | 2020-03-31 |  | 138 | 0 | 0.42 | 0 |  | Pecos | Pecos | Tier 3 | 2017-12-22 | 2018-02-02 |  | 6641, 6642, 6643, 38470, 38471, 60717, 60718, 60719, 60720, 6598, 6601, 6645 | Y | N |  |  | 14850 | 7028
44359 | Solstice: Install 138 kV series reactor | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138, reterminate into Solstice, install series reactor on the Fort Stockton Plant to Solstice at Solstice, and build new Ft. Stockton 138 kV station | NEW | Solstice |  | Planned | 908 - 1086 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2734 | 2020-03-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 3 | 2017-12-22 | 2018-02-02 |  | 60384, 6645, 60717, 6630, 60385 | Y | N |  | 0 | 44360 | 44359
44361 | Ft. Stockton SW: Build 138 kV station | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138, reterminate into Solstice, install series reactor on the Fort Stockton Plant to Solstice at Solstice, and build new Ft. Stockton 138 kV station | NEW | Fort Stockton Switch |  | Planned | 908 - 1086 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2735 | 2020-03-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 3 | 2017-12-22 | 2018-02-02 |  | 60717 | Y | N |  | 0 | 44362 | 44361
10TPIT0025 | Bluff Spring 138kV substation | Establish 138kV Bluff Spring substation with (2) 30MVA transformers and will cut into existing Ckt 987 (Lytton Springs to Slaughter Lane). | Changing name of substation from Rinard Creek to Bluff Springs | Lytton Springs substation | Bluff Springs Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P151 PLAN_117_P152 | 2020-04-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9262, 9075, 9267 | Y | N |  |  | 8206 | 1030
5166 | Borglum to Three Rivers: Rebuild 69 kV line | Reterminate Beeville to Three River 69 kV line into Borglum instead of Beeville and rebuild with 138 kV 795 ACSS conductor | Schedule Update | Borglum | Three Rivers | Planned | 742 - 0925 | AEP TCC | Dave Gotez dnlyons@aep.com 918-599-2698 | 2915 | 2020-04-30 |  | 138 | 6 | 22 | 0 |  | Bee | Live Oak | Tier 1 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8196, 8198, 8199, 8400, 8403 | Y | N |  |  | 13316 | 5166
6571 | Lake Pauline to Vernon 69 kV line: Rebuild taps | Lake Pauline to Vernon 69 kV line: Rebuild taps |  | Lake Pauline | Vernon Main | Planned | 891 - 1069 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2815 | 2020-04-30 |  | 69 | 0 | 2.5 | 0 |  | Hardeman | Wilbarger | Tier 4 |  |  |  | 6048, 6056, 6057, 6058 | Y | N |  |  | 14322 | 6571
6791 | Lake Pauline: Replace 138/69 kV Auto | Replace the 138/69 kV autotransformer at Lake Pauline with a 130 MVA autotransformer |  | Lake Pauline |  | Planned | 906 - 1084 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2730 | 2020-04-30 |  | 138 | 0 | 0 | 130 |  | Hardeman |  | Tier 4 |  |  |  | 6048, 6050 | Y | N |  |  | 14589 | 6791
44513 | Concho to Live Oak: Rebuild 69 kV line | Rebuild remaining portions of the Concho to Live Oak 69 kV line | NEW | Concho | Live Oak | Planned | 941 - 1119 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2755 | 2020-04-30 01:00 |  | 69 | 0 | 3.3 | 0 |  | Tom Green | Schleicher | Tier 4 |  |  |  | 6450, 6494, 6495, 6496, 6497, 6498, 6527 | Y | N |  | 0 | 44514 | 44513
6783 | Utopia-Tarpley Re-Termination | Re-Termination of existing T281 Transmission Line, related to reconfiguration of Utopia and Tarpley Substations. | Change in schedule | Utopia | Tarpley | Planned |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-33726078 | 353985 | 2020-05-01 |  | 69 | 0 | 0.25 | 0 |  | Bandera | Bandera | Tier 4 |  |  |  | 7428, 7440 | Y | N |  |  | 14577 | 6783
6788 | Tarpley Substation Upgrade | Add two 138 kV Circuit Breakers to Line Terminals to be operated at 69 kV. | Change in schedule | Tarpley |  | Planned |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-33726078 | 353985 | 2020-05-01 |  | 69 | 0 | 0 | 0 |  | Bandera |  | Tier 4 |  |  |  | 7426, 7428, 7439, 7440 | Y | N |  |  | 14582 | 6788
43623 | McCreeCristBenDavisLinesUpgrade | McCree to Crist to Ben Davis 138kV Lines Upgrade to Cumberland Conductor |  | McCree | Ben Davis | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2020-05-01 10:00 |  | 138 | 0 | 6.95 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 834, 850, 968 | Y | N |  | 0 | 43624 | 43623
6347 | Ballinger to Paint Rock 69 kV line: Rebuild 69 kV line | Rehab Ballinger to Paint Rock 69 kV line |  | Ballinger | Paint Rock | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2708 | 2020-05-03 |  | 69 | 0 | 14.6 | 0 |  | Runnels | Concho | Tier 4 |  |  |  | 6338, 6369 | Y | N |  |  | 14091 | 6347
4567 | BRYN_4567_Smetana_to_Leonard | Build Smetana to Leonard Rd 138 line in existing 69KV ROW of old Annex to Atkins line |  | 32897 | 32863 | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2020-05-05 |  | 138 | 0.75 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32853, 32851 | Y |  |  |  | 12149 | 4567
5428D | Phase 2 of the conversion to 138kV | Line will be reconfigured to through a 3way tie |  | Woodrow | Spencer Int | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-05-05 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 921, 982 | Y | N | N/A |  | 13116 | 5428
5429A | Phase 3 of the conversion to 138kV | Add a new 138kV line from the new Locust station to Woodrow to Spencer Interchange via a three way tie at Woodrow. The section going from the 3way tie to Spencer Int. was added in phase 2. |  | Locust | Spencer Int. | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-05-05 |  | 138 | 1.917 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 924, 99999, 921, 982 | Y | N | N/A |  | 13117 | 5429
5429B | Phase 3 of the conversion to 138kV | Retire the existing 69kV line from the existing 69kV locust substation to Spencer Switch |  | Locust | Spencer Switch | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-05-05 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 904, 914 | Y | N | N/A |  | 13118 | 5429
5792 | Leonard Road Substation 138 | Upgrade Leonard Rd from 69kV to 138kV and construct 138 from Leonard to Atkins |  |  |  | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2020-05-05 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32851, 32862, 32864 | Y |  |  |  | 14760 | 5792
5429C | Phase 3 of the conversion to 138kV | The three way tie will be retired and 138kV locust will tie directly to 138kV Woodrow. The Spencer Int. to the 3way tie will be reconfigured to terminate at the new 138kV Brinker substation. |  | Locust | Spencer Int. | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-05-06 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 99999, 921, 924, 982 | Y | N | N/A |  | 13119 | 5429
08TPIT0104 | Elgin Switching Station - Elgin 69 kV line conversion to 138 | Rebuild existing 69 kV line and convert to 138 kV operation | Project Deferral | Elgin Switching Station | Elgin | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R471-E | 2020-05-15 |  | 138 | 0 | 5.9 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 3655, 3650, 3651, 3674, 13674 | Y | N |  |  | 10653 | 1335
11TPIT0034 | Sargent Road 345/138 kV autotransformer | Install second 345/138 kV autotransformer |  | Sargent Road |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M486-E | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  | 2946, 2949 | Y | N |  |  | 9001 | 1784
12TPIT0080 | Forney Sw. Sta. Second 600 MVA, 345/138 kV Autotransformer | Add second 345/138 autotransformer | Project Deferral | Forney Sw. Sta. |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4037 | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 4 | 2008-06-01 | 2008-07-01 |  | 2437, 2438 | Y | N | 2007-R2 |  | 9769 | 2489
14TPIT0056 | Northaven - Morrison 138 kV line | Upgrade existing double-circuit line |  | Northaven | Morrison | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4088-E | 2020-05-15 |  | 138 | 0 | 12 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2657, 2658, 2660, 2661, 2662, 2663, 2782, 2783 | Y | N |  |  | 9773 | 2493
14TPIT0010 | Handley - Pantego - Sherry 138 kV line | Upgrade existing line |  | Handley | Sherry | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5155-E | 2020-05-15 |  | 138 | 0 | 8.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1919, 1920, 1950, 1951, 2219, 2233, 2245, 2246, 2247, 2248, 2250, 2232, 2251, 2252 | Y | N |  |  | 11813 | 2582
16TPIT0054 | Dialville - Palestine South 138 kV Line | Upgrade existing Dialville - Palestine South line section |  | Dialville | Palestine South | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6019 | 2020-05-15 |  | 138 | 0 | 25 | 0 |  | Cherokee | Andrews | Tier 4 |  |  |  | 3111, 3160, 3271, 3110, 3296 | Y | N |  |  | 10458 | 3114
4554 | Ennis Creek - Cogdell 69 kV Line | Convert existing line to 138 kV operation |  | Ennis Creek | Cogdell | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9025 | 2020-05-15 |  | 138 | 0 | 8.6 | 0 |  | Scurry |  | Tier 3 | 2015-12-21 | 2016-10-11 |  | 1400, 1401, 1402, 1411, 1412, 752, 1410 | Y |  |  |  | 14945 | 4554
4733 | Midland County Northwest Sw. Sta. - Midland East 138 kV Line | Upgrade existing double-circuit line | Project Deferral | Midland County Northwest Sw. Sta. | Midland East | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8304 | 2020-05-15 |  | 138 | 0 | 32.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1171, 1178, 1179, 1182, 1183, 1184 | Y | N |  |  | 12327 | 4733
4802 | Lake Wichita Sw. Sta. Holliday 69 kV Line conversion | Convert existing 69 kV line to 138 kV operation |  | Lake Wichita Sw. Sta. | Holliday | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4009 | 2020-05-15 |  | 138 | 0 | 10.1 | 0 |  | Wichita | Archer | Tier 4 |  |  |  | 1447, 11527, 1423, 1424, 1446, 1449, 1527 | Y | N |  |  | 12408 | 4802
4822 | Bell County (BEC) - Gabriel (LCRA) 138 kV | Upgrade existing line | Construction schedule change | Bell County | Gabriel | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2008 | 2020-05-15 |  | 138 | 0 | 35.2 | 0 |  | Bell | Williamson | Tier 3 |  |  |  | 121, 132, 3640, 3688, 7346, 13640 | Y | N |  |  | 12428 | 4822
4825 | Crockett - Jewett 138kV Line | Upgrade existing line | Project Deferral | Crockett | Jewett | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6061 | 2020-05-15 |  | 138 | 0 | 39.5 | 0 |  | Houston | Leon | Tier 3 |  |  |  | 3354, 3355, 3357, 3358, 3345, 3394 | Y | N |  |  | 12432 | 4825
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line |  | Cresson | Rocky Creek | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5228 | 2020-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  | 1881, 2202 | Y | N |  |  | 12436 | 4834
4835 | DeCordova - Cleburne Sw. Sta. 138 kV Line | Upgrade existing line |  | DeCordova | Cleburne Sw. Sta. | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5226 | 2020-05-15 |  | 138 | 0 | 22.6 | 0 |  | Hood | Johnson | Tier 4 |  |  |  | 1891, 2279, 2280, 2281, 2283 | Y | N |  |  | 12437 | 4835
5310 | Everman - Venus 345 kV Double-circuit line | Upgrade existing line |  | Everman | Venus | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1735 | 2020-05-15 |  | 345 | 0 | 34.6 | 0 |  | Tarrant | Ellis | Tier 4 |  |  |  | 1882, 1886, 1906, 1907 | Y | N |  |  | 12986 | 5310
5408 | Herty N Sw. Sta. 138 kV Rebuild | Rebuild existing 138 kV switching station | Project Deferral | Herty North | Herty North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6069 | 2020-05-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3317, 3319 | Y | N |  |  | 13094 | 5408
5433 | Calf Creek 138 kV Switching Station | Construct new 138 kV switching station |  | Calf Creek |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8308 | 2020-05-15 |  | 138 | 0 | 0 | 0 |  | Howard |  | Tier 4 |  |  |  | 11322 | Y | N |  |  | 13136 | 5433
5466 | Herty North Sw. Sta. 345/138 kV Autotransformer | Install new 345/138 kV Autotransformer at Herty North Sw. Sta. |  | Herty North | Herty North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6076 | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Angelina | Angelina | Tier 4 |  |  |  | 3321, 3322, 3319 | Y | N |  |  | 13170 | 5466
5467 | Nacogdoches Southeast_HertyN 345kV Line | Establish a new 345kV Line |  | Nacogdoches Southeast | Herty North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6075 | 2020-05-15 |  | 345 | 13.4 | 0 | 0 |  | Nacogdoches | Angelina | Tier 2 |  |  |  | 3119, 3321 | Y | N |  |  | 13171 | 5467
5475 | Lufkin Sw. Sta. - Herty North Sw. Sta. 345 kV Line | Construct a new 345 kV Line from Lufkin Sw. Sta. to Herty North Sw. Sta. |  | Lufkin Sw. Sta | Herty North Sw. Sta. | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6077 | 2020-05-15 |  | 345 | 8.1 | 0 | 0 |  | Angelina | Angelina | Tier 2 |  |  |  | 3117, 3321 | Y | N |  |  | 13180 | 5475
5487 | NW Carrollton - Lewisville South (TNMP) 138 kV Line | Upgrade existing Northwest Carrollton - Lewisville South 138 |  | Northwest Carrollton | Lewisville South | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3210 | 2020-05-15 |  | 138 | 0 | 3.4 | 0 |  | Dallas | Denton | Tier 4 |  |  |  | 2363, 37100 | Y | N |  |  | 13225 | 5487
5490 | Liggett - Hackberry 138 kV DCKT Line | Upgrade existing Liggett - Hackberry 138 KV Double Ckt Line |  | Liggett | Hackberry | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4222 | 2020-05-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  | 1996, 1997, 2001, 2002, 2010, 11923, 15002, 15020, 15021, 2388, 15025, 15026, 15045, 15046 | Y | N |  |  | 13228 | 5490
5492 | Venus - Webb/Cedar Hill Sw. Sta. 345 kV DCKT Line | Upgrade existing Venus - Webb/Cedar Hill Sw. Sta. 345 kV Double Ckt Line |  | Ellis | Tarrant | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4230 | 2020-05-15 |  | 345 | 0 | 27 | 0 |  | Ellis | Tarrant | Tier 4 |  |  |  | 1904, 1906, 1907, 1911, 2420, 11901 | Y | N |  |  | 13230 | 5492
5496 | Forney - Royse 345 kV Line | Upgrade existing Royse - Forney 345 kV Line |  | Royse | Forney | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4235 | 2020-05-15 |  | 345 | 0 | 30 | 0 |  | Rockwall | Kaufman | Tier 4 |  |  |  | 2437, 2467, 2470, 2474, 2478 | Y | N |  |  | 13234 | 5496
5524 | Royse South 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | South Royse |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4234 | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Rockwall |  | Tier 3 |  |  |  | 2469, 2470, 12471, 2437, 2467, 2471, 2478, 2702, 2710, 3103, 12702 | Y | N |  |  | 13251 | 5524
5801 | Hutto - Rnd Rck SE - Gil | Upgrade138 kV line | Project Deferral | Hutto | Gilleland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2005 | 2020-05-15 |  | 138 | 0 | 7.5 | 0 |  | Williamson | Travis | Tier 4 |  |  |  | 3654, 3666, 7336 | Y | N |  |  | 13541 | 5801
5982 | Relocate existing Shamburger North - Shamburger 138 kV Line | Establish 138 kV Line |  | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6084 | 2020-05-15 |  | 138 | 10 | 0 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3104, 3206, 3226 | Y | N |  |  | 13697 | 5982
5984 | Mulberry Creek 345 kV Switching Station | Rebuild existing Mulberry Creek 345 kV Switching Station |  | Mulberry Creek |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9022 | 2020-05-15 |  | 345 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  | 6230 | Y | N |  |  | 13699 | 5984
6019 | North Main - Denton Ave/Springdale Line | Rebuild existing 69 kV and 138 kV Lines |  | North Main | Richland Junction | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5240 | 2020-05-15 |  | 138 |  | 4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2102, 2148, 2156, 1961, 2099, 2101, 2146, 2157 | Y | N |  |  | 13736 | 6019
6273 | Saginaw 345/138 kV autotransformer | Install new autotransformer and construct new 345 kV Line at Saginaw |  | SAGINAW | HICKS | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5274 | 2020-05-15 |  | 345 | 15.6 | 0 | 600 |  | Tarrant | Tarrant | Tier 2 |  |  |  | 2065, 2066, 2067, 11957, 11958, 1436, 1860, 1864, 1957, 2068, 2081, 2069, 2070, 11860 | Y | N |  |  | 14003 | 6273
6282 | Everman - Benbrook 345 kv line | Rebuild existing 345 kV Line |  | Everman | Benbrook | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5273 | 2020-05-15 |  | 345 |  | 29 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1870, 1886, 1935 | Y |  |  |  | 14014 | 6282
6288 | Watermill - Trinidad 345 kV Line | Install a breaker at Watermill Sw. on the Watermill - Trinidad 345 kV Line to establish double-breaker configuration |  | Watermill | Trinidad | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4249 | 2020-05-15 |  | 345 | 0 | 0 | 0 |  | Dallas | Henderson | Tier 4 |  |  |  | 2996, 2427, 2428, 2432 | Y |  |  |  | 14017 | 6288
6296 | Cowden North - Odessa North 69 kV Line Conversion | Cowden North - Odessa North 69 kV Line Conversion |  | Cowden North | Odessa North | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9028 | 2020-05-15 |  | 138 | 0 | 10.5 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1259, 1122, 1123, 1141, 1142 | Y |  |  |  | 14025 | 6296
6302 | Black Fork-Tyler West 69 kV to 138 kV Line Conversion | Rebuild existing 69 kV line and convert to 138 kV operation |  | Black Fork | Tyler West | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6071 | 2020-05-15 |  | 138 | 0 | 4.9 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3138, 3140, 3142, 3198, 3207, 3139, 3197, 3137, 13235, 3141 | Y | Y |  |  | 14031 | 6302
6792 | Royse - Anna Tap 138 kV Line | Upgrade existing line |  | ROYSE | ANNA TAP | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4275 | 2020-05-15 |  | 138 | 0 | 31.3 | 0 |  | Rockwall | Collin | Tier 3 |  |  |  | 2472, 2527, 2707, 2374, 2528, 2708, 12527 | Y | N |  |  | 14590 | 6792
7020 | Cedar Hill - Camp Wisdom 138 kV Line | Upgrade existing Cedar Hill - Camp Wisdom 138 kV Line |  | Cedar Hill | Camp Wisdom | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4250 | 2020-05-15 |  | 138 | 0 | 9.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2421, 2990, 2993, 2994, 2992, 2999 | Y | N |  |  | 14842 | 7020
7021 | Collin 345/138 kV Autotransformer 2 Series Reactor | Install 2-ohm series reactor on Collin 345/138 kV Autotransformer 2 |  | Collin Sw. Sta. |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R960 | 2020-05-15 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 2370, 29555 | Y | N |  |  | 14843 | 7021
7022 | Forney - Seagoville/Tri Corner 345 kV Double-circuit Line | Upgrade Forney - Seagoville/Tri Corner 345 kV Double-circuit Line |  | Forney | Tri Corner | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4227 | 2020-05-15 |  | 345 | 0 | 32.2 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2432, 2433, 2437, 3105 | Y |  |  |  | 14844 | 7022
7025 | Renner Sw. Sta. - Plano Tennyson Sw. Sta. 138 kV Line | Upgrade existing Renner Sw. Sta. - Plano Tennyson Sw. Sta. 138 kV Line |  | Renner Sw. Sta. | Plano Tennysson Sw. Sta. | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3047 | 2020-05-15 |  | 138 | 0 | 10.6 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 2352, 2353, 2521, 2523, 2524 | Y | N |  |  | 14847 | 7025
7026 | Cedar Hill Sw-Sorcey-Cedar Hill 138 kV Line | Upgrade existing Cedar Hill Sw-Sorcey-Cedar Hill 138 kV Line |  | Cedar Hill Sw. Sta. | Cedar Hill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4131 | 2020-05-15 |  | 138 | 0 | 5.9 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2422, 3049, 3051, 3052, 3053, 3050, 3055 | Y | N |  |  | 14848 | 7026
7044 | Cedar Crest Sw. Sta. - Wall St. 69 kV Line | Convert Cedar Crest Sw. Sta. - Wall St. 69 kV Line to 138 kV |  | Cedar Crest | Wall Street | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4071 | 2020-05-15 |  | 138 | 0 | 2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2982, 2983, 2486, 2494 | Y | N |  |  | 14866 | 7044
7115 | Quarry Field - Kyle Ranch 138 kV Line | Quarry Field - Kyle Ranch 138 kV Line |  | Quarry Field | Kyle Ranch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8384 | 2020-05-15 |  | 138 | 12 | 0 | 0 |  | Loving |  | Tier 4 |  |  |  | 11089, 11189 | Y |  |  |  | 14951 | 7115
7118 | Everman 345 kV Sw. Sta. | Rebuild Everman 345 kV Sw. Sta. |  | Everman |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5278 | 2020-05-15 |  | 345 | 0 | 0 | 0 |  | Tarrant |  | Tier 3 |  |  |  | 1882 | Y |  |  |  | 14954 | 7118
7124 | Barr Ranch Tap - Barr Ranch 138 kV line | Barr Ranch Tap - Barr Ranch 138 kV line |  | Barr Ranch Tap | Barr Ranch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8373 | 2020-05-15 |  | 138 | 12.4 | 0 | 0 |  | Upton | Upton | Tier 2 |  |  |  | 11235, 71214 | Y |  |  |  | 14962 | 7124
7125 | Greenville Ave 138 kV Capacitors | Upgrade existing capacitor banks |  | Greenville Ave | Greenville Ave | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4177 | 2020-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas | Dallas | Tier 4 |  |  |  | 2882, 2883 | Y | N |  |  | 14963 | 7125
7171 | Andrews County South Sw. Sta. - No Trees Sw. Sta. 138 kV Lin |  |  | Andrews Co South | No Trees | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8407 | 2020-05-15 |  | 138 | 0 | 8.8 | 0 |  | Andrews | Winkler | Tier 4 |  |  |  | 1149, 1150, 1157, 131853 | Y |  |  |  | 15012 | 7171
44393 | Zapata Reactor | [6 empty] | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2020-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 8299 | Y |  |  | 0 | 44394 | 44393
7129 | Decordova 345/138 kV Sw. Sta. | Rebuild existing switching station | Project Deferral | Decordova |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5066 | 2020-05-15 02:00 |  | 345 | 0 | 0 | 0 |  | Hood |  | Tier 4 |  |  |  | 1888 | Y | N |  |  | 14967 | 7129
6777 | Venus - Cedar Hill 138 kV Line | Loop Venus - Cedar Hill 138 kV line in to Arlington ED Substation | Project Deferral | Grand Prairie West | Cedar Hill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4270 | 2020-05-15 02:01 |  | 138 | 7 | 0 | 0 |  | Dallas | Tarrant | Tier 4 |  |  |  | 1912, 1919, 2138, 2143, 2265 | Y | N |  |  | 14571 | 6777
5981 | Shamburger North 345/138 kV Sw. Sta. | Establish Shamburger North 345/138 kV Sw. Sta. |  | Shamburger North |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6083 | 2020-05-16 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  | 3217, 3223, 3226, 2470, 3103, 3201, 3206 | Y | N |  |  | 13696 | 5981
7116 | Riverton Sw. Sta.- Kyle Ranch 138 kV Line | Riverton Sw. Sta.- Kyle Ranch 138 kV Line |  | Riverton | Kyle Ranch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8427 | 2020-05-18 |  | 138 | 15 | 0 | 0 |  | Reeves | Loving | Tier 2 | 2018-02-02 | 2018-05-22 |  | 11083, 11089 | Y |  |  |  | 14952 | 7116
6304 | Shamburger North - Shamburger 345 kV Line | Upgrade existing 345 kV Line |  | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6085 | 2020-05-28 |  | 345 | 10 | 10 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3103, 3223 | Y | N |  |  | 14033 | 6304
43284D | Baytown Area Upgrades | Upgrade portions of reconfigured Ckt.87 SR Bertron to TEXAS to increase thermal ratings |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41405, 41540 | Y |  |  | 0 | 43289 | 43284
43284C | Baytown Area Upgrades | Reconfigure SRB to Texas |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-29 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40089, 40120, 40170, 40430, 40470, 40480, 40540, 41350, 41391, 41405, 41410, 41415, 44051, 44052, 40570, 41355, 41360, 41380, 41400, 41419, 41420, 41540, 44140, 44141, 44780 | Y |  |  | 0 | 43288 | 43284
43284E | Baytown Area Upgrades | Upgrade Ckt.21 DIABOX to MOMENT to increase thermal ratings |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-29 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40480, 41090 | Y |  |  | 0 | 43291 | 43284
4186C | University Area 138kV Conversions | Convert Blodgett substation from double-tap service to 138kV Ckt.37 loop service. Convert Blodgett TR1 load to 138kV. |  | Blodgett | TECO/Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2020-05-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47520, 47521, 47522, 42690, 47430, 47660 | Y | N |  | Cost included in 4186A | 14513 | 4186
6753 | Quihi: Build 138kV Station | Build new Quihi 138kV In and Out Station on Razorback to Castroville 138kV Line |  | Razorback |  | Planned | 900 -1078 | AEP TCC/STEC | Daniel Lyons dnlyons@aep.com 918-599-2698 | 3684 | 2020-05-30 |  | 138 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 8248, 88248, 5083, 8241 | Y | Y |  |  | 14546 | 6753
43284F | Baytown Area Upgrades | Upgrade Ckt.87 TEXAS to Cedar Bayou tap to increase thermal ratings |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40011, 41540 | Y |  |  | 0 | 43290 | 43284
4186D | University Area 138kV Conversions | Remove University Auto A1 from service |  | University |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 49030, 47755, 47760 | Y | N |  | Cost included in 4186A | 14514 | 4186
4488 | Campwood to Uvalde: Rebuild 69 kV line | Rebuild Campwood to Uvalde 69 kV line, built to 138 kV standard with 795 ACSS conductor, but energized at 69 kV. |  | Campwood | Uvalde | Planned | 707 - 0877 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 2901 | 2020-05-31 |  | 138 | 0 | 37.1 | 0 |  | Real | Uvalde | Tier 3 | 2017-01-17 | 2017-03-20 | 2017-03-20 | 8230, 8633, 8231 | Y | N |  |  | 12057 | 4488
5276 | Flatonia - Hallettsville Transmission Line Upgrade | Upgrade T132 Hallettsville to Flatonia (18.7 mi) 138-kV transmission line to a minimum rating of 380 MVA with OPGW. |  | Flatonia | Hallettsville | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016188 | 2020-05-31 |  | 138 | 0 | 18.7 | 0 |  | Fayette | Lavaca | Tier 4 |  |  |  | 7246, 7248 | Y | N |  |  | 12952 | 5276
5277 | Glidden Area Transmission Line Upgrade | Convert existing 69-kV lines (T544) from Glidden to Altair and (T545) from Altair to Nada to 138-kV transmission lines. Relocate existing 45 MVA auto from Glidden to Altair. Add a second new 45 MVA auto at Altair substation. |  | Glidden | Nada | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016219 | 2020-05-31 |  | 138 | 0 | 0.77 | 45 |  | Colorado | Colorado | Tier 4 |  |  |  | 78107, 78111, 78115, 78118, 78170, 78171, 78520, 5536, 7258, 78103, 78106 | Y | N |  |  | 12953 | 5277
5286A | Fayette Area Upgrades | Upgrade existing Fayette - Frelsburg - Mockingbird - Glidden (T176) TL with a minimum rating of 380 MVA and with OPGW. | Planning In-Service Date Change. Updated to a phased project, the original TPIT project number is 5286. | Fayetteville | Glidden | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1019024 | 2020-05-31 |  | 138 | 0 | 20 | 0 |  | Fayette | Colorado | Tier 4 | 2017-06-29 | 2017-07-28 |  | 7258, 7263, 7286, 78259 | Y | N |  |  | 14583 | 5286
5964 | Belknap: Build new 138 kV station | Construct new 138 kV ring bus on the Albany to Rainey Creek 69 kV line, remove existing Spillway SW, reterminate Albany to Rainey Creek and Ft Phantom Pump to Onyx lines into Belknap |  | Belknap |  | Planned | 843 - 1027 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2684 | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  | 6211, 60409, 6178, 6219, 6220 | Y | N |  |  | 13679 | 5964
5965 | Benjamin Tap to Katz (BEC): Build new 138 kV line | Construct new 138 kV ring bus Tardis on the Munday to Paducah 138 kV line, rebuild exiting Benjamin Tap to 138 kV, terminate into Tardis, convert Benjamin to 138 kV operation and build new 138 kV line from Benjamin to Katz (BEC) |  | Benjamin Tap | Katz (BEC) | Planned | 769-0954 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2685 | 2020-05-31 |  | 138 | 17.7 | 9 | 0 |  | Knox | Knox | Tier 2 | 2016-02-03 | 2016-05-01 | 2016-05-01 | 6320 | Y | N |  |  | 13680 | 5965
6072 | Eldorado to Ft. McKavitt 69 kV line: Rebuild 69 kV line | Rehab Eldorado to Ft. McKavitt 69 kV line |  | Eldorado Tap | Ft. McKavitt | Planned | 786 - 0971 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2677 | 2020-05-31 |  | 69 | 0 | 19.41 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  | 6505, 6506, 6507, 6508 | Y | N |  |  | 13794 | 6072
6325 | Install two distribution transfomers at Jones Creek | Install two distribution transformers at Jones Creek. Tap Ckt.59 Jones Creek to Freeport/Surfside and Ckt.59 Jones Creek to CORTEZ |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 42546, 42547, 42541, 42542, 42645, 43440 | Y |  |  |  | 14060 | 6325
6573 | Reconductor Dunlavey to Heights Ckt. 31 | Reconductor the Dunlavy to Heights as identified in the 2015 RTP case |  | Dunlavy | Heights | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 47580, 47680 | Y |  |  |  | 14324 | 6573
6971 | Magnolia Mercer Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Magnolia Mercer Substation. |  | Magnolia Mercer |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 69 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  | 7218, 7215, 7220 | Y | N |  |  | 14788 | 6971
6972 | Dimmit Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Dimmit Substation. |  | Dimmit |  |  |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  | 78281 | Y | N |  |  | 14789 | 6972
6973 | Welcome Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement,at Welcome Substation. |  | Welcome |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Austin |  | Tier 4 |  |  |  | 7577 | Y | N |  |  | 14790 | 6973
6974 | New Bremen Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at New Bremen Substation. |  | New Bremen |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Austin |  | Tier 4 |  |  |  | 7271, 7270, 7273 | Y | N |  |  | 14791 | 6974
6976 | Riverside Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Riverside Substation. |  | Riverside |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Fayette |  | Tier 4 |  |  |  | 7275 | Y | N |  |  | 14793 | 6976
6978 | Ranch Road 12 Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Ranch Road 12 Substation. |  | Ranch Road 12 |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  | 7186 | Y | N |  |  | 14795 | 6978
6979 | Lexington Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Lexington Substation. |  | Lexington |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Burleson |  | Tier 4 |  |  |  | 7571 | Y | N |  |  | 14796 | 6979
6980 | Weimar Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Weimar Substation. |  | Weimar |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Colorado |  | Tier 4 |  |  |  | 7254 | Y | N |  |  | 14797 | 6980
6981 | Highway 36 Substation Upgrade | Upgrade the Highway 36 138-kV substation bus to a breaker and a half configuration. |  | Highway 36 |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Washington |  | Tier 4 |  |  |  | 7291 | Y | N |  |  | 14798 | 6981
6982 | Boerne Cico - Comfort - Kendall Transmission Line Upgrade | Upgrade the 138-kV Boerne Cico - Comfort transmission line supporting circuit T148 to bundled 795 ACSR conductor. The planned T148 circuit rating is (MVA): Rate A=440, Rate B=440, Rate C=440. Upgrade the 138-kV Comfort - Kendall transmission line supporting circuit T243 to bundled 959 ACSS/TW conductor. The planned T243 circuit rating is (MVA): Rate A=760, Rate B=760, Rate C=760. |  | Boerne Cico | Kendall | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 18.1 | 0 |  | Kendall | Kendall | Tier 4 |  |  |  | 7151, 7152, 7155 | Y | N |  |  | 14799 | 6982
6983 | Fayetteville - Winchester Transmission Line Upgrade | Upgrade the 138-kV Fayetteville - Winchester transmission line supporting circuit T165 to single 1433 ACSS/TW conductor and OPGW static. The planned T165 circuit rating is (MVA): Rate A=470, Rate B=470, Rate C=470. |  | Fayetteville | Winchester | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 18.8 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  | 7286, 7306 | Y | N |  |  | 14800 | 6983
6984 | Rim Rock - Turtle Creek Transmission Line Storm Hardening | Overhaul and upgrade the 138-kV Rim Rock - Turtle Creek transmission line supporting circuit T270 with single 795 ACSR capable structures, single 795 ACSR conductor, and OPGW static. The planned T270 circuit rating is (MVA): Rate A=220, Rate B=220, Rate C=220. |  | Rim Rock | Turtle Creek | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 7.6 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  | 7143, 7442 | Y | N |  |  | 14801 | 6984
6985 | Gonzales - Harwood Transmission Line Overhaul | Overhaul and upgrade the 69-kV Gonzales - Harwood transmission line supporting circuit T542 with 138-kV capable structures, 795 ASCR Drake, and OPGW static. The planned T542 circuit rating will be (MVA): Rate A=28, Rate B=28, Rate C=28. |  | Luling | Hochheim | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 69 | 0 | 10 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  | 7223, 78577 | Y | N |  |  | 14802 | 6985
43284G | Baytown Area Upgrades | Upgrade Ckt.87 Cedar Bayou to Cedar Bayou tap to increase thermal ratings |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 40011, 40015 | Y |  |  | 0 | 43287 | 43284
43460 | Moody to Stewart Ckt.63 Upgrades | Upgrade Ckt.63 Moody to Stewart |  | Moody | Stewart | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 42950, 43290 | Y |  |  | 0 | 43461 | 43460
17TPIT0002 | Hunt Lane to Pinn Road - 138 kV Transmission Line Rebuild | Rebuild approximately eight circuit miles of 138 kV transmission from Hunt Lane to Pinn Road |  | Hunt Lane | Pinn Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0190 | 2020-06-01 |  | 138 | 0 | 8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5054, 5305, 5345, 5427 | Y | N |  | There are no transformers associated with this project | 9558 | 2307
3277 | Shepherd Road - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Valley line. |  | Shepherd Road | Cagnon-Valley | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5378, 5053, 5465 | Y | N |  | There are no transformers associated with this project | 10628 | 3277
3298 | Skyline - Install a Fourth 345kV Autotransformer. | Install one 600 MVA autotransformer at Skyline switchyard. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0670 | 2020-06-01 |  | 345 | 0 | 0 | 600 |  | Bexar | Bexar | Tier 4 |  |  |  | 5372, 5371, 5368 | Y | N |  | There are no transmission line additions associated with this project | 10649 | 3298
3820 | Rebuild Casa Blanca to Sandia to AEP Mathis | Rebuild 69 kV 4-0 ACSR line sections to 795 ACSR on 138 kV capable structures. |  | Sandia | AEP Mathis | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-06-01 |  | 69 | 0 | 11.45 | 0 |  | Jim Wells | San Patricio | Tier 4 |  |  |  | 5666, 8166, 8407 | Y | N |  |  | 11277 | 3820
3894 | Fowlerton 345 station and 345/138 autotransformer | Add 345 kV bus and autotransformer |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-06-01 |  | 345 | 0 | 0 | 600 |  | McMullen |  | Tier 4 |  |  |  | 5706, 5709, 5901, 80219, 5705 | Y | N |  | 2017 RTP moved project up to 2019. Still studying size needed and possible relocation of existing autotransformer. | 44403 | 3894
4010 | Rebuild Magnolia - Seminole 138 kV line. | *Project pushed back to 2020. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07216 | 2020-06-01 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 38950, 38990 | Y |  |  |  | 11530 | 4010
4895 | CPSE_Capitol Cement Transmission Reconfiguration | Re-configurate Capitol Cement by loop into the existing Dresden to Skyline 138 kV transmission line and removing the existing Captiol Cement to Tuttle 138 kV transmission line. |  | Capitol Cement | Dresden/Skyline | Planned | S-0767 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0246 | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5075, 5130, 5370, 5435 | Y | N |  |  | 12507 | 4895
5145C | Rafter - New 138 kV Substation | Build a new 138 kV transmission line from Cagnon to Rafter. |  | CAGNON | RAFTER | Planned | S-0837 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0261 | 2020-06-01 |  | 138 | 7.86 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5055, 5355 | Y | N |  |  | 14399 | 5145
5417 | Buckeye to LA_HTS Rebuild | Rebuild 1.8 mile 138 kV t-line from Buckeye to LA_Hts. Upgrade line terminal at Buckeye Station for Buckeye to LA_HTS t-line. |  | Buckeye | LA_Hts | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0266, S-0899a | 2020-06-01 |  | 138 | 0 | 1.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5050, 5285 | Y |  |  |  | 13105 | 5417
6255 | Rebuild BEVO to Brundage to Big Wells 69 kV lines. | Rebuild 69 kV 4-0 to 795 ACSR on 138 kV capable structures. |  | BEVO | Big Wells | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-06-01 |  | 69 | 0 | 18.35 | 0 |  | Dimmit | Dimmit | Tier 4 |  |  |  | 5868, 5870, 5871 | Y | N |  |  | 13983 | 6255
6685 | Van Vleck substation loop | Replaces single circuit radial line connected to a pole mounted switch with a double circuit transmission loop to the Van Vleck substation. |  | Van Vleck Substation | Van Vleck Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-06-01 |  | 69 | 0 | 2 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  | 5556, 5554, 5558, 5560 | Y | N |  |  | 14456 | 6685
13TPIT0106 | Killeen SS to Ding Dong | Rebuild 477 ACSR line with 955 ACSS |  | Killeen SS | Ding Dong | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 11037 | 2020-06-30 |  | 138 | 0 | 5.8 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 115, 117, 136, 3423 | Y | N |  |  | 9901 | 2608
3877 | Meadow Lake Substation Addtion | Add a new load serving substation (ring-bus) at Meadow Lake. The station will be built between Cushman and Highway 123 off T572. | Customer Schedule Change | Cushman | Highway 123 | Planned |  | LCRATSC/GVEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016198 | 2020-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7720, 7221, 7226 | Y | N |  |  | 12940 | 3877
5274 | Camp Wood - Leakey Transmission Line Overhaul | Rebuild T269 Camp Wood to Leakey to be 138-kV capable with a nominal conductor rating of 223 MVA at 138-kV (Single Drake) with OPGW and operated at 69-kV. |  | Camp Wood | Leakey | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016183 | 2020-06-30 |  | 69 | 0 | 17.3 | 0 |  | Real | Real | Tier 4 | 2015-12-16 | 2016-01-27 |  | 7426, 8633 | Y | N |  |  | 12950 | 5274
5621 | South McAllen-Bentsen and North Edinburg-West Edinburg | Replace MLSE equipment at North Edinburg and South McAllen |  | North Edinburg | North McAllen | Planned | 795 - 0980 | AEP TCC | Eric Johnson dnlyons@aep.com 918-599-2698 | 3585 | 2020-06-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 5771, 8371, 8380, 8822 | Y | N |  |  | 13351 | 5621
5946 | Winchester Autotransformer Additions | Add two 672 MVA autotransformers at Winchester Substation. Cut the new 345-kV bus at Winchester into an existing Austin Energy owned 345-kV transmission line from FPP to Lost Pines. |  | FPP #1 | Lost Pines | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017413 | 2020-06-30 |  | 345 | 0 | 0 | 1344 |  | Fayette | Bastrop | Tier 3 | 2017-02-01 | 2017-03-20 |  | 77306, 77308, 77309, 7056, 9041, 7306 | Y | N |  |  | 13657 | 5946
44368 | Amos Creek Substation Addition | Construct a 345-kV breakered substation, in a ring bus arrangement, between Red Creek and Bow Wood on circuit T424. The substation will provide transmission service for a generation interconnection request. |  | Red Creek | Bow Wood | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-06-30 |  | 345 | 0 | 0 | 0 |  | Tom Green | McCulloch | Tier 4 |  |  |  | 7077, 6444, 76006 | Y | N |  | 0 | 44369 | 44368
5457 | Load serving | New station to aid in DME's load serving |  | Brinker |  | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 927, 906, 907, 913, 921, 982 | Y | N |  |  | 13160 | 5457
5167 | Borglum to Tuleta: Build new double circuit 138/69 kV line | Construct new Borglum station near Beeville, add 138/69 kV autotransformer capacity at Borglum, rebuild Three Rivers to Beeville 69 kV line with 959.6 ACSS/TW and convert to 138 kV and terminate into Borglum, rebuild the Beeville to Kenedy Switch 69 kV line as double circuit 138/69 kV with 959.6 ACSS/TW from Tuleta and terminate into Borglum, cut-in Beeville to Sinton 69 kV line into Borglum, and cut-in Beeville to Mathis 69 kV line into Borglum | Schedule Update | Borglum | Tuleta | Planned | 742 - 0925 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2916 | 2020-07-31 |  | 138 | 23.5 | 10.5 | 0 |  | Bee | Bee | Tier 1 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 88198, 8196, 8197, 8198, 8592, 8590, 8593 | Y | N |  |  | 13317 | 5167
4971 | Magic Valley II: Build new four breaker 345 kV station | Interconnect Magic Valley II Windfarm at Magic Valley II to connect Magic Valley II to the North Edinburg to Rio Hondo 345 kV line and construct 345 kV line from Bonilla to Ladekidde |  | Cebolla | Ladekidde | Planned | 731 - 0913 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3562 | 2020-08-15 |  | 345 | 0 | 0 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  | 8601, 80512, 80076, 8902, 161753 | Y |  |  |  | 12721 | 4971
5604 | Stewart Road: Construct 345 kV cut-in | Construct new 345 kV 4 breaker ring bus station at AEP Stewart Rd, with two 450 MVA 345/138 autotransformers connected to Stewart Rd 138 station. Hairpin the North Edinburg to SU Palmito 345 kV line into new Stewart Rd 345 station. The hairping will be constructed in a double circuit configuration, approximately 5 miles long. Also install 100 Mvar shunt reactor at the new Stewart Rd 345 kV station. |  | Stewart Road |  | Planned | 792 - 0977 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3582 | 2020-08-31 |  | 345 | 0 | 0 | 900 | 100,0 | Hidalgo | Hidalgo | Tier 2 | 2015-07-10 | 2016-05-19 | 2016-06-14 | 80137, 8951 | Y | N |  |  | 13334 | 5604
6382 | Stewart Road: Construct 345 kV cut-in | Hairpin the North Edinburg to SU Palmito 345 kV line into new Stewart Rd 345 station. The hairpin will be constructed in a double circuit configuration, approximately 5 miles long. |  | Stewart Road | North Edinburg, SU Palmito | Planned | 874 - 1052 | ETT | Teresea Trotman dnlyons@aep.com 918-599-2698 | 3661 | 2020-08-31 |  | 345 | 5 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 2 | 2015-07-10 | 2016-05-19 | 2016-06-14 | 80137, 5966, 8383 | Y | N |  |  | 14126 | 6382
11TPIT0008 | DOWNTOWN 138kV substation | Establish a new 138kV Downtown Substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2020-09-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9261, 9118, 9132 | Y | N |  |  | 8208 | 1032
6348 | Paint Rock to CRMWD Tap #1 69 kV line: Rebuild 69 kV line | Rehab Paint Rock to CRMWD Tap #1 69 kV line |  | Paint Rock | CRMWD Tap #1 | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2709 | 2020-09-09 |  | 69 | 0 | 6.09 | 0 |  | Concho | Concho | Tier 4 |  |  |  | 6369, 6370, 6376 | Y | N |  |  | 14092 | 6348
44383 | Las Majadas | [6 empty] | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2020-09-28 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 80051, 8318 | Y |  |  | 0 | 44384 | 44383
18TPIT0001 | Wiederstein Substation Transformer Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Wiederstein |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-09-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7461 | Y | N |  |  | 10675 | 3319
4571 | Atkins Substation Upgrade | Rebuild Atkins 69kV bus |  | 32864 |  | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2020-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  | No MOD Changes Necessary | 12153 | 4571
5440 | Riverton 345 kV Switching Station | Construct new 345 kV switching station |  | Riverton |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8351 | 2020-11-15 |  | 345 | 0 | 0 | 1200 |  | Reeves |  | Tier 1 | 2016-04-20 | 2017-05-23 | 2017-06-13 | 11075, 11084, 11085, 11083 | Y | N |  |  | 13143 | 5440
7119 | Sand Lake 345 kV Sw. Sta. | Sand Lake 345 kV Sw. Sta. |  | Sand Lake |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8420 | 2020-11-15 |  | 345 | 0 | 0 | 1200 |  | Ward |  | Tier 1 | 2018-02-02 | 2018-05-22 |  | 11098, 11099, 11109, 11097 | Y |  |  |  | 14955 | 7119
7120 | Riverton Sw. Sta. - Sand Lake Sw. Sta. 345 kV Line | Riverton Sw. Sta. - Sand Lake Sw. Sta. 345 kV Line |  | Riverton | Sand Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8443 | 2020-11-16 |  | 345 | 26 | 0 | 0 |  | Reeves | Ward | Tier 1 | 2018-02-02 | 2018-05-22 |  | 11084, 11098 | Y |  |  |  | 14956 | 7120
4875 | Red Gate: Build new 138 kV line | Interconnect STEC Red Gate Power Plant at Permanent with a new 138 kV line into North Edinburg |  | Falfurrias | North Edinburg | Planned | 724 - 0906 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3558 | 2020-11-20 |  | 138 | 7.5 | 7.5 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 88380, 8380, 8896, 161031 | Y | Y |  |  | 12486 | 4875
44426 | Foxtail: Add 345 kV reactor | Add new 345 kV reactor at Foxtail | NEW | Foxtail |  | Planned | 940 - 1118 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2754 | 2020-11-30 01:00 |  | 345 | 0 | 0 | 0 | -50,0 | Baylor |  | Tier 4 |  |  |  | 6076 | Y | N |  | 0 | 44427 | 44426
6934A | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0873 | 2020-12-01 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  | 5133 | Y |  |  |  | 14753 | 6934
6874 | BenDavisAuto1Upgraded | Ben Davis auto1 replacement and at new rating 600 MVA |  | Ben Davis | Ben Davis | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2020-12-01 10:00 |  | 345 | 0 | 0 | 600 |  | Dallas | Dallas | Tier 4 |  |  |  | 970, 968, 993 | Y | N |  |  | 14683 | 6874
5445 | Riverton-Odessa EHV/Moss 345 kV Line | Riverton-Odessa EHV/Moss 345 kV Line |  | Riverton | Odessa EHV | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8356 | 2020-12-15 |  | 345 | 186 | 16 | 0 |  | Reeves | Ector | Tier 1 | 2016-04-20 | 2017-05-23 | 2017-06-13 | 1018, 1029, 11028, 11084 | Y |  |  |  | 14960 | 5445
7121 | Sand Lake Sw. Sta. - Solstice 345 kV Line | Sand Lake Sw. Sta. - Solstice 345 kV Line |  | Sand Lake | Solstice | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8380 | 2020-12-15 |  | 345 | 80 | 0 | 0 |  | Ward |  | Tier 1 | 2018-02-02 | 2018-05-22 |  | 11098, 60404 | Y |  |  |  | 14957 | 7121
6349 | CRMWD Tap #1 to Eden 69 kV line: Rebuild 69 kV line | Rehab CRMWD Tap #1 to Eden 69 kV line |  | CRMWD Tap #1 | Eden | Planned | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2710 | 2020-12-20 |  | 69 | 0 | 13.6 | 0 |  | Concho | Concho | Tier 4 |  |  |  | 6372, 6376 | Y | N |  |  | 14093 | 6349
3774 | Olinger-Ben Davis Line Upgrade | Olinger to Ben Davis 138 kV line upgrade to Cumberland conductor |  | Olinger | Ben Davis | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2020-12-31 |  | 138 | 0 | 17.25 | 0 |  | Collin | Dallas | Tier 4 |  |  |  | 818, 968 | Y | N |  |  | 11194 | 3774
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0733 | 2020-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5045, 5085 | Y | Y |  |  | 11872 | 4320
5835 | Rebuild Sardis to Reagor Springs | Rebuild Sardis (Bus #202) to Reagor Springs (Bus #210) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 16027 | 2020-12-31 |  | 69 | 0 | 15.46 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  | 202, 210 | Y |  |  |  | 13577 | 5835
6112 | Causeway - Sunchase 138 kV Line | Rehab Causeway - Sunchase 138 kV Line |  | Causeway | Sunchase | Planned | 826 - 1010 | AEP TCC | Rich Haley dnlyons@aep.com 918-599-2698 | 3627 | 2020-12-31 |  | 138 | 0 | 3.56 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8744, 8917 | Y | N |  |  | 13838 | 6112
44511 | Aransas_Pass-Seawall: Rebuild and re-conductor with 795 ACSS | Rebuild and re-conductor Aransas Pass - Seawall with 795 ACSS (2000 A conductor). This will relieve overload seen in the 2025 SSWG Summer Peak case for loss of Naval Base- North Padre. |  | Aransas Pass | Seawall | Planned |  | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2021-01-01 |  | 69 | 0 | 3.2 | 0 |  | Nueces | Nueces | Tier 3 |  |  |  | 8427, 8435 | Y | N |  | 0 | 44512 | 44511
7161 | Naval_Base-North_Padre: Rebuild and re-conductor | For Naval Base-North Padre Tap: Rebuild line to 138 kV standards with 2000A conductor (795 ACSS). For North Padre Tap - North Padre station, double ckt. line is already built to 138 kV standards with 477 ACSR. Re-conductor both circuits with largest possible conductor to achieve maximum rating. The 2nd ckt. is part of the North Padre - Mustang Island branch |  |  |  | Planned | 909 - 1087 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3690 | 2021-01-31 |  | 69 | 0 | 12.7 | 0 |  | Nueces | Nueces | Tier 3 |  |  |  | 8495, 8847, 8856 | Y | N |  |  | 15002 | 7161
6873 | Support 69kV to 138kV East Loop Conversion Projects | Upgraded lines Apollo to Naaman to Walnut to Newman to support 69kV to 138kV East Loop Conversion Projects |  | Apollo | Newman | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2021-02-26 |  | 138 | 0 | 10.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 800, 814, 825, 826, 849, 802, 823, 806 | Y | N |  |  | 14682 | 6873
5889 | MIRAGE - 138kV Substation Removal | Remove 138kV MIRAGE customer-owned substation from CNP service. |  | MIRAGE | MCCABE/BIMONT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 111161, 111162, 40209, 42351 | Y | N |  |  | 13606 | 5889
6167 | Harlingen SS - Raymondville #2: Convert to 138 kV | Harlingen SS - Raymondville #2: Convert to 138 kV |  | Harlingen SS | Raymondville #2 | Planned | 864 - 1042 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3650 | 2021-03-31 |  | 138 | 0 | 0 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  | 8300, 8700, 80436, 8302, 8325, 8327 | Y | N |  |  | 13892 | 6167
5940A | Mountain Home Substation and Transmission Line Addition | Construct new Mountain Home substation and construct a 138-kV transmission line from Hunt substation to Mountain Home substation. | For total project cost please see 5940_C | Hunt | Mountain Home | Planned |  | LCRATSC/CTEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017394 | 2021-04-01 |  | 138 | 7.5 | 0 | 0 |  | Kerr | Kerr | Tier 1 | 2016-11-18 |  |  | 7750, 7144 | Y | N |  |  | 13970 | 5940
5530 | Solstice: Build 345 kV station | Construct new 345 kV station with two 345/138 kV autotransformers, reactor, and build new 345 kV line from Solstice to Bakersfield | Schedule Update | Solstice |  | Planned | 789 - 0974 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2649 | 2021-04-30 |  | 345 | 0 | 0 | 1486 |  | Pecos |  | Tier 1 | 2016-04-01 | 2017-05-23 | 2017-06-21 | 60402, 60404, 60418, 60385 | Y | Y |  |  | 13257 | 5530
5539 | Solstice to Bakersfield: Build 345 kV line | Construct new 345 kV station with two 345/138 kV autotransformers, reactor, and build new 345 kV line from Solstice to Bakersfield | Schedule Update | Solstice | Bakersfield | Planned | 789 - 0974 | AEP TNC/LCRATSC | Brent Harris mlforcum@aep.com 918-599-2674 | 2651 | 2021-04-30 |  | 345 | 68 | 0 | 0 |  | Pecos | Pecos | Tier 1 | 2016-04-01 | 2017-05-23 | 2017-06-21 | 60404, 76002 | Y | Y |  |  | 13267 | 5539
6594 | Solstice: Add 345 kV reactor | Construct new 345 kV station with two 345/138 kV autotransformers, reactor, and build new 345 kV line from Solstice to Bakersfield |  | Solstice |  | Planned | 789 - 0974 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2729 | 2021-04-30 |  | 345 | 0 | 0 | 0 | 50,0 | Pecos |  | Tier 1 | 2016-04-01 | 2017-05-01 | 2017-06-01 | 60404 | Y | N |  |  | 14356 | 6594
13TPIT0064 | Rocky Mound Switching Station series capacitors | Install series capacitors for Willow Creek - Clear Crossing - Dermott Switch (Central B) 345 kV line (Oncor Electric Delivery part) |  | Rocky Mound Switching Station |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | C079-E | 2021-05-15 |  | 345 | 0 | 0 | 0 |  | Haskell |  | CREZ |  |  |  | 17012, 17013, 17014, 17015, 1421, 60515 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 9943 | 2644
16TPIT0060 | Midland East - Spraberry 138 kV Line | Upgrade existing line |  | Midland East | Spraberry | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8147-E | 2021-05-15 |  | 138 | 0 | 18.8 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1132, 1133, 1329 | Y | N |  |  | 10518 | 3172
4304 | Tradinghouse - Sam Switch 345 kV Line | Upgrade existing double-circuit line |  | Tradinighouse | Sam Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1706 | 2021-05-15 |  | 345 | 0 | 45.4 | 0 |  | McLennan | Hill | Tier 4 |  |  |  | 3405, 13405, 68090 | Y | N |  |  | 11860 | 4304
4847 | Belton - Killeen Sw. Sta. 138 kV Line | Upgrade existing line |  | Belton | Killeen Sw. Sta. | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R902 | 2021-05-15 |  | 138 | 0 | 17.2 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3423, 3610, 3633, 13610 | Y | N |  |  | 12449 | 4847
5526 | Forney 345 kV Switching Station | Reconstruct existing 345 kV switching station |  | Forney |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4114 | 2021-05-15 |  | 345 | 0 | 0 | 0 |  | Kaufman |  | Tier 3 |  |  |  | 2467, 2433, 2437, 2470, 2478, 150189, 2438, 12438 | Y | N |  |  | 13253 | 5526
5624 | Killeen Sw. Sta. 345/138 kV Autotransformer Replacement | Replace existing autotransformer |  | Killeen Sw. Sta. | Killeen Sw. Sta | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R797 | 2021-05-15 |  | 345 | 0 | 0 | 600 | -75,0 | Bell | Bell | Tier 4 |  |  |  | 3422, 3423, 13423 | Y | N |  |  | 13354 | 5624
6287 | Sherry Sw. - Webb/Kennedale 345 kV DCKT Line | Rebuild existing 345 kV Line |  | Sherry | Webb/Kennedale | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4252 | 2021-05-15 |  | 345 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1911, 1918, 1930, 1929, 1932, 1934 | Y |  |  |  | 14016 | 6287
7024 | Norwood Sw. Sta. - Cedar Hill Sw. Sta. 345 kV Line | Upgrade existing Norwood Sw. Sta. - Cedar Hill Sw. Sta. 345 kV Line |  | Norwood | Cedar Hill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4248 | 2021-05-15 |  | 345 | 0 | 12.4 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2406, 2410, 2420 | Y | N |  |  | 14846 | 7024
5525 | Forney - Lake Hubbard 345 kV Line | Construct new 345 kV line |  | Forney | Lake Hubbard | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4233 | 2021-05-16 |  | 345 | 0 | 7.5 | 0 |  | Kaufman | Dallas | Tier 4 |  |  |  | 2455, 2467 | Y | N |  |  | 13252 | 5525
5522 | Lake Hubbard 345/138 kV Switching Station | Construct new 345/138 kV switching station |  | Lake Hubbard |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4139 | 2021-05-17 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  | 12455, 12456, 2401, 2402, 2455 | Y | N |  |  | 13249 | 5522
6875 | Support 69kV to 138kV West Loop Conversion Projects | Upgraded line Apollo to Jupiter to support 69kV to 138kV West Loop Conversion Projects |  | Apollo | Jupiter | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2021-05-27 |  | 138 | 0 | 3.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 803, 806, 802, 815, 829 | Y | N |  |  | 14684 | 6875
6668A | Freeport - Master Plan | Upgrade Ckts. 18 & 27 DOW to Jones Creek to increase thermal limits |  | DOW | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 |  |  | 2017-12-12 | 42500, 42530 | Y | N |  |  | 14449 | 6668
5286B | Fayette Area Upgrades | Upgrade existing Plum - Flatonia (T133) TL with a minimum rating of 380 MVA and with OPGW. Upgrade terminal equipment at Plum to achieve a planned static normal and emergency rating of 530 MVA on Piney Creek - Plum (T535). | Planning In-Service Date Change. Updated to a phased project, the original TPIT project number is 5286. | Flatonia | Plum | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1019024 | 2021-05-31 |  | 138 | 0 | 19.6 | 0 |  | Fayette | Fayette | Tier 4 | 2017-06-29 | 2017-07-28 |  | 7248, 7274, 7307 | Y | N |  |  | 14584 | 5286
5939 | Cooks Point Substation and Transmission Line Addition | Construct a load serving 138-kV substation in Northern Burleson County called Cooks Point. Construct a 16.7-mile single circuit 138-kV transmission line from Lyle Wolz to Cooks Point 138-kV transmission line with bundled 795 ACSR Drake (440 MVA). Bryan Texas Utilities will construct a 138-kV transmission line from Steele Store Substation to Cooks Point bundled 1033 ACSR Curlew (495 MVA). |  | Cooks Point | Lyle Wolz | Planned | 6666 | LCRATSC/BBEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017348 | 2021-05-31 |  | 138 | 16.7 | 0 | 0 |  | Burleson | Burleson | Tier 4 | 2016-07-07 |  |  | 7569, 7567 | Y | N |  |  | 13650 | 5939
6029 | Anson to Stamford 69 kV line: Rebuild 69 kV line | Rehab Anson to Stamford 69 kV line | Schedule Update | Anson | Stamford | Planned | 786 - 0971 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2667 | 2021-05-31 |  | 69 | 0 | 16.08 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6172, 6173, 6175, 6180 | Y | N |  |  | 13753 | 6029
6572 | Ballinger to Eden 69 kV line: Rebuild taps | Ballinger to Eden 69 kV line: Rebuild taps | Contact Update | Ballinger | Eden | Planned | 890 - 1068 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2814 | 2021-05-31 |  | 69 | 0 | 2.8 | 0 |  | Runnels | Concho | Tier 4 |  |  |  | 6338, 6369, 6370, 6372, 6376 | Y | N |  |  | 14323 | 6572
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into future 138kV Martinez to Skyline transmission line |  | Converse | Martinez-Skyline | Planned | T-0177 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0601 | 2021-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5098, 5294, 5368 | Y | N |  | There are no transformers associated with this project | 8143 | 967
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  | 5601, 5600, 5602 | Y | N |  |  | 8729 | 1538
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0196 | 2021-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 9559 | 2308
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 2000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2021-06-01 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 9723 | 2443
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-06-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 5626, 5634 | Y | N |  |  | 11275 | 3818
3821 | Pearsall to Palo Duro 138 kV line upgrade | Upgrade Pearsall to Palo Duro 138 kV line as recommended in 2013 RTP. Will investigate using a reconductor on existing structures with ACCC and other high temperature conductors. |  | Pearsall | Paloduro | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-06-01 |  | 138 | 0 | 10.8 | 0 |  | Frio | Frio | Tier 4 |  |  |  | 5866, 5895 | Y | N |  |  | 11278 | 3821
4883 | McCoy 69 KV substation | Add a new load serving substation between Pleasanton and Tordillo |  | McCoy |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-06-01 |  | 69 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5721, 5714, 5715 | Y | N |  |  | 12494 | 4883
43367A | LP&L Integration Tie Lines | 345 kV Line from Ogallala to Abernathy |  | 345 kV Ogallala | 345 kV Abernathy | Planned |  | SHRY | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2021-06-01 |  | 345 | 50.9 | 0 | 0 |  | Castro | Hale | Tier 1 | 2015-12-29 | 2016-06-09 |  | 79501, 79506 | Y |  |  | Cost includes the expansion required at the existing stations to accommodate the new lines | 43371 | 43367
43367C | LP&L Integration Tie Lines | 345 kV Line from Abernathy to Wadsworth |  | 345 kV Abernathy | 345 kV Wadsworth | Planned |  | SHRY | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2021-06-01 |  | 345 | 26.2 | 0 | 0 |  | Hale | Lubbock | Tier 1 | 2015-12-29 | 2016-06-09 |  | 59178, 79506 | Y |  |  | 0 | 43373 | 43367
43367B | LP&L Integration Tie Lines | 345 kV Line from Abernathy to North |  | 345 kV Abernathy | 345 kV North | Planned |  | SHRY | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2021-06-01 |  | 345 | 23.32 | 0 | 0 |  | Hale | Lubbock | Tier 1 | 2015-12-29 | 2016-06-09 |  | 59156, 79506 | Y |  |  | 0 | 43372 | 43367
11TPIT0011 | Northeast 138kV Substation | Northeast 138kV Substation |  | Techridge | Northeast SUB |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2021-06-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9195, 9045, 9190 | Y |  |  |  | 13043 | 5357
44372 | Geronimo T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Geronimo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-06-25 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 7606 | Y |  |  | 0 | 44373 | 44372
5430E | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2021-07-01 |  | 138 | 0 | 1.521 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 928, 931 | Y | N | N/A | 0 | 43910 | 5430
5430F | Conversion to 138kV | Retire the existing 69kV North Lakes substation together with the transformer relocated from Denton North |  | North Lakes |  | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2021-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 915, 928 | Y | N | N/A | 0 | 43911 | 5430
5430D | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2021-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 905, 915 | Y | N | N/A | 0 | 43909 | 5430
5430G | Conversion to 138kV | Line already insulated for 138kV. Line will be terminated at the new 138kV Hickory substation |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2021-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 905, 910 | Y | N | N/A | 0 | 43912 | 5430
5430H | Conversion to 138kV | Construct new 138kV Hickory substation and terminate the existing Bonnie Brae - Hickory (which is already insulated for 138kV) at the new 138kV Hickory substation. |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2021-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 922, 931 | Y | N | N/A | 0 | 43913 | 5430
5559 | Add new 138kV Bonnie Brae Substation and retire the 69kV sta |  |  | Bonnie Brae |  | Planned | N/A | DENTON | Charles Sears cxsears@cityofdenton.com 940-349-7111 |  | 2021-07-01 |  | 138 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  | 905, 931 | Y | N | N/A |  | 13291 | 5559
6526 | Place second auto at Einstein |  |  | Einstein345 | Einstein138 | Planned |  | SHRY | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2021-07-01 |  | 345 | 0 | 0 | 708 |  | Glasscock | Glasscock | Tier 4 |  |  |  | 79634, 79632, 79565 | Y |  |  |  | 14264 | 6526
6988 | Sheriff's Posse to Marion Transmission Line Upgrade | Replace existing T-340 795 ACSR with 959 ACSS. |  | Sheriff's Posse | Marion | Planned |  | NBU | Gregory Thomas gthomas@nbutexas.com 830-608-8953 |  | 2021-07-01 |  | 138 | 0 | 3.35 | 0 |  | Comal | Guadalupe | Tier 4 |  |  |  | 7178, 7460 | Y | N |  |  | 14806 | 6988
6540 | LCRA Gonzales to GVEC Gonzales Transmission Line Upgrade | Replace 0.98 miles of 4/0 ACSR 69 kV T-line, with double circuit 138kV structures, 795 ACSR "Drake", initially operate one circuit at 69 kV; plus terminal improvements |  | LCRA Gonzales | GVEC Gonzales | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-08-31 |  | 69 | 0 | 0.98 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  | 7592, 7626 | Y | N |  |  | 14280 | 6540
6666 | BRYN_6666_Steele_Store_to_Cooks_Point | Construct 138kV line from BTU Steele Store to LCRA Cooks Point (Bundled 1033 ACSR - Curlew) |  | 32852 | 7569 | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2021-09-30 |  | 138 | 6 | 0 | 0 |  | Brazos | Burleson | Tier 4 | 2016-07-07 | 2017-07-07 |  | 32852, 7569 | Y |  |  |  | 14422 | 6666
5206 | Brackettville to Escondido: Construct 138 kV line | Build a double circuit capable 138 kV circuit from Brakettville to Escondido station |  | Brackettville | Escondido | Under Construction | 762-0947 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3570 | 2021-11-30 |  | 138 | 45 | 0 | 0 |  | Kinney | Maverick | Tier 2 | 2016-01-05 | 2017-01-20 | 2017-02-08 | 8252, 8260 | Y | N |  |  | 12865 | 5206
5940B | Mountain Home Substation and Transmission Line Addition | Construct a 138-kV transmission line from Harper substation to Mountain Home substation. | For total project cost please see 5940_C | Mountain Home | Harper | Planned |  | LCRATSC/CTEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017394 | 2021-11-30 |  | 138 | 11.5 | 0 | 0 |  | Kerr | Gillespie | Tier 1 | 2016-11-18 |  |  | 74100, 7410, 7750 | Y | N |  |  | 13971 | 5940
5940C | Mountain Home Substation and Transmission Line Addition | Add one(1) 138/69-kV autotransformer at Harper substation, convert the existing 69-kV Harper to Live Oak transmission line (T288) to 138-kV, convert Live Oak substation to 138-kV, cut-in the existing Gillespie to Fredericksburg 138-kV transmission line (T379) at Live Oak, and connect the 69-kV Gillespie to Live Oak (T131) and Live Oak to Goehman Tap (T287) transmission lines to create a continuous 69-kV circuit from Gillespie to Goehman Tap. |  | Harper | Live Oak | Planned |  | LCRATSC/CTEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017394 | 2021-11-30 |  | 138 | 0 | 21.7 | 45 |  | Gillespie | Gillespie | Tier 1 | 2016-11-18 |  |  | 7412, 7130, 7132, 7149, 7410, 7413, 74100 | Y | N |  |  | 13972 | 5940
17TPIT0005 | St. Jo Autos | Replace 40 MVA autos with 60 MVA autos |  | St. Jo | St. Jo | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12005 | 2021-12-01 |  | 138 | 0 | 0 | 60 |  | Cooke |  | Tier 4 |  |  |  | 750, 746 | Y | N |  |  | 9491 | 2243
6934B | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0873 | 2021-12-01 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  | 5133 | Y |  |  |  | 14754 | 6934
6786 | Schumansville T2 Replacement | Replace T2, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Schumansville |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-12-17 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7609 | Y |  |  |  | 14580 | 6786
3948 | Steamboat to Tuscola: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola |  | Steamboat | Tuscola | Planned | 685 - 0855 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 1851 | 2021-12-31 |  | 69 | 0 | 9.856 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6328, 6331, 60332 | Y | N |  |  | 11441 | 3948
3949 | Steamboat to Winters: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola |  | Steamboat | Winters | Planned | 685 - 0855 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 1850 | 2021-12-31 |  | 69 | 0 | 9.944 | 0 |  | Taylor | Runnels | Tier 4 |  |  |  | 6333, 60332 | Y | N |  |  | 11442 | 3949
6668B | Freeport - Master Plan | New 345 kV double-circuit line from Bailey Substation to Jones Creek Substation |  | Bailey | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 345 | 96 | 0 | 0 |  | Wharton | Brazoria | Tier 1 |  |  | 2017-12-12 | 42530, 44040 | Y | N |  |  | 14424 | 6668
6876 | Support 69kV to 138kV West Loop Conversion Projects | Upgraded line Jupiter to College to support 69kV to 138kV West Loop Conversion Projects |  | Jupiter | College | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2021-12-31 |  | 138 | 0 | 2.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 806, 829 | Y |  |  |  | 14685 | 6876
44399 | SPI GIS | [6 empty] | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2022-03-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 8335, 8917 | Y |  |  | 0 | 44400 | 44399
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line | Project Deferral | Handley | Hemphill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5214 | 2022-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 11818 | 4270
4829 | Hutto Sw. Sta. second 345/138 kV autotransformer | Install new autotransformer |  | Hutto |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R750 | 2022-05-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 4 |  |  |  | 13660, 3696, 3666 | Y | N |  |  | 12435 | 4829
5480 | Trinidad - RichLC 345kV DCKT Line | Upgrade existing DCKT Line | Project Deferral | Trinidad Sw. Sta. | Richland Chambers Sw. Sta | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6027 | 2022-05-15 |  | 345 | 0 | 37.4 | 0 |  | Henderson | Freestone | Tier 4 |  |  |  | 3123, 3124, 3133, 3134 | Y | N |  |  | 13199 | 5480
6360 | Hicks - Roanoke 138 kV Line with Alliance 138 kV Sub | Construct new 138 kV Line |  | Hicks | Roanoke | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5253 | 2022-05-15 |  | 138 | 10 | 0 | 0 |  | Tarrant | Denton | Tier 2 |  |  |  | 1855, 1851, 1854, 2081, 2082 | Y |  |  |  | 14104 | 6360
4804 | Wichita Falls South 345/138 kV autotransformer | Install autotransformer |  | Wichita Falls South |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4010 | 2022-05-16 |  | 345 | 0 | 0 | 600 |  | Archer |  | Tier 4 |  |  |  | 11464, 11465, 1422, 1425, 1464 | Y | N |  |  | 12410 | 4804
4465 | Wirtz to FlatRock to Paleface Transmission Line Upgrade | Upgrade the 17.34 mile Wirtz (7104) - Flat Rock (7111) - Paleface (7477) 138-kV transmission line to single 795 ACSR Drake, 221 MVA. |  | Wirtz | Paleface | Conceptual |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2022-05-31 |  | 138 | 0 | 17.34 | 0 |  | Burnet | Travis | Tier 3 |  |  |  | 7104, 7111, 7477 | N | N |  |  | 12026 | 4465
5244 | Hardy to Northside Ckt.91 Thermal Uprate | Upgrade Ckt.91 Hardy to Northside to increase thermal ratings | - Overall Date Update | Hardy | Northside | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45840, 47711 | N | N |  |  | 12919 | 5244
5945 | Howard Lane to Wells Branch Transmission Line Upgrade | Rebuild the 0.9-mile 138-kV line from Wells Branch (7288) to Howard Lane Tap (7335) in Travis county such that the new 2-hour emergency rating is at least 710 MVA. |  | Howard Lane | Wells Branch | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2022-05-31 |  | 138 | 0 | 0.9 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 7288, 7335 | N | N |  |  | 13656 | 5945
5949 | Study Butte Substation and Transmission Line Addition | Rebuild Altuda - Persimmon Gap to 138-kV capable structures. Establish a new transmission line 138-kV capable operated at 69-kV from Persimmon Gap to Study Butte Substation. | Scope of project redefined | Persimmon Gap | Study Butte | Conceptual |  | LCRATSC/RGEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017405 | 2022-05-31 |  | 69 | 61 | 0 | 0 |  | Presidio | Brewster | Tier 4 |  |  |  | 76667, 76668, 76669 | N | N |  |  | 13660 | 5949
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2022-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9077, 9238 | Y | N |  | Will add the ptoject to the base case. | 8207 | 1031
15TPIT0031 | Chavaneaux_Chavaneaux Tap - 138 kV Transmission Line Rebuild | Rebuild approximately three circuit miles of 138 kV transmission from Brooks to Chavaneaux Tap. |  | Brooks | Chavaneaux | Conceptual |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0260 | 2022-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5045, 5085, 5330 | Y | N |  | There are no transformers associated with this project | 9555 | 2304
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-06-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  | 5705 | Y | N |  |  | 9835 | 2554
3334 | Fort Sam to Kirby and Fort Sam to Tenth Street MLSE Upgrade | Upgrade entire bus and terminals at Fort Sam and ensure a rating of 2000 A. |  | Fort Sam | Kirby/Tenth Street | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0744 | 2022-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5160, 5250, 5420 | Y | N |  | There are no transformers associated with this project | 10692 | 3334
4425 | New TR-JV Ckt 961 | Add 2nd Ckt from TR to HL to tie-in to HL-JV Ckt 961 bypassing HL and creating TR-JV Ckt. |  | Techridge | Jollyville | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2022-06-01 |  | 138 | 1.7 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9190, 9223, 9224 | Y | N |  |  | 11984 | 4425
5430J | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line |  | Eagle |  | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2022-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 926, 924 | Y | N | N/A | 0 | 43915 | 5430
5430I | Conversion to 138kV | Switch the Hickory - Locust line on to the 138kV substations |  | Hickory | Locust | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2022-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 914, 910 | Y | N | N/A | 0 | 43914 | 5430
44416 | Add a 2nd circuit at Brinker - Denton Steam |  |  | Brinker | Denton Steam | Planned |  | DENTON | Chuck Sears |  | 2022-07-01 |  | 138 | 0.63068 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 927, 982 | Y | N |  | 0 | 44417 | 44416
3505 | Cibolo Substation, T3 transformer addition | Add T3, 40 MVA 138-26.18 kV power transformer, CSW and low side |  | Cibolo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-10-14 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7608 | Y | N |  |  | 10887 | 3505
13TPIT0070 | Nash Creek Substation | Replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7596 | Y | N |  |  | 10678 | 3322
6373 | Hamilton Road to Picacho ckt #2, rebuild 138 kV line | Rebuild Hamilton Road to Picacho 138 kV line ckt #2 |  | Hamilton Road | Picacho | Planned | 870-1051 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3660 | 2023-03-30 |  | 138 | 0 | 8.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  | 8186, 8255, 8690, 8688, 8684 | Y | N |  |  | 14117 | 6373
4732 | Big Spring West - Stanton East 138 kV Line | Upgrade existing line | Project Deferral | Big Spring West | Stanton East | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8303 | 2023-05-15 |  | 138 | 0 | 17.6 | 0 |  | Howard | Martin | Tier 4 |  |  |  | 1324, 1326 | Y | N |  |  | 12326 | 4732
4827 | Lufkin - Nacogdoches Southeast 138 kV Line | Upgrade existing line |  | Lufkin | Nacogdoches | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6062 | 2023-05-15 |  | 138 | 0 | 21.6 | 0 |  | Angelina | Nacogdoches | Tier 3 |  |  |  | 3120, 3314, 3316, 3315, 3318 | Y | N |  |  | 12434 | 4827
5436 | Morgan Creek - McDonald 138 kV Line | Upgrade existing line | Project Deferral | Morgan Creek | McDonald Rd | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8360 | 2023-05-15 |  | 138 | 0 | 31.8 | 0 |  | Howard | Mitchell | Tier 3 |  |  |  | 1032, 1333 | Y | N |  |  | 13139 | 5436
5479 | Trinidad_TriC_Watermill_345kV_DCKT | Upgrade existing DCKT line |  | Trinidad Sw. Sta | TriCorner/Watermill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4045 | 2023-05-15 |  | 345 | 0 | 92.1 | 0 |  | Henderson | Dallas | Tier 4 |  |  |  | 2427, 2432, 3123, 3124 | Y | N |  |  | 13184 | 5479
6291 | Royse Sw. Sta. - Farmersville Sw. Sta. 345 kV DCKT Line | Rebuild existing 345 kV Line |  | Royse | Farmersville | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4255 | 2023-05-15 |  | 345 | 0 | 30.4 | 0 |  | Rockwall | Collin | Tier 3 |  |  |  | 1685, 2461, 2478 | Y |  |  |  | 14020 | 6291
7023 | Hicks Sw. Sta. - Roanoke Sw. Sta. 345 kV Double-circuit Line | Upgrade existing Hicks Sw. Sta. - Roanoke Sw. Sta. 345 kV Double-circuit Line |  | Hicks Sw. Sta. | Roanoke Sw. Sta. | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4227 | 2023-05-15 |  | 345 | 0 | 19.4 | 0 |  | Tarrant | Denton | Tier 4 |  |  |  | 1845, 1851, 1847, 1853, 2081 | Y | N |  |  | 14845 | 7023
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0385 | 2023-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5416, 5250, 5395 | Y | N |  | There are no transformers associated with this project | 10365 | 3021
3297 | Tezel Road - New 138kV Substation | Loop new 138 kV substation into the existing 138 kV Helotes to Bandera line. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2023-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 5421, 5020, 5200 | Y |  |  | There are no transformers associated with this project | 10840 | 3297
5942 | Merriltown Substation Addition | Add a new 138-kV breakered substation between Wells Branch and Round Rock South on T526 approximately 0.21 miles from Wells Branch. The substation will serve Oncor load. |  | Wells Branch | Round Rock South | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2023-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Williamson | Tier 4 |  |  |  | 7290, 3672, 7288 | Y | N |  |  | 13653 | 5942
6253 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2023-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9276, 9077, 9238 | Y |  |  |  | 13981 | 6253
20TPIT0000 | Parkway Substation T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7611 | Y | N |  |  | 10679 | 3323
5430L | Conversion to 138kV | Reconnect the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 922, 930 | Y | N | N/A | 0 | 43917 | 5430
5430M | Conversion to 138kV | Transfer the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 910, 932 | Y | N | N/A | 0 | 43918 | 5430
5430K | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line |  | Eagle |  | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 922, 926 | Y | N | N/A | 0 | 43916 | 5430
5430N | Conversion to 138kV | Retire the existing 69kV RD Wells substation together with the autotransformers |  | RD Wells |  | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 932, 930 | Y | N | N/A | 0 | 43919 | 5430
5461 | Load serving |  |  | Puckrus | Mayhill | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 1.9 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 929, 917 | Y | N |  |  | 13164 | 5461
4490 | LaPalma: Add 2nd 345/138 kV autotransformer | Add 345/138 kV autotransformer capacity at LaPalma |  | LaPalma |  | Planned | 710 - 0880 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2664 | 2904 | 2023-09-30 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 3 |  |  |  | 8356, 8317, 8314 | N | N |  |  | 12067 | 4490
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-11-17 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7622 | Y | N |  |  | 10677 | 3321
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing autotransformer |  | Elkton | Elkton | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6032-E | 2024-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 4 |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 10501 | 3155
4821 | Nacogdoches Southeast - Herty North 138 kV Line | Upgrade existing line |  | Nacogdoches Southeast | Herty North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6049 | 2024-05-15 |  | 138 | 0 | 13.4 | 0 |  | Nacogdoches | Angelina | Tier 4 |  |  |  | 3120, 3319 | Y | N |  |  | 12427 | 4821
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-05-24 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7611 | Y | N |  |  | 10680 | 3324
4477 | Austrop to Sandow Double 345-kV Transmission Line Upgrade | Upgrade 33.98-mile Austrop (7040) to Sandow (13429) 345-kV double circuit transmission lines to bundled 959 Suwannee conductor (1921 MVA). |  | Austrop | Sandow | Conceptual |  | LCRATSC/Oncor | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2024-05-31 |  | 345 | 0 | 67.96 | 0 |  | Travis | Milam | Tier 1 |  |  |  | 7040, 13429 | N | N |  |  | 12038 | 4477
4479 | Cut T511 Gilleland Creek to Clear Springs into AEN Dunlap | Cut-In the existing Gilleland Creek (7340) to Clear Springs (7050) T511 345kV transmission line into Austin Energy's Dunlap (9044) substation. |  | Gilleland Creek | Clear Springs | Conceptual |  | LCRATSC/AEN | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2024-05-31 |  | 345 | 4 | 0 | 0 |  | Travis | Guadalupe | Tier 1 |  |  |  | 7050, 7340, 9044 | N | N |  |  | 12043 | 4479
5287 | Buda to Turnersville Transmission Line Addition | Construct a second 138-kV transmission line between Buda and Turnersville Substations. |  | Buda | Turnersvile | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 3 |  |  |  | 7498, 7500 | N | N |  |  | 12963 | 5287
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Howard line. |  | Masterson Rd. | Cagnon-Howard | Planned | T-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0538 | 2024-06-01 |  | 138 | 8 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5296, 5054, 5230 | Y | N |  | There are no transformers associated with this project | 9466 | 2218
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-06-28 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  | 7239 | Y | N |  |  | 10694 | 3336
3901 | Lobo to Freer: Rebuild 69 kV line | Rebuild Lobo to Freer 69 kV line with 795 ACSS | Description Update | Lobo | Freer | Planned | 677 - 0846 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2596 | 2024-06-30 |  | 69 | 0 | 49.8 | 0 |  | Webb | Duval | Tier 3 |  |  |  | 8505, 80222 | N | N |  |  | 11371 | 3901
44419 | Load serving |  |  | Mayhill | Denton Steam/Brinker | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 138 | 5.1 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 927, 929, 982 | Y | N |  | 0 | 44420 | 44419
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and-or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle-Weiderstein | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0645b | 2025-06-01 12:00 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5360, 5435 | Y | N |  | There are no transformers associated with this project | 9557 | 2306
6774 | Marina: Add New Distribution Station | Add New Marina Distribution Station |  | Highway 9 | Nueces Bay | Planned | 878 - 1056 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3665 | 2026-01-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8026, 8441, 8470, 8474 | Y | N |  |  | 14780 | 6774
1549 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2026-06-01 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 5828, 5857 | N | N |  |  | 8754 | 1549
2161 | Oaks to Loxley | Build new 138 kV 795 ACSR circuit from Oaks to a new AEP switching station Loxley in the Leon Creek to Pleasanton line | Load forecasts have changed since project was RPG approved | Oaks | Loxley | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2026-06-01 |  | 138 | 6 | 0 | 0 |  | Atascosa | Atascosa | Tier 3 | 2011-12-16 | 2012-04-25 |  | 5713, 80491 | N | N |  | This new line was part of Karnes Electric Cooperative Project that was approved in 2012. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 9408 | 2161
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits, as recommended in 2013 RTP. |  | Bevo | Carrizo Springs | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2026-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 1 | 2012-04-12 | 2012-08-12 | 2012-09-12 | 5871, 8244 | N | N |  | This new line was part of Karnes and Medina Electric Cooperatives Project that was approved in 2012. This also helped voltage on AEP transmission under contingencies. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 10984 | 3595
3822 | San Miguel to Sigmor 138 kV line upgrade | Upgrade San Miguel to Sigmor 138 kV line as recommended in 2013 RTP. Will investigate re-conductoring on existing structures with ACCC and other high temperature conductors. |  | San Miguel | Sigmor | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2026-06-01 |  | 138 | 0 | 26.3 | 0 |  | Atascosa | Live Oak | Tier 3 |  |  |  | 5689, 5902, 8404 | N | N |  | Studies after the 2013 RTP have shown that AEP's approved project to rebuild the 69 kV Beeville to Three Rivers to 138 kV, TPIT 5166, reduces the loading on this line. STEC believes that rebuilding San Miguel to Sigmor is likely to be justified in the future by load growth and or generation additions. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 11279 | 3822
5220 | Move Orange Grove load to 138 kV bus | Move load from the 69 KV to the 138 KV instead of replacing auto. 2015 RTP |  | Orange Grove |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  | 5660 | Y | N |  |  | 12887 | 5220
4280 | Allen Switching Station 138 kV series reactor | Install series reactor on 345/138 kV autotransformer #2 |  | Allen Switching Station |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R961 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 12514, 2512, 2514, 12512 | N | N |  |  | 11830 | 4280
5717 | Waller 138kV Substation Reconfiguration | Convert Waller substation from single-circuit radial service to radial & tap service. Install new tap section from Ckt.65 Hockley to Peters. |  | Waller | Hockley/Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-12-31 |  | 138 | 2.4 | 0 | 0 |  | Harris | Austin | Tier 4 |  |  |  | 46561, 46560, 45885, 46220 | N | N |  |  | 13459 | 5717
5763A | CHORIN to STRANG Ckt.87 | Upgrade 138kV Ckt.87 CHORIN to STRANG to increase thermal ratings. | - Transmission upgrade portion now on hold...Substation upgrades still expected | CHORIN | STRANG | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40000, 40010, 40015, 40120, 40320, 40171, 40240, 41440, 41500 | Y | N |  |  | 44226 | 5763
5763C | CHORIN to STRANG Ckt.87 | STRANG to Cedar Bayou Ckt.87 |  | STRANG | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40010, 41500 | Y | N |  | 0 | 44228 | 5763
4706B | HO Clarke to Webster Ckt.05 | Upgrade Southwyck to Webster Ckt.05 to increase thermal ratings |  | Southwyck | Friendswood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2031-06-29 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42651, 43260 | Y | N |  | 0 | 43254 | 4706
4997E | Deepwater Area Conversions | Upgrade Harrisburg substation for Ckt.33 loop service. | - Project cancelled...Breakers will remain at Harrisburg substation | Harrisburg | TEXPET/ Reed | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 986 | 2099-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40470, 40800, 41040, 41560 | Y |  |  | 0 | 43263 | 4997

## CompletedTPIT100118NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2018
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
5430B | Conversion to 138kV | Retire the existing 69kV Denton North station together with the auto transformers. Cost includes construction of two new 138kV terminals at 138kV Denton North |  | Denton North |  | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-01-01 | 2017-01-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 912, 915, 985 | Y | N | N/A |  | 13133 | 5430
5428C | Phase 2 of the conversion to 138kV | Retire existing 69kV Kings Row to Denton North line |  | Kings Row | Denton North | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-01-01 | 2017-07-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 909, 912 | Y | N | N/A |  | 13115 | 5428
3398 | Cedar Hill: Add 69 kV capacitor bank | Add one 7.2 Mvar capacitor bank at Cedar Hill | IN-SERVICE | Cedar Hill |  | Under Construction | 629 - 0797 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2587 | 2017-02-02 | 2017-02-02 | 69 | 0 | 0 | 0 | 0,7.2 | Coke |  | Tier 4 |  |  |  | 6423 | Y | N |  |  | 10771 | 3398
3396 | Cedar Hill: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Cedar Hill | IN-SERVICE | Cedar Hill |  | In-Service | 626 - 0794 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2584 | 2017-02-02 | 2017-02-02 | 69 | 0 | 0 | 90 |  | Coke |  | Tier 4 |  |  |  | 6423, 6425 | Y | N |  |  | 10769 | 3396
3402 | Abilene Northwest to Ely Tap: Rebuild 69 kV line | Rebuild Abilene Northwest to Ely Tap 69 kV line | IN SERVICE | Abilene Northwest | Ely Tap | Under Construction | 630 - 0798 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2589 | 2017-02-03 | 2017-02-03 | 69 | 0 | 8.2 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6225, 6241 | Y | N |  |  | 10775 | 3402
3745 | Interconnect Los Vientos III at Del Sol 345 kV Station | Del Sol: Add 345 kV breaker terminal for WF interconnect and install second 345 kV circuit to POI |  | DEL SOL |  | In-Service | 666 - 0835 | ETT | KENNETH 'RICH' HALEY dnlyons@aep.com 918-599-2698 | 3530 | 2017-02-06 | 2017-02-14 | 345 |  |  |  |  | Starr |  | Tier 4 |  |  |  | 80355 | Y | N |  |  | 11166 | 3745
5683A | Line H Rebuild and 138kV conversion. | Install temporary 10 MVAR cap bank and de-energize IH20-Collie Field Tap 69 kV line (38040-38041). |  | 38041 | 38041 | Under Construction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-02-10 |  | 69 | 0 | 0 | 0 | 0,10 | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38040, 38041, 38150 | Y |  |  | Temporary 10 MVAR Capbank at Collie Field Tap (Bus# 38041). | 13743 | 5683
5191 | Gas Pad Tap: Build 138 kV station | Construct 138 kV POD box bay for customer interconnection | IN SERVICE | Gas Pad Tap |  | In-Service | 755 - 0938 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2629 | 2017-02-28 | 2017-02-28 | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60397 | Y | N |  |  | 12850 | 5191
5207 | Goliad 138 kV Station: Upgrade 69 kV Station | Add 138 kV design box bay with two breakers, expandable to three breakers and operated at 69 kV. |  | Goliad |  | In-Service | 763-0948 | AEP TCC | Wilbur Roberts dnlyons@aep.com 918-599-2664 | 3571 | 2017-02-28 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | Y | N |  |  | 12866 | 5207
3825 | Jordan: Install 2nd 800MVA Autotransformer | Install 2nd 800MVA autotransformer at Jordan substation |  | Jordan |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 992 | 2017-02-28 |  | 345 | 0 | 0 | 800 |  | Chambers |  | Tier 4 |  |  |  | 49078, 40850, 40855 | Y | N |  |  | 11282 | 3825
5267 | MLSE Upgrade: T152 Sim Gideon to Winchester | Upgrade terminal equipment at Sim Gideon and Winchester for a static normal and emergency rating of 193 MVA. |  | Sim Gideon | Winchester | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016216 | 2017-03-01 | 2017-03-02 | 138 | 0 | 0 | 0 |  | Bastrop | Fayette | Tier 4 |  |  |  | 7306, 7310 | Y | N |  |  | 12943 | 5267
4978 | Helena Circuit Breaker Addition | Install two 138-kV circuit breakers at Helena in a single bus-single breaker configuration. |  | Helena |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015114 | 2017-03-01 | 2017-02-17 | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  | 78584 | Y | N |  |  | 12613 | 4978
5042 | BRYN_5042_BRYN_TAMU_Enterprise | Build and Loop in New TAMU Enterprise Substation |  |  |  | Planned |  | BRYN |  |  | 2017-03-01 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32790, 32005, 32799 | Y |  |  |  | 12691 | 5042
5080 | Bronco: Build 69 kV temporary tap | Interconnect Solaire Holman solar farm at temporary tap to connect Solaire Holman to the Alpine to Fort Stockton Plant 69 kV line | IN SERVICE | Bronco |  | In-Service | 740 - 0923 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2620 | 2017-03-15 | 2017-03-15 | 69 |  |  |  |  | Brewster |  | Tier 4 |  |  |  | 6674, 6666, 38490 | Y | N |  |  | 12735 | 5080
4503 | BRYN_4503_Rayburn_Tabor_Upgrade | Reconductor Rayburn to Tabor Line with 1033 |  | 32861 | 32870 | Planned |  | BRYN |  |  | 2017-03-15 | 2017-10-01 | 69 | 0 | 4.06 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32861, 32870 | Y |  |  |  | 12075 | 4503
4754 | Walnut Springs 69 kV capacitors | Install shunt capacitors |  | Walnut Springs |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1723 | 2017-03-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Bosque |  | Tier 4 |  |  |  | 1647 | Y | N |  |  | 12349 | 4754
3353 | Aransas Pass to Rockport: Convert 69 kV line to 138 kV | Expand Aransas Pass and Rockport 138 kV stations and add 138/69 kV autotransformer capacity at Rockport |  | Aransas Pass | Rockport | In-Service | 624 - 0792 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3507 | 2017-03-31 |  | 138 | 0 | 0 | 90 |  | Medina |  | Tier 4 |  |  |  | 8427, 8430, 8432, 8434 | Y | N |  |  | 10717 | 3353
4770 | Temple Switch | Upgrade terminal equipment on the Temple Switch - Bell County 138 kV Line |  | Temple Switch |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2007 | 2017-04-01 |  | 138 | 0 | 0 | 0 |  | Bell |  | Tier 4 |  |  |  | 3415, 3425 | Y | N |  |  | 12367 | 4770
3992 | Rebuild Dickinson - League City 138 kV line. | Rebuilding Dickinson to League City 138 kV (G138-09). |  | Dickinson Sub | League City Sub | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07215 | 2017-04-05 |  | 138 | 0 | 3.6 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 38850, 38920 | Y |  |  |  | 11493 | 3992
5430C | Conversion to 138kV | Add new 138kV North Lakes substation and reconstruct 0.72miles of the existing North lakes - Denton North then connect the line to the 138kV Denton North substation and the new 138kV North Lakes substation. Additionally relocate 112MVA 138/69kV auto transformer from Denton North to North Lakes. |  | Denton North | North Lakes | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-04-18 | 2017-04-18 | 138 | 0 | 0.75 | 112 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 928, 985, 915 | Y | N | N/A |  | 13121 | 5430
4858 | Hendrick: Build 138 kV station | Interconnect Alamo 7 solar farm at Hendrick to connect Alamo 7 to the Abilene Northwest to Paint Creek 138 kV line | IN SERVICE | Hendrick |  | In-Service | 721 - 0903 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2613 | 2017-04-27 | 2017-04-27 | 138 | 0.9 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  | 60387, 6169, 6228 | Y | N |  |  | 12461 | 4858
4516 | City of Brady to North Brady: Reterminate 69 kV line | Rebuild the 69 kV line from the City of Brady Tap to North Brady double circuit to allow retermination of the City of Brady Tap line into North Brady station with the addition of a breaker | IN SERVICE | City of Brady | North Brady | In-Service | 715 - 0881 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2813 | 2017-04-27 | 2017-04-27 | 69 | 0 | 0.8 | 0 |  | McCulloch | McCulloch | Tier 4 |  |  |  | 6006, 6382, 6383 | Y | N |  |  | 12088 | 4516
5797 | MIRAGE 138 kV Sub - Gen Interconnection-17INR0022-Net Power | Construct service to new 138kV MIRAGE customer-owned substation. Loop through Ckt.96 MCCABE to BIMONT. For Generation Interconnection 17INR0022 Net Power |  | MIRAGE | MCCABE/BIMONT | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-04-30 | 2017-03-23 | 138 | 0.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40200, 40209, 40941, 42160, 42351, 40160, 111162 | Y | N |  |  | 13537 | 5797
4973 | Blewett Substation Addition | Provide transmission service for a new substation to be served off of the T570 Uvalde to Odlaw transmission line. |  | Odlaw | Asphalt Mines | Planned |  | LCRATSC/RGEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015146 | 2017-04-30 | 2017-05-05 | 138 | 0 | 0 | 0 |  | Uvalde | Uvalde | Tier 4 |  |  |  | 78424, 7425, 8246 | Y | N |  |  | 12608 | 4973
5551 | CITIES Substation Upgrades | Upgrade substation equipment at CITIES to increase thermal ratings |  | CITIES | WINFRE/JORDAN | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-04-30 | 2017-05-09 | 138 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  | 40340, 40764, 40857 | Y | N |  |  | 13279 | 5551
4776 | Lyondell Ckt.03 Distribution Tap | Add 3rd transformer at Lyondell substation. Tap from Ckt.03 BIGVUE to Channelview |  | Lyondell | BIGVUE/Channelview | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-04-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 41021, 41022, 41023, 40190, 40280, 40281, 40560, 40716, 41300, 41652 | Y | N |  |  | 12376 | 4776
5140 | Friendswood Generation (13INR0049) Transmission Network | New 138 kV, 3 breaker ring with generator lead. Ckt. 05 WAP to HOC will be relocated FEGC @ HOC bus. | - Overall Cost Update - Overall Date Update | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1140 | 2017-04-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 47156, 47170, 47171, 42041, 44081, 47150 | Y | N |  |  | 12793 | 5140
5047 | Upgrade conductor for 138 kV line from Sales to Buffalo |  |  | Buffalo | Sales Ranch | In-Service |  | SHRY | Brad Schwarz 512-289-7425 |  | 2017-05-01 |  | 138 | 0 | 6 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79508, 79549 | Y | N |  |  | 12696 | 5047
14TPIT0100 | Tilden Capacitor | Add 19.2 MVAR capacitor |  | Tilden |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-05-01 | 2017-05-31 | 138 | 0 | 0 | 0 | 0,19.2 | McMullen |  | Tier 4 |  |  |  | 5701 | Y | N |  |  | 9836 | 2555
4496 | AEP_4496_Las Pulgas | Loop STEC radial 138kV Raymondville #2 to East Raymondville line into Las Pulgas. |  | Las Pulgas |  | In-Service | 615 - 3446 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 516 | 2017-05-08 |  | 138 | 0 | 0 | 0 |  | Willacy |  | Tier 4 |  |  |  | 80309 | Y | N |  |  | 12065 | 4496
5793 | Silver Hill Substation | Add new 10MVA station near the TAMU RELLIS Campus |  |  |  | Planned |  | BRYN |  |  | 2017-05-10 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32850, 32864, 32868 | Y |  |  |  | 13532 | 5793
4523 | McKenzie Draw Switching Station | Construct new switching station |  | McKenzie Draw |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8288 | 2017-05-14 |  | 138 | 0 | 0 | 0 | 0,73.6 | Martin |  | Tier 4 |  |  |  | 11169 | Y | N |  |  | 12095 | 4523
2013 | 138kV Longneck Conversion. Rebuild Climax-Longneck (138kV) | Convert Longneck substation to 138 kV service. Rebuild 4.2 miles of 138kV transmission line (conductor 795 ACSS) from Longneck 138 kV Substation to Climax 138 kV Substation. |  | 37251 | 37260 | Under Construction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-05-15 |  | 138 | 0 | 4.2 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 37250, 37251, 37260, 37280 | Y |  |  |  | 13801 | 2013
5486 | Holliday 69 kV Capacitors | Install shunt capacitors |  | Holliday |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4013 | 2017-05-15 |  | 69 | 0 | 0 | 0 | 0,13.8 | Wichita |  | Tier 4 |  |  |  | 1527 | Y | N |  |  | 13224 | 5486
4573 | Briarcrest to Atkins Cable Upgrade | Upgrade Briarcrest to Atkins Cable to match OH capacity |  | 32864 | 32877 | Planned |  | BRYN |  |  | 2017-05-15 |  | 69 | 0.15 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32864, 32877 | Y |  |  |  | 12155 | 4573
11TPIT0012 | Euless - Grapevine Ball St - Grapevine Jnct 138 kV Line | Reconductor existing double-circuit 138 kV line (Euless - Grapevine Ball Street east circuit and Euless - Grapevine Junction west circuit) |  | Euless | Grapevine Ball Street/Grapevine Junction | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5131-E | 2017-05-15 |  | 138 | 0 | 11.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2014, 2016, 2021, 12022, 12021, 12040 | Y | N |  | Euless - Highway 360 Substation section by 5/2014 | 10287 | 2943
5309 | Mitchell Bend - DeCordova 345 kV Line | Upgrade existing line |  | Mitchell Bend | DeCordova | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1734 | 2017-05-15 |  | 345 | 0 | 6 | 0 |  | Hood |  | Tier 4 |  |  |  | 1877, 1890 | Y |  |  |  | 12985 | 5309
4765 | Leon 69 kV Sw Sta | Upgrade switching station |  | Leon Sw. |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1725 | 2017-05-15 |  | 69 | 0 | 0 | 0 |  | Eastland |  | Tier 4 |  |  |  | 1625 | Y | N |  |  | 12363 | 4765
14TPIT0012 | Mountain Creek - Norwood 138 kV line | Upgrade existing line |  | Mountain Creek | Norwood | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4074-E | 2017-05-15 |  | 138 | 0 | 7.2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2407, 2412, 2805, 12804 | Y | N |  |  | 10438 | 3094
4780 | Cedar Crest Sw. Sta. | Upgrade terminal equipment on Cedar Crest Sw.Sta. - Watermill 138 kV Line |  | Cedar Crest Sw. Sta. |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4209 | 2017-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2493, 2494, 2495 | Y | N |  |  | 12382 | 4780
4240 | McKenzie Draw - Texaco Mabee 138 kV Line | Construct new line |  | McKenzie Draw | Texaco Mabee | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8213 | 2017-05-15 |  | 138 | 10 | 0 | 0 |  | Martin | Andrews | Tier 4 | 2015-04-01 | 2015-05-22 |  | 11169, 1177 | Y | N |  |  | 11788 | 4240
5426 | Holt - North Andrews 138 kV Line (Amoco) | Upgrade the Amoco Midland Farms - XTO University line section |  | Amoco Midland Farms | XTO University | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8354 | 2017-05-15 |  | 138 | 0 | 15 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1264, 1265, 1263, 1269, 1281, 1282, 1283 | Y | N |  |  | 13111 | 5426
4220 | Screwbean 138 kV capacitors | Install shunt capacitors |  | Screwbean |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8224 | 2017-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Culberson |  | Tier 4 |  |  |  | 1090 | Y | N |  |  | 11765 | 4220
4801 | Wichita Falls Cogen - Bowman 138 kV Line | upgrade existing line |  | Wichita Falls Cogen | Bowman | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4001 | 2017-05-15 |  | 138 | 0 | 0.1 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  | 1496, 1498 | Y | N |  |  | 13259 | 4801
4979 | Upton Circuit Breaker Addition | Install two 138-kV circuit breakers at Upton in a single bus-single breaker configuration. |  | Upton |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015131 | 2017-05-19 | 2017-08-18 | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  | 71212, 1212, 71214, 71213 | Y | N |  |  | 12614 | 4979
4710A | Jones Creek Project | Build 345/138 kV Jones Creek Substation. Install first 800MVA autotransformer. | - Overall Cost Update | Jones Creek |  | In-Service | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-23 | 2017-03-23 | 345 | 0 | 0 | 800 |  | Brazoria |  | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42530, 42540, 49036 | Y | N |  |  | 12297 | 4710
4710B | Jones Creek Project | Install second 800MVA autotransformer at Jones Creek substation. |  | Jones Creek |  | In-Service | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-24 | 2017-05-04 | 345 | 0 | 0 | 800 |  | Brazoria |  | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 49037, 42530, 42540 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 12298 | 4710
4710C | Jones Creek Project | Loop 345kV Ckt.18 into Jones Creek Substation |  | Jones Creek | DOW/STP | In-Service | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-25 | 2017-03-23 | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 5915, 42500, 42530 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 12299 | 4710
14TPIT0067 | Red Creek: Replace one of the 345/138 kV autotransformers | Replace both 345/138 kV autotransformers at Red Creek with 480 MVA autotransformers |  | Red Creek |  | Under Construction | 566 - 0740 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2570 | 2017-05-25 | 2017-05-25 | 345 | 0 | 0 | 480 |  | Tom Green |  | Tier 4 |  |  |  | 6295, 6444, 6442 | Y | N |  |  | 11360 | 1824
4710D | Jones Creek Project | Loop 138kV circuits 02, 48, and 59 into Jones Creek Substation |  | Jones Creek | Velasco/Freeport | In-Service | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-26 | 2017-03-23 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42540, 42645, 43360 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 12300 | 4710
4710E | Jones Creek Project | Reconfigure Freeport area circuits to create a loop with Ckt.59 from Velasco to Surfside to Freeport to Jones Creek and Ckt.02 Jones Creek to Velasco. |  | Velasco | Surfside/Freeport/Jones Creek/Velasco | In-Service | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-27 | 2017-03-23 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42645, 43155, 43315, 43360 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 12301 | 4710
4710F | Jones Creek Project | Reconfigure Freeport area circuits to create a Ckt.48 circuit from Velasco to MARINE to CORTEZ to Quintana to Jones Creek. |  | Jones Creek | MARINE/CORTEZ/Quintana/Jones Creek | In-Service | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-28 | 2017-03-23 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42540, 42645, 43155, 43435, 43315, 43360 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 12302 | 4710
3682A | Katy Area Upgrades | Convert Franz Substation to loop service from 138kV Ckt.09. Install new conductor and reconfigure/upgrade existing lines to create new Ckt.09 Zenith to Franz to Katy to Flewellen. | - Overall Cost Update | Zenith | Katy | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 860 | 2017-05-29 | 2017-07-28 | 138 | 6.4 | 1.6 | 0 |  | Harris | Waller | Tier 2 | 2013-12-18 | 2014-05-15 |  | 44260, 44261, 44262, 44230, 44256, 44422, 44500, 45675, 44420, 44421, 44900, 44910, 45770, 46220 | Y | N |  |  | 11096 | 3682
4710H | Jones Creek Project | De-energize a portion of existing Ckt.02 Velasco to Franklins Camp and reconfigure create new Ckt.02 Jones Creek to Franklins Camp. |  | Jones Creek | Franklins Camp | In-Service | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-30 | 2017-03-23 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 43211, 43212, 43220, 43221, 43222, 48006, 42195, 42215, 42540, 43360 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 12304 | 4710
4707 | Velasco Cap Bank #1 | Install capacitor bank #1 at Velasco substation (120MVAR). |  | Velasco |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-30 | 2017-07-21 | 138 | 0 | 0 | 0 | 0,120 | Brazoria |  | Tier 4 |  |  |  | 43361, 43360, 42190 | Y | N |  |  | 12294 | 4707
4458 | Altair to Glidden Transmission Line Overhaul | Overhaul Altair (78106) - Stafford Hill (78520) - Columbus (78111) - Glidden (78107) transmission line with 138-kV capable structures and replace conductor with 795 ACSR Drake New circuit rating (MVA): Rate A= 46, Rate B=46, Rate C=119 |  | Altair | Glidden | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1011917 | 2017-05-30 | 2017-06-30 | 69 | 0 | 12.2 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  | 78106, 78107, 78111, 78520 | Y | N |  |  | 12018 | 4458
3682B | Katy Area Upgrades | Convert Katy substation ckt 09 tap to loop service to modify Ckt.09 Flewellen to Katy to Franz. |  | Katy |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 860 | 2017-05-30 | 2017-07-28 | 138 | 0 | 0 | 0 |  | Waller |  | Tier 2 | 2013-12-18 | 2014-05-15 |  | 44420, 44421, 44422, 44230, 45770 | Y | N |  | Cost included in project 17TPIT3682A. | 11097 | 3682
14TPIT0061 | Briarcrest to Atkins Upgrade | Upgrade to 795 ACSR to alleviate overload during double contingency situations. Add OPGW. Add new poles/structures. |  | Atkins | Briarcrest | Planned |  | BRYN |  |  | 2017-05-31 |  | 138 | 0 | 3.4 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32864, 32877 | Y |  |  |  | 9227 | 2001
5714 | WAP-Bellaire Ckt50 Substation Equip Upgrade | Upgrade substation equipment at Bellaire and WA Parish to increase Ckt.50 thermal ratings |  | Bellaire | WA Parish | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-05-31 | 2017-02-09 | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44005, 47000 | Y | N |  |  | 13453 | 5714
3761 | Victoria to Fannin: 69 kV Transmission Line Rebuild | Rebuild Victoria to Fannin 69 kV line | Add Super project, and transmission status, ISD | VICTORIA | FANNIN | In-Service | 662-0831 | AEP TCC | William Clarke dnlyons@aep.com 918-599-2698 | 3527 | 2017-05-31 |  | 69 |  | 13.5 |  |  | Victoria | Victoria | Tier 4 |  |  |  | 5736, 8169 | Y | N |  |  | 11181 | 3761
15TPIT0057 | Wylie 138 kV new switchyard and connections | Wylie 138 kV switchyard and its connections to Olinger, to Firewheel, to Elm Grove, and to Nevada | On Hold For Funding | New switches at Wylie | Switches at Olinger, at Friewheel, at Elm Grove, and at Nevada | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2017-05-31 |  | 138 | 0 | 36.75 | 0 |  | Collin | Dallas | Tier 4 |  |  |  | 833, 811, 818, 821, 855 | Y | N |  |  | 9925 | 2629
6088 | CAPITOL Substation Removal | Remove 138kV CAPITOL substation from CNP transmission service. Remove Ckt.35 CAPITOL to CELNEC from CNP transmission service. Reconnect circuits to create new Ckt.94 HIMONT to BAYWAY. |  | CAPITOL | HIMONT/BAYWAY | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-05-31 | 2017-05-23 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 42230, 42260, 42170, 42790 | Y | N |  |  | 13813 | 6088
5266 | Cuero - Luling Transmission Line Overhaul | Rebuild T542 Luling to Hocheim Tap from Luling to vicinity of Harwood to be 138-kV capable with a nominal conductor rating of 223 MVA at 138-kV (Single Drake) with OPGW and operated at 69-kV. |  | Hocheim | Luling | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016221 | 2017-05-31 | 2017-06-02 | 69 | 0 | 10 | 0 |  | DeWitt | Gonzales | Tier 4 |  |  |  | 7223, 78577 | Y | N |  |  | 12942 | 5266
5055 | Maxwell Tap: Build new 138 kV temporary tap | Interconnect Val Verde Wind Farm temporarily at Maxwell Tap via Fermi Collector station |  | Maxwell Tap |  | In-Service | 735-0917 | AEP TCC | Wilburt Robert dnlyons@aep.com 918-599-2698 | 3567 | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  | 88998, 8257, 8261 | Y | N |  |  | 12705 | 5055
4446 | Luling to Nixon Transmission Line Overhaul | Upgrade the 15.62 mile Luling (7223) - Malone - Darst Creek - Deer Creek (7597) 69kV transmission line to 795 ACSR Drake, 138kV capable with OPGW shield wire. The updated rating will be 44 MVA at 69kV. |  | Luling | Deer Creek | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1012406 | 2017-05-31 | 2017-06-20 | 69 | 0 | 15.62 | 0 |  | Caldwell | Guadalupe | Tier 4 | 2015-02-18 | 2015-03-23 |  | 7223, 7597, 78195, 78579 | Y | N |  |  | 12009 | 4446
3682C | Katy Area Upgrades | Install a second 800MVA autotransformer at Zenith Substation. |  | Zenith |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 860 | 2017-05-31 | 2017-05-04 | 345 | 0 | 0 | 800 |  | Harris |  | Tier 2 | 2013-12-18 | 2014-05-15 |  | 49090, 44230, 44256, 44422, 44500, 45675, 44900, 45770, 46220, 44910 | Y | N |  | Cost included in project 17TPIT3682A. | 11098 | 3682
5284 | Tahitian Village Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Tahitian Village Substation. |  | Tahitian Village |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016212 | 2017-05-31 | 2017-06-16 | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  | 7575 | Y | N |  |  | 12960 | 5284
5283 | Starcke Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Starcke. |  | Starcke |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016206 | 2017-05-31 | 2017-06-26 | 138 | 0 | 0 | 0 |  | Burnet |  | Tier 4 |  |  |  | 7351 | Y | N |  |  | 12959 | 5283
4708 | Meadow: Install 600MVA Autotransformer A2 | Install 600MVA autotransformer A2 at Meadow (from PH Robinson substation) | Delay in Project Schedule | Meadow |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1116 | 2017-05-31 | 2017-04-10 | 345 | 0 | 0 | 600 |  | Brazoria |  | Tier 4 |  |  |  | 43031, 43032, 49051, 39015, 43030 | Y | N |  |  | 12295 | 4708
4145 | Ckt.38 Galena Park to Greens Bayou De-Energization | De-energize Ckt.38 Galena Park to Greens Bayou. Reconfigure GYPSUM tap to be served radially out of Greens Bayou on Ckt.38. |  | Galena Park | Greens Bayou | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1128 | 2017-05-31 | 2017-06-29 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40619, 40751, 40100, 40190, 40280, 40281, 40330, 40352, 40370, 40470, 40555, 40580, 40590, 40610, 40611, 40700, 40710, 40715, 40716, 40725, 40780, 40841, 40990, 41000, 41009, 41191, 41260, 41530, 41670, 41675, 47630, 48102, 48130, 48210, 48211, 48230, 48231, 48260, 48261, 48264, 48299, 48372, 48384, 48385, 48402, 48412, 40270, 40420, 40450, 40460, 40630, 40717, 40720, 41080, 41250, 41300, 41430, 41681, 46610 | Y | N |  |  | 11665 | 4145
4995 | Sandy Point 138kV Distribution Substation | Build new 138kV Sandy Point distribution substation. Loop through Ckt.96 ALKANE to LaPorte. | - Overall Cost Update | Sandy Point | ALKANE/LaPorte | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 954 | 2017-05-31 | 2017-05-19 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40090, 40160, 40941 | Y |  |  |  | 12628 | 4995
3903 | Lobo 345 kV Station: Add 345/138 kV Auto | Add 2nd 345/138 kV Autotransformer at Lobo Switching Station |  | Lobo |  | In-Service | 663 - 0832 | ETT | Terri Weeks dnlyons@aep.com 918-599-2698 | 3538 | 2017-05-31 |  | 345 | 0 | 0 | 675 |  | Webb |  | Tier 4 |  |  |  | 80219, 80221 | Y | N |  |  | 11374 | 3903
5553A | Village Creek 138kV Substation | Install temporary service for Village Creek (Mobile) 138kV substation. Tap from Ckt.09 Zenith to Franz. |  | Village Creek (Mobile) | Zenith/Franz | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-05-31 | 2017-07-28 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44271, 44230, 44256, 44260, 44420, 44422, 44900, 45770, 44500, 44910, 45675, 46220 | Y | N |  |  | 13649 | 5553
3681 | TH Wharton to Addicks Ckt.71 Sub Upgrade | Upgrade substation equipment at TH Wharton and Addicks to increase thermal ratings for 345kV Ckt.71. | Delay in Project Schedule | TH Wharton | Addicks | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1111 | 2017-05-31 | 2016-12-22 | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45500, 45600 | Y | N |  |  | 11443 | 3681
4950A | Oyster Creek 138kV Substation - GINR - 16INR0003 | Loop new 138kV Oyster Creek substation from Ckt.82 Velasco to BIPORT. Install 40MVAR cap bank at Oyster Creek. | - Overall Cost Update - Overall Date Update - Updated for cap bank | Oyster Creek | Velasco/BIPORT | Planned | 4710 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 932 | 2017-05-31 00:01 |  | 138 | 0 | 0 | 0 | 0,40 | Brazoria |  | Tier 4 |  |  |  | 43335, 43336, 42190, 43360, 43361 | Y | N |  |  | 12583 | 4950
16TPIT0009 | Five Points to Westside - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from Five Points to Westside to be upgraded to 326 MVA, minimum |  | Five Points | Westside | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0195 | 2017-06-01 |  | 138 | 0 | 3.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5150, 5490 | Y | N |  | There are no transformers associated with this project | 8149 | 973
5031 | Install 30 MVar Cap Bank at Barilla Draw Tap | Changed Capbank from 80 to 30 MVAR. TNMP is planning to pursue additional 50-60 MVAR capacitive reactance via SVC when Transient Switching study completed. |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-06-01 |  | 138 | 0 | 0 | 0 | 0,30 |  |  | Tier 4 |  |  |  | 38065 | Y |  |  |  | 12676 | 5031
09TPIT0037 | Blossom - New 138 kV Substation | Loop new 138 kV substation into the existing 138kV Harmony Hills to Skyline line | Delayed due to budget constraint | Blossom | Harmony Hills-Skyline | Planned | T-0178 | CPS | Ulrich Skerhut UKSkerhut@cpsenergy.com 210-353-2923 | S-0602 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5022, 5195, 5368 | Y | N |  | There are no transformers associated with this project | 8125 | 949
16TPIT0010 | Bulverde - New 138kV Substation | Loop new 138kV substation into the existing Green Mountain to Stonegate transmission line |  | Green Mountain | Stonegate | Planned | T-0189 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0665 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5051, 5180, 5415 | Y | N |  | There are no transformers associated with this project | 8147 | 971
14TPIT0041 | Coliseum_to_Holbrook_Rebuild_&_Reconfiguration | Rebuild 2.8 miles of 138 kV transmission line from Coliseum to Holbrook and ensure a minimum conductor rating of 331 MVA |  | Colesium | Holbrook | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0164 | 2017-06-01 |  | 138 | 0 | 2.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5095, 5160, 5218, 5250, 5420 | Y | N |  | There are no transformers associated with this project | 8131 | 955
5683B | Line H Rebuild and 138kV conversion. | Convert Collie Field facilities to 138 kV. Rebuild line from IH20-Collie Tap (38045-38037). De-energize 69 kV line Collie Field Tap-Birds of Prey (38030-38041). Remove temporary 10 MVAR capbank from Collie Field Tap. |  | 38037 | 38045 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-06-22 |  | 138 | 0 | 2.95 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38027, 38028, 38029, 38030, 38031, 38032, 38037, 38038, 38039, 38041, 38042, 38033, 38040 | Y |  |  |  | 13744 | 5683
5280 | Georgetown South Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Georgetown South. |  | Georgetown South |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016215 | 2017-06-30 | 2017-06-19 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  | 7532 | Y | N |  |  | 12956 | 5280
4492 | Marconi: Build new three breaker 138 kV station | Interconnect San Roman Windfarm at Marconi to connect San Roman to the Port Isabel to Laureles 138 kV line by building new 138 kV line from Marconi to San Roman |  | Marconi | San Roman | Under Construction | 712 - 0883 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 2906 | 2017-06-30 |  | 138 | 0.6 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8262, 8266, 5756, 8338, 161601 | Y | N |  |  | 12061 | 4492
5279 | Chappell Hill Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Chappell Hill. |  | Chappel Hill |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016181 | 2017-06-30 | 2017-07-28 | 138 | 0 | 0 | 0 |  | Washington |  | Tier 4 |  |  |  | 7574 | Y | N |  |  | 12955 | 5279
16TPIT0032 | Esmeralda to Yucca: Build 138 kV line | Construct new Esmeralda station along Big Lake to Friend Ranch 138 kV line and build new 138 kV line from Esmeralda to Yucca | Schedule Update | Esmeralda | Yucca | Under Construction | 585 - 0745 | AEP TNC | David Baker mlforcum@aep.com 918-599-2674 | 2577 | 2017-06-30 |  | 138 | 13 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6034, 6035, 6036, 6531, 6525 | Y | N |  |  | 9936 | 2637
3507 | Nopal Substation | Build a new 138-26.18 kV 18/24/30 MVA substation to be served by Gillett to Nopal 138 kV transmission line |  | Nopal |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7233 | Y | N |  |  | 10889 | 3507
5269 | MLSE Upgrade: T147 Gilleland Creek to McNeil | Upgrade terminal equipment at Gilleland Creek and McNeil for a static normal and emergency rating of 493 MVA. |  | Gilleland Creek | McNeil | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016216 | 2017-06-30 | 2017-05-30 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 7334, 7336 | Y | N |  |  | 12945 | 5269
5282 | Shadow Glen Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Shadow Glen. |  | Shadow Glen |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016205 | 2017-06-30 | 2017-08-11 | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7323 | Y | N |  |  | 12958 | 5282
6076 | Joslin: Add 138 kV breaker terminal for WF interconnect | Interconnect Point Comfor Gas Turbine at Joslin and construct a 138 kV breaker terminal |  | Joslin |  | In-Service | 862-1040 | AEP TCC | Wilbur Robert dnlyons@aep.com 918-599-2664 | 2698 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | Y | N |  |  | 13799 | 6076
16TPIT0031 | Esmeralda: Build 138 kV station | Construct new Esmeralda station along the Big Lake to Friend Ranch 138 kV line and build a new 138 kV line from Esmeralda to Yucca | Schedule Update | Esmeralda |  | Under Construction | 585 - 0738 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2576 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6525, 6562, 60375 | Y | N |  |  | 11821 | 3241
3636 | Welsh HVDC: Upgrade Station Svc and Install New Filter | Welsh HVDC Tie: Phase 2 Station Upgrades | PM, PVID, Prj Desc, In-Service Changes | WELSH HVDC Tie |  | Under Construction | 625 - 0793 | AEP TCC | Tommy Vannoy dnlyons@aep.com 918-599-2698 | 3568 | 2017-06-30 |  | 345 | 0 | 0 | 0 | 100100 | Titus |  | Tier 4 |  |  |  | 5925 | Y | Y |  |  | 11041 | 3636
3509 | Gillett Sub (LCRA) to Nopal Sub 138 kV Transmission Line | Add 138 Terminal at LCRA Gillett Station; Build approx 9 miles of single ckt 138 kV t-line, 795 ACSR |  | Gillett | Nopal | Planned | 15TPIT0063 | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-06-30 |  | 138 | 8.5 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  | 7233, 78582 | Y | N |  |  | 10891 | 3509
5268 | MLSE Upgrade: T231 Austrop to Bastrop City | Upgrade terminal equipment at Austrop and Bastrop City for a static normal and emergency rating of 221 MVA. |  | Austrop | Bastrop City | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016216 | 2017-06-30 | 2017-05-30 | 138 | 0 | 0 | 0 |  | Travis | Bastrop | Tier 4 |  |  |  | 7322, 7329, 9328 | Y | N |  |  | 12944 | 5268
5231 | Schneeman Draw Substation Addition | Provide transmission service for a generator off T21421 345-kV STEC line between Big Hill and Bakersfield Substations. |  | Big Hill | Bakersfield | Planned |  | LCRATSC/STEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015885 | 2017-07-01 | 2017-08-11 | 345 | 0 | 0 | 0 |  | Schleicher | Pecos | Tier 4 |  |  |  | 76005, 76002, 76003 | Y | N |  |  | 12904 | 5231
10TPIT0148 | Las Pulgas Tap - Renamed from Willacy Tap Switch 138kV | Move normally open 138 kV connection to the Raymondville Tap line switch and add a postion at Las Pulgas. E Raymondville will be radial from Las Pulgas and La Sara will be radial from Raymondville #2. |  | Las Pulgas |  | Planned | 12TPIT0103 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-07-01 | 2017-07-15 | 138 | 0 | 0 | 0 |  | Willacy | Willacy | Tier 4 |  |  |  | 5745, 5790, 80309 | Y | N |  |  | 9582 | 2330
3911 | Hecker 138kV Substation Expansion: Cheniere LNG Project | Hecker 138kV Substation Expansion: Cheniere LNG Project |  | Hecker |  | In-Service | 616 - 0784 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3534 | 2017-07-14 | 2017-01-02 | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8568, 8565, 8961, 80470 | Y | N |  |  | 11384 | 3911
15TPIT0085 | Eagle Mountain - Wagley Robertson - Saginaw 138 kV Line | Upgrade the existing Eagle Mountain - Wagley Robertson line section |  | Eagle Mountain | Wagley Robertson | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5200-E | 2017-07-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 11862, 1860, 2075, 2076, 2082, 11860, 12065 | Y | N |  |  | 10557 | 3209
4873 | Smoky Hill: Build 345 kV station | Interconnect Horse Creek wind farm at Smoky Hill to connect Horse Creek to the Clear Crossing to Edith Clarke 345 kV line | Schedule Update | Smoky Hill |  | Under Construction | 726 - 0908 | ETT | Mark Strabala mlforcum@aep.com 918-599-2674 | 2909 | 2017-07-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  | 6104, 60515, 60701 | Y | N |  |  | 13812 | 4873
5550 | Jeanetta to WA Parish Ckt.64 & 72 Upgrades | Upgrade substation equipment at Jeanetta to WA Parish Ckt.64 and upgrade Ckts. 64 & 72 to increase thermal ratings |  | Jeanetta | WA Parish | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-07-31 | 2017-07-27 | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 43035, 44000, 44005, 44010, 44020, 44081, 44082, 44120, 44170, 44171, 44180, 44280, 44311, 44342, 44481, 44482, 44551, 44650, 44672, 44760, 44762, 47010, 47012, 47072, 47191, 44172, 44310, 44312, 44341, 44490, 44500, 44570, 44651, 44652, 44671, 44761, 47000, 47150, 47300, 47310, 47442 | Y | N |  |  | 13278 | 5550
4967 | Nelson Sharpe: Add 138 kV term. for generator interconnect | Interconnect Chapman Ranch Windfarm at Nelson Sharpe and construct 138 kV line from Nelson Sharpe to Santa Cruz |  | Nelson Sharpe | Santa Cruz | In-Service | 732 - 0914 | ETT | Dave Goetz dnlyons@aep.com 918-599-2698 | 3563 | 2017-08-01 | 2017-06-30 | 138 | 6 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 80503, 85001 | Y |  |  |  | 12602 | 4967
5929 | Moulton South Circuit Breaker Addition | Add circuit breakers in a breaker and a half arrangement at Moulton South Substation. |  | Moulton South |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016540 | 2017-08-02 | 2017-08-02 | 138 | 0 | 0 | 0 |  | Lavaca |  | Tier 4 |  |  |  | 7237 | Y | N |  |  | 13637 | 5929
5410 | Sierra Vista: Add 2nd Dist Bank | Add 2nd distribution bank and string circuit between Sierra Vista and Sierra Vista Tap |  | Sierra Vista | Sierra Vista Tap | In-Service | 785 - 0970 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 3578 | 2017-08-03 | 2017-07-18 | 138 | 1.75 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 8922, 88641, 8295, 8641, 80230 | Y | N |  |  | 13097 | 5410
4239 | McKenzie Draw - North Andrews/Lamesa 138 kV Line | Rebuild existing tap line as a double-circuit line |  | McKenzie Draw | Paul Davis Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8220 | 2017-08-15 |  | 138 | 12 | 12 | 0 |  | Dawson | Martin | Tier 4 |  |  |  | 1170, 1168, 1169, 11169, 18880 | Y | N |  |  | 11787 | 4239
5076 | Smoky Hill: Build 345 kV terminal | Interconnect Willow Springs wind farm at Smoky Hill to connect Willow Springs to the Clear Crossing to Edith Clarke 345 kV line | IN SERVICE | Smoky Hill |  | In-Service | 734 - 0916 | ETT | Mark Strabala mlforcum@aep.com 918-599-2674 | 2614 | 2017-08-30 | 2017-08-30 | 345 |  |  |  |  | Haskell |  | Tier 4 |  |  |  | 6104 | Y | N |  |  | 12731 | 5076
15TPIT0055 | Naval Base Station: Add 138/69 kV Auto | Construct new 138 kV line and add tranformation at Naval Base to remove contingency overloads during off-peak maintenance |  | NAVAL BASE |  | In-Service | 607 - 0648 | AEP TCC | Terry Weeks DNLYONS@AEP.COM 918-599-2698 | 3485 | 2017-08-31 | 2017-09-11 | 138 |  |  | 220 |  | Nueces |  | Tier 1 | 2012-07-15 | 2012-12-20 | 2013-01-04 | 8997, 8495 | Y | N |  |  | 10896 | 3514
3848 | Derrick to Powell Field: Rebuild 69 kV line | Rebuild Derrick to Powell Field 69 kV line | Schedule Update | Derrick | Powell Field | Under Construction | 670 - 0839 | AEP TNC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | 2806 | 2017-08-31 |  | 69 | 0 | 6.8 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  | 6540, 60396, 6539, 6544, 6545 | Y | N |  |  | 12813 | 3848
5999 | La Pryor: Rebuild Distribution Station | Rebuild La Pryor Distribution Station |  | Turtle Creek | Uvalde | In-Service | 813 - 0997 | AEP TCC | Aaron Schwerman dnlyons@aep.com 918-599-2698 | 3603 | 2017-08-31 | 2017-07-12 | 69 | 0 | 0 | 0 |  | Zavala |  | Tier 4 |  |  |  | 88672, 8231, 8243, 8672 | Y | N |  |  | 13716 | 5999
15TPIT0054 | Barney Davis To Naval Base Construct 138 kV line | Construct new 138 kV line and add tranformation at Naval Base to remove contingency overloads during off-peak maintenance |  | BARNEY DAVIS | NAVAL BASE | In-Service | 607 - 0648 | ETT | JOHN PULAY DNLYONS@AEP.COM 918-599-2698 | 3484 | 2017-08-31 | 2017-09-11 | 138 | 7 |  |  |  | Nueces | Nueces | Tier 1 | 2013-07-15 | 2013-12-20 | 2013-01-24 | 8458, 8997 | Y | N |  |  | 10901 | 3519
5229 | Bow Wood Substation Addition | Provide transmission service for a generator off T424 345-kV line between Red Creek and Brown Switch Substations. |  | Bow Wood |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015831 | 2017-09-01 | 2017-06-20 | 345 | 0 | 0 | 0 |  | McCulloch |  | Tier 4 |  |  |  | 76006, 1444, 6444 | Y | N |  |  | 12902 | 5229
6045 | Mainland Substation | Updated Associated TPIT project TNMP_15TPIT0030_Mainland_NewSubstation (Project ID# 2025). |  | Mainland |  | Under Construction | 2025 | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-09-01 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38830, 38820, 39030 | Y | N |  |  | 13764 | 6045
5081 | Bronco: Build 69 kV station | Interconnect Solaire Holman solar farm at Bronco to connect Solaire Holman to the Alpine to Fort Stockton Plant 69 kV line | IN SERVICE | Bronco |  | In-Service | 740 - 0923 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2621 | 2017-09-25 | 2017-09-25 | 69 |  |  |  |  | Brewster |  | Tier 4 |  |  |  | 6674 | Y | N |  |  | 12736 | 5081
5177 | Tesla: Add 345 kV reactor | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley | IN SERVICE | Tesla |  | In-Service | 754 - 0937 | ETT | Steve Stein mlforcum@aep.com 918-599-2674 | 2624 | 2017-09-28 | 2017-09-28 | 345 | 0 | 0 | 0 | -100,0 | Wilbarger |  | Tier 4 |  |  |  | 60501 | Y | N |  |  | 12836 | 5177
5270A | Twin Buttes Autotransformer Addition | Install a new 345-kV 50 MVAR reactor at Divide Substation. Total project cost shown in 5270B. | Changed to phased project to show in-service date for major equipment associated with project. | Divide |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016445 | 2017-09-30 | 2017-10-17 | 345 | 0 | 0 | 0 | 50,0 | Coke |  | Tier 4 |  |  |  | 76090 | Y | N |  |  | 14272 | 5270
5030D | Flat Top Tie with AEP Pig Creek | Install IH20 138/69 kV Auto. |  | 38040 | 38045 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-10-01 |  | 138 | 0 | 0 | 150 |  | Reeves | Reeves | Tier 3 | 2015-01-13 | 2015-06-19 |  | 38040, 38045 | Y |  |  |  | 13712 | 5030
5232 | Castillo Substation Addition | Provide transmission service for a generator off T4521 138-kV line between North McCamey and LCRA Crane Substations. |  | North McCamey | LCRA Crane | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016047 | 2017-10-01 | 2017-08-28 | 138 | 1.64 | 0 | 0 |  | Upton | Crane | Tier 4 |  |  |  | 76040, 76032, 76615 | Y | N |  |  | 12905 | 5232
5030C | Flat Top Tie with AEP Pig Creek | Construct IH20 138 kV station. Rebuild line from Barilla Draw Tap-IH20 138 kV bus with 1926 ACSR/TW Cumberland. |  | 38040 | 38060 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-10-01 |  | 138 | 0 | 11.57 | 0 |  | Reeves | Reeves | Tier 3 | 2015-01-13 | 2015-06-19 |  | 38045, 38040, 38060 | Y |  |  | Conductor changed from RPG submittal from 795 ACSR to 1926 ACSR/TW Cumberland. | 12675 | 5030
5947 | Radial Autotransformer Redundancy Substation Upgrade | Install a second 138/69-kV autotransformer at Mason CTEC. | Construction Schedule | Mason (CTEC) |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016201 | 2017-10-01 | 2018-10-27 | 69 | 0 | 0 | 44.8 |  | Mason |  | Tier 4 |  |  |  | 7395, 76389 | Y | N |  |  | 13658 | 5947
4456 | Gilleland Creek Autotransformer | Install a new 345/138 kV 672 MVA auto transformer at Gilleland Creek substation. |  | Gilleland Creek |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015112 | 2017-10-06 | 2017-10-06 | 345 | 0 | 0 | 672 |  | Travis |  | Tier 4 |  |  |  | 77341, 7340, 7336 | Y | N |  |  | 12016 | 4456
5683C | Line H Rebuild and 138kV conversion. | Convert Birds of Prey facilities to 138 kV. Rebuild line from Collie Field Tap-Birds of Prey (38027-38037). De-energize 69 kV line Birds of Prey Tap-Quito Draw Tap (38030-38033). |  | 38027 | 38037 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-10-15 |  | 138 | 0 | 2.25 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38027, 38028, 38029, 38037, 38038, 38039, 38033, 38040, 38045 | Y |  |  |  | 13745 | 5683
6375 | Tennyson: Build 138 kV temporary tap | Construct new 138 kV box bay on the Red Creek to Nicole 138 kV line | IN SERVICE | Tennyson |  | In-Service | 871 - 1047 | AEP TNC | Bill Roberts mlforcum@aep.com 918-599-2674 | 2724 | 2017-10-15 | 2017-10-15 | 138 | 0 | 0 | 0 |  | Coke |  | Tier 4 |  |  |  | 60417, 6351, 6441 | Y | N |  |  | 14119 | 6375
5019 | Pig Creek: Build 138 kV station | Construct new 138 kV ring bus on the Barrilla Junction to Permian Basin Line | IN SERVICE | Pig Creek |  | In-Service | 737 - 0920 | AEP TNC | David Baker mlforcum@aep.com 918-599-2674 | 2618 | 2017-10-20 | 2017-10-20 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6673, 38069, 60385, 60393 | Y | N |  |  | 12652 | 5019
6093 | CHAMON 138 kV Sub - Gen Interconnection-17INR0042 Castleman | Install two new generator leads for new Castleman Power generator interconnection. Connect to existing CHAMON 138kV customer-owned substation. Expand CHAMON substation to 4-breaker ring bus. |  | Castleman Power | CHAMON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41050, 41300 | Y | N |  |  | 13818 | 6093
5233 | Lincoln Substation Addition | Construct a load serving substation (ring bus) at Lincoln. The station will be built off between Giddings and Lexington off T255. | Construction Schedule | Giddings | Lexington | Planned |  | LCRATSC/BBEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015961 | 2017-10-31 | 2018-10-23 | 138 | 0 | 0 | 0 |  | Lee | Lee | Tier 4 |  |  |  | 7568, 7302, 7571 | Y | N |  |  | 12906 | 5233
5281 | Mason (CTEC) Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Mason (CTEC). | Construction Schedule | Mason (CTEC) |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016196 | 2017-10-31 | 2018-10-24 | 138 | 0 | 0 | 0 |  | Mason |  | Tier 4 |  |  |  | 7395 | Y | N |  |  | 12957 | 5281
4459 | Goldthwaite to Lampasas Transmission Line Upgrade | Convert the 18.2 mile Goldthwaite (7073) - San Saba (7078) 69-kV to 795 ACSR Drake 138-kV (223 MVA) and Convert the 33.3 mile San Saba (7078) - Lometa (7080) - Lampasas (7082) 69-kV to 795 ACSR Drake 138-kV (223 MVA). |  | Goldthwaite | Lampasas | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014204 | 2017-11-01 | 2017-10-31 | 138 | 0 | 51.5 | 0 |  | Mills | Lampasas | Tier 4 | 2014-11-11 | 2015-06-25 |  | 7064, 7070 | Y | N |  |  | 12019 | 4459
6534 | Pipeline Substation Addition | Add new load serving substation on the Seward Junction to Andice (T396) 138kV transmission line. |  | Seward Junction | Andice | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2017-11-01 |  | 138 | 0.25 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 7390, 7522, 7524 | Y | N |  |  | 14274 | 6534
5409 | Jayton to Clairmont Tap: Rehab 69 kV line | Rehab Jayton to Clairmont Tap 69 kV line | IN SERVICE | Jayton | Clairmont Tap | In-Service | 786 - 0971 | AEP TNC | Jake Tucker mlforcum@aep.com 918-599-2674 | 2646 | 2017-11-02 | 2017-11-02 | 69 | 0 | 10.55 | 0 |  | Kent | Kent | Tier 4 |  |  |  | 6153, 6197 | Y | N |  |  | 13096 | 5409
4493 | Pharr 138 kV Loop | McColl Road & North McAllen to Pharr: Reroute 138 kV Line |  | MCCOLL ROAD & NORTH MCALLEN | PHARR | In-Service | 704-0874 | AEP TCC | William Clarke dnlyons@aep.com 918-599-2698 | 3548 | 2017-11-03 |  | 138 | 2.2 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8368, 8372, 8908 | Y | N |  |  | 12727 | 4493
5683D | Line H Rebuild and 138kV conversion. | Convert Worsham and Quito Draw facilities to 138 kV. Rebuild line from Worsham-Birds of Prey Tap (38021-38027). De-energize 69 kV line Pyote-Worsham (38000-38020). |  | 38021 | 38027 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-11-15 |  | 138 | 0 | 5.84 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38020, 38021, 38022, 38033, 38034, 38035, 38000, 38027 | Y |  |  |  | 13746 | 5683
4200 | Sage: Build 69 kV station | Construct new 69 kV in and out substation off the Crane loop, and demolish Crane Gulf #1 | IN SERVICE | Sage |  | In-Service | 697 - 0867 | AEP TNC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | 2266 | 2017-11-15 | 2017-11-15 | 69 | 0 | 0 | 0 |  | Crane |  | Tier 4 |  |  |  | 6604, 6608 | Y | N |  |  | 11731 | 4200
5178 | Edith Clarke: Add 345 kV reactor | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley | IN SERVICE | Edith Clarke |  | In-Service | 754 - 0937 | ETT | Steve Stein mlforcum@aep.com 918-599-2674 | 2625 | 2017-11-30 |  | 345 | 0 | 0 | 0 | -100,0 | Foard |  | Tier 4 |  |  |  | 60500 | Y | N |  |  | 12837 | 5178
4706A | HO Clarke to Webster Ckt.05 | Upgrade HO Clarke to Southwyck Ckt.05 to increase thermal ratings |  | HO Clark | Southwyck | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2017-11-30 | 2018-01-11 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42000, 42015, 42041, 42042, 42061, 42581, 42651, 42652, 42800, 43082, 43260, 44010, 44082, 44180, 44361, 44362, 44551, 42681, 42860, 42960, 43030, 43500, 43505, 44490, 44552, 44651, 47150 | Y | N |  | 0 | 43253 | 4706
4606 | Moulton South 138/69-kV Autotransformer Addition | Add Moulton South Substation 138/69-kV Autotransformer | New autotransformer failed test. | Moulton South |  | Planned | 5929 | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-11-30 | 2018-02-23 | 138 | 0 | 0 | 45 |  | Lavaca |  | Tier 4 |  |  |  | 7587, 77587, 7588, 7590, 7237 | Y | N |  |  | 13424 | 4606
4970 | Magic Valley Tap: Build new 345 kV temporary tap | Interconnect Magic Valley II Windfarm at temporary tap to connect Magic Valley II to the Ajo to Rio Hondo 345 kV line |  | Ajo | Rio Hondo | Under Construction | 731 - 0912 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3561 | 2017-11-30 | 2017-10-20 | 345 | 0 | 0 | 0 |  | Willacy |  | Tier 4 |  |  |  | 80512, 8902, 80076 | Y |  |  |  | 12605 | 4970
4546 | Upgrade 138kV Vealmoor - Salt Mine line |  |  | Vealmoor | Salt Mine | Planned |  | CTT | Brad Schwarz 512-289-7425 |  | 2017-12-01 |  | 138 | 0 | 54.5 | 0 |  | Borden | Mitchell | Tier 4 |  |  |  | 79559, 79603, 79604, 79600, 79605 | Y | N |  |  | 12123 | 4546
3963 | Lockhart to Luling Transmission Line Upgrade | Upgrade the 16.9 miles Lockhart to Luling City 138kV line from existing 136 MVA to 221 MVA. Replace existing 45 MVA auto with 70 MVA auto. Upgrade both Lockhart and Luling to breaker and a half configuration. | Construction Schedule | Lockhart | Luling | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014350 | 2017-12-01 | 2018-01-23 | 138 | 0 | 16.9 | 70 |  | Caldwell | Caldwell | Tier 4 |  |  |  | 7216, 7224, 7215 | Y | N |  |  | 11459 | 3963
5201 | Magill 138 kV Station: Install 28.8 MVAR Cap Bank | Install a 28.8 MVAR Cap Bank at Magill 138 kV station |  | Magill |  | In-Service | 766-0951 | AEP TCC | Mark Strabala dnlyons@aep.com 918-599-2698 | 3574 | 2017-12-07 |  | 138 | 0 | 0 | 0 | 28.8,0 | Matagorda |  | Tier 4 |  |  |  | 8111 | Y | N |  |  | 12860 | 5201
6376 | Tennyson: Build 138 kV station | Construct new 138 kV box bay on the Red Creek to Nicole 138 kV line | IN SERVICE | Tennyson |  | In-Service | 871 - 1047 | AEP TNC | Bill Roberts mlforcum@aep.com 918-599-2674 | 2725 | 2017-12-12 | 2017-12-12 | 138 | 0 | 0 | 0 |  | Coke |  | Tier 4 |  |  |  | 60417, 6351, 6441 | Y | N |  |  | 14120 | 6376
3479 | Cassava: Build 69 kV station | Construct new Cassava station along the Big Lake to Mathis Field 69 kV line (at Barnhart Phillips Tap location) | IN SERVICE | Cassava |  | In-Service | 635 - 0804 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2590 | 2017-12-13 | 2017-12-13 | 69 | 0 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6003, 60359, 6035, 6526, 6532 | Y | N |  |  | 10861 | 3479
3480 | Cassava to Yucca: Rebuild 69 kV line | Rebuild 69 kV line as 138 kV from Cassava (Barnhart Phillips Tap) to Yucca and add 138/69 kV autotransformer capacity at Cassava | IN SERVICE | Cassava | Yucca | In-Service | 635 - 0804 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2591 | 2017-12-13 | 2017-12-13 | 138 | 12.3 | 0 | 90 |  | Taylor | Taylor | Tier 4 |  |  |  | 6034, 6035, 6531, 60360, 6036, 60359 | Y | N |  |  | 10862 | 3480
5202 | Bay City 138 kV Station: Install 14.4 MVAR Cap Bank | Install a 14.4 MVAR Cap Bank at Bay City 138 kV station |  | Bay City |  | In-Service | 767-0952 | AEP TCC | Mark Strabala dnlyons@aep.com 918-599-2698 | 3575 | 2017-12-14 |  | 138 | 0 | 0 | 0 | 0,14.4 | Matagorda |  | Tier 4 |  |  |  | 8113 | Y | N |  |  | 12861 | 5202
4931 | Yukon Switching Station | Construct new switching station |  | Yukon |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8345 | 2017-12-14 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 3 | 2015-06-19 | 2015-07-29 |  | 1250, 1019, 11140 | Y | N |  |  | 12564 | 4931
16TPIT0062 | Hutto Sw Sta - Gilleland Creek (LCRA) 138 kV Line | Upgrade existing line |  | Hutto Sw Sta | Gilleland Creek | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R773 | 2017-12-15 |  | 138 | 0 | 22 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 3654, 3665, 3666, 7336 | Y | N |  |  | 12373 | 3079
4743 | Plano Tennyson - Collin/Northwest Carrollton 138 kV Line | Upgrade the Plano Tennyson - Austin Ranch Junction double-circuit line section |  | Plano Tennyson | Austin Ranch Junction | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M369 | 2017-12-15 |  | 138 | 0 | 8.2 | 0 |  | Collin | Denton | Tier 4 |  |  |  | 676, 678, 2377, 2378, 2523, 2518, 2519, 2568, 2570 | Y | N |  |  | 12338 | 4743
6551 | Basin: Build 138 kV temporary tap | Construct new 138 kV box bay on the Solstice to Permian Basin 138 kV line | IN SERVICE | Basin |  | In-Service | 860 - 1038 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2728 | 2017-12-15 | 2017-12-15 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60415, 60392, 60397 | Y | N |  |  | 14291 | 6551
3671 | Moran to Putnam: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line | IN SERVICE | Moran | Putnam | In-Service | 645 - 0814 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 1807 | 2017-12-15 | 2017-12-15 | 69 | 0 | 12.9 | 0 |  | Shackelford | Callahan | Tier 4 |  |  |  | 60426, 6202, 6209, 6307 | Y | N |  |  | 14332 | 3671
5393 | Alpine REA Tap to Barrilla Junction: Rehab 69 kV line | Rehab Alpine REA Tap to Barrilla Junction 69 kV line | IN SERVICE | Alpine REA Tap | Barrilla Junction | In-Service | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2643 | 2017-12-15 | 2017-12-15 | 69 | 0 | 41.9 | 0 |  | Brewster | Pecos | Tier 4 |  |  |  | 6653, 6665 | Y | N |  |  | 13078 | 5393
11TPIT0050 | Roanoke Switch - Elizabeth Creek 138 kV line | Construct new double-circuit line. |  | Roanoke Switch | Elizabeth Creek | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M509-E | 2017-12-15 |  | 138 | 3.8 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 11863, 640, 1852, 1854, 1866, 1867 | Y | N |  |  | 10233 | 2884
5404 | Crowell to Truscott Humble Tap: Rehab 69 kV line | Rehab Crowell to Truscott Humble Tap 69 kV line | IN SERVICE | Crowell | Truscott Humble Tap | In-Service | 786 - 0971 | AEP TNC | Jake Tucker mlforcum@aep.com 918-599-2674 | 2645 | 2017-12-21 | 2017-12-21 | 69 | 0 | 16.22 | 0 |  | Foard | Knox | Tier 4 |  |  |  | 6082, 6084 | Y | N |  |  | 13090 | 5404
5156 | Fort Stockton Plant: Build 138 kV terminal | Interconnect Oak Solar solar farm at Fort Stockton Plant | IN SERVICE | Fort Stockton |  | In-Service | 752 - 0935 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2622 | 2017-12-21 | 2017-12-21 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6630 | Y | N |  |  | 12812 | 5156
4969 | Pomelo: Build new four breaker 345 kV station | Interconnect Hidalgo Windfarm at Pomelo to connect Hidalgo to the Del Sol to North Edinburg 345 kV line |  | Del Sol | North Edinburg | In-Service | 733 - 0915 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3564 | 2017-12-21 | 2017-08-25 | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 8574, 88574, 8383, 80355, 161705 | Y |  |  |  | 12604 | 4969
5193 | Ft. Griffin: Build 69 kV station and add capacitor bank | Construct new 69 kV ring bus near Albany and add one 14.4 Mvar capacitor bank | IN SERVICE | Ft. Griffin |  | In-Service | 756 - 0940 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2631 | 2017-12-22 | 2017-12-22 | 69 | 0 | 0 | 0 | 0,14.4 | Shackelford |  | Tier 4 |  |  |  | 6207, 6213, 6214, 60398 | Y | N |  |  | 14301 | 5193
5397 | Cassava to Mertzon REA Tap: Rehab 69 kV line | Rehab Cassava to Mertzon REA Tap 69 kV line | IN SERVICE | Cassava | Mertzon REA Tap | In-Service | 786 - 0971 | AEP TNC | Bill Roberts mlforcum@aep.com 918-599-2674 | 2644 | 2017-12-28 | 2017-12-28 | 69 | 0 | 16.45 | 0 |  | Irion | Irion | Tier 4 |  |  |  | 6526, 60359 | Y | N |  |  | 13084 | 5397
5640 | Bringhurst 69kV Substation - Loop Conversion | Convert Bringhurst substation from tap service to 69kV loop service. Loop Ckt.12 Clinton to Brown |  | Bringhurst | Clinton/Brown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-12-31 |  | 69 | 0 | 0.3 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47540, 40352, 47550, 47670, 41040, 47752 | Y | N |  |  | 13373 | 5640
5056 | Maxwell: Build new three breaker 138 kV station | Interconnect Val Verde Wind Farm permanently at Maxwell station via Fermi Collector station |  | MAXWELL |  | Under Construction | 735-0917 | AEP TCC | Wilburt Robert dnlyons@aep.com 918-599-2698 | 3565 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  | 8998, 88998, 8257, 8261, 181754 | Y | N |  |  | 13095 | 5056
5833 | Rebuild Rockett to Rockett SW | Rebuild Rockett (Bus #218) to Rockett SW (Bus #214) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 16026 | 2017-12-31 |  | 69 | 0 | 6.44 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  | 214, 218 | Y |  |  |  | 13575 | 5833
5411 | Haisley: Add Distribution Station | Add New Haisley Distribution Station |  | Lon Hill | Medio Creek | Under Construction | 783 - 0968 | AEP TCC | Bill Roberts dnlyons@aep.com 918-599-2698 | 3576 | 2017-12-31 | 2017-04-14 | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8920, 8452, 8912 | Y | N |  |  | 13098 | 5411
5888 | Stewart to West Bay Ckt.48 & 59 | Reconductor Ckt.48 & 59 Stewart to West Bay as a restoration project |  | Stewart | West Bay | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 43290, 43520, 43521 | Y | N |  |  | 13605 | 5888
5950 | Smithville to Rosanky Rebuild | Part 2: Upgrade Structures on Smithville to Rosanky Transmission Line |  | Smithville | Rosanky | Planned |  | BBEC | Thomas Ellis thomas.ellis@bluebonnet.coop |  | 2017-12-31 |  | 69 | 0 | 5.4 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  | 7315, 7558 | Y | N |  |  | 13661 | 5950
4453 | Henne to McCarty Lane Transmission Line Upgrade | Upgrade the 6.6 mile Henne (7172) - McCarty Lane (7182) 138-kV transmission line to single 959 ACSS Suwannee, 380 MVA. |  | Henne | McCarty Lane | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015117 | 2017-12-31 | 2018-01-09 | 138 | 0 | 6.6 | 0 |  | Comal | Hays | Tier 4 |  |  |  | 7172, 7182 | Y | N |  |  | 12013 | 4453
5203 | Bessel 138 kV Station: Install Cap Bank | Install a 14.4 MVAR Cap Bank at Bessel 138 kV station |  | Bessel |  | In-Service | 764-0949 | AEP TCC | James Weaver dnlyons@aep.com 918-599-2698 | 3572 | 2018-01-04 |  | 138 | 0 | 0 | 0 | 0,24.4 | Nueces |  | Tier 4 |  |  |  | 8060 | Y | N |  |  | 12862 | 5203
6562B | Crowley - Cresson 69 kV Line Conversion | Rebuild existing 69 kV line section from Crowley - Cresson |  | Crowley | Cresson | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5244 | 2018-01-15 |  | 138 | 0 | 9.1 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2203, 2204, 2205, 12205, 12209, 1883, 1884, 1967, 1968 | Y | N |  |  | 14308 | 6562
4268 | Breckenridge - Leon Switch 69 kV Line | Upgrade existing line |  | Breckenridge | Leon Switch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R783 | 2018-01-15 |  | 69 | 0 | 17 | 0 |  | Stephens | Eastland | Tier 3 |  |  |  | 271, 1622, 1615, 1625 | Y | N |  |  | 11816 | 4268
5405 | Lufkin Corridor Expansion | Rebuild existing Lufkin - Lufkin Sw. Sta. 138 kV lines |  | Lufkin | Lufkin | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6074 | 2018-01-15 |  | 138 | 0 | 4.2 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3118, 3316, 3340, 3268, 3341 | Y | Y |  |  | 13091 | 5405
5713 | Upgrade the Brownwood - Brownwood Sw. | Upgrade the Brownwood - Brownwood Sw. Sta. 138 kV Line |  | Brownwood Sw. Sta. | Brownwood South | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1738 | 2018-01-15 |  | 138 | 0 | 7.4 | 0 |  | Brown | Brown | Tier 4 |  |  |  | 1655, 1656, 1657, 1661 | Y |  |  |  | 13452 | 5713
5398 | Lufkin Pershing 138 kV Emergency Capacitors | Install 18.4 MVar Cap Bank at Lufkin PershingTap |  | Lufkin Pershing Tap | Lufkin Pershing Tap | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6070 | 2018-01-15 |  | 138 | 0 | 0 |  | 0,18.4 | Angelina | Angelina | Tier 4 |  |  |  | 3329 | Y | N |  |  | 13085 | 5398
09TPIT0122 | Shamburger - Tyler NW 138 kV line | Upgrade existing 138 kV line | Construction schedule change | Shamburger | Tyler NW | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6001-E | 2018-01-15 |  | 138 | 0 | 6.3 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3104, 3141 | Y | N | 2009-E6 |  | 8418 | 1240
4263 | Tyler Northwest - Elkton 138 kV Line | Upgrade existing Tyler West - Tyler Northwest 138 kV line Section |  | Tyler West | Tyler Northwest | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6053 | 2018-01-15 |  | 138 | 0 | 3.7 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3139, 3141 | Y | N |  |  | 11811 | 4263
5403 | Lufkin 138 kV Sw. Sta. Rebuild | Rebuild existing 138 kV switching station |  | Lufkin Sw. Sta. | Lufkin Sw. Sta. | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6067 | 2018-01-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3118, 3349 | Y | N |  |  | 13089 | 5403
4273 | Corsicana - Trinidad 69 kV Line | Upgrade existing line | Construction schedule change | Corsicana | Trinidad | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R794 | 2018-01-15 |  | 69 | 0 | 26.5 | 0 |  | Navarro | Henderson | Tier 3 | 2015-06-15 | 2015-08-15 |  | 3128, 3466, 3467, 3468, 3469 | Y | N |  |  | 11822 | 4273
4299 | Big Brown - Navarro Switch 345 kV Line | Upgrade existing double-circuit line | Construction Schedule Change | Big Brown | Navarro Switch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1705 | 2018-01-15 |  | 345 | 0 | 62 | 0 |  | Freestone | Navarro | Tier 4 | 2015-06-15 |  |  | 3380, 68091 | Y | N |  |  | 11855 | 4299
6087 | Flat Top 345 kV Switching Station | Flat Top 345 kV Switching Station |  | Comanche | Brown | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1740 | 2018-01-15 |  | 345 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  | 11441, 1440, 1444 | Y | N |  |  | 13811 | 6087
4082 | CPSE_Howard to Somerset Rebuild | Rebuild approximately seven miles of 138 kV transmission circuit from Howard to Somerset. The Howard to Somerset circuit should be upgraded to 469 MVA, minimum. |  | Howard | Somerset | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0232 | 2018-01-19 |  | 138 | 0 | 7.56 | 0 |  | Bexar | Bexar | Tier 2 | 2014-05-07 | 2014-09-04 |  | 5230, 5390 | Y | N |  |  | 11607 | 4082
5208A | SPLIT INTO PHASES SC ADDITIONS |  |  | Alibates |  |  |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-01-23 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  | 79520, 79522, 79500 | Y |  |  |  | 14503 | 5208
5891A | LUBZOL Substation Removal and Substation PATRIK Addition | Remove LUBZOL 138kV substation from CNP service |  | LUBZOL | TIDAL/TRAVIS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-01-28 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40980, 41580, 41590 | Y | N |  |  | 13608 | 5891
4253 | Eagle Mountain-Calmont 138 kV Line | Upgrade existing double-circuit line |  | Eagle Mountain | Calmont | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5213 | 2018-01-30 |  | 138 | 0 | 40.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1953, 1954, 1975, 1976, 902835, 1865, 1955, 2085, 2086, 2087, 2088, 11860 | Y | N |  |  | 14425 | 4253
6599 | Service to Danforth Substation | GVEC will tie into the AEP Kenedy Switch to Coleto Creek 138 T-line ckt to service the DCP Midstream Danforth Substation, GVEC will only meter the load. |  | Rosata POD | Danforth | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-01-30 |  | 138 | 0.029 | 0 | 0 |  | Goliad | Goliad | Tier 4 |  |  |  | 7241, 88153 | Y | N |  |  | 14585 | 6599
5731A | Tri Corner 345 kV Sw Sta | Temporary Configuration for Tri Corner |  | Tri Corner | Tri Corner | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4228 | 2018-02-01 |  | 345 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2432, 2428, 2433, 3102, 3124 | Y |  |  |  | 14310 | 5731
4186E | University Area 138kV Conversions |  |  | University |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2018-02-01 00:03 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47750, 47752, 49030 | Y |  |  |  | 14905 | 4186
3272 | Potranco - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to AMD line. |  | Cagnon | AMD | Planned | S-845 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0219 | 2018-02-08 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5346, 5002, 5053 | Y | N |  | There are no transformers associated with this project | 10623 | 3272
11TPIT0107 | Steamboat: Reterminate 69 kV Happy Valley tap | Reterminate the Happy Valley tap into Steamboat | IN SERVICE | Happy Valley | Steamboat | In-Service | 341 - 0515 | ETT | Teresa Trotman mlforcum@aep.com 918-599-2674 | 2092 | 2018-02-14 | 2018-02-14 | 69 | 0 | 0.6 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6332, 6328, 6330, 6331, 60332 | Y | N |  |  | 7474 | 302
4752 | Venus Sw Sta - Cedar Hill 138 kV line | Rebuild existing line |  | Venus Sw Sta | Cedar Hill | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4201 | 2018-02-15 |  | 138 | 0 | 20.6 | 0 |  | Ellis | Dallas | Tier 4 |  |  |  | 1908, 2300, 2310, 2311, 2313, 2314, 3053, 3054 | Y | N |  |  | 12347 | 4752
5554 | Jones Creek Cap Bank #1 | Install capacitor bank #1 at Jones Creek substation (120MVAR). | - Updated project title and description - Updated expected date | Jones Creek |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1113 | 2018-02-28 | 2018-01-25 | 138 | 0 | 0 | 0 | 0,120 | Brazoria |  | Tier 4 |  |  |  | 42541, 42540, 42645 | Y | N |  |  | 13282 | 5554
5764 | Obrien to WA Parish Ckts.98 & 99 | Increase thermal ratings of Ckst.98 & 99 Obrien to WA Parish by installing shunts on line and upgrading substation equipment |  | Obrien | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-02-28 |  | 345 | 0 | 34 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44000, 44500 | Y | N |  |  | 13510 | 5764
5791 | GEBHRT - 138kV Substation | Build new 138kV GEBHRT customer-owned substation. Loop through Ckt.65 Sealy to Wallis. | New Project | GEBHRT | Sealy/Wallis | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-02-28 |  | 138 | 0 | 0 | 0 |  | Austin | Austin | Tier 4 |  |  |  | 44700, 44190, 44640, 44740, 46220 | Y | N |  |  | 13530 | 5791
5765 | TECO to Blodgett Tap Ckt37 | Upgrade substation equipment at TECO to increase TECO to Blodgett Tap Ckt37 thermal ratings |  | TECO | Blodgett | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47430, 47521, 47660 | Y | N |  |  | 13511 | 5765
4705 | San Felipe to Eureka Ckt.09 | Upgrade Ckt.09 San Felipe to Eureka to increase thermal ratings | Change in project description | San Felipe | Eureka | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1132 | 2018-02-28 |  | 138 | 0 | 3.3 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45750, 47380, 47382 | Y | N |  |  | 12292 | 4705
5944 | TEXWAL - Ckt.10 Loop Conversion | Convert existing 69kV TEXWAL substation from tap service to loop service on Ckt.10 Greens Bayou to Wallisville. Remove existing tap from Ckt.61. |  | TEXWAL | Green Bayou/Wallisville | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-02-28 |  | 69 | 0.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41570, 48372, 905620, 40250, 40725, 41682, 40352, 41681 | Y | N |  | 0 | 44191 | 5944
4711A | CORTEZ 138kV Substation | Construct service to new 138kV CORTEZ customer-owned substation. As part of the project, Quintana substation will be disconnected from direct CNP service, and will be served through CORTEZ substation. CORTEZ will loop through Ckt.48 MARINE to Jones Creek. | Delay in project schedule | CORTEZ | MARINE/Quintana | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 55 | 2018-02-28 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43435, 43440, 42540, 43155, 43362 | Y | N |  |  | 12305 | 4711
5768 | Garrott to Blodgett tap Ckt.37 | Upgrade Ckt.37 Garrott to Blodgett tap to increase thermal ratings |  | Garrott | Blodgett | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-02-28 |  | 138 | 0 | 1.3 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47521, 47660 | Y | N |  |  | 13514 | 5768
5270B | Twin Buttes Autotransformer Addition | Replace the existing Twin Buttes AT1 autotransformer with a new 345/138-kV 672 MVA autotransformer. Remove the existing 36 MVAR Twin Buttes AT1 tertiary reactor. | Changed to phased project to show in-service date for major equipment associated with project. | Twin Buttes |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016445 | 2018-03-01 | 2018-01-31 | 345 | 0 | 0 | 672 |  | Tom Green |  | Tier 4 |  |  |  | 77281, 76009, 76011 | Y | N |  |  | 12946 | 5270
6655 | Rosata: Build 138kV Substation | Build new Rosata 138kV POD Switch on Coleto Creek to Kenedy 138kV Line. |  | Coleto Creek | Kenedy | Planned |  | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2018-03-02 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  | 88153, 8162, 8186 | Y | N |  |  | 14412 | 6655
5169 | Harlingen SS to Raymondville #2: Rebuild 69 kV line | Rehab Harlingen SS to Raymondville #2 |  | Harlingen SS | Raymondville #2 | Under Construction | 749 - 0932 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 2923 | 2018-03-02 | 2017-12-15 | 138 | 0 | 22.8 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  | 8300, 8325, 8700 | Y | N |  |  | 12827 | 5169
5174 | Nelson Sharpe: Reconfigure PST | Relocate the PST at Nelson Sharpe from the Barney Davis to Nelson Sharpe 138 kV line to the Nelson Sharpe to Celanese Bishop 138 kV line |  | Nelson Sharpe |  | In-Service | 747 - 0930 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2921 | 2018-03-02 | 2017-09-28 | 138 | 0 | 0 | 150 |  | Nueces |  | Tier 4 |  |  |  | 85002, 85007, 8515, 8516, 85001 | Y | N |  |  | 12833 | 5174
4756 | Wink - Screwbean 138 kV circuit | Add second circuit to existing line |  | Wink | Culberson | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8337 | 2018-03-05 |  | 138 | 54 | 0 | 0 |  | Winkler | Culberson | Tier 4 |  |  |  | 1074, 1081, 1083, 1084, 1093, 1094, 1095 | Y | N |  |  | 12351 | 4756
4755 | Barstow NW - Culberson 138 kV Line | Construct a new DCKT Line |  | Barstow NW | Culberson | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8342 | 2018-03-15 |  | 138 | 57.12 | 0 | 0 |  | Ward | Culberson | Tier 4 | 2013-02-15 | 2013-02-15 |  | 1080, 1086, 1097 | Y | N |  |  | 12350 | 4755
2941A | North Main Switch third transmission source | Construct a third 138 kV line into North Main Switch | Construction schedule change | Randol Mill | North Main Switch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5161-E | 2018-03-15 |  | 138 | 4.4 | 4.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1958, 1964, 2093, 2157, 3011, 12093, 902761, 1952, 2106, 2158 | Y | N |  |  | 10285 | 2941
5985 | Holt - Cowden North 69 kV Line | Holt - Cowden North 69 kV Line |  | Holt | Cowden North | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9024 | 2018-03-15 |  | 69 | 0 | 7.3 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1142, 1259 | Y | N |  |  | 13700 | 5985
5683E | Line H Rebuild and 138kV conversion. | Convert Pyote facility to 138 kV. Rebuild line from Pyote-Worsham (38001-38021). De-energize 69 kV line Wickett-Pyote (37980-38000). |  | 38001 | 38021 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2018-03-15 |  | 138 | 0 | 15.43 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38000, 38001, 37980, 38021 | Y |  |  |  | 13747 | 5683
6748 | Gillrina Build 138kV Tap | Gillrina Temporary Hard Tap on Stadium to Calallen 69kV Line. |  | Stadium |  | In-Service | 901 - 1079 | AEP TCC/STEC | Daniel Lyons dnlyons@aep.com 918-599-2698 | 3594 | 2018-03-16 |  | 69 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8031, 88031, 8888, 8889 | Y | Y |  |  | 14541 | 6748
5145A | Rafter - New 138 kV Substation | Tap new 138 kV load serving substation into existing Castroville to Texas Research 138 kV transmission line. |  | RAFTER | CASTROVILLE/TX_RSCH | Planned | S-0837 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0261 | 2018-03-29 |  | 138 | 0.5 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5355, 55355, 5083, 5430 | Y | N |  |  | 14398 | 5145
6256 | Rebuild Saltdome to a loop | Rebuild single 69 kV 4-0 ACSR lines with 795 ACSR 138 capable double circuit and remove the Clemville Switching Station. |  | Clemville Switch | Saltdome | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-03-30 | 2018-03-07 | 69 | 2.6 | 3.4 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  | 5549, 5559, 5548, 5550, 5551, 5553, 5555 | Y | N |  |  | 13984 | 6256
5808 | Install 160MVAR capacitor bank at Jones Creek substation. | Install 160MVAR capacitor bank at Jones Creek substation. |  | Jones Creek | CORTEZ | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-03-30 |  | 138 | 0 | 0 | 0 | 0,160 | Brazoria | Brazoria | Tier 4 |  |  |  | 42542, 42540, 43440 | Y | N |  |  | 13548 | 5808
5553B | Village Creek 138kV Substation | Construct service to new 138kV Village Creek distribution substation. Loop through Ckt.09 Zenith to Franz. | Delay in project schedule | Village Creek | Zenith/Franz | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-03-30 |  | 138 | 0.1 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | Y | N |  |  | 13281 | 5553
6674 | Oyster Creek 2nd Cap Bank | Install 2nd capacitor bank (40MVAR) at Oyster Creek sub |  | Oyster Creek | Velasco | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-03-30 |  | 138 | 0 | 0 | 0 | 0,40 | Brazoria | Brazoria | Tier 4 |  |  |  | 43337, 43335, 43361 | Y |  |  |  | 14474 | 6674
3937 | Brazos Valley Connection | Construct 345kV double circuit from Gibbons Creek to Zenith. Circuit numbers are 18 & 50. | Circuit mileage update | Gibbons Creek | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 717 | 2018-03-31 |  | 345 | 126 | 0 | 0 |  | Harris | Grimes | Tier 1 | 2013-07-25 | 2014-02-20 | 2014-04-08 | 967, 3390, 3391, 44645, 44900, 46020 | Y | Y |  |  | 12068 | 3937
3268 | AEP_McCampbell: New Substation Cut In | Customer to construct 138kV substation. Two 138kV circuits Cut-In to McCampbell substation. | Transmission Status, Contact, and schedue update | Dupont SS | Whitepoint SS | Under Construction | 561 - 0729 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3435 | 2018-03-31 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 80469, 8414, 8422, 8961, 80470 | Y | N |  | This project was previously referred to as 4578. Project 4578 was deleted and replaced by this project 3268. | 10619 | 3268
5235 | Bakersfield Reactor Bank Addition(s) | Add two (2) 50 MVAR reactor banks at Bakersfield Substation | Construction Schedule | Bakersfield |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016061 | 2018-03-31 |  | 345 | 0 | 0 | 0 | 0,-100 | Pecos |  | Tier 4 |  |  |  | 76002 | Y | N |  |  | 12908 | 5235
6565 | THW A3 Replacement | Replacement of TH Wharton Auto #3 |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-03-31 |  | 345 | 0 | 0 | 600 |  |  |  | Tier 4 |  |  |  | 49071, 45500, 45515 | Y |  |  |  | 14315 | 6565
5807 | Velasco Cap Bank #2 | Install capacitor bank #2 at Velasco substation (120MVAR). |  | Velasco |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-03-31 00:01 |  | 138 | 0 | 0 | 0 | 0,120 | Brazoria |  | Tier 4 |  |  |  | 43362, 905182, 905183, 43360, 42510, 43155, 43361 | Y | N |  | 0 | 43252 | 5807
6350 | Sonora Atlantic to Sonora 69 kV line: Rebuild 69 kV line | Rehab Sonora Atlantic to Sonora 69 kV line | IN SERVICE | Sonora Atlantic | Sonora | In-Service | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2707 | 2018-04-01 | 2018-04-01 | 69 | 0 | 11.9 | 0 |  | Sutton | Sutton | Tier 4 |  |  |  | 6511, 6513 | Y | N |  |  | 14094 | 6350
6527 | Bellville South Autotransformer Refurbishment | Restores Bellville South 138/69-kV autotransformer (failed in January 2017) to service. | Autotransformer delivery date update. | Bellville South |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1018388 | 2018-04-01 |  | 69 | 0 | 0 | 0 |  | Austin |  | Tier 4 |  |  |  | 7269, 7270 | Y | N |  |  | 14265 | 6527
5955 | Mesquite: Build new distribution station | Mequite: Build new distribution station |  | Rangerville | Wesmer | In-Service | 803 - 0988 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 3594 | 2018-04-01 | 2018-02-16 | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8554, 8347, 80103 | Y | N |  |  | 13668 | 5955
6164 | Unitec: Build new distribution station | Unitec: Build new distribution station |  | North Laredo SS | Gateway Tap | In-Service | 866 - 1044 | AEP TCC | Rich Haley dnlyons@aep.com 918-599-2698 | 3653 | 2018-04-03 | 2018-04-03 | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 8134, 8650, 8909 | Y | N |  |  | 13889 | 6164
5171 | Bates to Wormser: Raise structures increase MOT | Increase the MOT rating of the Bates to Wormser 138kV line by raising four structures and remedying MLSE Equipment |  | Bates | Wormser | Under Construction | 750 - 0933 | AEP TCC | Eric Johnson dnlyons@aep.com 918-599-2698 | 2924 | 2018-04-15 |  | 138 | 0 | 126.48 | 0 |  | Hidalgo | Webb | Tier 4 |  |  |  | 8299, 8392, 8394, 8399, 8795, 8957, 8985, 80106, 80230, 8295 | Y | N |  |  | 12829 | 5171
5886 | Bellaire Auto A1 - Upgrade Limiting Equipment | Upgrade limiting equipment for Bellaire auto A1 |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-04-30 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47000, 47010, 49001 | Y |  |  |  | 13602 | 5886
5278 | Arco Tap Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Arco Tap. |  | Arco |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016390 | 2018-04-30 |  | 138 | 0 | 0 | 0 |  | Crane |  | Tier 4 |  |  |  | 1199, 71199, 1201, 71230, 76615 | Y | N |  |  | 12954 | 5278
3669 | Albany Foundry to Moran: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line | IN SERVICE | Albany Foundry | Moran | In-Service | 645 - 0814 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 1808 | 2018-04-30 |  | 69 | 0 | 10 | 0 |  | Shackelford | Shackelford | Tier 4 |  |  |  | 6202, 60426 | Y | N |  |  | 11081 | 3669
6351 | Friend Ranch to Crockett Heights 69 kV line: Rbld 69 kV line | Rehab Friend Ranch to Crockett Heights 69 kV line | IN SERVICE | Friend Ranch | Crockett Heights | In-Service | 786 - 0971 | AEP TNC | Tram Trinh mlforcum@aep.com 918-599-2674 | 2705 | 2018-05-01 | 2018-05-01 | 69 | 0 | 1.23 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  | 6550, 6552 | Y | N |  |  | 14095 | 6351
5933 | Tippett Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Tippet Substation and move the existing generation interconnection at Desert Sky #2 to Tippet Substation. |  | Desert Sky Tap #2 | Tippet | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017409 | 2018-05-01 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 76016, 76021, 6586, 76001, 76013, 76595, 131033 | Y | N |  |  | 13641 | 5933
5208B | SPLIT INTO PHASES SC ADDITIONS |  |  | Tule Canyon |  |  |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-05-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  | 79521, 79523, 79503 | Y |  |  |  | 14504 | 5208
6396 | Treadwell: Build temporary tap | Interconnect Cactus Flats wind farm on the SAPS to Yellowjacket 138 kV line | IN SERVICE | Treadwell |  | In-Service | 875 - 1053 | AEP TNC | Tom Reynolds mlforcum@aep.com 918-599-2674 | 2726 | 2018-05-11 | 2018-05-11 | 138 | 0 | 0 | 0 |  | Concho |  | Tier 4 |  |  |  | 60423, 6365, 6480 | Y | Y |  |  | 14155 | 6396
4574 | Briarcrest to Nall Cable Upgrade | Upgrade Briarcrest to Nall Cable to match OH section |  | 32877 | 32872 | Planned |  | BRYN |  |  | 2018-05-14 |  | 69 | 0 | 0.5 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32872, 32877 | Y |  |  |  | 12156 | 4574
4937 | Wolf 138 kV Switching Station | Construct new 138 kV switching station |  | Wolf Switching Station |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8262 | 2018-05-14 |  | 138 | 0 | 0 | 0 |  | Ward |  | Tier 4 |  |  |  | 1013, 1001, 1009, 1010, 1019, 1074, 1087, 1103, 1107, 1146, 1292, 1015 | Y | N |  |  | 12570 | 4937
4843 | Hicks Sw. Sta. 345/138 kV autotransformer #2 | Install second 345/138 kV autotransformer |  | Hicks Sw. Sta. |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5229 | 2018-05-15 |  | 345 | 0 | 0 | 600 |  | Tarrant |  | Tier 4 |  |  |  | 2082, 2081 | Y | N |  |  | 12445 | 4843
09TPIT0044 | E. Richardson - Apollo 138kV line (Oncor' section) | Upgrade existing 138 kV line |  | E. Richardson | Apollo | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3033-WA | 2018-05-15 |  | 138 | 0 | 2.3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 802, 2690 | Y | N |  |  | 10414 | 3070
4757 | Riverton 138 kV Switching Station | Construct new switching station |  | Mason |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8338 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 11083, 1083, 1094, 11080, 11091 | Y | N |  |  | 12352 | 4757
6301 | Tyler Northwest 138 kV Sw. Sta. | Establish Black Fork Sw. Sta. |  | Black Fork |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6072 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Smith |  | Tier 4 |  |  |  | 3137, 3139, 3141, 3202 | Y | Y |  |  | 14030 | 6301
5983 | Pyote 138 kV Capacitors | Pyote 138 kV Capacitors |  | Whiting Oil |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9023 | 2018-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Ward |  | Tier 4 |  |  |  | 1080 | Y | N |  |  | 13698 | 5983
15TPIT0058 | Permian Basin - Ward Gulf Tap - Wink 138 kV line | Upgrade existing 138 kV line |  | Permian Basin | Wink | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8189-E | 2018-05-15 |  | 138 | 0 | 16.5 | 0 |  | Ward | Winkler | Tier 4 |  |  |  | 1010, 1074, 1087 | Y | N |  |  | 10182 | 2834
4367 | Screwbean Tap - Culberson 138 kV Line | Rebuild existing 138 kV line | Construction schedule change | Screwbean Tap | Culberson | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8274 | 2018-05-15 |  | 138 | 0 | 19.6 | 0 |  | Culberson | Culberson | Tier 4 |  |  |  | 1083, 1095, 1096, 1097, 11079 | Y | N |  |  | 11916 | 4367
4257 | Stryker Creek - Gresham Road 138 kV line | Upgrade existing line |  | Stryker Creek | Gresham Road | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6054 | 2018-05-15 |  | 138 | 0 | 9.1 | 0 |  | Cherokee | Rusk | Tier 4 |  |  |  | 3110, 3301 | Y | N |  |  | 11803 | 4257
6027 | Cockrell Hill - Hampton Rd 138 kV Line Double-circuit Line | Upgrade terminal equipment on Cockrell Hill - Hampton Rd 138 kV Double-circuit Line |  | Cockrell Hill | Hampton Rd | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4163 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 3014, 3016 | Y | N |  |  | 13751 | 6027
6036 | Roanoke Sw. - Park Vista POI 138 kV Line | Upgrade terminal equipment on Roanoke Sw. - Park Vista POI 138 kV Line |  | Roanoke Sw. | Park Vista POI | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4168 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Denton | Tarrant | Tier 4 |  |  |  | 1852, 1854, 15100, 15101 | Y |  |  |  | 13755 | 6036
6385 | BRECKENRIDGE TAP-GRAHAM SW. STA. | Upgrade Terminal Equipment at BRECKENRIDGE TAP-GRAHAM SW. STA. |  | Breckenridge | Graham | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2022 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Stephens | Young | Tier 4 |  |  |  | 1431, 1613, 1618 | Y | N |  |  | 14139 | 6385
6026 | Mountain Creek - Cockrell Hill 138 kV Line | Upgrade terminal equipment on Mountain Creek - Cockrell Hill 138 kV Line |  | Mountain Creek | Cockrell Hill | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4162 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2411, 3015 | Y | N |  |  | 13750 | 6026
6028 | Rice Sw. - Markley 138 kV Line | Upgrade terminal equipment on Rice Sw. - Markley 138 kV Line |  | Rice Sw. | Markley | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4016 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Young |  | Tier 4 |  |  |  | 1476, 1477 | Y | N |  |  | 13752 | 6028
6039 | Carrollton NW 345/138 kV Auto #1 | Upgrade terminal equipment on Carrollton NW 345/138 kV Auto #1 |  | Carrollton NW |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4167 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2360, 2362, 2363 | Y | N |  |  | 13758 | 6039
6037 | Irving Grant - Norwood 138 kV Line Section | Upgrade terminal equipment on Irving Grant - Norwood 138 kV Line |  | Irving Grant | Norwood | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4165 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2055, 2408 | Y | N |  |  | 13756 | 6037
15TPIT0083B | Collin - Arco (TMPA) 138 kV Line (Oncor's section) | Add second circuit to existing line from Krugerville to Arco (TMPA) |  | Krugerville | Arco (TMPA) | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R929 | 2018-05-15 |  | 138 | 5.7 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 923, 33662 | Y | N |  |  | 12101 | 3216
4932 | Wink - Yukon 138 kV Line | Wink - Yukon 138 kV Line | Construction schedule change | Wink | Yukon | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8346 | 2018-05-15 |  | 138 | 36 | 9 | 0 |  | Ector | Winkler | Tier 3 | 2015-06-19 | 2015-07-29 |  | 1252, 1074, 1075, 1250, 1251, 1254, 1253, 1258 | Y | N |  |  | 12565 | 4932
4524 | Culberson 138 kV Switching Station | Rebuild 138 kV bus | Construction schedule change | Culberson Switching station |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8366 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Culberson |  | Tier 4 | 2013-02-15 | 2013-02-15 |  | 1097, 1080, 1086, 11078 | Y | N |  |  | 12096 | 4524
5197 | Abilene Northwest to Elm Creek: Rebuild 69 kV line | Rebuild Abilene Northwest to Elm Creek 69 kV line |  | Abilene Northwest | Elm Creek | In-Service | 759 - 0943 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2634 | 2018-05-16 | 2018-05-16 | 69 | 0 | 3.07 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6253, 6225 | Y | N |  |  | 12856 | 5197
5020 | Red Creek: Replace the other 345/138 kV autotransformer | Replace both 345/138 kV autotransformers at Red Creek with 480 MVA autotransformers | IN SERVICE | Red Creek |  | In-Service | 566 - 0740 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2615 | 2018-05-24 | 2018-05-24 | 345 | 0 | 0 | 480 |  | Tom Green |  | Tier 4 |  |  |  | 6769, 6444, 6442, 6295 | Y | N |  |  | 12653 | 5020
3819 | Rebuild San Miguel Tap to North Calliham | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. Not Rebuild 336 ACSR portion from San Miguel to San Miguel Tap. |  | Sam Miguel Tap | North Calliham | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-05-29 | 2018-06-01 | 69 | 0 | 17.5 | 0 |  | Atascosa | McMullen | Tier 4 |  |  |  | 5693, 5698 | Y | N |  | Not Rebuild 336 ACSR portion from San Miguel to San Miguel Tap. | 11276 | 3819
4997B | Deepwater Area Conversions | Convert CHANEL sub to 138kV service. Loop from Ckt.70 BRANUM to LYDELL. |  | CHANEL | BRANUM/LYDELL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 986 | 2018-05-29 00:02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 40275, 40270, 41009, 40640 | Y | N |  | 0 | 43260 | 4997
6356 | Cedar Hill to Edith 69 kV line: Rebuild 69 kV line | Rehab Cedar Hill to Edith 69 kV line | IN SERVICE | Cedar Hill | Edith | In-Service | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2714 | 2018-05-30 | 2018-05-30 | 69 | 0 | 12.6 | 0 |  | Coke | Coke | Tier 4 |  |  |  | 6422, 6423 | Y | N |  |  | 14100 | 6356
6312A | PH Robinson Autotransformer A3 800MVA Addition | Install PH Robinson 800MVA 345/138kV Auto A3 |  | PH Robinson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-30 00:01 |  | 345 | 0 | 0 | 800 |  | Harris |  | Tier 4 |  |  |  | 49049, 42000, 42015 | Y | N |  | 0 | 43464 | 6312
4706D | HO Clarke to Webster Ckt.05 | Outage Southwyck to Friendswood Tap for upgrades |  | Southwyck | Friendswood Tap | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2018-05-30 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42651, 43262, 44361, 43505, 47150 | Y |  |  | 0 | 43256 | 4706
4997D | Deepwater Area Conversions | Remove CHANEL 69kV Service |  | CHANEL | Harris/Deepwater | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 986 | 2018-05-30 00:04 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 40270, 40470, 40800 | Y | N |  | 0 | 43262 | 4997
5923 | Fayetteville - FPP 138-kV Transmission Line Overhaul | Overhaul FPP to Fayetteville 138-kV and reconductor with 959 ACSS/TW Suwannee. New circuit rating (MVA): Rate A=287, Rate B=287, Rate C=380. |  | Fayetteville | FPP | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016108 | 2018-05-31 |  | 138 | 0 | 6.9 | 0 |  | Fayette |  | Tier 4 |  |  |  | 7278, 7286 | Y | N |  |  | 13631 | 5923
5925 | Gilleland Creek - Hutto Transmission Line Upgrade | Upgrade terminal equipment on T21452 at Gilleland Creek to minimum 3000 Amp rating. Needed to support an ONCOR project to upgrade the Hutto Sw. Station to Round Rock Southeast to Gilleland Creek 138-kV line. |  | Gilleland Creek | Hutto | Planned | 16TPIT0062 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017384 | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Travis | Williamson | Tier 4 |  |  |  | 7336 | Y | N |  |  | 13633 | 5925
5922 | Flatonia - Waelder Transmission Line Overhaul | Overhaul the Flatonia to Waelder and reconductor with 795 ACSR Drake conductor. New rating (MVA): Rate A=42, Rate B=42, Rate C=111. | Project Schedule Expedited | Flatonia | Waelder | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017377 | 2018-05-31 |  | 69 | 0 | 11.8 | 0 |  | Gonzales | Fayette | Tier 4 |  |  |  | 7232, 7247 | Y | N |  |  | 13630 | 5922
5600 | New 138 kV Retrieve Breakered Substation | Expand existing 138kV Retrieve substation to switching substation with breaker-and-half configuration. Loop Ckt.02 West Columbia to Lake Jackson. Also loop two TNMP circuits into new substation. |  | Retrieve | West Columbia/Lake Jackson | Planned |  | CNP/CNP/TNMP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0.2 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 43145, 43170, 43171, 43172, 39560, 39600, 42150, 42215, 42810, 42880, 43380, 48006 | Y | N |  |  | 13330 | 5600
6669 | CNP_TPIT6669_Satsuma_Tap_Reconductor | Reconductor Satsuma Tap |  | Satsuma Tap | Satsuma | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  | 2017-12-12 | 42011, 42562, 42842, 44120, 44910, 45515, 45610, 45611, 45711, 45801, 45802, 46300, 46302, 43502, 43610, 45811, 45812, 45952, 46301, 46311, 46312 | Y |  |  |  | 14454 | 6669
5271 | FPP Bus Tie Upgrades | Add a second bus tie between LCRA TSC FPP 345-kV Yard #1 and Yard #2 with a minimum 1793 MVA rating. Upgrade T405 to a minimum rating of 1793 MVA. |  | FPP #1 | FPP #2 | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016189 | 2018-05-31 |  | 345 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  | 7055, 7056 | Y | N |  |  | 12947 | 5271
4445 | Kerrville Stadium to Harper Road Transmission Line Upgrade | Upgrade the 1.6 mile Kerrville Stadium (7138) - Harper Road (7140) 138-kV transmission line to bundled 795 ACSR Drake, 440 MVA. |  | Kerrville Stadium | Harper Road | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015115 | 2018-05-31 |  | 138 | 0 | 1.6 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  | 7138, 7140 | Y | N |  |  | 12008 | 4445
5919 | Fort Mason Substation Upgrade | Convert Fort Mason to entirely 138-kV. Upgrade terminal equipment on T21444 to 2000 Amps. Remove autotransformer. |  | Fort Mason | Mason | Planned | 5962 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017379 | 2018-05-31 | 2018-05-01 | 138 | 0 | 0 | 0 |  | Mason |  | Tier 4 |  |  |  | 76388, 76390, 6393 | Y | N |  |  | 13627 | 5919
5272 | Smithville - Winchester Line Overhaul | Rebuild T175 Smithville to Winchester with 795 ACSR (Drake) and OPGW. |  | Smithville | Winchester | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016207 | 2018-05-31 |  | 138 | 0 | 14.6 | 0 |  | Bastrop | Fayette | Tier 4 |  |  |  | 7306, 7314 | Y | N |  |  | 12948 | 5272
13TPIT0160 | Whitepoint: Add 138 kV breaker terminal for WF interconnect | Interconnect Midway Wind Farm at Whitepoint and construct a 138 kV breaker terminal |  | Whitepoint |  | Under Construction | 573-0750 | AEP TCC | Terry Weeks DNLYONS@AEP.COM 918-599-2698 | 3454 | 2018-05-31 |  | 138 |  |  |  |  | San Patricio |  | Tier 4 |  |  |  | 8961 | Y | N |  |  | 11151 | 3731
5921 | Cuero - Guadalupe Transmission Line Overhaul | Tear down and rebuild 28 structures from Cuero to Structure 238. The replacement conductor on this section of T542 will be 795 ACSR Drake, the line rating will not change. Add OPGW to the line section. |  | Cuero | Guadalupe | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016350 | 2018-05-31 |  | 69 | 0 | 3 | 0 |  | DeWitt | Guadalupe | Tier 4 |  |  |  | 78190, 78577 | Y | N |  |  | 13629 | 5921
3951 | TH Wharton to Fairbanks Ckt.81 | Reconductor 138kV Ckt.81 TH Wharton to Fairbanks and upgrade substation equipment at TH Wharton and Fairbanks to increase thermal ratings. | - Overall Date Update | TH Wharton | Fairbanks | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 995 | 2018-05-31 |  | 138 | 0 | 3.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45511, 45760 | Y | N |  |  | 11446 | 3951
5204 | Jourdanton to Pleasanton: 69 kV Transmission Line Rebuild | Rebuild 69 kV line from Jourdanton to Pleasanton. Install 2 x 7.2 MVAR Cap Bank at Jourdanton station |  | Jourdanton | Pleasanton | In-Service | 765-0950 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3573 | 2018-05-31 |  | 69 | 0 | 6 | 0 | 0,14.4 | Atascosa | Atascosa | Tier 4 |  |  |  | 8607, 8200 | Y | N |  |  | 12863 | 5204
5924 | Harwood - Waelder Transmission Line Overhaul | Upgrade T145 from Harwood to Waelder to 795 ACSR Drake conductor with minimum rating of 111 MVA at 69-kV and 221 MVA at 138-kV and add OPGW. Rate A=44, Rate B=44, Rate C=111. | Project Schedule Expedited | Harwood | Waelder | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017388 | 2018-05-31 |  | 138 | 0 | 12.5 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7223, 7230, 7231, 7232 | Y | N |  |  | 13632 | 5924
6315A | Distribution Cap Banks at Knight | Add 7.2 MVAr Distribution Capacitor Bank at Knight. |  | Knight |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 00:01 |  | 138 | 0 | 0 | 0 | 0,7.2 | Harris |  | Tier 4 |  |  |  | 47332 | Y | N |  | 0 | 43269 | 6315
6315B | Distribution Cap Banks at Knight | Add 7.2 MVAr Distribution Capacitor Bank at Pearland |  |  | Pearland | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 00:02 |  | 138 | 0 | 0 | 0 | 0,7.2 | Harris |  | Tier 4 |  |  |  | 43051 | Y | N |  | 0 | 43270 | 6315
6315C | Distribution Cap Banks at Knight | Add two 7.2 MVAr Distribution Capacitor Banks at Gulf Gate. |  | Gulf Gate |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 00:03 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  | 42742 | Y | N |  | 0 | 43271 | 6315
4706C | HO Clarke to Webster Ckt.05 | Reconfigure Southwyck TR1 to tap from Ckt.26 between Telview and Karsten. Upgrade Ckt.26 with partial reconductor. Southwyck TR2 & TR3 will continue to have loop service from Ckt.05. |  | Southwyck | Southwyck | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2018-05-31 00:03 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 43261, 43260, 42041, 44361, 44390, 44552, 47150 | Y |  |  | 0 | 43255 | 4706
4962 | Adding second 345/138 kV auto at Vealmoor station |  |  | Vealmoor 345 | Vealmoor 138 | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-06-01 |  | 345 | 0 | 0 | 708 |  | Borden | Borden | Tier 4 |  |  |  | 79602, 79640, 79600 | Y | N |  |  | 12595 | 4962
5131 | CPSE_Brooks to Chavaneaux Transmission Rebuild | Rebuild approximately 11 circuit miles of 138 kV transmission along the 410 corridor between Brooks and Chavaneaux. Included in the rebuild are segments of Harlandale to Sommers and Merida to Sommers 138 kV transmission lines. |  | Brooks/Sommers | Chavaneaux/Merida/Harlandale | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0230 | 2018-06-01 |  | 138 | 0 | 11 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5045, 5190, 5310, 5085, 5395 | Y | N |  |  | 12784 | 5131
5603 | Holbrook_to_Kirby_Rebuild | Rebuild 2.3 miles of 138 kV transmission line from Holbrook to Kirby. |  | Holbrook | Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0264 | 2018-06-01 |  | 138 | 0 | 2.3 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5005, 5160, 5218, 5250, 5420 | Y |  |  |  | 13333 | 5603
5683F | Line H Rebuild and 138kV conversion. | Construct Wickett 138 kV substation. Rebuild line from Wickett-Pyote (37981-38001). Build 138 kV line Oncor Wolf-TNMP Wickett (1013-37981). |  | 38001 | 1013 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2018-06-01 |  | 138 | 6.1 | 12.89 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 37981, 1013, 38001 | Y |  |  |  | 13748 | 5683
6161 | Las Cruces: Build new distribution station | Las Cruces: Build new distribution station |  | Laredo VFT North | Milo | Planned | 865 - 1043 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 3652 | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 8112, 8918, 80013 | Y | N |  |  | 13886 | 6161
5188 | Quaint Station: Build 69 kV station | Construct new 69 kV ring bus on the Abilene Northwest to Anson 69 kV Line | IN SERVICE | Quaint |  | In-Service | 753 - 0936 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2623 | 2018-06-05 | 2018-06-05 | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  | 6237, 6388, 6236, 6238, 6243, 6249 | Y | N |  |  | 12847 | 5188
7146 | Howard Lane Tie Upgrade | Upgrade the 138-kV Howard Lane tie line to bundle 2250 AAC. The planned tie line rating will be (MVA): Rate A=640, Rate B=710, Rate C=710. |  | Howard Lane | Howard Lane | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-06-27 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 7335, 9217 | Y | N |  |  | 14985 | 7146
5918 | Evant Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Evant Substation. |  | Evant |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017373 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Lampasas |  | Tier 4 |  |  |  | 7065 | Y | N |  |  | 13626 | 5918
5273 | Bergheim Substation Upgrade | Add a 345-kV bus and a 345/138-kV 336 MVA autotransformer at Bergheim Substation. | Construction schedule update | Bergheim |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016178 | 2018-06-30 |  | 345 | 0 | 0 | 336 |  | Comal |  | Tier 4 |  |  |  | 7770, 7771, 7043, 7046, 7170 | Y | N |  |  | 12949 | 5273
5912 | Bellville North Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Bellville North Substation. |  | Bellville North |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017342 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Austin |  | Tier 4 |  |  |  | 7287 | Y | N |  |  | 13620 | 5912
5928 | McElmurray Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at McElmurray Substation. |  | McElmurray |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017393 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  | 76319 | Y | N |  |  | 13636 | 5928
5910 | Butler Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Butler Substation. |  | Butler |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017345 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  | 7324 | Y | N |  |  | 13617 | 5910
5494 | Bus Differential Redundancy | Upgrade the 138-kV bus differential protection at Gillespie, North McCamey and Zorn Substations. |  | Zorn |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016182 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7180 | Y | N |  |  | 13232 | 5494
6097 | Amoco to Mustang Bayou Ckt.04 | Upgrade 138kV Ckt.04 Amoco to Mustang Bayou to increase thermal ratings. |  | Amoco | Mustang Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-06-30 |  | 138 | 0 | 7.5 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 42090, 42960 | Y | N |  |  | 13822 | 6097
5935 | Webberville Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Webberville (S470). |  | Webberville |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017412 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7329 | Y | N |  |  | 13643 | 5935
4710G | Jones Creek Project | Upgrade CORTEZ loop: Reconductor portions of Ckt.48 Velasco to MARINE to CORTEZ to Jones Creek. |  | Velasco | Jones Creek | Planned | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42540, 42542, 43155, 43360, 43440, 43362 | Y | N |  |  | 12303 | 4710
5180 | Add second circuit to SLU panhandle loop |  |  | Alibates | Tule Canyon | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-07-01 |  | 345 | 166 | 0 | 0 |  | Carson | Briscoe | Tier 1 |  |  |  | 79500, 79501, 79502, 79503, 79504 | Y | N |  |  | 12839 | 5180
5187 | Add 2nd Palmito Transfomer |  |  | Palmito | Loma Alta | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-07-01 |  | 345 | 0 | 0 | 450 |  | Cameron | Cameron | Tier 4 |  |  |  | 5962, 79652, 79690, 5966 | Y | N |  |  | 12846 | 5187
5683G | Line H Rebuild and 138kV conversion. | Install 69-138 kV Autotransformer at Wickett. |  | 37980 | 37981 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2018-07-23 |  | 138 | 0 | 0 | 150 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 37980, 37981 | Y |  |  |  | 13749 | 5683
6368 | Jacintoport Substation Upgrades | Upgrade equipment and transmission conductor at Jacintoport substation to increase thermal ratings |  | Jacintoport | BORDEN/EPOTH | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-07-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40860, 40210, 40290, 40520, 40410 | Y | N |  |  | 14112 | 6368
14TPIT0079 | Glen Rose to Meridian Rebuild NOMCR 54300 energized 8/1/2018 | Rebuild Glen Rose to Meridian with 795 ACSR, 138 kV construction (operate at 69 kV) |  | Glen Rose | Meridian | Planned |  | BEPC | Dwight Beckman kdye@brazoselectric.com 254-750-6373 | 15024 | 2018-08-01 |  | 69 | 0 | 18.18 | 0 |  | Somervell | Bosque | Tier 4 |  |  |  | 315, 319 | Y | N |  |  | 9485 | 2237
4761 | Trinidad - Jewett 138 kV Line | Upgrade Trinidad - Big Brown Tap line section |  | Trinidad | Big Brown Tap | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2004 | 2018-08-02 |  | 138 | 0 | 26.4 | 0 |  | Henderson | Leon | Tier 4 |  |  |  | 212, 3127, 3505 | Y | N |  |  | 12359 | 4761
5971 | Truscott Hmble T to Benjamin T 69 kV line: Rbld 69 kV line | Rehab Truscott Humble Tap to Benjamin Tap 69 kV line | Cost Update | Truscott Humble Tap | Benjamin Tap | Planned | 786 - 0971 | AEP TNC | Guillermo Taylor mlforcum@aep.com 918-599-2674 | 2660 | 2018-08-02 |  | 69 | 0 | 11.08 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 790, 6084, 6085, 6086, 6087 | Y | N |  |  | 13686 | 5971
5179 | Clear Crossing: Add 345 kV reactor | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley | Cost Update | Clear Crossing |  | Under Construction | 754 - 0937 | ETT | Steve Stein mlforcum@aep.com 918-599-2674 | 2626 | 2018-08-02 |  | 345 | 0 | 0 | 0 | -100,0 | Haskell |  | Tier 4 |  |  |  | 60515 | Y | N |  |  | 12838 | 5179
4751 | Lufkin Sw Sta - Crockett 138 kV Line | Rebuild existing line |  | Lufkin | Crockett | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6004 | 2018-08-02 |  | 138 | 0 | 42.9 | 0 |  | Angelina | Houston | Tier 3 | 2015-06-15 | 2015-08-15 |  | 3118, 3349, 3351, 3354 | Y | N |  |  | 12346 | 4751
5173 | Airline to Westside: Reconductor 138 kV line | Reconductor Airline to Westside |  | Airline | Westside | Under Construction | 746 - 0929 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2920 | 2018-08-02 |  | 138 | 0 | 6.1 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8485, 8490, 8882 | Y | N |  |  | 12832 | 5173
4241 | Texaco Mabee Tap - Texaco Mabee 138 kV Line | Rebuild existing line as a double-circuit line |  | Texaco Mabee Tap | Texaco Mabee | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8221 | 2018-08-02 |  | 138 | 11.4 | 11.4 | 0 |  | Midland | Andrews | Tier 4 |  |  |  | 1171, 1175, 1177, 1179, 11175, 1184, 11169, 11177, 11179 | Y | N |  |  | 11789 | 4241
5537 | Gila-Hwy9_ckt1: replace underground cable | Install new underground conduits and dielectric cable with 1300A normal/2150A emergency rating, below Corpus Ship channel, from Gila 138 kV station yard to cable terminal. |  | Gila | Cable Terminal | Under Construction | 790 - 0975 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3580 | 2018-08-02 | 2017-05-13 | 138 | 0 | 0.41 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8470, 80260 | Y | N |  |  | 13265 | 5537
5189 | Exxon Hawley Tap to Onyx Switch Station: Rebuild 69 kV line | Rebuild Hawley Tap to Onyx Switch Station |  | Hawley Tap | Onyx Switch Station | Planned | 753 - 0939 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2630 | 2018-08-02 |  | 69 | 0 | 6.57 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6236, 6238, 6388 | Y | N |  |  | 12848 | 5189
4548 | Yucca Drive Switching Station | Construct new switching station |  | Yucca Drive Switching Station |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8261 | 2018-08-02 |  | 138 | 0 | 0 | 300 |  | Ward |  | Tier 4 |  |  |  | 1001, 1015, 18110, 1009, 1010 | Y | N |  |  | 12125 | 4548
6092 | Port Aransas - Seawall 69 kV line rebuild | Rebuild ~8.1 miles of 69 kV line from Port Aransas to Seawall |  | Port Aransas | Seawall | Under Construction | 861-1039 | AEP TCC | Mark Strabala dnlyons@aep.com 918-599-2698 | 2698 | 2018-08-02 |  | 69 | 0 | 8.1 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8435, 8442 | Y | N |  |  | 13817 | 6092
5176 | Riley: Add 345 kV reactors | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley |  | Riley |  | Under Construction | 754 - 0937 | ETT | Steve Stein mlforcum@aep.com 918-599-2674 | 2627 | 2018-08-02 |  | 345 | 0 | 0 | 0 | -200,0 | Wilbarger |  | Tier 4 |  |  |  | 6101 | Y | N |  |  | 12835 | 5176
5542 | Gila-Hwy9_ckt2: replace underground cable | Gila-Hwy9 circuit 2: Install new underground conduits and dielectric cable with 1300A normal/2150A emergency rating, below Corpus ship channel, from Gila 138 kV station yard to cable terminal. Also, remove Gila-Morris St. 138 kV line from service and return Gila-Nueces Bay 138 kV line to service. |  | Gila | Cable Terminal | Under Construction | 791 - 0975 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3581 | 2018-08-02 | 2017-07-28 | 138 | 0 | 0.41 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8441, 8470, 8474, 80260 | Y | N |  |  | 13270 | 5542
4267 | Andrews County South - North Andrews 138 kV Line | Upgrade existing line |  | Andrews County South | North Andrews | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8235 | 2018-08-02 |  | 138 | 0 | 19 | 0 |  | Andrews | Andrews | Tier 3 | 2016-02-01 | 2016-05-01 |  | 1155, 1153, 1157, 1159 | Y | N |  |  | 11815 | 4267
1332 | Elm Mott - Waco West/Waco East 138 kV Line | Upgrade existing Elm Mott - Waco Northeast Tap line section |  | Elm Mott | Waco Northeast Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1719 | 2018-08-02 12:00 |  | 138 | 0 | 6.7 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  | 3407, 3550, 3551, 3575 | Y | N |  |  | 8511 | 1332
7046 | Pig Creek to County Road 101: Rebuild 138 kV line | Rebuild Solstice to Yucca Drive 138 kV line and add dynamic reactive devices at Lotebush | IN SERVICE | Pig Creek | County Road 101 | In-Service | 713 - 0946 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2737 | 2018-08-04 | 2018-08-04 | 138 | 0 | 13.411 | 0 |  | Reeves | Reeves | Tier 1 | 2015-12-15 | 2016-09-21 | 2016-10-26 | 6657, 6673, 60393 | Y | N |  |  | 14868 | 7046
43284A | Baytown Area Upgrades | Reconfigure Baytown to Miller |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-08-14 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40170, 41405, 41420 | Y |  |  | 0 | 43286 | 43284
5168 | Airline to Holly: Build new 138 kV line | Build new Airline to Holly 138 kV line by installing a second circuit on the existing Barney Davis to Holly 138 kV line |  | Airline | Holly | Under Construction | 745 - 0928 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2919 | 2018-08-17 |  | 138 | 1.7 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8486, 8490, 8517 | Y | N |  |  | 12910 | 5168
5145B | Rafter - New 138 kV Substation | Loop existing Rafter 138 kV substation into existing Castroville to Texas Research 138 kV transmission line. |  | RAFTER | CASTROVILLE/TX_RSCH | Planned | S-0837 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0261 | 2018-08-26 |  | 138 | 0.5 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 55355, 5083, 5355, 5430 | Y | N |  |  | 12799 | 5145
5913 | Colton Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Colton Substation. | Construction Schedule | Colton |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1017347 | 2018-08-30 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7208 | Y | N |  |  | 13621 | 5913
6387A | Greenville Arera System Enhancements | [6 empty] | RYBRN | Charles Gibune 214-678-1192 |  | 2018-08-30 | 2018-09-01 | 138 | 0 | 0 | 0 |  | Hunt |  | Tier 3 | 2015-12-15 | 2016-02-15 |  | 6883 | Y | N |  | 0 | 44051 | 6387
13TPIT0045 | Blumenthal Substation | Construct a new 11.5 mile 138 kV transmission line from a new station tap point on the Kendall CTEC - Mountain Top 138 kV transmission line named Maenius Road to the new Blumenthal substation using 336 ACSR Linnet. | CCN approved November 19, 2015 | Blumenthal | Kendall CTEC - Mountain Top | Planned |  | LCRATSC/CTEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1010656 | 2018-08-31 |  | 138 | 12.8 | 0 | 0 |  | Kendall | Gillespie | Tier 4 |  |  |  | 7418, 7419 | Y | N |  |  | 13618 | 990
6925 | Additional capacitors at Driver and Canal |  |  | 138 kV Driver | 138 kV Canal Rd | Planned |  | SHRY | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2018-09-01 |  | 138 | 0 | 0 | 0 | 0,48 | Midland | Upton | Tier 4 |  |  |  | 79612, 79624 | Y |  |  |  | 14743 | 6925
5941 | T-283 Quanex Switch to Quanex Substation | Replacement of wood poles from Quanex Switch to Quanex Substation. |  | Quanex Switch | Quanex | Under Construction |  | SBEC | Don Roberts droberts@sbec.org | WO# 17-6070 | 2018-09-01 | 2018-08-23 | 69 | 0 | 1.73 | 0 |  | Austin | Austin | Tier 4 |  |  |  | 7660, 7662 | Y | N |  |  | 13652 | 5941
4950B | Oyster Creek 138kV Substation - GINR - 16INR0003 | Build two 138 kV leads to LEVEE substation. |  | Oyster CReek | LEVEE | Planned | 4710 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 932 | 2018-09-02 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 43335, 111302 | Y | N |  | Cost is Included in 4950A Project. | 14160 | 4950
4538 | Add new 138kV line from Tall City to Glass Ranch |  |  | Tall City | Glass Ranch | Planned |  | CTT | Brad Schwarz 512-289-7425 |  | 2018-09-05 |  | 138 | 10 | 0 | 0 |  | Midland | Martin | Tier 2 |  |  |  | 79507, 79558 | Y | N |  |  | 12115 | 4538
5585 | West Edinburg loop in line | Loops the North Edinburg to Palmhurst line into West Edinburg |  | West Edinburg |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-09-07 | 2018-10-31 | 138 | 0.1 | 0 | 0 |  | Hidalgo |  | Tier 1 | 2015-07-01 | 2016-05-19 | 2016-06-01 | 5771, 5774, 8380 | Y | N |  | Part of AEPSC Hidalgo Starr transmission project | 13312 | 5585
7045 | County Road 101 to Yucca Drive: Rebuild 138 kV line | Rebuild Solstice to Yucca Drive 138 kV line and add dynamic reactive devices at Lotebush | IN SERVICE | County Road 101 | Yucca Drive | In-Service | 713 - 0946 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2738 | 2018-09-20 | 2018-09-20 | 138 | 0 | 8.889 | 0 |  | Reeves | Ward | Tier 1 | 2015-12-15 | 2016-09-21 | 2016-10-26 | 6656, 60392, 60397, 6657, 60415 | Y | N |  |  | 14867 | 7045
6583 | Del Sol-Cenizo: Create Temporary Tap | Install temporary tap on the Del Sol - Cenizo 345 kV line for the Rio Bravo windfarm temporary itnerconnection. The windfarm will build and own the gen-tie line from their collector station up to the tap point. The collector station name is CABEZON. |  | Del Sol | Cenizo | Planned | 895 - 1073 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3679 | 2018-09-21 |  | 345 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  | 80380, 80225, 80307 | Y | N |  |  | 14337 | 6583
6582 | Ajo-Zorillo: Create Temporary Tap | Create temporary tap on the Ajo-Zorillo 345 kV line for Stella Windfarm. |  | Ajo | Zorillo | Planned | 893 - 1071 | ETT | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3677 | 2018-09-21 |  | 345 | 0 | 0 | 0 |  | Kenedy |  | Tier 4 |  |  |  | 80070, 80071, 80076 | Y | N |  |  | 14336 | 6582
6394 | Bakersfield to Waymark: Build 345 kV line | Interconnect Waymark solar farm at Bakersfield | IN SERVICE | Bakersfield | Waymark | In-Service | 802 - 0987 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2655 | 2018-09-22 | 2018-09-22 | 345 | 5 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 60419, 76002 | Y | N |  |  | 14153 | 6394
6670 | Katy to Flewellen Ckt.09 | Upgrade Ckt.09 Katy to Flewellen to increase thermal ratings |  | Katy Tap | Flewellen | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-09-30 |  | 138 | 0 | 0 | 0 |  | Waller | Fort Bend | Tier 4 |  |  |  | 44230, 44420 | Y |  |  |  | 14473 | 6670
6311 | Obrien Auto A2 | Replace the failed 600MVA autotransformer 2A and existing 600MVA autotransformer 2B with a new 800MVA autotransformer A2 | - Delayed project schedule | Obrien |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-09-30 00:01 |  | 345 | 0 | 0 | 800 |  | Harris |  | Tier 4 |  |  |  | 44500, 44505, 44510, 44515, 49064, 49065, 44513 | Y | N |  |  | 14040 | 6311
6222 | DERICK - 138kV Customer-Owned Substation | Install 138kV DERICK customer-owned substation. Loop through Ckt.85 South Channel to Shell. |  | DERICK | South Channel/Shell | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-09-30 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41320, 40070, 40089, 40470, 40530, 41370, 41210, 41380, 41410, 41415, 41450, 41590 | Y | N |  |  | 13947 | 6222
4960 | Adding Nat Dam to Sales 17 miles 138 kV line |  |  | Sales Ranch | Natural Dam | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-10-01 |  | 138 | 17 | 0 | 0 |  | Martin | Howard | Tier 4 | 2015-06-29 | 2015-07-29 |  | 79508, 79509 | Y | N |  |  | 12593 | 4960
3887 | Relocate Hallettsville Auto to Nixon | Relocate 138/69 kV Auto at Hallettsville to LCRA Nixon, associated GCBs, Bus |  | LCRA Nixon |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-10-01 |  | 138 | 0 | 0 | 40 |  | Gonzales |  | Tier 1 | 2012-09-01 | 2012-10-31 | 2013-03-10 | 7585, 7617, 7246, 7621 | Y | N |  |  | 11352 | 3887

## CancelledTPIT100118NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2018
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
4252 | Eagle Mountain - Saginaw 138 kV Line | Upgrade existing double-circuit line | Scope and construction schedule change | Eagle Mountain | Saginaw | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5211 | 2019-05-15 |  | 138 | 0 | 27.9 | 0 |  | Tarrant | Tarrant | Tier 3 |  |  |  | 1860, 1864, 1957, 2065, 2066, 2067, 2070, 11860 | N | N |  |  | 11798 | 4252
4800 | Pleasant Valley - Wichita Falls Cogen 138 kV Line | Upgrade existing line |  | Pleasant Valley | Wichita Falls Cogen | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4002 | 2019-05-15 |  | 138 | 0 | 5.6 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  | 1450, 1498 | N | N |  |  | 12406 | 4800
4795 | Argyle Sw. Sta. - Spencer (TMPA) 138 kV Line | Upgrade Argyle Sw. Sta. - Corinth line section |  | Argyle Sw. Sta. | Corinth | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3202 | 2019-05-15 |  | 138 | 0 | 3 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 1984, 1985 | N | N |  |  | 12396 | 4795
5543 | Richland Hills 138 kV Switch | Rebuild the existing 138 kV Switching Station |  | Richland Hills | Richland Hills | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5240 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2099, 2100 | N | N |  |  | 13271 | 5543
5495 | Handley - Sherry 138 kV Line | Upgrade existing Hurst - Brookhollow 138 kV Line section |  | Hurst | Brookhollow | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5216 | 2019-05-18 |  | 138 | 0 | 9.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2116, 2121, 2134, 2244 | N | N |  |  | 13233 | 5495
5258 | Ft. Stockton: Add dynamic reactive device | Rebuild Solstice to Permian Basin 138 kV line and add dynamic reactive devices at Lotebush | CANCELLED | Ft. Stockton |  | Planned | 713 - 0946 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2637 | 2019-06-30 |  | 138 | 0 | 0 | 0 | -25100 | Pecos |  | Tier 1 | 2015-12-15 |  |  | 6630 | N | N |  |  | 12933 | 5258
13TPIT0198 | Seawillow Substation | Construct 138kV-12.5kV distribution substation Seawillow (7559) on T-184 Lockhart and Luling. |  | Seawillow | Luling / Lockhart | Planned |  | LCRATSC/BBEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013521 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  | 7559, 7216, 7224 | N | N |  |  | 9947 | 2648
6570 | Big Lake to Bison 69 kV line: Rebuild taps | Big Lake to Bison 69 kV line: Rebuild taps | CANCELLED | Big Lake | Bison | Planned | 892 - 1070 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2816 | 2019-12-31 |  | 69 | 0 | 1 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  | 6533, 6546, 6547, 60395 | N | N |  |  | 14321 | 6570
3900 | La Palma to Stewart Road: Rebuild 69 kV line | Rebuild La Palma to Stewart Road 69 kV line and add 138/69 kV autotransformer capacity at Stewart Road | Title, Description, and Schedule Update | La Palma | Stewart Road | Conceptual | 678 - 0847 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2597 | 2019-12-31 |  | 69 | 0 | 40.9 | 130 |  | Cameron | Hidalgo | Tier 3 |  |  |  | 8310, 8748, 8751, 8949, 8951 | N | N |  |  | 11370 | 3900
4787 | Venus - Sardis - Sterrett 138 kV Line | Upgrade existing line | Construction schedule change | Venus | Sterrett | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4203 | 2020-05-15 |  | 138 | 0 | 14.4 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  | 203, 1908, 2305, 2307, 2308, 2309, 2317 | N | N |  |  | 12387 | 4787
09TPIT0116 | Gatesville Tap - Gatesville TDC 69 kV line | Upgrade existing 69 kV line |  | Gatesville Tap | Gatesville TDC | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R497-WA | 2020-05-15 |  | 69 | 0 | 4.4 | 0 |  | McLennan | Coryell | Tier 4 |  |  |  | 3583, 3587 | N | N |  |  | 12358 | 466
4116 | FM-725 Substation | Build a new 138-26.18 kV, 40 MVA substation on the GVEC McQueeney(7606) - Schumansville(7609) 138 kV transmission line |  | FM 725 | McQueeney-Schumansville | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7725, 7606, 7609 | N | N |  |  | 11637 | 4116
5299 | Red Creek to Coke Street: Rebuild 138 kV line | Rebuild Red Creek to Coke Street 138 kV line | CANCELLED | Red Creek | Coke Street | Planned | 768 - 0953 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2639 | 2020-06-30 |  | 138 | 0 | 8.01 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6442, 6449 | N | N |  |  | 12975 | 5299
16TPIT0024 | Hamilton Road to Escondido: Rebuild 138kV Line | Rebuild Hamilton Road to Escondido 138 kV line | Reformated project number to match other numbers | Hamilton Road | Escondido | Conceptual | 602 - 0764 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3471 | 2020-12-31 |  | 138 | 0 | 53.7 | 0 |  | Val Verde | Maverick | Tier 3 |  |  |  | 8255, 8260, 8264, 8692 | N | N |  | 0 | 9830 | 2550
3777 | Ozona to Midway Lane: Rebuild 69 kV line | Rebuild Ozona to Midway Lane 69 kV line | CANCELLED | Ozona | Midway Lane | Planned | 667 - 0836 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2594 | 2020-12-31 |  | 69 | 0 | 16.96 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  | 6549, 6560 | N | N |  |  | 11197 | 3777
4841 | Rivercrest - Sulphur Springs Switch 138 kV Line | Upgrade existing line |  | Rivercrest | Sulphur Springs Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R980 | 2021-05-15 |  | 138 | 0 | 35.7 | 0 |  | Red River | Hopkins | Tier 3 |  |  |  | 6842, 1698, 1780, 1793, 1794, 1796, 1797, 11796, 1800, 11797 | N | N |  |  | 12443 | 4841
08TPIT0132 | Melon Creek to Tatton: Build 69 KV Line | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Melon Creek | Tatton | Conceptual | 100 - 0100 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2028 | 2022-03-31 |  | 69 | 9 | 0 | 0 |  | Refugio | Aransas | Tier 2 |  |  |  | 80066, 8410, 8800 | N | N |  |  | 8350 | 1172
5752 | City of Brady to Heartland: Build 69 kV line | Construct new 69 kV line from City of Brady to Heartland | CANCELLED | City of Brady | Heartland | Planned | 796 - 0981 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3587 | 2022-05-31 |  | 69 | 2 | 0 | 0 |  | McCulloch | McCulloch | Tier 2 |  |  |  | 6383, 60386 | N | N |  |  | 13492 | 5752
5544 | Lynx to Bakersfield: Build 345 kV line | Construct two new 345 kV stations, Lynx and Solstice, and new 345 kV lines from Lynx to Solstice and Lynx to Bakersfield | CANCELLED | Lynx | Bakersfield | Planned | 789 - 0974 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2652 | 2022-06-30 |  | 345 | 9 | 0 | 0 |  | Pecos | Pecos | Tier 1 | 2016-04-01 |  |  | 60401, 76002 | N | Y |  |  | 13272 | 5544
5538 | Lynx: Build a 345 kV station | Construct two new 345 kV stations, Lynx and Solstice, and new 345 kV lines from Lynx to Solstice and Lynx to Bakersfield | CANCELLED | Lynx |  | Planned | 789 - 0974 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2650 | 2022-06-30 |  | 345 | 0 | 0 | 743 | -50,0 | Pecos |  | Tier 1 | 2016-04-01 |  |  | 60401, 60403, 60400 | N | Y |  |  | 13266 | 5538
07TPIT0252 | Greta: Install 1-7.2 MVAR 69 kV Cap Bank | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Greta |  | Conceptual | 100 - 0100 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2045 | 2022-07-31 |  | 69 | 0 | 0 | 0 | 0,7.2 | Refugio |  | Tier 4 |  |  |  | 8409 | N | N |  |  | 8349 | 1171
11TPIT0036 | Caddo - New Substation | Construct a new 69-13.09x26.18-kV 10 MVA substation on GVEC La Vernia-GVEC Nixon 69 kV transmission line |  | Caddo | La Vernia/GVEC Nixon | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 69 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  | 7628, 7614, 7616 | N | N |  |  | 11635 | 3368
15TPIT0008 | Triple R - New Substation (7627) | Build a 138-26.18kV. 40 MVA substation on the GVEC Wilson-Sutherland Springs (T549) 138 kV transmission line |  | Triple R | Wilson/Sutherland Springs | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  | 7627, 5418, 7615 | N | N |  |  | 11634 | 3367
12TPIT0025 | Refugio - Tatton: Rebuild Irreparable 69 kV Line | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Refugio | Tatton | Conceptual | 100 - 0100 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2027 | 2022-12-30 |  | 69 | 0 | 12.6 | 0 |  | Refugio | Aransas | Tier 4 |  |  |  | 8410, 8800 | N | N |  |  | 8342 | 1164
5647 | Del Rio to Buena Vista, rebuild 138 kV line | Rebuild Del Rio to Buena Vista 138 kV line |  | Del Rio | Buena Vista | Conceptual |  | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2023-04-01 |  | 138 | 0 | 2.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  | 8690 | N | N |  |  | 13381 | 5647
5646 | Buena Vista to Picacho, rebuild 138 kV line | Rebuild Buena Vista to Picacho 138 kV line |  | Buena Vista | Picacho | Conceptual |  | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2023-08-01 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  | 8186 | N | N |  |  | 13380 | 5646
5645 | Hamilton Road to Picacho, rebuild 138 kV line | Rebuild Hamilton Road to Picacho 138 kV line |  | Hamilton Road | Picacho | Conceptual |  | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2024-06-01 |  | 138 | 0 | 8.8 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  | 8255, 8684 | N | N |  |  | 13379 | 5645

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2017-N1 | Kiamichi Energy Facility (140077) 345-kV reactors addition | KIOWA POWER PARTNERS LLC (RE) | 2020 |  |  |  | A mitigation plan has been identified to address this issue. The plan is currently implemented in Ercot Operations.
2017-N2 | Wichita Falls (1449) - Henrietta West (1543) - Lanham Tap 69kV line upgrades | Oncor | 2022
2017-N3 | Payne Switch (1758) - Anna Switch (2374) 138-kV line upgrades | Oncor | 2019 | 2019-05-15 | Planned | 17TPIT0024
2017-NC1 | Ranger Gulf (1627) -Thurber TNP (37850) 69-kV terminal equipment upgrade | TNMP/Oncor | 2019
2017-NC2 | Liggett Switch - Hackberry (2388) 138-kV double circuit line upgrade | Oncor | 2022 | 2020-05-15 | Planned | 5490
2017-NC3 | College (803)-Lawlert (815)-Jupiter (806) 69kV to 138kV line conversion and new 345 KV station additions. | Garland/Oncor | 2019
2017-NC4 | Olsen (37470) - Clifton (37600) - Walnut Spring 69-kV terminal equipment upgrade | TNMP | 2019
2017-NC5 | Allen Switch (2509) - Plano Custer Road (2525) 138-kV line upgrade | Oncor | 2019
2017-NC6 | Roanoke Switch (1854,1852) - Park Vista (15101,15100) 138-kV line upgrades | Oncor | 2019
2017-NC7 | Watermill Switch (2430) - Witt Road (3068) 138-kV line upgrade | Oncor | 2019
2017-NC8 | Plano West (2673,2680) - Richardson Alcatel (2685) - Richardson Spring (2689) 138-kV line upgrades | Oncor | 2019
2017-NC9 | Add a Capacitor Bank of minimum 112.5 MVAr at Heritage(559) | BREC | 2019
2017-NC10 | Wagley Robertson (2076) - Blue Mound (2071) 138-kV line upgrade | Oncor | 2019 | 2018-12-15 | Planned | 6779
2017-NC11 | Weatherford West Switch (1585) - Weatherford East (1586,1587) - Hilltop (506) 69-kV line upgrade | Oncor/BEPC | 2020
2017-NC12 | Wichita Falls (1449) - Wichita Falls Basin Tap (1508) 69-kV line upgrade | Oncor | 2023
2017-NC13 | Collins Switch (2372-2370) 345/138-kV transformer #2 reactor addition | Oncor | 2022
2017-NC14 | Richardson Spring Creek (2689) to Richardson East (2690) 138-kV line upgrade | Oncor | 2022
2017-NC15 | Add a Capacitor Bank of minimum 120 MVAr at LookOut (828) | Garland | 2020
2017-NC16 | Cedar Hill (2422) - Eagle Ford (3049) - Sorcey Road (3050) - Duncanville South (3052) 138-kV line upgrades | Oncor | 2019 | 2020-05-15 | Planned | 7026
2017-NC 17 | Highlands TNP (1974) - Argyle (1984) 138-kV line upgrade | Oncor | 2022
2017-NC 18 | Industrial (2976) - West Network (2875) - East Levee (2482) 138-kV line upgrades | Oncor | 2020
2017-NC19 | Liggett 345/138-kV transformers #1 and #2 series reactors | Oncor | 2020
2017-NC20 | Sargent Road (2941,2947,2940) - St Augustine (2951) - Southerland (2973) 138-kV line upgrades | Oncor | 2020
2017-NC21 | Rebuild existing Plano Tennyson 345/138 kV switching station (2522). | Oncor | 2022
2017-NC22 | Hicks Switch (2082) - Alliance (1855) - Roanoke (1854) 138-kV lines extension | Oncor | 2023 | 2022-05-15 | Planned | 6360
2017-NC23 | Bosque Switch (252) - Olsen TNP (37460) 138-kV line terminal equipment upgrade | TNMP | 2019
2017-NC 24 | Cedar Crist Switch(2493) - Dealey Street Switch(2842) 138-kV line upgrade | Oncor | 2019
2017-NC 25 | Everman Switch(1883) - Forest Hill Switch(1967) - Alcon Tap (2194) 138-kV line upgrade | Oncor | 2019
2017-NC 26 | Cooper Creek(906) - Arco(1993)138-kV line upgrade | TTMPA,TDME | 2019
2017-NC 27 | McCree(834) - Crist(850) - Ben Davis(968) 138-kV line upgrade | TTMPA | 2019 | 2020-05-01 10:00 | Planned | 43623
2017-NC 28 | Ben Davis 345/138-kV auto #2 upgrade | TTMPA | 2019 | 2020-12-01 10:00 | Planned | 6874
2017-NC 29 | Norwood Switch (2404) to Norwood Switch(2405) 138 -kV bus tie upgrade | Oncor | 2019
2017-NC 30 | Desoto Switch(2424) - Glenn Heights (2426) 138-kV line upgrade | Oncor | 2019
2017-NC 31 | Mesquite Forney Road (2752)-Thorne(12747)-Thornton East Tap(2747) 138-kV line upgrade | Oncor | 2020
2017-NC32 | Randol Mill Tap East (2104) to Randol Mill(2106) 138-kV line upgrade | Oncor | 2020
2017-NC34 | South Royse (2478) 345/138-kV transformer addition and line extensions | Oncor | 2022 | 2020-05-15 | Planned | 5524
2017-C1 | Grant Avenue TNP (39400) - Arco Pipeline TNP (39410) 69-kV line upgrade | TNMP | 2019
2017-C2 | Add a Capacitor Bank of minimum 50 MVAr at Plaza 138-kV substation | CNP | 2019 | 2018-05-31 00:01 | Planned | 6315
2017-C3 | Dunlavy (47580) - Heights (47680) 69-kV line upgrade | CNP | 2022 | 2020-05-31 | Planned | 6573
2017-C4 | New line from Villick (44270) - Tanner (46311) 138-kV line | CNP | 2022 | 2018-09-30 | Planned | 6670
2017-C5 | Jones Creek (42530) area bridge the gap upgrades | CNP | 2020 | 2019-05-29 | BOD Approved | 6673
2017-C7 | New Copper (42215) - Jones Creek (42541) 138-kV line | CNP | 2019 | 2019-03-30 | Planned | 6314
2017-C8 | SR Bertron (41400) - Alexander Island (41392) - Dowlap (40490) - Russel (40125) 138-kV line upgrade | CNP | 2019 | 2019-05-30 | Planned | 4426
2017-C9 | Add 4th 345/138-kV transformer at PH Robinson (42000) | CNP | 2023 | 2018-12-30 00:01 | Planned | 6312
2017-C10 | Add 6th 345/138-kV transformer at Dow Chemical (42500) | DOW | 2019
2017-FW1 | Big Lake - Bison -Midway 69kV line upgrade | AEP | 2019
2017-W1 | Hamilton Road (8255) - Del Rio City (8690) 138-kV line rebuild | AEP | 2022
2017-W2 | Picacho (8684) - Buena Vista (8688) 138-kV line rebuild | AEP | 2022
2017-W3 | San Angelo Power Station (6480) – Schkade (76320) 138-kV line terminal equipment upgrade | LCRA/AEP | 2019 | 2019-04-01 | Planned | 6568
2017-S1 | Holly (8486) - Holly (8517) 138-kV bus tie upgrade | AEP/STEC | 2019 | 2018-08-17 | Planned | 5168
2017-S2 | Azteca Sub (8708) - SE Edinburg (8374) - Pharr (5762) and North Edinburg (8380) - McColl Road (8908) 138-kV terminal equipment upgrade | AEP | 2019
2017-S3 | Melon Creek substation and transformer addition and 69-kV line rebuild | AEP | 2019
2017-S4 | Escondido (8260) - Eagle Pass (8270) 138-kV line upgrade | AEP | 2019
2017-S6 | North McAllen (8368) - North Edinburg (8380) 138-kV line upgrade | AEP | 2023
2017-S7 | Charlotte (8206) - Dilley2 (8208) 69-kV line upgrade | AEP | 2023
2017-S8 | Add 345/138-kV transformer at Fowlerton (5709) | STEC | 2019 | 2020-06-01 | Planned | 3894
2017-S9 | North McAllen (8368) - West McAllen (8367) - South McAllen (8371) 138-kV line upgrades | AEP | 2019 | 2020-06-30 | Planned | 5621
2017-SC1 | Gay Hill (7572) - Lyons (7573) 138-kV line rebuild | LCRA/BBEC | 2023 | 2021-05-31 | Planned | 5939
2017-SC2 | -Fayette Plant 138 (7278) - Weimar (7254) 138-kV line addition. -Fayette Plant 138 (7278) - Fayette River Pump (7280) 138-kV line terminal upgrade -Fayette Plant 138 (7278) - Fayetteville (7286) 138-kV line rebuild | LCRA | 2022 | 2020-05-31 | Planned | 5286
2017-SC3 | Wirtz (7104) - Johnson City (7516) - Blanco Tap (7514) - Mountain Top (7480) 138-kV line rebuilds | LCRA/PDECO | 2023 | 2019-12-01 | Planned | 6789

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Bob Healey; Cindy Miller | bhealey@aep.com; Camiller2@aep.com | Bob Healey: 918 599 2249; Cindy Miller: 918 599 2891 | Glen Reed; David Kidd; Brad Myers; Mabel See; Mike Forcum; Doug Lee; Daniel Lyons; Bob Lager; Mina Turner; Lisa Kelso; Carole Myser | gareed@aep.com; dekidd@aep.com; blmyers@aep.com; msee@aep.com; mlforcum@aep.com; dnlyons@aep.com; dlee@aep.com; rjlager@aep.com; myturner@aep.com; lokelso@aep.com; camyser@aep.com | David Kidd: 918 599 2637 Glen Reed: 918 599 2664 Brad Myers: 918 599 2690
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Hunt, Dandy; Ron Krautz; Brion Ryan | dandy.hunt@austinenergy.com; ron.krautz@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | Reza:512 322 6740 Dandy:512 322 6748 Ron:512 322 6835 Brion: 512-322-6879
BPUB | Primary | Ramon Sanz | rsanz@brownsville-pub.com; | Ramon: 956 983 6203 | James McCann | jmccann@brownsville-pub.com; | James: 956 983 6204
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Dwight Beckman | dbeckman@brazoselectric.com | Dwight: 254 750 6373 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | James Tanneberger | jtanneberger@btutilities.com | James: 979 821 5763 | Shawndra Green | sgreen@btutilities.com | Shawndra: 979 821 5744
CNP | Primary & Secondary | Wesley Woitt | wesley.woitt@centerpointenergy.com | Wesley Woitt: 713-207-2760 | Yingying Huang; Raja Sekhar Kakarla; Cody Mann | Yingying.Huang@centerpointenergy.com; rajasekhar.kakarla@centerpointenergy.com; cody.mann@centerpointenergy.com | Yingying Huang: 713-207-2831 Raja Sekhar Kakarla: 713-207-3614 Cody Mann: 713-207-3149
COCS | Primary | Tony Michalsky | tmichalsky@cstx.gov; | Tony: 979 764 3438 | Timothy Crabb, Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | Basileo Rocha, Sunil Dhakal | bdrocha@cpsenergy.com; SDhakal@cpsenergy.com | Basileo: 210 353 4933 Sunil: 210 353 2008 | Kenneth Bowen Trieu Vo | kbowen@cpsenergy.com; tvo@cpsenergy.com; | Kenneth: 210 353 4142 Trieu: 210 353 2127
CTT (Cross Texas Transmission) | Primary & Secondary | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310 | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310
DENTON | Primary & Secondary | Chuck Sears | Chuck.Sears@cityofdenton.com; | Chuck: 940 349 7111 | Brent Heath | brent.heath@cityofdenton.com; | Brent: 940 349 7180
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Grubbs, David; Juan Santos | Dgrubbs@gpltexas.org; Jsantos@gpltexas.org | David: 972 205 2664 Juan: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; BEC (Bandera); BBEC; CTEC; GVEC; NBU; PEC; SBEC; RGEC | Primary & Secondary | Charles DeWitt | Charles.dewitt@lcra.org | Charlie: 512-578-4199 | Cris Urena, Ken Chui | cris.urena@lcra.org; ken.chui@lcra.org | Cris: 512 578 4525, Ken: 512 578 4510
Lone Star | Primary & Secondary | Chenyan Guo | chenyan.guo@fpl.com | Chenyan: 561-304-5692 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Charles Saker | charles.saker@oncor.com | Charles: 214-743-6896 | Paul Bell | paul.bell@oncor.com | Paul: 214-743-6676
Sharyland Utilities | Primary & Secondary | Brad Schwarz | bschwarz@huntpower.com | Brad: 512-289-7425 | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243
STEC | Primary & Secondary | Doug Evans | devans@stec.org | Doug: 361 485 6459 | Paul Person Loretta Gallaga | pperson@stec.org; lgallaga@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Ahmad Saboor | asaboor@texasmpa.org | Ahmad: 936 873 1104 | Frank Owens | fowens@texasmpa.org; | Frank: 936 873 1120
TNMP | Primary & Secondary | Robert Lona | Robert.Lona@tnmp.com | Robert: 281-581-4732 | Anthony, Hudson Ballay, Dustin Cloninger, Ross | Anthony.Hudson@tnmp.com; Dustin.Ballay@tnmp.com; Ross.Cloninger@tnmp.com; | Anthony: 281 581 4712 Dustin:281 581 4730 Ross:281 581 4733
Wind Energy Texas Transmission (WETT) | Primary | Julius Horvath | julius.horvath@windenergyoftexas.com | Julius: 512 436 9585; cell: 512 496 9186 | Christina Minchew | christina.Minchew@windenergyoftexas.com | Christina: 512-436-9469