## ImprovementCostSummary02012014
| Project Cost | [5 empty] | XFMR MVA
| 345 | 138 | 69 | Total |  |  | 345 | 138 | 69 | Total
2013 | 4966382303 | 428852942 | 132190847 | 5527426092 |  | 2013 | 4822 | 323 | 150 | 5295 |  | For ROS and BOD reports
2014 | 250180655 | 552166083 | 229007851 | 1031354589 | 6558780681 | 2014 | 2972 | 667 | 0 | 3639 | 8934
2015 | 127924922 | 583760305 | 213560187 | 925245414 |  | 2015 | 2800 | 1442 | 180 | 4422 |  | ·All Projects (in engineering, routing, licensing and construction) |  |  |  | 4425167792
2016 | 741094000 | 618844244 | 52489000 | 1412427244 |  | 2016 | 3000 | 390 | 0 | 3390
2017 | 75890000 | 319310951 | 40725000 | 435925951 |  | 2017 | 3400 | 595 | 0 | 3995 |  | ·Transmission Projects Energized in 201 |  |  |  | 123328572
2018 | 0 | 127992248 | 17500000 | 145492248 |  | 2018 | 0 | 0 | 0 | 0
2019 | 0 | 14250000 | 10000000 | 24250000 |  | 2019 | 0 | 0 | 0 | 0
2020+ | 223423294 | 288136681 | 62240943 | 573800918 | 3517141775 | 2020+ | 4300 | 470 | 0 | 4770 | 16577
2014COM | 0 | 69708572 | 53620000 | 123328572 |  | 2014COM | 0 | 0 | 0 | 0
2014PLAN | 250180655 | 482457511 | 175387851 | 908026017 |  | 2014PLAN | 2972 | 667 | 0 | 3639
2013-2020+ | 6384895174 | 2933313454 | 757713828 | 10075922456 |  | 2013-2020+ | 21294 | 3887 | 330 | 25511
2013-2014 | 5216562958 | 981019025 | 361198698 | 6558780681 |  | 2013-2014 | 7794 | 990 | 150 | 8934
2015-2020+ | 1168332216 | 1952294429 | 396515130 | 3517141775 |  | 2015-2020+ | 13500 | 2897 | 180 | 16577
| Circuit Miles New | [5 empty] | Circuit Miles Rebuilt, Reconductored or Upgraded |  |  |  |  | Total
| 345 | 138 | 69 | Total |  |  | 345 | 138 | 69 | total |  | 345 | 138 | 69 | total
2013 | 3615.3 | 127.68 | 0 | 3742.98 |  | 2013 | 83.295 | 259.44 | 129.04 | 471.775 |  | 3698.595 | 387.12 | 129.04
2014 | 6.9 | 107.67 | 0.52 | 115.09 | 3858.07 | 2014 | 80.7 | 414.59 | 156.15 | 651.44 | 1123.215 | 87.6 | 522.26 | 156.67
2015 | 0 | 121.6 | 0 | 121.6 |  | 2015 | 0 | 502.49 | 170.02 | 672.51 |  | 0 | 624.09 | 170.02
2016 | 281.5 | 188.4 | 0 | 469.9 |  | 2016 | 143.69 | 352.77 | 67.7 | 564.16 |  | 425.19 | 541.17 | 67.7
2017 | 0 | 50.44 | 32 | 82.44 |  | 2017 | 52 | 215.3 | 8.75 | 276.05 |  | 52 | 265.74 | 40.75
2018 | 0 | 16.2 | 0 | 16.2 |  | 2018 | 0 | 51.4 | 17.01 | 68.41 |  | 0 | 67.6 | 17.01
2019 | 0 | 0 | 0 | 0 |  | 2019 | 0 | 7.6 | 10 | 17.6 |  | 0 | 7.6 | 10
2020+ | 125.8 | 99.9 | 9 | 234.7 | 924.84 | 2020+ | 94.6 | 128.1 | 82.71 | 305.41 | 1904.14 | 220.4 | 228 | 91.71
2014COM | 0 | 0.2 | 0 | 0.2 |  | 2014COM | 0 | 72.8 | 15.5 | 88.3 |  | 0 | 73 | 15.5
2014PLAN | 6.9 | 107.47 | 0.52 | 114.89 |  | 2014PLAN | 80.7 | 341.79 | 140.65 | 563.14 |  | 87.6 | 449.26 | 141.17
2013-2020+ | 4036.4 | 819.56 | 42.04 | 4898 |  | 2013-2020+ | 454.285 | 1931.69 | 641.38 | 3027.355 |  | 4490.685 | 2751.25 | 683.42
2013-2014 | 3622.2 | 235.35 | 0.52 | 3858.07 |  | 2013-2014 | 163.995 | 674.03 | 285.19 | 1123.215
2015-2020+ | 407.3 | 476.54 | 41 | 924.84 |  | 2015-2020+ | 290.29 | 1257.66 | 356.19 | 1904.14

## FutureTPIT020114NoCost
PRIVILEGED AND CONFIDENTIAL, DO NOT release outside of ERCOT Staff or Transmission Providers organization. Contains critical cost information that can affect bids for projects.
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/01/2014
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
00TPIT0004 | DeCordova - Benbrook 345 kV line upgrade | Upgrade existing 345 kV line |  | DeCordova | Benbrook | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5034-E | 2021-05-15 |  | 345 | 0 | 27 | 0 |  | Hood | Tarrant | Tier 4 |  |  |  |  | N | N |  |  | 3243 | 3074
05TPIT0065 | Highway 32-Wimberley | Construct a new 795 ACSR (220-MVA) 138-kV double circuit transmission line (approximately four miles) between the Highway 32(7546) and Wimberley(7496) substations. |  | Highway 32 | Wimberley | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2014-12-31 |  | 138 | 4 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  | 7496, 7545, 7546 | Y | N |  |  | 998 | 997
05TPIT0072 | Mountain Top-Blanco-Devil's Hill | Close the 69-kV switch (SW 458) at the Blanco substation (7482) to loop the load located at the Blanco substation. Upgrade the capacity of the 138-69-kV auto-transformer (T2) at the Devil's Hill substation (7493) from 20-MVA to 45-MVA. | Devil's Hill Auto Installed. Construction for Blanco bus to close Loop not scheduled to complete until July 2013. Material delivery delaying energization to Dec 2014. | Mountain Top | Devil's Hill | Under Construction |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 | 1005443 | 2014-02-28 |  | 138 | 0 | 0 | 45 |  | Blanco | Comal | Tier 4 |  |  |  | 7482, 7484 | Y | N |  |  | 3709 | 3502
06TPIT0036 | Ennis Switch - Ennis 138 kV line | Upgrade existing 138 kV line |  | Ennis Switch | Ennis | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M280-E | 2023-05-15 |  | 138 | 0 | 6.3 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | N | N |  |  | 3273 | 3104
06TPIT0042 | Lake Wichita Switch - Wichita Falls Switch 69 kV line | Upgrade existing 69 kV line |  | Lake Wichita Switch | Wichitia Falls Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R933-E | 2016-05-15 |  | 138 | 0 | 6.3 | 0 |  | Archer | Wichita | Tier 4 |  |  |  | 1447, 1449 | Y | N |  |  | 3390 | 3217
06TPIT0043 | Sherry - Liggett 138 kV line and Liggett - International Air | Upgrade 138 kV line | Construction schedule change | Sherry | Liggett | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5042-WA | 2015-05-15 |  | 138 | 0 | 13 | 0 |  | Tarrant | Dallas | Tier 4 |  |  |  | 1922, 1924, 2124, 2128, 2133, 2137, 2125, 2140, 2141 | Y | N |  | Sherry - GM section was completed in 2009. | 2777 | 2653
06TPIT0047 | Elkton - Tyler West 138 kV line | Upgrade existing 138 kV line |  | Elkton | Tyler West | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6023-E | 2016-05-15 |  | 138 | 0 | 4 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3106, 3139 | Y | N |  |  | 1434 | 1433
06TPIT0068 | Hamilton Road to Picacho, reconductor 138 kV line | Reconductor Del Rio 138 kV System | CHANGES | HAMILTON ROAD | PICACHO | CONCEPTUAL | 301-0449 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 |  | 2016-05-31 |  | 138 | 0 | 8.76 | 0 |  | Val Verde | Val Verde | Tier 1 | 2016-01-01 | 2016-08-01 | 2016-08-01 | 8255, 8684 | Y | N | NA | NA | 3742 | 3535
06TPIT0082 | Buena Vista to Picacho, reconductor 138 kV line | Reconductor Del Rio 138 kV System | CHANGES | BUENA VISTA | PICACHO | PLANNED | 301-0449 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 |  | 2020-06-30 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8688 | Y | N | NA | NA | 3745 | 3537
06TPIT0083 | Del Rio to Buena Vista, reconductor 138 kV line | Reconductor Del Rio 138 kV System | CHANGES | DEL RIO | BUENA VISTA | PLANNED | 301-0449 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 |  | 2020-05-30 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8690 | Y | N | NA | NA | 3748 | 3540
06TPIT0084 | Hamilton Road to Del Rio reconductor 138 kV line | Reconductor Del Rio 138 kV System | CHANGES | HAMILTON ROAD | DEL RIO | CONCEPTUAL | 301-0449 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 |  | 2020-04-20 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8255 | Y | N | NA | NA | 3749 | 3541
06TPIT0092 | Wichita Falls Switch - Wichita Falls North 69 kV line | Upgrade existing 69 kV line |  | Wichita Falls Switch | Wichita Falls North | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R168A-E | 2022-05-15 |  | 69 | 0 | 3.6 | 0 |  | Archer | Wichita | Tier 4 |  |  |  |  | N | N |  |  | 3755 | 3198
07TPIT0001 | Liggett - Trinity Switch 345 kV line | Construct Liggett - Trinity 345 kV line | Studies indicate timing of project should be changed | Liggett | Trinity Switch | Conceptual | M5014-E | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5015-E | 2021-12-15 |  | 345 | 12.8 | 0 | 0 |  | Dallas | Tarrant | Tier 2 |  |  |  |  | N | N |  |  | 3244 | 3075
07TPIT0002 | Trinity Switch 345/138 kV autotransformer | Create Trinity Switch and install a 600 MVA 345/138 kV autotransformer |  | Trinity Switch |  | Conceptual | M5015-E | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5014-E | 2021-12-15 |  | 345 | 0 | 0 | 600 |  | Tarrant |  | Tier 4 |  |  |  |  | N | N |  |  | 3245 | 3076
07TPIT0012 | Trinity Switch - Richland 138 kV line | Upgrade existing 138 kV line |  | Trinity Switch | Richland | Conceptual | M5014-E | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5069-E | 2021-12-15 |  | 138 | 0 | 0.5 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | N | N |  |  | 3246 | 3077
07TPIT0014 | Plano West - Richardson Tap 138 kV line | Upgrade existing 138 kV line |  | Plano West | Richardson Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M364-E | 2024-05-15 |  | 138 | 0 | 1.9 | 0 |  | Collin | Dallas | Tier 4 |  |  |  |  | N | N |  |  | 3371 | 3200
07TPIT0017 | Handley - Hurst 138 kV line | Reconductor existing 138 kV line |  | Handley | Hurst | Under construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M572-WAC | 2014-05-15 |  | 138 | 0 | 18.7 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1950, 1951, 2109, 2110, 2113, 2114, 2115, 2116 | Y | N |  | Interim rating increase was implemented in May 2012. | 3108 | 2939
07TPIT0050 | Dunlap to Techridge 138kV Circuit Relocation | This project will reroute the existing Ckt 975 Dunlap-Techridge from near the intersection of Howard Lane and Dessau Road to the Techridge substation. The reroute will use 3000 amp bundled 795 ACSS Drake conductor. |  | Dunlap Substation | Techridge Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | PLAN_117_P071 | 2016-06-01 |  | 138 | 0 | 2.7 | 0 |  | Travis | Travis | Tier 2 | 2009-01-26 | 2009-06-01 |  | 9045, 9190 | Y | N |  |  | 1014 | 1013
07TPIT0060 | Howard Lane to Techridge Reconductor | The project re-conductors Circuit 1004 (Techridge to Howard Lane) using 795 ACSS Drake conductors to increase the capacity to 3000 Amp. |  | Howard Lane Substation | Techridge Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | PLAN_117_P067 PLAN_117_P194 | 2016-06-15 |  | 138 | 0 | 1.72 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9190, 9217 | Y | N |  |  | 1029 | 1028
07TPIT0069 | Sterrett - Sardis 138 kV line | Upgrade existing 138 kV line |  | Sterrett | Sardis | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M361-E | 2022-05-15 |  | 138 | 0 | 2 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | N | N |  |  | 3271 | 3102
07TPIT0073 | Venus - Webb 345 kV line | Upgrade existing 345 kV line |  | Venus | Webb | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5098-E | 2024-05-15 |  | 345 | 0 | 11.3 | 0 |  | Ellis | Dallas | Tier 4 |  |  |  |  | N | N |  |  | 3278 | 3109
07TPIT0077 | Big Foot to Devine: Rebuild 69 kV Line | Add CPS Lytle to ETT Lytle 795 ACSR 138 kV line and 93 MVA 69-138 kV autotransformer at Lytle |  | Big Foot | Devine | UnderConstruction | 028 - 0028 | AEP TCC | Terry Weeks 918-599-2664 | 1777 | 2014-05-01 |  | 69 | 0 | 6.13 | 0 |  | Frio | Medina | Tier 4 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8223, 8218 | Y | N |  |  | 1255 | 1252
07TPIT0083 | Picacho to CFE, construct new 138 kV line | Convert Amistad to CFE Amistad 12.5 kV distribution to 138 kV line | CHANGES | PICACHO | CFE | CONCEPTUAL | 301-0449 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 | TP2007094 | 2020-06-30 |  | 138 | 8.8 | 0 | 0 |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8684 | N | N | NA | NA | 3750 | 3542
07TPIT0115 | Elgin Switch - Taylor 138 kV line | Upgrade existing 138 kV line |  | Elgiin Switch | Taylor | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R026-E | 2023-05-15 |  | 138 | 0 | 11.4 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  | 3650, 3658 | N | N |  |  | 1344 | 1340
07TPIT0116 | Handley - Duval 69 kV line | Upgrade existing 69 kV line |  | Handley | Duval | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5116-E | 2015-05-15 |  | 69 | 0 | 5.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1952, 2158 | Y | N |  |  | 2779 | 2655
07TPIT0118 | Lavon 345/138 kV Switching Station | Construct 345/138 kV switching station |  | Lavon Switch |  | Conceptual | M375B, M375C | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M375A-E | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Collin |  | Tier 4 |  |  |  |  | N | N |  |  | 3362 | 3191
07TPIT0119 | Lavon Switch - Allen Switch 138 kV line | Create a new 138 kV line by reconfiguring existing lines and adding circuit to existing structures |  | Lavon Switch | Allen Switch | Conceptual | M375A | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M375B-E | 2023-05-15 |  | 138 | 8.9 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | N | N |  |  | 3364 | 3193
07TPIT0122 | Royse - Dalrock 138 kV line | Upgrade existing 138 kV line |  | Royse | Dalrock | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3035-E | 2023-05-15 |  | 138 | 0 | 6.8 | 0 |  | Rockwall | Rockwall | Tier 4 |  |  |  |  | N | N |  |  | 3274 | 3105
07TPIT0126 | Tri Corner - Seagoville Switch 345 kV line | Upgrade existing 345 kV line |  | Tri Corner | Seagoville Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4044-WAC | 2014-05-15 |  | 345 | 0 | 9.4 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2432, 2433 | Y | N |  |  | 1823 | 1781
07TPIT0138 | Oates (GPL) - Garland Bobtown Tap 138 kV line | Upgrade existing 138 kV line |  | Oats (GPL) | Garland Bobtown Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M322-E | 2023-05-15 |  | 138 | 0 | 1.5 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | N | N |  |  | 3276 | 3107
07TPIT0140 | Trinidad - Tri Corner - Watermill 345 kV line | Upgrade existing 345 kV line |  | Trinidad | Watermill | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4045-E | 2017-05-15 |  | 345 | 0 | 52 | 0 |  | Henderson | Dallas | Tier 3 |  |  |  | 2427, 2432, 3123, 3124 | Y | N |  |  | 1824 | 1782
07TPIT0210 | Hilltop - White Settlement 69 kV line | Rebuild 4/0 ACSR section of line |  | Hilltop | White Settlement | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5135-E | 2016-05-15 |  | 69 | 0 | 14.3 | 0 |  | Parker | Tarrant | Tier 4 |  |  |  | 506, 2089 | Y | N |  |  | 2685 | 2569
07TPIT0234 | Collin Switch - NW. Carrollton 345 kV line | Upgrade existing 345 kV line |  | Collin Switch | NW. Carrollton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3061-E | 2022-05-15 |  | 345 | 0 | 19.3 | 0 |  | Collin | Dallas | Tier 4 | 2006-10-01 | 2007-02-01 |  |  | N | N |  | The ERCOT Staff determined this project is not economically justified in their February 2007 study. | 3363 | 3192
07TPIT0236 | N. Terrell Tap - Rose Hill 138 kV line | Rebuild existing line |  | N. Terrell Tap | Rose Hill | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3059-E | 2017-12-15 |  | 138 | 0 | 8.7 | 0 |  | Kaufman | Kaufman | Tier 4 |  |  |  | 2714, 2715, 2717, 2719, 2723 | Y | N |  |  | 3100 | 2925
07TPIT0252 | Greta: Install 1-7.2 MVAR 69 kV Cap Bank | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Greta |  | Conceptual | 100 - 0100 | AEP TCC | Glen Reed 918-599-2664 | 2045 | 2020-07-31 |  | 69 | 0 | 0 | 0 | 0,7.2 | Refugio |  | Tier 4 |  |  |  | 8409 | Y | N |  |  | 1174 | 1171
08TPIT0007 | Austin Ranch - Hebron 138 kV line | Upgrade existing 138 kV line |  | Austin Ranch | Hebron | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3002-E | 2023-12-15 |  | 138 | 0 | 0.7 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | N | N |  |  | 3366 | 3195
08TPIT0033 | Gilleland to Techridge 138kV Circuit | Establish a new 138kV circuit from Gilleland to Techridge and maintain a normally close tie between AEN and LCRA's switchyard at Gilleland. |  | Gilleland Substation | Techridge Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | PLAN_117_4276 PLAN_117_P207 | 2016-06-15 |  | 345 | 8 | 0 | 0 |  | Travis | Travis | Tier 1 |  |  | 2004-12-01 | 9054, 7336, 9190 | Y | N |  |  | 1030 | 1029
08TPIT0069 | Lake Creek - East Waco 138 kV line | Upgrade existing 138 kV line |  | Lake Creek | East Waco | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R470-E | 2020-05-15 |  | 138 | 0 | 10.5 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  | 3410, 3438, 3442, 3452 | Y | N |  |  | 3539 | 1348
08TPIT0071 | North Lake 345/138 kV autotransformer | Install a 345/138 kV autotransformer |  | North Lake |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3020-E | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  |  | N | N |  |  | 3267 | 3098
08TPIT0104 | Elgin Switching Station - Elgin 69 kV line conversion to 138 | Rebuild existing 69 kV line and convert to 138 kV operation |  | Elgin Switching Station | Elgin | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R471-E | 2017-12-15 |  | 138 | 0 | 5.9 | 0 |  | Williamson |  | Tier 4 |  |  |  | 3655, 3650, 3651, 3674, 7327, 13674 | Y | N |  |  | 3478 | 1335
08TPIT0109 | Payne - Collin Switching Station 138 kV line | Rebuild existing 138 kV line |  | EPCO | Collin Switching Station | Under construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R519-E | 2014-05-15 |  | 138 | 0 | 17 | 0 |  | Grayson | Collin | Tier 3 |  |  |  | 1757, 1758, 2350, 2366, 12349, 12468, 2349, 2370 | Y | N | 2009-R12 | Payne - EPCO section will be completed by 12/2013. | 3379 | 2174
08TPIT0110 | Temple - Little River 69 kV line | Rebuild existing 69 kV line |  | Temple | Little River | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R097-E | 2022-05-15 |  | 69 | 0 | 7.4 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3644, 3645 | N | N |  |  | 1345 | 1341
08TPIT0111 | Lufkin Switching Station - Texas Foundries Tap 138 kV line | Upgrade existing 138 kV line |  | Lufkin Switching Station | Texas Foundries tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R389-E | 2024-05-15 |  | 0 | 0 | 0.7 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3118, 3333 | N | N |  |  | 3286 | 3117
08TPIT0131 | Melon Creek: Install 138/69kV Auto | Construct Melon Creek substation on Airco to Rincon 138kV line with 138/69kV, 93 MVA auto. Build new 69kV line from Melon Creek to Tatton. Rebuild 69kV line from Refugio to Tatton. |  | Melon Creek |  | Conceptual | 100 - 0100 | AEP TCC | Glen Reed 918-599-2664 | 2021 | 2020-03-31 |  | 138 | 0 | 0 | 50 |  | Refugio |  | Tier 4 |  |  |  | 8144, 8418, 80065, 80066, 80067 | N | N |  |  | 3148 | 2979
08TPIT0132 | Melon Creek to Tatton: Build 69 KV Line | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Melon Creek | Tatton | Conceptual | 100 - 0100 | AEP TCC | Glen Reed 918-599-2664 | 2028 | 2020-03-31 |  | 69 | 9 | 0 | 0 |  | Refugio | Aransas | Tier 2 |  |  |  | 80066, 8410, 8800 | Y | N |  |  | 1175 | 1172
08TPIT0153 | Elkton - Athens 138 kV line | Upgrade existing 138 kV line |  | Elkton | Athens | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R651-E | 2015-12-15 |  | 138 | 0 | 27.9 | 0 |  | Henderson | Henderson | Tier 3 | 2007-11-26 |  |  | 3106, 3238 | Y | N |  |  | 1246 | 1243
08TPIT0172 | Gunsight 138 kV Switching Station | Construct new switching station to connect a new wind farm |  | Gunsight Switching Station |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R829-WA | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Howard |  | Tier 4 |  |  |  | 1360, 1355, 1395 | N | N |  |  | 2680 | 2564
09TPIT0012 | Hill Country to Skyline - 345 kV 2nd Circuit | Build second 345 kV line from Hillcountry to Skyline. The second circuit will be installed on existing transmission structures |  | Hill Country | Skyline | Planned | S-0470 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0052 | 2016-06-01 |  | 345 | 11 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5211, 5371 | Y | N |  | There are no transformers associated with this project | 1404 | 1403
09TPIT0024 | Electra - KMA Tap 69 kV line | Upgrade existing 69 kV line |  | Electra | KMA Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R185-E | 2024-05-15 |  | 69 | 0 | 9.9 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | N | N |  |  | 3368 | 3197
09TPIT0037 | Blossom - New 138 kV Substation | Loop new 138 kV substation into the existing 138kV Harmony Hills to Skyline line | Delayed due to budget constraint | Blossom | Harmony Hills-Skyline | Planned | T-0178 | CPS | Ulrich Skerhut UKSkerhut@cpsenergy.com 210-353-2923 | S-0602 | 2016-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5022, 5195, 5368 | Y | N |  | There are no transformers associated with this project | 950 | 949
09TPIT0042 | Collin 345-138 kV autotransformer | Install second 345/138 kV autotransformer |  | Collin Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M318-E | 2014-05-15 |  | 345 | 0 | 0 | 600 |  | Collin |  | Tier 4 |  |  |  | 29578, 2372, 2370 | Y | N | 2009-R15 |  | 1247 | 1244
09TPIT0043 | Coppell - North Lake 138 kV line | Construct 138 kV line |  | Coppell | North Lake | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M549-E | 2024-05-15 |  | 138 | 4.8 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | N | N |  |  | 3247 | 3078
09TPIT0044 | E. Richardson - Apollo 138kV line (Oncor Electric Delivery) | Upgrade existing 345 kV line |  | E. Richardson | Apollo | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3033-WA | 2015-12-01 |  | 138 | 0 | 2.3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 802, 2690 | Y | N |  |  | 3239 | 3070
09TPIT0046 | N. Midlothian - Midlothian TXI Tap 138 kV line | Upgrade existing 138 kV line |  | N. Midlothian | Midlothian TXI Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3031-E | 2024-05-15 |  | 138 | 0 | 6.2 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | N | N |  |  | 3295 | 3126
09TPIT0047 | N. Waco - NE. Waco 138 kV line | Upgrade existing 138 kV line |  | N. Waco | NE. Waco | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R477-E | 2024-05-15 |  | 138 | 0 | 1.9 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  | 3551, 3552 | N | N |  |  | 1355 | 1351
09TPIT0050 | Rowlett - Garland Bobtown Tap 138 kV line | Upgrade existing 138 kV line |  | Rowlett | Garland Bobtown Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3032-E | 2024-05-15 |  | 138 | 0 | 4.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | N | N |  |  | 3296 | 3127
09TPIT0051 | Salado Sw- Cedar Valley Sw(BEC) 138 kV line and Sw.Sta | Establish two new 138 kV switching stations and connect them with a new 138 kV line |  | Saldo Switch | Cedar Valley Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R469-E | 2024-05-15 |  | 138 | 7 | 0 | 0 |  | Bell | Bell | Tier 2 |  |  |  |  | N | N |  |  | 3377 | 3206
09TPIT0066 | Boggy Creek 138 kV Switching Station and associated line | Construct 138 kV switching station and add second circuit to a 138 kV line |  | Boggy Creek | Little River | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R488-E | 2024-05-15 |  | 138 | 0 | 3.5 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3424, 3415, 3425 | Y | N |  |  | 1365 | 1361
09TPIT0067 | Bonham Switching Station 138/69 kV autotransformer replaceme | Replace existing 138/69 kV autotransformer |  | Bonham Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R516-E | 2024-05-15 |  | 138 | 0 | 0 | 100 |  | Fannin |  | Tier 4 |  |  |  |  | N | N |  |  | 3372 | 3201
09TPIT0068 | W. Weatherford - Weatherford 69 kV line | Rebuild existing 69 kV line |  | W. Weatherford | Weatherford | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R515-E | 2022-05-15 |  | 69 | 0 | 7.5 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | N | N |  |  | 3249 | 3080
09TPIT0116 | Gatesville Tap - Gatesville TDC 69 kV line | Upgrade existing 69 kV line |  | Gatesville Tap | Gatesville TDC | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R497-WA | 2024-05-15 |  | 69 | 0 | 4.4 | 0 |  | McLennan | Coryell | Tier 4 |  |  |  | 3583, 3586, 3587 | N | N |  |  | 466 | 466
09TPIT0117 | Stryker Creek - Dialville 138 kV line | Upgrade existing 138 kV line | Construction schedule change | Stryker Creek | Dialville | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R664-E | 2014-12-01 |  | 138 | 0 | 15.2 | 0 |  | Cherokee | Cherokee | Tier 4 |  |  |  | 3110, 3111, 3160 | Y | N |  |  | 1244 | 1241
09TPIT0118 | Fisher Road - Wichita Falls 138 kV line | Upgrade existing 138 kV line. |  | Fisher Road | Wichita Falls | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R191-E | 2024-05-15 |  | 138 | 0 | 1.5 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | N | N |  |  | 3373 | 3202
09TPIT0122 | Shamburger - Tyler NW 138 kV line | Upgrade existing 138 kV line |  | Shamburger | Tyler NW | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6001-E | 2019-05-15 |  | 138 | 0 | 6.3 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3104, 3141 | Y | N | 2009-E6 |  | 1243 | 1240
10TPIT0001 | Trumbo - New 138 kV Substation | Loop new 138 kV substation into the existing 138kV Leon Creek to Pleasanton Rd-Loxley (AEP) line | Accelarated by Disribution Planning | Trumbo | Leon Creek-Pleasanton Rd | Planned | T-0082 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0181 | 2015-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5429, 5260, 8203 | Y | N |  | There are no transformers associated with this project | 976 | 975
10TPIT0009 | Trinity Switch - Hurst 138 kV Line | Upgrade existing 138 kV line. |  | Trinity Switch | Hurst | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5040-E | 2021-05-15 |  | 138 | 0 | 4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | N | N |  |  | 3250 | 3081
10TPIT0010 | Coppell to Roanoke Reconductor | Reconductor existing Coppell to Roanoke 138kv line with 959ACSS conductor |  | Coppell | Roanoke | planned | 12TPIT0079 | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 2005 | 2015-12-01 |  | 138 | 0 | 17 | 0 |  | Tarrant | Dallas | Tier 4 |  |  |  | 555, 556, 661, 648, 1852 | Y | N |  | construction by Oncor | 230 | 233
10TPIT0017 | Allen Switch - Plano Custer - Collin Junction 138 kV line | Upgrade existing double-circuit 138 kV line |  | Allen Switch | Collin Junction | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3047-E | 2022-05-15 |  | 138 | 0 | 9 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 651, 2509, 2510, 2524, 2525, 2526 | Y | N |  |  | 1059 | 1058
10TPIT0019 | Everman - Cleburne Switch 138 kV line sections | Upgrade existing 138 kV line |  | Everman | Cleburne Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3034-E | 2024-05-15 |  | 138 | 0 | 8.5 | 0 |  | Tarrant | Johnson | Tier 4 |  |  |  |  | N | N |  |  | 3261 | 3092
10TPIT0025 | Rinard Creek 138kV substation | Establish 138kV Rinard Ck substation with (2) 30MVA transformers and will cut into existing Ckt 987 (Lytton Springs to Slaughter Lane). |  | Rinard Creek substation | Rinard Creek Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | PLAN_117_P151 PLAN_117_P152 | 2016-06-15 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9262, 9075, 9267 | Y | N |  |  | 1031 | 1030
10TPIT0027 | West Batesville, Install 138 kV ring bus | West Batesville: Construct bundled 2x795 ACSR 138 kV line, add 138 kV circuit breaker and convert to 4 breaker ring bus | CHANGES | WEST BATESVILLE |  | CONCEPTUAL | 383 - 0560 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 | 2168 | 2020-12-31 |  | 138 | 0 | 0 | 0 |  | Zavala |  | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8236 | N | N | NA | NA | 3751 | 3543
10TPIT0028 | Escondido to West Batesville, build 138 kV Line | West Batesville: Construct bundled 2x795 ACSR 138 kV line, add 138 kV circuit breaker and convert to 4 breaker ring bus | CHANGES | ESCONDIDO | WEST BATESVILLE | CONCEPTUAL | 383 - 0560 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 | 2169 | 2020-12-31 |  | 138 | 46.2 | 0 | 0 |  | Maverick | Zavala | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8260 | N | Y | NA | NA | 3752 | 3544
10TPIT0034 | Leon Switch #2 138/69 kV autotransformer replacement | Replace existing 138/69 kV autotransformer |  |  |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R517-E | 2021-05-14 |  | 138 | 0 | 0 | 100 |  |  |  | Tier 4 |  |  |  |  | Y | N |  |  | 3696 | 3489
10TPIT0053 | Kaufman South 138 kV Capacitors | Install 138 kV capacitors |  | Kaufman South |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3064-E | 2024-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Kaufman |  | Tier 4 |  |  |  |  | N | N |  |  | 3297 | 3128
10TPIT0054 | Royse 138/69 kV autotransformer | Install larger autotransformer |  | Royse |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3065-E | 2024-05-15 |  | 138 | 0 | 0 | 120 |  | Rockwall |  | Tier 4 |  |  |  |  | N | N |  |  | 3298 | 3129
10TPIT0062 | Weil Road (Marion South) - New Substation | Build new 138-26.18 kV 40 MVA substation on the GVEC Marion(7178)-Cibolo(7608) 138 kV transmission line by the Marion Interchange |  | Weil Road | Marion-Cibolo | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2016-03-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7603, 7178, 7608 | Y | N |  |  | 2473 | 2384
10TPIT0063 | Geronimo(7604)-CMC Tap-McQueeney T-Line | Rebuild 5.5 miles of existing 69-kV T-line to 138-kV, 1192 ACSR between Geronimo and McQueeney substations on existing eight-of-way. |  | Geronimo | McQueeney | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2014-04-28 |  | 138 | 0 | 5.5 | 0 |  | Guadalupe | Guadalupe | Tier 4 | 2012-12-01 |  |  | 7604, 7606 | Y | N |  |  | 3211 | 3042
10TPIT0091 | Elm Mott - Waco Northcrest 138 kV line upgrade | Upgrade existing 138 kV line |  | Elm Mott | Waco Northcrest | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R714-E | 2024-05-15 |  | 138 | 0 | 3.6 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  | 3407, 3575 | N | N |  |  | 1336 | 1332
10TPIT0148 | Las Pulgas Tap - Renamed from Willacy Tap Switch 138kV | Move normally open 138kV connection to the AEP Raymondville #2 bus and add breakers at Las Pulgas to serve E Raymondville and La Sara from Las Pulgas. |  | Las Pulgas |  | Planned | 12TPIT0103 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-05-30 |  | 138 | 0 | 0 | 0 |  | Willacy | Willacy | Tier 4 |  |  |  | 5745, 5790, 8302, 80309 | Y | N |  |  | 2407 | 2330
11TPIT0001 | Lobo to Molina, build 345 kV circuit energized at 138kV | Construct 345 kV circuit from Lobo to Molina energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Molina 138kV stations. | Changes | Lobo | Rio Bravo | UNDER CONSTRUCTION | 206 - 0288 | AEP TCC | Kenneth 'Rich' Haley GAREED@AEP.COM 918-599-2664 | 880 | 2015-05-31 |  | 138 | 26 | 0 | 0 |  | Webb | Webb | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 8646, 80221 | Y | N | NA | NA | 1248 | 1245
11TPIT0002 | Lobo to North Edinburg: Construct 345 kV Line | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Lobo | North Edinburg | Planned | 065 - 0273 | ETT | Rich Haley 918-599-2664 | 3421 | 2016-06-30 |  | 345 | 156 | 0 | 0 |  | Webb | Hidalgo | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80220, 80225, 80307, 80355, 8383, 80219 | Y | N |  |  | 1325 | 1321
11TPIT0008 | Rainey St 138kV substation | Establish a new 138kV Rainey St substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2017-06-15 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9261, 9118, 9132 | Y | N |  |  | 1033 | 1032
11TPIT0009 | Dunlap 138kV substation | Install one 30MVA Transformer at Dunlap Substation |  | Dunlap Substation | Dunlap Substation | UnderConstruction |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | 3230_117_2930 3230_117_2933 3240_117_4930 3240_117_4933 | 2014-06-15 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9045 | Y | N |  |  | 1021 | 1020
11TPIT0011 | Northeast 138kV Substation | Establish a 138kV substation with (2) 30MVA transformers and 4 distribution circuits with underground get-a-ways. The station will cut into existing Gilleland - Techridge line. | Original Project title is "East Substation" | Northeast Substation | Northeast Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | PLAN_117_P142 PLAN_117_P143 PLAN_117_P144 | 2018-06-15 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9195, 9054, 9190 | Y | N |  |  | 1053 | 1052
11TPIT0012 | Euless - Grapevine Ball Street 138 kV line | Upgrade existing 138 kV line |  | Euless | Grapevine Ball Street | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5131-E | 2015-05-15 |  | 138 | 0 | 11.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2014, 2016, 2021, 12012, 12022, 12021, 12040 | Y | N |  | Euless - Highway 360 Substation section by 5/2014 | 3112 | 2943
11TPIT0014 | Muenster - St. Jo (BEC) 69 kV line | Upgrade existing 69 kV line |  | Muenster | St. Jo | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R186B-E | 2024-05-15 |  | 69 | 0 | 7.8 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | N | N |  |  | 3370 | 3199
11TPIT0015 | Sherry - Park Row - Grand Prairie 138 kV line | Upgrade existing 138 kV line |  | Sherry | Grand Prairie | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5121-E | 2015-05-15 |  | 138 | 0 | 11.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1920, 2258, 2259, 2262, 12491 | Y | N |  |  | 2686 | 2570
11TPIT0027 | East Richardson Switch - Ben Davis Switch (TMPA) 138 kV line | Create a new 138 kV line by reconfiguring existing lines |  | East Richardson Switch | Ben Davis Switch | Conceptual | M375A | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M375D-E | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Collin | Dallas | Tier 4 |  |  |  |  | N | N |  |  | 3358 | 3187
11TPIT0028 | Allen Switch - West Plano Switch 138 kV line | Create a new 138 kV line by reconfiguring existing lines and adding circuit to existing structures |  | Allen Switch | West Plano Switch | Conceptual | M375A | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M375C-E | 2021-05-15 |  | 138 | 3.5 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | N | N |  |  | 3360 | 3189
11TPIT0032 | NW Carrollton - Collin second 138 kV circuit | Rebuild existing 138 kV line for double-circuit operation. |  |  |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M368-E | 2015-05-15 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 12376, 12516, 12517, 12519, 12688, 663, 2362, 2363, 2370, 2378, 2519, 2377, 2518 | Y |  | 2009-R13 |  | 3971 | 1055
11TPIT0033 | Saginaw - American MFG Tap 138 kV line | Upgrade existing 138 kV line |  | Saginaw | American MFG Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5070-E | 2024-05-15 |  | 138 | 0 | 1.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | N | N |  |  | 3262 | 3093
11TPIT0034 | Sargent Road 345/138 kV autotransformer | Install second 345/138 kV autotransformer |  | Sargent Road |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M486-E | 2016-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  | 2946, 2949 | Y | N |  |  | 1826 | 1784
11TPIT0036 | Caddo - New Substation | Construct a new 69-13.09x26.18-kV 10 MVA substation |  | Caddo | La Vernia/GVEC Nixon | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-12-30 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  | 7239 | Y | N |  |  | 3563 | 3368
11TPIT0037 | Santa Clara - New Substation | Build a new 138-26.18 kV 40 MVA substation on the GVEC McQueeney(7606)-Cibolo(7608) 138 kV transmission line |  | Santa Clara | McQueeney/Cibolo | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7239 | Y | N |  |  | 3564 | 3369
11TPIT0048 | Austin Ranch 138 kV capacitors | Install capacitors |  | Austin Ranch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3074-E | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Denton |  | Tier 4 |  |  |  | 2378 | N | N |  |  | 1051 | 1050
11TPIT0050 | Roanoke Switch - Elizabeth Creek 138 kV line | Construct new line. |  | Roanoke Switch | Elizabeth Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M509-E | 2016-05-15 |  | 138 | 3.8 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1867, 640, 1850, 1852, 1866 | Y | N |  |  | 3058 | 2884
11TPIT0084 | Hidden Lakes - New Substation | Build a new 138-12.47 kV substation to accommodate new subdivision growth along the FM 517 and FM 646 corridors in Dickinson, Texas |  | Leave blank | Leave blank | Planned |  | TNMP | Anthony Hudson Anthony.Hudson@tnmp.com. 281-581-4712 | STE02416 | 2017-06-01 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38900, 38890, 38920 | Y | N |  |  | 1264 | 1261
11TPIT0097 | Norwood Switch autotransformer | Replace #1 345/138 kV autotransformer |  | Norwood Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4070-E | 2015-12-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  | 2410, 2404, 12404 | Y | N |  |  | 3233 | 3064
11TPIT0107 | Happy Valley: Tie 69 kV tap into Steamboat | Happy Valley: Tie 69 kV tap into Steamboat | Schedule Update | Happy Valley | Steamboat | Planned | 341 - 0515 | ETT | Teresa Trotman 918-599-2664 | 2092 | 2014-12-31 |  | 69 | 0 | 0.6 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6332, 6328, 6330, 6331, 60332 | Y | N |  |  | 299 | 302
11TPIT0108 | Penascal: Add 345 kV EPS Metering for Phase 3 | Penascal Wind Phases 2 and 3 | Updated Project Title and Schedule | Penascal |  | Under Construction | 489 - 0690 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 3370 | 2014-08-31 |  | 345 | 0 | 0 | 0 |  | Kenedy |  | Tier 4 |  |  |  | 80171 | Y | N |  |  | 3275 | 3106
11TPIT0114 | Alberta Switch-Doedyns 138kV Line | Rebuild 3.1 Miles of 138kV line from Alberta Switch to Doedyns Substation | Pending completion of Doedyns-Sioux 11TPIT0085 | Alberta Switch | Doedyns | Planned | 07TPIT7777 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-05-01 |  | 138 | 0 | 3.1 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 5753, 5759 | Y | N |  |  | 355 | 358
11TPIT0174 | Nall to Briarcrest Upgrade | Upgrade 0.82 miles of conductor from 2-0 ACSR to 795 ACSR and replace transmission poles as needed. |  | Nall Lane Substation | Briarcrest Substation | planned |  | BRYN | James Tanneberger 9798215763 |  | 2014-04-01 |  | 69 | 0 | 0.82 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32798, 32857, 32860, 32861, 32872, 32862, 32863, 32870, 32877 | Y | N |  |  | 1827 | 1430
11TPIT0179 | Hicks Switch - Elizabeth Creek 138 kV line | Construct new 138 kV line |  | Hicks Switch | Elizabeth Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M523-E | 2016-05-15 |  | 138 | 10 | 0 | 0 |  | Tarrant | Tarrant | Tier 2 | 2013-02-01 | 2013-03-01 |  | 1866, 1867, 2082 | Y | N |  |  | 2786 | 2662
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0385 | 2020-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5416, 5250, 5395 | Y | N |  | There are no transformers associated with this project | 3190 | 3021
12TPIT0006 | Olmos(7613)- New Substation | Build a new 138-13.09 kV 20 MVA substation on the Olmos switching station site |  | Olmos | Olmos Switching Station | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-11-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7239 | Y | N |  |  | 3566 | 3371
12TPIT0007 | FM-725 - New Substation | Build a new 138-26.18 kV, 40 MVA substation on the GVEC McQueeney(7606) - Schumansville(7609) 138 kV transmission line |  | FM 725 | McQueeney-Schumansville | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2016-10-31 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7607, 7606, 7609 | Y | N |  |  | 2222 | 2150
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Valley Rd line. |  | Masterson Rd. | Cagnon-Valley | Conceptual | T-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0538 | 2021-06-01 |  | 138 | 20 | 0 | 0 |  | Bexar | Bexar | Tier 2 |  |  |  | 5296, 5053, 5054, 5230, 5465 | N | N |  | There are no transformers associated with this project | 2291 | 2218
12TPIT0019 | Pleasant Valley second 138/69 kV autotransformer | Install second 138/69 kV autotransformer |  | Pleasant Valley |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R555-E | 2021-05-15 |  | 138 | 0 | 0 | 100 |  | Wichita |  | Tier 4 |  |  |  |  | N | N |  |  | 3361 | 3190
12TPIT0025 | Refugio - Tatton: Rebuild Irreparable 69 kV Line | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Refugio | Tatton | Conceptual | 100 - 0100 | AEP TCC | Glen Reed 918-599-2664 | 2027 | 2020-12-30 |  | 69 | 0 | 12.6 | 0 |  | Refugio | Aransas | Tier 4 |  |  |  | 8410, 8800 | Y | N |  |  | 1167 | 1164
12TPIT0062 | UTMB - New Substation | Build a new 138-12.47 kV substation to serve proposed UTMB Medical Center at Victory Lakes in League City. |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE04512 | 2015-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38930, 38920, 38950 | Y | N |  | Project pushed out based on revised load forecast from UTMB. | 1194 | 1191
12TPIT0078 | Southeast Nacogdoches - Lufkin Switch 345 kV line | Construct new 345 kV line, add second circuit to existing structures and add 345 kV circuit breakers at existing switching stations |  | Southeast Nacogdoches | Lufkin Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R862 | 2022-12-15 |  | 345 | 8 | 13 | 0 |  | Nacogdoches | Angelina | Tier 2 | 2008-07-01 |  | 2008-09-01 | 3117, 3119 | N | N | 2007-E4 |  | 3287 | 3118
12TPIT0079 | Grapevine Junction - Coppell 138 kV line | Rebuild 138 kV line | Construction schedule change | Grapevine Junction | Coppell | Under construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5001A-WAC | 2014-05-15 |  | 138 | 0 | 4.4 | 0 |  | Dallas | Tarrant | Tier 4 |  |  |  | 2014, 2015, 2025 | Y | N | 2007-R4 | Interim rating increase for Coppell - Grapevine Junction section was implemented in May 2012. | 3104 | 2929
12TPIT0080 | Forney Sw. Sta. Second 600 MVA, 345/138 kV Autotransformer | Add second 345/138 autotransformer |  | Forney Sw. Sta. |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4037 | 2016-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 4 | 2008-06-01 | 2008-07-01 |  | 2437, 2438 | Y | N | 2007-R2 |  | 2594 | 2489
12TPIT0081 | 36th St - New 138kV Substation | Loop new 138kV substation into existing 138kV Merida to Medina Base line and replace exiting Kelly Field #3 138kV substation | Delayed due to Budget Constraints | Merida | Medina Base | Planned | T-0161 | CPS | Hector Torres HVTorres@cpsenergy.com 210-353-2404 | S-0578 | 2014-10-14 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5245, 5305, 5310, 5427 | Y | N |  | There are no transformers associated with this project | 952 | 951
12TPIT0084 | Lookout 138 kV new substation and connections | Lookout 138 kV new substation and its connections to Apollo and to Firewheel | On Hold For Funding | Switch 8622 at Apollo | Switch 8512 at Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2015-06-01 |  | 138 | 4.1 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 828, 12683, 802, 821 | Y | N |  | This project is a line reconductor for solving overload | 765 | 764
12TPIT0090 | Whitney 2nd Auto | Replace 60 MVA, 138-69 kV auto with 75 MVA auto |  | Whitney |  | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 10048 | 2014-10-01 |  | 138 | 0 | 0 | 75 |  | Bosque |  | Tier 4 |  |  |  | 243, 3546 | Y | N |  |  | 883 | 882
12TPIT0109 | Laguna to Naval Base | Upgrade the 3.09-mile Laguna (8494)-Naval Base (8495) 69 kV transmission line to 69kV 959.6 ACSS , 191 MVA with 138 kV capable structures. |  | Laguna | Naval Base | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-04-01 |  | 69 | 0 | 3.1 | 0 |  | Nueces | Nueces | Tier 4 | 2012-07-06 | 2012-12-15 | 2013-01-15 | 8494, 8495 | Y | N |  |  | 988 | 987
12TPIT0123 | Braunig West Bus - 138 kV Substation Equipment Upgrade | Upgrade Terminals at Braunig West for Valley Rd., Mauermann Rd., Streich Rd. circuits and upgrade terminals at remote ends to ensure a 2420 A rating and remove the existing MLSE on the 138kV transmission lines. |  | Braunig_W | Valley Rd Mauermann Streich Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0658 | 2014-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 | 2011-12-16 | 2012-04-25 |  | 5007, 5025, 5297, 5417, 5465 | Y | N |  | There are no transformers associated with this project | 639 | 639
12TPIT0140 | South Batesville breaker addition | Adds breakers to South Batesville to allow closing of normally open South Batesville to Frio Town. Creates 3- terminal switching station |  | South Batesville |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-09-01 |  | 69 | 0 | 0 | 0 |  | Zavala |  | Tier 4 |  |  |  | 5832, 5848 | Y | N |  |  | 1553 | 1537
12TPIT0141 | Dinero 138 kV Substation | Build new load serving station in the 138 kV line from Orange Grove to AEP's George West. |  | Dinero |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-03-01 |  | 138 | 0.5 | 0 | 0 |  | Live Oak |  | Tier 4 |  |  |  | 5670, 5660, 8167 | Y | N |  |  | 1546 | 1534
12TPIT0142 | Choate to Fashing Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. | The Fashing to Coy City line section is now needed due to newest load forecast. Changes prior quarter comment. | Choate | Coy City | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-02-07 |  | 69 | 0 | 30 | 0 |  | Atascosa | Karnes | Tier 2 | 2011-12-16 | 2012-04-25 |  | 5716, 5720, 5722, 5729 | Y | N |  |  | 1550 | 1536
12TPIT0143 | Danevang Switch to El Campo Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. |  | Industrial Park | El Campo | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-09-30 |  | 69 | 0 | 2.2 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  | 5538, 5540, 5543, 5544 | Y | N |  |  | 1547 | 1535
12TPIT0143 | Danevang Switch to El Campo Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. |  | Industrial Park | Plainview | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-10-27 |  | 69 | 0 | 5.3 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  | 5538, 5540, 5543, 5544 | Y | N |  |  | 1548 | 1535
12TPIT0143 | Danevang Switch to El Campo Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. |  | Danevang Switch | Plainview | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-11-24 |  | 69 | 0 | 4.89 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  | 5538, 5540, 5543, 5544 | Y | N |  |  | 1549 | 1535
12TPIT0156 | Brundage Capacitor | Add 9.6 MVAR capacitor |  | Brundage |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-06-06 |  | 69 | 0 | 0 | 0 | 0,9.6 | Dimmit |  | Tier 4 |  |  |  | 5870 | Y | N |  |  | 1405 | 1404
12TPIT0180 | Lon Hill to City of Robstown: Rebuild 69kV line | Rebuild Lon Hill - City of Robstown 69kV Line | Reformated project number to match other numbers | Lon Hill | City of Robstown | Planned | 582 - 0735 | AEP TCC | Teresa Trotman 918-599-2664 | 3460 | 2014-05-02 |  | 69 | 0 | 4.6 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  | 8448, 8884, 5630 | Y | N |  | 0 | 1819 | 1777
12TPIT0181 | Lon Hill to Calallen: Rebuild 69kV line | Rebuild Lon Hill - Calallan 69kV Line | Date Change | Lon Hill | Calallan | Operational | 581 - 0736 | AEP TCC | Teresa Trotman 918-599-2664 | 3461 | 2014-02-19 |  | 69 | 0 | 2.1 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  | 5626, 8448 | Y | N |  | 0 | 1818 | 1776
12TPIT0182 | Crystal City - Turtle Creek: Reconductor 69kV Line | Reconductor Crystal City - Turtle Creek 69kV Line | Reformated project number to match other numbers, changed ISD, and Dollars. PM Updated | Crystal City | Turtle Creek | Under Construction | 591 - 0761 | AEP TCC | Rick McCracken Gareed@aep.com 918-599-2664 | 3468 | 2014-06-30 |  | 69 | 0 | 3.3 | 0 |  | Zavala | Zavala | Tier 4 |  |  |  | 8242, 8243 | Y | N | NA | 0 | 1944 | 1895
12TPIT0184 | Lon Hill: Replace 138-69kV Autotransformers #1 and #2 | Upgrade Both 138-69kV Autotransformers at Lon Hill to 240MVA |  | Lon Hill |  | Planned | 580 - 0734 | AEP TCC | Teresa Trotman 918-599-2664 | 3463 | 2014-06-01 |  | 138 | 0 | 0 | 240 |  | San Patricio |  | Tier 4 |  |  |  | 8448, 8452 | Y | N |  | 0 | 1820 | 1778
12TPIT0185 | Airline to Westside: Add 138kV Circuit | Add a Second 138kV Circuit between Airline and Westside | CHANGES | AIRLINE | WESTSIDE | CONCEPTUAL | 587-0747 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 | 3464 | 2020-06-30 |  | 138 | 0 | 5.5 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8490 | N | N | NA | NA | 3753 | 3545
12TPIT0190 | Boots: Build 138 kV Box Bay Structure with three breakers | Interconnect White Camp Solar Farm at Boots to connect White Camp to the Spur to Sun 138 kV line | Schedule Update | Boots |  | Under Construction | 507 - 0718 | AEP TNC | Eric Scott 918-599-2664 | 2502 | 2014-06-30 |  | 138 | 0 | 0 | 0 |  | Kent |  | Tier 4 |  |  |  | 6179, 720, 6150 | Y | N |  |  | 1849 | 1806
12TPIT0205 | AEP_McCampbell: New Substation Cut In | Customer to construct 138kV substation. Two 138kV circuits Cut-In to McCampbell substation. | Planned | Dupont SS | Whitepoint SS | Planned | 561 - 0729 | AEP TCC | Glen Reed 918-599-2664 | 3435 | 2014-06-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 80469, 8414, 8422, 8961, 80470 | Y | N |  |  | 3444 | 3268
13TPIT0013 | Perry to Midway Rebuild | Rebuild Perry to Midway with 959ACSS |  | Perry | Midway | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 8050 | 2014-03-28 |  | 69 | 0 | 12.4 | 0 |  | Falls | Falls | Tier 4 |  |  |  | 92, 185 | Y | N |  |  | 1063 | 1062
13TPIT0045 | Blumenthal | Construct a new 8.4-mile 138 kV transmission line from a tap point on the Kendall CTEC (7147) - Mountain Top (7148)138 kV transmission line to the new Blumenthal substation (7418). | Delayed from initial May 2013 in-service date | Blumenthal | Kendall CTEC-Mountain Top | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-06-30 |  | 138 | 8.4 | 0 | 0 |  | Kendall |  | Tier 2 |  |  |  | 7418, 7419, 7147, 7148 | Y | N |  |  | 991 | 990
13TPIT0047 | Parkway to EC Mornhinweg | Construct a new 138 kV 795 ACSR transmission line between the new EC Mornhinweg substation (7463) and the Parkway substation (7611). |  | Parkway | EC Mornhinweg | Planned | 13TPIT0066 | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2015-05-30 |  | 138 | 8 | 0 | 0 |  | Comal | Guadalupe | Tier 2 | 2009-02-01 | 2009-06-15 |  | 7463, 7611 | Y | N |  |  | 1004 | 1003
13TPIT0058 | Circuit 941 Summit - Williamson Reconductor | Reconductor the 3.54 miles circuit from single 795 ACSR to single 795 ACSS Drake conductor. |  | Summit Substation | Williamson Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | PLAN_117_079 | 2014-06-15 |  | 138 | 0 | 3.54 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9279, 9295 | Y | N |  |  | 1023 | 1022
13TPIT0059 | Cedar Crest - Industrial 138 kV line | Upgrade existing line |  | Cedar Crest | Industrial | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4072-E | 2016-05-15 |  | 138 | 0 | 3.2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2494, 2976, 2981 | Y | N | 2009-R23 |  | 2600 | 2495
13TPIT0060 | Cedar Hill Switch - Mountain Creek 138 kV line | Upgrade existing line |  | Cedar Hill Switch | Mountain Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4068-E | 2015-05-15 |  | 138 | 0 | 11.4 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2411, 2412, 2421, 2422 | Y | N |  |  | 2593 | 2488
13TPIT0061 | Terrell Switch - North Terrell Tap 138 kV line | Upgrade existing line |  | Terrell Switch | North Terrell Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M363-E | 2024-05-15 |  | 138 | 0 | 7.9 | 0 |  | Kaufman | Kaufman | Tier 4 |  |  |  |  | N | N |  |  | 3299 | 3130
13TPIT0062 | Cedar Hill Switch second 345/138 kV autotransformer | Install autotransformer |  | Cedar Hill Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4071-E | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  |  | N | N |  |  | 3270 | 3101
13TPIT0063 | Salado 138 kV Switch | Construct 138 kV switching station |  | Salado |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R445B-E | 2018-12-15 |  | 138 | 0 | 0 | 0 |  | Bell |  | Tier 4 |  |  |  |  | N | N |  |  | 3367 | 3196
13TPIT0064 | Rocky Mound Switching Station series capacitors | Install series capacitors for Willow Creek - Clear Crossing - Dermott Switch (Central B) 345 kV line (Oncor Electric Delivery part) |  | Rocky Mound Switching Station |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C079-E | 2015-12-15 |  | 345 | 0 | 0 | 0 |  | Haskell |  | CREZ |  |  |  | 17012, 17013, 17014, 17015, 1421, 60515 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2768 | 2644
13TPIT0070 | Nash Creek Substation | Replace existing PWT with new 69kVx13.09 kV, PWT w/associated CSW, structures, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2015-12-30 |  | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7596 | Y | N |  |  | 3503 | 3322
13TPIT0094 | Lamesa - Buzzard Draw 138kV line | Add second circuit to existing line |  | Lamesa | Buzzard Draw | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8032-E | 2014-12-15 |  | 138 | 21.5 | 0 | 0 |  | Dawson | Howard | Tier 2 | 2008-10-01 | 2011-01-01 |  | 1163, 1355 | Y | N |  |  | 2682 | 2566
13TPIT0100 | Correction of Effective date for 13TPIT0100 to 12/1/2015 | Build Westminster 138 kV Substation and transmission line tap from Oncor's Anna Switch - Van Alstyne 138 kV line. | Budget |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07612 | 2015-12-01 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 37270 | Y | N |  |  | 3812 | 3598
13TPIT0104 | Jack County Auto | Install 345-138 kV, 700 MVA auto at Jack County |  | Jack County | Jack County | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 11038 | 2020-06-01 |  | 345 | 0 | 0 | 700 |  | Jack |  | Tier 4 |  |  |  | 575, 579 | Y | N |  |  | 1184 | 1181
13TPIT0106 | Killeen SS to Ding Dong | Rebuild 477 ACSR line with 955 ACSS |  | Killeen SS | Ding Dong | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 11037 | 2014-12-01 |  | 138 | 0 | 23.8 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 115, 117, 136, 3423 | Y | N |  |  | 2726 | 2608
13TPIT0108 | Nelson Sharpe to Ajo: Reconductor 345kV Line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo | Date Change | Nelson Sharpe | Ajo | Under Construction | 071 - 0281 | AEP TCC | Michael Glueck 918-599-2664 | 3181 | 2014-06-30 |  | 345 | 0 | 36.2 | 0 |  | Kleberg | Kenedy | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 80076, 85000 | Y | N |  |  | 1423 | 1422
13TPIT0110 | Rio Hondo: Replace 345 kV Series Capacitors | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo |  | Rio Hondo |  | Under Construction | 071 - 0281 | AEP TCC | Michael Glueck 918-599-2664 | 3185 | 2014-02-28 |  | 345 | 0 | 0 | 0 | 0,933.1 | Cameron |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8903, 8318, 8902 | Y | N |  |  | 2522 | 2417
13TPIT0112 | North Andrews 138 kV capacitors | Install shunt capacitors | Construction schedule change | North Andrews |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8157-E | 2014-09-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Andrews |  | Tier 4 |  |  |  | 1159 | Y | N |  |  | 3355 | 3184
13TPIT0113 | Renner 345/138 kV autotransformer | Replace existing 345/138 kV autotransformer with larger autotransformer |  | Renner |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3099-E | 2016-05-15 |  | 345 | 0 | 0 | 600 |  | Collin |  | Tier 4 |  |  |  | 2355, 2359, 2354, 2358, 12354, 16358 | Y | N |  |  | 2826 | 1300
13TPIT0114 | Silver to Silver Tap 1: Reterminate the 69 kV line into the | Reterminate Silver Tap 1 to Silver with 795 ACSR and add 7.2 Mvar capacitor bank at Silver |  | Cedar Hill | Silver Tap 1 | Planned | 557 - 0719 | AEP TNC | Eric Scott gareed@aep.com 918-599-2664 | 2559 | 2014-06-30 |  | 69 | 0.02 | 0 | 0 | 0,7.2 | Coke | Coke | Tier 4 |  |  |  | 6000, 6431, 6423, 6430 | Y | N |  |  | 2752 | 2631
13TPIT0119 | Vanderbilt to Ricebird 138 kV circuit | Install 795 ACSR 138 kV on other side of new towers once CCN is complete. Includes building new load serving station with a 2 mile double circuit that loops into the 138 kV line near the Cordele substation. 2nd phase of 13tpit0119a |  | ETP | Ricebird | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-06-15 |  | 138 | 22 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5523, 5584, 78104 | Y | N |  | Project costs are included with 13TPIT0119a | 2673 | 2558
13TPIT0119 | Vanderbilt to Ricebird 138 kV circuit | Install 795 ACSR 138 kV on other side of new towers once CCN is complete. Includes building new load serving station with a 2 mile double circuit that loops into the 138 kV line near the Cordele substation. 2nd phase of 13tpit0119a |  | Vanderbilt | ETP | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-04-28 |  | 138 | 26.5 | 0 | 0 |  | Jackson | Jackson | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5523, 5584, 78104 | Y | N |  | Project costs are included with 13TPIT0119a | 2674 | 2558
13TPIT0121 | Tilden to Reveille 138 kV line | Construct a new 138 kV double circuit capable line from Tilden to Reveille. For new Eagleford shale oil and gas needs. |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-01 |  | 138 |  | 0 | 0 |  | McMullen | La Salle | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5705, 5701, 8612 | Y | N |  |  | 2355 | 2282
13TPIT0121 | Tilden to Reveille 138 kV line | Construct a new 138 kV double circuit capable line from Tilden to Reveille. For new Eagleford shale oil and gas needs. |  | Tilden | Fowlerton | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-01 |  | 138 | 47 | 0 | 0 |  | McMullen | La Salle | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5705, 5701, 8612 | Y | N |  |  | 2356 | 2282
13TPIT0121 | Tilden to Reveille 138 kV line | Construct a new 138 kV double circuit capable line from Tilden to Reveille. For new Eagleford shale oil and gas needs. |  | Fowlerton | Reveille | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-01 |  | 138 | 0 | 0 | 0 |  | McMullen | La Salle | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5705, 5701, 8612 | Y | N |  |  | 2357 | 2282
13TPIT0123 | Tordillo Station and Autotransformer | Build new Tordillo station with 138-69 kV 150 MVA autotransformer close to Fashing station with a short 69 kV line Fashing. | Project was renamed from Fashing Autotransformer and modifed due to property constraints. | Tordillo |  | Planned | 13TPIT0130 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-06-03 |  | 138 | 0 | 0 | 150 |  | Atascosa |  | Tier 3 | 2011-12-12 | 2012-04-01 |  | 5716, 5715, 5717 | Y | N |  |  | 2675 | 2559
13TPIT0123b | Reconnect 69 lines from Fashing at Tordillo | Moves the Fashing lines from Pleasanton and Coy City to Tordillo |  | Tordillo |  | Planned | 13TPIT0123 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-06-04 |  | 69 | 0.5 | 0 | 0 |  | Atascosa |  | Tier 3 | 2011-12-16 | 2012-04-25 |  | 5714, 5715, 5716, 5720 | Y | N |  |  | 3118 | 2949
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-07-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  | 5601, 5600, 5602 | Y | N |  |  | 1554 | 1538
13TPIT0125 | CR343 138 kV Substation | Build new load serving station in the 138 kV line between Cross and Pearsall. |  | CR343 |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-02-01 |  | 138 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5897, 5707, 5895 | Y | N |  |  | 2353 | 2280
13TPIT0128 | Danevang Switch to Danevang Substaton Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. |  | Danevang Switch | Danevang Substation | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-04-27 |  | 69 | 0 | 2.2 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  | 5544, 5548 | Y | N |  |  | 1578 | 1548
13TPIT0130 | San Miguel to Fashing Conversion | Convert 69 kV line to 138 kV line. The line was originally built for 138 kV operation. 138 kV circuit will terminate at Tordillo | Likely to be sped up with new load forecast | San Miguel | Fashing | Planned | 13TPIT0123 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-06-03 |  | 138 | 0 | 23.05 | 0 |  | Atascosa | Atascosa | Tier 3 | 2011-12-12 | 2012-04-01 |  | 5715, 5717, 5702, 5706, 5716 | Y | N |  |  | 2677 | 2561
13TPIT0133 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-01-01 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 5828, 5857 | Y | N |  |  | 1579 | 1549
13TPIT0136 | Odessa North 138 kV Switching Station | Construction 138 kV switching station |  | Odessa North |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8050B-WAC | 2014-05-15 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  |  | Y | N |  |  | 3265 | 3096
13TPIT0137 | Odessa North - Goldsmith Junction 138 kV line | Rebuild existing 69 kV line to create a double-circuit line with 69 kV and 138 kV circuits |  | Odessa North Switch | Goldsmith Junction | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8050C-WAC | 2014-05-15 |  | 138 | 13.3 | 0 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 11253, 1019, 1122, 1254, 1255, 11140, 1123, 1261, 11254 | Y | N |  |  | 2694 | 2578
13TPIT0149 | Oaks to Loxley | Build new 138 kV 795 ACSR circuit from Oaks to a new AEP switching station Loxley in the Leon Creek to Pleasanton line |  | Oaks | Loxley | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-06-03 |  | 138 | 6 | 0 | 0 |  | Atascosa | Atascosa | Tier 3 | 2011-12-16 | 2012-04-25 |  | 5713, 80491 | Y | N |  |  | 2233 | 2161
13TPIT0151 | Gibbons Creek Upgrades Project | Gibbons Creek upgrades project will be including 3 phases such as adding of the 2x100 MVAr new reactors into the 345 kV North and South buses, replacing and upgrading of the auto transformer #1 to 600 MVA as well as removing its 2 reactors at tertiary side from the system, and then removing of the auto transformer #3 from the system and using as for a spare transformer |  | Gibbons Creek | Gibbons Creek | Planned |  | GARLAND | Paul Ricciardi 972-205-3476 |  | 2015-09-01 |  | 345 | 0 | 0 | 0 | 200,0 | Grimes | Grimes | Tier 3 |  |  |  | 969, 967, 964, 965 | Y | N |  |  | 3930 | 3689
13TPIT0151 | Gibbons Creek Upgrades Project | Gibbons Creek upgrades project will be including 3 phases such as adding of the 2x100 MVAr new reactors into the 345 kV North and South buses, replacing and upgrading of the auto transformer #1 to 600 MVA as well as removing its 2 reactors at tertiary side from the system, and then removing of the auto transformer #3 from the system and using as for a spare transformer |  | Gibbons Creek | Gibbons Creek | Planned |  | GARLAND | Paul Ricciardi 972-205-3476 |  | 2015-12-01 |  | 345 | 0 | 0 | 600 |  | Grimes | Grimes | Tier 3 |  |  |  | 969, 967, 964, 965 | Y | N |  |  | 3931 | 3689
13TPIT0151 | Gibbons Creek Upgrades Project | Gibbons Creek upgrades project will be including 3 phases such as adding of the 2x100 MVAr new reactors into the 345 kV North and South buses, replacing and upgrading of the auto transformer #1 to 600 MVA as well as removing its 2 reactors at tertiary side from the system, and then removing of the auto transformer #3 from the system and using as for a spare transformer |  | Gibbons Creek | Gibbons Creek | Planned |  | GARLAND | Paul Ricciardi 972-205-3476 |  | 2016-05-01 |  | 345 | 0 | 0 | 0 |  | Grimes | Grimes | Tier 3 |  |  |  | 969, 967, 964, 965 | Y | N |  |  | 3932 | 3689
13TPIT0152 | Loving - Elmar 138 kV line | Rebuild existing 138 kV line | Construction schedule change | Loving | Elmar | Under Construction | R8066-E | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 |  | 2014-05-15 |  | 138 | 0 | 40 | 0 |  | Winkler | Reeves | Tier 3 |  |  |  | 1092, 1093 | Y | N |  |  | 3961 | 3717
13TPIT0152 | Elmar - Mason 138 kV line | Rebuild existing 138 kV line |  | Elmar | Mason | Construction schedule change |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8066-E | 2014-12-15 |  | 138 | 0 | 40 | 0 |  | Winkler | Reeves | Tier 3 | 2012-05-15 | 2012-06-15 |  | 1093, 1094 | Y | N |  | Wink - Loving complete in 11/2013, Loving - Elmar complete in 12/2013 and Elmar - Mason complete in 5/2014 | 3158 | 2989
13TPIT0153 | Moss - Odessa Southwest - Odessa EHV 138 kV line | Reconductor existing 138 kV line |  | Moss | Odessa EHV | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8064-WAC | 2014-05-15 |  | 138 | 0 | 14.2 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1019, 1027, 1111, 1113 | Y | N |  |  | 2995 | 2822
13TPIT0155 | Yucca: Add 10 MVA DRCS with 7.2 Mvar capacitor bank | Add 3.6 Mvar capacitor bank at Barnhart SWTEC and add 10 MVA DRCS with 7.2 Mvar capacitor bank at Yucca | Schedule Update | Yucca |  | Planned | 558 - 0721 | AEP TNC | Michael Tallon 918-599-2664 | 2563 | 2014-02-28 |  | 69 | 0 | 0 | 0 | -10,17.2 | Crockett |  | Tier 4 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 6034, 60202, 6035, 6550 | Y | N | 0 | 0 | 1891 | 1847
13TPIT0157 | Cactus to Ft. Lancaster: Rebuild 69 kV line | Rebuild Cactus to Ft. Lancaster 69 kV line with 795 ACSS | Schedule Update | Cactus | Ft. Lancaster | Planned | 569 - 0743 | AEP TNC |  | 2573 | 2015-12-31 |  | 69 | 0 | 9.28 | 0 |  | Crockett | Pecos | Tier 4 |  |  |  | 6577, 6578, 6579 | Y | N |  |  | 1844 | 1801
13TPIT0160 | Whitepoint: Add 138 kV breaker terminal for WF interconnect | Construct a 138 kV breaker terminal at Whitepoint for the Generator Interconnect | Changes | Whitepoint |  | Planned | 573-0750 | AEP TCC | Frank Pritzlaff gareed@aep.com 918-599-2664 | 3454 | 2015-12-31 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8961 | Y | N | NA | NA | 3976 | 3731
13TPIT0171 | Farmersville West - New Substation | Build a new 138-12.47 kV substation to accommodate load growth in Farmersville. Cut Oncor's Princeton - Royce City 138 kV line into the new substation. |  |  |  | Planned | 16TPIT0005 | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07214 | 2015-05-01 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 37291, 12527 | Y | N |  |  | 2062 | 2010
13TPIT0174 | Piloncillo 138 kV Station: Install breaker ring bus | Construct 4 CB ring bus at new Piloncillo station on Asherton to North Laredo 138 kV line |  | Piloncillo |  | Under Construction | 600 - 0762 | AEP TCC | RICK McCRACKEN GAREED@AEP.COM 918-599-2664 | 3469 | 2014-05-02 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  | 80481, 89631 | Y | N |  |  | 3567 | 3372
13TPIT0177 | Colorado - Nada Transmission Line Upgrade | Upgrade the 20 mile Colorado (7636) - Nada (5536) 69-kV transmission line to 795 ACSR 69-kV, 111 MVA. |  | Colorado | Nada | Planned | 13TPIT0150 (STEC) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-04-30 |  | 69 | 0 | 20 | 0 |  | Colorado | Colorado | Tier 2 | 2012-02-01 |  |  | 5536, 7636 | Y | N |  |  | 2190 | 2118
13TPIT0180 | Salem Autotransformer Replacement | Replace failed autotransformer at the Salem substation | A spare autotransformer will be in service at Salem temporarily until the replacement is installed. The in-service date for the spare is June 15, 2012. | Salem |  | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-03-21 |  | 345 | 0 | 0 | 672 |  | Washington |  | Tier 4 |  |  |  | 7058, 7289 | Y | N |  | Cost will be determined in the near future. | 3811 | 3597
13TPIT0186 | Trinidad second 345/138 kV autotransformer |  |  | TRINIDAD SES | TRINIDAD SES | Under Constrcution |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6015-WAC | 2014-05-01 |  | 345 | 0 | 0 | 600 |  | Henderson | Henderson | Tier 4 |  |  |  | 3124, 3127 | Y | N |  |  | 3985 | 3739
13TPIT0187 | Harlandale to Sommers - 138 kV Transmission Line Rebuild | Rebuild approximately 40 circuit miles of 138 kV transmission from Harlandale to Sommers |  | Harlandale | Sommers | Planned | S-0732 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0192 | 2018-12-01 |  | 138 | 0.1 | 40 | 0 |  | Bexar | Bexar | Tier 3 |  |  |  | 5190, 5385, 5395 | Y | N |  | There are no transformers associated with this project | 2379 | 2303
13TPIT0193 | Tomball Reactor | Install 50MVAR reactor at Tomball substation. |  | Tomball |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-31 |  | 138 | 0 | 0 | 0 | -50,0 | Harris |  | Tier 4 |  |  |  | 46510 | Y | N |  |  | 2378 | 2302
13TPIT0198 | Seawillow Substation | Construct 138kV-12.5kV distribution substation Seawillow (7559) on T-184 Lockhart and Luling. |  | Seawillow | Luling-Lockhart | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2015-09-30 |  | 138 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  | 7559, 7216, 7224 | Y | N |  |  | 2772 | 2648
13TPIT0199 | Caddo Mills HWY 66 Substation 69 kV Capacitors | Install shunt capacitors |  | Caddo Mills HWY 66 |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R513-E | 2014-05-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Hunt |  | Tier 4 |  |  |  | 1831, 1827, 1829 | Y | N |  |  | 3684 | 1972
13TPIT0203 | Correction to in service date, bus & load | Old 13TPIT0203 (project ID:3132) with 1/1/14 in service date deleted. New 13TPIT0203 (project ID:3741) will replace and include bus, load and in service date corrections. Blossom PMCR (project ID:3742) to be used to remove Blossom from planning model until new in service date. | Still Constructing Station |  |  | Planned | 3132, 3742 | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE02916 | 2014-05-30 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 37400, 1687 | Y |  |  |  | 3987 | 3741
13TPIT0203 | PMCR to resolve case builds | PMCR to resolve case builds which have Blossom in service from period between 1/1/2014-5/29/2014 (approximately). Old 13TPIT0203 (project ID:3132) with 1/1/14 in service date deleted. New 13TPIT0203 (project ID:3741) will replace and include bus, load and in service date corrections. | Still Constructing |  |  |  |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2014-02-20 |  | 0 | 0 | 0 | 0 | [7 empty] | 37400, 1687 | Y |  |  |  | 3988 | 3742
13TPIT0226 | New Switching station btw Gray & Alibates | Build new breaker and a half configuration substation for the interconnection of generation. | Upated project information and cost |  |  | Under Construction |  | CTT | Tim Cook 636-534-3250 |  | 2014-05-10 |  | 0 | 0 | 0 | 0 |  | Carson |  | Tier 4 |  |  |  | 79005, 79000, 79500 | Y |  |  |  | 3086 | 2911
13TPIT0227 | Langston 138kV Substation | Construct service to new 138kV Langston customer-owned substation. Loop through Ckt.86 Brine to Mont Belvieu. | Delay in Project Schedule | Langston | Brine/Mont Belvieu | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-04-30 |  | 138 | 1.2 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  | 40775, 40000, 40220, 40255, 40300, 40764, 41700, 40012, 40500, 40900, 41113, 46100 | Y | N |  |  | 2865 | 2739
13tpit0148 | Cotulla 138 kV bus load and auto | First phase moves load from 69 to 138 kV in May. Second phase installs 138 kV and autotransformer in December. |  | Cotulla |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-05-10 |  | 69 | 0 | 0 | 0 |  | La Salle |  | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 8520, 5876 | Y | N |  |  | 3649 | 3449
13tpit0148 | Cotulla 138 kV bus load and auto | First phase moves load from 69 to 138 kV in May. Second phase installs 138 kV and autotransformer in December. |  | Cotulla |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-12-15 |  | 69 | 0 | 0 | 150 |  | La Salle |  | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 8520, 5876 | Y | N |  |  | 3650 | 3449
13tpit2946 | New Choke Canyon substation | New substation in San Miguel to Sigmor 138 kV line |  | AEPCHKCN |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-04-01 |  | 138 | 0 | 0 | 0 |  | Live Oak |  | Tier 4 |  |  |  | 5689, 5706, 8404 | Y | N |  |  | 3115 | 2946
14TPIT0003 | Ranchtown - New 138 kV Substation | Loop new 138kV substation into the existing 138kV Helotes to Menger Creek line |  | Ranchtown | Helotes-Menger Creek | Planned | T-0175 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0567 | 2015-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5358, 5200, 7665 | Y | N |  | There are no transformers associated with this project. There is no transmission line additions associated with this project | 958 | 957
14TPIT0004 | Cushman-Highway 123 | Construct a new 6.2 mile single 795 ACSR 138 kV transmission line (rated 220 MVA) from the new Highway 123 substation (7221) located near the intersection of State Highway 123 and the GVEC Hickory Forest (7225)-New Berlin (7612) 138 kV (T¿529) transmissio |  | Highway 123 | Cushman-New Berlin-Hickory Forrest | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-06-15 |  | 138 | 6.2 | 0 | 0 |  | Guadalupe |  | Tier 2 | 2009-02-06 | 2009-06-01 |  | 7221, 7225, 7226, 7228, 7612 | Y | N |  | Coordinate with GVEC | 1001 | 1000
14TPIT0008 | Holt - Emma 69 Tap kV line | Upgrade existing line |  | Holt | Emma | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8144-E | 2024-05-15 |  | 69 | 0 | 6.2 | 0 |  | Ector | Andrews | Tier 4 |  |  |  | 1142, 1262 | N | N | 2009-R5 |  | 3331 | 3160
14TPIT0009 | Odessa North - North Cowden 69 kV line | Upgrade existing line |  | Odessa North | North Cowden | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8008-E | 2014-05-15 |  | 69 | 0 | 12.4 | 0 |  | Ector | Ector | Tier 4 |  |  |  |  | N | N | 2009-R4 |  | 3357 | 3186
14TPIT0010 | Handley - Pantego 138 kV line | Upgrade existing line |  | Handley | Pantego | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5155-E | 2022-05-15 |  | 138 | 0 | 3.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1950, 2245, 2247 | N | N |  |  | 2698 | 2582
14TPIT0011 | Midessa - Windwood - Midland East 138 kV Line | Upgrade existing line |  | Midessa | Midland East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8148-E | 2015-05-15 |  | 138 | 0 | 10.4 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1059, 1116, 1117 | Y | N |  |  | 3631 | 3431
14TPIT0012 | Mountain Creek - Norwood 138 kV line | Upgrade existing line |  | Mountain Creek | Norwood | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4074-E | 2018-05-15 |  | 138 | 0 | 7.2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2407, 2412, 2804, 2805, 12804 | Y | N |  |  | 3263 | 3094
14TPIT0015 | Troup - Walnut Grove - Whitehouse - Tyler Grande 138 kV line | Upgrade existing line | Construction schedule change | Troup | Tyler Grande | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6002-WAC | 2016-05-15 |  | 138 | 0 | 13.34 | 0 |  | Cherokee | Smith | Tier 4 |  |  |  | 3143, 3147, 3156, 3227 | Y | N |  |  | 1435 | 1434
14TPIT0016 | East Mesquite - Prairie Creek 138 kV line | Upgrade existing line |  | East Mesquite | Prairie Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4069-E | 2015-05-15 |  | 138 | 0 | 2.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2441, 2754, 2759 | Y | N | 2009-R19 |  | 1825 | 1783
14TPIT0021 | Buttercup-Whitestone Upgrade | Upgrade the 2.3-mile Buttercup (7531)-Whitestone (7529) 795 ACSR (220-MVA) 138-kV transmission line to bundled 795 ACSR (440MVA). The Wavetrap will be replaced at Whitestone uprating Blockhouse to Whitestone line to (221MVA, 221MVA, 221MVA). |  | Buttercup Substation | Whitestone Substation | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2014-03-06 |  | 138 | 0 | 2.3 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 7527, 7529, 7531 | Y | N |  |  | 1002 | 1001
14TPIT0029 | Lake Creek - Robinson 138 kV line | Rebuild 138 kV line |  | Lake Creek | Robinson | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R476 | 2021-05-15 |  | 138 | 0 | 8.3 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  | 3410, 3567 | N | N | 2007-R8 |  | 1353 | 1349
14TPIT0031 | Project to add new Auto #2 and moving existing #3 to new pos | Install one 600 MVA autotransformer and move current autotransformer #3 to new position. |  |  |  | Planned | T-0176 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0588 | 2014-10-01 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5052, 5058, 5054, 5055, 5430, 5056, 5057, 5059 | Y | N |  | There are no transmission line additions associated with this project | 2861 | 2736
14TPIT0031 | Project to add new Auto #2 and moving existing #3 to new pos | Install one 600 MVA autotransformer and move current autotransformer #3 to new position. |  |  |  | Planned | T-0176 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0588 | 2015-01-30 |  | 345 | 0 | 0 | 600 |  | Bexar | Bexar | Tier 4 |  |  |  | 5052, 5058, 5054, 5055, 5430, 5056, 5057, 5059 | Y | N |  | There are no transmission line additions associated with this project | 2862 | 2736
14TPIT0032 | Downing to Mountary | Existing 69 kV line. |  | Downing | Mountary | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 10044 | 2014-06-15 |  | 69 | 0 | 15 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  | 281, 294 | Y | N | 2009-R29 |  | 1065 | 1064
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 2000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | NEW | 2016-06-15 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 1 |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 2548 | 2443
14TPIT0040 | Springwoods 138kV Substation | Build new 138kV Springwoods distribution substation. Loop through Ckt.66 Rayford to Westfield. | Accelerated Project Schedule | Springwoods | Rayford-Louetta | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-04-30 |  | 138 | 6.2 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 46270, 46051, 46261 | Y | N |  |  | 2204 | 2132
14TPIT0041 | Coliseum to Kirby - 138 kV Transmission Line Rebuild | Rebuild 4.2 miles of 138 kV transmission line from Coliseum to Holbrook to Kirby and ensure a minimum conductor rating of 331 MVA |  | Colesium | Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0164 | 2017-12-01 |  | 138 | 0 | 4.2 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5095, 5160, 5218, 5250 | Y | N |  | There are no transformers associated with this project | 956 | 955
14TPIT0042 | Five Points to Broadview - 138 kV Transmission Line Rebuild | Rebuild 9.4 miles of 138 kV transmission line from Five Points to Broadview and ensure a minimum conductor rating of 331 MVA |  | Five Points | Broadview | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0208 | 2014-12-01 |  | 138 | 0 | 9.4 | 0 |  | Bexar | Bexar | Tier 3 |  |  |  | 5040, 5150 | Y | N |  | There are no transformers associated with this project | 957 | 956
14TPIT0043 | Tri-County - New 138kV Substation | Loop new 138kV substation into the existing Skyline to Wiederstein and Green Mountain to Parkway transmission lines. |  | Skyline-Green Mountain | Tri_County-Wiederstein Tri_County-Parkway | Planned | T-0191 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0620 | 2014-06-06 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5445, 5180, 5370, 7461, 7611 | Y | N |  | There are no transformers associated with this project | 959 | 958
14TPIT0044 | Helotes to Hill Country - 138 kV Substation Equipment Upgrad | Upgrade terminals at Helotes and Hill Country to ensure a 2420 A rating and remove existing MLSE on Helotes to Hill Country 138 kV transmission line |  | Helotes | Hill Country | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0651 | 2014-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5200, 5210, 5461 | Y | N |  | There are no transformers associated with this project | 964 | 963
14TPIT0045 | Anderson to Cagnon - 138 kV Substation Equipment Upgrade | Upgrade terminals at Anderson and Cagnon to ensure at 2420 A rating and remove the existing MLSE on Anderson to Cagnon 138kV transmission line |  | Anderson | Cagnon | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0479 | 2014-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5003, 5054 | Y | N |  | There are no transformers associated with this project | 955 | 954
14TPIT0046 | Hill Country to La Sierra - 138 kV Substation Equipment Upgr | Upgrade termainls at Hill Country and La Sierrra to ensure a 2420 A rating and remove the existing MLSE on Hill Country to La Sierra 138kV transmission line |  | Hill Country | La Sierra | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0485 | 2014-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5209, 5257 | Y | N |  | There are no transformers associated with this project | 965 | 964
14TPIT0047 | GPLTMPA_14TPIT0047_DentonLoopPhase2 | Denton 138kV System Upgrades Phase2. Reliability projects necessary for the Denton area. Reconductoring 138kV loop line segments from North Denton to Jim Christal to West Denton to Fort Worth to Teasley, etc. |  |  |  | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2014-06-04 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 916, 918, 919, 985, 986 | Y |  |  |  | 3790 | 3576
14TPIT0048 | Clear Fork Substation (aka Maxwell) | Construct 69kV-12.5kV distribution substation Clear Fork (7195) on T-519 between Reedville and Lockhart. |  | Clear Fork | Reedville-Lockhart | Planned |  | BBEC | Thomas Ellis thomas.ellis@bluebonnet.coop |  | 2014-05-30 |  | 69 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  | 7195, 7194, 7215 | Y | N |  |  | 1000 | 999
14TPIT0049 | Big Foot SW Station: Install 138 kV Ring Bus | Add CPS Lytle to ETT Lytle 795 ACSR 138 kV line and 93 MVA 69/138 kV autotransformer at Lytle | CHANGES | BIG FOOT |  | UNDER CONSTRUCTION | 028 - 0028 | AEP TCC | RICK MCCRAKKEN GAREED@AEP.COM 918-599-2664 | 1786 | 2014-04-01 |  | 138 | 0 | 0 | 0 |  | Frio |  | Tier 4 |  |  |  | 8221 | Y | N | NA | NA | 3671 | 3466
14TPIT0050 | Lon Hill to North Edinburg: Reconductor 345kV Line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo | Date Change | Lon Hill | North Edinburg | Planned | 071 - 0281 | AEP TCC | Michael Glueck 918-599-2664 | 3183 | 2016-01-31 |  | 345 | 0 | 122.88 | 0 |  | Nueces | Hidalgo | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 5660, 8455, 8452, 8905 | Y | N |  |  | 1420 | 1419
14TPIT0051 | North Edinburg: Replace 345 kV Series Capacitors | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo |  | North Edinburg |  | Under Construction | 071 - 0281 | AEP TCC | Michael Glueck 918-599-2664 | 3184 | 2014-04-30 |  | 345 | 0 | 0 | 0 | 0,933.1 | Hidalgo |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8383, 8901, 8905 | Y | N |  |  | 1890 | 1846
14TPIT0052 | Stanton East - Buffalo (SU) - Midland E138 kV line | Rebuild existing line |  | Midland East | Stanton East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8025-WAC | 2014-12-15 |  | 138 | 0 | 27.2 | 0 |  | Martin | Midland | Tier 4 |  |  |  | 1023, 1326, 79549, 79616 | Y | N |  |  | 3005 | 2832
14TPIT0053 | Moss - Westover 138 kV line | Reconductor existing line |  | Moss | Westover | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8016-E | 2014-12-15 |  | 138 | 0 | 3.4 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1019, 1129 | Y | N |  |  | 2806 | 2682
14TPIT0055 | Seagoville - Wilmer 138 kV line | Upgrade existing line |  | Seagoville | Wilmer | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4081-E | 2016-05-15 |  | 0 | 0 | 10.9 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2434, 3076, 3077, 3079, 3083 | Y | N |  |  | 2599 | 2494
14TPIT0056 | Northaven - Welch 138 kV line | Upgrade existing line |  | Northaven | Welch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4088-E | 2016-05-15 |  | 0 | 0 | 3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2657, 2658, 2660, 2661 | Y | N |  |  | 2598 | 2493
14TPIT0057 | Cedar Hill - Mayfield Tap North 138 kV line | Upgrade existing line |  | Cedar HIll Switch | Mayfield Tap North | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5041-E | 2023-05-15 |  | 138 | 0 | 4.3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 1912, 2422 | Y | N |  |  | 3101 | 2926
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | JORDAN |  | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-30 |  | 345 | 0 | 0 | 800 |  | Chambers |  | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2913 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | JORDAN | Cedar Bayou | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-30 |  | 345 | 0.2 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2914 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | JORDAN | Northbelt | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-30 |  | 345 | 0.2 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2915 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | JORDAN | BARHIL | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-02-26 |  | 138 | 0.87 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2916 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | JORDAN | RALYND | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-02-27 |  | 138 | 0.87 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2917 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | DUNCAN | ENPROD | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-02-28 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2922 | 2758
14TPIT0061 | Briarcrest to Atkins Upgrade | Upgrade to 795 ACSR to alleviate overload during double contingency situations. Add OPGW. Add new poles/structures. |  | Atkins | Briarcrest | Planned |  | BRYN | James Tanneberger 9798215763 |  | 2014-09-01 |  | 138 | 0 | 3.4 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32864, 32877 | Y |  |  |  | 2052 | 2001
14TPIT0062 | Kurten Substation Upgrade | Install (3) Breaker ring to support (2) existing 138 lines and (1) existing 138/12.5 transformer (No MOD changes necessary) |  |  |  | planned |  | BRYN | James Tanneberger 9798215763 |  | 2015-09-01 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 3041 | 2867
14TPIT0063 | Munday to BEC Munday: Rebuild 69 kV line | Rebuild Munday to BEC Munday 69 kV line with 795 ACSR |  | Munday | BEC Munday | Planned | 568 - 0742 | AEP TNC |  | 2572 | 2014-12-31 |  | 69 | 0 | 2.4 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 764, 6107 | Y | N |  |  | 1847 | 1804
14TPIT0064 | West Yates to Air Products: Rebuild 69 kV line | Rebuild West Yates to Air Products 69 kV line with 795 ACSS | Schedule Update | West Yates | Air Products | Planned | 570 - 0744 | AEP TNC |  | 2574 | 2015-12-31 |  | 69 | 0 | 2.28 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  | 6556, 6581 | Y | N |  |  | 1846 | 1803
14TPIT0065 | Rusthill: Build a new 138 kV ring bus station | Build new 138 kV four breaker ring bus station, Rusthill, reterminate the 138 kV lines from Concho into Rusthill and add 138/69 kV autotransformer capacity | Description Change | Rusthill |  | Planned | 567 - 0741 | AEP TNC | Eric Scott 918-599-2664 | 2571 | 2014-08-31 |  | 138 | 0 | 0 | 90 |  | Tom Green |  | Tier 4 |  |  |  | 61010, 61011, 6448, 6449, 6450, 6452, 6453 | Y | N |  |  | 3948 | 1795
14TPIT0066 | Jim Treece: Build new three breaker ring bus | Interconnect Blue Summit Wind Farm at Jim Treece to connect Blue Summit to the Riley to Tesla 345 kV line | Schedule Update | Jim Treece |  | Planned | 512 - 0724 | ETT | Dave Goetz 918-599-2664 | 2515 | 2014-06-30 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  | 61001, 61004, 6050, 6060, 6101, 60501 | Y | N |  |  | 1882 | 1838
14TPIT0067 | San Angelo Area: Replace both 345/138 kV autotransformers | Replace both 345/138 kV autotransformers at Red Creek with 800 MVA autotransformers | Cost, Description, and Tier Update | Red Creek |  | Planned | 566 - 0740 | AEP TNC |  | 2570 | 2017-05-31 |  | 345 | 0 | 0 | 800 |  | Tom Green |  | Tier 4 |  |  |  | 6295, 6769, 6444, 6442 | Y | N |  |  | 1867 | 1824
14TPIT0068 | Future 69kV upgrades & North Denton Auto Upgrade |  |  |  |  | Planned |  | DME | Chuck Sears 9403497111 |  | 2015-06-01 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 905, 915, 912, 985 | Y |  |  |  | 1425 | 1424
14TPIT0070 | New 138kV line from LaPalma to Palo Alto | Construct new La Palma ¿ Palo Alto 138 kV line (~12 mi) and station upgrades | New Changed Dollars to include the station costs associated with the project (Approved by RPG, see comments for breakout) | LaPalma | Palo Alto | Planned |  | SLU |  |  | 2014-06-01 |  | 138 | 12 | 0 | 0 |  | Cameron | Cameron | Tier 1 | 2011-05-03 | 2011-12-19 | 2012-01-17 | 8314, 5965 | Y | N |  |  | 2456 | 2367
14TPIT0071 | Princeton South - New Substation | Build a new 138-12.47 kV substation to accommodate load growth in Princeton. |  |  |  | Planned | 16TPIT0005 | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE02815 | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 37295 | Y | N |  |  | 2063 | 2011
14TPIT0072 | Las Pulgas Ringbus Expansion | Loop STEC radial 138 kV Raymondville #2 to East Raymondville line into Las Pulgas |  | Las Pulgas |  | Conceptual | 615 - 3446 | AEP TCC | Glen Reed 918-599-2664 | 516 | 2016-05-31 |  | 138 | 0 | 0 | 0 |  | Willacy |  | Tier 4 |  |  |  | 80309 | N | N |  | Associated STEC Project: 10TPIT0148 | 3309 | 3140
14TPIT0073 | Kokernut Substation | Build a new 138x69-26.18 kV 18-24-30 MVA substation on the GVEC Gonzales-GVEC Shiner 69 kV transmission line |  | Kokernut | Gonzales-Shiner | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2014-06-18 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7591, 7590, 7592 | Y | N |  |  | 2223 | 2151
14TPIT0074 | Thompson Creek to Snook Transmission Line | Build 6 miles of 1033ACSR transmission line (operated at 138 kV) to Snook substation. | The Thompson Creek to Koppe Bridge Line is now broken into two segments with different completion dates. | Thompson Creek | Snook Substation | planned |  | BRYN | James Tanneberger 979-821-5763 |  | 2014-12-01 |  | 138 | 2.4 | 3.6 | 0 |  | Brazos | Burleson | Tier 4 |  |  |  | 32857, 32863 | Y | N |  |  | 2050 | 1999
14TPIT0075 | Millican to BEC HWY 6Line | Build(6) miles of new 1033 ACSR energized at 138 kV to planned BEC HWY 6 substation as part of Dobbin Project |  | Millican Substation | BEC HWY 6 Substation | planned |  | BRYN | James Tanneberger 9798215763 |  | 2014-10-01 |  | 138 | 6 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 6, 32856 | Y | N |  |  | 2367 | 2292
14TPIT0076 | Fry Road 138kV Substation | Build new 138kV Fry Road distribution substation. Double tap off Ckt.09 Zenith - Gertie tap and Ckt.76 Zenith - Gertie tap. | Delay in Project Schedule | Fry Road | Zenith-Gertie | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-10-31 |  | 138 | 0.1 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 45811, 45812, 44910, 45801, 45802 | Y | N |  |  | 2424 | 2347
14TPIT0077 | PH Robinson Autotransformer Upgrade | Replace existing 400MVA PH Robinson autotransformer A1 with 800MVA autotransformer. |  | PH Robinson |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-31 |  | 345 | 0 | 0 | 400 |  | Galveston |  | Tier 4 |  |  |  | 42000, 42015, 49026 | Y | N |  |  | 2543 | 2438
14TPIT0078 | Advance Capacitor Bank | Install 15 MVAR at Advance substation |  | Advance | Advance | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12011 | 2014-12-01 |  | 69 | 0 | 0 | 0 | 0,15 | Parker |  | Tier 4 |  |  |  | 518 | Y | N |  |  | 2309 | 2236
14TPIT0079 | Glen Rose to Meridian Rebuild | Rebuild Glen Rose to Meridian with 959 ACSS, 138 kV construction (operate at 69 kV) |  | Glen Rose | Meridian | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12044 | 2021-07-01 |  | 69 | 0 | 18.18 | 0 |  | Somervell | Bosque | Tier 4 |  |  |  | 315, 319 | Y | N |  |  | 2310 | 2237
14TPIT0080 | Oran to Advance Rebuild | Rebuild Oran to Advance with 959 ACSS, 138 kV construction (operate at 69 kV) |  | Oran | Advance | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12010 | 2014-12-01 |  | 69 | 0 | 13.7 | 0 |  | Palo Pinto | Parker | Tier 4 |  |  |  | 518, 519, 785 | Y | N |  |  | 2311 | 2238
14TPIT0081 | Bowie Capacitor Bank | Install 15 MVAR at Bowie substation |  | Bowie | Bowie | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12012 | 2014-12-01 |  | 138 | 0 | 0 | 0 | 0,15 | Montague |  | Tier 4 |  |  |  | 620 | Y | N |  |  | 2727 | 2609
14TPIT0082 | Kenedy Switch to Pettus: Rebuild 69 kV line | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. | KENEDY SWITCHING STATION | PETTUS | UNDER CONSTRUCTION | 603-0765 | AEP TCC | FRANK PRITZLAFF GAREED@AEP.COM 918-599-2664 | 3473 | 2015-12-31 |  | 69 |  | 15.9 | 0 |  | Karnes | Bee | Tier 4 |  |  |  | 8184, 8188, 8593 | Y | N |  |  | 3669 | 3464
14TPIT0083 | Electra 69 kV capacitors | Install capacitors |  | Electra |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R561-WAC | 2014-05-15 |  | 69 | 0 | 0 | 0 | 0,9.2 | Wichita |  | Tier 4 |  |  |  | 1538 | Y | N |  |  | 1965 | 1914
14TPIT0084 | Buzzard Draw 138 kV Switching Station | Install 138 kV circuit breakers |  | Buzzard Draw |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8034-E | 2014-12-15 |  | 138 | 0 | 0 | 0 |  | Dawson |  | Tier 4 |  |  |  |  | Y | N |  |  | 3292 | 3123
14TPIT0085 | Lamesa Switching Station | Install 138 kV circuit breakers |  | Lamesa |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8033-E | 2014-12-15 |  | 138 | 0 | 0 | 0 |  | Howard |  | Tier 4 |  |  |  |  | Y | N |  |  | 3294 | 3125
14TPIT0086 | Allen Switch - Parker Maxwell Creek - Ben Davis 138 kV line | Reconductor existing 138 kV line |  | Allen Switch | Ben Davis Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4102-E | 2015-05-15 |  | 138 | 0 | 9.4 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 968, 2477, 2509, 12509 | Y | N |  |  | 2351 | 2278
14TPIT0089 | North Main Switch third transmission source | Construct a third 138 kV line into North Main Switch |  | North Main Tap | North Main Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5161-E | 2015-05-15 |  | 138 | 4.4 | 4.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1961, 2158, 2105, 3011 | Y | N |  |  | 3110 | 2941
14TPIT0090 | Monticello shunt reactors | Install shunt reactors |  | Monticello SES |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R919-WAC | 2014-05-15 |  | 345 | 0 | 0 | 0 | -100,0 | Titus |  | Tier 4 |  |  |  | 1695 | Y | N |  |  | 2349 | 2276
14TPIT0091 | Riley (Oklaunion) - Fisher Road 345 kV line relocation | Relocate 345 kV line |  | Oklaunion | Fisher Road | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R921-WAC | 2014-05-15 |  | 345 | 6.9 | 0 | 0 |  | Wilbarger | Wichita | Tier 4 |  |  |  | 1425, 6101 | Y | N |  |  | 3354 | 3183
14TPIT0092 | Temple Switch - Bell County East 345 kV line | Upgrade existing 345 kV line |  | Temple Switch | Bell County East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R764-E | 2022-05-15 |  | 345 | 0 | 24 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3414, 3687, 13434 | N | N |  |  | 2464 | 2375
14TPIT0093 | Paris Switch shunt reactor | Install shunt reactor |  | Paris Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R920-WAC | 2014-05-15 |  | 345 | 0 | 0 | 0 | -100,0 | Lamar |  | Tier 4 |  |  |  | 1692 | Y | N |  |  | 2348 | 2275
14TPIT0096 | Nevada-Olinger 138 kV line upgrade | Nevada-Olinger 138 kV line upgrade | On Hold For Funding | A new switch at new Nevada | A switch at Olinger | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2014-12-04 |  | 138 | 0 | 9.5 | 0 |  | Dallas |  | Tier 4 |  |  |  | 811, 818 | Y | N |  | This project is a new line for new load serving at Nevada | 2619 | 2514
14TPIT0097 | Colorado - Nada 138 kV Transmission Line Conversion | Convert the 20 mile Colorado (7636) - Nada (5536) 69-kV transmission line to 138-kV, 220 MVA. |  | Colorado | Nada | Planned | 13TPIT0150 (STEC) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-06-03 |  | 138 | 0 | 20 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  | 7636, 78103 | Y | N |  | Coordinate with STEC Coordinate with SBEC | 2775 | 2651
14TPIT0098 | Cost Substation Addition | Replace existing station, add 138x69kV-13.09x26.18 dual kV, 12/16/20 MVA PWT w/associated structures, bus, panels, etc |  | Cost |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2016-09-30 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7622 | Y | N |  |  | 3502 | 3321
14TPIT0099 | Treaschwig - Westfield Ckt.66 | Upgrade 138kV Ckt. 66 Treaschwig to Westfield to increase thermal ratings. |  | Treaschwig | Westfield | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 |  | 138 | 0 | 8.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 46550, 46570 | Y | N |  | Project is part of the 2012 ERCOT 5-Year Plan. | 2751 | 2630
14TPIT0100 | Tilden Capacitor | Add 19.2 MVAR capacitor |  | Tilden |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-06-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | McMullen |  | Tier 4 |  |  |  | 5701 | Y | N |  |  | 2661 | 2555
14TPIT0101 | Penwell 138 kV Switching Station | Construct new switching station |  | Penwell |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8106-E | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  | 1012, 1010, 1019 | Y | N |  |  | 2996 | 2823
14TPIT0103 | Moss Switching Station | Install 345 kV breakers |  | Moss |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8140-E | 2014-05-15 |  | 345 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  |  | Y | N |  |  | 3291 | 3122
14TPIT0104 | Mason 138 kV capacitors | Install shunt capacitors |  | Mason |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8085-WAC | 2014-05-15 |  | 138 | 0 | 0 | 0 | 0,52.4 | Reeves |  | Tier 4 |  |  |  | 1094 | Y | N |  |  | 2989 | 2816
14TPIT0105 | 69E LINE INSTALL |  |  | Wink | Pecos | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2014-07-01 |  | 69 | 0 | 32.8 | 0 |  | Reeves | Winkler | Tier 4 |  |  |  | 37920, 38090, 38150, 38180, 38230 | Y |  |  |  | 3677 | 3471
14TPIT0106 | SW Vernon to Vernon Main: Rebuild 69 kV line with 795 ACSS | SW Vernon to Vernon Main: Rebuild 69 kV line with 959.6 ACSS/TW |  | SW Vernon | Vernon Main | Planned | 315 - 0470 | AEP TNC | Dave Goetz 918-599-2664 | 3154 | 2014-08-31 |  | 69 | 0 | 4.6 | 0 |  | Wilbarger | Wilbarger | Tier 4 |  |  |  | 6062, 6063, 6079, 6058, 6061, 6064 | Y | Y |  |  | 3954 | 2755
14TPIT0107 | Bond Road: Add two 7.2 Mvar capacitor banks | Construct new Bond Road station along the Sonora to Uvalde 69 kV line and add two 7.2 Mvar capacitor banks |  | Bond Road |  | Planned | 587 - 0768 | AEP TNC | Rick McCracken gareed@aep.com 918-599-2664 | 2804 | 2014-07-31 |  | 69 | 0 | 0 | 0 | 0,14.4 | Sutton |  | Tier 4 |  |  |  | 6570, 6513, 8239 | Y | N |  |  | 2927 | 2761
14TPIT0108 | Kenedy 138/69 kV Switching Station: Upgrade | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. | CHANGES | KENEDY SWITCHING STATION |  | UNDER CONSTRUCTION | 603 - 0765 | AEP TCC | FRANK PRITZLAFF(AEP) GAREED@AEP.COM 918-599-2664 | 3482 | 2014-12-31 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  | 8186 | Y | N |  |  | 3683 | 3477
14TPIT0109 | Kenedy Switch to Tuleta: Build double circuit 138 kV line | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. | CHANGES | KENEDY SWITCHING STATION | TULETA | UNDER CONSTRUCTION | 603 - 0765 | AEP TCC | Frank Pritzlaff (AEP) gareed@aep.com 918-599-2664 | 3483 | 2015-05-31 |  | 138 | 16.9 | 16.9 | 0 |  | Karnes | Bee | Tier 4 |  |  |  | 8590, 8593, 8186 | Y | N | NA | NA | 3169 | 3000
14TPIT0110 | MCCABE 138kV Substation | Construct service to new 138kV MCCABE customer-owned substation. Loop through Ckt. 96 Bayou to Bimont. | Accelerated project schedule | MCCABE | Bayou/Bimont | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-04-30 |  | 138 | 0.2 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 42350, 41205, 41615, 42160, 40200, 41520 | Y | N |  |  | 2869 | 2742
14TPIT0111 | Connor 138kV Substation | Construct service to new 138kV CONNOR customer-owned substation. Loop through Ckt.86 Crosby to Bender |  | CONNOR | Crosby/Bender | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-04-29 |  | 138 | 1.8 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  | 40665, 40000, 40155, 40255, 40390, 40900, 41150, 46100 | Y | N |  |  | 2870 | 2743
14TPIT0118 | Permian Basin - Wink 138 kV line | Rebuild existing 138 kV line |  | Permian Basin | Wink | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8105-E | 2014-12-15 |  | 138 | 0 | 16.5 | 0 |  | Ward | Winkler | Tier 4 |  |  |  | 1010, 1074 | Y | N |  |  | 2998 | 2825
14TPIT0119 | Mason Road to Obrien Ckt25 | Upgrade substation equipment at Mason Road and Obrien to increase Ckt.25 thermal ratings. | Accelerated project schedule | Mason Road | Obrien | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  | 44450, 44510 | Y | N |  |  | 3049 | 2875
14TPIT0120 | Moore Road 138kV Substation | Build new 138kV Moore Road substation. Loop through Ckt.03 EXPLOR to Uvalde. | Delay in project schedule | Moore Road | EXPLOR/Uvalde | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-01-31 |  | 138 | 0.6 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40555, 40560, 41652 | Y | N |  |  | 3047 | 2873
14TPIT0121 | Channelview to CONIAL Ckt.84 Thermal Uprate | Upgrade 138kV Ckt.84 Channelview to CONIAL to increase thermal ratings. |  | Channelview | CONIAL | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40280, 40370, 40580, 40780, 40841, 41260, 41530, 41670 | Y | N |  |  | 3048 | 2874
14TPIT0122 | Bevo Station Addition | Construct a new 138-kV substation, Bevo (78280), which will cut into the LCRA TSC Asherton (8283) to Escondido (8260) 138-kV transmission line. |  | Asherton | Escondido | Planned | 14TPIT0059 (STEC) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-12-12 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  | 78280, 8283, 78281 | Y | N |  |  | 2418 | 2341
14TPIT0123 | Dimmit Substation Addition | Construct a new 138-kV substation, Dimmit (78281), on the LCRA Asherton to Rosita Creek 138-kV transmission line. |  | Asherton | Rosita Creek | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-08-30 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  | 78281, 8274, 8283 | Y | N |  |  | 3203 | 3034
14TPIT0124 | Menger Creek Transmission Line Addition | Add 2.9 miles of 138-kV bundled 795 ACSR, 440 MVA, to an existing single circuit to establish a double circuit between Menger Creek Tap (7663) - Menger Creek substation (7665) |  | Menger Creek | Menger Creek Tap | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-05-02 |  | 138 | 2.9 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7663, 5200, 7151, 7665 | Y | N |  |  | 3518 | 3335
14TPIT0125 | Plum - Flatonia Transmission Line Upgrade | Upgrade the 19.62 mile Plum (7274) - Flatonia (7248) 138-kV transmission line to 795 ACSR, 220 MVA |  | Plum | Flatonia | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-05-28 |  | 138 | 0 | 19.6 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  | 7248, 7274 | Y | N |  |  | 3127 | 2958
14TPIT0126 | Geronimo Substation Upgrade | Convert the 138-kV ring bus to a double bus-double breaker configuration and extend the 138-kV bus for termination of GVEC's McQueeney (7606) - Geronimo (7604) 138-kV transmission line. |  | Geronimo |  | Planned | 10TPIT0063, 15TPIT0029 | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-03-04 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 2 |  |  |  | 7604 | Y | N |  | Coordinate with GVEC | 3495 | 3315
14TPIT0127 | Purgatory Road Substation Addition | Construct the new Purgatory Road Substation (7489) on the PEC Sattler (7488) - Hunter (7491) 138-kV transmission line |  | Sattler | Hunter | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2014-11-28 |  | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 |  |  |  | 7489, 7488, 7491 | Y | N |  |  | 3205 | 3036
14TPIT0128 | Whitestone-Blockhouse | Replace under-rated limiting linr terminal equipment at Whitestone to increase Whitestone (7529)-Blockhouse (7527) to the conductor's rating. |  | Whitestone | Blockhouse | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2014-03-06 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  | 7527, 7529 | Y | N |  |  | 3213 | 3044
14TPIT0129 | Glidden to Colorado Transmission Upgrade to 138kV | Rebuild Rock Island, Sheridan, and Colorado substations to 138kV and convert to 138kV by tapping 138kV bus at Glidden substation. | ERCOT approval through RPG review process was granted March 27, 2012 | Glidden | Colorado | Planned | 13TPIT0150 | SBEC | Don Roberts droberts@sbec.org | WO#12-5327 WO#12-5328 WO#12-5329 WO#12-5330 WO#12-5331 | 2014-03-31 |  | 138 | 0 | 27 | 0 |  | Colorado | Colorado | Tier 3 |  |  |  | 7636, 7639, 7640, 77639, 77640, 5536, 7257, 7258 | Y | N |  |  | 3733 | 3526
14TPIT0130 | Triangle Park Substation | Install (3) Breaker ring to allow loop-in of 138 kV line (Dansby to Jack Creek) and 138 kV line to industrial customer. |  | Triangle Park | Triangle Park | planned |  | BRYN | James Tanneberger 9798215763 |  | 2014-10-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32854 | Y |  |  |  | 3305 | 3136
14TPIT0131 | Dansby to Triangle Park Tap | 138kV loop-in of Dansby to Jack Creek. Double circuit will be approximately 0.5 miles long. |  | Dansby | Triangle Park | Planned |  | BRYN | James Tanneberger 9798215763 |  | 2014-03-01 |  | 138 | 1 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 3666 | 3461
14TPIT0132 | Spraberry 69kV capacitors | Install shunt capacitors |  | Spraberry |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8164-WAC | 2014-05-15 |  | 69 | 0 | 0 | 0 | 0,55.2 | Midland |  | Tier 4 |  |  |  | 1330 | Y | N |  |  | 3003 | 2830
14TPIT0133 | Texaco Harvey 69 kV capacitors | Install shunt capacitors |  | Texaco Harvey |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8163-WAC | 2014-05-15 |  | 69 | 0 | 0 | 0 | 0,36.8 | Midland |  | Tier 4 |  |  |  | 1221 | Y | N |  |  | 3004 | 2831
14TPIT0134 | Ennis Creek 138 kV capacitors | Install shunt capacitors |  | Ennis Creek |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8188-WAC | 2014-05-15 |  | 138 | 0 | 0 | 0 | 0,73.6 | Scurry |  | Tier 4 |  |  |  | 1410 | Y | N |  |  | 3001 | 2828
14TPIT0135 | Midland Farms Substation conversion | Convert Midland Farms Substation to 138 kV operation |  | Midland Farms Tap | Midland Farms | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8168-WAC | 2014-05-15 |  | 138 | 0.1 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1266, 1264, 1282 | Y | N |  |  | 3006 | 2833
14TPIT0136 | Bakke Substation conversion | Convert Bakke Substation to 138 kV operation | Construction schedule change | Bakke Tap | Bakke | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8169-WAC | 2014-06-15 |  | 138 | 0 | 3 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1154, 1280, 1159, 1277, 1161 | Y | N |  |  | 2999 | 2826
14TPIT0137 | Odessa EHV - Odessa 138 kV Line | Reconductor existing 138 kV line |  | Odessa EHV | Odessa | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8143-E | 2014-12-15 |  | 138 | 0 | 2.3 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1027, 1126 | Y | N |  |  | 3002 | 2829
14TPIT0138 | Roanoke Switch - Southlake 138 kV Line | Rebuild existing line |  | Roanoke Switch | Southlake | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5001B-WAC | 2014-12-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1852, 2018, 2020 | Y | N |  | An interim rating increase for the Roanoke Switch - Roanoke West line section was implemented in July 2012. | 2689 | 2573
14TPIT0139 | WALKER 138kV Substation | Construct service to new 138kV WALKER customer-owned substation. Loop through Ckt.85 QUANUM to Cedar Bayou. |  | WALKER | QUANUM/ Cedar Bayou | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-06-01 |  | 138 | 0.4 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41440, 40010, 40070, 41330, 41500, 41610 | Y | N |  |  | 3147 | 2978
14TPIT0140 | Station: Construct new Bunsen 138 kV station | Construct a new 138 kV 4 breaker ring station to accommodate new TexStar T customer and 0.8 miles of double circuit 138 kV line |  | Lon Hill | Kingsville | Planned | 610 - 0778 | AEP TCC |  | 3493 | 2015-06-30 |  | 138 | 1.6 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8459, 8452, 8518 | Y |  |  |  | 3221 | 3052
14TPIT0141 | Add Preliminary SECO Info | Cut-In the Uvalde - Castroville 138 kV to a new breakered station |  | Uvalde | Castroville STEC | Planned | 611 - 0779 | AEP TCC |  | 3494 | 2015-03-01 |  | 138 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 8241, 5083, 8234 | Y |  |  |  | 3544 | 3355
14TPIT3257 | Smithers to Bellaire Ckt.98 | Upgrade 138kV Ckt.98 Smithers to Bellaire to increase thermal ratings. |  | Smithers | Bellaire | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-31 |  | 345 | 0 | 25.4 | 0 |  | Fort Bend | Harris | Tier 4 |  |  |  | 44650, 47000 | Y | N |  |  | 3431 | 3257
14TPIT3265 | Paredes switch new switching station for wind farm | A new swtiching station in the E Rio Hondo to Central 138 kV line |  | Paredes |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-06-01 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  | 5761, 5764, 5766 | Y | N |  |  | 3441 | 3265
14TPIT3344 | Katy Tap to Franz Ckt.09 | Upgrade 138kV Ckt.09 Katy tap to Franz to increase thermal ratings. |  | Katy | Franz | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-31 |  | 138 | 0 | 4.1 | 0 |  | Waller | Harris | Tier 4 |  |  |  | 44230, 44261, 44422, 45770, 44262, 44421 | Y | N |  |  | 3532 | 3344
14TPIT3346 | Clinton Conversion | Convert all Clinton load to 138kV. Convert Clinton 138kV from tap to loop service. |  | Clinto | Ninth/Anbush | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40350, 40351, 40352, 40235, 41160 | Y | N |  |  | 3534 | 3346
14TPIT3389 | Dunlavy to Hyde Park Ckt 32 Upgrade | Upgrade substation equipment at Dunlavy to increase Ckt.32 thermal ratings |  | Dunlavy | Hyde Park | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47580, 47690 | Y | N |  |  | 3587 | 3389
14TPIT3390 | Alvin Auto Removal | Disconnect Alvin Autotransformer A1. |  | Alvin Auto |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-31 |  | 138 | 0 | 0 | -83 |  | Brazoria |  | Tier 4 |  |  |  | 42130, 42140, 48001, 49086, 42651, 43260, 42820 | Y | N |  |  | 3588 | 3390
14TPIT3420 | Crosby to CONNOR Ckt.86 Reconductor | Reconductor Ckt.86 Crosby to CONNOR |  | Crosby | CONNOR | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-04-30 |  | 138 | 0 | 5.9 | 0 |  | Harris | Chambers | Tier 4 |  |  |  | 40390, 40665 | Y | N |  | Reconductor with test conductor. | 3620 | 3420
14tpit0059 | Bevo Station and Autotransformer | 69 kV bus and capacitor by June 2014. 138 kV and autotransformer by December 2014. |  | BEVO |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-06-02 |  | 69 | 0 | 0 |  | 0,9.6 | Dimmit |  | Tier 1 | 2012-04-01 | 2012-08-01 | 2012-09-01 | 5871, 5870, 5872, 78280 | Y | N |  |  | 3439 | 3264
14tpit0059 | Bevo Station and Autotransformer | 69 kV bus and capacitor by June 2014. 138 kV and autotransformer by December 2014. |  | BEVO |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-12-01 |  | 138 | 0 | 0 | 150 |  | Dimmit |  | Tier 1 | 2012-04-01 | 2012-08-01 | 2012-09-01 | 5871, 5870, 5872, 78280 | Y | N |  |  | 3440 | 3264
14tpit3417 | North Calliham Capacitor | Adds 9.6 MVAR capacitor to North Calliham |  | North Calliham |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-07-01 |  | 69 | 0 | 0 | 0 | 0,9.6 | McMullen |  | Tier 4 |  |  |  | 5698 | Y | N |  |  | 3617 | 3417
15TPIT0000 | Bird Pond Substation | Install (3) Breaker ring to include (2) 138 lines and (1) 138-12.5 transformer |  | Bird Pond | Bird Pond | planned |  | BRYN | James Tanneberger 9798215763 |  | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32858, 962, 964 | Y | N |  |  | 1855 | 1812
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into existing 138kV Deely to Skyline line |  | Converse | Deely-Skyline | Planned | T-0177 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0601 | 2016-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5098, 5110, 5368 | Y | N |  | There are no transformers associated with this project | 968 | 967
15TPIT0007 | Green Mountain to Stonegate - 138kV 2nd Circuit | Build second 138kV transmission line from Green Mountain to Stonegate on existing transmission structures |  | Green Mountain | Stonegate | Planned | S-0608 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0179 | 2015-06-01 |  | 138 | 11.5 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5180, 5415 | Y | N |  | There are no transformers associated with this project | 970 | 969
15TPIT0008 | Triple R - New Substation | Build a 138-26.18kV. 40 MVA substation on the GVEC Wilson-Sutherland Springs (T549) 138 kV transmission line |  | Triple R | Wilson/Sutherland Springs | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-12-30 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  | 7239 | Y | N |  |  | 3562 | 3367
15TPIT0011 | Shannon to Montague | Rebuild Shannon to Montague 69 kV line with 959 ACSS. |  | Shannon | Montague | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 10045 | 2015-06-01 |  | 69 | 0 | 23.36 | 0 |  | Clay | Montague | Tier 4 |  |  |  | 768, 769, 772, 1548 | Y | N |  |  | 2536 | 2431
15TPIT0018 | Kerrville Stadium to Raymond F. Barker | Upgrade the 10.1-mile Kerrville Stadium (7136) - Kerrville Travis (7162) - Kerrville Legion (7160) - Raymond F. Barker (7159) 69 kV transmission lines to 795 ACSR, 138 kV (220 MVA - 920 Amperes) and OPGW. |  | Kerrville Stadium | Raymond F Barker | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2015-01-09 |  | 138 | 0 | 10.1 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  | 7136, 7159, 7160, 7162, 7138, 7158 | Y | N |  | Coordinate with KPUB | 1006 | 1005
15TPIT0019 | Blockhouse (7527) | Add a 31.2 MVAR Capacitor Bank at the Blockhouse (7527) substation | Project moved up due to outage schedules on Buttercup-Whitestone project, Material Lead times result delay to Feb 2014. Still on schedule to coordinate with BC-WS outages. | Blockhouse |  | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2014-02-28 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson |  | Tier 4 |  |  |  | 7527 | Y | N |  |  | 1007 | 1006
15TPIT0020 | Braunig to Highland Hills-Brooks - 138 kV Substation Equipme | Replace Line and Bus Switches at Brooks and ensure a 1385 A rating and remove existing MLSE on the Brooks to Southton 138 kV transmission line |  | Braunig_W | Highland Hills-Brooks | Planned | T-0194 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0669 | 2018-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  |  | 5030, 5045, 5175, 5205, 5394 | Y | N |  | There are no transformers associated with this project | 2385 | 2309
15TPIT0023 | Seaton Auto | Upgrade 138-69 kV auto to 100 MVA |  | Seaton | Seaton | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 11036 | 2015-06-01 |  | 138 | 0 | 0 | 100 |  | Bell |  | Tier 4 |  |  |  | 131, 130 | Y | N |  |  | 1188 | 1185
15TPIT0024 | Lon Hill to Nelson Sharpe: Reconductor 345kV Line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo | Date Change | Lon Hill | Nelson Sharpe | Planned | 071 - 0281 | AEP TCC | Michael Glueck 918-599-2664 | 3180 | 2016-04-30 |  | 345 | 0 | 20.81 | 0 |  | Nueces | Kleberg | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8455, 85000 | Y | N |  |  | 1422 | 1421
15TPIT0025 | Monticello SES - Monticello Tap 138 kV line | Reconductor existing 138 kV line |  | Monticello SES | Monticello Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R906-E | 2015-12-15 |  | 138 | 0 | 20.1 | 0 |  | Titus | Franklin | Tier 4 |  |  |  | 1791, 1794, 1795 | Y | N |  |  | 2767 | 2643
15TPIT0026 | Wellborn to Millican Upgrade | ReBuild-Reconductor (3.6) miles of 69kV line converting to 138 kV as part of 138 kV BEC Roans Prairie Project |  | Wellborn Susbstation | Millican Substation | planned |  | BRYN | James Tanneberger 9798215763 |  | 2014-10-01 |  | 138 | 0 | 3.6 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32856, 32895 | Y | N |  |  | 1833 | 1790
15TPIT0027 | Millican Substation Upgrade | Install (3) Breaker ring to support (2) 138kV lines and (1) 138-69 auto-transformer |  | Millican Substation | Millican Substation | planned |  | BRYN | James Tanneberger 9798215763 |  | 2014-10-01 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32855, 32898, 32889, 32895, 32856 | Y | N |  |  | 1834 | 1791
15TPIT0029 | CMC Tap to CMC (SMI) 138kV Transmission Line | Build 2 miles of new double ckt 138kV t-line loop, 1192 ACSR between CMC Tap and CMC (SMI) substation. |  | CMC Tap | CMC (SMI) | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2015-10-31 |  | 138 | 2.2 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7602, 7604, 7606 | Y | N |  |  | 3403 | 3230
15TPIT0030 | Mainland - New Substation | Build a new 138-12.47 kV substation to accommodate load growth along I45 between Texas City and Dickinson. Cut TNMP's Freeway Park - Alvin 138 kV line into the new substation. |  | Mainland |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38830, 38820, 39030 | Y | N |  |  | 2089 | 2025
15TPIT0031 | Brooks to Chavaneaux - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from Brooks to Chavaneaux |  | Brooks | Chavaneaux | Conceptual | S-0733 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0207 | 2021-06-01 |  | 138 | 0.1 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5030, 5045, 5085, 5330 | N | N |  | There are no transformers associated with this project | 2380 | 2304
15TPIT0032 | Fort Sam to Tenth Street - 138 kV Transmission Line Rebuild | Rebuild approximately five circuit miles of 138 kV transmission from Ft. Sam to Tenth Street |  | Fort Sam | Tenth St | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0188 | 2015-12-01 |  | 138 | 0 | 5 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5160, 5420 | Y | N |  | There are no transformers associated with this project | 2381 | 2305
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and-or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle-Weiderstein | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0645b | 2015-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5360, 5435 | Y | N |  | There are no transformers associated with this project | 2382 | 2306
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0034A - Upgrade Ckt.47 Velasco to Freeport 15TPIT0034B - Convert Ckt.47 Velasco to Freeport to 138kV 15TPIT0034C - Upgrade Ckt.47 Freeport to Quintana 15TPIT0034D - Convert Ckt.47 Freeport to Quintana to 138kV 15TPIT0034E - Convert to 138kV Ckt.47 Freeport to Bryan 15TPIT0034F - Upgrade Ckt.47 Surfside to Quintana 15TPIT0034G - Convert Ckt.47 Surfside to Quintana to 138kV 15TPIT0034H - Upgrade Ckt.10 Velasco to Surfside 15TPIT0034I - Convert Ckt.10 Velasco to Surfside to 138kV |  | Velasco | Freeport | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-25 |  | 69 | 0 | 4.5 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 42640, 42645, 43135, 43310, 43315, 43435, 44205, 43360, 43370 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost shown is for all project phases. | 2491 | 2389
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0034A - Upgrade Ckt.47 Velasco to Freeport 15TPIT0034B - Convert Ckt.47 Velasco to Freeport to 138kV 15TPIT0034C - Upgrade Ckt.47 Freeport to Quintana 15TPIT0034D - Convert Ckt.47 Freeport to Quintana to 138kV 15TPIT0034E - Convert to 138kV Ckt.47 Freeport to Bryan 15TPIT0034F - Upgrade Ckt.47 Surfside to Quintana 15TPIT0034G - Convert Ckt.47 Surfside to Quintana to 138kV 15TPIT0034H - Upgrade Ckt.10 Velasco to Surfside 15TPIT0034I - Convert Ckt.10 Velasco to Surfside to 138kV |  | Velasco | Freeport | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-26 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 42640, 42645, 43135, 43310, 43315, 43435, 44205, 43360, 43370 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost shown is for all project phases. | 2492 | 2389
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0034A - Upgrade Ckt.47 Velasco to Freeport 15TPIT0034B - Convert Ckt.47 Velasco to Freeport to 138kV 15TPIT0034C - Upgrade Ckt.47 Freeport to Quintana 15TPIT0034D - Convert Ckt.47 Freeport to Quintana to 138kV 15TPIT0034E - Convert to 138kV Ckt.47 Freeport to Bryan 15TPIT0034F - Upgrade Ckt.47 Surfside to Quintana 15TPIT0034G - Convert Ckt.47 Surfside to Quintana to 138kV 15TPIT0034H - Upgrade Ckt.10 Velasco to Surfside 15TPIT0034I - Convert Ckt.10 Velasco to Surfside to 138kV |  | Freeport | Quintana | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-27 |  | 69 | 0 | 3.9 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 42640, 42645, 43135, 43310, 43315, 43435, 44205, 43360, 43370 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost shown is for all project phases. | 2493 | 2389
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0034A - Upgrade Ckt.47 Velasco to Freeport 15TPIT0034B - Convert Ckt.47 Velasco to Freeport to 138kV 15TPIT0034C - Upgrade Ckt.47 Freeport to Quintana 15TPIT0034D - Convert Ckt.47 Freeport to Quintana to 138kV 15TPIT0034E - Convert to 138kV Ckt.47 Freeport to Bryan 15TPIT0034F - Upgrade Ckt.47 Surfside to Quintana 15TPIT0034G - Convert Ckt.47 Surfside to Quintana to 138kV 15TPIT0034H - Upgrade Ckt.10 Velasco to Surfside 15TPIT0034I - Convert Ckt.10 Velasco to Surfside to 138kV |  | Freeport | Quintana | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-28 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 42640, 42645, 43135, 43310, 43315, 43435, 44205, 43360, 43370 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost shown is for all project phases. | 2494 | 2389
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0034A - Upgrade Ckt.47 Velasco to Freeport 15TPIT0034B - Convert Ckt.47 Velasco to Freeport to 138kV 15TPIT0034C - Upgrade Ckt.47 Freeport to Quintana 15TPIT0034D - Convert Ckt.47 Freeport to Quintana to 138kV 15TPIT0034E - Convert to 138kV Ckt.47 Freeport to Bryan 15TPIT0034F - Upgrade Ckt.47 Surfside to Quintana 15TPIT0034G - Convert Ckt.47 Surfside to Quintana to 138kV 15TPIT0034H - Upgrade Ckt.10 Velasco to Surfside 15TPIT0034I - Convert Ckt.10 Velasco to Surfside to 138kV |  | Freeport | Bryan | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-29 |  | 138 | 0 | 2.4 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 42640, 42645, 43135, 43310, 43315, 43435, 44205, 43360, 43370 | Y |  |  | Part of ERCOT RPG Freeport Area Upgrades. Cost shown is for all project phases. | 3527 | 2389
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0034A - Upgrade Ckt.47 Velasco to Freeport 15TPIT0034B - Convert Ckt.47 Velasco to Freeport to 138kV 15TPIT0034C - Upgrade Ckt.47 Freeport to Quintana 15TPIT0034D - Convert Ckt.47 Freeport to Quintana to 138kV 15TPIT0034E - Convert to 138kV Ckt.47 Freeport to Bryan 15TPIT0034F - Upgrade Ckt.47 Surfside to Quintana 15TPIT0034G - Convert Ckt.47 Surfside to Quintana to 138kV 15TPIT0034H - Upgrade Ckt.10 Velasco to Surfside 15TPIT0034I - Convert Ckt.10 Velasco to Surfside to 138kV |  | Surfside | Quintana | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-30 |  | 69 | 0 | 2.1 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 42640, 42645, 43135, 43310, 43315, 43435, 44205, 43360, 43370 | Y |  |  | Part of ERCOT RPG Freeport Area Upgrades. Cost shown is for all project phases. | 3528 | 2389
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0034A - Upgrade Ckt.47 Velasco to Freeport 15TPIT0034B - Convert Ckt.47 Velasco to Freeport to 138kV 15TPIT0034C - Upgrade Ckt.47 Freeport to Quintana 15TPIT0034D - Convert Ckt.47 Freeport to Quintana to 138kV 15TPIT0034E - Convert to 138kV Ckt.47 Freeport to Bryan 15TPIT0034F - Upgrade Ckt.47 Surfside to Quintana 15TPIT0034G - Convert Ckt.47 Surfside to Quintana to 138kV 15TPIT0034H - Upgrade Ckt.10 Velasco to Surfside 15TPIT0034I - Convert Ckt.10 Velasco to Surfside to 138kV |  | Surfside | Quintana | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 42640, 42645, 43135, 43310, 43315, 43435, 44205, 43360, 43370 | Y |  |  | Part of ERCOT RPG Freeport Area Upgrades. Cost shown is for all project phases. | 3529 | 2389
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0034A - Upgrade Ckt.47 Velasco to Freeport 15TPIT0034B - Convert Ckt.47 Velasco to Freeport to 138kV 15TPIT0034C - Upgrade Ckt.47 Freeport to Quintana 15TPIT0034D - Convert Ckt.47 Freeport to Quintana to 138kV 15TPIT0034E - Convert to 138kV Ckt.47 Freeport to Bryan 15TPIT0034F - Upgrade Ckt.47 Surfside to Quintana 15TPIT0034G - Convert Ckt.47 Surfside to Quintana to 138kV 15TPIT0034H - Upgrade Ckt.10 Velasco to Surfside 15TPIT0034I - Convert Ckt.10 Velasco to Surfside to 138kV |  | Velasco | Surfside | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-01-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 42640, 42645, 43135, 43310, 43315, 43435, 44205, 43360, 43370 | Y |  |  | Part of ERCOT RPG Freeport Area Upgrades. Cost shown is for all project phases. | 3531 | 2389
15TPIT0035 | Velasco to West Columbia Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0035A - Convert Retrieve substation to 138kV and energize with existing Ckt. 02 Lake Jackson to West Columbia. Upgrade Ckt. 02 Lake Jackson to Retrieve and parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035B - Upgrade Ckt. 02 Retrieve to West Columbia. Parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035C - Parallel bundle a portion of Ckt. 02 Hofman to Lake Jackson with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035D - Parallel bundle a portion of Ckt. 02 BASF to Hofman with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035E - Parallel bundle a portion of Ckt. 02 Brazosport to Velasco with converted 69kV Ckt.47 Velasco to West Columbia. |  | Lake Jackson | Retrieve | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-27 |  | 138 | 0 | 5.34 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43140, 43145, 43370, 49032, 42150, 42210, 42640, 42810, 42880, 43222, 43380, 43390, 43360 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades; Cost shown is for all project phases | 2485 | 2388
15TPIT0035 | Velasco to West Columbia Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0035A - Convert Retrieve substation to 138kV and energize with existing Ckt. 02 Lake Jackson to West Columbia. Upgrade Ckt. 02 Lake Jackson to Retrieve and parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035B - Upgrade Ckt. 02 Retrieve to West Columbia. Parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035C - Parallel bundle a portion of Ckt. 02 Hofman to Lake Jackson with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035D - Parallel bundle a portion of Ckt. 02 BASF to Hofman with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035E - Parallel bundle a portion of Ckt. 02 Brazosport to Velasco with converted 69kV Ckt.47 Velasco to West Columbia. |  | Retrieve | West Columbia | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-28 |  | 138 | 0 | 11.9 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43140, 43145, 43370, 49032, 42150, 42210, 42640, 42810, 42880, 43222, 43380, 43390, 43360 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades; Cost shown is for all project phases | 2486 | 2388
15TPIT0035 | Velasco to West Columbia Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0035A - Convert Retrieve substation to 138kV and energize with existing Ckt. 02 Lake Jackson to West Columbia. Upgrade Ckt. 02 Lake Jackson to Retrieve and parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035B - Upgrade Ckt. 02 Retrieve to West Columbia. Parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035C - Parallel bundle a portion of Ckt. 02 Hofman to Lake Jackson with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035D - Parallel bundle a portion of Ckt. 02 BASF to Hofman with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035E - Parallel bundle a portion of Ckt. 02 Brazosport to Velasco with converted 69kV Ckt.47 Velasco to West Columbia. |  | Hofman | Lake Jackson | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-29 |  | 138 | 0 | 3.9 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43140, 43145, 43370, 49032, 42150, 42210, 42640, 42810, 42880, 43222, 43380, 43390, 43360 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades; Cost shown is for all project phases | 2487 | 2388
15TPIT0035 | Velasco to West Columbia Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0035A - Convert Retrieve substation to 138kV and energize with existing Ckt. 02 Lake Jackson to West Columbia. Upgrade Ckt. 02 Lake Jackson to Retrieve and parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035B - Upgrade Ckt. 02 Retrieve to West Columbia. Parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035C - Parallel bundle a portion of Ckt. 02 Hofman to Lake Jackson with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035D - Parallel bundle a portion of Ckt. 02 BASF to Hofman with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035E - Parallel bundle a portion of Ckt. 02 Brazosport to Velasco with converted 69kV Ckt.47 Velasco to West Columbia. |  | BASF | Hofman | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-30 |  | 138 | 0 | 0.84 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43140, 43145, 43370, 49032, 42150, 42210, 42640, 42810, 42880, 43222, 43380, 43390, 43360 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades; Cost shown is for all project phases | 2488 | 2388
15TPIT0035 | Velasco to West Columbia Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0035A - Convert Retrieve substation to 138kV and energize with existing Ckt. 02 Lake Jackson to West Columbia. Upgrade Ckt. 02 Lake Jackson to Retrieve and parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035B - Upgrade Ckt. 02 Retrieve to West Columbia. Parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035C - Parallel bundle a portion of Ckt. 02 Hofman to Lake Jackson with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035D - Parallel bundle a portion of Ckt. 02 BASF to Hofman with converted 69kV Ckt.47 Velasco to West Columbia. 15TPIT0035E - Parallel bundle a portion of Ckt. 02 Brazosport to Velasco with converted 69kV Ckt.47 Velasco to West Columbia. |  | Brazosport | Velasco | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 |  | 138 | 0 | 1.32 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43140, 43145, 43370, 49032, 42150, 42210, 42640, 42810, 42880, 43222, 43380, 43390, 43360 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades; Cost shown is for all project phases | 2489 | 2388
15TPIT0036 | Bethel Area Improvements | Build Bethel Switching Station, Rebuild Sardis to Reqgor Springs with 959 ACSS and 138 kV construction. Relocate Auto from Sardis to Bethel Switching Station. Connect Bethel Switching Station to Oncor's 138 kV system in the area (Ennis to Waxahachie 138 |  | Multiple | Multiple | conceptual |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12016 | 2015-12-01 |  | 138 | 14 | 4 | 40 |  | Ellis | Ellis | Tier 4 |  |  |  | 202, 204, 205, 203, 2241, 210, 2321 | Y | N | load serving project: improvments are requires to serve furture Enterprise pipleline pumping stations |  | 2313 | 2240
15TPIT0039 | Plano Tennyson Road - McDermott | Upgrade 138 kV line |  | Plano Tennyson Road | McDermott | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4103-E | 2015-05-15 |  | 138 | 0 | 5.3 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 2523, 10010, 2516 | Y | N |  |  | 2346 | 2273
15TPIT0040 | Temple Switch 345-138 kV autotransformer | Replace existing autotransformer |  | Temple |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R758-E | 2017-05-15 |  | 345 | 0 | 0 | 600 |  | Bell |  | Tier 4 |  |  |  | 3414, 13415, 13414 | Y | N |  |  | 2465 | 2376
15TPIT0041 | Knob Creek 345 kV Switching Station Phase II | Expand 345 kV switching station |  | Knob Creek |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R749B-E | 2015-05-15 |  | 345 | 0 | 0 | 0 |  | Bell |  | Tier 4 |  |  |  | 3413, 3414, 3699 | Y | N |  |  | 3272 | 3103
15TPIT0042 | FM 237 Yorktown Substation | Replace T1, 138kV-26.18 kV, 30 MVA PWT w/associated bus, structures, panels, etc. |  | FM 237 |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2014-12-30 |  | 138 | 0 | 0 | 0 |  | DeWitt |  | Tier 4 |  |  |  | 78191 | Y | N |  |  | 3501 | 3320
15TPIT0043 | Fort Bend Area Upgrades | Multi-Phase Project: 15TPIT0043A - Convert FOSTER substation from 69kv service to 138kv tap off of Ckt.25 Flewellen - Peters 15TPIT0043B - Remove COLLIN substation from CNP transmission service 15TPIT0043C - Remove Richmond substation from CNP transmission service 15TPIT0043D - Convert 69kv Rosenberg substation to 138kv and reconfigure existing circuits to create new Ckt.60 Orchard - Rosenberg - Fort Bend. 15TPIT0043E - Remove 69kv facilities at Flewellen substaton and reconfigure existing circuit to create new Ckt.49 Flewellen - Fort Bend. |  | Richmond |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-03-29 |  | 69 | 0 | 0 | 0 |  | Fort Bend |  | Tier 3 | 2012-09-14 | 2012-10-29 |  | 44160, 44240, 44250, 44255, 44580, 44610, 44611, 49013, 44010, 44070, 44171, 44230, 44290, 44300, 44540, 44280, 44341, 46220 | Y | N |  | Cost shown is for all project phases | 2895 | 2636
15TPIT0043 | Fort Bend Area Upgrades | Multi-Phase Project: 15TPIT0043A - Convert FOSTER substation from 69kv service to 138kv tap off of Ckt.25 Flewellen - Peters 15TPIT0043B - Remove COLLIN substation from CNP transmission service 15TPIT0043C - Remove Richmond substation from CNP transmission service 15TPIT0043D - Convert 69kv Rosenberg substation to 138kv and reconfigure existing circuits to create new Ckt.60 Orchard - Rosenberg - Fort Bend. 15TPIT0043E - Remove 69kv facilities at Flewellen substaton and reconfigure existing circuit to create new Ckt.49 Flewellen - Fort Bend. |  | Flewellen | Fort Bend | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-31 |  | 138 | 0 | 9.3 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 2012-09-14 | 2012-10-29 |  | 44160, 44240, 44250, 44255, 44580, 44610, 44611, 49013, 44010, 44070, 44171, 44230, 44290, 44300, 44540, 44280, 44341, 46220 | Y | N |  | Cost shown is for all project phases | 2897 | 2636
15TPIT0043 | Fort Bend Area Upgrades | Multi-Phase Project: 15TPIT0043A - Convert FOSTER substation from 69kv service to 138kv tap off of Ckt.25 Flewellen - Peters 15TPIT0043B - Remove COLLIN substation from CNP transmission service 15TPIT0043C - Remove Richmond substation from CNP transmission service 15TPIT0043D - Convert 69kv Rosenberg substation to 138kv and reconfigure existing circuits to create new Ckt.60 Orchard - Rosenberg - Fort Bend. 15TPIT0043E - Remove 69kv facilities at Flewellen substaton and reconfigure existing circuit to create new Ckt.49 Flewellen - Fort Bend. |  | Rosenberg | Orchard/Fort Bend | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-11-29 |  | 138 | 0 | 1.5 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 2012-09-14 | 2012-10-29 |  | 44160, 44240, 44250, 44255, 44580, 44610, 44611, 49013, 44010, 44070, 44171, 44230, 44290, 44300, 44540, 44280, 44341, 46220 | Y | N |  | Cost shown is for all project phases | 2898 | 2636
15TPIT0043 | Fort Bend Area Upgrades | Multi-Phase Project: 15TPIT0043A - Convert FOSTER substation from 69kv service to 138kv tap off of Ckt.25 Flewellen - Peters 15TPIT0043B - Remove COLLIN substation from CNP transmission service 15TPIT0043C - Remove Richmond substation from CNP transmission service 15TPIT0043D - Convert 69kv Rosenberg substation to 138kv and reconfigure existing circuits to create new Ckt.60 Orchard - Rosenberg - Fort Bend. 15TPIT0043E - Remove 69kv facilities at Flewellen substaton and reconfigure existing circuit to create new Ckt.49 Flewellen - Fort Bend. |  | FOSTER | Peters/Flewellen | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-27 |  | 138 | 0 | 1.3 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 2012-09-14 | 2012-10-29 |  | 44160, 44240, 44250, 44255, 44580, 44610, 44611, 49013, 44010, 44070, 44171, 44230, 44290, 44300, 44540, 44280, 44341, 46220 | Y | N |  | Cost shown is for all project phases | 2899 | 2636
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  | 5705 | Y | N |  |  | 2660 | 2554
15TPIT0045 | ETP Capacitor | Add 19.2 MVAR capacitor |  | ETP |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-06-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | Jackson |  | Tier 4 |  |  |  | 5523 | Y | N |  |  | 2659 | 2553
15TPIT0046 | Permian Basin - Culberson 138 kV line | Construct new line. | Timing change | Permian Basin | Culberson | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8070-E | 2016-12-15 |  | 138 | 80 | 0 | 0 |  | Ward | Culberson | Tier 1 | 2013-02-15 | 2013-02-15 |  | 1010, 1097 | Y | N |  |  | 2305 | 2232
15TPIT0047 | Permian Basin - Moss 345 kV Line | Construct new double-circuit line. | Studies indicated project timing should be changed | Moss | Permian Basin | Conceptual | R8135-E & R8100B-E | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8100C-E | 2024-07-15 |  | 345 | 90 | 0 | 0 |  | Ector | Ward | Tier 1 | 2013-02-15 | 2013-09-15 |  | 1018, 11010 | N | N |  |  | 3008 | 2835
15TPIT0048 | Odessa EHV - Moss 345 kV Line | Add second circuit to an existing line | Studies indicated project timing should be changed | Odessa EHV | Moss | Conceptual | R8100-E & R8100B-E | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8135- E | 2024-07-15 |  | 345 | 15 | 0 | 0 |  | Ector | Ector | Tier 1 | 2013-02-15 | 2013-09-15 |  | 1028, 11010 | N | N |  | Estimated cost is included in total estimated cost for 15TPIT0047. | 2701 | 2585
15TPIT0049 | Permian Basin 345 kV Switching Station | Construct 345 kV switching station and install 345/138 kV autotransformer | Studies indicated project timing should be changed | Permian Basin |  | Conceptual | R8100C-E & R8100B-E | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8100B-E | 2024-07-15 |  | 345 | 0 | 0 | 600 |  | Ward |  | Tier 1 | 2013-02-15 |  | 2013-09-15 | 11010, 1010 | N | N |  | Estimated cost is included in total estimated cost for 15TPIT0047. | 3009 | 2836
15TPIT0050 | Loxley 138kV substation: STEC Interconnect | Loxley 138kV substation: STEC Interconnect. Loxley in service 6/2/2016 | Date Change | Pleasanton | Trumbo (CPS) | Planned | 044 - 0420 | AEP TCC | Glen Reed 918-599-2664 | 3472 | 2016-06-02 |  | 138 | 0 | 0 | 0 |  | Atascosa | Atascosa | Tier 4 |  |  |  | 80491, 5429, 8203 | Y | N |  |  | 3219 | 3050
15TPIT0051 | Kenedy Switch - Nixon - Seguin Transmission Line Upgrade | Upgrade the 54.2 mile Kenedy Switch (8184) - Nixon (78580) - Deer Creek (New) (7595) from 69kV to 138kV 795 ACSR Drake, 223 MVA. |  | Kenedy Switch | Deer Creek | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2016-06-16 |  | 138 | 0 | 54.2 | 0 |  | Karnes | Guadalupe | Tier 1 | 2012-09-01 | 2012-10-30 | 2013-03-31 | 78580 | Y | N |  |  | 3969 | 3725
15TPIT0052 | Molina to Wormser: Cut-In | Construct 345 kV circuit from Lobo to Molina energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Molina 138kV stations. | CHANGES | MOLINA | WORMSER | UNDER CONSTRUCTION | 206-0288 | AEP TCC | KENNETH 'RICH' HALEY GAREED@AEP.COM 918-599-2664 | 38190 | 2015-05-31 |  | 138 | 0.5 | 0 | 0 |  | Webb | Webb | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 8277, 80230 | Y | N | NA | NA | 3704 | 3497
15TPIT0053 | Molina to Zapata: Cut-In | Construct 345 kV circuit from Lobo to Molina energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Molina 138kV stations. | CHANGES | MOLINA | ZAPATA | UNDER CONSTRUCTION | 206-0288 | AEP TCC | KENNETH 'RICH' HALEY GAREED@AEP.COM 918-599-2664 | 38191 | 2015-05-31 |  | 138 | 2 |  | 0 |  | Webb | Webb | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 8646, 8985, 80230 | Y | N | NA | NA | 3703 | 3496
15TPIT0054 | Barney Davis To Naval Base Construct 138 kV line | Construct new 138 kV line and add tranformation at Naval Base to remove contingency overloads during off-peak maintenance | CHANGES | BARNEY DAVIS | NAVAL BASE | PLANNED | 607-0648 | AEP TCC | JOHN PULAY GAREED@AEP.COM 918-599-2664 | 3484 | 2016-10-31 |  | 138 | 7 | 0 | 0 |  | Nueces | Nueces | Tier 1 | 2013-07-15 | 2013-12-20 | 2013-01-24 | 8458, 8997 | Y | N | NA | NA | 3726 | 3519
15TPIT0055 | Naval Base Station: Add 138/69 kV Auto | Construct new 138 kV line and add tranformation at Naval Base to remove contingency overloads during off-peak maintenance | CHANGES | NAVAL BASE |  | Under Construction | 607 - 0648 | AEP TCC | MICHAEL GLUECK GAREED@AEP.COM 918-599-2664 | 3485 | 2015-05-31 |  | 138 | 7 | 0 | 220 |  | Nueces |  | Tier 1 | 2012-07-15 | 2012-12-20 | 2013-01-04 | 8997, 8495 | Y | N | NA | NA | 3721 | 3514
15TPIT0057 | Wylie 138 kV new switchyard and connections | Wylie 138 kV switchyard and its connections to Olinger, to Firewheel, to Elm Grove, and to Nevada | On Hold For Funding | New switches at Wylie | Switches at Olinger, at Friewheel, at Elm Grove, and at Nevada | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2015-06-01 |  | 138 | 0 | 36.75 | 0 |  | Collin | Dallas | Tier 4 |  |  |  | 833, 811, 818, 821, 855 | Y | N |  |  | 2750 | 2629
15TPIT0058 | Permian Basin - Ward Gulf Tap - Wink 138 kV line | Upgrade existing 138 kV line |  | Permian Basin | Wink | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8189-E | 2015-05-15 |  | 138 | 0 | 16.5 | 0 |  | Ward | Winkler | Tier 4 |  |  |  | 1010, 1074, 1087 | Y | N |  |  | 3007 | 2834
15TPIT0059 | Avery Ranch - Jollyville Transmission Line Upgrade | Upgrade the 1.1 mile Avery Ranch (7534) - Jollyville (9223) 138-kV transmission line to bundled 959.6 ACSS/TW Suwanee, 660MVA. |  | Avery Ranch | Jollyville | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2015-02-03 |  | 138 | 0 | 1.1 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 7534, 9223 | Y | N |  |  | 3404 | 3231
15TPIT0060 | Convert KenedySw - Guadalupe (Cuero) to 138kV | Convert the 42.3 miles Kenedy Switch (8186) - Guadalupe (7253) 69-kV line to 138-kV line, 220 MVA. Guadalupe is a new substation to be built near Cuero Hydro (78189). |  | Kenedy Switch | Guadalupe | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2015-03-31 |  | 138 | 0 | 42.3 | 0 |  | Karnes | DeWitt | Tier 1 | 2013-02-15 | 2013-02-15 |  | 78188 | Y | N |  | Coordinate with AEP Coordinate with GVEC | 3968 | 3724
15TPIT0061 | Marshall Ford to Lago Vista Transmission Line Upgrade | Upgrade the 6.5 mile Marshall Ford (7356) - Lago Vista (7352) 138-kV transmission line to bundled 795 ACSR, 440 MVA. |  | Marshall Ford | Lago Vista | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2015-04-30 |  | 138 | 0 | 6.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 7352, 7356 | Y | N |  |  | 3406 | 3233
15TPIT0062 | McNeil - Marshall Ford Transmission Line Upgrade | Upgrade and convert the 14.5 mile McNeil (7334) - Marshall Ford (7356) 69-kV transmission line to 138-kV bundled 795 ACSR, 440 MVA. |  | McNeil | Marshall Ford | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2015-03-19 |  | 138 | 0 | 14.5 | 0 |  | Travis | Travis | Tier 3 | 2013-03-01 | 2013-03-30 |  | 7334, 7356 | Y | N |  |  | 3407 | 3234
15TPIT0063 | Gillett Substation | Construct the new Gillett Substation (78582) on the existing LCRA TSC Nixon (78580) - Kenedy Switch 138-kV transmission line. |  | Gillett |  | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2015-02-09 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 78582, 78580 | Y | N |  |  | 3408 | 3235
15TPIT0067 | Tuleta 138 kV Station: Construct a new station | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. | CHANGES | TULETA |  | Under Construction | 603-0765 | AEP TCC | FRANK PRITZLAFF (AEP) GAREED@AEP.COM 918-599-2664 | 3483 | 2015-12-31 |  | 138 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  | 8590 | Y | N | NA | NA | 3689 | 3482
15TPIT0068 | Add Hecker 138kV substation | Add Hecker 138kV substation | Changed Dollars | Dupont SS | Whitepoint SS | Planned | 608 - 0776 | AEP TCC | Glen Reed 918-599-2664 | 3488 | 2015-06-30 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  | 8565, 8422, 8961 | Y | N |  |  | 3268 | 3099
15TPIT0069 | Kleberg: Add 138 kV PST | Add 138 kV PST | CHANGES | Kleberg |  | Planned | 592 - 0769 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 | 3479 | 2015-10-01 |  | 138 | 0 | 0 | 0 | 0,220 | Kleberg |  | Tier 4 |  |  |  | 88519, 5648, 8519 | Y | N | NA | NA | 3543 | 3354
15TPIT0070 | Andrews Switch - Frankel City 69 kV Line | Upgrage existing line |  | Andrews Switch | Frankel City | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8175-E | 2015-05-15 |  | 69 | 0 | 11.6 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1267, 1270 | Y | N |  |  | 3327 | 3156
15TPIT0071 | Eastland 69 kV capacitors | Install shunt capacitors |  | Eastland |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R768-E | 2015-05-15 |  | 69 | 0 | 0 | 0 | 0,9.2 | Eastland |  | Tier 4 |  |  |  | 1621 | Y | N |  |  | 3688 | 3481
15TPIT0072 | Eddy 69 kV capacitors | Install shunt capacitors |  | Eddy |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R769-E | 2015-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | McLennan |  | Tier 4 |  |  |  | 3580 | Y | N |  |  | 3252 | 3083
15TPIT0073 | Frankston 69 kV capacitors | Install shunt capacitors |  | Frankston |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6044-E | 2015-05-15 |  | 69 | 0 | 0 | 0 | 0,9.2 | Anderson | Anderson | Tier 4 |  |  |  | 3255 | Y | N |  |  | 3317 | 3146
15TPIT0074 | Little River 69 kV capacitors | Install shunt capacitors |  | Little River |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R772-E | 2015-05-15 |  | 69 | 0 | 0 | 0 | 0,9.2 | Bell |  | Tier 4 |  |  |  | 3645 | Y | N |  |  | 3253 | 3084
15TPIT0075 | Midway 69 kV capacitors | Install shunt capacitors |  | Midway |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8145-E | 2015-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Ector |  | Tier 4 |  |  |  | 1253 | Y | N |  |  | 3446 | 3270
15TPIT0076 | North Andrews - Means 69 kV Line | Upgrade existing line |  | North Andrews | Means | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8142-E | 2015-05-15 |  | 69 | 0 | 2.8 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1160, 1285 | Y | N |  |  | 3328 | 3157
15TPIT0077 | Oak Creek 69 kV capacitors | Install shunt capacitors |  | Oak Creek |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8154-E | 2015-05-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Nolan |  | Tier 4 |  |  |  | 1406 | Y | N |  |  | 3374 | 3203
15TPIT0078 | Tyler Northwest - Tyler 69 kV Line | Upgrade existing line |  | Tyler Northwest | Tyler | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6021-E | 2015-05-15 |  | 69 | 0 | 3 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3142, 3207 | Y | N |  |  | 3231 | 3062
15TPIT0079 | Southlake - Grapevine Junction 138 kV Line | Rebuild existing line |  | Southlake | Grapevine Junction | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5001C-E | 2015-12-15 |  | 138 | 0 | 7.7 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2014, 2019, 2020, 2023 | Y | N |  |  | 2690 | 2574
15TPIT0080 | Big Springs Switch - Big Springs West 138 kV Line | Upgrade existing line |  | Big Springs Switch | Big Springs W | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8139-E | 2015-05-15 |  | 138 | 0 | 7.9 | 0 |  | Howard | Howard | Tier 4 |  |  |  | 1322, 1324 | Y | N |  |  | 3332 | 3161
15TPIT0081 | Centerville Switch 138 kV Series Reactors | Increase size of series reactors |  | Centerville Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4105-E | 2015-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2439, 2450, 12439, 12450 | Y | N |  |  | 3230 | 3061
15TPIT0082 | Collin - Custer (Brazos) 138 kV Line (Oncor's section) | Upgrade existing line |  | Collin | Custer (Brazos) | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R937-E | 2015-05-15 |  | 138 | 0 | 3.5 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 2364, 2365, 2566, 2567 | Y | N |  |  | 3378 | 3207
15TPIT0083 | Collin - Arco (TMPA) 138 kV Line (Oncor's section) | Add second circuit to existing line |  | Collin | Arco (TMPA) | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R929-E | 2017-05-15 |  | 138 | 7.5 | 0 | 0 |  | Collin | Denton | Tier 4 |  |  |  |  | Y | N |  |  | 3389 | 3216
15TPIT0084 | Commerce 138/69 kV autotransformer | Replace existing autotransformer |  | Commerce |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R941-E | 2015-05-15 |  | 138 | 0 | 0 | 150 |  | Hunt |  | Tier 4 |  |  |  | 1820, 1821, 11820 | Y | N |  |  | 3385 | 3212
15TPIT0085 | Eagle Mountain - Saginaw 138 kV Line | Upgrade existing line |  | Eagle Mountain | Saginaw | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5200-E | 2015-05-15 |  | 138 | 0 | 13.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1860, 2076, 11860, 2075, 12065 | Y | N |  |  | 3382 | 3209
15TPIT0086 | Mockingbird 138 kV capacitors | Install shunt capacitors |  | Mockingbird |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8153-E | 2015-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Ector |  | Tier 4 |  |  |  | 1182 | Y | N |  |  | 3334 | 3163
15TPIT0087 | Morgan Creek - Barber Lake - China Grove 138 kV Lines | Upgrade two existing lines |  | Morgan Creek Sw | China Grove Sw | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8141-E | 2015-05-15 |  | 138 | 0 | 28 | 0 |  | Mitchell | Mitchell | Tier 4 |  |  |  | 1032, 1189, 1190, 1318, 19520, 19521 | Y | N |  |  | 3743 | 3164
15TPIT0088 | North Andrews #1 138/69 kV autotransformer | Replace existing autotransformer |  | North Andrews |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8149-E | 2015-05-15 |  | 138 | 0 | 0 | 150 |  | Andrews |  | Tier 4 |  |  |  | 1159, 1160 | Y | N |  |  | 3336 | 3165
15TPIT0089 | Odessa 138 kV capacitors | Install shunt capacitors |  | Odessa |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8155-E | 2015-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Midland |  | Tier 4 |  |  |  | 1127 | Y | N |  |  | 3337 | 3166
15TPIT0090 | Odessa EHV - Midessa - Spraberry 138 kV Line | Upgrade existing line |  | Odessa EHV | Spraberry | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8138-E | 2015-12-15 |  | 138 | 0 | 39.5 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1027, 1059, 1137, 1138, 1329 | Y | N |  |  | 3333 | 3162
15TPIT0091 | Odessa EHV - Glenhaven - CRMWD Tap - Midland Airport - Mides | Upgrade existing line |  | Odessa EHV | Midessa | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8137-E | 2015-05-15 |  | 138 | 0 | 18.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1027, 1059, 1118, 1121, 1127, 1120, 1128 | Y | N |  |  | 3338 | 3167
15TPIT0092 | Odessa North - Westover 138 kV Line | Upgrade existing line |  | Odessa North | Westover | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8182-E | 2015-12-15 |  | 138 | 0 | 4.9 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1122, 1129, 1130 | Y | N |  |  | 3341 | 3170
15TPIT0093 | Round Rock Westinghouse 138 kV capacitors | Install shunt capacitors |  | Round Rock Westinghouse |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R780-E | 2015-05-15 |  | 138 | 0 | 0 | 0 | 0,36.8 | Williamson |  | Tier 4 |  |  |  | 3669 | Y | N |  |  | 3256 | 3087
15TPIT0094 | Texaco Mabee 138 kV capacitors | Install shunt capacitors |  | Texaco Mabee |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8152-E | 2015-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Midland |  | Tier 4 |  |  |  | 1177 | Y | N |  |  | 3339 | 3168
15TPIT0095 | Tyler Northwest 138/69 kV autotransformer | Replace existing autotransformer |  | Tyler Northwest |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6020-E | 2015-05-15 |  | 138 | 0 | 0 | 150 |  | Smith | Smith | Tier 4 |  |  |  | 3141, 3142, 3157 | Y | N |  |  | 3254 | 3085
15TPIT0096 | Moss 345 kV circuit breakers | Install circuit breakers |  | Moss |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8100A-E | 2016-07-15 |  | 345 | 0 | 0 | 0 |  | Ector | Ector | Tier 4 |  |  |  |  | Y | N |  |  | 3359 | 3188
15TPIT0097 | Moss 345/138 kV autotransformer | Install autotransformer |  | Moss |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8140B-E | 2024-05-15 |  | 345 | 0 | 0 | 600 |  | Ector | Ector | Tier 4 |  |  |  | 18526, 1018, 1019 | N | N |  |  | 3340 | 3169
15TPIT3100 | Palestine - Carroll Springs 69 kV Line | Upgrade existing line |  | Palestine | Carroll Springs | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6045-E | 2015-12-15 |  | 69 | 0 | 22.1 | 0 |  | Anderson | Anderson | Tier 3 |  |  |  | 3270, 3273, 3274 | Y | N |  |  | 3269 | 3100
15TPIT3253 | Treaschwig to Humble Ckt. 66 | Upgrade 138kV Ckt. 66 Treaschwig to Humble to increase thermal ratings. |  | Treaschwig | Humble | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 |  | 138 | 0 | 9.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40830, 46550 | Y | N |  |  | 3427 | 3253
15TPIT3363 | Obrien Autotransformer Upgrade | Parallel existing Obrien autotransformers A1 & A2. Install new 800MVA auto at Obrien substation. |  | Obrien |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 |  | 345 | 0 | 0 | 800 |  | Fort Bend |  | Tier 4 |  |  |  | 49031, 44500, 44510 | Y | N |  |  | 3558 | 3363
15TPIT3391 | Bellaire Autotransformer Upgrade | Replace existing 600MVA Bellaire autotransformer A4 with 800MVA autotransformer. |  | Bellaire |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 |  | 345 | 0 | 0 | 200 |  | Harris |  | Tier 4 |  |  |  | 47000, 47010, 49002 | Y | N |  |  | 3589 | 3391
15tpit3405 | New SECO station with load and line | Adds a new 138 kV line to a new load serving substation SECO |  | SECO | SECOSwitch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-03-02 |  | 138 | 9.2 | 0 | 0 |  | Medina | Medina | Tier 4 |  |  |  | 5806, 8241 | Y | N |  |  | 3605 | 3405
16TPIT0000 | Del Sol: Add a 24 Ohm, 3600 A Series Capacitor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Del Sol |  | Planned | 065 - 0273 | ETT | Rich Haley 918-599-2664 | 629 | 2016-06-30 |  | 345 | 0 | 0 | 0 | 0,933.1 | Starr |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80307, 80355 | Y | N |  | Modeling in 11TPIT0002 | 3312 | 3143
16TPIT0003 | Longneck to Princeton South - new 138 kV line | Build 3.5 miles of 138kV transmission line from Longneck Substation to Princeton South Substation. | Budget | Longneck | Princeton South | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07317 | 2017-06-01 |  | 138 | 3.5 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 37250, 37280, 37295 | Y | N |  |  | 2065 | 2013
16TPIT0005 | Farmersville West to Princeton South - new 138 kV line. | Build approximately 7.5 miles of 138 kV transmission line from Farmersville West Substation to Princeton South Substation. |  | Farmersville West | Princeton South | Planned | New projects added on rows 18 and 19. Please add TPIT numbers here after they have been assigned. | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE08016 | 2017-06-01 |  | 138 | 7.5 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 37291, 37295 | Y | N |  |  | 2064 | 2012
16TPIT0006 | Climax to Longneck - Rebuild and conversion from 69 kV to 13 | Rebuild Climax to Longneck 69 kV transmission line and convert to 138 kV. |  | Climax | Longneck | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07618 | 2018-06-01 |  | 138 | 7.5 | 4.2 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 37260, 37250 | Y | N |  |  | 2066 | 2014
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | P396 | 2016-06-15 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9077, 9238 | Y | N |  | Will add the ptoject to the base case. | 1032 | 1031
16TPIT0009 | Five Points to Westside - 138 kV Transmission Line Rebuild | Rebuild 3.8 miles of 138 kV transmission line from Five Points to Westside and ensure a minimum conductor rating of 331 MVA |  | Five Points | Westside | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0195 | 2016-12-01 |  | 138 | 0 | 3.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5150, 5490 | Y | N |  | There are no transformers associated with this project | 974 | 973
16TPIT0010 | Bulverde - New 138kV Substation | Loop new 138kV substation into the existing Green Mountain to Stonegate transmission line |  | Green Mountain | Stonegate | Planned | T-0189 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0665 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5051, 5180, 5415 | Y | N |  | There are no transformers associated with this project | 972 | 971
16TPIT0011 | JT Deely to Streich - 138 kV Substation Equipment Upgrade | Upgrade terminals at JT Deely and Streich Rd. to ensure a 2420 A rating and remove existing MLSE on JT Deely to Streich 138 kV transmission line |  | JT Deely | Streich Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0674 | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5110, 5417 | Y | N |  | There are no transformers associated with this project | 977 | 976
16TPIT0012 | Encino to Skyline - 138 kV Substation Equipment Upgrade | Upgrade terminals at Encino and Skyline to ensure a 2420 A rating and remove existing MLSE on Encino to Skyline 138 kV transmission line |  | Encino | Skyline | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0671 | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5140, 5369 | Y | N |  | There are no transformers associated with this project | 973 | 972
16TPIT0013 | Skyline to Spruce - 345 kV Substation Equipment Upgrade | Replace the Line MDS at Skyline and Spruce (both circuits) and ensure all terminals have a 2420 A rating and remove existing MLSE on Skyline to Spruce 345 kV transmission lines (both circuits) |  | Skyline | Spruce | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0468 | 2016-06-01 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5371, 5400 | Y | N |  | There are no transformers associated with this project | 971 | 970
16TPIT0017 | Cenizo: Add a 24 Ohm 3600, A Series Capacitor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Cenizo |  | Planned | 065 - 0273 | ETT | Rich Haley 918-599-2664 | 630 | 2016-06-30 |  | 345 | 0 | 0 | 0 | 0,933.1 | Webb |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80220, 80225 | Y | N |  | Modeled in 11TPIT0002 | 3313 | 3144
16TPIT0018 | Hicks Switch Autotransformer | Install 345/138 kV autotransformer |  | Hicks Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5145-E | 2016-05-15 |  | 345 | 0 | 0 | 600 |  | Tarrant |  | Tier 4 |  |  |  | 2082, 1860, 2075, 2076, 12065, 2081 | Y | N |  |  | 2700 | 2584
16TPIT0019 | Lobo 138 kV station: install 3 additional CB | Construct 345 kV circuit from Lobo to Rio Bravo energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Rio Bravo 138kV stations. | CHANGES | LOBO |  | UNDER CONSTRUCTION | 206-0288 | AEP TCC | KENEATH 'RICH' HALEY GAREED@GMAIL.COM 918-599-2664 | 634 | 2015-05-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 80221 | Y | N | NA | NA | 3727 | 3520
16TPIT0020 | Constrcut: Molina 138 kV Station | Construct 345 kV circuit from Lobo to Molina energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and build Molina 138kV stations. | CHANGES | MOLINA |  | UNDER CONSTRUCTION | 206-0288 | AEP TCC | Kenneth 'Rich' Haley GAREED@AEP.COM 918-599-2664 | 900 | 2015-05-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 80230 | Y | N | NA | NA | 3673 | 3468
16TPIT0023 | South McAllen - Stewart Road: Rebuild 138kV Line | Rebuild South McAllen - Stewart Road 138kV Line | Reformated project number to match other numbers, Chnaged ISD | South McAllen | Stewart Road | Planned | 601 - 0763 | AEP TCC | Aaron Schwerman gareed@aep.com 918-599-2664 | 3470 | 2015-12-31 |  | 138 | 0 | 9.8 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8371, 8758, 8951 | Y | N |  | 0 | 1945 | 1896
16TPIT0024 | Hamilton Road to Escondido: Rebuild 138kV Line | Rebuild Hamilton Road to Escondido 138 kV line | Reformated project number to match other numbers | Hamilton Road | Escondido | Conceptual | 602 - 0764 | AEP TCC |  | 3471 | 2016-12-31 |  | 138 | 0 | 53.7 | 0 |  | Val Verde | Maverick | Tier 3 |  |  |  | 8255, 8260, 8264, 8692 | Y | N |  | 0 | 2655 | 2550
16TPIT0026 | Lon Hill to Smith: Rebuild 69kV line | Rebuild Lon Hill - Smith 69kV Line with 1533.3 ACSR/TW conductor | Reformated project number to match other numbers | Lon Hill | Smith | Planned | 583 - 0739 | AEP TCC | William Clarke 918-599-2664 | 3462 | 2015-06-30 |  | 69 | 0 | 3.1 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8448, 8866, 80479, 80480 | Y | N |  | 0 | 1821 | 1779
16TPIT0027 | Beeville to Sinton: Rebuild 69 kV Line | Rebuild Beeville - Sinton 69kV Line for future 138 kV operation | CHANGES | BEEVILLE | SINTON | PLANNED | 579-0737 | AEP TCC | FRANK PRITZLAFF GAREED@AEP.COM 918-599-2664 | 3465 | 2015-08-31 |  | 69 | 0 | 29.4 | 0 |  | Bee | San Patricio | Tier 3 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8198, 8405, 8904, 8413 | Y | N | NA | NA | 3717 | 3510
16TPIT0030 | New 345kV line from Loma Alta to N Edinburgh | Construct a new 345 kV transmission line from N.Edinburg to Loma Alta (~106.5 mi) and station upgrades | New Changed Dollars to include the station costs associated with the project (Approved by RPG, see comments for breakout) | Loma Alta | N Edinburgh | Planned |  | SLU |  |  | 2016-06-01 |  | 345 | 106.5 | 0 | 0 |  | Cameron | Hidalgo | Tier 1 | 2011-05-03 | 2011-12-19 | 2012-01-17 | 5966, 8383, 5962 | Y | N |  |  | 2460 | 2371
16TPIT0031 | Esmeralda: Build new five breaker ring bus | Construct new Esmeralda station along the Big Lake to Friend Ranch 138 kV line and build new 138 kV line from Esmeralda to Yucca with 795 ACSS |  | Esmeralda |  | Planned | 585 - 0738 | AEP TNC |  | 2576 | 2016-12-31 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6525, 6535, 6562 | Y | N |  |  | 3415 | 3241
16TPIT0032 | Esmeralda to Yucca: Build 138 kV line | Construct new Esmeralda station along the Big Lake to Friend Ranch 138 kV line and build new 138 kV line from Esmeralda to Yucca with 795 ACSS |  | Esmeralda | Yucca | Planned | 585 - 0745 | AEP TNC |  | 2577 | 2016-12-31 |  | 138 | 13 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6036, 6525 | Y | N |  |  | 2761 | 2637
16TPIT0033 | Culberson - Mason 138 kV Line | Upgrade existing 138 kV line |  | Culberson | Mason | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8173-E | 2016-12-15 |  | 138 | 0 | 33 | 0 |  | Culberson | Loving | Tier 3 |  |  |  | 1083, 1084, 1095, 1096, 1094, 1097 | Y | N |  |  | 3010 | 2837
16TPIT0034 | Coleto Creek to Tuleta: New 138 kV Line | Build a double circuit capable 138 kV circuit from Coleto Creek station to new Tuleta station. | CHANGES | COLETO CREEK | TULETA | PLANNED | 606-0771 | AEP TCC | FRANK PRITZLAFF GAREED@AEP.COM 918-2=599-2664 | TP2012157 | 2016-05-31 |  | 138 | 56 | 0 | 0 |  | Goliad | Bee | Tier 1 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8162, 8590 | Y | N | NA | NA | 3702 | 3495
16TPIT0035 | Rebuild BEC Munday to Gillespie 69 kV line with 795 ACSR | Rebuild BEC Munday to Gillespie 69 kV line with 795 ACSR |  | BEC Munday | Gillespie | Planned | 568 - 0742 | AEP TNC |  | 2578 | 2015-05-31 |  | 69 | 0 | 7.2 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 764, 6112 | Y | N |  |  | 2911 | 2756
16TPIT0040 | Del Sol: Add a 100 MVAR Shunt Reactor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Del Sol |  | Planned | 065 - 0273 | ETT | Rich Haley 918-599-2664 |  | 2016-06-30 |  | 345 | 0 | 0 | 0 | -100,0 | Starr |  | Tier 4 |  |  |  | 80355 | Y | N |  |  | 3310 | 3141
16TPIT0041 | Cenizo: Add a 100 MVAR Shunt Reactor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Cenizo |  | Planned | 065 - 0273 | ETT | Rich Haley 918-599-2664 |  | 2016-06-30 |  | 345 | 0 | 0 | 0 | -100,0 | Webb |  | Tier 4 |  |  |  | 80220 | Y | N |  |  | 3311 | 3142
16TPIT0042 | Uvalde Station: Add 2nd 138/69 kV Auto | Add 2nd 138/69 kV Auto at Uvalde Station | CHANGES | UVALDE | UVALDE | PLANNED | 593-0770 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 |  | 2015-05-31 |  | 138 | 0 | 0 | 130 |  | Uvalde |  | Tier 4 |  |  |  | 8231, 8234 | Y | N |  |  | 3741 | 3534
16TPIT0043 | Andrews Switch - Emma Tap 69 kV Line | Upgrade existing line |  | Andrews Switch | Emma Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8177-E | 2016-05-15 |  | 69 | 0 | 10 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1262, 1267 | Y | N |  |  | 3329 | 3158
16TPIT0044 | Brownwood 69 kV capacitors | Install shunt capacitor |  | Brownwood |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R782-E | 2016-05-15 |  | 69 | 0 | 0 | 0 | 0,9.2 | Brown |  | Tier 4 |  |  |  | 1662 | Y | N |  |  | 3694 | 3487
16TPIT0045 | Eddy - Troy 69 kV Line | Upgrade existing line |  | Eddy | Troy | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R774-E | 2016-12-15 |  | 69 | 0 | 6.8 | 0 |  | Bell | McLennan | Tier 4 |  |  |  | 3580, 3581 | Y | N |  |  | 3242 | 3073
16TPIT0046 | Frankel City - Exxon Fullerton 69 kV Line | Upgrade existing line |  | Frankel City | Exxon Fullerton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8176-E | 2016-05-15 |  | 69 | 0 | 2.8 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1270, 1275 | Y | N |  |  | 3330 | 3159
16TPIT0047 | Reynolds Street 69 kV capacitors | Install shunt capacitors |  | Reynolds Street |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6045-E | 2016-05-15 |  | 69 | 0 | 0 | 0 | 0,9.2 | Cherokee | Cherokee | Tier 4 |  |  |  | 3245 | Y | N |  |  | 3318 | 3147
16TPIT0048 | Trinidad - Athens 69 kV Line | Upgrade existing line |  | Trinidad SES | Athens | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6033-E | 2016-05-15 |  | 69 |  | 17.5 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  | 3128, 3239 | Y | N |  |  | 3590 | 3392
16TPIT0049 | Wichita Falls - Wichita Falls North Tap 69 kV line | Upgrade existing line |  | Wichita Falls | Wichita Falls North Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R942-E | 2016-12-15 |  | 69 | 0 | 0.9 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  | 1449, 1504 | Y | N |  |  | 3391 | 3218
16TPIT0050 | Alpha Road - Preston North 138 kV Line | Upgrade existing line |  | Alpha Road | Preston North | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4108-E | 2016-05-15 |  | 138 | 0 | 3.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2597, 2598, 2614, 2616 | Y | N |  |  | 3234 | 3065
16TPIT0051 | Athens - AthensTap - Athens Northwest 138 kV line | Upgrade existing line |  | Athens | Athens Northwest | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6018-E | 2016-05-15 |  | 138 | 0 | 11 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  | 3238, 3247, 3248 | Y | N |  |  | 3280 | 3111
16TPIT0052 | Cedar Crest - South Oak Cliff 138 kV line | Upgrade existing line |  | Cedar Crest | South Oak Cliff | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4089-E | 2016-05-15 |  | 138 | 0 | 1.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2493, 2494, 3023, 3024 | Y | N |  |  | 3235 | 3066
16TPIT0053 | Corsicana West 138 kV capacitors | Install shunt capacitors |  | Corsicana West |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R771-E | 2016-05-15 |  | 138 | 0 | 0 | 0 | 0,18.4 | Navarro |  | Tier 4 |  |  |  | 3456 | Y | N |  |  | 3615 | 3415
16TPIT0054 | Dialville - Palestine South 138 kV Line | Upgrade existing line |  | Dialville | Palestine South | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6019-E | 2016-12-15 |  | 138 | 0 | 25 | 0 |  | Cherokee | Andrews | Tier 3 |  |  |  | 3160, 3271, 3296 | Y | N |  |  | 3283 | 3114
16TPIT0055 | Elkton - Jacksonville 138 kV Line | Upgrade existing line |  | Elkton | Jacksonville | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6029-E | 2016-05-15 |  | 138 | 0 | 20.2 | 0 |  | Smith | Cherokee | Tier 4 |  |  |  | 3106, 3251, 3253 | Y | N |  |  | 3279 | 3110
16TPIT0056 | Getty Vealmoor 138 kV capacitors | Install shunt capacitors |  | Getty Vealmoor |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8159-E | 2016-05-15 |  | 138 | 0 | 0 | 0 | 0,18.4 | Howard |  | Tier 4 |  |  |  | 1395 | Y | N |  |  | 3346 | 3175
16TPIT0057 | Hutto Switch - Taylor 138 kV Line | Upgrade existing line |  | Hotto Switch | Taylor | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R775-E | 2016-05-15 |  | 138 | 0 | 15.6 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 3658, 3666, 3673 | Y | N |  |  | 3240 | 3071
16TPIT0058 | Lufkin Switch - Lufkin 138 kV line | Upgrade existing line |  | Lufkin Switch | Lufkin | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6038-E | 2016-05-15 |  | 138 | 0 | 2.8 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3118, 3340 | Y | N |  |  | 3281 | 3112
16TPIT0059 | Midland East 138 kV capacitor | Install shunt capacitor |  | Midland East |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8158-E | 2016-05-15 |  | 138 | 0 | 0 | 0 | 0,73.6 | Midland |  | Tier 4 |  |  |  | 1023 | Y | N |  |  | 3344 | 3173
16TPIT0060 | Midland East - Spraberry 138 kV Line | Upgrade existing line |  | Midland East | Spraberry | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8147-E | 2016-05-15 |  | 138 | 0 | 18.8 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1132, 1133, 1329 | Y | N |  |  | 3343 | 3172
16TPIT0061 | Norwood - Reagan Street 138 kV Line | Upgrade existing line |  | Norwood | Reagan Street | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4107-E | 2016-05-15 |  | 138 | 0 | 6.7 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2405, 2811, 2813, 2815, 2814, 2819, 2823 | Y | N |  |  | 3236 | 3067
16TPIT0062 | Pflugerville - Gilleland Creek 138 kV Line | Upgrade existing line |  | Pflugerville | Gilleland Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R773-E | 2016-12-15 |  | 138 | 0 | 3.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 3665, 7336 | Y | N |  |  | 3248 | 3079
16TPIT0063 | Saginaw Switch 138/69 kV autotransformers | Replace existing autotransformer |  | Saginaw Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5201-E | 2016-05-15 |  | 138 | 0 | 0 | 300 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1957, 1958 | Y | N |  |  | 3383 | 3210
16TPIT0064 | Simpson Stuart - Lancaster Witt 138 kV Line | Upgrade existing line |  | Simpson Stuart | Lancaster Witt | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4112-E | 2016-05-15 |  | 138 | 0 | 3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2988, 3068 | Y | N |  |  | 3241 | 3072
16TPIT0065 | Stryker Creek - Nacogdoches 138 kV line | Upgrade existing line |  | Stryker Creek | Nacogdoches | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6035-E | 2016-12-15 |  | 138 | 0 | 21.3 | 0 |  | Cherokee | Nacogdoches | Tier 3 |  |  |  | 3110, 3299, 3300, 3301, 3303 | Y | N |  |  | 3284 | 3115
16TPIT0066 | Stryker Creek - Troup 138 kV Line | Upgrade existing line |  | Stryker Creek | Troup | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6031-E | 2016-05-15 |  | 138 | 0 | 15.5 | 0 |  | Cherokee | Cherokee | Tier 4 |  |  |  | 3110, 3147 | Y | N |  |  | 3282 | 3113
16TPIT0067 | Teaselville Tap 138 kV capacitors | Install shunt capacitor |  | Teaselville |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6042-E | 2016-05-15 |  | 138 | 0 | 0 | 0 | 0,9.2 | Cherokee |  | Tier 4 |  |  |  | 3224 | Y | N |  |  | 3319 | 3148
16TPIT0068 | Venus - Chaparral Steel Tap 138 kV Line | Upgrade existing line |  | Venus | Chaparral Steel Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4113-E | 2016-05-15 |  | 138 | 0 | 5.5 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  | 1908, 2300 | Y | N |  |  | 3251 | 3082
16tpit0037 | Rebuild Orange Grove to Casa Blanca | Rebuild 4/0 ACSR 69 kV to 795 ACSR circuit on 138 kV capable structures. Other wires are being studied. |  | Orange Grove | Casa Blanca | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-04-01 |  | 69 | 0 | 6.7 | 0 |  | Jim Wells | Jim Wells | Tier 1 | 2012-09-05 | 2013-01-31 | 2013-03-12 | 5662, 8166 | Y | N |  |  | 3116 | 2947
16tpit0038 | Rebuild STEC Mathis to AEP Mathis | Rebuild 69 kV 4-0 to 795 ACSR on 138 kV capable structures. |  | Mathis | AEP Mathis | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-06-01 |  | 69 | 0 | 5.3 | 0 |  | Live Oak | San Patricio | Tier 1 | 2012-09-05 | 2013-01-31 | 2013-03-12 | 5668, 8407 | Y | N |  |  | 3117 | 2948
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0196 | 2017-12-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 2384 | 2308
17TPIT0002 | Hunt Lane to Pinn Road - 138 kV Transmission Line Rebuild | Rebuild approximately eight circuit miles of 138 kV transmission from Hunt Lane to Pinn Road |  | Hunt Lane | Pinn Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0190 | 2017-12-01 |  | 138 | 0 | 8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5054, 5305, 5345, 5427 | Y | N |  | There are no transformers associated with this project | 2383 | 2307
17TPIT0004 | Frisco to Krugerville Second Circuit | Add second circuit from Frisco to Krugerville |  | Frisco | Krugerville | conceptual |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12042 | 2017-12-01 |  | 138 | 12 | 0 | 0 |  | Collin | Denton | Tier 4 |  |  |  | 623, 654, 662, 1993, 2370 | Y | N |  |  | 2537 | 2432
17TPIT0005 | St. Jo Autos | Replace 40 MVA autos with 60 MVA autos |  | St. Jo | St. Jo | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12005 | 2017-12-01 |  | 138 | 0 | 0 | 40 |  | Cooke |  | Tier 4 |  |  |  | 750, 746 | Y | N |  |  | 2316 | 2243
17TPIT0007 | Rebuild Gillespie to Pointer 69 kV line with 795 ACSR | Rebuild Gillespie to Pointer 69 kV line with 795 ACSR |  | Gillespie | Pointer | Planned | 568 - 0742 | AEP TNC |  | 2579 | 2015-12-31 |  | 69 | 0 | 6.7 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 6112, 6113, 60346 | Y | N |  |  | 2912 | 2757
17TPIT0008 | Marion to Cibolo T-Line (T-302) Circuit Addition | Add another 138 kV circuit, to existing Marion to Cibolo T-Line (T-302), 1192 ACSR, 4.81 miles |  | Marion | Cibolo | Conceptual |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-04-28 |  | 138 | 4.81 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | N | N |  |  | 2962 | 2792
17TPIT0009 | East Munday: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at East Munday | Schedule Update | East Munday |  | Planned | 588 - 0746 | AEP TNC |  | 2580 | 2015-05-31 |  | 69 | 0 | 0 | 90 |  | Knox |  | Tier 4 |  |  |  | 6108, 6110 | Y | N |  |  | 3400 | 3227
17TPIT0010 | Brownsboro 69 kV capacitors | Install shunt capacitor |  | Brownsboro |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6025-E | 2017-05-15 |  | 69 | 0 | 0 | 0 | 0,9.2 | Henderson | Henderson | Tier 4 |  |  |  | 3236 | Y | N |  |  | 3285 | 3116
17TPIT0011 | Carroll Springs 69 kV capacitors | Install shunt capacitor |  | Carroll Springs |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6041-E | 2017-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Anderson | Anderson | Tier 4 |  |  |  | 3270 | Y | N |  |  | 3591 | 3393
17TPIT0012 | Willow Springs 69 kV capacitors | Install shunt capacitor |  | Willow Springs |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6026-E | 2017-05-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Anderson | Anderson | Tier 4 |  |  |  | 3269 | Y | N |  |  | 3290 | 3121
17TPIT0013 | Tyler Grande Switch shunt reactors | Install shunt reactors on tertiary of 345/138 kV autotransformer |  | Tyler Grande |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6047-E | 2017-05-15 |  | 138 | 0 | 0 | 0 | 0,-75 | Smith | Smith | Tier 4 |  |  |  | 3338 | Y | N |  |  | 3316 | 3145
17TPIT0014 | Copperas Cove 138 kV capacitors | Install shunt capacitor |  | Copperas Cove |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R786-E | 2017-05-15 |  | 138 | 0 | 0 | 0 | 0,18.4 | Coryell |  | Tier 4 |  |  |  | 3630 | Y | N |  |  | 3277 | 3108
17TPIT0015 | Ennis Creek Switch 138/69 kV autotransformer | Replace existing autotransformer |  | Ennis Creek Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8179-E | 2017-05-15 |  | 138 | 0 | 0 | 50 |  | Scurry |  | Tier 4 |  |  |  | 1411, 1410 | Y | N |  |  | 3376 | 3205
17TPIT0016 | North Andrews #2 138/69 kV autotransformer | Replace existing autotransformer |  | North Andrews |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8178-E | 2017-05-15 |  | 138 | 0 | 0 | 150 |  | Andrews |  | Tier 4 |  |  |  | 1160, 1159 | Y | N |  |  | 3348 | 3177
17TPIT0017 | Spraberry 138/69 kV autotransformer | Replace existing autotransformer |  | Spraberry |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8180-E | 2017-05-15 |  | 138 | 0 | 0 | 75 |  | Midland |  | Tier 4 |  |  |  | 1330, 1329 | Y | N |  |  | 3350 | 3179
17TPIT0018 | Wink 138/69 kV autotransformer | Replace existing autotransformer |  | Wink |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8181-E | 2017-05-15 |  | 138 | 0 | 0 | 100 |  | Winkler |  | Tier 4 |  |  |  | 1075, 1074 | Y | N |  |  | 3352 | 3181
17TPIT0019 | Forney - South Rockwall 138 kV Line | Upgrade existing line |  | Forney | South Rockwall | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4111-E | 2017-05-15 |  | 138 | 0 | 9.4 | 0 |  | Kaufman | Rockwall | Tier 4 |  |  |  | 2438, 2709, 2711, 2712 | Y | N |  |  | 3255 | 3086
17TPIT0020 | Forest Grove - Trinidad 138 kV Line | Upgrade existing line |  | Forest Grove | Trinidad | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6034-E | 2017-05-15 |  | 138 | 0 | 14.5 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  | 3127, 3131, 3276, 29266 | Y | N |  |  | 3322 | 3151
17TPIT0021 | Liggett - Norwood 138 kV Line | Upgrade existing line |  | Liggett | Norwood | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4109-E | 2017-05-15 |  | 138 | 0 | 12.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 1922, 1924, 2053, 2054, 2055, 2408 | Y | N |  |  | 3257 | 3088
17TPIT0022 | Nacogdoches - Nacogdoches North 138 kV Line | Upgrade existing line |  | Nacogdoches | Nacogdoches North | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6037-E | 2017-05-15 |  | 138 | 0 | 3.9 | 0 |  | Nacogdoches | Nacogdoches | Tier 4 |  |  |  | 3303, 3310 | Y | N |  |  | 3323 | 3152
17TPIT0023 | Northwest Carrollton - Carrollton 138 kV Line | Upgrade existing line |  | Northwest Carrollton | Carrollton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4110-E | 2017-05-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2362, 2363, 2535, 2536, 2537, 2538, 2539 | Y | N |  |  | 3258 | 3089
17TPIT0024 | Payne - Anna Switch 138 kV Line | Upgrade existing line |  | Payne | Anna Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R938-E | 2017-05-15 |  | 138 | 0 | 20.8 | 0 |  | Grayson | Collin | Tier 3 |  |  |  | 1713, 1748, 1754, 1758, 2374 | Y | N |  |  | 3386 | 3213
17TPIT0025 | Payne - Anna Tap 138 kV Line | Upgrade existing line |  | Payne | Anna Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R945-E | 2017-12-15 |  | 138 | 0 | 23 | 0 |  | Grayson | Collin | Tier 3 |  |  |  | 1740, 1750, 1751, 1753, 2528, 1752, 1758, 12704 | Y | N |  |  | 3387 | 3214
17TPIT0026 | Stryker Creek - Lufkin 138 kV Line | Upgrade existing line |  | Stryker Creek | Lufkin | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6040-E | 2017-05-15 |  | 138 | 0 | 44.3 | 0 |  | Cherokee | Angelina | Tier 3 |  |  |  | 3110, 3340, 3341, 3342, 3343 | Y | N |  |  | 3324 | 3153
17TPIT0027 | Stryker Creek - Jacksonville 138 kV Line | Upgrade existing line |  | Stryker Creek | Jacksonville | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6030-E | 2017-12-15 |  | 138 | 0 | 16.4 | 0 |  | Cherokee | Cherokee | Tier 4 |  |  |  | 3110, 3112, 3253 | Y | N |  |  | 3289 | 3120
17TPIT0028 | Temple Switch - Belton 138 kV Line | Upgrade existing line |  | Temple Switch | Belton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R784-E | 2017-05-15 |  | 138 | 0 | 12.9 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3415, 3602, 3610, 3611, 3612 | Y | N |  |  | 3353 | 3182
17TPIT0029 | Tyler Grande - Tyler Omen Road 138 kV Line | Upgrade existing line |  | Tyler Grande | Tyler Omen Road | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6017-E | 2017-12-15 |  | 138 | 0 | 4.8 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3143, 3212, 3213 | Y | N |  |  | 3288 | 3119
17TPIT0030 | Tyler West Switch | Construct new switching station |  | Tyler West |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6022-E | 2017-05-15 |  | 138 | 0 | 0 | 0 |  | Smith | Smith | Tier 4 |  |  |  |  | Y | N |  |  | 3325 | 3154
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing autotransformer |  | Elkton |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6032-E | 2017-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 4 |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 3326 | 3155
17TPIT0032 | Fisher Road 345/138 kV autotransformer | Install second autotransformer |  | Fisher Road |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R931-E | 2017-12-15 |  | 345 | 0 | 0 | 600 |  | Wichita |  | Tier 4 |  |  |  | 11426, 1425, 1426 | Y | N |  |  | 3388 | 3215
18TPIT0001 | Wiederstein Substation | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Wiederstein |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2015-09-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7461 | Y | N |  |  | 3500 | 3319
18TPIT0002 | Martinez - New 138kV Substation | Loop new 138kV substation into the existing 138kV Deely to Walzem line and the future 138kV Deely to Converse line |  | Deely | Walzem Converse | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2018-05-31 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5294, 5098, 5110, 5485 | Y | N |  | There are no transformers associated with this project | 2336 | 2263
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-06-30 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  | 7239 | Y | N |  |  | 3519 | 3336
19TPIT0001 | Sargent Road - Saint Augustine Tap 138 kV Line | Upgrade existing line |  | Sargent Road | Saint Augustine Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4090-E | 2019-05-15 |  | 138 | 0 | 1.3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2941, 2951 | Y | N |  |  | 3264 | 3095
20TPIT0000 | Parkway Substation | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7611 | Y | N |  |  | 3504 | 3323
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7611 | Y | N |  |  | 3505 | 3324
2379 | Wirtz-JC-Mt. Top | Close 69-kV loop on Wirtz-Johnson City - Mt. Top | This switching to be performed after completion of the Mt. Top - Blanco- Devil's Hill project | Wirtz | Mt. Top | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2014-02-28 |  | 69 | 0 | 0 | 0 |  | Burnet | Blanco | Tier 4 |  |  |  | 7107, 7516 | Y | N |  |  | 2468 | 2379
3040 | WA Parish to Fort Bend Ckt.09 | Multi-Phase Project: 14TPIT3040A - Upgrade 138kV Ckt.09 Fort Bend to Reading to increase thermal ratings. 14TPIT3040B - Upgrade 138kV Ckt.09 Reading to Crabb River Road to increase thermal ratings. 14TPIT3040C - Upgrade 138kV Ckt.09 Crabb River Road to WA Parish to increase thermal ratings. |  | Fort Bend | Reading | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-29 |  | 138 | 0 | 2.6 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44010, 44170, 44280, 44172, 44570 | Y | N |  | Cost included in main project | 3894 | 3040
3040 | WA Parish to Fort Bend Ckt.09 | Multi-Phase Project: 14TPIT3040A - Upgrade 138kV Ckt.09 Fort Bend to Reading to increase thermal ratings. 14TPIT3040B - Upgrade 138kV Ckt.09 Reading to Crabb River Road to increase thermal ratings. 14TPIT3040C - Upgrade 138kV Ckt.09 Crabb River Road to WA Parish to increase thermal ratings. |  | Reading | Crabb River Road | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-30 |  | 138 | 0 | 3.8 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44010, 44170, 44280, 44172, 44570 | Y | N |  | Cost included in main project | 3895 | 3040
3040 | WA Parish to Fort Bend Ckt.09 | Multi-Phase Project: 14TPIT3040A - Upgrade 138kV Ckt.09 Fort Bend to Reading to increase thermal ratings. 14TPIT3040B - Upgrade 138kV Ckt.09 Reading to Crabb River Road to increase thermal ratings. 14TPIT3040C - Upgrade 138kV Ckt.09 Crabb River Road to WA Parish to increase thermal ratings. |  | Crabb River Road | WA Parish | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-31 |  | 138 | 0 | 9.5 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44010, 44170, 44280, 44172, 44570 | Y | N |  | Cost included in main project | 3896 | 3040
3138 | Dansby to Triangle Park Temp | Temporary T-Line to serve Triangle Park Sub while project is under construction |  | Dansby | Triangle Park | planned | 14TPIT0131 | BRYN | James Tanneberger 9798215763 |  | 2014-03-01 |  | 138 | 0.5 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32854, 32881, 32897 | Y |  |  |  | 3307 | 3138
3267 | E Rio Hondo to Central Avenue | Rebuild line where generation interconnection is planned |  | E Rio Hondo | Central Avenue | planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-06-02 |  | 138 | 0 | 27 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  | 5761, 5764, 5766 | Y | N |  |  | 3443 | 3267
3271 | Comal Street - New 138kV Substation | Loop new 138kV substation into the existing 138kV Ball Park to Olmos line. |  | Comal St | Ball Park-Olmos | Planned | T-0216 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0721 | 2015-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5096, 5011, 5325 | Y | N |  | There are no transformers associated with this project | 3447 | 3271
3272 | Potranco - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to AMD line. |  | Cagnon | AMD | Planned | S-0753 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0219 | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5346, 5002, 5053 | Y | N |  | There are no transformers associated with this project | 3448 | 3272
3273 | Southton - New 138kV Substation | A new 138kV substation from 138kV Braunig to Brooks. |  | Southton | Braunig-Brooks | Planned | S-0750 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0217 | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5394, 5030, 5045 | Y | N |  | There are no transformers associated with this project | 3449 | 3273
3274 | Nacogdoches to Skyline MLSE Upgrade | Upgrade terminals at Skyline and Nacogdoches to ensure a rating of 2386 A (minimum). |  | Skyline | Nacogdoches | Planned | S-0731b | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2015-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5315, 5369 | Y | N |  | There are no transformers associated with this project | 3450 | 3274
3275 | JT Deely to Converse MLSE Upgrade | Upgrade terminal at JT Deely to ensure a rating of 2386 A (minimum). |  | JT Deely | Converse | Planned | S-0759a | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2018-05-30 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5098, 5110 | Y | N |  | There are no transformers associated with this project | 3451 | 3275
3276 | JT Deely to Martinez MLSE Upgrade | Upgrade terminal at JT Deely to ensure a rating of 2386 A (minimum). |  | JT Deely | Martinez | Planned | S-0759b | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5294, 5110 | Y | N |  | There are no transformers associated with this project | 3452 | 3276
3277 | Shepherd Road - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Valley line. |  | Shepherd Road | Cagnon-Valley | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2019-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5378, 5053, 5465 | Y | N |  | There are no transformers associated with this project | 3453 | 3277
3297 | Tezel Road - New 138kV Substation | Loop new 138 kV substation into the existing 138 kV Helotes to Bandera line. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 5378, 5421, 5020, 5053, 5200, 5465 | Y |  |  | There are no transformers associated with this project | 3665 | 3297
3298 | Skyline - Install a Fourth 345kV Autotransformer. | Install one 600 MVA autotransformer at Skyline switchyard. |  |  |  | Planned | S-0670 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2016-06-01 |  | 345 | 0 | 0 | 600 |  | Bexar | Bexar | Tier 4 |  |  |  | 5372, 5371, 5368 | Y | N |  | There are no transmission line additions associated with this project | 3474 | 3298
3329 | Garfield Auto2 back in service |  |  |  |  | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 |  | 2014-07-01 |  | 0 | 0 | 0 | 0 | [7 empty] | 9071, 9048 | Y |  |  |  | 3510 | 3329
3334 | Fort Sam to Kirby MLSE Upgrade | Upgrade terminals at Fort Sam and ensure a rating of 2000 A at both Fort Sam and Kirby terminals. |  | Fort Sam | Kirby | Planned | S-0747 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5160, 5250 | Y | N |  | There are no transformers associated with this project | 3517 | 3334
3353 | Convert Aransas Pass - Rockport Line from 69 kV to 138 kV | Convert the Aransas Pass - Rockport line from 69 kV to 138 kV. It was previously built to 138 kV standards. |  | Aransas Pass | Rockport | Planned | 624 - 0792 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3507 | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 8427, 8430, 8432, 8434 | Y |  |  |  | 3542 | 3353
3361 | Magill Station: New 138kV Station for STEC Interconnect | Build New 138kV Station to Accommodate STEC Interconnection to serve customer load |  | Bay City | Lane City | Planned | 609-0777 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3496 | 2015-07-15 |  | 138 | 0 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  | 8111, 8113, 8127 | Y | N |  |  | 3556 | 3361
3396 | Cedar Hill: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Cedar Hill | Schedule Update | Cedar Hill |  | Planned | 626 - 0794 | AEP TNC |  | 2584 | 2015-05-31 |  | 69 | 0 | 0 | 90 |  | Coke |  | Tier 4 |  |  |  | 6423, 6425 | Y | N |  |  | 3594 | 3396
3397 | Sterling City: Add two 7.2 Mvar capacitor banks | Add two 7.2 Mvar capacitor banks at Sterling City, one 7.2 Mvar capacitor bank at Cedar Hill and two 7.2 Mvar capacitor banks at Bronte | Schedule Update | Sterling City |  | Planned | 629 - 0797 | AEP TNC |  | 2586 | 2015-05-31 |  | 69 | 0 | 0 | 0 | 0,14.4 | Sterling |  | Tier 4 |  |  |  | 6435 | Y | N |  |  | 3595 | 3397
3398 | Cedar Hill: Add 7.2 Mvar capacitor bank | Add two 7.2 Mvar capacitor banks at Sterling City, one 7.2 Mvar capacitor bank at Cedar Hill and two 7.2 Mvar capacitor banks at Bronte | Schedule Update | Cedar Hill |  | Planned | 629 - 0797 | AEP TNC |  | 2587 | 2015-05-31 |  | 69 | 0 | 0 | 0 | 0,7.2 | Coke |  | Tier 4 |  |  |  | 6423 | Y | N |  |  | 3596 | 3398
3399 | Bronte: Add two 7.2 Mvar capacitor banks | Add two 7.2 Mvar capacitor banks at Sterling City, one 7.2 Mvar capacitor bank at Cedar Hill and two 7.2 Mvar capacitor banks at Bronte | Schedule Update | Bronte |  | Planned | 629 - 0797 | AEP TNC |  |  | 2015-05-31 |  | 69 | 0 | 0 | 0 | 0,14.4 |  |  | Tier 4 |  |  |  | 6414 | Y | N |  |  | 3597 | 3399
3402 | Abilene Northwest to Ely Tap: Rebuild 69 kV line | Rebuild Abilene Northwest to Ely Tap 69 kV line with 959.6 ACSS/TW | Schedule Update | Abilene Northwest | Ely Tap | Planned | 630 - 0798 | AEP TNC |  | 2589 | 2017-05-31 |  | 69 | 0 | 8.2 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6225, 6241 | Y | N |  |  | 3600 | 3402
3406 | Tenaris 138 kV station | Connects new load to new Magill station with 138 kV line |  | Magill | Tenaris | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-07-16 |  | 138 | 4.5 | 4.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  | 5562, 5554, 5556, 5560, 8111 | Y | N |  |  | 3606 | 3406
3418 | Nelson Sharpe: Add 345 kV Breaker Terminal for WF Interconne | Add a new 345 kV line terminal at Nelson Sharpe for the Patriot WF Interconnect |  | Nelson Sharpe |  | Under Construction | 515 - 0756 | AEP TCC | Dave Goetz 918-599-2664 | 3474 | 2014-07-31 |  | 345 | 0 | 0 | 0 |  | Kleberg |  | Tier 4 |  |  |  | 85000 | Y | N |  |  | 3618 | 3418
3429 | Andrews County South 345/138 kV Switching Station | Construct new switching station with a 345/138 kV autotransformer |  |  |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8200-E | 2015-05-15 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 3 |  |  |  | 1157, 1158, 1150, 1153 | Y | N |  |  | 3768 | 3429
3430 | Midland County Northwest Sw. Sta. - Midessa 138 kV Line | Construct new 138 kV line |  | Midland County Northwest | Midessa | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8201-E | 2017-05-15 |  | 138 | 7.2 | 0 | 0 |  | Midland | Midland | Tier 3 |  |  |  | 1059, 1183 | Y | N |  |  | 3630 | 3430
3432 | Willow Valley Switch shunt reactor | Install shunt reactors on tertiary of 345/138 kV autotransformer |  | Willow Valley |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8193-WAC | 2014-03-15 |  | 345 | 0 | 0 | 0 | -75,0 | Borden |  | Tier 4 |  |  |  | 18537 | Y | N |  |  | 3632 | 3432
3433 | Midland County Northwest 345/138 kV Switching Station | Construct new switching station with a 345/138 kV autotransformer |  | Midland County Northwest |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8199-E | 2015-05-15 |  | 345 | 0 | 0 | 600 |  | Midland |  | Tier 3 |  |  |  | 1183, 1185, 1018, 1022, 1176, 1182 | Y | N |  |  | 3633 | 3433
3441 | Falfurias Autotransformer Upgrade | Move Lon Hill Auto #2 Serial # 01-8226-58010-1 to Falfurias after Lon Hill XFMR upgrade happens. |  | Falfurias |  | Planned | 632 - 0801 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3511 | 2015-06-01 |  | 138 | 0 | 0 | 92 |  | Brooks |  | Tier 4 |  |  |  | 8508, 8510 | Y |  |  |  | 3641 | 3441
3454 | Braunig_to_Toyota_Rebuild | Rebuild an existing 138 kV transmissions line between the Toyota and Valley Road Substations. |  | Braunig-Alamo1_8-Mauerman-Valley | Alamo1_8-Mauerman-Toyota-Cagnon | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0181 | 2015-06-01 |  | 138 | 0 | 13.7 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5007, 5053, 5297, 5025, 5428, 5465 | Y | N |  | There are no transformers associated with this project | 3655 | 3454
3456 | Morgan Creek 138/69 kV autotransformer | Replace existing autotransformer |  | Morgan Creek Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8151-E | 2015-05-15 |  | 138 | 0 | 0 | 150 |  | Mitchell |  | Tier 4 |  |  |  | 1032, 1033, 11035 | Y | N |  |  | 3659 | 3456
3463 | Shady Bus Split | Reconfigure 69kV bus |  |  |  | Planned |  | BRYN | James Tanneberger 9798215763 |  | 2017-07-01 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 3668 | 3463
3479 | Cassava: Build new three breaker 69 kV ring bus | Construct new Cassava station along the Big Lake to Mathis Field 69 kV line (at Barnhart Phillips Tap location) |  | Cassava |  | Planned | 635 - 0804 | AEP TNC |  | 2590 | 2015-12-31 |  | 69 | 0 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6003, 60359, 6035, 6526, 6532 | Y | N |  |  | 3686 | 3479
3480 | Cassava to Yucca: Rebuild 69 kV line | Rebuild 69 kV line as 138 kV from Cassava (Barnhart Phillips Tap) to Yucca with 795 ACSR and add 138/69 kV autotransformer capacity at Cassava |  | Cassava | Yucca | Planned | 635 - 0804 | AEP TNC |  | 2591 | 2016-12-31 |  | 138 | 12.3 | 0 | 90 |  | Taylor | Taylor | Tier 4 |  |  |  | 6034, 6035, 6531, 60360, 6036, 60359 | Y | N |  |  | 3687 | 3480
3507 | Nopal Substation | Build a new 138-26.18 kV 18/24/30 MVA substation to be served by Gillett to Nopal 138 kV transmission line |  | Nopal |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2015-06-29 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7233 | Y | N |  |  | 3714 | 3507
3509 | Gillett Sub (LCRA) to Nopal Sub 138 kV Transmission Line | Build 8.5 miles of single ckt 138 kV t-line, 795 ACSR |  | Gillett | Nopal | Planned | 15TPIT0063 | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2015-06-30 |  | 138 | 8.5 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  | 7233, 78582 | Y | N |  |  | 3716 | 3509
3527 | Randado: Add 138 kV breaker terminal for SF interconnect | Construct a 138 kV breaker terminal at Randado for generation Interconnect | CHANGES | RANDADO |  | UNDER CONSTRUCTION |  | AEP TCC | BRENT HASSIS GAREED@AEP.COM 918-599-2664 | TP2010005 | 2014-03-31 |  | 138 | 0 | 0 | 0 |  | Jim Hogg |  | Tier 4 |  |  |  | 8699 | Y |  | NA | NA | 3734 | 3527
3546 | Edroy 69 kV station: Install series reactor | Construct a 15-ohm series reactor at Edroy on the terminal to Mathis 69 kV | CHANGES | EDROY |  | CONCEPTUAL |  | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 |  | 2015-03-31 |  | 69 | 0 | 0 | 0 | 15,0 | San Patricio |  | Tier 3 |  |  |  | 8408 | N | N | NA | NA | 3754 | 3546
3575 | Raymondville #1 to Raymondville #2: Open 69 kV Line | Segment the Harlingen Switching Station to Raymondville #2 69 kV throughpath by opening the line between Raymondville #1 and Raymondville #2 | NEW | Raymondville #1 | Raymondville #2 | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2015-06-30 |  | 69 | 0 | 0 | 0 |  | Willacy | Willacy | Tier 4 |  |  |  | 8300, 8325, 8700 | Y | N |  | RTP: 2012-R11 | 3789 | 3575
3580 | Cottulla STEC tap into AEP Line | Cotttulla STEC Substation tap into existing AEP Dilley SS to Reveille 138kV Line. |  | Jardin | Cotulla | Planned | 631 - 0800 | AEP TCC | Glen Reed 918-599-2664 | 3510 | 2014-05-10 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 8520, 8610, 8611 | Y | N |  |  | 3794 | 3580
3582 | Skyline 80 MVAR Capacitor Bank | Install 80 MVAR capacitor bank on the North bus |  |  |  | Planned | S-0707 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2014-02-05 |  | 138 | 0 | 0 | 0 | 0,80 | Bexar | Bexar | Tier 4 |  |  |  | 5368, 5435 | Y | N |  | There are no transformers associated with this project | 3796 | 3582
3587 | PH Robinson-South Shore rebuild |  |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2014-05-31 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 38890, 42015 | Y |  |  |  | 3801 | 3587
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits. |  | Bevo | Carrizo Springs | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 2 |  |  |  | 5871, 8244 | Y | N |  |  | 3809 | 3595
3636 | Welsh HVDC: Upgrade Station Svc and Install New Filter | Welsh HVDC Tie: Phase 2 Station Upgrades | PM, PVID, Prj Desc, In-Service Changes | WELSH HVDC Tie |  | Planned | 625 - 0793 | AEP TCC | Bill Clarke 918-599-2664 |  | 2015-12-31 |  | 345 | 0 | 0 | 0 | 0,100 | Titus |  | Tier 4 |  |  |  | 5925 | Y | Y |  |  | 3866 | 3636
3659 | New Midstream 138 kV station | New load serving station with two short lines to AEP Bessel sub |  | Midstream |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-01-01 |  | 138 | 0.4 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 5643, 80601 | Y | N |  |  | 3893 | 3659
3663 | College Hills: Replace 138/69 kV autotransformer | Add 138/69 kV autotranformer capacity at College Hills | NEW | College Hills |  | Planned | 641 - 0810 | AEP TNC |  | 1805 | 2017-05-31 |  | 138 | 0 | 0 | 90 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6468, 6470 | Y | N |  |  | 3900 | 3663
3664 | San Angelo North: Replace 138/69 kV autotransformer | Add 138/69 kV autotranformer capacity at San Angelo North | NEW | San Angelo North |  | Planned | 642 - 0811 | AEP TNC |  | 1806 | 2017-05-31 |  | 138 | 0 | 0 | 90 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6462, 6464 | Y | N |  |  | 3901 | 3664
3665 | Texon Tap to Texon: Rebuild 69 kV line and convert to 138 kV | Rebuild Texon Tap to Texon 69 kV line with 959.6 ACSR/TW and tap the Big Lake to N. Mcamey 138 kV line and convert Texon to 138 kV | NEW | Texon Tap | Texon | Planned | 643 - 0812 | AEP TNC |  | 1460 | 2017-05-31 |  | 138 | 0.75 | 2.9 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 6538, 6541, 60361, 60363, 60364, 6536, 6542, 6544, 6555, 6589, 76032 | Y | N |  |  | 3902 | 3665
3666 | Atlantic Best Tap to Atlantic Best: Rebuild 69 kV line | Rebuild Atlantic Best Tap to Atlantic Best 69 kV line with 959.6 ACSR/TW and tap the Big Lake to N. Mcamey 138 kV line and convert Atlantic Best to 138 kV | NEW | Altantic Best Tap | Atlantic Best | Planned | 644 - 0813 | AEP TNC |  | 1461 | 2017-05-31 |  | 138 | 0.58 | 5.6 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 6542, 6555, 60362, 60361, 60364 | Y | N |  |  | 3903 | 3666
3668 | New Kittie West substation | Add new station for AEP load on 69 kV |  | Kittie West |  | planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2014-11-15 |  | 0 | 0 | 0 | 0 |  | Live Oak |  | Tier 4 |  |  |  | 5683, 5685, 5690 | Y | N |  |  | 3905 | 3668
3669 | Albany Foundry to Moran: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line with 959.6 ACSR/TW | NEW | Albany Foundry | Moran | Planned | 645 - 0814 | AEP TNC |  | 1808 | 2019-05-31 |  | 69 | 0 | 10 | 0 |  | Shackelford | Shackelford | Tier 4 |  |  |  | 6202, 6209 | Y | N |  |  | 3906 | 3669
3670 | Albany to Albany Foundry: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line with 959.6 ACSR/TW | NEW | Albany | Albany Foundry | Planned | 645 - 0814 | AEP TNC |  | 1809 | 2020-05-31 |  | 69 | 0 | 5.13 | 0 |  | Shackelford | Shackelford | Tier 4 |  |  |  | 6202, 6207, 6213 | Y | N |  |  | 3907 | 3670
3671 | Moran to Putnam: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line with 959.6 ACSR/TW | NEW | Moran | Putnam | Planned | 645 - 0814 | AEP TNC |  | 1807 | 2018-05-31 |  | 69 | 0 | 12.86 | 0 |  | Shackelford | Callahan | Tier 4 |  |  |  | 6209, 6307 | Y | N |  |  | 3908 | 3671
3673 | TNC Mason to LCRA Ft. Mason: Rebuild 69 kV line | Rebuild TNC Mason to LCRA Ft. Mason 69 kV line with 959.6 ACSR/TW | NEW | TNC Mason | LCRA Ft. Mason | Planned | 646 - 0815 | AEP TNC |  | 1810 | 2017-05-31 |  | 69 | 0 | 0.15 | 0 |  | Mason | Mason | Tier 4 |  |  |  | 6393, 76388 | Y | N |  |  | 3910 | 3673
3674 | Puncher: Add one 7.2 Mvar capacitor bank | Puncher: Add one 7.2 Mvar capacitor bank | NEW | Puncher |  | Planned | 647 - 0816 | AEP TNC |  | 1811 | 2017-05-31 |  | 69 | 0 | 0 | 0 | 0,7.2 | Mason |  | Tier 4 |  |  |  | 6407 | Y | N |  |  | 3911 | 3674
3675 | Foxtail: Build temporary tap | Interconnect Green Pastures Wind Farm at Foxtail to connect Green Pastures and Vertigo to the Oklaunion to Mulberry Creek 345 kV line | NEW | Foxtail |  | Planned | 650 - 0818 | AEP TNC |  | 1812 | 2014-12-31 |  | 345 | 0 | 0 | 0 |  | Baylor |  | Tier 4 |  |  |  | 6076, 6100, 6235 | Y | N |  |  | 3912 | 3675
3676 | Foxtail: Build four breaker 345 kV ring bus | Interconnect Green Pastures Wind Farm at Foxtail to connect Green Pastures and Vertigo to the Oklaunion to Mulberry Creek 345 kV line | NEW | Foxtail |  | Planned | 648 - 0817 | AEP TNC |  | 1813 | 2015-12-31 |  | 345 | 0 | 0 | 0 |  | Baylor |  | Tier 4 |  |  |  | 6076, 6100, 6235 | Y | N |  |  | 3913 | 3676
3677 | Replace Meadow Failed 500MVA Auto with 400MVA GBY A2 Auto | Replace failed 500MVA autotransformer A1 at Meadow with spare 400MVA transformer. |  | Meadow |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-31 |  | 345 | 0 | 0 | -100 |  | Brazoria |  | Tier 4 |  |  |  | 43030, 43031, 49046 | Y | N |  |  | 3914 | 3677
3678 | Barrilla Junction : Add new 138 kV terminal position | Interconnect Barrilla Solar farm at Barrilla Junction 138 kV station | NEW | Barrilla Junction |  | Planned | 649 - 0819 | AEP TNC |  | 1814 | 2014-12-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6653 | Y | N |  |  | 3915 | 3678
3679 | Remove Brisco and Juliff from transmission service | Multi-Phase Project: 14TPIT3679A - Remove Brisco substation from CNP transmission service. 14TPIT3679B - Remove Juliff substation from CNP transmission service. |  | Brisco |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-03-30 |  | 69 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  | 44110, 44380, 42041, 43260, 44362, 44400, 47150, 44361, 44552, 47165 | Y | N |  | Cost included in main project | 3916 | 3679
3679 | Remove Brisco and Juliff from transmission service | Multi-Phase Project: 14TPIT3679A - Remove Brisco substation from CNP transmission service. 14TPIT3679B - Remove Juliff substation from CNP transmission service. |  | Juliff |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-03-31 |  | 69 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  | 44110, 44380, 42041, 43260, 44362, 44400, 47150, 44361, 44552, 47165 | Y | N |  | Cost included in main project | 3917 | 3679
3680 | Decker-Exxon Ckt83 Thermal Uprate | Upgrade 138kV Ckt.83 Decker to Exxon to increase thermal ratings. |  | Decker | Exxon | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-05-31 |  | 138 | 0 | 1 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40430, 40570 | Y | N |  |  | 3918 | 3680
3681 | TH Wharton to Addicks Ckt.71 | Multi-Phase Project: 15TPIT3681A - Upgrade 345kV Ckt.71 TH Wharton to Addicks to increase thermal ratings. 15TPIT3681B - Upgrade substation equipment at TH Wharton and Addicks to increase thermal ratings for 345kV Ckt.71. |  | TH Wharton | Addicks | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-04-30 |  | 345 | 0 | 9.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45500, 45600 | Y | N |  |  | 3919 | 3681
3681 | TH Wharton to Addicks Ckt.71 | Multi-Phase Project: 15TPIT3681A - Upgrade 345kV Ckt.71 TH Wharton to Addicks to increase thermal ratings. 15TPIT3681B - Upgrade substation equipment at TH Wharton and Addicks to increase thermal ratings for 345kV Ckt.71. |  | TH Wharton | Addicks | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45500, 45600 | Y | N |  |  | 3920 | 3681
3682 | Katy Area Upgrades | Multi-Phase Project: 17TPIT3682A - Convert Franz Substation to loop service from 138kV Ckt.09. Install new conductor and reconfigure/upgrade existing lines to create new Ckt.09 Zenith to Franz to Katy. 17TPIT3682B - Convert Katy substation ckt 09 tap to loop service to modify Ckt.09 Flewellen to Katy to Franz. 17TPIT3682C - Install a second 800MVA autotransformer at Zenith Substation. |  | Zenith | Katy | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-05-31 |  | 138 | 6.4 | 1.6 | 0 |  | Harris | Waller | Tier 2 | 2013-12-18 |  |  | 44260, 44261, 44262, 44420, 44421, 49090, 44230, 44422, 44910, 45770, 44900 | N | N |  | Part of ERCOT RPG Katy Area Upgrades. | 3921 | 3682
3682 | Katy Area Upgrades | Multi-Phase Project: 17TPIT3682A - Convert Franz Substation to loop service from 138kV Ckt.09. Install new conductor and reconfigure/upgrade existing lines to create new Ckt.09 Zenith to Franz to Katy. 17TPIT3682B - Convert Katy substation ckt 09 tap to loop service to modify Ckt.09 Flewellen to Katy to Franz. 17TPIT3682C - Install a second 800MVA autotransformer at Zenith Substation. |  | Katy |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Waller |  | Tier 2 | 2013-12-18 |  |  | 44260, 44261, 44262, 44420, 44421, 49090, 44230, 44422, 44910, 45770, 44900 | N | N |  | Part of ERCOT RPG Katy Area Upgrades. | 3922 | 3682
3682 | Katy Area Upgrades | Multi-Phase Project: 17TPIT3682A - Convert Franz Substation to loop service from 138kV Ckt.09. Install new conductor and reconfigure/upgrade existing lines to create new Ckt.09 Zenith to Franz to Katy. 17TPIT3682B - Convert Katy substation ckt 09 tap to loop service to modify Ckt.09 Flewellen to Katy to Franz. 17TPIT3682C - Install a second 800MVA autotransformer at Zenith Substation. |  | Zenith |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-05-31 |  | 345 | 0 | 0 | 800 |  | Harris |  | Tier 2 | 2013-12-18 |  |  | 44260, 44261, 44262, 44420, 44421, 49090, 44230, 44422, 44910, 45770, 44900 | N | N |  | Part of ERCOT RPG Katy Area Upgrades. | 3923 | 3682
3683 | Ab South to Ab West TX Gulf Tap: Rebuild 69 kV line | Rebuild Abilene South to Abilene Power Station 69 kV line with 959.6 ACSR/TW | NEW | Abilene South | Abilene West Texas Gulf Tap | Planned | 651 - 0820 | AEP TNC |  | 1815 | 2018-05-31 |  | 69 | 0 | 2.15 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6258, 6284 | Y | N |  |  | 3924 | 3683
3684 | Jerry: Build new 138 kV station | Construct new Jerry station along the Big Lake to Twin Buttes 138 kV line | NEW | Jerry |  | Planned | 656 - 0825 | AEP TNC |  | 1820 | 2014-04-30 |  | 138 | 0 | 0 | 0 |  | Reagan |  | Tier 4 |  |  |  | 6559, 6648, 6535, 76011 | Y | N |  |  | 3925 | 3684
3685 | Hargrove: Build new 138 kV station | Construct new Hargrove station along the Big Lake to Twin Buttes 138 kV line | NEW | Hargrove |  | Planned | 652 - 0821 | AEP TNC |  | 1816 | 2014-06-30 |  | 138 | 0 | 0 | 0 |  | Irion |  | Tier 4 |  |  |  | 6559, 6648, 6535, 76011 | Y | N |  |  | 3926 | 3685
3686 | Viinson: Build new 138 kV station | Construct new Vinson station along the South Abilene to Putnam 138 kV line | NEW | Vinson |  | Planned | 653 - 0822 | AEP TNC |  | 1817 | 2014-05-31 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  | 60355, 6260, 6313 | Y | N |  |  | 3927 | 3686
3687 | Estes: Build new 138 kV station | Construct new Estes station along the South Abilene to Putnam 138 kV line | NEW | Estes |  | Planned | 655 - 0824 | AEP TNC |  | 1819 | 2014-12-31 |  | 138 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  | 60365, 6309, 6773 | Y | N |  |  | 3928 | 3687
3693 | Add_HOLCOMB | Distribution Project DP13X0014 |  | NORTH LAREDO SWITCHING STATION | REVEILLE | Planned |  | AEP TCC |  |  | 2014-12-31 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 8108, 8619, 8909 | Y |  |  |  | 3936 | 3693
3694 | AEP_Add_MAYBERRY | Distribution Project DR13X0003 |  | FRONTERA | SLU TAYLOR ROAD | Planned |  | AEP TCC |  |  | 2014-08-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 8109, 8391, 8980 | Y |  |  |  | 3937 | 3694
3695 | AEP_Add_TYNAN | Distribution Project DP13X0037 |  | BEEVILLE | MATHIS | Planned |  | AEP TCC |  |  | 2014-10-31 |  | 69 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  | 8107, 8198, 8407 | Y |  |  |  | 3938 | 3695
3696 | Friend Ranch to Ozona: Rebuild 69 kV line | Rebuild Friend Ranch to Ozona line with 959.6 ACSS/TW | NEW | Friend Ranch | Ozona | Planned | 657 - 0826 | AEP TNC |  | 1821 | 2016-12-31 |  | 69 | 0 | 3.4 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  | 6550, 6560 | Y | N |  |  | 3939 | 3696
3697 | Neas: Build new 138 kV station | Construct new Neas station along the Ft. Phantom to South Abilene 138 kV line | NEW | Neas |  | Planned | 654 - 0823 | AEP TNC |  | 1818 | 2014-08-31 |  | 138 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  | 60366, 6222, 6292 | Y | N |  |  | 3940 | 3697
3702 | Oklaunion: HVDC tie | Build a new HVDC tie to replace the old one between SPP and ERCOT at Oklaunion | NEW | Oklaunion |  | Planned | 425 - 0614 | AEP TNC |  | 3198 | 2014-05-31 |  | 345 | 0 | 0 | 0 | 0,135 | Wilbarger |  | Tier 4 |  |  |  | 6102 | Y | N |  |  | 3944 | 3702
3705 | Barrilla Junction: Convert to a ring bus | Convert the 138 kV straight bus at Barrilla Junction to a ring bus | NEW | Barrilla Junction |  | Planned | 658 - 0827 | AEP TNC |  | 1822 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6653 | Y | N |  |  | 3947 | 3705
3712 | Wink (Oncor) to TNP 69 kV Line | Upgrade terminal equipment at Wink (Oncor) |  | Wink |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 |  | 2014-05-15 |  | 69 | 0 | 0 | 0 |  | Winkler |  | Tier 4 |  |  |  | 1075, 37920 | Y | N |  |  | 3956 | 3712
3715 | Cottulla STEC 138kV Station | Cotulla STEC 138kV Substation | NEW | JARDIN | COTULLA (AEP) | Planned | 631 - 800 | AEP TCC | Glen Reed 918-599-2664 | 3528 | 2015-09-30 |  | 138 | 0 | 0 | 0 |  | La Salle | La Salle | Tier 4 |  |  |  | 8526, 8610, 8611 | Y | N |  |  | 3959 | 3715
3723 | Benedum Substation Addition | Construct a new 138-kV substation, Benedum (71213), on the LCRA Midkiff (1210) to Upton (1212) 138-kV transmission line. |  | Benedum |  | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2014-09-01 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  | 71213, 1210, 1212 | Y | N |  |  | 3967 | 3723
3732 | Cedar Bayou to Jordan Ckt.99 | Upgrade equipment at Cedar Bayou to increase Ckt.99 thermal ratings. |  | Cedar Bayou | Jordan | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-12-31 |  | 345 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  | 40000, 40850 | Y | N |  |  | 3977 | 3732
3745 | Del Sol: Add 345 kV breaker terminal for WF interconnect | Construct four 345 kV breaker ring exdable at Del Sol Station for the Generator Interconnect | CHNAGES | DEL SOL |  | UNDER CONSTRUCTION | 666-0835 | AEP TCC | KENNETH 'RICH' HALEY GAREED@AEP.COM 918-599-2664 | 3530 | 2016-06-30 |  | 345 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  | 80355 | Y | N | NA | NA | 3991 | 3745
3754 | Yellowjacket to North Brady: Build new 69 kV line | Build new 69 kV line from Yellowjacket to City of Brady and rebuild 69 kV line from City of Brady to North Brady with 959.6 ACSR/TW |  | Yellowjacket | North Brady | Planned | 637 - 0806 | AEP TNC |  | 2592 | 2017-05-31 |  | 69 | 32 | 0.4 | 0 |  | Mason | McCulloch | Tier 2 |  |  |  | 6006, 6363, 6382, 6383 | Y | N | 2014-01-23 |  | 3999 | 3754
3757 | Rebuild Lake Whitney - Olsen 69 KV with 795 ACSR | Rebuild Lake Whitney - Olsen 69 KV (CT06902), reconductor with 795 ACSR. |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07314 | 2014-12-01 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 37420, 37470 | Y |  |  |  | 4002 | 3757
3760 | Asherton to Carrizo Spring: 69 kV Transmission Line Rebuild | Rebuild 69 kV line from Asherton to Carrizo Spring | CHANGES | ASHERTON | CORIZO SPRING | CONCEPTUAL | 661-0830 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 | 3526 | 2015-06-30 |  | 69 | 0 | 8.3 | 0 |  | Dimmit | Dimmit | Tier 4 |  |  |  | 8244, 8280 | N | N | NA | NA | 4005 | 3760
3761 | Victoria to Fannin: 69 kV Transmission Line Rebuild | Rebuild Victoria to Fannin 69 kV line | changes | VICTORIA | FANNIN | CONCEPTUAL | 662-0831 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 | 3527 | 2015-12-31 |  | 69 | 0 | 13.5 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  | 5736, 8169 | Y | N | NA | NA | 4006 | 3761
3764 | Brackettville 138 kV Station: Upgrade 138 kV Station | Construct a five breakers ring at the expanded Brackettville 138 kV Statio for the Generator Interconnect | CHANGES | BRACKETTVILLE |  | UNDER CONSTRUCTION | 665-0834 | AEP TCC | MICHAEL TALLON GAREED@AEP.COM 918-599-2664 | 3529 | 2015-12-01 |  | 138 | 0 | 0 | 0 |  | Kinney |  | Tier 4 |  |  |  | 8252 | Y | N | NA | NA | 4009 | 3764
3765 | Bessel 138 kV Station: Construct a new station | Construct 4 breaker ring for custormer interconenction | CHANGES | BESSEL |  | CONCEPTUAL |  | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 |  | 2014-11-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 80901, 8452, 8514 | N | N | NA | NA | 4010 | 3765
3766 | Asherton to Carrizo Spring: 69 kV Transmission Line Rebuild | Rebuild 69 kV line from Asherton to Carrizo Spring | CHANGES | ASHERTON |  | CONCEPTUAL | 659-0828 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 | 3524 | 2015-12-31 |  | 138 | 0 | 0 | 130 |  | Dimmit |  | Tier 4 |  |  |  | 89633, 8283, 8280 | N | N | NA | NA | 4011 | 3766
3767 | Three River 138 kV: Replace 138/69 kV Autotransformer | Replace 138/69 kV Auto at Three Rivers 138 kV Station | CHANGES | THREE RIVER |  | CONCEPTUAL | 660-0829 | AEP TCC | GLEN REED GAREED@AEP.COM 918-599-2664 | 3525 | 2015-12-31 |  | 138 | 0 | 0 | 130 |  | Live Oak |  | Tier 4 |  |  |  | 8344, 8403, 8400 | N | N | NA | NA | 4012 | 3767
TPIT3503 | Rebuild Seguin-Deer Creek to 138kV | Rebuild 6/1 miles (Capote to Deer Creek, back to Seguin is 138) single Ckt 69 to 138 kV, 795 ACSR, terminals at Seguin and Deer Creek |  | Seguin | Deer Creek | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2016-03-31 |  | 138 | 0 | 6.1 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7228 | Y | N |  |  | 3710 | 3503
TPIT3505 | Cibolo Substation | Add T3, 40 MVA 138-26.18 kV power transformer, CSW and low side |  | Cibolo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2015-12-31 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7608 | Y | N |  |  | 3712 | 3505

## CompletedTPIT020114NoCost
PRIVILEGED AND CONFIDENTIAL, DO NOT release outside of ERCOT Staff or Transmission Providers organization. Contains critical cost information that can affect bids for projects.
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/01/2014
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
06TPIT0057 | AEP_06TPIT0057_Magr_line update | AEP_06TPIT0057_Magr_line update | In Service | Magruder |  | Planned | 389-0567 | AEP TCC |  | 3375 | 2013-04-30 | 2013-04-30 | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  | 8172, 8183, 8194 | Y | N |  |  | 3014 | 2841
07TPIT0024 | Lytle: Add 138-69 kV Auto | Add CPS Lytle to ETT Lytle 795 ACSR 138 kV line and 93 MVA 69-138 kV autotransformer at Lytle | IN-SERVICE | Lytle |  | IN-SERVICE | 028 - 0028 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 3373 | 2013-04-02 | 2013-04-02 | 138 | 0 | 0 | 93 |  | Medina |  |  | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8622, 8962 | Y | N |  |  | 1245 | 1242
07TPIT0078 | Devine to Lytle: Rebuild 69 kV Line | Add CPS Lytle to ETT Lytle 795 ACSR 138 kV line and 93 MVA 69-138 kV autotransformer at Lytle |  | Devine | Lytle | UnderConstruction | 028 - 0028 | AEP TCC | RICK McCRAKEN 918-599-2664 | 1778 | 2013-11-15 | 2013-11-15 | 69 | 0 | 7 | 0 |  | Medina | Medina | Tier 4 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8223, 8622 | Y | N |  |  | 1241 | 1238
07TPIT0250 | Lone Tree: Install 1-14.4 MVAR 69 kV Cap Banks | Add capacitors in Victoria area at the McGruder Victoria plant and Lone Tree | In Service | Lone Tree |  | UnderConstruction | 389 - 0667 | AEP TCC |  | 2047 | 2013-03-01 | 2013-03-01 | 69 | 0 | 0 | 0 | 0,14.4 | Victoria |  | Tier 4 |  |  |  | 8180 | Y | N |  |  | 1020 | 1019
07TPIT0250 | Lone Tree: Install 1-14.4 MVAR 69 kV Cap Banks | Add capacitors in Victoria area at the McGruder Victoria plant and Lone Tree | Changed Status | Lone Tree |  | UnderConstruction | 389 - 0667 | AEP TCC |  | 2047 | 2013-03-31 | 2013-03-31 | 69 | 0 | 0 | 0 | 0,14.4 | Victoria |  | Tier 4 |  |  |  | 88179 | Y | N |  |  | 2045 | 1995
08TPIT0097 | Rhome to Roanoke Rebuild | Rebuild existing Rhome to Roanoke |  | Rhome | Roanoke | UnderConstruction |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 6062 | 2013-12-31 | 2013-12-31 | 138 | 0 | 16.6 | 0 |  | Wise | Denton | Tier 4 |  |  |  | 640, 1852, 1866 | Y | N |  | 602-640 completed 4-19-2012 640-1852-1866 completed 12-31-2012 | 895 | 894
08TPIT0109 | Payne - Collin Switching Station 138 kV line | Rebuild existing 138 kV line |  | Payne | EPCO | Under construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R519-E | 2014-01-15 | 2014-01-15 | 138 | 0 | 14.8 | 0 |  | Grayson | Collin | Tier 3 |  |  |  | 1757, 1758, 2350, 2366, 12349, 12468, 2349, 2370 | Y | N | 2009-R12 | Payne - EPCO section will be completed by 12/2013. | 3380 | 2174
09TPIT0032 | Williamson 31.2 Mvar Capacitor bank | Install one 31.2 Mvar capacitor bank at Williamson substation. |  | Williamson Substation | Williamson Substation | Planned |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | PLAN_117_P063 | 2013-08-15 | 2013-08-15 | 138 | 0 | 0 | 0 | 0,31.2 | Travis | Travis | Tier 4 |  |  |  | 9295 | Y | N |  |  | 255 | 258
10TPIT0020 | Anna Switch - Krum W. Switch 345 kV line | Construct a double-circuit 345 kV line |  | Anna Switch | Krum W. Switch | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C060-E | 2013-12-15 | 2013-12-15 | 345 | 140 | 0 | 0 |  | Denton | Collin | CREZ |  |  |  | 1730, 2373 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 1052 | 1051
10TPIT0031 | Dunlap 138/345kV Autotransformer Project | Install a 138-345 672 MVA autoxfmr at Dunlap, configuring a Dunlap to Lost Pines 345 kV circuit, add a new 345kV line from Dunlap to Austrop and merge 138kv Dunlap to Decker and Decker to Techridge into one single circuit bypassing Decker. Re-terminate t | As part of the project, the existing Webber Solar Tap will be removed and the solar plant will be connected to the existing vacant position at Austrop substation. | Dunlap Substation | Dunlap Substation | UnderConstruction |  | AEN | Biju Mathew biju.mathew@austinenergy.com 512-322-6737 | PLAN_117_P132 | 2013-07-16 | 2013-07-16 | 345 | 0 | 0 | 672 |  | Travis | Travis | Tier 3 | 2010-04-01 | 2010-06-01 |  | 9044, 9045, 7040, 9041, 9187, 9188, 9190, 9328 | Y | N |  |  | 1013 | 1012
10TPIT0048 | Koppe Bridge Substation | Install (4) Breaker ring to include (2) 138 lines and (1) 138-12.5 transformer |  | Koppe Bridge | Koppe Bridge | UnderConstruction | 10TPIT0049 | BRYN | James Tanneberger 9798215763 |  | 2013-09-01 | 2013-09-01 | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32860 | Y | N |  |  | 1828 | 1785
10TPIT0049 | Koppe Bridge to Wellborn Transmission | Build (5.8) miles of 138 kV line(s) to serve station |  | Koppe Bridge | Wellborn | planned | 10TPIT0048 | BRYN | James Tanneberger 9798215763 |  | 2013-09-01 | 2013-09-01 | 138 | 6.2 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32860, 32895 | Y | N |  |  | 1830 | 1787
10TPIT0070 | AEP_10TPIT0070_Magr-Vict | AEP_10TPIT0070_Magr-Vict | In Service | Magruder | North Victoria | Under Construction | 389-0567 | AEP TCC |  | 3261 | 2013-04-01 | 2013-04-01 | 69 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  | 8169, 8177, 8178 | Y | N |  |  | 2981 | 2808
10TPIT0070 | Magruder to North Victoria: Rebuild 69 kV Line | Reconductor Magruder to North Victoria 69 kV line to 795 ACSS. Install 138-69 kV, 187 MVA, autotransformer at Magruder on the Victoria to Thomaston 138kV line. |  | Magruder | North Victoria | UnderConstruction | 389 - 0567 | AEP TCC |  | 3261 | 2013-03-30 | 2013-03-30 | 69 | 0 | 3.7 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  | 8177, 8178 | Y | N |  |  | 1011 | 1010
10TPIT0082 | Carlton Switch to Mountary Rebuild | Rebuild Carlton Switch to Mountary with 959ACSS |  | Carlton | Mountary | UnderConstruction |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 8051 | 2013-01-14 | 2013-01-14 | 69 | 0 | 9.6 | 0 |  | Erath | Comanche | Tier 4 |  |  |  | 294, 297 | Y | N |  |  | 2583 | 2478
11TPIT0024 | TCC - 138kV Line Reroutes | The following 138kV lines will be rerouted: Cagnon - AMDTP - AMD becomes Cagnon - AMD Cagnon - AMDTP - Pinn becomes Cagnon - Pinn Pinn - SWRI becomes Pinn - Westside Construct a new 138kV line from TCC - SWRI Cagnon - AMD line upgrade to 1590AAC |  | Cagnon Cagnon Pinn Rd TCC | AMD Pinn Rd Westside SWRI | Planned | S-0384 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0106 | 2013-05-01 | 2013-05-01 | 138 | 5.8 | 0 | 0 |  | Bexar | Bexar | Tier 4 | 2012-08-07 |  |  | 5004, 5424, 5002, 5054, 5345, 5423, 5490 | Y | N |  | There are no transformers associated with this project | 2332 | 2259
11TPIT0038 | COCS Northgate Substation | Install (3) Breaker ring to include (2) 138 lines and tap to City of College Station |  | COCS Northgate | COCS Northgate | planned |  | COCS | Mike Duff mduff@cstx.gov 979-764-3682 |  | 2013-12-01 | 2013-12-01 | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32006, 32798, 32862 | Y |  |  |  | 3214 | 3045
11TPIT0076 | Cottonwood 345 kV Station and Cotttonwood to Dermott 345 kV | Establish new 345 kV Cottonwood station and construct a new double circuit 345 kV transmission line WETT new Cottonwood and Oncor's Dermott 345 kV stations. Includes 2x50 MVAR shunt reactor banks at Cottonwood. |  | Cottonwood | Dermott | Planned |  | LST |  |  | 2013-03-15 | 2013-03-15 | 345 | 74.2 | 0 | 0 | -100,0 | Dickens | Scurry | CREZ |  |  |  | 59904, 11305 | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases | 2368 | 2293
11TPIT0077 | Riley, add two 130.9 MVar capacitors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In-Service |  |  | In-Service | 467 - 0668 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2379 | 2013-03-31 | 2013-03-31 | 0 | 0 | 0 | 0 | 0,261.8 | Wilbarger |  | CREZ Modified |  |  |  | 6101 | Y | N |  |  | 3419 | 3245
11TPIT0078 | Riley, add four 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In Service | Riley |  | In Service | 467 - 0668 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2380 | 2013-03-31 | 2013-03-31 | 345 | 0 | 0 | 0 | -200,0 | Wilbarger |  | CREZ Modified |  |  |  | 6101 | Y | N |  |  | 1071 | 1070
11TPIT0079 |  | Build new Riley 345 kV switch station, cut in the existing and future 345 kV lines as described in ERCOT CREZ Scenario 2 | In-Service | Riley |  | In-Service | 467 - 0668 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2435 | 2013-03-31 | 2013-03-31 | 0 | 0 | 0 | 0 |  | Wilbarger |  | CREZ |  |  |  | 6101 | Y | N |  |  | 3420 | 3246
11TPIT0085 | Doedyns-Sioux 138kV Line | Build New 138kV Line from Doedyns-Sioux Substations | Delays due to Right of Way process | Doedyns | Sioux | Under Construction | 06TPIT0166 | STEC | Doug Evans devans@stec.org 361-485-6459 | 789640 | 2013-06-01 | 2013-06-01 | 138 | 5.5 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 2 | 2005-02-01 | 2005-04-20 |  | 5753, 5792 | Y | N |  |  | 1929 | 1880
11TPIT0111 | Snook to Koppe Bridge Transmission Line | Build 13 miles of 1033ACSR transmission line (operated at 138 kV) to Koppe Bridge substation. | The Thompson Creek to Koppe Bridge Line is now broken into two segments with different completion dates. | Snook Substation | Koppe Bridge | planned |  | BRYN | James Tanneberger 9798215763 |  | 2013-09-01 | 2013-09-01 | 138 | 13 | 0 | 0 |  | Burleson | Brazos | Tier 4 |  |  |  | 32857, 32860 | Y | N |  |  | 1370 | 1365
11TPIT0133 | Bowie to Montague Rebuild | Rebuild Bowie to Montague 69kV line with 959 ACSS |  | Bowie | Montague | planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 10015 | 2013-06-10 | 2013-06-10 | 69 | 0 | 11 | 0 |  | Montague | Montague | Tier 4 |  |  |  | 621, 632, 1548 | Y | N |  |  | 222 | 225
11TPIT0134 | Dye Mound Capacitor Bank | Install 25 MVAR at Dye Mound substation |  | Dye Mound |  | Completed |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 10026 | 2013-04-11 | 2013-04-11 | 138 | 0 | 0 | 0 | 0,25 | Montague |  | Tier 4 |  |  |  | 741 | Y | N |  |  | 1898 | 1854
11TPIT0167 | AEP_11TPIT0167_Lyssy update line | AEP_11TPIT0167_Lyssy update line | In Service | Kenedy Switching Station | Pleasanton | Planned | 497-0702 | AEP TCC |  | 3413 | 2013-04-30 | 2013-04-30 | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  | 8186, 8193, 8203 | Y | N |  |  | 3015 | 2842
12TPIT0022 | North McCamey Autotransformer Addition | Add two new 345-138 kV 800 MVA autotransformer at the North McCamey substation (76595). |  | North McCamey |  | Planned | 12TPIT0026 (STEC) 12TPIT0027 (STEC) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-07-01 | 2013-07-01 | 345 | 0 | 0 | 1600 |  | Upton |  | CREZ |  |  |  | 76000, 76998, 76999, 76032, 76595 | Y | N |  | CREZ Default project assigned to LCRA TSC | 2185 | 2113
12TPIT0026 | North McCamey (76000) to Odessa EHV (11028) | Construct a new double circuit capable 345 kV transmission line (approximately 50 miles) between the existing LCRA TSC North McCamey (McCamey A) and the existing Oncor Odessa EHV stations. The new transmission line will consist of 2x1590 ACSR Falcon condu | Project reassigned by PUCT to STEC from LCRA. | Odessa | North McCamey | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-12-31 | 2013-12-31 | 345 | 59.6 | 0 | 0 |  | Upton | Ector | CREZ |  |  |  | 11028, 76000 | Y | N |  | Cost estimates for this project include TPIT project # 12TPIT0027. Both projects will be filed in one PUCT Project # in 2011. | 981 | 980
12TPIT0027 | North McCamey (76000) to Bakersfield (76002) | Construct a new double circuit capable 345 kV transmission line (approximately 12 miles) between the LCRA TSC North McCamey (76000) and Bakersfield (76002) stations. The new transmission line will consist of 2x1590 ACSR Falcon conductor to provide a therm | Project reassigned by PUCT to STEC from LCRA. | Bakersfield | North McCamey | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-09-18 | 2013-09-18 | 345 | 15.9 | 0 | 0 |  | Upton | Pecos | CREZ |  |  |  | 76000, 76002 | Y | N |  | Cost estimates for this project have been included with TPIT project # 12TPIT0026. Both projects will be filed in one PUCT Project # in 2011. | 983 | 982
12TPIT0029 | Big Hill to Kendall 345kV | Construct a new double circuit 345kV transmisison line (approximately 137 miles) between Big Hill (76003) and Kendall (7046) substation. The new transmission line will be Cumberland conductor. |  | Big Hill | Kendall | Planned | 13TPIT0018 (STEC), 13TPIT0029 (AEP), 13TPIT0084 (AEP), 13TPIT0086 (AEP), 13TPIT0087 (AEP) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-09-01 | 2013-09-01 | 345 | 274 | 0 | 0 |  | Schleicher | Kendall | CREZ |  |  |  | 60616, 60618, 60619, 60621, 60708, 60709, 60710, 60711, 7046, 76003 | Y | N |  |  | 3031 | 2857
12TPIT0036a | Brown - Newton 345 kV line (SEE COMMENTS) | Convert existing line to double-circuit operation and increase rating to design level |  | Brown | Newton | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C048-E | 2013-10-01 | 2013-10-01 | 345 | 0 | 0 | 0 |  | Brown | Lampasas | CREZ Modified |  |  |  | 1444, 3422 | Y |  |  | Double-circuit line was placed in service in 12/2012 with circuits parallelled. The line will be converted to double-circuit operation. | 2830 | 2705
12TPIT0037a | Newton - Killeen Switch 345 kV line (SEE COMMENTS) | Convert existing line to double-circuit operating and increase rating to design level |  | Newton | Killeen Switch | Completed |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C049-E & C006B-E | 2013-12-15 | 2013-12-15 | 345 | 0 | 0 | 0 |  | Lampasas | Bell | CREZ |  |  |  |  | Y | Y |  | Double-circuit line was placed in service in 12/2012 with circuits parallelled. The line will be converted to double-circuit operation. | 3994 | 3749
12TPIT0048 | Hereford Collection Station | Construct the new 345 kV Hereford switching station.Initial build is 7 element folded breaker and one half bus arrangement | New |  |  | UnderConstruction | 13TPIT0042, 13TPIT0043 | SLU |  |  | 2013-07-20 | 2013-07-20 | 345 | 0 | 0 | 0 | -200,0 | Deaf Smith |  | CREZ |  |  |  | 79502 | Y | N |  |  | 1097 | 1096
12TPIT0049 | LS04 Silverton to Cottonwood | Construct a new 345kV double circuit line from Silverton switching station to WETT's Cottonwod switching station | New | Cottonwood | Silverton | UnderConstruction | 12TPIT0050 | SLU |  |  | 2013-03-15 | 2013-03-15 | 345 | 64.5 | 0 | 0 |  | Briscoe | Dickens | CREZ |  |  |  | 59904, 79503 | Y | N |  |  | 1098 | 1097
12TPIT0050 | Silverton Collection Station | Construct the new 345 kV Silverton switching station.Initial build is 14 element folded breaker and one half bus arrangement. | New |  |  | UnderConstruction | 12TPIT0049 | SLU |  |  | 2013-03-01 | 2013-03-01 | 345 | 0 | 0 | 0 | -150,50 | Briscoe |  | CREZ |  |  |  | 79503 | Y | N |  |  | 1876 | 1833
12TPIT0051 | LS01 Silverton to Nazareth | Construct a new 345kV single circuit line from Silverton switching station to Nazareth switching station. | New | Silverton | Nazareth | UnderConstruction | 12TPIT0053 | SLU |  |  | 2013-06-20 | 2013-06-20 | 345 | 46 | 0 | 0 |  | Briscoe | Castro | CREZ |  |  |  | 79501, 79503 | Y | N |  |  | 1100 | 1099
12TPIT0052 | LS02 Nazareth to Hereford | Construct a new 345kV single circuit line from Nazareth Switching to Hereford switching station | New | Nazareth | Hereford | UnderConstruction |  | SLU |  |  | 2013-07-20 | 2013-07-20 | 345 | 25.5 | 0 | 0 |  | Castro | Deaf Smith | CREZ |  |  |  | 79501, 79502 | Y | N |  |  | 1101 | 1100
12TPIT0053 | Nazareth Collection Station | Construct the new 345 kV Nazareth switching station.Initial build is 7 element ring bus arrangement. | New |  |  | UnderConstruction | 12TPIT0051 | SLU |  |  | 2013-06-20 | 2013-06-20 | 345 | 0 | 0 | 0 | -50,0 | Castro |  | CREZ |  |  |  | 79501 | Y | N |  |  | 1102 | 1101
12TPIT0056 | Grelton 345 kV Station and Grelton to Long Draw 345 kV line |  |  |  |  | Planned |  | WETT | Julius Horvath 512-436-9585 |  | 2013-09-30 | 2013-09-30 | 0 | 0 | 0 | 0 | [7 empty] | 59901, 59900 | Y |  |  |  | 3065 | 2891
12TPIT0057 | Grelton to Odessa 345 kV line |  |  |  |  | Planned |  | WETT | Julius Horvath 512-436-9585 |  | 2013-09-30 | 2013-09-30 | 0 | 0 | 0 | 0 | [7 empty] | 11028, 59901 | Y |  |  |  | 3066 | 2892
12TPIT0058 | Long Draw 345 kV Station and Long Draw to Scurry County Sout |  |  |  |  | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2013-09-30 | 2013-09-30 | 0 | 0 | 0 | 0 | [7 empty] | 59900, 11318 | Y |  |  |  | 3064 | 2890
12TPIT0059 | Sand Bluff 345 kV Station and Sand Bluff to Divide 345 kV l | Establish new 345 kV Sand Bluff station and construct a new single circuit, double circuit capable 345 kV transmission line between WETT's new Sand Bluff and LCRA TSC's Divide 345 kV stations. |  | Sand Bluff | Divide | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2013-11-15 | 2013-11-15 | 345 | 37 | 0 | 0 |  | Glasscock | Coke |  |  |  |  | 59902, 76090 | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases | 1114 | 1113
12TPIT0060 | Bearkat 345 kV Station and Bearkat to Sand Bluff 345 kV lin | Establish new 345 kV Bearkat station and construct a new single circuit, double circuit capable 345 kV transmission line between WETT's new Sand Bluff and new Bearkat 345 kV stations. |  | Bearkat | Sandbluff | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2013-11-15 | 2013-11-15 | 345 | 28.9 | 0 | 0 |  | Glasscock | Sterling |  |  |  |  | 59903, 59902 | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases | 1115 | 1114
12TPIT0061 | Sand Bluff to Long Draw 345 kV line | Construct a new single circuit, double circuit capable 345 kV transmission line between WETT's new Sand Bluff and new Long Draw 345 kV stations. |  | Sand Bluff | Long Draw | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2013-11-15 | 2013-11-15 | 345 | 77.4 | 0 | 0 |  | Glasscock | Borden |  |  |  |  | 59900, 59902 | Y | N |  | Projects are shown in the DSB 2013 and later (2014, 2015, etc) cases starting with the August 2009 TPIT and the 2010 SSWG DSB cases | 1116 | 1115
12TPIT0075 | Knob Creek 345 kV Switching Station Phase I | Construct 345 kV switching station |  | Knob Creek |  | Completed |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R749A-WAC | 2013-12-15 | 2013-12-15 | 345 | 0 | 0 | 0 |  | Bell |  | Tier 4 |  |  |  |  | Y | N |  |  | 3996 | 3751
12TPIT0097 | Cross substation | Construct new 138 kV load serving substation in San Miguel to Pearsall line. |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-03-01 | 2013-03-01 | 138 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5707, 5706, 5895 | Y | N |  |  | 1129 | 1126
12TPIT0098 | Bruni relay upgrade | Additional relays will be installed to allow the autotransformer to be normally closed. |  |  |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-11-08 | 2013-11-08 | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 5888, 5887 | Y | N |  |  | 2678 | 2562
12TPIT0099 | Knippa to Sabinal 69 kV line, transfer to new 138-69 double | Construct Uvalde to CPS Castroville 138 kV line with 2x795 ACSR utilizing open circuit for existing 69kV circuits in ROW | IN-SERVICE | Knippa | Sabinal | IN-SERVICE | 291 - 0046 | AEP TCC |  | 1521 | 2014-01-10 | 2014-01-10 | 69 | 0 | 8.5 | 0 |  | Uvalde | Medina |  |  |  |  | 8628, 8630 | Y | N |  |  | 206 | 209
12TPIT0100 | Uvalde to Knippa 69 kV line, tranfer to new 138-69 double ci | Construct Uvalde to CPS Castroville 138 kV line with 2x795 ACSR utilizing open circuit for existing 69kV circuits in ROW | IN-SERVICE | Uvalde | Knippa | IN-SERVICE | 291 - 0046 | AEP TCC |  | 1520 | 2014-01-10 | 2014-01-10 | 69 | 0 | 4.5 | 0 |  | Uvalde | Medina |  |  |  |  | 8231, 8628 | Y | N |  |  | 291 | 294
12TPIT0102 | AEP_12TPIT0102_Lone_tree_FosterTap | AEP_12TPIT0102_Lone_tree_FosterTap | In Service | Lone Tree |  | Under Construction | 555-0496 | AEP TCC |  | 2555 | 2013-04-30 | 2013-04-30 | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  | 8179, 8169, 8180, 88179 | Y |  |  |  | 3016 | 2843
12TPIT0126 | Pyote cap bank | Install 10 MVAR, 69kV cap bank at Pyote Substation |  | Pyote |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE03912 | 2013-03-01 | 2013-03-01 | 69 | 0 | 0 | 0 | 0,10 | Ward |  | Tier 4 |  |  |  | 38000 | Y | N |  |  | 2392 | 2316
12TPIT0128 | WA Parish - Sienna Ckt. 02 |  | IN-SERVICE | WA Parish | Sienna | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-05-30 | 2013-05-30 | 138 | 0 | 4.2 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44010, 44342, 44651 | Y | N |  |  | 2984 | 2811
12TPIT0132 | BARNES 138kV Substation | Construct service to new 138kV BARNES customer-owned substation. Loop through Ckt.88 SRB - ROHMAS | IN-SERVICE | BARNES | SR Bertron-ROHMAS | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-01-31 | 2013-01-31 | 138 | 0.1 | 0.4 | 0 |  | Harris |  | Tier 4 |  |  |  | 41355, 41350, 41405 | Y | N |  |  | 1595 | 1160
12TPIT0135 | Spring to Bridgeport Switch | Rebuild 30.3 miles of line with 959 ACSS |  | Spring | Bridgeport Switch | Completed |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 11008 | 2013-03-02 | 2013-03-02 | 138 | 0 | 33.3 | 0 |  | Cooke | Wise | Tier 4 |  |  |  | 587, 634, 684, 685, 686, 992 | Y | N |  |  | 2128 | 2056
12TPIT0137 | New Barksdale: Construct new 69 kV Substation including box | Add new 69 kV New Barksdale Substation for PEC distribution interconnection | IN-SERVICE | New Barksdale |  | IN-SERVICE | 4690671 | AEP TCC |  | 3343 | 2013-01-02 | 2013-01-02 | 69 | 0 | 0 | 0 |  | Edwards | Edwards | Tier 4 |  |  |  | 8365, 8238, 8633 | Y | N | 8365 |  | 934 | 933
12TPIT0142 | Choate to Fashing Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. | The Fashing to Coy City line section is now needed due to newest load forecast. Changes prior quarter comment. | Choate | Coy City | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-06-28 | 2013-06-28 | 69 | 0 | 30 | 0 |  | Atascosa | Karnes | Tier 2 | 2011-12-16 | 2012-04-25 |  | 5716, 5720, 5722, 5729 | Y | N |  |  | 1551 | 1536
12TPIT0142 | Choate to Fashing Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. | The Fashing to Coy City line section is now needed due to newest load forecast. Changes prior quarter comment. | Choate | Coy City | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-09-05 | 2013-09-05 | 69 | 0 | 30 | 0 |  | Atascosa | Karnes | Tier 2 | 2011-12-16 | 2012-04-25 |  | 5716, 5720, 5722, 5729 | Y | N |  |  | 1552 | 1536
12TPIT0149 | Cordele Capacitor | Add 19.2 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-04-01 | 2013-04-01 | 69 | 0 | 0 | 0 | 0,19.2 | Jackson |  |  | 2011-12-16 | 2012-04-25 |  | 5524 | Y | N |  |  | 705 | 704
12TPIT0153 | Cotulla Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-01-27 | 2013-01-27 | 69 | 0 | 0 | 0 | 0,9.6 | La Salle |  | Tier 4 |  |  |  | 5876 | Y | N |  |  | 2402 | 2325
12TPIT0157 | West Sinton Capacitor | Add 9.6 MVAR capacitor |  |  |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-06-14 | 2013-06-14 | 69 | 0 | 0 | 0 | 0,9.6 | San Patricio |  | Tier 4 |  |  |  | 5622 | Y | N |  |  | 2403 | 2326
12TPIT0158 | Permian Basin terminal equipment | Upgrade terminal equipment at Permian Basin in the Permian Basin - Wickett 69 kV line |  |  |  | Completed |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8052-WAC | 2013-05-15 | 2013-05-15 | 69 | 0 | 0 | 0 |  | Ward |  | Tier 4 |  |  |  | 1010, 1074 | Y | N |  |  | 2607 | 2502
12TPIT0160 | Clear Creek Substation terminal equipment | Upgrade terminal equipment at Clear Creek Substation in the Killeen Switch - Lampasas 138 kV line |  | Clear Creek |  | Planned |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R760A, B & C-WAC | 2013-10-15 | 2013-10-15 | 138 | 0 | 0 | 0 |  | Bell |  | Tier 4 |  |  |  | 3627, 3628, 3629 | Y | N |  |  | 3293 | 3124
12TPIT0172 | Western Dawson 138 kV POI/Patricia Sub | Tap the 138 kV Andrews-Lamesa Line where the line intersects FM 829. Build 7.5 miles of 138 kV transmission south to new Patricia Sub, which will be loaded approximately 5 MVA when energized. |  |  |  | UnderConstruction |  | GOLDENSPREAD | Chris Koenig ckoeng@gsec.coop 806-349-5201 |  | 2013-03-01 | 2013-03-01 | 138 | 7.5 | 0 | 0 |  | Dawson | Dawson | Tier 4 |  |  |  | 9418, 9419, 18880 | Y | N |  |  | 1952 | 1902
12TPIT0174 | Pointer, Build new three breaker ring bus | Construct new Pointer station along the Munday to Rule 69 kV line | In-Service | Pointer |  | Under Construction | 504 - 0715 | AEP TNC | Terry Weeks 918-599-2664 | 2496 | 2013-10-21 | 2013-10-21 | 69 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  | 6114, 60346, 764, 765, 6107, 6112, 6113, 6115, 6120 | Y | N |  |  | 1629 | 1592
12TPIT0183 | Gonzales: Add terminal position and rebuild 2.43 mile 69 kV | Interconnect Acacia Solar Farm into the Gonzales 69 kV station, rebuild 69 kV line with 477 ACSR | In Service | Gonzales |  | In Service | 513 - 0710 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2568 | 2013-05-31 | 2013-05-31 | 69 | 0 | 2.2 | 0 |  | Presidio | Presidio | Tier 4 |  |  |  | 60339, 6675 | Y | N |  |  | 2745 | 2627
12TPIT0188 | AEP_12TPIT0188_update Mayo | AEP_12TPIT0188_update Mayo | In Service | Gila | Whitepoint | Under Construction | 562-0730 | AEP TCC |  | 3440 | 2013-04-30 | 2013-04-30 | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 80258 | Y | N |  |  | 3017 | 2844
12TPIT0202 | West Substation upgrade | Upgrade the 138 kV portion of the West substation to 3000 Amp. |  | West |  | Completed |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE03612 | 2013-01-23 | 2013-01-23 | 138 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  | 37050, 37060, 37080 | Y | N |  |  | 2085 | 2021
12TPIT0217 | Moss - Holt Switch 138 kV line | Increase line rating by raising operating temperature of conductor | Construction taking longer than projected | Moss | Holt Switch | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 |  | 2013-06-15 | 2013-06-15 | 138 | 0 | 0 | 0 |  | Ector | Ector | Tier 4 |  |  |  |  | Y | N |  |  | 3232 | 3063
13TPIT0011 | Palo Alto - New 138kV Substation | Loop new 138kV substation into the existing 138kV Leon Creek to Chavaneaux line |  | Palo Alto | Leon Creek-Chavaneaus | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0527 | 2014-01-31 | 2014-01-31 | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 | 2011-02-08 | 2011-09-22 |  | 5330, 5085, 5260 | Y | N |  | There are no transformers associated with this project | 953 | 952
13TPIT0012 | Zorn Autotransformer Addition | Add a new 345-138 kV 478 MVA autotransformer at the Zorn substation (7042). |  | Big Hill |  | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-06-01 | 2013-06-01 | 345 | 0 | 0 | 478 |  | Guadalupe |  | Tier 3 | 2008-01-30 | 2008-06-10 |  | 77180, 7042, 7180 | Y | N |  |  | 990 | 989
13TPIT0015 | Wellborn Switching Sub | Install (3) Breaker ring to include (2) 138 lines and (1) 138-69 auto transformer relocated from Greens Prairie |  | Wellborn | Wellborn | planned | 10TPIT0049 | BRYN | James Tanneberger 9798215763 |  | 2013-09-01 | 2013-09-01 | 138 | 0 | 0 | 20 |  | Brazos |  | Tier 4 |  |  |  | 32895, 32898, 32885, 32889, 32878 | Y | N |  |  | 1371 | 1366
13TPIT0016 | Greens Prairie to Wellborn Transmission | ReBuild-Reconductor (3.75) miles of 69kV line converting to 138 kV to serve Wellborn |  | Greens Prairie | Wellborn | planned |  | BRYN | James Tanneberger 9798215763 |  | 2013-09-01 | 2013-09-01 | 138 | 0 | 3.82 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32885, 32878, 32895 | Y | N |  |  | 1832 | 1789
13TPIT0017 | Greens Prairie Substation | Install (1) Breaker in existing ring bus for a 138 line from Wellborn/Millican Substation(s) |  | Greens Prairie | Greens Prairie |  |  | BRYN | James Tanneberger 9798215763 |  | 2013-09-01 | 2013-09-01 | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 3304 | 3135
13TPIT0018 | McCamey C to McCamey D (Bakersfield to Big Hill) | Construct new 113 miles 1590 ACSR 345 kV line from Bakersfiled to Big Hill (McCamey C to McCamey D). |  | Bakersfield | Big Hill | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-09-18 | 2013-09-18 | 345 | 111.4 | 0 | 0 |  | Pecos | Schleicher | CREZ |  |  |  | 76002, 76003 | Y | N |  |  | 1226 | 1223
13TPIT0019 | Riley to Edith Clarke double circuit 345 kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis | Schedule Update | Riley | Edith Clarke | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2381 | 2013-07-31 | 2013-07-31 | 345 | 86.6 | 0 | 0 |  | Wilbarger | Cottle | CREZ |  |  |  | 60500, 6101 | Y | N |  |  | 1637 | 1600
13TPIT0020 | Tesla to Edith Clarke double circuit 345 kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis | Schedule Update | Tesla | Edith Clarke | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2382 | 2013-07-31 | 2013-07-31 | 345 | 110.4 | 0 | 0 |  | Cottle | Cottle | CREZ |  |  |  | 60500, 60501 | Y | N |  |  | 1638 | 1601
13TPIT0021 | Edith Clarke to Cottonwood double circuit 345 kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis | In-Service | Edith Clarke | Cottonwood | Under Construction | 478 - 0680 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2383 | 2013-11-11 | 2013-11-11 | 345 | 178 | 0 | 0 |  | Dickens | Cottle | CREZ |  |  |  | 59904, 60500 | Y | N |  |  | 1639 | 1602
13TPIT0022 | Tesla to Riley double circuit 345 kV line | [6 empty] | ETT | Glen Reed gareed@aep.com 918-599-2664 |  | 2013-08-31 | 2013-08-31 | 0 | 0 | 0 | 0 |  |  |  | CREZ |  |  |  | 60501, 6101 | Y |  |  |  | 3559 | 3364
13TPIT0023 | Edith Clarke 345 kV station |  |  | Edith Clarke |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2389 | 2013-07-31 | 2013-07-31 | 345 | 0 | 0 | 0 |  | Cottle |  | CREZ |  |  |  | 60500 | Y | N |  |  | 3392 | 3219
13TPIT0024 | Edith Clarke, add two 130.9 MVar capacitors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Edith Clarke |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2389 | 2013-07-31 | 2013-07-31 | 345 | 0 | 0 | 0 | 0,261.8 | Cottle |  | CREZ |  |  |  | 60500 | Y | N |  |  | 3393 | 3220
13TPIT0025 | Edith Clarke, add four 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | Schedule Update | Edith Clarke |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2390 | 2013-07-31 | 2013-07-31 | 345 | 0 | 0 | 0 | -200,0 | Cottle |  | CREZ |  |  |  | 60500 | Y | N |  |  | 1076 | 1075
13TPIT0026 | Tesla 345 kV station | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis **Complete but Not in Service** |  | Tesla |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2393 | 2013-07-31 | 2013-07-31 | 345 | 0 | 0 | 0 |  | Cottle |  | CREZ |  |  |  | 60501 | Y | N |  |  | 3395 | 3222
13TPIT0027 | Tesla, add two 130.9 MVar capacitors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Tesla |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2394 | 2013-07-31 | 2013-07-31 | 345 | 0 | 0 | 0 | 0,261.8 | Cottle |  | CREZ |  |  |  | 60501 | Y | N |  |  | 3396 | 3223
13TPIT0028 | Tesla, add four 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis **Complete but Not in Service** | Schedule Update | Tesla |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2395 | 2013-06-30 | 2013-06-30 | 345 | 0 | 0 | 0 | -200,0 | Cottle |  | CREZ |  |  |  | 60501 | Y | N |  |  | 1077 | 1076
13TPIT0029 | Big Hill to Kendall Series Compensation (Edison) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In-Service | Edison |  | Under Construction | 478 - 0680 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2398 | 2013-10-11 | 2013-10-11 | 345 | 0 | 0 | 0 | 0,933 | Schleicher | Kendall | CREZ |  |  |  | 60616, 60618, 60619, 60621 | Y | N |  |  | 1078 | 1077
13TPIT0030 | Clear Crossing to Dermott double circuit 345 kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis | In-Service | Clear Crossing | Dermott | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2391 | 2013-10-24 | 2013-10-24 | 345 | 180.6 | 0 | 0 |  | Scurry | Haskell | CREZ |  |  |  | 11305, 60515, 60704, 60705, 60706, 60707 | Y | N |  |  | 1640 | 1603
13TPIT0031 | Dermott to Clear Crossing Series Compensation (Kirchhoff) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In-Service | Kirchhoff |  | Under Construction | 478 - 0680 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2392 | 2013-11-05 | 2013-11-05 | 345 | 0 | 0 | 0 | 0,737 | Scurry | Haskell | CREZ |  |  |  | 60704, 60706, 60705, 60707 | Y | N |  |  | 1476 | 1475
13TPIT0032 | Edith Clarke to Clear Crossing double circuit 345 kV line | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis | In-Service | Edith Clarke | Clear Crossing | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2385 | 2013-10-22 | 2013-10-22 | 345 | 158.4 | 0 | 0 |  | Cottle | Shackelford | CREZ |  |  |  | 6037, 60500, 60515, 60700, 60701, 60702, 60703, 6117, 6169, 6050, 6161, 6228 | Y | N |  |  | 2828 | 2703
13TPIT0033 | Clear Crossing to West Shackelford double circuit 345 kV lin | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis | In-Service | Clear Crossing | West Shackleford | Under Construction | 478 - 0680 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2386 | 2013-11-21 | 2013-11-21 | 345 | 67.6 | 0 | 0 |  | Cottle | Shackelford | CREZ |  |  |  | 60515, 68000 | Y | N |  |  | 1641 | 1604
13TPIT0034 | Edith Clarke to West Shackelford Series Compensation (Gauss) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In-Service | Gauss |  | Under Construction | 478 - 0680 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2388 | 2013-11-06 | 2013-11-06 | 345 | 0 | 0 | 0 | 0,737 | Cottle | Cottle | CREZ |  |  |  | 60700, 60702, 60701, 60703 | Y | N |  |  | 1083 | 1082
13TPIT0035 | Willow Creek - Clear Crossing - Dermott Switch (Central B) 3 | Construct double-circuit 345 kV line |  | Willow Creek | Dermott Switch | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C054-E | 2013-12-15 | 2013-12-15 | 345 | 220 | 0 | 0 |  | Wise | Haskell | CREZ |  |  |  | 1421, 60515 | Y | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2765 | 2641
13TPIT0036 | Krum West - Riley (Oklaunion) 345 kV line (Oncor Electric De | Construct double-circuit 345 kV line |  | Krum West Switch | Riley | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C050-E | 2013-06-15 | 2013-06-15 | 345 | 326.2 | 0 | 0 |  | Denton | Wilbarger | CREZ |  |  |  | 1730, 6101 | Y | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2764 | 2640
13TPIT0037 | Krum West Switch | Construct 345 kV switching station |  | Krum West Switch |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C017-E | 2013-06-15 | 2013-06-15 | 345 | 0 | 0 | 0 |  | Denton |  | CREZ |  |  |  |  | Y | Y |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 3345 | 3174
13TPIT0038 | Hicks Switch | Construct 345 kV switching station |  |  |  | Under Construction |  | ONCOR | Michael Juricek Michael.Juricek@oncor.com 214.743.6671 | C030-E | 2013-06-01 | 2013-06-01 | 345 | 0 | 0 | 0 |  | Tarrant |  | CREZ |  |  |  | 2081, 1436, 1845, 1855, 1859 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2691 | 2575
13TPIT0039 | Willow Creek - Hicks Switch 345 kV line | Construct double-circuit 345 kV line |  | Hicks Switch | Willow Creek | Under Construction |  | ONCOR | Michael Juricek Michael.Juricek@oncor.com 214.743.6671 | C061-E | 2013-06-01 | 2013-06-01 | 345 | 80.4 | 0 | 0 |  | Tarrant | Wise | CREZ |  |  |  | 1421, 2081 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2780 | 2656
13TPIT0040 | Willow Creek Switch circuit breakers | Install 345 kV circuit breakers. |  | Willow Creek Switch |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C012B-E | 2013-06-15 | 2013-06-15 | 345 | 0 | 0 | 0 |  | Wise |  | CREZ |  |  |  |  | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 3349 | 3178
13TPIT0041 | Anna Switch circuit breakers | Install 345 kV circuit breakers |  | Anna Switch |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C015-E | 2013-12-15 | 2013-12-15 | 345 | 0 | 0 | 0 |  | Collin |  | CREZ |  |  |  |  | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 3351 | 3180
13TPIT0042 | LS03 White Deer to Hereford | Construct a new 345kV single circuit line from White Deer switching station to Hereford switching station | New | White Deer | Hereford | UnderConstruction | 12TPIT0048, 13TPIT0043 | SLU |  |  | 2013-08-30 | 2013-08-30 | 345 | 91.2 | 0 | 0 |  | Carson | Deaf Smith | CREZ |  |  |  | 79500, 79502 | Y | N |  |  | 1103 | 1102
13TPIT0043 | White Deer Collection Station | Construct the new 345 kV White Deer switching station.Initial build is 10 element folded breaker and one half bus arrangement. | New |  |  | UnderConstruction | 12TPIT0048, 13TPIT0042 | SLU |  |  | 2013-08-30 | 2013-08-30 | 345 | 0 | 0 | 0 | -100,0 | Carson |  | CREZ |  |  |  | 79500 | Y | N |  |  | 1104 | 1103
13TPIT0046 | Flatonia-Yoakum Gartner Road | Upgrade and convert the 27.7 mile Flatonia (7248)-Moulton (7236)-Henkhaus (7237)-Shiner (7238)-Yoakum Gartner Road (7242) 2-0 ACSR 69 kV transmission line to 795 ACSR 138 kV. |  | Flatonia | Yoakum Gartner Road | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-05-31 | 2013-05-31 | 138 | 0 | 27.7 | 0 |  | Fayette | Dewitt | Tier 3 |  | 2009-03-01 |  | 7236, 7238, 7241, 7237, 7242, 7247, 7248, 7588 | Y | N |  |  | 992 | 991
13TPIT0048 | Scurry County (Central A) - West Shackelford (Central C) | CREZ Assigned Project to build West Shackelford (Central C) substation in Shackelford county and double ckt 345 kV lines from Scurry County sub (Oncor Central A facility) to West Shackelford substation utilizing 2-1590 ACSS-TW "Falcon" conductor; Approxi |  | Scurry County South | West Shackelford | UnderConstruction |  | LST |  |  | 2013-03-01 | 2013-03-01 | 345 | 206.2 | 0 | 0 | -200,0 | Scurry | Shackelford | CREZ |  |  |  | 68000, 68005, 68006, 11318 | Y | N |  |  | 2258 | 2185
13TPIT0049 | West Shackelford (Central C) - Sam Switch/Navarro | CREZ Assigned Project to build double ckt 345 kV lines from S West Shackelford -Romney-Kopperl-Sam Switch and Shackelford -Romney-Kopperl-Navarro transmission lines utilizing 2-1590 ACSS-TW "Falcon" conductor; Approximate route distance is 190 miles betw |  | West Shackelford | Circuit 1 - Sam Switch Circuit 2 - Navarro | UnderConstruction |  | LST |  |  | 2013-03-01 | 2013-03-01 | 345 | 414.1 | 0 | 0 | -200,0 | Shackelford | Hill - Navarro | CREZ |  |  |  | 68010, 68020, 68030, 68040, 68050, 68060, 68070, 68080, 68090, 1906, 1907, 2428, 2435, 3380, 3405, 3409, 13405, 46020, 68005, 68006, 68091 | Y | N | Revised as of 12/1/2012 - LST successfully cut-in and energized Navarro and Sam Switch and Navarro switchyards (only) on existing Oncor lines according to the following schedule: ¿ Navarro (first set of lines) - October 1 - | Project scope also include two series capacitor bank stations (Kopperl, Romney) equally spaced between West Shackelford and Sam Switch consisting of two series capacitor banks rated at 683 MVAR and 817 MVAR, with associated switches and line terminals an | 2260 | 2186
13TPIT0050 | LS05 Silverton to White Deer | Construct a new 345kV double circuit line from Silverton switching station to White Deer switching station | New | Silverton | White Deer | UnderConstruction |  | SLU |  |  | 2013-12-01 | 2013-12-01 | 345 | 68.2 | 0 | 0 |  | Briscoe | Carson | CREZ |  |  |  | 79500, 79503 | Y | N |  |  | 1105 | 1104
13TPIT0051 | Gray to Tesla, build double circuit 345 kV line | Build new Gray Substation (Panhandle B-B) including 150 to 200 MVAR of reactive compensation and 345 kV double circuit line from Gray to Tesla | The transmission line is still scheduled to be completed March, 2013 but CTT expects the in-service date will be dependent on the in-service date of downstream facilities. | Gray | Tesla | Planned |  | CTT | Tim Cook tcook@lspower.com 636-534-3310 |  | 2013-07-31 | 2013-07-31 | 345 | 218 | 0 | 0 |  | Gray | Childress | CREZ |  |  |  | 60501, 79000 | Y | Y |  |  | 1091 | 1090
13TPIT0052 | Gray Substation (Panhandle B-B), build new collector substat | Build new Gray Substation (Panhandle B-B) including 150 to 200 MVAR of reactive compensation and 345 kV double circuit line from Gray to Tesla | The Gray Substation is still scheduled to be completed March, 2013 but CTT expects the in-service date will be dependent on the in-service date of downstream facilities. | - | - | Planned |  | CTT | Tim Cook tcook@lspower.com 636-534-3310 |  | 2013-07-31 | 2013-07-31 | 345 | 0 | 0 | 0 |  | Gray | - | CREZ |  |  |  | 79000 | Y | N |  |  | 1875 | 1832
13TPIT0053 | Gray Substation (Panhandle B-B), build 150 to 200 MVAR of Re | Build new Gray Substation (Panhandle B-B) including 150 to 200 MVAR of reactive compensation and 345 kV double circuit line from Gray to Tesla | The installation of the reactors are still scheduled to be completed March, 2013 but CTT expects the in-service date will be dependent on the in-service date of downstream facilities. | - | - | Planned |  | CTT | Tim Cook tcook@lspower.com 636-534-3310 |  | 2013-07-31 | 2013-07-31 | 345 | 0 | 0 | 0 | -200,0 | Gray | - | CREZ |  |  |  | 79000 | Y | N |  |  | 1093 | 1092
13TPIT0054 | Gray to Alibates, build double circuit 345 kV line | Build 345 kV double circuit line from Gray to Alibates | Updated station names. | Gray | Alibates | Planned |  | CTT | Tim Cook tcook@lspower.com 636-534-3310 |  | 2013-08-30 | 2013-08-30 | 345 | 83 | 0 | 0 |  | Gray | Carson | CREZ |  |  |  | 79000, 79500 | Y | N |  |  | 1094 | 1093
13TPIT0055 | Tule Canyon to Tesla, build double circuit 345 kV line | Build 345 kV double circuit line from Tule Canyon to Tesla | Updated station names. | Tule Canyon | Tesla | Planned |  | CTT | Tim Cook tcook@lspower.com 636-534-3310 |  | 2013-09-18 | 2013-09-18 | 345 | 172 | 0 | 0 |  | Briscoe | Childress | CREZ |  |  |  | 60501, 79001, 79003, 79002, 79004, 79503 | Y | Y |  |  | 1095 | 1094
13TPIT0056 | Tule Canyon to Tesla |  |  |  |  | Under Construction |  | CTT | Tim Cook 636-534-3250 |  | 2013-09-18 | 2013-09-18 | 0 | 0 | 0 | 0 |  |  |  | CREZ |  |  |  | 79001, 79002, 79003, 79004 | Y |  |  | CREZ | 3411 | 3237
13TPIT0069 | Panther Springs - New 138kV Substation | Loop new 138kV substation into existing 138kV Hill Country to Stonegate circuit #1 line |  | Panther Springs | Hill Country-Stonegate | Planned | T-0172 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0616 | 2013-06-01 | 2013-06-01 | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5331, 5210, 5415 | Y | N |  | There are no transformers associated with this project | 954 | 953
13TPIT0072 | Scurry County South Switch (Central A) | Install shunt capacitor |  | Scurry County South |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | RC0088-E | 2013-12-15 | 2013-12-15 | 345 | 0 | 0 | 0 | 0,160 | Scurry |  | CREZ |  |  |  | 11318 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2814 | 2690
13TPIT0073 | Killeen Switch | Install shunt capacitors |  | Killeen |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | RC0089-E | 2013-12-15 | 2013-12-15 | 345 | 0 | 0 | 0 | 0,160 | Bell |  | CREZ |  |  |  | 3422 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 597 | 597
13TPIT0074 | Willow Creek Switch | Install shunt reactors. |  | Willow Creek Switch |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C054B-E | 2013-06-15 | 2013-06-15 | 345 | 0 | 0 | 0 | -100,0 | Wise |  | CREZ |  |  |  | 1421 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 1937 | 1888
13TPIT0075 | Graham Switching Station | Install shunt reactor |  | Graham Switching Station |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | RC083-E | 2013-12-15 | 2013-12-15 | 345 | 0 | 0 | 0 | -200,0 | Young |  | CREZ |  |  |  | 1430 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2693 | 2577
13TPIT0076 | Parker Switching Station | Install a dynamic reactive device |  | Parker |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | RC087-E | 2013-12-01 | 2013-12-01 | 0 | 0 | 0 | 0 | -265,300 | Parker | Parker | CREZ |  |  |  | 1436 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 3602 | 2579
13TPIT0077 | Kendall to Miller Creek to Paleface | Upgrade existing Kendall (7150) to Miller Creek (7479)line to 1433 ACSS-TW (Merrimack) and Miller Creek (7479) Creek to Paleface (7476) line to 795 ACSR (Drake). |  | Kendall | Paleface | Planned | 13TPIT0210 (PEC) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-05-01 | 2013-05-01 | 138 | 0 | 56.88 | 0 |  | Kendall | Burnet | CREZ |  |  |  | 7147, 7148, 7476, 7478, 7150, 7479 | Y | N |  |  | 1529 | 1521
13TPIT0077 | Kendall to Miller Creek to Paleface | Upgrade existing Kendall (7150) to Miller Creek (7479)line to 1433 ACSS-TW (Merrimack) and Miller Creek (7479) Creek to Paleface (7476) line to 795 ACSR (Drake). |  | Kendall | Paleface | Planned | 13TPIT0210 (PEC) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-05-02 | 2013-05-02 | 138 | 0 | 56.88 | 0 |  | Kendall | Burnet | CREZ |  |  |  | 7147, 7148, 7476, 7478, 7150, 7479 | Y | N |  |  | 1530 | 1521
13TPIT0081 | Brown Switch capacitors | Install shunt capacitors | Brown | Brown |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | RC082-E | 2013-12-15 | 2013-12-15 | 345 | 0 | 0 | 0 | 0,240 | Brown |  | CREZ |  |  |  | 1444 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. The estimated cost is included in the estimated cost of Brown Switch (12TPIT0045). | 3238 | 3069
13TPIT0082 | Brown Switch dynamic reactive device | Install two dynamic reactive devices |  |  |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | RC086-E | 2013-12-01 | 2013-12-01 | 345 | 0 | 0 | 0 | -530,600 | Brown | Brown | CREZ |  |  |  | 1444, 11444, 11445 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. The estimated cost is included in the estimated cost of Brown Switch (12TPIT0045). | 3603 | 2694
13TPIT0083 | Snook Substation | Install (3) Breaker ring to include (2) 138 lines and (1) 138-69 auto transformer relocated from Thompson Creek. |  | Snook Substation | Snook Substation | planned |  | BRYN | James Tanneberger 9798215763 |  | 2013-09-01 | 2013-09-01 | 138 | 0 | 0 | 0 |  | Burleson |  | Tier 4 |  |  |  | 32864, 32865, 32857 | Y | N |  |  | 1831 | 1788
13TPIT0084 | Big Hill to Kendall Series Compensation (Orsted) | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In-Service | Orsted |  | Under Construction | 478 - 0680 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2485 | 2013-10-12 | 2013-10-12 | 345 | 0 | 0 | 0 | 0,933 | Kendall |  | CREZ |  |  |  | 60708, 60709, 60710, 60711 | Y | N |  |  | 1084 | 1083
13TPIT0085 | Clear Crossing 345 kV station | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In-Service | Clear Crossing |  | Under Construction | 478 - 0680 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2486 | 2013-10-15 | 2013-10-15 | 345 | 0 | 0 | 0 |  | Haskell |  | CREZ |  |  |  | 60515 | Y | N |  |  | 3962 | 3718
13TPIT0085 | Clear Crossing 345 kV station | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Clear Crossing |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2486 | 2013-10-31 | 2013-10-31 | 345 | 0 | 0 | 0 |  | Haskell |  | CREZ |  |  |  | 60515 | Y | N |  |  | 3398 | 3225
13TPIT0086 | Edison, add two 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In-Service | Edison |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2487 | 2013-10-15 | 2013-10-15 | 345 | 0 | 0 | 0 | -100,0 | Kendall |  | CREZ |  |  |  | 60616, 60618, 60619, 60621 | Y | N |  |  | 1085 | 1084
13TPIT0087 | Orsted, add two 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In-Service | Orsted |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2488 | 2013-10-15 | 2013-10-15 | 345 | 0 | 0 | 0 | -100,0 | Kendall |  | CREZ |  |  |  | 60708, 60709, 60710, 60711 | Y | N |  |  | 1086 | 1085
13TPIT0088 | Clear Crossing, add six 50 MVar reactors | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Clear Crossing |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2489 | 2013-10-15 | 2013-10-15 | 345 | 0 | 0 | 0 | -300,0 | Haskell |  | CREZ |  |  |  | 60515 | Y | N |  |  | 1087 | 1086
13TPIT0089 | Tesla, add dynamic reactive compensation | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study | In-Service | Tesla |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2491 | 2013-10-02 | 2013-10-02 | 345 | 0 | 0 | 0 | -100,300 | Cottle |  | CREZ |  |  |  | 60501, 60502, 60503 | Y | N |  |  | 1088 | 1087
13TPIT0090 | Hamilton Road, add dynamic reactive compensation | PUCT mandated facility additions and upgrades identified from ERCOT's scenario 2 analysis, as modified by ERCOT through the reactive study |  | Hamilton Road |  | Under Construction | 478 - 0680 | ETT | Glen Reed 918-599-2664 | 2492 | 2013-07-26 | 2013-07-26 | 345 | 0 | 0 | 0 | -50,200 | Val Verde |  | CREZ Modified |  |  |  | 8255, 80479, 80480 | Y | N |  |  | 1089 | 1088
13TPIT0091 | Big Hill Reactive Devices | Install two each 50 MVAR Reactor Banks and two each 72 MVAR Capacitor Banks at the Big Hill station (76003). |  | Big Hill |  | Planned | 13TPIT0029 (AEP) 13TPIT0084 (AEP) 13TPIT0086 (AEP) 13TPIT0087 (AEP) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-05-01 | 2013-05-01 | 345 | 0 | 0 | 0 | -100,144 | Schleicher |  | CREZ |  |  |  | 76003 | Y | N |  | Cost is included in the 12TPIT0028 project | 2467 | 2378
13TPIT0092 | Killeen Switch - Killeen Elms Road - Harker Heights 138 kV l | Upgrade existing 138 kV line |  | Killeen Switch | Harker Heights | UnderConstruction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R777-WAC | 2013-06-14 | 2013-06-14 | 138 | 0 | 14.8 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3616, 3619, 3618, 13426, 13427 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2453 | 2364
13TPIT0093 | Willow Valley Switch | Install 345/138 kV autotransformer | Delay in completion of Faraday Switching Station | Willow Valley |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8029-WAC | 2013-08-15 | 2013-08-15 | 345 | 0 | 0 | 600 |  | Borden |  | Tier 2 | 2011-03-15 | 2011-04-15 |  |  | Y | N |  | Willow Valley Switching Station 345/138 kV autotransformer installation completed in June 2013. | 3381 | 3208
13TPIT0095 | Krum West Switch capacitors | Install shunt capacitors |  | Krum West Switch |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C085-E | 2013-12-01 | 2013-12-01 | 345 | 0 | 0 | 0 | 0,80 | Denton |  | CREZ |  |  |  | 1730 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 1936 | 1887
13TPIT0096 | Krum West Switch reactors | Install shunt reactors |  | Krum West Switch |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C085R-E | 2013-06-01 | 2013-06-01 | 345 | 0 | 0 | 0 | -100,0 | Denton |  | CREZ |  |  |  | 988, 1429, 1730, 33646 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 1935 | 1886
13TPIT0098 | Faraday Switch | Establish new 345 kV Faraday station in WETT's Long Draw-S. Scurry 345 kV line. |  |  |  | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2013-09-30 | 2013-09-30 | 345 | 0 | 0 | 0 |  | Borden |  |  | 2011-03-18 | 2011-04-18 |  | 59905, 11318, 59900 | Y | N |  | Project is shown in the DSB 2013 and later (2014, 2015, etc) cases | 1146 | 1143
13TPIT0099 | League City-Magnolia rebuild | Rebuild League City to Magnolia 138 kV transmission line with 795 ACSS conductor. |  | League City | Magnolia | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07513 | 2013-06-01 | 2013-06-01 | 138 | 0 | 3.62 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 38920, 38950 | Y | N |  |  | 1198 | 1195
13TPIT0100 | Westminster Substation and transmission line | Build Westminster 138 kV Substation and transmission line tap from Oncor's Anna Switch - Van Alstyne 138 kV line. |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07612 | 2013-05-31 | 2013-05-31 | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 37270, 12704 | Y | N |  |  | 2053 | 2002
13TPIT0100 | Westminster Substation and transmission line | Build Westminster 138 kV Substation and transmission line tap from Oncor's Anna Switch - Van Alstyne 138 kV line. |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07612 | 2013-05-31 | 2013-05-31 | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 37270, 12704 | Y | N |  |  | 2054 | 2002
13TPIT0102 | Greens Bayou Autotransformer Upgrade | Replace existing 400MVA Greens Bayou autotransformer A2 with 800MVA autotransformer. |  | Greens Bayou |  | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-05-29 | 2013-05-29 | 345 | 0 | 0 | 400 |  | Harris |  | Tier 4 |  |  |  | 40700, 40716, 49019 | Y | N |  |  | 1486 | 1485
13TPIT0103 | Obrien Autotransformer Upgrade | Replace existing 400MVA Obrien autotransformer A3 with 800MVA autotransformer. | IN-SERVICE | Obrien |  | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-05-29 | 2013-05-29 | 345 | 0 | 0 | 400 |  | Fort Bend |  | Tier 4 |  |  |  | 44500, 44510, 49063 | Y | N |  |  | 1485 | 1484
13TPIT0105 | Silver City to Calvert Switch | Install additional poles and modify existing structures to raise normal operating temperature to 100° C |  | Silver City | Calvert Switch | planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 11051 | 2013-09-02 | 2013-09-02 | 69 | 0 | 7.95 | 0 |  | Milam | Milam | Tier 4 |  |  |  | 65, 73 | Y | N |  |  | 1185 | 1182
13TPIT0109 | Ajo to Rio Hondo: Reconductor 345kV Line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo | In-Service | Ajo | Rio Hondo | Under Construction | 071 - 0281 | AEP TCC | Michael Glueck 918-599-2664 | 3182 | 2013-11-07 | 2013-11-07 | 345 | 0 | 66.795 | 0 |  | Kenedy | Cameron | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8902, 80076 | Y | N |  |  | 1421 | 1420
13TPIT0111 | WA Parish Split Bus | Split WA Parish 345kV Bus 44000 |  |  |  | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-05-31 | 2013-05-31 | 345 | 0 | 0 | 0 |  | Fort Bend |  | Tier 2 | 2011-02-08 | 2011-09-22 |  | 44005, 44000, 44200, 44650, 47000, 47300, 110018 | Y | N |  |  | 1599 | 1451
13TPIT0115 | Barnhart SWTEC: Add 3.6 Mvar capacitor bank | Add 3.6 Mvar capacitor bank at Barnhart SWTEC and add 10 MVA DRCS with 7.2 Mvar capacitor bank at Yucca | In Service | Barnhart |  | In Service | 558 - 0721 | AEP TNC |  | 2560 | 2013-05-31 | 2013-05-31 | 69 | 0 | 0 | 0 | 0,3.6 | Irion |  | Tier 4 |  |  |  | 6530 | Y | N |  |  | 1399 | 1398
13TPIT0116 | North Brady: Add two 7.2 Mvar capacitor banks | Add two 7.2 Mvar capacitor banks at North Brady and add 7.2 Mvar capacitor bank at Katemcy | In-Service | North Brady |  | Planned | 559 - 0722 | AEP TNC | Eric Scott 918-599-2664 | 2561 | 2013-12-03 | 2013-12-03 | 69 | 0 | 0 | 0 | 0,14.4 | McCulloch |  | Tier 4 |  |  |  | 6006 | Y | N |  |  | 1400 | 1399
13TPIT0117 | AEP_13TPIT0117_Sunniland update | AEP_13TPIT0117_Sunniland update | In Service | Sunniland |  | Under Construction | 556-0716 | AEP TCC |  | 3431 | 2013-03-29 | 2013-03-29 | 69 | 0 | 0 | 0 |  | Live Oak |  | Tier 4 |  |  |  | 8400, 8406, 8600 | Y | N |  |  | 3090 | 2915
13TPIT0117 | Sunniland 69 kV substation: STEC Interconnect | Sunniland 69 kV STEC Interconnection: Construct 69 kV Substation Including Motor Operated Switches with Interconnection on Pleasanton - Three Rivers 69kV line. | Changed inservice date and reformated project number to match other numbers | Sunniland |  | UnderConstruction | 556 - 0716 | AEP TCC |  | 3431 | 2013-03-31 | 2013-03-31 | 69 | 0 | 0 | 0 |  | Live Oak |  | Tier 4 |  |  |  | 8400, 8406, 8600 | Y | N |  |  | 2518 | 2413
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-01-22 | 2013-01-22 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2663 | 2557
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-01-02 | 2013-01-02 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2664 | 2557
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-01-31 | 2013-01-31 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2665 | 2557
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-03-15 | 2013-03-15 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2666 | 2557
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-05-17 | 2013-05-17 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2667 | 2557
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-06-14 | 2013-06-14 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2668 | 2557
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-08-30 | 2013-08-30 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2669 | 2557
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-10-25 | 2013-10-25 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2670 | 2557
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-10-25 | 2013-10-25 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2671 | 2557
13TPIT0119a | Vanderbilt to Ricebird 138 kV circuit | Rebuild single circuit 4/0 ACSR 69 kV to double circuit 138 kV capable structures. Initially operate with one 69 kV circuit. |  | Vanderbilt | Ricebird | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-11-22 | 2013-11-22 | 138 | 52 | 0 | 0 |  | Jackson | Wharton | Tier 2 | 2011-10-07 | 2012-01-26 |  | 5516, 5518, 5522, 5524, 5525, 5528, 5530, 5535, 5532, 5538, 5582 | Y | N |  | Project costs include 13TPIT0119b | 2672 | 2557
13TPIT0120 | Ricebird Station and autotransformer. | Construct 69 kV Ricebird station, install 150 MVA autotransformer, tie into El Campo to Round Mott Switch 69 kV line and connect 69 kV line from Nada at Ricebird. |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-03-16 | 2013-03-16 | 69 | 0 | 0 | 150 |  | Wharton |  | Tier 3 | 2011-10-14 | 2011-11-09 |  | 5535, 5530, 5538, 78104 | Y | N |  | Coordinated project with LCRA | 1562 | 1543
13TPIT0122 | Choate Station and Autotransformer | Build new Choate substation where Pawnee to Four Corners 138 kV and Kenedy to Charco 69 kV lines cross and add a 150 MVA 139-69 kV autotransformer |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-01-15 | 2013-01-15 | 138 | 0 | 0 | 150 |  | Karnes |  | Tier 4 | 2011-12-16 | 2012-04-25 |  | 5728, 5729, 5722, 5727, 5730, 5732 | Y | N |  |  | 2244 | 2172
13TPIT0122 | Choate Station and Autotransformer | Build new Choate substation where Pawnee to Four Corners 138 kV and Kenedy to Charco 69 kV lines cross and add a 150 MVA 139-69 kV autotransformer |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-04-01 | 2013-04-01 | 138 | 0 | 0 | 150 |  | Karnes |  | Tier 4 | 2011-12-16 | 2012-04-25 |  | 5728, 5729, 5722, 5727, 5730, 5732 | Y | N |  |  | 2245 | 2172
13TPIT0127 | Tilden 138 kV Substation | Convert Tilden from 69 kV to 138 kV and connect to new 138 kV line from Tilden to George West. |  |  |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-08-01 | 2013-08-01 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 5700, 5701, 5688, 5699 | Y | N |  |  | 1557 | 1541
13TPIT0129 | George West to Tilden Rebuild | Rebuild 4-0 ACSR 69 kV to double circuit 138 kV capable 795 ACSR. One circuit will be operated at 69 kV from George West to Choke Canyon Prison Sub. The other will be 138 kV from George West to Tilden |  | George West | Tilden | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-02-28 | 2013-02-28 | 138 | 20.6 | 8.4 | 0 |  |  | Live Oak | Tier 4 |  |  |  | 5686, 5695, 5696, 5697, 5699 | Y | N |  |  | 1558 | 1542
13TPIT0129 | George West to Tilden Rebuild | Rebuild 4-0 ACSR 69 kV to double circuit 138 kV capable 795 ACSR. One circuit will be operated at 69 kV from George West to Choke Canyon Prison Sub. The other will be 138 kV from George West to Tilden |  | George West | Tilden | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-03-21 | 2013-03-21 | 138 | 20.6 | 8.4 | 0 |  | McMullen | Live Oak | Tier 4 |  |  |  | 5686, 5695, 5696, 5697, 5699 | Y | N |  |  | 1559 | 1542
13TPIT0129 | George West to Tilden Rebuild | Rebuild 4-0 ACSR 69 kV to double circuit 138 kV capable 795 ACSR. One circuit will be operated at 69 kV from George West to Choke Canyon Prison Sub. The other will be 138 kV from George West to Tilden |  | George West | Tilden | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-04-12 | 2013-04-12 | 138 | 20.6 | 8.4 | 0 |  |  | Live Oak | Tier 4 |  |  |  | 5686, 5695, 5696, 5697, 5699 | Y | N |  |  | 1560 | 1542
13TPIT0129 | George West to Tilden Rebuild | Rebuild 4-0 ACSR 69 kV to double circuit 138 kV capable 795 ACSR. One circuit will be operated at 69 kV from George West to Choke Canyon Prison Sub. The other will be 138 kV from George West to Tilden |  | George West | Tilden | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-05-10 | 2013-05-10 | 138 | 20.6 | 8.4 | 0 |  |  | Live Oak | Tier 4 |  |  |  | 5686, 5695, 5696, 5697, 5699 | Y | N |  |  | 1561 | 1542
13TPIT0132 | Freer Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-08-30 | 2013-08-30 | 69 | 0 | 0 | 0 | 0,9.6 | Webb |  | Tier 4 |  |  |  | 5880 | Y | N |  |  | 1730 | 1691
13TPIT0135 | Holt Switch - Goldsmith - Goldsmith South 138 kV line | Rebuild existing 69 kV line to create a double-circuit line with 69 kV and 138 kV circuits and convert Goldsmith South to 138 kV. |  | Holt Switch | Goldsmith South Substation | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8050A-WAC | 2013-06-15 | 2013-06-15 | 138 | 8 | 0 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 11255, 1141, 1142, 1255, 1257, 1261, 11250, 11256 | Y | N |  | Goldsmith - Goldsmith South section completed in 3/2013 | 2801 | 2677
13TPIT0141 | NORTON 138kV Substation | Construct service to new 138kV NORTON customer-owned substation. Loop through Ckt. 86 HACHER - ENPROD. |  | NORTON | HACHER-ENPROD | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-04-30 | 2013-04-30 | 138 | 1.98 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  | 40760, 40510, 40770 | Y | N |  |  | 2115 | 1563
13TPIT0142 | Broadview 72 MVAR Capacitor Bank | Install 72 MVAR capacitor bank on the East bus and remove both back-to-back capacitor banks from the West bus |  |  |  | Planned |  | CPS | Hector Torres HVTorres@cpsenergy.com 210-353-2404 | S-0395 | 2014-01-31 | 2014-01-31 | 138 | 0 | 0 | 0 | 0,72 | Bexar | Bexar | Tier 4 |  |  |  | 5040 | Y | N |  | There are no transformers associated with this project | 1930 | 1881
13TPIT0143 | El Campo - Ricebird - Nada Transmission Line Upgrade and Sub | Construct a new 138 kV Ricebird Substation (78104) and terminate the 138 kV transmission lines from El Campo (8102) and Nada (78103) at the Ricebird Substation. Install a new 60MVA 138-69kV autotransformer at the Nada substation. |  | El Campo Substation | Nada Substation | Planned | 13TPIT0120 (STEC) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-01-03 | 2013-01-03 | 138 | 0 | 17.5 | 60 |  | Colorado | Wharton | Tier 3 | 2011-10-14 | 2011-11-09 |  | 78103, 78104, 5536, 8100, 8102, 78106 | Y | N |  | Coordinate this project with STEC | 1584 | 1553
13TPIT0144 | Central Dawson 69 kV POI/South Lamesa Sub | Tap the 69 kV Lamesa-Ackerly Line where the line intersects Dawson Co. Road 22 and construct a 10 MVA substation to replace a distribution metering point |  |  |  | UnderConstruction |  | GOLDENSPREAD | Chris Koenig ckoeng@gsec.coop 806-349-5201 |  | 2013-02-01 | 2013-02-01 | 69 | 0 | 0 | 0 |  | Dawson | Dawson | Tier 4 |  |  |  | 9413, 18920 | Y | N |  |  | 1954 | 1904
13TPIT0150 | Glidden to Colorado Transmission upgrade | Rebuild entire line from Glidden to Colorado substation to 795 MCM 138 Kv insulation | ERCOT approval through RPG review process was granted March 27,2012 | Glidden | Colorado | UnderConstruction |  | SBEC | Don Roberts droberts@sbec.org | WO#12-6056 WO#12-6057 WO#12-6058 WO#12-6061 WO#12-5315 WO#12-5316 WO#12-5317 WO#12-5327 WO#12-5328 WO#12-5329 WO#12-5330 WO#12-5331 | 2013-08-30 | 2013-08-30 | 69 | 0 | 27 | 0 |  | Colorado | Colorado | Tier 3 | 2012-02-27 | 2012-03-27 |  | 7257, 7636, 7639, 7640 | Y | N |  |  | 2496 | 2391
13TPIT0152 | Loving - El Mar 138 kV line | Rebuild existing 138 kV line |  | Wink Switch | Mason | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8066-E | 2013-12-15 | 2013-12-15 | 138 | 0 | 40 | 0 |  | Winkler | Reeves | Tier 3 | 2012-05-15 | 2012-06-15 |  | 1092, 1093 | Y | N |  | Wink - Loving complete in 11/2013, Loving - El Mar complete in 12/2013 and El Mar - Mason complete in 5/2014 | 3159 | 2990
13TPIT0152 | Wink Switch - Loving 138 kV line | Rebuild existing 138 kV line | Construction schedule change | Wink Switch | Mason | In Service |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8066-E | 2014-01-15 | 2014-01-15 | 138 | 0 | 40 | 0 |  | Winkler | Reeves | Tier 3 | 2012-05-15 | 2012-06-15 |  | 1074, 1092 | Y | N |  | Wink - Loving complete in 11/2013, Loving - El Mar complete in 12/2013 and El Mar - Mason complete in 5/2014 | 3160 | 2991
13TPIT0154 | Barber Lake 138 kV Switching Station | Construct new switching station |  | Barber Lake |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8060-E | 2013-12-15 | 2013-12-15 | 138 | 0 | 0 | 0 |  | Mitchell |  | Tier 4 |  |  |  | 1189, 1190, 1032, 19520, 19521 | Y | N |  |  | 3494 | 2692
13TPIT0156 | Katemcy: Add 7.2 Mvar capacitor bank | Add two 7.2 Mvar capacitor banks at North Brady and add 7.2 Mvar capacitor bank at Katemcy | In-Service | Katemcy |  | Planned | 559 - 0722 | AEP TNC | Eric Scott 918-599-2664 | 2562 | 2013-12-31 | 2013-12-31 | 69 | 0 | 0 | 0 | 0,7.2 | McCulloch |  | Tier 4 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 6406, 6379, 6386, 6393 | Y | N | 0 | 0 | 2197 | 2125
13TPIT0158 | Bruni to MEC Bruni: Rebuild 138 kV line | Reterminate MEC Bruni tap into Bruni sub-station and upgrade sub-station to 4 breaker ring bus | Reformated project number to match other numbers | Bruni | MEC Bruni | In Service | 572 - 0749 | AEP TCC |  | 3450 | 2013-11-05 | 2013-11-05 | 138 | 0.5 | 0.1 | 0 |  | Webb | Webb | Tier 4 |  |  |  | 8958, 5887, 8297, 80439 | Y | N |  |  | 1946 | 1897
13TPIT0159 | Bruni 138 kV station: Install 138 kV breakers ring bus | Reterminate MEC Bruni tap into Bruni sub-station and upgrade sub-station to 4 breaker ring bus | CHANGES | BRUNI |  | UNDER CONSTRUCTION | 572-0749 | AEP TCC | MICHAEL TALLON GAREED@AEP.COM 918-599-2664 | TP2011154 | 2013-10-31 | 2013-10-31 | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 8297 | Y | N | NA | NA | 3685 | 3478
13TPIT0160 | Whitepoint: Add 138 kV breaker terminal for WF interconnect | Construct a 138 kV breaker terminal at Whitepoint for the Generator Interconnect | CHANGES | WHITEPOINT |  | UNDER CONSTRUCTION | 573-0750 | AEP TCC | FRANK PRITZLAFF GAREED@AEP.COM 918-599-2664 | TP2010078 | 2013-12-31 | 2013-12-31 | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8961 | Y | N | NA | NA | 3672 | 3467
13TPIT0164 | Big Oak 69 kV Substation | Build new load serving station in the 69 kV line between Beeville and Goliad Switch. |  |  |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-06-03 | 2013-06-03 | 69 | 0 | 0 | 0 | 0,9.6 | Goliad |  | Tier 4 |  |  |  | 5675, 5674, 5676 | Y | N |  |  | 2007 | 1957
13TPIT0173 | Friend Ranch: Remove 10 MVA DRCS | Add 3.6 Mvar capacitor bank at Barnhart SWTEC and add 10 MVA DRCS with 7.2 Mvar capacitor bank at Yucca | In-Service | Friend Ranch |  | Planned | 558 - 0721 | AEP TNC | Michael Tallon 918-599-2664 | 2564 | 2013-11-01 | 2013-11-01 | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 60202, 6550 | Y | N |  |  | 3950 | 3707
13TPIT0175 | Wormser Road: Install DRCS | Relocate DRCS from Hamilton Road to Wormser Road. | In Service | Wormser |  | In Service | 563 - 0731 | AEP TCC | Glen Reed 918-599-2664 | 3441 | 2013-09-20 | 2013-09-20 | 138 | 0 | 0 | 0 |  | Val Verde |  | Tier 4 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 8276, 8295 | Y | N | 0 | 0 | 2198 | 2126
13TPIT0176 | Wormser Road: Install Capacitor Bank | Install one (1) - 14.4 MVAR Capacitor Bank at Wormser Road substation. | Reformated project number to match other numbers | Wormser |  | In Service | 563 - 0731 | AEP TCC | Glen Reed 918-599-2664 | 3457 | 2013-12-31 | 2013-12-31 | 69 | 0 | 0 | 0 |  | Val Verde |  | Tier 4 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 8295 | Y | N | 0 | 0 | 2199 | 2127
13TPIT0178 | Skywest | Cut in the new Skywest (71210) substation on the LCRA TSC Midkiff (1210) - Sprayberry (1329) 138kV transmission line. |  | Skywest | Midkiff-Sprayberry | Planned | 13TPIT0166 (SU) | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-03-31 | 2013-03-31 | 138 | 0 | 0 | 0 |  | Midland |  | Tier 4 |  |  |  | 71210, 1210, 1329 | Y | N |  |  | 2416 | 2339
13TPIT0179 | McCarty Lane Terminal Equipment Upgrade | Upgrade the jumper continuous ratings to minimum 2000 Amps on Zorn - McCarty Lane line at the McCarty Lane (7182) substation. |  | McCarty Lane |  | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-05-31 | 2013-05-31 | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  | 7180, 7182 | Y | N |  |  | 2193 | 2121
13TPIT0181 | Gilleland Creek Autotransformer Replacement | Replace failed autotransformer at the Gilleland Creek substation | No autotransformer will be in service at Gilleland Creek until the replacement is installed |  |  | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-11-30 | 2013-11-30 | 345 | 0 | 0 | 672 |  | Travis |  | Tier 4 |  |  |  | 77340, 7340, 7336 | Y | N |  | Cost will be determined during the September TPIT. | 1985 | 1934
13TPIT0182 | Comanche cap bank | Install a 30 MVAR, 138 kV capacitor bank at Comanche Switching Station. |  | Comanche |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2013-05-31 | 2013-05-31 | 138 | 0 | 0 | 0 | 0,30 | Galveston |  | Tier 4 |  |  |  | 38560 | Y | N |  |  | 2088 | 2024
13TPIT0183 | Coy City Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-04-01 | 2013-04-01 | 69 | 0 | 0 | 0 | 0,9.6 | Karnes |  | Tier 2 | 2011-12-16 | 2012-04-25 |  | 5720 | Y | N |  | This location was chosen for 9.6 MVAR instead of having all 19.2 MVAR at Kenedy. | 2110 | 2046
13TPIT0184 | Poteet Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-04-01 | 2013-04-01 | 69 | 0 | 0 | 0 | 0,9.6 | Atascosa |  | Tier 2 | 2011-12-16 | 2012-04-25 |  | 5710 | Y | N |  | This location was chosen for a capcitor bank because there is not room for a capacitor bank at Pleasanton unless more land is purchased. | 2108 | 2044
13TPIT0185 | Fashing Capacitor | Add two 9.6 MVAR capacitors |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-02-01 | 2013-02-01 | 69 | 0 | 0 | 0 | 0,19.2 | Atascosa |  | Tier 2 | 2011-12-16 | 2012-04-25 |  | 5716 | Y | N |  |  | 2109 | 2045
13TPIT0188 | Crabb River Road Substation Reconfiguration | Multi-Phase Project: 13TPIT0188A & 13TPIT0188B - Reconfigure 138kV Crabb River Road substation from loop to double tap. Tap Ckt.80 between WA Parish and Imperial. | IN-SERVICE | Crabb River Road | WA Parish-Imperial | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-10-30 | 2013-10-30 | 138 | 0.2 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44171, 44172, 44170, 44010, 44341 | Y | N |  | Part of Fort Bend Area Upgrades. | 2373 | 2298
13TPIT0188 | Crabb River Road Substation Reconfiguration | Multi-Phase Project: 13TPIT0188A & 13TPIT0188B - Reconfigure 138kV Crabb River Road substation from loop to double tap. Tap Ckt.80 between WA Parish and Imperial. | IN-SERVICE | Crabb River Road | WA Parish-Imperial | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-10-31 | 2013-10-31 | 138 | 0.2 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44171, 44172, 44170, 44010, 44341 | Y | N |  | Part of Fort Bend Area Upgrades. | 2374 | 2298
13TPIT0189 | CNP_13TPIT0189_FTBend_BrazosV_Upgrade | Upgrade 138kV Ckt. 09 Brazos Valley to Fort Bend to increase thermal ratings. | IN-SERVICE | Brazos Valley | Fort Bend | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-04-30 | 2013-04-30 | 138 | 0 | 5.62 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44100, 44250, 44300, 44231, 44280, 44540, 44610 | Y | N |  | Part of Fort Bend Area Upgrades. | 2542 | 2437
13TPIT0190 | Busch Substation Conversion | Convert Busch substation from double-tap to 138kV loop service Ckt. 08. | IN-SERVICE | Busch | Anbush-Clinton | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-12-23 | 2013-12-23 | 138 | 0 | 0.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40231, 40232, 40235, 40100, 40250, 40352, 40611, 40725, 41160, 41681, 40351, 40720, 41040, 41570, 41682, 47540 | Y | N |  |  | 2371 | 2296
13TPIT0191 | Southwyck Cap Bank | Install 28.8MVAR capacitor bank at Southwyck substation. |  | Southwyck |  | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-05-30 | 2013-05-30 | 138 | 0 | 0 | 0 | 0,28.8 | Brazoria |  | Tier 4 |  |  |  | 43260 | Y | N |  |  | 2377 | 2301
13TPIT0192 | Lockwood Cap Bank | Install 14.4MVAR capacitor bank at Lockwood substation. |  | Lockwood |  | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-05-31 | 2013-05-31 | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  | 46032 | Y | N |  |  | 2375 | 2299
13TPIT0194 | Cardiff Substation Conversion | Convert Cardiff substation from double-tap to 138kV loop service Ckt. 96. | IN-SERVICE | Cardiff | South-Deer Park | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-12-07 | 2013-12-07 | 138 | 0 | 0.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42240, 42241, 42242, 40442, 42010, 42120, 42291, 42292, 42562, 42610, 42611, 42841, 42970, 43102, 41631, 41711, 43101, 43250, 43500, 43503, 43504 | Y | N |  |  | 2372 | 2297
13TPIT0195 | Arcola Substation Conversion | Convert Arcola substation from double-tap to 138kV loop service Ckt.82. | IN-SERVICE | Arcola | Thompsons/Karsten | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-12-25 | 2013-12-25 | 138 | 0 | 0.2 | 0 |  | Fort Bend |  | Tier 4 |  |  |  | 44031, 43035, 44010, 44032, 44390, 44000, 44721, 44722 | Y | N |  |  | 2370 | 2295
13TPIT0196 | MILLER 138kV Substation | Construct service to new 138kV MILLER customer-owned substation. Loop through Ckt.88 BARNES to SR Bertron. |  | MILLER | BARNES-SR Bertron | COMPLETE |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-04-30 | 2013-04-30 | 138 | 0.2 | 0.3 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41420, 40081, 40540, 41350, 41355, 41405, 41580, 41415, 41620 | Y | N |  |  | 2376 | 2300
13TPIT0197 | Pleasanton Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-04-22 | 2013-04-22 | 69 | 0 | 0 | 0 | 0,9.6 | Atascosa |  | Tier 4 | 2011-12-16 | 2012-04-25 |  | 5714 | Y | N |  |  | 2358 | 2283
13TPIT0201 | Goldsmith South - Goldsmith Junction 138 kV line | Rebuild existing 69 kV line to create a double-circuit line with 69 kV and 138 kV circuits and connect the 138 kV circuit to an existing Moss - Ector County North 138 kV line. | Transfer of 69 kV conductor is taking more time than expected | Goldsmith South Substation | Goldsmith Junction | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8120-E | 2013-09-15 | 2013-09-15 | 138 | 5.5 | 5.5 | 0 |  | Ector | Ector | Tier 4 |  |  |  |  | Y | N |  | 138 kV work was completed in June 2013. | 3653 | 3452
13TPIT0202 | Barstow Capbank Install |  |  | Barstow Tap |  | Operational |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2013-10-03 | 2013-10-03 | 69 | 0 | 0 | 0 | 0,10 | Reeves |  | Tier 4 |  |  |  | 38000, 38090, 38150 | Y | N |  |  | 3680 | 3474
13TPIT0202 | Barstow Tap cap bank | Install 10 MVAR, 69kV cap bank at Barstow Tap Substation |  | Barstow Tap |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2013-07-01 | 2013-07-01 | 69 | 0 | 0 | 0 | 0,10 | Reeves |  | Tier 4 |  |  |  | 38150 | Y | N |  |  | 2790 | 2666
13TPIT0205 | Barilla Draw 69 kV Tap | This project will tap TNMP's IH20 to Flattop 69kV line to serve the Barilla Draw Field customer load and Install a 15 MVAR 69 kV Cap Bank at Barilla Draw Station |  | IH20 | Barilla Draw Tap | UnderConstruction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2013-03-31 | 2013-03-31 | 69 | 0 | 0 | 0 | 0,15 | Reeves | Reeves | Tier 4 |  |  |  | 38060, 38065, 38040, 38070 | Y | N |  | Barilla Draw Tap will be Approximately 11.57 Miles from IH20 | 2398 | 2321
13TPIT0206 | Bone Springs 69 kV Tap | This project will tap TNMP's Wink to Cochise 69kV line to serve the Bone Springs customer load. |  | Wink | Bone Springs Tap | UnderConstruction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2013-02-20 | 2013-02-20 | 69 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  | 38170, 38175, 37920, 38160 | Y | N |  | Bone Springs Tap will be Approximately 3.48 Miles from Cochise. | 2399 | 2322
13TPIT0207 | Texas City Main Cap Bank | Install a New 25 MVAR 69 kV Cap Bank at Texas City Main Station and Retire the 14.4 MVAR Cap Bank at Amoco 69kV Bus |  | Texas City Main |  | UnderConstruction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE08512 | 2013-02-15 | 2013-02-15 | 69 | 0 | 0 | 0 | 0,25 | Galveston |  | Tier 4 |  |  |  | 38650, 39140 | Y | N |  | 14.4 MVAR 69kV Cap Bank at Amoco Station to be retired. | 2099 | 2035
13TPIT0208 | Nevada 138 kV new substation and connections | Nevada 138 kV new load serving substation and its connections to Shelby and to Royse City | Funded | New switches at new Nevada | Switches at Shelby and at Royse City | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2013-12-11 | 2013-12-11 | 138 | 0 | 0 | 0 |  | Hunt | Dallas | Tier 4 |  |  |  | 811, 960, 2471 | Y | N |  | This project is a new load serving project | 2618 | 2513
13TPIT0209 | Mockingbird Substation Addition | Construct a new substation named Mockingbird (78259) on the Glidden - Fayetteville 138-kV transmission line. |  | Mockingbird | Glidden-Fayetteville | Planned |  | LCRA | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2013-11-02 | 2013-11-02 | 138 | 0 | 0 | 0 |  | Colorado |  | Tier 4 |  |  |  | 78259, 7258, 7263 | Y | N |  | Coordinate with AEP | 2771 | 2647
13TPIT0209 | Mockingbird Substation Addition | Construct a new substation named Mockingbird (78259) on the Glidden - Fayetteville 138-kV transmission line. |  | Mockingbird | Glidden-Fayetteville | Planned |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 |  | 2013-05-15 | 2013-05-15 | 138 | 0 | 0 | 0 |  | Colorado |  | Tier 4 |  |  |  | 1972, 37010 | Y | N |  | Coordinate with AEP | 2774 | 2650
13TPIT0210 | Mountain Top 138kV Bus Upgrade | Upgrade existing 138kV operate and transfer busses from 795ACSR to bundled 795 ACSR |  | Mountain Top |  | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2013-12-31 | 2013-12-31 | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 |  |  |  | 7148 | Y | N |  |  | 3493 | 3314
13TPIT0211 | Edna Capacitor | Add 9.6 MVAR capacitor |  |  |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2013-05-01 | 2013-05-01 | 69 | 0 | 0 | 0 | 0,9.6 | Jackson |  | Tier 4 |  |  |  | 5522 | Y | N |  |  | 2662 | 2556
13TPIT0212 | Mont Belvieu Area Upgrades | Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. | IN-SERVICE | CROSBY | BENDER | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-11-30 | 2013-11-30 | 138 | 0 | 1.4 | 0 |  | Harris | Chambers | Tier 4 |  |  |  | 40000, 40130, 40155, 40255, 40390, 40391, 40900, 41150, 46100 | Y | N |  | This TPIT entry includes the completion of the cicuit segment upgrade which is scheduled to be complete by Sept. 2013 | 2794 | 2670
13TPIT0213 | Mont Belvieu Area Upgrades | Install second 73.3MVAR capacitor bank at Mont Belvieu substation. | IN-SERVICE | Mont Belvieu |  | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-06-30 | 2013-06-30 | 138 | 0 | 0 | 0 | 0,73.3 | Chambers |  | Tier 4 |  |  |  | 41114, 41111, 41700 | Y | N |  |  | 2759 | 2635
13TPIT0214 | RALYND 138kV Substation | Construct service to new 138kV RALYND customer-owned substation. Loop through ENPROD - NORTON and rename circuits to 59. | IN-SERVICE | RALYND | ENPROD/NORTON | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-06-07 | 2013-06-07 | 138 | 0.3 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  | 40762, 40150, 40510, 40760, 40770 | Y | N |  |  | 2902 | 2747
13TPIT0215 | Construct service to new 138kV TANKER customer-owned substat |  |  | TANKER | Galena Park/CROWN | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-05-31 | 2013-05-31 | 138 | 0.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40630 | Y | N |  |  | 2905 | 2750
13TPIT0216 | Reveille Substation 138kV: STEC Interconnect | Reveille Substation 138kV: STEC Interconnect | In Service | Reveille |  | Under Construction | 564-0732 | AEP TCC |  | 3442 | 2013-01-16 | 2013-01-16 | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 8602, 8610, 8619 | Y | N |  |  | 3091 | 2916
13TPIT0216 | Reveille substation 138kV: STEC Interconnect | Reveille substation 138kV: STEC Interconnect | Changed Status and Associated project number format | Reveille |  | UnderConstruction | 564 - 0732 | AEP TCC |  | 3442 | 2013-01-31 | 2013-01-31 | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 8612, 8610, 8619 | Y | N |  |  | 2037 | 1987
13TPIT0217 | Jardin Substation 138kV: STEC Interconnect | Jardin Substation 138kV: STEC Interconnect | In Service | Jardin |  | Under Construction | 565-0733 | AEP TCC |  | 3443 | 2013-07-12 | 2013-07-12 | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 8611 | Y | N |  |  | 3092 | 2917
13TPIT0217 | Jardin substation 138kV: STEC Interconnect | Jardin substation 138kV: STEC Interconnect | Changed associated Project number format, and changed status | Jardin |  | UnderConstruction | 565 - 0733 | AEP TCC |  | 3443 | 2013-03-30 | 2013-03-30 | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 8212, 8610, 8611, 8619, 8909 | Y | N |  |  | 2036 | 1986
13TPIT0220 | Permian Basin - Wink 138 kV line | Upgrade terminal equipment at Wink | Construction taking longer than projected | Permian Basin | Wink | Under Construction | R8066 | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 |  | 2013-06-15 | 2013-06-15 | 138 | 0 | 0 | 0 |  | Ward | Winkler | Tier 4 |  |  |  |  | Y | N |  | Switches at Wink will be replaced as part of the Wink Switch - Loving - El Mar - Mason 138 kV line reconstruction project (13TPIT0152). | 3260 | 3091
13TPIT0225 | Bobwhite: Build new 138 kV Box Bay Switch Structure | Construct new Bobwhite station along the East Munday to Lake Pauline 138 kV line | In Service | Bobwhite |  | In Service | 586 - 0767 | AEP TNC |  | 2803 | 2013-05-31 | 2013-05-31 | 138 | 0 | 0 | 0 |  | Foard |  | Tier 4 |  |  |  | 6037, 6038, 6050, 6110 | Y | N |  |  | 2827 | 2702
13TPIT0228 | Move Hall Marys Creek tap from Ckt91 to Ckt92 | Move existing Hall/ Mary's Creek tap from Ckt.91 to Ckt.92. | IN-SERVICE |  |  | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-11-11 | 2013-11-11 | 138 | 0.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42582, 42680, 42762, 43272, 43322 | Y | N |  |  | 3105 | 2936
13TPIT0229 | Harrisburg Cap Bank | Install new 10.8 MVAR cap bank and increase existing cap bank capacity to 10.8 MVAR. | IN-SERVICE | Harrisburg |  | Complete |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-09-20 | 2013-09-20 | 69 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  | 40800 | Y | N |  | Part of South Houston conversion project | 2866 | 2740
13TPIT0230 | Cedar Bayou to PHR Ckt.97 upgrade | Multi-Phase Project: 13TPIT0230B - Upgrade 345kV Ckt.97 Cedar Bayou to Center to increase thermal ratings. 13TPIT0230A - Upgrade 345kV Ckt.97 Center to PH Robinson to increase thermal ratings. | IN-SERVICE | Center | PH Robinson | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-11-30 | 2013-11-30 | 345 | 0 | 16.5 | 0 |  | Harris | Galveston | Tier 4 |  |  |  | 40000, 40010, 40015, 40170, 40240, 42160, 40171, 40870, 40871, 41330, 41500, 42000, 42014 | Y | N |  | Cost shown is for all project phases. | 2867 | 2741
13TPIT0230 | Cedar Bayou to PHR Ckt.97 upgrade | Multi-Phase Project: 13TPIT0230B - Upgrade 345kV Ckt.97 Cedar Bayou to Center to increase thermal ratings. 13TPIT0230A - Upgrade 345kV Ckt.97 Center to PH Robinson to increase thermal ratings. | IN-SERVICE | Cedar Bayou | Center | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-11-30 | 2013-11-30 | 345 | 0 | 9.5 | 0 |  | Chambers | Harris | Tier 4 |  |  |  | 40000, 40010, 40015, 40170, 40240, 42160, 40171, 40870, 40871, 41330, 41500, 42000, 42014 | Y | N |  | Cost shown is for all project phases. | 2868 | 2741
13TPIT0231 | South Houston Conversion | Multi-Phase Project: 13TPIT0231A - Convert the 69kV portion of South Houston substation to 138kV and use portion of de-energized Ckt.13 to create a new Ckt.91 tap to South Houston & Spencer. Remove 7.2 MVAR cap bank at South Houston. 13TPIT0231B - De-energize 69kV Deepwater to South Houston to Webster Ckt.13. Use portions of de-energized circuit to reconfigure South Houston substation. | IN-SERVICE | South Houston | Deepwater/Webster | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-11-22 | 2013-11-22 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42762, 43170, 43171, 43172, 43173, 43174, 43272, 43371, 43372, 40470, 42582, 43322, 43510, 43610 | Y | N |  | Cost shown is for all project phases | 2900 | 2746
13TPIT0231 | South Houston Conversion | Multi-Phase Project: 13TPIT0231A - Convert the 69kV portion of South Houston substation to 138kV and use portion of de-energized Ckt.13 to create a new Ckt.91 tap to South Houston & Spencer. Remove 7.2 MVAR cap bank at South Houston. 13TPIT0231B - De-energize 69kV Deepwater to South Houston to Webster Ckt.13. Use portions of de-energized circuit to reconfigure South Houston substation. | IN-SERVICE | South Houston | PH Robinson/Cougar | Completed |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-12-05 | 2013-12-05 | 138 | 0 | 4.2 | 0 | 0,-7.2 | Harris | Harris | Tier 4 |  |  |  | 42762, 43170, 43171, 43172, 43173, 43174, 43272, 43371, 43372, 40470, 42582, 43322, 43510, 43610 | Y | N |  | Cost shown is for all project phases | 2901 | 2746
13TPIT0233 | Polecat Creek 138 kV Switching Station | Construct 138 kV switching station |  | Polecat |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8172-E | 2013-12-15 | 2013-12-15 | 138 | 0 | 0 | 0 |  | Glasscock |  | Tier 4 |  |  |  | 11337, 1335, 1337 | Y | N |  |  | 3191 | 3022
13TPIT0234 | Fullerton - Exxon Fullerton 69 kV Line | Upgrade existing 69 kV line | Construction schedule change | Fullerton | Exxon Fullerton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8160-WAC | 2013-07-15 | 2013-07-15 | 69 | 0 | 0.1 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1274, 1275 | Y | N |  |  | 3192 | 3023
13TPIT0238 | Puncher: Build new 69 kV station | [6 empty] | AEP TNC |  |  | 2013-09-30 | 2013-09-30 | 0 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 6394, 6395, 6407 | Y |  |  |  | 3573 | 3378
13TPIT0239 | Hornet: Build new 69 kV station | Construct new Hornet station along the Menard Phillips to Menard Phillips Tap 69 kV line |  | Hornet |  | Planned | 594 - 0774 | AEP TNC |  | 2582 | 2013-09-30 | 2013-09-30 | 69 | 0 | 0 | 0 |  | Kimble |  | Tier 4 |  |  |  | 6401, 6516, 6402 | Y | N |  |  | 3402 | 3229
13TPIT0240 | Pandale: Build new 69 kV station | Construct new Pandale station along the Illinois #4 to Ozona 69 kV line | In-Service | Pandale |  | Under Construction | 595 - 0775 | AEP TNC | Eric Scott 918-599-2664 |  | 2013-12-26 | 2013-12-26 | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6567, 6551, 6565 | Y | N |  |  | 3644 | 3444
13TPIT0242 | Welsh HVDC: Add 100 MVAR Shunt Reactor | Welsh HVDC Tie: Phase 1A Station Upgrades | In-Service | WELSH HVDC Tie |  | Under Construction | 625 - 0793 | AEP TCC | Terry Weeks 918-599-2664 | 3508 | 2013-12-31 | 2013-12-31 | 345 | 0 | 0 | 0 | -100,0 | Titus |  | Tier 4 |  |  |  | 5925 | Y | Y |  |  | 3397 | 3224
14TPIT0054 | Odessa - Odessa North 138 kV line | Reconductor existing 138 kV line |  | Odessa | Odessa North | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8019-E | 2013-12-15 | 2013-12-15 | 138 | 0 | 7.2 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1122, 1126 | Y | Y |  |  | 2809 | 2685
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | JORDAN | DUNCAN | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-10-28 | 2013-10-28 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2918 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | JORDAN | BENDER | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-10-29 | 2013-10-29 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2919 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | JORDAN | ENPROD | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-10-30 | 2013-10-30 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2920 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | JORDAN | CITIES | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-10-31 | 2013-10-31 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2921 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | BENDER | DUNCAN | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-07-31 | 2013-07-31 | 138 | 0 | 1.91 | 0 |  | Chambers | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2923 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | CROSBY | BENDER | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-05-31 | 2013-05-31 | 138 | 0 | 7.89 | 0 |  | Harris | Chambers | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2924 | 2758
14TPIT0058 | Mont Belvieu Area Upgrades | Multi-Phase Project: 14TPIT0058A - Build new 345kV JORDAN substation. Install new 800 MVA autotransformer. 14TPIT0058B - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Cedar Bayou. 14TPIT0058C - Loop existing Ckt.99 Cedar Bayou - Northbelt into new JORDAN substation to create new Ckt.99 JORDAN - Northbelt. 14TPIT0058D - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing DUNCAN - BARHIL circuit to create new Ckt.59 JORDAN - BARHIL. 14TPIT0058E - Build new circuit out of JORDAN 138kV substation and reconnect portion of existing ENPROD - HACHER circuit to create new Ckt.59 JORDAN - RALYND. 14TPIT0058F - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.48 JORDAN - DUNCAN. 14TPIT0058G - Loop existing Ckt.86 DUNCAN - BENDER into new 138kV JORDAN substation to create new Ckt.86 JORDAN - BENDER. 14TPIT0058H - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.48 JORDAN - ENPROD. 14TPIT0058I - Loop existing Ckt.86 ENPROD - CITIES into new 138kV JORDAN substation to create new Ckt.86 JORDAN - CITIES. 14TPIT0058J - Reconfigure existing Ckt.86 DUNCAN - BARHIL and Ckt.86 ENPROD - HACHER to create new Ckt.48 DUNCAN - ENPROD. 14TPIT0058K - Upgrade 138kV Ckt. 86 Bender to Duncan to increase thermal ratings. 14TPIT0058L - Upgrade 138kV Ckt. 86 Crosby to Bender to increase thermal ratings. (Thermal uprate) |  | Mont Belvieu |  | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-01-31 | 2013-01-31 | 138 | 0 | 0 | 0 | 0,73.3 | Chambers |  | Tier 3 | 2012-02-03 | 2012-03-05 |  | 40511, 40850, 40855, 41114, 49077, 40000, 40150, 40155, 40255, 40340, 40360, 40510, 40762, 40900, 41111, 45822, 40390, 41113, 41700, 46031, 46100 | Y | N |  | Cost shown is for all project phases. | 2928 | 2758
14TPIT0088 | Moss - Holt Switch 138 kV line | Reconductor existing 138 kV line |  | Moss | Holt Switch | In Service |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8065B-WAC | 2014-01-15 | 2014-01-15 | 138 | 0 | 18 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1019, 1141, 1143 | Y | N |  |  | 2807 | 2683
14TPIT0112 | SEADOC 138 kV Customer Substation | Multi-Phase Project: 14TPIT0112A - Construct service to new 138kV SEADOC customer-owned double-tap substation. Tap existing Ckt.02 Booster to Seaway Switchrack. 14TPIT0112B - Construct service to new 138kV SEADOC customer-owned double-tap substation. Tap existing Ckt.02 Velasco to Brazosport. |  | SEADOC | Booster/Seaway Switchrack | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-01-30 | 2014-01-30 | 138 | 0.1 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43220, 43222, 43226, 5915, 42150, 42195, 42210, 43140, 43360, 42500, 43221, 43370 | Y | N |  | Cost shown is for all project phases | 2871 | 2744
14TPIT0112 | SEADOC 138 kV Customer Substation | Multi-Phase Project: 14TPIT0112A - Construct service to new 138kV SEADOC customer-owned double-tap substation. Tap existing Ckt.02 Booster to Seaway Switchrack. 14TPIT0112B - Construct service to new 138kV SEADOC customer-owned double-tap substation. Tap existing Ckt.02 Velasco to Brazosport. |  | SEADOC | Velasco/Brazosport | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-01-31 | 2014-01-31 | 138 | 5.3 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43220, 43222, 43226, 5915, 42150, 42195, 42210, 43140, 43360, 42500, 43221, 43370 | Y | N |  | Cost shown is for all project phases | 2872 | 2744
15TPIT0006 | Bandera to Broadview - 138kV substation equipment upgrade | Upgrade substation equipment at Broadview to remove existing MLSE on the Bandera to Broadview 138kV line |  | Bandera | Broadview | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0395 | 2013-03-29 | 2013-03-29 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5020, 5040, 5150, 5170 | Y | N |  | There are no transformers associated with this project | 2748 | 966
15TPIT0006 | Bandera to Broadview - 138kV substation equipment upgrade | Upgrade substation equipment at Broadview to remove existing MLSE on the Bandera to Broadview 138kV line |  | Bandera | Broadview | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0395 | 2013-06-01 | 2013-06-01 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5020, 5040, 5150, 5170 | Y | N |  | There are no transformers associated with this project | 2749 | 966
15TPIT0012 | Petteway to Ben Hur | Rebuild Petteway to Ben Hur 69 kV line with 795 ACSR |  | Petteway | Ben Hur | planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 10046 | 2013-02-21 | 2013-02-21 | 69 | 0 | 23.59 | 0 |  | Robertson | Limestone | Tier 4 |  |  |  | 85, 93, 99 | Y | N |  |  | 248 | 251
15TPIT0013 | Seymour to Lake Kemp Switch | Rebuild Seymour to Lake Kemp Switch 69 kV line with 795 ACSR |  | Seymour | Lake Kemp Switch | planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 10047 | 2013-09-13 | 2013-09-13 | 69 | 0 | 6.9 | 0 |  | Baylor | Baylor | Tier 4 |  |  |  | 779, 782 | Y | N |  |  | 1070 | 1069
15TPIT0015 | Hastings-Friendswood rebuild | Rebuild Hastings to Friendswood 138 kV transmission line with 795 ACSS conductor. Upgrade terminal equipment at Friendswood Substation. |  | Hastings | Friendswood | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07412 | 2013-03-15 | 2013-03-15 | 138 | 0 | 7.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 38980, 39010 | Y | N |  |  | 1017 | 1016
15TPIT0034 | Freeport Area Upgrades and Conversion to 138kV | Multi-Phase Project: 15TPIT0034A - Upgrade Ckt.47 Velasco to Freeport 15TPIT0034B - Convert Ckt.47 Velasco to Freeport to 138kV 15TPIT0034C - Upgrade Ckt.47 Freeport to Quintana 15TPIT0034D - Convert Ckt.47 Freeport to Quintana to 138kV 15TPIT0034E - Convert to 138kV Ckt.47 Freeport to Bryan 15TPIT0034F - Upgrade Ckt.47 Surfside to Quintana 15TPIT0034G - Convert Ckt.47 Surfside to Quintana to 138kV 15TPIT0034H - Upgrade Ckt.10 Velasco to Surfside 15TPIT0034I - Convert Ckt.10 Velasco to Surfside to 138kV |  | Velasco | Surfside | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2014-01-31 | 2014-01-31 | 69 | 0 | 2.5 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 42640, 42645, 43135, 43310, 43315, 43435, 44205, 43360, 43370 | Y | N |  | Part of ERCOT RPG Freeport Area Upgrades. Cost shown is for all project phases. | 3530 | 2389
15TPIT0043 | Fort Bend Area Upgrades | Multi-Phase Project: 15TPIT0043A - Convert FOSTER substation from 69kv service to 138kv tap off of Ckt.25 Flewellen - Peters 15TPIT0043B - Remove COLLIN substation from CNP transmission service 15TPIT0043C - Remove Richmond substation from CNP transmission service 15TPIT0043D - Convert 69kv Rosenberg substation to 138kv and reconfigure existing circuits to create new Ckt.60 Orchard - Rosenberg - Fort Bend. 15TPIT0043E - Remove 69kv facilities at Flewellen substaton and reconfigure existing circuit to create new Ckt.49 Flewellen - Fort Bend. |  | COLLIN |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2013-05-15 | 2013-05-15 | 69 | 0 | 0 | 0 |  | Fort Bend |  | Tier 3 | 2012-09-14 | 2012-10-29 |  | 44160, 44240, 44250, 44255, 44580, 44610, 44611, 49013, 44010, 44070, 44171, 44230, 44290, 44300, 44540, 44280, 44341, 46220 | Y | N |  | Cost shown is for all project phases | 2896 | 2636
3404 | Elm Mott 138 kV terminal equipment | Upgrade terminal equipment on 138 kV line from Elm Mott to Rogers Hill to Bosque |  | Elm Mott |  | Planned |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 |  | 2013-07-15 | 2013-07-15 | 138 | 0 | 0 | 0 |  | McLennan |  | Tier 4 |  |  |  |  | Y |  |  |  | 3604 | 3404
3553 | McCampbell Tap | Tap to existing Dupont SS to Whitepoint SS ckt 3. | In Service | Dupont SS | Whitepoint SS | In Service | 561 - 0729 | AEP TCC | Terry Weeks 918-599-2664 | 3435 | 2013-05-17 | 2013-05-17 | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8414, 8422, 8961, 80469 | Y | N |  |  | 3762 | 3553

## CancelledTPIT020114NoCost
PRIVILEGED AND CONFIDENTIAL, DO NOT release outside of ERCOT Staff or Transmission Providers organization. Contains critical cost information that can affect bids for projects.
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/01/2014
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
06TPIT0143 | Temple Switch - Temple SE 138 kV line | Upgrade existing 138 kV line |  | Temple Switch | Temple SE | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R448-E | 2024-05-15 |  | 138 | 0 | 4.4 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3415, 3612 | Y | N |  |  | 1346 | 1342
09TPIT0074 | Apollo-Jupiter-Lawler-College 69 kV lines reconductor | Apollo-Jupiter-Lawler-College 69 kV lines reconductor | On Hold For Funding | Switch 6612 at Apollo | Switch 6832 at College | Conceptual |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2014-12-30 |  | 69 | 0 | 5.5 | 0 |  | Dallas |  | Tier 4 |  |  |  | 800, 803, 806, 815 | Y | N |  | This project is a line reconductor for solving overload | 438 | 438
10TPIT0038 | College-Brand 138 kV line reconductor | College-Brand 138 kV line reconductor | On Hold For Funding | Switch 8832 at College | Switch 1364 at Brand | Conceptual |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2014-06-01 |  | 138 | 0 | 4.2 | 0 |  | Dallas |  | Tier 4 |  |  |  | 827, 829 | Y | N |  | This project is a line reconductor for solving overload | 984 | 983
10TPIT0095 | VH Braunig - Grandview 138kV Line Reroute | Reroute VH Braunig - Grandview to become VH Braunig - Coliseum Rd | Delayed due to Rail Road permit | VH Braunig | Grandview | Cancelled | S-0554 | CPS | Ulrich Skerhut UKSkerhut@cpsenergy.com 210-353-2923 | T-0130 | 2014-06-01 |  | 138 | 2.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5030, 5095, 5175 | Y | N |  | There are no transformers associated with this project | 1465 | 1464
12TPIT0014 | Laguna: Add 138-69 kV Auto | Construct new 138 kV line and add tranformation at Laguna to remove contingency overloads during off-peak maintenance | Cancelled | Laguna |  | Planned | 400 - 0648 | AEP TCC |  | 3307 | 2014-12-31 |  | 138 | 0 | 0 | 240 |  | Nueces |  | Tier 1 | 2009-03-24 | 2009-10-09 | 2009-12-01 | 8494, 80373, 80374 | Y | N |  |  | 1258 | 1255
12TPIT0015 | Barney Davis to Laguna, Construct 138 kV transmission line | Construct new 138 kV line and add tranformation at Laguna to remove contingency overloads during off-peak maintenance | Cancelled | Barney Davis | Laguna | Planned | 400 - 0648 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 3302 | 2014-12-31 |  | 138 | 4.2 | 0 | 0 |  | Nueces | Nueces | Tier 1 | 2009-03-26 | 2009-10-09 | 2009-12-01 | 8458, 80373 | Y | N |  |  | 1256 | 1253
13TPIT0107 | Bobville Switching Station | Construct 345-138 kV switching station in CNP's Roans Prairie to Kuykendahl line |  | Dobbin | Dobbin | planned | 13TPIT0107 15TPIT0022 16TPIT0016 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 11045 | 2018-06-02 |  | 345 | 0 | 0 | 700 |  | Montgomery |  | Tier 4 | 2010-10-04 | 2010-12-20 | 2011-05-05 | 40640, 40600, 45972, 40630, 3 | Y | Y |  |  | 1159 | 1156
13TPIT0107 | Bobville Switching Station | Construct 345-138 kV switching station in CNP's Roans Prairie to Kuykendahl line |  |  |  | planned | 13TPIT0107 15TPIT0022 16TPIT0016 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 11045 | 2018-06-02 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 4 | 2010-10-04 | 2010-12-20 | 2011-05-05 | 40640, 40600, 45972, 40630, 3 | Y |  |  |  | 3021 | 1156
14TPIT0022 | Sand Dollar 345 kV: Construct GIS 4 Breaker Ring Bus | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Sand Dollar |  | Planned | 495 - 0698 | AEP TCC | Glen Reed 918-599-2664 | 3388 | 2017-01-31 |  | 345 | 0 | 0 | 0 |  | Nueces |  | Tier 3 |  |  |  | 80388 | Y | N |  |  | 1249 | 1246
14TPIT0023 | Nopalito 345 kV: Construct 5 Breaker Ring Bus | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Napalito |  | Planned | 495 - 0698 | AEP TCC | Glen Reed 918-599-2664 | 3390 | 2018-01-31 |  | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 3 |  |  |  | 80382, 5915, 8455, 8956 | Y | N |  |  | 1250 | 1247
14TPIT0024 | Lon Hill to Sand Dollar 345 kV: Construct New 345 kV Transmi | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Lon Hill | Sand Dollar | Planned | 495 - 0698 | AEP TCC | Glen Reed 918-599-2664 | 3389 | 2017-01-31 |  | 345 | 11.5 | 0 | 0 |  | Nueces | Nueces | Tier 1 |  |  |  | 80388, 8455 | Y | N |  |  | 1251 | 1248
14TPIT0025 | Nopalito to Sand Dollar 345 kV: Construct New 345 kV Transmi | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Nopalito | Sand Dollar | Planned | 495 - 0698 | AEP TCC | Glen Reed 918-599-2664 | 3391 | 2018-01-31 |  | 345 | 14.5 | 0 | 0 |  | Nueces | San Patricio | Tier 2 |  |  |  | 80382, 80388 | Y | N |  |  | 1253 | 1250
14TPIT0026 | Sand Dollar to Las Brisas EC #1: Construct New 345 kV Line | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Sand Dollar | Las Brisas | Planned | 495 - 0698 | AEP TCC | Glen Reed 918-599-2664 | 3392 | 2017-01-31 |  | 345 | 2 | 0 | 0 |  | Nueces | Nueces | Tier 2 |  |  |  | 160792, 80388 | Y | N |  | Backfeed 13 months prior to commercial operation date | 1252 | 1249
15TPIT0003 | Sand Dollar to Las Brisas Energy Center #2 345 kV: Construct | Construct new Sand Dollar 345 kV station for direct interconnections with Las Brisas Energy Center. Construct 345 kV lines connecting Sand Dollar to existing Lon Hill and new Napalito 345 kV stations. |  | Sand Dollar | Las Brisas | Planned | 495 - 0698 | AEP TCC | Glen Reed 918-599-2664 | 3393 | 2018-01-31 |  | 345 | 2 | 0 | 0 |  | Nueces | Nueces | Tier 2 |  |  |  | 160794, 80388 | Y | N |  | Backfeed 13 months prior to commercial operation date | 1254 | 1251
3506 | Sinton to Skidmore: Rebuild 69kV Line | Rebuild Sinton to Skidmore 69kV Line for future 138 kV operation | CHANGES | SINTON | SKIDMORE | UNDER CONSTRUCTION | 579-0737 | AEP TCC | FRANK PRITZLAFF gareed@aep.com 918-599-2664 | TP2012071 | 2015-05-31 |  | 69 |  | 10.5 | 0 |  | San Patricio | Bee | Tier 3 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8405, 8413 | Y | N | NA | NA | 3713 | 3506

## RTPProjects
Project Number | Project Name | Transmission Owner | Proposed in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2013-R1 | East Munday 138/69-kV autotransformer upgrade | AEP/TNC | 2016 | Planned | 17TPIT0009
2013-R2 | Knox City – Gillespie – Munday 69-kV line upgrade | AEP/TNC | 2016 | Planned | 16TPIT0035; 17TPIT0007
2013-R3 | Paris 345/138-kV autotransformer upgrade | Oncor | 2018
2013-R4 | Upgrade Series Reactors at Centerville Road Switch | Oncor | 2016 | Conceptual | 15TPIT0081
2013-R5 | Coryell County – Sycamore 69-kV line upgrade | TNMP | 2018
2013-R6 | Reagan – Amelia – UT Southwest Medical Center 138-kV line upgrade | Oncor | 2016
2013-R7 | New 345/138-kV autotransformer at Lavon between Allen Switch and Royse Switch | Oncor | 2016 | Conceptual | 07TPIT0118
2013-R8 | Renner Switch – Allen Switch 345-kV line terminal equipment upgrade | Oncor | 2016
2013-R9 | Olsen 138/69-kV autotransformer upgrade | TNMP | 2014
2013-R10 | Handley SES – Randol Mill Tap West 138-kV line upgrade | Oncor | 2016
2013-R11 | Olsen – Lake Whitney 69-kV line upgrade | TNMP | 2014
2013-R12 | Northaven – Welch double circuit 138-kV line upgrade | Oncor | 2016 | Conceptual | 14TPIT0056
2013-R13 | Bosque Switch – Olsen 138-kV line terminal equipment upgrade | TNMP/BEPC | 2014
2013-R14 | Place 2nd Whitney 138/69-kV autotransformer into full-time operation | BEPC | 2016
2013-R15 | Renner Switch 345/138-kV autotransformer #1 upgrade | Oncor | 2016
2013-R16 | Trinidad – Tri Corner – Watermill 345-kV line upgrade | Oncor | 2014 | Conceptual | 07TPIT0140
2013-R17 | Forney – South Rockwall 138-kV line upgrade | Oncor | 2016 | Conceptual | 17TPIT0019
2013-R18 | Temple Switch – Belton 138-kV line upgrade | Oncor | 2016 | Conceptual | 17TPIT0028
2013-R19 | Trinidad – Powell 69-kV line upgrade | Oncor | 2018
2013-R20 | Trinidad – Seven Points 138-kV line and Trinidad – Montfort Switch 138-kV line upgrades | Oncor | 2016
2013-R21 | Terrell Switch – North Terrell Tap 138-kV upgrade | Oncor | 2016 | Conceptual | 13TPIT0061
2013-R22 | Mountain Creek – Norwood Switch 138-kV line upgrade | Oncor | 2014 | Conceptual | 14TPIT0012
2013-R23 | Oates – Garland Bobtown Tap 138-kV line upgrade | Oncor | 2016 | Conceptual | 07TPIT0138
2013-R24 | Eagle Mountain – Saginaw 138-kV line upgrade | Oncor | 2014 | Conceptual | 15TPIT0085
2013-R25 | Simpson Stuart – Witt Road 138-kV line upgrade | Oncor | 2016 | Conceptual | 16TPIT0064
2013-R26 | Sargent Road – Saint Augustine Tap 138-kV line upgrade | Oncor | 2016 | Conceptual | 19TPIT0001
2013-R27 | Record Crossing – UT Southwest Medical Center 138-kV line upgrade | Oncor | 2018 | Conceptual | 16TPIT0061
2013-R28 | Calmont 138/69-kV autotransformer upgrades | Oncor | 2016
2013-R29 | Northwest Carrollton East – Lake Pointe 138-kV line upgrade | Oncor/TNMP/BEPC | 2014
2013-R30 | Eddy – Troy 69-kV line upgrade | Oncor | 2016 | Conceptual | 16TPIT0045
2013-R31 | Highlands TNP – West TNP 138-kV line terminal equipment upgrade | TNMP | 2016
2013-R32 | Walnut Springs 69-kV bus capacitor bank upgrade | TNMP | 2016
2013-R33 | Belton – Belton Southwest 138-kV terminal equipment upgrade | Oncor | 2016
2013-R34 | Big Brown – Navarro 345-kV double circuit upgrade | Oncor | 2014
2013-R35 | Navarro – Hubbard 138-kV line upgrade | Oncor | 2016
2013-R36 | Firewheel – Wylie Switch 138-kV line upgrade | Garland | 2016
2013-R37 | Gatesville Switch – Gatesville Army 69-kV line upgrade | Oncor | 2016 | Conceptual | 09TPIT0116
2013-R38 | Cedar Crest Switch 138-kV bus tie upgrade | Oncor | 2016
2013-R39 | Tradinghouse – Sam Switch 345-kV double circuit upgrade | Oncor | 2016
2013-R40 | Industrial Blvd – Cedar Crest Switch 138-kV line upgrade | Oncor | 2016 | Conceptual | 13TPIT0059
2013-R41 | Elizabeth Creek 138-kV capacitor bank addition | Oncor | 2018
2013-R42 | Elm Mott – Bosque Switch 138-kV line upgrade | Oncor | 2016
2013-R43 | Jack County Substation 345/138-kV autotransformer addition | BEPC | 2016 | Planned | 13TPIT0104
2013-R44 | Norwood Switch – Cedar Hill Switch 345-kV line upgrade | Oncor | 2016
2013-R45 | Norwood Switch 345/138-kV autotransformer #1 upgrade | Oncor | 2016 | Conceptual | 11TPIT0097
2013-R46 | Buntin Drive – Simpson Stuart 138-kV line upgrade | Oncor | 2016
2013-R47 | Killeen Switch – Salado Switch 345-kV double circuit upgrade | Oncor | 2016
2013-R48 | Royse Switch – Shamburger Switch 345-kV line upgrade | Oncor | 2018
2013-R49 | Montfort Switch – Ennis Pump Tap and Trinidad – Goodloe Switch 138-kV line upgrades | Oncor | 2016
2013-R50 | Venus Switch – Chaparral Steel Tap 138-kV line upgrade | Oncor | 2016 | Conceptual | 16TPIT0068
2013-R51 | Lake Creek – Tradinghouse 345-kV line upgrades | Oncor | 2016
2013-R52 | Cedar Hill Switch – Watermill Switch 345-kV line upgrade | Oncor | 2018
2013-R53 | Medill Termination – East Network 138-kV line upgrade | Oncor | 2018
2013-R54 | Cedar Hill 138-kV terminal equipment upgrade | Oncor | 2016
2013-R55 | Temple Pecan Creek – Temple Switch 345-kV line upgrade | Oncor | 2018
2013-R56 | Industrial Blvd 138-kV bus tie upgrade | Oncor | 2016
2013-R57 | Series Reactor SPS on Norwood Switch 345/138-kV autotransformer #1 | Oncor | 2016
2013-R58 | Venus Switch – Navarro 345-kV double circuit line upgrade | Oncor | 2018
2013-R59 | Dickinson – League City 138-kV line upgrade | TNMP | 2016
2013-R60 | Dickinson – Freeway Park 138-kV line terminal equipment upgrade | TNMP | 2018
2013-R61 | Roans Prairie – King 345-kV line looped into Rothwood 345-kV substation | CNP | 2016
2013-R62 | Katy Area upgrades | CNP | 2018
2013-R63 | Houston Import Project |  | 2018
2013-R64 | T H Wharton to Addicks 345-kV line upgrade | CNP | 2018
2013-R65 | South Shore – Hidden Lakes 138-kV line upgrade | TNMP | 2018
2013-R66 | Tyler Northwest upgrades | Oncor | 2016 | Conceptual | 15TPIT0078; 15TPIT0095
2013-R67 | Dialville – Palestine South 138-kV line upgrade | Oncor | 2018 | Conceptual | 16TPIT0054
2013-R68 | Trinidad – Richland 345-kV line upgrade | Oncor | 2016
2013-R69 | Series Reactor SPS on Big Brown – Jewett 345-kV double circuit and Rattlesnake Rd Switch – Lake Creek 345-kV terminal equipment upgrade | Oncor | 2016
2013-R70 | Midland Area Upgrades | Oncor/Sharyland | 2016
2013-R71 | Midland West – Windwood – Midland East 138-kV line upgrade | Oncor | 2014 | Conceptual | 14TPIT0011
2013-R72 | Westover – Amoco South Foster – Odessa North 138-kV line upgrade | Oncor | 2014 | Conceptual | 15TPIT0092
2013-R73 | Glenhaven – CRMWD 8 Tap – Midland Airport 138-kV line upgrade | Oncor | 2014 | Conceptual | 15TPIT0091
2013-R74 | Wink SS – TN Wink 69-kV line terminal equipment upgrade | TNMP | 2014
2013-R75 | IH 20 – Pecos 69-kV line terminal equipment upgrade | TNMP | 2014
2013-R76 | Uvalde 138/69-kV autotransformer upgrade | AEP/TCC | 2014
2013-R77 | Morgan Creek 138/69-kV autotransformer upgrade | Oncor | 2016 | Conceptual | 3456
2013-R78 | Ferguson – Sandy Creek 138-kV line upgrade | LCRA | 2018
2013-R79 | Lockhart – Magnolia – Luling voltage conversion from 69-kV to 138-kV | LCRA | 2016
2013-R80 | Round Rock – Chief Brady – Georgetown 138-kV line upgrade | LCRA | 2016
2013-R81 | Fayette – Frelsburg – Mocking Bird – Glidden 138-kV line upgrade | LCRA | 2018
2013-R82 | CPS Northeast Switchyard | CPS/LCRA | 2014
2013-R83 | Zorn – York Creek – Seguin 138-kV line upgrade | LCRA | 2016
2013-R84 | Plum – Flatonia 138-kV line upgrade | LCRA | 2018 | Planned | 14TPIT0125
2013-R85 | Howard – Somerset 138-kV line upgrade | CPS | 2018
2013-R86 | Series reactor SPS at Pawnee Switching Station | CPS/STEC | 2018
2013-R87 | Cross Valley Project tap at South McAllen | AEP | 2014
2013-R88 | New 138-kV line from Escondido to West Batesville | AEP | 2014 | Conceptual | 10TPIT0028
2013-R89 | Pleasanton 138/69-kV autotransformer upgrade | AEP | 2016
2013-R90 | Lobo – Freer – San Diego 69-kV line upgrade | AEP | 2014
2013-R91 | Stewart 138/69-kV autotransformer upgrade, Steward – Rio Rico and La Palma – Rangerville 69-kV line upgrades | AEP | 2016
2013-R92 | George West 138/69-kV transformer upgrade | STEC | 2018
2013-R93 | San Miguel Tap – N. Calliham 69-kV line upgrade | STEC | 2016
2013-R94 | Victoria – Fannin 69-kV line upgrade | AEP | 2014
2013-R95 | Calallen – Robstown 69-kV line upgrade | STEC | 2018
2013-R96 | Mathis – Sandia 69-kV line upgrade | STEC | 2018
2013-R97 | Pearsall – Paloduro 138-kV line upgrade | STEC | 2018
2013-R98 | Duke – Azteca 138-kV line upgrade | AEP | 2014
2013-R99 | Gonzales area 69-kV line upgrade | TGVEC | 2018
2013-R100 | Lobo 345/138-kV second autotransformer | AEP | 2016
2013-R101 | Three Rivers 138/69-kV autotransformer upgrade | AEP | 2018
2013-R102 | San Miguel – Choke Canyon – Sigmor 138-kV line upgrade | STEC | 2018
2013-R103 | Fowlerton 345/138-kV autotransformer addition | STEC | 2014
2013-R104 | Bevo – Carrizo 69-kV line addition | STEC | 2014
2013-E1 | Add Series Reactor on the Nueces Bay - Morris 138 kV line | AEP/TCC | 2016

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Bob Healey; Veronica Billings | bhealey@aep.com; vbillings@aep.com | Bob Healey: 918 599 2249; Veronica Billings: 918 599 2945 | Glen Reed; David Kidd; Brad Myers; Mabel See; Mike Forcum; Doug Lee; Daniel Lyons; Bob Lager; Mina Turner; Lisa Kelso; Carole Myser | gareed@aep.com; dekidd@aep.com; blmyers@aep.com; msee@aep.com; mlforcum@aep.com; dnlyons@aep.com; dlee@aep.com; rjlager@aep.com; myturner@aep.com; lokelso@aep.com; camyser@aep.com | David Kidd: 918 599 2637 Glen Reed: 918 599 2664 Brad Myers: 918 599 2690
AUSTIN ENERGY | Primary & Secondary | Biju Mathew | biju.mathew@austinenergy.com; | Biju: 512 322 6737 | Armke, James; Mathew, Biju; Ebrahimian, Reza; Hunt, Dandy; Ron Krautz; Brion Ryan | James.Armke@austinenergy.com; biju.mathew@austinenergy.com; reza.ebrahimian@austinenergy.com; dandy.hunt@austinenergy.com; ron.krautz@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | James:512 322 6705 Biju:512 322 6381 Reza:512 322 6740 Dandy:512 322 6748 Ron:512 322 6835 Brion: 512-322-6879
Bandera Electric | Primary | David Baker | d.baker@banderaelectric.com | David: 830-796-6084
BPUB | Primary | Ramon Sanz | rsanz@brownsville-pub.com; | Ramon: 956 983 6203 | James McCann | jmccann@brownsville-pub.com; | James: 956 983 6204
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Dwight Beckman | dbeckman@brazoselectric.com | Dwight: 254 750 6373 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | James Tanneberger | jtanneberger@btutilities.com | James: 979 821 5763 | Shawndra Green | sgreen@btutilities.com | Shawndra: 979 821 5744
CNP | Primary & Secondary | Wayne Kemper | wayne.kemper@centerpointenergy.com | Wayne: 713 207 2192 | Wesley Woitt; Cody Mann; Roy Palacios | wesley.woitt@centerpointenergy.com; Roy.Palacios@centerpointenergy.com cody.mann@centerpointenergy.com; | Wesley Woitt: 713-207-2760 Cody Mann: 713-207-3149
COCS | Primary | Tony Michalsky | tmichalsky@cstx.gov; | Tony: 979 764 3438 | Timothy Crabb; Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | Basileo Rocha, Mario De La Garza | bdrocha@cpsenergy.com; MADelagarza1@CPSEnergy.com | Basileo: 210 353 4933; Mario: 210 353 6312 | Kenneth Bowen Blake Williams | kbowen@cpsenergy.com; bawilliams@cpsenergy.com; | Kenneth: 210 353 4142 Blake: 210 353 3557
CTT (Cross Texas Transmission) | Primary & Secondary | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310 | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310
DENTON | Primary & Secondary | Chuck Sears | Chuck.Sears@cityofdenton.com; | Chuck: 940 349 7111 | Brent Heath | brent.heath@cityofdenton.com; | Brent: 940 349 7180
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@garlandpower-light.org | Danh: 972 205 3826 | Grubbs, David; Fred Sherman; Steve Zaragoza | Dgrubbs@garlandpower-light.org; FredS@gplops.org; stevez@gplops.org | David: 972 205 2664 Fred: 972 205 3184 Steve: 972-205-3098
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; PEC; SBEC; GVEC; City of Georgetown; BBEC,CTEC, NBU | Primary & Secondary | Charles DeWitt | Charles.dewitt@lcra.org | Charlie: 512-578-4199 | Sergio Garza, Cris Urena, Ken Chui | sergio.garza@lcra.org; cris.urena@lcra.org; ken.chui@lcra.org | Sergio: 512 578 4149 Cris: 512 578 4525 Ken: 512 578 4510
Lone Star | Primary & Secondary | Don Le | don.le@lonestar-transmission.com | Don - 512-236-3144 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Mike Juricek | Michael.Juricek@oncor.com; | Mike: 214 743 6671 | Jim Painter | jpainte1@oncor.com | Jim: 214 743 6779
Sharyland Utilities | Primary & Secondary | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243 | Michael Glass, Dwight Yarbrough, Miguel Alvarado | mglass@sharyland.com; dyarbrough@sharyland.com; malvarado@sharyland.com | Michael: (956) 687-5600, Dwight: (432) 684-0321, Miguel: (214) 855-6103
STEC | Primary & Secondary | Doug Evans | devans@stec.org | Doug: 361 485 6459 | Dotty DiSanto Loretta Gallaga | dottyd@stec.org; lgallaga@stec.org; | Dotty: 361 645 6146 Loretta: 956 377 7120
TMPA | Primary & Secondary | Ahmad Saboor | asaboor@texasmpa.org | Ahmad: 936 873 1104 | Frank Owens | fowens@texasmpa.org; | Frank: 936 873 1120
TNMP | Primary & Secondary | Robert Lona | Robert.Lona@tnmp.com | Robert: 281-581-4732 | Anthony, Hudson Ballay, Dustin Cloninger, Ross | Anthony.Hudson@tnmp.com; Dustin.Ballay@tnmp.com; Ross.Cloninger@tnmp.com; | Anthony: 281 581 4712 Dustin:281 581 4730 Ross:281 581 4733
Wind Energy Texas Transmission (WETT) | Primary | Julius Horvath | julius.horvath@windenergyoftexas.com | Julius: 512 436 9585; cell: 512 496 9186 | Christina Eckhoff | christina.eckhoff@windenergyoftexas.com | Christina: Christina: 512 279 7371