## ImprovementCostSummary01242023
| Project Cost |  |  |  |  | XFMR MVA
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total
2022 | 251109000 | 1002242243 | 297847000 | 1551198243 | 2022 | 2072 | 331 | 0 | 2403 | For ROS and BOD Reports
2023 | 976867000 | 2453644460 | 753277000 | 4183788460 | 2023 | 7610 | 712 | -120 | 8202 | ·All Projects (in engineering, routing, licensing and construction): |  |  |  | 11643077896
2024 | 895549000 | 1992065000 | 758993000 | 3646607000 | 2024 | 4800 | 468.8 | 0 | 5268.8 | ·Transmission Projects Energized in 2023: |  |  |  | 149073000
2025 | 504500000 | 730113000 | 223838000 | 1458451000 | 2025 | 3600 | 1376 | 0 | 4976
2026 | 853950000 | 171573000 | 221400000 | 1246923000 | 2026 | 600 | 0 | 200 | 800
2027 | 1058016436 | 21270000 | 56150000 | 1135436436 | 2027 | 600 | 0 | 0 | 600
2028 | 0 | 55900000 | 3100000 | 59000000 | 2028 | 0 | 0 | 0 | 0
2029+ | 0 | 57745000 | 4200000 | 61945000 | 2029+ | 0 | 0 | 0 | 0
2023COM | 44400000 | 86081000 | 18592000 | 149073000 | 2023COM | 1200 | 0 | 0 | 1200
2023PLAN | 932467000 | 2367563460 | 734685000 | 4034715460 | 2023PLAN | 6410 | 712 | -120 | 7002
2022-2029+ | 4539991436 | 6484552703 | 2318805000 | 13343349139 | 2022-2029+ | 19282 | 2887.8 | 80 | 22249.8
2022-2023 | 1227976000 | 3455886703 | 1051124000 | 5734986703 | 2022-2023 | 9682 | 1043 | -120 | 10605
2024-2029+ | 3312015436 | 3028666000 | 1267681000 | 7608362436 | 2024-2029+ | 9600 | 1844.8 | 200 | 11644.8
| Circuit Miles New |  |  |  | Circuit Miles Rebuilt, Reconductored or Upgraded |  |  |  |  | Total
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total | 345 | 138 | 69 | Total
2022 | 45.9 | 54.193 | 0 | 100.093 | 2022 | 27 | 242.843 | 161.35 | 431.193 | 72.9 | 297.036 | 161.35 | 531.286
2023 | 317.54 | 139.51 | 23.3 | 480.35 | 2023 | 5.23 | 743.471 | 281.23 | 1029.931 | 322.77 | 882.981 | 304.53 | 1510.281
2024 | 97.8 | 102.49 | 8 | 208.29 | 2024 | 36.82 | 805.808 | 473.28 | 1315.908 | 134.62 | 908.298 | 481.28 | 1524.198
2025 | 13.1 | 28.95 | 0 | 42.05 | 2025 | 108 | 233.22 | 125.361 | 466.581 | 121.1 | 262.17 | 125.361 | 508.631
2026 | 217.5 | 21.4 | 20.5 | 259.4 | 2026 | 243.9 | 37.52 | 91.95 | 373.37 | 461.4 | 58.92 | 112.45 | 632.77
2027 | 429.6 | 5.22 | 13.1 | 447.92 | 2027 | 11.2 | 17.4 | 32.7 | 61.3 | 440.8 | 22.62 | 45.8 | 509.22
2028 | 0 | 18.2 | 0 | 18.2 | 2028 | 0 | 4 | 6.26 | 10.26 | 0 | 22.2 | 6.26 | 28.46
2029+ | 0 | 13.7 | 0 | 13.7 | 2029+ | 0 | 30.35 | 2 | 32.35 | 0 | 44.05 | 2 | 46.05
2023COM | 0 | 8.66 | 0 | 8.66 | 2023COM | 0 | 2.831 | 1.9 | 4.731 | 0 | 11.491 | 1.9 | 13.391
2023PLAN | 317.54 | 130.85 | 23.3 | 471.69 | 2023PLAN | 5.23 | 740.64 | 279.33 | 1025.2 | 322.77 | 871.49 | 302.63 | 1496.89
2022-2029+ | 1121.44 | 383.663 | 64.9 | 1570.003 | 2022-2029+ | 432.15 | 2114.612 | 1174.131 | 3720.893 | 1553.59 | 2498.275 | 1239.031 | 5290.896
2022-2023 | 363.44 | 193.703 | 23.3 | 580.443 | 2022-2023 | 32.23 | 986.314 | 442.58 | 1461.124
2024-2029+ | 758 | 189.96 | 41.6 | 989.56 | 2024-2029+ | 399.92 | 1128.298 | 731.551 | 2259.769

## FutureTPIT020123NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2023
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
45174 | Ollin to LCRA Crane: Partial Build, Partial Rebuild, and Conversion | Build new Ollin 138 kV station; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage |  | Ollin | LCRA Crane | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2767 | 2023-02-02 01:00 |  | 138 | 0.52 | 0 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6600, 6605, 6606, 6669, 60428, 60429, 60431, 60432, 60441, 6610, 6613, 6668, 76615 | Y | N |  | 0 | 65527 | 45174
51996 | Rebuild Markham Tap to AEP Markham Tap | Rebuild Markham Tap to AEP Markham Tap with 138 kV capable structures |  | Markham Tap | AEP MarkhamTap | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-02-15 |  | 69 | 0 | 1.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5557, 8984 | Y | N |  | 0 | 51997 | 51996
59518 | upgrade the Desoto-Sterrett 138 kV Line | upgrade the existing Desoto-Sterrett 138 kV Line |  | Desoto | Sterrett | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4122 | 2023-02-15 |  | 138 | 0 | 8.3 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  |  | 217, 2317, 2424 | Y |  |  | 0 | 59519 | 59518
59763 | Construct three terminal 138 kV capable switching station | Change Markham hard wire tap point to 3 way switching station |  | Cayce Switch |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-02-15 |  | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5554, 5557, 5555, 5556, 8984 | Y | N |  | 0 | 65899 | 59763
3505 | Cibolo Substation, T3 transformer addition | Add T3, 40 MVA 138-26.18 kV power transformer, CSW and low side |  | Cibolo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-02-24 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7608 | Y | N |  |  | 10887 | 3505
4146 | Hillje 345kV Substation Expansion for Juanita Hill Solar - (21INR0480) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Juanita Hill Solar |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-02-28 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 11666 | 4146
49546 | Resnik: Construct New 138 kV Station | Resnik: Construct New 138 kV Station |  | Resnik |  | Under Construction | 996 - 1174 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 3749 | 2023-02-28 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8580, 8422, 8565, 80470 | Y | N |  | 0 | 49547 | 49546
50872 | Structure 25/7 - Medio Creek: Rebuild 138 kV Line | Rehab Structure 25/7 to Medio Creek 138 kV Line | Project Title, Project Description, Contact, Schedule, Date Sumbitted, Date RPG Review Update | Haisley | Medio Creek | Under Construction |  | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | TA2018060 | 2023-02-28 |  | 138 | 0 | 14.9 | 0 |  | San Patricio | Refugio | Tier 3 | 19RPG014 | 2019-08-13 | 2019-10-07 |  | 8912, 8920 | Y | N |  | 0 | 65546 | 50872
61264B | Marshall Ford to Trading Post Storm Hardening | Phase 1: Reconductor segment of T323 Marshall Ford to Paleface and T315 Marshall Ford to Trading Post that is double circuit using Galveston ACCC conductor. |  | Marshall Ford | Trading Post | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2023-02-28 |  | 138 | 0 | 3.6 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7477, 77356 | Y | N |  | 0 | 63792 | 61264
63633 | Tribute: Build 138 kV Temorary Tap | Build new 138 kV temporary tap on the San Angelo Power to Red Creek 138 kV line | Schedule Update | Tribute |  | Under Construction | 1131 - 1309 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1876 | 2023-02-28 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 60008, 6442, 6473 | Y | N |  | 0 | 63634 | 63633
63900 | Nebula: Build New 345 kV Station | Interconnect Andromeda Solar on the Dermott to Figaro 345 kV Line |  | Nebula |  | Planned | 1135 - 1313 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 1880 | 2023-02-28 |  | 345 | 0 | 0 | 0 |  | Scurry |  | Tier 4 |  |  |  |  | 60011, 11305, 60715 | Y | N |  | 0 | 63901 | 63900
65652 | Interconnects Tarbush Data Canter |  |  | TNMP Tarbush (bus # 38295) | Customer substation (bus # 38296) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-02-28 |  | 138 | 0 | 0 | 0 | 0,160 | Pecos | Pecos | Tier 4 |  |  |  |  | 38296, 38295 | Y |  |  | 0 | 65653 | 65652
66292 | Salvare: Build 345 kV station | Interconnect Iris Energy on the Jim Treece to Tesla 345 kV line | Project Description, Transmission Status, Contact Update | Salvare | Iris Data | Under Construction |  | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-02-28 |  | 345 | 0.01 | 0 | 0 |  | Childress | Childress | Tier 4 |  |  |  |  | 60510, 60511, 60504, 61001 | Y | N |  | 0 | 66293 | 66292
68252 | Lobo: Update settings | Connect Guajillo to the Lobo 345 kV station |  | Lobo |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-02-28 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219, 163223 | Y |  |  | 0 | 68253 | 68252
68266 | Dry Frio: Build new 138 kV station | Interconnect Sunray Solar to the Dry Frio 138 kV station |  | Dry Frio |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-02-28 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 4 |  |  |  |  | 8707, 8234, 8241 | Y |  |  | 0 | 68267 | 68266
48814 | Albany Foundry to Fort Griffin: Rebuild 69 kV line | Rehab 69 kV line from Albany Foundry to Fort Griffin, build new Salt Prong station, install capacitor banks at Albany Foundry | Project Description, Schedule Update | Albany Foundry | Fort Griffin | Planned | 1014 - 1192 | AEP TNC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 | 2775 | 2023-02-28 01:00 |  | 69 | 0 | 4.66 | 0 |  | Shackelford | Shackelford | Tier 4 |  |  |  |  | 6208, 6213, 60445, 6202, 6212, 6214, 60398 | Y | N |  | 0 | 48815 | 48814
49574 | Tesla: Build 345 kV terminal | Interconnect Misae II solar farm at Tesla | Contact Update | Tesla |  | Planned | 1023 - 1201 | ETT | Raza Ansari mlforcum@aep.com 918-599-2674 | 2785 | 2023-03-01 |  | 345 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501 | Y | N |  | 0 | 49575 | 49574
54084 | King Mountain Sub Upgrade | Provide transmission service to a generator. Add a 138-kV bay and associated circuit breaker to the existing substation. ERCOT (ERCOT Generation Interconnection or Change Request No. 20INR0226) |  | King Mountain Sub | King Mountain Sub | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-03-01 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 76635 | Y | N |  | 0 | 54085 | 54084
57343 | Rosita Creek Substation 138-kV T2 Power Transformer Addition | Add second 138/13.09-kV power transformer bay with new 138-kV transmission switch and circuit switcher interconnected at LCRA Switch# 12669. New power transformer capacity will be 15/20/25 MVA. | Recent projected load increases beyond ALDR. Justification is to provide on-site backup power source for new and existing critical medical center, governmental and educational facility loads. Power transformer lead-time increases. | Pueblo | Escondido | Planned |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2023-03-01 |  | 138 | 0 | 0 | 0 |  | Maverick | Maverick | Tier 4 | [5 empty] | Y | N |  | 0 | 57344 | 57343
58542B | CATTAIL_SUBSTATION | 1) Cat Tail to Cherokee 138kv line |  | Cherokee (39075) | Cat Tail ( 38580 ) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-03-01 |  | 138 | 1.5 | 0 | 0 |  | Galveston | Galveston | Tier 2 |  | 2020-04-16 | 2020-09-16 |  | 38580, 39075 | Y |  |  | 0 | 71934 | 58542
68673 | Reconductor TNMP Wink-Oncor Wink Ckt 2 |  |  | TNMP WInk (37900) | Oncor Wink (1074) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-03-01 |  | 138 | 0 | 1.18 | 0 |  | Winkler | Winkler | Tier 4 |  |  |  |  | 1074, 37900 | Y |  |  | 0 | 68674 | 68673
50878 | North Edinburg: 345 kV Reconfigure | North Edinburg: 345 kV Reconfigure |  | North Edinburg |  | Planned | 1056 - 1229 | AEP TCC | Rich Haley bcogan@aep.com 918-599-2857 | 3786 | 2023-03-10 |  | 345 | 0 | 0 | 0 | -100,0 | Hidalgo |  | Tier 4 |  |  |  |  | 8341, 8383 | Y | N |  | 0 | 50879 | 50878
61398 | Whitepoint 138 kV Station: Upgrade Pelican Terminal | Whitepoint 138 kV Station: Upgrade Pelican Terminal |  | Pelican | Whitepoint | Planned |  | AEP TCC | Brandon Cogan 918-599-2857 bcogan@aep.com | TP2020040 | 2023-03-14 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 | 19RPG0016 |  |  |  | 8961, 80259 | Y |  |  | 0 | 61399 | 61398
7124 | Flat Iron - Barr Ranch - Pegasus South 138 kV Line | Construct new Flat Iron - Barr Ranch - Pegasus South 138 kV Line and Barr Ranch 138 kV Switch |  | Flat Iron | Pegasus South | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8574 | 2023-03-15 |  | 138 | 18 | 0 | 0 | 0,55.2 | Midland | Midland | Tier 2 | 21RPG010 | 2021-06-02 | 2021-06-23 | 2021-12-13 | 11235, 1237, 11217 | Y |  |  | 0 | 62668 | 7124
59265 | Hurst - International Airport 138 kV Double-Circuit Line Section | Upgrade existing 138 kV Line |  | Hurst | International Airport | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5216 | 2023-03-15 |  | 138 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 2115, 2116, 2117, 2121, 2125, 2243, 2244 | Y |  |  | 0 | 59266 | 59265
14TPIT0010 | Handley - Sherry 138 kV line | Upgrade existing line |  | Handley | Sherry | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5155-E | 2023-03-15 12:00 |  | 138 | 0 | 8.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1919, 1920, 1950, 1951, 2245, 2247, 2251, 2252 | Y | N |  | 0 | 59262 | 2582
59093 | Starr Solar Connection | Starr Solar Connection | Contact, Schedule Update | Roma Tap |  | Under Construction |  | AEP TCC | William Lovelace bcogan@aep.com 918-599-2857 | TP2020209 | 2023-03-16 |  | 138 | 0.1 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 88795, 8795 | Y |  |  | 0 | 59094 | 59093
59095 | Athey: Build 138 kV Temporary Hard Tap | Build new 138 kV temporary tap on the Ft Stockton to Rio Pecos 138 kV line | Contact Update | Athey |  | Planned | 1123 - 1301 | AEP TNC | Shawn Ketcher mlforcum@aep.com 918-599-2674 | 1868 | 2023-03-16 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60792, 60718, 60798 | Y | N |  | 0 | 59096 | 59095
60625 | AEN_22TPIT60625_DECKER_BUS_TIE_CLOSE | Close the Decker 138 kV bus tie |  | 9187 | 9188 |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2023-03-21 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 | [5 empty] | Y | N |  | 0 | 60626 | 60625
61264A | Marshall Ford to Trading Post Storm Hardening | Phase 2: Rebuild single circuit section of Marshall Ford to Trading Post (T315) and reconductor with bundled 795 ACSR Conductor, 440 MVA; Reconductor segment of T323 Marshall Ford to Paleface that is double circuited with T315 using Cardinal ACCC conductor. |  | Marshall Ford | Trading Post | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2023-03-22 |  | 138 | 0 | 4.1 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7356, 7505 | Y | N |  | 0 | 61265 | 61264
68970 | ETT 2nd Ckt: Expand 345 kV stations | Construct new terminals at Cenizo, Del Sol, Lobo, and Pomelo for the ETT 2nd circuits project |  | Cenizo | Del Sol | Planned |  | ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021704 | 2023-03-23 |  | 345 | 0 | 0 | 0 |  | Webb | Starr | Tier 1 |  |  |  |  | 80219, 80220, 80335 | Y | Y |  | 0 | 68971 | 68970
68179 | North Edinburg Red Gate | North Edinburg: Install 3 - 138 kV breakers. Re-terminate Falfurrias 138 kV Line. Terminate Redgate (STEC) 138 kV Line. |  | North Edinburg | Redgate (STEC) | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-03-27 |  | 138 | 0.08 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8380, 88380 | Y |  |  | 0 | 68180 | 68179
66011A | CNP ARCHER POI for BROTMAN Power | CNP ARCHER POI for BROTMAN Power |  | ARCHER | Rosharon/MANVEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-29 12:00 |  | 138 | 0.66 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44600, 44410, 112969 | Y | N |  | 0 | 66012 | 66011
6373 | Hamilton Road to Picacho ckt #2 | Rebuild Hamilton Road to Picacho 138 kV line ckt #2 |  | Hamilton Road | Picacho | Planned | 870-1051 | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | 3660 | 2023-03-30 |  | 138 | 0 | 8.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8186, 8255, 8690, 8688, 8684 | Y | N |  | 0 | 65505 | 6373
66011B | CNP ARCHER POI for BROTMAN Power | Upgrade Ckt.26 Rosharon to ARCHER to increase thermal limits. |  | ARCHER | Rosharon/MANVEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-30 12:00 |  | 138 | 1.28 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44600 | Y | N |  | 0 | 66015 | 66011
66011C | CNP ARCHER POI for BROTMAN Power | Upgrade Ckt 26 Angleton to WINMIL to increase thermal limits |  | Angleton | WINMIL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-30 12:01 |  | 138 | 1.15 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 44531 | Y | N |  | 0 | 66016 | 66011
43460 | Moody to Stewart Ckt.63 Upgrades P1016 | Upgrade Ckt.63 Moody to Stewart as a Hardening project |  | Moody | Stewart | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-31 |  | 138 | 0 | 3.81 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42951, 42953, 43290, 43355, 42950, 43520, 43521 | Y |  |  | 0 | 43461 | 43460
50440 | Delhi Substation Addition | Add a new load serving substation 10 miles north of IH-10 along 304, w/30 MVA PWT. |  | Delhi | Delhi | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-03-31 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7896 | Y | N |  | 0 | 50441 | 50440
55217 | Putnam to Leon: Rebuild 138 kV line | Rehab Putnam to Leon 138 kV line |  | Putnam | Leon | Planned | 1042 - 1269 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1859 | 2023-03-31 |  | 138 | 0 | 20.81 | 0 |  | Callahan | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | N |  | 0 | 55218 | 55217
57549A | Garden Villas 138kV Load Conversion | Reposition existing Garden Villas dual-voltage transformers TR1/TR2. Reposition one of the transformers with Ckt.06G Garden Villas to Drouet and rename transformer as TR4. |  | Garden Villas | Drouet | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42684, 42680, 42690, 42550 | Y | N |  | 0 | 61867 | 57549
57549B | Garden Villas 138kV Load Conversion | Reposition existing Garden Villas dual-voltage transformers TR1/TR2. Reposition one of the transformers with Ckt.07A Garden Villas to Chocolate Bayou tap and rename transformer as TR3. |  | Garden Villas | Chocolate Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42681, 42683, 42690, 42042, 42680 | Y | N |  | Cost included in main project | 61868 | 57549
57645 | Hillje 345kV Danish Fields Solar (21INR0069) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Danish Fields Solar |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 57646 | 57645
63964 | Bronco: Build new 69 kV Terminal | Interconnect House Mountain BESS to the Bronco 69 kV Station |  | Bronco |  | Planned | 1140 - 1318 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1885 | 2023-03-31 |  | 69 | 0 | 0 | 0 |  | Brewster |  | Tier 4 | [5 empty] | Y | N |  | 0 | 63965 | 63964
67173 | GPLTMPA_67173_AddsLookoutSTATCOM | Garland adds +/-120MVAr Lookout STATCOM for serving local voltage problems |  | Lookout | Lookout | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2023-03-31 |  | 138 | 0 | 0 | 120 | -120120 | Dallas | Dallas | Tier 4 |  |  |  |  | 846, 847, 857, 828 | Y | N |  | 0 | 67174 | 67173
51734 | Blue Stem to Delhi Transmission Line | Build new 9.5 mile 138/69 kV transmission. |  | BlueStem | Delhi | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-03-31 02:00 |  | 69 | 9.5 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7895, 7230, 7231, 7896 | Y | N |  | 0 | 51843 | 51734
69481 | Resaca: Install Cap Bank | Resaca Capacitor |  | Resaca |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-04-01 |  | 69 | 0 | 0 | 0 | 0,11.5 | Cameron |  | Tier 4 |  |  |  |  | 8626 | Y |  |  | 0 | 69482 | 69481
4487 | Nueces Area 69kV Reinforcement | Expand and add new 138/69kV Auto at Valero East 69kV substation. Add 5th breaker to Champlin 138kV substation. Construct Champlin to Valero East 138kV Line. |  | Champlin | Valero East | Planned | 709 - 0879 | AEP TCC | John Pulay mlforcum@aep.com 918-599-2857 | 2903 TP2016067 | 2023-04-01 01:00 |  | 138 | 1.6 | 0 | 200 |  | Nueces |  | Tier 4 | 19RPG011 |  |  |  | 8528, 8476, 8859 | Y | N |  |  | 13570 | 4487
4495 | Champlin: Station Reconfigure | Expand existing breaker configuration to a four (4) breaker ring bus expandable to a six (6) breaker ring bus configuration. |  | Champlin |  | Planned | 694 - 0864 | AEP TCC | John Pulay bcogan@aep.com 918-599-2857 | 3541 TP2014064 | 2023-04-02 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8476 | Y | N |  |  | 12064 | 4495
59452 | Air Liquide Pass Through 138 kV Station | Air Liquide to construct 138 kV Ring Bus |  | Dupont SW Ingleside |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020197 | 2023-04-15 |  | 138 | 0.01 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8978, 8979, 8422, 8818 | Y | Y |  | 0 | 59453 | 59452
61262A | Hunter to McCarty Lane Storm Hardening | Rebuild single-circuit section of Hunter to McCarty Lane 138 kV with single, circuit bundled 795 ACSR Conductor, 440 MVA. |  | McCarty Lane | Hunter | Planned |  | PEC/LCRATSC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2023-04-22 |  | 138 | 0 | 1.57 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7491 | Y | N |  | 0 | 61263 | 61262
5621 | South McAllen-Bentsen and North Edinburg-West Edinburg 138 kV Station Upgrades | 138 kV Upgrades at North Edinburg and South McAllen |  | North Edinburg | North McAllen | Planned | 795 - 0980 | AEP TCC | Michael Richardson bcogan@aep.com 918-599-2857 | 3585 | 2023-04-23 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8367, 8371, 8631, 79603 | Y | N |  |  | 13351 | 5621
66130 | North Shore Reactive Project | Install 57.6 Mvar Capacitor Banks at Hecker and Resnik 138 kV stations. |  | Hecker | Resnik | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021207 | 2023-04-23 |  | 138 | 0 | 0 | 0 | 0,69.2 | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 8580 | Y |  |  | 0 | 66131 | 66130
50446 | Santa Clara Substation Addition | Add a new load serving substation 10 miles west of City of Seguin, of IH-10, w/ twin 40 MVA PWTs. |  | Santa Clara Substation | Santa Clara Substation | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-04-28 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7891 | Y | N |  | 0 | 50447 | 50446
51736 | Cibolo to McQueeney Transmission Line | Install 10.62 miles of 1192 Bunting to existing transmission structures, circuit to help with load flows per the TPA and will be source for Santa Clara Substation. |  | Cibolo | McQueency | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-04-28 |  | 138 | 10.62 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7608, 7606 | Y | N |  | 0 | 51737 | 51736
51841 | Cibolo-McQueeney Tap to Santa Clara Transmission Line Addtition | Build 5 onmiles of new double circuit 138kV t-line loop, 1192 ACSR Bunting, from H-pole structure to Santa Clara Substation |  | H-pole ( Structure/Tap) | Santa Clara | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-04-28 |  | 69 | 10 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7890, 7892, 7606, 7608, 7891 | Y | N |  | 0 | 57331 | 51841
50847 | Sage: Expand 69 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line |  | Sage |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2799 | 2023-04-30 |  | 69 | 0 | 0 | 0 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-06-21 |  | 6604 | Y | N |  | 0 | 50848 | 50847
61865 | Muldoon Substation Addition | Provide transmission service to a generator. LCRA TSC will construct a new substation, Muldoon Substation, on T133 between LCRA TSC Flatonia and Plum Substations and more specifically between str #192 and str #197. The substation will be a three breaker ring bus configuration and will provide a 138-kV line termination for a 240 MW solar generation facility. |  | Muldoon Substation | Muldoon Substation | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-04-30 |  | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7279, 7248, 7274 | Y | N |  | 0 | 61866 | 61865
65987 | Install Gibbs to Jackalope Solar branch | Install Gibbs to Jackalope Solar branch |  | Gibbs |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021288 | 2023-04-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 88173, 8173 | Y |  |  | 0 | 65988 | 65987
66192 | Abilene NW: Build 138 kV terminal | Interconnect Lancium to the Abilene NW 138 kV station | Project Title, Project Description, Transmission Status, Contact Update | Abilene Northwest | Lancium | Under Construction |  | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 |  | 2023-04-30 |  | 138 | 0.2 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6476, 6228 | Y | N |  | 0 | 66193 | 66192
70188 | LCRATSC_ClearSprings_CB_Addition | Provide a transmission point of interconnection for a new Battery Energy Storage System at the Clear Springs Substation by adding an additional 138-kV double bus, double breaker bay to accommodate the new interconnection. Contingency Update |  | Clear Springs | Clear Springs | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-04-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 | [5 empty] | Y | Y |  | 0 | 70189 | 70188
70998 | Hillje 345kV Substation - Danish Fields Battery Storage - Generator Interconnection (21INR0450) | Install Danish Fields Battery Storage¿ Connect at the same generator lead as Danish Fields Solar I-II-III at Hillje CNP station. |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-04-30 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 70999 | 70998
4567 | BRYN_4567_Smetana_to_Leonard | Build Smetana to Leonard Rd 138 line in existing 69KV ROW of old Annex to Atkins line |  | 32897 | 32863 | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2023-05-01 |  | 138 | 0.75 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32853, 32851 | Y |  |  | 0 | 64546 | 4567
5792 | Leonard Road Substation 138 | Upgrade Leonard Rd from 69kV to 138kV and construct 138 from Leonard to Atkins |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2023-05-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32051, 32851, 32862, 32864 | Y |  |  | 0 | 67470 | 5792
50882 | Lon Hill to Structure 25/4: Rebuild 138 kV Line | Rehab Lon Hill to Structure 25/4 138 kV Line |  | Lon Hill | Haisley | Planned | 1055 - 1228 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3785 | 2023-05-01 |  | 138 | 0 | 10.2 | 0 |  | San Patricio | San Patricio | Tier 3 | 19RPG014 | 2019-08-13 | 2019-10-07 |  | 8027, 8920, 8452, 8924 | Y | N |  | 0 | 65548 | 50882
55873 | Upgrade Moore to Hondo Creek 138 kV line | Replace the 336 ACSR with 1020 ACCC conductor while keeping the existing structures that still meet our standards. |  | Moore | Hondo Creek | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-05-01 |  | 138 | 0 | 13.5 | 0 |  | Medina | Frio | Tier 2 | 19RPG021 | 2019-11-20 | 2020-05-21 |  | 5819, 5827 | Y | N | Field engineering is still occurring due to short timeline for this upgrade. Details may change. | Current plan is to upgrade the line using mostly existing structures. Detailed field engineering is underway and could change the plan. | 55874 | 55873
63491 | Schneeman Draw to Big Hill 2nd circuit | Add the 2nd circuit to CREZ Schneeman Draw to Big Hill 345 kV line |  | Schneeman Draw | Big Hill | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-05-01 |  | 345 | 59.1 | 0 | 0 |  | Crockett | Schleicher | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76003, 76005 | Y | N |  |  | 63492 | 63491
65725 | James Rowe: Construct New Distribution Station | Construct New Distribution Station on the North McAllen to West McAllen 138 kV Line |  | North McAllen | West McAllen | Planned | 1030 - 1208 | AEP TCC | Alison Scribailo bcogan@aep.com 918-599-2857 | 3769 | 2023-05-01 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8041, 8367, 8631 | Y | N |  | 0 | 65726 | 65725
71871 | Update Line Characteristics and Rating. |  |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0280 | 2023-05-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5053, 5054, 5230, 5378 | Y |  |  | 0 | 71872 | 71871
59088 | Alice - Falfurrias: Line Rebuild | Alice - Falfurrias: Line Rebuild |  | Alice | Falfurrias | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020088 | 2023-05-10 |  | 69 | 0 | 3.67 | 0 |  | Jim Wells | Brooks | Tier 2 |  |  |  |  | 8500, 8508, 8878, 8894 | Y |  |  | 0 | 65586 | 59088
69007 | Tiempo: Build new 345 kV station | Construct new Tiempo 345 kV station for the ETT 2nd circuits project |  | Tiempo |  | Planned |  | ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021706 | 2023-05-12 |  | 345 | 0 | 0 | 0 |  | Zapata |  | Tier 1 |  |  |  |  | 80224, 80226, 80220, 162499 | Y | Y |  | 0 | 69008 | 69007
55421 | Ballinger to Concho: Rebuild 69 kV line | Rebuild Ballinger to Concho 69 kV line, install POD box bay for Rowena, install CB at Miles, install POP switch for Harriett REA | Project Description, Contact Update | Ballinger | Concho | Planned | 1088 - 1271 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1861 | 2023-05-13 |  | 69 | 0 | 20.45 | 0 |  | Runnels | Tom Green | Tier 3 | 20RPG004 | 2020-04-08 | 2020-04-30 | 2020-05-08 | 6409, 6413, 6338, 6410, 6412, 6411, 6450 | Y | N |  | 0 | 55422 | 55421
44854 | Lipton: Build 138 kV Box Bay | New Lipton 138 kV Station, replaces Lipton Hard Tap | Schedule Update | Lipton |  | Under Construction |  | AEP TCC | Jeremy Brazeal bcogan@aep.com 918-599-2857 | TP2018214 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Zavala |  | Tier 4 |  |  |  |  | 8285, 88285, 8236, 8283 | Y | N |  | 0 | 44855 | 44854
51740 | Buttercup Bus Upgrade | Upgrade the Buttercup bus from operate/transfer to double-bus double-breaker |  | Buttercup |  | Planned |  | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7531 | Y | N |  | 0 | 51750 | 51740
52322 | Establish Courtney Creek Switch | Establish Courtney Creek 138/69 kV Switch |  | Courtney Creek Switch | Athey (AEP) | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8479 | 2023-05-15 |  | 138 |  |  | 82 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 11242, 11258, 1240, 1242, 60792 | Y |  |  | 0 | 56445 | 52322
53958 | Fairland - Lago Vista Transmission Line Rehabilitation | Increase the reliability of transmission facilities on the T414 Fairland - Lago Vista 21-mile 138-kV transmission line by replacing the existing Condor conductor with Drake conductor. |  | Fairland | Lago Vista | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Burnet | Travis | Tier 3 | 22RPG029 | 2022-09-14 |  |  | 7352, 7518 | Y | N |  | 0 | 53959 | 53958
53999 | ElCampo - Ricebird Transmission Line Strom Hardening | Increase the reliability of transmission facilities on the T589 El Campo ¿ Ricebird 4.6-mile 138-kV transmission line. |  | El Campo | Ricebird | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8102, 78104 | Y | N |  | 0 | 54000 | 53999
54080 | Lockhart - Lulig Transmission Line Overhaul | LCRA TSC will perform an overhaul of T184 (from Lockhart structure #301 to Luling) with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T184 will be 795 ACSR Drake. Note: Condor conductor replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7216, 7224 | Y | N |  | 0 | 54081 | 54080
54082 | Lockhart - Red Rock Transmission Line Overhaul | LCRA TSC will perform an overhaul of T578 (from Lockhart structure #301 to Red Rock) with replacement structures that are capable of operating at 138-kV and supporting a single 959 ACSR Suwannee conductor. The replacement conductor on T578 will be 959 ACSR Suwannee. This overhaul will include the installation of a 72-count optical ground wire (OPGW). Note: Condor conductor, new OPGW and any structure replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Red Rock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Bastrop | Tier 4 |  |  |  |  | 7216, 7560 | Y | N |  | 0 | 54083 | 54082
54103 | Hilltop - Strahan Transmission Line Upgrade | Increase the reliability of transmission facilities on the T445: Hilltop ¿ Strahan 1.25-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | Hilltop | Strahan | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7190, 7193 | Y | N |  | 0 | 54104 | 54103
59263 | Weatherford Switch - Azle 138 kV Line | Upgrade existing 138 kV Line |  | Weatherford | Azle | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5172 | 2023-05-15 |  | 138 | 0 | 11.5 | 0 |  | Parker | Tarrant | Tier 4 |  |  |  |  | 1592, 2062, 15015 | Y |  |  | 0 | 59524 | 59263
59552 | Rebuild Eskota - Sweetwater No.2 69 kV Line | Rebuild Eskota - Sweetwater No.2 69 kV Line |  | Eskota | Sweetwater No. 2 | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8570 | 2023-05-15 |  | 69 | 0 | 16.3 | 0 |  | Nolan | Nolan | Tier 4 |  |  |  |  | 1382, 1383, 1386, 1387, 1340, 1381, 1384, 1385, 11384 | Y |  |  | 0 | 59554 | 59552
61440 | Harper Road - Jack Furman Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 4.6-mile Harper Road ¿ Jack Furman (T368) transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Harper Road | Jack Furman | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7140, 7141 | Y | N |  | 0 | 61441 | 61440
61453 | Ingram - Jack Furman Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 3.3-mile Ingram ¿ Jack Furman (T521) transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Ingram | Jack Furman | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7142, 7141 | Y | N |  | 0 | 61454 | 61453
61455 | Hunt - Ingram Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 6.4-mile Hunt ¿ Ingram (T487) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Hunt | Ingram | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7144, 7142 | Y | N |  | 0 | 61456 | 61455
61516 | Blissard - East Stiles 138 kV Line Section | Rebuild the Blissard - East Stiles 138 kV Line Section |  | Blissard | East Stiles | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8565 | 2023-05-15 |  | 138 | 0 | 13.1 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 11353, 23869 | Y |  |  | 0 | 61518 | 61516
61591 | Sandy Creek Autotransformer Upgrade | Increase the reliability of substation equipment at Sandy Creek Substation through the replacement of the Sandy Creek 138/69-kV AT1 autotransformer with a new 70 MVA unit. Increase the capacity of T400 Sandy Creek - Sunrise Beach 69-kV transmission circuit by upgrading limiting element jumper at Sunrise Beach Substation. |  | Sandy Creek | Sunrise Beach | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7121, 7400, 7127 | Y | N |  | 0 | 61592 | 61591
61599 | Pinto Creek Circuit Breaker Addition | This project provides a point of interconnection for a new generator by converting Pinto Creek Substation into a ring bus (GINR # 21INR0019). |  | Pinto Creek | Pinto Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kinney |  | Tier 4 |  |  |  |  | 78255 | Y | N |  |  | 61600 | 61599
61853 | LCRATSC Lampasas Substation Upgrade | This project will improve the reliability of Lampasas Substation by replacing obsolete and aged equipment and by converting the substation from single-bus-single-breaker design to double-bus-double-breaker design. Lampasas Substation is an important hub for the transmission system in Burnet, Lampasas, San Saba, and Mills counties, and this project will improve transmission system reliability in those areas. |  | Lampasas | Lampasas | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Lampasas | Lampasas | Tier 4 | [5 empty] | Y | N |  | 0 | 61854 | 61853
61932 | Holliday - Seymour 69 kV Line | Rebuild the Holliday - Seymour 69 kV Line. |  | Holliday | Seymour | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4028 | 2023-05-15 |  | 69 | 0 | 0 | 0 |  | Archer | Baylor | Tier 3 | 21RPG007 | 2021-04-26 | 2021-05-18 |  | 779, 1527, 1530, 1532, 1534 | Y |  |  | 0 | 61933 | 61932
62349 | Rebuild Fairfield West as Ranchland 138 kV Switch | Rebuild Fairfield West as Ranchland 138 kV Switch |  | Ranchland | Ranchland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6136 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3504, 3558, 196, 3495, 3503, 3625, 13501, 13681 | Y |  |  | 0 | 71865 | 62349
62636 | Rebuild Waco West (Peppervine) 138 kV Switch | Rebuild Waco West (Peppervine) 138 kV Switch |  | Waco West | Waco West | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6141 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3446, 3436, 3433, 3560, 3563, 3590, 3591, 3437, 13436 | Y |  |  | 0 | 62637 | 62636
62669 | Pegasus South - Pleasant Farms Tap 138 kV Line Rebuild | Rebuild existing Pegasus South - Pleasant Farms Tap 138 kV Line |  | Pegasus South | Pleasant Farms Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8574 | 2023-05-15 |  | 138 | 0 | 9.6 | 0 |  | Midland | Ector | Tier 4 | 21RPG010 | 2021-06-02 | 2021-06-23 | 2021-12-13 | 1236, 1237, 71230 | Y |  |  | 0 | 62672 | 62669
62728 | Wink - Shifting Sands 69 kV Line Conversion to 138 kV | Convert the existing Wink - Shifting Sands 69 kV Line to 138 kV |  | Wink | Shifting Sands | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8581 | 2023-05-15 |  | 69 | 0 | 13 | 0 |  | Winkler | Winkler | Tier 4 |  |  |  |  | 1244, 1245, 1246, 1249, 11392, 18539, 1074, 1075, 6583, 6665, 7046, 60708, 60710, 11391, 60618, 60621, 76003, 76583, 76668 | Y |  |  | 0 | 62730 | 62728
63929 | Buntin Drive 69 kV Substation Conversion To 138 kV | Convert Buntin Drive 69 kV Substation To 138 kV |  | Buntin |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4064 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2984, 2486, 2494, 2951 | Y |  |  | 0 | 63930 | 63929
66006 | Sherry 138 KV Switch Terminal Equipment | Upgrade terminal equipment a Sherry 138 kV Switch |  | Sherry |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5101 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 1919, 2257 | Y |  |  | 0 | 66007 | 66006
66175 | Liggett 138 kV Terminal Equipment | Upgrade the terminal equipment at Liggett 138 kV Switch |  | Liggett |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4094 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 1922, 1924, 2053, 2055 | Y |  |  | 0 | 66176 | 66175
66194 | Holiday - Navy Kickapoo 69 kV Line | Relocate current substations on Holliday - Navy Kickapoo 69 kV Line |  | Holliday | Navy Kickapoo | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4022 | 2023-05-15 |  | 69 | 0 | 0 | 0 |  | Archer | Archer | Tier 4 |  |  |  |  | 1525, 1526, 1528, 11525, 11528, 1527, 1424, 1431, 1473, 11527 | Y |  |  | 0 | 66195 | 66194
66196 | WichitaFalls PPG Terminal Equipment | Upgrade the existing terminal equipment at PPG |  | Wichita Falls PPG |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4025 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1484, 1485, 17005 | Y |  |  | 0 | 66197 | 66196
66522 | Andrews North - Paul Davis Tap 138 kV Line Rebuild | Add Andrews North - Paul Davis Tap 138 kV Line Rebuild |  | Andrews North | Paul Davis Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8596 | 2023-05-15 |  | 138 | 0 | 25 | 0 |  | Andrews | Dawson | Tier 4 | 21RPG012 | 2021-08-03 | 2021-08-26 |  | 1159, 1165, 1167, 1168 | Y |  |  | 0 | 66523 | 66522
66571 | Texaco Mabee Tap - Midland East 138 kV Line Rebuild | Add Texaco Mabee Tap - Midland East 138 kV Line Rebuild |  | Texaco Mabee Tap | Midland East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8304 | 2023-05-15 |  | 138 | 0 | 15.4 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11278, 11279, 11280, 1023, 1171, 1178, 1184, 11301 | Y |  |  | 0 | 69634 | 66571
66621 | Sandhills - Sandhills Tap 138 kV Line Rebuild | Add Sandhills - Sandhills Tap 138 kV Line Rebuild |  | Sandhills | Sandhills Tap | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8612 | 2023-05-15 |  | 138 | 0 | 23 | 0 | 0,55.2 | Ector | Crane | Tier 4 |  |  |  |  | 10006, 10007, 1103, 1104, 11111, 11117 | Y |  |  | 0 | 66681 | 66621
67766 | Southlake Capacitors | Install new 138 kV capacitor bank |  | Southlake |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3011 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 2020 | Y |  |  | 0 | 67767 | 67766
67904 | Haggerty 138 kV Switch | Establish Haggerty 138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4330 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  |  | 1740, 12677, 1714, 1715, 1717, 1749, 1750, 1753 | Y |  |  | 0 | 67905 | 67904
68793 | Expanse 345/138 kV Switch | Construct a new 345/138 kV switch |  | Brown | Grady | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8593 | 2023-05-15 |  | 345 | 0 | 0 | 1200 |  | Martin | Martin | Tier 3 | 22RPG007 | 2022-03-06 | 2022-04-04 |  | 11367, 11368, 11369, 11370, 11338, 23842 | Y |  |  | 0 | 68795 | 68793
70596 | LCRATSC_CraneEast_CB_Sub_Upgrade | Install circuit breakers in a ring bus configuration at Crane East Substation. Install two (2) 31.2 MVAR 138-kV capacitor banks at Crane East Substation. All substation equipment at Crane East Substation connected in series with the existing 138-kV transmission lines shall support a minimum rating of 3000 A at 105 degree F ambient temperature. |  | Crane EAst |  | Planned |  | LCRATSC | Dylan Preas dylan.preas.@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 | 0,62.4 | Upton | Upton | Tier 4 |  |  |  |  | 71214 | Y | N |  | 0 | 70597 | 70596
70824 | Lavender 138 kV Switch | Establish Lavender 138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5326 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2261, 2429, 2967 | Y |  |  | 0 | 70825 | 70824
72000 | DeCordova Switch_Carmichael Bend Switch 138 kV Line | Upgrade existing DeCordova Switch Carmichael Bend Switch 138 kV Line |  | DeCordova Switch | Carmichael Bend Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3019 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Hood | Hood | Tier 4 |  |  |  |  | 1891, 2888 | Y |  |  | 0 | 72001 | 72000
67610 | LCRATSC_ChiefBrady_Substation_Upgrade | Chief Brady Substation will be upgraded to increase the bus rating and replace equipment identified as obsolete. The substation upgrade will also install Tier 3 Physical Security Measures. -Contingency Update |  | Chief Brady | Chief Brady | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG +151-257-84514 |  | 2023-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y | N |  | 0 | 67611 | 67610
67906 | LCRATSC_WeltnerRoad_CB_Addition | LCRA TSC will install circuit breakers at Weltner Road Substation in order to increase the reliability to the load served by NBU. This project will also configure the bus at Weltner Road to a ring bus. Update contingencies |  | Weltner Road | Weltner Road | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG +151-257-84514 |  | 2023-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 | [5 empty] | Y | N |  | 0 | 67907 | 67906
6572 | Ballinger to Eden 69 kV line: Rebuild taps | Rebuild Taps on the Ballinger to Eden 69 kV line | Project Description Update | Ballinger | Eden | Planned | 890 - 1068 | AEP TNC | Shawn Ketcher mlforcum@aep.com 918-599-2674 | 2814 | 2023-05-16 |  | 69 | 0 | 2.8 | 0 |  | Runnels | Concho | Tier 4 |  |  |  |  | 6338, 6369, 6370, 6372, 6376 | Y | N |  | 0 | 65513 | 6572
48818 | Ballinger: Rebuild 138 kV Station | Rehab the 138/69 kV autotransformer at Ballinger | Project Title, Project Description Update | Ballinger |  | Planned | 1016 - 1194 | AEP TNC | Shawn Ketcher mlforcum@aep.com 918-599-2674 | 2777 | 2023-05-23 01:00 |  | 138 | 0 | 0 | 130 |  | Runnels |  | Tier 4 |  |  |  |  | 6338, 6340 | Y | N |  | 0 | 65537 | 48818
57908 | North Edinburg:138 kV Station Work | Install two 138 kV series reactors |  | North Edinburg |  | Planned | 1112 - 1290 | AEP TCC | Rich Haley bcogan@aep.com 918-599-2857 | 3831 | 2023-05-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 88381, 88382, 8380, 8383, 8341 | Y | N |  | 0 | 57909 | 57908
59804C | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86N Jonte to Lockwood tap to Scenic Woods radial |  | Lockwood | Jonte/Scenic Woods | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46331, 46032, 45660, 46336 | Y | N |  | Cost included in main project | 59807 | 59804
63902 | Bakersfield: Build New 345 kV Terminal | Interconnect Hydra BESS to the Bakersfield 345 kV Station |  | Bakersfield |  | Planned | 1136 - 1314 | ETT | Rasa Ansari mlforcum@aep.com 918-599-2674 | 1881 | 2023-05-30 |  | 345 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 76002, 135602 | Y | N |  | 0 | 63903 | 63902
71299 | McKenzie to Westside: Rebuild 138 kV Line | Rebuild McKenzie to Westside 138 kV Line | Project Title, Project Description, Schedule Update | McKenzie Road | Westside | Under Construction | 968 - 1146 | ETT | James Weaver bcogan@aep.com 918-599-2857 | TP2018126 | 2023-05-30 |  | 138 | 0 | 11.48 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8485, 8858 | Y | N |  | 0 | 71300 | 71299
72051 | Twinwood Mobile (TWM) 138kV Distribution Substation |  |  | Twinwood | Foster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 | [5 empty] | Y | N |  | 0 | 72052 | 72051
4010 | Rebuild Magnolia - Seminole 138 kV line. | *Project pushed back to 2023. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07216 | 2023-05-31 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38950, 38990 | Y |  |  |  | 11530 | 4010
50876 | Victoria to Port Lavaca: Retire 69 kV Line | Retire 69 kV Line on Victoria to Port Lavaca |  | Port Lavaca | Victoria | Planned | 1054 - 1227 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3782 | 2023-05-31 |  | 69 | 0 | 29 | 0 |  | Calhoun | Victoria | Tier 1 |  |  |  |  | 8135, 8136, 8169 | Y | N |  | 0 | 50877 | 50876
52183 | EXTER 69kV Substation Removal | Remove EXTER 69kV Substation from Ckt.53B |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Harris | Tier 4 |  |  |  |  | 42600, 42080, 43510, 44440 | Y | N |  | Cost included in MOD 52181 - ENCO new customer sub | 52184 | 52183
56012 | PSARCO Fault Duty Upgrade with Bus Reactors | Install (3) 10-Ohm Reactors at PSARCO by splitting PSARCO bus as a fault duty upgrade |  | PSARCO |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41300, 41303, 41305, 40190, 41021, 110560, 110579, 110571, 110572, 110573, 110574, 110577 | Y | N |  | 0 | 65112 | 56012
58008 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild Laredo VFT North to North Laredo Switch 138 kV lilne |  | Laredo | Laredo | Planned | 1116 - 1294 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3835 | 2023-05-31 |  | 138 | 11.68 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8112, 8643, 8909, 8918, 80013 | Y |  |  | 0 | 65582 | 58008
59317 | Deer Park Tap to Cardiff Ckt.96E Upgrades | Upgrade Deer Park Tap to Cardiff Ckt.96E to Minimum 300 MVA Emergency rating |  | Deer Park | Cardiff | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 5.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40442, 42240 | Y | N |  | 0 | 59318 | 59317
59398B | San Bernard (SAN) Sub for Brazoria County Solar (20INR0098) | Upgrade San Bernard to West Columbia Ckt.60 to increase thermal limits. Increase fault duty at West Columbia to 63KA |  | San Bernard | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43010, 43110, 43190, 43341, 43120, 43380 | Y | N |  | 0 | 59768 | 59398
62133 | West Columbia to Damon Ckt.89A Thermal Uprate | Upgrade West Columbia to Damon to Ckt.89A to Minimum 210 MVA Continuous rating |  | West Columbia | Damon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 10.3 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42370, 43380, 43384 | Y | N |  | 0 | 62134 | 62133
63922 | Tiki Island Distribution Upgrades | Install double-tap distribution service to Tiki Island. Existing tap will remain on Ckt.63E La Marque to Stewart. Tap Ckt.93C La Marque to West Galveston for the new tap section to Tiki Island. |  | Tiki Island | LaMarque/West Galveston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 43351, 43352, 43355, 42860, 43290, 43401 | Y | N |  | 0 | 63923 | 63922
63971 | Mykawa Distribution Facilities | Install distribution facilities at MYKAWA substation |  | Mykawa |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 42751, 42752, 42753, 42750, 42741, 42742, 43051 | Y | N |  | 0 | 63972 | 63971
64491 | Bellaire to Smithers Ckt.98A Upgrade | Upgrade Bellaire to Smithers Ckt.98A to increase thermal limits |  | Bellaire | Smithers | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 47000, 44650 | Y | N |  | 0 | 64492 | 64491
64493 | Bellaire to WAP Ckt.50A Upgrade | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits |  | Bellaire | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 47000, 44005 | Y | N |  | 0 | 64494 | 64493
64589 | Jeanetta Auto A3 Upgrade | Upgrade Jeanetta Auto A3 to increase thermal limits |  | Jeanetta |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47300, 47310, 49082 | Y | N |  | 0 | 64590 | 64589
64999C | Ckt93 AlgoaCorner to Alta Loma Rebuild | Rebuild and reconductor portions of Ckt.93B Hitchcock to LarMarque as a Hardening upgrade. Upgrade substation equipment at Hitchcock to increase thermal limits. |  | Hitchcock | LarMarque | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 4.95 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-13 | 2021-05-14 | 42800, 42860 | Y | N |  |  | 65002 | 64999
64999A | Ckt93 AlgoaCorner to Alta Loma Rebuild | Rebuild and reconductor portions of Ckt.93B AlgoaCorner to Alta Loma as a Hardening upgrade. |  | PH Robinson | Alta Loma | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 22.31 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-13 | 2021-05-14 | 42015, 42061 | Y | N |  | 0 | 65000 | 64999
66043B | Ckt29 THW-WhiteOak Reconductor and 138kV Conversion | Reconductor remaining portions of 69kV Ckt.29A TH Wharton to Little York to White Oak for 138kV conversion. Reconnect as 138kV Ckt.11A TH Wharton to Little York to White Oak. Swap positions for Ckt.95A and Ckt. 81K at the approach spans into TH Wharton. |  | TH Wharton | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 12.33 | 0 |  | Harris | Harris | Tier 4 | 21RPG016 | 2021-09-08 | 2021-09-30 | 2021-09-30 | 45512, 45990, 45995, 45510, 45530, 45782, 45922, 46615, 46620 | Y | N |  | 0 | 66045 | 66043
66046 | Ckt09 Zenith-VillageCreek Reconfigurations | Expand Zenith 138kV substation and install radial section Ckt.45 Zenith to Village Creek. Reconfigure Ckt.09K at Village Creek to create Ckt.09K Zenith to Village Creek tap to Franz. |  | Zenith | Village Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 3.6 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44270, 44271, 44272, 44260, 44910 | Y | N |  | 0 | 66047 | 66046
66221C | Galena Park Area Conversion Project | De-energize Ckt.17A Galena Park to Greens Bayou |  | Galena Park | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40720 | Y | N |  | Cost included in main entry | 66224 | 66221
66221J | Galena Park Area Conversion Project | Expand Clinton 138kV Facilities and Install 200MVA Autotransformer. Loop existing 138kV Clinton circuits into expanded 138kV Clinton substation. Install as Clinton Auto A1. |  | Clinton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 200 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 49004, 40350, 40352 | Y | N |  | Cost included in main entry | 66230 | 66221
66221D | Galena Park Area Conversion Project | De-energize Ckt.38B Clinton to Greens Bayou |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40352, 40720 | Y | N |  | Cost included in main entry | 66225 | 66221
66221B | Galena Park Area Conversion Project | De-energize Ckt.38A Galena Park to GYPSUM |  | Galena Park | GYPSUM | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40619, 40611, 40751 | Y | N |  | Cost included in main entry | 66223 | 66221
66221H | Galena Park Area Conversion Project | Join 69kV Greens Bayou buses 40720 & 40725 at a Minimum 40KAIC |  | Greens Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40725, 40720, 41570, 41681 | Y | N |  | Cost included in main entry | 66229 | 66221
66221A | Galena Park Area Conversion Project | Remove Galena Park Auto A1. Remove Galena Park 69kV facilities. Remove Galena Park 138kV ring bus. Rebuild Galena Park substation for double-tap 138kV service. |  | Galena Park |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | -200 |  | Harris |  | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40610, 49015, 40612, 40630, 41172, 40611 | Y | N |  | 0 | 66222 | 66221
66221E | Galena Park Area Conversion Project | De-energize Ckt.20C Galena Park to Greens Bayou |  | Galena Park | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40725 | Y | N |  | Cost included in main entry | 66226 | 66221
66221G | Galena Park Area Conversion Project | Rebuild Galena Park substation for double tap service. Tap Galena Park TR2 on Ckt.21K between Fidelity and Witter. |  | Fidelity | Witter | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40612, 40590, 41712 | Y | N |  | Cost included in main entry | 66228 | 66221
67217B | Addicks to Campbell Ckts 09 & 21 Upgrades | Upgrade Ckt.21H Addicks to Campbell tap to increase thermal limits |  | Addicks | Campbell | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 3.53 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45610, 45682 | Y | N |  | Cost included in Phase A | 67219 | 67217
67217A | Addicks to Campbell Ckts 09 & 21 Upgrades | Upgrade Ckt.09I Addicks to Campbell tap to increase thermal limits |  | Addicks | Campbell | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 3.53 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45620, 45681 | Y | N |  | 0 | 67218 | 67217
67270C | BP23 Reliability Upgrades | Upgrade Ckt.08L HO Clarke to BUNKER to increase thermal limits |  | HO Clarke | BUNKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47150, 47340 | Y | N |  | 0 | 67273 | 67270
67270B | BP23 Reliability Upgrades | Upgrade Ckt.37A Bellaire to Kirby to increase thermal limits |  | Bellaire | Kirby | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47320 | Y | N |  | 0 | 67272 | 67270
67270E | BP23 Reliability Upgrades | Upgrade Ckt.27A DOW to Jones Creek to increase thermal limits |  | DOW | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 42530 | Y | N |  | 0 | 67275 | 67270
67270D | BP23 Reliability Upgrades | Upgrade Ckt.08B Knight tap to Stadium to Fannin to increase thermal limits |  | Knight | Fannin | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47090, 47331, 47420 | Y | N |  | 0 | 67274 | 67270
67270A | BP23 Reliability Upgrades | Upgrade Ckt.21J Airline to White Oak to increase thermal limits |  | Airline | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 3 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45630, 46610 | Y | N |  | 0 | 67271 | 67270
67604 | Stafford Reconfigurations Ckt.05D |  |  | Stafford | Missouri City | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44670, 44672, 44674, 44483, 44761 | Y | N |  | 0 | 67605 | 67604
67933 | Rayford 3rd Transformer Addition |  |  | Rothwood | Springwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46260, 46270, 46295 | Y | N |  | 0 | 67934 | 67933
67987 | BIGVUE to Channelview Relay Upgrades |  |  | BIGVUE | Lyondell | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40190, 41023 | Y | N |  | 0 | 67988 | 67987
68205 | GENRAL to Garden Villas Rebuild |  |  | GENRAL | Garden Villas | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 9.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42690, 47670 | Y | N |  | 0 | 68206 | 68205
68242A | Garrott to Midtown to Polk Ckt.90 Upgrades Phase Two | Replace Midtown reactor R2 at 0.343 Ohm. Adjust underground circuit ratings to reflect the updated reactor R2 values. |  | Garrott | Midtown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47661, 47707, 47709, 47730, 47706, 47708, 47731 | Y | N |  | 0 | 72026 | 68242
68242B | Garrott to Midtown to Polk Ckt.90 Upgrades Phase Two | Adjust underground circuit ratings to reflect the updated reactor R2 values. |  | Midtown | Polk | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47707, 47709, 47731, 47730 | Y | N |  | 0 | 72027 | 68242
69221 | Rebuild 69 kV Line from Blessings to Palacios | Rebuild 69 kV Line from Blessings to Palacios |  | Blessing | Palacios | Planned |  | AEP TCC | Lorraine Timmerman bcogan@aep.com 918-599-2875 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8720, 8119, 8131 | Y |  |  | 0 | 69222 | 69221
69226 | Rebuild 69 kV Line from Point Comfort to Carancahua | Rebuild 69 kV Line from Point Comfort to Carancahua |  | Point Comfort | Carancahua | Planned |  | AEP TCC | Lorraine Timmerman bcogan@aep.com 918-599-2875 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Calhoun | Jackson | Tier 4 |  |  |  |  | 8132, 8555 | Y |  |  | 0 | 69227 | 69226
69888B | Deepwater to Clinton Ckts.33B-33C Line Upgrades | Rebuild-Reconductor portions of Ckt.33C Clinton to Harrisburg ahead of future 138kV conversions. |  | Clinton | Harrisburg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 4.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40352, 40800 | Y | N |  | Cost included in other phase. | 70972 | 69888
69888A | Deepwater to Clinton Ckts.33B-33C Line Upgrades | Fully reconductor Ckt.33B Deepwater to Texpet Switchrack to Harrisburg ahead of future 138kV conversions. |  | Deepwater | Harrisburg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 3.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40470, 40800, 41560 | Y | N |  | 0 | 70971 | 69888
69896 | Singleton Expansion for Limousin Oak Storage (22INR0338) | Expand Singleton 345kV substation and install one generator lead for new interconnection to Limousin Oak Storage |  | Singleton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 345 | 0 | 0 | 0 |  | Grimes |  | Tier 4 | [5 empty] | Y | N |  |  | 69897 | 69896
70606 | ARCHER to Karsten Ckt.26 Upgrades | Upgrade Ckt.26 Archer to Karsten to increase thermal limits. |  | ARCHER | Karsten | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 8.51 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44410 | Y | N |  | 0 | 70607 | 70606
72057 | Greens Bayou to LYCHEM Ckt.08 Upgrade (2023) |  |  | Moore Road | Uvalde | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 3.25 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | 0 | 72058 | 72057
59804A | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86E Crosby to Newport to Jonte |  | Jonte | Crosby/Newport | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 41150, 46032 | Y | N |  | 0 | 59805 | 59804
59804B | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86M Jonte to Greens Road tap |  | Jonte | Greens Road | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45821, 45660, 46331 | Y | N |  | Cost included in main project | 59806 | 59804
59804D | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90C North Belt to Greens Road tap to Jonte |  | Greens Road | North Belt/Jonte | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45822, 45660, 46031 | Y | N |  | Cost included in main project | 59808 | 59804
59804E | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90E Jonte to Lockwood tap to Lauder tap to Scenic Woods radial |  | Jonte | Lockwood/Lauder/Scenic Woods | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46031, 45660 | Y | N |  | Cost included in main project | 59809 | 59804
64505A | Flewellen to Peters Ckt.25E Upgrades | Upgrade Ckt.25E Flewellen to Foster to increase thermal limits |  | Flewellen | Foster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:01 |  | 138 | 0 | 1.9 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 21RPG011 | 2021-06-04 | 2021-07-02 |  | 44230, 44256 | Y | N |  | 0 | 64506 | 64505
64572A | HO Clarke Bus Upgrade | Upgrade bus work at HO Clarke 138kV facilities |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47150, 47175, 47170 | Y | N |  | 0 | 64573 | 64572
64999B | Ckt93 AlgoaCorner to Alta Loma Rebuild | Rebuild and reconductor portions of Ckt.93B Alta Loma to Hitchcock as a Hardening upgrade. Upgrade substation equipment at Hitchcock to increase thermal limits. |  | Alta Loma | Hitchcock | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:01 |  | 138 | 0 | 6.38 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-13 | 2021-05-14 | 42061, 42800 | Y | N |  |  | 65001 | 64999
67422A | Greens Bayou to Clinton 138kV Conversion | Rebuild and Reconductor Ckt.61A Greens Bayou to Wallisville to Prepare for 138kV Conversion |  | Greens Bayou | Wallisville | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:01 |  | 69 | 0 | 6.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40720, 41681 | Y | N |  | 0 | 67528 | 67422
64505B | Flewellen to Peters Ckt.25E Upgrades | Upgrade Ckt.25E Foster to Twinwood Mobile to Peters to increase thermal limits |  | Foster | Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:02 |  | 138 | 0 | 27.4 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 21RPG011 | 2021-06-04 | 2021-07-02 |  | 44256, 44860, 46220 | Y | N |  | Cost included in main entry | 64507 | 64505
70657 | Add dedicated transformer at Galena for Lehigh | Add dedicated transformer at Galena for Lehigh |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:10 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 40614, 40613, 40731 | Y | N |  | 0 | 70658 | 70657
51001 | Friess Ranch to Sonora: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line | Project Description, Transmission Owner Update | Friess Ranch | Sonora | Planned | 1044 - 1217 | AEP TNC/AEP TCC | Dave Baker mlforcum@aep.com 918-599-2674 | 2791 | 2023-05-31 12:00 |  | 69 | 0 | 24.3 | 0 |  | Sutton | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 8238, 8239, 60438, 6513, 60210, 6570 | Y | N |  | 0 | 65554 | 51001
64941 | PETSON to MONSAN Ckt.04D Upgrade | Upgrade Ckt 04D PETSON to MONSAN to increase thermal limits |  | PETSON | MONSAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43070, 42940 | Y | N |  | 0 | 64942 | 64941
65704 | Expand Crosby substation with 35kV Distribution Facilities |  |  | Crosby | Highlands/Atascosita |  |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40394, 40397, 40390, 40391, 40130, 40790, 40811 | Y | N |  | 0 | 65705 | 65704
65716A | Jonte Related Upgrades | Upgrade Ckt.86N Jonte to Lockwood tap to increase thermal limits |  | Jonte | Lockwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 46032 | Y | N |  | 0 | 65717 | 65716
66013 | CNP WATERHOLE POI for G Star Solar | New 345kV Waterhole (WAT) substation for generator interconnection to G-Star Solar. Loop Ckt.62 into substation to create new Ckt.62 Bailey to Waterhole to Jones Creek. |  | Waterhole | BAILEY/Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 345 | 0.08 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44880, 42530, 44040 | Y | N |  | 0 | 66014 | 66013
66017A | Westpark Area Upgrades | Upgrade Ckt.05E Bellaire to Sharpstown tap and Dunvale tap to Jeanetta to increase thermal limits |  | Bellaire | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 3.6 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47071, 47310, 47411 | Y | N |  | 0 | 66018 | 66017
65716B | Jonte Related Upgrades | Install 20 MVAR cap bank at Jonte substation |  | Jonte |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0 | 0 | 0,20 | Harris |  | Tier 4 |  |  |  |  | 45660 | Y | N |  | 0 | 65718 | 65716
66017B | Westpark Area Upgrades | Upgrade Ckt.24B Dunvale tap to Westchase tap to increase thermal limits. |  | Dunvale | Westchase | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:01 |  | 138 | 0 | 2.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44762, 47072 | Y | N |  | 0 | 66019 | 66017
4895 | CPSE_Capitol Cement Transmission Reconfiguration | Re-configurate Capitol Cement by loop into the existing Dresden to Skyline 138 kV transmission line and removing the existing Captiol Cement to Tuttle 138 kV transmission line. |  | Capitol Cement | Dresden/Skyline | Planned | S-0767 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0246 | 2023-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5075, 5130, 5370, 5435 | Y | N |  |  | 12507 | 4895
45101 | Chavaneaux_Chavaneaux Tap (Chavaneaux to Palo Alto)- 138 kV | CPSE_Chavaneaux_Chavaneaux 138 kV Tap Rebuild (Chavaneaux to Palo Alto). |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0256 | 2023-06-01 |  | 138 | 0 | 0.9 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5085, 5330 | Y |  |  | 0 | 45102 | 45101
45136 | CPSE_New Midtown Substation | New Mid Town substation looped into Comal St to Olmos transmission line. |  |  |  |  | S-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0283 | 2023-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5311, 5096, 5325 | Y |  |  | 0 | 45137 | 45136
57912 | Champlin to Weil Tract: Rebuild 138 kV Line | Rebuild Champlin to Weil Tract 138 kV Line |  | Champlin | Weil Tract | Planned | 1111 - 1289 | ETT | John Pulay mlforcum@aep.com 918-599-2674 | 3830 | 2023-06-01 |  | 138 | 0 | 1.37 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8476, 8482 | Y | N |  | 0 | 65581 | 57912
63493 | Noelke to Schneeman Draw 2nd circuit | Add the 2nd circuit to the CREZ Noelke to Schneeman Draw 345 kV line |  | Noelke | Schneeman Draw | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-06-01 |  | 345 | 15.8 | 0 | 0 |  | Crockett | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 7053, 76005 | Y | N |  |  | 63494 | 63493
64484 | Cumby_Kiowa Conversion | Converting voltages for several Rayburn buses from 69 kV to 138 kV. |  | Cumby | Kiowa | Planned |  | RYBRN |  |  | 2023-06-01 |  | 138 | 0 | 0 | 0 |  | Hunt | Hunt | Tier 4 |  |  |  |  | 6823, 6861, 6869, 6871, 37361 | Y |  |  | 0 | 72036 | 64484
65663 | Double Ckt Line M138-K |  |  | Pecos (bus # 38091) | Faulkner (bus # 38124) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-06-01 |  | 138 | 0 | 26.2 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38091, 38124 | Y |  |  | 0 | 65664 | 65663
66074 | Double ckt Soaptree-Holiday-AlamoSt |  |  | Soaptree (bus # 38450) | Alamo Street (bus # 38330) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-06-01 |  | 138 | 0 | 31.9 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38450 | Y |  |  | 0 | 66075 | 66074
66635 | Lamesa 69 kV Substation Conversion to 138 kV | Add Lamesa 69 kV Substation Conversion to 138 kV |  | Lamesa 69 kV | Lamesa 138 kV | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8595 | 2023-06-15 |  | 69 | 0 | 0 | 0 |  | Dawson | Dawson | Tier 4 |  |  |  |  | 1164, 10008, 1163, 18880 | Y |  |  | 0 | 66638 | 66635
69417 | Crater Rock 138 kV Switch | Establish Crater Rock 138 kV Switch |  | Horseshoe Springs | Three Mile Draw | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8604 | 2023-06-15 |  | 138 | 0 | 0 | 0 |  | Culberson | Culberson | Tier 4 |  |  |  |  | 11224, 1095, 11103 | Y |  |  | 0 | 69419 | 69417
54204 | Gonzales - Hochheim Transmission Line Overhaul | Increase the reliability and capacity of transmission facilities on the T542 Luling ¿ Cuero 19.6-mile 69-kV transmission line from Gonzales (structure #33) to Hochheim Tap. LCRA TSC will perform an overhaul of T542 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T542 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Gonzales | DeWitt | Tier 4 |  |  |  |  | 7223, 78577 | Y | N |  | 0 | 54205 | 54204
61459 | Buchanan CTEC-Buchanan Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 2.8-mile Buchanan ¿ Buchanan CTEC (T106) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Buchanan CTEC | Buchanan | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7092, 7101 | Y | N |  | 0 | 61460 | 61459
61461 | Buchanan CTEC - Pitsburg Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 14.5-mile Buchanan CTEC ¿ Pitsburg (T267) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Buchanan CTEC | Pitsburg | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Llano | Llano | Tier 3 | 22RPG030 | 2022-09-14 |  |  | 7101, 7119, 7116 | Y | N |  | 0 | 61462 | 61461
65003 | WA Parish to Nash Ckt.02B Upgrades | Upgrade Ckt.02B WA Parish to Nash to replace aging infrastructure and to address line clearance concerns |  | WA Parish | Nash | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-06-30 |  | 138 | 0 | 18.02 | 0 |  | Fort Bend | Brazoria | Tier 4 | 21RPG013 | 2021-08-08 | 2021-09-10 |  | 42980, 44721, 44722, 42410, 44010 | Y | N |  | 0 | 65004 | 65003
67921 | Sisseton: Build 69 kV tap | Build new 69 kV tap on the Aspermont to Hamlin 69 kV line. |  | Sisseton |  | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-282-8376 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6073, 60068, 6156, 6184, 6186, 6185, 6187 | Y |  |  | 0 | 67922 | 67921
71940 | LCRATSC_Saxet_Substation_Addition | LCRA TSC will provide two transmission points of interconnection by installing taps on the LCRA TSC owned 138-kV transmission lines T522 Weil – Lon Hill and T437 Lon Hill – Nueces Bay to serve AEP customer load. |  | Saxet |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 | [5 empty] | Y | N |  | 0 | 71941 | 71940
71942 | LCRATSC_Birdhouse_Substation_Addition | LCRATSC will provide a point of interconnection for a new solar and battery energy storage system at a new 138-kV Birdhouse Substation |  | Birdhouse | Birdhouse | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 138 | 0 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 | [5 empty] | Y | N |  | 0 | 71943 | 71942
72034 | Blodgett to TECO Ckt.37C Upgrades |  |  | Blodgett | TECO | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-06-30 |  | 138 | 0 | 3.02 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47520, 47430 | Y | N |  | 0 | 72035 | 72034
72049 | Crabb River Road to Imperial Ckt.80B Upgrades |  |  | Crabb River | Imperial | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-06-30 |  | 138 | 0 | 5.04 | 0 |  | Fort Bend | Fort Bend | Tier 4 | [5 empty] | Y | N |  | 0 | 72050 | 72049
5461 | Load serving |  |  | Puckrus | Mayhill | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 1.9 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 929, 917 | N | N |  |  | 13164 | 5461
45511 | Laredo - Del Mar: 138 kV Line Rebuild | Rebuild Laredo - Del Mar 138 kV Line with 795 ACSS |  | Laredo | Del Mar | Conceptual | 992 - 1170 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3746 | 2023-07-01 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645 | Y | N |  | 0 | 65531 | 45511
45566 | Holly - Southside: 138 kV Line Rating Increase | Increase MOT for Holly - Southside 138 kV Line |  | Holly | Southside | Planned | 994 - 1172 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3747 TP-2019-065 | 2023-07-01 |  | 138 | 0 | 1.8 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486 | Y | N |  | 0 | 65532 | 45566
63495 | Cedar Canyon to Noelke 2nd circuit | Add the 2nd circuit to CREZ Cedar Canyon to Noelke 345 kV line |  | Cedar Canyon | Noelke | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-07-01 |  | 345 | 16 | 0 | 0 |  | Crockett | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76015, 7053 | Y | N |  |  | 63496 | 63495
66124 | Prarie Swiitch Wind Interconnect | Connect Crawfish to El Campo to Lane City 138 kV Line |  | EL CAMPO | LANE CITY PUMP | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021286 | 2023-07-06 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8679, 8102, 8104 | Y |  |  | 0 | 66125 | 66124
45084B | Braunig to Highland Rebuild | Rebuild approximately sixteen circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Schillers Tap to Braunig'. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0194, T-0238 | 2023-07-15 |  | 138 | 0 | 16 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  | 0 | 45086 | 45084
5165 | Poesta: Construct a new 138/69 kV station | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. |  | Borglum |  | Under Construction | 742 - 0925 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 2914 TP2014129 | 2023-08-01 |  | 138 | 0 | 0 | 130 |  | Bee |  | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8196, 8197, 8205, 8107, 8198, 8199, 8904 | Y | N |  |  | 13315 | 5165
5166 | Poesta to Three Rivers: Rebuild 69 kV line | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. |  | Borglum | Three Rivers | Under Construction | 742 - 0925 | AEP TCC | Dave Gotez bcogan@aep.com 918-599-2857 | 2915 | 2023-08-02 |  | 138 | 6 | 22 | 0 |  | Bee | Live Oak | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8156, 8142, 8199, 84006, 8196, 8400, 8403 | Y | N |  | 0 | 57889 | 5166
5167 | Poesta to Tuleta: Build new double circuit 138/69 kV line | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. | Schedule Update | Borglum | Tuleta | Under Construction | 742 - 0925 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 2916 | 2023-08-03 |  | 138 | 23.5 | 23.5 | 0 |  | Bee | Bee | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8195, 8584, 8592, 8629, 88198, 8197, 8198, 8586, 85851, 8196, 8585, 8590, 8593 | Y | N |  | 0 | 61033 | 5167
66128 | Construct a 138 kV dead end structure outside of the Clarkwood station along with the first span. Construct a 138 kV breaker terminal at the Clarkwood station. | Construct a 138 kV dead end structure outside of the Clarkwood station along with the first span. Construct a 138 kV breaker terminal at the Clarkwood station. Connect BRP Carina to the Clarkwood 138 kV station |  | BRP Carina | Clarkwood | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021308 | 2023-08-03 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 88479, 8479 | Y |  |  | 0 | 66129 | 66128
57890 | Brightside Permanent Connection | Construct Charter Station |  | Beeville | Three Rivers | Planned | 1114 - 1292 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3833 | 2023-08-25 |  | 138 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8142, 8156, 8403 | Y |  |  | 0 | 57891 | 57890
61851 | Marion AT2 Autotransformer Upgrade | Increase the reliability of substation equipment at Marion Substation through the replacement of the Marion AT2 345/138-kV autotransformer and installation of three 345-kV shunt reactors. |  | Marion 345 | Marion 138 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-08-25 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7044, 7178, 7822 | Y | N |  | 0 | 61852 | 61851
67917 | Brackettville and Hamilton Road Relay Upgrades for Pinto Creek | Upgrade relays at Brackettville 138 kV station and upgrade relays at Hamilton Road 138 kV station |  | Brackettville | Hamilton Road | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-08-25 |  | 138 | 0 | 0 | 0 |  | Kinney | Val Verde | Tier 4 |  |  |  |  | 78255, 8252, 8255 | Y |  |  | 0 | 67918 | 67917
69894 | HO Clarke Substation Expansion for Callisto Energy Center (22INR0490 & 22INR0491) | Expand HO Clarke substation for Callisto Energy Center generator interconnection (22INR0490 & 22INR0491) |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-08-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 69895 | 69894
52147 | Rising Star Area Conversions | Converts voltage to 138 KV from Holder to Nimrod to Rising Star. |  | Holder | Rising Star | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2023-09-01 |  | 138 | 0 | 0 | 0 |  | Brown | Comanche | Tier 4 |  |  |  |  | 285, 289, 293, 292, 281 | Y |  |  | 0 | 52148 | 52147
61138 | Bergstrom Sub Cap Addition | Add a 31.2 MVAR Cap Bank at the Bergstrom Substation |  | Bergstrom | Bergstrom | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2023-09-01 |  | 138 | 0 | 0 | 0 | 0,31.2 | Travis | Travis | Tier 4 |  |  |  |  | 9165 | Y |  |  | 0 | 61139 | 61138
63497 | Bakersfield to Cedar Canyon 2nd circuit | Add the 2nd circuit to CREZ Bakersfield to Cedar Canyon 345 kV line |  | Bakersfield | Cedar Canyon | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-09-01 |  | 345 | 21.1 | 0 | 0 |  | Pecos | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76002, 76015 | Y | N |  |  | 63498 | 63497
68974 | Second circuit from San Miguel to Fowlerton 345 kV | String the second circuit on existing towers from San Miguel to Fowlerton |  | San Miguel | Fowlerton | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-09-01 |  | 345 | 36.4 | 0 | 0 |  | Atascosa | McMullen | Tier 1 |  |  |  |  | 5901, 5709 | Y | N |  | 0 | 68975 | 68974
69463 | Gulch: Construct new 345 kV Station | Arroyo Solar Interconnect |  | Rio Hondo | La Palma | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-09-01 |  | 345 | 0.1 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 8704, 8705, 8317, 8318 | Y |  |  | 0 | 70802 | 69463
67913 | Anemoi Energy Storge interconnection | Connect a 205 MW storage facility called ¿Anemoi Energy Storage¿ at ETT¿s Pomelo 345 kV. |  | Hidalgo | Hidalgo | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-09-05 |  | 345 | 0.05 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 | [5 empty] | Y |  |  | 0 | 67914 | 67913
66200A | Upgrade Taylor - Holland 69 kV Line | Rebuild the Holland - Bartlett Tap 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6173 | 2023-09-15 |  | 69 |  | 5.7 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3646, 13647 | Y |  |  | 0 | 66201 | 66200
66202A | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Palestine - Elkhart 69 kV Line |  | Palestine | Elkhart | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6182 | 2023-09-15 |  | 69 | 0 | 9.8 | 0 |  | Anderson | Anderson | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3273, 3285, 3286, 3289, 3290 | Y |  |  | 0 | 66203 | 66202
64754 |  | Loop new 138kV Crossroads substation into existing 138kV Potranco to AMD transmission line |  |  |  | Planned | T-0310 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0962 | 2023-09-28 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5102, 5002, 5346 | Y |  |  | 0 | 64755 | 64754
64774 |  | Loop new 138kV Donop substation into existing 138kV Southton to Braunig transmission line. |  |  |  | Planned | T-0311 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0963 | 2023-09-28 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5128, 5030, 5394 | Y |  |  | 0 | 64775 | 64774
57731B | Hornsby Substation Addition | Construct a new 345-kV substation between Clear Springs to Gilliland Creek 345-kV transmission line to provide transmission service to a load-serving substation. Restore 138-kV transmission line from Decker to Sand Hill by removing temporary substation/arrangements made in first phase to serve load. |  | Clear Springs | Gilleland Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-09-29 |  | 345 | 0 | 0 | 960 |  | Travis | Travis | Tier 4 |  |  |  |  | 7047, 7916, 7050, 9187, 7340, 9216 | Y | N |  | 0 | 57740 | 57731
71946 | LCRATSC_Hornsby_CircuitBreaker_Addition | Provide transmission service to a generator by adding an additional breaker-and-a-half bay to Hornsby Substation to accommodate a new circuit termination. |  | Hornsby |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-09-29 |  | 345 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 | [5 empty] | Y | N |  | 0 | 71947 | 71946
64063 | BRP Antlia BESS Interconnection | Connect BRP Antlia BESS to the Maxwell 138 kV station | Contact, Schedule Update | MAXWELL | ANTLIA | Conceptual |  | AEP TCC | Joseph Isaac bcogan@aep.com 918-599-2858 |  | 2023-09-30 |  | 138 | 0 | 0 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 88999, 8998 | Y |  | TP2021260 | 0 | 64064 | 64063
69890 | Bailey 345kV Substation Expansion for Ray Gulf Wind (22INR0517) |  |  | Bailey |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-09-30 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 | [5 empty] | Y | N |  |  | 69891 | 69890
7161 | Naval Base to North Padre Island: Rebuild 69 kV Line | Rehab Naval Base to North Padre Island 69 kV Line |  | Naval Base | North Padre Tap | Planned | 909 - 1087 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3690 | 2023-10-01 |  | 69 | 0 | 12.7 | 0 |  | Nueces | Nueces | Tier 3 | 19RPG001 |  |  |  | 8495, 8847, 8856 | Y | N |  | 0 | 65519 | 7161
48327 | Reconductor 138kV ckt 972 Howard Lane to McNeil to 3000A. |  |  | 9079 | 9217 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinene (512) 322-6740 |  | 2023-10-01 |  | 138 | 0 | 2.81 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9079, 9217 | Y |  |  | 0 | 48328 | 48327
52169 | Rising Star Area Conversions | This converts the voltage to 138 following Rising Star Substation Voltage Conversion |  | Rising Star | Downing | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2023-10-01 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 281, 277, 285, 294 | Y |  |  | 0 | 52170 | 52169
57797 | Athey: Build 138 kV Station | Build new 138 kV Station on the Ft Stockton to Rio Pecos 138 kV line | Transmission Status, Contact Update | Athey |  | Under Construction | 1109 - 1287 | AEP TNC | Shawn Ketcher mlforcum@aep.com 918-599-2674 | 1866 | 2023-10-01 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60792, 60718, 60798 | Y | N |  | 0 | 65578 | 57797
68972 | Tiempo to Fowlerton: Build second circuit 345 kV line | Hang conductor to complete a double circuit between Tiempo and Fowlerton for the ETT 2nd circuits project |  | Tiempo | Fowlerton | Planned |  | ETT/STEC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021703 | 2023-10-03 |  | 345 | 63.38 | 0 | 0 |  | Webb | Zapata | Tier 1 |  |  |  |  | 80219, 80220, 80221, 5709, 80224, 80230 | Y | Y |  | 0 | 68973 | 68972
68055 | Rio Colorado substation | Adds new Rio Colorado load serving station between Bay City and Tin Top |  | Rio Colorado |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-10-07 |  | 69 | 3.8 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5563, 5560, 5569 | Y | N |  | 0 | 68056 | 68055
11TPIT0011 | East_Village138kV Substation | East_Village 138kV Substation |  | Techridge | East_Village SUB |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2023-10-09 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9195, 9045, 9190 | Y |  |  |  | 13043 | 5357
71161 | Haggerty-Anna and Haggerty-Stone Creek 138 kV Lines | Establish Haggerty-Anna and Haggerty-Stone Creek 138 kV Lines |  | Haggerty | Anna and stone creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4333 | 2023-10-15 |  | 138 | 0 | 0 | 0 |  | Grayson | Grayson | Tier 4 |  |  |  |  | 1713, 1699, 1715, 1717, 1753, 1754, 1839, 12677 | Y |  |  | 0 | 71162 | 71161
69002 | Pronto: Build new 345 kV station | Construct new Pronto 345 kV station for the ETT 2nd circuits project |  | Pronto |  | Planned |  | ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021709 | 2023-10-27 |  | 345 | 0 | 0 | 0 |  | Starr |  | Tier 1 |  |  |  |  | 80231, 80355, 80381, 160885, 161855 | Y | Y |  | 0 | 69003 | 69002
64089 | Peregrine Solar Interconnection | Connect the Peregrine Solar to the Coleto Creek to Grissom 345 kV line |  | Coleto Creek | Grissom | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-10-30 |  | 345 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8673, 88673, 8164, 8624 | Y |  |  | 0 | 64090 | 64089
71944 | LCRATSC_SingleTree_Substation_Addition | LCRATSC will provide a transmission point of interconnection for a new wind resource on the Noelke – Schneeman Draw 345-kV double circuit transmission line by adding a new 345-kV breaker-and-a-half substation, Single Tree Substation. |  | Single Tree | Single Tree | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-10-30 |  | 345 | 0 | 0 | 0 |  | Crockett | Crockett | Tier 4 | [5 empty] | Y | N |  | 0 | 71945 | 71944
7013 | NASA Substation Upgrades | Upgrade substation equipment at NASA on Ckt.06 NASA to Webster to increase thermal limits |  | NASA | NASA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42970, 42610 | Y | N |  |  | 14835 | 7013
57350 | Lyons to Gay Hill T-line pole change out and reconductor | Replace existing structure with upgraded structures and replace existing 336.4 ACSR Linnet with 795 ACSR Drake on Lyons to Gay Hill transmission line. |  | Lyons | Gay Hill | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet.coop curtis.fischer@bluebonnet (979) 716-0253 |  | 2023-10-31 |  | 138 | 0 | 11.51 | 0 |  | Burleson | Washington | Tier 4 |  |  |  |  | 7572, 7573 | Y |  |  | 0 | 57351 | 57350
64499 | Hyde Park to Downtown Ckt.32A Upgrades | Upgrade Hyde Park to Downtown Ckt.32A |  | Downtown | Hyde Park | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 345 | 0 | 1.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47690, 47510 | Y | N |  | 0 | 64500 | 64499
70225 | Junction: Install capacitor bank | Install Capacitor Bank at Junction Station | Project Description Update | Junction |  | Planned |  | AEP TNC | Tommy Vannoy mlforcum@aep.com 918-599-2674 |  | 2023-10-31 |  | 69 | 0 | 0 | 0 | 0,7.7 | Kimble |  | Tier 4 |  |  |  |  | 6400 | Y | N |  | 0 | 70226 | 70225
71011 | Solstice: CT Removal | Remove CTs from Solstice station located along the Solstice to Sand Lake ONCOR and the Solstice to Bakersfield LCRA 345 kV double circuit lines | Service Level kV Update | Solstice |  | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-10-31 |  | 345 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 11098, 60404, 76002 | Y | N |  | 0 | 71012 | 71011
72063 | Moody to Stewart Ckt.63 Upgrades P1041 | Reconductor portions of Ckt.63 Stewart to West Galveston as a Hardening project |  | Stewart | West Galveston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 345 | 0 | 4.03 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42951, 42950 | Y | N |  | 0 | 72064 | 72063
72065 | Lake Jackson Distribution Substation Conversion to Low-Profile |  |  | Lake Jackson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | 0 | 72066 | 72065
6931 | New Tres Lagos Substation | Adds new station and short line from W Edinburg-Alton line |  | West Edinburg | Alton | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-11-01 |  | 138 | 1.8 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5770, 5771, 5772 | Y | N |  |  | 14750 | 6931
49556 | Ozona: Rebuild 69 kV station | Replace existing Ozona 69 kV station with a new 69 kV ring bus |  | Ozona |  | Planned | 1018 - 1196 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 2780 | 2023-11-01 |  | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6550, 6560 | Y | N |  | 0 | 65538 | 49556
52064 | Bay City - Lane City: 138 kV Line Rebuild | Rebuild the Bay City - Magill - Lane City 138 kV Line |  | Bay City | Lane City | Planned | 1078 - 1251 | AEP TCC | Marc E. Wilson bcogan@aep.com 918-599-2857 | 3803 | 2023-11-01 |  | 138 | 0 | 16 | 0 |  | Matagorda | Wharton | Tier 3 |  |  |  |  | 8111, 8113, 8127 | Y | N |  | 0 | 65558 | 52064
57169 | Rebuild Redgate to N Edinburg 138 kV | Rebuild Redgate to N Edinburg 138kV and opens Redgate tap |  | Redgate | Faysville Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-11-01 |  | 138 | 0 | 3.45 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8380, 88380, 5779, 5784 | Y | N |  | 0 | 63733 | 57169
69483 | Wolf Tank Storage Interconnect | Wolf Tank Storage Interconnect |  | Lobo Station | Wolf Tank Storage WSL | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021136 | 2023-11-01 |  | 138 | 0.2 | 0 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 80221 | Y |  |  | 0 | 69484 | 69483
68229 | Penumbra: Build new 345 kV Station | Interconnect Montgomery Ranch Wind to the Avogadro to Edith Clarke 345 kV line | Contact Update | Penumbra |  | Planned |  | AEP TNC | Adam Wells mlforcum@aep.com 918-599-2674 |  | 2023-11-15 |  | 345 | 0 | 0 | 0 |  | Foard |  | Tier 4 |  |  |  |  | 60059, 60500, 60506, 60722 | Y | N |  | 0 | 68230 | 68229
45399 | Bearkat Loop - Bearkat to Longshore | Adds 345 KV line from Bearkat to Longshore. |  | Bearkat | Longshore | Planned |  | WETT/ONCOR | Yang Zhang yzhang@wettllc.com 737-218-4520 |  | 2023-11-16 |  | 345 | 27 | 0 | 0 |  | Glasscock | Howard | Tier 1 |  | 2017-08-15 | 2018-09-19 | 2018-10-09 | 1058, 59903 | Y | N |  | 0 | 45473 | 45399
69005 | Rapido: Build new 345 kV station | Construct new Rapido 345 kV station for the ETT 2nd circuits project |  | Rapido |  | Planned |  | ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021707 | 2023-11-17 |  | 345 | 0 | 0 | 0 |  | Starr |  | Tier 1 |  |  |  |  | 80227, 80381, 80355, 161855 | Y | Y |  | 0 | 69006 | 69005
50896 | Garnet: Build new 138 kV station | Interconnect Norton solar farm on the Ballinger to Oak Creek 138 kV line | Cost Update | Garnet |  | Planned | 1049 - 1222 | AEP TNC | Bryan Oyster mlforcum@aep.com 918-599-2674 | 2824 | 2023-11-23 |  | 138 | 0 | 0 | 0 |  | Runnels |  | Tier 4 |  |  |  |  | 60451, 6325, 6340 | Y | N |  | 0 | 50897 | 50896
69487 | Wahpekute: Build 69 kV temporary tap | Build new 69 kV temporary tap on the Jayton to Rotan 69 kV line. | Schedule Update | Wahpekute |  | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-282-8376 |  | 2023-11-29 |  | 69 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 60057, 6162, 6196 | Y |  |  | 0 | 69488 | 69487
50966 | North Shore: 345 kV (Chienere LNG) RPG | Construct Naismith 345/138 kV station with two (2) - 345/138 kV autos. Construct Angstrom to Grissom and Angstrom to Naismith 345 kV Lines. Construct Naismith to Resnik 138 kV Lines. |  | Naismith |  | Planned | 1063 - 1236 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2017032 | 2023-11-30 |  | 345 | 0 | 0 | 1350 |  | San Patricio |  | Tier 1 | 19RPG0016 |  |  |  | 8659, 8660 | Y | N |  | 0 | 69279 | 50966
51005 | Rocksprings to Friess Ranch: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line |  | Rocksprings | Friess Ranch | Planned | 1044 - 1217 | AEP TCC | Dave Baker mlforcum@aep.com 918-599-2674 | 2792 | 2023-11-30 |  | 69 | 0 | 22.6 | 0 |  | Edwards | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 8238, 60210 | Y | N |  | 0 | 51006 | 51005
54811 | Winecup: Build 69 kV station | Construct new 69 kV box bay on the North San Angelo to San Angelo Grape Creek Tap 69 kV line |  | Winecup |  | Planned | 1041 - 1268 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1858 | 2023-11-30 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 60796, 6459, 6465 | Y | N |  | 0 | 54812 | 54811
62041 | Twinwood 138kV Distribution Substation | Remove Twinwood Mobile (TWM) substation and install new Twinwood (TWN) 138kV Distribution Substation. Loop from existing Ckt.25E to create new Ckt.25E Foster to Twinwood to Peters |  | Twinwood | Foster/ Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 |  | 138 | 0.08 | 0 | 0 |  | Fort Bend | Austin | Tier 4 |  |  |  |  | 44860, 44256, 46220 | Y | N |  | 0 | 62042 | 62041
64069 | Charger Solar Interconnection | Connect the Charger Interconnection to the Angstrom to STP 345 kV line | Contact, Schedule Update | Angstrom | STP | Planned |  | AEP TCC | Teresa Trotman bcogan@aep.com 918 599 2857 | TP2021165 | 2023-11-30 |  | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 8676, 8678, 5915, 8249 | Y |  |  | 0 | 64070 | 64069
66221F | Galena Park Area Conversion Project | Rebuild GYPSUM customer substation for 138kV loop-tap service. Rebuild Galena Park substation for double tap service. Tap new GYPSUM substation (SPEAR) from Ckt.94 between TANKER and new Galena Park TR1 tap. |  | CITFIL | TANKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40613, 40731, 40751, 40630, 41172 | Y | N |  | Cost included in main entry | 66227 | 66221
69485 | Wahpekute: Build 69 kV Permanent Interconnection | Build New Box Bay with Capacitor Bank on Jayton to Rotan 69 kV Line | Schedule Update | Wahpekute |  | Planned |  | AEP | Michael Forcum mlforcum@aep.com 918-282-8376 |  | 2023-11-30 |  | 69 | 0 | 0 | 0 | 0,3.8 | Fisher |  | Tier 4 |  |  |  |  | 60057, 60066, 6162, 6196 | Y |  |  | 0 | 69486 | 69485
69900 | Eastgate (EAS) 138kV CNP Substation for XE Murat Solar (22INR0354) |  |  | Eastgate | Atascocita/Crosby | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40690, 40130, 40391 | Y | N |  | Loop Ckt.66E into new substation to create new Ckt.66 Crosby to Eastgate to Atascocita. | 69901 | 69900
70671 | Anson to Radium: Rebuild 69 kV Line | Rebuild Anson to Radium 69 kV Line |  | Anson | Radium | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2020038 | 2023-11-30 |  | 69 | 0 | 0 | 0 |  | Jones | Jones | Tier 4 |  |  |  |  | 6175, 6180 | Y |  |  | 0 | 70672 | 70671
71950 | Twin Buttes Load 138kV Circuit Breaker Addition | Install a new 138-kV transmission point of interconnection at Twin Buttes Substation. |  | Twin Buttes |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-11-30 |  | 138 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 | [5 empty] | Y | N |  | 0 | 71951 | 71950
72055 | Fort Bend 138kV Substation Expansion for Brazos Bend BESS (23INR0363) |  |  | Fort Bend |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 | [5 empty] | Y | N |  | 0 | 72056 | 72055
72061 | HO Clarke to Kirby Ckt.90A Upgrade to Limiting Section |  |  | HO Clarke | Kirby | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 |  | 138 | 0 | 6.78 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | 0 | 72062 | 72061
69283 | Naismith to Resnik: Build New 345 kV Line | Build New 345 kV Line from Naismith to Resnik |  | Naismith | Resnik | Planned | 1063 - 1236 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2017032 | 2023-11-30 12:00 |  | 138 | 3 | 0 | 0 |  | San Patricio | San Patricio | Tier 1 | 19RPG0016 |  |  |  | 8660, 8580 | Y | N |  | 0 | 69284 | 69283
50954 | Whitepoint: Add Second Auto | Whitepoint: Add Second Auto |  | Whitepoint |  | Planned | 1085 - 1258 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3805 | 2023-12-01 |  | 345 | 0 | 0 | 500 |  | San Patricio |  | Tier 4 |  |  |  |  | 8956, 8961 | Y | N |  | 0 | 50955 | 50954
54120 | Rebuild Tejas-Commanche (Bundled 795 ACSS) | Rebuild Tejas - Commanche 138 kV line with Bundled 795 ACSS conductor. |  | Tejas 138 kV Substation (Bus # 38530) | Commanche 138 kV Substation (Bus # 38560) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07318 | 2023-12-01 |  | 138 | 0 | 0.95 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38530, 38560 | Y |  |  | 0 | 54121 | 54120
55464 | Adds new Morrow sub near Pearsall | Adds new Morrow substation and short line from Morrow to the Pearsall substation |  | Pearsall | Morrow | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-12-01 |  | 138 | 0.91 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5896, 5895 | Y | N |  | 0 | 55465 | 55464
57906 | Laredo to University: Rebuild 138 kV Line | Rebuild Laredo to University 138 kV Line |  | Laredo | University | Planned | 1119 - 1297 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3838 | 2023-12-01 |  | 138 | 0 | 5.19 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645, 8647 | Y | N |  | 0 | 65579 | 57906
60502 | Rebuild Apache-Amoco with bundled 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38620, 38720 | Y |  |  | 0 | 60503 | 60502
60504 | Rebuild Caddo-Apache with bundled 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38710, 38720 | Y |  |  | 0 | 60505 | 60504
60522 | Rebuild Hidden Lakes-League City with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  | 0 | 60523 | 60522
60526 | Rebuild West Columbia Local-Angleton with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39530, 39560 | Y |  |  | 0 | 60527 | 60526
63906 | PEC_HeroWay_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Nameless and Leander and install 46.7 MVA distribution transformer. The new substation will be located approximately 3.1 miles (45% of existing line length) from Leander substation. |  | Nameless | Leander | Planned | 61279 | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 ryan.morlino@peci.com 830-868-5166 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7536, 7525, 7526 | Y | N |  | 0 | 70878 | 63906
65683 | To add Open Sky Station | To interconnect GINR 20INR0241 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2023-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68014, 68000, 68013 | Y | N |  | 0 | 65684 | 65683
66077 | Reconductor both Pecos-Cedarvale 138 kV ckts |  |  | Pecos (bus # 38091) | Cedarvale (bus # 38145) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 15.34 | 0 |  | Reeves | Ward | Tier 4 |  |  |  |  | 38091, 38145 | Y |  |  | 0 | 66078 | 66077
66118 | Reconductor TI-Lakepointe with 959 ACSS/TW |  |  | Lakepoint (bus # 37010) | TI (bus # 37080) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 2.78 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 37010, 37080 | Y |  |  | 0 | 66119 | 66118
66120 | Rebuild Freeway Park-Dickinson with bundled 795 ACSS |  |  | Freeway Park (bus # 38820) | Dickinson (bus # 38820) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 6.25 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38820, 38850 | Y |  |  | 0 | 66121 | 66120
66198 | Rebuild West Columbia Main-CNP West Columbia with bundled 795 ACSS |  |  | TNMP West Columbia Main (bus # 39500) | CenterPoint West Columbia (bus # 43380) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0.32 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 43380 | Y |  |  | 0 | 66199 | 66198
66204 | Rebuild Hidden Lakes-PH Robinson with bundled 795 ACSS |  |  | TNMP Hidden Lakes (bus # 38900) | CenterPoint PH Robinson (bus # 42015) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 3.15 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 42015 | Y |  |  | 0 | 66205 | 66204
66208 | Rebuild League City-Hidden Lakes with bundled 795 ACSS |  |  | Hidden Lakes (bus # 38900) | League City (bus # 38920) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 3.21 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  | 0 | 66209 | 66208
66368 | Rebuild West Columbia Main - Brazoria 138kV with 795 ACSS |  |  | West Columbia Main (bus # 39500) | Brazoria (bus # 39600) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 10.2 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 39600 | Y |  |  | 0 | 66369 | 66368
69908 | Install 138kV Capacitor Bank at FM524 |  |  | TNMP FM524 Substation (bus # 39703) |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39703 | Y |  |  | 0 | 69909 | 69908
71319 | Upgrade Pearsall Station | Upgrade Pearsall Station to breaker and a half |  | Pearsall | Pearsall | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5893, 5895 | Y |  |  | 0 | 71320 | 71319
44946 | CPSE_New_Scenic_Loop_138kV_Load_Serving_Station | The new Scenic Loop 138 kV load serving station will be looped into existing Ranchtown to LCRA (Menger Creek) 138 kV transmission line. The substation should be located south west of the existing Fair Oaks Ranch and north east of the existing Ranchtown substation. |  |  |  | Planned | S-0885 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0275 | 2023-12-01 20:00 |  | 138 | 9 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5363, 5358, 7665 | Y |  |  | 0 | 44947 | 44946
6749 | Rosata: Build 138kV Substation | Build new Rosata 138kV POD Switch on Coleto Creek to Kenedy 138kV Line |  | Rosata |  | Planned | 898 - 1076 | AEP TCC | James Lutz bcogan@aep.com 918-599-2857 | 3682 | 2023-12-14 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8153, 88153, 7241, 8162, 8186 | Y | Y |  |  | 14542 | 6749
58917 | Horizon 138 bus and line to Pearsall | Adds new Horizon Switch station to connect Horizon solar generation and a line to Pearsall |  | Horizon Swttch | Pearsall | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-12-14 |  | 138 | 0.4 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5897, 5895 | Y | N |  | 0 | 58918 | 58917
62448 | Rebuild Marlin 69 kV Switch | Rebuild Marlin 69 kV Switch |  | Marlin | Marlin | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1752 | 2023-12-14 |  | 69 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3418, 3638, 13639 | Y |  |  | 0 | 62658 | 62448
45670 | East Stiles - Rocky Road 138 kV Line | Upgrade the existing 138 kV line |  | East Stiles | Rocky Road | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8597 | 2023-12-15 |  | 138 | 0 | 7.1 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 23864, 23869 | Y |  |  | 0 | 71129 | 45670
45689 | Pronghorn - Salt Flat Road 138 kV Line | Upgrade the existing 138 kV line |  | Pronghorn | Salt Flat Road | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8642 | 2023-12-15 |  | 138 | 0 | 7.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23856, 23859 | Y |  |  | 0 | 71135 | 45689
48587 | Tesoro 345/138 kV Switch | Construct a new 345/138 kV switch (formerly known as Quail East) |  | Consavvy | Quail/Midessa South | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8634 | 2023-12-15 |  | 345 | 0 | 0 | 1200 |  | Midland | Midland | Tier 3 | 22RPG032 | 2022-10-11 | 2022-11-07 |  | 18540, 18541, 18542, 18543, 1124, 1125, 1139, 10004, 11016, 11028, 11139, 11387 | Y |  |  | 0 | 71111 | 48587
52247 | Marrs - Handley 69 kV Line Conversion to 138 kV | Convert the existing Marrs-Handley 69 kV line to 138 kV operation |  | Marrs SW | Handley | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5222 | 2023-12-15 |  | 138 | 2.2 | 13 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1952, 1968, 2158, 2159, 2160, 2161, 2162, 11952, 1950, 1951, 1967, 1969, 11950, 11951, 11967 | Y |  |  | 0 | 69011 | 52247
56350A | Burnett - Bowie 69 kV Line | Upgrade and convert Burnett-Ringgold Magnolia Tap Line from 69 kV to 138 kV |  | Burnett | Ringgold Magnolia Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2023-12-15 |  | 69 | 0 | 21 | 100 |  | Wichita | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 1452, 1505, 1543, 1544, 1545, 11540, 11541, 1426, 1491, 1524, 17010, 775, 33770 | Y | N |  | 0 | 68746 | 56350
59835 | Royse Switch-Terrell Switch 69 kV Line Conversion to 138 kV | Convert the existing 69 kV Line to 138 kV |  | Royse | Terrell | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3223 | 2023-12-15 |  | 69 | 0 | 0 | 0 |  | Rockwall | Rockwall | Tier 4 |  |  |  |  | 2722, 2773, 12722, 12730, 2463, 2471, 2472, 12729, 2721, 2729, 3188 | Y |  |  | 0 | 59836 | 59835
60094 | Convert Waco East - Elm Mott 69 kV Line to 138 kV | Convert Waco East - Elm Mott 69 kV Line to 138 kV and relocate the Waco East Substation to the double circuit line going towards Lake Creek/Waco West |  | Waco East | Elm Mott | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6147 | 2023-12-15 |  | 138 | 0 | 10 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3439, 3443, 3571, 3573, 13438, 3407, 3408, 3438 | Y |  |  | 0 | 62645 | 60094
61279A | Nameless to Leander Transmission Line Upgrade | Rebuild and upgrade Nameless to Hero Way with double-circuit capable structures and cut in Hero Way substation (ERCOT Project #63916). Install 1 ckt with bundled 795 kcmil conductor (440 MVA). Final span of conductor and terminal equipjment at Nameless will be upgraded to 440 MVA with ERCOT project #61279C. | 1/10/2023: Identified related substation project and added information to clarify timing for final circuit rating upgrade. | Hero Way | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7526, 7536 | Y | N |  | 0 | 70677 | 61279
62327 | Upgrade Fairfield West - Big Brown Tap 138 kV Line | Upgrade Fairfield West - Big Brown Tap 138 kV Line |  | Fairfield West | Big Brown Tap Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6138 | 2023-12-15 |  | 138 | 0 | 8 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 196, 3510 | Y |  |  | 0 | 62328 | 62327
62436 | Cedar Hill - Desoto Hampton Road 138 kV Line | Rebuild the existing 138 kV Line |  | Cedar Hill Switch | Desoto Hampton Road | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4175 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 3058, 3059, 3060, 3066, 3065 | Y |  |  | 0 | 62437 | 62436
62666 | Upgrade and convert McGregor - Waco West Line | Upgrade and convert McGregor - Waco West Line |  | McGregor Phillips | Waco West | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6172 | 2023-12-15 |  | 138 | 0 | 24.3 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3441, 3584, 3585, 3586, 3589, 3596, 3437, 3440, 3446, 3583, 3594 | Y |  |  | 0 | 62667 | 62666
62712 | Driver - Skywest 138 kV Line Rebuild | Rebuild the existing Driver - Skywest 138 kV Line |  | Driver | Skywest | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8564 | 2023-12-15 |  | 138 | 0 | 11.9 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 23863, 71210 | Y |  |  | 0 | 62716 | 62712
64310 | Cumby-Cumby Tap Line Conversion | Cumby - Cumby Tap Radial Line 69 to 138 kV Conversion. Project requires coordination with RCEC and TNMP. |  | Cumby Tap | Cumby Substation | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R944 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1812, 1813, 1815, 6861 | Y | N |  | 0 | 66059 | 64310
64382 | Bowman Auto 1 Upgrade | Upgrade existing Bowman Auto #1 300 MVA to 600 MVA. |  | Bowman | Bowman | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4021 | 2023-12-15 |  | 345 | 0 | 0 | 600 |  | Archer | Archer | Tier 3 | 22RPG008 | 2022-03-15 | 2022-04-15 |  | 1422, 1423, 29048 | Y | N |  | 0 | 64383 | 64382
65366 | Converts TNMP Lone Oak to 138 kV. | TNMP Lone Oak conversion projected to be ready by 5/15/2023. |  | Rayburn Loan Oak (Bus # 6871) | TNMP Loan Oak (Bus # 37360) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Rains | Rains | Tier 4 |  |  |  |  | 37360, 37361 | Y |  |  | 0 | 65367 | 65366
66178 | Centerville Switch - Centerville Road - Lake Hubbard Switch 138 kV Double-Circuit Line | Upgrade the existing 138 kV DCKT Line |  | Lake Hubbard | Centerville | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4127 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2439, 2450, 2917, 2918, 2401, 2402 | Y |  |  | 0 | 66179 | 66178
66186 | Carrollton Northwest - Carrollton East 138 kV Line | Terminate the existing Northlake - Carrollton East 138 kV Line at Carrollton Northwest |  | Carrollton East |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4205 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2362, 2363, 2385, 2578 | Y |  |  | 0 | 66187 | 66186
66210 | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV. Relocate the Lake Creek 138/69 kV Auto to Marlin. |  | Lake Creek | Marlin | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1743 | 2023-12-15 |  | 138 | 0 | 13.7 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3416, 3418, 3694, 3695, 3410, 13639 | Y |  |  | 0 | 66211 | 66210
66214 | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV |  | Brownwood | Firerock | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6164 | 2023-12-15 |  | 138 | 0 | 15.5 | 0 |  | Brown | Brown | Tier 4 |  |  |  |  | 1671, 1661, 1670, 1662, 6359, 6408 | Y |  |  | 0 | 66215 | 66214
66218 | Hillsboro - Italy 69 kV Line | Rebuild the existing 69 kV Line |  | Hillsboro Switch | Italy | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4326 | 2023-12-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2337, 2338, 3523 | Y |  |  | 0 | 66220 | 66218
66289A | Upgrade and convert Tyler - Athens 69 kV Line | Rebuild the Chandler West - STR 29/2 69 kV Line |  | Chandler West | Murchison | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6094 | 2023-12-15 |  | 69 | 0 | 21.3 | 0 |  | Henderson | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3236, 3240, 13235 | Y |  |  | 0 | 71921 | 66289
66532 | South Midland - Pronghorn 138 kV Line Rebuild | Add South Midland - Pronghorn 138 kV Line Rebuild |  | South Midland | Pronghorn | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8606 | 2023-12-15 |  | 138 | 9.9 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 1133, 11388, 23860, 23856 | Y |  |  | 0 | 66533 | 66532
66569 | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch |  | Mulberry Creek | Mulberry Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9022 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  | Jones | Jones | Tier 3 | 21RPG021 | 2021-12-17 | 2022-01-12 |  | 6235 | Y |  |  | 0 | 66570 | 66569
68754 | Buchanan Ranch 138 kV Expansion | Expand existing substation with additional transformers and capacitor bank |  | Buchanan Ranch | Buchanan Ranch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8616 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 11335, 23857, 23858 | Y |  |  | 0 | 68756 | 68754
68761 | Blue Acres - South Midland 138 kV Line | Upgrade the existing 138 kV Line |  | Blue Acres | South Midland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8617 | 2023-12-15 |  | 138 | 0 | 5.5 | 0 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 23857, 23860 | Y |  |  | 0 | 68764 | 68761
68768 | Buffalo - Triangle 138 kV Line | Upgrade the existing 138 kV Line |  | Buffalo | Triangle | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8618 | 2023-12-15 |  | 138 | 0 | 3.5 | 0 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 23837, 23839 | Y |  |  | 0 | 68770 | 68768
68780 | Triangle - Yosemite 138 kV Line | Upgrade the existing 138 kV Line |  | Triangle | Yosemite | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8626 | 2023-12-15 |  | 138 | 0 | 11.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11390, 23839, 23843, 23858 | Y |  |  | 0 | 68782 | 68780
68797 | Morgan Creek - Barber Lake East 138 kV Line | Upgrade the existing 138 kV Line |  | Morgan Creek | Barber Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8624 | 2023-12-15 |  | 138 | 0 | 4.83 | 0 |  | Mitchell | Mitchell | Tier 4 |  |  |  |  | 1032, 1190, 11393 | Y |  |  | 0 | 68845 | 68797
68804 | Loop Nine 345/138 kV Switch | Establish Loop Nine 345/138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4327 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  | Ellis | Dallas | Tier 3 | 22RPG014 | 2022-05-15 | 2022-06-15 |  | 12435, 22427, 123436, 123437, 2229, 2420, 2427, 2428, 2431 | Y |  |  | 0 | 69349 | 68804
68968 | North Edinburg to Tiempo: Build second circuit 345 kV line | Hang conductor to complete a double circuit between North Edinburg and Tiempo for the ETT 2nd circuits project |  | North Edinburg | Tiempo | Planned |  | ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021702 | 2023-12-15 |  | 345 | 78.52 | 0 | 0 |  | Hidalgo | Zapata | Tier 1 |  |  |  |  | 8383, 80224, 80227, 80231, 8574, 80355 | Y | Y |  | 0 | 68969 | 68968
69552 | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 345/138 kV Switch connected to LCRA POI (Limmer) |  | Hutto East | Hutto East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6165 | 2023-12-15 |  | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 13364, 3666, 3673, 7341 | Y |  |  | 0 | 69553 | 69552
71180 | Hutto - Brushy Creek 138 kV Line | Hutto - Hutto East (Teal) - Brushy Creek 138 kV Line |  | Hutto | Brushy Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6211 | 2023-12-15 |  | 138 | 11.6 | 10.4 | 0 |  | Williamson | Williamson | Tier 3 | 22RPG016 | 2022-05-01 | 2022-06-01 |  | 3362, 3541, 3673, 3666, 3692, 3693 | Y |  |  | 0 | 71181 | 71180
71190 | Einstein - St Lawrence 138 kV Line | Upgrade the existing 138 kV line |  | Einstein | St. Lawrence | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8646 | 2023-12-15 |  | 138 | 0 | 4.6 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 23852, 23854 | Y |  |  | 0 | 71192 | 71190
71193 | Blue Acres - Yosemite 138 kV Line | Upgrade the existing 138 kV line |  | Blue Acres | Yosemite | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8638 | 2023-12-15 |  | 138 | 0 | 5.9 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11335, 23858 | Y |  |  | 0 | 71195 | 71193
71196 | Grey Well Draw - Pecan Grove 138 kV Line | Rebuild existing 138 kV line |  | Grey Well Draw | Pecan Grove | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8640 | 2023-12-15 |  | 138 | 0 | 7.8 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23860, 23861 | Y |  |  | 0 | 71198 | 71196
71991 | Valley South 345 kV Reactors | Install new 345 kV reactors |  | Valley South |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3013 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1729 | Y |  |  | 0 | 71992 | 71991
71995 | Weatherford West 138 kV Switch Terminal Equipment | Upgrade terminal equipment at Weatherford West 138 kV Switch |  | Weatherford |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5519 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 512, 1589 | Y |  |  | 0 | 71996 | 71995
71997 | Collin Autotransformer #2 tertiary reactors | Install new reactors on Collin Autotransformer #2 |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4014 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  |  | 29578 | Y |  |  | 0 | 71998 | 71997
72002 | Anna Autotransformer #2 tertiary reactors | Install new reactors on Anna Autotransformer #2 |  | Anna |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4013 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  |  | 12374 | Y |  |  | 0 | 72003 | 72002
52318 | Royse Switch - Greenbriar Switch 138 kV Line | Upgrade the Royse Switch - Greenbriar Switch 138 kV Line |  | Royse | Greenbriar | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4292 | 2023-12-15 01:00 |  | 138 | 0 | 0 | 0 |  | Collin | Rockwall | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 2472, 2707, 2708, 12527 | Y |  |  | 0 | 52319 | 52318
62643 | Rebuild Waco East 138 kV Switch | Rebuild Waco East 138 kV Switch |  | Waco East | Waco East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6146 | 2023-12-16 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3439, 3481, 3482, 13438, 3438, 3434, 3443, 3452, 3551, 3559, 3573 | Y |  |  | 0 | 62664 | 62643
71164 | Haggerty-Bells 138 kV Line Section | Rebuild portion of Haggerty-Bells 138 kV Line Section |  | Haggerty | Bells | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4336 | 2023-12-16 |  | 138 | 0 | 0 | 0 |  | Grayson | Grayson | Tier 4 |  |  |  |  | 1753, 1699, 12677 | Y |  |  | 0 | 71165 | 71164
6216 | Bartlett Switch to Bartlett | Bartlett Switch to Bartlett |  | Bartlett Switch | Bartlett | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2023-12-28 |  | 69 | 0 | 2.7 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 114, 118 | Y |  |  |  | 13941 | 6216
1275 | Hawkins to Gainesville | Hawkins to Gainesville |  | Hawkins | Gainesville | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2023-12-30 |  | 69 | 0 | 6.72 | 80 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 705, 706, 33705, 33726, 707, 726 | Y |  |  | 0 | 67891 | 1275
50160 | Beeville to Goliad: Rebuild 69 kV Line | Rehab 69 kV Line from Beeville to Goliad |  | Beeville | Goliad | Planned | 961 - 1139 | AEP TCC | Eric Scott bcogan@aep.com 918-599-2857 | 3719 TA2018010 | 2023-12-31 |  | 69 | 0 | 22.21 | 0 |  | Bee | Goliad | Tier 3 | 19RPG008 | 2019-04-30 | 2019-05-30 |  | 8584, 8586, 8587 | Y | N |  | 0 | 65542 | 50160
57412 | GENRAL Substation Removal | Remove 69kV GENRAL substation from CNP service |  | GENRAL | Garden Villas | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 |  | 69 | 0 | 9.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47670, 42690, 47540 | Y | N |  | 0 | 61869 | 57412
66050 | 138 kV Fulshear Distribution Substation | Install Fulshear Distribution Substation to create Ckt.25 FOSTER to Fulshear to Twinwood. |  | Fulshear | FOSTER/Twinwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44750, 44230, 44256, 44860 | Y | N |  | 0 | 66051 | 66050
69489 | Shepley: Construct New Distribution Station | Shepley: Construct New Distribution Station |  | Victoria | Dupont Sw. | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-12-31 |  | 138 | 0 | 0 | 50 |  | Victoria |  | Tier 4 |  |  |  |  | 8719, 8143, 8172 | Y |  |  | 0 | 69490 | 69489
70633B | Burke to Eagles Nest Ckt.02J Upgrades | Upgrade Ckt.02K Eagles Nest to West Columbia as a Hardening upgrade |  | Eagles Nest | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 |  | 138 | 0 | 1.86 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42430, 43380 | Y | N |  | 0 | 72025 | 70633
71106 | Dunlavy to HO Clarke Ckt.40A Partial Reconductor | Reconductor portions of Ckt.40A Dunlavy to HO Clarke ahead of future 138kV conversions |  | Dunlavy | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 |  | 69 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47151, 47160, 47320, 47322, 47580 | Y | N |  | 0 | 71107 | 71106
72029A | Ashville (ASH) 138kV Station for SUNLIT/Dori BQ BESS (23INR0040) | Loop new CNP 138kV substation Ashville (ASH) into Ckt.06F Garden Villas to Holmes to create new Ckt.06 Garden Villas to Ashville to Holmes |  | Ashville | Garden Villas | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | 0 | 72030 | 72029
72029B | Ashville (ASH) 138kV Station for SUNLIT/Dori BQ BESS (23INR0040) | Install one generator lead from CNP 138kV substation Ashville (ASH) to SUNLIT/Dori BQ BESS |  | Ashville | SUNLIT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | 0 | 72031 | 72029
63834A | Alvin Area 138kV Conversions | Reconfigure existing Ckt.26H Archer to Karsten to create new Ckt.26H Archer to Manvel. |  | Karsten | Manvel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44430, 44440, 42570, 44410 | Y | N |  | 0 | 64472 | 63834
63834B | Alvin Area 138kV Conversions | Reconfigure existing Ckt.26B Rosharon to Karsten to create new Ckt.26B Manvel to Alvin tap to Karsten. |  | Manvel | Rosharon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42073, 44410, 44390, 44430 | Y | N |  | Cost in main project | 64473 | 63834
63834C | Alvin Area 138kV Conversions | Reconfigure existing Ckt.05B LIMBERG to Friendswood tap to Webster to create new Ckt.05B LIMBERG to Alvin tap to Friendswood tap. Rebuild Alvin substation for double-tap service. |  | LIMBERG | Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Harris | Tier 4 |  |  |  |  | 42072, 42651, 43280 | Y | N |  | Cost in main project | 64474 | 63834
63834D | Alvin Area 138kV Conversions | Rebuild portions of Ckt.53 Webster to Karsten to HO Clarke for 138kV Line Conversion. Retire the remaining portions of Ckt.53. Retire KR-A1 and WEB-A1 |  | Karsten | Webster/HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 00:04 |  | 69 | 0 | 0 | -300 |  | Brazoria | Harris | Tier 4 |  |  |  |  | 43510, 44400, 49022, 49087, 44440, 47160, 43500, 44390 | Y | N |  | Cost in main project | 64475 | 63834
66009 | CNP SNUG POI for COTTONWOOD Solar |  |  | SNUG | Liverpool/PETSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 12:00 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44890, 42870, 43070 | Y | N |  | 0 | 66010 | 66009
52260 | India to DWU Rebuild | India to DWU Rebuild |  | India | Dallas Water Utilities | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-01-01 |  | 69 | 0 | 0 | 0 |  | Ellis | Dallas | Tier 4 |  |  |  |  | 230, 2351 | Y |  |  | 0 | 52261 | 52260
63635 | Tribute: Build 138 kV Station | Build new 138 kV Station on the San Angelo Power to Red Creek 138 kV line |  | Tribute |  | Planned | 1132 - 1310 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1877 | 2024-01-01 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6442, 6473, 60008 | Y | N |  | 0 | 63636 | 63635
70550 | Create_GP_Solar_POI_Bus | Created GP Solar POI bus. |  | Glen Pine | Explorer | Planned |  | RYBRN | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2024-01-01 |  | 138 | 0 | 0 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 6802, 6829, 6833 | Y |  |  | 0 | 72028 | 70550
67919 | Avanzada: Build new 138 kV station | Connect Outpost Solar to the Lobo to Fowlerton 345 kV line |  | Lobo | Fowlerton | Planned |  | AEP TCC | Brandon K Cogan bcogan@aep.com 918-599-2857 |  | 2024-01-13 |  | 345 | 0.1 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80235, 5709, 80219 | Y |  |  | 0 | 67920 | 67919
59959 | CPSE_New_Old_Hickory_Switchyard | Build a new Old Hickory 345 switchyard to connect Old Hickory Solar plant. |  | 5133 | 5915 | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0303; S-0940 | 2024-01-18 20:00 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5323, 5133, 5915 | Y |  |  | 0 | 59960 | 59959
68928 | Project has been pushed back. | BPUB Waterport and BPUB Price Rd. Transmission Lines at BPUB Loma Alta Substation will be relocated to Sharyland Stillman Switchyard. |  | 59450, 59410 | 79601 | Planned |  | BPUB | Javier Martinez jamartinez@brownsville-pub.com 956-083-6530 |  | 2024-01-24 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 59410, 59450, 79601 | Y |  |  | 0 | 68929 | 68928
6934B | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0873 | 2024-01-31 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  |  | 5133 | Y |  |  |  | 14754 | 6934
63579 | Roby to Rotan: Rebuild 69 kV Line | Rebuild the Roby to Rotan 69 kV Line | Contact, Schedule Update | Roby | Rotan | Planned | 1130 - 1308 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1875 | 2024-01-31 |  | 69 | 0 | 8 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 6194, 6195, 6196 | Y | N |  | 0 | 63580 | 63579
70665A | Danek (DNK) CNP Sub for Remy Jade - 23INR0339 | New 138kV Danek (DNK) substation for generator interconnection to Remy Jade. Loop Ckt.08G into substation to create new Ckt.08 Crosby to Danek to Highlands tap |  | Danek | Crosby/Highlands | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40890, 40397, 40811 | Y | N |  | 0 | 70666 | 70665
70665C | Danek (DNK) CNP Sub for Remy Jade - 23INR0339 | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits |  | PSARCO | BIGVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0.83 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41300, 40190 | Y | N |  | 0 | 70668 | 70665
70665B | Danek (DNK) CNP Sub for Remy Jade - 23INR0339 | Upgrade Ckt.03G BIGVUE to Lyondell tap to increase thermal limits |  | BIGVUE | Lyondell | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40190, 41023 | Y | N |  | 0 | 70667 | 70665
72053 | Oasis 345kV Substation Expansion for SOHO BESS (23INR0419) | Expand 345kV Oasis substation for SOHO BESS (23INR0419). Reposition existing Ckts. 18B and 27B Oasis to Dow and Ckt.99E Meadow to Oasis. |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | 0 | 72054 | 72053
5206 | Brackettville to Escondido: Construct 138 kV line | Build a single circuit capable 138 kV circuit from Brackettville to Escondido station |  | Brackettville | Escondido | Planned | 762-0947 | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | 3570 TP2017041 | 2024-02-01 |  | 138 | 45 | 0 | 0 |  | Kinney | Maverick | Tier 2 | 16RPG001 | 2016-01-05 | 2017-01-20 | 2017-02-08 | 8252, 8260 | Y | N |  |  | 12865 | 5206
49572 | Goodlett to Quanah: Build a new portion of 69 kV line | Build new section of 69 kV line between Goodlett and Quanah |  | Goodlett | Quanah | Planned | 1022 - 1200 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2784 | 2024-02-01 |  | 69 | 6 | 0 | 0 |  | Hardeman |  | Tier 2 | 19RPG020 | 2019-11-01 | 2020-01-01 |  | 6052, 6051, 60446 | Y | N |  | 0 | 49573 | 49572
52670 | BEPC_20TPITXXXX_DowningStephenville |  |  | Stephenville | Carlton Switch | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-02-05 |  | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 286, 299, 295, 297, 294 | Y |  |  | 0 | 52671 | 52670
44963 | USAA Rebuild 138 kV Station | CPSE_USAA 138 kV Substation Rebuild and Line Reconfiguration. |  |  |  | Planned | S-0896 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0285 | 2024-02-09 |  | 138 | 0.6 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-10 |  |  | 5450, 5451, 5452, 5125, 5170, 5208, 5300, 5453 | Y |  |  | 0 | 44964 | 44963
66122 | Tiempo: Build new 345 kV terminal | Interconnect Redonda Solar to the Tiempo 345 kV station |  | Tiempo |  | Planned |  | ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022009 | 2024-02-15 |  | 345 | 0.1 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 80224, 80232 | Y |  |  | 0 | 66511 | 66122
6253 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-02-26 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9276, 9077, 9238 | Y |  |  |  | 13981 | 6253
61228 | AEN_McNeil__JustinLane__ckt_811_reconductor | Reconductor 3.98 miles of circuit to 3000 Amps. |  | McNeil [9080] | Justin Lane [9225] | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-02-28 |  | 138 | 0 | 3.98 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9080, 9225 | Y |  |  | 0 | 61229 | 61228
69902 | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. |  |  | MISSION | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 |  | 345 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  |  | 44920, 967, 44900 | Y | N |  |  | 69903 | 69902
70633A | Burke to Eagles Nest Ckt.02J Upgrades | Upgrade Ckt.02J Burke to Eagles Nest as a Hardening upgrade |  | Burke | Eagles Nest | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 |  | 138 | 0 | 4.59 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42410, 42430 | Y | N |  | 0 | 72024 | 70633
72059 | Hillje 345kV Substation Expansion for Ramsey Storage - Generator Interconnection to FLATLA (FLA) (21INR0505) |  |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 72060 | 72059
68254 | Friend Ranch: Build new 138 kV Terminal | Interconnect Blue Sky Solar to the Friend Ranch 138 kV Station |  | Friend Ranch |  | Planned |  | AEP TNC | Robert Younger mlforcum@aep.com 918-599-2674 |  | 2024-02-29 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 | [5 empty] | Y | N |  | 0 | 68255 | 68254
70889 | SA College Hills: Rebuild 69 kV Station | Rehab SA College Hills Station |  | SA College Hills |  | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-02-29 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6468, 6470 | Y |  |  | 0 | 70890 | 70889
70891 | Eola Tap: Rebuild 69 kV Line | Rehab Eola Tap 69 kV Line |  | Eola Tap | Eola | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-02-29 |  | 69 | 0 | 11.69 | 0 |  | Concho | Concho | Tier 4 |  |  |  |  | 6370, 6371 | Y | N |  | 0 | 70892 | 70891
70961A | Crosby Sub Exp for HOLY/Citadel BESS and Upgrades | Expand Crosby substation for HOLY/Citadel BESS generator interconnection (24INR0147). Reposition Ckt.08H to a new breaker position. |  | Crosby |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-29 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  | 0 | 70962 | 70961
70961B | Crosby Sub Exp for HOLY/Citadel BESS and Upgrades | Upgrade Ckt.66F Baytown to Baytown TR1 tap to increase thermal limits |  | Baytown | Baytown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-29 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40170, 40172 | Y | N |  | 0 | 70963 | 70961
69471 | Villa Cavazos: Station Work | Eval BESS Interconnect |  | La Palma | Military HWY | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-03-01 |  | 138 | 0.35 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 80229 | Y |  |  | 0 | 69472 | 69471
69479 | Radiant: Build new 345 kV Station | Lunis Creek Solar Interconnect |  | Angstrom | STP | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-03-01 |  | 345 | 0.2 | 0 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 8715, 5915, 8676 | Y |  |  | 0 | 69480 | 69479
63956 | Clear Crossing: Build 345 kV terminal | Interconnect HODL Ranch II at Clear Crossing 345 kV station | Project Title, Project Description, Schedule Update | Clear Crossing | HODL Ranch II | Planned | 1139 - 1317 | ETT | Michael Glueck mlforcum@aep.com 918-599-2674 | 1884 | 2024-03-15 |  | 345 | 0 | 0 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  |  | 60017, 60515 | Y | N |  | 0 | 63957 | 63956
50870 | Coleto Creek - Rosata: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Coleto Creek | Rosata | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3778 | 2024-03-16 01:00 |  | 138 | 0 | 15.3 | 0 |  | Goliad | Goliad | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8162, 8153 | Y | N |  | 0 | 50871 | 50870
70305 | Camp Elizabeth: Build new 69 kV station | Construct new 69 kV box bay station with capacitor bank on the College Hills West to Sterling City 69 kV line |  | Camp Elizabeth |  | Planned |  | AEP TNC | Lance Price mlforcum@aep.com 918-599-2674 |  | 2024-03-31 |  | 69 | 0 | 0 | 0 | 0,7.7 | Sterling |  | Tier 4 |  |  |  |  | 6436, 6641, 6417, 6435, 11352 | Y | N |  | 0 | 70306 | 70305
70623A | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04B Hudson to MONSAN to increase thermal limits |  | Hudson | MONSAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 138 | 0 | 2 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42100, 42940 | Y | N |  | 0 | 70624 | 70623
71004 | Julia CNP-Owned Sub for Melaza Solar (21INR0220) | Install new Julia (JUL) CNP substation for generator interconnection to Maleza Solar. Loop Ckt.72 into Julia substation to create new Ckt.72 Hillje to Julia to Blue |  | Julia | Hillje/Blue | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44220, 44060, 44200 | Y | N |  | 0 | 71005 | 71004
70623B | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04A Mustang Bayou to Hudson to increase thermal limits |  | Hudson | Mustang | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 00:01 |  | 138 | 0 |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42960, 42100 | Y | N |  | 0 | 70625 | 70623
70623C | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04 Danbury to Liverpool to Snug to increase thermal limits |  | Liverpool | Danbury/Snug | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 00:02 |  | 138 | 0 |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42870, 42875, 44890 | Y | N |  | 0 | 70626 | 70623
70623D | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04 Snug to PETSON to increase thermal limits |  | Snug | PETSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 00:03 |  | 138 | 0 |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44890, 43070 | Y | N |  | 0 | 70627 | 70623
48774 | Fincas: Construct New Distribution Station | Construct New Distribution Station on the Wormser to N. Laredo SW 138 kV Line |  | Gateway Tap West | Wormser | Planned | 1026 - 1204 | AEP TCC | Alison Scrobiao bcogan@aep.com 918-599-2857 | 3765 | 2024-04-01 |  | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8039, 8295, 8650 | Y | N |  | 0 | 48775 | 48774
50948 | Angstrom - Grissom: Build New Line | Angstrom - Grissom: Build New Line |  | Angstrom | Grissom | Planned | 1063 - 1236 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3797 | 2024-04-01 |  | 345 | 17 | 0 | 0 |  | San Patricio | Bee | Tier 1 |  |  |  |  | 8249, 8624 | Y | N |  | 0 | 50949 | 50948
52175 | Rising Star Area Conversions | This continues the Rising Star Area Conversions with Carlton Switch to Downing | Carlton to Downing 138 kV Conversion | Carlton | Downing | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-04-01 |  | 138 | 0 | 0 | 0 |  | Erath | Comanche | Tier 4 |  |  |  |  | 294, 281, 286, 297 | Y |  |  | 0 | 52176 | 52175
69473 | Jaguar: Construct New Distribution Station | Jaguar: Construct New Distribution Station |  | Magruder | Thomaston | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-04-01 |  | 138 | 0 | 0 | 40 |  | Victoria |  | Tier 4 |  |  |  |  | 8724, 8183, 8194 | Y |  |  | 0 | 69474 | 69473
70777 | Bunsen: Install Cap Bank | Bunsen Capacitor |  | Bunsen |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022722 | 2024-04-01 |  | 138 | 0 | 0 | 0 | 0,15.8 | Nueces |  | Tier 4 |  |  |  |  | 8459 | Y |  |  | 0 | 70778 | 70777
71954 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 |  | Orange Grove | Talitha | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-04-01 |  | 138 | 0.73 | 0 | 0 |  | Jim Wells | Jim Wells | Tier 4 |  |  |  |  | 5661, 5660 | Y |  |  | 0 | 71955 | 71954
71982 | Upgrade Orange Grove station | Upgrade Orange Grove stationto ring bus |  | Orange Grove | Orange Grove |  |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-04-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  | 0 | 71983 | 71982
61279B | Nameless to Leander Transmission Line Upgrade | Rebuild and upgrade Leander to Hero Way with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA). |  | Leander | Hero Way | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-04-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7525, 7536 | Y | N |  | 0 | 70678 | 61279
65837 | New Cachena Substation |  |  | 5133 | 5323 | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2024-04-15 |  | 345 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 5068, 5133, 5323 | Y |  |  | 0 | 65838 | 65837
62652 | Removing 69kV BES elements from BPUB Airport Substation. | BPUB plans to remove the 138/69kV transformer and 69kV bus at Airport Substation. BPUB will be upgrading to a 138/12.5kV transformer. |  | 59460 | 59460 | Planned |  | BPUB | Javier Martinez jamartinez@brownsville-pub.com 956-083-6530 |  | 2024-04-18 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5946, 59460 | Y |  |  | 0 | 62653 | 62652
55470 | Bison to Ozona: Rebuild 69 kV line | Rehab 69 kV line from Bison to Ozona |  | Bison | Ozona | Planned | 1095 - 1273 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1863 | 2024-04-22 |  | 69 | 0 | 27 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  |  | 6549, 6560, 60395 | Y | N |  | 0 | 65570 | 55470
52068 | Pleasanton to Three Rivers: Rebuild 69 kV line | Convert Pleasanton to Three Rivers 69 kV line and Coy City Tap to Fashing 69 kV line to 138 kV, reterminate Pleasanton to Three Rivers into 138 kV yards at Pleasanton and Three Rivers, install new terminal for the Trumbo line at Pleasanton, and convert Fashing, Coy City Tap, and Schottky stations to 138 kV |  | Pleasanton | Three Rivers | Planned | 1077 - 1250 | AEP | Nathan Cowan bcogan@aep.com 918-599-2857 | 3802 TP2020193 | 2024-04-30 |  | 138 | 8.46 | 0.06 | 0 |  | Atascosa | Live Oak | Tier 4 |  |  |  |  | 8406, 8507, 8599, 8600, 84061, 85071, 85991, 86001, 8142, 8199, 8200, 8203, 8400, 8403, 88507 | Y | N |  | 0 | 65610 | 52068
59197 | Mason to Mason Switch: Rebuild 69 kV Line | Rehab the Mason to Mason Switch 69 kV Line | Project Title, Project Description Update | Mason | Mason Swicth | Planned | 1126 - 1304 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 1871 | 2024-04-30 |  | 69 | 0 | 10.3 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6394, 60458, 6393, 6396, 6407 | Y | N |  | 0 | 59198 | 59197
69281 | Angstrom to Naismith: Build New 345 kV Line | Build New 345 kV Line from Angstrom to Naismith |  | Angstrom | Naismith | Planned | TP2020205 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-04-30 |  | 345 | 19 | 0 | 0 |  | San Patricio | San Patricio | Tier 1 | 19RPG0016 |  |  |  | 8249, 8659 | Y | N |  | 0 | 69282 | 69281
72042 | Oasis 345kV Substation Expansion for SMT Ironman BESS (24INR0265) | Expand 345kV Oasis substation for SMT Ironman BESS (24INR0265) |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-04-30 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | 0 | 72043 | 72042
61274B | PEC_MarshallFord_Paleface_StormHardening | Rebuild single circuit section of Paleface to Marshal Ford and reconductor with single 959 ACSS Conductor, 380 MVA; Reconductor triple circuit section in conjunction with LCRA TSC Storm Hardening project (ERCOT Project #62068) with Single Suwanee Conductor. | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC/LCRATSC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-05-01 |  | 138 | 0 | 11.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7477, 77356 | Y | N |  | 0 | 63833 | 61274
61274A | PEC_MarshallFord_Paleface_StormHardening | Rebuild single circuit section of Paleface to Marshal Ford and reconductor with Single 959 ACSS Conductor, 380 MVA; | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-05-01 |  | 138 | 0 | 3.65 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7477, 77356 | Y | N |  | 0 | 63793 | 61274
64021 | Texana Solar Interconnection | Connect the Texana Solar to the El Campo to Victoria 138 kV line |  | El Campo | Victoria | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020888 | 2024-05-01 |  | 138 | 0 | 0 | 0 |  | Wharton | Victoria | Tier 4 |  |  |  |  | 8192, 8675, 8099, 8102 | Y |  |  | 0 | 64022 | 64021
70371 | D'Hanis Capacitor | Add 9.6 MVAR cap at D'Hanis |  | D'Hanis |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-05-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5814 | Y | N |  | 0 | 70372 | 70371
70373 | Driscoll Capacitor | add 19.2 MVAR capacitor at Driscoll |  | Driscoll |  |  |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-05-01 |  | 69 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5640 | Y |  |  | 0 | 70374 | 70373
70884 | Rebuild Rio Colorado - Bay City | Rebuild Rio Colorado - Bay City 795 ACSR |  | Rio Colorado | Bay City | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-05-01 |  | 69 | 0 | 9.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5560, 5563 | Y |  |  | 0 | 70885 | 70884
71930 | Upgrade RIOHONDO to BURNS line | Upgrade RIOHONDO to BURNS line to be 478MVA capable |  | Rio Hondo | Burns | Planned | 7192671928 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-05-01 |  | 138 | 0 | 12.2 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5763, 8319 | Y |  |  | 0 | 71931 | 71930
5467 | Nacogdoches Southeast_Redland 345kV Line | Establish a new 345kV Line between Nacogdoches Southeast Switch and Redland Switch |  | Nacogdoches Southeast | Redland | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6075 | 2024-05-14 |  | 345 | 13.4 | 0 | 0 |  | Nacogdoches | Angelina | Tier 2 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3119, 3321 | Y | N |  |  | 13171 | 5467
5466 | Redland Switch 345/138 kV Autotransformer | Install new 345/138 kV Autotransformer at Redland Switch previously known as Herty North |  | Redland | Redland | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6076 | 2024-05-15 |  | 345 | 0 | 0 | 600 |  | Angelina | Angelina | Tier 3 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3319, 3321, 3322 | Y | N |  |  | 13170 | 5466
47428 | Bellville South - Prairie View Transmission Line Upgrade | The proposed project converts the existing 69-kV transmission line T283 from Bellville South - Quanex Switch - Sunnyside Prairie View Substation to 138-kV. The proposed project improves the reliability of transmission facilities on the 26.1-mile transmission line and increases the line capacity for long term system growth. |  | Bellville South | Prairie View | Conceptual |  | SBEC | James Jouett jjouett@sbec.org 979-413-7714 |  | 2024-05-15 |  | 69 | 0 | 0 | 0 |  | Austin | Waller | Tier 3 |  |  |  |  | 7269, 7660, 7664, 7666 | N | N |  | 0 | 47429 | 47428
50710 | Quartz Sand 138 kV Switch | Construct a new 138 kV switch |  | Spraberry | Polecat Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8670 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 1328 | Y |  |  | 0 | 71170 | 50710
50725 | Coalson Draw 138 kV Switch | Construct a new 138 kV switch |  | Culberson | Sand Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8658 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 11078, 11086, 11114 | Y |  |  | 0 | 71163 | 50725
51225 | Driver - Hadacol Corner 138 kV Line | Upgrade the existing 138 kV line |  | Driver Tap | Hadacol Corner | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8637 | 2024-05-15 |  | 138 | 0 | 3.2 | 0 |  | Midland | Reagan | Tier 4 |  |  |  |  | 23863, 23867 | Y |  |  | 0 | 71134 | 51225
52728 | Add Foundry 138 kV Switch | Oncor's portion of AEP's Crane Area Transmission Project |  | LCRA Arco Crane | Navajo Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8502 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  | 2019-06-01 | 2019-07-22 |  | 10002, 11202, 60448, 71199 | Y |  |  | 0 | 52730 | 52728
53968 | Fayetteville_Salem_TransmissionLine_Rehabilitation | Increase the reliability of transmission facilities on the T177 Fayetteville to Salem 138-kV and T211 FPP Yard #1 to Salem 345-kV 19.3-mile double-circuit transmission line by replacing the existing Condor conductor from Fayetteville Substation to Salem Substation. |  | Fayetteville | Salem | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 345 | 0 | 19.3 | 0 |  | Fayette | Washington | Tier 3 | 22RPG011 | 2022-04-19 |  |  | 7056, 7286, 7058, 7289 | Y | N |  | 0 | 53969 | 53968
56350B | Burnett - Bowie 69 kV Line | Upgrade Ringgold Magnolia Tap-Bowie 69 kV Line |  | Bowie | Ringgold Magnolia Tap | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2024-05-15 |  | 69 | 0 | 21 | 0 |  | Montague | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 1540, 1547, 1548, 1549, 1550, 11548, 11550, 17010, 632, 768, 33770, 11582 | Y | N |  | 0 | 68747 | 56350
59745 | Royse Switch - Oates (GP&L) 138 kV Line | Upgrade existing 138 kV Line |  | Royse | Oates | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4236 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Rockwall | Dallas | Tier 4 |  |  |  |  | 831, 2472, 2733, 2735, 2736, 2739, 12703, 12735 | Y |  |  | 0 | 59746 | 59745
61356 | Hays Energy-Henne Split Transmission Line Upgrade | This project will increase the reliability and capacity of the transmission facilities on the T389 Bergheim to Hays Energy 5.4-mile 345-kV section of transmission line by replacing the aging conductor from Hays Energy Substation to Henne Split. |  | Hays Energy | Henne Split | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 345 | 0 | 5.4 | 0 |  | Hays | Comal | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7043, 7770 | Y | N |  | 0 | 61357 | 61356
61362 | Henne-River Oaks Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the 2.4-mile T237 River Oaks to Henne 138-kV and T389 Bergheim to Hays Energy 345-kV double-circuit transmission line between River Oaks Substation and Henne Split and the 1.4-mile T237 River Oaks to Henne 138-kV single-circuit transmission line between Henne Split and Henne Substation by replacing the aging conductors. |  | Henne | River Oaks | Planned | 61406, 61358, 61392, 61350, 61234, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 345 | 0 | 3.8 | 0 |  | Comal | Comal | Tier 4 | 22RPG005 | 2022-03-04 |  |  | 7173, 7770, 7043, 7172 | Y | N |  | 0 | 61363 | 61362
61400 | Esperanza-Fair Oaks Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the 4.3-mile T503 Esperanza to Fair Oaks Ranch 138-kV and T656 Bergheim to Kendall 345-kV double-circuit transmission line between Esperanza Substation and existing structure #173 and the 0.12-mile T506 Fair Oaks to Fair Oaks Ranch 138-kV and T656 double-circuit transmission line between Fair Oaks Substation and structure #173B by replacing the aging conductors. |  | Esperanza | Fair Oaks | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 345 | 0 | 4.42 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 5470, 7710, 7770, 7046, 7169 | Y | N |  | 0 | 61401 | 61400
61402 | Boerne-Esperanza Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the 1.7-mile T657 Boerne to Esperanza 138-kV and T656 Bergheim to Kendall 345-kV double-circuit transmission line between Boerne Split and Esperanza Substation and the 2.2-mile T657 Boerne to Esperanza 138-kV and T228 Boerne to Welfare double-circuit transmission line between Boerne Substation and Boerne Split by replacing the aging conductors. |  | Boerne | Esperanza | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 345 | 0 | 3.9 | 0 |  | Kendall | Kendall | Tier 4 | 22RPG005 | 2022-03-04 |  |  | 7153, 7168, 7770, 7046, 7710 | Y | N |  | 0 | 61403 | 61402
61436 | Bastrop West - Split Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 2.4-mile portion of Bastrop West ¿ Sim Gideon (T410) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Bastrop West | Sim Gideon | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7555, 7310 | Y | N |  | 0 | 61437 | 61436
61438 | Sim Gideon - Tahitian Village Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 5.1-mile Sim Gideon ¿ Tahitian Village (T648) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Sim Gideon | Tahitian Village | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7310, 7575 | Y | N |  | 0 | 61439 | 61438
61457 | Nada - Ricebird Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 13.1-mile Nada ¿ Ricebird (T588) 138-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Nada | Ricebird | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Colorado | Wharton | Tier 4 |  |  |  |  | 78103, 78104 | Y | N |  | 0 | 61458 | 61457
61463 | Marshall Ford - McNeil Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 14.2-mile Marshall Ford ¿ McNeil (T197) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Marshall Ford | McNeil | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 | 22RPG018 |  | 2022-07-08 |  | 7356, 7334 | Y | N | 22RPG018 reclassified as Teir 4 neutral by REPG review on 1/08/2022 | 0 | 61464 | 61463
61465 | Starcke - Wirtz Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 6.7-mile Starcke - Wirtz (T654) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Starcke | Wirtz | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  |  | 7351, 7104 | Y | N |  | 0 | 61466 | 61465
63933 | Cedar Crest 69 kV Substation Conversion To 138 kV | Convert Cedar Crest 69 kV Substation To 138 kV |  | Cedar Crest |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4193 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2486, 12486, 2495, 2982, 2985, 2493, 2494 | Y |  |  | 0 | 68789 | 63933
66188 | Cedar Crest - Dealey - West Levee 138 kV Line | Upgrade the existing 138 kV Line |  | Ceadr Crest | West Levee | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4212 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2493, 2842, 2400 | Y |  |  | 0 | 66189 | 66188
66289B | Upgrade and convert Tyler - Athens 69 kV Line | Rebuild the Chandler West - Tyler 69 kV Line and STR 29/2 - Forest Grove Line and convert to 138 kV |  | Tyler | Forest Grove | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6094 | 2024-05-15 |  | 138 | 3.7 | 13 | 0 |  | Smith | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3142, 3236, 3239, 3240, 3288, 13235, 3126, 3131, 3197, 3238, 3248, 3256, 3269, 3270, 3247, 3801 | Y |  |  | 0 | 68779 | 66289
66473 | Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line | Upgrade the Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line |  | Mesquite East | Oates | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4137 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 831, 2742, 2747, 2756, 2764, 2765, 2766, 2767 | Y |  |  | 0 | 66475 | 66473
66567 | Add Wolf - Moss 138 kV Line Rebuild | Add Wolf - Moss 138 kV Line Rebuild |  | Wolf | Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8530 | 2024-05-15 |  | 138 | 0 | 34.5 | 0 |  | Ward | Ector | Tier 3 | 22RPG013 | 2022-05-11 | 2022-06-03 |  | 1013, 1019, 1292, 11292, 11293 | Y |  |  | 0 | 66568 | 66567
67377 | Upgrade Bowman Autotransfomer 2 | Upgrade existing Bowman Auto #2 300 MVA to 600 MVA. |  | Bowman | Bowman | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4026 | 2024-05-15 |  | 345 | 0 | 0 | 600 |  | Archer | Archer | Tier 3 | 22RPG008 | 2022-03-29 | 2022-04-15 |  | 1422, 1424, 29050 | Y | N |  | 0 | 67378 | 67377
68955 | Meteor 345 kV Switch | Establish Meteor 345 kV Switch |  | Wolf | Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8619 | 2024-05-15 |  | 345 | 0 | 0 | 0 |  | Ward | Ector | Tier 4 |  |  |  |  | 10012, 1018, 11010 | Y |  |  | 0 | 68957 | 68955
69345 | LCRATSC_Limmer_Substation_Addition | Construct a new LCRA TSC-owned Limmer Substation in the Hutto to Zorn 345 kV line approximately 3 miles east of Hutto. Limmer Substation will be installed initially as a five-breaker 345 kV breaker-and-a-half arrangement. |  | Zorn, Hutto | Limmer | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org +151-257-84514 |  | 2024-05-15 |  | 345 | 0 | 0 | 0 |  | Williamson | Travis | Tier 3 | 22RPG027 | 2022-08-29 |  |  | 7341, 3696, 7042, 7340 | Y | Y |  | 0 | 69346 | 69345
69352 | Pebble Creek - Desoto 138 kV Line | Rebuild the Pebble Creek - Desoto 138 kV Line |  | Desoto | Pebble Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4328 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 | 22RPG014 | 2022-05-15 | 2022-06-15 |  | 2229, 2328, 2424 | Y |  |  | 0 | 69353 | 69352
70190 | LCRATSC_Cuero_Substation_Upgrade | Increase the reliability of substation equipment at the Cuero Substation by converting the station bus layout from single bus single breaker to a breaker and a half configuration, replacing obsolete and/or aged equipment, upgrade facility structures as required, and installing a new control enclosure to adhere to high wind requirements. Contingency Update |  | Cuero | Cuero | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | DeWitt | DeWitt | Tier 4 | [5 empty] | Y | Y |  | 0 | 70191 | 70190
70200 | LCRATSC_ChiefBrady_RoundRock_TL_Upgrade | LCRA TSC will upgrade T378 Chief Brady - Round Rock 138-kV transmission line to achieve a higher operational rating. |  | Chief Brady | Round Rock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 5.1 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3668, 7366 | Y | N |  | 0 | 70201 | 70200
70354 | LCRATSC_WolfLane_Substation_Upgrade | Upgrade Wolf Lane Substation to a 3000 A, 138-kV ring bus arrangement. Contingency Update |  | Wolf Lane |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 | [5 empty] | Y | Y |  | 0 | 70355 | 70354
70361 | Seward Junction capacitor bank addition | Install 31.2 Mvar capacitor bank at Seward Junction. |  | Seward Junction |  | Planned |  | PEC | Joshua Rivers Joshua.Rivers@peci.com (830) 330-4192 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson |  | Tier 4 |  |  |  |  | 7524 | Y | Y |  | 0 | 70362 | 70361
70363 | Highway 32 capacitor bank addition | Install 31.2 Mvar capacitor bank at Highway 32. |  | Highway 32 |  | Planned |  | PEC | Joshua Rivers Joshua.Rivers@peci.com (830) 330-4192 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 | 0,31.2 | Hays |  | Tier 4 |  |  |  |  | 7546 | Y | Y |  | 0 | 70364 | 70363
70534 | LCRATSC_Hueco_Springs_Sub_Add | NBU is constructing a new 138-kV substation to serve a new residential development. LCRA TSC will provide transmission service to the new load serving substation on the T235 Henne to Comal. |  | Henne | Comal | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7179, 7174, 7176 | Y | N |  | 0 | 70535 | 70534
70704 | PEC_Florence_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Andice and Glasscock and install 46.7 MVA distribution transformer. The new substation will be located approximately 4.87 miles from Glasscock substation. |  | Andice | Glasscock | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7521, 7522, 7523 | Y | N |  | 0 | 70705 | 70704
70900A | Roanoke Area Upgrades | Establish Keller Wall Price 138 kV Switch |  | Keller Wall Price | Keller Wall Price | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 12043, 12044, 12045, 12046, 566, 2027, 2034, 2037, 2038, 12034, 12033 | Y | N |  | 0 | 72013 | 70900
70922 | LCRATSC_ChiefBrady_Georgetown_TL_Upgrade | LCRA TSC will upgrade T355 Chief Brady - Georgetown 138-kV transmission line to achieve a higher operational rating. |  | Chief Brady | Georgetown | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 3 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7343, 7366 | Y | N |  | 0 | 70923 | 70922
70977 | Ozark Trail 345 kV Switch | Establish Ozark Trail 345 kV Switch to provide a POI for Hornet Solar |  | Ogallala | Tule Canyon | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8027 | 2024-05-15 |  | 345 | 0 | 0 | 0 |  | Castro | Swisher | Tier 4 |  |  |  |  | 23901, 23912, 23914 | Y |  |  | 0 | 70980 | 70977
71130 | Centerville Switch - Lake Hubbard Switch 138 kV Double-Circuit Line | Upgrade the existing 138 kV Double-Circuit Line |  | Lake Hubbard | Centerville | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4126 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2439, 2450, 2401, 2402 | Y |  |  | 0 | 71131 | 71130
71172 | Luther - Vealmoor 138 kV Line | Upgrade the existing 138 kV line |  | Luther | Vealmoor | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8636 | 2024-05-15 |  | 138 | 0 | 10 | 0 |  | Borden | Howard | Tier 4 |  |  |  |  | 23831, 23835 | Y |  |  | 0 | 71174 | 71172
71199 | Yucca Drive - Moss 138 kV Line | Rebuild existing 138 kV line |  | Yucca Drive | Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9047 | 2024-05-15 |  | 138 | 0 | 35.2 | 0 |  | Ector | Winkler | Tier 4 |  |  |  |  | 11015, 1009, 1019, 11128 | Y |  |  | 0 | 71201 | 71199
71948 | LCRATSC_Copperas_Copperas_TL_Overhaul | LCRA TSC will perform an overhaul on the 2.4-mile portion of Copperas Cove Oncor – Copperas Cove PEC (T393) 138-kV transmission line between Copperas Cove PEC Substation and Oncor Tie existing structure #35/8. |  | Copperas (ONCOR) | Copperas (PEC) | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 3 | 0 |  | Coryell | Coryell | Tier 4 | [5 empty] | Y | N |  | 0 | 71949 | 71948
57726 | Commerce - Royse 69 kV Line Conversion to 138 kV | Convert existing 69 kV Line to 138 kV |  | Commerce Switch | Royse | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R985 | 2024-05-15 01:00 |  | 138 | 0 | 38.3 | 0 |  | Hunt | Rockwall | Tier 3 | 20RPG023 | 2020-12-23 | 2021-01-19 |  | 1818, 1821, 1824, 1826, 1827, 1828, 1829, 1830, 1831, 1837, 2463, 6944, 1816, 2472, 1820 | Y | N |  | 0 | 60030 | 57726
59525 | Cedar Crest Switch - Wall Street 69 kV Line Section Conversion To 138 kV | Convert existing 69 kV Line to 138 kV operation |  | Cedar Crest | Wall Street | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4071 | 2024-05-16 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2982, 2983, 12486, 2486, 2972, 2975, 2493, 2976, 2977 | Y |  |  | 0 | 68717 | 59525
71136 | Waxahachie-Waxahachie OCF 69 kV Line Rebuild | Rebuild the existing Waxahachie-Waxahachie OCF 69 kV Line |  | Wilmer | Waxahachie | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4339 | 2024-05-16 |  | 69 | 0 | 0 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  |  | 2335, 2343 | Y |  |  | 0 | 71137 | 71136
64856 | North Edinburg to Palmito: Build second circuit 345 kV line | Hang conductor to complete a double circuit between North Edinburg and Palmito for the ETT 2nd circuits project |  | North Edinburg | Palmito | Planned |  | ETT/SHARYLAND | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021701 | 2024-05-19 |  | 345 | 48 | 0 | 0 |  | Hidalgo | Cameron | Tier 1 |  |  |  |  | 8383, 79500 | Y | Y |  | 0 | 68950 | 64856
50874 | Smith - Mathis: Line Rebuild | Smith - Mathis: Line Rebuild |  | Smith | Mathis | Planned | 1053 - 1226 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3781 | 2024-05-30 |  | 69 | 0 | 22.47 | 0 |  | San Patricio | San Patricio | Tier 3 | 20RPG001 |  |  |  | 8407, 8408, 8424, 8866 | Y | N |  | 0 | 65547 | 50874
55626 | Ganso to Hamilton Road: Rebuild 138 kV line | Rebuild 138 kV line from Ganso to Hamilton Road |  | Maverick | Hamilton Road | Planned | 1105 - 1283 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3824 | 2024-05-30 |  | 138 | 0 | 41.1 | 0 |  | Maverick | Val Verde | Tier 3 |  |  |  |  | 8267, 8692, 8255 | Y |  |  | 0 | 65576 | 55626
59099 | Blessing to Celanese: 138 KV Line Rebuild | Rebuild 138 kV Line from Blessing to Celanese |  | BLESSING | CELANESE BAY CITY | Planned |  | AEP | Glen Reed gareed@aep.com 918-599-2664 | TP2020227 | 2024-05-30 |  | 138 | 11.54 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 8116, 8121, 8191, 8558 | Y |  |  | 0 | 65587 | 59099
69467 | Dupont to Resnik:Rebuild138 kV line | Rebuild Dupont to Resnik 138 kV Line |  | Dupont | Resnik | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-05-30 |  | 138 |  | 0.83 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8422, 8580 | Y |  |  | 0 | 69468 | 69467
70675 | Aransas Pass- Rincon 138 kV: Line Upgrade | Upgrade 69 kV line between Aransas Pass and Rincon to 138 kV capable line. |  | Aransas Pass | Rincon | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022132 | 2024-05-30 |  | 69 | 0 | 16 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8421, 8668, 8416, 8418, 8430, 8427 | Y |  |  | 0 | 70676 | 70675
43212B | Caymus Capbanks in TNMP West Texas System | Expands Caymus Capacitor bank by 1 block of 20 Mvar. |  | Caymus (Bus #38410) | Caymus (Bus #38410) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07819 | 2024-05-31 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38410 | Y |  |  | 0 | 48414 | 43212
48415B | TransPecos Capbank in TNMP West Texas System | Expands TransPecos Capacitor bank by 1 block of 20 Mvar. |  | TransPecos (Bus #38377) | TransPecos (Bus #38377) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07919 | 2024-05-31 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38377 | Y |  |  | 0 | 48417 | 48415
50900 | Mason to North Brady: Rebuild 69 kV line | Rehab Mason to North Brady 69 kV line | Schedule Update | Mason | North Brady | Planned | 1046 - 1219 | AEP TNC | David Baker mlforcum@aep.com 918-599-2674 | 2794 | 2024-05-31 |  | 69 | 0 | 30.24 | 0 |  | Mason | McCulloch | Tier 3 | 19RPG019 | 2019-10-01 | 2019-11-01 |  | 6006, 6381, 6393, 6406, 60386 | Y | N |  | 0 | 65550 | 50900
55572 | Burma to Sterling City: Rebuild 69 kV Line | Rehab the Burma to Sterling City 69 kV Line | Project Title, Project Description Update | Burma | Sterling City | Planned | 1096 - 1274 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 1864 | 2024-05-31 |  | 69 | 0 | 32 | 0 |  | Tom Green | Sterling | Tier 3 | 20RPG021 | 2020-10-01 | 2020-11-01 |  | 6439, 6445, 6460, 61016, 61017, 6435, 6446, 6461, 60411 | Y | N |  | 0 | 55573 | 55572
57750 | Seabrook 138kV Distribution Substation | Build new 138kV Seabrook distribution substation. Double tap from Ckt.79F PH Robinson to Hanna and Ckt.96A PH Robinson to Bayou. |  | Seabrook |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42851, 42852, 42013, 42014, 42160, 42780 | Y | N |  | 0 | 57751 | 57750
57910 | Uvalde - West Batesville: Rebuild 138 kV Line | Rebuild the 20.61 mile Uvalde to West Batesville 138 kV line |  | Uvalde | West Batesville | Planned | 1117 - 1295 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3836 | 2024-05-31 |  | 138 | 0 | 20.6 | 0 |  | Uvalde | Zavala | Tier 4 |  |  |  |  | 8234, 8236 | Y | N |  | 0 | 65580 | 57910
59086 | Pulsar to Victoria: Rebuild 138 kV line | Rebuild 138 kV line from Pulsar to Victoria |  | Edna | Victoria | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020888 | 2024-05-31 |  | 138 | 0 | 42.76 | 0 |  | Jackson | Victoria | Tier 3 |  | 2022-02-22 | 2022-03-01 |  | 8118, 8172 | Y | N |  | 0 | 65585 | 59086
64581A | New 138kV Waterfowl substation | Reconfigure existing Ckt.02F (move Seadoc/Seaway onto other circuit) resulting in Ckt.36 COPPER to Booster tap to Jones Creek. |  | COPPER | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 43212, 43221, 48006, 5568, 42195, 42199, 42540, 43211, 42215, 43222 | Y | N |  | 0 | 64582 | 64581
69475 | Laredo area: Install cap banks | Install (1) 15.4 MVAR cap bank at Molina, (1) 15.4 MVAR and (1) 7.7 MVAR cap bank at Santo Nino, and (1) 23.0 MVAR cap bank at Wormser |  | Wormser | Molina | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8295, 8653, 80230 | Y |  |  | 0 | 69476 | 69475
70628 | Japhet 138kV Distribution Sub and Upgrades | Upgrade portions of 69kV Ckt.12 Garden Villas to Bringhurst to Clinton. Install new 138kV Japhet distribution substation. Move 69kV Bringhurst substation load to new Japhet substation and retire Bringhurst substation. Retire portions of Ckt.12 and convert the remaining portions of Ckt.12 to 138kV service. Loop new Japhet substation to create new 138kV Ckt.xx University to Japhet to Clinton. |  | Japhet | University/Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45070, 47540, 40350, 40352, 42690, 47760 | Y | N |  | 0 | 70629 | 70628
70742 | Pleak 35kV Distribution Substation | Install new Pleak (PLK) 138/35kV Distribution Substation. Loop from existing Ckt.89A to create new Ckt.89 Big Creek to Pleak to Fort Bend. Convert Needville to a breakered substation. |  | Pleak | Big Creek/Fort Bend | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42380, 44680, 42370, 42390, 44280 | Y | N |  | 0 | 70743 | 70742
70796 | El Campo to Pulsar: Rebuild 138 kV line | Rehab 138 kV Line from El Campo to Pulsar |  | El Campo | Pulsar | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TA2018020 | 2024-05-31 |  | 138 | 0 | 13.26 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8099, 8102, 8192 | Y |  |  | 0 | 70797 | 70796
70898 | Flomot Tap: Rebuild 69 kV Line | Rehab Flomot Tap 69 kV Line |  | Flomot Tap | Flomot | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-05-31 |  | 69 | 0 | 7.06 | 0 |  | Motley | Motley | Tier 4 |  |  |  |  | 6041, 6042 | Y | N |  | 0 | 70899 | 70898
72040 | Blueridge to WA Parish Ckt.02A Upgrades (22RPG041) |  |  | HO Clarke | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 9.08 | 0 |  | Harris | Harris | Tier 4 | 22RPG041 | 2022-11-21 | 2022-12-15 | 2022-12-15 |  | Y | N |  | 0 | 72041 | 72040
64581B | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Reconfigure existing Ckt.02F and install new conductor to create new Ckt.02 Jones Creek to Waterfowl |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 43470, 42540 | Y | N |  | Cost included in main entry | 64583 | 64581
67422B | Greens Bayou to Clinton 138kV Conversion | Reduce existing Greens Bayou cap bank CB1 from 120 MVAR to 100 MVAR |  | Greens Bayou | 0 | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 |  | 138 | 0 | 0 | 0 | 0,-20 | Harris | Harris | Tier 4 |  |  |  |  | 40717 | Y | N |  | 0 | 67529 | 67422
67422C | Greens Bayou to Clinton 138kV Conversion | Remove CASTEN |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 |  | 69 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 40250, 41570, 41681, 41682, 40352, 40720 | Y | N |  | 0 | 67530 | 67422
67422D | Greens Bayou to Clinton 138kV Conversion | Rebuild TEXWAL substation as 138kV breakered station. Rebuild Wallisville substation as 138kV loop-tap station. Expand Greens Bayou 138kV 'West' bus and Clinton 138kV station with new line positions. Reconfigure and connect new 138kV stations to create new 138kV Ckt.xx Greens Bayou to TEXWAL to Wallisville to Clinton. |  | Greens Bayou | Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 |  | 138 | 2.2 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41575, 41660, 40350, 40715 | Y | N |  | Cost included in Phase C | 67531 | 67422
64581C | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Convert customer-owned Seadoc and Seaway substations to loop service. Reconfigure existing Ckt.02F and reconnect Seadoc/Seaway to create new Ckt.02x Jones creek to Seadoc to Seaway to Waterfowl. |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 42540, 43211, 43222, 43470 | Y | N |  | Cost included in main entry | 64584 | 64581
64581D | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Remove existing Seaway Switchrack. Reconfigure existing Ckt.02F to create new Ckt.02y Waterfowl to Franklins Camp. |  | Waterfowl | Franklins Camp | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 5568, 43470 | Y | N |  | Cost included in main entry | 64585 | 64581
70660 | Plaza to Grant Ckt.08I Upgrade | Install parallel underground portion of Ckt.08I Plaza to Grant to increase thermal limits. |  | Plaza | Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:10 |  | 138 | 0 | 0.44 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47110, 47350 | Y | N |  | 0 | 70661 | 70660
65719 | Rebuild and reconductor portion of Missouri City to Sienna Ckt.05A as a Hardening upgrade |  |  | Missouri City | Sienna | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 12:00 |  | 138 | 0 | 3.7 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44482, 44652 | Y | N |  | 0 | 65720 | 65719
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures. Kramer Lane (KA) substation will be cut-into this line in 2023 |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2024-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238, 9276 | Y | N |  | Will add the ptoject to the base case. | 8207 | 1031
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0196 | 2024-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 9559 | 2308
3297 | Tezel Road - New 138kV Substation | Loop new 138 kV substation into the existing 138 kV Helotes to Bandera line. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2024-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5421, 5020, 5200 | Y |  |  | There are no transformers associated with this project | 10840 | 3297
45125 | Quintana Rd to South San Rebuild | Rebuild 1.3 miles of 138 kV transmission line form Quintana Rd substation to South San substation. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0271 | 2024-06-01 |  | 138 | 0 | 1.29 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-15 |  |  | 5350, 5385 | Y |  |  | 0 | 45126 | 45125
61394 | Portilla: 138 kV Station | Construct 4 breaker 138 kV ring bus expandable to a 6 breaker ring bus. The Portilla 138 kV Station will tie into the Lon Hill - Warburton 138 kV Line |  | Portilla |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | DP21X0008 | 2024-06-01 |  | 138 | 1.5 | 0 | 0 | 0,14.4 | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8046, 8924, 8027, 8920 | Y |  |  | 0 | 61395 | 61394
66113 | Add WalnutSpr Auto & 138kV Switchyard |  |  | Oncor Walnut Springs (Bus # 1646, 1647) | TNMP Walnut Springs (Bus # 37680, 37681) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2024-06-01 |  | 138 | 0 | 0 | 208.8 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 1647, 37681, 1646, 37680 | Y |  |  | 0 | 66115 | 66113
67093 | New 138 kV station cut-in between Garfield and Hi-Cross | New 138 kV Easton Park Substation cut-in on CKT963 from Garfield to Hi-Cross substation to serve BBEC Load |  | 9143 |  | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9143, 9071, 9147 | Y |  |  | 0 | 67094 | 67093
70798 | Stewart Road: Station work | Kiskadee Storage |  | Stewart Road | Kiskadee | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022166 | 2024-06-01 |  | 138 | 1 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 | [5 empty] | Y |  |  | 0 | 70799 | 70798
45501 | Eldorado Live Oak to Sonora: Rebuild 69 kV line | Rehab Eldorado Live Oak to Sonora 69 kV line |  | Eldorado Live Oak | Sonora | Planned | 982 - 1160 | AEP TNC | Dave Baker mlforcum@aep.com 918-599-2674 | 2769 | 2024-06-01 01:00 |  | 69 | 0 | 23.92 | 0 |  | Schleicher | Sutton | Tier 3 | 18RPG012 | 2018-12-18 | 2019-01-17 |  | 6498, 6505, 6509, 6510, 6513 | Y | N |  | 0 | 65530 | 45501
70012 | West Weatherford to Oran Voltage Conversion | West Weatherford to Oran Voltage Conversion |  | West Weatherford | Oran | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-06-03 |  | 138 | 0 | 0.1 | 0 |  | Palo Pinto | Parker | Tier 4 |  |  |  |  | 515, 518, 519, 785, 1571, 1585, 1589 | Y |  |  | 0 | 70013 | 70012
62693 | Courtney Creek - Yucca Drive 69 kV Line Conversion to 138 kV | Add Courtney Creek - Yucca Drive 69 kV Line Conversion to 138 kV |  | Courtney Creek | Yucca Drive | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8591 | 2024-06-15 |  | 69 | 0 | 44 | 0 |  | Pecos | Ward | Tier 3 | 22RPG025 | 2022-08-24 | 2022-09-16 |  | 1202, 1238, 1239, 11204, 11238, 11262, 1009, 1015, 1203, 1240, 1241, 1242, 11242, 1204, 11246, 11258, 60792 | Y |  |  | 0 | 64552 | 62693
66216 | Upgrade and convert Waco West - Temple 69 kV Line to 138 kV | Upgrade and convert Waco West - Temple 69 kV Line to 138 kV |  | Waco West | Temple | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6191 | 2024-06-15 |  | 138 | 0 | 31.4 | 0 |  | McLennan | Bell | Tier 4 | 22RPG046 | 2022-12-01 | 2023-01-01 |  | 147, 3437, 3544, 3578, 3580, 3581, 13436, 3446, 3644, 13662 | Y |  |  | 0 | 67582 | 66216
18TPIT0001 | Wiederstein Substation Transformer Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Wiederstein |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-06-28 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7461 | Y | N |  |  | 10675 | 3319
13TPIT0070 | Nash Creek Substation | Rebuild existing substation, and replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-06-28 |  | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7596 | Y | N |  |  | 10678 | 3322
61230 | Altair - Garwood Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 9.4-mile Altair ¿ Garwood (T542) (including all the tap lines) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Altair | Garwood | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-06-28 |  | 69 | 0 | 0 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  |  | 78106, 78530 | Y | N |  | 0 | 61231 | 61230
5940B | Mountain Home Substation and Transmission Line Addition | Cut-in the existing Gillespie to Fredericksburg 138-kV transmission line (T379) at Peach substation (converted to 138-kV, located adjacent to Live Oak substation), re-terminate and convert the existing 69-kV Harper to Live Oak transmission line to form 138-kV Headwaters to Peach transmission line, and connect the existing 69-kV Gillespie to Live Oak (T131) and existing Live Oak to Goehman Tap (T287) transmission lines to create a continuous 69-kV circuit from Gillespie to Goehman Tap. |  | Headwater | Goehman Tap. | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017394 | 2024-06-30 |  | 138 | 0 | 22.5 | 0 |  | Kerr | Gillespie | Tier 1 | 16RPG015 | 2016-11-18 |  |  | 7412, 7752, 7130, 7132, 7149, 7410, 7751, 7413 | Y | N |  | 0 | 61874 | 5940
70019 | Add 138kV Locust-Hickory line 700MVA |  |  | Locust | Hickory | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2024-06-30 |  | 138 | 0 | 1.85 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 922, 924 | Y | N |  | 0 | 70020 | 70019
70192 | LCRATSC_Doss_Headwaters_TL_Overhaul | LCRA TSC will perform an overhaul on the 14.2-mile Doss ¿ Headwaters (T508) 69-kV transmission line. |  | Doss | Headwaters | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org +151-257-84514 |  | 2024-06-30 |  | 69 | 0 | 14.2 | 0 |  | Gillespie | Gillespie | Tier 4 |  |  |  |  | 7408, 7410 | Y | Y |  | 0 | 70193 | 70192
48816 | Mulberry Creek: Rebuild 345 kV station | Rebuild Mulberry Creek 345 kV station and replace both autotransformers |  | Mulberry Creek |  | Planned | 1015 - 1193 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 2776 | 2024-06-30 01:00 |  | 345 | 0 | 0 | 900 |  | Jones |  | Tier 4 | 21RPG021 | 2021-12-15 | 2022-01-13 |  | 6230, 6231, 6232, 60788, 60789, 1435, 6235, 6287, 6288, 60040 | Y | N |  | 0 | 65536 | 48816
5430N | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line |  | Eagle |  | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 926 | Y | N | N/A | 0 | 55208 | 5430
5430O | Conversion to 138kV | Reconnect the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 930 | Y | N | N/A | 0 | 55209 | 5430
5430K | Conversion to 138kV | Construct new 138kV Hickory substation and terminate the existing Bonnie Brae - Hickory (which is already insulated for 138kV) at the new 138kV Hickory substation. |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 931 | Y | N | N/A | 0 | 55205 | 5430
70662 | Cobra: Build new 345 kV station | Interconnect Garcitas Solar to the Radiant to Static 345 kV line | Schedule Update | Radiant | Static | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022750 | 2024-07-15 |  | 345 | 0 | 0 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 8728, 8676, 8715 | Y |  |  | 0 | 70663 | 70662
70800 | Siete Wind Interconnection | New Station: Triada |  | Avanzada |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022749 | 2024-07-30 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8718, 80219, 80235 | Y |  |  | 0 | 70801 | 70800
64042 | Barrilla Junction: 69 kV Loop Rebuild | Rebuild Barrilla Junction to Saragosa to Cherry Creek to Verhalen to Hoefs Road stations, convert to 138 kV |  | Barrilla Junction | Hoefs Road Station | Planned | 1141 - 1319 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1886 | 2024-07-31 |  | 69 | 0 |  | 0 |  | Pecos | Reeves | Tier 3 | 21RPG023 | 2021-12-17 | 2022-01-14 |  | 6649, 6650, 6651, 6652, 6654, 60206, 60207, 60208, 60808, 6653, 60385, 60716, 69023, 69047 | Y | N |  | 0 | 64043 | 64042
49550 | Port Isabel: Rebuild As GIS Station | Rebuild Port Isabel as a GIS |  | Port Isabel |  | Planned | 958 - 1136 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3716 | 2024-08-01 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  | 0 | 49551 | 49550
61232 | RGEC Persimmon Gap Substation 69-kV Transmission Line Extension and Substation Expansion | Extend Alpine-Persimmon Gap 69-kV Transmission Line at Switch# 6669 and Install Circuit Switcher to accommodate new substation power transformer and distribution bays. New power transformer capacity will be 12/16/20 MVA. | Scheduled RUS Construction Work Plan Project | Persimmon Gap | Persimmon Gap | Planned |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2024-08-01 |  | 69 | 0 | 0 | 0 |  | Brewster | Brewster | Tier 4 | [5 empty] | Y | N |  | 0 | 61233 | 61232
72037B | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | Install generator lead from Seabreeze (SEB) substation to TANGLE (TNG) customer substation (23INR0054). |  | Seabreeze | TANGLE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-08-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | Cost included in main phase | 72039 | 72037
72037A | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | New 345kV Seabreeze (SEB) substation for generator interconnection to Tanglewood Solar (23INR0054). Loop Ckt.27B into Seabreeze substation to create new Ckt.27 DOW to Seabreeze to Oasis. |  | Seabreeze | DOW/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-08-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  | 0 | 72038 | 72037
50843 | Heron: Build 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line |  | Heron |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2796 | 2024-09-11 |  | 138 | 0 | 0 | 90 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60447, 60448, 6610, 6611, 6614 | Y | N |  | 0 | 50844 | 50843
66200B | Upgrade Taylor - Holland 69 kV Line | Rebuild the Bartlett Tap - Bartlett 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6173 | 2024-09-15 |  | 69 | 0 | 5.3 | 0 |  | Bell | Williamson | Tier 4 |  |  |  |  | 3647, 13647 | Y |  |  | 0 | 71895 | 66200
52179 | Rising Star Area Conversions | This converts Hasse to Downing to 138 KV |  | Downing | Hasse | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-10-01 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 277, 281, 1649 | Y |  |  | 0 | 52180 | 52179
70536 | New 138 kV Verde Circle Substation | New 138 kV Verde Circle Substation looping into existing 138 kV Westover Hills and VLSI line. |  |  |  | Planned | T-0316 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0971 | 2024-10-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5466, 5467, 5488 | Y |  |  | 0 | 70537 | 70536
44399 | South Padre Island: Rebuild as GIS station | Rebuild South Padre Island as a GIS |  | South Padre Island | - | Planned | 948 - 1126 | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | 3712 | 2024-10-15 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8335, 8917 | Y | N |  | 0 | 44400 | 44399
49564 | Mantle: Construct New 345 kV Station | Mantle: Construct New 345 kV Station |  | Bonilla | North Edinburg | Planned | 1035 - 1213 | AEP TCC | Joe Yeagler bcogan@aep.com 918-599-2857 | 3774 TP2018166 | 2024-10-18 20:00 |  | 345 | 0 | 0 | 0 |  | Cameron | Hidalgo | Tier 4 |  |  |  |  | 8059, 80598, 8383, 8573 | Y | N |  | 0 | 49565 | 49564
6719 | Twelvemile Substation Addition | Construct a new substation named Twelvemile off the Bakersfield to Schneeman Draw transmission line to support a generation interconnection request (16INR0104) |  | Bakersfield | Schneeman Draw | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018769 | 2024-10-31 |  | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  |  | 76008, 7053, 76015 | Y | N |  | 0 | 58408 | 6719
50845 | Kinnison: Expand 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Schedule Update | Kinnison |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2797 | 2024-10-31 |  | 138 | 0 | 0 | 130 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60431, 60432 | Y | N |  | 0 | 65545 | 50845
51010 | Heron to Ollin: Rebuild and convert to 138 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Schedule Update | Heron | Ollin | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2798 | 2024-10-31 |  | 138 | 0 | 2 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60448, 60441 | Y | N |  | 0 | 51011 | 51010
51012 | Kinnison to Sage: Rebuild 69 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Schedule Update | Kinnison | Sage | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2823 | 2024-10-31 |  | 69 | 0 | 0.25 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-17 |  | 60431, 6604 | Y | N |  | 0 | 65555 | 51012
45421 | McElroy to Sage: Rebuild 69 kV line | Build new Ollin 138 kV station with a 138/69 kV auto; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage | Schedule Update | McElroy | Sage | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2768 | 2024-10-31 01:00 |  | 69 | 0 | 1.99 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6604, 6607 | Y | N |  | 0 | 65529 | 45421
61396 | Hamilton - Maxwell: Line Rebuild | Hamilton - Maxwell: Line Rebuild |  | Hamilton Road | Maxwell | Planned |  | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2853 | TA2019800 | 2024-11-01 |  | 138 | 0 | 29 | 0 |  | Val Verde | Val Verde | Tier 3 | 20RPG022 | 2020-11-02 | 2021-01-19 |  | 8257, 8998 | Y |  |  | 0 | 65593 | 61396
71002 | Tidehaven: Construct New Distribution Station | Tidehaven: Construct New Distribution Station | Project Title, Project Description, Terminal "to" Location, Schedule Update | Blessing | PORT LAVACA | Planned | 1028 - 1206 | AEP | Brandon Cogan bcogan@aep.com 918-599-2857 | 3767 DP21X0007 | 2024-11-01 |  | 138 | 0 | 0 | 0 |  | Matagorda | Calhoun | Tier 4 |  |  |  |  | 8044, 8666, 8119, 8131, 8132, 8121, 8133, 8555 | Y | N |  | 0 | 71003 | 71002
6072 | Eldorado to Ft. McKavitt 69 kV line: Rebuild 69 kV line | Rehab Eldorado to Ft. McKavitt 69 kV line |  | Eldorado Tap | Ft. McKavitt | Planned | 786 - 0971 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2677 | 2024-11-24 |  | 69 | 0 | 19.41 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  |  | 6505, 6506, 6507, 6508 | Y | N |  |  | 13794 | 6072
61550 | East Munday to Lake Pauline: Rebuild 138 kV Line | Rehab East Munday to Lake Pauline 138 kV line | Project Description, Contact Update | East Munday | Lake Pauline | Planned | 1129 - 1307 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 1874 | 2024-11-27 |  | 138 | 0 | 59.97 | 0 |  | Knox | Hardeman | Tier 4 | 20RPG018 |  |  |  | 6037, 6050, 6110 | Y | N |  | 0 | 65594 | 61550
55624 | Escondido to Ganso: Rebuild 138 kV line | Rebuild 138 kV line from Escondido to Hamilton Road |  | Escondido | Ganso | Planned | 1105 - 1283 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3825 | 2024-11-30 |  | 138 | 0 | 10.198 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 8260, 8267 | Y |  |  | 0 | 65575 | 55624
59394 | Pointer to Rule: Rebuild 69 kV Line | Rehab the Pointer to Rule 69 kV Line | Project Title. Project Description, Contact, Cost Update | Pointer | Rule | Planned | 1122 - 1300 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 1867 | 2024-11-30 |  | 138 | 0 | 14.78 | 0 |  | Haskell | Knox | Tier 4 |  |  |  |  | 6014, 6115, 763, 6120, 60346 | Y | N |  | 0 | 59395 | 59394
61552 | Matador to Turkey: Rebuild 69 kV Line | Rebuild 69 kV line from Matador to Turkey |  | Matador | Turkey | Planned | 1128 - 1306 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1873 | 2024-11-30 |  | 69 | 0 | 26.9 | 0 |  | Motley | Hall | Tier 4 |  |  |  |  | 6020, 6044, 6024, 6039, 6041, 6140, 60351 | Y | N |  | 0 | 65596 | 61552
68960 | North Edinburg: Expand 345 kV station | Construct new terminals at North Edinburg for the ETT 2nd circuits project |  | North Edinburg |  | Planned |  | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | TP2021705 | 2024-11-30 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 1 |  |  |  |  | 8383, 8455, 8901, 8905, 8341 | Y |  |  | 0 | 71132 | 68960
70712 | SAPS to Red Creek: Rebuild 138 kV Line | Rehab SAPS to Red Creek 138 kV Line |  | SAPS | Red Creek | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | TA2020210 | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  |  | 6442, 6473, 6480, 60008 | Y |  |  | 0 | 70713 | 70712
1205 | Planned reconductor from Hasse to Gustine | Planned reconductor from Hasse to Gustine |  | HASSE | GUSTINE | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-12-01 |  | 69 | 0 | 7.34 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 273, 277 | Y |  |  | 0 | 54001 | 1205
1549 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-12-01 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 | [5 empty] | Y | N |  |  | 8754 | 1549
3334 | Fort Sam to Kirby and Fort Sam to Tenth Street MLSE Upgrade | Upgrade entire bus and terminals at Fort Sam and ensure a rating of 2000 A. |  | Fort Sam | Kirby/Tenth Street | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0744 | 2024-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5160, 5250, 5420 | Y | N |  | There are no transformers associated with this project | 10692 | 3334
4645 | Rebuild of Myra to Spring | Rebuild of Myra to Spring |  | Myra | Spring | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-12-01 |  | 138 | 0 | 13.9 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 684, 690, 691 | Y |  |  |  | 12221 | 4645
6685 | Van Vleck substation loop | Replaces single circuit radial line connected to a pole mounted switch with a double circuit transmission loop to the Van Vleck substation and upgrades the 4/0 ACSR to 795 ACSR on 138 kV capable poles. |  | Van Vleck Substation | Van Vleck Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-12-01 |  | 69 | 2 | 2 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5556, 5557, 5558, 5560 | Y | N |  |  | 14456 | 6685
55299 | Munday to Throckmorton: Rebuild 69 kV line | Rehab 69 kV line from Munday to Throckmorton | Contact Update | Munday | Throckmorton | Planned | 1094 - 1272 | AEP TNC | Raza Ansari mlforcum@aep.com 918-599-2857 | 1862 | 2024-12-01 |  | 69 | 0 | 34.55 | 0 |  | Knox | Throckmorton | Tier 4 | 21RPG015 | 2021-08-24 | 2021-09-28 |  | 6107, 6204, 6205 | Y | N |  | 0 | 65569 | 55299
60530 | Rebuild TI-South with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2024-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37080, 37100 | Y |  |  | 0 | 60531 | 60530
66366 | Rebuild Brazoria - Retrieve 138kV with bundled 795 ACSS |  |  | TNMP Brazoria (bus # 39600) | CenterPoint Retrieve (bus # 43170) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2024-12-01 |  | 138 | 0 | 6.17 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39600, 43170 | Y |  |  | 0 | 66367 | 66366
70714 | PEC_La_Cima_Substation_Addition | Add new substation to 138 kV line between Ranch Road 12 and Hill Top and install 46.7 MVA distribution transformer. The new substation will be located approximately 0.30 miles from Ranch Road 12 substation. |  | Ranch Road 12 | La Cima | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-12-01 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7185, 7186, 7190 | Y | N |  | 0 | 70715 | 70714
70886 | Rebuild TinTop - Rio Colorado | Rebuild TinTop- Rio Colorado 795ACSR |  | Tin Top | Rio Colorado | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-12-01 |  | 69 | 0 | 15.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5563, 5569 | Y |  |  | 0 | 70887 | 70886
71926 | Upgrade BURNS to Heidelberg line | Upgrade BURNS to Heidelberg line to be 478MVA capable |  | Burns | Heidelberg | Planned | 7192871930 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-12-01 |  | 138 | 0 | 10 | 0 |  | Cameron | Hidalgo | Tier 4 |  |  |  |  | 5763, 5765 | Y |  |  | 0 | 71927 | 71926
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-12-07 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  |  | 5705 | Y | N |  |  | 9835 | 2554
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing autotransformer |  | Elkton | Elkton | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6032-E | 2024-12-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 4 |  |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 10501 | 3155
5436 | Morgan Creek - McDonald 138 kV Line | Upgrade existing line | Project Deferral | Morgan Creek | McDonald Rd | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8360 | 2024-12-15 |  | 138 | 0 | 31.8 | 0 |  | Howard | Mitchell | Tier 3 |  |  |  |  | 1032, 1333 | Y |  |  |  | 13139 | 5436
45640 | Spraberry - Polecat Creek 138 kV Line | Upgrade the existing 138 kV line |  | Spraberry | Polecat Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8645 | 2024-12-15 |  | 138 | 0 | 32.4 | 0 |  | Midland | Glasscock | Tier 3 |  |  |  |  | 1328, 1329, 1337, 11372, 11337, 11394 | Y |  |  | 0 | 71166 | 45640
45693 | Rocky Road - Stiles 138 kV Line | Upgrade the existing 138 kV line |  | Rocky Road | Stiles | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8599 | 2024-12-15 |  | 138 | 0 | 6.6 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 23864, 23868 | Y |  |  | 0 | 71171 | 45693
52332 | Lamesa - Paul Davis Tap 138 kV Line Section | Upgrade the existing 138 kV line |  | Lamesa | Paul Davis Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8499, R8475 | 2024-12-15 |  | 138 | 0 | 17 | 0 |  | Dawson | Dawson | Tier 3 |  |  |  |  | 1163, 1170, 10008, 18880 | Y |  |  | 0 | 71169 | 52332
62445 | Eagle Mountain 138kV Switch Rebuild | Rebuild existing 138 kV Switch |  | Eagle Mountain |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5261 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 11859, 11860, 11864, 11865, 568, 1860, 1864, 1865, 12065, 1859, 11861, 11866 | Y |  |  | 0 | 70920 | 62445
66190 | East Levee - Industrial Blvd 138 kV DCKT Line | Rebuild East Levee - Industrial Blvd 138 kV DCKT Line |  | East Levee | Industrial | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4213 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2481, 2482, 2875, 2974, 2874, 2876, 2976 | Y |  |  | 0 | 66191 | 66190
68681 | Lamar Blossom Switch - Clarksville 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Lamar | River Crest | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5325 | 2024-12-15 |  | 69 | 0 | 0 | 0 |  | Lamar | Red River | Tier 4 |  |  |  |  | 1772, 1785, 11784 | Y |  |  | 0 | 68682 | 68681
68700 | Bonham - Toco Switch 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Bonham | Toco | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3016 | 2024-12-15 |  | 69 | 0 | 35 | 0 |  | Fannin | Lamar | Tier 4 |  |  |  |  | 1703, 1761, 1788, 1789, 1790, 11789 | Y |  |  | 0 | 68701 | 68700
68790 | Wolf - General Tire - Odessa EHV 138 kV Line | Rebuild existing 138 kV line |  | Wolf | Odessa EHV | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8528 | 2024-12-15 |  | 138 | 0 | 40.7 | 0 |  | Ector | Ward | Tier 3 | 22RPG024 | 2022-08-19 | 2022-09-14 |  | 1054, 1055, 1056, 1099, 1112, 11018, 11281, 1013, 1027, 1052, 1053, 1102, 1103, 1110, 1111 | Y |  |  | 0 | 68792 | 68790
70717 | PEC_Yarrington_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Rohr and Goforth and install 46.7 MVA distribution transformer. The new substation will be located approximately 0.17 miles from Rohr substation. |  | Rohr | Goforth | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7514, 7501, 7515 | Y | N |  | 0 | 70718 | 70717
70900B | Roanoke Area Upgrades | Establish Exchange 345 kV Switch |  | Exchange Switch | Exchange Switc | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2024-12-15 |  | 345 | 0 | 0 | 1500 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 12077, 12078, 12079, 12080, 12081, 1855, 559, 566, 1845, 1851, 2027, 2033, 2034, 2037, 12036, 2038, 2081, 12033, 12034 | Y | N |  | 0 | 72014 | 70900
71156 | Ennis West Switch-Waxahachie Switch 138 kV Line Rebuild | Rebuild the Ennis West-Waxahachie 138 kV Line |  | Ennis West | Waxahachie | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4200 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2241, 2321, 12320 | Y |  |  | 0 | 71160 | 71156
71175 | Tall City - Pecan Grove 138 kV Line | Upgrade the existing 138 kV line |  | Tall City | Pecan Grove | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8635 | 2024-12-15 |  | 138 | 0 | 11.6 | 0 |  | Midland | Martin | Tier 4 |  |  |  |  | 23840, 23855, 23861 | Y |  |  | 0 | 71177 | 71175
71898 | Install two additional 9.2 Mvar stages at Carroll Springs 69 kV Cap Bank | Install two additional 9.2 Mvar stages at Carroll Springs 69 kV Cap Bank |  | Carroll Springs | Carroll Springs | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6241 | 2024-12-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Anderson | Anderson | Tier 4 |  |  |  |  | 3270 | Y |  |  | 0 | 71899 | 71898
71901 | Install 110.4 Mvar 138 kV capacitor bank at Thorndale North | Install 110.4 Mvar 138 kV capacitor bank at Thorndale North |  | Thorndale North | Thorndale North | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6236 | 2024-12-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Milam | Milam | Tier 4 |  |  |  |  | 3659 | Y |  |  | 0 | 71902 | 71901
71908 | Install second 345/138 kV Auto at Temple Pecan Creek | Install second 345/138 kV Auto at Temple Pecan Creek and cut in the Temple - Lake Creek 345 kV Line |  | Temple Pecan Creek | Temple Pecan Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6239 | 2024-12-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 3 |  |  |  |  | 13412, 3409, 3412, 3414, 3420 | Y |  |  | 0 | 71909 | 71908
71910 | Rebuild the Hillsboro - Elm Mott 69 kV Line | Rebuild the Hillsboro - Elm Mott 69 kV Line |  | Hillsboro | Elm Mott | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6221 | 2024-12-15 |  | 69 | 0 | 25.4 | 0 |  | Hill | McLennan | Tier 3 |  |  |  |  | 3408, 3521, 3524, 3525, 3526, 3528, 3527, 3529, 13525 | Y |  |  | 0 | 71911 | 71910
71912A | Rebuild the Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Fort Hood - Killeen Park Street Tap 138 kV Line |  | Killeen Fort Hood | Killeen Park Street Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6245 | 2024-12-15 |  | 138 | 0 | 3.9 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3626, 3627 | Y |  |  | 0 | 71913 | 71912
71960 | Upgrade Grady - Expanse 138 kV Line | Rebuild the existing 138 kV line |  | Grady | Expanse | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8639 | 2024-12-15 |  | 138 | 0 | 6.4 | 0 |  | Martin | Martin | Tier 4 |  |  |  |  | 11368, 23842 | Y |  |  | 0 | 71962 | 71960
71968 | Midkiff - Pemkiff 138 kV Line | Rebuild the existing 138 kV line |  | Midkiff | Pemkiff | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8641 | 2024-12-15 |  | 138 | 0 | 0.31 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 1210, 23871 | Y |  |  | 0 | 71970 | 71968
71971 | Peck - Driver 138 kV Line | Construct a new 138 kV line |  | Peck | Driver | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8603 | 2024-12-15 |  | 138 | 4.1 | 4 | 0 |  | Glasscock | Glasscock | Tier 2 | 22PRG047 | 2022-12-27 | 2023-01-20 |  | 1218, 1222, 1223, 11222, 11282, 11283, 11285, 1210, 1217, 1226, 1333, 11226, 11227, 23863, 1329, 1330, 23871, 71210 | Y |  |  | 0 | 71979 | 71971
71973 | Morgan Creek - Barber Lake Rebuild West Ckt | Rebuild the existing 138 kV line |  | Morgan Creek | Barber Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8623 | 2024-12-15 |  | 138 | 0 | 4.75 | 0 |  | Mitchell | Mitchell | Tier 4 |  |  |  |  | 1032, 1189 | Y |  |  | 0 | 71975 | 71973
71976 | Watermill 138 kV Switch | Rebuild the existing Watermill 138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3031 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 2429, 2430, 12433, 3067, 3068, 2427, 12430 | Y |  |  | 0 | 71977 | 71976
71985 | Northlake 138 kV Switch | Rebuild the existing Northlake 138 kV Switch |  | Northlake |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4353 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 | [5 empty] | Y |  |  | 0 | 71986 | 71985
71989 | Big Spring West - Stanton East 138 kV Line | Rebuild the existing 138 kV line |  | Big Spring West | Stanton East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8303 | 2024-12-15 |  | 138 | 0 | 17.6 | 0 |  | Martin | Howard | Tier 4 |  |  |  |  | 1324, 11316, 1322, 1325, 1326, 11324, 11331 | Y |  |  | 0 | 71990 | 71989
71993 | Tributary - Vincent 138 kV Line Section | Rebuild the existing 138 kV line |  | Tributary | Vincent | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8667 | 2024-12-15 |  | 138 | 0 | 11.2 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 1394, 1395, 1397 | Y |  |  | 0 | 71999 | 71993
72004 | Midkiff 138 kV Dynamic Reactive Device | Install a new Dynamic Reactive Device at Midkiff |  | Midkiff | Midkiff | Planned | R8675 | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 |  | 2024-12-15 |  | 138 | 0 | 0 | 0 | -250250 | Upton | Upton | Tier 3 |  |  |  |  | 11286, 11287, 1210 | Y |  |  | 0 | 72006 | 72004
54521 | Hilltop_Weatherford_Rebuild |  |  | Weatherford (1589) | Hilltop (501) | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-12-26 |  | 138 | 0 | 13 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 501, 505, 512, 1589 | Y |  |  | 0 | 54522 | 54521
50898 | Alamito Creek to Paisano to Alpine: Rebuild 69 kV line | Rehab Alamito Creek to Paisano to Alpine 69 kV line | Contact Update | Alamito Creek | Alpine | Planned | 1045 - 1218 | AEP TNC | Charles Gibson mlforcum@aep.com 918-599-2674 | 2793 | 2024-12-31 |  | 69 | 0 | 22.26 | 0 |  | Presidio | Brewster | Tier 4 | 20RPG017 |  |  |  | 6667, 6666, 6672 | Y | N |  | 0 | 50899 | 50898
64065 | Alice to Kingsville 138 kV Line Rebuild | Rebuild the Alice to Kingsville 138 kV line to address aging infrastructure |  | Alice | Kingsville | Planned |  | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | TA2021079 | 2024-12-31 |  | 138 | 22.48 | 0 | 0 |  | Jim Wells | Kleberg | Tier 4 |  |  |  |  | 8503, 8518 | Y |  |  | 0 | 66649 | 64065
68150 | Abilene South to Estes: Rebuild 138 kV line | Rehab the Abilene South to Putnam 138 kV line | Contact, Schedule Update | Abilene South | Estes | Planned |  | AEP TNC | Jim Nivens mlforcum@aep.com 918-5992674 |  | 2024-12-31 |  | 138 | 0 | 18.3 | 0 |  | Taylor | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6313, 60063, 6260, 60365, 60336, 60355, 60773, 61015 | Y | N |  |  | 68151 | 68150
69892 | Deer Park Tap to NOBEL Ckt.21C Upgrades |  |  | Underwood | NOBEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 1.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40441, 41632 | Y | N |  |  | 69893 | 69892
70902 | LCRATSC_Settlers_Substation_Addition | Provide two transmission Points of Interconnection (POIs) on LCRA TSC-owned transmission lines T231 Bastrop City to Webberville and T171 Austrop to Sim Gideon to serve new BBEC customer load. |  | Austrop, Webberville | Sim Gideon, Bastrop City | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org +151-257-84514 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7327, 7328, 7310, 7322, 7329, 9328 | Y | N |  | 0 | 70903 | 70902
72032 | Stewart to West Bay Ckts 48A & 59A Upgrades | Reconductor Ckts. 48A & 59A Stewart to West Bay as a Hardening upgrade. |  | Stewart | West Bay | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 40 | 0 |  | Galveston | Galveston | Tier 4 | [5 empty] | Y |  |  | 0 | 72033 | 72032
45397 | Lion: 138 kV Station & Transmission Line | Lion: 138 kV Station with new line to Stewart Road |  | Lion | Stewart Road | Planned | 885 - 1063 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3672 TP2018218 | 2025-01-01 |  | 138 | 2.71 | 0 | 40 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8969, 8758, 8951 | Y | N |  | 0 | 65528 | 45397
50868 | Rosata - Structure 31/8: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3780 | 2025-01-12 |  | 138 | 0 | 15.5 | 0 |  | Goliad | Karnes | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8186, 8153 | Y | N |  | 0 | 50869 | 50868
61090 | Southeast138kV substation | Establish 138kV Southeast substation with (2) 40MVA transformers and will cut into existing Ckt 1026 (Stoney Ridge to Hi-Cross |  | Stoney Ridge | Hi-Cross |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-01-31 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9240, 9237, 9251 | Y |  |  | 0 | 61091 | 61090
61224 | AEN_Decker_SH_ckt_1008__reconductor | Upgrade the 7.04 mile Decker to Sand Hill 138 kV transmission line (Ckt 1008) with bundled 795 ACSS Drake conductor rated for 3000 amps |  | Decker [9187] | Sandhill [9216] | Planned |  | AEN | Shirley Mathew shirley.mathew@austinener (512) 322-6103 |  | 2025-01-31 |  | 138 | 0 | 7.04 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9187, 9216 | Y |  |  | 0 | 61225 | 61224
71935 | Upgrade Hondo Creek to Castroville to 138kV | Upgrade Castroville sub to 138kV and line from Hondo creek to Castroville |  | Hondo Creek | Castroville | Planned | 71917 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2025-02-01 |  | 138 | 0 | 18.59 | 0 |  | Medina | Medina | Tier 2 | 22RPG022 |  |  |  | 5807, 5808, 5810, 5819, 5821 | Y |  |  | 0 | 71936 | 71935
52464 | Alamito Creek to Ft. Davis: Rebuild 69 kV line | Rehab Alamito Creek to Ft. Davis 69 kV line |  | Alamito Creek | Ft Davis | Planned | 1070 - 1243 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2831 | 2025-02-25 |  | 69 | 0 | 20.5 | 0 |  | Presidio |  | Tier 4 |  |  |  |  | 6676, 6677, 6691, 6678, 6692 | Y | N |  | 0 | 65564 | 52464
70880 | Rebuild Carancahua -TinTop | Rebuild Carancahua to TinTop with 795ACSR |  | Carancahua | Tin Top | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2025-03-01 |  | 69 | 0 | 12.93 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5569, 5570, 5571, 5573 | Y |  |  | 0 | 70881 | 70880
71937 | Caterpillar Substation | Add T6, 40 MVA. 138-26.08 kV PWT to Caterpillar Substation |  | Caterpillar |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-03-18 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 | [5 empty] | Y | N |  | 0 | 71938 | 71937
64780 | Upgrade 138kV Locust-DMENODE line to 700MVA |  |  | Locust | DMENODE | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2025-04-01 |  | 138 | 0 | 1.92 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 924, 59000 | Y | N |  | 0 | 64781 | 64780
70779 | Tortuga: Install Cap Bank | Tortuga Capacitor |  | Tortuga |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022188 | 2025-04-01 |  | 138 | 0 | 0 | 0 | 0,23 | Nueces |  | Tier 4 |  |  |  |  | 8697 | Y |  |  | 0 | 70780 | 70779
61277A | Lago Vista to Nameless Transmission Line Upgrade | Rebuild and upgrade Nameless to Lago Vista with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA). Final span of conductor and terminal equipjment at Nameless will be upgraded to 440 MVA with ERCOT project #61277B. | 1/10/2023: Added information to clarify timing for final circuit rating upgrade. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2025-04-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7352, 7526 | Y | N |  | 0 | 70669 | 61277
61266 | Trading Post to Cedar Valley Storm Hardening | Rebuild single circuit section of Trading Post to Cedar Valley and reconductor with bundled 795 ACSR Conductor, 440 MVA |  | Trading Post | Cedar Valley | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2025-04-22 |  | 138 | 0 | 6.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7505, 7506 | Y | N |  | 0 | 70370 | 61266
59260 | Mason Phillips Tap to Mason Phillips: Rebuild 69 kV Line | Rehab the Mason Phillips Tap to Mason Phillips 69 kV Line | Project Title, Project Description Update | Seaquist | Mason Phillips | Planned | 1127 - 1305 | AEP TNC | David Baker mlforcum@aep.com 918-599-2674 | 1872 | 2025-04-30 |  | 69 | 0 | 13.7 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6395, 6407, 60458 | Y | N |  | 0 | 65588 | 59260
64067 | Bessel to King Ranch: 138 kV Line Rebuild | Rehab the Bessel to King Ranch 138 kV line |  | Bessel | STRATTON | Planned |  | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | TA2020081 | 2025-05-01 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8498, 8512, 8665, 8060, 8514, 80228 | Y |  |  | 0 | 64068 | 64067
65661 | Rebuild Wickett-Pyote 138 kV line |  |  | Wickett (but # 37981) | Pyote (bus # 38001) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2025-05-01 |  | 138 | 0 | 12.88 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37981, 38001 | Y |  |  | 0 | 65662 | 65661
71917 | Upgrade STEC castroville to Pearson to 138kV | Upgrade STEC Bader station to 138kV. Upgrade STEC Castroville to bader and bader to pearson to 138kV |  | 5808 | 5813 | Planned | 71935 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2025-05-01 |  | 138 | 0 | 10.51 | 0 |  | Medina | Medina | Tier 2 | 22RPG022 | 2022-08-08 | 2022-12-06 |  | 5810, 5808, 5811, 5813 | Y |  |  | 0 | 71918 | 71917
71928 | Upgrade Heidelberg to AEP Weslaco line | Upgrade Heidelberg to STEC WESLACO and STEC WESLACO to AEP Weslaco lines to be 478MVA capable |  | Heidelberg | Weslaco | Planned | 7193071926 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2025-05-01 |  | 138 | 0 | 8.6 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5765, 5768, 8354 | Y |  |  | 0 | 71929 | 71928
45015 | Barnhart to Cassava: Rebuild 69 kV line | Rebuild the Barnhart to Cassava 69 kV line |  | Barnhart | Cassava | Planned | 942 - 1120 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2756 | 2025-05-01 01:00 |  | 69 | 0 | 6.021 | 0 |  | Irion | Irion | Tier 4 |  |  |  |  | 6532, 6530, 6537, 60359 | Y | N |  | 0 | 65525 | 45015
50866 | Structure 31/8 - Kenedy SS: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3779 | 2025-05-01 01:00 |  | 138 | 0 | 14.3 | 0 |  | Karnes | Karnes | Tier 3 | 20RPG014 |  |  |  | 8186, 8153 | Y | N |  | 0 | 50867 | 50866
5479 | Trinidad - Tri Corner 345 kV Double-Circuit Line | Upgrade existing DCKT line |  | Trinidad Sw. Sta | TriCorner/Watermill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4045 | 2025-05-15 |  | 345 | 0 | 92.1 | 0 |  | Henderson | Dallas | Tier 3 |  |  |  |  | 2432, 3123, 3124 | Y | N |  |  | 13184 | 5479
5496 | Forney Switch 345 kV Terminal Equipment | Upgrade the terminal equipment at Forney 345 kV Switch |  | Royse |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3022 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 4 |  |  |  |  | 2437, 2478 | Y |  |  | 0 | 62442 | 5496
5526 | Forney 345/138 kV Switching Station | Rebuild existing 345/138 kV switching station |  | Forney |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4114 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Kaufman |  | Tier 3 | [5 empty] | Y | N |  | 0 | 49916 | 5526
47541 | Crane Circuit Breaker Addition | Provide transmission service to American Electric Power at Crane Substation. Adding one (1) breaker and associated equipment needed to connect the AEP-owned Crane to Kinnison 138-kV transmission line. |  | Crane Substation | Crane Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 76615 | Y | N |  | 0 | 47542 | 47541
61358 | Highway 46-River Oaks Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T518 Highway 46 to River Oaks 138-kV and T389 Bergheim to Hays Energy 345-kV 8.6-mile double-circuit transmission line by replacing the aging conductor. Project ID 61356 captures the T389 Bergheim - Hays Energy 345-kV conductor upgrade for modeling purposes. |  | Highway 46 | River Oaks | Planned | 61406, 61392, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 345 | 0 | 8.6 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7043, 7173, 7177, 7770 | Y | N |  | 0 | 61359 | 61358
61404 | Boerne Split-Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T228 Boerne to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 7.3-mile double-circuit transmission line by replacing the aging conductor. |  | Boerne, Bergheim | Welfare, Kendall | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 345 | 0 | 7.3 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7046, 7153, 7168, 7770 | Y | N |  | 0 | 61405 | 61404
61406 | Kendall-Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T584 Kendall to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 10.2-mile double-circuit transmission line by replacing the aging conductor. |  | Kendall | Welfare | Planned | 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 10.2 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7046, 7152, 7153, 7770 | Y | N |  | 0 | 61407 | 61406
62068 | Lakeway-Marble Falls Transmission Line Storm Hardening | Increase the reliability of transmission facilities on the T497 Lakeway ¿ Marble Falls 23-mile 138-kV transmission line. |  | Lakeway | Marble Falls | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Burnet | Tier 4 | 22RPG031 |  | 2022-11-03 |  | 7348, 7349, 7351, 7356, 7476, 7538, 7474, 7540 | Y | N | 22RPG031 reclassified as Tier 4 neutral by RPG review on 11/03/2022 | 0 | 62069 | 62068
62434 | Sargent Road - Industrial Blvd 138 kV DCKT Line | Upgrade existing 138 kV Line |  | Sargent Road Switch | Industrial Blvd Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4128 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2940, 2947, 2972, 2973, 2977, 2982, 2983, 2974, 2975, 2976 | Y |  |  | 0 | 62435 | 62434
70194 | LCRATSC_Hallettsville_Mont_TL_Overhaul | LCRA TSC will perform an overhaul on the 2.3-mile Hallettsville ¿ Mont (T593) 138-kV transmission line. |  | Hallettsville | Mont | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 2.3 | 0 |  | Lavaca | Lavaca | Tier 4 |  |  |  |  | 7246, 7249 | Y | Y |  | 0 | 70195 | 70194
70204 | LCRATSC_McCarty_Rattler_TL_Upgrade | LCRA plans to upgrade T725 McCarty Lane - Rattler 138-kV transmission line to obtain a higher operational rating. |  | McCarty Lane | Rattler | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 1.27 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7184 | Y | N |  | 0 | 70205 | 70204
70223 | LCRATSC_Mont_PilotGrove_TL_Overhaul | LCRA TSC will perform an overhaul on the 8-mile Mont ¿ Pilot Grove (T140) 138-kV transmission line. |  | Mont | Pilot Grove | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 8 | 0 |  | Lavaca | Lavaca | Tier 4 |  |  |  |  | 7234, 7235, 7249 | Y | Y |  | 0 | 70224 | 70223
70351 | LCRATSC_Rattler_Redwood_TL_Upgrade | Upgrade T262 Rattler - Redwood 138-kV transmission line to obtain a higher operational rating. |  | Rattler | Redwood | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 1.07 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7184, 7188 | Y | N |  | 0 | 70352 | 70351
70365 | Andice capacitor bank addition | Install 31.2 Mvar capacitor bank at Andice. |  | Andice |  | Planned |  | PEC | Joshua Rivers Joshua.Rivers@peci.com (830) 330-4192 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson |  | Tier 4 |  |  |  |  | 7522 | Y | Y |  | 0 | 70366 | 70365
70538 | LCRATSC_PilotGrove_YoakumGartner_TL_Overhaul | Perform an overhaul on the 7.8 mile T614 Pilot Grove (structure #8/2) - Yoakum Gartner Road 138-kV transmission line. Structure #8/2 and the remaining portion of T614 will be overhauled as part of the FY23 Mont - Pilot Grove Transmission Line Overhaul project. |  | Pilot Grove | Yoakum Gartner | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Lavaca | DeWitt | Tier 4 |  |  |  |  | 7234, 7242 | Y | N |  | 0 | 70539 | 70538
70900C | Roanoke Area Upgrades | Establish Dunham 345 kV Switch |  | Dunham Switch | Dunham Switc | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 21851, 646, 1730, 1849, 33646 | Y | N |  | 0 | 72015 | 70900
71178 | Seagoville-Watermill 138 kV Line | Rebuild Seagoville-Watermill 138 kV Line |  | Seagoville | Watermill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4081 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 2429, 2434, 3076, 3077, 3079, 3083 | Y |  |  | 0 | 71179 | 71178
71187 | Reiter - Tesoro 345 kV Double-Circuit Line | Construct new 2.5-mile 345 kV double-circuit line from Tesoro to Reiter |  | Tesoro | Reiter | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8629 | 2025-05-15 |  | 345 | 5 | 0 | 0 |  | Midland | Ector | Tier 2 |  |  |  |  | 18540, 18544 | Y |  |  | 0 | 71189 | 71187
71903 | Establish Launch Pad 138 kV Switch | Establish Launch Pad 138 kV Switch |  | Launch Pad | Launch Pad | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6156 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3594, 3709, 3440, 3593, 3601 | Y |  |  | 0 | 71904 | 71903
71956 | LCRATSC_ElginSwitch_Substation_Addition | LCRATSC will install a new three-breaker ring bus substation at Elgin Switch. Oncor will relocate its facilities from Elgin Switch to Brushy Creek. Install a temporary shoo-fly between T668 and T260 to maintain through-path during construction. |  | Elgin Switch |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 1 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y | N |  | 0 | 71957 | 71956
71980 | Watermill 345 kV Switch | Rebuild the existing Watermill 345 kV Switch |  | Watermill |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4012 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 2428, 2435, 2997, 2398, 2427, 2432, 2466, 3159, 22427 | Y |  |  | 0 | 71981 | 71980
58010 | North McAllen: Rebuild 138 kV Station | North McAllen Station Rebuild |  | McAllen |  | Planned | 1118 - 1296 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3837 | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8368, 8631, 8632 | Y |  |  | 0 | 65583 | 58010
61449 | Clark Church (Ottine New) Substation | Build New 69/138 Substation by Birdhouse to Replace existing Ottine station, add 20MVA; demo existing Ottine substation |  | Ottine | Ottine | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7594 | Y | N |  | 0 | 61450 | 61449
63924 | Quasar: Build New 345 kV Station | Interconnect Brass Fork Solar to the Clear Crossing to Coulomb 345 kV Line | Schedule Update | Quasar |  | Planned | 1138 - 1316 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 1883 | 2025-05-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60712, 60514, 60703 | Y | N |  | 0 | 63925 | 63924
70349 | Belknap to Fort Griffin: Rebuild 69 kV Line | Rehab Belknap to Fort Griffin 69 kV line |  | Belknap | Fort Griffin | Planned |  | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 |  | 2025-05-31 |  | 69 | 0 | 23.6 | 0 |  | Jones | Shackelford | Tier 3 |  |  |  |  | 6178, 6210, 6214, 60466, 60471, 60398, 60409, 60445 | Y | N |  | 0 | 70350 | 70349
72044C | Clute 138kV Switching Station | Reconfigure existing Ckt.26D STRATT to SINTEK and loop into new CNP-owned 138kV Clute switching station to create new Ckt.26 Clute to SINTEK. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  | 0 | 72047 | 72044
72044A | Clute 138kV Switching Station | Reconfigure existing Ckt.82F RIWOOD to CAVERN to BIPORT and loop into new CNP-owned 138kV Clute switching station to create new Ckt.82 RIWOOD to Clute to CAVERN to BIPORT. |  | Clute | RIWOOD | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  | 0 | 72045 | 72044
72044D | Clute 138kV Switching Station | Reconfigure existing circuits out of STRATT and connect to new CNP-owned 138kV Clute switching station to create new parallel Ckts. xx & yy Clute to STRATT. Clute to STRATT lines are expected to be customer-owned. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  | 0 | 72048 | 72044
72044B | Clute 138kV Switching Station | Reconfigure existing Ckt.26C Angleton to STRATT and loop into new CNP-owned 138kV Clute switching station to create new Ckt.26 Angleton to Clute. |  | Angleton | Clute | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  | 0 | 72046 | 72044
45029 | Grandview Highland Hills Rebuild | CPSE_Rebuild of 138 kV double circuit line Line between Grandview to Highland Hills. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0273 | 2025-06-01 |  | 138 | 0 | 11.6 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-11 |  |  | 5030, 5175, 5095, 5205 | Y |  |  | 0 | 45030 | 45029
45084A | Braunig to Highland Rebuild | Rebuild approximately six circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Highland Hills to Schillers Tap'. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0194, T-0238 | 2025-06-01 |  | 138 | 0 | 6 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  | 0 | 45085 | 45084
67992C | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Upgrade Medina to 36th Street 138KV Line to 213MVA. This change will remove a clearance related limit and not change the conductor. |  | 5305 | 5427 | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2025-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5305, 5427 | Y |  |  | 0 | 67995 | 67992
67992B | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Upgrade Hamilton to Medical Center 138KV Line to 469MVA |  | 5187 | 5300 | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2025-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5187, 5300 | Y |  |  | 0 | 67994 | 67992
67992A | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Looping of 345KV Howard Rd switching station into existing Cagnon to AVR and Cagnon to Spruce 34KV lies. The switching station will have 2 600MVA 345KV/138KV autotransformers. |  | 5056 | 5400 and 5475 | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2025-06-01 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5231, 5056, 5400, 5475, 5230 | Y |  |  | 0 | 67993 | 67992
68669 | Adds Staghorn Switching Station |  |  | Wickett (37981) Pyote (38001) | Staghorn (37990) | Under Construction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2025-06-01 |  | 138 | 0.04 | 0 | 0 | 0,160 | Ward | Ward | Tier 4 |  |  |  |  | 37990, 37981, 38001, 38002 | Y |  |  | 0 | 68670 | 68669
70882 | Rebuild Olivia - Carancahua | rebuild Olivia sw to Carancahua 795 ACSR |  | Olivia SW | Carancahua | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2025-06-01 |  | 69 | 0 | 8.71 | 0 |  | Jackson | Matagorda | Tier 4 |  |  |  |  | 5573, 5574 | Y |  |  | 0 | 70883 | 70882
70941 | Preliminary RPG for Cedarvale 345kV |  |  | Cedarvale 138 kV (bus # 38145) | Cedarvale 345 kV (bus # 38144) | Conceptual |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2025-06-01 |  | 138 | 0 | 0 | 1336 |  | Ward | Ward | Tier 2 |  |  |  |  | 38144, 38147, 38148, 11098, 76000, 38145 | Y |  |  | 0 | 70942 | 70941
70943 | Double circuit 138kV tie between Pyote and Coyanosa |  |  | Pyote (bus # 38001) | Coyanosa (bus # 38380) | Conceptual |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2025-06-01 |  | 138 | 15 | 0 | 0 |  | Ward | Reeves | Tier 2 |  |  |  |  | 38001, 38380 | Y |  |  | 0 | 70944 | 70943
71873 | CPSE_Hill Country Auto# 2 Impedance Upgrade |  |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2025-06-01 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2022-07-09 |  | 5211, 5210, 5213 | Y |  |  | 0 | 71874 | 71873
71879 | Update Ratings |  |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0939b | 2025-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5133, 5371 | Y |  |  | 0 | 71880 | 71879
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 3000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2025-06-10 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 9723 | 2443
20TPIT0000 | Parkway Substation T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10679 | 3323
70186 | LCRATSC_BuchananCTEC_Kingsland1_TL_Overhaul | LCRA TSC will perform an overhaul on the 6.2-mile Buchanan to Kingsland 2 to Kingsland 1 (T291) 69-kV transmission line. |  | Buchanan CTEC | Kingsland 1 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG +151-257-84514 |  | 2025-06-30 |  | 69 | 0 | 6.2 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7402, 7404 | Y | Y |  | 0 | 70187 | 70186
70196 | LCRATSC_Kingsland1_SandyCreek_TL_Overhaul | LCRA TSC will perform an overhaul on the 7.3-mile Kingsland 1 ¿ Sandy Creek (T400) 69-kV transmission line. |  | Kingsland 1 | Sandy Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-06-30 |  | 69 | 0 | 7.3 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7121, 7400, 7404 | Y | Y |  | 0 | 70197 | 70196
64776 | Upgrade 138kV DentonWest-RDWells line to 700MVA |  |  | RD Wells | Denton West | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2025-07-01 |  | 138 | 0 | 4.47 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 930, 986 | Y | N |  | 0 | 64777 | 64776
65723 | Riedel: Build New Distribution Station | Riedel will have 1 ¿ 69/138 kV ¿ 13.09 kV 10/12.5 MVA non-LTC Transformer, 3 ¿ 1241 kVA, 7.62 kV regulators, 1 ¿ 3,000 A totalizer breaker, 1 ¿ 3,000 A bus-tie switch, 2 ¿ 1200 A feeder breakers with SEL-351 relays, Urban design distribution bus with four bays and disconnects per transformer, transformer metering, overload and differential relaying, 1 ¿ 138 kV - 50 kVA station service transformer (SSVT), high-side circuit switcher, site and grading work for substation, and install two new feeder exits of overhead D-line out of new substation. |  | Magnolia Tap | Nixon | Planned | 1032 - 1210 | AEP TCC/LCRA | Brandon Cogan bcogan@aep.com 918-599-2857 | 3771 | 2025-07-01 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  |  | 8583 | Y | Y |  | 0 | 65724 | 65723
70282 | New 138kV Brushy Creek Substation |  |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-08-31 |  | 138 | 2.81 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32867, 32857, 32863 | Y |  |  | 0 | 70301 | 70282
66200C | Upgrade Taylor - Holland 69 kV Line | Rebuild the Bartlett - Granger 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6173 | 2025-09-15 |  | 69 | 0 | 6.9 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3647, 3648 | Y |  |  | 0 | 71896 | 66200
66202B | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Elkhart - Crockett 69 kV Line |  | Elkhart | Crockett | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6182 | 2025-09-15 |  | 69 | 0 | 19.5 | 0 |  | Anderson | Houston | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3285, 3286, 3289, 3290 | Y |  |  | 0 | 71894 | 66202
70710 | Eden to Yellowjacket: Rebuild 69 kV Line | Rehab Eden to Yellowjacket 69 kV line |  | Eden | Yellowjacket | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | TA2021119 | 2025-10-30 |  | 69 | 0 | 0 | 0 |  | Concho | Menard | Tier 4 |  |  |  |  | 6363, 6372 | Y |  |  | 0 | 70711 | 70710
69469 | Equinox Solar Project | Equinox Solar Project | Schedule Update | Cenizo | Del Sol | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2025-11-14 |  | 345 | 0 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  |  | 88355, 80355 | Y |  |  | 0 | 69470 | 69469
61268 | Cedar Valley to Friendship Storm Hardening | Rebuild single circuit section of Cedar Valley to Friendship and reconductor with bundled 795 ACSR Conductor, 440 MVA |  | Cedar Valley | Friendship | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2025-11-30 |  | 138 | 0 | 4.3 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7506, 7507 | Y | N |  | 0 | 61269 | 61268
67915 | Asherton to West Basteville 138 kV line Rebuild | Rebuild 36.09 miles from Asherton to West Batesville 138 kV line |  | ASHERTON | WEST BATESVILLE | Planned |  | AEP TCC | Brandon K cogan bcogan@aep.com 918-599-2857 |  | 2025-11-30 |  | 138 | 0 | 36.09 | 0 |  | Dimmit | Zavala | Tier 3 |  |  |  |  | 8236, 8283, 8285 | Y |  |  | 0 | 67916 | 67915
69224 | Brookhollow to Port Lavaca: Rebuild 138 kV Line | Rebuild 138 kV Line from Brookhollow to Port Lavaca |  | Brookhollow | Port Lavaca | Planned |  | AEP | Lorraine Timmerman bcogan@aep.com 918-599-2857 |  | 2025-11-30 |  | 138 | 0 | 2.7 | 0 |  | Calhoun | Calhoun | Tier 1 |  |  |  |  | 8720, 8723, 8133, 8536, 8135 | Y |  |  | 0 | 71834 | 69224
69253 | Rebuild 138 kV Line from Cangrejo to Dacosta | Rebuild 138 kV Line from Cangrejo to Dacosta |  | Cangrejo | Dacosta | Planned |  | AEP | Lorraine Timmerman bcogan@aep.com 918-599-2857 |  | 2025-11-30 |  | 138 | 0 | 17.97 | 0 |  |  |  | Tier 1 |  |  |  |  | 8135, 8136, 8721, 8722, 8723, 8133, 8140, 8141, 8143, 80064, 8169, 8536 | Y |  |  | 0 | 69254 | 69253
70367A | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Mountan Top to Blanco and Blanco to Devil's Hill 69 kV circuits to 138 kV with bundled 795 kcmil conductor (440 MVA). |  | Mountain Top | Blanco | Planned |  | PEC | Joshua Rivers Joshua.Rivers@peci.com (830) 330-4192 |  | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 7480, 7482, 7148, 7484 | Y | Y |  | 0 | 70368 | 70367
70673 | Clairemont Sun Oil Tap: Rebuild 69 kV Line | Rehab Clairemont Sun Oil Tap 69 kV Line |  | Clairmont |  | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | TA2021233 | 2025-11-30 |  | 69 | 0 | 0 | 0 |  | Kent |  | Tier 4 |  |  |  |  | 6197, 6198 | Y |  |  | 0 | 70674 | 70673
69277 | Cangrejo to Carbide: Rebuild 138 kV Line | Rebuild 138 kV Line from Cangrejo to Carbide |  | Cangrejo | Carbide | Planned |  | AEP TCC | Lorraine Timmerman bcogan@aep.com 918-599-2875 |  | 2025-11-30 |  | 138 | 0 | 11 | 0 |  | Calhoun | Calhoun | Tier 1 |  |  |  |  | 8140, 8155, 8190, 8723 | Y |  |  | 0 | 69278 | 69277
5475 | Lufkin Switch - Redland Switch 345 kV Line | Construct a new 345 kV Line from Lufkin Switch to Redland Switch |  | Lufkin Switch | Redland Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6077 | 2025-12-15 |  | 345 | 8.1 | 0 | 0 |  | Angelina | Angelina | Tier 2 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3117, 3321 | Y | N |  |  | 13180 | 5475
61601 | Add Coody Crossing 345 kV Switch | Add Coody Crossing 345 kV Switch |  | Clear Crossing | Tecumseh Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8560 | 2025-12-15 |  | 345 | 0 | 0 | 0 |  | Throckmorton | Throckmorton | Tier 4 |  |  |  |  | 11419, 11418, 60514 | Y |  |  | 0 | 64014 | 61601
64239 | Vineyard Switch-North Lake Switch 138 kV Line | Construct a new 138 kV circuit from Vineyard to Northlake |  | North Lake Switch | Vineyard Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5320 | 2025-12-15 |  | 138 | 7.4 | 0 | 0 |  | Dallas | Tarrant | Tier 3 |  |  |  |  | 2017, 2022, 2386, 12012, 12013, 15030, 2388, 15035, 15040 | Y |  |  | 0 | 70741 | 64239
68706 | Edgewood Switch _ Royse Switch&Terrell Switch 138 kV Double-Circuit Line | Rebuild and convert the Edgewood-Iron Bridge 69 kV to 138 kV operation |  | Edgewood | Able Springs | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3227 | 2025-12-15 |  | 69 | 0 | 0 | 0 |  | Van Zandt | Kaufman | Tier 4 |  |  |  |  | 3182, 3185, 3187, 3188, 3189, 3191, 3192, 3193, 6920, 6922, 13191, 121470, 3163, 12467, 2465, 2471, 2721, 2773, 3165, 3167, 3181, 12469, 3168, 3169, 12470 | Y |  |  | 0 | 68707 | 68706
70900D | Roanoke Area Upgrades | Establish Ramhorn Hill 345 kV Switch and Ramhorn Hill – Dunham 345 kV Double-Circuit Line |  | Dunham Switch | Ramhorn Switc | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2025-12-15 |  | 345 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 31875, 1421, 2081, 21851 | Y | N |  | 0 | 72016 | 70900
71182 | Reiter 345/138 kV Switch | Construct a new 345/138 kV switch |  | Odessa EHV | Wolf/Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8629 | 2025-12-15 |  | 345 | 0 | 0 | 1200 |  | Ector | Ector | Tier 3 |  |  |  |  | 18544, 18545, 18546, 18547, 1018, 1027, 1111, 11010, 11028, 11111 | Y |  |  | 0 | 71184 | 71182
72007 | Morgan Creek North 345/138 kV Switch | Construct a new 345/138 kV Switch to replace existing Morgan Creek Switch |  | Morgan Creek North 345138 kV Switch | Morgan Creek North 345138 kV Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3024 | 2025-12-15 |  | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 |  |  |  |  | 1030 | Y |  |  | 0 | 72008 | 72007
72009 | Morgan Creek South 345/138 kV Switch | Construct a new 345/138 kV Switch to replace existing Morgan Creek Switch |  | Morgan Creek | Morgan Creek | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8647 | 2025-12-15 |  | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 |  |  |  |  | 1030 | Y |  |  | 0 | 72010 | 72009
61444 | Wilson South Substation Addition | Add a new load serving substation about 4.35 miles south of La Vernia along FM 775, w/40 MVA PWT |  | Wilson South | Wilson South | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-19 |  | 138 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7629 | Y | N |  | 0 | 61445 | 61444
61446 | Wilson-SS Felps Tap to Wilson South | Build 0.99 miles of new double circuit 138kV t-line loop, 795 ACSR Drake, along FM 775 to Wilson South Substation, about 4.35 miles south of La Vernia |  | Wilson South | Wilson | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-20 |  | 138 | 0.99 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7627, 7628, 5418, 7615, 7629 | Y | N |  | 0 | 61448 | 61446
63916 | PEC_Junction_Bus_Upgrade | Upgrade Junction from tap station to a three terminal ring bus. |  | Junction |  | Conceptual |  | PEC/PEC/AEP | Ryan Morlino ryan.morlino@peci.com 830-868-5166 ryan.morlino@peci.com 830-868-5166 |  | 2025-12-25 |  | 69 | 0 | 0 | 0 |  | Kimble |  | Tier 4 | [5 empty] | Y | N |  | 0 | 63917 | 63916
68183 | Estes to Putnam: Rebuild 138 kV line | Rehab the Abilene South to Putnam 138 kV line | Contact, Schedule Update | Estes | Putnam | Planned | 68150 | AEP TNC | Jim Nivens mlforcum@aep.com 918-599-2674 |  | 2025-12-31 |  | 138 | 0 | 15 | 0 |  | Callahan | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6309, 60365, 61015 | Y | N |  |  | 68184 | 68183
55605 | Rebuild 69 kV line from Campwood to Rocksprings | New Barksdale to Rocksprings: Rebuild 69 kV line |  | New Barksdale | Rocksprings | Planned | 1102 - 1280 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3819 | 2026-01-01 |  | 69 | 0 | 19.51 | 0 |  | Edwards | Edwards | Tier 3 |  |  |  |  | 8365, 8238 | Y |  |  | 0 | 65572 | 55605
55617 | Rebuild 69 kV line from Campwood to Rocksprings | Campwood to New Barksdale: Rebuild 69 kV line |  | New Barksdale | Campwood | Planned | 1102 - 1280 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3820 | 2026-01-01 |  | 69 | 0 | 7.73 | 0 |  | Edwards | Edwards | Tier 3 |  |  |  |  | 8633, 8365 | Y |  |  | 0 | 65573 | 55617
61277B | Lago Vista to Nameless Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. | 1/10/2023: Added information to clarify circuit rating. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2026-01-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7352, 7526 | Y | N |  | 0 | 70670 | 61277
61279C | Nameless to Leander Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. | 1/10/2023: Added information to clarify circuit rating. | Hero Way | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2026-01-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7526, 7536 | Y | N |  | 0 | 70679 | 61279
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-01-20 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10680 | 3324
65154 | Mason Switch to Yellowjacket: Rebuild 69 kV Line | Rehab the Mason Switch to Yellowjacket 69 kV Line |  | Mason Switch | Yellowjacket | Planned | 1142 - 1320 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2836 | 2026-01-31 |  | 69 | 0 | 26.45 | 0 |  | Menard | Mason | Tier 4 | 21RPG014 | 2021-08-01 | 2021-09-01 |  | 6363, 6396, 23824 | Y | N |  | 0 | 65155 | 65154
64858 | La Palma Expansion | Construct 3 Breaker Ring Bus. Construct 345 kV Line from La Palma 345 kV station to Kingfisher 345 kV (Sharyland) station. |  | La Palma | Kingfisher | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021588 | 2026-04-30 |  | 345 | 6.5 | 0 | 0 |  | Cameron | Cameron | Tier 2 |  |  |  |  | 79501, 8317, 8383, 79500, 80137 | Y |  |  | 0 | 65264 | 64858
5981 | Shamburger North 345/138 kV Sw. Sta. | Establish Shamburger North 345/138 kV Sw. Sta. | Project Deferral | Shamburger North | Shamburger North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6083 | 2026-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 3217, 3223, 3226, 2478, 3103, 3201, 3206 | Y | N |  |  | 13696 | 5981
5982 | Relocate existing Shamburger North - Shamburger 138 kV Line | Establish 138 kV Line | Project Deferral | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6084 | 2026-05-15 |  | 138 | 10 | 0 | 0 |  | Smith | Smith | Tier 4 |  |  |  |  | 3104, 3206, 3226 | Y | N |  |  | 13697 | 5982
61234 | Antler-Bergheim Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the T493 Antler to Bergheim 138-kV and T389 Bergheim to Hays Energy 345-kV 7.2-mile double-circuit transmission line by replacing the aging conductors from Antler to Bergheim substations. |  | Antler | Bergheim | Planned | 61406, 61358, 61392, 61350, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-05-15 |  | 345 | 0 | 7.2 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7171, 7770, 7043, 7170 | Y | N |  | 0 | 61235 | 61234
61350 | Antler-Highway 46 Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the T610 Antler to Highway 46 138-kV and T389 Bergheim to Hays Energy 345-kV 10.4-mile double-circuit transmission line by replacing the aging conductors from Antler to Highway 46 substations. |  | Antler | Highway 46 | Planned | 61406, 61358, 61392, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-05-15 |  | 345 | 0 | 10.4 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 |  |  | 7171, 7770, 7043, 7177 | Y | N |  | 0 | 61351 | 61350
61392 | Bergheim-Fair Oaks Ranch Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T238 Bergheim to Fair Oaks 138-kV and T656 Bergheim to Kendall 345-kV 4.1-mile double-circuit transmission line by replacing the aging conductor. |  | Bergheim | Fair Oaks Ranch/Kendall | Planned | 61406, 61358, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-05-15 |  | 345 | 0 | 4.1 | 0 |  | Comal | Kendall | Tier 4 | 22RPG005 | 2022-03-04 |  |  | 7046, 7170, 7169, 7770 | Y | N |  | 0 | 61393 | 61392
6304 | Shamburger North - Shamburger 345 kV Line | Upgrade existing 345 kV Line | Project Deferral | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6085 | 2026-05-28 |  | 345 | 10 | 10 | 0 |  | Smith | Smith | Tier 3 |  |  |  |  | 3103, 3223 | Y | N |  |  | 14033 | 6304
61270 | Friendship to Rutherford Storm Hardening | Rebuild single circuit section of Friendship to Rutherford and reconductor with bundled 795 ACSR Conductor, 440 MVA. |  | Friendship | Rutherford | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2026-05-30 |  | 138 | 0 | 4.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7507, 7509 | Y | N |  | 0 | 61271 | 61270
70706 | Tungsten(Carbide): Rebuild Station | Rehab Tungsten(Carbide) 138/69 kV Station |  | Tungsten |  | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2026-05-30 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 3 |  |  |  |  | 8152, 8161, 8189, 8190, 8144, 8149, 8154, 8159, 8536, 8723, 80135 | Y |  |  | 0 | 70707 | 70706
66101 | Del Sol - Frontera: Build new 345 kV Dbl Circuit Line | Build New 345 kv Double Circuit line from Del Sol to Frontera 345 kV Station |  | Del Sol | Frontera | Planned |  | ETT | Charity Kreher bcogan@aep.com 918-599-2857 | TP2020838 | 2026-05-31 |  | 345 | 36 | 0 | 0 |  | Starr | Hidalgo | Tier 1 |  |  | 2021-12-10 |  | 8992, 80119, 8355, 80355, 8980 | Y |  |  | 0 | 66102 | 66101
66386 | Albany to Throckmorton: Rebuild 69 kV line | Rehab 69 kV line from Albany to Throckmorton |  | Albany | Throckmorton | Planned |  | AEP TNC | Raza Ansari mlforcum@aep.com 918-599-2674 |  | 2026-05-31 |  | 69 | 0 | 32.36 | 0 |  | Shackelford | Throckmorton | Tier 4 | 21RPG015 | 2022-08-21 | 2022-09-21 |  | 6205, 6206, 6207 | Y | N |  | 0 | 66387 | 66386
15TPIT0031 | Chavaneaux_Chavaneaux Tap Rebuild (Brooks to Chavaneaux ckt) | Rebuild 138 kV transmission from Chavaneaux to Chavaneaux Tap. This rebuild is for Brooks to Chavaneaux ckt. |  | Brooks | Chavaneaux | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0260 | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y |  |  | There are no transformers associated with this project | 9555 | 2304
4577 | BRYN_4577_Dansby_Rebuild | Convert Dansby 69kV bus to Double Bus, Double Breaker configuration |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-06-01 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  |  | 32875, 32897 | Y |  |  | 0 | 64551 | 4577
6687 | Rebuild Rio Hondo to East Rio Hondo | Rebuild the 138 kV line from Rio Hondo to East Rio Hondo. |  | Rio Hondo | East Rio Hondo | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2026-06-01 |  | 138 | 0 | 8.19 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5764, 8319 | Y | N |  |  | 14458 | 6687
69709 | LCRATSC_Bearkat_NorthMcCamey_SandLake_TransmsissionLineAddition | LCRA TSC, Oncor , and WETT joint project to add the Bearkat-North McCamey 345-kV double-circuit transmission line and North McCamey-Sand Lake 345-kV double-circuit transmission line. 22RPG010 |  | Bearkat | Sand Lake | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG +151-257-84514 |  | 2026-06-01 |  | 345 | 165 | 0 | 0 |  | Glasscock | Ward | Tier 1 | 22RPG010 |  | 2022-04-12 |  | 11098, 59903, 76000 | Y | Y |  | 0 | 69710 | 69709
71408 | Upgrade CKT943 to 3000 amperes | Replace existing 2-795ACSR conductors with 2-795 ACSS conductors and the upgrade the terminal equipment to 3000 amperes. |  | Lytton Springs | Pilot Knob | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-01 |  | 138 | 0 | 11.13 | 0 |  | Caldwell | Travis | Tier 4 |  |  |  |  | 9075, 9259 | Y |  |  | 0 | 71409 | 71408
71877 | CPSE_Cagnon to Shepherd Rebuild (Phase B) |  |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0281 | 2026-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5054, 5378, 5230, 5465 | Y |  |  | 0 | 71878 | 71877
71952 | LCRA TSC Bluffton to Buchanan Transmission Line Overhaul | Overhaul circuit and replace conductor with single-Drake conductor (117 MVA) from Bluffton to Buchanan. Replacement structures should be 138-kV double-circuit capable of supporting a single-Suwannee conductor. Install OPGW. |  | Bluffton | Buchanan | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 138 | 0 | 7 | 0 |  | Llano | Llano | Tier 4 | [5 empty] | Y | N |  | 0 | 71953 | 71952
70367B | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Mountan Top to Blanco and Blanco to Devil's Hill 69 kV circuits to 138 kV with bundled 795 kcmil conductor (440 MVA). |  | Blanco | Devil's Hill | Planned |  | PEC | Joshua Rivers Joshua.Rivers@peci.com (830) 330-4192 |  | 2026-07-01 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 7484, 7482, 7493 | Y | Y |  | 0 | 70369 | 70367
66023 | T340 T-Line Upgrade | Upgrading the Marion to Sheriff's Posse Transmission Line T340 from 795 ACSR to 959 ACSS conductor. Upgrades to conductor and structures are included. Structures designed for ultimate build-out of double-circuit bundled 959 ACSS in preparation for additional future capacity. |  | Marion | Sheriff's Posse | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2026-07-31 |  | 138 | 0 | 3.4 | 0 |  | Guadalupe | Comal | Tier 4 |  |  |  |  | 7178, 7460 | Y | N |  | 0 | 66024 | 66023
66200D | Upgrade Taylor - Holland 69 kV Line | Rebuild the Granger - Taylor 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6173 | 2026-09-15 |  | 69 | 0 | 5.9 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3644, 3645, 3646, 3648, 3649, 13646 | Y |  |  | 0 | 71897 | 66200
66206A | Upgrade Temple - Minerva 69 kV Line | Upgrade Temple - Marak 69 kV Line |  | Temple | Marak | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6186 | 2026-09-15 |  | 69 | 20.5 | 0 | 0 |  | Bell | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3643, 3689 | Y |  |  | 0 | 68923 | 66206
70630 | Ballinger to Santa Anna: Rebuild 69 kV line | Rebuild 69 kV line and rebuild taps on the Ballinger to Santa Anna 69 kV line. |  | Ballinger | Santa Anna | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-282-8375 |  | 2026-11-30 |  | 69 | 0 | 0 | 0 |  | Runnels | Coleman | Tier 3 | 22RPG028 | 2022-09-01 |  |  | 6341, 6342, 6344, 6345, 6346, 60019, 60024, 60029, 6329, 6338, 6343, 6349, 6353 | Y |  |  | 0 | 70664 | 70630
50647 | CPSE_Merida to Westside MLSE | Upgrade terminal at Merida to ensure a 2000 A rating. |  | Merida | Westside | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0773 | 2026-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5490 | Y |  |  | 0 | 50648 | 50647
66492 | Chico West - Oran Switch 69 kV Line Conversion to 138 kV | Convert existing 69 kV Line to 138 kV |  | Chico West | Oran | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3006 | 2026-12-15 |  | 69 | 0 | 0 | 0 |  | Wise | Palo Pinto | Tier 4 |  |  |  |  | 1542, 1553, 1554, 1555, 1556, 1557, 1558, 1572, 11556 | Y |  |  | 0 | 71939 | 66492
70900E | Roanoke Area Upgrades | Establish Roanoke_Exchange 138 kV Line |  | Roanoke Switch | Exchange Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5281 M5144 M5146 M5148 | 2026-12-15 |  | 138 | 11.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 1854, 12077 | Y | N |  | 0 | 72017 | 70900
71912B | Rebuild the Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Park Street Tap - Killeen Taft 138 kV Line |  | Killeen Park Street Tap | Killeen Taft | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6245 | 2026-12-15 |  | 138 | 0 | 3.3 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3619, 3621, 3639 | Y |  |  | 0 | 71914 | 71912
72011 | Tonkawa - Morgan Creek - Midland East 345 kV Project | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Morgan Creek | Midland East - Tonkawa | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3025 | 2026-12-15 |  | 345 | 0 | 212.2 | 0 |  | Martin | Scurry | Tier 1 |  |  |  |  | 1030 | Y |  |  | 0 | 72012 | 72011
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0733 | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y | Y |  |  | 11872 | 4320
66447 | Reforzar: Build new 345 kV station | Construct a new 345 kV 9-breaker breaker-and-a-half station (Reforzar) |  | REFORZAR |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022035 | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Brooks |  | Tier 1 |  |  |  |  | 80078, 8455, 8905 | Y |  |  | 0 | 67317 | 66447
67318 | Cruce: Build new 345 kV station | Construct a new 345 kV 12-breaker breaker-and-a-half station (Cruce) |  | Cruce |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022034 | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Duval |  | Tier 1 |  |  |  |  | 80079 | Y |  |  | 0 | 67319 | 67318
67320 | Cruce to Reforzar: Build new 345 kV double circuit line | Construct a new 345 kV double circuit from Cruce to Reforzar |  | Cruce | Reforzar | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022033 | 2027-01-01 |  | 345 | 48 | 0 | 0 |  | Duval | Brooks | Tier 1 |  |  |  |  | 80078, 80079 | Y |  |  | 0 | 67339 | 67320
67322 | Cenizo to Cruce: Build new 345 kV double circuit line | Construct a new 345 kV double circuit from Cenizo to Cruce |  | Cenizo | Cruce | Planned |  | AEP TCC/ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022031 | 2027-01-01 |  | 345 | 69 | 0 | 0 |  | Webb | Duval | Tier 1 |  |  |  |  | 80079, 80220 | Y |  |  | 0 | 67323 | 67322
67324 | Cruce to Del Sol: Build new 345 kV double circuit line | Construct a new 345 kV double circuit from Cruce to Del Sol |  | Cruce | Del Sol | Planned |  | AEP TCC/ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022032 | 2027-01-01 |  | 345 | 36 | 0 | 0 |  | Duval | Starr | Tier 1 |  |  |  |  | 80079, 80355 | Y |  |  | 0 | 67325 | 67324
67326 | Ajo to Reforzar: Build new 345 kV double circuit line | Construct a new 345 kV double circuit from Ajo to Reforzar |  | Ajo | Reforzar | Planned |  | AEP TCC/ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022030 | 2027-01-01 |  | 345 | 11 | 0 | 0 |  | Kenedy | Brooks | Tier 1 |  |  |  |  | 80076, 80078 | Y |  |  | 0 | 67327 | 67326
67329 | San Miguel to Cruce 345 kV lines | New San Miguel to Cruce 345 kV double circuit lines |  | San Miguel | Cruce | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2027-01-01 |  | 345 | 265.6 | 0 | 0 |  | Atascosa | Duval | Tier 1 | 21RPG017 | 2021-09-23 | 2021-12-23 |  | 5901, 80079 | Y |  |  | 0 | 67330 | 67329
54892 | Eden to North Brady: Rebuild 69 kV line | Rehab Eden to North Brady 69 kV line | Schedule Update | Eden | North Brady | Planned | 1039 - 1266 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1856 | 2027-04-30 |  | 69 | 0 | 32.7 | 0 |  | Concho | McCulloch | Tier 3 |  |  |  |  | 6384, 60797, 6006, 6372, 6380, 6385 | Y | N |  | 0 | 65568 | 54892
12TPIT0080 | Forney Sw. Sta. Second 600 MVA, 345/138 kV Autotransformer | Add second 345/138 autotransformer | Project Deferral | Forney Sw. Sta. |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4037 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 3 |  | 2008-06-01 | 2008-07-01 |  | 2437, 2438 | Y | N | 2007-R2 |  | 9769 | 2489
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line | Project Deferral | Handley | Hemphill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5214 | 2027-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 11818 | 4270
6287 | Sherry Sw. - Webb/Kennedale 345 kV DCKT Line | Upgrade the existing 345 kV Line |  | Sherry | Webb/Kennedale | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4252 | 2027-05-15 |  | 345 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 3 |  |  |  |  | 1911, 1918, 1930, 1929, 1932, 1934 | Y |  |  |  | 14016 | 6287
5524 | Royse South 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | Royse | Forney | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4234 | 2027-05-15 12:00 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 3 |  |  |  |  | 2469, 2470, 12471, 2437, 2467, 2471, 2478, 2702, 2472, 2474, 2710, 3223 | Y | N |  | 0 | 49918 | 5524
4323 | CPSE_Braunig to Brooks_MLSE | Upgrade terminal at Brooks and ensure a rating of 2000 A (minimum) at both Braunig and Brooks terminals |  | Braunig | Brooks | In-Service |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0669 | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5394, 5045 | Y | Y |  |  | 11875 | 4323
67091 | Second 138 kV transmission Line from DL-DP CKT1034 | Second 138 kV transmission Line from Dunlap to Decker CKT1034 |  | 9045 | 9188 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 138 | 5.22 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9045, 9188 | Y |  |  | 0 | 67092 | 67091
45068 | Merida to Harlandale Rebuild | CPSE_Merida to Harlandale Rebuild |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0233 | 2027-06-05 |  | 138 | 0 | 10 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5310, 5385, 5395 | Y |  |  | 0 | 45069 | 45068
66206B | Upgrade Temple - Minerva 69 kV Line | Upgrade Marak - Minerva 69 kV Line |  | Marak | Minerva | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6186 | 2027-09-15 |  | 69 | 13.1 | 0 | 0 |  | Milam | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3643, 3684, 3685, 3689 | Y |  |  | 0 | 68924 | 66206
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2027-11-20 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7622 | Y | N |  |  | 10677 | 3321
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2027-12-18 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7239 | Y | N |  |  | 10694 | 3336
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line | Project Deferral | Cresson | Rocky Creek | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5228 | 2028-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  |  | 1881, 2202 | Y | N |  |  | 12436 | 4834
6777 | Cedar Hill - Liggett 138 kV Line | Loop Cedar Hill - Liggett 138 kV line in to Home Run Substation | Project Deferral | Grand Prairie West | Mayfield Tap | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4270 | 2028-05-15 02:01 |  | 138 | 7 | 0 | 0 |  | Dallas | Tarrant | Tier 4 |  |  |  |  | 2143, 1912, 1919, 2138, 2265 | Y | N |  | 0 | 51988 | 6777
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into future 138kV Martinez to Skyline transmission line |  | Converse | Martinez-Skyline | Planned | T-0177 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0601 | 2028-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5098, 5294, 5368 | Y | N |  | There are no transformers associated with this project | 8143 | 967
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Howard line. |  | Masterson Rd. | Cagnon-Howard | Planned | T-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0538 | 2028-06-01 |  | 138 | 8 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5296, 5054, 5230 | Y | N |  | There are no transformers associated with this project | 9466 | 2218
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0385 | 2028-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5416, 5250, 5395 | Y | N |  | There are no transformers associated with this project | 10365 | 3021
45535 | Valley_to_ValleyTap_Rebuild | Rebuild an approximate four circuits miles of 138 kV Transmission line from Valley Tap to Valley Road substation. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0279 | 2028-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5025, 5053, 5465 | Y |  |  | 0 | 45536 | 45535
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and-or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle-Weiderstein | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0645b | 2028-06-01 12:00 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5360, 5435 | Y | N |  | There are no transformers associated with this project | 9557 | 2306
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2028-12-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5626, 5634 | Y | N |  |  | 11275 | 3818
55550 | Brushline: Construct New Distribution Station | Brushline: Construct New Distribution Station |  | HIDALGO ENERGY CENTER (HEC) | STEC ADERHOLD | Planned | 1106 - 1284 | AEP TCC | Rick Garcia bcogan@aep.com 918-599-2857 | 3826 | 2029-07-01 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8972, 5754, 8963 | Y |  |  | 0 | 55551 | 55550
6666 | BRYN_6666_Steele_Store_to_Cooks_Point | Construct 138kV line from BTU Steele Store to LCRA Cooks Point (Bundled 1033 ACSR - Curlew) |  | 32852 | 7569 | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2030-12-31 |  | 138 | 6 | 0 | 0 |  | Brazos | Burleson | Tier 4 |  | 2016-07-07 | 2017-07-07 |  | 32852, 7569 | Y |  |  | 0 | 64750 | 6666

## CompletedTPIT020123NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2023
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
61262B | Hunter to McCarty Lane Storm Hardening | Rebuild double-circuit section of Hunter to McCarty Lane 138 kV with single, circuit bundled 795 ACSR Conductor, 440 MVA. This project is in conjunction with LCRA TSC project of McCarty Lane - Ranch Road ( and ERCOT Project #54105). | For total project cost please see 61262A | McCarty Lane | Hunter | In-Service |  | PEC/LCRATSC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2022-01-01 | 2022-01-01 | 138 | 0 | 1.57 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7491 | Y | N |  | 0 | 63728 | 61262
52072 | Conan: Build new 69 kV box bay | Construct new 69 kV box bay on the Santa Anna to Cross Plains 69 kV line and install capacitor bank | IN-SERVICE | Conan |  | In-Service | 1066 - 1239 | AEP TNC | William Lovelace mlforcum@aep.com 918-599-2674 | 2827 | 2022-01-12 | 2022-01-12 | 69 | 0 | 0 | 0 | 0,7.2 | Callahan |  | Tier 4 |  |  |  |  | 6350, 6356, 60455, 6352, 6357 | Y | N |  | 0 | 52073 | 52072
52533 | Gebhardt to Sealy Ckt.65A Upgrades | Upgrade Ckt.65A Gebhardt to Sealy to increase thermal limits (Transmission Design Hardening Project). |  | Gebhardt | Sealy | In-Service | 525535253359322 | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2022-01-22 | 2022-02-01 | 138 | 0 | 2.46 | 0 |  | Austin | Austin | Tier 3 | 20RPG020 | 2020-10-27 | 2020-11-18 |  | 44640, 44700 | Y | N |  | 0 | 52534 | 52533
57414 | BEARLE (BER) 138kV Customer Substation | BEARLE (BER) 138kV customer substation looped into Ckt.96C Philip to South Channel |  | BEARLE | Philip/South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 | 2022-01-31 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41230, 41250, 41370 | Y | N |  | 0 | 57415 | 57414
64150 | Smithers Sub Exp Braes Power - (20INR0221) | Expand Smithers 345kV substation and install one generator lead for new interconnection to Braes Power. |  | Smithers |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 | 2021-11-09 | 345 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 44650, 112419 | Y | N |  | 0 | 64151 | 64150
52529 | Jordan to Cities to Dalton Ckt.86I | Upgrade Ckt.86I Jordan to Cities to Dalton to increase thermal limits. |  | Jordan | Dalton | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 | 2022-01-24 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40340, 40740, 40857 | Y | N |  | 0 | 52530 | 52529
51216E | Ward Winkler RPG | Construct two 138kV tie-lines between TNMP Cedarvale and Oncor Sand Lake. |  | TNMP Cedarvale (38145) | Oncor Sand Lake (11097) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-01-31 |  | 138 | 1.56 | 0 | 0 |  | Ward | Ward | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 11097, 38145 | Y |  |  | 0 | 56660 | 51216
64161 | Addicks Auto A2 Replacement for Failed Auto | Replace failed Addicks auto A2 with 800MVA spare auto |  | Addicks |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 | 2022-01-27 | 345 | 0 | 0 | 200 |  | Harris |  | Tier 4 |  |  |  |  | 45600, 45610, 49083 | Y | N |  | 0 | 64162 | 64161
60493 | Rebuild West-TI with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-01-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37060, 37080 | Y |  |  | 0 | 60494 | 60493
62841 | Add TresBahias | Re-terminate the Dupont to Joslin line. Re-terminate the Formosa to Joslin line. Install one span to POI. Install a new 138 kV rung with double breakers. Install a 138 kV breaker on the new Formosa terminal. Install EPS metering on the Tres Bahias terminal |  | Joslin | Tres Bahias | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2019312 | 2022-01-31 |  | 138 | 0.05 | 0 | 0 |  | Calhoun | Calhoun | Tier 4 |  |  |  |  | 8661, 8140 | Y |  |  | 0 | 65597 | 62841
3949 | Steamboat to Winters: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola | IN-SERVICE | Steamboat | Winters | In-Service | 685 - 0855 | ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | 1850 | 2022-02-01 | 2022-02-01 | 69 | 0 | 9.944 | 0 |  | Taylor | Runnels | Tier 4 |  |  |  |  | 6333, 60332 | Y | N |  |  | 11442 | 3949
57161 | Rebuild Vanderbilt to VanHumble | Rebuild 4/0 ACSR with 795 ACSR on 138 kV capable poles |  | Vanderbilt | Van Humble Switch | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-02-15 | 2022-03-15 | 69 | 0 | 0.97 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 5580, 5582 | Y | N |  | 0 | 57162 | 57161
62367 | Close Feed to Martin | [6 empty] | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2022-02-16 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 9483, 61015 | Y |  |  | 0 | 62368 | 62367
6352 | Crckett Hghts to Sonora Atlntic 69 kV line: Rbld 69 kV line | Rehab Crockett Heights to Sonora Atlantic 69 kV line | IN-SERVICE | Crockett Heights | Sonora Atlantic | In-Service | 786 - 0971 | AEP TNC | Joseph Page mlforcum@aep.com 918-599-2674 | 2706 | 2022-02-21 | 2022-02-21 | 69 | 0 | 16.8 | 0 |  | Crockett | Sutton | Tier 4 |  |  |  |  | 6511, 6552 | Y | N |  |  | 14096 | 6352
55367 | Wolfcamp: Build 138 kV box bay | Build new 138 kV box bay on the Big Lake to North McCamey line | IN-SERVICE | Wolfcamp |  | In-Service | 1087 - 1270 | AEP TNC | Michael Richardson mlforcum@aep.com 918-599-2674 | 1860 | 2022-02-21 | 2022-02-21 | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | 60799, 60361, 60723 | Y | N |  | 0 | 55368 | 55367
47442 | Graphite Mine Circuit Breaker Addition | LCRA TSC will increase the reliability of transmission facilities along T109 by adding three 138-kV, 3000A, 40kAIC circuit breakers in ring-bus configuration at the Graphite Mine Substation. |  | Graphite Mine | Graphite Mine | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-02-24 | 2022-06-01 | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  |  | 7084 | Y | N |  | 0 | 47443 | 47442
54105 | McCarty Lane - Ranch Road 12 Transmission Line Upgrade | Increase the reliability of transmission facilities on the T699 McCarty Lane ¿ Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | McCarty Lane | Ranch Road 12 | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-02-24 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7186 | Y | N |  | 0 | 54106 | 54105
59117 | Tres Bahias Solar Interconnection | Tres Bahias Solar Interconnection | IN-SERVICE | Joslin |  | In-Service |  | AEP TCC | Michael Miller bcogan@aep.com 918-599-2857 | TP2019312 | 2022-02-24 | 2022-02-24 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8661, 8140 | Y |  |  | 0 | 59118 | 59117
49834 | Fullerton 138 kV Switch Terminal Addition | Fullerton 138 kV Switch Terminal Addition |  | Fullerton | Fullerton | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9037 | 2022-02-24 01:00 | 2021-06-21 | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1274, 11275, 1272, 11274, 11277, 11284 | Y |  |  | 0 | 49835 | 49834
49841 | Fullerton_to_NorthAndrews_138_kV_Conversion_East | Fullerton_to_NorthAndrews_138_kV_Conversion_East |  | Fullerton | North Andrews | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9038 | 2022-02-25 | 2021-06-21 | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1285, 1159, 1160, 11274, 11275 | Y |  |  | 0 | 49842 | 49841
49858 | Fullerton_to_NorthAndrews_138_kV_Conversion_West | Fullerton_to_NorthAndrews_138_kV_Conversion_West |  | Fullerton | North Andrews | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9039 | 2022-02-26 | 2021-05-25 | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1160, 1267, 1270, 11274, 1159, 1272, 11275 | Y |  |  | 0 | 49859 | 49858
59550 | Relocate Exxon Means to Landfill 138 kV POD | Relocate Exxon Means to new Landfill 138 kV POD and remove 4.3 miles of 138 kV line |  | Andrews North | Means | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8563 | 2022-02-27 | 2021-12-20 | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1159, 1165, 11264, 1166, 1285 | Y |  |  | 0 | 59572 | 59550
62001 | Tex Gulf Customer Substation Bypass as Ckt.60C | Disconnect Tex Gulf customer substation. Convert New Gulf substation to loop service to create new Ckt.60C South Lane City to New Gulf to to Pledger tap to West Columbia |  | South Lane City/ New Gulf | Pledger tap/ West Columbia | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 | 2022-02-22 | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 43010, 43011, 43012, 43120, 43340, 43341, 48253, 48254, 48341, 904839, 905294, 43380, 43190 | Y | N |  | 0 | 67129 | 62001
52565F | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Thermally-uprate Ckt.05B HO Clarke to Intermediate tap to a minimum 340 MVA Continuous. Thermally-uprate Ckt.05B Intermediate tap to Southwyck to increase thermal limits |  | HO Clarke | Southwyck | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 |  | 138 | 0 | 2.86 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44361, 47150, 43260 | Y | N |  | 0 | 63577 | 52565
6112 | Causeway to Sunchase:Build new 138 kV Line | Rehab Causeway - Sunchase 138 kV Line | IN-SERVICE | Causeway | Sunchase | In-Service | 826 - 1010 | AEP TCC | Kenneth Haley bcogan@aep.com 918-599-2857 | 3627 | 2022-02-28 | 2022-02-28 | 138 | 0 | 3.56 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8744, 8917 | Y | N |  |  | 13838 | 6112
55957 | COUGAR to Gulfgate Ckt.91 Upgrades | Upgrade Ckt.91 COUGAR to Gulfgate tap to minimum 478MVA emergency rating |  | COUGAR | Gulfgate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 | 2022-04-30 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42741, 47560 | Y | N |  | 0 | 55958 | 55957
44872 | Asherton 138 kV Station | Add breaker at Asherton 138 kV Station to Accommodate Shakes Solar | IN-SERVICE | Asherton | - | In-Service | 966 - 1144 | AEP TCC | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3724 | 2022-02-28 | 2022-02-28 | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  |  | 88283, 8283 | Y | N |  | 0 | 44873 | 44872
64495 | Cedar Bayou Generator Lead Upgrade | Upgrade equipment on the generator lead to Cedar Bayou CBY-1 unit Upgrade to Minimum 851 MVA Continuous rating |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 | 2022-03-01 | 138 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  |  | 40015, 49200 | Y | N |  | 0 | 64496 | 64495
55628 | Rio Hondo: Upgrade 138 kV terminal | Upgrade 138 kV STEC East Rio Hondo terminal at Rio Hondo | IN-SERVICE | Rio Hondo |  | In-Service | 1103 - 1281 | AEP TCC | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3821 | 2022-02-28 | 2022-02-28 | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8319 | Y |  |  | 0 | 55629 | 55628
44862 | Schottky: Build 69 kV Box bay | New Schottky 69 kV Station, replaces Hard Tap | IN-SERVICE | Schottky |  | In-Service | 971 - 1149 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3729 TP2018130 | 2022-02-28 | 2022-02-28 | 69 | 0 | 0 | 0 |  | Live Oak |  | Tier 4 |  |  |  |  | 8507, 88507, 8400, 8406 | Y | N |  | 0 | 45151 | 44862
64997 | SYLVAN to Morgans Point Ckt.79B Rebuild for Hardening | Rebuild Ckt.79B SYLVAN to LaPorte tap to Morgans Point as a Hardening upgrade |  | SYLVAN | Morgans Point | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 12:00 | 2022-03-09 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40942, 41520, 41100 | Y | N |  | 0 | 64998 | 64997
57165 | Red Gate138/69 autotransformer and lines to McCook and Faysw | Adds 69 kV bus at Red Gate, a 138/69 autotransformer at Red Gate, and connects 69 kV lines to McCook#1 and Faysville Switch. |  | Red Gate | McCook and Faysville SW | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-03-15 | 2022-06-27 | 138 | 1 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5779, 5780, 5784, 5782, 88380, 5783, 8377, 161031 | Y | N |  | 0 | 63729 | 57165
45334 | Corichi: Build 138 kV Box Bay | Build New Box Bay on El Campo - Victoria Line | IN-SERVICE | Corichi |  | In-Service | 986 - 1164 | AEP TCC | Marc Wilson bcogan@aep.com 918-599-2857 | 3737 TP2018143 | 2022-03-16 | 2022-03-16 | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 8099, 88099, 8102, 8117 | Y | N |  | 0 | 45335 | 45334
53962 | Turtle Creek - Verde Creek Transmission Line Overhaul | LCRA TSC will perform an overhaul of T221 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T221 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  | Turtle Creek | Verde Creek | In-Service |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-03-22 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7146, 7442 | Y | N |  | 0 | 53963 | 53962
52100 | Bradshaw to Steamboat: Rebuild 69 kV line | Rebuild Bradshaw to Steamboat 69 kV line | IN-SERVICE | Bradshaw | Steamboat | In-Service | 1069 - 1242 | ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | 2830 | 2022-03-28 | 2022-03-28 | 69 | 0 | 0.25 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6331, 60332, 6328, 60456 | Y | N |  | 0 | 65563 | 52100
51990 | AEN_21TPIT51990_New_Dunlap_345kV_Auto_AT2_PMCR | Second 345/138 kV autotransformer addition at Dunlap substation |  | 9044 | 9045 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2022-03-30 |  | 345 | 0 | 0 | 672 |  |  |  | Tier 4 |  |  |  |  | 90007, 9044, 9045 | Y |  |  | 0 | 59171 | 51990
62305 | STP to WA Parrish: Increase 345 kV Line MOT | Increase the MOT on STP to WA Parrish 345 kV line | In Service | STP | WA Parrish | In-Service |  | AEP TCC | Marc Wilson bcogan@aep.com 918-599-2857 | TA2021002 | 2022-03-30 | 2022-03-27 | 345 | 0 | 0 | 0 |  | Matagorda | Fort Bend | Tier 4 |  |  |  |  | 5915, 44000 | Y | Y |  | 0 | 62306 | 62305
59119 | Sparta Solar Interconnection | Sparta Solar Interconnection | IN-SERVICE | Tango |  | In-Service |  | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | TP2020136 | 2022-03-30 | 2022-03-30 | 345 | 0.01 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 88690, 8689 | Y |  |  | 0 | 59120 | 59119
44361 | Ft. Stockton SW: Build 138 kV station | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138 kV, reterminate into Solstice, install 138 kV capacitor bank at Solstice, and build new Ft. Stockton Switch 138 kV station | IN-SERVICE | Fort Stockton Switch |  | In-Service | 908 - 1086 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 2735 | 2022-03-30 | 2022-03-30 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 3 | 17RPG018 | 2017-12-22 | 2018-02-02 |  | 60717 | Y | N |  | 0 | 44362 | 44361
6022 | Stamford to Haskell Tap 1 69 kV line: Rebuild 69 kV line | Rehab Stamford to Haskell Tap 1 69 kV line | IN-SERVICE | Stamford | Haskell Tap 1 | In-Service | 786 - 0971 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2668 | 2022-03-30 | 2022-03-30 | 69 | 0 | 12.22 | 0 |  | Jones | Haskell | Tier 4 |  |  |  |  | 6171, 6172 | Y | N |  |  | 13739 | 6022
62365 | Close Feed to Martin | [6 empty] | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2022-03-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 9486, 60799 | Y |  |  | 0 | 62366 | 62365
64497 | Dyann to South Lane City Ckt.60D Upgrade | Upgrade Dyann to South Lane City Ckt.60D to increase thermal limits |  | Dyann | South Lane City | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 | 2022-04-11 | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 42985, 43190 | Y | N |  | 0 | 64498 | 64497
57756 | WOLF 345kV for Fighting Jays Solar (21INR0278) | New 345kV CNP WOLF (WLF) substation for generator interconnection to Fighting Jays Solar. Loop Ckt.64C into substation to create new Ckt.64 Hillje to WOLF to WA Parish. |  | WOLF | Hillje/WA Parish | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 | 2022-03-13 | 345 | 0 | 0 | 0 |  | Wharton | Fort Bend | Tier 4 |  |  |  |  | 44160, 44000, 44200, 112495 | Y | N |  | 0 | 57757 | 57756
55971 | Eagle Nest (EGL) Sub for Brazoria West Solar (20INR0101) | Install new 138kV Eagle Nest substation for generator interconnection to Brazoria West Solar. Loop Ckt.02 into Eagle Nest substation to create new Ckt.02 BURKE to Eagle Nest to West Columbia |  | Eagle Nest | BURKE/ West Columbia | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 | 2022-03-11 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42430, 42410, 43380, 111911 | Y | N |  | 0 | 56717 | 55971
6938 | Leonard Road Substation 69 | Construct Leonard Rd Substation with Dual Voltage Transformer. Will be served at 69kV until completion of Smetana to Leonard Rd 138kV line. | [5 empty] | BRYN |  |  | 2022-03-31 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 32051, 32850, 32868, 32864 | Y |  |  | 0 | 67229 | 6938
59319A | Garrott to Midtown to Polk Ckt.90 Upgrades | Upgrade Ckt.90D Garrott to Midtown to increase thermal limits |  | Garrott | Midtown | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 | 2022-04-30 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47660, 47661, 47706, 47708, 47705 | Y | N |  | 0 | 59320 | 59319
59319B | Garrott to Midtown to Polk Ckt.90 Upgrades | Upgrade Ckt.90B Midtown to Polk to increase thermal limits |  | Midtown | Polk | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 | 2022-04-30 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47705, 47707, 47709, 47731, 47730 | Y | N |  | Cost included in main entry | 59321 | 59319
63425 | Adds TNMP Devon POI |  |  | TNMP Gemsbok (38109) | TNMP Devon (38112) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-04-01 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38112, 38107 | Y |  |  | 0 | 63426 | 63425
63661 | Interconnects Cedarvale Data Center | NOMCR ID # 71708-1 |  | TNMP Cedarvale (bus # 38145) | Customer substation (bus # 38146) | In-Service |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-04-01 |  | 138 | 0.18 | 0 | 0 | 0,480 | Ward | Ward | Tier 4 |  |  |  |  | 38146, 38145 | Y |  |  | 0 | 63662 | 63661
51216F | Ward Winkler RPG | Convert & re-conductor existing TNMP Wickett - Oncor Yucca 69kV line to 138kV, construct line extension (~1.3 miles) and re-terminate line to Oncor Wolf 138kV station. |  | TNMP Wickett (37980 / 37981) | Oncor Wolf (1013) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-04-02 |  | 138 | 1.3 | 4.7 | 0 |  | Ward | Ward | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 1013, 1015, 37940, 37960, 37980, 37981 | Y |  |  | 0 | 56661 | 51216
6281 | CPSE_Harlandal_Sommers_MLSE | Upgrade terminals at Harlandale and Sommers Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0732 | 2022-04-04 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5395 | Y |  |  |  | 14013 | 6281
53956 | Coronado - Fairland Transmission Line Upgrade | Increase the reliability of transmission facilities on the T110 Coronado - Fairland 12.4-mile 138-kV transmission line by replacing the existing Condor conductor with Drake conductor. |  | Coronado | Fairland | In-Service |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-04-14 |  | 138 | 0 | 0 | 0 |  | Burnet | Llano | Tier 4 |  |  |  |  | 7087, 7518 | Y | N |  | 0 | 53957 | 53956
44866 | Dilley - Jourdanton 69 kV Line | Rebuild Dilley - Jourdanton 69 kV Line | IN-SERVICE | Dilley | Jourdanton | In-Service | 967 - 1145 | AEP TCC | Brian Oyster bcogan@aep.com 918-599-2857 | 3725 TP2018043 | 2022-04-16 | 2022-04-16 | 69 | 0 | 44.8 | 0 |  | Frio | Atascosa | Tier 3 | 19RPG010 | 2019-05-23 | 2019-05-24 | 2019-06-17 | 8206, 8208, 8607 | Y | N |  | 0 | 66651 | 44866
17TPIT0002 | Hunt Lane to Pinn Road - 138 kV Transmission Line Rebuild | Rebuild approximately eight circuit miles of 138 kV transmission from Hunt Lane to Pinn Road |  | Hunt Lane | Pinn Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0190 | 2022-04-21 |  | 138 | 0 | 8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5054, 5234, 5305, 5345, 5427 | Y | N |  | There are no transformers associated with this project | 9558 | 2307
54109 | Fayetteville - Substation Upgrade | Increase the reliability of substation equipment at Fayetteville Substation through the replacement of the Fayetteville AT2 autotransformer and installation of two 138-kV shunt reactors. |  | Sayetteville Substation | Sayetteville Substation | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-04-25 |  | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7057, 7286, 7853 | Y | N |  | 0 | 54110 | 54109
53965 | Red Rock - Tahitian Transmission Line Overhaul | LCRA TSC will perform an overhaul of T153 with replacement structures that are capable of operating at 138-kV and supporting a single 959 ACSR Suwannee conductor. The replacement conductor on T153 will be 595 ACSR Suwannee. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  | Red Rock | Tahitian Village | In-Service |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-04-28 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7560, 7575, 7576 | Y | N |  | 0 | 53966 | 53965
58907 | AEN_22TPIT_NEW_GEN_BIGSTAR_CONNECTION_CISTERN_SUB | New 345 kV station to interconnect Big Star Solar and Storage generation interconnection |  | Holman | Lytton | Planned |  | AEN | Reza Ebrahimian Reza.Ebrahimian@austinene 512-322-6740 |  | 2022-04-30 |  | 345 | 0 | 0 | 0 |  | Fayette | Caldwell | Tier 4 |  |  |  |  | 9043, 9073, 9074 | Y |  |  |  | 58908 | 58907
59363A | Hungerford (HUG) CNP-Owned Sub for SBranch Solar (22INR0205) | New 138kV Hungerford (HUG) substation for generator interconnection to SBranch Solar. Loop Ckt.60 into substation to create new Ckt.60 East Bernard to Hungerford to Caney tap. |  | Hungerford | East Bernard/Caney | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-04-30 | 2022-04-19 | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44150, 42985, 43570, 44130, 44131, 44190, 112093 | Y | N |  | 0 | 59364 | 59363
59293 | Maddux: Build New 138 kV Station | Interconnect Concho Valley Solar to the SAPS to Treadwell AND the SAPS to Eldorado Live Oak 138 kV Lines | IN-SERVICE | Maddux |  | In-Service | 1125 - 1303 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 1870 | 2022-04-30 | 2022-04-30 | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6015, 6016, 6480, 6490, 60423 | Y | N |  | 0 | 59294 | 59293
59363B | Hungerford (HUG) CNP-Owned Sub for SBranch Solar (22INR0205) | Upgrade Ckt.60A Beasly to Orchard to Minimum 525/580 MVA to increase thermal limits |  | Beasly | Orchard | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-04-30 | 2022-03-23 | 138 | 0 | 0 | 0 |  | Wharton | Fort Bend | Tier 4 |  |  |  |  | 44190, 44541, 44540 | Y | N |  | 0 | 59365 | 59363
65711 | Rebuild Ckt.06F Holmes to Plaza as a Hardening upgrade |  |  | Holmes | Plaza | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-04-30 12:00 | 2022-04-25 | 138 | 0 | 3 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42680, 47210, 47350 | Y | N |  | 0 | 65712 | 65711
59305A | Attwater TNMP-Owned Substation (Ckt.02 PHR to Attwater) | Upgrade Ckt.02 PHR to new TNMP-owned Attwater substation |  | PHR | Attwater | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-04-30 12:00 | 2022-04-28 | 138 | 0 | 0.41 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 38745, 42015 | Y | N |  | 0 | 64489 | 59305
59305B | Attwater TNMP-Owned Substation (Ckt.02 PHR to Attwater) | Upgrade Ckt.03 PHR to new TNMP-owned Attwater substation |  | PHR | Attwater | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-04-30 12:01 | 2022-04-28 | 138 | 0 | 0.41 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 38745, 42015 | Y | N |  | See main project | 64490 | 59305
64778 | Rebuild 138kV Industrial-Brinker line to 700MVA |  |  | Industrial | Brinker | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2022-05-01 | 2022-04-01 | 138 | 0 | 0.21117 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 913, 927 | Y | N |  | 0 | 64779 | 64778
64782 | Rebuild 138kV Spencer-Industrial line to 700MVA |  |  | Industrial | Brinker | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2022-05-01 | 2022-04-01 | 138 | 0 | 0.32008 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 913, 982 | Y | N |  | 0 | 64783 | 64782
60528 | Rebuild West Columbia Main-West Columbia Local with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39500, 39530 | Y |  |  | 0 | 60529 | 60528
63772 | Hyperion: Build 345 kV Station | Build new 345 kV switch and meter structure next to the Cottonwood 345 kV station | IN-SERVICE | Hyperion |  | In-Service | 1133 - 1311 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1878 | 2022-05-04 | 2022-05-04 | 345 | 0 | 0 | 0 |  | Dickens |  | Tier 4 |  |  |  |  | 60006, 60007, 59904 | Y | N |  | 0 | 63773 | 63772
44868 | McKenzie - Westside 138 kV Line: Rebuild | Rebuild McKenzie - Westside 138 kV Line |  | McKenzie Road | Westside | Under Construction | 968 - 1146 | ETT | James Weaver bcogan@aep.com 918-599-2857 | 3726 TP2018126 | 2022-05-04 |  | 138 | 0 | 11.48 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8485, 8858 | Y | N |  | 0 | 65524 | 44868
63429 | Adds TNMP Alamo Street Substation |  |  | 16th Street (bus # 38310), Soaptree (bus # 38450), and Airport (bus # 38340) | Alamo Street Substation (bus # 38330) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-05-05 |  | 138 | 0.135 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38310, 38340, 38450 | Y |  |  | 0 | 63430 | 63429
63431 | Adds TNMP Holiday Switching Station |  |  | Century (bus # 38432), Soaptree (bus # 38450), and Alamo Street (bus # 38330) | Holiday Switching Station (bus # 38455) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-05-06 |  | 138 | 0.845 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38455, 6671, 38331, 38432, 38450 | Y |  |  | 0 | 63432 | 63431
50643 | CPSE_Spruce_Skyline MLSE | Upgrade terminals at Spruce and Skyline to ensure a 3000 A rating (minimum). |  | Skyline | Spruce | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0899b/S-0899c | 2022-05-13 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5371, 5400 | Y |  |  | 0 | 50644 | 50643
61849 | Clear Springs AT2 Autotransformer Upgrade | Increase the reliability of substation equipment at Clear Springs Substation through the replacement of the Clear Springs AT2 345/138-kV autotransformer. |  | Clear Springs 138 | Clear Springs 345 | In-Service |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-05-13 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7050, 7680, 77680 | Y | N |  | 0 | 61850 | 61849
46968 | Gabriel Substation Upgrade | LCRA TSC will upgrade the configuration of the 138-kV bus from single bus/single breaker to a breaker and a half bus configuration and replace five existing CBs at Gabriel Substation and provide for future Georgetown PWT addition. |  | Gabriel | Gabriel | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-13 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y | N |  | 0 | 46969 | 46968
6980 | Weimar Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Weimar Substation. |  | Weimar |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Colorado |  | Tier 4 |  |  |  |  | 7254, 7258 | Y | N |  |  | 14797 | 6980
61522 | Salt Flat Road 138 kV Capacitors | Add Salt Flat Road 138 kV Capacitors |  | Salt Flat Road | Salt Flat Road | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8575 | 2022-05-15 | 2022-05-09 | 138 | 0 | 0 | 0 | 0,55.2 | Midland | Midland | Tier 4 |  |  |  |  | 23859 | Y |  |  | 0 | 61526 | 61522
58002 | Foxtrot: Construct new 345 kV Station | Cut the 345 kV Goddard to Pawnee 345 kV line into the new 345 kV Tango station. Install one span to Foxtrot POI | IN-SERVICE | GODDARD | STEC PAWNEE | In-Service | 1120 - 1298 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020080 | 2022-05-15 | 2022-05-15 | 345 | 45.84 | 0 | 0 |  | San Patricio | Bee | Tier 4 |  |  |  |  | 8689, 88689, 5725, 8606 | Y |  |  | 0 | 58003 | 58002
7118 | Everman 345 kV Sw. Sta. | Rebuild Everman 345 kV Sw. Sta. |  | Everman |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5278 | 2022-05-15 |  | 345 | 0 | 0 | 0 |  | Tarrant |  | Tier 3 | 20RPG013 | 2020-07-01 | 2020-09-10 |  | 1882, 1885, 1886, 1887, 11885, 11886, 11888, 1880, 1900, 1906, 1907, 1931, 1932, 1935, 2285, 11882, 11887, 11884, 24997 | Y |  |  | 0 | 60063 | 7118
59409 | Centralia 138 kV Capacitors | Add Centralia 138 kV Capacitors |  | Centralia | Centralia | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8568 | 2022-05-15 | 2022-05-24 | 138 | 0 | 0 | 0 | 0,55.2 | Upton | Upton | Tier 4 |  |  |  |  | 11209 | Y |  |  | 0 | 59534 | 59409
57163 | Rebuild VanHumble to Olivia Switch | Rebuild 4/0 ACSR with 795 ACSR on 138 kV capable poles |  | Van Humble Switch | Olivia Switch | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-05-15 | 2022-06-21 | 69 | 0 | 14.4 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 5574, 5580 | Y | N |  | 0 | 57164 | 57163
54101 | Ranch Road - Hilltop Transmission Line Upgrade | Increase the reliability of transmission facilities on the T375: Hilltop-Ranch Road 12 3.95-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | Ranch Road 12 | Hilltop | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7186, 7190 | Y | N |  | 0 | 54102 | 54101
5624 | Killeen Sw. Sta. 345/138 kV Autotransformer Replacement | Replace existing autotransformer |  | Killeen Sw. Sta. | Killeen Sw. Sta | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R797 | 2022-05-15 | 2022-05-01 | 345 | 0 | 0 | 600 | -75,0 | Bell | Bell | Tier 4 |  |  |  |  | 3422, 3423, 13423 | Y | N |  |  | 13354 | 5624
59421 | Aquifer Tap 138 kV Capacitors | Add Aquifer Tap138 kV Capacitors |  | McIlvain POI | Pecone POI | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8562 | 2022-05-15 | 2022-07-05 | 138 | 0 | 0 | 0 | 0,110.4 | Reeves | Reeves | Tier 4 |  |  |  |  | 11377, 11105, 11182 | Y |  |  | 0 | 69443 | 59421
59412 | Grady 138 kV Capacitors | Add Grady 138 kV Capacitors |  | Grady | Grady | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8571 | 2022-05-15 | 2022-06-14 | 138 | 0 | 0 | 0 | 0,55.2 | Martin | Martin | Tier 4 |  |  |  |  | 23842 | Y |  |  | 0 | 59535 | 59412
47426 | Clear Fork - Robert Brown Transmission Line Overhaul | Increase the reliability and capability of circuit T519 on the Clear Fork - Robert Brown Jr 8.8-mile 69-kV transmission line. Upgrade all structures to 138-kV class and bundled Suwannee capable. Upgrade conductor to bundled 959 ACSS Suwannee. Add OPGW. |  | Clear Fork | Robert Brown Jr | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-15 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7194, 7195 | Y | N |  | 0 | 47427 | 47426
14TPIT0056 | Northaven - Morrison 138 kV line | Upgrade existing double-circuit line |  | Northaven | Morrison | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4088-E | 2022-05-15 |  | 138 | 0 | 12 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2655, 2656, 2660, 2661, 2662, 2663, 2782, 2783 | Y | N |  |  | 9773 | 2493
65924 | Soap Creek Switch (Ellis Solar) |  |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4324 | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2289, 2300, 2310 | Y |  |  | 0 | 65925 | 65924
60064 | Add Harris Creek 69 kV Capacitor | Add Harris Creek 69 kV Capacitor (Formerly known as McGregor East) |  | Harris Creek | Harris Creek | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R790 | 2022-05-15 |  | 69 | 0 | 0 | 0 | 0,55.2 | McLennan | McLennan | Tier 4 |  |  |  |  | 3596, 3441, 3586 | Y |  |  | 0 | 62663 | 60064
59541 | Wolf 138 kV Terminal Addition | Add Wolf 138 kV Terminal Addition |  | Wolf Switch | Wolf Switch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8505 | 2022-05-15 | 2022-05-18 | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 1013 | Y |  |  | 0 | 59543 | 59541
50880 | Medio Creek to Warburton (STEC) | Lon Hill - STEC Warburton: Line Rebuild | In Service | Medio Creek | STEC Warburton | In-Service | 1055 - 1228 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3783 | 2022-05-15 | 2022-05-13 | 138 | 0 | 32.7 | 0 |  | San Patricio | Refugio | Tier 3 | 19RPG014 | 2019-09-05 | 2019-10-07 |  | 5607, 8912 | Y | Y |  | 0 | 65544 | 50880
59201 | Brushy Creek 138 kV Switch | Brushy Creek 138 kV Switch |  | Brushy Creek Switch | Brushy Creek Switch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6148 | 2022-05-15 | 2022-05-01 | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3541, 3650, 3658, 13430 | Y |  |  | 0 | 59202 | 59201
64390 | Install two series reactors at Sandow Switch | Install two 2 ohm series reactors at Sandow Switch in series with the 345/138 kV Autotransformer #1 and Autotransformer #2 |  | Sandow | Sandow | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6116 | 2022-05-15 | 2022-12-01 | 138 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 13441, 13442, 13430, 13429, 13439, 13440 | Y |  |  | 0 | 64391 | 64390
64388 | Install second 110.4 Mvar 138 kV capacitor bank at Sandow | Install second 110.4 Mvar 138 kV capacitor bank at Sandow |  | Sandow | Sandow | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6189 | 2022-05-15 | 2022-05-01 | 138 | 0 | 0 | 0 | 0,110.4 | Milam | Milam | Tier 4 |  |  |  |  | 13430 | Y |  |  | 0 | 64389 | 64388
59546 | Lamesa 138/69 kV Autotransformer #1 | Replace Lamesa 138/69 kV Autotransformer #1 |  | Lamesa | Lamesa | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8561 | 2022-05-15 | 2022-05-20 | 138 | 0 | 0 | 86 |  | Dawson | Dawson | Tier 4 |  |  |  |  | 1163, 1355, 1164, 1356 | Y |  |  | 0 | 59548 | 59546
59418 | Brown 138 kV Capacitors | Add Brown 138 kV Capacitors |  | Brown | Brown | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8551 | 2022-05-15 | 2022-05-12 | 138 | 0 | 0 | 0 | 0,55.2 | Martin | Martin | Tier 4 |  |  |  |  | 23838 | Y |  |  | 0 | 59538 | 59418
59406 | Tex Harvey 138 kV Capacitors | Add Tex Harvey 138 kV Capacitors |  | Tex Harvey | Tex Harvey | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8567 | 2022-05-15 | 2022-06-16 | 138 | 0 | 0 | 0 | 0,55.2 | Midland | Midland | Tier 4 |  |  |  |  | 1221 | Y |  |  | 0 | 59408 | 59406
47424 | Clear Fork - Lockhart Transmission Line Overhaul | Increase the reliability and capability of circuit T601 on the Clear Fork - Lockhart 3.0-mile 69-kV transmission line.Upgrade all structures to 138-kV class and bundled Suwannee capable. Upgrade conductor to bundled 959 ACSS Suwannee. Add OPGW. |  | ClearFork | Lockhart | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-15 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7195, 7215 | Y |  |  | 0 | 47425 | 47424
5491 | Whitestone - Leander 138kV Transmission Line Upgrade | Upgrade the Whitestone - Blockhouse (T469) and the Blockhouse - Leander (T326) 138kV Line to 441MVA and upgrade the Blockhouse Substation to a ring bus. |  | Whitestone | Leander | In-Service |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2022-05-15 |  | 138 | 0 | 5.4 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7525, 7527, 7529 | Y | N |  | 0 | 51769 | 5491
57919 | Buzzard Draw 138 kV Terminal Additions | Buzzard Draw 138 kV Terminal Additions |  | Buzzard Draw | Buzzard Draw | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8555 | 2022-05-15 01:00 | 2022-06-01 | 138 | 0 | 0 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 1355, 23829, 23838 | Y |  |  | 0 | 57921 | 57919
52316 | Anna Tap - Princeton 138 kV Line | Upgrade the Anna Tap - Princeton 138 kV Line |  | Anna Tap | Princeton Switch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4275 | 2022-05-15 01:00 |  | 138 |  | 9.6 | 0 |  | Collin | Collin | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 2527, 2707, 2528, 2708 | Y |  |  | 0 | 52317 | 52316
45527 | Plano West - Richardson Collins 138 kV Line | Upgrade the Plano West - Richardson Collins 138 kV Line |  | Plano West Switch | Richardson Collins Switch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M364 | 2022-05-15 12:00 |  | 138 | 0 | 0 | 0 |  | Collin | Dallas | Tier 4 |  |  |  |  | 2685, 2628, 2673, 2683, 2684, 2686, 12684 | Y |  |  | 0 | 45528 | 45527
48782 | Progreso: Construct New Distribution Station | Progreso: Construct New Distribution Station | In Service | Rio Rico | Stewart Road | In-Service | 1031 - 1209 | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | 3770 DP20X0009 | 2022-05-30 | 2022-06-28 | 69 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8040, 8751, 8949 | Y | N |  | 0 | 48783 | 48782
64501 | Dunlavy to Heights Ckt.31C Upgrade | Upgrade Dunlavy to Heights Ckt.31C to increase thermal limits |  | Dunlavy | Heights | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47580, 47581, 47682, 47680 | Y | N |  | 0 | 64502 | 64501
63519 | Ashton Woods Capacitor Bank Addition | 138 kV, 31.2 MVAR Cap Bank addition at Ashton Woods substation |  | Ashton Woods 138 kV Substation |  | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 | 0,31.2 | Travis | Travis | Tier 4 |  |  |  |  | 9226 | Y |  |  | 0 | 63520 | 63519
59387 | DANBUR (DAB) 138kV Sub for Long Bow Solar (20INR0026) | Loop new CNP 138kV substation DANBUR (DAB) into Ckt.04C Angleton to Liverpool to create new Ckt.04 Angleton to DANBUR to Liverpool. Install one generator lead for new interconnection to Longbow Solar. |  | DANBUR | Angleton/Liverpool | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-05-30 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42875, 42110, 42870 | Y | N |  | 0 | 59388 | 59387
55961 | PSARCO to Highlands Ckt.08G Upgrades | Upgrade Ckt.08G PSARCO to Highlands with minimum 427MVA Continuous Rating |  | Highlands | PSARCO | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2021-01-21 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40811, 41300 | Y | N |  | 0 | 55962 | 55961
52565D | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Upgrade Ckt.90A HO Clarke to Kirby to Garrott to increase thermal limits |  | Kirby | HO Clarke/Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 9.51 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47151, 47175, 47322, 47660 | Y | N |  | Cost included in phase F | 59282 | 52565
64482 | Angleton Substation Expansion for Mark One | Expand Angleton substation for Mark One Gas Generator (22INR0369) |  | Angleton |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-05-10 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 112597, 42110 | Y | N |  | 0 | 64483 | 64482
59342 | Greens Bayou to LYCHEM Ckt.08 Upgrade | Rebuild and reconductor a de-energized section of Ckt.38Z. Loop the rebuilt section into 138kV Ckt.08F between Moore Road and Uvalde tap. The reconfiguration creates additional conductor impedance on the line to increase the fault duty margin for future generation. |  | Moore Road | Uvalde | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-04-04 | 138 | 3.25 | 3.25 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40559, 40281, 40555, 41023, 41651 | Y | N |  | 0 | 59343 | 59342
6971 | Magnolia Mercer Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Magnolia Mercer Substation. |  | Magnolia Mercer |  | In-Service | 1018915 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018915 | 2022-05-31 |  | 69 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7218, 7215, 7220 | Y | N |  |  | 14788 | 6971
59392 | Riverside (RVR) Sub for CHAMON Phase 2 (19INR0056) | Install new 138kV Riverside (RVR) CNP substation for generator interconnection to customer LIGNIN (LIG). Loop Ckt.94C into Riverside substation to create new Ckt.94 CHAMON to Riverside to Metals Switchrack |  | Riverside | CHAMON/Metals Switchrack | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-05-15 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40270, 40260, 41050 | Y | N |  | 0 | 59393 | 59392
59313 | Beasly (BEA) CNP-Owned Sub for Fort Bend Solar (18INR0053) | Loop new 138kV Beasly (BEA) substation for generator interconnection to Fort Bend Solar. Loop Ckt.60 into Beasly substation to create new Ckt.60 East Bernard to Beasly to Orchard |  | Beasly | East Bernard/Orchard | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-05-24 | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 42420, 44190, 44541 | Y | N |  | 0 | 59314 | 59313
59322 | Sealy to Peters Ckt.65A Upgrades | Upgrade Ckt.65A Sealy to Peters to increase thermal limits |  | Sealy | Peters | In-Service | 525535253359322 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-06-15 | 138 | 0 | 5.07 | 0 |  | Austin | Austin | Tier 3 | 20RPG020 | 2020-10-27 | 2020-11-18 |  | 44640, 46220 | Y | N |  | 0 | 59323 | 59322
57735A | Mykawa 138kV Switching Station | Install new CNP-owned 138kV switching station |  | Pearland |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-04-29 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42750 | Y | N |  | 0 | 57736 | 57735
4465 | Wirtz to FlatRock to Paleface Transmission Line Upgrade | Upgrade the 17.34 mile Wirtz (7104) - Flat Rock (7111) - Paleface (7477) 138-kV transmission line to bundled 795 ACSR Drake, 441 MVA and add Breakers at Flatrock. |  | Wirtz | Paleface | In-Service |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2022-05-31 |  | 138 | 0 | 17.34 | 0 |  | Burnet | Travis | Tier 4 |  |  |  |  | 7104, 7111, 7477 | Y | N |  |  | 12026 | 4465
59398A | San Bernard (SAN) Sub for Brazoria County Solar (20INR0098) | New 138kV San Bernard (SAN) substation for generator interconnection to Brazoria County Solar. Loop Ckt.04 into new substation to create new Ckt.60 West Columbia to San Bernard to Pledger tap |  | San Bernard | West Columbia/Pledger | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-05-22 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43110, 43010, 43019, 43120, 43190, 43380, 112215 | Y | N |  | 0 | 59767 | 59398
4418A | HO Clarke Upgrades | Join existing HO Clarke 69kV buses. Upgrade fault duty to minimum 60KA. |  | HO Clarke |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-05-31 | 69 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47165, 44400, 47160, 47680 | Y | N |  | 0 | 63539 | 4418
57735B | Mykawa 138kV Switching Station | Loop Ckt.06K into new CNP-owned 138kV switching station to create new Ckt.06 Gulfgate to Mykawa to Pearland |  | Mykawa | Gulfgate/Pearland | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-04-29 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42742, 42750, 43051 | Y | N |  | Cost include in main project | 57737 | 57735
4418B | HO Clarke Upgrades | Retire existing HO Clarke auto A3. |  | HO Clarke |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 | 2022-05-31 | 69 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 49009, 47175, 47165 | Y | N |  | Cost included in main project | 63540 | 4418
50950 | Whitepoint Area Improvements | Whitepoint Area Improvements |  | Whitepoint | Hecker | In-Service | 1061 - 1234 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 3792 | 2022-06-01 | 2022-06-01 | 138 | 0 | 12 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8418, 8565, 8961 | Y | N |  | 0 | 65551 | 50950
63665 | Interconnects Lonestar Bitcoin | NOMCR ID # 71885-1 | Customer substation (bus # 38356) | TNMP Lonestar (bus # 38190) | Customer substation (bus # 38191) | In-Service |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-06-01 |  | 138 | 0.233 | 0 | 0 | 0,160 | Ward | Ward | Tier 4 |  |  |  |  | 38191, 38190 | Y |  |  | 0 | 63666 | 63665
63663 | Interconnects Cottonwood Data Center | NOMCR ID # 72100-1 | Delayed energizing Capacitor Banks, estimated ISD October 2022. | TNMP Leon Creek (bus # 38355) | Customer substation (bus # 38356) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-06-01 |  | 138 | 1.5 | 0 | 0 | 0,240 | Reeves | Reeves | Tier 4 |  |  |  |  | 38097, 11078, 38099 | Y |  |  | 0 | 63664 | 63663
69465 | Skid (Bull Moose):Construct New Distribution Station | Skid (Bull Moose):Construct New Distribution Station | In Service | Lon Hill | Haisley | In-Service |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | DP21X0016 | 2022-06-01 | 2022-06-24 | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8046, 8027, 8920 | Y |  |  | 0 | 69466 | 69465
3948 | Steamboat to Tuscola: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola | IN-SERVICE | Steamboat | Tuscola | In-Service | 685 - 0855 | ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | 1851 | 2022-06-14 | 2022-06-14 | 69 | 0 | 9.856 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6328, 6331, 60332 | Y | N |  |  | 11441 | 3948
62112 | Establish Battleground138 kV Substation | Establish Battleground (Formerly Coupland) 138 kV Substation |  | Coupland | Coupland | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6139 | 2022-06-15 | 2022-06-01 | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3690, 3541, 3658 | Y |  |  | 0 | 62632 | 62112
61595 | Add Pinkney (Blanket South) 138 kV Substation | Add Pinkney (Blanket South) 138 kV Substation |  | Comanche | Brownwood | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6145 | 2022-06-15 | 2022-06-01 | 138 | 0 | 0 | 0 |  | Brown | Brown | Tier 4 |  |  |  |  | 1666, 1667, 1441, 1661, 1662 | Y |  |  | 0 | 61596 | 61595
47448 | Motorman Substation Addition | Construct a new 138-kV Motorman substation. Motorman Substation is located in west Texas approximately 0.25 miles west of the LCRA TSC Crane East Substation. Construct a 3-breaker ring bus cut in to the existing Crane East to LCRA Crane transmission line. |  |  |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-06-22 | 2022-06-30 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7869, 11238, 11239, 71214, 76615 | Y |  |  | 0 | 60784 | 47448
52565G | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Reposition existing Ckt.05B HO Clarke to Intermediate tap to the HOC ring bus. |  | HO Clarke | Intermediate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-06-30 01:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44361, 47150, 47170 | Y | N |  | Cost included in phase F | 63578 | 52565
44513 | Concho to Live Oak: Rebuild 69 kV line | Rebuild remaining portions of the Concho to Live Oak 69 kV line | IN-SERVICE | Concho | Live Oak | In-Service | 941 - 1119 | AEP TNC | Jim Nivens mlforcum@aep.com 918-599-2674 | 2755 | 2022-06-30 01:00 | 2022-06-30 | 69 | 0 | 3.3 | 0 |  | Tom Green | Schleicher | Tier 4 |  |  |  |  | 6450, 6494, 6495, 6496, 6497, 6498, 6527 | Y | N |  | 0 | 65522 | 44513
63667 | GSEC_539_Modify_Buses_Loads.prj |  |  |  |  | Planned |  | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2022-07-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6413, 9487, 60008 | Y |  |  | 0 | 63668 | 63667
57586 | Cedar Bayou to Center Ckt.97D Upgrade | Upgrade Cedar Bayou to Center Ckt.97D. |  | Cedar Bayou | CENTER | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-07-26 | 2022-07-26 | 345 | 0 | 0 | 0 |  | Chambers | Harris | Tier 4 |  |  |  |  | 40000, 40240 | Y | N |  | 0 | 57587 | 57586
47436 | ROBERT BROWN JR ¿ SAN MARCOS Transmission Line OverHaul | Increase the reliability and capability of circuit T220 on the Robert Brown Jr ¿ San Marcos 4.9-mile 69-kV transmission line. Upgrade all structures to 138-kV class and bundled Suwannee capable. Upgrade conductor to bundled 959 ACSS Suwannee. Add OPGW. |  | Robert Brown JR | San Marcos | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-07-29 | 2022-07-30 | 138 | 0 | 0 | 0 |  | Hays | Caldwell | Tier 4 |  |  |  |  | 7191, 7194, 7196 | Y | N |  | 0 | 47437 | 47436
57543 | Angleton to West Columbia Ckt 04E Line Upgrades | Reconductor Ckt 04E Angleton to West Columbia to address line clearance concerns. |  | Angleton | West Columbia | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-07-31 | 2022-07-14 | 138 | 0 | 16.11 | 0 |  | Brazoria | Brazoria | Tier 4 | 21RPG005 | 2021-03-10 | 2021-04-02 |  | 42110, 43381, 43380 | Y | N |  | 0 | 61529 | 57543
59389 | Johnson Draw POD - Flat Iron Substation 138 kV line | Johnson Draw POD - Flat Iron Substation 138 kV line |  | Johnson Draw POD | Flat Iron Substation | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8580 | 2022-08-02 | 2022-08-02 | 138 | 3 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11217, 11344 | Y |  |  | 0 | 59391 | 59389
65646 | Interconnects Coyanosa Data Center |  |  | TNMP Coyanosa (bus # 38380) | Customer substation (bus # 38382) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-08-03 |  | 138 | 0.06 | 0 | 0 | 0,160 | Reeves | Reeves | Tier 4 |  |  |  |  | 38382, 38380 | Y |  |  | 0 | 65647 | 65646
6571 | Lake Pauline to Vernon 69 kV line: Rebuild taps | Lake Pauline to Vernon 69 kV line: Rebuild taps | IN-SERVICE | Lake Pauline | Vernon Main | In-Service | 891 - 1069 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2815 | 2022-08-03 | 2022-08-03 | 69 | 0 | 2.5 | 0 |  | Hardeman | Wilbarger | Tier 4 |  |  |  |  | 6048, 6056, 6057, 6058 | Y | N |  | 0 | 65511 | 6571
59839 | Duck Cove Tap #1 - Wills Point 69 kV Double Circuit Line | Rebuild Duck Cove Tap - Wills Point 69 kV Line |  | Edgewood | Iron Bridge | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6137 | 2022-08-15 | 2022-08-01 | 69 | 0 | 3.1 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 3187, 3188, 2722, 3189 | Y |  |  | 0 | 59840 | 59839
62110 | WHALEY 345kV Sub for Cutlass Solar (19INR0131) | New 345kV CNP WHALEY (WLY) substation for generator interconnection to Cutlass Solar. Loop Ckt.72x into substation to create new Ckt.72x Cedar Creek to WHALEY to WA Parish |  | WHALEY | Cedar Creek/ WA Parish | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-08-15 | 2022-05-20 | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44070, 44005, 44090 | Y | N |  | 0 | 62111 | 62110
10TPIT0025 | Bluff Spring 138kV substation | Establish 138kV Bluff Spring substation with (2) 30MVA transformers and will cut into existing Ckt 988 (Lytton Springs to Slaughter Lane). New circuits will be CKT988: from LY-BF and CKT1031 from BF-SL | [5 empty] | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P151 PLAN_117_P152 | 2022-08-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 9262, 9075, 9267 | Y |  |  | 0 | 61089 | 1030
70439 | Move_DuckCove_Load_TPIT |  |  |  |  | Planned |  | RYBRN |  |  | 2022-09-01 |  | 138 | 0 | 0 | 0 |  | Kaufman | Kaufman | Tier 4 |  |  |  |  | 6920, 6921, 2465 | Y |  |  | 0 | 70608 | 70439
58542A | CATTAIL_SUBSTATION | 1) Construct a new Cattail 138-KV substation near the existing Texas City Main 69-kV substation 2) Install a new 138-69-kV transformer at Texas City Main with normal and emergency ratings of at least 200 MVA. 3) Cat Tail to Greenbelt 138kv line 4) Cat Tail to TxCity Main 138kv line. |  | Cat Tail ( 38580 ), Greenbelt ( 38575 ) | Texas City Main ( 39140, 39141 ) | In-Service |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-09-15 |  | 138 | 2.6 | 0 | 200 |  | Galveston | Galveston | Tier 2 |  | 2020-04-16 | 2020-09-16 |  | 38580, 39141, 38575, 39140 | Y |  |  | 0 | 71933 | 58542
67524 | Oncor_Saltillo_Switch_Stampede_Solar | Add new Saltillo Switch- POI for Stampede Solar. |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4702 | 2022-09-15 |  | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 11700, 1685, 11688 | Y | N |  | 0 | 67525 | 67524
63427 | Adds TNMP Girvin Switching Station |  |  | AEP Rio Pecos (bus # 6601),TNMP Soaptree (bus # 38450), and TNMP Whitebaker (bus # 38430) | Girvin Switching Station (bus # 38445) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-09-21 |  | 138 | 1 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38445, 6601, 38430, 38450 | Y |  |  | 0 | 63428 | 63427
5940A | Mountain Home Substation and Transmission Line Addition | Construct new Mountain Home substation, add one(1) 138/69-kV autotransformer at Headwaters substation (located adjacent to Harper substation), construct a 138-kV transmission line from Hunt substation to Mountain Home substation to Headwaters substation. | For total project cost please see phase 5940B | Hunt | Headwaters | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017394 | 2022-09-22 |  | 138 | 19 | 0 | 45 |  | Kerr | Gillespie | Tier 1 | 16RPG015 | 2016-11-18 |  |  | 7410, 7750, 7751, 74100, 74101, 7144 | Y | N |  | 0 | 61873 | 5940
64503 | Dunlavy to Hyde Park Ckt.32A Reconductor | Reconductor Dunlavy to Hyde Park Ckt.32A ahead of future 138kV conversions |  | Dunlavy | Hyde Park | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-09-23 | 2022-09-23 | 69 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47580, 47690 | Y | N |  | 0 | 64504 | 64503
57735C | Mykawa 138kV Switching Station | Loop Ckt.91A into new CNP-owned 138kV switching station to create new Ckt.91 Gulfgate to Mykawa to Pearland |  | Mykawa | Gulfgate/Pearland | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-09-29 | 2022-09-29 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42741, 42750, 43052 | Y | N |  | Cost include in main project | 57738 | 57735
56003H | Mont Belvieu Reliability Project | Upgrade Ckt.86A Cedar Bayou Plant to Chevron with minimum 669MVA Emergency Rating |  | Cedar Bayou Plant | Chevron | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-09-30 | 2022-09-13 | 138 | 0 | 0 | 0 |  | Chambers | Harris | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40015, 40300 | Y | N |  |  | 56082 | 56003
4576 | BRYN_4576_Smetana_to_Steele_Store | Construct New 138kV line (Bundled 1033 ACSR - Curlew) to new Steele Store substation as part of the reliability project to loop in Steele Store |  | 32853 | 32852 | Planned |  | BRYN |  |  | 2022-10-01 |  | 138 | 4.5 | 0 | 0 |  | Brazos | Burleson | Tier 4 |  | 2015-10-09 | 2015-11-06 |  | 32852, 32853 | Y |  |  | 0 | 64545 | 4576
64554 |  | REC's Walton to North Athens 138 kV line reconductoring. |  | 6842 | 6867 | Planned |  | RYBRN |  |  | 2022-10-01 |  | 138 | 0 | 0 | 0 |  | Hopkins | Henderson | Tier 4 |  |  |  |  | 6842, 6867 | Y |  |  | 0 | 64555 | 64554
4505 | BRYN_4505_Smetana_Sub | Construction of a new Smetana Substation at 138kV |  |  |  | Planned |  | BRYN |  |  | 2022-10-01 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32850, 32853, 32868 | Y |  |  | 0 | 63548 | 4505
64480 |  | Converting straight bus to a ring bus configuration. |  | 6842 | 6842 | Planned |  | RYBRN |  |  | 2022-10-01 |  | 138 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 | [5 empty] | Y |  |  | 0 | 64481 | 64480
68671 | Adds Foxtail Switching Station |  |  | Flat Top (38069) Pig Creek (60393) Tarbush (38295) | Foxtail (38070) | Under Construction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-10-01 |  | 138 | 1.98 | 0 | 0 | 0,160 | Reeves | Pecos | Tier 4 |  |  |  |  | 38294, 38069, 38295, 38296, 60393 | Y |  |  | 0 | 68672 | 68671
48288C | BOGGY (BOG) 138kV Substation (SHELL Substation Replacement) | Install new customer-owned BOGGY 138kV substation. Loop from Ckt.88 to create new Ckt.88 PAIR to BOGGY to ESBELT |  | BOGGY | PAIR/ESBELT | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-10-18 | 2022-10-18 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40530, 41210, 41350, 41370, 41460 | Y | N |  | Cost Included in 48288A | 57334 | 48288
62843 | El Sauz Ranch Wind Interconnection | Connect the El Sauz Ranch Wind to the Cebolla Station | IN-SERVICE | Cebolla |  | In-Service |  | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | TP2021023 | 2022-10-31 | 2022-10-28 | 345 | 0.05 | 0 | 0 |  | Willacy |  | Tier 4 |  |  |  |  | 8663, 8601 | Y | Y |  | 0 | 62844 | 62843
66043A | Ckt29 THW-WhiteOak Reconductor and 138kV Conversion | Rebuild-Reconductor 69kV Ckt.29 TH Wharton to Little York to White Oak ahead of 138kV conversion. |  | TH Wharton | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-10-31 |  | 69 | 0 | 12.2 | 0 |  | Harris | Harris | Tier 4 | 21RPG016 | 2021-09-08 | 2021-09-30 | 2021-09-30 | 45530, 45990, 46620 | Y | N |  | Cost included in final phase of project | 66044 | 66043
49570 | Goodlett: Build 69 kV station | Build new Goodlett 69 kV station on the Childress to Quanah 69 kV line | IN-SERVICE | Goodlett |  | In-Service | 1021 - 1199 | AEP TNC | Alison Scribailo mlforcum@aep.com 918-599-2674 | 2783 | 2022-10-31 | 2022-10-31 | 69 | 0 | 0 | 0 |  | Hardeman |  | Tier 4 | 19RPG020 |  |  |  | 60446, 6052, 6053 | Y | N |  | 0 | 49571 | 49570
59315 | BLUE (BLU) CNP-Owned Sub for Red-Tailed Hawk Solar (21INR0389) | New 345kV BLUE (BLU) substation for generator interconnection to Red-Tailed Hawk Solar. Loop Ckt.72 into substation to create new Ckt.72 Hillje to BLUE to Bailey |  | BLUE | Hillje/Bailey | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-10-31 12:00 | 2022-10-06 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44060, 5915, 44040, 44000, 44200 | Y | N |  | 0 | 59316 | 59315
50892 | Seawall to Port Aransas: Replace 69 kV undersea cable | Replace Seawall to Port Aransas 69 kV undersea cable |  | Seawall | Port Aransas | In-Service | 1058 - 1231 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3789 TP2019166 | 2022-11-01 | 2021-09-15 | 69 | 0 | 0.5 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8435, 8442 | Y | N |  | 0 | 65549 | 50892
65642 | Interconnects Airport Bitcoin |  |  | TNMP Airport (bus # 38340) | Customer substation (bus # 38341) | Under Construction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-11-01 |  | 138 | 0 | 0 | 0 | 0,160 | Pecos | Pecos | Tier 4 |  |  |  |  | 38341, 38340 | Y |  |  | 0 | 65643 | 65642
67132 | Update RoseHill to Talty | Update Rose Hill to Talty. Patton should be radial off Rose Hill. |  |  |  | Planned |  | RYBRN |  |  | 2022-11-01 |  | 138 | 0 | 0 | 0 |  | Kaufman | Kaufman | Tier 4 |  |  |  |  | 6801, 6894, 6902 | Y |  |  | 0 | 67133 | 67132
58065 | Alvin Approach Upgrades Ckt.53 | Upgrade portions of Ckt.53B and Ckt.53C ahead of future 138kV conversions. |  | Alvin | EXTER/Manvel | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-11-02 | 2022-11-02 | 69 | 0 | 9.51 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42080, 43035, 44400, 44440, 42600, 44000 | Y | N |  | 0 | 58066 | 58065
70584 | RCEC_CottonWoodCreek_TPIT_Sub | Build a new substation that will connect with two paths to GP&L¿S Elm Grove Station in Dallas County. |  |  |  | Planned |  | RYBRN |  |  | 2022-11-02 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 6898, 855 | Y |  |  | 0 | 70587 | 70584
65659 | Adds Fishhook Switch |  |  | Wink (bus # 37900) | Fishhook Switch (bus # 37180) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-11-03 |  | 138 | 0 | 26.132 | 0 |  | Winkler | Ward | Tier 4 |  |  |  |  | 38180, 38196, 37900, 38135, 38140, 38152, 38165, 38195 | Y |  |  | 0 | 65660 | 65659
44804 | Tinsley: Build 138 kV station | Construct new 138 kV box bay on the Carver to Maxwell 138 kV line | IN-SERVICE | Tinsley |  | In-Service | 957 - 1135 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 2761 | 2022-11-08 01:00 | 2022-11-08 | 138 | 0 | 0 | 0 |  | Sutton |  | Tier 4 |  |  |  |  | 60440, 8259, 60412 | Y | N |  | 0 | 44805 | 44804
68057 | Crossroads Sw (Estonian Solar) |  |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3009 | 2022-11-15 |  | 138 | 0 | 0 | 0 |  | Delta | Delta | Tier 4 |  |  |  |  | 1844, 1816, 17011 | Y |  |  | 0 | 68058 | 68057
68677 |  | this is for Mercury Solar (21INR0257) and Mercury Solar II (23INR0153) project |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2022-11-20 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68092, 68090, 152433, 163273 | Y |  |  | 0 | 68678 | 68677
57584 | Cedar Bayou Auto A1 and A3 Position Swaps at 138kV | Swap Cedar Bayou Auto A1 and A3 Positions on the 138kV side to address fault concerns |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-11-30 | 2022-10-25 | 345 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  |  | 40000, 40010, 40015, 49005, 49008 | Y | N |  | 0 | 57585 | 57584
59346 | Hillcroft to Dunvale Ckt.24B Upgrades | Upgrade Ckt.24B Hillcroft tap to Dunvale tap with minimum 340MVA Emergency Rating |  | Hillcroft | Dunvale | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-11-30 |  | 138 | 0 | 1.04 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47072, 47191 | Y | N |  | 0 | 59347 | 59346
60491 | Rebuild Alamo Street-Airport with 1926 ACSS |  |  | Alamo Street (bus # 38330) | Airport (bus # 38340) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-11-30 |  | 138 | 0 | 3.01 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38340 | Y |  |  | 0 | 60492 | 60491
48109 | Dolan Creek: Construct 138 kV Box Bay | Dolan Creek: Construct 138 kV Box Bay |  | Dolan Creek |  | In-Service | 930 - 1108 | AEP TCC/PEC | Alison Scribailo bcogan@aep.com 918-599-2857 | 3706 | 2022-11-30 | 2022-11-14 | 138 | 0 | 0 | 0 |  | Val Verde | Sutton | Tier 4 |  |  |  |  | 8991, 88991, 8259, 8261, 72194 | Y | Y |  | 0 | 65534 | 48109
48288A | BOGGY (BOG) 138kV Substation (SHELL Substation Replacement) | Remove existing customer-owned SHELL (_SL) 138kV Substation |  | SHELL |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-11-30 | 2022-11-04 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41450, 40070, 41460 | Y | N |  | 0 | 57332 | 48288
66053 | 138 kV GULFTIE Substation to connect TexGulf generator |  |  | Tex Gulf | South Lane City/San Bernard | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-11-30 | 2022-12-07 | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 43340, 43341, 43010, 43120, 110262 | Y | N |  | 0 | 66054 | 66053
6934A | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0873 | 2022-12-01 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  |  | 5133 | Y |  |  |  | 14753 | 6934
50952 | Whitepoint: 138 kV Line Upgrades | 138 kV Line Upgrades at Whitepoint | IN-SERVICE | Whitepoint |  | In-Service | 1086 - 1259 | AEP TCC | Douglas James bcogan@aep.com 918-599-2857 | 3806 TP2020034 | 2022-12-01 | 2022-12-14 | 138 | 0 | 0 | 0 | -18.16,0 | San Patricio |  | Tier 4 |  |  |  |  | 8961, 80128, 80129 | Y | N |  | 0 | 65552 | 50952
70591 | RCEC_Walton_NAthens_ReConfiguration | Build a new Walton switch yard. |  |  |  | Planned |  | RYBRN |  |  | 2022-12-01 |  | 138 | 0 | 0 | 0 |  | Hopkins | Henderson | Tier 4 |  |  |  |  | 6867, 6899, 6842, 6843, 6951 | Y |  |  | 0 | 70593 | 70591
69906 | Install 138kV Capacitor Bank at Whitebaker |  |  | TNMP Whitebaker (bus # 38430) |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0 | 0 | 0,160 | Pecos | Pecos | Tier 4 |  |  |  |  | 38430 | Y |  |  | 0 | 69907 | 69906
60524 | Rebuild Angleton-Retrieve with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39560, 43170 | Y |  |  | 0 | 60525 | 60524
66111 | Upgrade Airport bus |  |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38340 | Y |  |  | 0 | 66112 | 66111
63904 | Pendulo: Build New 345 kV Station | Interconnect Inertia (Wind and BESS) to the Clear Crossing to Smoky Hill 345 kV Line | IN-SERVICE | Pendulo |  | In-Service | 1137 - 1315 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 1882 | 2022-12-12 | 2022-12-12 | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60507, 60509, 6104, 60514 | Y | N |  | 0 | 63905 | 63904
63898 | Palouse: Build New 138 kV Station | Interconnect Appaloosa Run Wind on the North McCamey to Santa Rita 138 kV Line | IN-SERVICE | Palouse |  | In-Service | 1134 - 1312 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 1879 | 2022-12-12 | 2022-12-12 | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | 60728, 60729, 60723, 60799, 141052, 141151, 141154, 141202, 141204, 141205, 141207, 141861, 141862, 141863, 141866, 161701, 161702, 161706, 161707, 170161, 170163, 182001, 182054 | Y | N |  | 0 | 63899 | 63898
63410 | Cyclone Switch (Bright Arrow Solar) | Establish station for Bright Arrow Solar on Thorn Tree Switch to Farmersville 345 kV Line. |  | Cyclone | Cyclone | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4701 | 2022-12-14 |  | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 11689, 1685, 11688, 120445 | Y | N |  | 0 | 63412 | 63410
62638 | Rebuild Trinidad (Creslenn) 69 kV Switch | Rebuild Trinidad (Creslenn) 69 kV Switch |  | Creslenn | Creslenn | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6142 | 2022-12-15 | 2022-12-22 | 69 | 0 | 0 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  |  | 3128, 3200, 3126, 3269, 3479, 3127, 24039 | Y |  |  | 0 | 68695 | 62638
59765 | Loy Lake 138 kV Capacitors | Install new 138 kV Capacitors |  | Loy Lake |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R989 | 2022-12-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Grayson |  | Tier 4 |  |  |  |  | 1834 | Y |  |  | 0 | 64020 | 59765
60060 | Add Marlin South 69 kV Cap Bank | Add Marlin South 69 kV Cap Bank |  | Marlin South | Marlin South | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R468 | 2022-12-15 | 2022-12-27 | 69 | 0 | 0 | 0 | 0,27.6 | Falls | Falls | Tier 4 |  |  |  |  | 3641 | Y |  |  | 0 | 60061 | 60060
61519 | Salt Flat Road - Skywest 138 kV Line Rebuild | Salt Flat Road - Skywest 138 kV Line Rebuild |  | Salt Flat Road | Skywest | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8569 | 2022-12-15 | 2022-07-20 | 138 | 0 | 1 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23859, 71210 | Y |  |  | 0 | 61521 | 61519
62633 | Install 2nd distribution transformer at Rockdale Substation | Install 2nd distribution transformer at Rockdale Substation |  | Rockdale | Rockdale | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6140 | 2022-12-15 | 2022-12-22 | 138 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3686, 3678, 3684 | Y |  |  | 0 | 62634 | 62633
66116 | Add Buckeye Switchyard (22INR0359 Dileo POI) |  |  | Lake Whitney (bus # 37420) | Olsen (bus # 37470) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 37450, 37420, 37470 | Y |  |  | 0 | 66117 | 66116
5492 | Venus - Webb/Cedar Hill Sw. Sta. 345 kV DCKT Line | Upgrade existing Venus - Webb/Cedar Hill Sw. Sta. 345 kV Double Ckt Line |  | Ellis | Tarrant | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4230 | 2022-12-15 |  | 345 | 0 | 27 | 0 |  | Ellis | Tarrant | Tier 3 | 21RPG004 | 2021-02-22 | 2021-03-17 |  | 1904, 1906, 2420, 11901 | Y | N |  |  | 13230 | 5492
59402 | Add Midland East Switch 345138 kV Autotransformer #2 | Add a new 345/138 kV autotransformer to existing switch |  | Midland East | Midland East | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8258 | 2022-12-15 | 2022-12-15 | 345 | 0 | 0 | 600 |  | Midland | Midland | Tier 3 | 21RPG003 | 2021-02-16 | 2021-03-12 |  | 1014, 11298, 1021, 1023 | Y |  |  | 0 | 59404 | 59402
62641 | Establish Sabana138 kV Substation | Establish Sabana (Formerly known Proctor) 138 kV Substation |  | Proctor | Proctor | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6144 | 2022-12-15 | 2022-11-22 | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 1665, 1684, 1636, 1637, 1649 | Y |  |  | 0 | 62642 | 62641
62659 | Upgrade Temple - Holland 69 kV Line | Upgrade Temple - Holland 69 kV Line |  | Temple | Holland | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6151 | 2022-12-15 | 2022-12-22 | 69 | 0 | 16.6 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3644, 3645, 3646, 13646 | Y |  |  | 0 | 62660 | 62659
7115 | Quarry Field - Kyle Ranch 138 kV Line | Quarry Field - Kyle Ranch 138 kV Line |  | Quarry Field | Kyle Ranch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8384 | 2022-12-15 | 2022-12-15 | 138 | 12 | 0 | 0 |  | Loving | Loving | Tier 4 |  |  |  |  | 11089, 11189 | Y |  |  |  | 14951 | 7115
62143 | Rebuild Taylor 138 kV Switch | Rebuild Taylor 138 kV Switch and relocate 138/69 kV auto from Elgin to Taylor |  | Taylor | Taylor | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6143 | 2022-12-15 | 2022-12-22 | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3651, 3652, 3649, 3650, 3658 | Y |  |  | 0 | 62640 | 62143
62440 | Ferris - Waxahachie OCF 69 kV Line | Rebuild existing 69 kV Line |  | Ferris Switch | Waxahachie OCF | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4323 | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 201, 2342, 2343 | Y |  |  | 0 | 62441 | 62440
57934 | Midland East - Spraberry 138 kV Line Rebuild | Add Midland East - Spraberry 138 kV Line Rebuild |  | Midland East | Spraberry | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8147 | 2022-12-15 | 2022-06-01 | 138 | 0 | 13.5 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 | 2021-03-12 |  | 11294, 11295, 11296, 1023, 1132, 11123, 11134, 1329 | Y |  |  | 0 | 60082 | 57934
62438 | Waxahachie - Bardwell Lake - Italy 69 kV Line | Rebuild existing 69 kV Line |  | Bardwell Lake Switch | Italy | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4320 | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2295, 2336, 2337, 3523, 2335, 2338 | Y |  |  | 0 | 62439 | 62438
71000 | TCC& TNC Cap Bank Rehab | TCC& TNC Cap Bank Rehab |  |  |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TA2022031 | 2022-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6216, 6338, 6468, 6570, 6615, 8169, 8275, 8295, 8314, 8348, 8354, 8427, 8980 | Y | N |  | 0 | 71001 | 71000
62116 | Upgrade Brushy Creek - Taylor 138 kV Line | Upgrade Brushy Creek - Taylor 138 kV Line |  | Brushy Creek | Taylor | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6153 | 2022-12-15 | 2022-12-22 | 138 | 0 | 11.4 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3541, 3690, 3658 | Y |  |  | 0 | 62117 | 62116
7020 | Cedar Hill - Camp Wisdom 138 kV Line | Upgrade existing Cedar Hill - Camp Wisdom 138 kV Line |  | Cedar Hill | Camp Wisdom | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4250 | 2022-12-15 |  | 138 | 0 | 9.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2421, 2990, 2993, 2994, 2992, 2999 | Y | N |  |  | 14842 | 7020
57925 | Midland County Northwest to Texaco Mabee Tap 138 kV Double-Circuit Line Section | Add Midland County NW - Texaco Mabee Tap 138 kV Double-Circuit Line Section Rebuild |  | Midland County Northwest | Texaco Mabee Tap | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8558 | 2022-12-15 01:00 | 2022-12-21 | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 | 2021-03-12 |  | 11299, 11300, 11301, 1178, 1179, 1182, 1183 | Y |  |  | 0 | 60059 | 57925
69477 | Quintana: Construct New Distribution Station | Construct New Distribution Station on the Melon Creek to Refugio 138 kV Line | IN-SERVICE | Melon Creek | Refugio | In-Service |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | DP20X0015 | 2022-12-20 | 2022-12-21 | 138 | 0 | 0 | 0 |  | Aransas | Refugio | Tier 4 |  |  |  |  | 8813, 8412, 80065 | Y |  |  | 0 | 69478 | 69477
52638 | Solanum: Build 138 kV station | Construct new 138 kV box bay on the Abilene South to Putnam 138 kV line | IN-SERVICE | Solanum |  | In-Service | 1074 - 1247 | AEP TNC | Charles Gibson mlforcum@aep.com 918-599-2674 | 2835 | 2022-12-20 | 2022-12-20 | 138 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  |  | 61015, 6309, 60365 | Y | N |  | 0 | 65565 | 52638
59324 | Creosote: Build 138 kV Station | Build new 138 kV Station on the Pig Creek to Lotebush 138 kV line | IN-SERVICE | Creosote |  | In-Service | 1124 - 1302 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1869 | 2022-12-20 | 2022-12-20 | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 6657, 60377, 6673, 38376, 60392 | Y | N |  | 0 | 65589 | 59324
67618 | LCRATSC_KerrvilleStadium_Substation_Upgrade | LCRA TSC will install a circuit breaker on the tie line between 138-kV bus #1 and bus #2 at Kerrville Stadium as well as a 138-kV circuit breaker on the power transformer connection bay (Bay #3) at Kerrville Stadium substation. In addition, LCRA TSC will replace obsolete equipment: oil circuit breaker CB5270, PT4, and the control house battery and charger |  | Chief Brady | Chief Brady | In-Service |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG +151-257-84514 |  | 2022-12-21 01:00 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y | N |  | 0 | 67619 | 67618
54092 | Sheriff's Posse Circuit Breaker Addition | Increase transmission service reliability to the Sheriff¿s Posse Substation. Increase the reliability of substation equipment at the Sheriff¿s Posse Substation. Note: NBU is adding a third power transformer at Sheriff¿s Posse and reconfiguring the substation to a ring bus arrangement. LCRA TSC will complete this project to support the NBU substation reconfiguration. LCRA TSC will ultimately own a section of the ring bus at Sheriff¿s Posse where an existing LCRA TSC transmission line terminates. |  | Sheriff's Posse | Sheriff's Posse | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-12-30 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7460 | Y | N |  | 0 | 54093 | 54092
57521A | Stone Lake New Sub Ckt66 | Install Stone Lake Distribution Substation AP2022 to create new Ckt..66 Hockley to Stone Lake to Tomball. |  | Stone Lake | Hockley/Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45886, 46511 | Y | N |  | 0 | 57530 | 57521
6988 | Sheriff's Posse Switch & Breaker Upgrades | At Sheriff's Posse - Upgrade/Replace underrated switches 2967, 2969, 2971 to 3,000 Amp Switches. Replace and increase fault interrupting rating of breaker 2970 to 63kA, and its continuous rating to 3,000 Amp. Replace CS 2965 and CS 2975 to 40kA units. Add a Ring Bus at Sheriff's Posse as well, adding one new NBU owned 3,000 Amp breaker and isolation switches as well. | The scope of work related to the project is being limited to just the substation work at Sheriff's Posse. NBU is delaying the upgrade of T-340 to 959 ACSS due to budget limitations. That line upgrade is tentatively proposed to be completed by 7/31/2026. | Sheriff's Posse | Marion | In-Service |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2022-12-30 | 2022-06-01 | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 |  |  |  |  | 7460 | Y | N |  |  | 14806 | 6988
5430G | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2022-12-30 | 2018-12-11 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 905, 915 | Y | N | N/A | 0 | 55201 | 5430
52688 | Angleton Substation Expansion | Expand Angleton substation for the Myrtle Solar generator interconnection (19INR0041). |  | Angleton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 111533 | Y | N |  | 0 | 55842 | 52688
66048 |  |  |  | 6821, 6904, |  | Planned |  | RYBRN |  |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6904 | Y |  |  | 0 | 66052 | 66048
52218 | Alvin 69kV Substation Bypass | Bypass Alvin 69kV Substation while substation is being rebuilt. Transfer Alvin load to neighboring substations |  | Webster | Manvel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 69 | 0 | 0 | 0 |  | Galveston | Brazoria | Tier 4 |  |  |  |  | 42080, 42600, 43510, 44440 | Y | N |  | 0 | 52225 | 52218
5559 | Add new 138kV Bonnie Brae Substation and retire the 69kV sta |  |  | Bonnie Brae |  | Planned | N/A | DENTON | Charles Sears cxsears@cityofdenton.com 940-349-7111 |  | 2022-12-31 | 2018-12-11 | 138 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  |  | 905, 931 | Y | N | N/A |  | 13291 | 5559
5430J | Conversion to 138kV | Line already insulated for 138kV. Line will be terminated at the new 138kV Hickory substation |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2022-12-31 | 2018-12-11 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 905, 910 | Y | N | N/A | 0 | 55204 | 5430
64486 | Angleton to WINMIL Ckt.26B Upgrades | Upgrade Ckt 26B Angleton to WINMIL to increase thermal limits |  | Angleton | WINMIL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 44531 | Y | N |  | 0 | 64487 | 64486
71008 | Angleton Sub - Myrtle Battery Storage (21INR0442) | Install Myrtle Battery Storage...Connect at the same generator lead as Myrtle Solar I & II (21INR0442) |  | Angleton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | 0 | 71009 | 71008
57521B | Stone Lake New Sub Ckt66 | Upgrade Ckt.66 Hockley to Stone Lake BP2023 as a transmission project. |  | Stone Lake | Hockley/Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 15.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45880, 45886 | Y | N |  | Cost included in main entry | 57531 | 57521
56003A | Mont Belvieu Reliability Project | Expand Jordan and Mont Belvieu with new line positions |  | Jordan | Winfre | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 | 2022-10-07 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40500, 40764, 40857, 40740, 40855 | Y | N |  | 0 | 56075 | 56003
5430I | Conversion to 138kV | Retire the existing 69kV North Lakes substation together with the transformer relocated from Denton North |  | North Lakes |  | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2022-12-31 | 2018-12-11 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 915, 928 | Y | N | N/A | 0 | 55203 | 5430
56003B | Mont Belvieu Reliability Project | Remove existing Jordan TR1 tap from Ckt.86I Jordan to Cities. Reconnect at new Ckt.52A Jordan to Winfre |  | Jordan | Cities | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 | 2022-10-07 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40340, 40740, 40855, 40857 | Y | N |  | Cost included in main entry | 56076 | 56003
56003C | Mont Belvieu Reliability Project | Reconfigure existing 86B/86H/86K to create new Ckt.52B Winfre to Eagle with minimum 360/440 MVA |  | Winfre | Eagle | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 | 2022-11-04 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40220, 40300, 40500, 40764 | Y | N |  |  | 56077 | 56003
56003D | Mont Belvieu Reliability Project | Expand Jordan and Mont Belvieu with new line positions |  | Eagle | Mont Belvieu | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 | 2022-11-04 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40500, 41111 | Y | N |  | Cost included in main entry | 56078 | 56003
56003E | Mont Belvieu Reliability Project | Expand Jordan and Mont Belvieu with new line positions |  | Dalton | BRINE/Mont Belvieu | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 | 2022-10-19 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40220, 40775, 41111, 40740, 41113 | Y | N |  |  | 56079 | 56003
56003F | Mont Belvieu Reliability Project | Reconfigure existing 86B/86H/86K to create new Ckt.86B Chevron to Langston with minimum 440/525 MVA |  | Chevron | Langston | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 | 2022-11-06 | 138 | 0 | 0 | 0 |  | Harris | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40300, 40775 | Y | N |  |  | 56080 | 56003
57521C | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 00:01 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 57532 | 57521
57521D | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 00:02 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 57533 | 57521
5430P | Conversion to 138kV | Transfer the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2023-01-01 | 2019-07-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 910, 932 | Y | N | N/A | 0 | 55210 | 5430
5430Q | Conversion to 138kV | Retire the existing 69kV RD Wells substation together with the autotransformers |  | RD Wells |  | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2023-01-01 | 2019-07-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 932, 930 | Y | N | N/A | 0 | 55211 | 5430
5430H | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2023-01-01 | 2018-12-11 | 138 | 0 | 1.521 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 928, 931 | Y | N | N/A | 0 | 55202 | 5430
67900 | NBU ECMornhinweg Substation Upgrade | NBU is adding a second power transformer at EC Mornhinweg and reconfiguring the substation to a ring bus arrangement. |  | EC Mornhinweg | GPI Switch | Under Construction | 61593 | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2023-01-01 01:00 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 | [5 empty] | Y | N |  | 0 | 67901 | 67900
69904 | Interconnects Leon Creek Bitcoin |  |  | TNMP Leon Creek (bus # 38355) | Customer substation (bus # 38356) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-01-15 |  | 138 | 0 | 0 | 0 | 0,160 | Pecos | Pecos | Tier 4 |  |  |  |  | 38356, 38355 | Y |  |  | 0 | 69905 | 69904
62450 | Pin Oak 138 kV Switch (Formerly Big Brown Tap) | Pin Oak 138 kV Switch (Formerly Big Brown Tap) |  | Pin Oak | Pin Oak | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2014 | 2023-01-15 |  | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3505, 3506, 3510, 196, 212, 3507 | Y |  |  | 0 | 62451 | 62450
66020 | New substation to connect Mustang Creek INR | New substation to connect Mustang Creek INR |  | Galow |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-01-27 |  | 138 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5521, 5523, 78104 | Y | N |  | 0 | 66021 | 66020
63433 | Rebuilds AEP Creosote-TNMP Coyanosa138 kV line as Dbl Ckt |  |  | AEP Creosote (bus # 60377) and TNMP TransPecos Tap (bus # 38376) | TNMP Coyanosa (bus # 38380) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-01-28 |  | 138 | 0 | 0.87 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38376, 38380, 60377 | Y |  |  | 0 | 63434 | 63433
58006 | Magnolia Cap Bank | Install Cap bank at Magnolia | IN-SERVICE | Magnolia |  | In-Service |  | AEP TCC | James Douglas bcogan@aep.com 918-599-2674 | TP2020066 | 2023-01-30 | 2022-12-19 | 138 | 0 | 0 | 0 | 0,14.4 | Karnes |  | Tier 4 |  |  |  |  | 8583 | Y |  |  | 0 | 58007 | 58006
66530 | Add Consavvy 345/138 kV Switch | Add Consavvy 345/138 kV Switch |  | Consavvy | Consavvy | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8498 | 2023-01-30 |  | 345 | 0 | 0 | 1200 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 11386, 11387, 11388, 11389, 1058, 1125, 1133, 1329, 11016, 11123, 19000, 23856 | Y |  |  | 0 | 66531 | 66530
61875 | Hungerford to East Bernard Ckt.60 Upgrades | Upgrade Hungerford to East Berrnard Ckt.60 to increase thermal limits |  | Hungerford | Caney | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-01-31 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44150, 44190 | Y | N |  | 0 | 61876 | 61875
57167 | Faysville substation conversion from 69 to 138 kV | Converts Faysville to 138 and connects to Redgate |  | Faysville | Red Gate | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-01-31 |  | 138 | 8.46 |  | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5780, 5782, 5786, 5788, 5784, 8377 | Y | N |  | 0 | 63732 | 57167
67427 | Greens Bayou to Clinton 138kV Conversion | Upgrade Ckt.16C MINING Switchrack to MINING/BENTON ahead of future 138kV Conversions |  | Mining Switchrack | BENTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-01-31 |  | 69 | 0 | 1.9 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41062, 41063, 48177, 40470, 41380, 48171 | Y | N |  | 0 | 67428 | 67427
56003G | Mont Belvieu Reliability Project | Upgrade Ckt.84D Cedar Bayou Plant to Cedar Bayou Tap to HOPSON with minimum 682MVA Emergency Rating |  | Cedar Bayou Plant | Cedar Bayou/HOPSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-01-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40012, 40015, 41690 | Y | N |  |  | 56081 | 56003
64572B | HO Clarke Bus Upgrade | Upgrade Ckt.90A HO Clarke to HOC TR1 to increase thermal limits |  | HO Clarke | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-01-31 00:02 |  | 138 | 0 | 0.44 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47175, 47151 | Y | N |  | Cost included in main entry | 64574 | 64572
11TPIT0008 | RAINEY_ST 138kV substation | Establish a new 138kV Rainey St. Substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2023-02-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9261, 9118, 9132 | Y | N |  |  | 8208 | 1032
45155 | Ollin: Build 138 kV station | Construct new Ollin 138 kV station |  | Ollin |  | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2752 | 2023-02-01 01:00 |  | 138 | 0.1 | 0 | 0 |  | Crane |  | Tier 4 | 19RPG013 |  |  |  | 6600, 6605, 6606, 6668, 6669, 60428, 60429, 60432, 60441, 6604, 6610, 6613, 6607, 6611, 60431, 76615 | Y | N |  | 0 | 45156 | 45155

## CancelledTPIT020123NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2023
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
55622 | Dilley to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley |  | Dilley | Pearsal | Planned | 1104 - 1282 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3822 | 2023-05-01 |  | 69 | 0 | 17.7 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8216, 8208 | N |  |  | 0 | 65574 | 55622
55622 | Dilley to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley |  | Dilley | Pearsal | Planned | 1104 - 1282 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3822 | 2023-05-01 |  | 69 | 0 | 17.7 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8216, 8208 | N |  |  | 0 | 55623 | 55622
55622 | Dilley to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley | Cancelled, incorrectly submitted prior to RPG submission. | Dilley | Pearsal | Planned | 1104 - 1282 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3822 | 2023-05-01 |  | 69 | 0 | 17.7 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8216, 8208 | N |  |  | 0 | 66650 | 55622
4804 | Wichita Falls South 345/138 kV autotransformer | Install autotransformer |  | Wichita Falls South |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4010 | 2023-05-15 |  | 345 | 0 | 0 | 600 |  | Archer |  | Tier 3 |  |  |  |  | 11464, 11465, 1422, 1425, 1464 | N | N |  |  | 12410 | 4804
44416 | Add a 2nd circuit at Brinker - Denton Steam |  |  | Brinker | Denton Steam | Planned |  | DENTON | Chuck Sears |  | 2023-07-01 | 2022-07-01 | 138 | 0.631 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 982 | N | N |  | 0 | 44417 | 44416
45513 | Santo Nino - Wormser: 138 kV Line Rebuild | Rebuild Santo Nino - Wormser 138 kV line with 795 ACSS | CANCELLED | Santo Nino | Wormser | Conceptual | 991 - 1169 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3745 | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8295, 8649, 8653 | N | N |  | 0 | 45514 | 45513
66632 | Coyote - Bulldog 138 kV Line Rebuild | Add Coyote - Bulldog 138 kV Line Rebuild | [5 empty] | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8553 | 2023-12-15 |  |  | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 23832, 23833 | N |  |  | 0 | 66633 | 66632
66632 | Coyote - Bulldog 138 kV Line Rebuild | Add Coyote - Bulldog 138 kV Line Rebuild |  | Coyote | Bulldog | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8553 | 2023-12-15 |  | 138 | 0 | 11.9 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 23832, 23833 | N |  |  | 0 | 66634 | 66632
61467 | Merrilltown Substation Addition | New 138 kV station - Oncor load | [5 empty] | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-03-24 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson | Williamson | Tier 4 |  |  |  |  | 9230, 9231, 9223, 9224 | N |  |  | 0 | 61468 | 61467
49926 | Brinker-DentonSteam Ckt1 Upgrade |  |  | Brinker | Denton Steam | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2024-07-01 | 2024-07-01 | 138 | 0 | 0.63 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 982 | N | N |  | 0 | 49927 | 49926
49926 | Brinker-DentonSteam Ckt1 Upgrade |  |  | Brinker | Denton Steam | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2024-07-01 | 2024-07-01 | 138 | 0 | 0.63 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 982 | N | N |  | 0 | 49929 | 49926
61451 | La Vernia Substation | Replace T2, 20 MVA with a 40MVA dual high-dual low |  | La Vernia | La Vernia | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.or |  | 2025-05-16 |  | 138 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7614 | N | N |  | 0 | 61452 | 61451
52070 | Carver - Maxwell: Line Rebuild | Rebuild Carver to Maxwell 138 kV Line | Cancelled | Carver | Maxwell | Planned | 1079 - 1252 | AEP TCC | Charity Kreher bcogan@aep.com 918-599-2853 | 3804 | 2026-05-31 |  | 138 | 0 | 60.24 | 0 |  | Sutton | Val Verde | Tier 3 |  |  |  |  | 8259, 8261, 60412, 8991, 8998, 60440 | N | N |  | 0 | 65562 | 52070
52070 | Carver - Maxwell: Line Rebuild | Rebuild Carver to Maxwell 138 kV Line |  | Carver | Maxwell | Planned | 1079 - 1252 | AEP TCC | Charity Kreher bcogan@aep.com 918-599-2853 | 3804 | 2026-05-31 |  | 138 | 0 | 60.24 | 0 |  | Sutton | Val Verde | Tier 3 |  |  |  |  | 8259, 8261, 60412, 8991, 8998, 60440 | N | N |  | 0 | 52071 | 52070
5525 | Forney - Lake Hubbard 345 kV Line | Construct new 345 kV line |  | Forney | Lake Hubbard | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4233 | 2027-05-15 |  | 345 | 0 | 7.5 | 0 |  | Kaufman | Dallas | Tier 2 |  |  |  |  | 2455, 2467 | N | N |  |  | 13252 | 5525
5522 | Lake Hubbard 345/138 kV Switching Station | Construct new 345/138 kV switching station |  | Lake Hubbard |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4139 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 |  |  |  |  | 12455, 12456, 2401, 2402, 2455 | N | N |  |  | 13249 | 5522
44870 | Charlotte 69 kV Station | Charlotte 69 kV Station: Add Cap Bank |  | Charlotte | - | Planned | 976 - 1154 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3734 | 2027-07-01 |  | 69 | 0 | 0 | 0 | 0,7.2 | Atascosa |  | Tier 3 | [5 empty] | N | N |  | 0 | 44871 | 44870
4490 | LaPalma: Add 2nd 345/138 kV autotransformer | Add 345/138 kV autotransformer capacity at LaPalma | CANCELLED | LaPalma |  |  | 710 - 0880 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 2904 | 2027-09-30 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 4 |  |  |  |  | 8356, 8317, 8314 | N | N |  |  | 12067 | 4490

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2022-C1 | Cap bank Addition at AIRPRO Station | CNP | 2025 min
2016-N1 | Kiamichi Energy Facility (140077) 345-kV Reactor Addition | KIOWA POWER PARTNERS LLC (RE) | 2025 min
2021-N2 | City View (1483) – Ceramic (1485) 138-kV Line Terminal Equipment Upgrade | Oncor | 2024
2020-NC19 | Cedar Crest (2493) to Dealey (2842) to West Levee (2400) 138-kV Line Upgrades | Oncor | 2024
2021-NC9 | Sargant – Saint Augustine 138-kV Line Upgrade | Oncor | 2024
2022-NC1 | Waco Northeast Tap (3551) to Waco North (3552) 138-kV Line Upgrade | Oncor | 2024
2022-NC2 | Brand (827) to Ben Davis (968) 138-kV Line Upgrade | GPL | 2024
2022-NC3 | Argyle - Corinth 138-kV Line Upgrade | ONCOR | 2024
2022-NC4 | Wilmer - Southside Filtration Tap East - Kleberg - Seagoville - Seagoville Switch 138-kV Line Upgrade | Oncor | 2024
2022-NC5 | New International Airport Switch 345/138-kV Station | Oncor | 2024
2022-NC6 | Hackberry - DFW D-East 138-kV Line Upgrades | Oncor | 2024
2022-NC7 | Liggett Switch- DFW Area 138-kV Line Upgrades | Oncor | 2024
2022-NC8 | Lake Creek - Elm Mott 138-kV Line Upgrades | Oncor | 2024
2022-NC9 | Tin Roof 345-kV Expansion | Oncor | 2024
2022-NC10 | Randol Mill Tap East - Randol Mill 138-kV Line Upgrade | Oncor | 2024
2021-FW2 | Yucca Drive Switch - Wolfcamp - Courtney Creek 69-kV to 138-kV Line Conversion | Oncor | 2024
2021-FW4 | Rio Pecos - Rankin - Texon Tap - Atlantic Best Tap - Kemper Tap - Big Lake 69-kV to 138-kV Line Conversion | AEP | 2024
2021-FW5 | Caymus TNP - Gas Pad and Caymus TNP - Caymus Compressor TNP 138-kV Line Terminal Equipment Upgrade | TNMP, AEP | 2024
2021-FW6 | Monument Draw TNP to Monument Draw Gray Oak TNP 138-kV Line Terminal Equipment Upgrade | TNMP | 2027
2021-FW7 | TNMP Flat Top 138/25-kV Transformer Upgrade | TNMP | 2024
2021-FW8 | Wink TNP - California TNP 69-kV to 138-kV Line Conversion | TNMP | 2027
2021-FW12 | Moss Switch - Ector Harper - Red Lakes Switch - Penwell POD - Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2021-FW16 | 16th Street TNP - Fort Stockton TNP 69-kV Line Upgrade | TNMP | 2024
2021-FW19 | Morgan Creek SES - Longshore Switch 345-kV Line Upgrade | ONCOR | 2027
2021-FW20 | Lamesa - Key Sub - Gail Sub - Willow Valley Switch 138-kV Line Upgrade | Oncor | 2024
2021-FW23 | Big Spring West - Stanton East 138-kV Line Upgrade | Oncor | 2024
2021-FW24 | Adobe Meadow - Midland East 138-kV Line Upgrade | Oncor | 2025 min
2022-FW1 | Lynx - Tombstone - Fort Stockton Plant - Leon Creek TNP 138-kV Line Upgrade | AEP, TNMP | 2024
2022-FW2 | Cedarvale 345-kV Subtation Expansion | TNMP, Oncor | 2024
2022-FW3 | New Reiter 345/138-kV Substation and Quail East 345-kV Substation | Oncor | 2024
2022-FW4 | New Opyote to Pyote 138-kV Line Addition | TNMP, Oncor | 2024
2022-FW5 | New Load Bus 900012 - New Load Bus 900021 138-kV Line Addition | Oncor | 2024
2022-FW6 | Far West Reactive Power Support Device Additions | TNMP, Oncor, AEP | 2024
2022-FW7 | Leon Creek TNP - Airport TNP 138-kV Line Limiting Element Upgrade | TNMP | 2024
2022-FW8 | New Load Bus 900080 - New Load Bus 900032 138-kV Line Addition | Oncor | 2024
2022-FW9 | Cholla 345/138-kV Station Addition | TNMP, Oncor | 2024
2022-FW10 | Dollarhide - Dollarhide Unocal 138-kV Line Upgrade | Oncor | 2024
2022-FW11 | Pecos TNP - Faulkner Toyah TNP 138-kV Line Addition | TNMP | 2024
2022-FW12 | Tarbush TNP - Pig Creek 138-kV Line Upgrade | TNMP, AEP | 2024
2022-FW13 | Yarbrough Sub - Pecos Trails POD - Monahans Tap 2 - Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2022-FW14 | Odessa EHV Switch - Rexall - General Tire Switch - Southwestern Portland Tap - Edwards Tap - Judkins - Sandhills Tap - Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2022-FW15 | Holt Switch - Turnbaugh Corner Switch - Scharbauer POI - Oncor 900053 Tap - Notrees Southeast POI - Blockline POD - Amburguey - Yucca Drive Switch 138-kV Line Upgrade | Oncor | 2024
2022-FW16 | Moss Switch - Shin Oak POD - Yucca Drive Switch 138-kV Line Upgrade | Oncor | 2024
2022-FW17 | Moss Switch - Trigas Odessa Southwest - Big Three Odessa Tap 138-kV Line Upgrade | Oncor | 2024
2022-FW18 | Odessa EHV Switch - Trigas Odessa Tap 138-kV Line Upgrade | Oncor | 2024
2022-FW19 | Lamesa - Jim Payne POI - Paul D Tap 138-kV Line Upgrade | Oncor | 2024
2022-FW20 | Spraberry Switch - CRMWD 7 Tap - Meyers Draw - Dewey Lake Tap - Polecat Creek Switch 138-kV Line Upgrade | Oncor | 2025 min
2022-FW21 | Midland East – Midland County NW 345-kV Line Rebuild and Second Circuit Addition | Oncor | 2025 min
2022-FW22 | Midessa South 345/138-kV Transformer Upgrade and Second 345/138-kV Transformer Addition | Oncor | 2025 min
2022-FW23 | Consavvy South 345/138-kV Station Addition | Oncor | 2024
2022-FW24 | Faraday - Lamesa - Clearfork - Riverton 345-kV Double Circuit Line Addition | Oncor, WETT | 2024
2022-FW25 | Cedarvale Third 345/138-kV Transformer Addition | TNMP | 2024
2022-FW26 | Tarbush TNP - Leon Creek TNP and Woodward - Airport TNP - Leon Creek TNP 138-kV Line Additions | TNMP | 2024
2021-W1 | Cassava - San Angelo Concho 69-kV to 138-kV Line Conversion | AEP | 2025 min
2021-W2 | Morgan Creek - McDonald 138-kV Line Upgrade | Oncor | 2024
2021-W7 | San Angelo Highland Street - San Angelo South Tap - San Angelo Power Station 138-kV Line Upgrade | AEP | 2025
2021-W9 | San Angelo Paulann - San Angelo North 138-kV Line Upgrade | AEP | 2027
2021-W10 | San Angelo Red Creek - San Angelo Coke Street - Rusthill 138-kV Line Upgrade | AEP | 2025
2021-W12 | Cap Bank Addition at 138-kV Hargrove Substation | AEP | 2027
2022-W1 | China Grove - Getty Tap 138-kV Line Upgrade | ONCOR | 2028
2022-W2 | Morgan Creek SES - Tonkawa 345-kV Line Rebuild and Second Circuit Addition | ONCOR | 2025
2022-W3 | Colorado City - Plowboy 69-kV to 138-kV Line Conversion | ONCOR | 2025
2022-W4 | Abilene Northwest - Abilene Mulberry Creek - Abilene Industrial Park - Abilene Elmcreek 138-kV Line Upgrade | AEP | 2024
2022-W5 | Scurry Chevron - Kndrsacrc - New Load Bus 900041 Tap - Knapp 138-kV Line Upgrade | Oncor | 2027
2022-W6 | Morgan Creek - Westbrook - Latan Howard Tap 69-kV Line Upgrade | Oncor | 2024
2022-W7 | Knapp - Bluff Creek Switch - Exxon Sharon Ridge 138-kV Line Upgrade | Oncor | 2027
2021-WFW1 | Big Lake - Barnhart - Cassava 69-kV to 138-kV Line Conversion | AEP | 2027
2022-WFW1 | Twin Buttes - Hargrove - Pumpjack - Jerry - Russek Street - Big Lake 138-kV line Upgrade | AEP, LCRA TSC | 2024
2022-WFW2 | Midessa South SW - Consavvy - Longshore Switch - Morgan Creek SES 345-kV Line Upgrades | Oncor | 2025 min
2022-WFW3 | Morgan Creek SES - Falcon Seaboard - Midland East 345-kV Line Rebuild and Second Circuit Addition | Oncor | 2025 min
2022-SC1 | Sim Gideon - Bastrop City - Swiftex 138-KV Line Upgrade | LCRA TSC | 2027
2022-SC2 | San Marcos - Camp Gray - Robert Brown Jr - Clear Fork - Lockhart 69-kV to 138-kV Line Conversion | LCRA TSC | 2028
2022-SC3 | Pintail and Mallard 138-kV Substation and Line Additions | Oncor | 2025
2022-SC4 | Samsung 345-kV Substation and Line Addition | Oncor | 2028
2022-SC5 | Sandow Switch 345/138-kV Substation Expansion | Oncor | 2024
2022-SC6 | Howard - San Miguel 345-kV Double Circuit Line Addition and Beck Road 345/138-kV Substation Expansion | CPS, STEC | 2027
2022-SC7 | Decker 138-kV Bus Tie Breaker Upgrade | AEN | 2027
2022-SC8 | Lytton Substation 345/138-kV Transformer Addition | AEN | 2027
2022-S1 | Corpus Christi Sub 138/69-kV Transformer Addition and New 138-kV (8462) Substation and Line Additions | AEP, STEC | 2024
2022-S2 | Fannisub - Goliad 69-kV Line Upgrade | AEP, STEC | 2024
2022-S3 | Pearsall 138/69-kV Transformer Upgrade | STEC | 2027
2022-S4 | Cap Bank Addition at 138-kV Wormser Road Substation | AEP | 2025
2022-S5 | Reactor Addition at 345-kV NSub Substation | AEP | 2027
2022-S6 | San Diego - Freer 69-kV Line Upgrade | AEP | 2024
2022-S7 | Rincon - Gregory 69-kV Line Upgrade | AEP | 2024
2022-S8 | Rio Hondo - Burns - Heidelburg 138-kV Line Upgrade | STEC | 2024
2022-S9 | LA Palma – Haine Dr 138-kV Line Upgrade | AEP | 2025
2022-S10 | Wesmer - Pantera 138-kV Line Upgrade | AEP | 2024
2022-S11 | North Laredo- Unitec - Gateway West Tap 138-kV Line Upgrade | AEP | 2025

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Cindy Miller | Camiller2@aep.com | Cindy Miller: 918 599 2891 | Glen Reed; David Kidd; Brad Myers; Mabel See; Mike Forcum; Doug Lee; Daniel Lyons; Bob Lager; Mina Turner; Lisa Kelso; Carole Myser | gareed@aep.com; dekidd@aep.com; blmyers@aep.com; msee@aep.com; mlforcum@aep.com; dnlyons@aep.com; dlee@aep.com; rjlager@aep.com; myturner@aep.com; lokelso@aep.com; camyser@aep.com | David Kidd: 918 599 2637 Glen Reed: 918 599 2664 Brad Myers: 918 599 2690
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Hunt, Dandy; Brion Ryan | dandy.hunt@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | Reza:512 322 6740 Dandy:512 322 6748 Brion: 512-322-6879
BPUB | Primary | Ramon Sanz | rsanz@brownsville-pub.com; | Ramon: 956 983 6203 | James McCann | jmccann@brownsville-pub.com; | James: 956 983 6204
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Dwight Beckman | dbeckman@brazoselectric.com | Dwight: 254 750 6373 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | Edward Lopez | elopez@btutilities.com | Edward: 979 821 5697 | David Hering | dhering@btutilities.com | David: 979 821 5652
CNP | Primary & Secondary | Wesley Woitt | wesley.woitt@centerpointenergy.com | Wesley Woitt: 713-207-2760 | Yingying Huang; Raja Sekhar Kakarla; Cody Mann | Yingying.Huang@centerpointenergy.com; rajasekhar.kakarla@centerpointenergy.com; cody.mann@centerpointenergy.com | Yingying Huang: 713-207-2831 Raja Sekhar Kakarla: 713-207-3614 Cody Mann: 713-207-3149
COCS | Primary | Glenn Gavit | ggavit@cstx.gov | Glenn: 979 764 3682 | Timothy Crabb, Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | Basileo Rocha, Sunil Dhakal | bdrocha@cpsenergy.com; SDhakal@cpsenergy.com | Basileo: 210 353 4933 Sunil: 210 353 2008 | Kenneth Bowen Trieu Vo | kbowen@cpsenergy.com; tvo@cpsenergy.com; | Kenneth: 210 353 4142 Trieu: 210 353 2127
CTT (Cross Texas Transmission) | Primary & Secondary | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310 | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310
DENTON | Primary & Secondary | Mark Zimmerer | Mark.Zimmerer@cityofdenton.com | Mark: 940-349-7169 | Michael Spanos | michael.spanos@dnv.com
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Grubbs, David; Juan Santos | Dgrubbs@gpltexas.org; Jsantos@gpltexas.org | David: 972 205 2664 Juan: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; BEC (Bandera); BBEC; CTEC; GVEC; NBU; PEC; SBEC; RGEC | Primary & Secondary | Dylan Preas | dylan.preas@lcra.org | Dylan: 512-578-4514 | Naved Khan | naved.khan@lcra.org | Naved: 512-578-4176
Lone Star | Primary & Secondary | Chenyan Guo | chenyan.guo@fpl.com | Chenyan: 561-304-5692 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Charles Saker | charles.saker@oncor.com | Charles: 214-743-6896 | Paul Bell | paul.bell@oncor.com | Paul: 214-743-6676
Rayburn | Primary & Secondary | Stephen Geiger | sgeiger@rayburnelectric.com | Stephen: 469-402-2112 | Scott Donahm | sdonham@rayburnelectric.com | Scott: 469-402-2024
Sharyland Utilities | Primary & Secondary | Brad Schwarz | bschwarz@huntpower.com | Brad: 512-289-7425 | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243
STEC | Primary & Secondary | Doug Evans | devans@stec.org | Doug: 361 485 6459 | Paul Person Loretta Gonzalez | pperson@stec.org; lgonzalez@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Ahmad Saboor | asaboor@texasmpa.org | Ahmad: 936 873 1104 | Frank Owens | fowens@texasmpa.org; | Frank: 936 873 1120
TNMP | Primary & Secondary | Robert Lona | Robert.Lona@tnmp.com | Robert: 281-581-4732 | Anthony, Hudson Ballay, Dustin Cloninger, Ross | Anthony.Hudson@tnmp.com; Dustin.Ballay@tnmp.com; Ross.Cloninger@tnmp.com; | Anthony: 281 581 4712 Dustin:281 581 4730 Ross:281 581 4733
Wind Energy Texas Transmission (WETT) | Primary | Chris Ramirez | cramirez@wettllc.com | Chris: 737-218-4525 | Christina Minchew | cminchew@wettllc.com | Christina: 737-218-4520