## ImprovementCostSummary02222017
| Project Cost |  |  |  |  | XFMR MVA
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total
2016 | 1105774850 | 723647955 | 166648000 | 1996070805 | 2016 | 6247 | 1565 | 0 | 7812 | For ROS and BOD Reports
2017 | 321219628 | 1155657053.36 | 263911112 | 1740787793.36 | 2017 | 7007 | 1027 | 334.8 | 8368.8 | ·All Projects (in engineering, routing, licensing and construction): |  |  |  | 6909264396.36
2018 | 844326712 | 1034772740 | 516224051 | 2395323503 | 2018 | 4530 | 1315 | 0 | 5845 | ·Transmission Projects Energized in 2017: |  |  |  | 3709000
2019 | 344329000 | 717568000 | 197510000 | 1259407000 | 2019 | 6501 | 220 | 130 | 6851
2020 | 348300000 | 269525000 | 94753000 | 712578000 | 2020 | 3000 | 645 | 0 | 3645
2021 | 103900000 | 251554000 | 9100000 | 364554000 | 2021 | 1800 | 105 | 0 | 1905
2022 | 162145000 | 73400000 | 116938100 | 352483100 | 2022 | 2086 | 0 | 0 | 2086
2023+ | 33600000 | 50240000 | 4000000 | 87840000 | 2023+ | 1275 | 0 | 0 | 1275
2017COM | 0 | 1725000 | 1984000 | 3709000 | 2017COM | 0 | 0 | 0 | 0
2017PLAN | 321219628 | 1153932053.36 | 261927112 | 1737078793.36 | 2017PLAN | 7007 | 1027 | 334.8 | 8368.8
2016-2023+ | 3263595190 | 4276364748.36 | 1369084263 | 8909044201.36 | 2016-2023+ | 32446 | 4877 | 464.8 | 37787.8
2016-2017 | 1426994478 | 1879305008.36 | 430559112 | 3736858598.36 | 2016-2017 | 13254 | 2592 | 334.8 | 16180.8
2018-2023+ | 1836600712 | 2397059740 | 938525151 | 5172185603 | 2018-2023+ | 19192 | 2285 | 130 | 21607
| Circuit Miles New |  |  |  | Circuit Miles Rebuilt, Reconductored or Upgraded |  |  |  |  | Total
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total | 345 | 138 | 69 | Total
2016 | 358.738 | 291.76 | 15.9 | 666.398 | 2016 | 145.39 | 467.31 | 149.691 | 762.391 | 504.128 | 759.07 | 165.591 | 1428.789
2017 | 0 | 287.907 | 0.15 | 288.057 | 2017 | 102 | 778.561 | 255.62 | 1136.181 | 102 | 1066.468 | 255.77 | 1424.238
2018 | 364.35 | 151.47 | 0 | 515.82 | 2018 | 71.94 | 408.761 | 476.53 | 957.231 | 436.29 | 560.231 | 476.53 | 1473.051
2019 | 44.5 | 79.97 | 33.11 | 157.58 | 2019 | 137 | 502.12 | 147.838 | 786.958 | 181.5 | 582.09 | 180.948 | 944.538
2020 | 171 | 112.54 | 0 | 283.54 | 2020 | 16 | 105.07 | 103.72 | 224.79 | 187 | 217.61 | 103.72 | 508.33
2021 | 0 | 55.7 | 0 | 55.7 | 2021 | 137.5 | 105.51 | 15.8 | 258.81 | 137.5 | 161.21 | 15.8 | 314.51
2022 | 68 | 0 | 72 | 140 | 2022 | 0 | 103.9 | 12.6 | 116.5 | 68 | 103.9 | 84.6 | 256.5
2023+ | 4 | 6.1 | 0 | 10.1 | 2023+ | 67.96 | 44.5 | 2 | 114.46 | 71.96 | 50.6 | 2 | 124.56
2017COM | 0 | 0 | 0 | 0 | 2017COM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017PLAN | 0 | 287.907 | 0.15 | 288.057 | 2017PLAN | 102 | 778.561 | 255.62 | 1136.181 | 102 | 1066.468 | 255.77 | 1424.238
2016-2023+ | 1010.588 | 985.447 | 121.16 | 2117.195 | 2016-2023+ | 677.79 | 2515.732 | 1163.799 | 4357.321 | 1688.378 | 3501.179 | 1284.959 | 6474.516
2016-2017 | 358.738 | 579.667 | 16.05 | 954.455 | 2016-2017 | 247.39 | 1245.871 | 405.311 | 1898.572
2018-2023+ | 651.85 | 405.78 | 105.11 | 1162.74 | 2018-2023+ | 430.4 | 1269.861 | 758.488 | 2458.749

## FutureTPIT020117NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2017
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
3396 | Cedar Hill: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Cedar Hill | IN-SERVICE | Cedar Hill |  | In-Service | 626 - 0794 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2584 | 2017-02-02 |  | 69 | 0 | 0 | 90 |  | Coke |  | Tier 4 |  |  |  | 6423, 6425 | Y | N |  |  | 3594 | 3396
3398 | Cedar Hill: Add 69 kV capacitor bank | Add one 7.2 Mvar capacitor bank at Cedar Hill | IN-SERVICE | Cedar Hill |  | Under Construction | 629 - 0797 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2587 | 2017-02-02 |  | 69 | 0 | 0 | 0 | 0,7.2 | Coke |  | Tier 4 |  |  |  | 6423 | Y | N |  |  | 3596 | 3398
3745 | Interconnect Los Vientos III at Del Sol 345 kV Station | Del Sol: Add 345 kV breaker terminal for WF interconnect and install second 345 kV circuit to POI |  | DEL SOL |  | In-Service | 666 - 0835 | ETT | KENNETH 'RICH' HALEY dnlyons@aep.com 918-599-2698 | 3530 | 2017-02-06 |  | 345 |  |  |  |  | Starr |  | Tier 4 |  |  |  | 80355 | Y | N |  |  | 3991 | 3745
5683A | Line H Rebuild and 138kV conversion. | Install temporary 10 MVAR cap bank and de-energize IH20-Collie Field Tap 69 kV line (38040-38041). |  | 38041 | 38041 | Under Construction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-02-10 |  | 69 | 0 | 0 | 0 | 0,10 | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38040, 38041, 38150 | Y |  |  | Temporary 10 MVAR Capbank at Collie Field Tap (Bus# 38041). | 6568 | 5683
3402 | Abilene Northwest to Ely Tap: Rebuild 69 kV line | Rebuild Abilene Northwest to Ely Tap 69 kV line | Project Description and Schedule Update | Abilene Northwest | Ely Tap | Under Construction | 630 - 0798 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2589 | 2017-02-28 |  | 69 | 0 | 8.2 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6225, 6241 | Y | N |  |  | 3600 | 3402
3825 | Jordan: Install 2nd 800MVA Autotransformer | Install 2nd 800MVA autotransformer at Jordan substation |  | Jordan |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 992 | 2017-02-28 |  | 345 | 0 | 0 | 800 |  | Chambers |  | Tier 4 |  |  |  | 49078, 40850, 40855 | Y | N |  |  | 4107 | 3825
5191 | Gas Pad Tap: Build 138 kV station | Construct 138 kV POD box bay for customer interconnection | Schedule Update | Gas Pad Tap |  | Under Construction | 755 - 0938 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2629 | 2017-02-28 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60397 | Y | N |  |  | 5675 | 5191
5207 | Goliad 138 kV Station: Upgrade 69 kV Station | Add 138 kV design box bay with two breakers, expandable to three breakers and operated at 69 kV. |  | Goliad |  | Under Construction | 763-0948 | AEP TCC | Wilbur Roberts dnlyons@aep.com 918-599-2664 | 3571 | 2017-02-28 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | Y | N |  |  | 5691 | 5207
5797 | MIRAGE 138 kV Sub - Gen Interconnection-17INR0022-Net Power | Construct service to new 138kV MIRAGE customer-owned substation. Loop through Ckt.96 MCCABE to BIMONT. For Generation Interconnection 17INR0022 Net Power |  | MIRAGE | MCCABE/BIMONT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-02-28 |  | 138 | 0.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42360, 40209, 42351 | Y | N |  |  | 6362 | 5797
4978 | Helena Circuit Breaker Addition | Install two 138-kV circuit breakers at Helena in a single bus-single breaker configuration. |  | Helena |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015114 | 2017-03-01 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  | 78584 | Y | N |  |  | 5438 | 4978
5172 | Laredo: Add two 138 kV breakers | Add two 138 kV breakers to the STATCOM yard and rebuild the Laredo to Laredo STATCOM 138 kV tie with 1026 ACCC/TW |  | Laredo | Laredo | Planned | 744 - 0927 | AEP TCC | Rich Haley dnlyons@aep.com 918-599-2698 | 2918 | 2017-03-01 |  | 138 | 0 | 0.111 | 0 |  | Webb | Webb | Tier 4 |  |  |  | 8293, 80021 | Y | N |  |  | 5656 | 5172
5174 | Nelson Sharpe: Reconfigure PST | Relocate the PST at Nelson Sharpe from the Barney Davis to Nelson Sharpe 138 kV line to the Nelson Sharpe to Celanese Bishop 138 kV line |  | Nelson Sharpe |  | Under Construction | 747 - 0930 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2921 | 2017-03-01 |  | 138 | 0 | 0 | 150 |  | Nueces |  | Tier 4 |  |  |  | 85002, 85007, 8515, 8516, 85001 | Y | N |  |  | 5658 | 5174
5229 | Bow Wood Substation Addition | Provide transmission service for a generator off T424 345-kV line between Red Creek and Brown Switch Substations. |  | Red Creek | Brown Switch | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015828 | 2017-03-01 |  | 345 | 0 | 0 | 0 |  | Tom Green | Brown | Tier 4 |  |  |  | 76006, 1444, 6444 | Y | N |  |  | 5727 | 5229
5267 | MLSE Upgrade: T152 Sim Gideon to Winchester | Upgrade terminal equipment at Sim Gideon and Winchester for a static normal and emergency rating of 193 MVA. |  | Sim Gideon | Winchester | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016216 | 2017-03-01 |  | 138 | 0 | 0 | 0 |  | Bastrop | Fayette | Tier 4 |  |  |  | 7306, 7310 | Y | N |  |  | 5768 | 5267
5999 | La Pryor: Rebuild Distribution Station | Rebuild La Pryor Distribution Station |  | Turtle Creek | Uvalde | Under Construction | 813 - 0997 | AEP TCC | Aaron Schwerman dnlyons@aep.com 918-599-2698 | 3603 | 2017-03-01 |  | 69 | 0 | 0 | 0 |  | Zavala |  | Tier 4 |  |  |  | 88672, 8231, 8243, 8672 | Y | N |  |  | 6541 | 5999
3353 | Aransas Pass to Rockport: Convert 69 kV line to 138 kV | Expand Aransas Pass and Rockport 138 kV stations and add 138/69 kV autotransformer capacity at Rockport |  | Aransas Pass | Rockport | Planned | 624 - 0792 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3507 | 2017-03-14 |  | 138 | 0 | 0 | 90 |  | Medina |  | Tier 4 |  |  |  | 8427, 8430, 8432, 8434 | Y |  |  |  | 3542 | 3353
4273 | Corsicana - Trinidad 69 kV Line | Upgrade existing line | Construction schedule change | Corsicana | Trinidad | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R794 | 2017-03-15 |  | 69 | 0 | 26.5 | 0 |  | Navarro | Henderson | Tier 3 | 2015-06-15 | 2015-08-15 |  | 3128, 3466, 3467, 3468, 3469 | Y | N |  |  | 4647 | 4273
4503 | BRYN_4503_Rayburn_Tabor_Upgrade | Reconductor Rayburn to Tabor Line with 1033 |  | 32861 | 32870 | Planned |  | BRYN |  |  | 2017-03-15 |  | 69 | 0 | 4.06 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32861, 32870 | Y |  |  |  | 4900 | 4503
4754 | Walnut Springs 69 kV capacitors | Install shunt capacitors |  | Walnut Springs |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1723 | 2017-03-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Bosque |  | Tier 4 |  |  |  | 1647 | Y | N |  |  | 5174 | 4754
5793 | Silver Hill Substation | Add new 10MVA station near the TAMU RELLIS Campus |  |  |  | Planned |  | BRYN |  |  | 2017-03-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32850, 32864, 32868 | Y |  |  |  | 6357 | 5793
16TPIT0032 | Esmeralda to Yucca: Build 138 kV line | Construct new Esmeralda station along Big Lake to Friend Ranch 138 kV line and build new 138 kV line from Esmeralda to Yucca | Project Description and Cost Update | Esmeralda | Yucca | Under Construction | 585 - 0745 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2577 | 2017-03-31 |  | 138 | 13 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6034, 6035, 6036, 6531, 6525 | Y | N |  |  | 2761 | 2637
3903 | Lobo 345 kV Station: Add 345/138 kV Auto | Add 2nd 345/138 kV Autotransformer at Lobo Switching Station |  | Lobo |  | Under Construction | 663 - 0832 | ETT | Terri Weeks dnlyons@aep.com 918-599-2698 | 3538 | 2017-03-31 |  | 345 | 0 | 0 | 675 |  | Webb |  | Tier 4 |  |  |  | 80219, 80221 | Y | N |  |  | 4199 | 3903
4145 | Ckt.38 Galena Park to Greens Bayou De-Energization | De-energize Ckt.38 Galena Park to Greens Bayou. Reconfigure GYPSUM tap to be served radially out of Greens Bayou on Ckt.38. |  | Galena Park | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1128 | 2017-03-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40619, 40751, 40100, 40190, 40280, 40281, 40330, 40352, 40370, 40470, 40555, 40580, 40590, 40610, 40611, 40700, 40710, 40715, 40716, 40725, 40780, 40841, 40990, 41000, 41009, 41191, 41260, 41530, 41670, 41675, 47630, 48102, 48130, 48210, 48211, 48230, 48231, 48260, 48261, 48264, 48299, 48372, 48384, 48385, 48402, 48412, 40270, 40420, 40450, 40460, 40630, 40717, 40720, 41080, 41250, 41300, 41430, 41681, 46610 | Y | N |  |  | 4490 | 4145
16TPIT0031 | Esmeralda: Build 138 kV station | Construct new Esmeralda station along the Big Lake to Friend Ranch 138 kV line and build a new 138 kV line from Esmeralda to Yucca | Project Title and Description Update | Esmeralda |  | Under Construction | 585 - 0738 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2576 | 2017-03-31 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6525, 6562, 60375 | Y | N |  |  | 4646 | 3241
4967 | Nelson Sharpe: Add 138 kV term. for generator interconnect | Interconnect Chapman Ranch Windfarm at Nelson Sharpe and construct 138 kV line with 2-795 ACSR from Nelson Sharpe to Santa Cruz |  | Nelson Sharpe | Santa Cruz | Under Construction | 733 - 0914 | ETT | Dave Goetz dnlyons@aep.com 918-599-2698 | 3563 | 2017-03-31 |  | 138 | 6 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 80503, 85001 | Y |  |  |  | 5427 | 4967
5065 | WATSON 138kV Substation | Construct service to new 138kV WATSON customer-owned substation. Loop through Ckt.21 Witter to DAVSON. | - Overall Cost Update - Overall Date Update | WATSON |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 55 | 2017-03-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 41720, 40370, 40400, 40420, 40590, 41240, 41711, 41712, 40630, 41670, 42311, 42312 | Y | N |  |  | 5543 | 5065
5080 | Bronco: Build 69 kV temporary tap | Interconnect Solaire Holman solar farm at temporary tap to connect Solaire Holman to the Alpine to Fort Stockton Plant 69 kV line | Schedule and Cost Update | Bronco |  | Under Construction | 740 - 0923 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2620 | 2017-03-31 |  | 69 |  |  |  |  | Brewster |  | Tier 4 |  |  |  | 6674, 6666, 38490 | Y | N |  |  | 5560 | 5080
5537 | Gila-Hwy9_ckt1: replace underground cable | Install new underground conduits and dielectric cable with 1300A normal/2150A emergency rating, below Corpus Ship channel, from Gila 138 kV station yard to cable terminal. |  | Gila | Cable Terminal | Under Construction | 790 - 0975 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3580 | 2017-03-31 |  | 138 | 0 | 0.41 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8470, 80260 | Y | N |  |  | 6090 | 5537
5542 | Gila-Hwy9_ckt2: replace underground cable | Gila-Hwy9 circuit 2: Install new underground conduits and dielectric cable with 1300A normal/2150A emergency rating, below Corpus ship channel, from Gila 138 kV station yard to cable terminal. Also, remove Gila-Morris St. 138 kV line from service and return Gila-Nueces Bay 138 kV line to service. |  | Gila | Cable Terminal | Under Construction | 791 - 0975 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3581 | 2017-03-31 |  | 138 | 0 | 0.41 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8441, 8470, 8474, 80260 | Y | N |  |  | 6095 | 5542
3268 | AEP_McCampbell: New Substation Cut In | Customer to construct 138kV substation. Two 138kV circuits Cut-In to McCampbell substation. | Planned | Dupont SS | Whitepoint SS | Planned | 561 - 0729 | AEP TCC | Rick McCracken rcmccracken@aep.com 918-599-2698 | 3435 | 2017-04-01 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 80469, 8414, 8422, 8961, 80470 | Y | N |  | This project was previously referred to as 4578. Project 4578 was deleted and replaced by this project 3268. | 3444 | 3268
3992 | Rebuild Dickinson - League City 138 kV line. | Rebuilding Dickinson to League City 138 kV (G138-09). |  | Dickinson Sub | League City Sub | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07215 | 2017-04-01 |  | 138 | 0 | 3.6 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 38850, 38920 | Y |  |  |  | 4318 | 3992
5030C | Flat Top Tie with AEP Pig Creek | Construct IH20 138 kV station. Rebuild line from Barilla Draw Tap-IH20 138 kV bus with 1926 ACSR/TW Cumberland. |  | 38040 | 38060 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-04-01 |  | 138 | 0 | 11.57 | 0 |  | Reeves | Reeves | Tier 3 | 2015-01-13 | 2015-06-19 |  | 38045, 38040, 38060 | Y |  |  | Conductor changed from RPG submittal from 795 ACSR to 1926 ACSR/TW Cumberland. | 5500 | 5030
5683B | Line H Rebuild and 138kV conversion. | Convert Collie Field facilities to 138 kV. Rebuild line from IH20-Collie Tap (38045-38037). De-energize 69 kV line Collie Field Tap-Birds of Prey (38030-38041). Remove temporary 10 MVAR capbank from Collie Field Tap. |  | 38037 | 38045 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-04-01 |  | 138 | 0 | 2.95 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38037, 38038, 38039, 38041, 38042, 38030, 38045 | Y |  |  |  | 6569 | 5683
5430C | Conversion to 138kV | Add new 138kV North Lakes substation and reconstruct 0.72miles of the existing North lakes - Denton North then connect the line to the 138kV Denton North substation and the new 138kV North Lakes substation. Additionally relocate 112MVA 138/69kV auto transformer from Denton North to North Lakes. |  | Denton North | North Lakes | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-04-18 |  | 138 | 0 | 0.75 | 112 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 928, 985, 915 | Y | N | N/A |  | 5946 | 5430
3705 | Solstice: Build 138 kV station | Construct new Solstice station along the Barrilla Junction to Fort Stockton Plant 138 kV line | Cost Update | Solstice |  | Under Construction | 658 - 0827 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 1822 | 2017-04-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60385, 6655, 6680, 60383, 60393, 181652 | Y | N |  |  | 4870 | 3705
4776 | Lyondell Transformer Addition | Add 3rd transformer at Lyondell substation. Tap from Ckt.03 BIGVUE to Channelview |  | Lyondell | BIGVUE/Channelview | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-04-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 41021, 41022, 41023, 40190, 40280, 40281 | Y | N |  |  | 5201 | 4776
4973 | Blewett Substation Addition | Provide transmission service for a new substation to be served off of the T570 Uvalde to Odlaw transmission line. |  | Odlaw | Asphalt Mines | Planned |  | LCRATSC/RGEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015146 | 2017-04-30 |  | 138 | 0 | 0 | 0 |  | Uvalde | Uvalde | Tier 4 |  |  |  | 78424, 7425, 8246 | Y | N |  |  | 5433 | 4973
5140 | Friendswood Generation (13INR0049) Transmission Network | New 138 kV, 3 breaker ring with generator lead. Ckt. 05 WAP to HOC will be relocated FEGC @ HOC bus. | - Overall Cost Update - Overall Date Update | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1140 | 2017-04-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 47156, 47170, 47171, 42041, 44081, 47150 | Y | N |  |  | 5618 | 5140
5551 | CITIES Substation Upgrades | Upgrade substation equipment at CITIES to increase thermal ratings |  | CITIES | WINFRE/JORDAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-04-30 |  | 138 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  | 40340, 40764, 40857 | Y | N |  |  | 6104 | 5551
5929 | Moulton South Circuit Breaker Addition | Add circuit breakers in a breaker and a half arrangement at Moulton South Substation. |  | Moulton South |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2017-04-30 |  | 138 | 0 | 0 | 0 |  | Lavaca |  | Tier 4 |  |  |  | 7237 | Y | N |  |  | 6462 | 5929
6088 | CAPITOL Substation Removal | Remove 138kV CAPITOL substation from CNP transmission service. Remove Ckt.35 CAPITOL to CELNEC from CNP transmission service. Reconnect circuits to create new Ckt.94 HIMONT to BAYWAY. |  | CAPITOL | HIMONT/BAYWAY | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-04-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 42230, 42170, 42260, 42790 | Y | N |  |  | 6638 | 6088
14TPIT0100 | Tilden Capacitor | Add 19.2 MVAR capacitor |  | Tilden |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-05-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | McMullen |  | Tier 4 |  |  |  | 5701 | Y | N |  |  | 2661 | 2555
4501 | Trading Post Circuit Breaker Addition | Install Line Breakers at Trading Post on the Trading Post to Marshall Ford and the Trading Post to Cedar Valley 138kV lines (T315). |  | Trading Post |  | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2017-05-01 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7505 | Y | N |  |  | 4898 | 4501
5713 | Upgrade the Brownwood - Brownwood Sw. | Upgrade the Brownwood - Brownwood Sw. Sta. 138 kV Line |  | Brownwood Sw. Sta. | Brownwood South | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1738 | 2017-05-01 |  | 138 | 0 | 7.4 | 0 |  | Brown | Brown | Tier 4 |  |  |  | 1655, 1656, 1657, 1661 | Y |  |  |  | 6277 | 5713
4873 | Smoky Hill: Build 345 kV station | Interconnect Horse Creek wind farm at Smoky Hill to connect Horse Creek to the Clear Crossing to Edith Clarke 345 kV line |  | Smoky Hill |  | Under Construction | 726 - 0908 | ETT | Rick McCracken mlforcum@aep.com 918-599-2674 | 2909 | 2017-05-01 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  | 6104, 60515, 60701 | Y | N |  |  | 6637 | 4873
5683C | Line H Rebuild and 138kV conversion. | Convert Birds of Prey facilities to 138 kV. Rebuild line from Collie Field Tap-Birds of Prey (38027-38037). De-energize 69 kV line Birds of Prey Tap-Quito Draw Tap (38030-38033). |  | 38027 | 38037 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-05-03 |  | 138 | 0 | 2.25 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38027, 38028, 38029, 38030, 38031, 38032, 38033, 38037 | Y |  |  |  | 6570 | 5683
4523 | McKenzie Draw Switching Station | Construct new switching station |  | McKenzie Draw |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8288 | 2017-05-14 |  | 138 | 0 | 0 | 0 | 0,73.6 | Martin |  | Tier 4 |  |  |  | 11169 | Y | N |  |  | 4920 | 4523
14TPIT0089 | North Main Switch third transmission source | Construct a third 138 kV line into North Main Switch | Construction schedule change | North Main Tap | North Main Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5161-E | 2017-05-15 |  | 138 | 4.4 | 4.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1961, 2158, 2106, 3011 | Y | N |  |  | 3110 | 2941
11TPIT0012 | Euless - Grapevine Ball St - Grapevine Jnct 138 kV Line | Reconductor existing double-circuit 138 kV line (Euless - Grapevine Ball Street east circuit and Euless - Grapevine Junction west circuit) | Construction schedule change | Euless | Grapevine Ball Street/Grapevine Junction | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5131-E | 2017-05-15 |  | 138 | 0 | 11.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2014, 2016, 2021, 12022, 12021, 12040 | Y | N |  | Euless - Highway 360 Substation section by 5/2014 | 3112 | 2943
14TPIT0012 | Mountain Creek - Norwood 138 kV line | Upgrade existing line |  | Mountain Creek | Norwood | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4074-E | 2017-05-15 |  | 138 | 0 | 7.2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2407, 2412, 2805, 12804 | Y | N |  |  | 3263 | 3094
15TPIT0085 | Eagle Mountain - Wagley Robertson - Saginaw 138 kV Line | Upgrade the existing Eagle Mountain - Wagley Robertson line section |  | Eagle Mountain | Wagley Robertson | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5200-E | 2017-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1860, 2075, 2076, 11860, 2082, 12065 | Y | N |  |  | 3382 | 3209
4220 | Screwbean 138 kV capacitors | Install shunt capacitors |  | Screwbean |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8224 | 2017-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Culberson |  | Tier 4 |  |  |  | 1095 | Y | N |  |  | 4590 | 4220
4239 | McKenzie Draw - North Andrews/Lamesa 138 kV Line | Rebuild existing tap line as a double-circuit line |  | McKenzie Draw | Paul Davis Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8220 | 2017-05-15 |  | 138 | 12 | 12 | 0 |  | Dawson | Martin | Tier 4 |  |  |  | 1170, 1168, 1169, 11169, 18880 | Y | N |  |  | 4612 | 4239
4240 | McKenzie Draw - Texaco Mabee 138 kV Line | Construct new line |  | McKenzie Draw | Texaco Mabee | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8213 | 2017-05-15 |  | 138 | 10 | 0 | 0 |  | Martin | Andrews | Tier 4 | 2015-04-01 | 2015-05-22 |  | 11169, 1177 | Y | N |  |  | 4613 | 4240
4263 | Tyler Northwest - Elkton 138 kV Line | Upgrade existing Tyler West - Tyler Northwest 138 kV line Section |  | Tyler West | Tyler Northwest | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6053 | 2017-05-15 |  | 138 | 0 | 3.7 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3139, 3141 | Y | N |  |  | 4636 | 4263
4573 | Briarcrest to Atkins Cable Upgrade | Upgrade Briarcrest to Atkins Cable to match OH capacity |  | 32864 | 32877 | Planned |  | BRYN |  |  | 2017-05-15 |  | 69 | 0.15 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32864, 32877 | Y |  |  |  | 4980 | 4573
4765 | Leon 69 kV Sw Sta | Upgrade switching station |  | Leon Sw. |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1725 | 2017-05-15 |  | 69 | 0 | 0 | 0 |  | Eastland |  | Tier 4 |  |  |  | 1625 | Y | N |  |  | 5188 | 4765
4780 | Cedar Crest Sw. Sta. | Upgrade terminal equipment on Cedar Crest Sw.Sta. - Watermill 138 kV Line |  | Cedar Crest Sw. Sta. |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4209 | 2017-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2493, 2494, 2495 | Y | N |  |  | 5207 | 4780
5230 | Sonne Substation Addition | Provide transmission service for a generator off T554 radial 138-kV line between North McCamey and Tippet Substations. |  | North McCamey | Tippet | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015963 | 2017-05-15 |  | 138 | 0 | 0 | 0 |  | Upton | Pecos | Tier 4 |  |  |  | 76020, 76001, 76595 | Y | N |  |  | 5728 | 5230
5309 | Mitchell Bend - DeCordova 345 kV Line | Upgrade existing line |  | Mitchell Bend | DeCordova | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1734 | 2017-05-15 |  | 345 | 0 | 6 | 0 |  | Hood |  | Tier 4 |  |  |  | 1877, 1890 | Y |  |  |  | 5810 | 5309
5426 | Holt - North Andrews 138 kV Line (Amoco) | Upgrade the Amoco Midland Farms - XTO University line section |  | Amoco Midland Farms | XTO University | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8354 | 2017-05-15 |  | 138 | 0 | 15 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1264, 1265, 1263, 1269, 1281, 1282, 1283 | Y | N |  |  | 5936 | 5426
5486 | Holliday 69 kV Capacitors | Install shunt capacitors |  | Holliday |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4013 | 2017-05-15 |  | 69 | 0 | 0 | 0 | 0,13.8 | Wichita |  | Tier 4 |  |  |  | 1527 | Y | N |  |  | 6049 | 5486
4801 | Wichita Falls Cogen - Bowman 138 kV Line | upgrade existing line |  | Wichita Falls Cogen | Bowman | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4001 | 2017-05-15 |  | 138 | 0 | 0.1 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  | 1496, 1498 | Y | N |  |  | 6084 | 4801
2013 | 138kV Longneck Conversion. Rebuild Climax-Longneck (138kV) | Convert Longneck substation to 138 kV service. Rebuild 4.2 miles of 138kV transmission line (conductor 795 ACSS) from Longneck 138 kV Substation to Climax 138 kV Substation. |  | 37251 | 37260 | Under Construction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-05-15 |  | 138 | 0 | 4.2 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 37250, 37251, 37260, 37280 | Y |  |  |  | 6626 | 2013
4743 | Plano Tennyson - Collin/Northwest Carrollton 138 kV Line | Upgrade the Plano Tennyson - Austin Ranch Junction double-circuit line section | Construction schedule change | Plano Tennyson | Austin Ranch Junction | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M369 | 2017-05-16 |  | 138 | 0 | 8.2 | 0 |  | Collin | Denton | Tier 4 |  |  |  | 676, 678, 2377, 2378, 2523, 2518, 2519, 2568, 2570 | Y | N |  |  | 5163 | 4743
4979 | Upton Circuit Breaker Addition | Install two 138-kV circuit breakers at Upton in a single bus-single breaker configuration. |  | Upton |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015131 | 2017-05-19 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  | 71212, 1212, 71214, 71213 | Y | N |  |  | 5439 | 4979
4710A | Jones Creek Project | Build 345/138 kV Jones Creek Substation. Install first 800MVA autotransformer. | - Overall Cost Update | Jones Creek |  | Planned | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-23 |  | 345 | 0 | 0 | 800 |  | Brazoria |  | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42530, 42540, 49036 | Y | N |  |  | 5122 | 4710
4710B | Jones Creek Project | Install second 800MVA autotransformer at Jones Creek substation. |  | Jones Creek |  | Planned | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-24 |  | 345 | 0 | 0 | 800 |  | Brazoria |  | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 49037, 42530, 42540 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 5123 | 4710
4710C | Jones Creek Project | Loop 345kV Ckt.18 into Jones Creek Substation |  | Jones Creek | DOW/STP | Planned | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-25 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 5915, 42500, 42530 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 5124 | 4710
3507 | Nopal Substation | Build a new 138-26.18 kV 18/24/30 MVA substation to be served by Gillett to Nopal 138 kV transmission line |  | Nopal |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-05-26 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7233 | Y | N |  |  | 3714 | 3507
4710D | Jones Creek Project | Loop 138kV circuits 02, 48, and 59 into Jones Creek Substation |  | Jones Creek | Velasco/Freeport | Planned | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-26 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42540, 42645, 43360 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 5125 | 4710
3509 | Gillett Sub (LCRA) to Nopal Sub 138 kV Transmission Line | Add 138 Terminal at LCRA Gillett Station; Build approx 9 miles of single ckt 138 kV t-line, 795 ACSR |  | Gillett | Nopal | Planned | 15TPIT0063 | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-05-27 |  | 138 | 8.5 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  | 7233, 78582 | Y | N |  |  | 3716 | 3509
3938A | Angleton Area Ckt.26 & 82 Upgrades | Upgrade 138kV Ckt.26 Angleton to STRATT to increase thermal ratings. | - Overall change in schedule | Angleton | STRATT | Under Construction |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2017-05-27 |  | 138 | 0 | 13.8 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 42110, 43300 | Y | N |  |  | 4249 | 3938
4710E | Jones Creek Project | Reconfigure Freeport area circuits to create a loop with Ckt.59 from Velasco to Surfside to Freeport to Jones Creek and Ckt.02 Jones Creek to Velasco. |  | Velasco | Surfside/Freeport/Jones Creek/Velasco | Planned | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-27 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42645, 43155, 43315, 43360 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 5126 | 4710
3938B | Angleton Area Ckt.26 & 82 Upgrades | Upgrade 138kV Ckt.26 STRATT to SINTEK to increase thermal ratings. | - Overall change in schedule | STRATT | SINTEK | Under Construction |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2017-05-28 |  | 138 | 0 | 6.4 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43240, 43300 | Y | N |  | Cost Included in TPIT Project 3938A | 4250 | 3938
4710F | Jones Creek Project | Reconfigure Freeport area circuits to create a Ckt.48 circuit from Velasco to MARINE to CORTEZ to Quintana to Jones Creek. |  | Jones Creek | MARINE/CORTEZ/Quintana/Jones Creek | Planned | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-28 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42540, 42645, 43155, 43435, 43315, 43360 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 5127 | 4710
3682A | Katy Area Upgrades | Convert Franz Substation to loop service from 138kV Ckt.09. Install new conductor and reconfigure/upgrade existing lines to create new Ckt.09 Zenith to Franz to Katy to Flewellen. | - Overall Cost Update | Zenith | Katy | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 860 | 2017-05-29 |  | 138 | 6.4 | 1.6 | 0 |  | Harris | Waller | Tier 2 | 2013-12-18 | 2014-05-15 |  | 44260, 44261, 44262, 44230, 44256, 44422, 44500, 45675, 44420, 44421, 44900, 44910, 45770, 46220 | Y | N |  |  | 3921 | 3682
3938C | Angleton Area Ckt.26 & 82 Upgrades | Upgrade 138kV Ckt.82 Angleton to Richwood to increase thermal ratings. | - Overall change in schedule | Angleton | Richwood | Under Construction |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2017-05-29 |  | 138 | 0 | 14.2 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 42110, 43150 | Y | N |  | Cost Included in TPIT Project 3938A | 4251 | 3938
3682B | Katy Area Upgrades | Convert Katy substation ckt 09 tap to loop service to modify Ckt.09 Flewellen to Katy to Franz. |  | Katy |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 860 | 2017-05-30 |  | 138 | 0 | 0 | 0 |  | Waller |  | Tier 2 | 2013-12-18 | 2014-05-15 |  | 44420, 44421, 44422, 44230, 45770 | Y | N |  | Cost included in project 17TPIT3682A. | 3922 | 3682
3938D | Angleton Area Ckt.26 & 82 Upgrades | Upgrade 138kV Ckt.82 Richwood to Cavern to increase thermal ratings. | - Overall change in schedule | Richwood | Cavern | Under Construction |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2017-05-30 |  | 138 | 0 | 5.4 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43150, 43330 | Y | N |  | Cost Included in TPIT Project 3938A | 4252 | 3938
4458 | Altair to Glidden Transmission Line Overhaul | Upgrade the 12.2 mile Altair (78106) - Stafford Hill (78520) - Columbus (78111) - Glidden (78107) 69-kV transmission line to 795 ACSR Drake (111 MVA), 138-kV capable with OPGE shield wire. |  | Altair | Glidden | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1011917 | 2017-05-30 |  | 69 | 0 | 12.2 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  | 78106, 78107, 78111, 78520 | Y | N |  |  | 4843 | 4458
4703A | Bellaire to San Felipe Ckt.09 | Reconductor Ckt.09 Bellaire to San Felipe and upgrade substation equipment to increase thermal ratings. | Accelerated Project Schedule | Bellaire | San Felipe | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1132 | 2017-05-30 |  | 138 | 0 | 2 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47010, 47380 | Y | N |  |  | 5115 | 4703
4707 | Velasco Cap Bank #1 | Install capacitor bank #1 at Velasco substation (120MVAR). |  | Velasco |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-30 |  | 138 | 0 | 0 | 0 | 0,120 | Brazoria |  | Tier 4 |  |  |  | 43361, 43360, 42190 | Y | N |  |  | 5119 | 4707
4710H | Jones Creek Project | De-energize a portion of existing Ckt.02 Velasco to Franklins Camp and reconfigure create new Ckt.02 Jones Creek to Franklins Camp. |  | Jones Creek | Franklins Camp | Planned | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-05-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 43211, 43212, 43220, 43221, 43222, 48006, 42195, 42215, 42540, 43360 | Y | N |  | Cost included in PhaseA (4710A) of the Project | 5129 | 4710
5715A | Red Bluff - 138kV Substation | Install temporary service for Red Bluff 138kV substation. Tap from Ckt.79 SEPTON to BAYWAY. |  | Red Bluff | SEPTON/BAYWAY | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42931, 42170, 43225 | Y | N |  |  | 6279 | 5715
14TPIT0061 | Briarcrest to Atkins Upgrade | Upgrade to 795 ACSR to alleviate overload during double contingency situations. Add OPGW. Add new poles/structures. |  | Atkins | Briarcrest | Planned |  | BRYN |  |  | 2017-05-31 |  | 138 | 0 | 3.4 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32864, 32877 | Y |  |  |  | 2052 | 2001
15TPIT0057 | Wylie 138 kV new switchyard and connections | Wylie 138 kV switchyard and its connections to Olinger, to Firewheel, to Elm Grove, and to Nevada | On Hold For Funding | New switches at Wylie | Switches at Olinger, at Friewheel, at Elm Grove, and at Nevada | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2017-05-31 |  | 138 | 0 | 36.75 | 0 |  | Collin | Dallas | Tier 4 |  |  |  | 833, 811, 818, 821, 855 | Y | N |  |  | 2750 | 2629
3682C | Katy Area Upgrades | Install a second 800MVA autotransformer at Zenith Substation. |  | Zenith |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 860 | 2017-05-31 |  | 345 | 0 | 0 | 800 |  | Harris |  | Tier 2 | 2013-12-18 | 2014-05-15 |  | 49090, 44230, 44256, 44422, 44500, 45675, 44900, 45770, 46220, 44910 | Y | N |  | Cost included in project 17TPIT3682A. | 3923 | 3682
14TPIT0067 | Red Creek: Replace one of the 345/138 kV autotransformers | Replace both 345/138 kV autotransformers at Red Creek with 480 MVA autotransformers |  | Red Creek |  | Under Construction | 566 - 0740 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2570 | 2017-05-31 |  | 345 | 0 | 0 | 480 |  | Tom Green |  | Tier 4 |  |  |  | 6295, 6444, 6442 | Y | N |  |  | 4185 | 1824
3681 | TH Wharton to Addicks Ckt.71 Sub Upgrade | Upgrade substation equipment at TH Wharton and Addicks to increase thermal ratings for 345kV Ckt.71. | Delay in Project Schedule | TH Wharton | Addicks | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1111 | 2017-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45500, 45600 | Y | N |  |  | 4268 | 3681
4446 | Luling to Nixon Transmission Line Overhaul | Upgrade the 15.62 mile Luling (7223) - Malone - Darst Creek - Deer Creek (7597) 69kV transmission line to 795 ACSR Drake, 138kV capable with OPGW shield wire. The updated rating will be 44 MVA at 69kV. |  | Luling | Deer Creek | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1012406 | 2017-05-31 |  | 69 | 0 | 15.62 | 0 |  | Caldwell | Guadalupe | Tier 4 | 2015-02-18 | 2015-03-23 |  | 7223, 7597, 78195, 78579 | Y | N |  |  | 4834 | 4446
4492 | Marconi: Build new three breaker 138 kV station | Interconnect San Roman Windfarm at Marconi to connect San Roman to the Port Isabel to Laureles 138 kV line by building new 138 kV line from Marconi to San Roman with 959.6 ACSS/TW |  | Marconi | San Roman | Planned | 712 - 0883 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 2906 | 2017-05-31 |  | 138 | 0.6 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8262, 8266, 5756, 8338, 161601 | Y | N |  |  | 4886 | 4492
4516 | City of Brady to North Brady: Reterminate 69 kV line | Rebuild the 69 kV line from the City of Brady Tap to North Brady double circuit to allow retermination of the City of Brady Tap line into North Brady station with the addition of a breaker | Project Description and Schedule Update | City of Brady | North Brady | Under Construction | 715 - 0881 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2813 | 2017-05-31 |  | 69 | 0 | 0.8 | 0 |  | McCulloch | McCulloch | Tier 4 |  |  |  | 6006, 6382, 6383 | Y | N |  |  | 4913 | 4516
4708 | Meadow: Install 600MVA Autotransformer A2 | Install 600MVA autotransformer A2 at Meadow (from PH Robinson substation) | Delay in Project Schedule | Meadow |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1116 | 2017-05-31 |  | 345 | 0 | 0 | 600 |  | Brazoria |  | Tier 4 |  |  |  | 43031, 43032, 49051, 39015, 43030 | Y | N |  |  | 5120 | 4708
4858 | Hendrick: Build 138 kV station | Interconnect Alamo 7 solar farm at Hendrick to connect Alamo 7 to the Abilene Northwest to Paint Creek 138 kV line | Schedule Update | Hendrick |  | Under Construction | 721 - 0903 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2613 | 2017-05-31 |  | 138 | 0.9 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  | 60387, 6169, 6228 | Y | N |  |  | 5286 | 4858
4950 | Oyster Creek 138kV Substation - GINR - 16INR0003 | Loop new 138kV Oyster Creek substation from Ckt.82 Velasco to BIPORT. Install 40MVAr cap bank at Oyster Creek. | - Overall Cost Update - Overall Date Update - Updated for cap bank | Oyster Creek | Velasco/BIPORT | Planned | 4710 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 932 | 2017-05-31 |  | 138 | 0 | 0 | 0 | 0,40 | Brazoria |  | Tier 4 |  |  |  | 43335, 43336, 42190, 43360, 43361 | Y | N |  |  | 5408 | 4950
4995 | Sandy Point 138kV Distribution Substation | Build new 138kV Sandy Point distribution substation. Loop through Ckt.96 ALKANE to LaPorte. | - Overall Cost Update | Sandy Point | ALKANE/LaPorte | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 954 | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40090, 40160, 40941 | Y |  |  |  | 5453 | 4995
5055 | Maxwell Tap: Build new 138 kV temporary tap | Interconnect Val Verde Wind Farm temporarily at Maxwell Tap via Fermi Collector station |  | Maxwell Tap |  | Under Construction | 735-0917 | AEP TCC | Rick McCracken dnlyons@aep.com 918-599-2698 | 3567 | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  | 88998, 8257, 8261 | Y | N |  |  | 5530 | 5055
5266 | Cuero - Luling Transmission Line Overhaul | Rebuild T542 Luling to Hocheim Tap from Luling to vicinity of Harwood to be 138-kV capable with a nominal conductor rating of 223 MVA at 138-kV (Single Drake) with OPGW and operated at 69-kV. |  | Hocheim | Luling | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016221 | 2017-05-31 |  | 69 | 0 | 10 | 0 |  | DeWitt | Gonzales | Tier 4 |  |  |  | 7223, 78577 | Y | N |  |  | 5767 | 5266
5283 | Starcke Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Starcke. |  | Starcke |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016206 | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Burnet |  | Tier 4 |  |  |  | 7351 | Y | N |  |  | 5784 | 5283
5284 | Tahitian Village Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Tahitian Village Substation. |  | Tahitian Village |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016212 | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  | 7575 | Y | N |  |  | 5785 | 5284
5410 | Sierra Vista: Add 2nd Dist Bank | Add 2nd distribution bank and string circuit between Sierra Vista and Sierra Vista Tap |  | Sierra Vista | Sierra Vista Tap | Planned | 785 - 0970 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 3578 | 2017-05-31 |  | 138 | 1.75 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 8922, 88641, 8295, 8641, 80230 | Y | N |  |  | 5922 | 5410
5550 | Jeanetta to WA Parish Ckt.64 & 72 Upgrades | Upgrade substation equipment at Jeanetta to WA Parish Ckt.64 and upgrade Ckts. 64 & 72 to increase thermal ratings |  | Jeanetta | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-05-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 44005, 47300 | Y | N |  |  | 6103 | 5550
5714 | WAP-Bellaire Ckt50 Substation Equip Upgrade | Upgrade substation equipment at Bellaire and WA Parish to increase Ckt.50 thermal ratings |  | Bellaire | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44005, 47000 | Y | N |  |  | 6278 | 5714
5553A | Village Creek 138kV Substation | Install temporary service for Village Creek (Mobile) 138kV substation. Tap from Ckt.09 Zenith to Franz. |  | Village Creek (Mobile) | Zenith/Franz | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44271, 44260, 44910 | Y | N |  |  | 6474 | 5553
09TPIT0037 | Blossom - New 138 kV Substation | Loop new 138 kV substation into the existing 138kV Harmony Hills to Skyline line | Delayed due to budget constraint | Blossom | Harmony Hills-Skyline | Planned | T-0178 | CPS | Ulrich Skerhut UKSkerhut@cpsenergy.com 210-353-2923 | S-0602 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5022, 5195, 5368 | Y | N |  | There are no transformers associated with this project | 950 | 949
14TPIT0041 | Coliseum_to_Holbrook_Rebuild_&_Reconfiguration | Rebuild 2.8 miles of 138 kV transmission line from Coliseum to Holbrook and ensure a minimum conductor rating of 331 MVA |  | Colesium | Holbrook | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0164 | 2017-06-01 |  | 138 | 0 | 2.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5095, 5160, 5218, 5250, 5420 | Y | N |  | There are no transformers associated with this project | 956 | 955
16TPIT0010 | Bulverde - New 138kV Substation | Loop new 138kV substation into the existing Green Mountain to Stonegate transmission line |  | Green Mountain | Stonegate | Planned | T-0189 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0665 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5051, 5180, 5415 | Y | N |  | There are no transformers associated with this project | 972 | 971
16TPIT0009 | Five Points to Westside - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from Five Points to Westside to be upgraded to 326 MVA, minimum |  | Five Points | Westside | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0195 | 2017-06-01 |  | 138 | 0 | 3.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5150, 5490 | Y | N |  | There are no transformers associated with this project | 974 | 973
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2017-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9077, 9238 | Y | N |  | Will add the ptoject to the base case. | 1032 | 1031
11TPIT0084 | Hidden Lakes - New Substation | Build a new 138-12.47 kV substation to accommodate new subdivision growth along the FM 517 and FM 646 corridors in Dickinson, Texas |  | Leave blank | Leave blank | Planned |  | TNMP | Anthony Hudson Anthony.Hudson@tnmp.com. 281-581-4712 | STE02416 | 2017-06-01 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38900, 38890, 42015 | Y | N |  |  | 1264 | 1261
3819 | Rebuild San Miguel Tap to North Calliham | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. Not Rebuild 336 ACSR portion from San Miguel to San Miguel Tap. |  | Sam Miguel | North Calliham | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-06-01 |  | 69 | 0 | 17.5 | 0 |  | Atascosa | McMullen | Tier 4 |  |  |  | 5693, 5698 | Y | N |  | Not Rebuild 336 ACSR portion from San Miguel to San Miguel Tap. | 4101 | 3819
5031 | Install 30 MVar Cap Bank at Barilla Draw Tap | Changed Capbank from 80 to 30 MVAR. TNMP is planning to pursue additional 50-60 MVAR capacitive reactance via SVC when Transient Switching study completed. |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-06-01 |  | 138 | 0 | 0 | 0 | 0,30 |  |  | Tier 4 |  |  |  | 38065 | Y |  |  |  | 5501 | 5031
3636 | Welsh HVDC: Upgrade Station Svc and Install New Filter | Welsh HVDC Tie: Phase 2 Station Upgrades | PM, PVID, Prj Desc, In-Service Changes | WELSH HVDC Tie |  | Planned | 625 - 0793 | AEP TCC | Tommy Vannoy dnlyons@aep.com 918-599-2698 | 3568 | 2017-06-30 |  | 345 | 0 | 0 | 0 | 100100 | Titus |  | Tier 4 |  |  |  | 5925 | Y | Y |  |  | 3866 | 3636
3761 | Victoria to Fannin: 69 kV Transmission Line Rebuild | Rebuild Victoria to Fannin 69 kV line | Add Super project, and transmission status, ISD | VICTORIA | FANNIN | Under Construction | 662-0831 | AEP TCC | Rick McCracken dnlyons@aep.com 918-599-2698 | 3527 | 2017-06-30 |  | 69 |  | 13.5 |  |  | Victoria | Victoria | Tier 4 |  |  |  | 5736, 8169 | Y | N |  |  | 4006 | 3761
4200 | Sage: Build 69 kV station | Construct new 69 kV in and out substation off the Crane loop, and demolish Crane Gulf #1 | Schedule and Cost Update | Sage |  | Under Construction | 697 - 0867 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2266 | 2017-06-30 |  | 69 | 0 | 0 | 0 |  | Crane |  | Tier 4 |  |  |  | 6604, 6608 | Y | N |  |  | 4556 | 4200
4496 | AEP_4496_Las Pulgas | Loop STEC radial 138kV Raymondville #2 to East Raymondville line into Las Pulgas. |  | Las Pulgas |  | Planned | 615 - 3446 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 516 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Willacy |  | Tier 4 |  |  |  | 80309 | Y | N |  |  | 4890 | 4496
15TPIT0083B | Collin - Arco (TMPA) 138 kV Line (Oncor's section) | Add second circuit to existing line from Krugerville to Arco (TMPA) |  | Krugerville | Arco (TMPA) | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R929 | 2017-06-30 |  | 138 | 5.7 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | Y | N |  |  | 4926 | 3216
4538 | Add new 138kV line from Tall City to Glass Ranch |  |  | Tall City | Glass Ranch | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2017-06-30 |  | 138 | 10 | 0 | 0 |  | Midland | Martin | Tier 2 |  |  |  | 79507, 79558 | Y | N |  |  | 4940 | 4538
4711A | CORTEZ 138kV Substation | Construct service to new 138kV CORTEZ customer-owned substation. As part of the project, Quintana substation will be disconnected from direct CNP service, and will be served through CORTEZ substation. CORTEZ will loop through Ckt.48 MARINE to Jones Creek. | Delay in project schedule | CORTEZ | MARINE/Quintana | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 55 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43435, 43440, 42540, 43155 | Y | N |  |  | 5130 | 4711
4962 | Adding second 345/138 kV auto at Vealmoor station |  |  | Vealmoor 345 | Vealmoor 138 | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2017-06-30 |  | 345 | 0 | 0 | 708 |  | Borden | Borden | Tier 4 |  |  |  | 79602, 79640, 79600 | Y | N |  |  | 5420 | 4962
5042 | BRYN_5042_BRYN_TAMU_Enterprise | Build and Loop in New TAMU Enterprise Substation |  |  |  | Planned |  | BRYN |  |  | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32790, 32005, 32799 | Y |  |  |  | 5516 | 5042
4493 | Pharr 138 kV Loop | McColl Road & North McAllen to Pharr: Reroute 138 kV Line |  | MCCOLL ROAD & NORTH MCALLEN | PHARR | Under Construction | 704-0874 | AEP TCC | William Clarke dnlyons@aep.com 918-599-2698 | 3548 | 2017-06-30 |  | 138 | 2.2 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8368, 8372, 8908 | Y | N |  |  | 5552 | 4493
3848 | Derrick to Powell Field: Rebuild 69 kV line | Rebuild Derrick to Powell Field 69 kV line | Project Description, Schedule and Cost Update | Derrick | Powell Field | Under Construction | 670 - 0839 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2806 | 2017-06-30 |  | 69 | 0 | 6.8 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  | 6540, 60396, 6539, 6544, 6545 | Y | N |  |  | 5638 | 3848
5268 | MLSE Upgrade: T231 Austrop to Bastrop City | Upgrade terminal equipment at Austrop and Bastrop City for a static normal and emergency rating of 221 MVA. |  | Austrop | Bastrop City | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016216 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Travis | Bastrop | Tier 4 |  |  |  | 7322, 7329, 9328 | Y | N |  |  | 5769 | 5268
5269 | MLSE Upgrade: T147 Gilleland Creek to McNeil | Upgrade terminal equipment at Gilleland Creek and McNeil for a static normal and emergency rating of 493 MVA. |  | Gilleland Creek | McNeil | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016216 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 7334, 7336 | Y | N |  |  | 5770 | 5269
5279 | Chappell Hill Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Chappell Hill. |  | Chappel Hill |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016181 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Washington |  | Tier 4 |  |  |  | 7574 | Y | N |  |  | 5780 | 5279
5280 | Georgetown South Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Georgetown South. |  | Georgetown South |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016215 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  | 7532 | Y | N |  |  | 5781 | 5280
5282 | Shadow Glen Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Shadow Glen. |  | Shadow Glen |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016205 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7323 | Y | N |  |  | 5783 | 5282
5640 | Addition of motorized switch at Bringhurst | Addition of motorized switch at Bringhurst |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-06-30 |  | 0 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 47540 | Y | N |  |  | 6198 | 5640
6076 | Joslin: Add 138 kV breaker terminal for WF interconnect | Interconnect Point Comfor Gas Turbine at Joslin and construct a 138 kV breaker terminal |  | Joslin |  | Under Construction | 862-1040 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2698 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | Y | N |  |  | 6624 | 6076
10TPIT0148 | Las Pulgas Tap - Renamed from Willacy Tap Switch 138kV | Move normally open 138kV connection to the AEP Raymondville #2 bus and add breakers at Las Pulgas to serve E Raymondville and La Sara from Las Pulgas. |  | Las Pulgas |  | Planned | 12TPIT0103 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-07-01 |  | 138 | 0 | 0 | 0 |  | Willacy | Willacy | Tier 4 |  |  |  | 5745, 5790, 80309 | Y | N |  |  | 2407 | 2330
4537 | Add new line to connect Rocky Rd to Coates station (new) |  |  | Rocky Rd | Coates | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2017-07-01 |  | 138 | 7 | 0 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 79563, 79614 | Y | N |  |  | 4939 | 4537
4584 | Addition of 2nd circuit on Pemkiff - Midkiff line |  |  | Pemkiff | Midkiff | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2017-07-01 |  | 138 | 0.3 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  | 1210, 79555 | Y | N |  |  | 4992 | 4584
4969 | Pomelo: Build new four breaker 345 kV station | Interconnect Hidalgo Windfarm at Pomelo to connect Hidalgo to the Del Sol to North Edinburg 345 kV line |  | Del Sol | North Edinburg | Under Construction | 733 - 0915 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3564 | 2017-07-01 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 8574, 88574, 8383, 80355, 161705 | Y |  |  |  | 5429 | 4969
5231 | Schneeman Draw Substation Addition | Provide transmission service for a generator off T21421 345-kV STEC line between Big Hill and Bakersfield Substations. |  | Big Hill | Bakersfield | Planned |  | LCRATSC/STEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015884 | 2017-07-01 |  | 345 | 0 | 0 | 0 |  | Schleicher | Pecos | Tier 4 |  |  |  | 76005, 76002, 76003 | Y | N |  |  | 5729 | 5231
5428D | Phase 2 of the conversion to 138kV | Line will be reconfigured to through a 3way tie |  | Woodrow | Spencer Int | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 921, 982 | Y | N | N/A |  | 5941 | 5428
5429A | Phase 3 of the conversion to 138kV | Add a new 138kV line from the new Locust station to Woodrow to Spencer Interchange via a three way tie at Woodrow. The section going from the 3way tie to Spencer Int. was added in phase 2. |  | Locust | Spencer Int. | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-07-01 |  | 138 | 1.917 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 924, 99999, 921, 982 | Y | N | N/A |  | 5942 | 5429
5429B | Phase 3 of the conversion to 138kV | Retire the existing 69kV line from the existing 69kV locust substation to Spencer Switch |  | Locust | Spencer Switch | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 904, 914 | Y | N | N/A |  | 5943 | 5429
3911 | Hecker 138kV Substation Expansion: Cheniere LNG Project | Hecker 138kV Substation Expansion: Cheniere LNG Project |  | Hecker |  | Planned | 616 - 0784 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3534 | 2017-07-31 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8568, 8565, 8961, 80470 | Y | N |  |  | 4209 | 3911
4606 | Moulton South 138/69-kV Autotransformer Addition | Add Moulton South Substation 138/69-kV Autotransformer |  | Moulton South |  | Planned | 5929 | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-07-31 |  | 138 | 0 | 0 | 45 |  | Lavaca |  | Tier 4 |  |  |  | 7587, 77587, 7586, 7588, 7237 | Y | N |  |  | 6249 | 4606
3418 | Nelson Sharpe: Add 345 kV Terminal for WF Interconnect | Add a new 345 kV line terminal at Nelson Sharpe for the Patriot WF Interconnect |  | Nelson Sharpe |  | Under Construction | 515 - 0756 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3474 | 2017-08-31 |  | 345 | 0 | 0 | 0 |  | Kleberg |  | Tier 4 |  |  |  | 85000 | Y | N |  |  | 3618 | 3418
15TPIT0055 | Naval Base Station: Add 138/69 kV Auto | Construct new 138 kV line and add tranformation at Naval Base to remove contingency overloads during off-peak maintenance |  | NAVAL BASE |  | Under Construction | 607 - 0648 | AEP TCC | Terry Weeks DNLYONS@AEP.COM 918-599-2698 | 3485 | 2017-08-31 |  | 138 |  |  | 220 |  | Nueces |  | Tier 1 | 2012-07-15 | 2012-12-20 | 2013-01-04 | 8997, 8495 | Y | N |  |  | 3721 | 3514
15TPIT0054 | Barney Davis To Naval Base Construct 138 kV line | Construct new 138 kV line and add tranformation at Naval Base to remove contingency overloads during off-peak maintenance |  | BARNEY DAVIS | NAVAL BASE | Under Construction | 607 - 0648 | ETT | JOHN PULAY DNLYONS@AEP.COM 918-599-2698 | 3484 | 2017-08-31 |  | 138 | 7 |  |  |  | Nueces | Nueces | Tier 1 | 2013-07-15 | 2013-12-20 | 2013-01-24 | 8458, 8997 | Y | N |  |  | 3726 | 3519
5281 | Mason (CTEC) Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Mason (CTEC). |  | Mason (CTEC) |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016196 | 2017-08-31 |  | 138 | 0 | 0 | 0 |  | Mason |  | Tier 4 |  |  |  | 7395 | Y | N |  |  | 5782 | 5281
4574 | Briarcrest to Nall Cable Upgrade | Upgrade Briarcrest to Nall Cable to match OH section |  | 32877 | 32872 | Planned |  | BRYN |  |  | 2017-09-01 |  | 69 | 0 | 0.5 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32872, 32877 | Y |  |  |  | 4981 | 4574
5270 | Twin Buttes Autotransformer Addition | Replace the existing Twin Buttes AT1 autotransformer with a new 345/138-kV 672 MVA autotransformer. Remove the existing 36 MVAR Twin Buttes AT1 tertiary reactor. Install a new 345-kV 50 MVAR reactor at Divide Substation |  | Twin Buttes |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016213 | 2017-09-01 |  | 345 | 0 | 0 | 672 | 50,0 | Tom Green |  | Tier 4 |  |  |  | 77281, 76009, 76011, 76090 | Y | N |  |  | 5771 | 5270
5947 | Radial Autotransformer Redundancy Substation Upgrade | Install a second 138/69-kV autotransformer at Mason CTEC. |  | Mason (CTEC) |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016201 | 2017-09-01 |  | 69 | 0 | 0 | 44.8 |  | Mason |  | Tier 4 |  |  |  | 7395, 76389 | Y | N |  |  | 6483 | 5947
5030D | Flat Top Tie with AEP Pig Creek | Install IH20 138/69 kV Auto. |  | 38040 | 38045 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-09-01 |  | 138 | 0 | 0 | 150 |  | Reeves | Reeves | Tier 3 | 2015-01-13 | 2015-06-19 |  | 38040, 38045 | Y |  |  |  | 6537 | 5030
6045 | Mainland Substation | Updated Associated TPIT project TNMP_15TPIT0030_Mainland_NewSubstation (Project ID# 2025). |  | Mainland |  | Under Construction | 2025 | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-09-01 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38830, 38820, 39030 | Y | N |  |  | 6589 | 6045
5177 | Tesla: Add 345 kV reactor | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley |  | Tesla |  | Under Construction | 754 - 0937 | ETT | Steve Stein mlforcum@aep.com 918-599-2674 | 2624 | 2017-09-02 |  | 345 | 0 | 0 | 0 | -100,0 | Wilbarger |  | Tier 4 |  |  |  | 60501 | Y | N |  |  | 5661 | 5177
15TPIT0067 | Tuleta 138 kV Station: Construct a new station | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. |  | TULETA |  | In-Service | 603-0765 | AEP TCC | Eric Scott DNLYONS@AEP.COM 918-599-2698 | 3552 | 2017-09-29 |  | 138 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  | 8590, 88590, 8592, 8593 | Y | N |  | NA | 3689 | 3482
5201 | Magill 138 kV Station: Install 28.8 MVAR Cap Bank | Install a 28.8 MVAR Cap Bank at Magill 138 kV station |  | Magill |  | Under Construction | 766-0951 | AEP TCC | Mark Strabala dnlyons@aep.com 918-599-2698 | 3574 | 2017-09-29 |  | 138 | 0 | 0 | 0 | 28.8,0 | Matagorda |  | Tier 4 |  |  |  | 8111 | Y | N |  |  | 5685 | 5201
5019 | Pig Creek: Build 138 kV station | Construct new 138 kV ring bus on the Barrilla Junction to Permian Basin Line |  | Pig Creek |  | Under Construction | 737 - 0920 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2618 | 2017-09-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | Y | N |  |  | 5477 | 5019
5076 | Smoky Hill: Build 345 kV terminal | Interconnect Willow Springs wind farm at Smoky Hill to connect Willow Springs to the Clear Crossing to Edith Clarke 345 kV line | Schedule Update | Smoky Hill |  | Under Construction | 734 - 0916 | ETT | Rick McCracken mlforcum@aep.com 918-599-2674 | 2614 | 2017-09-30 |  | 345 |  |  |  |  | Haskell |  | Tier 4 |  |  |  | 6104 | Y | N |  |  | 5556 | 5076
5278 | Arco Tap Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Arco Tap. |  | Arco Tap |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016176 | 2017-09-30 |  | 138 | 0 | 0 | 0 |  | Crane |  | Tier 4 |  |  |  | 1199, 71199, 1201, 71230, 76615 | Y | N |  |  | 5779 | 5278
3963 | Lockhart to Luling Transmission Line Upgrade | Upgrade the 16.9 miles Lockhart to Luling City 138kV line from existing 136 MVA to 221 MVA. Replace existing 45 MVA auto with 70 MVA auto. Upgrade both Lockhart and Luling to breaker and a half configuration. |  | Lockhart | Luling | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014350 | 2017-10-01 |  | 138 | 0 | 16.9 | 70 |  | Caldwell | Caldwell | Tier 4 |  |  |  | 7216, 7224, 7215 | Y | N |  |  | 4284 | 3963
5232 | Castillo Substation Addition | Provide transmission service for a generator off T4521 138-kV line between North McCamey and LCRA Crane Substations. |  | North McCamey | LCRA Crane | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015822 | 2017-10-01 |  | 138 | 1.64 | 0 | 0 |  | Upton | Crane | Tier 4 |  |  |  | 76040, 76032, 76615 | Y | N |  |  | 5730 | 5232
6087 | Flat Top 345 kV Switching Station | Flat Top 345 kV Switching Station |  | Comanche | Brown | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1740 | 2017-10-15 |  | 345 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  | 11441, 1440, 1444 | Y | N |  |  | 6636 | 6087
5081 | Bronco: Build 69 kV station | Interconnect Solaire Holman solar farm at Bronco to connect Solaire Holman to the Alpine to Fort Stockton Plant 69 kV line | Cost Update | Bronco |  | Under Construction | 740 - 0923 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2621 | 2017-10-22 |  | 69 |  |  |  |  | Brewster |  | Tier 4 |  |  |  | 6674 | Y | N |  |  | 5561 | 5081
4997B | Deepwater Area Conversions | Convert CHANEL sub to 138kV service. Loop from Ckt.70 BRANUM to LYDELL. |  | CHANEL | BRANUM/LYDELL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 986 | 2017-10-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 40275, 40270, 41009, 40640 | Y | N |  |  | 5720 | 4997
3683 | Abilene South to Sawgrass: Rebuild 69 kV line | Rebuild Abilene South to Sawgrass 69 kV line | Project Description and Schedule Update | Abilene South | Sawgrass | Under Construction | 651 - 0820 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 1815 | 2017-10-31 |  | 69 |  | 2.15 |  |  | Taylor | Taylor | Tier 4 |  |  |  | 6284, 60394, 6283, 6285, 6636 | Y | N |  |  | 5629 | 3683
4997D | Deepwater Area Conversions | Remove CHANEL 69kV Service |  | CHANEL | Harris/Deepwater | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 986 | 2017-10-31 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 40270, 40470, 40800 | Y | N |  |  | 6319 | 4997
6093 | CHAMON 138 kV Sub - Gen Interconnection-17INR0042 Castleman | Install two new generator leads for new Castleman Power generator interconnection. Connect to existing CHAMON 138kV customer-owned substation. Expand CHAMON substation to 4-breaker ring bus. |  | Castleman Power | CHAMON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | Y | N |  |  | 6643 | 6093
4459 | Goldthwaite to Lampasas Transmission Line Upgrade | Convert the 18.2 mile Goldthwaite (7073) - San Saba (7078) 69-kV to 795 ACSR Drake 138-kV (223 MVA) and Convert the 33.3 mile San Saba (7078) - Lometa (7080) - Lampasas (7082) 69-kV to 795 ACSR Drake 138-kV (223 MVA). |  | Goldthwaite | Lampasas | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014204 | 2017-11-01 |  | 138 | 0 | 51.5 | 0 |  | Mills | Lampasas | Tier 4 | 2014-11-11 | 2015-06-25 |  | 7064, 7070 | Y | N |  |  | 4844 | 4459
5235 | Bakersfield Reactor Bank Addition(s) | Add two (2) 50 MVAR reactor banks at Bakersfield Substation |  | Bakersfield |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016061 | 2017-11-01 |  | 345 | 0 | 0 | 0 | 0,-100 | Pecos |  | Tier 4 |  |  |  | 76002 | Y | N |  |  | 5733 | 5235
5683D | Line H Rebuild and 138kV conversion. | Convert Worsham and Quito Draw facilities to 138 kV. Rebuild line from Worsham-Birds of Prey Tap (38021-38027). De-energize 69 kV line Pyote-Worsham (38000-38020). |  | 38021 | 38027 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-11-01 |  | 138 | 0 | 5.84 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38020, 38021, 38025, 38026, 38033, 38034, 38035, 38000, 38027 | Y |  |  |  | 6571 | 5683
4960 | Adding Nat Dam to Sales 17 miles 138 kV line |  |  | Sales Ranch | Natural Dam | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2017-11-10 |  | 138 | 17 | 0 | 0 |  | Martin | Howard | Tier 4 | 2015-06-29 | 2015-07-29 |  | 79508, 79509 | Y | N |  |  | 5418 | 4960
4970 | Magic Valley Tap: Build new 345 kV temporary tap | Interconnect Magic Valley II Windfarm at temporary tap to connect Magic Valley II to the Ajo to Rio Hondo 345 kV line |  | Ajo | Rio Hondo | Under Construction | 731 - 0912 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3561 | 2017-11-30 |  | 345 | 0 | 0 | 0 |  | Willacy |  | Tier 4 |  |  |  | 80512, 8902, 80076 | Y |  |  |  | 5430 | 4970
5764 | Obrien to WA Parish Ckts.98 & 99 | Increase thermal ratings of Ckst.98 & 99 Obrien to WA Parish by installing shunts on line and upgrading substation equipment |  | Obrien | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-11-30 |  | 345 | 0 | 34 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44000, 44500, 45000 | Y | N |  |  | 6335 | 5764
4456 | Gilleland Creek Autotransformer | Install a new 345/138 kV 672 MVA auto transformer at Gilleland Creek substation. |  | Gilleland Creek |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015112 | 2017-12-01 |  | 345 | 0 | 0 | 672 |  | Travis |  | Tier 4 |  |  |  | 77341, 7340, 7336 | Y | N |  |  | 4841 | 4456
4546 | Upgrade 138kV Vealmoor - Salt Mine line |  |  | Vealmoor | Salt Mine | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2017-12-01 |  | 138 | 0 | 54.5 | 0 |  | Borden | Mitchell | Tier 4 |  |  |  | 79559, 79603, 79604, 79600, 79605 | Y | N |  |  | 4948 | 4546
5178 | Edith Clarke: Add 345 kV reactor | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley |  | Edith Clarke |  | Under Construction | 754 - 0937 | ETT | Steve Stein mlforcum@aep.com 918-599-2674 | 2625 | 2017-12-02 |  | 345 | 0 | 0 | 0 | -100,0 | Foard |  | Tier 4 |  |  |  | 60500 | Y | N |  |  | 5662 | 5178
15TPIT0058 | Permian Basin - Ward Gulf Tap - Wink 138 kV line | Upgrade existing 138 kV line | Construction schedule change | Permian Basin | Wink | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8189-E | 2017-12-14 |  | 138 | 0 | 16.5 | 0 |  | Ward | Winkler | Tier 4 |  |  |  | 1010, 1074, 1087 | Y | N |  |  | 3007 | 2834
4755 | Barstow NW - Culberson 138 kV Line | Construct a new DCKT Line |  | Barstow NW | Culberson | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8342 | 2017-12-14 |  | 138 | 53.8 | 0 | 0 |  | Ward | Culberson | Tier 4 | 2013-02-15 | 2013-02-15 |  | 1080, 1086, 1097 | Y | N |  |  | 5175 | 4755
4931 | Yukon Switching Station | Construct new switching station |  | Yukon |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8345 | 2017-12-14 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 3 | 2015-06-19 | 2015-07-29 |  | 1250, 1019, 11140 | Y | N |  |  | 5389 | 4931
09TPIT0122 | Shamburger - Tyler NW 138 kV line | Upgrade existing 138 kV line | Construction schedule change | Shamburger | Tyler NW | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6001-E | 2017-12-15 |  | 138 | 0 | 6.3 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3104, 3141 | Y | N | 2009-E6 |  | 1243 | 1240
11TPIT0050 | Roanoke Switch - Elizabeth Creek 138 kV line | Construct new double-circuit line. | Construction schedule change | Roanoke Switch | Elizabeth Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M509-E | 2017-12-15 |  | 138 | 3.8 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 11863, 640, 1852, 1854, 1866, 1867 | Y | N |  |  | 3058 | 2884
09TPIT0044 | E. Richardson - Apollo 138kV line (Oncor' section) | Upgrade existing 138 kV line |  | E. Richardson | Apollo | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3033-WA | 2017-12-15 |  | 138 | 0 | 2.3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 802, 2690 | Y | N |  |  | 3239 | 3070
06TPIT0042 | Lake Wichita Switch - Wichita Falls Switch 69 kV line | Upgrade existing 69 kV line |  | Lake Wichita Switch | Wichitia Falls Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R933-E | 2017-12-15 |  | 138 | 0 | 6.3 | 0 |  | Archer | Wichita | Tier 4 |  |  |  | 1446, 1447, 1448, 1449 | Y | N |  |  | 3390 | 3217
4241 | Texaco Mabee Tap - Texaco Mabee 138 kV Line | Rebuild existing line as a double-circuit line |  | Texaco Mabee Tap | Texaco Mabee | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8221 | 2017-12-15 |  | 138 | 11.4 | 11.4 | 0 |  | Midland | Andrews | Tier 4 |  |  |  | 1171, 1175, 1177, 1179, 11175, 1184, 11169, 11177, 11179 | Y | N |  |  | 4614 | 4241
4253 | Eagle Mountain - Calmont 138 kV Line | Upgrade existing double-circuit line | Construction schedule change | Eagle Mountain | Calmont | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5213 | 2017-12-15 |  | 138 | 0 | 40.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1860, 1865, 1955, 2085, 2086, 2087, 2088, 11860 | Y | N |  |  | 4624 | 4253
4267 | Andrews County South - North Andrews 138 kV Line | Upgrade existing line |  | Andrews County South | North Andrews | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8235 | 2017-12-15 |  | 138 | 0 | 19 | 0 |  | Andrews | Andrews | Tier 3 | 2016-02-01 | 2016-05-01 |  | 1153, 1155, 1157, 1159 | Y | N |  |  | 4640 | 4267
4268 | Breckenridge - Leon Switch 69 kV Line | Upgrade existing line | Construction schedule change | Breckenridge | Leon Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R783 | 2017-12-15 |  | 69 | 0 | 17 | 0 |  | Stephens | Eastland | Tier 3 |  |  |  | 271, 1622, 1615, 1625 | Y | N |  |  | 4641 | 4268
16TPIT0061 | Norwood - Record Crossing - East Levee 138 kV Line | Upgrade existing line | Construction schedule change | Norwood | East Levee | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4107-E | 2017-12-15 |  | 138 | 0 | 7.6 | 0 |  | Dallas | Dallas | Tier 3 |  | 2016-08-22 |  | 2405, 2407, 2482, 2811, 2812, 2813, 2815, 2816, 2814, 2819, 2823, 2824 | Y | N |  |  | 4671 | 3067
4299 | Big Brown - Navarro Switch 345 kV Line | Upgrade existing double-circuit line |  | Big Brown | Navarro Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1705 | 2017-12-15 |  | 345 | 0 | 62 | 0 |  | Freestone | Navarro | Tier 4 | 2015-06-15 |  |  | 3380, 68091 | Y | N |  |  | 4680 | 4299
4367 | Screwbean Tap - Culberson 138 kV Line | Rebuild existing 138 kV line | Construction schedule change | Screwbean Tap | Culberson | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8274 | 2017-12-15 |  | 138 | 0 | 19.6 | 0 |  | Culberson | Culberson | Tier 4 |  |  |  | 1095, 1096, 11079, 1097 | Y | N |  |  | 4741 | 4367
4524 | Culberson 138 kV Switching Station | Rebuild 138 kV bus | Construction schedule change | Culberson Switching station |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8366 | 2017-12-15 |  | 138 | 0 | 0 | 0 |  | Culberson |  | Tier 4 | 2013-02-15 | 2013-02-15 |  | 1097 | Y | N |  |  | 4921 | 4524
4751 | Lufkin Sw Sta - Crockett 138 kV Line | Rebuild existing line | Construction schedule change | Lufkin | Crockett | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6004 | 2017-12-15 |  | 138 | 0 | 42.9 | 0 |  | Angelina | Houston | Tier 3 | 2015-06-15 | 2015-08-15 |  | 3118, 3349, 3351, 3354 | Y | N |  |  | 5171 | 4751
4752 | Venus Sw Sta - Cedar Hill 138 kV line | Rebuild existing line | Construction schedule change | Venus Sw Sta | Cedar Hill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4201 | 2017-12-15 |  | 138 | 0 | 20.6 | 0 |  | Ellis | Dallas | Tier 4 |  |  |  | 1908, 2300, 2310, 2311, 2313, 2314, 3053, 3054 | Y | N |  |  | 5172 | 4752
4756 | Wink - Screwbean 138 kV circuit | Add second circuit to existing line |  | Wink | Culberson | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8337 | 2017-12-15 |  | 138 | 54 | 0 | 0 |  | Winkler | Culberson | Tier 4 |  |  |  | 1074, 1081, 1083, 1084, 1093, 1095, 1096, 1097, 1092, 1094, 11079 | Y | N |  |  | 5176 | 4756
4761 | Trinidad - Jewett 138 kV Line | Upgrade Trinidad - Big Brown Tap line section |  | Trinidad | Big Brown Tap | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2004 | 2017-12-15 |  | 138 | 0 | 26.4 | 0 |  | Henderson | Leon | Tier 4 |  |  |  | 212, 3127, 3505 | Y | N |  |  | 5184 | 4761
16TPIT0062 | Hutto Sw Sta - Gilleland Creek (LCRA) 138 kV Line | Upgrade existing line | Construction schedule change | Hutto Sw Sta | Gilleland Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R773-E | 2017-12-15 |  | 138 | 0 | 22 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 3654, 3665, 3666, 7336 | Y | N |  |  | 5198 | 3079
4932 | Wink - Yukon 138 kV Line | Construct new line |  | Wink | Yukon | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8346 | 2017-12-15 |  | 138 | 36 | 9 | 0 |  | Ector | Winkler | Tier 3 | 2015-06-19 | 2015-07-29 |  | 1252, 1074, 1075, 1250, 1251, 1254, 1253, 1258 | Y | N |  |  | 5390 | 4932
4937 | Wolf 138 kV Switching Station | Construct new 138 kV switching station |  | Wolf Switching Station |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8262 | 2017-12-15 |  | 138 | 0 | 0 | 0 |  | Ward |  | Tier 4 |  |  |  | 1013, 1009, 1010, 1105, 1087, 1103, 1107, 1292, 1015 | Y | N |  |  | 5395 | 4937
5398 | Lufkin Pershing 138 kV Emergency Capacitors | Install 18.4 MVar Cap Bank at Lufkin PershingTap |  | Lufkin Pershing Tap | Lufkin Pershing Tap | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6070 | 2017-12-15 |  | 138 | 0 | 0 |  | 0,18.4 | Angelina | Angelina | Tier 4 |  |  |  | 3329 | Y | N |  |  | 5910 | 5398
5400 | Tyler NW Sw. Sta. 138 kV Rebuild |  |  | Tyler NW | Tyler NW | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6072 | 2017-12-15 |  | 138 | 0 | 0 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3139, 3141 | Y | N |  |  | 5912 | 5400
5403 | Lufkin 138 kV Sw. Sta. Rebuild |  |  | Lufkin Sw. Sta. | Lufkin Sw. Sta. | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6067 | 2017-12-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3118, 3349 | Y | N |  |  | 5914 | 5403
5405 | Lufkin Corridor Expansion |  |  | Lufkin | Lufkin | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6074 | 2017-12-15 |  | 138 | 0 | 4.2 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3118, 3316, 3268, 3340 | Y | Y |  |  | 5916 | 5405
5484 | Royse-Terrell 138 kV Line | Upgrade existing Royse - Terrell 138 kV line |  | Royse | Terrell Sw | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4224 | 2017-12-15 |  | 138 | 0 | 28 | 0 |  | Rockwall | Kaufman | Tier 4 |  |  |  | 2715, 2472, 2713, 2717, 2718, 2719, 2721, 2723 | Y | N |  |  | 6047 | 5484
5532 | NW Paris 138 kV Sw. Sta. | Construct new 138/69 kV switching station |  | NW Paris | Paris | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4100 | 2017-12-15 |  | 138 | 0 | 3.5 | 100 |  | Lamar |  | Tier 4 |  |  |  | 1700, 1703, 1778, 1803, 1805, 1806, 6846, 1693, 1694, 1777, 1788, 1820, 1821, 11778 | Y | N |  |  | 6085 | 5532
5985 |  |  |  | Holt | Cowden North | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9024 | 2017-12-15 |  | 69 | 0 | 7.3 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1142, 1259 | Y | N |  |  | 6525 | 5985
4710G | Jones Creek Project | Upgrade CORTEZ loop: Reconductor portions of Ckt.48 Velasco to MARINE to CORTEZ to Jones Creek. |  | Velasco | Jones Creek | Planned | 4950 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 926 | 2017-12-29 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42540, 43155, 43440, 43360 | Y | N |  |  | 5128 | 4710
3272 | Potranco - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to AMD line. |  | Cagnon | AMD | Planned | S-0753 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0219 | 2017-12-30 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5346, 5002, 5053 | Y | N |  | There are no transformers associated with this project | 3448 | 3272
4577 | BRYN_4577_Dansby_Rebuild | Convert Dansby 69kV bus to Double Bus, Double Breaker configuration |  |  |  | Planned |  | BRYN |  |  | 2017-12-30 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  | 32875, 32897 | Y |  |  |  | 4984 | 4577
11TPIT0107 | Steamboat: Reterminate 69 kV Happy Valley tap | Reterminate the Happy Valley tap into Steamboat | Schedule Update | Happy Valley | Steamboat | Planned | 341 - 0515 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 2092 | 2017-12-31 |  | 69 | 0 | 0.6 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6332, 6328, 6330, 6331, 60332 | Y | N |  |  | 299 | 302
3479 | Cassava: Build 69 kV station | Construct new Cassava station along the Big Lake to Mathis Field 69 kV line (at Barnhart Phillips Tap location) | Schedule and Cost Update Update | Cassava |  | Under Construction | 635 - 0804 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2590 | 2017-12-31 |  | 69 | 0 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6003, 60359, 6035, 6526, 6532 | Y | N |  |  | 3686 | 3479
3480 | Cassava to Yucca: Rebuild 69 kV line | Rebuild 69 kV line as 138 kV from Cassava (Barnhart Phillips Tap) to Yucca and add 138/69 kV autotransformer capacity at Cassava | Project Description and Cost Update | Cassava | Yucca | Under Construction | 635 - 0804 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2591 | 2017-12-31 |  | 138 | 12.3 | 0 | 90 |  | Taylor | Taylor | Tier 4 |  |  |  | 6034, 6035, 6531, 60360, 6036, 60359 | Y | N |  |  | 3687 | 3480
3671 | Moran to Putnam: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line | Project Description, Schedule, and Cost Update | Moran | Putnam | Planned | 645 - 0814 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 1807 | 2017-12-31 |  | 69 | 0 | 12.86 | 0 |  | Shackelford | Callahan | Tier 4 |  |  |  | 6209, 6307 | Y | N |  |  | 3908 | 3671
13TPIT0160 | Whitepoint: Add 138 kV breaker terminal for WF interconnect | Interconnect Midway Wind Farm at Whitepoint and construct a 138 kV breaker terminal |  | Whitepoint |  | Under Construction | 573-0750 | AEP TCC | Rick McCraken DNLYONS@AEP.COM 918-599-2698 | 3454 | 2017-12-31 |  | 138 |  |  |  |  | San Patricio |  | Tier 4 |  |  |  | 8961 | Y | N |  |  | 3976 | 3731
4453 | Henne to McCarty Lane Transmission Line Upgrade | Upgrade the 6.6 mile Henne (7172) - McCarty Lane (7182) 138-kV transmission line to single 959 ACSS Suwannee, 380 MVA. |  | Henne | McCarty Lane | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015117 | 2017-12-31 |  | 138 | 0 | 6.6 | 0 |  | Comal | Hays | Tier 4 |  |  |  | 7172, 7182 | Y | N |  |  | 4838 | 4453
4705 | San Felipe to Eureka Ckt.09 | Upgrade Ckt.09 San Felipe to Eureka to increase thermal ratings | Change in project description | San Felipe | Eureka | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1132 | 2017-12-31 |  | 138 | 0 | 3.3 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45750, 47380, 47382 | Y | N |  |  | 5117 | 4705
5156 | Fort Stockton Plant: Build 138 kV terminal | Interconnect Oak Solar solar farm at Fort Stockton Plant | Schedule and Cost Update | Fort Stockton |  | Under Construction | 752 - 0935 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2622 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6630 | Y | N |  |  | 5637 | 5156
5169 | Harlingen SS to Raymondville #2: Rebuild 69 kV line | Rebuild Harlingen SS to Raymondville #2 with 959.6 ACSS/TW & OPGW |  | Harlingen SS | Raymondville #2 | Planned | 749 - 0932 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 2923 | 2017-12-31 |  | 138 | 0 | 22.8 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  | 8300, 8325, 8700 | Y | N |  |  | 5652 | 5169
5171 | Bates to Wormser: Raise structures increase MOT | Increase the MOT rating of the Bates to Wormser 138kV line by raising xx structures |  | Bates | Wormser | Planned | 750 - 0933 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2924 | 2017-12-31 |  | 138 | 0 | 126.48 | 0 |  | Hidalgo | Webb | Tier 4 |  |  |  | 8299, 8392, 8394, 8399, 8795, 8957, 8985, 80106, 80230, 8295 | Y | N |  |  | 5654 | 5171
5173 | Airline to Westside: Reconductor 138 kV line | Reconductor Airline to Westside with 1966 ACCC/TW |  | Airline | Westside | Planned | 746 - 0929 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2920 | 2017-12-31 |  | 138 | 0 | 6.1 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8485, 8490, 8882 | Y | N |  |  | 5657 | 5173
5197 | Abilene Northwest to Elm Creek: Rebuild 69 kV line | Rebuild Abilene Northwest to Elm Creek 69 kV line | Project Description and Cost Update | Abilene Northwest | Elm Creek | Planned | 759 - 0943 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2634 | 2017-12-31 |  | 69 | 0 | 3.07 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6253, 6225 | Y | N |  |  | 5681 | 5197
5233 | Lincoln Substation Addition | Construct a load serving substation (ring bus) at Lincoln. The station will be built off between Giddings and Lexington off T255. |  | Giddings | Lexington | Planned |  | LCRATSC/BBEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015961 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Lee | Lee | Tier 4 |  |  |  | 7568, 7302, 7571 | Y | N |  |  | 5731 | 5233
5393 | Alpine REA Tap to Barrilla Junction: Rehab 69 kV line | Rehab Alpine REA Tap to Barrilla Junction 69 kV line | Project Description and Cost Update | Alpine REA Tap | Barrilla Junction | Under Construction | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2643 | 2017-12-31 |  | 69 | 0 | 41.9 | 0 |  | Brewster | Pecos | Tier 4 |  |  |  | 6653, 6665 | Y | N |  |  | 5903 | 5393
5397 | Cassava to Mertzon REA Tap: Rehab 69 kV line | Rehab Cassava to Mertzon REA Tap 69 kV line | Project Description Update | Cassava | Mertzon REA Tap | Under Construction | 786 - 0971 | AEP TNC | Bill Roberts mlforcum@aep.com 918-599-2674 | 2644 | 2017-12-31 |  | 69 | 0 | 16.45 | 0 |  | Irion | Irion | Tier 4 |  |  |  | 6526, 60359 | Y | N |  |  | 5909 | 5397
5404 | Crowell to Truscott Humble Tap: Rehab 69 kV line | Rehab Crowell to Truscott Humble Tap 69 kV line | Project Description Update | Crowell | Truscott Humble Tap | Under Construction | 786 - 0971 | AEP TNC | Jake Tucker mlforcum@aep.com 918-599-2674 | 2645 | 2017-12-31 |  | 69 | 0 | 16.22 | 0 |  | Foard | Knox | Tier 4 |  |  |  | 6082, 6084 | Y | N |  |  | 5915 | 5404
5056 | Maxwell: Build new three breaker 138 kV station | Interconnect Val Verde Wind Farm permanently at Maxwell station via Fermi Collector station |  | MAXWELL |  | Under Construction | 735-0917 | AEP TCC | Rick McCracken dnlyons@aep.com 918-599-2698 | 3565 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  | 8998, 88998, 8257, 8261, 181754 | Y | N |  |  | 5920 | 5056
5409 | Jayton to Clairmont Tap: Rehab 69 kV line | Rehab Jayton to Clairmont Tap 69 kV line | Project Description Update | Jayton | Clairmont Tap | Under Construction | 786 - 0971 | AEP TNC | Jake Tucker mlforcum@aep.com 918-599-2674 | 2646 | 2017-12-31 |  | 69 | 0 | 10.55 | 0 |  | Kent | Kent | Tier 4 |  |  |  | 6153, 6197 | Y | N |  |  | 5921 | 5409
5411 | Haisley: Add Distribution Station | Add New Haisley Distribution Station |  | Lon Hill | Medio Creek | Under Construction | 783 - 0968 | AEP TCC | Daniel Lyons dnlyons@aep.com 918-599-2698 | 3576 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8920, 8452, 8912 | Y | N |  |  | 5923 | 5411
5768 | Garrott to Blodgett tap Ckt.37 | Upgrade Ckt.37 Garrott to Blodgett tap to increase thermal ratings |  | Garrott | Blodgett | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-12-31 |  | 138 | 0 | 1.3 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47521, 47660 | Y | N |  |  | 6339 | 5768
5833 | Rebuild Rockett to Rockett SW | Rebuild Rockett (Bus #218) to Rockett SW (Bus #214) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 16026 | 2017-12-31 |  | 69 | 0 | 6.44 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  | 214, 218 | Y |  |  |  | 6400 | 5833
4703B | Bellaire to San Felipe Ckt.09 | Upgrade Ckt.24 Bellaire to Bellaire tap |  | Bellaire | Bellaire | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1132 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47010, 47011 | Y |  |  |  | 6428 | 4703
5888 | Stewart to West Bay Ckt.48 & 59 | Reconductor Ckt.48 & 59 Stewart to West Bay as a hardening project |  | Stewart | West Bay | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 43290, 43520, 43521 | Y | N |  |  | 6430 | 5888
5950 | Smithville to Rosanky Rebuild | Part 2: Upgrade Structures on Smithville to Rosanky Transmission Line |  | Smithville | Rosanky | Planned |  | BBEC | Thomas Ellis thomas.ellis@bluebonnet.coop |  | 2017-12-31 |  | 69 | 0 | 5.4 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  | 7315, 7558 | Y | N |  |  | 6486 | 5950
6082 | Parsley: Build 138 kV station | Construct new 138 kV box bay on the Solstice to Permian Basin 138 kV line | NEW | Parsley |  | Planned | 860 - 1038 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2696 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60415, 60392, 60397 | Y | N |  |  | 6631 | 6082
5202 | Bay City 138 kV Station: Install 14.4 MVAR Cap Bank | Install a 14.4 MVAR Cap Bank at Bay City 138 kV station |  | Bay City |  | Under Construction | 767-0952 | AEP TCC | Mark Strabala dnlyons@aep.com 918-599-2698 | 3575 | 2018-01-12 |  | 138 | 0 | 0 | 0 | 0,14.4 | Matagorda |  | Tier 4 |  |  |  | 8113 | Y | N |  |  | 5686 | 5202
5168 | Airline to Holly: Build new 138 kV line | Build new Airline to Holly 138 kV line by installing a 1926 ACCC/TW circuit on the existing Barney Davis to Holly 138 kV line |  | Airline | Holly | Planned | 745 - 0928 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2919 | 2018-02-15 |  | 138 | 1.7 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8517, 8490 | Y | N |  |  | 5735 | 5168
5887A | RUSSEL 138kV Substation (ARITEK Substation Removal) | Remove ARITEK 138kV substation from CNP service |  | ARITEK | SR Bertron/CHORIN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-02-27 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40120, 40320, 41391 | Y | N |  |  | 6437 | 5887
5791 | GEBHRT - 138kV Substation | Build new 138kV GEBHRT customer-owned substation. Loop through Ckt.65 Sealy to Wallis. | New Project | GEBHRT | Sealy/Wallis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-02-28 |  | 138 | 0 | 0 | 0 |  | Austin | Austin | Tier 4 |  |  |  | 44700, 44640, 44740 | Y | N |  |  | 6355 | 5791
5887B | RUSSEL 138kV Substation (ARITEK Substation Removal) | Install 138kV customer-owned RUSSEL substation (ARITEK substation replacement). Loop from Ckt.84 DOWLAP to Morgans Point. |  | RUSSEL | DOWLAP/Morgans Point | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40125, 40490, 41100 | Y | N |  |  | 6438 | 5887
5963 | Big Hill: Build 345 kV terminal | Interconnect Live Oak wind farm at Big Hill | NEW | Big Hill |  | Planned | 844 - 1028 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2685 | 2018-02-28 |  | 345 | 0 | 0 | 0 |  | Schleicher |  | Tier 4 |  |  |  | 76003 | Y | N |  |  | 6503 | 5963
5179 | Clear Crossing: Add 345 kV reactor | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley |  | Clear Crossing |  | Under Construction | 754 - 0937 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2626 | 2018-03-02 |  | 345 | 0 | 0 | 0 | -100,0 | Haskell |  | Tier 4 |  |  |  | 60515 | Y | N |  |  | 5663 | 5179
5683E | Line H Rebuild and 138kV conversion. | Convert Pyote facility to 138 kV. Rebuild line from Pyote-Worsham (38001-38021). De-energize 69 kV line Wickett-Pyote (37980-38000). |  | 38001 | 38021 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2018-03-15 |  | 138 | 0 | 15.43 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 38000, 38001, 37980, 38021 | Y |  |  |  | 6572 | 5683
5891A | LUBZOL Substation Removal and Addition | Remove LUBZOL 138kV substation from CNP service |  | LUBZOL | TIDAL/TRAVIS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-03-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40980, 41580, 41590 | Y | N |  |  | 6433 | 5891
5891B | LUBZOL Substation Removal and Addition | Install 138kV customer-owned xxxxx substation (LUBZOL substation replacement) |  | LUBZOL | TIDAL/TRAVIS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-03-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40981, 41580, 41620 | Y | N |  |  | 6472 | 5891
5955 | Mequite: Build new distribution station | Mequite: Build new distribution station |  | Rangerville | Wesmer | Planned | 805 - 0990 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3594 | 2018-04-01 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8554, 5747, 8347 | Y | N |  |  | 6493 | 5955
4531 | Solstice to Clovis: Build 138 kV line | Interconnect Roserock solar farm with a new 138 kV line from Solstice to Clovis | Schedule Update | Solstice | Clovis | Planned | 705 - 0875 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2811 | 2018-04-30 |  | 138 | 4.5 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 60383, 6630, 60385, 132331 | Y | N |  |  | 4931 | 4531
5150 | Southwest Vernon: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Southwest Vernon | Schedule Update | Southwest Vernon |  | Planned | 741 - 0924 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2913 | 2018-04-30 |  | 138 | 0 | 0 | 130 |  | Wilbarger |  | Tier 4 |  |  |  | 6064, 6066 | Y | N |  |  | 5630 | 5150
6002 | Gregory - Rincon: Rebuild 69 kV line | Rehab Gregory - Rincon 69 kV line |  | Gregory | Rincon | Planned | 833 - 1017 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3634 | 2018-04-30 |  | 69 | 0 | 4.34 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8416, 8421 | Y | N |  |  | 6544 | 6002
3394 | Add Long Road Station |  |  | North Denton | Arco | Planned |  | DME | Chuck Sears 940-349-7111 |  | 2018-05-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 925, 923, 985 | Y | N |  |  | 3592 | 3394
4485 | Add new 345kV Limestone - Gibbons Crk double circuit line |  |  | Limestone | Gibbons Creek | Planned |  | CTT | Tim cook Tcook@lspower.com 636-534-3250 |  | 2018-05-01 |  | 345 | 70 | 0 | 0 |  | Limestone | Grimes | Tier 1 | 2013-07-29 | 2014-02-20 | 2014-04-08 | 967, 46020 | Y | Y |  |  | 4879 | 4485
5997 | Temple - Belton 138 kV Line | Temple - Belton 138 kV Line |  | Temple | Belton | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R784 | 2018-05-08 |  | 138 | 0 | 10.9 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3415, 3602, 3610, 3611, 3612 | Y | N |  |  | 6539 | 5997
1332 | Elm Mott - Waco West/Waco East 138 kV Line | Upgrade existing Elm Mott - Waco Northeast Tap line section |  | Elm Mott | Waco Northeast Tap | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1719 | 2018-05-15 |  | 138 | 0 | 6.7 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  | 3407, 3550, 3551, 3575 | Y | N |  |  | 1336 | 1332
13TPIT0059 | Cedar Crest - Industrial 138 kV line | Upgrade existing line | Construction schedule change | Cedar Crest | Industrial | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4072-E | 2018-05-15 |  | 138 | 0 | 3.2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2494, 2976, 2981 | Y | N | 2009-R23 |  | 2600 | 2495
14TPIT0057 | Cedar Hill Switch - Liggett 138 kV line | Upgrade Cedar Hill Switch - Dalworth existing line section | Construction schedule change | Cedar HIll Switch | Dalworth | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5041-E | 2018-05-15 |  | 138 | 0 | 8.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 1912, 1922, 2265, 2270, 2271, 2274, 2422 | Y | N |  |  | 3101 | 2926
17TPIT0023 | Northwest Carrollton - Norwood 138 kV Line | Upgrade existing double-circuit Northwest Carrollton - Carrollton line section |  | Northwest Carrollton | Carrollton | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4110-E | 2018-05-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 3 |  | 2017-01-11 |  | 2362, 2363, 2409, 2535, 2536, 2537, 2540, 2541, 2542, 2550, 2551, 2552, 12552 | Y | N |  |  | 3258 | 3089
17TPIT0024 | Payne - Anna Switch 138 kV Line | Upgrade existing line |  | Payne | Anna Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R938-E | 2018-05-15 |  | 138 | 0 | 20.8 | 0 |  | Grayson | Collin | Tier 3 |  |  |  | 1713, 1748, 1754, 1758, 2374 | Y | N |  |  | 3386 | 3213
4251 | Everman - Wedgwood 138 kV Line | Upgrade existing double-circuit line | Construction schedule changed | Everman | Wedgwood | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5210 | 2018-05-15 |  | 138 | 0 | 18 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1883, 1967, 2184, 2185, 2190, 2191, 2192, 2193, 2194, 2195 | Y | N |  |  | 4622 | 4251
4257 | Stryker Creek - Gresham Road 138 kV line | Upgrade existing line |  | Stryker Creek | Gresham Road | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6054 | 2018-05-15 |  | 138 | 0 | 9.1 | 0 |  | Cherokee | Rusk | Tier 4 |  |  |  | 3110, 3301 | Y | N |  |  | 4628 | 4257
4274 | Navarro - Corsicana 69 kV Line | Upgrade existing line |  | Navarro | Corsicana | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R793 | 2018-05-15 |  | 69 | 0 | 12.5 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  | 3468, 3475, 3479, 3480, 13468 | Y | N |  |  | 4648 | 4274
4280 | Allen Switching Station 138 kV series reactor | Install series reactor on 345/138 kV autotransformer #2 |  | Allen Switching Station |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R961 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 12514, 2512, 2514, 12512 | Y | N |  |  | 4655 | 4280
16TPIT0050 | Northaven - Renner 138 kV Line | Upgrade existing line | Construction schedule change | Northaven | Renner | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4108-E | 2018-05-15 |  | 138 | 0 | 8.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2356, 2357, 2596, 2597, 2613, 2614, 2615, 2616, 2657, 2659 | Y | N |  |  | 4670 | 3065
4527 | Fullerton Switching Station | Construct new switching station |  | Fullerton |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8277 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Andrews |  | Tier 4 |  |  |  | 1272, 1271, 1284 | Y | N |  |  | 4927 | 4527
4549 | Yucca Drive - Barilla Junction (AEP) 138 kV Line | Rebuild Oncor's section of the existing line |  | Yucca Drive | Barilla Junction (AEP) | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8272 | 2018-05-15 |  | 138 | 0 | 15 | 0 |  | Ward | Pecos | Tier 3 | 2015-12-15 | 2016-09-21 | 2016-10-11 | 1009, 60397 | Y | N |  |  | 4951 | 4549
4837 | Everman - Cleburne Sw. Sta. 138 kV Line | Upgrade existing Everman - Burleson line section | Construction schedule change | Everman | Burleson | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5204 | 2018-05-15 |  | 138 | 0 | 16.6 | 0 |  | Tarrant | Johnson | Tier 4 |  |  |  | 1883, 2208, 2209 | Y | N |  |  | 5264 | 4837
4840 | Crockett 138 kV Sw. Sta | Upgrade existing station | Construction schedule change | Crockett |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6060 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Houston |  | Tier 4 |  |  |  | 3351, 3354 | Y | N |  |  | 5267 | 4840
4843 | Hicks Sw. Sta. 345/138 kV autotransformer #2 | Install second 345/138 kV autotransformer |  | Hicks Sw. Sta. |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5229 | 2018-05-15 |  | 345 | 0 | 0 | 600 |  | Tarrant |  | Tier 4 |  |  |  | 2082, 2081 | Y | N |  |  | 5270 | 4843
4784B | Forest Hill - Cresson 69 kV Line Conversion | Convert existing 69 kV line section from Forest Hill to Crowley to 138 kV operation and rebuild existing 69 kV line section from Crowley to Cresson to 138 kV operation |  | Crowley | Cresson | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5227 | 2018-05-15 |  | 138 | 0 | 9.1 | 0 |  | Tarrant | Parker | Tier 4 | 2015-05-07 | 2015-06-01 |  | 2204, 2205, 12209, 1967, 1968 | Y | N |  |  | 5485 | 4784
5312 | Mitchell Bend - Rocky Creek 345 kV line | Upgrade existing line |  | Mitchell Bend | Rocky Creek | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1736 | 2018-05-15 |  | 345 | 0 | 32.8 | 0 |  | Hood | Tarrant | Tier 3 |  | 2016-07-22 | 2016-08-22 | 1877, 1880 | Y |  |  |  | 5813 | 5312
5427 | Holt-Andrews North-Andrews County South 138 kV DCKT Line | Upgrade existing line |  | Holt | Andrews North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8352 | 2018-05-15 |  | 138 | 0 | 30 | 0 |  | Andrews | Ector | Tier 3 | 2016-02-01 | 2016-05-01 |  | 1262, 1263, 1141, 1142, 1159, 1157, 1267 | Y | N |  |  | 5937 | 5427
5431 | Holt 138 kV Switching Station | Expand existing 138 kV switching station |  | Holt |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8353 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  | 1142, 1141 | Y | N |  |  | 5959 | 5431
5485 | Nacogdoches Southeast Switching Station | Upgrade existing 138 kV switching station |  | Nacogdoches Southeast Sw. Sta. | Nacogdoches Southeast Sw. Sta. | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6068 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Nacogdoches | Nacogdoches | Tier 4 |  |  |  | 3120, 3319 | Y | N |  |  | 6048 | 5485
5488 | Northwest Carrollton - LakePointe TNP 138 kV Line | Upgrade existing NW Carrollton - LakePointe 138 kV Line |  | Northwest Carrollton | LakePointe | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5156 | 2018-05-15 |  | 138 | 0 | 2.1 | 0 |  | Dallas | Denton | Tier 4 |  |  |  | 2362, 37010 | Y | N |  |  | 6051 | 5488
5490 | Liggett - Hackberry 138 kV DCKT Line | Upgrade existing Liggett - Hackberry 138 KV Double Ckt Line |  | Liggett | Hackberry | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4222 | 2018-05-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  | 1996, 1997, 2001, 2002, 2010, 11923, 15020, 15021, 2388, 15025, 15026, 15045, 15046 | Y | N |  |  | 6053 | 5490
5731 | Tri Corner 345 kV Sw Sta | Rebuild Tri Corner 345 kV Sw Sta |  | TriCorner |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4228 | 2018-05-15 |  | 345 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | Y |  |  |  | 6297 | 5731
5800 | Hutto-Taylor 138 kV Line | Upgrade existing 138 kV Line |  | Hutto | Taylor | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R775 | 2018-05-15 |  | 138 | 0 | 15.6 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 3658, 3666, 3673 | Y | N |  |  | 6365 | 5800
5805 | Holland 69 kV Capacitors | Install 69 kV Capacitors |  | Holland | Holland | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R772 | 2018-05-15 |  | 69 | 0 | 0 | 0 | 7.2,0 | Bell | Bell | Tier 4 |  |  |  | 3646 | Y | N |  |  | 6370 | 5805
5973 | Forest Hill 138 kV Switching Station | Rebuild existing Forest Hill 138 kV Switching Station |  | Forest Hill Sw. Sta. |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5268 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  | 1883, 1967, 2194 | Y | N |  |  | 6513 | 5973
5974 | Saginaw - Denton Ave/Springdale 138 kV DCKT Line | Rebuild existing 69 kV Lines |  | SAGINAW | DENTON AVE | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5245 | 2018-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1958, 1964, 2157, 1952, 1957, 2099, 2101, 2102, 2146, 2148, 3011 | Y | N |  |  | 6514 | 5974
5975 | Watermill - Camp Wisdom 138kV DCKT Line | Rebuild existing Watermill - Camp Wisdom 138 kV DCKT Line |  | Watermill Sw. Sta. | Camp Wisdom | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4216 | 2018-05-15 |  | 138 | 0 | 11.5 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  | 2430, 2988, 2989, 2990, 3068 | Y | N |  |  | 6515 | 5975
5976 | Handley - Richland Hills 138kV Line | Upgrade existing Handley - Richland Hills 138 kV Line |  | Handley | Richland Hills | Planned | M5265 | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 |  | 2018-05-15 |  | 138 | 0 | 5.6 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1951, 2099, 2103 | Y |  |  |  | 6516 | 5976
5983 | Add new capacitors | Add new capacitors |  | Whiting Oil |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9023 | 2018-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Ward |  | Tier 4 |  |  |  | 1080 | Y | N |  |  | 6523 | 5983
5996 | Corsicana 69 kV Switching Station | Corsicana 69 kV Switching Station |  | Corsicana | Corsicana | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2020 | 2018-05-15 |  | 138 | 0 | 0 | 100 |  | Navarro | Navarro | Tier 4 |  |  |  | 3466, 3467, 3469, 3480, 3127, 3128, 3455, 3468, 3478, 3479 | Y | N |  |  | 6538 | 5996
6026 | Mountain Creek - Cockrell Hill 138 kV Line | Upgrade terminal equipment on Mountain Creek - Cockrell Hill 138 kV Line |  | Mountain Creek | Cockrell Hill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4162 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2411, 3015 | Y | N |  |  | 6575 | 6026
6027 | Cockrell Hill - Hampton Rd 138 kV Line Double-circuit Line | Upgrade terminal equipment on Cockrell Hill - Hampton Rd 138 kV Double-circuit Line |  | Cockrell Hill | Hampton Rd | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4163 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 3014, 3016 | Y | N |  |  | 6576 | 6027
6028 | Rice Sw. - Markley 138 kV Line | Upgrade terminal equipment on Rice Sw. - Markley 138 kV Line |  | Rice Sw. | Markley | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4016 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Young |  | Tier 4 |  |  |  | 1476, 1477 | Y | N |  |  | 6577 | 6028
6035 | Liggett Sw. Sta. - Irving/Irving Grant 138 kV Double-circuit | Upgrade terminal equipment on Liggett Sw. Sta. - Irving/Irving Grant 138 kV Double-circuit Line section |  | Liggett | Irving Grant | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4164 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 1922, 1924, 2053, 2055 | Y | N |  |  | 6579 | 6035
6036 | Roanoke Sw. - Park Vista POI 138 kV Line | Upgrade terminal equipment on Roanoke Sw. - Park Vista POI 138 kV Line |  | Roanoke Sw. | Park Vista POI | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4168 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Denton | Tarrant | Tier 4 |  |  |  | 1857, 15101 | Y |  |  |  | 6580 | 6036
6037 | Irving Grant - Norwood 138 kV Line Section | Upgrade terminal equipment on Irving Grant - Norwood 138 kV Line |  | Irving Grant | Norwood | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4165 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2055, 2408 | Y | N |  |  | 6581 | 6037
6038 | Irving - Norwood 138 kV Line Section | Upgrade terminal equipment on Pleasant Valley - Ceramic 138 kV Line |  | Irving | Norwood | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4166 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2053, 2054, 2408 | Y | N |  |  | 6582 | 6038
6039 | Carrollton NW 345/138 kV Auto #1 | Upgrade terminal equipment on Carrollton NW 345/138 kV Auto #1 |  | Carrollton NW |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4167 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2360, 2362, 2363 | Y | N |  |  | 6583 | 6039
6019 | North Main - Denton Ave/Springdale Line | Rebuild existing 69 kV and 138 kV Lines |  | North Main | Denton Avenue | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 |  | 2018-05-16 |  | 138 |  | 7 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2148, 1961, 2102, 2157 | Y | N |  |  | 6561 | 6019
5499 | Everman - Cedar Hill Sw. Sta. 345 kV Line | Upgrade existing Everman - Cedar Hill Sw. Sta. 345 kV Line |  | Everman | Cedar Hill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5260 | 2018-05-18 |  | 345 | 0 | 39.14 | 0 |  | Tarrant | Dallas | Tier 4 |  |  |  | 1885, 1886, 1931, 1932, 2420 | Y | N |  |  | 6064 | 5499
4407 | Potencia: Build new 345/138 kV station | Interconnect La Paloma Generation at Potencia along the La Palma to Rio Hondo 345 kV and 138 kV lines and add 345/138 kV autotransformer capacity at Potencia |  | Potencia |  | Planned | 701 - 0871 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3545 | 2018-05-19 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 4 |  |  |  | 8460, 8461, 8314, 8317, 8318, 8319 | Y |  |  |  | 4786 | 4407
3937 | Brazos Valley Connection | Construct 345kV double circuit from Gibbons Creek to Zenith. Circuit numbers are 18 & 50. | Circuit mileage update | Gibbons Creek | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 717 | 2018-05-30 |  | 345 | 126 | 0 | 0 |  | Harris | Grimes | Tier 1 | 2013-07-25 | 2014-02-20 | 2014-04-08 | 967, 44900 | Y | Y |  |  | 4893 | 3937
5763A | Chorin to Cedar Bayou Ckt87 | CHORIN to STRANG Ckt.87 |  | CHORIN | STRANG | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-30 |  | 138 | 0 | 0.3 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40320, 41500 | Y | N |  |  | 6333 | 5763
18TPIT0002 | Martinez - New 138kV Substation | Loop new 138kV substation into the existing 138kV Deely to Skyline line |  | Deely | Skyline | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2018-05-31 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5294, 5110, 5368 | Y | N |  | There are no transformers associated with this project | 2336 | 2263
3669 | Albany Foundry to Moran: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line | Project Description, Schedule, and Cost Update | Albany Foundry | Moran | Planned | 645 - 0814 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 1808 | 2018-05-31 |  | 69 | 0 | 10 | 0 |  | Shackelford | Shackelford | Tier 4 |  |  |  | 6202, 6209 | Y | N |  |  | 3906 | 3669
3951 | TH Wharton to Fairbanks Ckt.81 | Reconductor 138kV Ckt.81 TH Wharton to Fairbanks and upgrade substation equipment at TH Wharton and Fairbanks to increase thermal ratings. | - Overall Date Update | TH Wharton | Fairbanks | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 995 | 2018-05-31 |  | 138 | 0 | 3.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45511, 45760 | Y | N |  |  | 4271 | 3951
4426A | Aritek to Chorin to SR Bertron Ckt. 87 Upgrades | Upgrade 138kV Ckt.87 ARITEK to CHORIN to increase thermal ratings. | Change in project schedule | ARITEK | CHORIN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40320, 41391 | Y | N |  |  | 4810 | 4426
4454 | Henne to Comal Transmission Line Upgrade | Upgrade the 7.6 mile Henne (7174) - Comal (7176) 138-kV transmission line from 159 MVA to 380 MVA using single 959 ACSS Suwannee conductors. |  | Henne | Comal | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015116 | 2018-05-31 |  | 138 | 0 | 7.6 | 0 |  | Comal | Comal | Tier 4 |  |  |  | 7172, 7174, 7176 | Y | N |  |  | 4839 | 4454
5020 | Red Creek: Replace the other 345/138 kV autotransformer | Replace both 345/138 kV autotransformers at Red Creek with 480 MVA autotransformers |  | Red Creek |  | Under Construction | 566 - 0740 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2615 | 2018-05-31 |  | 345 | 0 | 0 | 480 |  | Tom Green |  | Tier 4 |  |  |  | 6769, 6444, 6442 | Y | N |  |  | 5478 | 5020
5204 | Jourdanton to Pleasanton: 69 kV Transmission Line Rebuild | Rebuild 69 kV line from Jourdanton to Pleasanton. Install 2 x 7.2 MVAR Cap Bank at Jourdanton station |  | Jourdanton | Pleasanton | Planned | 765-0950 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3573 | 2018-05-31 |  | 69 | 0 | 6 | 0 | 0,7.2 | Atascosa | Atascosa | Tier 4 |  |  |  | 8607, 8200 | Y | N |  |  | 5688 | 5204
5271 | FPP Bus Tie Upgrades | Add a second bus tie between LCRA TSC FPP 345-kV Yard #1 and Yard #2 with a minimum 1793 MVA rating. Upgrade T405 to a minimum rating of 1793 MVA. |  | FPP #1 | FPP #2 | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016189 | 2018-05-31 |  | 345 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  | 7055, 7056 | Y | N |  |  | 5772 | 5271
5272 | Smithville - Winchester Line Overhaul | Rebuild T175 Smithville to Winchester with 795 ACSR (Drake) and OPGW. |  | Smithville | Winchester | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016207 | 2018-05-31 |  | 138 | 0 | 14.6 | 0 |  | Bastrop | Fayette | Tier 4 |  |  |  | 7306, 7314 | Y | N |  |  | 5773 | 5272
5493 | Hays Energy Substation Upgrade | Upgrade the Hays Energy 345-kV substation bus to a double bus double breaker configuration. |  | Hays Energy |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016230 | 2018-05-31 |  | 345 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  | 7043 | Y | N |  |  | 6056 | 5493
5600 | New 138 kV Retrieve Breakered Substation |  |  |  |  | Planned |  | CNP/CNP/TNMP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 43145, 43170, 43171, 43172, 39560, 39600, 42880, 43380 | Y | N |  |  | 6155 | 5600
5763B | Chorin to Cedar Bayou Ckt87 | STRANG to Cedar Bayou Ckt.87 |  | STRANG | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0.3 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40010, 41500 | Y | N |  |  | 6334 | 5763
5765 | TECO to Blodgett Tap Ckt37 | Upgrade substation equipment at TECO to increase TECO to Blodgett Tap Ckt37 thermal ratings |  | TECO | Blodgett | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47430, 47521 | Y | N |  |  | 6336 | 5765
5766A | Knight to BUNKER to HOC Ckt.08 Upgrades | Upgrade Ckt.08 Knight to BUNKER to increase thermal ratings |  | Knight | BUNKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 1.6 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47331, 47340 | Y | N |  |  | 6337 | 5766
5767 | TECO to Grant Ckt.37 | Upgrade Ckt.37 TECO to Grant to increase thermal ratings |  | TECO | Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47110, 47430 | Y | N |  |  | 6338 | 5767
5794 | Mason to Fort Mason: Rebuild 69 kV line | Rebuild Mason to Fort Mason 69 kV line and convert to 138 kV | Project Description and Schedule Update | Mason | Ft. Mason | Planned | 646 - 0815 | AEP TNC | Nick Newman mlforcum@aep.com 918-599-2674 | 1810 | 2018-05-31 |  | 69 | 0 | 0.15 | 0 |  | Mason | Mason | Tier 4 |  |  |  | 6393, 76388 | Y | N |  |  | 6358 | 5794
5766B | Knight to BUNKER to HOC Ckt.08 Upgrades | Upgrade Ckt.08 HOC to BUNKER to increase thermal ratings |  | HO Clarke | BUNKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47150, 47340 | Y | N |  | Cost is Reflected in Phase A of TPIT Project 5766 | 6361 | 5766
5807 | Velasco Cap Bank #2 | Install capacitor bank #2 at Velasco substation (120MVAR). |  | Velasco |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 | 0,120 | Brazoria |  | Tier 4 |  |  |  | 43362, 43155, 43360 | Y | N |  |  | 6372 | 5807
5808 | Install 160MVAR capacitor bank at Jones Creek substation. | Install 160MVAR capacitor bank at Jones Creek substation. |  | Jones Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 | 0,160 | Brazoria |  | Tier 4 |  |  |  | 42542, 42540, 43440 | Y | N |  |  | 6373 | 5808
5886 | Bellaire Auto A1 - Upgrade Limiting Equipment | Upgrade limiting equipment for Bellaire auto A1 |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47000, 47010, 49001 | Y |  |  |  | 6427 | 5886
5894 | Install Third Zenith 345/138kV 800MVA Transformer | Install a third 800MVA autotransformer at Zenith Substation. |  | Zenith |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 345 | 0 | 0 | 800 |  | Harris |  | Tier 4 |  |  |  | 49091, 44900, 44910 | Y | N |  |  | 6440 | 5894
5919 | Fort Mason Substation Upgrade | Convert Fort Mason to entirely 138-kV. Upgrade terminal equipment on T21444 to 2000 Amps. Remove autotransformer. |  | Fort Mason | Mason | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Mason |  | Tier 4 |  |  |  | 76388, 76390, 6393 | N | N |  |  | 6452 | 5919
5921 | Cuero - Guadalupe Transmission Line Overhaul | Tear down and rebuild 28 structures from Cuero to Structure 238. Upgrade conductor on this section of T542 to minimum rating of 111 MVA. Add OPGW to the line section. |  | Cuero | Guadalupe | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-05-31 |  | 69 | 0 | 3 | 0 |  | DeWitt | Guadalupe | Tier 4 |  |  |  | 78190, 78577 | N | N |  |  | 6454 | 5921
5923 | Fayetteville - FPP 138-kV Transmission Line Overhaul | Upgrade T253 from FPP 138-kV Yard to Fayetteville to 959 ACSS/TW Suwannee conductor with minimum rating of 380 MVA with OPGW. |  | Fayetteville | FPP | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-05-31 |  | 138 | 0 | 6.9 | 0 |  | Fayette |  | Tier 4 |  |  |  | 7278, 7286 | N | N |  |  | 6456 | 5923
5924 | Harwood - Waelder Transmission Line Overhaul | Upgrade T145 from Harwood to Waelder to 795 ACSR Drake conductor with minimum rating of 111 MVA at 69-kV and 221 MVA at 138-kV and add OPGW. |  | Harwood | Waelder | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-05-31 |  | 138 | 0 | 12.5 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7223, 7230, 7231, 7232 | N | N |  |  | 6457 | 5924
5925 | Gilleland Creek - Hutto Transmission Line Upgrade | Upgrade terminal equipment on T21452 at Gilleland Creek to minimum 3000 Amp rating. Needed to support an ONCOR project to upgrade the Hutto Sw. Station to Round Rock Southeast to Gilleland Creek 138-kV line. |  | Gilleland Creek | Hutto | Planned | 16TPIT0062 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Travis | Williamson | Tier 4 |  |  |  | 7336 | N | N |  |  | 6458 | 5925
5962 | Mason: Add new 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Mason | NEW | Mason |  | Planned | 646 - 0815 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2687 | 2018-05-31 |  | 138 | 0 | 0 | 130 |  | Mason |  | Tier 4 |  |  |  | 60410, 6393 | Y |  |  |  | 6502 | 5962
5969 | Clairmont Tap to Wolfgang 69 kV line: Rebuild 69 kV line | Rehab Clairmont Tap to Wolfgang 69 kV line | NEW | Clairmont Tap | Wolfgang | Planned | 786 - 0971 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2658 | 2018-05-31 |  | 69 | 0 | 7.82 | 0 |  | Kent | Kent | Tier 4 |  |  |  | 6162, 6197 | Y | N |  |  | 6509 | 5969
6077 | Bronte Atlantic to Miles 69 kV line: Rebuild 69 kV line | Rehab Bronte Atlantic to Miles 69 kV line | NEW | Bronte Atlantic | Miles | Planned | 786 - 0971 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2691 | 2018-05-31 |  | 69 | 0 | 17.44 | 0 |  | Coke | Runnels | Tier 4 |  |  |  | 6410, 6418 | Y | N |  |  | 6625 | 6077
4426B | Aritek to Chorin to SR Bertron Ckt. 87 Upgrades | Upgrade 138kV Ckt.87 Alexander Island to SR Bertron to increase thermal ratings. |  | Alexander Island | SRB | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41391, 41400 | Y | N |  | Cost Shown in TPIT Project 4426 Phase A | 6634 | 4426
6095 | South Channel to Jefferson Ckt.06 | Upgrades substation equipment at South Channel and/or Jefferson substation to increase thermal ratings. |  | South Channel | Jefferson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41370, 41371 | Y | N |  |  | 6645 | 6095
10TPIT0025 | Rinard Creek 138kV substation | Establish 138kV Rinard Ck substation with (2) 30MVA transformers and will cut into existing Ckt 987 (Lytton Springs to Slaughter Lane). |  | Rinard Creek substation | Rinard Creek Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P151 PLAN_117_P152 | 2018-06-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9262, 9075, 9267 | Y | N |  |  | 1031 | 1030
3273 | Southton - New 138kV Substation | A new 138kV substation from 138kV Braunig to Brooks. |  | Southton | Braunig-Brooks | Planned | S-0750 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0217 | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5394, 5030, 5045 | Y | N |  | There are no transformers associated with this project | 3449 | 3273
3276 | JT Deely to Martinez MLSE Upgrade | Upgrade terminal at JT Deely to ensure a rating of 2386 A (minimum). |  | JT Deely | Martinez | Planned | S-0759 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5294, 5110 | Y | N |  | There are no transformers associated with this project | 3452 | 3276
3820 | Rebuild Sandia to AEP Mathis | Rebuild 69 kV 4-0 to 795 ACSR on 138 kV capable structures. |  | Sandia | AEP Mathis | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 69 | 0 | 7.85 | 0 |  | Jim Wells | San Patricio | Tier 4 |  |  |  | 5666, 8407 | Y | N |  |  | 4102 | 3820
4082 | CPSE_Howard to Somerset Rebuild | Rebuild approximately seven miles of 138 kV transmission circuit from Howard to Somerset. The Howard to Somerset circuit should be upgraded to 469 MVA, minimum. |  | Howard | Somerset | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0232 | 2018-06-01 |  | 138 | 0 | 7.56 | 0 |  | Bexar | Bexar | Tier 2 | 2014-05-07 | 2014-09-04 |  | 5230, 5390 | Y | N |  |  | 4432 | 4082
4138 | DME_Hickory_Locust |  |  | Hickory | Locust | Planned | N/A | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2018-06-01 |  | 69 | 0 | 2.5 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 910, 914, 926 | Y | N | N/A |  | 4483 | 4138
4883 | McCoy 69 KV substation | Add a new load serving substation between Pleasanton and Tordillo |  | McCoy |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 69 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5721, 5714, 5715 | Y | N |  |  | 5319 | 4883
5017 | Lotebush: Build 138 kV station | Construct new 138 kV station on the Barrilla Junction to Permian Basin Line | Cost Update | Lotebush |  | Planned | 736 - 0919 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2616 | 2018-06-01 |  | 138 |  | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60392 | Y | N |  |  | 5475 | 5017
5131 | CPSE_Brooks to Chavaneaux Transmission Rebuild | Rebuild approximately 11 circuit miles of 138 kV transmission along the 410 corridor between Brooks and Chavaneaux. Included in the rebuild are segments of Harlandale to Sommers and Merida to Sommers 138 kV transmission lines. |  | Brooks/Sommers | Chavaneaux/Merida/Harlandale | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0230 | 2018-06-01 |  | 138 | 0 | 11 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5045, 5190, 5310, 5085, 5395 | Y | N |  |  | 5609 | 5131
5145A | Rafter - New 138 kV Substation | Loop new 138 kV load serving substation into the existing Castroville to Texas Research 138 kV transmission line. |  | RAFTER | CASTROVILLE/TX_RSRCH | Planned | S-0837 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0261 | 2018-06-01 |  | 138 | 0.77 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5355, 5083, 5430 | Y |  |  |  | 5623 | 5145
5193 | Ft. Griffin: Build 69 kV station and add capacitor bank | Construct new 69 kV ring bus near Albany and add one 14.4 Mvar capacitor bank |  | Ft. Griffin |  | Under Construction | 756 - 0940 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2631 | 2018-06-01 |  | 69 | 0 | 0 | 0 | 0,14.4 | Shackelford |  | Tier 4 |  |  |  | 6213, 60398, 6206, 6207, 6214 | Y | N |  |  | 5677 | 5193
5217 | Rebuild Cotulla to Big Wells 69 kV line | Rebuild 69 kV line with 138 kV capable 795 ACSR 2015- NERC assessment. |  | Cotulla | Big Wells | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 69 | 0 | 22.2 | 0 |  | La Salle | Dimmit | Tier 4 |  |  |  | 5868, 5876 | Y | N |  |  | 5707 | 5217
5223A | 2015 RTP rebuild 4 sections from George West through Mathis | Rebuild 4/0 ACSR from George West Switch to Kittie West with 795 ACSR that is 138 kV capable. 2015 RTP |  | George West Switch | Kittie West | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 69 | 0 | 4.25 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  | 5683, 5685, 5686 | Y | N |  |  | 5715 | 5223
5585 | West Edinburg loop in line | Loops the North Edinburg to Palmhurst line into West Edinburg |  | West Edinburg |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 138 | 0.1 | 0 | 0 |  | Hidalgo |  | Tier 1 | 2015-07-01 | 2016-05-19 | 2016-06-01 | 5771, 5774, 8380 | Y | N |  | Part of AEPSC Hidalgo Starr transmission project | 6137 | 5585
5603 | Holbrook_to_Kirby_Rebuild | Rebuild 2.3 miles of 138 kV transmission line from Holbrook to Kirby. |  | Holbrook | Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0264 | 2018-06-01 |  | 138 | 0 | 2.3 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5160, 5218, 5250 | Y |  |  |  | 6158 | 5603
5634 | Rebuild Danevang to Clemville Sw 69 kV line | Rebuild the Danevang Sub to Clemville Switch 4/0 ACSR 69 kV line with 795 ACSR 138 capable. 2016 RTP |  | Danevang | Clemville | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 69 | 0 | 5.1 | 0 |  | Wharton | Matagorda | Tier 4 |  |  |  | 5548, 5549 | Y | N |  |  | 6193 | 5634
5954 | Gillrina: Build new distribution station | Gillrina: Build new distribution station for STEC load |  | Banquette | Stadium | Planned | 805 - 0990 | AEP TCC/STEC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3594 | 2018-06-01 |  | 69 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8031, 8888, 8889 | Y | Y |  |  | 6492 | 5954
5956 | Young: Build new distribution station | Young: Build new distribution station |  | Polk Avenue | Pharr | Planned | 804 - 0989 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3593 | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 8030, 8372, 8373 | Y | N |  |  | 6494 | 5956
5683F | Line H Rebuild and 138kV conversion. | Construct Wickett 138 kV substation. Rebuild line from Wickett-Pyote (37981-38001). Build 138 kV line Oncor Wolf-TNMP Wickett (1013-37981). |  | 38001 | 1013 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2018-06-01 |  | 138 | 6.1 | 12.89 | 0 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 37981, 1013, 38001 | Y |  |  |  | 6573 | 5683
5223B | 2015 RTP rebuild 4 sections from George West through Mathis | Rebuild 4/0 ACSR from George West Tap to George West Sub with 795 ACSR that is 138 kV capable. 2015 RTP |  | GW Tap | GW Substation | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-02 |  | 69 | 0 | 6.44 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  | 5684, 5685 | Y | N |  |  | 5716 | 5223
5048 | Falfurius SVC: Upgrade | Replace SVC at Falfurius station +/- 65 MVAR capability |  | Falfurrias |  | Under Construction |  | ETT | Mark Strabala 918-599-2664 dnlyons@aep.com |  | 2018-06-03 |  | 69 | 0 | 0 | 0 |  | Brooks |  | Tier 4 |  |  |  | 88508, 8508 | Y | N |  |  | 5524 | 5048
5223C | 2015 RTP rebuild 4 sections from George West through Mathis | Rebuild 4/0 ACSR from George West Sub to Mathis with 795 ACSR that is 138 kV capable. 2015 RTP |  | GW Substation | Mathis | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-03 |  | 69 | 0 | 18.44 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  | 5668, 5684 | Y | N |  |  | 5717 | 5223
20TPIT0000 | Parkway Substation | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-06-29 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7611 | Y | N |  |  | 3504 | 3323
5716A | GLOBAL - 138kV Substation | Build new 138kV ME Global customer-owned substation. Loop through Ckt.82 Oyster Creek to Velasco. |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-06-29 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 43345, 43335, 43361 | Y | N |  |  | 6282 | 5716
13TPIT0106 | Killeen SS to Ding Dong | Rebuild 477 ACSR line with 955 ACSS |  | Killeen SS | Ding Dong | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 11037 | 2018-06-30 |  | 138 | 0 | 5.8 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 115, 117, 136, 3423 | Y | N |  |  | 2726 | 2608
2979 | Melon Creek: Build new 138/69 kV station | Construct new Melon Creek station near Refugio, add 138/69 kV autotransformer capacity at Melon Creek, cut-in Airco to Rincon 138 kV line into Melon Creek, and cut-in Refugio to Tatton 69 kV line into Melon Creek. | Company Contact Update | Melon Creek |  | Planned | 100 - 0100 | AEP TCC | Bill Roberts dnlyons@aep.com 918-599-2698 | 2021 | 2018-06-30 |  | 138 | 3 | 0 | 90 |  | Refugio |  | Tier 4 |  |  |  | 8144, 8437, 80065, 80066, 80067 | Y | N |  |  | 3148 | 2979
5176 | Riley: Add 345 kV reactors | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley |  | Riley |  | Under Construction | 754 - 0937 | ETT | Steve Stein mlforcum@aep.com 918-599-2674 | 2627 | 2018-06-30 |  | 345 | 0 | 0 | 0 | -200,0 | Wilbarger |  | Tier 4 |  |  |  | 6101 | Y | N |  |  | 5660 | 5176
5199 | Vernon Main Street: Add 138 kV capacitor banks | Add two 14.4 Mvar capacitor banks at Vernon Main Street | Project Title, Project Descrption, and Contact Update | Vernon Main Street |  | Planned | 760 - 0944 | AEP TNC | Dave Goetz mlforcum@aep.com 918-599-2674 | 2635 | 2018-06-30 |  | 138 | 0 | 0 | 0 | 0,28.8 | Wilbarger |  | Tier 4 |  |  |  | 6060 | Y | N |  |  | 5683 | 5199
5203 | Bessel 138 kV Station: Install Cap Bank | Install a 14.4 MVAR Cap Bank at Bessel 138 kV station |  | Bessel |  | Under Construction | 764-0949 | AEP TCC | James Weaver dnlyons@aep.com 918-599-2698 | 3572 | 2018-06-30 |  | 138 | 0 | 0 | 0 | 0,24.4 | Nueces |  | Tier 4 |  |  |  | 8060 | Y | N |  |  | 5687 | 5203
5494 | Bus Differential Redundancy | Upgrade the 138-kV bus differential protection at Gillespie, North McCamey and Zorn Substations. |  | Zorn |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016182 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7180 | Y | N |  |  | 6057 | 5494
5552 | North Belt to Greens Road Ckt.90 Thermal Uprate | Upgrade Ckt.90 North Belt to Greens Road to increase thermal ratings |  | North Belt | Greens Road | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1126 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45822, 46112 | Y | N |  |  | 6105 | 5552
5553B | Village Creek 138kV Substation | Construct service to new 138kV Village Creek distribution substation. Loop through Ckt.09 Zenith to Franz. | Delay in project schedule | Village Creek | Zenith/Franz | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-06-30 |  | 138 | 0.1 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 44270, 44271, 44260, 44910 | Y | N |  |  | 6106 | 5553
5715B | Red Bluff - 138kV Substation | Construct service to new 138kV Red Bluff distribution substation. Loop through Ckt.79 Terminal to Bayway |  | Red Bluff | Terminal/Bayway | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-06-30 |  | 138 | 1.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42930, 42931, 42170, 42955, 43225 | Y | N |  |  | 6280 | 5715
5716B | GLOBAL - 138kV Substation | Install 40MVAR capacitor bank at Oyster Creek substation |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-06-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 43337, 43335, 43345 | Y | N |  |  | 6283 | 5716
5912 | Bellville North Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Bellville North Substation. |  | Bellville North |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Austin |  | Tier 4 |  |  |  | 7287 | N | N |  |  | 6445 | 5912
5918 | Evant Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Evant Substation. |  | Evant |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Lampasas |  | Tier 4 |  |  |  | 7065 | N | N |  |  | 6451 | 5918
5926 | Kendall CTEC Circuit Breaker Addition | Add circuit breakers in a SB/SB arrangement at Kendall CTEC Tap (S343). |  | Kendall CTEC |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7147 | N | N |  |  | 6459 | 5926
4711B | CORTEZ 138kV Substation | Add 138kV CORTEZ Load |  | CORTEZ |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 55 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43440 | Y |  |  |  | 6473 | 4711
5944 | TEXWAL - Ckt.10 Loop Conversion | Convert existing 69kV TEXWAL substation from tap service to loop service on Ckt.10 Greens Bayou to Wallisville. Remove existing tap from Ckt.61. |  | TEXWAL | Green Bayou/Wallisville | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-06-30 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41570, 40725, 41681, 41682 | Y | N |  |  | 6480 | 5944
6021 | Haskell Tap 1 to Paint Creek 69 kV line: Rebuild 69 kV line | Rehab Haskell Tap 1 to Paint Creek 69 kV line | NEW | Haskell Tap 1 | Paint Creek | Planned | 786 - 0971 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2669 | 2018-06-30 |  | 69 | 0 | 14 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  | 6005, 6159, 6171, 6174 | Y |  |  |  | 6563 | 6021
6041 | Ely Tap to Scott REA Tap 69 kV line: Rebuild 69 kV line | Rehab Ely Tap to Scott REA Tap 69 kV line | NEW | Ely Tap | Scott REA Tap | Planned | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2670 | 2018-06-30 |  | 69 | 0 | 8.79 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6242, 6246, 60405 | Y | N |  |  | 6585 | 6041
6064 | Anson to Exxon Hawley Tap 69 kV line: Rebuild 69 kV line | Rehab Anson to Exxon Hawley Tap 69 kV line | NEW | Anson | Exxon Hawley Tap | Planned | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2674 | 2018-06-30 |  | 69 | 0 | 10.39 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6175, 6176, 6238 | Y | N |  |  | 6609 | 6064
6068 | Onyx to Nugent Tap 69 kV line: Rebuild 69 kV line | Rehab Onyx to Nugent Tap 69 kV line | NEW | Onyx | Nugent Tap | Planned | 786 - 0971 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2676 | 2018-06-30 |  | 69 | 0 | 6.71 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6219, 6237, 6243 | Y | N |  |  | 6614 | 6068
10TPIT0062 | Marion Power Transformer Addition (Formerly Weil Road) | Expand the Marion substation 138-kV bus. Install a 138-26.18 kV 40 MVA power transformer at Marion 138 kV bus. |  | Marion |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org | 1015120 | 2018-07-01 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7178 | Y | N |  |  | 2473 | 2384
5180 | Add second circuit to SLU panhandle loop |  |  | Alibates | Tule Canyon | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-07-01 |  | 345 | 166 | 0 | 0 |  | Carson | Briscoe | Tier 1 |  |  |  | 79500, 79501, 79502, 79503, 79504 | Y | N |  |  | 5664 | 5180
5187 | Add 2nd Palmito Transfomer |  |  | Palmito | Loma Alta | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-07-01 |  | 345 | 0 | 0 | 450 |  | Cameron | Cameron | Tier 4 |  |  |  | 79652, 5966, 79690 | Y | N |  |  | 5671 | 5187
5208 | Addition of synchronous condensers at Alibates and Tule Cany |  |  | Alibates | Tule Canyon | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-07-01 |  | 345 | 0 | 0 | 175 | 150300 | Carson | Briscoe | Tier 1 |  |  |  | 79520, 79521, 79500, 79503 | Y | N |  |  | 5692 | 5208
08TPIT0033 | Gilleland to Techridge 138kV Circuit | Establish a new 138kV circuit from Gilleland to Techridge and maintain a normally close tie between AEN and LCRA's switchyard at Gilleland. |  | Gilleland Substation | Techridge Substation | Planned |  | AEN | Reza Ebrahimian 512-322-6740 |  | 2018-07-06 |  | 138 | 8 | 0 | 0 |  | Travis | Travis | Tier 2 |  | 2009-07-21 |  | 9054, 9190, 9191, 7336, 9045 | Y |  |  |  | 6432 | 5890
5941 | T-283 Quanex Switch to Quanex Substation | Replacement of wood poles from Quanex Switch to Quanex Substation. |  | Quanex Switch | Quanex | Planned |  | SBEC | Don Roberts droberts@sbec.org | WO# 17-6070 | 2018-09-01 |  | 69 | 0 | 1.73 | 0 |  | Austin | Austin | Tier 4 |  |  |  | 7660, 7662 | Y | N |  |  | 6477 | 5941
5943 | T-283 Prairie View to Sunnyside | Rebuild transmission line to 138-kV capable 959.6 ACSS-TW conductor due to maintenance on old 69 KV wood pole line and the future conversion to 138 KV. |  | Prairie View | Sunnyside | Planned |  | SBEC | Don Roberts droberts@sbec.org | WO# 17-6069 | 2018-09-01 |  | 69 | 0 | 13 | 0 |  | Waller | Austin | Tier 4 |  |  |  | 7664, 7666 | Y | N |  |  | 6479 | 5943
3463 | Shady Bus Split | Reconfigure 69kV bus |  |  |  | Planned |  | BRYN | James Tanneberger 979-821-5763 |  | 2018-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 3668 | 3463
4504 | BRYN_4504_Rayburn_Nall_Upgrade | Reconductor Rayburn to Nall with 1033 |  | 32861 | 32872 | Planned |  | BRYN |  |  | 2018-09-30 |  | 69 | 0 | 1.06 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32861, 32872 | Y |  |  |  | 4901 | 4504
5045 | BRYN_5045_Nall_Relocation | Relocate Nall Lane Substation Across the Street |  |  |  | Planned |  | BRYN |  |  | 2018-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 5519 | 5045
5792 | Leonard Road Substation | Construct new substation on the Atkins to Dansby 138kV Line | [5 empty] | BRYN |  |  | 2018-09-30 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32851, 32862, 32897 | Y |  |  |  | 6356 | 5792
3887 | Relocate Hallettsville Auto to Nixon | Relocate 138/69 kV Auto at Hallettsville to LCRA Nixon, associated GCBs, Bus |  | LCRA Nixon |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-10-01 |  | 138 | 0 | 0 | 40 |  | Gonzales |  | Tier 1 | 2012-09-01 | 2012-10-31 | 2013-03-10 | 7585, 7617, 7246, 7621 | Y | N |  |  | 4177 | 3887
13TPIT0045 | Blumenthal Substation | Construct a new 11.5 mile 138 kV transmission line from a tap point on the Kendall CTEC (7147) - Mountain Top (7148) 138 kV transmission line to the new Blumenthal substation (7418) using 336 ACSR Linnet. | Delayed from initial May 2013 in-service date | Blumenthal | Kendall CTEC-Mountain Top | Planned |  | LCRATSC/CTEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1010656 | 2018-10-01 |  | 138 | 12.8 | 0 | 0 |  | Kendall | Gillespie | Tier 4 |  |  |  | 7418, 7419, 7147, 7148 | Y | N |  |  | 6443 | 990
5683G | Line H Rebuild and 138kV conversion. | Install 69-138 kV Autotransformer at Wickett. |  | 37980 | 37981 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2018-10-01 |  | 138 | 0 | 0 | 150 |  | Reeves | Reeves | Tier 1 | 2016-03-14 | 2016-08-11 |  | 1015, 37980, 37981 | Y |  |  |  | 6574 | 5683
18TPIT0001 | Wiederstein Substation | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Wiederstein |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-10-26 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7461 | Y | N |  |  | 3500 | 3319
5205 | Carrizo Springs-Crystal City: 69 kVLine Rebuild | Rebuild 69 kV line from Carrizo Spring to Crystal City |  | Carrizo Springs | Crystal City | Planned | 761-0945 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3569 | 2018-10-31 |  | 69 | 0 | 13.9 | 0 |  | Dimmit | Zavala | Tier 4 |  |  |  | 8244, 8242 | Y | N |  |  | 5689 | 5205
6074 | Concho to Veribest Tap 69 kV line: Rebuild 69 kV line | Rehab Concho to Veribest Tap 69 kV line | NEW | Concho | Veribest Tap | Planned | 786 - 0971 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2689 | 2018-10-31 |  | 69 | 0 | 1.86 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6409, 6450 | Y | N |  |  | 6621 | 6074
07TPIT0060 | Howard Lane to Techridge Reconductor | The project re-conductors Circuit 1004 (Techridge to Howard Lane) using 795 ACSS Drake conductors to increase the capacity to 4000 Amp. |  | Howard Lane | Techridge | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P067 PLAN_117_P194 | 2018-11-30 |  | 138 | 0 | 1.72 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9190, 9217 | Y | N |  |  | 1029 | 1028
3897 | Add New FM758 Sub | Construct a new 138-kV FM758 (7758) substation, which will cut into the LCRA TSC Clear Springs (7680) to Freiheit (7462) 138-kV transmission line |  | FM758 | Freiheit Road / Clear Springs | Planned |  | LCRATSC/NBU | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015105 | 2018-11-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7758, 7462, 7680 | Y | N |  |  | 4847 | 3897
5356 | Bakersfield: Build 345 kV terminal | Interconnect Maplewood solar farm at Bakersfield | Schedule Update | Bakersfield | Red Barn | Under Construction | 780 - 0965 | ETT | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2640 | 2018-11-30 |  | 345 | 2.35 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 6895, 76002 | Y | N |  |  | 5867 | 5356
5188 | Quaint Station: Build 69 kV station | Construct new 69 kV ring bus on the Abilene Northwest to Anson 69 kV Line |  | Quaint |  | Planned | 753 - 0936 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2623 | 2018-12-01 |  | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  | 6237, 6249, 6388, 6236, 6238, 6243, 60335 | Y | N |  |  | 5672 | 5188
5430D | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the "Reconstruct 69kV BonnieBrae-NLakes" sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2018-12-11 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 905, 915 | Y | N | N/A |  | 5947 | 5430
5430E | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the "Reconstruct 69kV BonnieBrae-NLakes" sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2018-12-11 |  | 138 | 0 | 1.521 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 928, 931 | Y | N | N/A |  | 5948 | 5430
5430F | Conversion to 138kV | Retire the existing 69kV North Lakes substation together with the transformer relocated from Denton North |  | North Lakes |  | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2018-12-11 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 915, 928 | Y | N | N/A |  | 5949 | 5430
5430G | Conversion to 138kV | Line already insulated for 138kV. Line will be terminated at the new 138kV Hickory substation |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2018-12-11 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 905, 910 | Y | N | N/A |  | 5950 | 5430
5430H | Conversion to 138kV | Construct new 138kV Hickory substation and terminate the existing Bonnie Brae - Hickory (which is already insulated for 138kV) at the new 138kV Hickory substation. |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2018-12-11 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 922, 931 | Y | N | N/A |  | 5951 | 5430
5559 | Add new 138kV Bonnie Brae Substation and retire the 69kV sta |  |  | Bonnie Brae |  | Planned | N/A | DENTON | Charles Sears cxsears@cityofdenton.com 940-349-7111 |  | 2018-12-11 |  | 138 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  | 905, 931 | Y | N | N/A |  | 6116 | 5559
07TPIT0050 | Dunlap to Techridge 138kV Circuit Relocation | This project will reroute the existing Ckt 975 Dunlap-Techridge from near the intersection of Howard Lane and Dessau Road to the Techridge substation. The reroute will use 3000 amp bundled 795 ACSS Drake conductor. |  | Dunlap Substation | Techridge Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P071 | 2018-12-13 |  | 138 | 0 | 2.7 | 0 |  | Travis | Travis | Tier 2 | 2009-01-26 | 2009-07-21 |  | 9045, 9190 | Y | N |  |  | 1014 | 1013
17TPIT0022 | Nacogdoches - Nacogdoches Southeast 138 kV Line | Upgrade existing Nacogdoches - Nacogdoches Southeast Line |  | Nacogdoches | Nacogdoches North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6037-E | 2018-12-15 |  | 138 | 0 | 3.9 | 0 |  | Nacogdoches | Nacogdoches | Tier 4 |  |  |  | 3303, 3310 | Y | N |  |  | 3323 | 3152
17TPIT0019 | Forney - Royse 138 kV Line | Upgrade existing line | Construction schedule change | Forney | Royse | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4111-E | 2018-12-15 |  | 138 | 0 | 18.32 | 0 |  | Kaufman | Rockwall | Tier 4 |  |  |  | 2438, 2471, 2709, 2710, 2711, 2712 | Y | N |  |  | 4664 | 3086
5434 | Littman - Fullerton 138 kV Line | Construct new 138 kV line | Construction Schedule Change | Littman | Fullerton | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8344 | 2018-12-15 |  | 138 | 10 | 5.5 | 0 |  | Andrews | Andrews | Tier 3 | 2016-08-24 | 2016-10-10 |  | 1273, 1134, 1272, 1274 | Y | N |  |  | 5962 | 5434
16TPIT0034 | Coleto Creek to Tuleta: New 138 kV Line | Build a double circuit capable 138 kV circuit from Coleto Creek station to new Tuleta station. |  | COLETO CREEK | TULETA | Under Construction | 606-0771 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3481 | 2018-12-30 |  | 138 | 56 | 0 | 0 |  | Goliad | Bee | Tier 1 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8595, 8162, 8590 | Y | N |  |  | 3702 | 3495
4065 | Add Graham Road Substation |  |  | BTU South | BTU Greens Prairie | Planned |  | COCS | Tony Mickalsky tmichalsky@cstx.gov 979-764-3438 |  | 2018-12-30 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32007, 32878, 32880 | Y |  |  |  | 4415 | 4065
4495 | AEP_4495_Champlin | Expand existing breaker configuration to a four (4) breaker ring bus expandable to a six (6) breaker ring bus configuration. |  | Champlin | Champlin | Planned | 694 - 0864 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3541 | 2018-12-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8476 | Y | N |  |  | 4889 | 4495
5527 | Euler 138 kV Station: Construct a new station | Build a double circuit capable 138 kV circuit from Coleto Creek station to new Tuleta station. |  | Euler |  | Under Construction | 606-0771 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3481 | 2018-12-30 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 1 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8595 | Y | N |  |  | 6079 | 5527
5555A | Clodine-Obrien Ckt25 & Ck73 Thermal Uprate | Upgrade Ckt.25 Clodine to Obrien to increase thermal ratings | Delay in project schedule | Clodine | Obrien | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1118 | 2018-12-30 |  | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  | 44145, 44511 | Y | N |  |  | 6108 | 5555
4487 | Valero East: Expand for Third Source | Expand and add new 138/69kV Auto at Valero East 69kV substation. Add 5th breaker to Champlin 138kV substation. Construct Champlin to Valero East 138kV Line. |  | Champlin | Valero East | Planned | 709 - 0879 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2903 | 2018-12-30 |  | 138 | 1.6 | 0 | 200 |  | Nueces |  | Tier 4 |  |  |  | 8528, 8476, 8859 | Y | N |  |  | 6395 | 4487
14TPIT0079 | Glen Rose to Meridian Rebuild | Rebuild Glen Rose to Meridian with 795 ACSR, 138 kV construction (operate at 69 kV) |  | Glen Rose | Meridian | Planned |  | BEPC | Dwight Beckman kdye@brazoselectric.com 254-750-6373 | 15024 | 2018-12-31 |  | 69 | 0 | 18.18 | 0 |  | Somervell | Bosque | Tier 4 |  |  |  | 315, 319 | Y | N |  |  | 2310 | 2237
3774 | Olinger-Ben Davis Line Upgrade | Olinger to Ben Davis 138 kV line upgrade to 436 MVA ratings |  | Olinger | Ben Davis | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2018-12-31 |  | 138 | 0 | 17.25 | 0 |  | Collin | Dallas | Tier 4 |  |  |  | 818, 968 | Y | N |  |  | 4019 | 3774
3775 | Firewheel-WylieSW Line Upgrade | Firewheel to Wylie Switch 138 kV line upgrade to 436 MVA ratings |  | Firewheel | WylieSW | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2018-12-31 |  | 138 | 0 | 17.77 | 0 |  | Dallas | Collin | Tier 4 |  |  |  | 821, 833 | Y | N |  |  | 4020 | 3775
3948 | Steamboat to Tuscola: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola |  | Steamboat | Tuscola | Planned | 685 - 0855 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 1851 | 2018-12-31 |  | 69 | 0 | 9.856 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6328, 6331, 60332 | Y | N |  |  | 4266 | 3948
3949 | Steamboat to Winters: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola |  | Steamboat | Winters | Planned | 685 - 0855 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 1850 | 2018-12-31 |  | 69 | 0 | 9.944 | 0 |  | Taylor | Runnels | Tier 4 |  |  |  | 6333, 60332 | Y | N |  |  | 4267 | 3949
4185 | HO Clarke Partial Load Conversion (TR1) | Convert HO Clarke TR1 load to 138kV. Tap off of Ckt.09 HO Clarke to Brays | Delay in project schedule | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1112 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47151, 47050, 47150 | Y | N |  |  | 4540 | 4185
4716 | Tortuga: Build new 3 breaker 138 kV station | Construct new Tortuga 138 kV line and cut it into the Gila - Upriver (Koch) 138 kV line |  | Gila | Upriver (Koch) | Planned | 717 - 0899 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3553 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8168, 81680, 8467, 80136, 80260 | Y |  |  |  | 5214 | 4716
4871 | Webster Breaker Addition | Install breaker at Webster 138kV substation to connect ring buses | - Overall Date Update | Webster |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1134 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 43505, 42651, 42970, 43082, 43500, 43507 | Y | N |  |  | 5306 | 4871
4875 | Red Gate: Build new 138 kV line | Interconnect STEC Red Gate Power Plant at Permanent with a new 138 kV line into North Edinburg |  | Falfurrias | North Edinburg | Planned | 724 - 0906 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3558 | 2018-12-31 |  | 138 | 7.5 | 7.5 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 88380, 8380, 8896, 161031 | Y | Y |  |  | 5311 | 4875
4996 | HO Clarke Load Conversion | Convert HO Clarke TR2 & TR3 to 138kV service. Tap off of Ckt.25 HO Clarke to Fondren. | - Overall Cost Update | HO Clarke | Fondren | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 47151, 47152, 47160, 47150, 47412 | Y |  |  |  | 5454 | 4996
5533 | Lynx: Build a 138 kV station | Construct a new 138 kV ring bus near Woodward #1 Tap on the Fort Stockton to Rio Pecos Line and rebuild Lynx to Rio Pecos 138 kV line | Project Description and Contact Update | Lynx |  | Planned | 788 - 973 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2647 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6632, 60400, 6601, 6671, 130432, 130431 | Y | N |  |  | 6086 | 5533
5554 | Jones Creek Cap Bank #1 | Install capacitor bank #1 at Jones Creek substation (120MVAR). | - Updated project title and description - Updated expected date | Jones Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1113 | 2018-12-31 |  | 138 | 0 | 0 | 0 | 0,120 | Brazoria |  | Tier 4 |  |  |  | 42541, 42540, 42645 | Y | N |  |  | 6107 | 5554
5555B | Clodine-Obrien Ckt25 & Ck73 Thermal Uprate | Upgrade Ckt.73 Clodine to Obrien to increase thermal ratings | Delay in project schedule | Clodine | Obrien | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1118 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  | 44140, 44512 | Y | N |  | Cost Reflected in TPIT 5555A Project. | 6109 | 5555
5588 | La Palma SVC | Add +300/-150 MVAR SVC to La Palma 138 kV station |  | La Palma |  | Planned | 793 - 0978 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3583 | 2018-12-31 |  | 138 | 0 | 0 | 0 | 150300 | Cameron |  | Tier 3 | 2015-04-16 | 2016-05-19 | 2016-06-16 | 80319, 80320, 8314 | Y | N |  |  | 6143 | 5588
5596 | Pharr SVC | Add +300/-150 MVAR SVC to Pharr 138 kV station |  | Pharr |  | Planned | 794 - 0979 | AEP TCC | Rich Haley dnlyons@aep.com 918-599-2698 | 3584 | 2018-12-31 |  | 138 | 0 | 0 | 0 | 150300 | Hidalgo |  | Tier 3 | 2015-04-16 | 2016-05-19 | 2016-06-16 | 80372, 80373, 8372 | Y | N |  |  | 6151 | 5596
4706A | HO Clarke to Webster Ckt.05 | HO Clarke to Southwyck Ckt.05 |  | HO Clark | Southwyck | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44361, 47150, 43260 | Y | N |  |  | 6327 | 4706
4706B | HO Clarke to Webster Ckt.05 | HO Clarke Southwyck to Webster Ckt.05 |  | Southwyck | Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42651, 43260 | Y | N |  |  | 6328 | 4706
5831 | Rebuild Gustine to Energy SW | Rebuild Gustine (Bus #273) to Energy SW (Bus #265) per RTP study results |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 16013 | 2018-12-31 |  | 69 | 0 | 5.05 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  | 265, 273 | Y |  |  |  | 6398 | 5831
5834 | Salt Creek to Cogdell | RPG Project for Salt Creek (Bus# 743) to Clairmont (Bus# 752) to ONCOR's Cogdell (Bus# 1402) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 14032 | 2018-12-31 |  | 138 | 20 | 0 | 0 |  | Kent | Scurry | Tier 2 | 2015-12-21 | 2016-06-27 |  | 752, 743, 1402, 6198 | Y |  |  |  | 6401 | 5834
5838 | New Katz Auto to Benjamin 138 kV | Joint project with AEP to add autotransformer from Katz (bus# 774) to Katz8 (bus #798) and new line to Benjamin (bus # 6088) when AEP converts to 138 kV and builds line from the new Tardis switching station |  |  |  | Planned |  | BEPC/BEPC & AEP | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 15016 | 2018-12-31 |  | 138 | 18 | 0 | 75 |  | King | Knox | Tier 2 | 2016-02-03 | 2016-05-30 |  | 790, 798, 6087, 6088, 774 | Y |  |  |  | 6405 | 5838
5910 | Butler Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Butler Substation. |  | Butler |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  | 7324 | N | N |  |  | 6442 | 5910
5913 | Colton Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Colton Substation. |  | Colton |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7208 | N | N |  |  | 6446 | 5913
5928 | McElmurray Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at McElmurray Substation. |  | McElmurray |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  | 76319 | N | N |  |  | 6461 | 5928
5951 | Bishop-Stratton: Rebuild 69 kV line | Rebuild Bishop - Stratton 69 kV line |  | Bishop | Stratton | Planned | 825 - 1009 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3624 | 2018-12-31 |  | 69 |  | 4.73 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8498, 8512 | Y | N |  |  | 6487 | 5951
5961 | Tardis: Build new 138 kV station | Construct new 138 kV ring bus Tardis on the Munday to Paducah 138 kV line, rebuild exiting Benjamin Tap to 138 kV, terminate into Tardis, convert Benjamin to 138 kV operation and build new 138 kV line from Benjamin to Katz (BEC) | Schedule and Cost Update | Tardis |  | Planned | 769 - 0954 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2683 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Knox |  | Tier 2 |  |  |  | 6320 | Y | N |  |  | 6501 | 5961
5966 | College Hills to Grape Crk T 69 kV line: Rebuild 69 kV line | Rehab College Hills to Grape Creek Tap 69 kV line | NEW | College Hills | Burma | Planned | 786 - 0971 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2664 | 2018-12-31 |  | 69 | 0 | 10.45 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6416, 60411, 6437, 6460, 6468 | Y | N |  |  | 6506 | 5966
5967 | Burma: Build new 69 kV station | Construct a new 69 kV station near the exsiting Grape Creek tap and reterminate the College Hills to Sterling City and Grape Creek to North San Angelo 69 kV lines into Burma | NEW | Burma |  | Planned | 845 - 1029 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2688 | 2018-12-31 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  | 6416, 60411, 6437, 6460, 6468 | Y | N |  |  | 6507 | 5967
5968 | Alpine to Alpine REA 69 kV line: Rebuild 69 kV line | Rehab Alpine to Alpine REA 69 kV line | NEW | Alpine | Alpine REA | Planned | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2657 | 2018-12-31 |  | 69 | 0 | 8.82 | 0 |  | Brewster | Brewster | Tier 4 |  |  |  | 6665, 6666 | Y | N |  |  | 6508 | 5968
5970 | Wolfgang to Rotan 69 kV line: Rebuild 69 kV line | Rehab Wolfgang to Rotan 69 kV line | NEW | Wolfgang | Rotan | Planned | 786 - 0971 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2659 | 2018-12-31 |  | 69 | 0 | 12.41 | 0 |  | Kent | Fisher | Tier 4 |  |  |  | 6162, 6196 | Y | N |  |  | 6510 | 5970
5971 | Truscott Hmble T to Benjamin T 69 kV line: Rbld 69 kV line | Rehab Truscott Humble Tap to Benjamin Tap 69 kV line | NEW | Truscott Humble Tap | Benjamin Tap | Planned | 786 - 0971 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2660 | 2018-12-31 |  | 69 | 0 | 11.08 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 6086, 6087, 790, 6085, 6107 | Y | N |  |  | 6511 | 5971
5972 | Benjamin Tap to Munday 69 kV line: Rebuild 69 kV line | Rehab Benjamin Tap to Munday 69 kV line | NEW | Benjamin Tap | Munday | Planned | 786 - 0971 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2661 | 2018-12-31 |  | 69 | 0 | 13.12 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 6086, 6087, 790, 6085, 6107 | Y | N |  |  | 6512 | 5972
5977 | Mertzon (CVEC T) to Tankersley 69 kV line: Rbld 69 kV line | Rehab Mertzon (CVEC Tap) to Tankersley 69 kV line | Rehab Mertzon (CVEC Tap) to Tankersley 69 kV line | Mertzon (CVEC Tap) | Tankersley | Planned | 786 - 0971 | AEP TNC | Bill Roberts mlforcum@aep.com 918-599-2674 | 2662 | 2018-12-31 |  | 69 | 0 | 13.2 | 0 |  | Irion | Irion | Tier 4 |  |  |  | 6526, 6528, 6529 | Y | N |  |  | 6517 | 5977
5978 | Tankersley to Mathis Field 69 kV line: Rebuild 69 kV line | Rehab Tankersley to Mathis Field 69 kV line | NEW | Tankersley | Mathis Field | Planned | 786 - 0971 | AEP TNC | Bill Roberts mlforcum@aep.com 918-599-2674 | 2663 | 2018-12-31 |  | 69 | 0 | 9.99 | 0 |  | Irion | Tom Green | Tier 4 |  |  |  | 6477, 6528 | Y | N |  |  | 6518 | 5978
5979 | Carver: Build new 138 kV station | Construct a new 138 kV ring bus station to replace the 138 kV portion of the Sonora 138/69 kV station | NEW | Carver |  | Planned | 838 - 1022 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2678 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Sutton |  | Tier 4 |  |  |  | 60412, 6500, 6515, 6562, 8259 | Y | N |  |  | 6519 | 5979
5980 | Bison: Build 69 kV station | Construct new 69 kV ring bus at Powell Field Junction Tap | NEW | Bison |  | Planned | 840 - 1024 | AEP TNC | Randall Wantland mlforcum@aep.com 918-599-2674 | 2680 | 2018-12-31 |  | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6548, 60395, 6545, 6547, 6549 | Y | N |  |  | 6520 | 5980
5993 | Owls: Build 138 kV station | Construct new 138 kV ring bus with a 138/69 kV autotransformer | NEW | Owls |  | Planned | 841 - 1025 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2681 | 2018-12-31 |  | 138 | 0 | 0 | 90 |  | Reagan |  | Tier 4 |  |  |  | 60413, 60414, 6536, 6544, 60361, 60396 | Y | N |  |  | 6534 | 5993
5994 | Owls to Pwll Fld Jnctn T (Bison) 69 kV line: Rbld 69 kV line | Rehab Owls to Powell Field Junction Tap (Bison) 69 kV line | NEW | Owls | Bison | Planned | 786 - 0971 | AEP TNC | Michael Richardson mlforcum@aep.com 918-599-2674 | 2665 | 2018-12-31 |  | 69 | 0 | 11.53 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  | 6545, 60396, 60395, 60413 | Y | N |  |  | 6535 | 5994
5998 | Ganso: Build new 138 kV station | Build new three breaker ring in place of Eagle Pass Hydro Tap |  | Ganso |  | Planned | 835 - 1019 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3637 | 2018-12-31 |  | 138 | 0 | 0.3 | 0 |  | Maverick |  | Tier 4 |  |  |  | 8264, 8267, 8260, 8263, 8692 | Y | N |  |  | 6540 | 5998
6000 | Calallen - Banquete: Rebuild 69 kV line | Rehab Calallen - Banquete 69 kV line |  | Calallen | Banquete | Planned | 816 - 1000 | AEP TCC/STEC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3609 | 2018-12-31 |  | 69 | 0 | 12.7 | 0 |  | Nueces |  | Tier 4 |  |  |  | 5626, 8888 | Y | Y |  |  | 6542 | 6000
6001 | Goliad - Fannin: Rebuild 69 kV line | Rehab Goliad - Fannin 69 kV line |  | Goliad | Fannin | Planned | 809 - 0994 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3598 | 2018-12-31 |  | 69 | 0 | 5 | 0 |  | Goliad | Victoria | Tier 4 |  |  |  | 5736, 8587 | Y | N |  |  | 6543 | 6001
6003 | Knippa - Uvalde: Rebuild 69 kV line | Rehab Knippa - Uvalde 69 kV line |  | Knippa | Uvalde | Planned | 811 - 0996 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3601 | 2018-12-31 |  | 69 | 0 | 4.62 | 0 |  | Uvalde |  | Tier 4 |  |  |  | 8231, 8628 | Y | N |  |  | 6545 | 6003
6004 | Refugio - Melon Creek: Rebuild 69 kV line | Rehab Refugio - Melon Creek 69 kV line |  | Refugio | Melon Creek | Planned | 815 - 0999 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3607 | 2018-12-31 |  | 69 | 0 | 12.6 | 0 |  | Refugio | Calhoun | Tier 4 |  |  |  | 8410, 8800 | Y | N |  |  | 6546 | 6004
6009 | Kenedy Switch: Replace 138/69 kV autotransformer | Upgrade 138/69 kV autotransformer capacity at Kenedy Switch |  | Kenedy Switch |  | Planned | 837 - 1021 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3639 | 2018-12-31 |  | 138 | 0 | 0 | 130 |  | Karnes |  | Tier 4 |  |  |  | 8184, 8186 | Y | N |  |  | 6551 | 6009
6011 | Laredo Plant: Replace 138/69 kV autotransformer | Upgrade 138/69 kV autotransformer capacity at Laredo Plant |  | Laredo Plant |  | Planned | 806 - 0991 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3595 | 2018-12-31 |  | 138 | 0 | 0 | 180 |  | Webb |  | Tier 4 |  |  |  | 8293, 8290, 8298, 8303 | Y | N |  |  | 6553 | 6011
6022 | Stamford to Haskell Tap 1 69 kV line: Rebuild 69 kV line | Rehab Stamford to Haskell Tap 1 69 kV line | NEW | Stamford | Haskell Tap 1 | Planned | 786 - 0971 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2668 | 2018-12-31 |  | 69 | 0 | 12.22 | 0 |  | Jones | Haskell | Tier 4 |  |  |  | 6171, 6172 | Y | N |  |  | 6564 | 6022
6040 | Lon Hill: Replace 345/138 kV autotransformers | Replace 345/138 kV autotransformers at Lon Hill | NEW | Lon Hill |  | Planned | 829 - 1013 | AEP TNC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3630 | 2018-12-31 |  | 345 | 0 | 0 | 1350 |  | Nueces |  | Tier 4 |  |  |  | 8455, 8452, 8499, 8502 | Y | N |  |  | 6584 | 6040
6042 | Scott REA Tap to Eskota 69 kV line: Rebuild 69 kV line | Rehab Scott REA Tap to Eskota 69 kV line | NEW | Scott REA Tap | Eskota | Planned | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2671 | 2018-12-31 |  | 69 | 0 | 11.73 | 0 |  | Taylor | Nolan | Tier 4 |  |  |  | 1340, 6246, 6247 | Y | N |  |  | 6586 | 6042
6005 | Airline: Convert 69 kV Station | Upgrade Airline 69 kV station and lines to 138 kV |  | Airline | Naval Base | Planned | 808 - 0993 | AEP TCC/LCRA | Dan Lyons dnlyons@aep.com 918-599-2698 | 3597 | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8487, 8494, 8548, 8560, 8561, 8490, 8495, 8997, 8562, 8856 | Y | Y |  |  | 6596 | 6005
6065 | Abilene Northwest to Onyx 69 kV line: Rebuild 69 kV line | Rehab Abilene Northwest to Onyx 69 kV line | NEW | Abilene Northwest | Onyx | Planned | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2673 | 2018-12-31 |  | 69 | 0 | 3.61 | 0 |  | Taylor | Jones | Tier 4 |  |  |  | 6224, 6236 | Y | N |  |  | 6610 | 6065
6072 | Eldorado to Ft. McKavitt 69 kV line: Rebuild 69 kV line | Rehab Eldorado to Ft. McKavitt 69 kV line | NEW | Eldorado Tap | Ft. McKavitt | Planned | 786 - 0971 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2677 | 2018-12-31 |  | 69 | 0 | 19.41 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  | 6505, 6506, 6507, 6508 | Y | N |  |  | 6619 | 6072
6075 | Veribest T to Harriett 69 kV line: Rebuild 69 kV line | Rehab Veribest Tap to Harriett CVEC REA 69 kV line | NEW | Veribest Tap | Harriett CVEC REA | Planned | 786 - 0971 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2690 | 2018-12-31 |  | 69 | 0 | 8.4 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6409, 6412 | Y | N |  |  | 6622 | 6075
6078 | Bronte to Bronte Atlantic 69 kV line: Rebuild 69 kV line | Rehab Bronte to Bronte Atlantic 69 kV line | NEW | Bronte | Bronte Atlantic | Planned | 786 - 0971 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2692 | 2018-12-31 |  | 69 | 0 | 3.73 | 0 |  | Runnels | Coke | Tier 4 |  |  |  | 6414, 6418 | Y | N |  |  | 6627 | 6078
6079 | Childress to Kirkland 69 kV line: Rebuild 69 kV line | Rehab Childress to Kirkland 69 kV line | NEW | Childress | Kirkland | Planned | 786 - 0971 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2693 | 2018-12-31 |  | 69 | 0 | 5.61 | 0 |  | Childress | Childress | Tier 4 |  |  |  | 6032, 6053 | Y | N |  |  | 6628 | 6079
6080 | Concho to Christoval 69 kV line: Rebuild 69 kV line | Rehab Concho to Christoval 69 kV line | NEW | Concho | Christoval | Planned | 786 - 0971 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2694 | 2018-12-31 |  | 69 | 0 | 16.8 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6450, 6495, 6527 | Y | N |  |  | 6629 | 6080
6081 | Chillicothe to Vernon Main 69 kV line: Rebuild 69 kV line | Rehab Chillicothe to Vernon Main 69 kV line | NEW | Chillicothe | Vernon Main | Planned | 786 - 0971 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2695 | 2018-12-31 |  | 69 | 0 | 14.17 | 0 |  | Hardeman | Wilbarger | Tier 4 |  |  |  | 6056, 6057, 6058 | Y | N |  |  | 6630 | 6081
6083 | Wolfgang: Build 69 kV station | Construct new 69 kV ring bus at Wolfgang | NEW | Wolfgang |  | Planned | 842 - 1026 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2682 | 2018-12-31 |  | 69 | 0 | 0 | 0 |  | Kent |  | Tier 4 |  |  |  | 6162 | Y | N |  |  | 6632 | 6083
6092 | Port Aransas - Seawall 69 kV line rebuild | Rebuild ~8.1 miles of 69 kV line from Port Aransas to Seawall |  | Aransas Pass | Seawall | Planned | 862-1040 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2698 | 2018-12-31 |  | 69 | 0 | 8.1 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8435, 8442 | Y | N |  |  | 6642 | 6092
4425 | New TR-JV Ckt 961 | Add 2nd Ckt from TR to HL to tie-in to HL-JV Ckt 961 bypassing HL and creating TR-JV Ckt. |  | Techridge | Jollyville | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2019-03-02 |  | 138 | 1.7 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9190, 9217, 9223 | Y | N |  |  | 4809 | 4425
5429C | Phase 3 of the conversion to 138kV | The three way tie will be retired and 138kV locust will tie directly to 138kV Woodrow. The Spencer Int. to the 3way tie will be reconfigured to terminate at the new 138kV Brinker substation. |  | Locust | Spencer Int. | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2019-03-11 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 99999, 921, 924, 982 | Y | N | N/A |  | 5944 | 5429
5430I | Conversion to 138kV | Reconstruct the 69kV Hickory - Locust to be 138kV capable but temporarily operated at 69kV |  | Hickory | Locust | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2019-03-11 |  | 69 | 0 | 2.388 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 910, 914 | Y | N | N/A |  | 5952 | 5430
4464B | Comal to Loop 337 Transmission Line Upgrade | Upgrade/Replace underrated switches to 2000 Amp Switches. Replace and increase fault interrupting rating of breakers 430, 440, 3370, 3380, 5680, 5690, 5700, 2970 to 63kA. | Switches may be dynamically rated during Winter peak conditions. | Comal | GPI Switchyard | Planned |  | NBU | Greg Baumbach gbaumbach@nbutexas.com 830-629-8441 |  | 2019-05-01 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  | 7176, 7456, 7459 | Y | N |  |  | 5206 | 4464
14TPIT0056 | Northaven - Morrison 138 kV line | Upgrade existing double-circuit line | Construction schedule change | Northaven | Morrison | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4088-E | 2019-05-15 |  | 138 | 0 | 12 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2657, 2658, 2660, 2661, 2662, 2663, 2782, 2783 | Y | N |  |  | 2598 | 2493
08TPIT0104 | Elgin Switching Station - Elgin 69 kV line conversion to 138 | Rebuild existing 69 kV line and convert to 138 kV operation | Project Deferral | Elgin Switching Station | Elgin | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R471-E | 2019-05-15 |  | 138 | 0 | 5.9 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 3655, 3650, 3651, 3674, 13674 | Y | N |  |  | 3478 | 1335
4252 | Eagle Mountain - Saginaw 138 kV Line | Upgrade existing double-circuit line | Scope and construction schedule change | Eagle Mountain | Saginaw | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5211 | 2019-05-15 |  | 138 | 0 | 27.9 | 0 |  | Tarrant | Tarrant | Tier 3 |  |  |  | 1860, 1864, 1957, 2065, 2066, 2067, 2070, 11860 | Y | N |  |  | 4623 | 4252
14TPIT0010 | Handley - Pantego - Sherry 138 kV line | Upgrade existing line | Construction schedule change | Handley | Sherry | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5155-E | 2019-05-15 |  | 138 | 0 | 8.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1919, 1920, 1950, 1951, 2219, 2233, 2245, 2246, 2247, 2248, 2250, 2232, 2251, 2252 | Y | N |  |  | 4638 | 2582
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line |  | Handley | Hemphill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5214 | 2019-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 4643 | 4270
4275 | Hutto Switching Station 138 kV capacitors | Install shunt capacitors |  | Hutto Switching Station |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R798 | 2019-05-15 |  | 138 | 0 | 0 | 0 | 0,220.8 | Williamson |  | Tier 4 |  |  |  | 3666 | Y | N |  |  | 4649 | 4275
4554 | Ennis Creek - Cogdell 69 kV Line | Convert existing line to 138 kV operation |  | Ennis Creek | Cogdell | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9025 | 2019-05-15 |  | 138 | 0 | 9 | 0 |  | Scurry | Scurry | Tier 3 | 2016-12-15 | 2016-10-11 |  | 1400, 1401, 1402, 1411, 1412, 1410 | Y | N |  |  | 4956 | 4554
4732 | Big Spring West - Stanton East 138 kV Line | Upgrade existing line |  | Big Spring West | Stanton East | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8303 | 2019-05-15 |  | 138 | 0 | 17.6 | 0 |  | Howard | Martin | Tier 4 |  |  |  | 1324, 1326 | Y | N |  |  | 5151 | 4732
4733 | Midland County Northwest Sw. Sta. - Midland East 138 kV Line | Upgrade existing double-circuit line | Project Deferral | Midland County Northwest Sw. Sta. | Midland East | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8304 | 2019-05-15 |  | 138 | 0 | 32.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1171, 1178, 1179, 1182, 1183, 1184 | Y | N |  |  | 5152 | 4733
4757 | Riverton 138 kV Switching Station | Construct new switching station |  | Mason |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8338 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 11083, 1083, 1084, 1093, 1094 | Y | N |  |  | 5177 | 4757
4758 | Sand Lake 138 kV Switching Station | Construct new switching station |  | Sand Lake |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8340 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 11097, 1009, 1080, 1086, 1097 | Y | N |  |  | 5178 | 4758
4795 | Argyle Sw. Sta. - Spencer (TMPA) 138 kV Line | Upgrade Argyle Sw. Sta. - Corinth line section |  | Argyle Sw. Sta. | Corinth | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3202 | 2019-05-15 |  | 138 | 0 | 3 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 1984, 1985 | Y | N |  |  | 5221 | 4795
4800 | Pleasant Valley - Wichita Falls Cogen 138 kV Line | Upgrade existing line |  | Pleasant Valley | Wichita Falls Cogen | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4002 | 2019-05-15 |  | 138 | 0 | 5.6 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  | 1450, 1498 | Y | N |  |  | 5231 | 4800
4802 | Lake Wichita Sw. Sta. Holliday 69 kV Line conversion | Convert existing 69 kV line to 138 kV operation |  | Lake Wichita Sw. Sta. | Holliday | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4009 | 2019-05-15 |  | 138 | 0 | 10.1 | 0 |  | Wichita | Archer | Tier 4 |  |  |  | 1447, 11527, 1423, 1424, 1446, 1449, 1527 | Y | N |  |  | 5233 | 4802
4817 | TI Dallas - Kirkland Park/Coit Road 138 kV Line | Upgrade existing TI Dallas - Schroeder Road line section |  | TI Dallas | Schroeder Road | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4202 | 2019-05-15 |  | 138 | 0 | 1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2607, 2633, 2636, 2637 | Y | N |  |  | 5248 | 4817
4821 | Nacogdoches Southeast - Herty North 138 kV Line | Upgrade existing line |  | Nacogdoches Southeast | Herty North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6049 | 2019-05-15 |  | 138 | 0 | 13.4 | 0 |  | Nacogdoches | Angelina | Tier 4 |  |  |  | 3120, 3319 | Y | N |  |  | 5252 | 4821
4825 | Crockett - Jewett 138kV Line | Upgrade existing line |  | Crockett | Jewett | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6061 | 2019-05-15 |  | 138 | 0 | 39.5 | 0 |  | Houston | Leon | Tier 3 |  |  |  | 3354, 3355, 3357, 3358, 3394 | Y | N |  |  | 5257 | 4825
4827 | Lufkin - Nacogdoches Southeast 138 kV Line | Upgrade existing line |  | Lufkin | Nacogdoches | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6062 | 2019-05-15 |  | 138 | 0 | 21.6 | 0 |  | Angelina | Nacogdoches | Tier 3 |  |  |  | 3120, 3314, 3316, 3315, 3340 | Y | N |  |  | 5259 | 4827
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line |  | Cresson | Rocky Creek | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5228 | 2019-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  | 1881, 2204 | Y | N |  |  | 5261 | 4834
4835 | DeCordova - Cleburne Sw. Sta. 138 kV Line | Upgrade existing line |  | DeCordova | Cleburne Sw. Sta. | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5226 | 2019-05-15 |  | 138 | 0 | 22.6 | 0 |  | Hood | Johnson | Tier 3 |  |  |  | 1891, 2279, 2280, 2281, 2283 | Y | N |  |  | 5262 | 4835
5310 | Everman - Venus 345 kV Double-circuit line | Upgrade existing line |  | Everman | Venus | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1735 | 2019-05-15 |  | 345 | 0 | 34.6 | 0 |  | Tarrant | Ellis | Tier 4 |  |  |  | 1882, 1886, 1906, 1907 | Y | N |  |  | 5811 | 5310
5408 | Herty N Sw. Sta. 138 kV Rebuild |  |  | Herty North | Herty North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6069 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3317, 3319 | Y | N |  |  | 5919 | 5408
5433 | Calf Creek 138 kV Switching Station | Construct new 138 kV switching station |  | Calf Creek |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8308 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Howard |  | Tier 4 |  |  |  | 11322 | Y | N |  |  | 5961 | 5433
5436 | Morgan Creek - McDonald 138 kV Line | Upgrade existing line |  | Morgan Creek | McDonald Rd | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8360 | 2019-05-15 |  | 138 | 0 | 31.8 | 0 |  | Howard | Mitchell | Tier 3 |  |  |  | 1032, 1333 | Y | N |  |  | 5964 | 5436
5438 | Odessa North-Crane 69 kV Line Conversion to 138 kV | Convert existing 69 kV line to 138 kV operation |  | Odessa North | Crane | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8369 | 2019-05-15 |  | 138 | 0 | 35 | 0 |  | Ector | Crane | Tier 3 |  |  |  | 1197, 1232, 1234, 1276, 1122, 1123, 1196, 1198 | Y | N |  |  | 5966 | 5438
5439 | China Grove - Snyder 69 kV Line Conversion to 138 kV | Convert existing 69 kV line to 138 kV operation |  | China Grove | Snyder | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8375 | 2019-05-15 |  | 138 | 0 | 28 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  | 1367, 1368, 1369, 1370, 1372, 1305, 1306, 1318, 1319 | Y | N |  |  | 5967 | 5439
5467 | Establish a new 345 kV line | Establish a new 345 kV Line |  | Nacogdoches Southeast | Herty North | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6075 | 2019-05-15 |  | 345 | 13.4 | 0 | 0 |  | Nacogdoches | Angelina | Tier 4 |  |  |  | 3119, 3321 | Y | N |  |  | 5996 | 5467
5475 | Lufkin Sw. Sta. - Herty North Sw. Sta. 345 kV Line | Construct a new 345 kV Line from Lufkin Sw. Sta. to Herty North Sw. Sta. |  | Lufkin Sw. Sta | Herty North Sw. Sta. | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6077 | 2019-05-15 |  | 345 | 8.1 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3117, 3321 | Y | N |  |  | 6005 | 5475
5480 | Trinidad - RichLC 345kV DCKT Line | Upgrade existing DCKT Line |  | Trinidad Sw. Sta. | Richland Chambers Sw. Sta | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6027 | 2019-05-15 |  | 345 | 0 | 37.4 | 0 |  | Henderson | Freestone | Tier 4 |  |  |  | 3123, 3124, 3133, 3134 | Y | N |  |  | 6024 | 5480
5487 | NW Carrollton - Lewisville South (TNMP) 138 kV Line | Upgrade existing Northwest Carrollton - Lewisville South 138 |  | Northwest Carrollton | Lewisville South | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3210 | 2019-05-15 |  | 138 | 0 | 3.4 | 0 |  | Dallas | Denton | Tier 4 |  |  |  | 2363, 37100 | Y | N |  |  | 6050 | 5487
5492 | Venus - Webb/Cedar Hill Sw. Sta. 345 kV DCKT Line | Upgrade existing Venus - Webb/Cedar Hill Sw. Sta. 345 kV Double Ckt Line |  | Ellis | Tarrant | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4230 | 2019-05-15 |  | 345 | 0 | 27 | 0 |  | Ellis | Tarrant | Tier 4 |  |  |  | 1904, 1906, 1907, 1911, 2420, 11901 | Y | N |  |  | 6055 | 5492
5500 | Lamar Blossom - Paris East Tap 138 kV Line | Construct new 138 kV line and ring bus |  | Lamar Blossom | Paris East Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4103 | 2019-05-15 |  | 138 | 10 | 0 | 0 |  | Lamar | Lamar | Tier 4 |  |  |  | 1769, 1770, 1771 | Y | N |  |  | 6065 | 5500
5526 | Forney 345 kV Switching Station | Reconstruct existing 345 kV switching station |  | Forney |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4114 | 2019-05-15 |  | 345 | 0 | 0 | 0 |  | Kaufman |  | Tier 3 |  |  |  | 2467, 2433, 2437, 2478, 150189, 2438, 12438 | Y | N |  |  | 6078 | 5526
5543 | Richland Hills 138 kV Switch | Rebuild the existing 138 kV Switching Station |  | Richland Hills | Richland Hills | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5240 | 2019-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2099, 2100 | Y | N |  |  | 6096 | 5543
5801 | Hutto - Rnd Rck SE - Gil | Upgrade138 kV line | Construction schedule change | Hutto | Gilleland |  |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2005 | 2019-05-15 |  | 138 | 0 | 7.5 | 0 |  | Williamson | Travis | Tier 4 |  |  |  | 3654, 3666, 7336 | Y | N |  |  | 6366 | 5801
5981 | Shamburger North 345/138 kV Sw. Sta. | Establish Shamburger North 345/138 kV Sw. Sta. |  | Shamburger North |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6083 | 2019-05-15 |  | 345 | 0 | 0 | 600 |  | Smith |  | Tier 4 |  |  |  | 3217, 3223, 3226, 2470, 3103, 3201, 3206 | Y | N |  |  | 6521 | 5981
5982 | Relocate existing Shamburger North - Shamburger 138 kV Line |  |  | Shamburger North | Shamburger | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6084 | 2019-05-15 |  | 138 | 10 | 0 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3104, 3206, 3226 | Y | N |  |  | 6522 | 5982
5984 | Mulberry Creek 345 kV Switching Station | Rebuild existing Mulberry Creek 345 kV Switching Station |  | Mulberry Creek |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9022 | 2019-05-15 |  | 345 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  | 6230 | Y | N |  |  | 6524 | 5984
5524 | Royse South 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | South Royse |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4234 | 2019-05-16 |  | 345 | 0 | 0 | 600 |  | Rockwall |  | Tier 3 |  |  |  | 2469, 2470, 12471, 2467, 2471, 2478, 2702, 2710, 3103 | Y | N |  |  | 6076 | 5524
5525 | Forney - Lake Hubbard 345 kV Line | Construct new 345 kV line |  | Forney | Lake Hubbard | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4233 | 2019-05-16 |  | 345 | 0 | 8 | 0 |  | Kaufman | Dallas | Tier 4 |  |  |  | 2455, 2467 | Y | N |  |  | 6077 | 5525
5496 | Forney - Royse 345 kV Line | Upgrade existing Royse - Forney 345 kV Line |  | Royse | Forney | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4235 | 2019-05-17 |  | 345 | 0 | 30 | 0 |  | Rockwall | Kaufman | Tier 4 |  |  |  | 2437, 2467, 2470, 2474, 2478 | Y | N |  |  | 6059 | 5496
5522 | Lake Hubbard 345/138 kV Switching Station | Construct new 345/138 kV switching station |  | Lake Hubbard |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4139 | 2019-05-17 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  | 12455, 12456, 2401, 2402, 2455 | Y | N |  |  | 6074 | 5522
5495 | Handley - Sherry 138 kV Line | Upgrade existing Hurst - Brookhollow 138 kV Line section |  | Hurst | Brookhollow | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5216 | 2019-05-18 |  | 138 | 0 | 9.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2116, 2121, 2134, 2244 | Y | N |  |  | 6058 | 5495
5466 | Herty North Sw. Sta. 345/138 kV Autotransformer | Install new 345/138 kV Autotransformer at Herty North Sw. Sta. |  | Herty North | Herty North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6076 | 2019-05-28 |  | 345 | 0 | 0 | 600 |  | Angelina | Angelina | Tier 4 |  |  |  | 835, 3321, 3322, 3319 | Y | N |  |  | 5995 | 5466
4445 | Kerrville Stadium to Harper Road Transmission Line Upgrade | Upgrade the 1.6 mile Kerrville Stadium (7138) - Harper Road (7140) 138-kV transmission line to bundled 795 ACSR Drake, 440 MVA. |  | Kerrville Stadium | Harper Road | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015115 | 2019-05-31 |  | 138 | 0 | 1.6 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  | 7138, 7140 | Y | N |  |  | 4833 | 4445
4465 | Wirtz to FlatRock to Paleface Transmission Line Upgrade | Upgrade the 17.34 mile Wirtz (7104) - Flat Rock (7111) - Paleface (7477) 138-kV transmission line to single 795 ACSR Drake, 221 MVA. |  | Wirtz | Paleface | Conceptual |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2019-05-31 |  | 138 | 0 | 17.34 | 0 |  | Burnet | Travis | Tier 3 |  |  |  | 7104, 7111, 7477 | N | N |  |  | 4851 | 4465
4473 | Zorn to Marion 2nd 345-kV Transmission Line Addition | Add 345-kV Zorn (7042) to Marion (7044) 2nd circuit using bundled Suwannee. Portion of the CPS-Tie Project. |  | Zorn | Marion | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015208 | 2019-05-31 |  | 345 | 18 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 1 | 2014-06-29 | 2015-03-26 | 2015-04-14 | 7042, 7044 | Y | N |  |  | 4859 | 4473
4488 | Campwood to Uvalde: Rebuild 69 kV line | Rebuild Campwood to Uvalde 69 kV line with 959.9 ACSS/TW and energize as 138 kV and add 138/69 kV autotransformer capacity at Campwood |  | Campwood | Uvalde | Planned | 707 - 0877 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2901 | 2019-05-31 |  | 138 | 0 | 37.1 | 90 |  | Real | Uvalde | Tier 2 |  |  |  | 8230, 8633, 8231 | Y | N |  |  | 4882 | 4488
4844 | 2nd Marion Autotransformer | Add a Second 345/138-kV Autotransformer at Marion. Part of the CPS Tie Project |  | Marion | Marion | Planned | 4473 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015208 | 2019-05-31 |  | 345 | 0 | 0 | 478 |  | Guadalupe | Guadalupe | Tier 1 | 2014-06-29 | 2015-03-26 | 2015-04-14 | 77044, 7044, 7178 | Y | N |  |  | 5271 | 4844
5242 | Clodine to Barker Ckt.73 Thermal Uprate | Upgrade Ckt.73 Clodine to Barker to increase thermal ratings | Delay in project schedule | Clodine | Barker | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1055 | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44052, 44140 | Y | N |  |  | 5742 | 5242
5244 | Hardy to Northside Ckt.91 Thermal Uprate | Upgrade Ckt.91 Hardy to Northside to increase thermal ratings | - Overall Date Update | Hardy | Northside | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45840, 47711 | Y | N |  |  | 5744 | 5244
5273 | Bergheim Substation Upgrade | Add a 345-kV bus and a 345/138-kV 336 MVA autotransformer at Bergheim Substation. |  | Bergheim |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016178 | 2019-05-31 |  | 345 | 0 | 0 | 336 |  | Comal |  | Tier 4 |  |  |  | 7770, 7771, 7043, 7046, 7170 | Y | N |  |  | 5774 | 5273
5274 | Camp Wood - Leakey Transmission Line Overhaul | Rebuild T269 Camp Wood to Leakey to be 138-kV capable with a nominal conductor rating of 223 MVA at 138-kV (Single Drake) with OPGW and operated at 69-kV. |  | Camp Wood | Leakey | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016183 | 2019-05-31 |  | 69 | 0 | 17.3 | 0 |  | Real | Real | Tier 4 | 2015-12-16 | 2016-01-27 |  | 7426, 8633 | Y | N |  |  | 5775 | 5274
5717 | Waller 138kV Substation Reconfiguration | Convert Waller substation from single-circuit radial service to radial & tap service. Install new tap section from Ckt.65 Hockley to Peters. |  | Waller | Hockley/Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-05-31 |  | 138 | 2.4 | 0 | 0 |  | Harris | Austin | Tier 4 |  |  |  | 46561, 46560, 45885, 46220 | Y | N |  |  | 6284 | 5717
5922 | Flatonia - Waelder Transmission Line Overhaul | Upgrade T513 from Flatonia to Waelder to 795 ACSR Drake conductor with minimum rating of 111 MVA at 69-kV and 138-kV capable with OPGW. |  | Flatonia | Waelder | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-05-31 |  | 69 | 0 | 11.8 | 0 |  | Gonzales | Fayette | Tier 4 |  |  |  | 7232, 7247 | N | N |  |  | 6455 | 5922
5946 | Winchester Autotransformer Additions | Add two 672 MVA autotransformers at Winchester Substation. Cut the new 345-kV bus @ Winchester into existing Austin Energy owned 345-kV transmission line from FPP to Lost Pines. |  | FPP #1 | Lost Pines | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-05-31 |  | 345 | 0 | 0 | 1344 |  | Fayette | Bastrop | Tier 3 |  |  |  | 77306, 77308, 77309, 7056, 9041, 7306 | N | N |  |  | 6482 | 5946
11TPIT0008 | Rainey St 138kV substation | Establish a new 138kV Rainey St substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2019-06-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9261, 9118, 9132 | Y | N |  |  | 1033 | 1032
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  | 5601, 5600, 5602 | Y | N |  |  | 1554 | 1538
17TPIT0002 | Hunt Lane to Pinn Road - 138 kV Transmission Line Rebuild | Rebuild approximately eight circuit miles of 138 kV transmission from Hunt Lane to Pinn Road |  | Hunt Lane | Pinn Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0190 | 2019-06-01 |  | 138 | 0 | 8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5054, 5305, 5345, 5427 | Y | N |  | There are no transformers associated with this project | 2383 | 2307
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-06-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  | 5705 | Y | N |  |  | 2660 | 2554
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-06-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 5626, 5634 | Y | N |  |  | 4100 | 3818
4084 | Barton-Vega: Upgrade Ckt 928 | Reconductor to 2000 amps |  | Barton | Vega | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2019-06-01 |  | 138 | 0 | 4.05 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9158, 9285 | Y |  |  |  | 4434 | 4084
4438 | BenDavis-Murphy 138kV Line Upgrade | BenDavis-Murphy 138kV Line Upgrade |  | Ben Davis | Murphy | Planned |  | GARLAND/GPL-TMPA and Oncor | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2019-06-01 |  | 138 | 0 | 4.3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 968, 2696 | Y | Y |  |  | 4824 | 4438
4652 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2019-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9276, 9077, 9238 | Y |  |  |  | 5053 | 4652
5144 | CPSE_Pleasanton Rd Transmission Rebuild | Rebuild approximately seven circuit miles of 138 kV transmission on Pleasanton Road from Loop 410 to Harlandale Tap. This project includes partial rebuild of the Sommers to Harlandale and Sommers to Merida 138 kV transmission circuits. |  | Sommers | Harlandale/Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0192 | 2019-06-01 |  | 138 | 0 | 7 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5190, 5310, 5395 | Y | N |  |  | 5622 | 5144
5145B | Rafter - New 138 kV Substation | Build a new 138 kV transmission line from Cagnon to Rafter for voltage support under contingency. |  | CAGNON | RAFTER | Planned | S-0837 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0261 | 2019-06-01 |  | 138 | 8.06 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5055, 5355 | Y | N |  |  | 5624 | 5145
5218 | San Miguel 345/138 kV autotransformer replacements | Replace both existing 300 MVA autos with at least 600 MVA autos-2015 RTP |  | San Miguel |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-06-01 |  | 345 | 0 | 0 | 1200 |  | Atascosa |  | Tier 4 |  |  |  | 5901, 5902, 5908, 5909 | Y | N |  | Delayed from 2018 to 2019 in the 2016 RTP. | 5708 | 5218
5221 | Move Oaks load to 138 kV bus | Move the Oaks load from the 69 kV to the 138 kV instead of replacing auto. 2015 RTP |  | Oaks |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2019-06-01 |  | 138 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5713 | Y | N |  |  | 5713 | 5221
5417 | Buckeye to LA_HTS Rebuild | Rebuild 1.8 mile 138 kV t-line from Buckeye to LA_Hts. |  | Buckeye | LA_Hts | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0266 | 2019-06-01 |  | 138 | 0 | 1.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5050, 5285 | Y |  |  |  | 5930 | 5417
5024 | Crane Loop: Rebuild 69 kV line | Rebuild Crane Loop 69 kV line | Project Description and Contact Update | Crane | Crane | Planned | 738 - 0921 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2619 | 2019-06-30 |  | 69 | 0 | 8.05 | 0 |  | Crane | Crane | Tier 4 |  |  |  | 6600, 6603, 6607, 6609, 6606, 6608, 6613 | Y | N |  |  | 5486 | 5024
5257 | Solstice to Permian Basin: Rebuild 138 kV line | Rebuild Solstice to Permian Basin 138 kV line and add dynamic reactive devices at Lotebush | Project Description and Contact Update | Solstice | Permian Basin | Planned | 713 - 0946 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2636 | 2019-06-30 |  | 138 | 0 | 37.5 | 0 |  | Pecos | Ward | Tier 1 | 2015-12-15 |  |  | 6656, 6673, 60385, 60392, 60397, 6657, 60393, 60415 | Y | Y |  |  | 5757 | 5257
5259 | Lotebush: Add dynamic reactive device | Rebuild Solstice to Permian Basin 138 kV line and add dynamic reactive device and Lotebush | Project Description and Contact Update | Lotebush |  | Planned | 713 - 0946 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2638 | 2019-06-30 |  | 138 | 0 | 0 | 0 | -25100 | Reeves |  | Tier 1 | 2015-12-15 |  |  | 60392 | Y | N |  |  | 5759 | 5259
3877 | Meadow Lake Substation Addtion | Add a new load serving substation (ring-bus) at Meadow Lake. The station will be built between Cushman and Highway 123 off T572. |  | Cushman | Highway 123 | Planned |  | LCRATSC/GVEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016198 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7720, 7221, 7226 | Y | N |  |  | 5765 | 3877
5535 | Lynx to Rio Pecos: Rebuild 138 kV line | Construct a new 138 kV ring bus near Woodward #1 Tap on the Fort Stockton to Rio Pecos Line and rebuild Lynx to Rio Pecos 138 kV line | Cost Update | Lynx | Rio Pecos | Planned | 788 - 973 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2648 | 2019-06-30 |  | 138 | 0 | 2.23 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 6601, 60400 | Y | N |  |  | 6088 | 5535
5915 | Cypress Creek Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Cypress Creek Substation (This is a two year project). |  | Cypress Creek |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7156 | N | N |  |  | 6448 | 5915
5916 | Darst Creek Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Darst Creek Substation (138-kV capable). |  | Darst Creek |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 69 | 0 | 0 | 0 |  |  | Guadalupe | Tier 4 |  |  |  | 78195 | N | N |  |  | 6449 | 5916
5917 | Desert Mesa Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Desert Sky Tap #1 (S566). |  | Desert Sky Tap #1 |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 76022 | N | N |  |  | 6450 | 5917
5920 | Fourmile Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Indian Mesa/Orion/NWP Tap (S564). |  | Indian Mesa/Orion/NWP Tap |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 76019 | N | N |  |  | 6453 | 5920
5927 | King Mountain Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at King Mountain West Tap (S563). |  | King Mountain |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Crane |  | Tier 4 |  |  |  | 76635 | N | N |  |  | 6460 | 5927
5930 | Robbins Switch Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Robbins Switch (S547). |  | Robbins Switch |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  | 76597 | N | N |  |  | 6463 | 5930
5931 | Shiner Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Shiner (S183). |  | Shiner |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Lavaca |  | Tier 4 |  |  |  | 7238 | N | N |  |  | 6464 | 5931
5933 | Tippett Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Desert Sky #2 (S567). |  | Desert Sky Tap #2 | Tippet | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 76016, 6586, 76001, 76013, 76020, 131033 | N | N |  |  | 6466 | 5933
5934 | Warda Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Warda (S407). |  | Warda |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Fayette |  | Tier 4 |  |  |  | 7312 | N | N |  |  | 6467 | 5934
5935 | Webberville Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Webberville (S470). |  | Webberville |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7329 | N | N |  |  | 6468 | 5935
5154 | Holford 138 kV new load substation and connections | Holford 138 kV new substation and its connections to Lookout and to Firewheel as well as some load growths at Holford |  | Lookout | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2019-07-01 |  | 138 | 0 | 2.1 | 0 |  |  |  | Tier 4 |  |  |  | 835, 802, 821, 828 | Y |  |  |  | 5635 | 5154
5430J | Conversion to 138kV | Switch the Hickory - Locust line on to the 138kV substations |  | Hickory | Locust | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2019-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 914, 910 | Y | N | N/A |  | 5953 | 5430
5430K | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line, 1.38miles from Hickory. |  | Eagle |  | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2019-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 926, 922, 924 | Y | N | N/A |  | 5954 | 5430
5430L | Conversion to 138kV | Reconnect the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2019-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 922, 930 | Y | N | N/A |  | 5955 | 5430
5430M | Conversion to 138kV | Transfer the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2019-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 910, 932 | Y | N | N/A |  | 5956 | 5430
5430N | Conversion to 138kV | Retire the existing 69kV RD Wells substation together with the autotransformers |  | RD Wells |  | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2019-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 932, 930 | Y | N | N/A |  | 5957 | 5430
17TPIT0008 | Marion to Cibolo T-Line (T-302) Circuit Addition | Add another 138 kV circuit, to existing Marion to Cibolo T-Line (T-302), 1192 ACSR, 4.81 miles; Replace 3-138 breakers to 63 kA rating at Marion; Add 138 terminal w 138 breaker and associated relaying at Cibolo sub |  | Marion | Cibolo | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2019-09-01 |  | 138 | 4.81 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7178, 7608 | Y | N |  |  | 2962 | 2792
3505 | Cibolo Substation | Add T3, 40 MVA 138-26.18 kV power transformer, CSW and low side |  | Cibolo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2019-09-27 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7608 | Y | N |  |  | 3712 | 3505
4575 | BRYN_4575_New_Steele_Store | Construct New Steele Store substation at 138kV. Project includes the wreck out of the existing Atkins to Annex to Steele Store 69kV line and removal of existing Annex and Steele Store 69kV substations. |  |  |  | Planned |  | BRYN |  |  | 2019-09-30 |  | 138 | 0 | 0 | 0 |  | Burleson |  | Tier 4 | 2015-10-09 | 2015-11-06 |  | 32852, 32866, 32868 | Y |  |  |  | 4982 | 4575
5041 | BRYN_5041_Snook_to_Steele_Store | Construct 138kV line from Snook to Steele Store (Bundled 1033 ACSR - Curlew) as part of the reliability project to loop in Steele Store |  | 32857 | 32852 | Planned |  | BRYN |  |  | 2019-09-30 |  | 138 | 9.2 | 0 | 0 |  | Burleson | Brazos | Tier 4 | 2015-10-09 | 2015-11-06 |  | 32852, 32857 | Y |  |  |  | 5515 | 5041
5234 | Cibolo to Schertz T-Line (T303) | Add 138kV Breakers and associated relaying on both ends |  | Cibolo | Schertz | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2019-10-01 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7608, 7610 | Y | N |  |  | 5732 | 5234
3967 | Leander - Round Rock Transmission Line Addition | Construct a new 138kV transmission line from Leander to Hero Way (new substation) to Parmer (new substation) to Round Rock (approximately 13 miles) using bundled 795 ACSR Drake (446 MVA) conductor. |  | Leander | Round Rock | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014352 | 2019-10-30 |  | 138 | 13 | 0 | 0 |  | Williamson | Williamson | Tier 2 | 2013-12-10 | 2014-05-22 | 2014-06-10 | 7367, 7368, 3668, 7525 | Y | N |  |  | 4288 | 3967
5195 | Rio Pecos: Build 138 kV terminal | Interconnect Pecos solar farm at Rio Pecos | Schedule Update | Rio Pecos |  | Planned | 758 - 0942 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2633 | 2019-10-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6601 | Y | N |  |  | 5679 | 5195
5914 | Crosswinds Substation Addition | LCRA TSC will construct a new three breaker ring bus substation adjacent to PEC's planned distribution substation facility. |  | Turnersville | Goforth | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-10-31 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  | 7503, 7500, 7501 | N | N |  |  | 6447 | 5914
5558C | Proposed Substation |  |  |  |  | Planned |  | RYBRN | Charles Gibune 214-678-1192 |  | 2019-11-01 |  | 138 | 0 | 0 | 0 |  | Fannin |  | Tier 4 |  |  |  | 6817, 1807 | Y | N |  |  | 6114 | 5558
3754 | Heartland to Yellowjacket: Build 69 kV line | Build new 69 kV line from Heartland to Yellowjacket | Project Description and Cost Update | Heartland | Yellowjacket | Planned | 637 - 0806 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2592 | 2019-11-30 |  | 69 | 32 | 0 | 0 |  | Mason | McCulloch | Tier 2 | 2014-01-23 | 2014-11-17 |  | 6379, 60386, 6363, 6378, 6381, 6406 | Y | N |  |  | 4910 | 3754
4519 | Heartland: Build 69 kV station | Construct new 69 kV ring bus between MCEC Brady and Katemcy |  | Heartland |  | Planned | 637 - 0806 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2609 | 2019-11-30 |  | 69 | 0 | 0 | 0 |  | McCulloch |  | Tier 2 | 2014-01-23 | 2014-11-17 |  | 60386 | Y | N |  |  | 4916 | 4519
4530 | Heartland to South Brady Tap: Rebuild existing & build new | Construct a new 69 kV line from Heartland to South Brady Tap and rebuild the existing line from Heartland to South Brady Tap |  | Heartland |  | Planned | 637 - 0806 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2610 | 2019-11-30 |  | 69 | 1.11 | 1.11 | 0 |  | McCulloch | McCulloch | Tier 2 | 2014-01-23 | 2014-11-17 |  | 6379, 60386, 6378, 6381, 6406 | Y | N |  |  | 4930 | 4530
05TPIT0065 | Highway 32-Wimberley | Upgrade and convert the Highway 32 (7546) to Wimberley (7496) transmission line to 138-kV and 795 ACSR (220-MVA). |  | Highway 32 | Wimberley | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2019-12-01 |  | 138 | 0 | 4 | 0 |  | Hays | Hays | Tier 4 |  |  |  | 7496, 7545, 7546 | Y | N |  |  | 998 | 997
3277 | Shepherd Road - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Valley line. |  | Shepherd Road | Cagnon-Valley | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5378, 5053, 5465 | Y | N |  | There are no transformers associated with this project | 3453 | 3277
5275 | Esperanza Substation Addition | Add a new load serving substation (ring bus) at Esperanza. The station will be built between Boerne an Fair Oaks Ranch off T503. |  | Boerne | Fair Oaks Ranch | Planned |  | LCRATSC/PEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016187 | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7710, 5470, 7168 | Y | N |  |  | 5776 | 5275
5491 | Whitestone - Leander 138kV Transmission Line Upgrade | Upgrade the Whitestone - Blockhouse (T469) and the Blockhouse - Leander (T326) 138kV Line to 441MVA. |  | Whitestone | Leander | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2019-12-01 |  | 138 | 0 | 5.4 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 7525, 7527, 7529 | Y | N |  |  | 6054 | 5491
5558D | Proposed Substation |  |  |  |  | Planned |  | RYBRN | Charles Gibune 214-678-1192 |  | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Fannin |  | Tier 4 |  |  |  | 6807, 1835 | Y | N |  |  | 6113 | 5558
5932 | Strempel Substation Addition | New LCRA substation with motor operators. Construct substation with a 33.6 MVA 12.5kV transformer. |  | Seguin | Geronimo | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7219, 7228, 7604 | N | N |  |  | 6465 | 5932
13TPIT0070 | Nash Creek Substation | Replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2019-12-20 |  | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7596 | Y | N |  |  | 3503 | 3322
5964 | Belknap: Build new 138 kV station | Construct new 138 kV ring bus on the Albany to Rainey Creek 69 kV line, remove existing Spillway SW, reterminate Albany to Rainey Creek and Ft Phantom Pump to Onyx lines into Belknap | NEW | Belknap |  | Planned | 843 - 1027 | AEP TNC | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2684 | 2019-12-30 |  | 138 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  | 6211, 60409, 6178, 6219, 6220 | Y | N |  |  | 6504 | 5964
3900 | La Palma to Stewart Road: Rebuild 69 kV line | Rebuild La Palma to Stewart Road 69 kV line with 795 ACSS and add 138/69 kV autotransformer capacity at Stewart Road | Title, Description, and Schedule Update | La Palma | Stewart Road | Conceptual | 678 - 0847 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2597 | 2019-12-31 |  | 69 | 0 | 40.9 | 130 |  | Cameron | Hidalgo | Tier 3 |  |  |  | 8310, 8748, 8751, 8949, 8951 | Y | N |  |  | 4195 | 3900
5189 | Exxon Hawley Tap to Onyx Switch Station: Rebuild 69 kV line | Rebuild Hawley Tap to Onyx Switch Station | Project Description and Contact Update | Hawley Tap | Onyx Switch Station | Planned | 753 - 0939 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 2630 | 2019-12-31 |  | 69 | 0 | 6.57 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6236, 6238, 6388 | Y | N |  |  | 5673 | 5189
5165 | Borglum: Build new 138/69 kV station | Construct new Borglum station near Beeville, add 138/69 kV autotransformer capacity at Borglum, rebuild Three Rivers to Beeville 69 kV line with 959.6 ACSS/TW and convert to 138 kV and terminate into Borglum, rebuild the Beeville to Kenedy Switch 69 kV line as double circuit 138/69 kV with 959.6 ACSS/TW from Tuleta and terminate into Borglum, cut-in Beeville to Sinton 69 kV line into Borglum, and cut-in Beeville to Mathis 69 kV line into Borglum | Schedule Update | Borglum |  | Planned | 742 - 0925 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2914 | 2019-12-31 |  | 138 | 0 | 0 | 130 |  | Bee |  | Tier 1 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8196, 8197, 8205, 8107, 8198, 8904 | Y | N |  |  | 6140 | 5165
5604 | Stewart Road: Construct 345 kV cut-in | Construct new 345 kV 4 breaker ring bus station at AEP Stewart Rd, with two 743 MVA 345/138 autotransformers connected to Stewart Rd 138 station. Hairpin the North Edinburg to SU Palmito 345 kV line into new Stewart Rd 345 station. The hairping will be constructed in a double circuit configuration, approximately 5 miles long. Also install 100 Mvar shunt reactor at the new Stewart Rd 345 kV station. |  | Stewart Road |  | Planned | 792 - 0977 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3582 | 2019-12-31 |  | 345 | 5 | 0 | 743 | 100,0 | Hidalgo | Hidalgo | Tier 2 | 2015-07-10 | 2016-05-19 | 2016-06-14 | 80137, 5966, 8383, 8951 | Y | N |  |  | 6159 | 5604
5621 | South McAllen-Bentsen and North Edinburg-West Edinburg | Replace MLSE equipment at North Edinburg and South McAllen |  | North Edinburg | North McAllen | Planned | 795 - 0980 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3585 | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 5771, 8371, 8380, 8822 | Y | N |  |  | 6176 | 5621
5836 | Rebuild Shady Grove to Advance | Rebuild Shady Grove (Bus #515) to Advance (Bus #518) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 16017 | 2019-12-31 |  | 69 | 0 | 11.34 | 0 |  | Parker | Parker | Tier 4 |  |  |  | 515, 518 | Y |  |  |  | 6403 | 5836
5965 | Benjamin Tap to Katz (BEC): Build new 138 kV line | Construct new 138 kV ring bus Tardis on the Munday to Paducah 138 kV line, rebuild exiting Benjamin Tap to 138 kV, terminate into Tardis, convert Benjamin to 138 kV operation and build new 138 kV line from Benjamin to Katz (BEC) | NEW | Benjamin Tap | Katz (BEC) | Planned | 769-0954 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2685 | 2019-12-31 |  | 138 | 17.7 | 9 | 0 |  | Knox | Knox | Tier 2 |  |  |  | 6320 | Y | N |  |  | 6505 | 5965
6029 | Anson to Stamford 69 kV line: Rebuild 69 kV line | Rehab Anson to Stamford 69 kV line | NEW | Anson | Stamford | Planned | 786 - 0971 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2667 | 2019-12-31 |  | 69 | 0 | 16.08 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6172, 6173, 6175, 6180 | Y | N |  |  | 6578 | 6029
6044 | Big Lake to Barnhart 69 kV line: Rebuild 69 kV line | Rehab Big Lake to Barnhart 69 kV line | NEW | Big Lake | Barnhart | Planned | 786 - 0971 | AEP TNC | Randy Weaver mlforcum@aep.com 918-599-2674 | 2672 | 2019-12-31 |  | 69 | 0 | 17.71 | 0 |  | Reagan | Irion | Tier 4 |  |  |  | 6530, 6534 | Y | N |  |  | 6588 | 6044
6067 | Ft Phantom Splwy to Rainey Crk 69 kV line: Rebld 69 kV line | Rehab Fort Phantom Spillway to Rainey Creek 69 kV line | NEW | Fort Phantom Spillway | Rainey Creek | Planned | 786 - 0971 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2675 | 2019-12-31 |  | 69 | 0 | 8.33 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6215, 6220, 6221, 60409 | Y | N |  |  | 6613 | 6067
6097 | Amoco to Mustang Bayou Ckt.04 | Upgrade 138kV Ckt.04 Amoco to Mustang Bayou to increase thermal ratings. |  | Amoco | Mustang Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2019-12-31 |  | 138 | 0 | 7.5 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 42090, 42960 | Y | N |  |  | 6647 | 6097
5166 | Beeville to Three Rivers: Rebuild 69 kV line | Construct new Borglum station near Beeville, add 138/69 kV autotransformer capacity at Borglum, rebuild Three Rivers to Beeville 69 kV line with 959.6 ACSS/TW and convert to 138 kV and terminate into Borglum, rebuild the Beeville to Kenedy Switch 69 kV line as double circuit 138/69 kV with 959.6 ACSS/TW from Tuleta and terminate into Borglum, cut-in Beeville to Sinton 69 kV line into Borglum, and cut-in Beeville to Mathis 69 kV line into Borglum | Schedule Update | Borglum | Three Rivers | Planned | 742 - 0925 | AEP TCC | Dave Gotez dnlyons@aep.com 918-599-2698 | 2915 | 2020-04-30 |  | 138 | 6 | 22 | 0 |  | Bee | Live Oak | Tier 1 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8196, 8198, 8400, 8403 | Y | N |  |  | 6141 | 5166
5440 | Riverton 345 kV Switching Station | Construct new 345 kV switching station |  | Riverton |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8351 | 2020-05-14 |  | 345 | 0 | 0 | 600 |  | Reeves |  | Tier 1 | 2016-04-20 |  |  | 11084, 11085, 11083 | Y | N |  |  | 5968 | 5440
11TPIT0034 | Sargent Road 345/138 kV autotransformer | Install second 345/138 kV autotransformer | Construction schedule change | Sargent Road |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M486-E | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  | 2946, 2949 | Y | N |  |  | 1826 | 1784
16TPIT0054 | Dialville - Palestine South 138 kV Line | Upgrade existing Dialville - Palestine South line section |  | Dialville | Palestine South | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6019 | 2020-05-15 |  | 138 | 0 | 25 | 0 |  | Cherokee | Andrews | Tier 3 |  |  |  | 3160, 3271, 3296 | Y | N |  |  | 3283 | 3114
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing autotransformer |  | Elkton | Elkton | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6032-E | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 4 |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 3326 | 3155
4759 | Riverton - Sand Lake 138 kV Line | Construct new 138 kV line |  | Riverton | Sand Lake | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8341 | 2020-05-15 |  | 138 | 25 | 0 | 0 |  | Reeves | Reeves | Tier 2 | 2016-02-01 | 2016-11-11 |  | 1011, 1094, 11097, 11083 | Y | N |  |  | 5179 | 4759
09TPIT0116 | Gatesville Tap - Gatesville TDC 69 kV line | Upgrade existing 69 kV line |  | Gatesville Tap | Gatesville TDC | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R497-WA | 2020-05-15 |  | 69 | 0 | 4.4 | 0 |  | McLennan | Coryell | Tier 4 |  |  |  | 3583, 3587 | Y | N |  |  | 5183 | 466
5445 | Riverton-Odessa EHV 345 kV Line | Establish new 345 kV line |  | Riverton | Odessa EHV | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8356 | 2020-05-15 |  | 345 | 85 | 16 | 0 |  | Ector | Reeves | Tier 1 | 2016-04-20 |  |  | 1029, 11084 | Y | N |  |  | 5973 | 5445
5624 | Killeen Sw. Sta. 345/138 kV Autotransformer Replacement | Replace existing autotransformer |  | Killeen Sw. Sta. | Killeen Sw. Sta | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R797 | 2020-05-15 |  | 345 | 0 | 0 | 600 | -75,0 | Bell | Bell | Tier 4 |  |  |  | 3422, 3423, 13423 | Y | N |  |  | 6179 | 5624
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-05-29 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7611 | Y | N |  |  | 3505 | 3324
3776 | Big Lake to Powell Field Junction Tap: Rebuild 69 kV line | Rebuild Big Lake to Powell Field Junction Tap 69 kV line | Project Description, Company Contact, Schedule, and Cost Update | Big Lake | Powell Field Junction Tap | Planned | 667 - 0836 | AEP TNC | Michael Richardson mlforcum@aep.com 918-599-2674 | 2594 | 2020-05-31 |  | 69 | 0 | 11.7 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  | 6533, 6546, 6547, 60395 | Y | N |  |  | 4021 | 3776
5276 | Flatonia - Hallettsville Transmission Line Upgrade | Upgrade T132 Hallettsville to Flatonia (18.7 mi) 138-kV transmission line to a minimum rating of 380 MVA with OPGW. |  | Flatonia | Hallettsville | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016188 | 2020-05-31 |  | 138 | 0 | 18.7 | 0 |  | Fayette | Lavaca | Tier 4 |  |  |  | 7246, 7248 | Y | N |  |  | 5777 | 5276
5277 | Glidden Area Transmission Line Upgrade | Convert existing 69-kV lines (T544) from Glidden to Altair and (T545) from Altair to Nada to 138-kV transmission lines. Relocate existing 45 MVA auto from Glidden to Altair. Add a second new 45 MVA auto at Altair substation. |  | Glidden | Nada | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016219 | 2020-05-31 |  | 138 | 0 | 0.77 | 45 |  | Colorado | Colorado | Tier 4 |  |  |  | 78107, 78111, 78118, 78170, 78171, 78520, 5536, 7258, 78103, 78106 | Y | N |  |  | 5778 | 5277
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into future 138kV Martinez to Skyline transmission line |  | Converse | Martinez-Skyline | Planned | T-0177 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0601 | 2020-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5098, 5294, 5368 | Y | N |  | There are no transformers associated with this project | 968 | 967
3298 | Skyline - Install a Fourth 345kV Autotransformer. | Install one 600 MVA autotransformer at Skyline switchyard. |  |  |  | Planned | S-0670 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 345 | 0 | 0 | 600 |  | Bexar | Bexar | Tier 4 |  |  |  | 5372, 5371, 5368 | Y | N |  | There are no transmission line additions associated with this project | 3474 | 3298
3334 | Fort Sam to Kirby MLSE Upgrade | Upgrade terminals at Fort Sam and ensure a rating of 2000 A at both Fort Sam and Kirby terminals. |  | Fort Sam | Kirby | Planned | S-0747 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5160, 5250 | Y | N |  | There are no transformers associated with this project | 3517 | 3334
3297 | Tezel Road - New 138kV Substation | Loop new 138 kV substation into the existing 138 kV Helotes to Bandera line. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 5421, 5020, 5200 | Y |  |  | There are no transformers associated with this project | 3665 | 3297
3821 | Pearsall to Palo Duro 138 kV line upgrade | Upgrade Pearsall to Palo Duro 138 kV line as recommended in 2013 RTP. Will investigate using a reconductor on existing structures with ACCC and other high temperature conductors. |  | Pearsall | Paloduro | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-06-01 |  | 138 | 0 | 10.8 | 0 |  | Frio | Frio | Tier 4 |  |  |  | 5866, 5895 | Y | N |  |  | 4103 | 3821
4010 | Rebuild Magnolia - Seminole 138 kV line. | *Project pushed back to 2020. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07216 | 2020-06-01 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 38950, 38990 | Y |  |  |  | 4355 | 4010
4443 | CPSE_Fort Sam to Coliseum MLSE | Upgrade terminals at Fort Sam and ensure a rating of 2000 A at Fort Sam for the Fort Sam to Coliseum transmission circuit. |  | Forth Sam | Tenth Street | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5160, 5095 | Y |  |  |  | 4830 | 4443
11TPIT0011 | Northeast 138kV Substation | Northeast 138kV Substation |  | Techridge | Northeast SUB |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2020-06-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9195, 9054, 9190 | Y |  |  |  | 5868 | 5357
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-06-26 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  | 7239 | Y | N |  |  | 3519 | 3336
3901 | Lobo to Freer: Rebuild 69 kV line | Rebuild Lobo to Freer 69 kV line with 795 ACSS | Description Update | Lobo | Freer | Planned | 677 - 0846 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2596 | 2020-06-30 |  | 69 | 0 | 49.8 | 0 |  | Webb | Duval | Tier 3 |  |  |  | 8505, 80222 | N | N |  |  | 4196 | 3901
5206 | Brackettville to Escondido: Construct 138 kV line | Build a double circuit capable 138 kV circuit from Brakettville to Escondido station |  | Brackettville | Escondido | Conceptual | 762-0947 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3570 | 2020-06-30 |  | 138 | 45 | 0 | 0 |  | Kinney | Maverick | Tier 2 | 2016-01-05 | 2017-01-20 | 2017-02-08 |  | Y | N |  |  | 5690 | 5206
5299 | Red Creek to Coke Street: Rebuild 138 kV line | Rebuild Red Creek to Coke Street 138 kV line | Project Description and Schedule Update | Red Creek | Coke Street | Planned | 768 - 0953 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2639 | 2020-06-30 |  | 138 | 0 | 8.01 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6442, 6449 | Y | N |  |  | 5800 | 5299
5444 | Riverton-Solstice 345 kV Line | Establish new 345 kV line |  | Riverton | Solstice | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8355 | 2020-07-01 |  | 345 | 66 | 0 | 0 |  | Reeves | Pecos | Tier 1 | 2016-04-20 |  |  | 11084, 60404 | Y | N |  |  | 5972 | 5444
5882 | Blackland - Weilande 345/138kV additional source | [6 empty] | RYBRN | Charles Gibune 214-678-1192 |  | 2020-07-01 |  | 138 | 0.42 | 0 | 600 |  | Hunt |  | Tier 4 |  |  |  | 6878, 6879, 1647 | Y | N |  |  | 6423 | 5882
5167 | Borglum to Tuleta: Build new double circuit 138/69 kV line | Construct new Borglum station near Beeville, add 138/69 kV autotransformer capacity at Borglum, rebuild Three Rivers to Beeville 69 kV line with 959.6 ACSS/TW and convert to 138 kV and terminate into Borglum, rebuild the Beeville to Kenedy Switch 69 kV line as double circuit 138/69 kV with 959.6 ACSS/TW from Tuleta and terminate into Borglum, cut-in Beeville to Sinton 69 kV line into Borglum, and cut-in Beeville to Mathis 69 kV line into Borglum | Schedule Update | Borglum | Tuleta | Planned | 742 - 0925 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2916 | 2020-07-31 |  | 138 | 23.5 | 10.5 | 0 |  | Bee | Bee | Tier 1 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 88198, 8196, 8197, 8198, 8592, 8590, 8593 | Y | N |  |  | 6142 | 5167
4971 | Bonilla: Build new four breaker 345 kV station | Interconnect Magic Valley II Windfarm at Bonilla to connect Magic Valley II to the North Edinburg to Rio Hondo 345 kV line and construct 345 kV line with 3-954 ACSR from Bonilla to Ladekidde |  | Bonilla | Ladekidde | Planned | 731 - 0913 | AEP TCC | Terry Weeks dnlyons@aep.com 918-599-2698 | 3562 | 2020-08-15 |  | 345 | 20 | 0 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  | 8573, 80506, 80512, 8318, 8383, 80076, 8902 | Y |  |  |  | 5546 | 4971
4505 | BRYN_4505_Smetana_Sub | Construction of a new Smetana Substation at 138kV |  |  |  | Planned |  | BRYN |  |  | 2020-09-30 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32853 | Y |  |  |  | 4902 | 4505
4567 | BRYN_4567_Smetana_Line | Loop in new Smetana Substation at 138kV |  | 32897 | 32863 | Planned |  | BRYN |  |  | 2020-09-30 |  | 138 | 0.75 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32868, 32853, 32863, 32864, 32897 | Y |  |  |  | 4974 | 4567
4571 | Atkins Substation Upgrade | Rebuild Atkins 69kV bus |  | 32864 |  | Planned |  | BRYN |  |  | 2020-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  | No MOD Changes Necessary | 4978 | 4571
4576 | BRYN_4576_Smetana_to_Steele_Store | Construct New 138kV line (Bundled 1033 ACSR - Curlew) to new Steele Store substation as part of the reliability project to loop in Steele Store |  | 32853 | 32852 | Planned |  | BRYN |  |  | 2020-09-30 |  | 138 | 10 | 0 | 0 |  | Brazos | Burleson | Tier 4 | 2015-10-09 | 2015-11-06 |  | 32852, 32853 | Y |  |  |  | 4983 | 4576
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0385 | 2020-12-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5416, 5250, 5395 | Y | N |  | There are no transformers associated with this project | 3190 | 3021
4323 | CPSE_Braunig to Brooks_MLSE | Upgrade terminal at Brooks and ensure a rating of 1364 A (minimum) at both Braunig and Brooks terminals |  | Braunig | Brooks | In-Service |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0669 | 2020-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5030, 5045 | Y | Y |  |  | 4700 | 4323
3777 | Ozona to Midway Lane: Rebuild 69 kV line | Rebuild Ozona to Midway Lane 69 kV line | Project Description and Schedule Update | Ozona | Midway Lane | Planned | 667 - 0836 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2594 | 2020-12-31 |  | 69 | 0 | 16.96 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  | 6549, 6560 | Y | N |  |  | 4022 | 3777
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0733 | 2020-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5045, 5085 | Y | Y |  |  | 4697 | 4320
5198 | Albany to Albany Foundry: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line | Project Description and Schedule Update | Albany Foundry | Albany | Planned | 645 - 0814 | AEP TNC | Jason Bryant mlforcum@aep.com 918-599-2674 | 1809 | 2020-12-31 |  | 69 | 0 | 5.4 | 0 |  | Shackelford | Shackelford | Tier 4 |  |  |  | 6202, 6213, 60398 | Y | N |  |  | 5682 | 5198
5835 | Rebuild Sardis to Reagor Springs | Rebuild Sardis (Bus #202) to Reagor Springs (Bus #210) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 16027 | 2020-12-31 |  | 69 | 0 | 15.46 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  | 202, 210 | Y |  |  |  | 6402 | 5835
5885 | Tardis to Benjamin Tap: Rebuild 69 kV line | Construct new 138 kV ring bus Tardis on the Munday to Paducah 138 kV line, rebuild exiting Benjamin Tap to 138 kV, terminate into Tardis, convert Benjamin to 138 kV operation and build new 138 kV line from Benjamin to Katz (BEC) | Schedule and Cost Update | Benjamin | Tardis | Planned | 769 - 0954 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2656 | 2020-12-31 |  | 138 | 1.67 | 5.99 | 0 |  | Knox | Knox | Tier 2 |  |  |  | 6086, 6087, 6088, 6320, 790, 6037, 6085, 6110, 6107 | Y | N |  |  | 6426 | 5885
5889 | MIRAGE - 138kV Substation Removal | Remove 138kV MIRAGE customer-owned substation from CNP service. |  | MIRAGE | MCCABE/BIMONT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42360, 40209, 42351 | Y | N |  |  | 6431 | 5889
12TPIT0080 | Forney Sw. Sta. Second 600 MVA, 345/138 kV Autotransformer | Add second 345/138 autotransformer | Construction schedule change | Forney Sw. Sta. |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4037 | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 4 | 2008-06-01 | 2008-07-01 |  | 2437, 2438 | Y | N | 2007-R2 |  | 2594 | 2489
13TPIT0064 | Rocky Mound Switching Station series capacitors | Install series capacitors for Willow Creek - Clear Crossing - Dermott Switch (Central B) 345 kV line (Oncor Electric Delivery part) | Construction schedule change | Rocky Mound Switching Station |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | C079-E | 2021-05-15 |  | 345 | 0 | 0 | 0 |  | Haskell |  | CREZ |  |  |  | 17012, 17013, 17014, 17015, 1421, 60515 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2768 | 2644
16TPIT0060 | Midland East - Spraberry 138 kV Line | Upgrade existing line |  | Midland East | Spraberry | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8147-E | 2021-05-15 |  | 138 | 0 | 18.8 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1132, 1133, 1329 | Y | N |  |  | 3343 | 3172
4304 | Tradinghouse - Sam Switch 345 kV Line | Upgrade existing double-circuit line | Construction schedule change | Tradinighouse | Sam Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1706 | 2021-05-15 |  | 345 | 0 | 45.4 | 0 |  | McLennan | Hill | Tier 4 |  |  |  | 3405, 13405, 68090 | Y | N |  |  | 4685 | 4304
4781 | Riverton dynamic reactive device | Install a dynamic reactive device in an existing switching station |  | Mason |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8339 | 2021-05-15 |  | 138 | 0 | 0 | 0 | -60,60 | Reeves |  | Tier 3 |  |  |  | 11083 | Y | N |  |  | 5208 | 4781
4804 | Wichita Falls South 345/138 kV autotransformer | Install autotransformer |  | Wichita Falls South |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4010 | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Archer |  | Tier 4 |  |  |  | 11464, 11465, 1422, 1425, 1464 | Y | N |  |  | 5235 | 4804
4829 | Hutto Sw. Sta. second 345/138 kV autotransformer | Install new autotransformer | Construction schedule change | Hutto |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R750 | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 4 |  |  |  | 13660, 3696, 3666 | Y | N |  |  | 5260 | 4829
4841 | Rivercrest - Sulphur Springs Switch 138 kV Line | Upgrade existing line |  | Rivercrest | Sulphur Springs Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R980 | 2021-05-15 |  | 138 | 0 | 35.7 | 0 |  | Red River | Hopkins | Tier 3 |  |  |  | 6842, 1698, 1780, 1793, 1794, 1796, 1797, 11796, 1800, 11797 | Y | N |  |  | 5268 | 4841
4847 | Belton - Killeen Sw. Sta. 138 kV Line | Upgrade existing line |  | Belton | Killeen Sw. Sta. | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R902 | 2021-05-15 |  | 138 | 0 | 17.2 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3423, 3610, 3633, 13610 | Y | N |  |  | 5274 | 4847
5479 | Trinidad_TriC_Watermill_345kV_DCKT | Upgrade existing DCKT line |  | Trinidad Sw. Sta | TriCorner/Watermill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4045 | 2021-05-15 |  | 345 | 0 | 92.1 | 0 |  | Henderson | Dallas | Tier 4 |  |  |  | 2427, 2432, 3123, 3124 | Y | N |  |  | 6009 | 5479
5939 | Cooks Point Substation and Transmission Line Addition | Construct a load serving 138-kV substation in Northern Burleson County called Cooks Point. Construct a 16.7-mile single circuit 138-kV transmission line from Lyle Wolz to Cooks Point 138-kV transmission line with bundled 795 ACSR Drake (440 MVA). Bryan Texas Utilities will construct a 138-kV transmission line from Steele Store Substation to Cooks Point bundled 1033 ACSR Curlew (495 MVA). |  | Cooks Point | Lyle Wolz | Planned |  | LCRATSC/BBEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2021-05-31 |  | 138 | 16.7 | 0 | 0 |  | Burleson | Burleson | Tier 1 | 2016-07-07 |  |  | 7569, 7567, 32852 | N | N |  |  | 6475 | 5939
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Howard line. |  | Masterson Rd. | Cagnon-Howard | Planned | T-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0538 | 2021-06-01 |  | 138 | 20 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5296, 5054, 5230 | Y | N |  | There are no transformers associated with this project | 2291 | 2218
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and-or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle-Weiderstein | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0645b | 2021-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5360, 5435 | Y | N |  | There are no transformers associated with this project | 2382 | 2306
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0196 | 2021-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 2384 | 2308
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 2000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2021-06-01 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 2548 | 2443
4083 | CPSE_Merida to Westside Rebuild | Rebuild approximately four miles of 138 kV transmission circuit from Merida to Westside. The Merida to Westside circuit should be upgraded to 349 MVA, minimum. |  | Merida | Westside | Planned | S-0773 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0235 | 2021-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5310, 5490 | Y | N |  |  | 4433 | 4083
5222 | Rebuild Dilley to Cotulla 69 kV line | Rebuild 4/0 ACSR 69 kV line with 138 kV capable 795 ACSR. 2015 RTP |  | Dilley | Cotulla | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-06-01 |  | 69 | 0 | 15.8 | 0 |  | La Salle | Frio | Tier 4 |  |  |  | 5863, 5876 | Y | N |  |  | 5714 | 5222
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-11-01 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7622 | Y | N |  |  | 3502 | 3321
5940 | Mountain Home Substation and Transmission Line Addition | Construct new Mountain Home substation, add one(1) 138/69-kV autotransformer at Harper substation, construct a 138-kV transmission line from Hunt substation to Mountain Home substation to Harper substation, convert the existing 69-kV Harper to Live Oak transmission line (T288) to 138-kV, convert Live Oak substation to 138-kV, cut-in the existing Gillespie to Fredericksburg 138-kV transmission line (T379) at Live Oak, and connect the 69-kV Gillespie to Live Oak (T131) and Live Oak to Goehman Tap (T287) transmission lines to create a continuous 69-kV circuit from Gillespie to Goehman Tap. |  | Harper | Hunt | Planned |  | LCRATSC/CTEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2021-11-30 |  | 138 | 19 | 21.7 | 45 |  | Gillespie | Hunt | Tier 1 | 2016-11-18 |  |  | 7412, 7750, 74100, 7410, 7130, 7132, 7144, 7149, 7413 | N | Y |  |  | 6476 | 5940
17TPIT0005 | St. Jo Autos | Replace 40 MVA autos with 60 MVA autos |  | St. Jo | St. Jo | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12005 | 2021-12-01 |  | 138 | 0 | 0 | 60 |  | Cooke |  | Tier 4 |  |  |  | 750, 746 | Y | N |  |  | 2316 | 2243
08TPIT0132 | Melon Creek to Tatton: Build 69 KV Line | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Melon Creek | Tatton | Conceptual | 100 - 0100 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2028 | 2022-03-31 |  | 69 | 9 | 0 | 0 |  | Refugio | Aransas | Tier 2 |  |  |  | 80066, 8410, 8800 | Y | N |  |  | 1175 | 1172
4552 | Yucca Drive - Barnsley/Royalty 69 kV Line conversion | Rebuild existing 69 kV line and convert to 138 kV operation |  | Permian Basin | Barnsley | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8305 | 2022-05-15 |  | 138 | 0 | 50 | 0 |  | Ward | Crane | Tier 3 |  |  |  | 1202, 1203, 11204, 1009, 1015, 1238 | Y | N |  |  | 4954 | 4552
4553 | Yucca Dr - Northern Natural 69 kV Line | Convert existing line to 138 kV operation | Construction schedule change | Permian Basin | Northern Natural | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8295 | 2022-05-15 |  | 138 | 0 | 50 | 0 |  | Ward | Pecos | Tier 3 |  |  |  | 1238, 1239, 1240, 1241, 1242, 1009, 1015 | Y | N |  |  | 4955 | 4553
5286 | Fayette Area Upgrades | Upgrade existing Fayette - Frelsburg - Mockingbird - Glidden (T176) TL with a minimum rating of 380 MVA and with OPGW. Upgrade existing Plum - Flatonia (T133) TL with a minimum rating of 380 MVA and with OPGW. |  | Fayette | Glidden | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Fayette | Colorado | Tier 3 |  |  |  | 7248, 7258, 7263, 7274, 7286, 78259 | N | N |  |  | 5787 | 5286
5752 | City of Brady to Heartland: Build 69 kV line | Construct new 69 kV line from City of Brady to Heartland | Project Description Update | City of Brady | Heartland | Planned | 796 - 0981 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3587 | 2022-05-31 |  | 69 | 2 | 0 | 0 |  | McCulloch | McCulloch | Tier 2 |  |  |  | 6383, 60386 | Y | N |  |  | 6317 | 5752
5945 | Howard Lane to Wells Branch Transmission Line Upgrade | Rebuild the 0.9-mile 138-kV line from Wells Branch (7288) to Howard Lane Tap (7335) in Travis county such that the new 2-hour emergency rating is at least 710 MVA. |  | Howard Lane | Wells Branch | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2022-05-31 |  | 138 | 0 | 0.9 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 7288, 7335 | N | N |  |  | 6481 | 5945
5949 | Study Butte Substation and Transmission Line Addition | Establish a new 69-kV transmission line from Cienega to Study Butte Substation (approximately 61 miles). |  | Cienega | Study Butte | Planned |  | LCRATSC/RGEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2022-05-31 |  | 69 | 61 | 0 | 0 |  | Presidio | Brewster | Tier 4 |  |  |  | 76667, 6682 | N | N |  |  | 6485 | 5949
3894 | Fowlerton 345 station and 345/138 autotransformer | Add 345 kV bus and autotransformer |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-06-01 |  | 345 | 0 | 0 | 600 |  | McMullen |  | Tier 4 |  |  |  | 5709, 5901, 80219, 5705 | Y | N |  |  | 4189 | 3894
5530 | Solstice: Build 345 kV station | Construct two new 345 kV stations, Lynx and Solstice, and new 345 kV lines from Lynx to Solstice and Lynx to Bakersfield |  | Solstice |  | Planned | 789 - 0974 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2649 | 2022-06-30 |  | 345 | 0 | 0 | 743 | -100,0 | Pecos |  | Tier 1 | 2016-04-01 |  |  | 60402, 60404, 60385 | Y | Y |  |  | 6082 | 5530
5538 | Lynx: Build a 345 kV station | Construct two new 345 kV stations, Lynx and Solstice, and new 345 kV lines from Lynx to Solstice and Lynx to Bakersfield |  | Lynx |  | Planned | 789 - 0974 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2650 | 2022-06-30 |  | 345 | 0 | 0 | 743 | -50,0 | Pecos |  | Tier 1 | 2016-04-01 |  |  | 60401, 60403, 60400 | Y | Y |  |  | 6091 | 5538
5539 | Lynx to Solstice: Build 345 kV line | Construct two new 345 kV stations, Lynx and Solstice, and new 345 kV lines from Lynx to Solstice and Lynx to Bakersfield |  | Lynx | Solstice | Planned | 789 - 0974 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2651 | 2022-06-30 |  | 345 | 59 | 0 | 0 |  | Pecos | Pecos | Tier 1 | 2016-04-01 |  |  | 60401, 60404 | Y | Y |  |  | 6092 | 5539
5544 | Lynx to Bakersfield: Build 345 kV line | Construct two new 345 kV stations, Lynx and Solstice, and new 345 kV lines from Lynx to Solstice and Lynx to Bakersfield |  | Lynx | Bakersfield | Planned | 789 - 0974 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2652 | 2022-06-30 |  | 345 | 9 | 0 | 0 |  | Pecos | Pecos | Tier 1 | 2016-04-01 |  |  | 60401, 76002 | Y | Y |  |  | 6097 | 5544
5648 | Hamilton Road to Del Rio, rebuild 138 kV line | Rebuild Hamilton Road to Del Rio 138 kV line |  | Hamilton Road | Del Rio | Conceptual |  | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2022-12-01 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  | 8255 | N | N |  |  | 6207 | 5648
12TPIT0025 | Refugio - Tatton: Rebuild Irreparable 69 kV Line | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Refugio | Tatton | Conceptual | 100 - 0100 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2027 | 2022-12-30 |  | 69 | 0 | 12.6 | 0 |  | Refugio | Aransas | Tier 4 |  |  |  | 8410, 8800 | Y | N |  |  | 1167 | 1164
5647 | Del Rio to Buena Vista, rebuild 138 kV line | Rebuild Del Rio to Buena Vista 138 kV line |  | Del Rio | Buena Vista | Conceptual |  | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2023-04-01 |  | 138 | 0 | 2.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  | 8690 | N | N |  |  | 6206 | 5647
5626 | Hutto North 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | Hutto North | Hutto North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2015 | 2023-05-15 |  | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 4 |  |  |  | 3664, 13661, 13666, 13698, 3666, 3667, 3668, 3669, 3677, 3696, 3699 | Y | N |  |  | 6181 | 5626
15TPIT0031 | Brooks to Chavaneaux - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from Brooks to Chavaneaux |  | Brooks | Chavaneaux | Conceptual |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0207 | 2023-06-01 |  | 138 | 0.1 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5045, 5085, 5330 | Y | N |  | There are no transformers associated with this project | 2380 | 2304
5942 | Merriltown Substation Addition | Add a new 138-kV breakered substation between Wells Branch and Round Rock South on T526 approximately 0.21 miles from Wells Branch. The substation will serve Oncor load. |  | Wells Branch | Round Rock South | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2023-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Williamson | Tier 4 |  |  |  | 7290, 3672, 7288 | Y | N |  |  | 6478 | 5942
5646 | Buena Vista to Picacho, rebuild 138 kV line | Rebuild Buena Vista to Picacho 138 kV line |  | Buena Vista | Picacho | Conceptual |  | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2023-08-01 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  | 8186 | N | N |  |  | 6205 | 5646
4490 | LaPalma: Add 2nd 345/138 kV autotransformer | Add 345/138 kV autotransformer capacity at LaPalma |  | LaPalma |  | Planned | 710 - 0880 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2664 | 2904 | 2023-09-30 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 3 |  |  |  | 8356, 8317, 8314 | N | N |  |  | 4892 | 4490
4477 | Austrop to Sandow Double 345-kV Transmission Line Upgrade | Upgrade 33.98-mile Austrop (7040) to Sandow (13429) 345-kV double circuit transmission lines to bundled 959 Suwannee conductor (1921 MVA). |  | Austrop | Sandow | Conceptual |  | LCRATSC/Oncor | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2024-05-31 |  | 345 | 0 | 67.96 | 0 |  | Travis | Milam | Tier 1 |  |  |  | 7040, 13429 | N | N |  |  | 4863 | 4477
4479 | Cut T511 Gilleland Creek to Clear Springs into AEN Dunlap | Cut-In the existing Gilleland Creek (7340) to Clear Springs (7050) T511 345kV transmission line into Austin Energy's Dunlap (9044) substation. |  | Gilleland Creek | Clear Springs | Conceptual |  | LCRATSC/AEN | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2024-05-31 |  | 345 | 4 | 0 | 0 |  | Travis | Guadalupe | Tier 1 |  |  |  | 7050, 7340, 9044 | N | N |  |  | 4868 | 4479
5287 | Buda to Turnersville Transmission Line Addition | Construct a second 138-kV transmission line between Buda and Turnersville Substations. |  | Buda | Turnersvile | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 3 |  |  |  | 7498, 7500 | N | N |  |  | 5788 | 5287
13TPIT0133 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 5828, 5857 | N | N |  |  | 1579 | 1549
13TPIT0149 | Oaks to Loxley | Build new 138 kV 795 ACSR circuit from Oaks to a new AEP switching station Loxley in the Leon Creek to Pleasanton line | Load forecasts have changed since project was RPG approved | Oaks | Loxley | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 138 | 6 | 0 | 0 |  | Atascosa | Atascosa | Tier 3 | 2011-12-16 | 2012-04-25 |  | 5713, 80491 | N | N |  |  | 2233 | 2161
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits, as recommended in 2013 RTP. |  | Bevo | Carrizo Springs | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 1 | 2012-04-12 | 2012-08-12 | 2012-09-12 | 5871, 8244 | N | N |  |  | 3809 | 3595
3822 | San Miguel to Sigmor 138 kV line upgrade | Upgrade San Miguel to Sigmor 138 kV line as recommended in 2013 RTP. Will investigate re-conductoring on existing structures with ACCC and other high temperature conductors. |  | San Miguel | Sigmor | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 138 | 0 | 26.3 | 0 |  | Atascosa | Live Oak | Tier 3 |  |  |  | 5689, 5706, 8404 | N | N |  |  | 4104 | 3822
5645 | Hamilton Road to Picacho, rebuild 138 kV line | Rebuild Hamilton Road to Picacho 138 kV line |  | Hamilton Road | Picacho | Conceptual |  | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 |  | 2024-06-01 |  | 138 | 0 | 8.8 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  | 8255, 8684 | N | N |  |  | 6204 | 5645
5220 | Move Orange Grove load to 138 kV bus | Move load from the 69 KV to the 138 KV instead of replacing auto. 2015 RTP |  | Orange Grove |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-04 |  | 138 | 0 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  | 5660 | Y | N |  |  | 5712 | 5220
4895 | CPSE_Capitol Cement Transmission Reconfiguration | Re-configurate Capitol Cement by loop into the existing Dresden to Skyline 138 kV transmission line and removing the existing Captiol Cement to Tuttle 138 kV transmission line. |  | Capitol Cement | Dresden/Skyline | Planned | S-0767 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0246 | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5075, 5130, 5370, 5435 | Y | N |  |  | 5332 | 4895
6096 | Obrien to Zenith Ckt.71 | Upgrade Ckt.71 Obrien to Zenith to increase thermal ratings |  | Obrien | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2099-06-01 |  | 345 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44500, 44900 | Y | N |  |  | 6646 | 6096

## CompletedTPIT020117NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2017
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
3363B | Obrien Autotransformer Upgrade | Move existing 600MVA Obrien auto A1 and parallel with existing auto A2. Rename autos 2A & 2B. | Delay in Project Schedule | Obrien |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 681 | 2016-01-01 | 2016-01-17 | 345 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  | 49064, 49065, 44500, 44510 | Y | N |  |  | 4254 | 3363
4540 | Tap 138kV St. Lawrence - Eiland line to create Carterville s |  |  | St. Lawrence | Eiland | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-01-01 |  | 138 | 0 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  | 79560, 79620, 79625 | Y | N |  |  | 4942 | 4540
4401 | Javalina: Build 138 kV Temp Tap | Interconnect Javalina Windfarm at Javalina to connect Bordas to the Molina to Rio Bravo 138 kV line |  | Javalina |  | Planned | 699 - 0869 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3543 | 2016-01-01 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 80646, 80230, 8646 | Y |  |  |  | 4780 | 4401
15TPIT0078 | Tyler Northwest - Tyler 69 kV Line | Upgrade existing line | Construction schedule change | Tyler Northwest | Tyler | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6021-E | 2016-01-15 |  | 69 | 0 | 3 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3142, 3207 | Y | N |  |  | 3231 | 3062
3454 | Braunig_to_Toyota_Rebuild | Rebuild an existing 138 kV transmissions line between the Toyota and Valley Road Substations. |  | Braunig-Alamo1_8-Mauerman-Valley | Alamo1_8-Mauerman-Toyota-Cagnon | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0181 | 2016-01-15 |  | 138 | 0 | 13.7 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5007, 5025, 5053, 5297, 5428, 5465 | Y | N |  | There are no transformers associated with this project | 3655 | 3454
15TPIT0025A | Monticello SES - Monticello Tap 138 kV line | Reconductor existing Monticello Tap - Monticello Mining line section |  | Monticello Mining | Monticello Tap | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R906-E | 2016-01-15 |  | 138 | 0 | 14.7 | 0 |  | Titus | Franklin | Tier 4 |  |  |  | 1791, 1794 | Y | N |  |  | 4520 | 2643
4347 | Renner 345 kV bus rearrangement | Convert 345 kV bus to a ring bus arrangement | Under construction | Renner |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3099A | 2016-01-15 |  | 345 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 2354, 2355, 2359, 2358, 2361, 2513 | Y | N |  |  | 4720 | 4347
15TPIT0025B | Monticello SES - Monticello Tap 138 kV line | Rebuild existing Monticello SES - Monticello Mining 138 kV line section |  | Monticello SES | Monticello Mining | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R906-E | 2016-01-15 |  | 138 | 0 | 5.5 | 0 |  | Titus | Franklin | Tier 4 |  |  |  | 1791, 1795 | Y | N |  |  | 4521 | 2643
3397 | Sterling City: Add 69 kV capacitor banks | Add two 7.2 Mvar capacitor banks at Sterling City | IN-SERVICE and Cost Update | Sterling City |  | In-Service | 629 - 0797 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2586 | 2016-01-18 | 2016-01-18 | 69 | 0 | 0 | 0 | 0,14.4 | Sterling |  | Tier 4 |  |  |  | 6435 | Y | N |  |  | 3595 | 3397
3975 | Bessel 138 kV Station: Construct a new station | Construct four 138 kV breaker ring expandable to six breaker at Bessel 138 kV station | Updated In Service Date, Transmission Status | BESSEL |  | In-Service | 671-0840 | AEP TCC | DAVE GOETZ DNLYONS@AEP.COM 918-599-2698 | 3532 | 2016-01-18 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8060, 80601, 8452, 8514 | Y | N |  |  | 4300 | 3975
3881 | GSEC_3881_Add_Church_Sub |  | NA |  |  | In-Service | NA | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2016-01-19 |  | 138 | 0 | 0 | 0 |  | Callahan | Callahan | Tier 4 |  |  |  | 60367, 60365 | Y | N |  |  | 4171 | 3881
16TPIT0026 | Lon Hill to Smith: Rebuild 69kV line | Rebuild Lon Hill - Smith 69kV Line with 1533.3 ACSR/TW conductor | Reformated project number to match other numbers | Lon Hill | Smith | In-Service | 583 - 0739 | AEP TCC | William Clarke dnlyons@aep.com 918-599-2698 | 3462 | 2016-01-29 |  | 69 | 0 | 3.1 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8448, 8866, 80479, 80480 | Y | N |  | 0 | 1821 | 1779
3845 | Hindes 138kV Substation: STEC Interconnect | Hindes 138kV Substation: STEC Interconnect |  | Dilley SS | San Miguel | Planned | 682 - 0837 | AEP TCC | Mike Tallon dnlyons@aep.com 918-599-2698 | 3531 | 2016-01-30 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 8215, 88215, 5704, 8212 | Y | N |  |  | 4129 | 3845
16TPIT0042 | Uvalde Station: Replace138/69 kV Auto | Upgrade138/69 kV Auto at Uvalde Station | Transmission status, Contact and Cost Update | UVALDE | UVALDE | Under Construction | 739-0922 | AEP TCC | Rick McCraken GAREED@AEP.COM 918-599-2664 | 3566 | 2016-02-01 |  | 138 |  |  | 130 |  | Uvalde |  | Tier 4 |  |  |  | 8231, 8234 | Y | N |  |  | 3741 | 3534
15TPIT0035A | Velasco to West Columbia Upgrades and Conversion to 138kV | Remove 69kV facilities at Velasco. | Delay in project schedule | Velasco |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 637 | 2016-02-03 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43370, 42640, 43140, 49032, 43360 | Y | N |  |  | 2485 | 2388
4183 | Jordan Cap Bank | Move existing Mont Belvieu cap bank #2 to Jordan 138kV substation and increase to 80.0 MVAr | Change in project schedule | Jordan |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 95 | 2016-02-28 | 2016-02-28 | 138 | 0 | 0 | 0 | 0,6.7 | Chambers |  | Tier 4 |  |  |  | 40856, 41114, 40155, 40855, 41111 | Y | N |  |  | 4538 | 4183
3872 | MARINE 138kV Substation | Construct service to new 138kV MARINE customer-owned substation. Loop through Ckt.59 Surfside to Quintana. | Delay in project schedule | MARINE | Surfside/Quintana | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 55 | 2016-02-28 | 2016-03-24 | 138 | 1.5 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 43155, 43360, 43315, 43435 | Y | N |  |  | 4160 | 3872
4748 | Corral: Build 138 kV station | Construct 138 kV POD box bay for customer interconnection between Comstock and Illinois #4 | IN-SERVICE | Corral |  | In-Service | 720 - 0902 | ETT | Eric Scott mlforcum@aep.com 918-599-2674 | 2611 | 2016-02-29 | 2016-02-29 | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 60388, 60389, 6564, 8683 | Y | N |  |  | 5168 | 4748
4204 | Wink 138 kV Switching Station | Upgrade 138 kV bus arrangement to breaker and a half and upgrade 69 kV bus arrangement to a ring bus and install a second 138/69 kV autotransformer. | Combined with project #4206 Construction schedule change | Wink |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8263 | 2016-03-01 |  | 138 | 0 | 0 | 50 |  | Winkler |  | Tier 4 |  |  |  |  | Y | N |  |  | 4561 | 4204
3982 | EF 90 Corpus Tank Farm | EF 90 Corpus Tank Farm - Kepler 69kV substation: Costruct substation | In Service | Koch Upriver | Valero West | In-Service | 615 - 0783 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3498 | 2016-03-01 |  | 69 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8217, 8240, 8469, 8477 | Y | N |  |  | 4307 | 3982
3441 | Falfurrias: Replace 138/69 kV autotransformer | Add 138/69 kV autotranformer capacity at Falfurrias |  | Falfurias |  | Planned | 632 - 0801 | AEP TCC | Brent Harris dnlyons@aep.com 918-599-2698 | 3511 | 2016-03-02 |  | 138 | 0 | 0 | 92 |  | Brooks |  | Tier 4 |  |  |  | 8508, 8510 | Y |  |  |  | 3641 | 3441
17TPIT0007 | Gillespie to Pointer: Rebuild 69 kV line | Rebuild Gillespie to Pointer 69 kV line with 959.6 ACSR |  | Gillespie | Pointer | In-Service | 568 - 0742 | AEP TNC | Aaron Schwerman myturner@aep.com 918-599-2437 | 2579 | 2016-03-02 | 2016-02-05 | 69 | 0 | 6.7 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 6113, 60382, 60346 | Y | N |  |  | 2912 | 2757
15TPIT0024 | Lon Hill to Nelson Sharpe: Reconductor 345kV Line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo | In-Service | Lon Hill | Nelson Sharpe | In-Service | 071 - 0281 | AEP TCC | Michael Glueck dnlyons@aep.com 918-599-2698 | 3180 | 2016-03-04 | 2016-03-04 | 345 | 0 | 20.81 | 0 |  | Nueces | Kleberg | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8455, 85000 | Y | N |  |  | 1422 | 1421
14TPIT0050 | Lon Hill to North Edinburg: Reconductor 345kV Line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo | In-Service | Lon Hill | North Edinburg | In-Service | 071 - 0281 | AEP TCC | Michael Glueck dnlyons@aep.com 918-599-2698 | 3183 | 2016-03-04 | 2016-03-04 | 345 | 0 | 122.88 | 0 |  | Nueces | Hidalgo | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 5660, 8455, 8452, 8905 | Y | N |  |  | 1420 | 1419
4854 | Tunas Creek Substation Addition | Provide transmission service for a generator (15INR0070_1) off T449 138-kV line between Rio Pecos and Indian Mesa Substations. |  | RIO PECOS | INDIAN MESA | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014769 | 2016-03-08 | 2016-03-04 | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 76580, 6584, 6601 | Y | N |  |  | 5281 | 4854
4180 | Cinnamon: Build 69 kV station | Construct new Cinnamon tap on the North San Angelo to San Angelo Grape Creek Tap 69 kV line | IN-SERVICE | Cinnamon |  | In-Service | 695 - 0865 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2809 | 2016-03-15 | 2016-03-15 | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  | 60380, 6459, 6462 | Y | N |  |  | 4535 | 4180
4174 | Cosden 138 kV terminal equipment replacement | Replace terminal equipment on line to Morgan Creek |  | Cosden |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9011 | 2016-03-15 |  | 138 | 0 | 0 | 0 |  | Howard |  | Tier 4 |  |  |  | 1332 | Y | N |  |  | 4527 | 4174
11TPIT0032 | NW Carrollton - Collin second 138 kV circuit |  |  | Collin | Hebron | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M368 | 2016-03-15 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | Y | N | 2009-R13 |  | 5718 | 1055
4171 | Midessa - Midessa South 138 kV Line | Rebuild Midessa South - Midessa Sw. Sta. 138 kV Line on double-circuit 138 kV structures. Install a second circuit. |  | Midessa | Midessa South | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8254 | 2016-03-15 |  | 138 | 9.4 | 9.4 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 11159, 1059, 1120, 1124, 1138 | Y | N |  |  | 4524 | 4171
3934 | Spraberry - Garden City East 138 kV Line | Rebuild existing 69 kV line as a double-circuit 138 kV and 69 kV line |  | Spraberry | Garden City East | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8241 | 2016-03-15 |  | 138 | 33 | 33 | 0 |  | Midland | Glasscock | Tier 3 | 2014-12-01 | 2015-01-01 |  | 1224, 1218, 1221, 1222, 1226, 1328, 1225, 1329, 1330, 1337 | Y | N |  |  | 4236 | 3934
15TPIT0079 | Roanoke Switch - Coppell Switch 138 kV Line Phase 2 | Rebuild existing double-circuit Southlake - Grapevine Junction line section | Construction schedule change | Southlake | Grapevine Junction | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5001C-E | 2016-03-15 |  | 138 | 0 | 7.7 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1852, 2014, 2015, 2018, 2019, 2020, 2023, 2025 | Y | N |  |  | 2690 | 2574
3874 | Morgan Creek - Cosden 138 kV Line | Rebuild existing aged 138 kV line | Construction schedule change | Morgan Creek | Cosden | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9001 | 2016-03-15 |  | 138 | 32.5 | 0 | 0 |  | Mitchell | Howard | Tier 4 |  |  |  | 1032, 1332 | Y | N |  |  | 4164 | 3874
4855 | Mesa View Circuit Breaker Addition | Add a new Long Loop Substation with circuit breakers adjacent to Mesa View Substation between Mesa View Switchyard and West Yates Switch Substations |  | Mesa View Switchyard | West Yates Switch | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014332 | 2016-03-17 | 2016-05-13 | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 76583, 6583, 76013, 76582 | Y | N |  |  | 5282 | 4855
3676 | Foxtail: Build 345 kV station | Interconnect Green Pastures Wind Farm at Foxtail to connect Green Pastures and Vertigo to the Oklaunion to Mulberry Creek 345 kV line | IN-SERVICE | Foxtail |  | In-Service | 648 - 0817 | AEP TNC | Gregory Gibbs mlforcum@aep.com 918-599-2674 | 1813 | 2016-03-24 | 2016-03-24 | 345 | 0 | 0 | 0 |  | Baylor |  | Tier 4 |  |  |  | 6076, 6100, 6235 | Y | N |  |  | 3913 | 3676
4798 | GSEC_4798_Add_Plains_Pandale_Sub |  |  |  |  | Planned |  | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2016-03-24 |  | 138 | 0 | 0 | 10 |  |  |  | Tier 4 |  |  |  | 60388, 60389 | N |  |  |  | 5224 | 4798
4118 | GSEC_4118_Add_Carroll_K_Land_Sub |  |  |  |  | Under Construction | NA | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2016-03-24 |  | 69 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 60378, 6465, 60380 | Y | N |  |  | 4464 | 4118
3868 | Butman Substation | Construct the new Butman substation on the existing LCRA TSC Abilene South to Eskota 138-kV transmission line (T470). |  | Butman | Abilene S / Eskota | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014313 | 2016-03-25 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  | 76318, 76317, 76319 | Y | N |  |  | 4156 | 3868
4974 | Pleasant Farms Circuit Breaker Addition | Install three 138-kV circuit breakers at Pleasant Farms in a ring bus configuration. |  | Pleasant Farms |  | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014331 | 2016-03-29 | 2016-03-29 | 138 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  | 71230 | Y | N |  |  | 5434 | 4974
4522 | Hoefs Road: Build a 69 kV station | Construct new 69 kV in and out substation off the Barrilla Junction to Verhalen line | IN-SERVICE and Cost Update | Hoefs Road |  | In-Service | 690 - 0860 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2607 | 2016-03-31 | 2016-03-31 | 69 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 6654 | Y | N |  |  | 4919 | 4522
16TPIT0023 | South McAllen - Stewart Road: Rebuild 138kV Line | Rebuild South McAllen - Stewart Road 138kV Line |  | South McAllen | Stewart Road | In-Service | 601 - 0763 | AEP TCC | Aaron Schwerman DNLYONS@AEP.COM 918-599-2698 | 3470 | 2016-03-31 | 2016-03-04 | 138 | 0 | 9.8 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8371, 8758, 8951 | Y | N |  | 0 | 1945 | 1896
16TPIT0037 | Rebuild Orange Grove to Casa Blanca | Rebuild 4/0 ACSR 69 kV to 795 ACSR circuit on 138 kV capable structures. |  | Orange Grove | Casa Blanca | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-03-31 | 2016-03-29 | 69 | 0 | 6.7 | 0 |  | Jim Wells | Jim Wells | Tier 1 | 2012-09-05 | 2013-01-31 | 2013-03-12 | 5662, 8166 | Y | N |  |  | 3116 | 2947
3880 | GSEC_3880_Add_Butman_Sub |  | NA |  |  | Under Construction | NA | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2016-03-31 |  | 138 | 0 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 76318 | Y | N |  | Approximate energization date of 10/2015 | 4170 | 3880
15TPIT0051 | Kenedy Switch - Nixon - Seguin Transmission Line Upgrade | Upgrade the 54.2 mile Kenedy Switch (8184) - Nixon (78580) - Deer Creek (New) (7595) from 69kV to 138kV 795 ACSR Drake, 223 MVA. |  | Kenedy Switch | Deer Creek | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1012640 | 2016-04-01 | 2016-03-09 | 138 | 0 | 54.2 | 0 |  | Karnes | Guadalupe | Tier 1 | 2012-09-01 | 2012-10-30 | 2013-03-31 | 78580 | Y | N |  |  | 3969 | 3725
4535 | Add new 138kV Natural Dam Station |  |  | Natural Dam | Natural Dam | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-04-01 |  | 138 | 0 | 0 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79509 | Y | N |  |  | 4937 | 4535
4697 | Adding Blue Acre station & load |  |  | Yosemite | South Midland | Planned |  | SLU | Bradley Schwarz 512-289-7425 |  | 2016-04-01 |  | 138 | 0.9 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 79609, 79610, 79615 | Y | N |  |  | 5107 | 4697
5428A | Phase 2 of the conversion to 138kV | Transfer the load from the existing 69kV Kings Row substation to the new 138kV Kings Row substation |  | Kings Row |  | In-Service | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2016-04-05 | 2016-04-05 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 909 | Y | N | N/A |  | 5939 | 5428
4975 | Rosita Creek Circuit Breaker Addition | Install two 138-kV circuit breakers at Rosita Creek in a single bus-single breaker configuration. |  | Rosita Creek |  | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015128 | 2016-04-22 | 2016-04-25 | 138 | 0 | 0 | 0 |  | Maverick |  | Tier 4 |  |  |  | 78015 | Y | N |  |  | 5435 | 4975
15TPIT0035G | Velasco to West Columbia Upgrades and Conversion to 138kV | Convert Retrieve substation to 138kV and energize with existing Ckt. 02 Lake Jackson to West Columbia. Upgrade Ckt. 02 Lake Jackson to Retrieve and parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | Lake Jackson | Retrieve | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 637 | 2016-04-25 |  | 138 | 0 | 5.34 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43140, 43145, 42880, 43380, 43390 | Y | N |  | Cost included in project 15TPIT0035A. | 5538 | 2388
15TPIT0035B | Velasco to West Columbia Upgrades and Conversion to 138kV | Upgrade Ckt. 02 Retrieve to West Columbia. Parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | Retrieve | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 637 | 2016-04-26 |  | 138 | 0 | 11.9 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43145, 43380 | Y | N |  | Cost included in project 15TPIT0035A. | 2486 | 2388
5503 | Naval Base Station: GIS | Build six breaker expandable to nine breakers GIS |  | Naval Base |  | Under Construction | 607 - 0648 | AEP TCC | Michael Glueck dnlyons@aep.com 918-599-2698 | 3485 | 2016-04-26 |  | 69 | 0 | 0 | 0 |  | Nueces |  | Tier 1 | 2012-07-15 | 2012-12-20 | 2013-01-04 | 88495, 88560, 8487, 8494, 8856 | Y | N |  |  | 6067 | 5503
15TPIT0035C | Velasco to West Columbia Upgrades and Conversion to 138kV | Parallel bundle a portion of Ckt. 02 Hofman to Lake Jackson with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | Hofman | Lake Jackson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 637 | 2016-04-27 |  | 138 | 0 | 3.9 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42810, 42880 | Y | N |  | Cost included in project 15TPIT0035A. | 2487 | 2388
15TPIT0035D | Velasco to West Columbia Upgrades and Conversion to 138kV | Parallel bundle a portion of Ckt. 02 BASF to Hofman with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | BASF | Hofman | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 637 | 2016-04-28 |  | 138 | 0 | 0.84 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42150, 42810 | Y | N |  | Cost included in project 15TPIT0035A. | 2488 | 2388
15TPIT0035E | Velasco to West Columbia Upgrades and Conversion to 138kV | Parallel bundle a portion of Ckt. 02 Brazosport to Velasco with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | Brazosport | Velasco | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 637 | 2016-04-29 |  | 138 | 0 | 1.32 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42110, 42150, 42210, 42215, 42810, 42880, 42915, 43145, 43222, 43360, 43380, 43381 | Y | N |  | Cost included in project 15TPIT0035A. | 2489 | 2388
5030A | Flat Top Tie with AEP Pig Creek | Rebuild de-energized line from TNMP Flat Top-AEP's new Pig Creek station with 1926 ACSR/TW Cumberland. Convert Flat Top to 138 kV service and install circuit breakers. Switch line out of service from Barilla Draw Tap-Flat Top. |  | 60393 | 38070 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2016-04-30 |  | 138 | 0 | 8.85 | 0 |  | Pecos | Reeves | Tier 3 | 2015-01-13 | 2015-06-19 |  | 38070, 38060, 60393 | Y |  |  | Conductor changed from RPG submittal from 795 ACSR to 1926 ACSR/TW Cumberland. Flat Top station changed from RPG to include up to 5 breakers. | 5498 | 5030
4428 | CAMDEN 138kV Substation | Loop Ckt.26 SINTEK to Velasco into new 138kV CAMDEN substation |  | CAMDEN | SINTEK/Velasco | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 55 | 2016-04-30 | 2016-04-12 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43365, 42190, 42510, 43240, 43360, 43300 | Y | N |  |  | 4812 | 4428
3503 | Rebuild Seguin-Deer Creek to 138kV | Rebuild 6/1 miles (Capote to Deer Creek, back to Seguin is 138) single Ckt 69 to 138 kV, 795 ACSR, terminals at Seguin and Deer Creek. (This portion of the T-377 line segment will be out of service from Oct 1, 2015 - Mar 31, 2016) |  | Seguin | Deer Creek | In-Service |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2016-04-30 | 2016-04-18 | 138 | 0 | 6.1 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7228, 7595 | Y | N |  |  | 3710 | 3503
4398 | Razorback: Build new three breaker 138 kV station | Construct new Razorback station along the Uvalde to Castroville (STEC) 138 kV line |  | Uvalde | Castroville STEC | Planned | 611 - 0779 | ETT | Brent Smith dnlyons@aep.com 918-599-2698 | 3494 | 2016-05-01 |  | 138 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 8241, 80241, 5083, 8234 | Y | N |  |  | 4777 | 4398
4545 | Upgrade 138kV Brown - Vealmoor line |  |  | Brown | Vealmoor | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-05-01 |  | 138 | 0 | 15.3 | 0 |  | Martin | Borden | Tier 4 |  |  |  | 79551, 79553, 79600 | Y | N |  |  | 4947 | 4545
5018 | Pig Creek: Build 138 kV temporary tap | Construct new 138 kV temporary tap on the Barrilla Junction to Permian Basin line | IN-SERVICE | Pig Creek |  | In-Service | 737 - 0920 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2617 | 2016-05-04 | 2016-05-04 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60393, 6655, 6673 | Y | N |  |  | 5476 | 5018
5190 | Gas Pad Tap: Build 138 kV temporary tap | Construct 138 kV POD box bay for customer interconnection | IN-SERVICE | Gas Pad Tap |  | Under Construction | 755 - 0938 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2628 | 2016-05-04 | 2016-05-04 | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60397, 1010, 6656 | Y | N |  |  | 5674 | 5190
15TPIT0082 | Collin - Custer (Brazos) 138 kV Line (Oncor's section) | Upgrade existing line |  | Collin | Custer (Brazos) | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R937-E | 2016-05-15 |  | 138 | 0 | 3.5 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 2364, 2365, 2566, 2567 | Y | N |  |  | 3378 | 3207
17TPIT0011 | Carroll Springs 69 kV capacitors | Install shunt capacitor |  | Carroll Springs |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6041-E | 2016-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Anderson | Anderson | Tier 4 |  |  |  | 3270 | Y | N |  |  | 3591 | 3393
13TPIT0113 | Renner 345/138 kV autotransformer | Replace existing 345/138 kV autotransformer with larger autotransformer |  | Renner |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3099B | 2016-05-15 |  | 345 | 0 | 0 | 600 |  | Collin |  | Tier 4 |  |  |  | 2359, 2358, 16358 | Y | N |  |  | 2826 | 1300
06TPIT0047 | Elkton - Tyler Northwest 138 kV line | Upgrade existing Elkton - Tyler West 138 kV line section |  | Elkton | Tyler West | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6023-E | 2016-05-15 |  | 138 | 0 | 4 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3106, 3139 | Y | N |  |  | 1434 | 1433
11TPIT0032 | NW Carrollton - Collin second 138 kV circuit |  | Construction schedule change | NW Carrollton | Hebron | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M368 | 2016-05-15 |  | 138 | 21 | 21 | 0 |  | Dallas | Collin | Tier 4 |  |  |  | 2517, 12516, 902278, 902869, 33629, 629, 659, 663, 2363, 2370, 2377, 2378, 2518, 2519, 12519 | Y | N | 2009-R13 |  | 5719 | 1055
5130 | Establish Mitchell Bend 345 kV Switching Station |  |  |  |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5241 | 2016-05-15 |  | 345 | 0 | 0 | 0 |  | Hood |  | Tier 4 |  |  |  | 1877, 1878, 1879, 1890, 1900 | Y | N |  |  | 5608 | 5130
4529 | Fullerton - North Andrews 138 kV Line | Rebuild existing 69 kV line section as a double-circuit line with a 69 kV circuit and a 138 kV circuit |  | Fullerton | North Andrews | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8294 | 2016-05-15 |  | 138 | 21.7 | 6.9 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1277, 1155, 1156, 1160, 1267, 1159 | Y | N |  |  | 4929 | 4529
4769 | Lake Creek | Upgrade terminal equipment on Lake Creek - Rattlesnake Road 345 kV Line |  | Lake Creek |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2006 | 2016-05-15 |  | 345 | 0 | 0 | 0 |  | McLennan |  | Tier 4 |  |  |  | 3399, 3409 | Y | N |  |  | 5191 | 4769
4277 | Lott 69 kV capacitors | Install shunt capacitors |  | Lott |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R791 | 2016-05-15 |  | 69 | 0 | 0 | 0 | 0,9.2 | Falls |  | Tier 4 |  |  |  | 3642 | Y | N |  |  | 4652 | 4277
4212 | Lamar Blossom 69 kV capacitors | Install shunt capacitors |  | Lamar Blossom |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R974 | 2016-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Lamar |  | Tier 4 |  |  |  | 1772 | Y | N |  |  | 4651 | 4212
4750 | Belton | Upgrade terminal equipment on Belton - Killeen Switch 138 kV Line |  | Belton |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1703 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Bell |  | Tier 4 |  |  |  | 3610, 13610 | Y | N |  |  | 5170 | 4750
4237 | North Andrews - Andrews 69 kV Line | Rebuild existing Means - Fullerton 69 kV line section as a double-circuit line with a 69 kV circuit and a 138 kV circuit |  | Means | Fullerton | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8161 | 2016-05-15 |  | 69 | 15.1 | 15.1 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1284, 1159, 1274, 1285 | Y | N |  |  | 4610 | 4237
4210 | Paris Switch 345/138 kV autotransformer | Replace existing autotransformer |  | Paris Switch |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R959 | 2016-05-15 |  | 345 | 0 | 0 | 600 |  | Lamar |  | Tier 4 |  |  |  | 1692, 1693, 1686 | Y | N |  |  | 4571 | 4210
11TPIT0002 | Lobo to North Edinburg: Construct 345 kV Line | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg | In-Service | Lobo | North Edinburg | In-Service | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3421 | 2016-05-23 | 2016-05-23 | 345 | 154.6 | 0 | 0 |  | Webb | Hidalgo | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80220, 80225, 80307, 80355, 8383, 80219 | Y | N |  |  | 1325 | 1321
3696 | Friend Ranch to Ozona: Rebuild 69 kV line | Rebuild Friend Ranch to Ozona line with 959.6 ACSS/TW | IN-SERVICE | Friend Ranch | Ozona | In-Service | 657 - 0826 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 1821 | 2016-05-23 | 2016-05-23 | 69 | 0 | 3.4 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  | 6550, 6560 | Y | N |  |  | 3939 | 3696
16TPIT0000 | Del Sol: Add a 24 Ohm, 3600 A Series Capacitor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg | In-Service | Del Sol |  | In-Service | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 629 | 2016-05-25 | 2016-05-25 | 345 | 0 | 0 | 0 | 0,933.1 | Starr |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80307, 80355 | Y | N |  | Modeling in 11TPIT0002 | 3312 | 3143
16TPIT0017 | Cenizo: Add a 24 Ohm 3600, A Series Capacitor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg | In-Service | Cenizo |  | In-Service | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 630 | 2016-05-25 | 2016-05-25 | 345 | 0 | 0 | 0 | 0,933.1 | Webb |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80220, 80225 | Y | N |  | Modeled in 11TPIT0002 | 3313 | 3144
16TPIT0041 | Cenizo: Add a 100 MVAR Shunt Reactor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg | In-Service | Cenizo |  | In-Service | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 630 | 2016-05-25 | 2016-05-25 | 345 | 0 | 0 | 0 | -100,0 | Webb |  | Tier 4 |  |  |  | 80220 | Y | N |  |  | 3311 | 3142
16TPIT0040 | Del Sol: Add a 100 MVAR Shunt Reactor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg | In-Service | Del Sol |  | In-Service | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 629 | 2016-05-25 | 2016-05-25 | 345 | 0 | 0 | 0 | -100,0 | Starr |  | Tier 4 |  |  |  | 80355 | Y | N |  |  | 3310 | 3141
4421A | Rothwood Substation Upgrades | Add 2nd 800MVA autotransformer at Rothwood substation |  | Rothwood |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 989 | 2016-05-30 | 2016-07-15 | 345 | 0 | 0 | 800 |  | Harris |  | Tier 4 |  |  |  | 49045, 40900, 46290, 46295 | Y | N |  |  | 4801 | 4421
4460 | Hidden Valley Substation Upgrade | Construct a new 138-kV bus with tie breaker to existing Austin Energy bus at the Hidden Valley substation. Cut McNeil (7334) to Marshall Ford (7356) 138-kV line into the LCRA TSC 138-kV bus at Hidden Valley. |  | Hidden Valley |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015119 | 2016-05-30 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 78207, 7356, 9207, 78220 | Y | N |  |  | 5283 | 4460
4188 | Glenwood to Hardy Ckt.95 Upgrades | Upgrade 138kV Ckt.95 Glenwood to Hardy to increase thermal ratings. |  | Glenwood | Hardy | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1068 | 2016-05-31 | 2015-12-15 | 138 | 0 | 7.5 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40180, 40620, 45840 | Y | N |  |  | 4543 | 4188
5077 | Add 3rd Distribution Transformer at Orchard | Add 3rd Distribution Transformer at Orchard |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2016-05-31 | 2016-08-23 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 44541, 44190, 44540, 44615 | Y | N |  |  | 5557 | 5077
4462 | Clear Springs 345/138-kV Auto Transformer Addition | Energize the standby 345/138-kV 478 MVA auto transformer at Clear Springs substation. |  | Clear Springs |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2016-05-31 |  | 345 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7050, 7680, 77680 | Y | N |  |  | 4848 | 4462
5068 | Add Third Distribution Xer at OB by Tapping OB-FL Ckt73 | Install 3rd distribution transformer tap at Obrien on Ckt.73 Obrien to Flewellen |  | Obrien | Flewellen | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2016-05-31 | 2016-05-16 | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44511, 44512, 44513, 44230, 44510 | Y | N |  |  | 5547 | 5068
4525 | HO Clarke to Heights Ckt.34 | Upgrade 69kV Ckt.34 HO Clarke to Heights to increase thermal ratings. | Accelerated project schedule | HO Clarke | Heights | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2016-05-31 | 2016-06-14 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47165, 47680 | Y | N |  |  | 4922 | 4525
4491 | Marconi: Build new 138 kV temporary tap | Interconnect San Roman Windfarm at Temporary Tap to connect San Roman to the Port Isabel to Laureles 138 kV line |  | Port Isabel | Laureles | Planned | 711 - 0882 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 2905 | 2016-05-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8262, 5756, 8338 | Y | N |  |  | 4885 | 4491
4179 | Tanner 138kV Substation | Build new 138kV Tanner distribution substation. Double tap off Ckt.24 Satsuma - Addicks and Ckt.76 Satsuma - Addicks. |  | Tanner |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1036 | 2016-05-31 | 2016-04-12 | 138 | 1.9 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 46311, 46312, 44910, 45500, 45515, 45610, 45611, 45620, 45802, 46300, 46302, 45600, 45681, 45682, 45811, 46301 | Y | N |  |  | 4534 | 4179
4421B | Rothwood Substation Upgrades | Reconfigure existing 138kV Rothwood circuits to create new Ckt.22 loop from Rothwood to Rayford to Springwood to Rothwood. |  | Rothwood | Rayford/Springwood/Rothwood | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 989 | 2016-05-31 | 2016-08-18 | 138 | 0.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40900, 42110, 46051, 46052, 46261, 46270, 46570, 43150, 43300, 46290, 46295, 46512 | Y | N |  |  | 4802 | 4421
12TPIT0084 | Lookout 138 kV new substation and connections | Lookout 138 kV new substation and its connections to Apollo and to Firewheel | On Hold For Funding | Apollo | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2016-05-31 |  | 138 | 4.1 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 828, 12683, 802, 821 | Y | N |  |  | 765 | 764
10TPIT0095 | VH Braunig - Grandview 138kV Line Reroute | Reroute VH Braunig - Grandview to become VH Braunig - Coliseum Rd | Delayed due to Rail Road permit | VH Braunig | Grandview |  | S-0746 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0130 | 2016-06-01 |  | 138 | 2.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5030, 5095, 5175 | Y | N |  | There are no transformers associated with this project | 1465 | 1464
16TPIT0030 | New 345kV line from Loma Alta to N Edinburgh | Construct a new 345 kV transmission line from N.Edinburg to Loma Alta (~106.5 mi) and station upgrades | New Changed Dollars to include the station costs associated with the project (Approved by RPG, see comments for breakout) | Loma Alta | N Edinburgh | Planned |  | SLU | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2016-06-01 |  | 345 | 106.5 | 0 | 0 |  | Cameron | Hidalgo | Tier 1 | 2011-05-03 | 2011-12-19 | 2012-01-17 | 5966, 8383 | Y | N |  |  | 2460 | 2371
15TPIT0030 | Mainland - New Substation | Build a new 138-12.47 kV substation to accommodate load growth along I45 between Texas City and Dickinson. Cut TNMP's Freeway Park - Alvin 138 kV line into the new substation. |  | Mainland |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38830, 38820, 39030 | Y | N |  |  | 2089 | 2025
15TPIT0045 | ETP Capacitor | Add 19.2 MVAR capacitor |  | ETP |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-06-01 | 2016-09-15 | 138 | 0 | 0 | 0 | 0,19.2 | Jackson |  | Tier 4 |  |  |  | 5523 | Y | N |  |  | 2659 | 2553
09TPIT0012 | Hill Country to Skyline - 345 kV 2nd Circuit | Build second 345 kV line from Hillcountry to Skyline. The second circuit will be installed on existing transmission structures |  | Hill Country | Skyline | Planned | S-0470 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0052 | 2016-06-01 |  | 345 | 11 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5211, 5371 | Y | N |  | There are no transformers associated with this project | 1404 | 1403
4363 | Miracle Lake 138 kV substation | Add new 138 kV substation between Cross and Pearsall |  | Miracle Lake |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-06-01 | 2016-09-30 | 138 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5700, 5707, 5895 | Y | N |  |  | 4737 | 4363
14TPIT0071 | Princeton South - New Substation | Build a new 138-12.47 kV substation to accommodate load growth in Princeton. |  |  |  | Planned | 16TPIT0005 | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE02815 | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 37295 | N | N |  |  | 2063 | 2011
4608 | Olsen-Walnut Springs Rebuild | Olsen-Clifton-Clifton Tap-Meridian Tap-Walnut Springs Rebuild with 795 ACSR. |  | 37470 | 37680 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE09517 | 2016-06-01 |  | 69 | 0 | 24.77 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  | 37470, 37600, 37620, 37650, 37680 | Y |  |  |  | 5015 | 4608
4909 | Addition of 150 MVAR reactors at Claytonville |  |  | Claytonville | Claytonville | Planned |  | LST | Don Le 713-366-6105 |  | 2016-06-01 |  | 345 | 0 | 0 | 0 | 150,0 | Fisher | Fisher | Tier 4 |  |  |  | 68001 | Y | N |  |  | 5348 | 4909
4908 | Addition of 200 MVAR reactors at West Shackelford |  |  | West Shackelford | West Shackelford | Planned |  | LST | Don Le 713-366-6105 |  | 2016-06-01 |  | 345 | 0 | 0 | 0 | 200,0 | Shackelford | Shackelford | Tier 4 |  |  |  | 68000 | Y | N |  |  | 5347 | 4908
4906 | Addition of Calytonville station and 3-winding auto |  |  | West Shackelford | Scurry | Planned |  | LST | Don Le 713-366-6105 |  | 2016-06-01 |  | 345 | 0 | 0 | 250 |  | Fisher | Fisher | Tier 4 |  |  |  | 68001, 68002, 68003, 11318, 68000 | Y | N |  |  | 5345 | 4906
4882 | Rebuild North Calliham to South Calliham Switch | Rebuild North Calliham to South Calliham Switch from 4/0 to 795 ACSR 138 kV capable |  | South Calliham Switch | North Calliham | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-06-01 | 2016-05-24 | 69 | 0 | 11.8 | 0 |  | McMullen | Live Oak | Tier 4 |  |  |  | 5696, 5698 | Y | N |  |  | 5318 | 4882
4660 | GSEC_4660_Add_BG-Claytonville_Sub |  |  |  |  | Planned |  | GOLDENSPREAD | Chris Koenig ckoeng@gsec.coop 806-349-5201 |  | 2016-06-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 68002 | Y |  |  |  | 5062 | 4660
4977 | Georgetown East Circuit Breaker Addition | Install four 138-kV circuit breakers at Georgetown East in a ring bus configuration. |  | Georgetown East |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015108 | 2016-06-10 | 2016-08-08 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  | 7528 | Y | N |  |  | 5437 | 4977
3966 | Zorn to Seguin Transmission Line Upgrade | Upgrade the 13.2 miles Zorn (7180) - York Creek (7227) - Seguin (7228) 138kV transmission line to single 1433 Merrimack conductor (478 MVA). |  | Zorn | York Creek - Seguin | Planned | ERCOT RTP # 2013-R83 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014341 | 2016-06-16 | 2016-06-16 | 138 | 0 | 13.2 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7180, 7227, 7228 | Y | N |  |  | 4287 | 3966
4857 | Hendrick: Build 138 kV temporary tap | Interconnect Alamo 7 solar farm at temporary tap to connect Alamo 7 to the Abilene Northwest to Paint Creek 138 kV line | IN SERVICE and Cost Update | Hendrick |  | In-Service | 721 - 0903 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2612 | 2016-06-16 | 2016-06-16 | 138 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  | 60387, 6169, 6228 | Y | N |  |  | 5285 | 4857
5362 | Paint Creek: Replace 138/69 kV Autotransformer | Add 138/69 kV autotransformer capacity at Paint Creek | IN SERVICE | Paint Creek |  | In-Service | 781 - 0966 | AEP TNC | Brandon Cogan mlforcum@aep.com 918-599-2674 | 2641 | 2016-06-23 | 2016-06-23 | 138 | 0 | 0 | 90 |  | Haskell |  | Tier 4 |  |  |  | 6161, 6159 | Y | N |  |  | 5873 | 5362
4424A | Gable Street Upgrades | Convert to 138kV and reconfigure existing Ckt.46 Gable Street to Blodgett tap to create new 138kV Ckt.70 Gable Street to East Side. | Delay in project schedule | Gable Street | East Side | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 854 | 2016-06-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47522, 47600, 47630, 47640 | Y | N |  |  | 4805 | 4424
4481 | Linterna: Build a 138 kV tap | Interconnect Roserock solar farm at a temporary tap on the Barrilla Junction to Fort Stockton 138 kV line | IN SERVICE | Linterna |  | In-Service | 706 - 0876 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2812 | 2016-06-28 | 2016-06-28 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60383, 6630, 6655 | Y | N |  |  | 4871 | 4481
3953 | Marfa to Alamito Creek: Rebuild 69 kV line | Rebuild Marfa to Alamito Creek 69 kV line with 959.6 ACSS/TW | IN SERVICE | Marfa | Alamito Creek | In-Service | 669 - 0838 | AEP TNC | Greg Crane myturner@aep.com 918-599-2437 | 2805 | 2016-06-29 | 2016-06-29 | 69 | 0 | 0.7 | 0 |  | Presidio | Presidio | Tier 4 |  |  |  | 6678, 6681 | Y | N |  |  | 4273 | 3953
4424B | Gable Street Upgrades | Install 2nd autotransformer (200MVA) at Gable Street substation. | Delay in project schedule | Gable Street |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 854 | 2016-06-29 |  | 138 | 0 | 0 | 200 |  | Harris |  | Tier 4 |  |  |  | 49056, 47630, 47640 | Y | N |  | Cost included in main project. | 4806 | 4424
13TPIT0157 | Cactus to Ft. Lancaster: Rebuild 69 kV line | Rebuild Cactus to Ft. Lancaster 69 kV line with 959.6 ACSS | IN SERVICE and Cost Update | Cactus | Ft. Lancaster | In-Service | 569 - 0743 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2573 | 2016-06-30 | 2016-06-30 | 69 | 0 | 9.28 | 0 |  | Crockett | Pecos | Tier 4 |  |  |  | 6577, 6578, 6579 | Y | N |  |  | 1844 | 1801
4187 | LaMarque Substation Expansion & Circuit Reconfigurations | Expand LaMarque 138kV substation and loop Ckt.93 into LaMarque to create PHR - LaMarque and LaMarque - West Galveston circuits. Reconfigure circuits south of LaMarque. |  | LaMarque | Hitchcock/West Galv | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 859 | 2016-06-30 | 2016-06-13 | 138 | 0.5 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 42860, 42861, 42015, 42061, 42080, 42600, 42670, 42800, 43290, 43355, 43400, 43505, 43510, 43401, 43500, 43507 | Y | N |  |  | 4542 | 4187
4961 | Adding Pemkiff tap and 138 kV line to Midkiff |  |  | Pemkiff | Midkiff | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-06-30 |  | 138 | 0.3 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  | 79555, 1210, 79612, 79614 | Y | N |  |  | 5419 | 4961
14TPIT0120 | Moore Road 138kV Substation | Build new 138kV Moore Road substation. Loop-Tap through Ckt.08 GBY to Uvalde. | Delay in project schedule | Moore Road | Greens Bayou/Uvalde | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 55 | 2016-06-30 | 2016-03-24 | 138 | 0.6 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40555, 40190, 40560, 40611, 40700, 40710, 40990, 41022, 40281, 40720, 41021, 41430, 41651 | Y | N |  |  | 3047 | 2873
3665 | Texon Tap to Santa Rita: Rebuild & Convert to 138 kV | Rebuild Texon Tap to Santa Rita 69 kV line with 959.6 ACSS/TW and convert Santa Rita to 138 kV by rerouting the Big Lake to North McCamey line through Santa Rita | IN SERVICE and Cost Update | Texon Tap | Santa Rita | In-Service | 643 - 0812 | AEP TNC | Bill Clarke mlforcum@aep.com 918-599-2674 | 1460 | 2016-06-30 | 2016-06-30 | 69 | 0.8 | 3.7 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 6504, 6542, 6541, 6555 | Y | N |  |  | 4736 | 3665
4542 | Add new 345/138kV Einstein station |  |  | Einstein | Einstein | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-06-30 |  | 345 | 0.038 | 0 | 675 |  | Glasscock | Glasscock | Tier 2 |  |  |  | 79565, 79632, 59903, 79617, 79625 | Y | N |  |  | 4944 | 4542
15TPIT0043C | Fort Bend Area Upgrades | Remove Richmond substation from CNP transmission service | Delay in project schedule | Richmond |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 937 | 2016-06-30 | 2016-04-06 | 69 | 0 | 0 | 0 |  | Fort Bend |  | Tier 3 | 2012-09-14 | 2012-10-29 |  | 44580, 44290 | Y | N |  |  | 4569 | 4208
4424C | Gable Street Upgrades | Install in-series reactor at Gable Street substation on Ckt.32 Gable Street to Downtown | Delay in project schedule | Gable Street | Downtown | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 854 | 2016-06-30 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47641, 42015, 42042, 42561, 42581, 42582, 42680, 42690, 42741, 42762, 43052, 43082, 43322, 43372, 47210, 47510, 47600, 47640, 42681, 43505, 43610, 47160, 47350, 47522, 47560, 47630, 47750, 47752, 48098 | Y | N |  | Cost included in main project. | 4807 | 4424
4702 | Britmoore to Sauer Ckts. 73 & 81 | Reconductor Circuits 73 & 81 Britmoore to Sauer and upgrade substation equipment to increase thermal ratings. |  | Britmoore | Sauer | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1131 | 2016-06-30 | 2016-06-09 | 138 | 0 | 3.5 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44656, 44657, 44790, 44794, 44795, 44120, 44210, 44211, 44212, 44213, 44214, 44230, 44620, 44621, 44623, 44624, 44791, 44215, 44513, 44622, 44625, 44792, 44793, 46611, 46615 | Y | N |  |  | 5114 | 4702
4451 | Plum to Flatonia Transmission Line Upgrade | Replace existing conductor and shield wire to achieve conductor rating of 221 MVA for the 0.45 mile portion of T133 and T122 between Flatonia substation and structure 1/3. |  | Plum | Flatonia | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015098 | 2016-06-30 | 2016-06-30 | 138 | 0 | 0.45 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  | 7248, 7274 | Y | N |  |  | 4836 | 4451
4964 | Upgrade conductor on existing Grady to Brown 138 kV line |  |  | Grady | Brown | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-06-30 |  | 138 | 0 | 20.3 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79550, 79551 | Y | N |  |  | 5422 | 4964
4168 | PH Robinson Autotransformer A2 Upgrade | Replace existing 600MVA PH Robinson autotransformer A2 with 800MVA autotransformer. | Accelerated project schedule | P.H. Robinson |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 994 | 2016-06-30 |  | 345 | 0 | 0 | 200 |  | Galveston |  | Tier 4 |  |  |  | 42000, 42015, 49048 | Y | N |  |  | 4517 | 4168
3666 | Atlantic Best Tap to Santa Rita: Rebuild & convert to 138 kV | Rebuild Atlantic Best Tap to Santa Rita 69 kV line with 959.6 ACSS/TW and convert Santa Rita to 138 kV by rerouting the Big Lake to North McCamey line through Santa Rita | IN SERVICE and Cost Update | Altantic Best Tap | Santa Rita | In-Service | 644 - 0813 | AEP TNC | Bill Clarke mlforcum@aep.com 918-599-2674 | 1461 | 2016-06-30 | 2016-06-30 | 138 | 0.7 | 5 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 6504, 6541, 6542, 6555, 60361, 6036, 6536, 6544, 6589, 76032 | Y | N |  |  | 4634 | 3666
5428B | Phase 2 of the conversion to 138kV | Add a temporary 138kV tie from Woodrow to Spencer Interchange |  | Woodrow | Spencer Int | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2016-07-01 | 2016-07-01 | 138 | 0.32 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 921, 982 | Y | N | N/A |  | 5938 | 5428
5249 | Gray_Railhead_Reactors_Relocation |  |  | Railhead | Railhead | Planned |  | CTT | Tim Cook 512-473-2700 |  | 2016-07-01 |  | 345 | 0 | 0 | 0 |  | Carson | Carson | Tier 4 |  |  |  | 79005 | Y | N |  | No inductive capability added since reactors moved from Gray to Railhead | 5749 | 5249
5289 | Add Roughneck 138 kV station |  |  | Roughneck | Roughneck | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-07-01 |  | 138 | 0 | 0 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79567, 79610, 79627 | Y | N |  |  | 5790 | 5289
5288 | Add Pronghorn 138 kV station |  |  | Pronghorn | Pronghorn | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-07-01 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 79566, 79613, 79615 | Y | N |  |  | 5789 | 5288
5558A | Proposed Substation |  |  |  |  | Planned |  | RYBRN | Charles Gibune 214-678-1192 |  | 2016-07-01 | 2016-07-01 | 138 | 0 | 0 | 0 |  | Hopkins |  | Tier 4 |  |  |  | 6872, 1796 | Y | N |  |  | 6115 | 5558
4786 | Apollo-Lookout-Firewheel_LineUpgrade | Apollo to Lookout to Firewheel 138 kV lines upgrade to 495 MVA ratings as well as some load growths at Lookout |  | Apollo | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2016-07-01 |  | 138 | 0 | 4.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 828, 802, 821 | Y | N |  |  | 5211 | 4786
4541 | Add new 345kV Abernathy station and 51 miles line from WR-AN |  |  | White River | Abernathy | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-07-01 |  | 345 | 51 | 0 | 0 |  | Floyd | Hale | Tier 4 |  |  |  | 79506, 79505, 141607 | Y | N |  |  | 4943 | 4541
4555 | Gillette Substation | Construct the new 138-kV Gillette substation (78582) on the existing LCRA TSC Milton (78583) to Nixon AE (78580) 138-kV transmission line. |  | Gillette | Milton / NixonAE | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013518 | 2016-07-29 | 2016-08-12 | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 78582, 78580, 78583 | Y | N |  |  | 4959 | 4555
5241A | South Texas Project to DOW Ckts. 18 & 27 | Upgrade Ckt.18 STP to DOW to increase thermal ratings |  | South Texas Project | DOW | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 888 | 2016-07-30 |  | 345 | 0 | 0 | 0 |  | Matagorda | Brazoria | Tier 4 |  |  |  | 5568, 5915, 43222, 43360, 42195, 42210, 42500, 43221 | Y | N |  |  | 5740 | 5241
5030B | Flat Top Tie with AEP Pig Creek | Rebuild line from Flat Top-Barilla Draw Tap station with 1926 ACSR/TW Cumberland. Convert Barilla Draw Tap and Barilla Draw to 138 kV service and install circuit breakers. Switch line out of service from Barilla Draw Tap-IH20. |  | 38060 | 38070 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2016-07-30 |  | 138 | 0 | 5.73 | 0 |  | Reeves | Reeves | Tier 3 | 2015-01-13 | 2015-06-19 |  | 38060, 38065, 38040, 38070 | Y |  |  | Conductor changed from RPG submittal from 795 ACSR to 1926 ACSR/TW Cumberland. Barilla Draw Tap station changed from RPG to include up to 6 breakers. | 5499 | 5030
5241B | South Texas Project to DOW Ckts. 18 & 27 | Upgrade Ckt.27 STP to DOW to increase thermal ratings |  | South Texas Project | DOW | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 888 | 2016-07-31 |  | 345 | 0 | 0 | 0 |  | Matagorda | Brazoria | Tier 4 |  |  |  | 5915, 42500 | Y | N |  |  | 5741 | 5241
5290 | Add Ringo 138 kV station |  |  | Ringo | Ringo | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-08-01 |  | 138 | 0 | 0 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 79568, 79555, 79614 | Y | N |  |  | 5791 | 5290
5247 | Addition_Allen_Creek_Station |  |  | Allen Creek | Allen Creek | Planned |  | CTT | Tim Cook 512-473-2700 |  | 2016-08-01 |  | 345 | 0 | 0 | 0 |  | Donley | Donley | Tier 4 |  |  |  | 79006 | Y | N |  |  | 5747 | 5247
5248 | Addition_Gray_Allen_Creek_Line |  |  | Gray | Allen Creek | Planned |  | CTT | Tim Cook 512-473-2700 |  | 2016-08-01 |  | 345 | 24.3 | 0 | 0 |  | Gray | Donley | Tier 4 |  |  |  | 79000, 79006 | Y | N |  |  | 5748 | 5248
5558B | Proposed Substation |  |  |  |  | Planned |  | RYBRN | Charles Gibune 214-678-1192 |  | 2016-08-01 | 2016-08-01 | 138 | 0 | 0 | 0 |  | Henderson |  | Tier 4 |  |  |  | 6805, 3801 | Y | N |  |  | 6112 | 5558
14TPIT0011 | Midessa South - Windwood - Midland East 138 kV Line | Upgrade existing line |  | Midessa South | Midland East | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8148-E | 2016-08-04 |  | 138 | 0 | 10.4 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1059, 1116, 1117 | Y | N |  |  | 3631 | 3431
4778 | 800/900 Network Substation | Upgrade terminal equipment on 800/900 Network - West Levee double-circuit 138 kV Line |  | 800/900 Network Substation |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4210 | 2016-08-10 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2808, 2809, 2857, 2858 | Y | N |  |  | 5203 | 4778
15TPIT0083A | Collin - Arco (TMPA) 138 kV Line (Oncor's section) | Add second circuit to existing line from Collin to Frisco (Brazos) |  | Collin | Frisco (Brazos) | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R929 | 2016-08-10 |  | 138 | 1.9 | 0 | 0 |  | Collin | Denton | Tier 4 |  |  |  |  | Y | N |  |  | 3389 | 3216
4779 | West Levee Sw. Sta. | Upgrade terminal equipment on West Levee Sw.Sta. - 800/900 Network 138 kV Line |  | West Levee Sw. Sta. |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4211 | 2016-08-10 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2399, 2400, 12481, 12482 | Y | N |  |  | 5204 | 4779
11TPIT0009 | Dunlap 138kV substation | Install one 30MVA Transformer at Dunlap Substation |  | Dunlap Substation | Dunlap Substation | In-Service |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | 3230_117_2930 3230_117_2933 3240_117_4930 3240_117_4933 | 2016-08-17 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9045 | Y | N |  |  | 1021 | 1020
5243 | BAILEY - Colorado Bend Generator Interconnection (17INR0007) | New 345 kV, 4 breaker ring with two generator leads. Loop from 345kV Ckt.72 WA Parish to Hillje | Change in project schedule, cost, and county | BAILEY | WA Parish/Hillje | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 888 | 2016-08-30 | 2016-08-16 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  | 44040, 44005, 44200 | Y | N |  |  | 5743 | 5243
5004 | Install second Wink Auto | Project delayed until Aug 2016 while waiting for Autotransformer testing and installation. |  | 37900 | 37920 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2016-08-31 |  | 138 | 0 | 0 | 93 |  |  |  | Tier 4 |  |  |  | 37920, 37900 | Y |  |  |  | 5462 | 5004
3267B | Rebuild ERioHondoTo Paredes to Central Avenue 138 kV line | Rebuild Paredes Switch to Central Avenue |  | Central Avenue | Paredes Switch | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-31 | 2016-08-22 | 138 | 0 | 21 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  | 5761, 5766 | Y | N |  | Cost in other phase of project. Project was delayed in spring 2016 by high winds and rains. If new 345 kV line and auto get installed the outage may be allowed in summer of 2016. May be completed as early as August, but very speculative. | 4818 | 3267
5769 | Wirtz Special Protection System | Install an SPS at Wirtz Substation on the Wirtz - Paleface 138kV Line (T365) and the Wirtz - Johnson City 69kV line (T313). The SPS will prevent overload on these lines for several double circuit outages. SPS will over-ride dynamic ratings of these lines. |  | Wirtz | Paleface and Johnson City | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2016-08-31 | 2016-08-31 | 138 | 0 | 0 | 0 |  | Burnet | Travis | Tier 4 |  |  |  | 7104 | Y | N |  |  | 6340 | 5769
4872 | Smoky Hill: Build 345 kV temporary tap | Interconnect Horse Creek wind farm at temporary tap to connect Horse Creek to the Clear Crossing to Edith Clarke 345 kV line | Contact Update | Smoky Hill |  | Under Construction | 726 - 0908 | ETT | Rick McCracken mlforcum@aep.com 918-599-2674 | 2908 | 2016-09-01 |  | 345 |  |  |  |  | Haskell |  | Tier 4 |  |  |  | 6104, 60515, 60701 | Y | N |  |  | 5308 | 4872
4744 | Prairie View Substation 69 KV breaker replacement | Replace an oil breaker with a new 145 KV Siemens Breaker due to test results being marginal | Need to replace prior to next testing cycle | Prairie View | Sunnyside | Planned |  | SBEC | Don Roberts droberts@sbec.org | WO#15-5394 | 2016-09-01 |  | 69 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  | 7666 | Y | N |  | 69 KV oil Breaker testing results have deteriorated and requires replacing | 5164 | 4744
4310 | Long Draw Reactor Addition | Add three breakers and two 100 MVAR reactors at WETT's Long Draw substation |  | Long Draw |  | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2016-09-02 |  | 345 | 0 | 0 | 0 | 200,0 | Borden |  | Tier 4 |  |  |  | 59900 | Y | N |  |  | 4687 | 4310
4087 | Dunlap-Decker Plant: Upgrade Ckt 1027 | Reconductor to 3000 amps as part of AU-DP Corridor Upgrade |  | Dunlap | Decker Plant | In-Service |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2016-09-06 |  | 138 | 0 | 5.21 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9045, 9188 | Y |  |  |  | 4437 | 4087
4216 | Odessa EHV - Spraberry 138 kV Line | Upgrade existing line | Construction schedule change | Odessa EHV | Spraberry | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8257 | 2016-09-15 |  | 138 | 0 | 21.5 | 0 |  | Ector | Midland | Tier 4 |  |  |  | 1027, 1137, 1139, 1329 | Y | N |  |  | 4578 | 4216
13TPIT0121A | Tilden to Reveille 138 kV line | New station between Tilden and Reveille |  | Fowlerton |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-09-15 | 2016-12-01 | 138 | 0 | 0 | 0 |  | McMullen | La Salle | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5705 | Y | N |  | project cost in last phase | 2355 | 2282
3898 | Pleasanton: Replace 138/69 kV autotransformer | Replace 138/69 kV autotranformer capacity at Pleasanton |  | Pleasanton |  | In-Service | 676 - 0845 | AEP TCC | Mark Strabala dnlyons@aep.com 918-599-2698 | 2595 | 2016-09-15 | 2016-09-15 | 138 | 0 | 0 | 90 |  | Atascosa |  | Tier 4 |  |  |  | 8200, 8203 | Y | N |  |  | 4193 | 3898
13TPIT0121B | Tilden to Reveille 138 kV line | Construct a new 138 kV double circuit capable line from Tilden to Fowlerton |  | Tilden | Fowlerton | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-09-16 | 2016-12-01 | 138 | 20.8 | 0 | 0 |  | McMullen | La Salle | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5701, 5705 | Y | N |  | project cost in last phase | 2356 | 2282
13TPIT0121C | Tilden to Reveille 138 kV line | Construct a new 138 kV double circuit capable line from Fowlerton to Reveille |  | Fowlerton | Reveille | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-09-17 | 2016-12-01 | 138 | 38.6 | 0 | 0 |  | McMullen | La Salle | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5705, 8612 | Y | N |  |  | 2357 | 2282
14TPIT0082 | Kenedy Switch to Pettus: Rebuild 69 kV line | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. | KENEDY SWITCHING STATION | PETTUS | In-Service | 603-0765 | AEP TCC | Eric Scott DNLYONS@AEP.COM 918-599-2698 | 3473 | 2016-09-29 |  | 69 |  | 15.9 | 0 |  | Karnes | Bee | Tier 4 |  |  |  | 8184, 8188, 8593 | Y | N |  |  | 3669 | 3464
14TPIT0109 | Kenedy Switch to Tuleta: Build double circuit 138 kV line | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. |  | KENEDY SWITCHING STATION | TULETA | In-Service | 603 - 0765 | AEP TCC | Eric Scott DNLYONS@AEP.COM 918-599-2698 | 3483 | 2016-09-29 | 2016-09-29 | 138 | 16.9 | 16.9 | 0 |  | Karnes | Bee | Tier 4 |  |  |  | 8590, 8186 | Y | N | NA | NA | 3169 | 3000
14TPIT0062 | Kurten Substation Upgrade | Install (3) Breaker ring to support (2) existing 138 lines and (1) existing 138/12.5 transformer (No MOD changes necessary) |  |  |  | Planned |  | BRYN | James Tanneberger 979-821-5763 |  | 2016-09-30 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 3041 | 2867
4461 | Moulton South Substation | Build a new 138-26.18 kV 18-24-30 MVA substation on the LCRA TSC Flatonia to Yoakum 138-kV transmission line. |  | Flatonia | Yoakum | Planned |  | LCRATSC/GVEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015113 | 2016-09-30 | 2016-10-21 | 138 | 0 | 0 | 0 |  | Lavaca |  | Tier 4 |  |  |  | 7237, 7236, 7238 | Y | N |  |  | 4969 | 4461
4876 | Riley: Build 345 kV terminal | Interconnect Electra wind farm at Riley | IN-SERVICE | Riley |  | Under Construction | 727 - 0909 | ETT | Dave Goetz mlforcum@aep.com 918-599-2674 | 2910 | 2016-09-30 | 2016-09-30 | 345 |  |  |  |  | Wilbarger |  | Tier 4 |  |  |  | 6101 | Y | N |  |  | 5312 | 4876
5078 | Los Angeles 138 kV substation | Add a new 138 kV load serving station between Fowlerton and Reveille |  | Los Angeles |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-10-01 | 2017-01-01 | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 5723, 5705, 8612 | Y | N |  |  | 5558 | 5078
4411 | Transmission line upgrade | Upgrade and Reconductor 4.08 miles of transmission line from Switch Station Substation to Spring Creek Substation from 477 AAC to 1033 ACSS conductor. Replace 5.13 miles of static with OPGW. Replace and re-span poles as necessary. Project relieves contingency overload of Gibbons Creek (964) to Greens Prairie (32878), Switch Station (32000) to Post Oak (32001). |  | CSST | CSSC | Planned |  | COCS | Tony Mickalsky tmichalsky@cstx.gov 979-764-3438 |  | 2016-10-01 |  | 138 | 0 | 4.08 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32000, 32004 | Y | N |  |  | 4791 | 4411
16TPIT0012 | Encino to Skyline - 138 kV Substation Equipment Upgrade | Upgrade terminals at Encino and Skyline to ensure a 2420 A rating and remove existing MLSE on Encino to Skyline 138 kV transmission line |  | Encino | Skyline | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0671 | 2016-10-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5140, 5369 | Y | N |  | There are no transformers associated with this project | 973 | 972
4413 | Transmission line upgrade | Upgrade and Reconductor 2.11 miles of transmission line from Spring Creek Substation to Greens Prairie Substation from 477 AAC to 1033 ACSS conductor. Replace 3.81 miles of static with OPGW. Replace and re-span poles as necessary. Project relieves contingency overload conditions for loss of Gibbons Creek (964) to Greens Prairie (32878), Switch Station (32000) to Post Oak (32001). |  | CSSC | CSGP | Planned |  | COCS | Tony Mickalsky tmichalsky@cstx.gov 979-764-3438 |  | 2016-10-01 |  | 138 | 0 | 2.11 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32004, 32003 | Y |  |  |  | 4793 | 4413
4086 | Dunlap-Austrop: Upgrade Ckt 920 | Upgrade conductor and termination equipment to a minimum rating of 3000 amps as part of AU-DP Corridor Upgrade | Delay in Project Schedule | Dunlap | Austrop | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2016-10-15 |  | 138 | 0 | 3.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9045, 9328 | Y |  |  |  | 4436 | 4086
4296 | Midkiff 138 kV Switching Station POI | Establish a 138 kV point of interconnection (POI) | Construction schedule change | Midkiff |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8273 | 2016-10-15 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | Y | N |  |  | 4677 | 4296
16TPIT0038 | Rebuild STEC Mathis to AEP Mathis | Rebuild 69 kV 4-0 to 795 ACSR on 138 kV capable structures. The 1.8 mile section that loops into AEP Mathis will remain 336 ACSR. |  | Mathis | AEP Mathis | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-10-28 | 2016-12-15 | 69 | 0 | 3.42 | 0 |  | Live Oak | San Patricio | Tier 1 | 2012-09-05 | 2013-01-31 | 2013-03-12 | 5668, 8407 | Y | N |  | The original approved project called for 180 MVA rating of the line. Lower load forecasts have delayed the need for that high of an MVA rating. Part of the line will not be rebuilt at this time to save money. | 3117 | 2948
4933 | COPPER Substation | Loop new 138kV COPPER substation from Ckt.02 Brazosport to Seadoc tap |  | COPPER | Brazosport/Seadoc | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 55 | 2016-10-31 | 2016-11-21 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 42215, 42150, 42210, 43360, 42195, 43222 | Y |  |  |  | 5391 | 4933
4994 | Bunker Customer Owned 138 kV Station | Build new 138kV BUNKER customer-owned substation. Loop through Ckt.08 HO Clarke to Knight. | Change in project schedule | BUNKER | HO Clarke/Knight | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1074 | 2016-10-31 | 2016-11-02 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47340, 47090, 47150, 47331, 47420 | Y | N |  |  | 5452 | 4994
4980 | T326 - Wavetrap Upgrade | Replace Wavetrap at Leander Substation on T326 |  | Leander |  | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2016-11-01 | 2016-10-28 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  | 7525, 7527 | Y | N |  |  | 5440 | 4980
3817 | George West autotransformer upgrade | Upgrade autotransformer at George West to 150 MVA as recommended in 2013 RTP. |  | George West Switch |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-11-01 | 2016-12-22 | 138 | 0 | 0 | 150 |  | Live Oak |  | Tier 4 |  |  |  | 5686, 5688 | Y | N |  |  | 4099 | 3817
4773B | Smithville to Rosanky Rebuild | Part 2: Upgrade Structures on Smithville to Rosanky Transmission Line |  | Smithville | Rosanky | Planned |  | BBEC | Thomas Ellis thomas.ellis@bluebonnet.coop |  | 2016-11-10 |  | 69 | 0 | 5.4 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  | 7315, 7558 | Y | N |  |  | 5197 | 4773
5659 | Lotebush: Build 138 kV temporary tap | Construct new 138 kV temporary tap on the Barrilla Junction to Permian Basin Line | IN-SERVICE | Lotebush |  | Planned | 736 - 0919 | AEP TNC | Eric Scott mlforcum@aep.com 918-599-2674 | 2616 | 2016-11-15 | 2016-11-15 | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60392, 6656, 60397 | Y | N |  |  | 6223 | 5659
4311 | Sand Bluff Reactor Addition | Add three breakers and move one 50 MVAR shunt reactor from Cottonwood to Sand Bluff. |  | Sand Bluff |  | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2016-11-15 |  | 345 | 0 | 0 | 0 | 50,0 | Sterling |  | Tier 4 |  |  |  | 59902 | Y | N |  |  | 4688 | 4311
16TPIT0065 | Gresham Road - Nacogdoches 138 kV line | Upgrade existing line |  | Gresham Road | Nacogdoches | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6035-E | 2016-11-15 |  | 138 | 0 | 21.3 | 0 |  | Cherokee | Nacogdoches | Tier 3 | 2015-06-15 | 2015-07-15 |  | 3299, 3300, 3301, 3303 | Y | N |  |  | 3284 | 3115
4877 | Bakersfield: Build 345 kV terminal | Interconnect East Pecos solar farm at Bakersfield | IN-SERVICE | Bakersfield |  | Under Construction | 728 - 0910 | ETT | Aaron Schwerman mlforcum@aep.com 918-599-2674 | 2911 | 2016-11-16 | 2016-11-16 | 345 |  |  |  |  | Pecos |  | Tier 4 |  |  |  | 6101 | Y | N |  |  | 5313 | 4877
4878 | Twin Buttes Auto Transformer | Install a new 345/138 kV 672 MVA auto transformer at Twin Buttes substation |  | Twin Buttes |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014328 | 2016-11-16 | 2016-11-22 | 345 | 0 | 0 | 672 |  | Tom Green |  | Tier 4 |  |  |  | 77280, 76009, 76011, 77281 | Y | N |  |  | 5314 | 4878
5435 | Big Spring - Cosden 138 kV Line | Upgrade existing line |  | Big Spring | Cosden | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8359 | 2016-11-30 |  | 138 | 0 | 1 | 0 |  | Howard | Howard | Tier 4 |  |  |  | 1322, 1332 | Y | N |  |  | 5963 | 5435
4422 | Stewart 10MVAr Reactor Bank | Install 10MVAR shunt reactor at Stewart substation. | Delay in project schedule | Stewart |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 859 | 2016-11-30 |  | 138 | 0 | 0 | 0 | -10,0 | Galveston |  | Tier 4 |  |  |  | 43290 | Y | N |  |  | 4803 | 4422
4784A | Forest Hill - Cresson 69 kV Line Conversion | Rebuild existing 69 kV line section from Forest Hill to Crowley |  | Forest Hill | Crowley | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5227 | 2016-12-01 |  | 69 | 0 | 12.1 | 0 |  | Tarrant | Tarrant | Tier 4 | 2015-05-07 | 2015-06-01 |  | 1968, 2205, 12209 | Y | N |  |  | 5484 | 4784
4319 | Cottonwood Reactor Addition | Add one new 100 MVAR reactor at Cottonwood. Move one existing 50 MVAR reactor to Sand Bluff |  | Cottonwood |  | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2016-12-07 |  | 345 | 0 | 0 | 0 | 100,0 | Dickens |  | Tier 4 |  |  |  | 59904 | Y | N |  |  | 4696 | 4319
16TPIT0018 | Hicks Switch 345/138 kV autotransformer | Install 345/138 kV autotransformer and 138 kV bus |  | Hicks Switch |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5145-E | 2016-12-15 |  | 345 | 0 | 0 | 600 |  | Tarrant |  | Tier 4 |  |  |  | 2082, 1860, 2075, 2076, 12065, 2081 | Y | N |  |  | 2700 | 2584
11TPIT0179 | Hicks Switch - Elizabeth Creek 138 kV line | Construct new double-circuit 138 kV line |  | Hicks Switch | Elizabeth Creek | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M523-E | 2016-12-15 |  | 138 | 30.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 2 | 2013-02-01 | 2013-03-01 |  | 1867, 1852, 1866, 2082 | Y | N |  |  | 2786 | 2662
13TPIT0060 | Cedar Hill Switch - Mountain Creek 138 kV line | Upgrade existing line |  | Cedar Hill Switch | Mountain Creek | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4068-E | 2016-12-15 |  | 138 | 0 | 11.4 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2411, 2412, 2421, 2422 | Y | N |  |  | 2593 | 2488
15TPIT0039 | Plano Tennyson Road - McDermott | Upgrade 138 kV line |  | Plano Tennyson Road | McDermott | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4103-E | 2016-12-15 |  | 138 | 0 | 5.3 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 2523, 10011, 2516 | Y | N |  |  | 2346 | 2273
4739 | Wichita Fallls South | Upgrade terminal equipment on Wichita Falls South - Lake Wichita 138 kV Line |  | Wichita Falls South |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4003 | 2016-12-15 |  | 138 | 0 | 0 | 0 |  | Archer |  | Tier 4 |  |  |  | 1446, 1464 | Y | N |  |  | 5158 | 4739
4738 | Pleasant Valley - Ceramic 138 kV Line | Upgrade terminal equipment on Pleasant Valley - Ceramic 138 kV Line |  | Pleasant Valley | Ceramic | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4004 | 2016-12-15 |  | 138 | 0 | 0 | 0 |  | Wichita |  | Tier 4 |  |  |  | 1450, 1484, 1485 | Y | N |  |  | 5157 | 4738
4737 | Wichita Fallls South | Upgrade terminal equipment on Wichita Falls South -Windthorst 138 kV Line |  | Wichita Falls S |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4003 | 2016-12-15 |  | 138 | 0 | 0 | 0 |  | Archer |  | Tier 4 |  |  |  | 1464, 1474 | Y | N |  |  | 5156 | 4737
4215 | Midessa South - Spraberry 138 kV Line | Rebuild Spraberry - Odessa TI Tap 138 kV line section using double-circuit 138 kV structures. Install a second circuit from Midessa South to Spraberry |  | Midessa South | Spraberry | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8255 | 2016-12-15 |  | 138 | 16 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1124, 1137, 1329 | Y | N |  |  | 4576 | 4215
4548 | Yucca Drive Switching Station | Construct new switching station |  | Yucca Drive Switching Station |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8261 | 2016-12-15 |  | 138 | 0 | 0 | 300 |  | Ward |  | Tier 4 |  |  |  | 1009, 1015, 18110, 1010, 1019, 1074, 1105, 1146, 60397 | Y | N |  |  | 4950 | 4548
15TPIT0070 | North Andrews - Andrews Switch 69 kV Line | Rebuild existing Andrews Switch - Fullerton 69 kV line section as a double-circuit line with a 69 kV circuit and a 138 kV circuit. Includes 16TPIT0046 Frankel City - Exxon Fullerton 69 kV Line. |  | Andrews Switch | Fullerton | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8292 | 2016-12-15 |  | 69 | 0 | 14.8 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1156, 1267, 1270, 1271, 1274, 1275, 1284 | Y | N |  |  | 3327 | 3156
17TPIT0029 | Tyler Grande - Tyler East 138 kV Line | Upgrade existing line |  | Tyler Grande | Tyler East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6017-E | 2016-12-15 |  | 138 | 0 | 8.2 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3143, 3212, 3214, 3211, 3213 | Y | N |  |  | 3288 | 3119
4772 | Big Brown | Upgrade terminal equipment on Big Brown - Richland Chambers 345 kV Line |  | Big Brown |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2011 | 2016-12-15 |  | 345 | 0 | 0 | 0 |  | Freestone |  | Tier 4 |  |  |  | 3134, 3380 | Y | N |  |  | 5195 | 4772
4760 | Jewett 345/138 kV autotransformer | Jewett second 345/138 kV autotransformer |  | Jewett |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1914 | 2016-12-15 |  | 345 | 0 | 0 | 600 |  | Leon |  | Tier 3 | 2015-05-15 | 2015-06-15 |  | 13392, 3390, 3394 | Y | N |  |  | 5181 | 4760
5263 | Yucca Dr - Barstow NW 138 kV Line | Construct new DCKT Line |  | Yucca Drive | Barstow NW | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8070 | 2016-12-15 |  | 138 | 35.84 | 0 | 0 |  | Ward | Ward | Tier 4 | 2013-02-15 | 2013-02-15 |  | 1086, 1009, 1080, 1089, 38150 | Y | N |  |  | 5763 | 5263
4518 | Midessa South 345/138 kV autotransformer | Install 345/138 kV autotransformer in the existing Midessa South Switching Station |  | Midessa South |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8259 | 2016-12-15 |  | 345 | 0 | 0 | 450 |  | Midland |  | Tier 4 |  |  |  | 1125, 1058, 11028, 1124 | Y | N |  |  | 4915 | 4518
4243 | Holt - North Andrews 138 kV Line | Upgrade existing line |  | Holt | North Andrews | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8212 | 2016-12-15 |  | 138 | 0 | 22.1 | 0 |  | Ector | Andrews | Tier 4 |  |  |  | 1141, 1154, 1161, 1281, 1159, 1283 | Y | N |  |  | 4616 | 4243
3760 | Asherton to Carrizo Springs: 69 kV Transmission Line Rebuild | Rebuild 69 kV line from Asherton to Carrizo Spring |  | ASHERTON | CARRIZO SPRING | In-Service | 661-0830 | AEP TCC | Aaron Schwerman DNLYONS@AEP.COM 918-599-2698 | 3526 | 2016-12-16 | 2016-12-16 | 69 |  | 8.3 |  |  | Dimmit | Dimmit | Tier 4 |  |  |  | 8244, 8280 | Y | N | NA |  | 4005 | 3760
5194 | Weiss: Build 138 kV station | Construct new 138 kV box bay at the CRMWD tap #2 on the Red Creek to Ballinger 138 kV line | IN-SERVICE | Weiss |  | Under Construction | 757 - 0941 | AEP TNC | Rick McCracken mlforcum@aep.com 918-599-2674 | 2632 | 2016-12-20 | 2016-12-20 | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  | 60399, 6340, 6442, 6458 | Y | N |  |  | 5678 | 5194
4968 | Pomelo Tap: Build new 345 kV temporary tap | Interconnect Hidalgo Windfarm at temporary tap to connect Hidalgo to the Del Sol to North Edinburg 345 kV line |  | Del Sol | North Edinburg | Under Construction | 729 - 0911 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3560 | 2016-12-22 | 2016-09-08 | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 88574, 8383, 80355 | Y |  |  |  | 5428 | 4968
3766 | Asherton Station: Replace 138/69 kV Autotransformer | Replace 138/69 kV Auto at Asherton Station | Changed Project Title, Project Description, Transmission Status, PM, Estimates and ISD | ASHERTON |  | Under Construction | 659-0828 | AEP TCC | Aaron Schwerman dnlyons@aep.com 918-599-2698 | 3524 | 2016-12-22 |  | 138 |  |  | 130 |  | Dimmit |  | Tier 4 |  |  |  | 8280, 8283 | Y | N |  |  | 4011 | 3766
3546 | Edroy 69 kV Station: Install Series Reactor | Construct a 15-ohm series reactor at Edroy on the terminal to Mathis 69 kV | Added ERCOT RPG estimate, changed Tier, ransmission status. | Edroy |  | Under Construction | 692-0862 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3537 | 2016-12-22 |  | 69 |  |  |  | 15,0 | San Patricio |  | Tier 1 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8424, 8407, 8408 | Y | N |  |  | 4198 | 3546
4402 | Cenizo: Build new four breaker 345 kV station | Interconnect Javalina Windfarm at Cenizo to connect Bordas on the Lobo SS to North Edinburg 345 kV line |  | Cenizo |  | Planned | 700 - 0870 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3544 | 2016-12-22 | 2016-05-23 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 80646, 8295, 80230, 8646 | Y |  |  |  | 4781 | 4402
4851 | Del Sol to JackieHoward: New 345 kV Line | Interconnect Los Vientos IV at Del Sol 345 kV Station and build a double circuit capable 345 kV circuit to JackiwHoward collector station |  | DEL SOL | JACKIEHOWARD | Under Construction | 722-0904 | ETT | William Clark DNLYONS@AEP.COM 918-599-2698 | 3556 | 2016-12-22 |  | 345 | 10.8 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  | 80355, 161553 | Y | N |  |  | 5278 | 4851
4785 | Lobo: Connect Torrecillas Generation | Lobo: Add IPP Equipment and breaker to accommodate Torrecillas |  | Lobo |  | Under Construction | 723 - 0905 | ETT | Terry Weeks dnlyons@aep.com 918-599-2698 | 3557 | 2016-12-22 | 2016-09-14 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 80219, 80481, 89631 | Y |  |  |  | 5210 | 4785
4722 | Tortuga: Temporary Hard Tap | Construct hardtap on the Gila - Upriver (Koch) 138 kV line |  | Gila | Upriver (Koch) | Under Construction | 719 - 0901 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3555 | 2016-12-22 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 81680, 8467, 80260 | Y |  |  |  | 5213 | 4722
5413 | Terra Verde: Add new POD for transmission customer | Add new Point of Delivery for Tex Isle transmission customer with ~0.6 mile 477 ACSR line to customer |  | Bunsen | Kingsville | In-Service | 784 - 0969 | AEP TCC | Rick McCracken dnlyons@aep.com 918-599-2698 | 3577 | 2016-12-22 | 2016-12-14 | 138 | 0.6 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8921, 88921, 8459, 8518 | Y | Y |  |  | 5925 | 5413
4639 | Red Gate: Build new 138 kV temporary tap | Interconnect STEC Red Gate Power Plant at Temporary Tap on the Falfurrias to North Edinburg 138 kV line |  | Falfurrias | North Edinburg | Planned | 716 - 0897 | AEP TCC | Michael Tallon dnlyons@aep.com 918-599-2698 | 3551 | 2016-12-22 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 8380, 8510, 8896, 88380 | Y | Y |  |  | 5040 | 4639
5430A | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to be 138kV capable but operate at 69kV. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2016-12-22 | 2016-12-19 | 69 | 0 | 1.521 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 905, 915 | Y | N | N/A |  | 5945 | 5430
5412 | Raymondville #2 - Rio Hondo Relocate | Raymondville #2 - Rio Hondo Relocate |  | Raymondville #2 | Las Pulgas | Under Construction | 787 - 0972 | AEP TCC | Brent Harris dnlyons@aep.com 918-599-2698 | 3579 | 2016-12-22 |  | 138 | 0 | 1.98 | 0 |  | Willacy |  | Tier 4 |  |  |  | 8302, 80309 | Y | N |  |  | 5924 | 5412
4081 | CPSE_Skyline to Marion Reconfiguration | Reconfigure 4 - 345 kV transmission lines. Skyline to Marion and Skyline to Elm Creek will become double circuit lines from Skyline to Elm Creek. Hill Country to Marion and Hill Country to Elm Creek become double circuit lines from Hill Country to Marion. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0231 | 2016-12-30 |  | 345 | 0 | 0 | 0 |  | Bexar | Guadalupe | Tier 1 | 2014-06-27 |  | 2015-04-14 | 5133, 5211, 5371, 7044 | Y | N |  |  | 4431 | 4081
3767 | Three Rivers 138 kV: Replace 138/69 kV Autotransformer | Replace 138/69 kV Auto at Three Rivers 138 kV Station | Changed Super project ID, Transmission Status, ISD, PM, and Estimate | THREE RIVER |  | In-Service | 660-0829 | AEP TCC | Rick McCraken dnlyons@aep.com 918-599-2698 | 3525 | 2016-12-30 | 2016-12-30 | 138 |  |  | 130 |  | Live Oak |  | Tier 4 |  |  |  | 8400, 8403 | Y | N |  |  | 4012 | 3767
4709 | Install 100MVAr Capacitor Bank at Rothwood from EastSide | Remove East Side capacitor bank and move to Rothwood substation | Delay in project schedule | Rothwood |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 854 | 2016-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 46296, 47610, 46295, 47600, 46510, 47750 | Y | N |  |  | 5121 | 4709
4997C | Deepwater Area Conversions | Disconnect Deepwater 138kV substation from Ckt.70 service |  | Deepwater |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 986 | 2016-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 40460, 41009, 41000, 40650, 40717 | Y | N |  |  | 5721 | 4997
3796 | FrioAEP 69 kV station | Add new station for AEP load on 69 kV |  | Frio |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-12-31 | 2017-01-31 | 69 | 0 | 0 | 0 |  | Frio |  | Tier 4 |  |  |  | 5845, 5842, 5893 | Y | N |  |  | 4047 | 3796
4544 | Upgrade sections of 138kV Buffalo - Grady line |  |  | Buffalo | Grady | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-12-31 |  | 138 | 0 | 14.3 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79508, 79550, 79549, 79564 | Y | N |  |  | 4946 | 4544
3797 | Shropshire 69 kV station | Add new station for AEP load on 69 kV |  | Shropshire |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-12-31 | 2017-01-31 | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  | 5555, 5549, 5554 | Y | N |  |  | 4048 | 3797
3824 | Dow: Install 2nd 800MVA Autotransformer | Install 2nd DOW-Velasco 800MVA autotransformer at DOW substation | Delay in project schedule | DOW |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 993 | 2016-12-31 |  | 345 | 0.5 | 1.7 | 800 |  | Brazoria |  | Tier 3 | 2014-03-21 | 2014-04-30 |  | 42511, 49069, 42190, 42510, 43240, 43300, 43330, 43360, 42500 | Y | N |  |  | 4106 | 3824
12TPIT0090 | Whitney 2nd Auto | Replace 60 MVA, 138-69 kV auto with 100 MVA auto |  | Whitney |  | Planned |  | BEPC | Dwight Beckman kdye@brazoselectric.com 254-750-6373 | 10048 | 2016-12-31 |  | 138 | 0 | 0 | 100 |  | Bosque |  | Tier 4 |  |  |  | 243, 3546 | Y | N |  |  | 883 | 882
5175 | Albercas: Install RTU | Interconnect Albercas Windfarm at Cenizo to connect Albercas on the Cenizo to Bordas 345 kV line |  | Albercas | Bordas | In-Service | 751 - 0934 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 2925 | 2016-12-31 | 2016-10-20 | 345 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  | 80355 | Y | Y |  |  | 5659 | 5175
5623 | Texas Instruments 138 kV Sub Removal | Remove Texas Instruments substation from CNP transmission service |  | Texas Instruments |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2016-12-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  | 44710, 44000, 44005, 44010, 44020, 44180, 44311, 44481, 44650, 44672, 44082, 44312, 44482, 44652, 44671, 44761, 44762, 47000, 47300 | Y | N |  |  | 6178 | 5623
4770 | Temple Switch | Upgrade terminal equipment on the Temple Switch - Bell County 138 kV Line |  | Temple Switch |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2007 | 2017-01-01 |  | 138 | 0 | 0 | 0 |  | Bell |  | Tier 4 |  |  |  | 3415, 3425 | Y | N |  |  | 5192 | 4770
5430B | Conversion to 138kV | Retire the existing 69kV Denton North station together with the auto transformers. Cost includes construction of two new 138kV terminals at 138kV Denton North |  | Denton North |  | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-01-01 | 2017-01-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 912, 915, 985 | Y | N | N/A |  | 5958 | 5430
5428C | Phase 2 of the conversion to 138kV | Retire existing 69kV Kings Row to Denton North line |  | Kings Row | Denton North | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-01-01 | 2017-07-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 | 2015-11-10 |  | 2016-01-20 | 909, 912 | Y | N | N/A |  | 5940 | 5428
4997A | Deepwater Area Conversions | Convert MOCHEM sub to 138kV service. Loop from Ckt.70 Goodyear to CHANEL. New substation name is BRANUM. |  | BRANUM | Goodyear/CHANEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 986 | 2017-01-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40640, 41080, 40470, 40650, 40717, 40800, 41000, 41009, 41560, 41561, 47700 | Y | N |  |  | 5455 | 4997

## CancelledTPIT020117NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2017
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
5047 | Upgrade conductor for 138 kV line from Sales to Buffalo |  |  | Buffalo | Sales Ranch | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2017-05-01 |  | 138 | 0 | 6 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79508, 79549 | N | N |  |  | 5521 | 5047
16TPIT0005 | Farmersville West to Princeton South - new 138 kV line. | Build approximately 7.5 miles of 138 kV transmission line from Farmersville West Substation to Princeton South Substation. |  | Farmersville West | Princeton South | Planned | New projects added on rows 18 and 19. Please add TPIT numbers here after they have been assigned. | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE08016 | 2017-06-01 |  | 138 | 7.5 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 37291, 37295 | N | N |  |  | 2064 | 2012
4139 | DME_Locust-Spencer |  |  | Pockrus | Spencer | Planned | N/A | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-06-01 |  | 69 | 0 | 1.91 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 902, 904, 914, 981 | N | N | N/A |  | 4484 | 4139
5529 | Freer 69 KV 30 ohm series reactor | Install series reactor and bypass at Freer on line to Bruni |  | Freer |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-07-01 |  | 69 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 5881, 5880, 5888 | N | N |  |  | 6081 | 5529
5364 | Roans Chapel Substation |  |  |  |  | Planned |  | BRYN |  |  | 2017-12-30 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32858, 962, 964 | N |  |  |  | 5875 | 5364
4231 | Creosote: Build 138 kV station | Construct 138 kV, six breaker ring bus on the existing 138 kV line from Barrilla Junction to Permian Basin | Cancelled | Creosote |  | Planned | 689 - 0859 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2606 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 6657, 60377, 6656, 6673, 38375 | N | N |  |  | 4602 | 4231
3998 | Stewart Road to Weslaco Unit: Rebuild 138 kV line | Rebuild 138 kV line from Stewart Road to Weslaco Unit |  | STEWART ROAD | WESLACO UNIT | Planned | 680-0849 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3536 | 2017-12-31 |  | 138 |  | 15 |  |  | Hidalgo | Hidalgo | Tier 3 |  |  |  | 8348, 8951 | N | N |  |  | 4324 | 3998
3664 | San Angelo North: Replace 138/69 kV autotransformer | Add 138/69 kV autotranformer capacity at San Angelo North | CANCEL | San Angelo North |  | Planned | 642 - 0811 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1806 | 2018-05-31 |  | 138 | 0 | 0 | 90 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6462, 6464 | N | N |  |  | 3901 | 3664
3663 | College Hills: Replace 138/69 kV autotransformer | Add 138/69 kV autotranformer capacity at College Hills | CANCEL | College Hills |  | Planned | 641 - 0810 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1805 | 2018-05-31 |  | 138 | 0 | 0 | 90 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6468, 6470 | N | N |  |  | 3900 | 3663
4321 | Add Eagle Station |  |  | Hickory | Locust | Planned |  | DME | Chuck Sears 940-349-7111 |  | 2018-06-01 |  | 69 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  | 926, 910, 914 | N | N |  |  | 4698 | 4321
15TPIT0069 | AEP_Angstrom | Add 138 kV PST |  | RAYMONDVILLE #2 | LOYOLA | Planned | 592 - 0769 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3479 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Kenedy |  | Tier 4 |  |  |  | 8134, 8530, 5648, 8899 | N | N | NA |  | 4385 | 3354
5285 | Milton Capacitor Bank Addition(s) | Add two 138-kV 15.6 MVAR capacitor banks at the Milton Substation. |  | Milton |  | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-06-30 |  | 138 | 0 | 0 | 0 | 0,31.2 | Karnes |  | Tier 4 |  |  |  | 78583 | N | N |  |  | 5786 | 5285
4719 | AEP_Add_ Melon Creek 69kV | Construct Melon Creek 69kV Substation | New Project | Melon Creek |  | Planned | 718 - 0900 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3554 | 2018-07-31 |  | 69 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  | 80066, 8410, 8800 | N | N |  |  | 5137 | 4719
4572 | Atkins Bus Work for Power Transformer addition | Atkins Bus Work for Power Transformer addition |  | 32864 |  | Planned |  | BRYN |  |  | 2018-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | N |  |  | No MOD changes necessary | 4979 | 4572
10TPIT0027 | West Batesville, Install 138 kV ring bus | West Batesville: Construct bundled 2x795 ACSR 138 kV line, add 138 kV circuit breaker and convert to 4 breaker ring bus | CHANGES | WEST BATESVILLE |  | Conceptual | 383 - 0560 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2168 | 2019-03-31 |  | 138 | 0 | 0 | 0 |  | Zavala |  | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8236 | N | N |  | NA | 3751 | 3543
10TPIT0028 | Escondido to West Batesville, build 138 kV Line | West Batesville: Construct bundled 2x795 ACSR 138 kV line, add 138 kV circuit breaker and convert to 4 breaker ring bus | CHANGES | ESCONDIDO | WEST BATESVILLE | Conceptual | 383 - 0560 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2169 | 2019-03-31 |  | 138 | 46.2 | 0 | 0 |  | Maverick | Zavala | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8260 | N | Y |  | NA | 3752 | 3544
06TPIT0068 | Hamilton Road to Picacho, reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | HAMILTON ROAD | PICACHO | Conceptual | 774-0959 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 1544 | 2019-05-31 |  | 138 |  | 8.76 |  |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8255, 8684 | N | N |  |  | 3742 | 3535
5258 | Ft. Stockton: Add dynamic reactive device | Rebuild Solstice to Permian Basin 138 kV line and add dynamic reactive devices at Lotebush | CANCELLED | Ft. Stockton |  | Planned | 713 - 0946 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2637 | 2019-06-30 |  | 138 | 0 | 0 | 0 | -25100 | Pecos |  | Tier 1 | 2015-12-15 |  |  | 6630 | N | N |  |  | 5758 | 5258
13TPIT0198 | Seawillow Substation | Construct 138kV-12.5kV distribution substation Seawillow (7559) on T-184 Lockhart and Luling. |  | Seawillow | Luling / Lockhart | Planned |  | LCRATSC/BBEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013521 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  | 7559, 7216, 7224 | N | N |  |  | 2772 | 2648
4186 | University 138kV Load Conversion | Convert University TR2 & TR3 load to 138kV. |  | University |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47750, 47752 | N | N |  |  | 4541 | 4186
13TPIT0104 | Jack County Auto | Install 345-138 kV, 700 MVA auto at Jack County |  | Jack County | Jack County | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 11038 | 2020-06-01 |  | 345 | 0 | 0 | 700 |  | Jack |  | Tier 4 |  |  |  | 575, 579 | N | N |  |  | 1184 | 1181
15TPIT0000 | Bird Pond Substation | Install (3) Breaker ring to include (2) 138 lines and (1) 138-12.5 transformer |  | Bird Pond | Bird Pond | Planned |  | BRYN | James Tanneberger 979-821-5763 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32858, 962, 964 | N | N |  |  | 1855 | 1812
06TPIT0082 | Buena Vista to Picacho, reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | BUENA VISTA | PICACHO | Planned | 775-0960 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 1547 | 2020-06-30 |  | 138 |  | 3 |  |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8688 | N | N |  |  | 3745 | 3537
4116 | FM-725 Substation | Build a new 138-26.18 kV, 40 MVA substation on the GVEC McQueeney(7606) - Schumansville(7609) 138 kV transmission line |  | FM 725 | McQueeney-Schumansville | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7725, 7606, 7609 | N | N |  |  | 4462 | 4116
12TPIT0185 | Airline to Westside: Add 138kV Circuit | Add a Second 138kV Circuit between Airline and Westside | Change transmission status, ISD | AIRLINE | WESTSIDE | Planned | 587-0747 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3464 | 2020-12-31 |  | 138 | 6.22 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8490 | N | N |  | NA | 3753 | 3545
3999 | Airline to Holly: Build new 138 kV line | Build a new 138 kV line from Airline to Holly using the existing structures | Change transmission status, ISD | AIRLINE | HOLLY | Planned | 548-0747 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3464 | 2020-12-31 |  | 138 | 1.69 |  |  |  | Nueces | Nueces | Tier 4 |  |  |  | 8486, 8490 | N | N |  |  | 4325 | 3999
16TPIT0024 | Hamilton Road to Escondido: Rebuild 138kV Line | Rebuild Hamilton Road to Escondido 138 kV line | Reformated project number to match other numbers | Hamilton Road | Escondido | Conceptual | 602 - 0764 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 3471 | 2020-12-31 |  | 138 | 0 | 53.7 | 0 |  | Val Verde | Maverick | Tier 3 |  |  |  | 8255, 8260, 8264, 8692 | N | N |  | 0 | 2655 | 2550
11TPIT0037 | Add New Santa Clara Substation | Build a new 138-26.18 kV 40 MVA substation on the GVEC McQueeney(7606)-Cibolo(7608) 138 kV transmission line |  | Santa Clara | McQueeney/Cibolo | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7605, 7606, 7608 | N | N |  |  | 4461 | 3369
07TPIT0083 | Picacho to CFE, construct new 138 kV line | Convert Amistad to CFE Amistad 12.5 kV distribution to 138 kV line | CHANGES | PICACHO | CFE | Conceptual | 775-0960 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 1548 | 2022-06-30 |  | 138 | 8.8 | 0 | 0 |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8684 | N | N |  | NA | 3750 | 3542
06TPIT0083 | Del Rio to Buena Vista, reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | DEL RIO | BUENA VISTA | Planned | 775-0960 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 1546 | 2022-06-30 |  | 138 |  | 3 |  |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8690 | N | N |  |  | 3748 | 3540
06TPIT0084 | Hamilton Road to Del Rio reconductor 138 kV line | Reconductor Del Rio 138 kV System | CHANGES | HAMILTON ROAD | DEL RIO | Conceptual | 775-0960 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 1545 | 2022-06-30 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8255 | N | N | NA | NA | 3749 | 3541
07TPIT0252 | Greta: Install 1-7.2 MVAR 69 kV Cap Bank | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Greta |  | Conceptual | 100 - 0100 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2045 | 2022-07-31 |  | 69 | 0 | 0 | 0 | 0,7.2 | Refugio |  | Tier 4 |  |  |  | 8409 | N | N |  |  | 1174 | 1171
12TPIT0006 | Olmos(7613)- New Substation | Build a new 138-13.09 kV 20 MVA substation on the Olmos switching station site |  | Olmos | Olmos Switching Station | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-11-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7239 | N | N |  |  | 3566 | 3371
15TPIT0008 | Triple R - New Substation (7627) | Build a 138-26.18kV. 40 MVA substation on the GVEC Wilson-Sutherland Springs (T549) 138 kV transmission line |  | Triple R | Wilson/Sutherland Springs | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  | 7627, 5418, 7615 | N | N |  |  | 4459 | 3367
11TPIT0036 | Caddo - New Substation | Construct a new 69-13.09x26.18-kV 10 MVA substation on GVEC La Vernia-GVEC Nixon 69 kV transmission line |  | Caddo | La Vernia/GVEC Nixon | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 69 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  | 7628, 7614, 7616 | N | N |  |  | 4460 | 3368
4418 | HARBOR 138kV Substation | Loop Ckt. 59 Freeport to Quintana into new 138kV HARBOR substation Original Effective Date: 12/31/2015 |  | HARBOR | Freeport/Quintana | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-12-31 |  | 138 | 0.1 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 43165, 42645, 43435 | N | N |  |  | 4798 | 4418

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2016-N1 | Kiamichi Energy Facility (140077) 345-kV reactor addition | KIOWA POWER PARTNERS LLC (RE) | 2018 |  |  |  | A mitigation plan has been identified to address this issue. The plan is currently implemented in Ercot Operations.
2016-NC1 | Ranger Gulf (1627) -Thurber TNP (37850) 69-kV terminal equipment upgrade | TNMP | 2018
2016-NC2 | Bosque Switch (252) - Olsen TNP (37460) 138-kV line terminal equipment upgrade | TNMP | 2018
2016-NC3 | Energy Switch (265) - Gustine (273) 69-kV line upgrade | BEPC | 2018
2016-NC4 | Terrell North (2718) - Terrell North Tap (2715) - Terrell Switch (2721) 138-kV line upgrade | Oncor | 2018 | 2017-12-15 | Planned | 5484
2016-NC5 | Hurst (2116) - Euless (2121) 138-kV line upgrade | Oncor | 2018 | 2019-05-18 | Planned | 5495
2016-NC6 | Liggett Switch (1923, 1925) - Hackberry (2388) 138-kV double circuit line upgrade | Oncor | 2018 | 2018-05-15 | Planned | 5490
2016-NC7 | Kaufman Northwest (2724) - Rose Hill (2723) 138-kV line upgrade | Oncor | 2919
2016-FW1 | 1. Rebuild the 69kV line to 138kV line from IH-20 (38045) all the way to Wickett (37981) 2. Add a new 138kV bus and a 138/69kV autotransformer at Wickett 3. Build a new 138kV line from Wickett (37981) to Permian Basin (1009) | TNMP/ONCOR | 2018
2016-FW2 | Add two (2) 50 MVAR reactor banks at Bakersfield 345-kV Substation (76002) | LCRA | 2018 | 2017-11-01 | Planned | 5235
2016-FW3 | Riverton (1094) - Sandlake (1011) double-circuit 138-kV line addition | ONCOR | 2021 | 2020-05-15 | Planned | 4759
2016-FW4 | Add two (2) more 12 MVAR capacitor banks at St Lawrence 138-kV Substation (79617) | SHARYLAND | 2021
2016-S3 | South McAllen (8371) -Bensten (8822) terminal equipment upgrade | AEP/Sharyland | 2018
2016-S4 | W George West Switch (5685) - George West Switching Station (5686) 69-kV line upgrade | STEC | 2018 | 2018-06-01 | Planned | 5223
2016-S5 | Bessel (8060) 138-kV capacitor bank addition | AEP | 2018
2016-S6 | Beeville (8198) area upgrades | AEP | 2021
2016-S7 | Valero (8477) area upgrades | AEP/ETT | 2018
2016-S8 | Replace two Miguel (5901) 345/138-kV transformers | STEC | 2019 | 2019-06-01 | Planned | 5218
2016-C1 | PLACEHOLDER - Switched Shunt at Jones Creek (42540) | CNP | 2018 | 2018-12-31 | Planned | 5554
2016-C2 | PLACEHOLDER - Second Switched Shunt at Jones Creek (42540) | CNP | 2018 | 2018-05-31 | Planned | 5808
2016-C3 | PLACEHOLDER - Second Switched Shunt at Velasco (43360) | CNP | 2018 | 2018-05-31 | Planned | 5807
2016-C4 | PLACEHOLDER - Third Switched Shunt at Velasco (43360) | CNP | 2021
2016-C5 | Danevang 69 Sub (5548) - Clemville Switch (5549) 69-kV Upgrade | STEC | 2018 | 2018-06-01 | Planned | 5634
2016-C6 | 345/138-kV Transformer Addition at Zenith (44900/44910) | CNP | 2019 | 2018-05-31 | Planned | 5894
2016-C7 | Jordan (40855) - Cities (40340) 138-kV Terminal Equipment Upgrade | CNP | 2021 | 2017-04-30 | Planned | 5551
2016-C8 | Hardy (45840) - North Side (47711) 138-kV Line Uprate | CNP | 2018 | 2019-05-31 | Planned | 5244
2016-C9 | Britmoore (44120) - Sauer (44620/44625) Double-Circuit 138-kV Upgrade | CNP | 2018
2016-C10 | O'Brien (44512) - Clodine (44140) 138-kV Line Uprate | CNP | 2022 | 2018-12-30 | Planned | 5555
2016-C11 | Bunker Area 138-kV Upgrades | CNP | 2018 | 2018-05-31 | Planned | 5766
2016-C12 | Switched Shunt at MaGill (8111) | AEP | 2018
2016-E1 | Stryker Creek SES (3110) - Bayou Loco (3342) 138-kV Line Upgrades | ONCOR | 2018 | 2019-05-15 | Planned | 4827
2016-W1 | Mason AEP (6393) - Fort Mason (76388) 69-kV terminal equipment upgrade | AEP/LCRA | 2018 | 2018-05-31 | Planned Not in Case | 5919
2016-W2 | Add a second 345/138-kV transformer at Twin Buttes (76009) | AEP/LCRA | 2018 | 2017-09-01 | Planned | 5270
2016-SC1 | Bell and Williamson County upgrades | Oncor/LCRA | 2021
2016-SC2 | Moulton South (7237-7588) 138/69-kV transformer addition | LCRA | 2022 | 2017-07-31 | Planned | 4606
2016-SC3 | Fayette Plant 138 (7278) - Weimar (7254) 138-kV line addition. Fayette Plant 138 (7278) - Fayette River Pump (7280) 138-kV line terminal upgrade Fayette Plant 138 (7278) - Fayetteville (7286) 138-kV line rebuild | LCRA | 2022 | 2022-05-31 | Planned Not in Case | 5286
2016-SC4 | Flatonia (7248) - Hallettsville (7246) 138-kV line rebuild | LCRA | 2022 | 2020-05-31 | Planned | 5276
2016-SC5 | Wells Branch (7288) - Howard Lane Tap (7335) 138-kV line upgrade | LCRA | 2021 | 2022-05-31 | Planned Not in Case | 5945

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Bob Healey; Veronica Billings | bhealey@aep.com; vbillings@aep.com | Bob Healey: 918 599 2249; Veronica Billings: 918 599 2945 | Glen Reed; David Kidd; Brad Myers; Mabel See; Mike Forcum; Doug Lee; Daniel Lyons; Bob Lager; Mina Turner; Lisa Kelso; Carole Myser | gareed@aep.com; dekidd@aep.com; blmyers@aep.com; msee@aep.com; mlforcum@aep.com; dnlyons@aep.com; dlee@aep.com; rjlager@aep.com; myturner@aep.com; lokelso@aep.com; camyser@aep.com | David Kidd: 918 599 2637 Glen Reed: 918 599 2664 Brad Myers: 918 599 2690
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Armke, James; Hunt, Dandy; Ron Krautz; Brion Ryan | James.Armke@austinenergy.com; dandy.hunt@austinenergy.com; ron.krautz@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | James:512 322 6705 Biju:512 322 6381 Reza:512 322 6740 Dandy:512 322 6748 Ron:512 322 6835 Brion: 512-322-6879
Bandera Electric | Primary | David Baker | d.baker@banderaelectric.com | David: 830-796-6084
BPUB | Primary | Ramon Sanz | rsanz@brownsville-pub.com; | Ramon: 956 983 6203 | James McCann | jmccann@brownsville-pub.com; | James: 956 983 6204
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Dwight Beckman | dbeckman@brazoselectric.com | Dwight: 254 750 6373 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | James Tanneberger | jtanneberger@btutilities.com | James: 979 821 5763 | Shawndra Green | sgreen@btutilities.com | Shawndra: 979 821 5744
CNP | Primary & Secondary | Wesley Woitt | wesley.woitt@centerpointenergy.com | Wesley Woitt: 713-207-2760 | Yingying Huang; Raja Sekhar Kakarla; Cody Mann | Yingying.Huang@centerpointenergy.com; rajasekhar.kakarla@centerpointenergy.com; cody.mann@centerpointenergy.com | Yingying Huang: 713-207-2831 Raja Sekhar Kakarla: 713-207-3614 Cody Mann: 713-207-3149
COCS | Primary | Tony Michalsky | tmichalsky@cstx.gov; | Tony: 979 764 3438 | Timothy Crabb, Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | Basileo Rocha, Sunil Dhakal | bdrocha@cpsenergy.com; SDhakal@cpsenergy.com | Basileo: 210 353 4933 Sunil: 210 353 2008 | Kenneth Bowen Trieu Vo | kbowen@cpsenergy.com; tvo@cpsenergy.com; | Kenneth: 210 353 4142 Trieu: 210 353 2127
CTT (Cross Texas Transmission) | Primary & Secondary | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310 | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310
DENTON | Primary & Secondary | Chuck Sears | Chuck.Sears@cityofdenton.com; | Chuck: 940 349 7111 | Brent Heath | brent.heath@cityofdenton.com; | Brent: 940 349 7180
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Grubbs, David; Juan Santos | Dgrubbs@gpltexas.org; Jsantos@gpltexas.org | David: 972 205 2664 Juan: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; PEC; SBEC; GVEC; City of Georgetown; BBEC,CTEC, NBU | Primary & Secondary | Charles DeWitt | Charles.dewitt@lcra.org | Charlie: 512-578-4199 | Sergio Garza, Cris Urena, Ken Chui | sergio.garza@lcra.org; cris.urena@lcra.org; ken.chui@lcra.org | Sergio: 512 578 4149 Cris: 512 578 4525 Ken: 512 578 4510
Lone Star | Primary & Secondary | Don Le | don.le@lonestar-transmission.com | Don - 512-236-3144 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Charles Saker | charles.saker@oncor.com | Charles: 214-743-6896 | Paul Bell | paul.bell@oncor.com | Paul: 214-743-6676
Sharyland Utilities | Primary & Secondary | Brad Schwarz | bschwarz@huntpower.com | Brad: 512-289-7425 | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243
STEC | Primary & Secondary | Doug Evans | devans@stec.org | Doug: 361 485 6459 | Paul Person Loretta Gallaga | pperson@stec.org; lgallaga@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Ahmad Saboor | asaboor@texasmpa.org | Ahmad: 936 873 1104 | Frank Owens | fowens@texasmpa.org; | Frank: 936 873 1120
TNMP | Primary & Secondary | Robert Lona | Robert.Lona@tnmp.com | Robert: 281-581-4732 | Anthony, Hudson Ballay, Dustin Cloninger, Ross | Anthony.Hudson@tnmp.com; Dustin.Ballay@tnmp.com; Ross.Cloninger@tnmp.com; | Anthony: 281 581 4712 Dustin:281 581 4730 Ross:281 581 4733
Wind Energy Texas Transmission (WETT) | Primary | Julius Horvath | julius.horvath@windenergyoftexas.com | Julius: 512 436 9585; cell: 512 496 9186 | Christina Minchew | christina.Minchew@windenergyoftexas.com | Christina: 512-436-9469