## ImprovementCostSummary02242022
| Project Cost |  |  |  |  | XFMR MVA
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total
2021 | 1118483000 | 1224001102.56 | 232565296 | 2575049398.56 | 2021 | 4625 | 147 | 60 | 4832 | For ROS and BOD Reports
2022 | 464573000 | 1690883159 | 581837000 | 2737293159 | 2022 | 2572 | 951.8 | 200 | 3723.8 | ·All Projects (in engineering, routing, licensing and construction): |  |  |  | 8034419360
2023 | 344148000 | 1953079201 | 606205000 | 2903432201 | 2023 | 3360 | 510 | -200 | 3670 | ·Transmission Projects Energized in 2022: |  |  |  | 105483000
2024 | 645873000 | 510527000 | 350461000 | 1506861000 | 2024 | 2850 | 130 | 0 | 2980
2025 | 26000000 | 265691000 | 61700000 | 353391000 | 2025 | 0 | 0 | 0 | 0
2026 | 200250000 | 101510000 | 108950000 | 410710000 | 2026 | 600 | 0 | 0 | 600
2027 | 73500000 | 21100000 | 3100000 | 97700000 | 2027 | 1200 | 0 | 0 | 1200
2028+ | 0 | 126315000 | 4200000 | 130515000 | 2028+ | 0 | 0 | 0 | 0
2022COM | 9857000 | 34215000 | 61411000 | 105483000 | 2022COM | 200 | 0 | 0 | 200
2022PLAN | 454716000 | 1656668159 | 520426000 | 2631810159 | 2022PLAN | 2372 | 951.8 | 200 | 3523.8
2021-2028+ | 2872827000 | 5893106462.56 | 1949018296 | 10714951758.56 | 2021-2028+ | 15207 | 1738.8 | 60 | 17005.8
2021-2022 | 1583056000 | 2914884261.56 | 814402296 | 5312342557.56 | 2021-2022 | 7197 | 1098.8 | 260 | 8555.8
2023-2028+ | 1289771000 | 2978222201 | 1134616000 | 5402609201 | 2023-2028+ | 8010 | 640 | -200 | 8450
| Circuit Miles New |  |  |  | Circuit Miles Rebuilt, Reconductored or Upgraded |  |  |  |  | Total
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total | 345 | 138 | 69 | Total
2021 | 173.15 | 73.15 | 0 | 246.3 | 2021 | 34.6 | 533.82 | 207.07 | 775.49 | 207.75 | 606.97 | 207.07 | 1021.79
2022 | 132 | 88.76 | 25.5 | 246.26 | 2022 | 27 | 382.103 | 277.53 | 686.633 | 159 | 470.863 | 303.03 | 932.893
2023 | 74.41 | 162.241 | 0 | 236.651 | 2023 | 1.2 | 688.801 | 351.601 | 1041.602 | 75.61 | 851.042 | 351.601 | 1278.253
2024 | 361.08 | 22.48 | 2 | 385.56 | 2024 | 0 | 250.738 | 191.06 | 441.798 | 361.08 | 273.218 | 193.06 | 827.358
2025 | 0 | 0.99 | 0 | 0.99 | 2025 | 92.1 | 91.74 | 42.2 | 226.04 | 92.1 | 92.73 | 42.2 | 227.03
2026 | 52.5 | 10 | 0 | 62.5 | 2026 | 10 | 68.14 | 85.81 | 163.95 | 62.5 | 78.14 | 85.81 | 226.45
2027 | 0 | 0 | 0 | 0 | 2027 | 18.7 | 17.4 | 6.26 | 42.36 | 18.7 | 17.4 | 6.26 | 42.36
2028+ | 0 | 31.9 | 0 | 31.9 | 2028+ | 0 | 66.15 | 2 | 68.15 | 0 | 98.05 | 2 | 100.05
2022COM | 0 | 1.61 | 0 | 1.61 | 2022COM | 0 | 4.03 | 44.8 | 48.83 | 0 | 5.64 | 44.8 | 50.44
2022PLAN | 132 | 87.15 | 25.5 | 244.65 | 2022PLAN | 27 | 378.073 | 232.73 | 637.803 | 159 | 465.223 | 258.23 | 882.453
2021-2028+ | 793.14 | 389.521 | 27.5 | 1210.161 | 2021-2028+ | 183.6 | 2098.892 | 1163.531 | 3446.023 | 976.74 | 2488.413 | 1191.031 | 4656.184
2021-2022 | 305.15 | 161.91 | 25.5 | 492.56 | 2021-2022 | 61.6 | 915.923 | 484.6 | 1462.123
2023-2028+ | 487.99 | 227.611 | 2 | 717.601 | 2023-2028+ | 122 | 1182.969 | 678.931 | 1983.9

## FutureTPIT020122NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2022
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
51990 | AEN_21TPIT51990_New_Dunlap_345kV_Auto_AT2_PMCR | Second 345/138 kV autotransformer addition at Dunlap substation |  | 9044 | 9045 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2022-02-07 |  | 345 | 0 | 0 | 672 |  |  |  | Tier 4 |  |  |  |  | 90007, 9044, 9045 | Y |  |  | 0 | 59171 | 51990
54105 | McCarty Lane - Ranch Road 12 Transmission Line Upgrade | Increase the reliability of transmission facilities on the T699 McCarty Lane ¿ Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | McCarty Lane | Ranch Road 12 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-02-08 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7186 | Y | N |  | 0 | 54106 | 54105
57161 | Rebuild Vanderbilt to VanHumble | Rebuild 4/0 ACSR with 795 ACSR on 138 kV capable poles |  | Vanderbilt | Van Humble Switch | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-02-15 |  | 69 | 0 | 0.97 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 5580, 5582 | Y | N |  | 0 | 57162 | 57161
62367 | Close Feed to Martin | [6 empty] | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2022-02-16 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 9483, 61015 | Y |  |  | 0 | 62368 | 62367
55367 | Wolfcamp: Build 138 kV box bay | Build new 138 kV box bay on the Big Lake to North McCamey line | IN-SERVICE | Wolfcamp |  | In-Service | 1087 - 1270 | AEP TNC | Michael Richardson mlforcum@aep.com 918-599-2674 | 1860 | 2022-02-21 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | 60799, 60361, 60723 | Y | N |  | 0 | 55368 | 55367
59117 | Tres Bahias Solar Interconnection | Tres Bahias Solar Interconnection | IN-SERVICE | Joslin |  | Planned |  | AEP TCC | Michael Miller bcogan@aep.com 918-599-2857 | TP2019312 | 2022-02-24 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8661, 8140 | Y |  |  | 0 | 59118 | 59117
6112 | Causeway to Sunchase:Build new 138 kV Line | Rehab Causeway - Sunchase 138 kV Line | IN-SERVICE | Causeway | Sunchase | Planned | 826 - 1010 | AEP TCC | Kenneth Haley bcogan@aep.com 918-599-2857 | 3627 | 2022-02-28 |  | 138 | 0 | 3.56 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8744, 8917 | Y | N |  |  | 13838 | 6112
6352 | Crckett Hghts to Sonora Atlntic 69 kV line: Rbld 69 kV line | Rehab Crockett Heights to Sonora Atlantic 69 kV line |  | Crockett Heights | Sonora Atlantic | Planned | 786 - 0971 | AEP TNC | Joseph Page mlforcum@aep.com 918-599-2674 | 2706 | 2022-02-28 |  | 69 | 0 | 16.8 | 0 |  | Crockett | Sutton | Tier 4 |  |  |  |  | 6511, 6552 | Y | N |  |  | 14096 | 6352
44872 | Asherton 138 kV Station | Add breaker at Asherton 138 kV Station to Accommodate Shakes Solar | IN-SERVICE | Asherton | - | Planned | 966 - 1144 | AEP TCC | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3724 | 2022-02-28 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  |  | 88283, 8283 | Y | N |  | 0 | 44873 | 44872
48109 | Dolan Creek: Construct 138 kV Box Bay | Dolan Creek: Construct 138 kV Box Bay | Update Schedule | Dolan Creek |  | Planned | 930 - 1108 | AEP TCC/PEC | Alison Scribailo bcogan@aep.com 918-599-2857 | 3706 | 2022-02-28 |  | 138 | 0 | 0 | 0 |  | Val Verde | Sutton | Tier 4 |  |  |  |  | 8991, 88991, 8259, 8261, 72194 | Y | Y |  | 0 | 65534 | 48109
52565F | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Thermally-uprate Ckt.05B HO Clarke to Intermediate tap to a minimum 340 MVA Continuous. Thermally-uprate Ckt.05B Intermediate tap to Southwyck to increase thermal limits |  | HO Clarke | Southwyck | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 |  | 138 | 0 | 2.86 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44361, 47150, 43260 | Y | N |  | 0 | 63577 | 52565
55628 | Rio Hondo: Upgrade 138 kV terminal | Upgrade 138 kV STEC East Rio Hondo terminal at Rio Hondo | IN-SERVICE | Rio Hondo |  | Planned | 1103 - 1281 | AEP TCC | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3821 | 2022-02-28 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8319 | Y |  |  | 0 | 55629 | 55628
55957 | COUGAR to Gulfgate Ckt.91 Upgrades | Upgrade Ckt.91 COUGAR to Gulfgate tap to minimum 478MVA emergency rating |  | COUGAR | Gulfgate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42741, 47560 | Y | N |  | 0 | 55958 | 55957
64495 | Cedar Bayou Generator Lead Upgrade | Upgrade equipment on the generator lead to Cedar Bayou CBY-1 unit Upgrade to Minimum 851 MVA Continuous rating |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 |  | 138 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  |  | 40015, 49200 | Y | N |  | 0 | 64496 | 64495
59305A | Attwater TNMP-Owned Substation (Ckt.02 PHR to Attwater) | Upgrade Ckt.02 PHR to new TNMP-owned Attwater substation |  | PHR | Attwater | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 12:00 |  | 138 | 0 | 0.41 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 38745, 42015 | Y | N |  | 0 | 64489 | 59305
64997 | SYLVAN to Morgans Point Ckt.79B Rebuild for Hardening | Rebuild Ckt.79B SYLVAN to LaPorte tap to Morgans Point as a Hardening upgrade |  | SYLVAN | Morgans Point | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 12:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40942, 41520, 41100 | Y | N |  | 0 | 64998 | 64997
65711 | Rebuild Ckt.06F Holmes to Plaza as a Hardening upgrade |  |  | Holmes | Plaza | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 12:00 |  | 138 | 0 | 3 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42680, 47210, 47350 | Y | N |  | 0 | 65712 | 65711
59305B | Attwater TNMP-Owned Substation (Ckt.02 PHR to Attwater) | Upgrade Ckt.03 PHR to new TNMP-owned Attwater substation |  | PHR | Attwater | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 12:01 |  | 138 | 0 | 0.41 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 38745, 42015 | Y | N |  | See main project | 64490 | 59305
44862 | Schottky: Build 69 kV Box bay | New Schottky 69 kV Station, replaces Hard Tap | IN-SERVICE | Schottky |  | Planned | 971 - 1149 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3729 TP2018130 | 2022-03-01 |  | 69 | 0 | 0 | 0 |  | Live Oak |  | Tier 4 |  |  |  |  | 8507, 88507, 8400, 8406 | Y | N |  | 0 | 45151 | 44862
54092 | Sheriff's Posse Substation Upgrade | Increase transmission service reliability to the Sheriff¿s Posse Substation. Increase the reliability of substation equipment at the Sheriff¿s Posse Substation. Note: NBU is adding a third power transformer at Sheriff¿s Posse and reconfiguring the substation to a ring bus arrangement. LCRA TSC will complete this project to support the NBU substation reconfiguration. LCRA TSC will ultimately own a section of the ring bus at Sheriff¿s Posse where an existing LCRA TSC transmission line terminates. |  | Sheriff's Posse | Sheriff's Posse | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-03-01 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7460 | Y | N |  | 0 | 54093 | 54092
58002 | Foxtrot: Construct new 345 kV Station | Cut the 345 kV Goddard to Pawnee 345 kV line into the new 345 kV Tango station. Install one span to Foxtrot POI |  | GODDARD | STEC PAWNEE | Planned | 1120 - 1298 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020080 | 2022-03-01 |  | 345 | 45.84 | 0 | 0 |  | San Patricio | Bee | Tier 4 |  |  |  |  | 8689, 88689, 5725, 8606 | Y |  |  | 0 | 58003 | 58002
53956 | Coronado - Fairland Transmission Line Upgrade | Increase the reliability of transmission facilities on the T110 Coronado - Fairland 12.4-mile 138-kV transmission line by replacing the existing Condor conductor with Drake conductor. |  | Coronado | Fairland | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-03-04 |  | 138 | 0 | 0 | 0 |  | Burnet | Llano | Tier 4 |  |  |  |  | 7087, 7518 | Y | N |  | 0 | 53957 | 53956
54084 | King Mountain Circuit Breaker Addition | Provide transmission service to a generator. Add a 138-kV bay and associated circuit breaker to the existing substation. ERCOT (ERCOT Generation Interconnection or Change Request No. 20INR0226) |  | King Mountain Sub | King Mountain Sub | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-03-11 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 76635 | Y | N |  | 0 | 54085 | 54084
57165 | Red Gate138/69 autotransformer and lines to McCook and Faysw | Adds 69 kV bus at Red Gate, a 138/69 autotransformer at Red Gate, and connects 69 kV lines to McCook#1 and Faysville Switch. |  | Red Gate | McCook and Faysville SW | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-03-15 |  | 138 | 1 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5779, 5780, 5784, 5782, 88380, 5783, 8377, 161031 | Y | N |  | 0 | 63729 | 57165
59452 | Air Liquide Pass Through 138 kV Station | Air Liquide to construct 138 kV Ring Bus | NEW | Dupont SW Ingleside |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020197 | 2022-03-15 |  | 138 | 0.01 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8979, 8422, 8818, 8978 | Y | Y |  | 0 | 59453 | 59452
6980 | Weimar Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Weimar Substation. |  | Weimar |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-03-18 |  | 138 | 0 | 0 | 0 |  | Colorado |  | Tier 4 |  |  |  |  | 7254, 7258 | Y | N |  |  | 14797 | 6980
49574 | Tesla: Build 345 kV terminal | Interconnect Misae II solar farm at Tesla |  | Tesla |  | Planned | 1023 - 1201 | ETT | Michael Glueck mlforcum@aep.com 918-599-2674 | 2785 | 2022-03-24 |  | 345 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501 | Y | N |  | 0 | 49575 | 49574
45334 | Corichi: Build 138 kV Box Bay | Build New Box Bay on El Campo - Victoria Line | Update Schedule | Corichi |  | Planned | 986 - 1164 | AEP TCC | Marc Wilson bcogan@aep.com 918-599-2857 | 3737 TP2018143 | 2022-03-30 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 8099, 88099, 8102, 8117 | Y | N |  | 0 | 45335 | 45334
50878 | North Edinburg: 345 kV Reconfigure | North Edinburg: 345 kV Reconfigure | Update Contact and Schedule | North Edinburg |  | Planned | 1056 - 1229 | AEP TCC | Rich Haley bcogan@aep.com 918-599-2857 | 3786 | 2022-03-30 |  | 345 | 0 | 0 | 0 | -100,0 | Hidalgo |  | Tier 4 |  |  |  |  | 8341, 8383 | Y | N |  | 0 | 50879 | 50878
52100 | Bradshaw to Steamboat: Rebuild 69 kV line | Rebuild Bradshaw to Steamboat 69 kV line | Update Schedule | Bradshaw | Steamboat | Planned | 1069 - 1242 | ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | 2830 | 2022-03-30 |  | 69 | 0 | 0.25 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6331, 60332, 6328, 60456 | Y | N |  | 0 | 65563 | 52100
53962 | Turtle Creek - Verde Creek Transmission Line Overhaul | LCRA TSC will perform an overhaul of T221 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T221 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  | Turtle Creek | Verde Creek | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-03-30 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7146, 7442 | Y | N |  | 0 | 53963 | 53962
59119 | Sparta Solar Interconnection | Sparta Solar Interconnection | Update Contact and Schedule | Tango |  | Planned |  | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | TP2020136 | 2022-03-30 |  | 345 | 0.01 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 88690, 8689 | Y |  |  | 0 | 59120 | 59119
62305 | STP to WA Parrish: Increase 345 kV Line MOT | Increase the MOT on STP to WA Parrish 345 kV line | Update Contact, Schedule | STP | WA Parrish | Planned |  | AEP TCC | Marc Wilson bcogan@aep.com 918-599-2857 | TA2021002 | 2022-03-30 |  | 345 | 0 | 0 | 0 |  | Matagorda | Fort Bend | Tier 4 |  |  |  |  | 5915, 44000 | Y | Y |  | 0 | 62306 | 62305
62365 | Close Feed to Martin | [6 empty] | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2022-03-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 9486, 60799 | Y |  |  | 0 | 62366 | 62365
4495 | Champlin: Station Reconfigure | Expand existing breaker configuration to a four (4) breaker ring bus expandable to a six (6) breaker ring bus configuration. |  | Champlin |  | Planned | 694 - 0864 | AEP TCC | John Pulay bcogan@aep.com 918-599-2857 | 3541 TP2014064 | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8476 | Y | N |  |  | 12064 | 4495
6022 | Stamford to Haskell Tap 1 69 kV line: Rebuild 69 kV line | Rehab Stamford to Haskell Tap 1 69 kV line | Update Schedule | Stamford | Haskell Tap 1 | Planned | 786 - 0971 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2668 | 2022-03-31 |  | 69 | 0 | 12.22 | 0 |  | Jones | Haskell | Tier 4 |  |  |  |  | 6171, 6172 | Y | N |  |  | 13739 | 6022
6571 | Lake Pauline to Vernon 69 kV line: Rebuild taps | Lake Pauline to Vernon 69 kV line: Rebuild taps |  | Lake Pauline | Vernon Main | Planned | 891 - 1069 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2815 | 2022-03-31 |  | 69 | 0 | 2.5 | 0 |  | Hardeman | Wilbarger | Tier 4 |  |  |  |  | 6048, 6056, 6057, 6058 | Y | N |  | 0 | 65511 | 6571
6791 | Lake Pauline: Replace 138/69 kV Auto | Replace the 138/69 kV autotransformer at Lake Pauline with a 130 MVA autotransformer |  | Lake Pauline |  | Planned | 906 - 1084 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2730 | 2022-03-31 |  | 138 | 0 | 0 | 130 |  | Hardeman |  | Tier 4 |  |  |  |  | 6048, 6050 | Y | N |  | 0 | 66631 | 6791
6938 | Leonard Road Substation 69 | Construct Leonard Rd Substation with Dual Voltage Transformer. Will be served at 69kV until completion of Smetana to Leonard Rd 138kV line. | [5 empty] | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2022-03-31 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 32051, 32850, 32868 | Y |  |  | 0 | 65781 | 6938
44361 | Ft. Stockton SW: Build 138 kV station | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138 kV, reterminate into Solstice, install 138 kV capacitor bank at Solstice, and build new Ft. Stockton Switch 138 kV station | Update Contact and Schedule | Fort Stockton Switch |  | Planned | 908 - 1086 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 2735 | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 3 | 17RPG018 | 2017-12-22 | 2018-02-02 |  | 60717 | Y | N |  | 0 | 44362 | 44361
44399 | South Padre Island: Rebuild as GIS station | Rebuild South Padre Island as a GIS |  | South Padre Island | - | Planned | 948 - 1126 | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | 3712 | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8335, 8917 | Y | N |  | 0 | 44400 | 44399
49570 | Goodlett: Build 69 kV station | Build new Goodlett 69 kV station on the Childress to Quanah 69 kV line | Update Schedule | Goodlett |  | Planned | 1021 - 1199 | AEP TNC | Alison Scribailo mlforcum@aep.com 918-599-2674 | 2783 | 2022-03-31 |  | 69 | 0 | 0 | 0 |  | Hardeman |  | Tier 4 | 19RPG020 |  |  |  | 60446, 6052, 6053 | Y | N |  | 0 | 49571 | 49570
50892 | Seawall to Port Aransas: Replace 69 kV undersea cable | Replace Seawall to Port Aransas 69 kV undersea cable |  | Seawall | Port Aransas | Planned | 1058 - 1231 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3789 TP2019166 | 2022-03-31 |  | 69 | 0 | 0.5 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8435, 8442 | Y | N |  | 0 | 65549 | 50892
52638 | Solanum: Build 138 kV station | Construct new 138 kV box bay on the Abilene South to Putnam 138 kV line | Update Contact and Schedule | Solanum |  | Planned | 1074 - 1247 | AEP TNC | Charles Gibson mlforcum@aep.com 918-599-2674 | 2835 | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  |  | 61015, 6309, 60365 | Y | N |  | 0 | 65565 | 52638
53854 | Avenger: Build 69 kV station | Construct new 69 kV station on the Putnam to Cross Plains 69 kV line | Update Contact and Schedule | Avenger |  | Planned | 1084 - 1257 | AEP TNC | William Lovelace mlforcum@aep.com 918-599-2674 | 1854 | 2022-03-31 |  | 69 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  |  | 60457, 6312, 6357 | Y | N |  | 0 | 65567 | 53854
55971 | Eagle Nest (EGL) Sub for Brazoria West Solar (20INR0101) | Install new 138kV Eagle Nest substation for generator interconnection to Brazoria West Solar. Loop Ckt.02 into Eagle Nest substation to create new Ckt.02 BURKE to Eagle Nest to West Columbia |  | Eagle Nest | BURKE/ West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42430, 42410, 43380 | Y | N |  | 0 | 56717 | 55971
57756 | WOLF 345kV for Fighting Jays Solar (21INR0278) | New 345kV CNP WOLF (WLF) substation for generator interconnection to Fighting Jays Solar. Loop Ckt.64C into substation to create new Ckt.64 Hillje to WOLF to WA Parish. |  | WOLF | Hillje/WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Fort Bend | Tier 4 |  |  |  |  | 44160, 44000, 44200, 112495 | Y | N |  | 0 | 57757 | 57756
64486 | Angleton to WINMIL Ckt.26B Upgrades | Upgrade Ckt 26B Angleton to WINMIL to increase thermal limits |  | Angleton | WINMIL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 44531 | Y | N |  | 0 | 64487 | 64486
64497 | Dyann to South Lane City Ckt.60D Upgrade | Upgrade Dyann to South Lane City Ckt.60D to increase thermal limits |  | Dyann | South Lane City | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 42985, 43190 | Y | N |  | 0 | 64498 | 64497
59319A | Garrott to Midtown to Polk Ckt.90 Upgrades | Upgrade Ckt.90D Garrott to Midtown to increase thermal limits |  | Garrott | Midtown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47660, 47661, 47706, 47708, 47705 | Y | N |  | 0 | 59320 | 59319
59319B | Garrott to Midtown to Polk Ckt.90 Upgrades | Upgrade Ckt.90B Midtown to Polk to increase thermal limits |  | Midtown | Polk | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47705, 47707, 47709, 47731, 47730 | Y | N |  | Cost included in main entry | 59321 | 59319
64572A | HO Clarke Bus Upgrade | Upgrade bus work at HO Clarke 138kV facilities |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47150, 47175, 47170 | Y | N |  | 0 | 64573 | 64572
64572B | HO Clarke Bus Upgrade | Upgrade Ckt.90A HO Clarke to HOC TR1 to increase thermal limits |  | HO Clarke | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47175, 47151 | Y | N |  | Cost included in main entry | 64574 | 64572
4487 | Nueces Area 69kV Reinforcement | Expand and add new 138/69kV Auto at Valero East 69kV substation. Add 5th breaker to Champlin 138kV substation. Construct Champlin to Valero East 138kV Line. |  | Champlin | Valero East | Planned | 709 - 0879 | AEP TCC | John Pulay mlforcum@aep.com 918-599-2857 | 2903 TP2016067 | 2022-03-31 01:00 |  | 138 | 1.6 | 0 | 200 |  | Nueces |  | Tier 4 | 19RPG011 |  |  |  | 8528, 8476, 8859 | Y | N |  |  | 13570 | 4487
47426 | Clear Fork - Robert Brown Transmission Line Overhaul | Increase the reliability and capability of circuit T519 on the Clear Fork - Robert Brown Jr 8.8-mile 69-kV transmission line. Upgrade all structures to 138-kV class and bundled Suwannee capable. Upgrade conductor to bundled 959 ACSS Suwannee. Add OPGW. |  | Clear Fork | Robert Brown Jr | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-04-01 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7194, 7195 | Y | N |  | 0 | 47427 | 47426
63425 | Adds TNMP Devon POI |  |  | TNMP Gemsbok (38109) | TNMP Devon (38112) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-04-01 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38112, 38107 | Y |  |  | 0 | 63426 | 63425
64778 | Rebuild 138kV Industrial-Brinker line to 700MVA |  |  | Industrial | Brinker | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2022-04-01 |  | 138 | 0 | 0.21117 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 913, 927 | Y | N |  | 0 | 64779 | 64778
64782 | Rebuild 138kV Spencer-Industrial line to 700MVA |  |  | Industrial | Brinker | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2022-04-01 |  | 138 | 0 | 0.32008 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 913, 982 | Y | N |  | 0 | 64783 | 64782
51216F | Ward Winkler RPG | Convert & re-conductor existing TNMP Wickett - Oncor Yucca 69kV line to 138kV, construct line extension (~1.3 miles) and re-terminate line to Oncor Wolf 138kV station. |  | TNMP Wickett (37980 / 37981) | Oncor Wolf (1013) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-04-02 |  | 138 | 1.3 | 4.7 | 0 |  | Ward | Ward | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 1013, 1015, 37940, 37960, 37980, 37981 | Y |  |  | 0 | 56661 | 51216
5621 | South McAllen-Bentsen and North Edinburg-West Edinburg | Replace MLSE equipment at North Edinburg and South McAllen | Update Schedule | North Edinburg | North McAllen | Planned | 795 - 0980 | AEP TCC | Michael Richardson bcogan@aep.com 918-599-2857 | 3585 | 2022-04-07 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8367, 8371, 8631, 79603 | Y | N |  |  | 13351 | 5621
6971 | Magnolia Mercer Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Magnolia Mercer Substation. |  | Magnolia Mercer |  | Planned | 1018915 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018915 | 2022-04-14 |  | 69 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7218, 7215, 7220 | Y | N |  |  | 14788 | 6971
6988 | Sheriff's Posse Switch & Breaker Upgrades | At Sheriff's Posse - Upgrade/Replace underrated switches 2967, 2969, 2971 to 3,000 Amp Switches. Replace and increase fault interrupting rating of breaker 2970 to 63kA, and its continuous rating to 3,000 Amp. Replace CS 2965 and CS 2975 to 40kA units. Add a Ring Bus at Sheriff's Posse as well, adding one new NBU owned 3,000 Amp breaker and isolation switches as well. | The scope of work related to the project is being limited to just the substation work at Sheriff's Posse. NBU is delaying the upgrade of T-340 to 959 ACSS due to budget limitations. That line upgrade is tentatively proposed to be completed by 7/31/2026. | Sheriff's Posse | Marion | Under Construction |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 jmorriss@nbutexas.com 830-608-8881 |  | 2022-04-15 |  | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 |  |  |  |  | 7460 | Y | N |  |  | 14806 | 6988
63633 | Tribute: Build 138 kV Temorary Hard Tap | Build new 138 kV temp tap on the San Angelo Power to Red Creek 138 kV line | NEW | Tribute |  | Planned | 1131 - 1309 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1876 | 2022-04-29 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 60008, 6442, 6473 | Y | N |  | 0 | 63634 | 63633
7161 | Naval_Base-North_Padre: Rebuild and re-conductor | For Naval Base-North Padre Tap: Rebuild line to 138 kV standards with 2000A conductor (795 ACSS). For North Padre Tap - North Padre station, double ckt. line is already built to 138 kV standards with 477 ACSR. Re-conductor both circuits with largest possible conductor to achieve maximum rating. The 2nd ckt. is part of the North Padre - Mustang Island branch |  | Naval Base | North Padre Tap | Planned | 909 - 1087 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3690 | 2022-04-30 |  | 69 | 0 | 12.7 | 0 |  | Nueces | Nueces | Tier 3 | 19RPG001 |  |  |  | 8495, 8847, 8856 | Y | N |  | 0 | 65519 | 7161
48776 | Tidehaven: Construct New Distribution Station | Tidehaven: Construct New Distribution Station |  | Blessing | Lolita | Planned | 1028 - 1206 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3767 DP21X0007 | 2022-04-30 |  | 138 | 0 | 0 | 0 |  | Matagorda | Jackson | Tier 4 |  |  |  |  | 8044, 8121, 8125 | Y | N |  | 0 | 48777 | 48776
55217 | Putnam to Leon: Rebuild 138 kV line | Rehab Putnam to Leon 138 kV line |  | Putnam | Leon | Planned | 1042 - 1269 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1859 | 2022-04-30 |  | 138 | 0 | 20.81 | 0 |  | Callahan | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | N |  | 0 | 55218 | 55217
58907 | AEN_22TPIT_NEW_GEN_BIGSTAR_CONNECTION_CISTERN_SUB | New 345 kV station to interconnect Big Star Solar and Storage generation interconnection |  | Holman | Lytton | Planned |  | AEN | Reza Ebrahimian Reza.Ebrahimian@austinene 512-322-6740 |  | 2022-04-30 |  | 345 | 0 | 0 | 0 |  | Fayette | Caldwell | Tier 4 |  |  |  |  | 9043, 9073, 9074 | Y |  |  |  | 58908 | 58907
59088 | Alice - Falfurrias: Line Rebuild | Alice - Falfurrias: Line Rebuild | NEW | Alice | Falfurrias | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020088 | 2022-04-30 |  | 69 | 0 | 3.67 | 0 |  | Jim Wells | Brooks | Tier 2 |  |  |  |  | 8500, 8508, 8878, 8894 | Y |  |  | 0 | 65586 | 59088
59293 | Maddux: Build New 138 kV Station | Interconnect Concho Valley Solar to the SAPS to Treadwell AND the SAPS to Eldorado Live Oak 138 kV Lines | Update Schedule and Cost | Maddux |  | Planned | 1125 - 1303 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 1870 | 2022-04-30 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6015, 6016, 6480, 6490, 60423 | Y | N |  | 0 | 59294 | 59293
59363A | Hungerford (HUG) CNP-Owned Sub for SBranch Solar (22INR0205) | New 138kV Hungerford (HUG) substation for generator interconnection to SBranch Solar. Loop Ckt.60 into substation to create new Ckt.60 East Bernard to Hungerford to Caney tap. |  | Hungerford | East Bernard/Caney | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-04-30 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44150, 42985, 43570, 44130, 44131, 44190, 112093 | Y | N |  | 0 | 59364 | 59363
63772 | Hyperion: Build 345 kV Station | Build new 345 kV Station next to the Cottonwood 345 kV station | NEW | Hyperion |  | Planned | 1133 - 1311 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1878 | 2022-04-30 |  | 345 | 0 | 0 | 0 |  | Dickens |  | Tier 4 |  |  |  |  | 60006, 60007, 59904 | Y | N |  | 0 | 63773 | 63772
59363B | Hungerford (HUG) CNP-Owned Sub for SBranch Solar (22INR0205) | Upgrade Ckt.60A Beasly to Orchard to Minimum 525/580 MVA to increase thermal limits |  | Beasly | Orchard | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-04-30 |  | 138 | 0 | 0 | 0 |  | Wharton | Fort Bend | Tier 4 |  |  |  |  | 42420, 44541, 44540 | Y | N |  | 0 | 59365 | 59363
44513 | Concho to Live Oak: Rebuild 69 kV line | Rebuild remaining portions of the Concho to Live Oak 69 kV line |  | Concho | Live Oak | Planned | 941 - 1119 | AEP TNC | Jim Nivens mlforcum@aep.com 918-599-2674 | 2755 | 2022-04-30 01:00 |  | 69 | 0 | 3.3 | 0 |  | Tom Green | Schleicher | Tier 4 |  |  |  |  | 6450, 6494, 6495, 6496, 6497, 6498, 6527 | Y | N |  | 0 | 65522 | 44513
58542 | Texas City RPG | Texas City RPG |  | Cat Tail (38580), Cherokee (39075) & Greenbelt (38575) | Texas City Main (39140,39141) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-05-01 |  | 138 | 4.1 | 0 | 200 |  | Galveston | Galveston | Tier 2 |  | 2020-04-16 | 2020-09-16 |  | 38580, 39141, 38575, 39075, 39140 | Y |  |  | 0 | 58543 | 58542
60528 | Rebuild West Columbia Main-West Columbia Local with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39500, 39530 | Y |  |  | 0 | 60529 | 60528
44868 | McKenzie - Westside 138 kV Line: Rebuild | Rebuild McKenzie - Westside 138 kV Line | Update Project Title, Project Description, and Schedule | McKenzie Road | Westside | Under Construction | 968 - 1146 | ETT | James Weaver bcogan@aep.com 918-599-2857 | 3726 TP2018126 | 2022-05-04 |  | 138 | 0 | 11.48 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8485, 8858 | Y | N |  | 0 | 65524 | 44868
63429 | Adds TNMP Alamo Street Substation |  |  | 16th Street (bus # 38310), Soaptree (bus # 38450), and Airport (bus # 38340) | Alamo Street Substation (bus # 38330) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-05-05 |  | 138 | 0.135 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38310, 38340, 38450 | Y |  |  | 0 | 63430 | 63429
63431 | Adds TNMP Holiday Switching Station |  |  | Century (bus # 38432), Soaptree (bus # 38450), and Alamo Street (bus # 38330) | Holiday Switching Station (bus # 38455) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-05-06 |  | 138 | 0.845 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38455, 6671, 38331, 38432, 38450 | Y |  |  | 0 | 63432 | 63431
4895 | CPSE_Capitol Cement Transmission Reconfiguration | Re-configurate Capitol Cement by loop into the existing Dresden to Skyline 138 kV transmission line and removing the existing Captiol Cement to Tuttle 138 kV transmission line. |  | Capitol Cement | Dresden/Skyline | Planned | S-0767 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0246 | 2022-05-13 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5075, 5130, 5370, 5435 | Y | N |  |  | 12507 | 4895
46968 | Gabriel Substation Upgrade | LCRA TSC will upgrade the configuration of the 138-kV bus from single bus/single breaker to a breaker and a half bus configuration and replace five existing CBs at Gabriel Substation and provide for future Georgetown PWT addition. |  | Gabriel | Gabriel | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-13 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y | N |  | 0 | 46969 | 46968
50643 | CPSE_Spruce_Skyline MLSE | Upgrade terminals at Spruce and Skyline to ensure a 3000 A rating (minimum). |  | Skyline | Spruce | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0899b/S-0899c | 2022-05-13 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5371, 5400 | Y |  |  | 0 | 50644 | 50643
53965 | Red Rock - Tahitian Transmission Line Overhaul | LCRA TSC will perform an overhaul of T153 with replacement structures that are capable of operating at 138-kV and supporting a single 959 ACSR Suwannee conductor. The replacement conductor on T153 will be 595 ACSR Suwannee. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  | Red Rock | Tahitian Village | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-05-13 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7560, 7575, 7576 | Y | N |  | 0 | 53966 | 53965
54101 | Ranch Road - Hilltop Transmission Line Upgrade | Increase the reliability of transmission facilities on the T375: Hilltop-Ranch Road 12 3.95-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | Ranch Road 12 | Hilltop | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-05-13 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7186, 7190 | Y | N |  | 0 | 54102 | 54101
10TPIT0025 | Bluff Spring 138kV substation | Establish 138kV Bluff Spring substation with (2) 30MVA transformers and will cut into existing Ckt 988 (Lytton Springs to Slaughter Lane). New circuits will be CKT988: from LY-BF and CKT1031 from BF-SL | [5 empty] | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P151 PLAN_117_P152 | 2022-05-14 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 9262, 9075, 9267 | Y |  |  | 0 | 61089 | 1030
14TPIT0056 | Northaven - Morrison 138 kV line | Upgrade existing double-circuit line |  | Northaven | Morrison | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4088-E | 2022-05-15 |  | 138 | 0 | 12 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2655, 2656, 2660, 2661, 2662, 2663, 2782, 2783 | Y | N |  |  | 9773 | 2493
5491 | Whitestone - Leander 138kV Transmission Line Upgrade | Upgrade the Whitestone - Blockhouse (T469) and the Blockhouse - Leander (T326) 138kV Line to 441MVA and upgrade the Blockhouse Substation to a ring bus. |  | Whitestone | Leander | Under Construction |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2022-05-15 |  | 138 | 0 | 5.4 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7525, 7527, 7529 | Y | N |  | 0 | 51769 | 5491
5624 | Killeen Sw. Sta. 345/138 kV Autotransformer Replacement | Replace existing autotransformer |  | Killeen Sw. Sta. | Killeen Sw. Sta | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R797 | 2022-05-15 |  | 345 | 0 | 0 | 600 | -75,0 | Bell | Bell | Tier 4 |  |  |  |  | 3422, 3423, 13423 | Y | N |  |  | 13354 | 5624
7020 | Cedar Hill - Camp Wisdom 138 kV Line | Upgrade existing Cedar Hill - Camp Wisdom 138 kV Line |  | Cedar Hill | Camp Wisdom | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4250 | 2022-05-15 |  | 138 | 0 | 9.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2421, 2990, 2993, 2994, 2992, 2999 | Y | N |  |  | 14842 | 7020
7118 | Everman 345 kV Sw. Sta. | Rebuild Everman 345 kV Sw. Sta. |  | Everman |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5278 | 2022-05-15 |  | 345 | 0 | 0 | 0 |  | Tarrant |  | Tier 3 | 20RPG013 | 2020-07-01 | 2020-09-10 |  | 1882, 1885, 1886, 1887, 11885, 11886, 11888, 1880, 1900, 1906, 1907, 1931, 1932, 1935, 2285, 1888, 11882, 11887, 11884, 24997 | Y |  |  | 0 | 60063 | 7118
44359 | Solstice: Install 138 kV PST and capacitor bank | Install PST on the Fort Stockton Plant to Solstice 138 kV line at Solstice, install capacitor bank on the Solstice 138 kV bus |  | Solstice |  | Planned | 984 - 1162 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2734 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,14.4 | Pecos |  | Tier 3 | 19RPG002 | 2017-12-22 | 2018-02-02 |  | 60384, 6645, 60717, 6630, 60385 | Y | N |  | 0 | 65520 | 44359
46456 | LookoutAddsCapbanks | Lookout adds capbanks for voltage reliability |  | Lookout | Lookout | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,60 | Dallas | Dallas | Tier 4 | 20RPG003 |  |  |  | 828 | Y | N |  | 0 | 46457 | 46456
47424 | Clear Fork - Lockhart Transmission Line Overhaul | Increase the reliability and capability of circuit T601 on the Clear Fork - Lockhart 3.0-mile 69-kV transmission line.Upgrade all structures to 138-kV class and bundled Suwannee capable. Upgrade conductor to bundled 959 ACSS Suwannee. Add OPGW. |  | ClearFork | Lockhart | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-15 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7195, 7215 | Y |  |  | 0 | 47425 | 47424
54109 | Fayetteville - Substation Upgrade | Increase the reliability of substation equipment at Fayetteville Substation through the replacement of the Fayetteville AT2 autotransformer and installation of two 138-kV shunt reactors. |  | Sayetteville Substation | Sayetteville Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7057, 7286, 7853 | Y | N |  | 0 | 54110 | 54109
57163 | Rebuild VanHumble to Olivia Switch | Rebuild 4/0 ACSR with 795 ACSR on 138 kV capable poles |  | Van Humble Switch | Olivia Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-05-15 |  | 69 | 0 | 14.4 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 5574, 5580 | Y | N |  | 0 | 57164 | 57163
57934 | Midland East - Spraberry 138 kV Line Rebuild | Add Midland East - Spraberry 138 kV Line Rebuild |  | Midland East | Spraberry | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8147 | 2022-05-15 |  | 138 | 0 | 13.5 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 | 2021-03-12 |  | 11294, 11295, 11296, 1023, 1132, 1329, 11123, 11134, 11361 | Y |  |  | 0 | 60082 | 57934
59201 | Brushy Creek 138 kV Switch | Brushy Creek 138 kV Switch |  | Brushy Creek Switch | Brushy Creek Switch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6148 | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3541, 3650, 3658, 13430 | Y |  |  | 0 | 59202 | 59201
59406 | Tex Harvey 138 kV Capacitors | Add Tex Harvey 138 kV Capacitors |  | Tex Harvey | Tex Harvey | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8567 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Midland | Midland | Tier 4 |  |  |  |  | 1221 | Y |  |  | 0 | 59408 | 59406
59409 | Centralia 138 kV Capacitors | Add Centralia 138 kV Capacitors |  | Centralia | Centralia | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8568 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Upton | Upton | Tier 4 |  |  |  |  | 11209 | Y |  |  | 0 | 59534 | 59409
59412 | Grady 138 kV Capacitors | Add Grady 138 kV Capacitors |  | Grady | Grady | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8571 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Martin | Martin | Tier 4 |  |  |  |  | 23842 | Y |  |  | 0 | 59535 | 59412
59418 | Brown 138 kV Capacitors | Add Brown 138 kV Capacitors |  | Brown | Brown | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8551 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Martin | Martin | Tier 4 |  |  |  |  | 23838 | Y |  |  | 0 | 59538 | 59418
59421 | McIlvain 138 kV Capacitors | Add McIlvain 138 kV Capacitors |  | McIlvain | McIlvain | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8562 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Reeves | Reeves | Tier 4 |  |  |  |  | 11182 | Y |  |  | 0 | 59533 | 59421
59541 | Wolf 138 kV Terminal Addition | Add Wolf 138 kV Terminal Addition |  | Wolf Switch | Wolf Switch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8505 | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 1013 | Y |  |  | 0 | 59543 | 59541
59546 | Lamesa 138/69 kV Autotransformer #1 | Replace Lamesa 138/69 kV Autotransformer #1 |  | Lamesa | Lamesa | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8561 | 2022-05-15 |  | 138 | 0 | 0 | 86 |  | Dawson | Dawson | Tier 4 |  |  |  |  | 1163, 1355, 1164, 1356 | Y |  |  | 0 | 59548 | 59546
59765 | Loy Lake 138 kV Capacitors | Install new 138 kV Capacitors |  | Loy Lake |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R989 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Grayson |  | Tier 4 |  |  |  |  | 1834 | Y |  |  | 0 | 64020 | 59765
60060 | Add Marlin South 69 kV Cap Bank | Add Marlin South 69 kV Cap Bank |  | Marlin South | Marlin South | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R468 | 2022-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Falls | Falls | Tier 4 |  |  |  |  | 3641 | Y |  |  | 0 | 60061 | 60060
60064 | Add Harris Creek 69 kV Capacitor | Add Harris Creek 69 kV Capacitor (Formerly known as McGregor East) |  | Harris Creek | Harris Creek | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R790 | 2022-05-15 |  | 69 | 0 | 0 | 0 | 0,55.2 | McLennan | McLennan | Tier 4 |  |  |  |  | 3596, 3441, 3586 | Y |  |  | 0 | 62663 | 60064
61519 | Salt Flat Road - Skywest 138 kV Line Rebuild | Salt Flat Road - Skywest 138 kV Line Rebuild |  | Salt Flat Road | Skywest | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8569 | 2022-05-15 |  | 138 | 0 | 1 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23859, 71210 | Y |  |  | 0 | 61521 | 61519
61522 | Salt Flat Road 138 kV Capacitors | Add Salt Flat Road 138 kV Capacitors |  | Salt Flat Road | Salt Flat Road | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8575 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Midland | Midland | Tier 4 |  |  |  |  | 23859 | Y |  |  | 0 | 61526 | 61522
63410 | Cyclone Switch (Bright Arrow Solar) | Establish station for Bright Arrow Solar on Thorn Tree Switch to Farmersville 345 kV Line. |  | Cyclone | Cyclone | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4701 | 2022-05-15 |  | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 11689, 1685, 11688 | Y | N |  | 0 | 63412 | 63410
64388 | Install second 110.4 Mvar 138 kV capacitor bank at Sandow | Install second 110.4 Mvar 138 kV capacitor bank at Sandow |  | Sandow | Sandow | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6189 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Milam | Milam | Tier 4 |  |  |  |  | 13430 | Y |  |  | 0 | 64389 | 64388
64390 | Install two series reactors at Sandow Switch | Install two 2 ohm series reactors at Sandow Switch in series with the 345/138 kV Autotransformer #1 and Autotransformer #2 |  | Sandow | Sandow | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6116 | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 13441, 13442, 13430, 13429, 13439, 13440 | Y |  |  | 0 | 64391 | 64390
52316 | Anna Tap - Princeton 138 kV Line | Upgrade the Anna Tap - Princeton 138 kV Line |  | Anna Tap | Princeton Switch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4275 | 2022-05-15 01:00 |  | 138 |  | 9.6 | 0 |  | Collin | Collin | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 2527, 2707, 2528, 2708 | Y |  |  | 0 | 52317 | 52316
57919 | Buzzard Draw 138 kV Terminal Additions | Buzzard Draw 138 kV Terminal Additions |  | Buzzard Draw | Buzzard Draw | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8555 | 2022-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 1355, 23829, 23838 | Y |  |  | 0 | 57921 | 57919
14TPIT0010 | Handley - Sherry 138 kV line | Upgrade existing line |  | Handley | Sherry | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5155-E | 2022-05-15 12:00 |  | 138 | 0 | 8.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1919, 1920, 1950, 1951, 2245, 2246, 2247, 2251, 2252 | Y | N |  | 0 | 59262 | 2582
45527 | Plano West - Richardson Collins 138 kV Line | Upgrade the Plano West - Richardson Collins 138 kV Line |  | Plano West Switch | Richardson Collins Switch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M364 | 2022-05-15 12:00 |  | 138 | 0 | 0 | 0 |  | Collin | Dallas | Tier 4 |  |  |  |  | 2685, 2628, 2673, 2683, 2684, 2686, 12684 | Y |  |  | 0 | 45528 | 45527
61599 | Pinto Creek Circuit Breaker Addition | This project provides a point of interconnection for a new generator by converting Pinto Creek Substation into a ring bus (GINR # 21INR0019). |  | Pinto Creek | Pinto Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-18 |  | 138 | 0 | 0 | 0 |  | Kinney |  | Tier 4 |  |  |  |  | 78255 | Y | N |  |  | 61600 | 61599
3463 | Shady Bus Split | Reconfigure 69kV bus |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.co 979-821-5763 |  | 2022-05-21 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 | [5 empty] | Y |  |  |  | 10843 | 3463
48782 | Progreso: Construct New Distribution Station | Progreso: Construct New Distribution Station | Update schedule | Rio Rico | Stewart Road | Planned | 1031 - 1209 | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | 3770 DP20X0009 | 2022-05-30 |  | 69 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8040, 8751, 8949 | Y | N |  | 0 | 48783 | 48782
50880 | Medio Creek to Warburton (STEC) | Lon Hill - STEC Warburton: Line Rebuild |  | Medio Creek | STEC Warburton | Planned | 1055 - 1228 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3783 | 2022-05-30 |  | 138 | 0 | 32.7 | 0 |  | San Patricio | Refugio | Tier 3 | 19RPG014 | 2019-09-05 | 2019-10-07 |  | 5607, 8912 | Y | Y |  | 0 | 65544 | 50880
59099 | Rebuild Blessing to Celanese 138 kV Line | Rebuild Blessing to Celanese 138 kV Line | NEW | Matagorda |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020227 | 2022-05-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8116, 8121, 8191, 8558 | Y |  |  | 0 | 65587 | 59099
4465 | Wirtz to FlatRock to Paleface Transmission Line Upgrade | Upgrade the 17.34 mile Wirtz (7104) - Flat Rock (7111) - Paleface (7477) 138-kV transmission line to bundled 795 ACSR Drake, 441 MVA and add Breakers at Flatrock. |  | Wirtz | Paleface | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2022-05-31 |  | 138 | 0 | 17.34 | 0 |  | Burnet | Travis | Tier 4 |  |  |  |  | 7104, 7111, 7477 | Y | N |  |  | 12026 | 4465
5244 | Hardy to Northside Ckt.91 Thermal Uprate | Upgrade Ckt.91 Hardy to Northside to increase thermal ratings | - Overall Date Update | Hardy | Northside | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45840, 47711 | N | N |  |  | 12919 | 5244
52218 | Alvin 69kV Substation Bypass | Alvin 69kV Substation Bypass |  | Webster | Manvel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 69 | 0 | 0 | 0 |  | Galveston | Brazoria | Tier 4 |  |  |  |  | 42080, 42600, 43510, 44440 | Y | N |  | 0 | 52225 | 52218
52565D | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Upgrade Ckt.90A HO Clarke to Kirby to Garrott to increase thermal limits |  | Kirby | HO Clarke/Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 9.51 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47151, 47322, 47660 | Y | N |  | Cost included in phase F | 59282 | 52565
54811 | Winecup: Build 69 kV station | Construct new 69 kV box bay on the North San Angelo to San Angelo Grape Creek Tap 69 kV line |  | Winecup |  | Planned | 1041 - 1268 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1858 | 2022-05-31 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 60796, 6459, 6465 | Y | N |  | 0 | 54812 | 54811
55550 | Brushline: Construct New Distribution Station | Brushline: Construct New Distribution Station |  |  |  | Planned | 1106 - 1284 | AEP TCC | Rick Garcia bcogan@aep.com 918-599-2857 | 3826 | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8972, 5754, 8963 | Y |  |  | 0 | 55551 | 55550
55961 | PSARCO to Highlands Ckt.08G Upgrades | Upgrade Ckt.08G PSARCO to Highlands with minimum 427MVA Continuous Rating |  | Highlands | PSARCO | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40811, 41300 | Y | N |  | 0 | 55962 | 55961
56012 | PSARCO Fault Duty Upgrade with Bus Reactors | Install (3) 10-Ohm Reactors at PSARCO by splitting PSARCO bus as a fault duty upgrade |  | PSARCO |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41300, 41303, 41305, 40190, 41021, 110560, 110579, 110571, 110572, 110573, 110574, 110577 | Y | N |  | 0 | 65112 | 56012
57543 | Angleton to West Columbia Ckt 04E Line Upgrades | Reconductor Ckt 04E Angleton to West Columbia to address line clearance concerns |  | Angleton | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 16.11 | 0 |  | Brazoria | Brazoria | Tier 4 | 21RPG005 | 2021-03-10 | 2021-04-02 |  | 42110, 43381, 43380 | Y | N |  | 0 | 61529 | 57543
57584 | Cedar Bayou Auto A1 and A3 Position Swaps at 138kV | Swap Cedar Bayou Auto A1 and A3 Positions on the 138kV side to address fault concerns |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 345 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  |  | 40000, 40010, 40015, 49005, 49008 | Y | N |  | 0 | 57585 | 57584
57735A | Mykawa 138kV Switching Station | Install new CNP-owned 138kV switching station |  | Pearland |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42750 | Y | N |  | 0 | 57736 | 57735
57912 | Champlin to Weil Tract: Rebuild 138 kV Line | Champlin to Weil Tract Line Rebuild |  | Champlin | Weil Tract | Planned | 1111 - 1289 | ETT | Nathan Cowan mlforcum@aep.com 918-599-2674 | 3830 | 2022-05-31 |  | 138 | 0 | 1.37 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8476, 8482 | Y | N |  | 0 | 65581 | 57912
58006 | Magnolia Cap Bank | Install Cap bank (14.4 Mvar ) at Magnolia |  | Kosciusko |  | Planned | 1115 - 1293 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3834 | 2022-05-31 |  | 138 | 0 | 0 | 0 | 0,14.4 |  |  | Tier 4 |  |  |  |  | 8583 | Y |  |  | 0 | 58007 | 58006
58008 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild 11.691 miles of the Laredo VFT North to North Laredo Switch 138 kV transmission line and upgrade any limiting elements. |  | Laredo | Laredo | Planned | 1116 - 1294 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3835 | 2022-05-31 |  | 138 | 11.68 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8112, 8643, 8909, 8918, 80013 | Y |  |  | 0 | 65582 | 58008
58065 | Alvin Approach Upgrades Ckt.53 | Upgrade portions of Ckt.53B and Ckt.53C ahead of future 138kV conversions |  | Alvin | EXTER/Manvel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 69 | 0 | 9.51 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42080, 44440, 42600 | Y | N |  | 0 | 58066 | 58065
59086 | Edna to Victoria: Rebuild 138 kV line | Rebuild 138 kV line from Enda to Victoria | NEW | Edna | Victoria | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020888 | 2022-05-31 |  | 138 | 0 | 26.35 | 0 |  | Jackson | Victoria | Tier 3 |  |  |  |  | 8118, 8172 | Y | N |  | 0 | 65585 | 59086
59313 | Beasly (BEA) CNP-Owned Sub for Fort Bend Solar (18INR0053) | Loop new 138kV Beasly (BEA) substation for generator interconnection to Fort Bend Solar. Loop Ckt.60 into Beasly substation to create new Ckt.60 East Bernard to Beasly to Orchard |  | Beasly | East Bernard/Orchard | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 42420, 44190, 44541 | Y | N |  | 0 | 59314 | 59313
59322 | Sealy to Peters Ckt.65A Upgrades | Upgrade Ckt.65A Sealy to Peters to increase thermal limits |  | Sealy | Peters | Planned | 525535253359322 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 5.07 | 0 |  | Austin | Austin | Tier 3 | 20RPG020 | 2020-10-27 | 2020-11-18 |  | 44640, 46220 | Y | N |  | 0 | 59323 | 59322
59342 | Greens Bayou to LYCHEM Ckt.08 Upgrade | Rebuild and reconductor a de-energized section of Ckt.38Z. Loop the rebuilt section into 138kV Ckt.08F between Moore Road and Uvalde tap. The reconfiguration creates additional conductor impedance on the line to increase the fault duty margin for future generation. |  | Moore Road | Uvalde | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 3.25 | 3.25 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40559, 40281, 40555, 41023, 41651 | Y | N |  | 0 | 59343 | 59342
59346 | Hillcroft to Dunvale Ckt.24B Upgrades | Upgrade Ckt.24B Hillcroft tap to Dunvale tap with minimum 340MVA Emergency Rating |  | Hillcroft | Dunvale | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 1.04 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47072, 47191 | Y | N |  | 0 | 59347 | 59346
59387 | DANBUR (DAB) 138kV Sub for Long Bow Solar (20INR0026) | Loop new CNP 138kV substation DANBUR (DAB) into Ckt.04C Angleton to Liverpool to create new Ckt.04 Angleton to DANBUR to Liverpool. Install one generator lead for new interconnection to Longbow Solar. |  | DANBUR | Angleton/Liverpool | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42875, 42110, 42870 | Y | N |  | 0 | 59388 | 59387
59392 | Riverside (RVR) Sub for CHAMON Phase 2 (19INR0056) | Install new 138kV Riverside (RVR) CNP substation for generator interconnection to customer LIGNIN (LIG). Loop Ckt.94C into Riverside substation to create new Ckt.94 CHAMON to Riverside to Metals Switchrack |  | Riverside | CHAMON/Metals Switchrack | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40270, 40260, 41050 | Y | N |  | 0 | 59393 | 59392
61875 | Hungerford to East Bernard Ckt.60 Upgrades | Upgrade Hungerford to East Berrnard Ckt.60 to increase thermal limits |  | Hungerford | Caney | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44150, 44190 | Y | N |  | 0 | 61876 | 61875
62110 | WHALEY 345kV Sub for Cutlass Solar (19INR0131) | New 345kV CNP WHALEY (WLY) substation for generator interconnection to Cutlass Solar. Loop Ckt.72x into substation to create new Ckt.72x Cedar Creek to WHALEY to WA Parish |  | WHALEY | Cedar Creek/ WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44070, 44005, 44090 | Y | N |  | 0 | 62111 | 62110
62133 | West Columbia to Damon Ckt.89A Thermal Uprate | Upgrade West Columbia to Damon to Ckt.89A to Minimum 210 MVA Continuous rating |  | West Columbia | Damon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 10.3 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42370, 43380, 43384 | Y | N |  | 0 | 62134 | 62133
63519 | Ashton Woods Capacitor Bank Addition | 138 kV, 31.2 MVAR Cap Bank addition at Ashton Woods substation |  | Ashton Woods 138 kV Substation |  | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 | 0,31.2 | Travis | Travis | Tier 4 |  |  |  |  | 9226 | Y |  |  | 0 | 63520 | 63519
63902 | Bakersfield: Build New 345 kV Terminal | Interconnect Hydra BESS to the Bakersfield 345 kV Station | NEW | Bakersfield |  | Planned | 1136 - 1314 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 1881 | 2022-05-31 |  | 345 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60016, 76002 | Y | N |  | 0 | 63903 | 63902
64482 | Angleton Substation Expansion for Mark One | Expand Angleton substation for Mark One Gas Generator (22INR0369) |  | Angleton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 112597, 42110 | Y | N |  | 0 | 64483 | 64482
64501 | Dunlavy to Heights Ckt.31C Upgrade | Upgrade Dunlavy to Heights Ckt.31C to increase thermal limits |  | Dunlavy | Heights | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47580, 47581, 47682, 47680 | Y | N |  | 0 | 64502 | 64501
66043A | Ckt29 THW-WhiteOak Reconductor and 138kV Conversion | Rebuild-Reconductor 69kV Ckt.29 TH Wharton to Little York to White Oak ahead of 138kV conversion. |  | TH Wharton | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 69 | 0 | 12.2 | 0 |  | Harris | Harris | Tier 4 | 21RPG016 | 2021-09-08 | 2021-09-30 |  | 45530, 45990, 46620 | Y | N |  | Cost included in final phase of project | 66044 | 66043
4418A | HO Clarke Upgrades | Join existing HO Clarke 69kV buses. Upgrade fault duty to minimum 60KA. |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47165, 44400, 47160, 47680 | Y | N |  | 0 | 63539 | 4418
57735B | Mykawa 138kV Switching Station | Loop Ckt.06K into new CNP-owned 138kV switching station to create new Ckt.06 Gulfgate to Mykawa to Pearland |  | Mykawa | Gulfgate/Pearland | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42742, 42750, 43051 | Y | N |  | Cost include in main project | 57737 | 57735
59398A | San Bernard (SAN) Sub for Brazoria County Solar (20INR0098) | New 138kV San Bernard (SAN) substation for generator interconnection to Brazoria County Solar. Loop Ckt.04 into new substation to create new Ckt.60 West Columbia to San Bernard to Pledger tap |  | San Bernard | West Columbia/Pledger | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43110, 43010, 43019, 43120, 43190, 43380, 112215 | Y | N |  | 0 | 59767 | 59398
57735C | Mykawa 138kV Switching Station | Loop Ckt.91A into new CNP-owned 138kV switching station to create new Ckt.91 Gulfgate to Mykawa to Pearland |  | Mykawa | Gulfgate/Pearland | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42741, 42750, 43052 | Y | N |  | Cost include in main project | 57738 | 57735
59398B | San Bernard (SAN) Sub for Brazoria County Solar (20INR0098) | Upgrade San Bernard to West Columbia Ckt.60 to increase thermal limits. Increase fault duty at West Columbia to 63KA |  | San Bernard | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43010, 43019, 43110, 43190, 43120, 43380 | Y | N |  | 0 | 59768 | 59398
4418B | HO Clarke Upgrades | Retire existing HO Clarke auto A3. |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 49009, 47175, 47165 | Y | N |  | Cost included in main project | 63540 | 4418
52565G | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Reposition existing Ckt.05B HO Clarke to Intermediate tap to the HOC ring bus. |  | HO Clarke | Intermediate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 01:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44361, 47150, 47170 | Y | N |  | Cost included in phase F | 63578 | 52565
17TPIT0002 | Hunt Lane to Pinn Road - 138 kV Transmission Line Rebuild | Rebuild approximately eight circuit miles of 138 kV transmission from Hunt Lane to Pinn Road |  | Hunt Lane | Pinn Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0190 | 2022-06-01 |  | 138 | 0 | 8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5054, 5305, 5324, 5345, 5427 | Y | N |  | There are no transformers associated with this project | 9558 | 2307
60522 | Rebuild Hidden Lakes-League City with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  | 0 | 60523 | 60522
63427 | Adds TNMP Girvin Switching Station |  |  | AEP Rio Pecos (bus # 6601),TNMP Soaptree (bus # 38450), and TNMP Whitebaker (bus # 38430) | Girvin Switching Station (bus # 38445) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-06-01 |  | 138 | 1 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38445, 6601, 38430, 38450 | Y |  |  | 0 | 63428 | 63427
61595 | Add Pinkney (Blanket South) 138 kV Substation | Add Pinkney (Blanket South) 138 kV Substation |  | Comanche | Brownwood | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6145 | 2022-06-15 |  | 138 | 0 | 0 | 0 |  | Brown | Brown | Tier 4 |  |  |  |  | 1666, 1667, 1441, 1661, 1662 | Y |  |  | 0 | 61596 | 61595
4323 | CPSE_Braunig to Brooks_MLSE | Upgrade terminal at Brooks and ensure a rating of 2000 A (minimum) at both Braunig and Brooks terminals |  | Braunig | Brooks | In-Service |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0669 | 2022-06-18 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5394, 5045 | Y | Y |  |  | 11875 | 4323
6281 | CPSE_Harlandal_Sommers_MLSE | Upgrade terminals at Harlandale and Sommers Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0732 | 2022-06-18 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5395 | Y |  |  |  | 14013 | 6281
47448 | Motorman Substation Addition | Construct a new 138-kV Motorman substation. Motorman Substation is located in west Texas approximately 0.25 miles west of the LCRA TSC Crane East Substation. Construct a 3-breaker ring bus cut in to the existing Crane East to LCRA Crane transmission line. | [5 empty] | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-06-22 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7869, 11238, 11239, 71214, 76615 | Y |  |  | 0 | 60784 | 47448
4577 | BRYN_4577_Dansby_Rebuild | Convert Dansby 69kV bus to Double Bus, Double Breaker configuration |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2022-06-29 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  |  | 32875, 32897 | Y |  |  | 0 | 64551 | 4577
65924 | Soap Creek Switch (Ellis Solar) |  |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4324 | 2022-06-29 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2289, 2300, 2310 | Y |  |  | 0 | 65925 | 65924
3948 | Steamboat to Tuscola: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola |  | Steamboat | Tuscola | Planned | 685 - 0855 | ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | 1851 | 2022-06-30 |  | 69 | 0 | 9.856 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6328, 6331, 60332 | Y | N |  |  | 11441 | 3948
3949 | Steamboat to Winters: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola |  | Steamboat | Winters | Planned | 685 - 0855 | ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | 1850 | 2022-06-30 |  | 69 | 0 | 9.944 | 0 |  | Taylor | Runnels | Tier 4 |  |  |  |  | 6333, 60332 | Y | N |  |  | 11442 | 3949
43460 | Moody to Stewart Ckt.63 Upgrades | Upgrade Ckt.63 Moody to Stewart |  | Moody | Stewart | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-06-30 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42951, 42953, 43290, 43355, 42950, 43520, 43521 | Y |  |  | 0 | 43461 | 43460
47436 | ROBERT BROWN JR ¿ SAN MARCOS Transmission Line OverHaul | Increase the reliability and capability of circuit T220 on the Robert Brown Jr ¿ San Marcos 4.9-mile 69-kV transmission line. Upgrade all structures to 138-kV class and bundled Suwannee capable. Upgrade conductor to bundled 959 ACSS Suwannee. Add OPGW. |  | Robert Brown JR | San Marcos | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-06-30 |  | 138 | 0 | 0 | 0 |  | Hays | Caldwell | Tier 4 |  |  |  |  | 7191, 7194, 7196 | Y | N |  | 0 | 47437 | 47436
57797 | Athey: Build 138 kV Station | Build new 138 kV Station on the Ft Stockton to Rio Pecos 138 kV line | Update Schedule | Athey |  | Planned | 1109 - 1287 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 1866 | 2022-06-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60792, 60718, 60798 | Y | N |  | 0 | 65578 | 57797
63667 | GSEC_539_Modify_Buses_Loads.prj |  |  |  |  | Planned |  | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2022-07-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6413, 9487, 60008 | Y |  |  | 0 | 63668 | 63667
53999 | ElCampo - Ricebird Transmission Line Strom Hardening | Increase the reliability of transmission facilities on the T589 El Campo ¿ Ricebird 4.6-mile 138-kV transmission line. |  | El Campo | Ricebird | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2022-07-14 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8102, 78104 | Y | N |  | 0 | 54000 | 53999
59763 | Construct three terminal 138 kV capable switching station | Change Markham hard wire tap point to 3 way switching station |  | Cayce Switch |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-07-15 |  | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5554, 5557, 5555, 5556, 8984 | Y | N |  | 0 | 65899 | 59763
51996 | Rebuild Markham Tap to AEP Markham Tap | Rebuild Markham Tap to AEP Markham Tap with 138 kV capable structures |  | Markham Tap | AEP MarkhamTap | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-07-16 |  | 69 | 0 | 1.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5557, 8984 | Y | N |  | 0 | 51997 | 51996
49546 | Resnik: Construct New 138 kV Station | Resnik: Construct New 138 kV Station | Update Project Title/Description and Schedule | Resnik |  | Planned | 996 - 1174 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 3749 | 2022-07-30 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8580, 8422, 8565, 80470 | Y | N |  | 0 | 49547 | 49546
52066 | Blessing to Bay City Pumps: Rebuild 69 kV Line | Rebuild Blessing to Markham Tap and retire the radial line servicing Bay City Pumps | Update Schedule, Trans Circuit Miles | Blessing | Markham Tap | Planned | 1076 - 1249 | AEP TCC | Marc E. Wilson bcogan@aep.com 918-599-2857 | 3801 | 2022-07-30 |  | 69 | 0 | 9.15 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 8546, 8547, 8549, 8119, 8550, 8984 | Y | N |  | 0 | 65559 | 52066
4505 | BRYN_4505_Smetana_Sub | Construction of a new Smetana Substation at 138kV |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2022-07-31 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32850, 32853, 32868 | Y |  |  | 0 | 63548 | 4505
4567 | BRYN_4567_Smetana_to_Leonard | Build Smetana to Leonard Rd 138 line in existing 69KV ROW of old Annex to Atkins line |  | 32897 | 32863 | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2022-07-31 |  | 138 | 0.75 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32853, 32851 | Y |  |  | 0 | 64546 | 4567
4576 | BRYN_4576_Smetana_to_Steele_Store | Construct New 138kV line (Bundled 1033 ACSR - Curlew) to new Steele Store substation as part of the reliability project to loop in Steele Store |  | 32853 | 32852 | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2022-07-31 |  | 138 | 4.5 | 0 | 0 |  | Brazos | Burleson | Tier 4 |  | 2015-10-09 | 2015-11-06 |  | 32852, 32853 | Y |  |  | 0 | 64545 | 4576
5792 | Leonard Road Substation 138 | Upgrade Leonard Rd from 69kV to 138kV and construct 138 from Leonard to Atkins |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2022-07-31 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32051, 32850, 32851, 32868, 32862, 32864 | Y |  |  | 0 | 65779 | 5792
6072 | Eldorado to Ft. McKavitt 69 kV line: Rebuild 69 kV line | Rehab Eldorado to Ft. McKavitt 69 kV line |  | Eldorado Tap | Ft. McKavitt | Planned | 786 - 0971 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2677 | 2022-07-31 |  | 69 | 0 | 19.41 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  |  | 6505, 6506, 6507, 6508 | Y | N |  |  | 13794 | 6072
52688 | Angleton Substation Expansion | Expand Angleton substation for the Myrtle Solar generator interconnection (19INR0041). |  | Angleton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-07-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 111533 | Y | N |  | 0 | 55842 | 52688
64503 | Dunlavy to Hyde Park Ckt.32A Reconductor | Reconductor Dunlavy to Hyde Park Ckt.32A ahead of future 138kV conversions |  | Dunlavy | Hyde Park | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-07-31 |  | 69 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47580, 47690 | Y | N |  | 0 | 64504 | 64503
62843 | El Sauz Ranch Wind Interconnection | Connect the El Sauz Ranch Wind to the Cebolla Station |  | Cebolla |  | Conceptual |  | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 |  | 2022-08-01 |  | 345 | 0.05 | 0 | 0 |  | Willacy |  | Tier 4 |  |  |  |  | 8663, 8601 | Y | Y |  | 0 | 62844 | 62843
59389 | Johnson Draw POD - Flat Iron Substation 138 kV line | Johnson Draw POD - Flat Iron Substation 138 kV line |  | Johnson Draw POD | Flat Iron Substation | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8580 | 2022-08-02 |  | 138 | 3 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11217, 11344 | Y |  |  | 0 | 59391 | 59389
59839 | Duck Cove Tap #1 - Wills Point 69 kV Double Circuit Line | Rebuild Duck Cove Tap - Wills Point 69 kV Line |  | Edgewood | Iron Bridge | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6137 | 2022-08-15 |  | 69 | 0 | 3.1 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 3187, 3188, 3189 | Y |  |  | 0 | 59840 | 59839
57167 | Faysville substation conversion from 69 to 138 kV | Converts Faysville to 138 and connects to Redgate |  | Faysville | Red Gate | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-09-01 |  | 138 | 8.46 |  | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5782, 5786, 5788, 5780, 5784, 8377 | Y | N |  | 0 | 63732 | 57167
61932 | Holliday - Seymour 69 kV Line | Rebuild the Holliday - Seymour 69 kV Line. |  | Holliday | Seymour | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4028 | 2022-09-15 |  | 69 | 0 | 0 | 0 |  | Archer | Baylor | Tier 3 | 21RPG007 | 2021-04-26 | 2021-05-18 |  | 779, 1527, 1530, 1532, 1534 | Y |  |  | 0 | 61933 | 61932
62112 | Establish Battleground138 kV Substation | Establish Battleground (Formerly Coupland) 138 kV Substation |  | Coupland | Coupland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6139 | 2022-09-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3690, 3541, 3658 | Y |  |  | 0 | 62632 | 62112
62652 | Removing 69kV BES elements from BPUB Airport Substation. | BPUB plans to remove the 138/69kV transformer and 69kV bus at Airport Substation. BPUB will be upgrading to a 138/12.5kV transformer. |  | 59460 | 59460 | Planned |  | BPUB | Javier Martinez jamartinez@brownsville-pub.com 956-083-6530 |  | 2022-09-20 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5946, 59460 | Y |  |  | 0 | 62653 | 62652
5940A | Mountain Home Substation and Transmission Line Addition | Construct new Mountain Home substation, add one(1) 138/69-kV autotransformer at Headwaters substation (located adjacent to Harper substation), construct a 138-kV transmission line from Hunt substation to Mountain Home substation to Headwaters substation. | For total project cost please see phase 5940B | Hunt | Headwaters | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017394 | 2022-09-22 |  | 138 | 19 | 0 | 45 |  | Kerr | Gillespie | Tier 1 | 16RPG015 | 2016-11-18 |  |  | 7410, 7750, 7751, 74100, 74101, 7144 | Y | N |  | 0 | 61873 | 5940
59093 | Starr Solar Connection | Starr Solar Connection | NEW | Roma Tap |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020209 | 2022-09-28 |  | 138 | 0.1 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 88795, 8795 | Y |  |  | 0 | 59094 | 59093
11TPIT0008 | RAINEY_ST 138kV substation | Establish a new 138kV Rainey St. Substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2022-09-30 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9261, 9118, 9132 | Y | N |  |  | 8208 | 1032
45399 | Bearkat Loop - Bearkat to Longshore | Adds 345 KV line from Bearkat to Longshore. |  | Bearkat | Longshore | Planned |  | WETT/ONCOR | Christina Minchew christina.minchew@windene 512-436-9469 |  | 2022-09-30 |  | 345 | 27 | 0 | 0 |  | Glasscock | Howard | Tier 1 |  | 2017-08-15 | 2018-09-19 | 2018-10-09 | 1058, 59903 | Y | N |  | 0 | 45473 | 45399
50440 | Delhi Substation Addition | Add a new load serving substation 10 miles north of IH-10 along 304, w/30 MVA PWT. |  | Delhi | Delhi | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-09-30 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7896 | Y | N |  | 0 | 50441 | 50440
51734 | Blue Stem to Delhi Transmission Line | Build new 9.5 mile 138/69 kV transmission. |  | BlueStem | Delhi | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-09-30 02:00 |  | 69 | 9.5 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7895, 7230, 7231, 7896 | Y | N |  | 0 | 51843 | 51734
64941 | PETSON to MONSAN Ckt.04D Upgrade | Upgrade Ckt 04D PETSON to MONSAN to increase thermal limits |  | PETSON | MONSAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-09-30 12:00 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43070, 42940 | Y | N |  | 0 | 64942 | 64941
6873 | Support 69kV to 138kV East Loop Conversion Projects | Upgraded lines Apollo to Naaman to Walnut to Newman to support 69kV to 138kV East Loop Conversion Projects |  | Apollo | Newman | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-10-01 |  | 138 | 0 | 10.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 825, 826, 800, 802, 823 | Y | N |  |  | 14682 | 6873
64480 |  | Converting straight bus to a ring bus configuration. |  | 6842 | 6842 | Planned |  | RYBRN |  |  | 2022-10-01 |  | 138 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 | [5 empty] | Y |  |  | 0 | 64481 | 64480
64554 |  | REC's Walton to North Athens 138 kV line reconductoring. |  | 6842 | 6867 | Planned |  | RYBRN |  |  | 2022-10-01 |  | 138 | 0 | 0 | 0 |  | Hopkins | Henderson | Tier 4 |  |  |  |  | 6842, 6867 | Y |  |  | 0 | 64555 | 64554
3505 | Cibolo Substation, T3 transformer addition | Add T3, 40 MVA 138-26.18 kV power transformer, CSW and low side |  | Cibolo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-10-14 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7608 | Y | N |  |  | 10887 | 3505
63491 | Schneeman Draw to Big Hill 2nd circuit | Add the 2nd circuit to CREZ Schneeman Draw to Big Hill 345 kV line |  | Schneeman Draw | Big Hill | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-10-15 |  | 345 | 59.1 | 0 | 0 |  | Crockett | Schleicher | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76003, 76005 | Y | N |  |  | 63492 | 63491
48288C | BOGGY (BOG) 138kV Substation (SHELL Substation Replacement) | Install new customer-owned BOGGY 138kV substation. Loop from Ckt.88 to create new Ckt.88 PAIR to BOGGY to ESBELT |  | BOGGY | PAIR/ESBELT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-10-18 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40530, 41210, 41350, 41370, 41460 | Y | N |  | Cost Included in 48288A | 57334 | 48288
66020 | New substation to connect Mustang Creek INR | New substation to connect Mustang Creek INR |  | Galow |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-10-29 |  | 138 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5521, 5523, 78104 | Y | N |  | 0 | 66021 | 66020
49572 | Goodlett to Quanah: Build a new portion of 69 kV line | Build new section of 69 kV line between Goodlett and Quanah |  | Goodlett | Quanah | Planned | 1022 - 1200 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2784 | 2022-10-31 |  | 69 | 6 | 0 | 0 |  | Hardeman |  | Tier 2 | 19RPG020 | 2019-11-01 | 2020-01-01 |  | 6052, 6051, 60446 | Y | N |  | 0 | 49573 | 49572
50952 | Whitepoint: Replace reactors | Replace the 10 ohm reactors with 19.08 ohm reactors at Whitepoint |  | Whitepoint |  | Planned | 1086 - 1259 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3806 TP2020034 | 2022-10-31 |  | 138 | 0 | 0 | 0 | -18.16,0 | San Patricio |  | Tier 4 |  |  |  |  | 8961, 80128, 80129 | Y | N |  | 0 | 65552 | 50952
59315 | BLUE (BLU) CNP-Owned Sub for Red-Tailed Hawk Solar (21INR0389) | New 345kV BLUE (BLU) substation for generator interconnection to Red-Tailed Hawk Solar. Loop Ckt.72 into substation to create new Ckt.72 Hillje to BLUE to Bailey |  | BLUE | Hillje/Bailey | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-10-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44060, 44040, 44200 | Y | N |  | 0 | 59316 | 59315
48814 | Albany Foundry to Fort Griffin: Rebuild 69 kV line | Rebuild 69 kV line from Albany Foundry to Fort Griffin, install box bay at Salt Prong POD, install capacitor banks at Albany Foundry |  | Albany Foundry | Fort Griffin | Planned | 1014 - 1192 | AEP TNC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 | 2775 | 2022-10-31 01:00 |  | 69 | 0 | 4.66 | 0 | 0,14.4 | Shackelford | Shackelford | Tier 4 |  |  |  |  | 6208, 6213, 60445, 6202, 6212, 60398, 6214 | Y | N |  | 0 | 48815 | 48814
49564 | Mantle: Construct New 345 kV Station | Mantle: Construct New 345 kV Station | Update Contact, Schedule | Bonilla | North Edinburg | Planned | 1035 - 1213 | AEP TCC | Joe Yeagler bcogan@aep.com 918-599-2857 | 3774 TP2018166 | 2022-10-31 20:00 |  | 345 | 0 | 0 | 0 |  | Cameron | Hidalgo | Tier 4 |  |  |  |  | 8059, 80598, 8383, 8573 | Y | N |  | 0 | 49565 | 49564
48288A | BOGGY (BOG) 138kV Substation (SHELL Substation Replacement) | Remove existing customer-owned SHELL (_SL) 138kV Substation |  | SHELL |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-11-03 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41450, 40070, 40530, 41460, 41210 | Y | N |  | 0 | 57332 | 48288
50954 | Whitepoint: Add Second Auto | Whitepoint: Add Second Auto |  | Whitepoint |  | Planned | 1085 - 1258 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3805 | 2022-11-23 |  | 345 | 0 | 0 | 500 |  | San Patricio |  | Tier 4 |  |  |  |  | 8956, 8961 | Y | N |  | 0 | 50955 | 50954
6749 | Rosata: Build 138kV Substation | Build new Rosata 138kV POD Switch on Coleto Creek to Kenedy 138kV Line | Update Schedule | Rosata |  | Planned | 898 - 1076 | AEP TCC | James Lutz bcogan@aep.com 918-599-2857 | 3682 | 2022-11-30 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8153, 88153, 7241, 8162, 8186 | Y | Y |  |  | 14542 | 6749
49556 | Ozona: Rebuild 69 kV station | Replace existing Ozona 69 kV station with a new 69 kV ring bus |  | Ozona |  | Planned | 1018 - 1196 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 2780 | 2022-11-30 |  | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6550, 6560 | Y | N |  | 0 | 65538 | 49556
55603 | Big Foot to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley |  | Big Foot | Pearsall | Planned | 1104 - 1282 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3821 | 2022-11-30 |  | 69 | 0 | 14.79 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8218, 8216 | Y |  |  | 0 | 65571 | 55603
57908 | North Edinburg:138 kV Station Work | Install two 138 kV series reactors | Update Project Title/Description, Contact, and Schedule | North Edinburg |  | Planned | 1112 - 1290 | AEP TCC | Rich Haley bcogan@aep.com 918-599-2857 | 3831 | 2022-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 88381, 88382, 8380, 8383, 8341 | Y | N |  | 0 | 57909 | 57908
59324 | Creosote: Build 138 kV Station | Build new 138 kV Station on the Pig Creek to Lotebush 138 kV line |  | Creosote |  | Planned | 1124 - 1302 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1869 | 2022-11-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 6657, 60377, 6673, 38376, 60392 | Y | N |  | 0 | 65589 | 59324
60491 | Rebuild Alamo Street-Airport with 1926 ACSS |  |  | Alamo Street (bus # 38330) | Airport (bus # 38340) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-11-30 |  | 138 | 0 | 3.01 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38340 | Y |  |  | 0 | 60492 | 60491
61394 | Portilla: 138 kV Station | Construct 4 breaker 138 kV ring bus expandable to a 6 breaker ring bus. The Portilla 138 kV Station will tie into the Lon Hill - Warburton 138 kV Line |  | Portilla |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | DP21X0008 | 2022-11-30 |  | 138 | 1.5 | 0 | 0 | 0,14.4 | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8924, 8027, 8920 | Y |  |  | 0 | 61395 | 61394
61398 | Whitepoint 138 kV Station: Upgrade Pelican Terminal | Whitepoint 138 kV Station: Upgrade Pelican Terminal | Update Schedule | Pelican | Whitepoint | Planned |  | AEP TCC | Brandon Cogan 918-599-2857 bcogan@aep.com | TP2020040 | 2022-11-30 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 | 19RPG0016 |  |  |  | 8961, 80259 | Y |  |  | 0 | 61399 | 61398
63904 | Pendulo: Build New 345 kV Station | Interconnect Inertia (Wind and BESS) to the Clear Crossing to Smoky Hill 345 kV Line | NEW | Pendulo |  | Planned | 1137 - 1315 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 1882 | 2022-11-30 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60507, 60509, 6104, 60514 | Y | N |  | 0 | 63905 | 63904
63956 | Clear Crossing: Install 345 kV terminal | Connect HODL Ranch II to the Clear Crossing 345 kV station | NEW | Clear Crossing | HODL Ranch II | Planned | 1139 - 1317 | ETT | Michael Glueck mlforcum@aep.com 918-599-2674 | 1884 | 2022-11-30 |  | 345 | 0 | 0 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  |  | 60017, 60515 | Y | N |  | 0 | 63957 | 63956
6934B | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0873 | 2022-12-01 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  |  | 5133 | Y |  |  |  | 14754 | 6934
6934A | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0873 | 2022-12-01 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  |  | 5133 | Y |  |  |  | 14753 | 6934
48248 | BrandToCollegeLineUpgrade | Brand to College Line Upgrade to Cumberland |  | Brand | College | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-12-01 |  | 138 | 0 | 4.16 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 827, 829 | Y |  |  | 0 | 48249 | 48248
60524 | Rebuild Angleton-Retrieve with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39560, 43170 | Y |  |  | 0 | 60525 | 60524
61264B | Marshall Ford to Trading Post Storm Hardening | Phase 1: Reconductor segment of T323 Marshall Ford to Paleface and T315 Marshall Ford to Trading Post that is double circuit using Galveston ACCC conductor. |  | Marshall Ford | Trading Post | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2022-12-01 |  | 138 | 0 | 3.6 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7477, 7356 | Y | N |  | 0 | 63792 | 61264
63433 | Rebuilds AEP Creosote-TNMP Coyanosa138 kV line as Dbl Ckt |  |  | AEP Creosote (bus # 60377) and TNMP TransPecos Tap (bus # 38376) | TNMP Coyanosa (bus # 38380) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0.87 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38376, 38380, 60377 | Y |  |  | 0 | 63434 | 63433
63898 | Palouse: Build New 138 kV Station | Interconnect Appaloosa Run Wind on the North McCamey to Santa Rita 138 kV Line |  | Palouse |  | Planned | 1134 - 1312 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 1879 | 2022-12-01 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | 60728, 60729, 60723, 60799, 141052, 141151, 141154, 141202, 141204, 141205, 141207, 141861, 141862, 141863, 141866, 161701, 161702, 161706, 161707, 170161, 170163, 182001, 182054 | Y | N |  | 0 | 63899 | 63898
63900 | Nebula: Build New 345 kV Station | Interconnect Andromeda Solar on the Dermott to Figaro 345 kV Line | NEW | Nebula |  | Planned | 1135 - 1313 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 1880 | 2022-12-01 |  | 345 | 0 | 0 | 0 |  | Scurry |  | Tier 4 |  |  |  |  | 60011, 60020, 11305, 60715 | Y | N |  | 0 | 63901 | 63900
65659 | Adds Fishhook Switch |  |  | Wink (bus # 37900) | Fishhook Switch (bus # 37180) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 26.132 | 0 |  | Winkler | Ward | Tier 4 |  |  |  |  | 38180, 38196, 37900, 38135, 38140, 38152, 38165, 38195 | Y |  |  | 0 | 65660 | 65659
65837 | New Cachena Substation |  |  | 5133 | 5323 | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2022-12-01 |  | 345 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 5068, 5133, 5323 | Y |  |  | 0 | 65838 | 65837
66111 | Upgrade Airport bus |  |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38340 | Y |  |  | 0 | 66112 | 66111
66113 | Add WalnutSpr Auto & 138kV Switchyard |  |  | Oncor Walnut Springs (Bus # 1646, 1647) | TNMP Walnut Springs (Bus # 37680, 37681) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0 | 208.8 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 1647, 37681, 1646, 37680 | Y |  |  | 0 | 66115 | 66113
57890 | Brightside Permanent Connection | Construct Charter Station |  | Beeville | Three Rivers | Planned | 1114 - 1292 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3833 | 2022-12-11 |  | 138 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8142, 8156, 8403 | Y |  |  | 0 | 57891 | 57890
5492 | Venus - Webb/Cedar Hill Sw. Sta. 345 kV DCKT Line | Upgrade existing Venus - Webb/Cedar Hill Sw. Sta. 345 kV Double Ckt Line |  | Ellis | Tarrant | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4230 | 2022-12-15 |  | 345 | 0 | 27 | 0 |  | Ellis | Tarrant | Tier 3 | 21RPG004 | 2021-02-22 | 2021-03-17 |  | 1904, 1906, 2420, 11901 | Y | N |  |  | 13230 | 5492
7115 | Quarry Field - Kyle Ranch 138 kV Line | Quarry Field - Kyle Ranch 138 kV Line |  | Quarry Field | Kyle Ranch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8384 | 2022-12-15 |  | 138 | 12 | 0 | 0 |  | Loving | Loving | Tier 4 |  |  |  |  | 11089, 11189 | Y |  |  |  | 14951 | 7115
52247 | Marrs - Handley 69 kV Line Conversion to 138 kV | Convert the existing Marrs-Handley 69 kV line to 138 kV operation |  | Marrs SW | Handley | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5222 | 2022-12-15 |  | 138 | 2.2 | 13 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1952, 1968, 2158, 2159, 2160, 2161, 11952, 1951, 1967, 1969, 11967 | Y |  |  | 0 | 52248 | 52247
56350B | Burnett - Bowie 69 kV Line | Upgrade Ringgold Magnolia Tap-Bowie 69 kV Line |  | Bowie | Ringgold Magnolia Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2022-12-15 |  | 69 | 0 | 21 | 0 |  | Montague | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 1540, 1545, 1547, 1548, 1550, 33770 | Y | N |  | 0 | 56862 | 56350
59263 | Weatherford Switch - Azle 138 kV Line | Upgrade existing 138 kV Line |  | Weatherford | Azle | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5172 | 2022-12-15 |  | 138 | 0 | 11.5 | 0 |  | Parker | Tarrant | Tier 4 |  |  |  |  | 1592, 2062, 15015 | Y |  |  | 0 | 59524 | 59263
59265 | Hurst - International Airport 138 kV Double-Circuit Line Section | Upgrade existing 138 kV Line |  | Hurst | International Airport | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5216 | 2022-12-15 |  | 138 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 2115, 2116, 2117, 2121, 2125, 2243, 2244 | Y |  |  | 0 | 59266 | 59265
59402 | Add Midland East Switch 345138 kV Autotransformer #2 | Add a new 345/138 kV autotransformer to existing switch |  | Midland East | Midland East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8258 | 2022-12-15 |  | 345 | 0 | 0 | 600 |  | Midland | Midland | Tier 3 | 21RPG003 | 2021-02-16 | 2021-03-12 |  | 1014, 11298, 1021, 1023 | Y |  |  | 0 | 59404 | 59402
59518 | upgrade the Desoto-Sterrett 138 kV Line | upgrade the existing Desoto-Sterrett 138 kV Line |  | Desoto | Sterrett | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4122 | 2022-12-15 |  | 138 | 0 | 8.3 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  |  | 217, 2317, 2424 | Y |  |  | 0 | 59519 | 59518
59552 | Rebuild Eskota - Sweetwater No.2 69 kV Line | Rebuild Eskota - Sweetwater No.2 69 kV Line |  | Eskota | Sweetwater No. 2 | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8570 | 2022-12-15 |  | 69 | 0 | 16.3 | 0 |  | Nolan | Nolan | Tier 4 |  |  |  |  | 1377, 1382, 1383, 1386, 1387, 11385, 1340, 1381, 1384, 1385, 11384 | Y |  |  | 0 | 59554 | 59552
62116 | Upgrade Brushy Creek - Taylor 138 kV Line | Upgrade Brushy Creek - Taylor 138 kV Line |  | Brushy Creek | Taylor | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6153 | 2022-12-15 |  | 138 | 0 | 11.4 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3541, 3690, 3658 | Y |  |  | 0 | 62117 | 62116
62143 | Rebuild Taylor 138 kV Switch | Rebuild Taylor 138 kV Switch and relocate 138/69 kV auto from Elgin to Taylor |  | Taylor | Taylor | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6143 | 2022-12-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3651, 3652, 3649, 3650, 3658 | Y |  |  | 0 | 62640 | 62143
62436 | Cedar Hill - Desoto Hampton Road 138 kV Line | Rebuild the existing 138 kV Line |  | Cedar Hill Switch | Desoto Hampton Road | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4175 | 2022-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 3058, 3059, 3060, 3066, 3065 | Y |  |  | 0 | 62437 | 62436
62438 | Waxahachie - Bardwell Lake - Italy 69 kV Line | Rebuild existing 69 kV Line |  | Bardwell Lake Switch | Italy | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4320 | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2295, 2336, 2337, 3523, 2335, 2338 | Y |  |  | 0 | 62439 | 62438
62440 | Ferris - Waxahachie OCF 69 kV Line | Rebuild existing 69 kV Line |  | Ferris Switch | Waxahachie OCF | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4323 | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 201, 2342, 2343 | Y |  |  | 0 | 62441 | 62440
62448 | Rebuild Marlin 69 kV Switch | Rebuild Marlin 69 kV Switch |  | Marlin | Marlin | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1752 | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3418, 3638, 13639 | Y |  |  | 0 | 62658 | 62448
62450 | Pin Oak 138 kV Switch (Formerly Big Brown Tap) | Pin Oak 138 kV Switch (Formerly Big Brown Tap) |  | Pin Oak | Pin Oak | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R2014 | 2022-12-15 |  | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3505, 3510, 196, 212, 3506 | Y |  |  | 0 | 62451 | 62450
62633 | Install 2nd distribution transformer at Rockdale Substation | Install 2nd distribution transformer at Rockdale Substation |  | Rockdale | Rockdale | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6140 | 2022-12-15 |  | 138 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3686, 3678, 3684 | Y |  |  | 0 | 62634 | 62633
62636 | Rebuild Waco West 138 kV Switch | Rebuild Waco West 138 kV Switch |  | Waco West | Waco West | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6141 | 2022-12-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3446, 3436, 3433, 3560, 3563, 3590, 3591, 3437, 13436 | Y |  |  | 0 | 62637 | 62636
62638 | Rebuild Trinidad 69 kV Switch | Rebuild Trinidad 69 kV Switch |  | Trinidad | Trinidad | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6142 | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  |  | 3216, 3126, 3128, 3269, 3479 | Y |  |  | 0 | 62639 | 62638
62641 | Establish Sabana138 kV Substation | Establish Sabana (Formerly known Proctor) 138 kV Substation |  | Proctor | Proctor | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6144 | 2022-12-15 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 1665, 1684, 1636, 1637, 1649 | Y |  |  | 0 | 62642 | 62641
62659 | Upgrade Temple - Holland 69 kV Line | Upgrade Temple - Holland 69 kV Line |  | Temple | Holland | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6151 | 2022-12-15 |  | 69 | 0 | 16.6 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3644, 3645, 3646, 13646 | Y |  |  | 0 | 62660 | 62659
62728 | Wink - Shifting Sands 69 kV Line Conversion to 138 kV | Convert the existing Wink - Shifting Sands 69 kV Line to 138 kV |  | Wink | Shifting Sands | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8581 | 2022-12-15 |  | 69 | 0 | 13 | 0 |  | Winkler | Winkler | Tier 4 |  |  |  |  | 1244, 1245, 1246, 1249, 11392, 18539, 1074, 1075, 6583, 6665, 7046, 60708, 60710, 11391, 60618, 60621, 76003, 76583, 76668 | Y |  |  | 0 | 62730 | 62728
66116 | Add Buckeye Switchyard (22INR0359 Dileo POI) |  |  | Lake Whitney (bus # 37420) | Olsen (bus # 37470) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 37450, 37420, 37470 | Y |  |  | 0 | 66117 | 66116
66194 | Holiday - Navy Kickapoo 69 kV Line | Relocate current substations on Holliday - Navy Kickapoo 69 kV Line |  | Holliday | Navy Kickapoo | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4022 | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Archer | Archer | Tier 4 |  |  |  |  | 1525, 1526, 1528, 11525, 11528, 1527, 1424, 1431, 1473, 11527 | Y |  |  | 0 | 66195 | 66194
66621 | Sandhills - Sandhills Tap 138 kV Line Rebuild | Add Sandhills - Sandhills Tap 138 kV Line Rebuild |  | Sandhills | Sandhills Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8612 | 2022-12-15 |  | 138 | 0 | 23 | 0 | 0,55.2 | Ector | Crane | Tier 4 |  |  |  |  | 10006, 10007, 1103, 1104, 11111, 11117 | Y |  |  | 0 | 66681 | 66621
57925 | Midland County Northwest to Texaco Mabee Tap 138 kV Double-Circuit Line Section | Add Midland County NW - Texaco Mabee Tap 138 kV Double-Circuit Line Section Rebuild |  | Midland County Northwest | Texaco Mabee Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8558 | 2022-12-15 01:00 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 | 2021-03-12 |  | 11299, 11300, 11301, 1178, 1179, 1182, 1183 | Y |  |  | 0 | 60059 | 57925
50446 | Santa Clara Substation Addition | Add a new load serving substation 10 miles west of City of Seguin, of IH-10, w/ twin 40 MVA PWTs. |  | Santa Clara Substation | Santa Clara Substation | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7891 | Y | N |  | 0 | 50447 | 50446
52322 | Establish Courtney Creek Switch | Establish Courtney Creek 138/69 kV Switch |  | Courtney Creek Switch | Athey (AEP) | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8479 | 2022-12-16 |  | 138 |  |  | 82 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 11242, 11258, 1240, 1242, 60792 | Y |  |  | 0 | 56445 | 52322
64089 | Peregrine Solar Interconnection | Connect the Peregrine Solar to the Coleto Creek to Grissom 345 kV line | NEW | Coleto Creek | Grissom | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2022-12-19 |  | 345 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8673, 88673, 8164, 8624 | Y |  |  | 0 | 64090 | 64089
6719 | Twelvemile Substation Addition | Construct a new substation named Twelvemile off the Bakersfield to Schneeman Draw transmission line to support a generation interconnection request (16INR0104) |  | Bakersfield | Schneeman Draw | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018769 | 2022-12-22 |  | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  |  | 76008, 7053, 76015 | Y | N |  | 0 | 58408 | 6719
51736 | Cibolo to McQueeney Transmission Line | Install 10.62 miles of 1192 Bunting to existing transmission structures, circuit to help with load flows per the TPA and will be source for Santa Clara Substation. |  | Cibolo | McQueency | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-23 |  | 138 | 10.62 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7608, 7606 | Y | N |  | 0 | 51737 | 51736
51841 | Cibolo-McQueeney Tap to Santa Clara Transmission Line Addtition | Build 5 onmiles of new double circuit 138kV t-line loop, 1192 ACSR Bunting, from H-pole structure to Santa Clara Substation |  | H-pole ( Structure/Tap) | Santa Clara | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-23 |  | 69 | 10 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7890, 7892, 7606, 7608, 7891 | Y | N |  | 0 | 57331 | 51841
55873 | Upgrade Moore to Hondo Creek 138 kV line | Replace the 336 ACSR with 1020 ACCC conductor while keeping the existing structures that still meet our standards. |  | Moore | Hondo Creek | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-12-24 |  | 138 | 0 | 13.5 | 0 |  | Medina | Frio | Tier 2 | 19RPG021 | 2019-11-20 | 2020-05-21 |  | 5819, 5827 | Y | N | Field engineering is still occurring due to short timeline for this upgrade. Details may change. | Current plan is to upgrade the line using mostly existing structures. Detailed field engineering is underway and could change the plan. | 55874 | 55873
47541 | Crane Circuit Breaker Addition | Provide transmission service to American Electric Power at Crane Substation. Adding one (1) breaker and associated equipment needed to connect the AEP-owned Crane to Kinnison 138-kV transmission line. |  | Crane Substation | Crane Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-12-30 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 76615 | Y | N |  | 0 | 47542 | 47541
52183 | EXTER 69kV Substation Removal | Remove EXTER 69kV Substation from Ckt.53B |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-30 |  | 138 | 0 | 0 | 0 |  | Galveston | Harris | Tier 4 |  |  |  |  | 42600, 42080, 43510, 44440 | Y | N |  | Cost included in MOD 52181 - ENCO new customer sub | 52184 | 52183
57645 | Hillje 345kV Danish Fields Solar (21INR0069) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Danish Fields Solar |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-30 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 57646 | 57645
50896 | Garnet: Build new 138 kV station | Interconnect Norton solar farm on the Ballinger to Oak Creek 138 kV line | Update Cost | Garnet |  | Planned | 1049 - 1222 | AEP TNC | Bryan Oyster mlforcum@aep.com 918-599-2674 | 2824 | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Runnels |  | Tier 4 |  |  |  |  | 60451, 6325, 6340 | Y | N |  | 0 | 50897 | 50896
56003A | Mont Belvieu Reliability Project | Expand Jordan and Mont Belvieu with new line positions |  | Jordan | Winfre | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40500, 40764, 40857, 40740, 40855 | Y | N |  | 0 | 56075 | 56003
57521A | Stone Lake New Sub Ckt66 | Install Stone Lake Distribution Substation AP2022 to create new Ckt..66 Hockley to Stone Lake to Tomball. |  | Stone Lake | Hockley/Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45886, 46511 | Y | N |  | 0 | 57530 | 57521
59095 | Athey: Build 138 kV Temporary Hard Tap | Build new 138 kV temporary tap on the Ft Stockton to Rio Pecos 138 kV line | Update Schedule | Athey |  | Planned | 1123 - 1301 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 1868 | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60792, 60718, 60798 | Y | N |  | 0 | 59096 | 59095
62041 | Twinwood 138kV Distribution Substation | Install new Twinwood (TWN) 138kV Distribution Substation. Loop from existing Ckt.25E to create new Ckt.25E Foster to Twinwood to Peters |  | Twinwood | Foster/ Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Austin | Tier 4 |  |  |  |  | 44860, 44256, 46220 | Y | N |  | 0 | 62042 | 62041
66048 |  |  |  | 6821, 6904, |  | Planned |  | RYBRN |  |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6904 | Y |  |  | 0 | 66052 | 66048
56003B | Mont Belvieu Reliability Project | Remove existing Jordan TR1 tap from Ckt.86I Jordan to Cities. Reconnect at new Ckt.52A Jordan to Winfre |  | Jordan | Cities | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40340, 40740, 40855, 40857 | Y | N |  | Cost included in main entry | 56076 | 56003
57549A | Garden Villas 138kV Load Conversion | Reposition existing Garden Villas dual-voltage transformers TR1/TR2. Reposition one of the transformers with Ckt.06G Garden Villas to Drouet and rename transformer as TR4. |  | Garden Villas | Drouet | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42684, 42680, 42690, 42550 | Y | N |  | 0 | 61867 | 57549
56003C | Mont Belvieu Reliability Project | Reconfigure existing 86B/86H/86K to create new Ckt.52B Winfre to Eagle with minimum 360/440 MVA |  | Winfre | Eagle | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40220, 40300, 40500, 40764 | Y | N |  | Cost included in main entry | 56077 | 56003
57549B | Garden Villas 138kV Load Conversion | Reposition existing Garden Villas dual-voltage transformers TR1/TR2. Reposition one of the transformers with Ckt.07A Garden Villas to Chocolate Bayou tap and rename transformer as TR3. |  | Garden Villas | Chocolate Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42681, 42683, 42690, 42042, 42680 | Y | N |  | Cost included in main project | 61868 | 57549
56003D | Mont Belvieu Reliability Project | Expand Jordan and Mont Belvieu with new line positions |  | Eagle | Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40500, 41111 | Y | N |  | Cost included in main entry | 56078 | 56003
56003E | Mont Belvieu Reliability Project | Expand Jordan and Mont Belvieu with new line positions |  | Dalton | BRINE/Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40220, 40775, 41111, 40740, 41113 | Y | N |  | Cost included in main entry | 56079 | 56003
56003F | Mont Belvieu Reliability Project | Reconfigure existing 86B/86H/86K to create new Ckt.86B Chevron to Langston with minimum 440/525 MVA |  | Chevron | Langston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40300, 40775 | Y | N |  | Cost included in main entry | 56080 | 56003
56003G | Mont Belvieu Reliability Project | Upgrade Ckt.84D Cedar Bayou Plant to Cedar Bayou Tap to HOPSON with minimum 682MVA Emergency Rating |  | Cedar Bayou Plant | Cedar Bayou/HOPSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40012, 40015, 41690 | Y | N |  | Cost included in main entry | 56081 | 56003
56003H | Mont Belvieu Reliability Project | Upgrade Ckt.86A Cedar Bayou Plant to Chevron with minimum 669MVA Emergency Rating |  | Cedar Bayou Plant | Chevron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Harris | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40015, 40300 | Y | N |  | Cost included in main entry | 56082 | 56003
6875 | Support 69kV to 138kV West Loop Conversion Projects | Upgraded line Apollo to Jupiter to support 69kV to 138kV West Loop Conversion Projects |  | Apollo | Jupiter | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2023-01-01 |  | 138 | 0 | 3.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 800, 806, 802, 815 | Y | N |  |  | 14684 | 6875
44854 | Lipton: Build 138 kV Box Bay | New Lipton 138 kV Station, replaces Lipton Hard Tap | Update Contact and Schedule | Lipton |  | Planned | 973 - 1151 | AEP TCC | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3731 | 2023-01-14 |  | 138 | 0 | 0 | 0 |  | Zavala |  | Tier 4 |  |  |  |  | 8285, 88285, 8236, 8283 | Y | N |  | 0 | 44855 | 44854
63493 | Noelke to Schneeman Draw 2nd circuit | Add the 2nd circuit to the CREZ Noelke to Schneeman Draw 345 kV line |  | Noelke | Schneeman Draw | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-01-15 |  | 345 | 15.8 | 0 | 0 |  | Crockett | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 7053, 76005 | Y | N |  |  | 63494 | 63493
45155 | Ollin: Build 138 kV station | Construct new Ollin 138 kV station |  | Ollin |  | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2752 | 2023-01-30 01:00 |  | 138 | 0.1 | 0 | 0 |  | Crane |  | Tier 4 | 19RPG013 |  |  |  | 6600, 6605, 6606, 6668, 6669, 60428, 60429, 60432, 60441, 6604, 6610, 6613, 6607, 6611, 60431, 76615 | Y | N |  | 0 | 45156 | 45155
45174 | Ollin to LCRA Crane: Partial build | Build new Ollin 138 kV station; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage | Schedule Update | Ollin | LCRA Crane | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2767 | 2023-01-30 01:00 |  | 138 | 0.52 | 0 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6600, 6605, 6606, 6669, 60428, 60429, 60431, 60432, 60441, 6610, 6613, 6668, 76615 | Y | N |  | 0 | 65527 | 45174
45421 | McElroy to Sage: Rebuild 69 kV line | Build new Ollin 138 kV station with a 138/69 kV auto; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage |  | McElroy | Sage | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2768 | 2023-01-30 01:00 |  | 69 | 0 | 1.99 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6604, 6607 | Y | N |  | 0 | 65529 | 45421
50872 | Structure 25/7 - Medio Creek: Line Rebuild | Lon Hill - STEC Warburton: Line Rebuild |  | Haisley | Medio Creek | Planned | 1055 - 1228 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3784 | 2023-01-31 |  | 138 | 0 | 14.9 | 0 |  | San Patricio | Refugio | Tier 3 | 19RPG014 |  |  |  | 8912, 8920 | Y | N |  | 0 | 65546 | 50872
55464 | Adds new Morrow sub near Pearsall | Adds new Morrow substation and short line from Morrow to the Pearsall substation |  | Pearsall | Morrow | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-01-31 |  | 138 | 0.91 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5896, 5895 | Y | N |  | 0 | 55465 | 55464
64063 | BRP Antlia BESS Interconnection | Connect BRP Antlia BESS to the Maxwell 138 kV station |  |  |  | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-01-31 |  | 138 | 0 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  |  | 88999, 8998 | Y |  | TP2021260 | 0 | 64064 | 64063
66053 | 138 kV GULFTIE Substation to connect TexGulf generator |  |  | Tex Gulf | South Lane City/San Bernard | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-01-31 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 43340, 43341, 43010, 43120, 110262 | Y | N |  | 0 | 66054 | 66053
59959 | CPSE_New_Old_Hickory_Switchyard | Build a new Old Hickory 345 switchyard to connect Old Hickory Solar plant. |  | 5133 | 5915 | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0303; S-0940 | 2023-02-01 20:00 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5323, 5133, 5915 | Y |  |  | 0 | 59960 | 59959
45397 | Lion: 138 kV Station & Transmission Line | Lion: 138 kV Station with new line to Stewart Road |  | Lion | Stewart Road | Planned | 885 - 1063 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3672 TP2018218 | 2023-02-23 |  | 138 | 2.71 | 0 | 40 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8969, 8758, 8951 | Y | N |  | 0 | 65528 | 45397
4146 | Hillje 345kV Substation Expansion for Juanita Hill Solar - (21INR0480) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Juanita Hill Solar |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-02-28 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 11666 | 4146
63924 | Quasar: Build New 345 kV Station | Interconnect Brass Fork Solar to the Clear Crossing to Coulomb 345 kV Line | NEW | Quasar |  | Planned | 1138 - 1316 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 1883 | 2023-02-28 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60712, 60713, 60514, 60703 | Y | N |  | 0 | 63925 | 63924
66292 | Salvare: Build 345 kV station | Build new 345 kV Station on the Jim Treece to Tesla 345 kV line and 345 kV line from Salvare to Iris | NEW | Salvare | Iris Data | Planned |  | ETT | Glen Reed gareed@aep.com 918-599-2664 |  | 2023-02-28 |  | 345 | 0.01 | 0 | 0 |  | Childress | Childress | Tier 4 |  |  |  |  | 60510, 60511, 60504, 61001 | Y | N |  | 0 | 66293 | 66292
57343 | Rosita Creek Substation 138-kV T2 Power Transformer Addition | Add second 138/13.09-kV power transformer bay with new 138-kV transmission switch and circuit switcher interconnected at LCRA Switch# 12669. New power transformer capacity will be 15/20/25 MVA. | Recent projected load increases beyond ALDR. Justification is to provide on-site backup power source for new and existing critical medical center, governmental and educational facility loads. Power transformer lead-time increases. | Pueblo | Escondido | Planned |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2023-03-01 |  | 138 | 0 | 0 | 0 |  | Maverick | Maverick | Tier 4 | [5 empty] | Y | N |  | 0 | 57344 | 57343
61865 | Muldoon Substation Addition | Provide transmission service to a generator. LCRA TSC will construct a new substation, Muldoon Substation, on T133 between LCRA TSC Flatonia and Plum Substations and more specifically between str #192 and str #197. The substation will be a three breaker ring bus configuration and will provide a 138-kV line termination for a 240 MW solar generation facility. |  | Muldoon Substation | Muldoon Substation | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-03-01 |  | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7279, 7248, 7274 | Y | N |  | 0 | 61866 | 61865
63495 | Cedar Canyon to Noelke 2nd circuit | Add the 2nd circuit to CREZ Cedar Canyon to Noelke 345 kV line |  | Cedar Canyon | Noelke | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-03-15 |  | 345 | 16 | 0 | 0 |  | Crockett | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76015, 7053 | Y | N |  |  | 63496 | 63495
50870 | Coleto Creek - Rosata: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Coleto Creek | Rosata | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3778 | 2023-03-16 01:00 |  | 138 | 0 | 15.3 | 0 |  | Goliad | Goliad | Tier 3 | 20RPG014 |  |  |  | 8162, 8153 | Y | N |  | 0 | 50871 | 50870
66463 | GPLTMPA_66463_AddsLookoutSTATCOM | Adding of Lookout STATCOM for serving of local voltage issues |  | Lookout | Lookout | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2023-03-20 |  | 138 | 0 | 0 | 120 | -120120 | Dallas | Dallas | Tier 4 |  |  |  |  | 846, 828 | Y |  |  | 0 | 66464 | 66463
61264A | Marshall Ford to Trading Post Storm Hardening | Phase 2: Rebuild single circuit section of Marshall Ford to Trading Post (T315) and reconductor with bundled 795 ACSR Conductor, 440 MVA; Reconductor segment of T323 Marshall Ford to Paleface that is double circuited with T315 using Cardinal ACCC conductor. |  | Marshall Ford | Trading Post | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2023-03-22 |  | 138 | 0 | 4.1 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7356, 7505 | Y | N |  | 0 | 61265 | 61264
66011A | CNP ARCHER POI for BROTMAN Power | CNP ARCHER POI for BROTMAN Power |  | ARCHER | Rosharon/MANVEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-29 12:00 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44430, 44600 | Y | N |  | 0 | 66012 | 66011
6373 | Hamilton Road to Picacho ckt #2 | Rebuild Hamilton Road to Picacho 138 kV line ckt #2 |  | Hamilton Road | Picacho | Planned | 870-1051 | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | 3660 | 2023-03-30 |  | 138 | 0 | 8.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8186, 8255, 8690, 8688, 8684 | Y | N |  | 0 | 65505 | 6373
57731B | Hornsby Substation Addition | Construct a new 345-kV substation between Clear Springs to Gilliland Creek 345-kV transmission line to provide transmission service to a load-serving substation. Restore 138-kV transmission line from Decker to Sand Hill by removing temporary substation/arrangements made in first phase to serve load. |  | Clear Springs | Gilleland Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-03-30 |  | 345 | 0 | 0 | 960 |  | Travis | Travis | Tier 4 |  |  |  |  | 7047, 7916, 7050, 9187, 7340, 9216 | Y | N |  | 0 | 57740 | 57731
66011B | CNP ARCHER POI for BROTMAN Power | Upgrade Ckt.26 Rosharon to ARCHER to increase thermal limits. |  | ARCHER | Rosharon/MANVEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-30 12:00 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44430, 44600 | Y | N |  | 0 | 66015 | 66011
66011C | CNP ARCHER POI for BROTMAN Power | Upgrade Ckt 26 Angleton to WINMIL to increase thermal limits |  | Angleton | WINMIL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-30 12:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 44531 | Y | N |  | 0 | 66016 | 66011
51005 | Rocksprings to Friess Ranch: Rebuild 69 kV line | Rebuild Rocksprings to Sonora 69 kV line |  | Rocksprings | Friess Ranch | Planned | 1044 - 1217 | AEP TCC | Dave Baker mlforcum@aep.com 918-599-2674 | 2792 | 2023-03-31 |  | 69 | 0 | 22.6 | 0 |  | Edwards | Sutton | Tier 3 | 19RPG018 |  |  |  | 8238, 60210 | Y | N |  | 0 | 51006 | 51005
63964 | Bronco: Build new 69 kV Terminal | Interconnect House Mountain BESS to the Bronco 69 kV Station | Update Contact | Bronco |  | Planned | 1140 - 1318 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1885 | 2023-03-31 |  | 69 | 0 | 0 | 0 |  | Brewster |  | Tier 4 |  |  |  |  | 60018, 6674 | Y | N |  | 0 | 63965 | 63964
45015 | Barnhart to Cassava: Rebuild 69 kV line | Rebuild the Barnhart to Cassava 69 kV line |  | Barnhart | Cassava | Planned | 942 - 1120 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2756 | 2023-03-31 01:00 |  | 69 | 0 | 6.021 | 0 |  | Irion | Irion | Tier 4 |  |  |  |  | 6532, 6530, 6537, 60359 | Y | N |  | 0 | 65525 | 45015
51001 | Friess Ranch to Sonora: Rebuild 69 kV line | Rebuild Rocksprings to Sonora 69 kV line | Contact Update | Friess Ranch | Sonora | Planned | 1044 - 1217 | AEP TNC | Dave Baker mlforcum@aep.com 918-599-2674 | 2791 | 2023-03-31 12:00 |  | 69 | 0 | 24.3 | 0 |  | Sutton | Sutton | Tier 3 | 19RPG018 |  |  |  | 8238, 8239, 60438, 6513, 60210, 6570 | Y | N |  | 0 | 65554 | 51001
57169 | Rebuild Redgate to N Edinburg 138 kV | Rebuild Redgate to N Edinburg 138kV and opens Redgate tap |  | Redgate | Faysville Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-04-01 |  | 138 | 0 | 3.45 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8380, 88380, 5779, 5784 | Y | N |  | 0 | 63733 | 57169
66124 | Cut the El Campo to Lane City 138 kV line into the new Arroz 138 kV station. Construct a dead end structure and a single 138 kV span to the Crawfish point of interconnection. | Cut the El Campo to Lane City 138 kV line into the new Arroz 138 kV station. Construct a dead end structure and a single 138 kV span to the Crawfish point of interconnection. |  |  |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021286 | 2023-04-17 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8679, 8102, 8104 | Y |  |  | 0 | 66125 | 66124
55421 | Ballinger to Concho: Rebuild 69 kV line | Rebuild 69 kV line from Ballinger to Concho, install POD box bay for Rowena, install CB at Miles, install POP switch for Harriett REA | Update Cost | Ballinger | Concho | Planned | 1088 - 1271 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1861 | 2023-04-22 |  | 69 | 0 | 20.45 | 0 |  | Runnels | Tom Green | Tier 3 | 20RPG004 | 2020-04-08 | 2020-04-30 | 2020-05-08 | 6409, 6338, 6410, 6412, 6411, 6413, 6450 | Y | N |  | 0 | 55422 | 55421
61262A | Hunter to McCarty Lane Storm Hardening | Rebuild single-circuit section of Hunter to McCarty Lane 138 kV with single, circuit bundled 795 ACSR Conductor, 440 MVA. |  | McCarty Lane | Hunter | Planned |  | PEC/LCRATSC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2023-04-22 |  | 138 | 0 | 1.57 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7491 | Y | N |  | 0 | 61263 | 61262
63635 | Tribute: Build 138 kV Station | Build new 138 kV Station on the San Angelo Power to Red Creek 138 kV line | NEW | Tribute |  | Planned | 1132 - 1310 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1877 | 2023-04-28 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6442, 6473, 60008 | Y | N |  | 0 | 63636 | 63635
50843 | Heron: Build 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Schedule Update | Heron |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2796 | 2023-04-30 |  | 138 | 0 | 0 | 90 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60447, 60448, 6610, 6611, 6614 | Y | N |  | 0 | 50844 | 50843
50845 | Kinnison: Expand 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Update RPG Sumbittal Date and RPG Acceptance Date | Kinnison |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2797 | 2023-04-30 |  | 138 | 0 | 0 | 130 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60431, 60432 | Y | N |  | 0 | 65545 | 50845
50847 | Sage: Expand 69 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Update RPG Sumbittal Date and RPG Acceptance Date | Sage |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2799 | 2023-04-30 |  | 69 | 0 | 0 | 0 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-06-21 |  | 6604 | Y | N |  | 0 | 50848 | 50847
51010 | Heron to Ollin: Rebuild and convert to 138 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Schedule Update | Heron | Ollin | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2798 | 2023-04-30 |  | 138 | 0 | 2 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60448, 60441 | Y | N |  | 0 | 51011 | 51010
51012 | Kinnison to Sage: Rebuild 69 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Schedule Update | Kinnison | Sage | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2823 | 2023-04-30 |  | 69 | 0 | 0.25 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-17 |  | 60431, 6604 | Y | N |  | 0 | 65555 | 51012
65987 | Install Gibbs to Jackalope Solar branch | Install Gibbs to Jackalope Solar branch |  |  |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021288 | 2023-04-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 88173, 8173 | Y |  |  | 0 | 65988 | 65987
66192 | Abilene Northwest: Interconnect Lancium | Interconnect Lancium to the Abilene Northwest 138 kV station | NEW | Abilene Northwest | Lancium | Planned |  | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 |  | 2023-04-30 |  | 138 | 0.2 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6476, 6228 | Y | N |  | 0 | 66193 | 66192
55622 | Dilley to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley |  | Dilley | Pearsal | Planned | 1104 - 1282 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3822 | 2023-05-01 |  | 69 | 0 | 17.7 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8216, 8208 | Y |  |  | 0 | 66650 | 55622
64069 | Charger Solar Interconnection | Connect the Charger Interconnection to the Angstrom to STP 345 kV line |  | Angstrom | STP | Conceptual |  | AEP TCC | Michael Glueck bcogan@aep.com 918 599 2857 |  | 2023-05-01 |  | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 8676, 8678, 5915, 8249 | Y |  |  | 0 | 64070 | 64069
65725 | Rowe: Construct New Distribution Station |  | Schedule Update | North McAllen | West McAllen | Planned | 1030 - 1208 | AEP | Alison Scribailo bcogan@aep.com 918-599-2857 | 3769 | 2023-05-01 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8041, 8367, 8631 | Y | N |  | 0 | 65726 | 65725
5496 | Forney Switch 345 kV Terminal Equipment | Upgrade the terminal equipment at Forney 345 kV Switch |  | Royse |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3022 | 2023-05-15 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 4 |  |  |  |  | 2437, 2478 | Y |  |  | 0 | 62442 | 5496
6931 | New Tres Lagos Substation | Adds new station and short line from W Edinburg-Alton line |  | West Edinburg | Alton | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-05-15 |  | 138 | 1.8 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5770, 5771, 5772 | Y | N |  |  | 14750 | 6931
51740 | Buttercup Bus Upgrade | Upgrade the Buttercup bus from operate/transfer to double-bus double-breaker |  | Buttercup |  | Planned |  | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7531 | Y | N |  | 0 | 51750 | 51740
53958 | Fairland - Lago Vista Transmission Line Upgrade | Increase the reliability of transmission facilities on the T414 Fairland - Lago Vista 21-mile 138-kV transmission line by replacing the existing Condor conductor with Drake conductor. |  | Fairland | Lago Vista | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Burnet | Travis | Tier 4 |  |  |  |  | 7352, 7518 | Y | N |  | 0 | 53959 | 53958
53968 | Fayetteville - Salem Transmission Line Upgrade | Increase the reliability of transmission facilities on the T177 Fayetteville - Salem 138-kV and T211 FPP Yard #1 - Salem 345-kV 19.3-mile double-circuit transmission line by replacing the existing Condor conductor from Fayetteville Substation to Salem Substation. |  | Fayetteville | Salem | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 345 | 0 | 0 | 0 |  | Fayette | Washington | Tier 4 |  |  |  |  | 7056, 7286, 7058, 7289 | Y | N |  | 0 | 53969 | 53968
54080 | Lockhart - Lulig Transmission Line Overhaul | LCRA TSC will perform an overhaul of T184 (from Lockhart structure #301 to Luling) with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T184 will be 795 ACSR Drake. Note: Condor conductor replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7216, 7224 | Y | N |  | 0 | 54081 | 54080
54082 | Lockhart - Red Rock Transmission Line Overhaul | LCRA TSC will perform an overhaul of T578 (from Lockhart structure #301 to Red Rock) with replacement structures that are capable of operating at 138-kV and supporting a single 959 ACSR Suwannee conductor. The replacement conductor on T578 will be 959 ACSR Suwannee. This overhaul will include the installation of a 72-count optical ground wire (OPGW). Note: Condor conductor, new OPGW and any structure replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Red Rock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Bastrop | Tier 4 |  |  |  |  | 7216, 7560 | Y | N |  | 0 | 54083 | 54082
54103 | Hilltop - Strahan Transmission Line Upgrade | Increase the reliability of transmission facilities on the T445: Hilltop ¿ Strahan 1.25-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | Hilltop | Strahan | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7190, 7193 | Y | N |  | 0 | 54104 | 54103
59415 | Crane East 138 kV Capacitors | Add Crane East 138 kV Capacitors |  | Crane East | Crane East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8577 | 2023-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Upton | Upton | Tier 4 |  |  |  |  | 1214 | Y |  |  | 0 | 59537 | 59415
59745 | Royse Switch - Oates (GP&L) 138 kV Line | Upgrade existing 138 kV Line |  | Royse | Oates | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4236 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Rockwall | Dallas | Tier 4 |  |  |  |  | 831, 2472, 2733, 2735, 2736, 2739, 12703, 12735 | Y |  |  | 0 | 59746 | 59745
61440 | Harper Road - Jack Furman Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 4.6-mile Harper Road ¿ Jack Furman (T368) transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Harper Road | Jack Furman | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7140, 7141 | Y | N |  | 0 | 61441 | 61440
61453 | Ingram - Jack Furman Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 3.3-mile Ingram ¿ Jack Furman (T521) transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Ingram | Jack Furman | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7142, 7141 | Y | N |  | 0 | 61454 | 61453
61455 | Hunt - Ingram Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 6.4-mile Hunt ¿ Ingram (T487) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Hunt | Ingram | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7144, 7142 | Y | N |  | 0 | 61456 | 61455
61463 | Marshall Ford - McNeil Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 14.2-mile Marshall Ford ¿ McNeil (T197) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Marshall Ford | McNeil | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7356, 7334 | Y | N |  | 0 | 61464 | 61463
61465 | Starcke - Wirtz Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 6.7-mile Starcke - Wirtz (T654) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Starcke | Wirtz | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  |  | 7351, 7104 | Y | N |  | 0 | 61466 | 61465
61516 | Blissard - East Stiles 138 kV Line Section | Rebuild the Blissard - East Stiles 138 kV Line Section |  | Blissard | East Stiles | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8565 | 2023-05-15 |  | 138 | 0 | 13.1 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 11353, 23869 | Y |  |  | 0 | 61518 | 61516
61591 | Sandy Creek Autotransformer Upgrade | Increase the reliability of substation equipment at Sandy Creek Substation through the replacement of the Sandy Creek 138/69-kV AT1 autotransformer with a new 70 MVA unit. Increase the capacity of T400 Sandy Creek - Sunrise Beach 69-kV transmission circuit by upgrading limiting element jumper at Sunrise Beach Substation. |  | Sandy Creek | Sunrise Beach | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7121, 7400, 7127 | Y | N |  | 0 | 61592 | 61591
61593 | EC MORNHINWEG Substation Upgrade | NBU is adding a second power transformer at EC Mornhinweg and reconfiguring the substation to a ring bus arrangement. LCRA TSC will complete this project to support the NBU substation reconfiguration. |  | EC Mornhinweg | EC Mornhinweg | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7463 | Y | N |  |  | 61594 | 61593
61849 | Clear Springs AT2 Autotransformer Upgrade | Increase the reliability of substation equipment at Clear Springs Substation through the replacement of the Clear Springs AT2 345/138-kV autotransformer. |  | Clear Springs 138 | Clear Springs 345 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7050, 7680, 77680 | Y | N |  | 0 | 61850 | 61849
61851 | Marion AT2 Autotransformer Upgrade | Increase the reliability of substation equipment at Marion Substation through the replacement of the Marion AT2 345/138-kV autotransformer and installation of three 345-kV shunt reactors. |  | Marion 345 | Marion 138 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7044, 7178, 7822 | Y | N |  | 0 | 61852 | 61851
61853 | LCRATSC Lampasas Substation Upgrade | This project will improve the reliability of Lampasas Substation by replacing obsolete and aged equipment and by converting the substation from single-bus-single-breaker design to double-bus-double-breaker design. Lampasas Substation is an important hub for the transmission system in Burnet, Lampasas, San Saba, and Mills counties, and this project will improve transmission system reliability in those areas. |  | Lampasas | Lampasas | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Lampasas | Lampasas | Tier 4 | [5 empty] | Y | N |  | 0 | 61854 | 61853
62327 | Upgrade Fairfield West - Big Brown Tap 138 kV Line | Upgrade Fairfield West - Big Brown Tap 138 kV Line |  | Fairfield West | Big Brown Tap Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6138 | 2023-05-15 |  | 138 | 0 | 8 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 196, 3503, 3504, 3510 | Y |  |  | 0 | 62328 | 62327
62349 | Rebuild Fairfield West 138 kV Switch | Rebuild Fairfield West 138 kV Switch |  | Fairfield West | Fairfield West | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6136 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3503, 3504 | Y |  |  | 0 | 62350 | 62349
63929 | Buntin Drive 69 kV Substation Conversion To 138 kV | Convert Buntin Drive 69 kV Substation To 138 kV |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4064 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2984, 2486, 2494, 2951 | Y |  |  | 0 | 63930 | 63929
64310 | Cumby-Cumby Tap Line Conversion | Cumby - Cumby Tap Radial Line 69 to 138 kV Conversion. Project requires coordination with RCEC and TNMP. |  | Cumby Tap | Cumby Substation | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R944 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1812, 1813, 1815, 6861 | Y | N |  | 0 | 66059 | 64310
64382 | Bowman Auto 1 Upgrade | Upgrade existing Bowman Auto #1 300 MVA to 600 MVA. |  | Bowman | Bowman | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4021 | 2023-05-15 |  | 345 | 0 | 0 | 600 |  | Archer | Archer | Tier 3 |  |  |  |  | 1422, 1423, 29048 | Y | N |  | 0 | 64383 | 64382
66006 | Sherry 138 KV Switch Terminal Equipment |  |  | Sherry |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5101 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 1919, 2257 | Y |  |  | 0 | 66007 | 66006
66175 | Liggett 138 kV Terminal Equipment | Upgrade the terminal equipment at Liggett 138 kV Switch |  | Liggett |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4094 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 1922, 1924, 2053, 2055 | Y |  |  | 0 | 66176 | 66175
66178 | Centerville Switch - Centerville Road - Lake Hubbard Switch 138 kV Double-Circuit Line | Upgrade the existing 138 kV DCKT Line |  | Lake Hubbard | Centerville | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4127 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2439, 2450, 2917, 2918, 2401, 2402 | Y |  |  | 0 | 66179 | 66178
66186 | Carrollton Northwest - Carrollton East 138 kV Line | Terminate the existing Northlake - Carrollton East 138 kV Line at Carrollton Northwest |  | Carrollton East |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4205 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2362, 2363, 2385, 2578 | Y |  |  | 0 | 66187 | 66186
66188 | Cedar Crest - Dealey - West Levee 138 kV Line | Upgrade the existing 138 kV Line |  | Ceadr Crest | West Levee | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4212 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2493, 2842, 2400 | Y |  |  | 0 | 66189 | 66188
66190 | East Levee - Industrial Blvd 138 kV DCKT Line | Rebuild East Levee - Industrial Blvd 138 kV DCKT Line |  | East Levee | Industrial | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4213 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2481, 2482, 2875, 2974, 2874, 2876, 2976 | Y |  |  | 0 | 66191 | 66190
66200 | Upgrade Taylor - Holland 69 kV Line | Upgrade Taylor - Holland 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6173 | 2023-05-15 |  | 69 |  | 24 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3644, 3645, 3646, 3647, 3648, 3649, 13646, 13647 | Y |  |  | 0 | 66201 | 66200
66202 | Upgrade Palestine-Crockett 69 kV Line | Upgrade Palestine-Crockett 69 kV Line |  | Palestine | Crockett | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6182 | 2023-05-15 |  | 69 | 0 | 37.1 | 0 |  | Anderson | Houston | Tier 3 |  |  |  |  | 3273, 3285, 3286, 3289, 3290 | Y |  |  | 0 | 66203 | 66202
66206 | Upgrade Temple - Minerva 69 kV Line | Upgrade Temple - Minerva 69 kV Line |  | Temple | Minerva | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6186 | 2023-05-15 |  | 69 | 0 | 33.6 | 0 |  | Bell | Milam | Tier 3 |  |  |  |  | 3643, 3684, 3685, 3689 | Y |  |  | 0 | 66207 | 66206
66218 | Hillsboro - Italy 69 kV Line | Rebuild the existing 69 kV Line |  | Hillsboro Switch | Italy | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4326 | 2023-05-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2337, 2338, 3523 | Y |  |  | 0 | 66220 | 66218
66473 | Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line | Upgrade the Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line |  | Mesquite East | Oates | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4137 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 831, 2742, 2747, 2756, 2764, 2765, 2766, 2767 | Y |  |  | 0 | 66475 | 66473
66522 | Andrews North - Paul Davis Tap 138 kV Line Rebuild | Add Andrews North - Paul Davis Tap 138 kV Line Rebuild |  | Andrews North | Paul Davis Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8596 | 2023-05-15 |  | 138 | 0 | 25 | 0 |  | Andrews | Dawson | Tier 4 | 21RPG012 | 2021-08-03 | 2021-08-26 |  | 1159, 1165, 1167, 1168 | Y |  |  | 0 | 66523 | 66522
66530 | Add Consavvy 345/138 kV Switch | Add Consavvy 345/138 kV Switch |  | Consavvy | Consavvy | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8498 | 2023-05-15 |  | 345 | 0 | 0 | 1200 |  | Midland | Midland | Tier 3 |  |  |  |  | 11386, 11387, 11388, 11389, 1058, 1125, 1133, 1329, 11016, 11361, 19000, 23856 | Y |  |  | 0 | 66531 | 66530
66532 | South Midland - Pronghorn 138 kV Line Rebuild | Add South Midland - Pronghorn 138 kV Line Rebuild |  | South Midland | Pronghorn | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8606 | 2023-05-15 |  | 138 | 9.9 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23860, 1133 | Y |  |  | 0 | 66533 | 66532
66571 | Texaco Mabee Tap - Midland East 138 kV Line Rebuild | Add Texaco Mabee Tap - Midland East 138 kV Line Rebuild |  | Texaco Mabee Tap | Midland East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8304 | 2023-05-15 |  | 138 | 0 | 15.4 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 1023, 1171, 1178, 1184, 11301 | Y |  |  | 0 | 66572 | 66571
66635 | Lamesa 69 kV Substation Conversion to 138 kV | Add Lamesa 69 kV Substation Conversion to 138 kV |  | Lamesa 69 kV | Lamesa 138 kV | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8595 | 2023-05-15 |  | 69 | 0 | 0 | 0 |  | Dawson | Dawson | Tier 4 |  |  |  |  | 1164, 10008, 1163, 18880 | Y |  |  | 0 | 66638 | 66635
52318 | Royse Switch - Greenbriar Switch 138 kV Line | Upgrade the Royse Switch - Greenbriar Switch 138 kV Line |  | Royse | Greenbriar | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4292 | 2023-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Collin | Rockwall | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 2472, 2707, 12527 | Y |  |  | 0 | 52319 | 52318
63933 | Cedar Crest 69 kV Substation Conversion To 138 kV | Convert Cedar Crest 69 kV Substation To 138 kV |  | Cedar Crest |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4193 | 2023-05-16 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2486, 12486, 2495, 2982, 2985, 2493, 2494 | Y |  |  | 0 | 66658 | 63933
64484 |  | Converting voltages for several Rayburn buses from 69 kV to 138 kV. |  | 6823, 6861, 6869, 6871 |  | Planned |  | RYBRN |  |  | 2023-05-16 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6823, 6861, 6869, 6871, 37361 | Y |  |  | 0 | 65710 | 64484
61449 | Ottine Substation | Replace existing T1 with 10.5 MVA unit from GVEC Shiner substation |  | Ottine | Ottine | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-05-19 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7594 | Y | N |  | 0 | 61450 | 61449
5165 | Poesta: Construct a new 138/69 kV station | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. | Update Schedule and Cost | Borglum |  | Under Construction | 742 - 0925 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 2914 TP2014129 | 2023-05-25 |  | 138 | 0 | 0 | 130 |  | Bee |  | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8196, 8197, 8205, 8107, 8198, 8199, 8904 | Y | N |  |  | 13315 | 5165
5166 | Poesta to Three Rivers: Rebuild 69 kV line | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. |  | Borglum | Three Rivers | Under Construction | 742 - 0925 | AEP TCC | Dave Gotez bcogan@aep.com 918-599-2857 | 2915 | 2023-05-25 |  | 138 | 6 | 22 | 0 |  | Bee | Live Oak | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8156, 8142, 8199, 84006, 8196, 8400, 8403 | Y | N |  | 0 | 57889 | 5166
5167 | Poesta to Tuleta: Build new double circuit 138/69 kV line | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. |  | Borglum | Tuleta | Under Construction | 742 - 0925 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 2916 | 2023-05-25 |  | 138 | 23.5 | 23.5 | 0 |  | Bee | Bee | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8195, 8584, 8592, 8629, 88198, 8197, 8198, 8586, 85851, 8196, 8585, 8590, 8593 | Y | N |  | 0 | 61033 | 5167
4010 | Rebuild Magnolia - Seminole 138 kV line. | *Project pushed back to 2023. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07216 | 2023-05-31 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38950, 38990 | Y |  |  |  | 11530 | 4010
7013 | NASA Substation Upgrades | Upgrade substation equipment at NASA substation to increase thermal limits |  | NASA | NASA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42970, 42610 | Y | N |  |  | 14835 | 7013
57521C | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 57532 | 57521
57521B | Stone Lake New Sub Ckt66 | Upgrade Ckt.66 Hockley to Stone Lake BP2023 as a transmission project. |  | Stone Lake | Hockley/Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 15.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45880, 45886 | Y | N |  | Cost included in main entry | 57531 | 57521
57521D | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 57533 | 57521
57906 | Laredo to University: Rebuild 138 kV Line | Rebuild the 5.19 mile Laredo to University 138 kV transmission line and upgrade any limiting elements. |  | Laredo | University | Planned | 1119 - 1297 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3838 | 2023-05-31 |  | 138 | 0 | 5.19 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645, 8647 | Y | N |  | 0 | 65579 | 57906
59317 | Deer Park Tap to Cardiff Ckt.96E Upgrades | Upgrade Deer Park Tap to Cardiff Ckt.96E to Minimum 300 MVA Emergency rating |  | Deer Park | Cardiff | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 5.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40442, 42240 | Y | N |  | 0 | 59318 | 59317
63922 | Tiki Island Distribution Upgrades | Install double-tap distribution service to Tiki Island. Existing tap will remain on Ckt.63E La Marque to Stewart. Tap Ckt.93C La Marque to West Galveston for the new tap section to Tiki Island. |  | Tiki Island | LaMarque/West Galveston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 43351, 43352, 43355, 42860, 43290, 43401 | Y | N |  | 0 | 63923 | 63922
63971 | Mykawa Distribution Facilities | Install distribution facilities at MYKAWA substation |  | Mykawa |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 42751, 42752, 42753, 42750, 42741, 42742, 43051 | Y | N |  | 0 | 63972 | 63971
64491 | Bellaire to Smithers Ckt.98A Upgrade | Upgrade Bellaire to Smithers Ckt.98A to increase thermal limits |  | Bellaire | Smithers | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 47000, 44650 | Y | N |  | 0 | 64492 | 64491
64493 | Bellaire to WAP Ckt.50A Upgrade | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits |  | Bellaire | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 47000, 44005 | Y | N |  | 0 | 64494 | 64493
64499 | Hyde Park to Downtown Ckt.32A Upgrades | Upgrade Hyde Park to Downtown Ckt.32A |  | Downtown | Hyde Park | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 345 | 0 | 1.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47690, 47510 | Y | N |  | 0 | 64500 | 64499
64581A | New 138kV Waterfowl substation | Reconfigure existing Ckt.02F (move Seadoc/Seaway onto other circuit) resulting in Ckt.02F COPPER to Booster tap to Jones Creek. |  | COPPER | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 43212, 43221, 48006, 5568, 42195, 42199, 42540, 43211, 42215, 43222 | Y | N |  | 0 | 64582 | 64581
64589 | Jeanetta Auto A3 Upgrade | Upgrade Jeanetta Auto A3 to increase thermal limits |  | Jeanetta |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47300, 47310, 49082 | Y | N |  | 0 | 64590 | 64589
64999C | Ckt93 AlgoaCorner to Alta Loma Rebuild | Rebuild and reconductor portions of Ckt.93B Hitchcock to LarMarque as a Hardening upgrade. Upgrade substation equipment at Hitchcock to increase thermal limits. |  | Hitchcock | LarMarque | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 4.95 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-14 |  | 42800, 42860 | Y | N |  | Cost included in main project | 65002 | 64999
64999A | Ckt93 AlgoaCorner to Alta Loma Rebuild | Rebuild and reconductor portions of Ckt.93B AlgoaCorner to Alta Loma as a Hardening upgrade. |  | PH Robinson | Alta Loma | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 22.31 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-14 |  | 42015, 42061 | Y | N |  | 0 | 65000 | 64999
65003 | WA Parish to Nash Ckt.02B Upgrades | Upgrade Ckt.02B WA Parish to Nash to replace aging infrastructure and to address line clearance concerns |  | WA Parish | Nash | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 18.02 | 0 |  | Fort Bend | Brazoria | Tier 4 | 21RPG013 | 2021-08-08 | 2021-09-10 |  | 42980, 42410, 44010 | Y | N |  | 0 | 65004 | 65003
66043B | Ckt29 THW-WhiteOak Reconductor and 138kV Conversion | Reconductor remaining portions of 69kV Ckt.29 TH Wharton to Little York to White Oak for 138kV conversion. Reconnect as 138kV Ckt.xx TH Wharton to Little York to White Oak. |  | TH Wharton | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | 21RPG016 | 2021-09-08 | 2021-09-30 |  | 45512, 45990, 45995, 45510, 45530, 45782, 45922, 46615, 46620 | Y | N |  | 0 | 66045 | 66043
66046 | Ckt09 Zenith-VillageCreek Reconfigurations | Expand Zenith 138kV substation and install radial section Ckt.xx Zenith to Village Creek. Reconfigure Ckt.09K at Village Creek to create Ckt.09K Zenith to Village Creek tap to Franz. |  | Zenith | Village Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 3.6 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44270, 44271, 44272, 44260, 44910 | Y | N |  | 0 | 66047 | 66046
66221E | Galena Park Area Conversion Project | De-energize Ckt.20C Galena Park to Greens Bayou |  | Galena Park | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40725 | Y | N |  | Cost included in main entry | 66226 | 66221
66221A | Galena Park Area Conversion Project | Remove Galena Park Auto A1. Remove Galena Park 69kV facilities. Remove Galena Park 138kV ring bus. Rebuild Galena Park substation for double-tap 138kV service. |  | Galena Park |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | -200 |  | Harris |  | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40610, 49015, 40612, 40630, 41172, 40611 | Y | N |  | 0 | 66222 | 66221
66221B | Galena Park Area Conversion Project | De-energize Ckt.38A Galena Park to GYPSUM |  | Galena Park | GYPSUM | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40619, 40611, 40751 | Y | N |  | Cost included in main entry | 66223 | 66221
66221H | Galena Park Area Conversion Project | Join 69kV Greens Bayou buses 40720 & 40725 at a Minimum 40KAIC |  | Greens Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40725, 40720, 41570, 41681 | Y | N |  | Cost included in main entry | 66229 | 66221
66221J | Galena Park Area Conversion Project | Expand Clinton 138kV Facilities and Install 200MVA Autotransformer |  | Clinton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 200 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40350, 40352, 49004 | Y | N |  | Cost included in main entry | 66230 | 66221
66221G | Galena Park Area Conversion Project | Rebuild Galena Park substation for double tap service. Tap Galena Park TR2 on Ckt.21K between Fidelity and Witter. |  | Fidelity | Witter | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40612, 40590, 41712 | Y | N |  | Cost included in main entry | 66228 | 66221
66221D | Galena Park Area Conversion Project | De-energize Ckt.38B Clinton to Greens Bayou |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40352, 40720 | Y | N |  | Cost included in main entry | 66225 | 66221
66221F | Galena Park Area Conversion Project | Rebuild GYPSUM customer substation for 138kV loop-tap service. Rebuild Galena Park substation for double tap service. Tap new GYPSUM substation (SPEAR) from Ckt.94 between TANKER and new Galena Park TR1 tap. |  | CITFIL | TANKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40731, 40751, 40630, 41172 | Y | N |  | Cost included in main entry | 66227 | 66221
66221C | Galena Park Area Conversion Project | De-energize Ckt.17A Galena Park to Greens Bayou |  | Galena Park | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40720 | Y | N |  | Cost included in main entry | 66224 | 66221
59804A | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86 Crosby to Newport to Jonte |  | Jonte | Crosby/Newport | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 41150, 46032 | Y | N |  | 0 | 59805 | 59804
59804B | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86 Jonte to Greens Road tap |  | Jonte | Greens Road | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45821, 45660, 46331 | Y | N |  | Cost included in main project | 59806 | 59804
59804C | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86 Jonte to Lockwood tap to Scenic Woods radial |  | Lockwood | Jonte/Scenic Woods | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46331, 46032, 45660, 46336 | Y | N |  | Cost included in main project | 59807 | 59804
59804D | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90 North Belt to Greens Road tap to Jonte |  | Greens Road | North Belt/Jonte | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45822, 45660, 46031 | Y | N |  | Cost included in main project | 59808 | 59804
59804E | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90 Jonte to Lockwood tap to Lauder tap to Scenic Woods radial |  | Jonte | Lockwood/Lauder/Scenic Woods | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46031, 45660 | Y | N |  | Cost included in main project | 59809 | 59804
64505A | Flewellen to Peters Ckt.25E Upgrades | Upgrade Ckt.25E Flewellen to Foster to increase thermal limits |  | Flewellen | Foster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:01 |  | 138 | 0 | 1.9 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 21RPG011 | 2021-06-04 | 2021-07-02 |  | 44230, 44256 | Y | N |  | 0 | 64506 | 64505
64581B | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Reconfigure existing Ckt.02F and install new conductor to create new Ckt.54x Jones Creek to Waterfowl |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 43470, 42540 | Y | N |  | Cost included in main entry | 64583 | 64581
64999B | Ckt93 AlgoaCorner to Alta Loma Rebuild | Rebuild and reconductor portions of Ckt.93B Alta Loma to Hitchcock as a Hardening upgrade. Upgrade substation equipment at Hitchcock to increase thermal limits. |  | Alta Loma | Hitchcock | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:01 |  | 138 | 0 | 6.38 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-14 |  | 42061, 42800 | Y | N |  | Cost included in main project | 65001 | 64999
64505B | Flewellen to Peters Ckt.25E Upgrades | Upgrade Ckt.25E Foster to Peters to increase thermal limits |  | Foster | Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:02 |  | 138 | 0 | 27.4 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 21RPG011 | 2021-06-04 | 2021-07-02 |  | 44256, 44860, 46220 | Y | N |  | Cost included in main entry | 64507 | 64505
64581C | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Convert customer-owned Seadoc and Seaway substations to loop service. Reconfigure existing Ckt.02F and reconnect Seadoc/Seaway to create new Ckt.02x Jones creek to Seadoc to Seaway to Waterfowl. |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 42540, 43211, 43222, 43470 | Y | N |  | Cost included in main entry | 64584 | 64581
64581D | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Remove existing Seaway Switchrack. Reconfigure existing Ckt.02F to create new Ckt.02y Waterfowl to Franklins Camp. |  | Waterfowl | Franklins Camp | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 5568, 43470 | Y | N |  | Cost included in main entry | 64585 | 64581
65704 | Expand Crosby substation with 35kV Distribution Facilities |  |  | Crosby | Highlands/Atascosita |  |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40394, 40397, 40390, 40391, 40130, 40790, 40811 | Y | N |  | 0 | 65705 | 65704
65716A |  | Upgrade Ckt.86 Jonte to Lockwood tap to increase thermal limits |  | Jonte | Lockwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 46032 | Y | N |  | 0 | 65717 | 65716
66009 | CNP SNUG POI for COTTONWOOD Solar |  |  | SNUG | Liverpool/PETSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44890, 42870, 43070 | Y | N |  | 0 | 66010 | 66009
66013 | CNP WATERHOLE POI for G Star Solar | New 345kV Waterhole (WAT) substation for generator interconnection to G-Star Solar. Loop Ckt.62 into substation to create new Ckt.62 Bailey to Waterhole to Jones Creek. |  | Waterhole | BAILEY/Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44880, 42530, 44040 | Y | N |  | 0 | 66014 | 66013
66017A | Westpark Area Upgrades | Upgrade Ckt.05E Bellaire to Sharpstown tap and Dunvale tap to Jeanetta to increase thermal limits |  | Bellaire | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 3.6 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47071, 47310, 47411 | Y | N |  | 0 | 66018 | 66017
65716B |  | Install 20 MVAR cap bank at Jonte substation on Ckt.86 Jonte to Lockwood tap |  | Jonte |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 |  | 138 | 0 | 0 | 0 | 0,20 | Harris |  | Tier 4 |  |  |  |  | 45660 | Y | N |  | 0 | 65718 | 65716
66017B | Westpark Area Upgrades | Upgrade Ckt.24B Dunvale tap to Westchase tap to increase thermal limits. |  | Dunvale | Westchase | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:01 |  | 138 | 0 | 2.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44762, 47072 | Y | N |  | 0 | 66019 | 66017
44963 | USAA Rebuild 138 kV Station | CPSE_USAA 138 kV Substation Rebuild and Line Reconfiguration. |  |  |  | Planned | S-0896 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0285 | 2023-06-01 |  | 138 | 0.6 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-10 |  |  | 5450, 5451, 5452, 5125, 5170, 5208, 5300, 5453 | Y |  |  | 0 | 44964 | 44963
45101 | Chavaneaux_Chavaneaux Tap (Chavaneaux to Palo Alto)- 138 kV | CPSE_Chavaneaux_Chavaneaux 138 kV Tap Rebuild (Chavaneaux to Palo Alto). |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0256 | 2023-06-01 |  | 138 | 0 | 0.9 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5085, 5330 | Y |  |  | 0 | 45102 | 45101
45136 | CPSE_New Midtown Substation | New Mid Town substation looped into Comal St to Olmos transmission line. |  |  |  |  | S-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0283 | 2023-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5311, 5096, 5325 | Y |  |  | 0 | 45137 | 45136
48774 | Fincas: Construct New Distribution Station | Fincas: Construct New Distribution Station |  | Gateway Tap West | Wormser | Planned | 1026 - 1204 | AEP TCC | Alison Scrobiao bcogan@aep.com 918-599-2857 | 3765 | 2023-06-01 |  | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8039, 8295, 8650 | Y | N |  | 0 | 48775 | 48774
50645 | CPSE_Rafter 138kV Cap Bank | [6 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2023-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5355 | Y |  |  | 0 | 50646 | 50645
61138 | Bergstrom Sub Cap Addition | Add a 31.2 MVAR Cap Bank at the Bergstrom Substation |  | Bergstrom | Bergstrom | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2023-06-01 |  | 138 | 0 | 0 | 0 | 0,31.2 | Travis | Travis | Tier 4 |  |  |  |  | 9165 | Y |  |  | 0 | 61139 | 61138
61228 | AEN_McNeil__JustinLane__ckt_811_reconductor | Reconductor 3.98 miles of circuit to 3000 Amps. |  | McNeil [9080] | Justin Lane [9225] | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2023-06-01 |  | 138 | 0 | 3.98 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9080, 9225 | Y |  |  | 0 | 61229 | 61228
63497 | Bakersfield to Cedar Canyon 2nd circuit | Add the 2nd circuit to CREZ Bakersfield to Cedar Canyon 345 kV line |  | Bakersfield | Cedar Canyon | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-06-01 |  | 345 | 21.1 | 0 | 0 |  | Pecos | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76002, 76015 | Y | N |  |  | 63498 | 63497
63906 | PEC_HeroWay_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Nameless and Leander and install 46.7 MVA distribution transformer. The new substation will be located approximately 3.1 miles (45% of existing line length) from Leander substation. |  | Nameless | Leander | Planned | 61279 | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2023-06-01 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7536, 7525, 7526 | Y | N |  | 0 | 63907 | 63906
65661 | Rebuild Wickett-Pyote 138 kV line |  |  | Wickett (but # 37981) | Pyote (bus # 38001) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-06-01 |  | 138 | 0 | 12.88 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37981, 38001 | Y |  |  | 0 | 65662 | 65661
65663 | Double Ckt Line M138-K |  |  | Pecos (bus # 38091) | Faulkner (bus # 38124) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-06-01 |  | 138 | 26.37 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38091, 38114, 38117, 38121, 38124 | Y |  |  | 0 | 65664 | 65663
66074 | Double ckt Soaptree-Holiday-AlamoSt |  |  | Soaptree (bus # 38450) | Alamo Street (bus # 38330) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-06-01 |  | 138 | 0 | 31.9 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38450, 38455 | Y |  |  | 0 | 66075 | 66074
64021 | Texana | Texana sflsjdfldsajf sd fjsdf |  |  |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020888 | 2023-06-29 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8192, 8675, 8099, 8102 | Y |  |  | 0 | 64022 | 64021
5154 | Holford 138 kV new load substation and connections | Holford 138 kV new substation and its connections to CampbellSW and to Firewheel as well as some load growths at Holford |  | CampbellSW | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2023-06-30 |  | 138 | 0 | 1.5 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 835, 821, 838 | Y |  |  |  | 12810 | 5154
5940B | Mountain Home Substation and Transmission Line Addition | Cut-in the existing Gillespie to Fredericksburg 138-kV transmission line (T379) at Peach substation (converted to 138-kV, located adjacent to Live Oak substation), re-terminate and convert the existing 69-kV Harper to Live Oak transmission line to form 138-kV Headwaters to Peach transmission line, and connect the existing 69-kV Gillespie to Live Oak (T131) and existing Live Oak to Goehman Tap (T287) transmission lines to create a continuous 69-kV circuit from Gillespie to Goehman Tap. |  | Headwater | Goehman Tap. | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017394 | 2023-06-30 |  | 138 | 0 | 22.5 | 0 |  | Kerr | Gillespie | Tier 1 | 16RPG015 | 2016-11-18 |  |  | 7412, 7752, 7130, 7132, 7149, 7410, 7751, 7413 | Y | N |  | 0 | 61874 | 5940
52068 | Pleasanton to Three Rivers: Rebuild 69 kV line | Rebuild Pleasanton to Three Rivers 69 kV line |  | Pleasanton | Three Rivers | Planned | 1077 - 1250 | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | 3802 TP2020193 | 2023-06-30 |  | 69 | 0 | 0.06 | 0 |  | Atascosa | Live Oak | Tier 4 |  |  |  |  | 8400, 8406, 8507, 8599, 8600, 84061, 85071, 85991, 86001, 8403, 8142, 8199, 8200, 8203, 8543, 88507 | Y | N |  | 0 | 65610 | 52068
54204 | Gonzales - Hochheim Transmission Line Overhaul | Increase the reliability and capacity of transmission facilities on the T542 Luling ¿ Cuero 19.6-mile 69-kV transmission line from Gonzales (structure #33) to Hochheim Tap. LCRA TSC will perform an overhaul of T542 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T542 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Gonzales | DeWitt | Tier 4 |  |  |  |  | 7223, 78577 | Y | N |  | 0 | 54205 | 54204
61230 | Altair - Garwood Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 9.4-mile Altair ¿ Garwood (T542) (including all the tap lines) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Altair | Garwood | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  |  | 78106, 78530 | Y | N |  | 0 | 61231 | 61230
61459 | Buchanan CTEC-Buchanan Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 2.8-mile Buchanan ¿ Buchanan CTEC (T106) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Buchanan CTEC | Buchanan | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7092, 7101 | Y | N |  | 0 | 61460 | 61459
61461 | Buchanan CTEC - Pitsburg Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 14.5-mile Buchanan CTEC ¿ Pitsburg (T267) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Buchanan CTEC | Pitsburg | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 |  | 69 | 0 | 0 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7119, 7116 | Y | N |  | 0 | 61462 | 61461
5430I | Conversion to 138kV | Retire the existing 69kV North Lakes substation together with the transformer relocated from Denton North |  | North Lakes |  | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 915, 928 | Y | N | N/A | 0 | 55203 | 5430
5430K | Conversion to 138kV | Construct new 138kV Hickory substation and terminate the existing Bonnie Brae - Hickory (which is already insulated for 138kV) at the new 138kV Hickory substation. |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 931 | Y | N | N/A | 0 | 55205 | 5430
5430G | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 905, 915 | Y | N | N/A | 0 | 55201 | 5430
5430H | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 0 | 1.521 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 928, 931 | Y | N | N/A | 0 | 55202 | 5430
5430J | Conversion to 138kV | Line already insulated for 138kV. Line will be terminated at the new 138kV Hickory substation |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 905, 910 | Y | N | N/A | 0 | 55204 | 5430
5461 | Load serving |  |  | Puckrus | Mayhill | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 1.9 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 929, 917 | N | N |  |  | 13164 | 5461
5559 | Add new 138kV Bonnie Brae Substation and retire the 69kV sta |  |  | Bonnie Brae |  | Planned | N/A | DENTON | Charles Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  |  | 905, 931 | Y | N | N/A |  | 13291 | 5559
44416 | Add a 2nd circuit at Brinker - Denton Steam |  |  | Brinker | Denton Steam | Planned |  | DENTON | Chuck Sears |  | 2023-07-01 |  | 138 | 0.631 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 982 | Y | N |  | 0 | 44417 | 44416
45511 | Laredo - Del Mar: 138 kV Line Rebuild | Rebuild Laredo - Del Mar 138 kV Line with 795 ACSS |  | Laredo | Del Mar | Conceptual | 992 - 1170 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3746 | 2023-07-01 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645 | Y | N |  | 0 | 65531 | 45511
45566 | Holly - Southside: 138 kV Line Rating Increase | Increase MOT for Holly - Southside 138 kV Line |  | Holly | Southside | Planned | 994 - 1172 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3747 TP-2019-065 | 2023-07-01 |  | 138 | 0 | 1.8 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486 | Y | N |  | 0 | 65532 | 45566
5206 | Brackettville to Escondido: Construct 138 kV line | Build a single circuit capable 138 kV circuit from Brakettville to Escondido station |  | Brackettville | Escondido | Planned | 762-0947 | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | 3570 TP2017041 | 2023-07-30 |  | 138 | 45 | 0 | 0 |  | Kinney | Maverick | Tier 2 | 16RPG001 | 2016-01-05 | 2017-01-20 | 2017-02-08 | 8252, 8260 | Y | N |  |  | 12865 | 5206
66128 | Construct a 138 kV dead end structure outside of the Clarkwood station along with the first span. Construct a 138 kV breaker terminal at the Clarkwood station. | Construct a 138 kV dead end structure outside of the Clarkwood station along with the first span. Construct a 138 kV breaker terminal at the Clarkwood station. Connect BRP Carina to the Clarkwood 138 kV station | NEW | BRP Carina | Clarkwood | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021308 | 2023-08-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 88479, 8479 | Y |  |  | 0 | 66129 | 66128
52147 | Rising Star Area Conversions | Converts voltage to 138 KV from Holder to Nimrod to Rising Star. |  | Holder | Rising Star | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2023-09-01 |  | 138 | 0 | 0 | 0 |  | Brown | Comanche | Tier 4 |  |  |  |  | 285, 289, 293, 292, 281 | Y |  |  | 0 | 52148 | 52147
64754 |  | Loop new 138kV Crossroads substation into existing 138kV Potranco to AMD transmission line |  |  |  | Planned | T-0310 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0962 | 2023-09-28 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5102, 5002, 5346 | Y |  |  | 0 | 64755 | 64754
64774 |  | Loop new 138kV Donop substation into existing 138kV Southton to Braunig transmission line. |  |  |  | Planned | T-0311 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0963 | 2023-09-28 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5128, 5030, 5394 | Y |  |  | 0 | 64775 | 64774
6876 | Support 69kV to 138kV West Loop Conversion Projects | Upgraded line Jupiter to College to support 69kV to 138kV West Loop Conversion Projects |  | Jupiter | College | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2023-10-01 |  | 138 | 0 | 2.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 803, 815, 820, 806, 829 | Y |  |  |  | 14685 | 6876
48327 | Reconductor 138kV ckt 972 Howard Lane to McNeil to 3000A. |  |  | 9079 | 9217 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinene (512) 322-6740 |  | 2023-10-01 |  | 138 | 0 | 2.81 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9079, 9217 | Y |  |  | 0 | 48328 | 48327
52169 | Rising Star Area Conversions | This converts the voltage to 138 following Rising Star Substation Voltage Conversion |  | Rising Star | Downing | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2023-10-01 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 281, 277, 285, 294 | Y |  |  | 0 | 52170 | 52169
11TPIT0011 | East_Village138kV Substation | East_Village 138kV Substation |  | Techridge | East_Village SUB |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2023-10-09 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9195, 9045, 9190 | Y |  |  |  | 13043 | 5357
66130 | Add 2 - 34.6 Mvar Cap Banks at Hecker 138 kV station and 2 - 34.6 Mvar Cap Banks at Resnik 138 kV station | Add 2 - 34.6 Mvar Cap Banks at Hecker 138 kV station and 2 - 34.6 Mvar Cap Banks at Resnik 138 kV station |  |  |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021207 | 2023-10-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8565, 8580 | Y |  |  | 0 | 66131 | 66130
18TPIT0001 | Wiederstein Substation Transformer Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Wiederstein |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-10-27 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7461 | Y | N |  |  | 10675 | 3319
50160 | Beeville - Goliad: Rebuild 69 kV Line | Beeville - Goliad: Rebuild 69 kV Line |  | Beeville | Goliad | Planned | 961 - 1139 | AEP TCC | Eric Scott bcogan@aep.com 918-599-2857 | 3719 TA2018010 | 2023-10-31 |  | 69 | 0 | 22.21 | 0 |  | Bee | Goliad | Tier 3 | 19RPG008 | 2019-04-30 | 2019-05-30 |  | 8584, 8586, 8587 | Y | N |  | 0 | 65542 | 50160
57350 | Lyons to Gay Hill T-line pole change out and reconductor | Replace existing structure with upgraded structures and replace existing 336.4 ACSR Linnet with 795 ACSR Drake on Lyons to Gay Hill transmission line. |  | Lyons | Gay Hill | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet.coop curtis.fischer@bluebonnet (979) 716-0253 |  | 2023-10-31 |  | 138 | 0 | 11.51 | 0 |  | Burleson | Washington | Tier 4 |  |  |  |  | 7572, 7573 | Y |  |  | 0 | 57351 | 57350
52064 | Bay City - Lane City: 138 kV Line Rebuild | Rebuild the Bay City - Magill - Lane City 138 kV Line | Update Schedule, Dollars, Tier, Sponser | Bay City | Lane City | Planned | 1078 - 1251 | AEP TCC | Marc E. Wilson bcogan@aep.com 918-599-2857 | 3803 | 2023-11-01 |  | 138 | 0 | 16 | 0 |  | Matagorda | Wharton | Tier 3 |  |  |  |  | 8111, 8113, 8127 | Y | N |  | 0 | 65558 | 52064
55605 | New Barksdale to Rocksprings: Rebuild 69 kV line | Rebuild 69 kV line from Campwood to Rocksprings |  | New Barksdale | Rocksprings | Planned | 1102 - 1280 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3819 | 2023-11-01 |  | 69 | 0 | 19.51 | 0 |  | Edwards | Edwards | Tier 3 |  |  |  |  | 8365, 8238 | Y |  |  | 0 | 65572 | 55605
50882 | Lon Hill - Structure 25/4: Line Rebuild | Lon Hill - STEC Warburton: Line Rebuild |  | Lon Hill | Haisley | Planned | 1055 - 1228 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3785 | 2023-11-30 |  | 138 | 0 | 10.2 | 0 |  | San Patricio | San Patricio | Tier 3 | 19RPG014 |  |  |  | 8027, 8452, 8920 | Y | N |  | 0 | 65548 | 50882
55299 | Munday to Throckmorton: Rebuild 69 kV line | Rehab 69 kV line from Munday to Throckmorton | Update Tier, RPG Number, and RPG Acceptance Date | Munday | Throckmorton | Planned | 1094 - 1272 | AEP TNC | Charity Kreher mlforcum@aep.com 918-599-2857 | 1862 | 2023-11-30 |  | 69 | 0 | 34.55 | 0 |  | Knox | Throckmorton | Tier 4 | 21RPG015 | 2021-08-24 | 2021-09-28 |  | 6107, 6204, 6205 | Y | N |  | 0 | 65569 | 55299
54120 | Rebuild Tejas-Commanche (Bundled 795 ACSS) | Rebuild Tejas - Commanche 138 kV line with Bundled 795 ACSS conductor. |  | Tejas 138 kV Substation (Bus # 38530) | Commanche 138 kV Substation (Bus # 38560) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07318 | 2023-12-01 |  | 138 | 0 | 0.95 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38530, 38560 | Y |  |  | 0 | 54121 | 54120
60502 | Rebuild Apache-Amoco with bundled 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38620, 38720 | Y |  |  | 0 | 60503 | 60502
60504 | Rebuild Caddo-Apache with bundled 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38710, 38720 | Y |  |  | 0 | 60505 | 60504
60526 | Rebuild West Columbia Local-Angleton with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39530, 39560 | Y |  |  | 0 | 60527 | 60526
63916 | PEC_Junction_Bus_Upgrade | Upgrade Junction from tap station to a three terminal ring bus and upgrade distribution transformer to 37.37 MVA |  | Junction |  | Planned |  | PEC/PEC/AEP | Ryan Morlino ryan.morlino@peci.com 830-868-5166 ryan.morlino@peci.com 830-868-5166 |  | 2023-12-01 |  | 69 | 0 | 0 | 0 |  | Kimble |  | Tier 4 | [5 empty] | Y | N |  | 0 | 63917 | 63916
65683 | To add Open Sky Station | To interconnect GINR 20INR0241 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2023-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68014, 68000, 68013 | Y | N |  | 0 | 65684 | 65683
66077 | Reconductor both Pecos-Cedarvale 138 kV ckts |  |  | Pecos (bus # 38091) | Cedarvale (bus # 38145) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 15.34 | 0 |  | Reeves | Ward | Tier 4 |  |  |  |  | 38091, 38145 | Y |  |  | 0 | 66078 | 66077
66118 | Reconductor TI-Lakepointe with 959 ACSS/TW |  |  | Lakepoint (bus # 37010) | TI (bus # 37080) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 2.78 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 37010, 37080 | Y |  |  | 0 | 66119 | 66118
66120 | Rebuild Freeway Park-Dickinson with bundled 795 ACSS |  |  | Freeway Park (bus # 38820) | Dickinson (bus # 38820) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 6.25 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38820, 38850 | Y |  |  | 0 | 66121 | 66120
66198 | Rebuild West Columbia Main-CNP West Columbia with bundled 795 ACSS |  |  | TNMP West Columbia Main (bus # 39500) | CenterPoint West Columbia (bus # 43380) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0.32 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 43380 | Y |  |  | 0 | 66199 | 66198
66204 | Rebuild Hidden Lakes-PH Robinson with bundled 795 ACSS |  |  | TNMP Hidden Lakes (bus # 38900) | CenterPoint PH Robinson (bus # 42015) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 3.15 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 42015 | Y |  |  | 0 | 66205 | 66204
66208 | Rebuild League City-Hidden Lakes with bundled 795 ACSS |  |  | Hidden Lakes (bus # 38900) | League City (bus # 38920) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 3.21 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  | 0 | 66209 | 66208
66368 | Rebuild West Columbia Main - Brazoria 138kV with 795 ACSS |  |  | West Columbia Main (bus # 39500) | Brazoria (bus # 39600) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 10.2 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 39600 | Y |  |  | 0 | 66369 | 66368
44946 | CPSE_New_Scenic_Loop_138kV_Load_Serving_Station | The new Scenic Loop 138 kV load serving station will be looped into existing Ranchtown to LCRA (Menger Creek) 138 kV transmission line. The substation should be located south west of the existing Fair Oaks Ranch and north east of the existing Ranchtown substation. |  |  |  | Planned | S-0885 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0275 | 2023-12-01 20:00 |  | 138 | 9 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5363, 5358, 7665 | Y |  |  | 0 | 44947 | 44946
5467 | Nacogdoches Southeast_Redland 345kV Line | Establish a new 345kV Line between Nacogdoches Southeast Switch and Redland Switch |  | Nacogdoches Southeast | Redland | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6075 | 2023-12-14 |  | 345 | 13.4 | 0 | 0 |  | Nacogdoches | Angelina | Tier 2 | 20RPG019 | 2020-10-01 |  |  | 3119, 3321 | Y | N |  |  | 13171 | 5467
58917 | Horizon 138 bus and line to Pearsall | Adds new Horizon Switch station to connect Horizon solar generation and a line to Pearsall |  | Horizon Swttch | Pearsall | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-12-14 |  | 138 | 0.4 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5897, 5895 | Y | N |  | 0 | 58918 | 58917
5466 | Redland Switch 345/138 kV Autotransformer | Install new 345/138 kV Autotransformer at Redland Switch previously known as Herty North |  | Redland | Redland | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6076 | 2023-12-15 |  | 345 | 0 | 0 | 600 |  | Angelina | Angelina | Tier 3 | 20RPG019 | 2020-10-01 |  |  | 3319, 3321, 3322 | Y | N |  |  | 13170 | 5466
5475 | Lufkin Switch - Redland Switch 345 kV Line | Construct a new 345 kV Line from Lufkin Switch to Redland Switch |  | Lufkin Switch | Redland Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6077 | 2023-12-15 |  | 345 | 8.1 | 0 | 0 |  | Angelina | Angelina | Tier 2 | 20RPG019 | 2020-10-01 |  |  | 3117, 3321 | Y | N |  |  | 13180 | 5475
7124 | Flat Iron - Barr Ranch - Pegasus South 138 kV Line | Construct new Flat Iron - Barr Ranch - Pegasus South 138 kV Line and Barr Ranch 138 kV Switch |  | Flat Iron | Pegasus South | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8574 | 2023-12-15 |  | 138 | 18 | 0 | 0 | 0,55.2 | Midland | Midland | Tier 2 | 21RPG010 | 2021-06-02 | 2021-06-23 | 2021-12-13 | 11235, 1237, 11217 | Y |  |  | 0 | 62668 | 7124
52728 | Add Foundry 138 kV Switch | Oncor's portion of AEP's Crane Area Transmission Project |  | LCRA Arco Crane | Navajo Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8502 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  | 2019-06-01 | 2019-07-22 |  | 10002, 11202, 60448, 71199 | Y |  |  | 0 | 52730 | 52728
56350A | Burnett - Bowie 69 kV Line | Upgrade and convert Burnett-Ringgold Magnolia Tap Line from 69 kV to 138 kV |  | Burnett | Ringgold Magnolia Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2023-12-15 |  | 69 | 0 | 21 | 100 |  | Wichita | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 1452, 1523, 1543, 1544, 1426, 1491, 775, 1545 | Y | N |  | 0 | 56861 | 56350
59525 | Cedar Crest Switch - Wall Street 69 kV Line Section Conversion To 138 kV | Convert existing 69 kV Line to 138 kV operation |  | Cedar Crest | Wall Street | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4071 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2982, 12486, 2493, 2976 | Y |  |  | 0 | 59526 | 59525
59835 | Royse Switch-Terrell Switch 69 kV Line Conversion to 138 kV | Convert the existing 69 kV Line to 138 kV |  | Royse | Terrell | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3223 | 2023-12-15 |  | 69 | 0 | 0 | 0 |  | Rockwall | Rockwall | Tier 4 |  |  |  |  | 2722, 2773, 12722, 12730, 2463, 2471, 2472, 12729, 2721, 2729, 3188 | Y |  |  | 0 | 59836 | 59835
60094 | Convert Waco East - Elm Mott 69 kV Line to 138 kV | Convert Waco East - Elm Mott 69 kV Line to 138 kV and relocate the Waco East Substation to the double circuit line going towards Lake Creek/Waco West |  | Waco East | Elm Mott | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6147 | 2023-12-15 |  | 138 | 0 | 10 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3439, 3443, 3571, 3573, 13438, 3407, 3408, 3438 | Y |  |  | 0 | 62645 | 60094
61601 | Add Coody Crossing 345 kV Switch | Add Coody Crossing 345 kV Switch |  | Clear Crossing | Tecumseh Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8560 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  | Throckmorton | Throckmorton | Tier 4 |  |  |  |  | 11419, 11418, 60514 | Y |  |  | 0 | 64014 | 61601
62445 | Eagle Mountain 138kV Switch Rebuild | Rebuild existing 138 kV Switch |  | Eagle Mountain |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5261 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 11859, 11860, 11864, 568, 1860, 1864, 1865, 12065, 1859, 11865, 11861, 11866 | Y |  |  | 0 | 62446 | 62445
62666 | Upgrade and convert McGregor - Waco West Line | Upgrade and convert McGregor - Waco West Line |  | McGregor Phillips | Waco West | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6172 | 2023-12-15 |  | 138 | 0 | 24.3 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3441, 3584, 3585, 3586, 3589, 3596, 3437, 3440, 3446, 3583, 3594 | Y |  |  | 0 | 62667 | 62666
62669 | Pegasus South - Pleasant Farms Tap 138 kV Line Rebuild | Rebuild existing Pegasus South - Pleasant Farms Tap 138 kV Line |  | Pegasus South | Pleasant Farms Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8574 | 2023-12-15 |  | 138 | 0 | 9.6 | 0 |  | Midland | Ector | Tier 4 | 21RPG010 | 2021-06-02 | 2021-06-23 | 2021-12-13 | 1236, 1237, 71230 | Y |  |  | 0 | 62672 | 62669
62693 | Courtney Creek - Yucca Drive 69 kV Line Conversion to 138 kV | Add Courtney Creek - Yucca Drive 69 kV Line Conversion to 138 kV |  | Courtney Creek | Yucca Drive | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8591 | 2023-12-15 |  | 69 | 0 | 44 | 0 |  | Pecos | Ward | Tier 3 |  |  |  |  | 1202, 1238, 1239, 11204, 11236, 11262, 1009, 1015, 1203, 1240, 1241, 1242, 11242, 1204, 11246, 11258, 60792 | Y |  |  | 0 | 64552 | 62693
62712 | Driver - Skywest 138 kV Line Rebuild | Rebuild the existing Driver - Skywest 138 kV Line |  | Driver | Skywest | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8564 | 2023-12-15 |  | 138 | 0 | 11.9 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 23863, 71210 | Y |  |  | 0 | 62716 | 62712
64239 | Vineyard Switch-North Lake Switch 138 kV Line | Construct a new 138 kV circuit from Vineyard to Northlake |  | North Lake Switch | Vineyard Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5320 | 2023-12-15 |  | 138 | 7.4 | 0 | 0 |  | Dallas | Tarrant | Tier 3 |  |  |  |  | 2022, 2386, 12013, 15030, 15035 | Y |  |  | 0 | 64240 | 64239
66196 | WichitaFalls PPG Terminal Equipment | Upgrade the existing terminal equipment at PPG |  | Wichita Falls PPG |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4025 | 2023-12-15 |  | 138 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1484, 1485, 17005 | Y |  |  | 0 | 66197 | 66196
66210 | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV. Relocate the Lake Creek 138/69 kV Auto to Marlin. |  | Lake Creek | Marlin | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1743 | 2023-12-15 |  | 138 | 0 | 13.7 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3416, 3418, 3694, 3695, 3410, 13639 | Y |  |  | 0 | 66211 | 66210
66214 | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV |  | Brownwood | Firerock | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6164 | 2023-12-15 |  | 138 | 0 | 15.5 | 0 |  | Brown | Brown | Tier 4 |  |  |  |  | 1669, 1670, 1671, 1661, 1662, 6359, 6408 | Y |  |  | 0 | 66215 | 66214
66216 | Upgrade and convert Waco West - Temple 69 kV Line to 138 kV | Upgrade and convert Waco West - Temple 69 kV Line to 138 kV |  | Waco West | Temple Elm Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6191 | 2023-12-15 |  | 138 | 0 | 31.4 | 0 |  | McLennan | Bell | Tier 4 |  |  |  |  | 147, 3578, 3580, 3581, 703580, 3437, 3446, 3644, 13662 | Y |  |  | 0 | 66217 | 66216
66289 | Upgrade and convert Tyler - Athens 69 kV Line | Upgrade and convert Tyler - Athens 69 kV Line to 138 kV. Disconnect Tyler and Athens 138/69 kV Autos. Extend line from Athens - Forest Grove Switch. Disconnect 69 kV lines from Trinidad and Poynor. Tap Poynor line off of Trinidad - Palestine 69 kV Line. |  | Tyler | Forest Grove | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6094 | 2023-12-15 |  | 138 | 3.6 | 33.3 | 0 |  | Smith | Henderson | Tier 3 |  |  |  |  | 3142, 3236, 3239, 3240, 3287, 13235, 3126, 3131, 3197, 3256, 3269, 3270, 3238 | Y |  |  | 0 | 66290 | 66289
66492 | Chico West - Oran Switch 69 kV Line Conversion to 138 kV | Convert existing 69 kV Line to 138 kV |  | Chico West | Oran | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3006 | 2023-12-15 |  | 69 | 0 | 0 | 0 |  | Wise | Palo Pinto | Tier 3 |  |  |  |  | 1542, 1553, 1554, 1555, 1556, 1557, 1558, 11556, 1563, 1571, 1572, 11582 | Y |  |  | 0 | 66521 | 66492
66567 | Add Wolf - Moss 138 kV Line Rebuild | Add Wolf - Moss 138 kV Line Rebuild |  | Wolf | Moss | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8530 | 2023-12-15 |  | 138 | 0 | 34.5 | 0 |  | Ward | Ector | Tier 3 |  |  |  |  | 1013, 1019, 1292, 11292, 11293 | Y |  |  | 0 | 66568 | 66567
66569 | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch |  | Mulberry Creek | Mulberry Creek | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9022 | 2023-12-15 |  | 345 | 0 | 0 | 0 |  | Jones | Jones | Tier 3 | 21RPG021 | 2021-12-17 | 2022-01-12 |  | 6235 | Y |  |  | 0 | 66570 | 66569
66632 | Coyote - Bulldog 138 kV Line Rebuild | Add Coyote - Bulldog 138 kV Line Rebuild |  | Coyote | Bulldog | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8553 | 2023-12-15 |  | 138 | 0 | 11.9 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 23832, 23833 | Y |  |  | 0 | 66634 | 66632
57726 | Commerce - Royse 69 kV Line Conversion to 138 kV | Convert existing 69 kV Line to 138 kV |  | Commerce Switch | Royse | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R985 | 2023-12-15 01:00 |  | 138 | 0 | 38.3 | 0 |  | Hunt | Rockwall | Tier 3 | 20RPG023 | 2020-12-23 | 2021-01-19 |  | 1818, 1821, 1824, 1826, 1827, 1828, 1829, 1830, 1831, 2463, 6944, 1816, 2472, 1820 | Y | N |  | 0 | 60030 | 57726
62643 | Rebuild Waco East 138 kV Switch | Rebuild Waco East 138 kV Switch |  | Waco East | Waco East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6146 | 2023-12-16 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3439, 3481, 3482, 13438, 3438, 3434, 3443, 3452, 3551, 3559, 3573 | Y |  |  | 0 | 62664 | 62643
57412 | Remove Genral From Service | Remove 69kV GENRAL substation from CNP service |  | GENRAL |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-30 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47670, 42690, 47540 | Y | N |  | 0 | 61869 | 57412
50898 | Alamito Creek to Paisano to Alpine: Rebuild 69 kV line | Rehab Alamito Creek to Paisano to Alpine 69 kV line |  | Alamito Creek | Alpine | Planned | 1045 - 1218 | AEP TNC | Nathan Cowan mlforcum@aep.com 918-599-2674 | 2793 | 2023-12-31 |  | 69 | 0 | 22.26 | 0 |  | Presidio | Brewster | Tier 4 | 20RPG017 |  |  |  | 6667, 6666, 6672 | Y | N |  | 0 | 50899 | 50898
50950 | Whitepoint Area Improvements | Whitepoint Area Improvements | Update Contact and Schedule | Whitepoint | Hecker | Planned | 1061 - 1234 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 3792 | 2023-12-31 |  | 138 | 0 | 12 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8418, 8565, 8961 | Y | N |  | 0 | 65551 | 50950
57750 | Seabrook 138kV Distribution Substation | Build new 138kV Seabrook distribution substation. Double tap from Ckt.79F PH Robinson to Hanna and Ckt.96A PH Robinson to Bayou. |  | Seabrook |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42851, 42852, 42013, 42014, 42160, 42780 | Y | N |  | 0 | 57751 | 57750
63834A | Alvin Area 138kV Conversions | Reconfigure existing Ckt.26B Rosharon to Karsten to create new Ckt.26B Rosharon to Manvel. |  | Karsten | Manvel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44430, 44440, 44410, 44600 | Y | N |  | 0 | 64472 | 63834
63834B | Alvin Area 138kV Conversions | Reconfigure existing Ckt.26B Rosharon to Karsten to create new Ckt.26B Manvel to Alvin tap to Karsten. Rebuild Alvin substation for double-tap service. |  | Manvel | Rosharon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42073, 44410, 44390, 44430 | Y | N |  | Cost in main project | 64473 | 63834
63834C | Alvin Area 138kV Conversions | Reconfigure existing Ckt.05B LIMBERG to Friendswood tap to Webster to create new Ckt.05B LIMBERG to Alvin tap to Friendswood tap. Rebuild Alvin substation for double-tap service. |  | LIMBERG | Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Harris | Tier 4 |  |  |  |  | 42072, 42651, 43280 | Y | N |  | Cost in main project | 64474 | 63834
63834D | Alvin Area 138kV Conversions | Rebuild portions of Ckt.53 Webster to Karsten to HO Clarke for 138kV Line Conversion. Retire the remaining portions of Ckt.53. Retire KR-A1 and WEB-A1 |  | Karsten | Webster/HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 00:04 |  | 69 | 0 | 0 | -300 |  | Brazoria | Harris | Tier 4 |  |  |  |  | 43510, 44400, 49022, 49087, 44440, 47160, 43500, 44390 | Y | N |  | Cost in main project | 64475 | 63834
52260 | India to DWU Rebuild | India to DWU Rebuild |  | India | Dallas Water Utilities | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-01-01 |  | 69 | 0 | 0 | 0 |  | Ellis | Dallas | Tier 4 |  |  |  |  | 230, 2351 | Y |  |  | 0 | 52261 | 52260
50868 | Rosata - Structure 31/8: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3780 | 2024-01-12 |  | 138 | 0 | 15.5 | 0 |  | Goliad | Karnes | Tier 3 | 20RPG014 |  |  |  | 8186, 8153 | Y | N |  | 0 | 50869 | 50868
6253 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-02-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9276, 9077, 9238 | Y |  |  |  | 13981 | 6253
52670 | BEPC_20TPITXXXX_DowningStephenville |  |  | Stephenville | Carlton Switch | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-02-05 |  | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 286, 299, 295, 297, 294 | Y |  |  | 0 | 52671 | 52670
50900 | Mason to North Brady: Rebuild 69 kV line | Rehab Mason to North Brady 69 kV line |  | Mason | North Brady | Planned | 1046 - 1219 | AEP TNC | David Baker mlforcum@aep.com 918-599-2674 | 2794 | 2024-03-31 |  | 69 | 0 | 30.24 | 0 |  | Mason | McCulloch | Tier 3 | 19RPG019 | 2019-10-01 | 2019-11-01 |  | 6006, 6381, 6393, 6406, 60386 | Y | N |  | 0 | 65550 | 50900
45501 | Eldorado Live Oak to Sonora: Rebuild 69 kV line | Rehab Eldorado Live Oak to Sonora 69 kV line |  | Eldorado Live Oak | Sonora | Planned | 982 - 1160 | AEP TNC | Dave Baker mlforcum@aep.com 918-599-2674 | 2769 | 2024-03-31 01:00 |  | 69 | 0 | 23.92 | 0 |  | Schleicher | Sutton | Tier 3 | 18RPG012 | 2018-12-18 | 2019-01-17 |  | 6498, 6505, 6509, 6510, 6513 | Y | N |  | 0 | 65530 | 45501
50948 | Angstrom - Grissom: Build New Line | Angstrom - Grissom: Build New Line |  | Angstrom | Grissom | Planned | 1063 - 1236 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3797 | 2024-04-01 |  | 345 | 17 | 0 | 0 |  | San Patricio | Bee | Tier 1 |  |  |  |  | 8249, 8624 | Y | N |  | 0 | 50949 | 50948
50966 | North Shore: 345 kV (Chienere LNG) RPG | Construct Naismith 345/138 kV station with two (2) - 345/138 kV autos. Construct Angstrom to Grissom and Angstrom to Naismith 345 kV Lines. Construct Naismith to Resnik 138 kV Lines. |  | Angstrom | Resnik | Planned | 1063 - 1236 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3798 | 2024-04-01 |  | 345 | 50 | 0 | 1350 |  | San Patricio | San Patricio | Tier 1 | 19RPG0016 |  |  |  | 8659, 8660, 8249, 8580 | Y | N |  | 0 | 50970 | 50966
52175 | Rising Star Area Conversions | This continues the Rising Star Area Conversions with Carlton Switch to Downing | Carlton to Downing 138 kV Conversion | Carlton | Downing | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-04-01 |  | 138 | 0 | 0 | 0 |  | Erath | Comanche | Tier 4 |  |  |  |  | 294, 281, 286, 297 | Y |  |  | 0 | 52176 | 52175
64776 | Upgrade 138kV DentonWest-RDWells line to 700MVA |  |  | RD Wells | Denton West | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2024-04-01 |  | 138 | 0 | 4.47 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 930, 986 | Y | N |  | 0 | 64777 | 64776
61266 | Trading Post to Cedar Valley Storm Hardening | Rebuild single circuit section of Trading Post to Cedar Valley and reconductor with bundled 795 ACSR Conductor, 440 MVA |  | Trading Post | Cedar Valley | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-04-22 |  | 138 | 0 | 6.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7356, 7505 | Y | N |  | 0 | 61267 | 61266
61279 | Nameless to Leander Transmission Line Upgrade | Rebuild and upgrade Nameless to Leander with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA). |  | Nameless | Leander | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-04-22 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7526, 7536, 7525 | Y | N |  | 0 | 61280 | 61279
54892 | Eden to North Brady: Rebuild 69 kV line | Rehab Eden to North Brady 69 kV line |  | Eden | North Brady | Planned | 1039 - 1266 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1856 | 2024-04-30 |  | 69 | 0 | 32.7 | 0 |  | Concho | McCulloch | Tier 3 |  |  |  |  | 6384, 60797, 6006, 6372, 6380, 6385 | Y | N |  | 0 | 65568 | 54892
59197 | Mason - Mason Switch: Rebuild 69 kV Line | Rebuild Mason to Mason Switch 69 kV Line | Update Cost | Mason | Mason Swicth | Planned | 1126 - 1304 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 1871 | 2024-04-30 |  | 69 | 0 | 10.3 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6394, 60458, 6393, 6396, 6407 | Y | N |  | 0 | 59198 | 59197
46513 | Port Isabel: Rebuild As GIS Station | Rebuild Port Isabel as a GIS | Update Schedule | Port Isabel |  | Planned | 958 - 1136 | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | 3716 | 2024-05-01 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  | 0 | 50322 | 46513
61274A | PEC_MarshallFord_Paleface_StormHardening | Rebuild single circuit section of Paleface to Marshal Ford and reconductor with bundled 795 ACSR Conductor, 440 MVA; |  | Paleface | Marshall Ford | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-05-01 |  | 138 | 0 | 3.65 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7477, 7356 | Y | N |  | 0 | 63793 | 61274
50866 | Structure 31/8 - Kenedy SS: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3779 | 2024-05-13 01:00 |  | 138 | 0 | 14.3 | 0 |  | Karnes | Karnes | Tier 3 | 20RPG014 |  |  |  | 8186, 8153 | Y | N |  | 0 | 50867 | 50866
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing autotransformer |  | Elkton | Elkton | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6032-E | 2024-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 10501 | 3155
47428 | Bellville South - Prairie View Transmission Line Upgrade | The proposed project converts the existing 69-kV transmission line T283 from Bellville South - Quanex Switch - Sunnyside Prairie View Substation to 138-kV. The proposed project improves the reliability of transmission facilities on the 26.1-mile transmission line and increases the line capacity for long term system growth. |  | Bellville South | Prairie View | Conceptual |  | SBEC | James Jouett jjouett@sbec.org 979-413-7714 |  | 2024-05-15 |  | 69 | 0 | 0 | 0 |  | Austin | Waller | Tier 3 |  |  |  |  | 7269, 7660, 7664, 7666 | N | N |  | 0 | 47429 | 47428
61436 | Bastrop West - Split Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 2.4-mile portion of Bastrop West ¿ Sim Gideon (T410) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Bastrop West | Sim Gideon | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7555, 7310 | Y | N |  | 0 | 61437 | 61436
61438 | Sim Gideon - Tahitian Village Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 5.1-mile Sim Gideon ¿ Tahitian Village (T648) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Sim Gideon | Tahitian Village | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7310, 7575 | Y | N |  | 0 | 61439 | 61438
61457 | Nada - Ricebird Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 13.1-mile Nada ¿ Ricebird (T588) 138-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Nada | Ricebird | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Colorado | Wharton | Tier 4 |  |  |  |  | 78103, 78104 | Y | N |  | 0 | 61458 | 61457
62434 | Sargent Road - Industrial Blvd 138 kV DCKT Line | Upgrade existing 138 kV Line |  | Sargent Road Switch | Industrial Blvd Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4128 | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2983, 2940, 2947, 2972, 2973, 2975, 2977, 2982, 2974, 2976 | Y |  |  | 0 | 62435 | 62434
50874 | Smith - Mathis: Line Rebuild | Smith - Mathis: Line Rebuild | Update Schedule, Dollars | Smith | Mathis | Planned | 1053 - 1226 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3781 | 2024-05-30 |  | 69 | 0 | 22.47 | 0 |  | San Patricio | San Patricio | Tier 3 | 20RPG001 |  |  |  | 8407, 8408, 8424, 8866 | Y | N |  | 0 | 65547 | 50874
55626 | Ganso to Hamilton Road: Rebuild 138 kV line | Rebuild 138 kV line from Ganso to Hamilton Road |  | Maverick | Hamilton Road | Planned | 1105 - 1283 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3824 | 2024-05-30 |  | 138 | 0 | 41.1 | 0 |  | Maverick | Val Verde | Tier 3 |  |  |  |  | 8267, 8692, 8255 | Y |  |  | 0 | 65576 | 55626
6572 | Ballinger to Eden 69 kV line: Rebuild taps | Ballinger to Eden 69 kV line: Rebuild taps | Update Contact, Schedule, and Cost | Ballinger | Eden | Planned | 890 - 1068 | AEP TNC | Shawn Ketcher mlforcum@aep.com 918-599-2674 | 2814 | 2024-05-31 |  | 69 | 0 | 2.8 | 0 |  | Runnels | Concho | Tier 4 |  |  |  |  | 6338, 6369, 6370, 6372, 6376 | Y | N |  | 0 | 65513 | 6572
43212B | Caymus Capbanks in TNMP West Texas System | Expands Caymus Capacitor bank by 1 block of 20 Mvar. |  | Caymus (Bus #38410) | Caymus (Bus #38410) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07819 | 2024-05-31 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38410 | Y |  |  | 0 | 48414 | 43212
48415B | TransPecos Capbank in TNMP West Texas System | Expands TransPecos Capacitor bank by 1 block of 20 Mvar. |  | TransPecos (Bus #38377) | TransPecos (Bus #38377) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07919 | 2024-05-31 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38377 | Y |  |  | 0 | 48417 | 48415
55572 | Burma to Sterling City: Rebuild 69 kV line | Rehab 69 kV line from Burma to Sterling City |  | Burma | Sterling City | Planned | 1096 - 1274 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 1864 | 2024-05-31 |  | 69 | 0 | 32 | 0 |  | Tom Green | Sterling | Tier 3 | 20RPG021 | 2020-10-01 | 2020-11-01 |  | 6439, 6445, 6460, 61016, 61017, 6435, 6446, 6461, 60411 | Y | N |  | 0 | 55573 | 55572
57910 | Uvalde - West Batesville: Rebuild 138 kV Line | Rebuild the 20.61 mile Uvalde to West Batesville 138 kV line |  | Uvalde | West Batesville | Planned | 1117 - 1295 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3836 | 2024-05-31 |  | 138 | 0 | 20.6 | 0 |  | Uvalde | Zavala | Tier 4 |  |  |  |  | 8234, 8236 | Y | N |  | 0 | 65580 | 57910
66050 | 138 kV Fulshear Distribution Substation | Install Fulshear Distribution Substation to create Ckt.25 FOSTER to Fulshear to Twinwood. |  | Fulshear | FOSTER/Twinwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44750, 44230, 44256, 44860 | Y | N |  | 0 | 66051 | 66050
48816 | Mulberry Creek: Rebuild 345 kV station | Rebuild Mulberry Creek 345 kV station as a 6-breaker ring, replace 345/138 kV autotransformers with two 345/138 kV 450 MVA autotransformers (without LTCs), remove shunt reactors, remove series reactors | Update Contact, Schedule, Cost, Planning Tier, RPG Number, RPG Submittal Date, RPG Acceptance Date | Mulberry Creek |  | Planned | 1015 - 1193 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 2776 | 2024-05-31 01:00 |  | 345 | 0 | 0 | 900 |  | Jones |  | Tier 4 | 21RPG021 | 2021-12-15 | 2022-01-13 |  | 6230, 6231, 6232, 60788, 60789, 1435, 6235, 6287, 6288, 60040 | Y | N |  | 0 | 65536 | 48816
48818 | Ballinger: Replace the 138/69 kV autotransformer | Replace the 138/69 kV autotransformer at Ballinger with a 130 MVA autotransformer | Update Contact and Schedule | Ballinger |  | Planned | 1016 - 1194 | AEP TNC | Shawn Ketcher mlforcum@aep.com 918-599-2674 | 2777 | 2024-05-31 01:00 |  | 138 | 0 | 0 | 130 |  | Runnels |  | Tier 4 |  |  |  |  | 6338, 6340 | Y | N |  | 0 | 65537 | 48818
65719 | Rebuild and reconductor portion of Missouri City to Sienna Ckt.05A as a Hardening upgrade |  |  | Missouri City | Sienna | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 12:00 |  | 138 | 0 | 3.7 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44482, 44652 | Y | N |  | 0 | 65720 | 65719
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures. Kramer Lane (KA) substation will be cut-into this line in 2023 |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2024-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238, 9276 | Y | N |  | Will add the ptoject to the base case. | 8207 | 1031
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0196 | 2024-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 9559 | 2308
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  |  | 5705 | Y | N |  |  | 9835 | 2554
3297 | Tezel Road - New 138kV Substation | Loop new 138 kV substation into the existing 138 kV Helotes to Bandera line. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2024-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5421, 5020, 5200 | Y |  |  | There are no transformers associated with this project | 10840 | 3297
6687 | Rebuild Rio Hondo to East Rio Hondo | Rebuild the 138 kV line from Rio Hondo to East Rio Hondo. |  | Rio Hondo | East Rio Hondo | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 138 | 0 | 8.19 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5764, 8319 | Y | N |  |  | 14458 | 6687
45084A | Braunig to Highland Rebuild | Rebuild approximately six circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Highland Hills to Schillers Tap'. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0194, T-0238 | 2024-06-01 |  | 138 | 0 | 6 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  | 0 | 45085 | 45084
45084B | Braunig to Highland Rebuild | Rebuild approximately sixteen circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Schillers Tap to Braunig'. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0194, T-0238 | 2024-06-01 |  | 138 | 0 | 16 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  | 0 | 45086 | 45084
45125 | Quintana Rd to South San Rebuild | Rebuild 1.3 miles of 138 kV transmission line form Quintana Rd substation to South San substation. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0271 | 2024-06-01 |  | 138 | 0 | 1.29 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-15 |  |  | 5350, 5385 | Y |  |  | 0 | 45126 | 45125
13TPIT0070 | Nash Creek Substation | Replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-06-28 |  | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7596 | Y | N |  |  | 10678 | 3322
3774 | Olinger-Ben Davis Line Upgrade | Olinger to Ben Davis 138 kV line upgrade to Cumberland conductor |  | Olinger | Ben Davis | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2024-07-01 |  | 138 | 0 | 17.25 | 0 |  | Collin | Dallas | Tier 4 |  |  |  |  | 818, 968 | Y | N |  |  | 11194 | 3774
5430Q | Conversion to 138kV | Retire the existing 69kV RD Wells substation together with the autotransformers |  | RD Wells |  | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 932, 930 | Y | N | N/A | 0 | 55211 | 5430
5430M | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line |  | Eagle |  | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 926, 924 | Y | N | N/A | 0 | 55207 | 5430
5430N | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line |  | Eagle |  | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 926 | Y | N | N/A | 0 | 55208 | 5430
5430O | Conversion to 138kV | Reconnect the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 930 | Y | N | N/A | 0 | 55209 | 5430
5430P | Conversion to 138kV | Transfer the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 910, 932 | Y | N | N/A | 0 | 55210 | 5430
64856 | LRGV ETT Second Circuit | Hang 63.38 miles of conductor between Lobo and San Miguel. Hang 55.98 miles of conductor between Cenizo and Del Sol. Hang 11.48 miles of conductor between Del Sol and Pomelo. Hang 26.54 miles of conductor between North Edinburg and Pomelo. Hang 47.86 miles of conductor between North Edinburg and Palmito. Add (2) 345 kV terminals at Lobo: one for Del Sol and one for N. Edinburg. Add (2) terminals at Lobo: one for Fowlerton and one for Molina. Add (1) terminal at Cenizo for Lobo. Add (2) terminals at N. Edinburg: one for Pomelo and one for Palmito. Retire the 138 kV Lobo terminal at Molina. Convert Lobo to Molina 138 kV to 345 kV. Construct (3) 345 kV 3-breaker ring bus stations: Tiempo, Rapido, and Pronto. |  | San Miguel | Palmito | Planned |  | ETT/STEC, SHARYLAND | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021701 TP2021702 TP2021703 TP2021704 TP2021705 TP2021706 TP2021707 TP2021708 | 2024-07-23 |  | 345 | 293.98 | 0 | 0 |  | Atascosa | Cameron | Tier 1 |  |  |  |  | 80224, 80226, 80227, 80231, 80381, 5901, 8383, 8574, 80219, 80220, 80221, 80355, 5709, 79500, 80230, 160885, 161855, 162499 | Y | Y |  | 0 | 65263 | 64856
66122 | Tiempo: Build new 345 kV terminalInterconnect Redonda Solar to the Tiempo 345 kV station | ETT will construct and own a dead-end structure to serve as the point of interconnection (POI) and also construct a 345 kV terminal at the Tiempo station to accommodate a single line span to the dead-end structure POI outside Tiempo. |  | Tiempo |  | Planned |  | ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022009 | 2024-07-23 |  | 345 | 0.1 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 80232, 80224 | Y |  |  | 0 | 66511 | 66122
64042 | Barrilla Junction: 69 kV Loop Rebuild | Rebuild Barrilla Junction to Saragosa to Cherry Creek to Verhalen to Hoefs Road stations, convert to 138 kV | Update Schedule, RPG Number, RPG Submittal Date, and RPG Acceptance Date | Barrilla Junction | Hoefs Road Station | Planned | 1141 - 1319 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1886 | 2024-07-31 |  | 69 | 0 |  | 0 |  | Pecos | Reeves | Tier 3 | 21RPG023 | 2021-12-17 | 2022-01-14 |  | 6649, 6650, 6651, 6652, 6654, 60206, 60207, 60208, 60808, 6653, 60385, 60716, 69023, 69047 | Y | N |  | 0 | 64043 | 64042
61232 | RGEC Persimmon Gap Substation 69-kV Transmission Line Extension and Substation Expansion | Extend Alpine-Persimmon Gap 69-kV Transmission Line at Switch# 6669 and Install Circuit Switcher to accommodate new substation power transformer and distribution bays. New power transformer capacity will be 12/16/20 MVA. | Scheduled RUS Construction Work Plan Project | Persimmon Gap | Persimmon Gap | Planned |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2024-08-01 |  | 69 | 0 | 0 | 0 |  | Brewster | Brewster | Tier 4 | [5 empty] | Y | N |  | 0 | 61233 | 61232
52179 | Rising Star Area Conversions | This converts Hasse to Downing to 138 KV |  | Downing | Hasse | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-10-01 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 277, 281, 1649 | Y |  |  | 0 | 52180 | 52179
61396 | Hamilton - Maxwell: Line Rebuild | Hamilton - Maxwell: Line Rebuild |  | Hamilton Road | Maxwell | Planned |  | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2853 | TA2019800 | 2024-10-31 |  | 138 | 0 | 29 | 0 |  | Val Verde | Val Verde | Tier 3 | 20RPG022 | 2020-11-02 | 2021-01-19 |  | 8257, 8998 | Y |  |  | 0 | 65593 | 61396
55617 | Campwood to New Barksdale: Rebuild 69 kV line | Rebuild 69 kV line from Campwood to Rocksprings |  | New Barksdale | Campwood | Planned | 1102 - 1280 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3820 | 2024-11-01 |  | 69 | 0 | 7.73 | 0 |  | Edwards | Edwards | Tier 3 |  |  |  |  | 8633, 8365 | Y |  |  | 0 | 65573 | 55617
61274B | PEC_MarshallFord_Paleface_StormHardening | Rebuild single circuit section of Paleface to Marshal Ford and reconductor with bundled 795 ACSR Conductor, 440 MVA; Reconductor triple circuit section in conjunction with LCRA TSC Storm Hardening project (ERCOT Project #62068) with Single Suwanee Conductor. |  | Paleface | Marshall Ford | Planned |  | PEC/LCRATSC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2024-11-01 |  | 138 | 0 | 11.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7477, 7356 | Y | N |  | 0 | 63833 | 61274
55624 | Escondido to Ganso: Rebuild 138 kV line | Rebuild 138 kV line from Escondido to Hamilton Road |  | Escondido | Ganso | Planned | 1105 - 1283 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3825 | 2024-11-30 |  | 138 | 0 | 10.198 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 8260, 8267 | Y |  |  | 0 | 65575 | 55624
59394 | Pointer to Rule 69 kV Line Rehab | Rebuild 69 kV Line from Pointer to Rule |  | Pointer | Rule | Planned | 1122 - 1300 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1867 | 2024-11-30 |  | 138 | 0 | 14.78 | 0 |  | Haskell | Knox | Tier 4 |  |  |  |  | 6014, 6115, 763, 6120, 60346 | Y | N |  | 0 | 59395 | 59394
61552 | Matador to Turkey: Rebuild 69 kV Line | Rebuild 69 kV line from Matador to Turkey | NEW | Matador | Turkey | Planned | 1128 - 1306 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1873 | 2024-11-30 |  | 69 | 0 | 26.9 | 0 |  | Motley | Hall | Tier 4 |  |  |  |  | 6020, 6044, 6024, 6039, 6041, 6140, 60351 | Y | N |  | 0 | 65596 | 61552
64067 | Bessel to King Ranch 138 kV Line Rebuild | Rebuild the Bessel to King Ranch 138 kV line to address aging infrastructure |  | Bessel | STRATTON | Planned |  | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | TA2020081 | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8498, 8512, 8665, 8060, 8514, 80228 | Y |  |  | 0 | 64068 | 64067
3334 | Fort Sam to Kirby and Fort Sam to Tenth Street MLSE Upgrade | Upgrade entire bus and terminals at Fort Sam and ensure a rating of 2000 A. |  | Fort Sam | Kirby/Tenth Street | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0744 | 2024-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5160, 5250, 5420 | Y | N |  | There are no transformers associated with this project | 10692 | 3334
6685 | Van Vleck substation loop | Replaces single circuit radial line connected to a pole mounted switch with a double circuit transmission loop to the Van Vleck substation and upgrades the 4/0 ACSR to 795 ACSR on 138 kV capable poles. |  | Van Vleck Substation | Van Vleck Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-12-01 |  | 69 | 2 | 2 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5556, 5557, 5558, 5560 | Y | N |  |  | 14456 | 6685
60530 | Rebuild TI-South with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2024-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37080, 37100 | Y |  |  | 0 | 60531 | 60530
66366 | Rebuild Brazoria - Retrieve 138kV with bundled 795 ACSS |  |  | TNMP Brazoria (bus # 39600) | CenterPoint Retrieve (bus # 43170) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2024-12-01 |  | 138 | 0 | 6.17 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39600, 43170 | Y |  |  | 0 | 66367 | 66366
54521 | Hilltop_Weatherford_Rebuild |  |  | Weatherford (1589) | Hilltop (501) | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-12-26 |  | 138 | 0 | 13 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 501, 505, 512, 1589 | Y |  |  | 0 | 54522 | 54521
64065 | Alice to Kingsville 138 kV Line Rebuild | Rebuild the Alice to Kingsville 138 kV line to address aging infrastructure |  | Alice | Kingsville | Planned |  | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | TA2021079 | 2024-12-31 |  | 138 | 22.48 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8503, 8518 | Y |  |  | 0 | 66649 | 64065
61090 | Southeast138kV substation | Establish 138kV Southeast substation with (2) 40MVA transformers and will cut into existing Ckt 1026 (Stoney Ridge to Hi-Cross |  | Stoney Ridge | Hi-Cross |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-01-31 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9240, 9237, 9251 | Y |  |  | 0 | 61091 | 61090
61224 | AEN_Decker_SH_ckt_1008__reconductor | Upgrade the 7.04 mile Decker to Sand Hill 138 kV transmission line (Ckt 1008) with bundled 795 ACSS Drake conductor rated for 3000 amps |  | Decker [9187] | Sandhill [9216] | Planned |  | AEN | Shirley Mathew shirley.mathew@austinener (512) 322-6103 |  | 2025-01-31 |  | 138 | 0 | 7.04 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9187, 9216 | Y |  |  | 0 | 61225 | 61224
52464 | Alamito Creek to Ft. Davis: Rebuild 69 kV line | Rehab Alamito Creek to Ft. Davis 69 kV line | Schedule Update | Alamito Creek | Ft Davis | Planned | 1070 - 1243 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2831 | 2025-02-25 |  | 69 | 0 | 20.5 | 0 |  | Presidio |  | Tier 4 |  |  |  |  | 6676, 6677, 6691, 6678, 6692 | Y | N |  | 0 | 65564 | 52464
61550 | East Munday to Lake Pauline: Rebuild 138 kV Line | Rebuild 138 kV line from East Munday to Lake Pauline |  | East Munday | Lake Pauline | Planned | 1129 - 1307 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1874 | 2025-03-31 |  | 138 | 0 | 59.97 | 0 |  | Knox | Hardeman | Tier 4 | 20RPG018 |  |  |  | 6037, 6050, 6110 | Y | N |  | 0 | 65594 | 61550
64780 | Upgrade 138kV Locust-DMENODE line to 700MVA |  |  | Locust | DMENODE | Planned |  | DENTON | Mark Zimmerer 940-349-7169 |  | 2025-04-01 |  | 138 | 0 | 1.92 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 924, 59000 | Y | N |  | 0 | 64781 | 64780
61268 | Cedar Valley to Friendship Storm Hardening | Rebuild single circuit section of Cedar Valley to Friendship and reconductor with bundled 795 ACSR Conductor, 440 MVA |  | Cedar Valley | Friendship | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2025-04-16 |  | 138 | 0 | 4.3 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7506, 7507 | Y | N |  | 0 | 61269 | 61268
61277 | Lago Vista to Nameless Transmission Line Upgrade | Rebuild and upgrade Lago Vista to Nameless with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA). |  | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2025-04-22 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7352, 7526 | Y | N |  | 0 | 61278 | 61277
59260 | Mason Phillips Tap - Mason Phillips: Rebuild 69 kV Line | Rebuild the Mason Phillips Tap to Mason Phillips 69 kV Line |  | Seaquist | Mason Phillips | Planned | 1127 - 1305 | AEP TNC | David Baker mlforcum@aep.com 918-599-2674 | 1872 | 2025-04-30 |  | 69 | 0 | 13.7 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6395, 6407, 60458 | Y | N |  | 0 | 65588 | 59260
5479 | Trinidad - Tri Corner 345 kV Double-Circuit Line | Upgrade existing DCKT line |  | Trinidad Sw. Sta | TriCorner/Watermill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4045 | 2025-05-15 |  | 345 | 0 | 92.1 | 0 |  | Henderson | Dallas | Tier 3 |  |  |  |  | 2432, 3123, 3124 | Y | N |  |  | 13184 | 5479
62068 | Lakeway-Marble Falls Transmission Line Storm Hardening | Increase the reliability of transmission facilities on the T497 Lakeway ¿ Marble Falls 23-mile 138-kV transmission line. |  | Lakeway | Marble Falls | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Burnet | Tier 4 |  |  |  |  | 7538, 7348 | Y | N |  | 0 | 62069 | 62068
49948 | McCreeShilohLineUpgrades | McCree to Shiloh Line Upgrades to Cumberland |  | McCree | Shiloh | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2025-05-31 |  | 138 | 0 | 2.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 830, 834 | Y | N |  | 0 | 49949 | 49948
58010 | North McAllen: Rebuild 138 kV Station | North McAllen Station Rebuild |  | McAllen |  | Planned | 1118 - 1296 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3837 | 2025-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8368, 8631, 8632 | Y |  |  | 0 | 65583 | 58010
45029 | Grandview Highland Hills Rebuild | CPSE_Rebuild of 138 kV double circuit line Line between Grandview to Highland Hills. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0273 | 2025-06-01 |  | 138 | 0 | 11.6 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-11 |  |  | 5030, 5175, 5095, 5205 | Y |  |  | 0 | 45030 | 45029
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 3000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2025-06-10 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 9723 | 2443
20TPIT0000 | Parkway Substation T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10679 | 3323
65723 | Riedel: Build New Distribution Station |  | IN-SERVICE | Magnolia Tap | Nixon | In-Service | 1032 - 1210 | AEP TCC/LCRA | Brandon Cogan bcogan@aep.com 918-599-2857 | 3771 | 2025-07-01 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  |  | 8583 | Y | Y |  | 0 | 65724 | 65723
63579 | Roby to Rotan: Rebuild 69 kV Line | Rebuild the Roby to Rotan 69 kV Line | NEW | Roby | Rotan | Planned | 1130 - 1308 | AEP TNC | Craig Tabor mlforcum@aep.com 918-599-2674 | 1875 | 2025-08-31 |  | 69 | 0 | 8 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 6194, 6195, 6196 | Y | N |  | 0 | 63580 | 63579
61444 | Wilson South Substation Addition | Add a new load serving substation about 4.35 miles south of La Vernia along FM 775, w/40 MVA PWT |  | Wilson South | Wilson South | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-19 |  | 138 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7629 | Y | N |  | 0 | 61445 | 61444
61446 | Wilson-SS Felps Tap to Wilson South | Build 0.99 miles of new double circuit 138kV t-line loop, 795 ACSR Drake, along FM 775 to Wilson South Substation, about 4.35 miles south of La Vernia |  | Wilson South | Wilson | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-20 |  | 138 | 0.99 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7627, 7628, 5418, 7615, 7629 | Y | N |  | 0 | 61448 | 61446
65154 | Mason Switch to Yellowjacket: Rebuild 69 kV Line | Mason to Yellowjacket 69 kV line rebuild | Update Cost, Tier, RPG Number, RPG Acceptance Date | Mason Switch | Yellowjacket | Planned | 1142 - 1320 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2836 | 2026-01-31 |  | 69 | 0 | 26.45 | 0 |  | Menard | Mason | Tier 4 | 21RPG014 | 2021-08-01 | 2021-09-01 |  | 6363, 6396, 23824 | Y | N |  | 0 | 65155 | 65154
61270 | Friendship to Rutherford Storm Hardening | Rebuild single circuit section of Friendship to Rutherford and reconductor with bundled 795 ACSR Conductor, 440 MVA. |  | Friendship | Rutherford | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2026-04-22 |  | 138 | 0 | 4.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7507, 7509 | Y | N |  | 0 | 61271 | 61270
5981 | Shamburger North 345/138 kV Sw. Sta. | Establish Shamburger North 345/138 kV Sw. Sta. | Project Deferral | Shamburger North | Shamburger North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6083 | 2026-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 3217, 3223, 3226, 2478, 3103, 3201, 3206 | Y | N |  |  | 13696 | 5981
5982 | Relocate existing Shamburger North - Shamburger 138 kV Line | Establish 138 kV Line | Project Deferral | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6084 | 2026-05-15 |  | 138 | 10 | 0 | 0 |  | Smith | Smith | Tier 4 |  |  |  |  | 3104, 3206, 3226 | Y | N |  |  | 13697 | 5982
6304 | Shamburger North - Shamburger 345 kV Line | Upgrade existing 345 kV Line | Project Deferral | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6085 | 2026-05-28 |  | 345 | 10 | 10 | 0 |  | Smith | Smith | Tier 3 |  |  |  |  | 3103, 3223 | Y | N |  |  | 14033 | 6304
52070 | Carver - Maxwell: Line Rebuild | Rebuild Carver to Maxwell 138 kV Line |  | Carver | Maxwell | Planned | 1079 - 1252 | AEP TCC | Charity Kreher bcogan@aep.com 918-599-2853 | 3804 | 2026-05-31 |  | 138 | 0 | 60.24 | 0 |  | Sutton | Val Verde | Tier 3 |  |  |  |  | 8259, 8261, 60412, 8991, 8998, 60440 | Y | N |  | 0 | 65562 | 52070
66101 | Del Sol - Frontera: Build new 345 kV Dbl Circuit Line | Build New 345 kv Double Circuit line from Del Sol to Frontera 345 kV Station | NEW | Del Sol | Frontera | Planned |  | ETT | Charity Kreher bcogan@aep.com 918-599-2857 | TP2020838 | 2026-05-31 |  | 345 | 36 | 0 | 0 |  | Starr | Hidalgo | Tier 1 |  |  | 2021-12-10 |  | 8992, 80119, 8355, 80355, 8980 | Y |  |  | 0 | 66102 | 66101
66386 | Albany to Throckmorton: Rebuild 69 kV line | Rehab 69 kV line from Albany to Throckmorton | NEW | Albany | Throckmorton | Planned |  | AEP TNC | Raza Ansari mlforcum@aep.com 918-599-2674 |  | 2026-05-31 |  | 69 | 0 | 32.36 | 0 |  | Shackelford | Throckmorton | Tier 4 | 21RPG015 | 2022-08-21 | 2022-09-21 |  | 6205, 6206, 6207 | Y | N |  | 0 | 66387 | 66386
1549 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2026-06-01 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 | [5 empty] | Y | N |  |  | 8754 | 1549
15TPIT0031 | Chavaneaux_Chavaneaux Tap Rebuild (Brooks to Chavaneaux ckt) | Rebuild 138 kV transmission from Chavaneaux to Chavaneaux Tap. This rebuild is for Brooks to Chavaneaux ckt. |  | Brooks | Chavaneaux | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0260 | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y |  |  | There are no transformers associated with this project | 9555 | 2304
64858 | La Palma Expansion | Construct 3 Breaker Ring Bus. Construct 345 kV Line from La Palma 345 kV station to Kingfisher 345 kV (Sharyland) station. |  | La Palma | Kingfisher | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021588 | 2026-06-30 |  | 345 | 6.5 | 0 | 0 |  | Cameron | Cameron | Tier 2 |  |  |  |  | 79501, 8317, 8383, 79500, 80137 | Y |  |  | 0 | 65264 | 64858
66023 | T340 T-Line Upgrade | Upgrading the Marion to Sheriff's Posse Transmission Line T340 from 795 ACSR to 959 ACSS conductor. Upgrades to conductor and structures are included. Structures designed for ultimate build-out of double-circuit bundled 959 ACSS in preparation for additional future capacity. |  | Marion | Sheriff's Posse | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2026-07-31 |  | 138 | 0 | 3.4 | 0 |  | Guadalupe | Comal | Tier 4 |  |  |  |  | 7178, 7460 | Y | N |  | 0 | 66024 | 66023
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-11-20 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7622 | Y | N |  |  | 10677 | 3321
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-11-20 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10680 | 3324
55470 | Bison to Ozona: Rebuild 69 kV line | Rehab 69 kV line from Bison to Ozona | Schedule Update | Bison | Ozona | Planned | 1095 - 1273 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1863 | 2026-11-30 |  | 69 | 0 | 27 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  |  | 6549, 6560, 60395 | Y | N |  | 0 | 65570 | 55470
50647 | CPSE_Merida to Westside MLSE | Upgrade terminal at Merida to ensure a 2000 A rating. |  | Merida | Westside | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0773 | 2026-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5490 | Y |  |  | 0 | 50648 | 50647
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-12-18 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7239 | Y | N |  |  | 10694 | 3336
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0733 | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y | Y |  |  | 11872 | 4320
66447 | [5 empty] | Planned |  | AEP TCC/STEC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 80078, 80079, 5901, 8455, 8905, 80076, 80220, 80355 | Y |  |  | 0 | 66449 | 66447
12TPIT0080 | Forney Sw. Sta. Second 600 MVA, 345/138 kV Autotransformer | Add second 345/138 autotransformer | Project Deferral | Forney Sw. Sta. |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4037 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 3 |  | 2008-06-01 | 2008-07-01 |  | 2437, 2438 | Y | N | 2007-R2 |  | 9769 | 2489
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line | Project Deferral | Handley | Hemphill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5214 | 2027-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 11818 | 4270
5522 | Lake Hubbard 345/138 kV Switching Station | Construct new 345/138 kV switching station |  | Lake Hubbard |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4139 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 |  |  |  |  | 12455, 12456, 2401, 2402, 2455 | Y | N |  |  | 13249 | 5522
5525 | Forney - Lake Hubbard 345 kV Line | Construct new 345 kV line |  | Forney | Lake Hubbard | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4233 | 2027-05-15 |  | 345 | 0 | 7.5 | 0 |  | Kaufman | Dallas | Tier 2 |  |  |  |  | 2455, 2467 | Y | N |  |  | 13252 | 5525
5526 | Forney 345 kV Switching Station | Reconstruct existing 345 kV switching station |  | Forney |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4114 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Kaufman |  | Tier 3 |  |  |  |  | 2467, 2433, 2437, 2470, 2478, 150189, 2438, 12438 | Y | N |  | 0 | 49916 | 5526
6287 | Sherry Sw. - Webb/Kennedale 345 kV DCKT Line | Upgrade the existing 345 kV Line |  | Sherry | Webb/Kennedale | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4252 | 2027-05-15 |  | 345 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 3 |  |  |  |  | 1911, 1918, 1930, 1929, 1932, 1934 | Y |  |  |  | 14016 | 6287
5524 | Royse South 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | Royse | Forney | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4234 | 2027-05-15 12:00 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 3 |  |  |  |  | 2469, 2470, 12471, 2437, 2467, 2471, 2478, 2702, 2472, 2474, 2710, 3223 | Y | N |  | 0 | 49918 | 5524
45068 | Merida to Harlandale Rebuild | CPSE_Merida to Harlandale Rebuild |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0233 | 2027-06-05 |  | 138 | 0 | 10 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5310, 5385, 5395 | Y |  |  | 0 | 45069 | 45068
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2027-12-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5626, 5634 | Y | N |  |  | 11275 | 3818
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line | Project Deferral | Cresson | Rocky Creek | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5228 | 2028-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  |  | 1881, 2202 | Y | N |  |  | 12436 | 4834
5436 | Morgan Creek - McDonald 138 kV Line | Upgrade existing line | Project Deferral | Morgan Creek | McDonald Rd | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8360 | 2028-05-15 |  | 138 | 0 | 31.8 | 0 |  | Howard | Mitchell | Tier 3 |  |  |  |  | 1032, 1333 | Y | N |  |  | 13139 | 5436
6777 | Cedar Hill - Liggett 138 kV Line | Loop Cedar Hill - Liggett 138 kV line in to Home Run Substation | Project Deferral | Grand Prairie West | Mayfield Tap | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4270 | 2028-05-15 02:01 |  | 138 | 7 | 0 | 0 |  | Dallas | Tarrant | Tier 4 |  |  |  |  | 2143, 1912, 1919, 2138, 2265 | Y | N |  | 0 | 51988 | 6777
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into future 138kV Martinez to Skyline transmission line |  | Converse | Martinez-Skyline | Planned | T-0177 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0601 | 2028-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5098, 5294, 5368 | Y | N |  | There are no transformers associated with this project | 8143 | 967
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Howard line. |  | Masterson Rd. | Cagnon-Howard | Planned | T-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0538 | 2028-06-01 |  | 138 | 8 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5296, 5054, 5230 | Y | N |  | There are no transformers associated with this project | 9466 | 2218
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0385 | 2028-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5416, 5250, 5395 | Y | N |  | There are no transformers associated with this project | 10365 | 3021
45535 | Valley_to_ValleyTap_Rebuild | Rebuild an approximate four circuits miles of 138 kV Transmission line from Valley Tap to Valley Road substation. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0279 | 2028-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5025, 5053, 5465 | Y |  |  | 0 | 45536 | 45535
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and-or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle-Weiderstein | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0645b | 2028-06-01 12:00 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5360, 5435 | Y | N |  | There are no transformers associated with this project | 9557 | 2306
5889 | MIRAGE - 138kV Substation Removal | Remove 138kV MIRAGE customer-owned substation from CNP service. |  | MIRAGE | MCCABE/BIMONT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42360, 40209, 42351, 40200 | Y | N |  |  | 13606 | 5889
6666 | BRYN_6666_Steele_Store_to_Cooks_Point | Construct 138kV line from BTU Steele Store to LCRA Cooks Point (Bundled 1033 ACSR - Curlew) |  | 32852 | 7569 | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-12-31 |  | 138 | 6 | 0 | 0 |  | Brazos | Burleson | Tier 4 |  | 2016-07-07 | 2017-07-07 |  | 32852, 7569 | Y |  |  | 0 | 64750 | 6666
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2030-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 5601, 5600, 5602 | N | N |  |  | 8729 | 1538
2161 | Oaks to Loxley | Build new 138 kV 795 ACSR circuit from Oaks to a new AEP switching station Loxley in the Trumbo to Pleasanton line | Load forecasts have changed since project was RPG approved | Oaks | Loxley | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2030-06-01 |  | 138 | 6 | 0 | 0 |  | Atascosa | Atascosa | Tier 3 |  | 2011-12-16 | 2012-04-25 |  | 5713, 80491 | N | N |  | This new line was part of Karnes Electric Cooperative Project that was approved in 2012. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 9408 | 2161
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits, as recommended in 2013 RTP. |  | Bevo | Carrizo Springs | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2030-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 1 |  | 2012-04-12 | 2012-08-12 | 2012-09-12 | 5871, 8244 | N | N |  | This new line was part of Karnes and Medina Electric Cooperatives Project that was approved in 2012. This also helped voltage on AEP transmission under contingencies. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 10984 | 3595
3822 | San Miguel to Sigmor 138 kV line upgrade | Upgrade San Miguel to Sigmor 138 kV line as recommended in 2013 RTP. Will investigate re-conductoring on existing structures with ACCC and other high temperature conductors. |  | San Miguel | Sigmor | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2030-06-01 |  | 138 | 0 | 26.3 | 0 |  | Atascosa | Live Oak | Tier 3 |  |  |  |  | 5689, 5902, 8404 | N | N |  | Studies after the 2013 RTP have shown that AEP's approved project to rebuild the 69 kV Beeville to Three Rivers to 138 kV, TPIT 5166, reduces the loading on this line. STEC believes that rebuilding San Miguel to Sigmor is likely to be justified in the future by load growth and or generation additions. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 11279 | 3822
5220 | Move Orange Grove load to 138 kV bus | Move load from the 69 KV to the 138 KV instead of replacing auto. 2015 RTP |  | Orange Grove |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 5660 | N | N |  |  | 12887 | 5220
4084 | Barton-Vega: Upgrade Ckt 928 | Reconductor to 2000 amps |  | Barton | Vega | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2030-08-01 |  | 138 | 0 | 4.05 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9158, 9285 | Y |  |  |  | 11609 | 4084
4425 | New TR-AW Ckt 1032 AW-MR Ckt 1039 MR-JV Ckt 961 | Old Description in Planbook Add 2nd Ckt from TR to HL to tie-in to HL-JV Ckt 1032 (part of old CKT 961), bypassing HL and creating TR-AW-MR-JV Ckt. New description Ckt 1032 from TR-AW, Ckt 1039 from MR-AW and CKT 961 from MR - JV |  | Techridge 9190 AshtonWoods 9224 | AshtonWoods 9226 Jollyville 9223 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2030-08-01 |  | 138 | 1.7 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9190, 9223, 9230, 9224, 9226, 9231 | Y | N |  |  | 11984 | 4425
5763C | CHORIN to STRANG Ckt.87 | STRANG to Cedar Bayou Ckt.87 |  | STRANG | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40010, 41500 | Y | N |  | 0 | 45414 | 5763

## CompletedTPIT020122NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2022
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
45340 | Lemay: Build 138 kV Box Bay | Lemay: Build 138 kV Box Bay on North Laredo SS - Reveille Line |  | Lemay |  | In-Service | 988 - 1166 | AEP TCC | William Lovelace bcogan@aep.com 918-599-2857 | 3739 | 2021-01-26 | 2021-02-23 | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  |  | 8627, 88627, 8612, 8619 | Y | N |  | 0 | 45341 | 45340
5356 | Bakersfield: Build 345 kV terminal | Interconnect Maplewood solar farm at Bakersfield | IN-SERVICE | Bakersfield |  | In-Service | 780 - 0965 | ETT | Greg Crane mlforcum@aep.com 918-599-2674 | 2640 | 2021-01-26 | 2021-01-26 | 345 | 2.35 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 76002, 135327 | Y | N |  |  | 13042 | 5356
3877 | Meadow Lake Substation Addtion | Add a new load serving substation (ring-bus) at Meadow Lake. The station will be built between Cushman and Highway 123 off T572. | Customer Schedule Change | Cushman | Highway 123 | In-Service |  | LCRATSC/GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1016198 | 2021-01-28 | 2020-12-18 | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7720, 7221, 7226 | Y | N |  |  | 12940 | 3877
55596 | Clear Crossing: Install 345 kV terminal | Install 345 kV terminal at Clear Crossing to interconnect Azure Sky Solar & BESS | IN-SERVICE | Clear Crossing |  | In-Service | 1097 - 1275 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 1865 | 2021-01-28 | 2021-01-28 | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60464, 60514 | Y | N |  | 0 | 57651 | 55596
7028 | Ft. Stockton SW to Rio Pecos: Rebuild 69 kV line | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138 kV, reterminate into Solstice, install 138 kV capacitor bank at Solstice, and build new Ft. Stockton Switch 138 kV station | IN-SERVICE | Fort Stockton Switch | Rio Pecos | In-Service | 908 - 1086 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 2733 | 2021-01-30 | 2021-01-30 | 138 | 0 | 0.42 | 0 |  | Pecos | Pecos | Tier 3 | 17RPG018 | 2017-12-22 | 2018-02-02 |  | 6641, 6642, 6643, 38470, 60717, 60718, 60720, 60798, 6598, 6601, 6645 | Y | N |  | 0 | 65517 | 7028
6780 | Deen 138 kV Switching Station | Rebuild existing Saginaw 138 kV Switching Station |  | Deen |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5277 | 2021-01-31 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 1957, 2074, 2043, 2047, 2048, 2049, 2067, 2070, 2071, 2077, 2146, 2157 | Y |  |  | 0 | 57900 | 6780
6753 | Quihi: Build 138kV Station | Build new Quihi 138kV In and Out Station on Razorback to Castroville 138kV Line |  | Quihi |  | Planned | 900 -1078 | ETT/STEC | James Weaver bcogan@aep.com 918-599-2857 | 3684 | 2021-01-31 |  | 138 | 0.8 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  |  | 8248, 88248, 5083, 8241 | Y | Y |  |  | 14546 | 6753
50450 | LCRATSC_Escobares Substation Addition | Construct a new 138-kV Escobares substation.The Escobares substation will be located approximately 2 miles east of Roma (AEP) Substation and approximately 3.5 miles west of Garceno (AEP) Substation. |  | Escobares | Escobares | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-02-04 |  | 138 | 0 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  |  | 7870, 8796, 8923 | Y | N |  | 0 | 50451 | 50450
50342 | Rebuild Shropshire to Saltdome | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment |  | Saltdome | Shropshire | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-02-13 | 2021-02-09 | 69 | 0 | 5.4 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5551, 5555 | Y | N |  | 0 | 50343 | 50342
6019 | North Main - Denton Ave/Springdale Loop | Establish Northmain - Springdale Loop 138 kV line |  | North Main | Springdale | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5240 | 2021-02-15 |  | 138 | 0 | 4.6 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1965, 2102, 2148, 2156, 3010, 2092, 2099, 2101, 2157, 1961, 2146 | Y | N |  | 0 | 52337 | 6019
44485 | Pig Creek: Build 138 kV terminal | Interconnect 138 kV line to Tar Bush | IN-SERVICE | Pig Creek |  | In-Service | 938 - 1116 | AEP TNC | Dave Baker mlforcum@aep.com 918-599-2674 | 2751 | 2021-02-21 | 2021-02-21 | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60393, 60436, 60385 | Y | N |  | 0 | 44486 | 44485
48802 | Gillet: Build New Distribution Station | Gillet: Build New Distribution Station | IN-SERVICE | Magnolia Tap | Nixon | In-Service | 1032 - 1210 | AEP TCC/LCRA | Brandon Cogan bcogan@aep.com 918-599-2857 | 3771 | 2021-02-25 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  |  | 8583 | Y | Y |  | 0 | 48803 | 48802
6345 | Yellowjckt to Menard Phillips T 69 kV line: Rebld 69 kV line | Rehab Yellowjacket to Menard Phillips Tap 69 kV line | IN-SERVICE | Yellowjacket | Menard Phillips Tap | In-Service | 786 - 0971 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2711 | 2021-02-28 | 2021-02-28 | 69 | 0 | 15.3 | 0 |  | Menard | Kimble | Tier 4 |  |  |  |  | 6363, 6401 | Y | N |  |  | 14089 | 6345
7129 | DeCordova 345/138kV_Sw. | Rebuild existing switching DeCordova station |  | DeCordova |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5066 | 2021-02-28 |  | 345 | 0 | 0 | 0 |  | Hood |  | Tier 3 | 20RPG006 | 2020-05-05 | 2020-05-29 |  | 1888, 1890, 1891, 2285, 2888, 11890, 11891, 12288, 1873, 1877, 1887, 2277, 2278, 2281, 1895, 150721, 150722, 150723, 150724 | Y | N |  | 0 | 61389 | 7129
52365D | Spillman Island Restoration Plan | Upgrade Relays at QUANUM substation on QUANUM to WALKER to Cedar Bayou Ckt.85A (Future Option 3 to reconfigure as Ckt.xx QUANUM-WALKER-Alexander Island-SRB). |  | QUANUM | WALKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41330, 41440 | Y | N |  | Cost included in Phase A. | 52369 | 52365
52376 | MARICK (MCK) 138kV Customer Substation | MARICK (MCK) 138kV customer substation looped into Ckt.60A Orchard/Rosenberg |  | Orchard | Rosenberg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44520, 44540, 44615 | Y | N |  | 0 | 52377 | 52376
43454 | Gable Street Reconfigurations | Add 69kV breaker at Gable Street to mitigate P2 contingency load loss |  | Gable Street | Gable Street | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47640 | Y |  |  | 0 | 51311 | 43454
43284F | Baytown Area Upgrades | Upgrade Ckt.87 TEXAS to Cedar Bayou tap to increase thermal ratings |  | TEXAS | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 3.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40011, 40015, 41540 | Y | N |  | 0 | 56061 | 43284
6573 | Reconductor Dunlavey to Heights Ckt. 31 | Reconductor the Dunlavy to Heights as identified in the 2015 RTP case |  | Dunlavy | Heights | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 69 | 0 | 2.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47581, 47682, 47580, 47680 | Y | N |  | 0 | 50777 | 6573
52365F | Spillman Island Restoration Plan | Upgrade Relays at Cedar Bayou substation on Cedar Bayou-WALKER-QUANUM Ckt.85A. |  | Cedar Bayou | Quanum | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 02:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40010, 41440 | Y | N |  | Cost Included in Phase A. | 52372 | 52365
52284 | This adds a capacitor to Bell County |  |  | BellCounty | BellCounty | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2021-03-01 |  | 69 | 0 | 0 | 0 | 0,16 | Bell | Bell | Tier 4 |  |  |  |  | 133 | Y |  |  | 0 | 52285 | 52284
6255B | Rebuild BEVO to Brundage to Big Wells 69 kV lines. | Rebuild 69 kV line with 795 ACSR on 138 kV and double circuit capable structures 2015- NERC assessment |  | BEVO | Brundage | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-03-13 | 2021-05-07 | 69 | 0 | 7.3 | 0 |  | Dimmit | Dimmit | Tier 4 |  |  |  |  | 5870, 5871 | Y | N |  | 0 | 45067 | 6255
57957 | Construct Copperhead 138 kV Switch | Construct Copperhead 138 kV Switch for new solar interconnection |  | Copperhead Switch |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5288 | 2021-03-15 01:00 |  | 138 | 0 | 0 | 0 |  | Fannin |  | Tier 4 |  |  |  |  | 11809, 1808, 11808, 143424 | Y | N |  | 0 | 57958 | 57957
4488 | Campwood to Uvalde: Rebuild 69 kV line | Rebuild Campwood to Uvalde 69 kV line, built to 138 kV, but energized at 69 kV. |  | Campwood | Uvalde | In-Service | 707 - 0877 | AEP | Terry Weeks bcogan@aep.com 918-599-2857 | 2901 | 2021-03-16 | 2021-05-21 | 138 | 0 | 37.1 | 0 |  | Real | Uvalde | Tier 3 | 17RPG001 | 2017-01-17 | 2017-03-20 | 2017-03-20 | 8230, 8633, 8231 | Y | N |  |  | 12057 | 4488
50344 | Rebuild MarkhamTap to Shropshire | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment and 2019 RTP |  | Markham Tap | Shropshire | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-03-20 | 2021-04-12 | 69 | 0 | 1.87 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5554, 5555 | Y | N |  | 0 | 50345 | 50344
56581 | Kimbro Substation Addition | Provide transmission service to a generator by cutting -in a new substation between the LCRA TSC Gilleland Creek Substation and Oncor Elgin Switch. This is related to ERCOT Generation Interconnection or Change Request No. 15INR0090. |  | Kimbro |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017433 | 2021-03-20 | 2021-02-26 | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7337, 3650, 7336 | Y |  |  | 0 | 56582 | 56581
5024 | Crane Loop: Rebuild 69 kV line | Rebuild Crane Loop 69 kV line | IN-SERVICE | Crane | Crane | In-Service | 738 - 0921 | AEP TNC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | 2619 | 2021-03-22 | 2021-03-22 | 69 | 0 | 8.05 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 6600, 6603, 6607, 6609, 6606, 6608, 6613 | Y | N |  |  | 12661 | 5024
5205 | Carrizo Springs-Crystal City 69 kV Line: Rebuild | Rebuild Carrizo Spring to Crystal City 69 kV Line |  | Carrizo Springs | Crystal City | In-Service | 761-0945 | AEP | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3569 | 2021-03-24 | 2021-05-11 | 69 | 0 | 13.9 | 0 |  | Dimmit | Zavala | Tier 3 | 17RPG013 | 2017-07-12 | 2017-08-07 | 2017-08-21 | 8244, 8242 | Y | N |  |  | 12864 | 5205
49548 | Esperanza: Construct New 138 kV Station | Esperanza: Construct New 138 kV Station | Update Schedule | Esperanza |  | In-Service | 993 - 1171 | AEP | James Nivens bcogan@aep.com 918-599-2857 | 3742 | 2021-03-24 | 2021-03-31 | 138 | 0.6 | 0 | 0 | 0,46.6 | Matagorda |  | Tier 4 |  |  |  |  | 8191, 8116, 8558 | Y | N |  | 0 | 49549 | 49548
6121 | Sunchase to South Padre: Build new 138 kV Line | Rebuild Sunchase - South Padre Island 138 kV Line | IN-SERVICE | Sunchase | South Padre Island | In-Service | 826 - 1010 | AEP TCC | Kenneth Haley bcogan@aep.com 918-599-2857 | 3625 | 2021-03-24 | 2021-03-24 | 138 | 0 | 3.33 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8335, 8917 | Y | N |  | 0 | 65503 | 6121
6118 | Port Isabel - Causeway 138 kV Line | Rehab Port Isabel - Causeway 138 kV Line |  | Port Isabel | Causeway | In-Service | 826 - 1010 | AEP | Kenneth Haley bcogan@aep.com 918-599-2857 | 3626 | 2021-03-24 | 2020-07-30 | 138 | 0 | 6.74 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  |  | 13844 | 6118
44395 | Dupont SW: Connect 138 kV Gen Tie Line | Connect 138 kV Victoria Port Generation Tie Line into Dupont SW |  | Dupont SW | Rupley | In-Service | 950 - 1128 | AEP TCC | Tommy Vannoy bcogan@aep.com 918-599-2857 | 3714 | 2021-03-30 | 2021-03-23 | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 88142, 88143, 8143, 8172, 111343 | Y | N |  | 0 | 44396 | 44395
44858 | Luna 138 kV Station | Rayos Del Sol Solar interconnection |  | Mesquite | STEC Rangerville | In-Service | 964 - 1142 | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | 3722 | 2021-03-31 | 2021-06-04 | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8656, 88656, 8554, 80103 | Y | N |  | 0 | 44859 | 44858
44393 | Zapata: Add 138 kV Reactor | Add 138 kV Reactor at Zapata |  | Zapata |  | In-Service | 949 - 1127 | ETT | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3713 | 2021-03-31 | 2021-11-19 | 138 | 0 | 0 | 0 | -10,0 | Zapata |  | Tier 4 |  |  |  |  | 8299 | Y | N |  | 0 | 44394 | 44393
55959 | Crosby to Highlands Ckt.08G Upgrades | Upgrade Crosby to Highlands Ckt.08G as a clearance project |  | Crosby | Highlands | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-03-31 | 2021-01-21 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40390, 40811 | Y | N |  | 0 | 55960 | 55959
55270 | Stillman: Reterminate two AEP 138 kV lines | Stillman: Reterminate two AEP 138 kV lines |  | PUB Loma Alto | Stillman | In-Service | 1036 - 1214 | AEP TCC | William Loveless bcogan@aep.com 918-599-2698 | 3775 | 2021-03-31 | 2021-10-20 | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 8333, 8337, 79601 | Y | Y |  | 0 | 55271 | 55270
50336 | Rebuild Pleasanton to Mccoy | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment and 2019 RTP |  | Pleasanton | McCoy | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-04-01 | 2021-04-21 | 69 | 0 | 10.9 | 0 |  | Atascosa | Atascosa | Tier 4 |  |  |  |  | 5714, 5721 | Y | N |  | 0 | 50337 | 50336
57081 | Elara 138 bus and line to Palo Duro | Adds new Elara station to connect Elara Solar plant and a line to Palo Duro |  | Palo Duro | Elara | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-04-01 | 2021-06-01 | 138 | 2.77 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5890, 5866 | Y | N |  | 0 | 57082 | 57081
6978 | Ranch Road 12 Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Ranch Road 12 Substation. |  | Ranch Road 12 |  | In-Service | 1018923 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018923 | 2021-04-02 | 2021-04-01 | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7186 | Y | N |  |  | 14795 | 6978
6382 | Stewart Road: Construct 345 kV cut-in | Hairpin the North Edinburg to SU Palmito 345 kV line into new Stewart Rd 345 station. The hairpin will be constructed in a double circuit configuration, approximately 5 miles long. |  | Stewart Road | North Edinburg, SU Palmito | In-Service | 874 - 1052 | ETT | Teresea Trotman bcogan@aep.com 918-599-2857 | 3661 | 2021-04-02 | 2021-10-18 | 345 | 5 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 2 | 15RPG016 | 2015-07-10 | 2016-05-19 | 2016-06-14 | 80137, 5966, 8383, 79500 | Y | N |  |  | 14126 | 6382
65721 | Updated Effective Date | These lines will be energized on the updated effective date. |  | 5945059410 | 79601 |  |  | BPUB | Javier Martinez jamartinez@brownsville-pub.com 956-083-6530 |  | 2021-04-04 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 59410, 59450, 79601 | Y |  |  | 0 | 65722 | 65721
6201 | Alice - North Ella 69 kV Line | Rehab Alice - North Ella 69 kV Line |  | Alice | North Ella | In-Service | 818 - 1002 | AEP | Joe Yeagler bcogan@aep.com 918-599-2857 | 3614 | 2021-04-07 | 2021-04-30 | 69 | 0 | 11.56 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 8500, 8878 | Y | N |  |  | 13926 | 6201
57731A | Hornsby Substation Addition | Cut-in a temporary 138-kV single-bus/single-breaker substation to the Austin Energy-owned Decker to Sand Hill 138-kV transmission line to initially serve the load via two modular stations, one mobile transformer and 24.9-kV bus work. | For total project cost please see 57731B | Decker | Sand Hill | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-04-15 | 2021-04-15 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7916, 9187, 9216 | Y | N |  | 0 | 57732 | 57731
50340 | Rebuild Markham Tap to Van Vleck Sw | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment and 2019 RTP |  | Markham Tap | Van Vleck Switch | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-04-15 | 2021-04-12 | 69 | 0 | 4.65 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5554, 5556 | Y | N |  | 0 | 50341 | 50340
7077 | Horse Crossing - Rio Pecos Transmission Line Addition | Construct a new 138-kV transmission line to a new radially connected generator-serving substation called Horse Crossing from Rio Pecos using double 795 26/7 ACSR Drake OPGW static. The planned transmission circuit rating will be (MVA): Rate A=439, Rate B=448, Rate C=448. |  | Horse Crossing | Rio Pecos | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018600 | 2021-04-16 | 2021-06-01 | 138 | 0.9 | 0 | 0 |  | Crane | Crockett | Tier 4 |  |  |  |  | 76601, 76602, 6601 | Y | N |  |  | 14909 | 7077
45506 | Coulomb: Build 345 kV terminal | Interconnect TG East wind farm on the Clear Crossing to Edith Clarke 345 kV line | IN-SERVICE | Coulomb |  | In-Service | 980 - 1158 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 2821 | 2021-04-20 01:00 | 2021-04-20 | 345 | 0 | 0 | 0 |  | Hardeman |  | Tier 4 |  |  |  |  | 60722 | Y | N |  | 0 | 45507 | 45506
51041 | Rio Pecos: Add bus breakers and bus differential | Add 138 kV bus tie circuit breakers | IN-SERVICE | Rio Pecos |  | In-Service | 1043 - 1216 | AEP TNC | Thomas Neils mlforcum@aep.com 918-599-2674 | 2790 | 2021-04-21 | 2021-04-21 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60452, 60453, 6601, 60014, 76595, 76600, 76615 | Y | N |  | 0 | 51042 | 51041
54436 | Kent Street Substation Upgrade | LCRA TSC will remove the capacitor bank at the Buttercup Substation, and add a new capacitor bank to the Kent Street Substation. |  | Kent Street |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-04-22 | 2021-04-29 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7530, 7531 | Y | N |  | 0 | 54437 | 54436
47432 | LULING - ZORN Transmission Line OverHaul | Increase the reliability of transmission facilities on the T158 Luling - Zorn 28.3-mile 138-kV transmission line. Increase the reliability and capacity of transmission facilities on the T158 Luling - Zorn 28.3-mile 138-kV transmission line. Tear down and rebuild all existing wood structures on the SC section from Seguin split to Luling and replace with 795 ACSR Drake conductor. Add OPGW. |  | Luling | Zorn | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-04-28 | 2021-05-06 | 138 | 0 | 0 | 0 |  | Caldwell | Guadalupe | Tier 4 |  |  |  |  | 7180, 7222, 7224 | Y | N |  | 0 | 47433 | 47432
5218B | San Miguel 345/138 kV autotransformer replacements | Replace T2 300 MVA autos with much larger autos |  | San Miguel |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-04-30 | 2021-05-05 | 345 | 0 | 0 | 675 |  | Atascosa |  | Tier 4 |  |  |  |  | 5909, 5901, 5902 | Y | N |  | Delayed from 2018 to 2019 in the 2016 RTP. | 45091 | 5218
6202 | North Ella - Premont 69 kV Line | Rehab North Ella - Premont 69 kV Line |  | North Ella | Premont | In-Service | 818 - 1002 | AEP TCC | Joe Yeagler bcogan@aep.com 918-599-2857 | 3615 | 2021-04-30 | 2020-12-15 | 69 | 0 | 10.7 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 8878, 8894 | Y | N |  |  | 13927 | 6202
54115 | Lockhart Circuit Breaker Addition | Increase transmission service reliability to the Lockhart Substation. LCRA TSC will install two (2) 4000-A circuit breakers and associated terminal equipment such that Lockhart T2 has breakered connections to both 138-kV operating buses. |  |  |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-04-30 | 2021-05-05 | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7216 | Y | N |  | 0 | 54116 | 54115
48784 | Rowe: Construct New Distribution Station | Rowe: Construct New Distribution Station |  | North McAllen | West McAllen | Planned | 1030 - 1208 | AEP TCC | Alison Scribailo bcogan@aep.com 918-599-2857 | 3769 | 2021-04-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8041, 8367, 8631 | Y | N |  | 0 | 48785 | 48784
54086 | Fort Mason Circuit Breaker Addition | Provide transmission service to a generator. Upgrade 138-kV ring bus to accommodate new circuit termination. ERCOT Generation Interconnection or Change Request No. 21INR0365. |  | Fort Mason Substation | Fort Mason Substation | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-04-30 | 2021-04-30 | 138 | 0 | 0 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 76390 | Y | N |  | 0 | 54087 | 54086
57752 | West Columbia Roughneck Storage (19INR0176) | Install generator lead from CNP West Columbia substation to customer NORTCO substation for interconnection to Roughneck Battery Storage (19INR0176) |  | West Columbia |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-04-30 | 2021-08-11 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 120321, 120322, 43380 | Y | N |  | 0 | 57753 | 57752
44426 | Foxtail: Add 345 kV reactor | Add new 345 kV reactor at Foxtail | IN-SERVICE | Foxtail |  | In-Service | 940 - 1118 | AEP TNC | Todd Siegert mlforcum@aep.com 918-599-2674 | 2754 | 2021-04-30 01:00 | 2021-04-30 | 345 | 0 | 0 | 0 | -50,0 | Baylor |  | Tier 4 |  |  |  |  | 6076 | Y | N |  | 0 | 44427 | 44426
51744 | Buda Bus Upgrade | Upgrade the Buda bus from operate/transfer to breaker-and-a-half |  | Buda |  | In-Service |  | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 |  | 2021-05-01 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7498 | Y | N |  | 0 | 51752 | 51744
61908 | GSEC_539_Modify_Buses_Loads.prj | [6 empty] | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2021-05-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 9486 | Y |  |  | 0 | 61909 | 61908
61905 | GSEC_539_Modify_Buses_Loads.prj | [6 empty] | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2021-05-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 9483 | Y |  |  | 0 | 61906 | 61905
51216D | Ward Winkler RPG | Re-conductor TNMP Wink - Oncor Wink 138kV line. Convert existing TNMP Wink - Oncor Wink 69kV line to 138kV. |  | TNMP Wink (37900) | Oncor Wink (1074) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-05-05 |  | 138 | 0 | 2.66 | 0 |  | Winkler | Winkler | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 1074, 1075, 37900, 37920 | Y |  |  | 0 | 56659 | 51216
59585 | Avogadro: Build new 345 kV station | Interconnect Griffin Trail wind farm on the Clear Crossing to Edith Clarke 345 kV line | IN-SERVICE | Avogadro |  | In-Service | 1017 - 1195 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 2778 | 2021-05-06 | 2021-05-06 | 345 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 60506, 60500, 60700 | Y | N |  | 0 | 65590 | 59585
47440 | Rattler Substation Addition | Construct a new load-serving 138-kV substation. Rattler substation will be located on T262 transmission line between Redwood and McCarty Lane. |  | Rattler | Rattler | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-06 | 2021-05-12 | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7184, 7182, 7188 | Y | N |  | 0 | 47441 | 47440
60916 | Lemay: Build 138 kV Box Bay | Lemay: Build 138 kV Box Bay on North Laredo SS - Reveille Line | IN-SERVICE | Lemay |  | In-Service | 988 - 1166 | AEP TCC | William Lovelace bcogan@aep.com 918-599-2857 | 3739 TP2018152 | 2021-05-12 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  |  | 8627, 88627, 8612, 8619 | Y | N |  | 0 | 60917 | 60916
60459 | Rebuild Freeway Park-Mainland with 795 ACSS | Project previously associated with PMCR ID # 54118. NOMCR ID # 66716-1 | [5 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-05-12 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38820, 38830 | Y |  |  | 0 | 60460 | 60459
58540 | Rebuild 16th St - Soaptree | NOMCR ID # 66719-1 |  | TNMP 16th Street (38310) | TNMP Soaptree (38450) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-05-12 |  | 138 | 0 | 31.83 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38310, 38450 | Y |  |  | 0 | 58541 | 58540
49576 | Hayter: Build 138 kV box bay | Construct new 138 kV box bay on the Alamito Creek to Solstcie 138 kV line | IN-SERVICE | Hayter |  | In-Service | 1025 - 1203 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2788 | 2021-05-12 | 2021-05-12 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 6680, 60385, 60444 | Y | N |  | 0 | 49577 | 49576
5457 | Load serving | New station to aid in DME's load serving |  | Brinker |  | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2021-05-14 | 2020-07-01 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 906, 907, 913, 921 | Y | N |  |  | 13160 | 5457
47513 | Pooley Road Circuit Breaker Addition | LCRA TSC will convert Pooley Road Substation to ring bus configuration by installing three 138-kV, 3000A, 40kAIC circuit breakers. |  | Pooley Road Substation | Pooley Road Substation | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-14 | 2021-05-13 | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7222 | Y | N |  | 0 | 47514 | 47513
47034 | Gabriel- Rivery Transmission Line Storm Hardening | Overhaul and upgrade the 138-kV Gabriel - Rivery transmission line with bundled 795 ACSR capable structures, bundled 795 ACSR conductor (440 MVA), and OPGW static. |  | Gabriel | Rivery | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-14 | 2021-05-15 | 138 | 2.4 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7346, 7347 | Y | N |  | 0 | 47035 | 47034
53953 | Eckert - Nebo Transmission Line Overhaul | LCRA TSC will perform an overhaul of T126 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T126 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  | Eckert | Nebo | In-Service |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2021-05-14 | 2021-04-15 | 69 | 0 | 0 | 0 |  | Gillespie | Gillespie | Tier 4 |  |  |  |  | 7122, 7124 | Y | N |  | 0 | 53954 | 53953
54098 | Warda Winchester - Transmission Line Upgrade | Increase the transmission capacity of T170: Warda ¿ Winchester 138-kV transmission circuit. LCRA TSC will upgrade T170: Warda - Winchester transmission line to a minimum 105 degree F ambient temperature rating of 580 MVA at 138-kV using single 1433 Merrimack ACSS conductor with OPGW fiber addition. |  | Warda | Winchester | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-05-14 | 2021-05-14 | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7306, 7312 | Y | N |  | 0 | 54099 | 54098
51228B | Construct Kennedale 138 kV Substation and Burleson 138 kV Sw | Construct Burleson 138 kV Sw |  | Burleson |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5294 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 1967, 1969, 2205, 2209, 12205 | Y |  |  | 0 | 52342 | 51228
57857 | Ennis West Switch 138 kV Reconfiguration | Reconfigure existing 138 kV Switch |  | Ennis West |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4311 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  | 0 | 57858 | 57857
52151 | Upgrade Elkton - Tyler Switch 138 kV Line | Upgrade Elkton - Tyler Switch 138 kV Line |  | Elkton | Tyler | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6079 | 2021-05-15 |  | 138 | 0 | 5.3 | 0 |  | Smith | Smith | Tier 4 |  |  |  |  | 3106, 3107, 3196, 3197 | Y |  |  | 0 | 52152 | 52151
57754 | Install Quinlan Tap 138/69 kV Autotransformer | Install Quinlan Tap 138/69 kV Autotransformer |  | Quinlan Tap |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3058 | 2021-05-15 |  | 138 | 0 | 0 | 47 |  |  |  | Tier 4 |  |  |  |  | 2729, 12729, 12730, 2471, 2472, 2730, 12470 | Y |  |  | 0 | 59517 | 57754
52253 | Wink Switch 138 kV Terminal Addition | Add a 138 kV terminal at Wink Switch |  | Wink | Wink | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8503 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Winkler | Winkler | Tier 4 |  | 2019-03-01 | 2019-09-01 | 2019-10-01 | 1074 | Y |  |  | 0 | 52254 | 52253
52827 | Keller Wall Price 138 kV Capacitor Banks | Upgrade the existing 138 kV capacitor banks at Keller Wall Price |  | Keller Wall Price |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5223 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 2037, 2038 | Y |  |  | 0 | 52828 | 52827
61292 | Thorn Tree Switch | Construct Thorn Tree Switch to interconnect Delilah Solar Generator |  | Thorn Tree |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5315 | 2021-05-15 |  | 345 | 0 | 0 | 0 |  | Franklin |  | Tier 4 |  |  |  |  | 11688, 1685, 1695 | Y | N |  | 0 | 61293 | 61292
52303 | Quarry Field 345/138 kV Switch | Construct a new 345/138 kV Switch |  | Quarry Field | Quarry Field | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8481 | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Loving | Loving | Tier 3 | 20RPG008 | 2020-05-18 | 2020-06-15 |  | 11188, 11194, 11216, 11010, 11084, 11189 | Y |  |  | 0 | 52494 | 52303
47450 | Naruna Circuit Breaker Addition | LCRA TSC will increase the reliability of transmission facilities along T219 Burnet - Lampasas by adding three 138-kV, 3000A, 40kAIC circuit breakers in a ring bus configuration at Naruna Substation. |  | Naruna | Naruna | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-15 | 2020-11-19 | 138 | 0 | 0 | 0 |  | Lampasas | Lampasas | Tier 4 |  |  |  |  | 7063 | Y | N |  | 0 | 47451 | 47450
50338 | Rebuild Van Vleck Sw to Bay City | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment |  | Van Vleck Switch | Bay City | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-05-15 | 2021-04-23 | 69 | 0 | 1.23 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5556, 5560 | Y | N |  | 0 | 50339 | 50338
5408 | Herty N Sw. Sta. 138 kV Rebuild | Rebuild existing 138 kV switching station, it will be named Redland Switch after the completion of the project | Project Deferral | Herty North | Herty North | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6069 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3317, 3319 | Y | N |  |  | 13094 | 5408
47539 | Frelsburg Circuit Breaker Addition | Increase the reliability of transmission facilities on the T176 Fayetteville - Glidden 20.0-mile 138-kV transmission line. LCRA TSC will add three 138-kV, 3000A, 40kAIC circuit breakers in ring-bus configuration next to Frelsburg Substation. |  | Frelsburg Substation | Frelsburg Substation | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-15 | 2021-03-03 | 138 | 0 | 0 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  |  | 7263 | Y | N |  | 0 | 47540 | 47539
6792 | Anna - Anna Tap 138 kV Line | Upgrade existing Anna Switch - Anna Tap 138 kV Line |  | Anna Switch | Anna Tap | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4314 | 2021-05-15 01:00 |  | 138 | 8.3 | 8.3 | 0 |  | Collin | Collin | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 12705, 2340, 2374, 2520, 2528, 2704, 12704 | Y | N |  | 0 | 49821 | 6792
45545 | Norwood Switch - Denton Drive 138 kV DCKT Line | Upgrade the Norwood Switch - Denton Drive 138 kV DCKT Line |  | Norwood Switch | Denton Drive Switch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | m4245 | 2021-05-15 12:00 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2405, 2407, 2488, 2796, 2797, 12487, 2487, 2800, 2801 | Y |  |  | 0 | 45546 | 45545
48822 | Carrollton East - Renner_Northaven Double-circuit Line | Upgrade existing line |  | Carollton East | Alpha Road And Knoll Trail | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4232 | 2021-05-15 12:00 |  | 138 | 0 | 13 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2571, 2575, 2582, 2583, 2584, 2596, 2578, 2598, 2613 | Y | N |  | 0 | 49080 | 48822
45541 | Watermill Switch - Camp Wisdom 138 kV Line | Upgrade the Camp Wisdom - Witt Road 138 kV Line Section |  | Camp Wisdom | Witt Road | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4216 | 2021-05-15 12:00 |  | 138 | 0 | 6.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2988, 2989, 2990, 3068 | Y |  |  | 0 | 52172 | 45541
44511 | Aransas_Pass-Seawall: Rebuild and re-conductor with 795 ACSS | Rebuild and re-conductor Aransas Pass - Seawall with 795 ACSS (2000 A conductor). This will relieve overload seen in the 2025 SSWG Summer Peak case for loss of Naval Base- North Padre. | IN-SERVICE | Aransas Pass | Seawall | Planned | 947 - 1125 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3711 | 2021-05-16 |  | 69 | 0 | 3.2 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8427, 8435 | Y | N |  | 0 | 65521 | 44511
47434 | Zorn Auto Replacement | Increase the reliability of substation equipment at Zorn Substation through replacement of the Zorn AT1 autotransformer. |  | Zorn | Zorn | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-17 | 2021-05-14 | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7042 | Y | N |  | 0 | 47435 | 47434
50672 | Black Cat: New 138 kV Distribution Station | Black Cat: In & Out capable bus with manual bus tie switch for double bank station | IN-SERVICE | Bay City | Conoco | In-Service |  | AEP TCC | Marc Wilson bcogan@aep.com 918-599-2857 |  | 2021-05-19 | 2021-05-12 | 138 | 0 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 80124, 8547, 8549, 8113, 8138 | Y | N |  |  | 50673 | 50672
6789 | Wirtz to Johnson City to Mountain Top Rebuild to 138kV | Rebuild the Wirtz to Johnson City to Mountain Top 69kV Line and convert to 138kV. Convert Johnson City Substation to 138kV. |  | Johnson City | Mountain Top | In-Service |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2021-05-20 |  | 138 | 0 | 25 | 0 |  | Burnet | Blanco | Tier 4 | 17RPG015, 18RPG009 | 2017-10-01 | 2017-12-01 |  | 7104, 7107, 7110, 7514, 7516, 7148, 7480 | Y | N |  | 0 | 51771 | 6789
52181 | ENCO (ENC) 138kV Substation | Install new customer-owned 138kV ENCO (ENC) substation. Loop into existing Ckt.91A between PH Robinson and El Dorado |  | ENCO |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-30 | 2021-08-11 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47780, 42015, 42561, 42860, 43507 | Y | N |  | 0 | 52182 | 52181
6668A | Freeport - Master Plan | Upgrade Ckts. 18 & 27 DOW to Jones Creek to increase thermal limits |  | DOW | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 17RPG005 | 2017-04-04 | 2017-06-05 | 2017-12-12 | 42500, 42530 | Y | N |  | 0 | 64155 | 6668
6325 | Install two distribution transfomers at Jones Creek | Install two distribution transformers at Jones Creek. Tap Ckt.59 Jones Creek to Freeport/Surfside and Ckt.59 Jones Creek to CORTEZ |  | Jones Creek |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-30 | 2021-08-03 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42546, 42547, 48546, 48547, 42540, 42541, 42542, 42645, 43315, 43440, 44205 | Y | N |  | 0 | 64154 | 6325
50670 | Angstrom: Build new 345 kV Station | Build new station on the STP to Whitepoint 345 kV line | IN-SERVICE | Angstrom |  | In-Service | 1050 - 1223 | AEP | Teresa Trotman bcogan@aep.com 918-599-2857 | 3776 | 2021-05-30 | 2021-01-26 | 345 | 0.5 | 0 | 0 |  | San Patricio | Matagorda | Tier 4 |  |  |  |  | 8249, 88249, 5915, 8956 | Y | N |  |  | 50671 | 50670
52519A | Jones Creek Area Reconfigurations | Reconfigure existing Ckt.02H COPPER to Velasco to create new Ckt.36x COPPER to Jones Creek. |  | Copper | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42195, 43211, 43222, 48006, 42199, 42210, 42215, 42540, 43360 | Y | N |  | 0 | 59982 | 52519
5717 | Waller 138kV Substation Reconfiguration | Convert Waller substation from single-circuit radial service to radial & tap service. Install new tap section from Ckt.65 Hockley to Peters. |  | Waller | Hockley/Peters | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 | 2021-08-11 | 138 | 2.4 | 0 | 0 |  | Harris | Austin | Tier 4 |  |  |  |  | 44564, 46564, 46560, 45880, 45885, 46220, 7671, 46511 | Y | N |  |  | 13459 | 5717
52167B | El Dorado 10.8 MVar Cap Bank | Install old harrisburg cap bank at El Dorado (Electrically connected to Ckt.91) |  | El Dorado/Harrisburg |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 | 0,10.8 | Harris |  | Tier 4 |  |  |  |  | 42561 | Y | N |  | 0 | 55385 | 52167
57859 | West Galveston New Distribution Transformer | Install 3rd distribution transformer at West Galveston substation. Tap from Ckt.01B to create new Galveston 26th Street to West Galveston tap to Webster |  | West Galveston | Galveston 26th Street/Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 43403, 42670, 43500, 43400, 43401 | Y | N |  | 0 | 57860 | 57859
55963 | Pearland 40 MVAr Cap Bank | Install Pearland 40 MVAr Cap Bank tapped on Ckt.06K |  | Pearland |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 | 0,40 | Brazoria |  | Tier 4 |  |  |  |  | 42680, 42741, 42742, 47331, 47332, 43051, 43052, 47210, 47340, 47350, 47420 | Y | N |  | 0 | 61647 | 55963
52519B | Jones Creek Area Reconfigurations | Unbundle existing Ckt.02G Velasco to Jones Creek to create parallel circuits Ckt.02G and Ckt.36y Velasco to Jones Creek. This project entry is for Ckt.02G. Existing Jones Creek fixed cap bank #3 will remain on this line with no expected change in capacity. |  | Velasco | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42150, 42540, 42543, 43212, 43360, 42210, 43221, 43363 | Y | N |  | Cost Included in Phase A. | 59984 | 52519
57518A | Wortham 138kV Distribution Substation | New Ckt.21G CAMRON to Wortham tap to TH Wharton. |  | Wortham | CAMRON/TH Wharton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45101, 45515, 45700 | Y | N |  | 0 | 57520 | 57518
57534A | Heights and White Oak Upgrades | Install New 200MVA White Oak 138-69kV Auto A4. |  | White Oak |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 200 |  | Harris |  | Tier 4 |  |  |  |  | 49021, 49098, 46615, 46620 | Y | N |  | 0 | 57535 | 57534
52173 | Spencer 7.2MVar Cap Bank | Install Spencer 7.2MVar Distribution Cap Bank (Electrically connected to Ckt.91) |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 | 0,7.2 | Harris |  | Tier 4 |  |  |  |  | 43272 | Y | N |  | 0 | 52174 | 52173
4186F | University Area 138kV Conversions | Disconnect Ckt.12B and Ckt.30A at University and Reconnect 69kV circuits to create New Ckt.xx GENRAL to Garden Villas |  | Garden Villas | Genral | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2021-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47755, 42690, 42741, 43052, 47560, 47670, 47764, 43322, 47760, 47762 | Y | N |  | Cost included in Phase D | 57373 | 4186
59207 | Missouri City (MC) Distribution Transformer TR1 | Missouri City (MC) 3rd distribution transformer TR1 tapped on Ckt.02A Blueridge tap to Dewalt |  | Missouri City | Blueridge/Dewalt | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Harris | Tier 4 |  |  |  |  | 44481, 44482, 44483, 40010, 44081, 44082, 44180, 44342, 41440, 44652, 44672, 47150 | Y | N |  | 0 | 64153 | 59207
57534B | Heights and White Oak Upgrades | Upgrade Ckt.34A Heights - White Oak |  | Heights | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46620, 47680 | Y | N |  | 0 | 57536 | 57534
52141 | Cedar Bayou 138kV - West Bus In-Series 10-Ohm Reactor | Cedar Bayou 138kV - West Bus In-Series 10-Ohm Reactor |  | Cedar Bayou | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40015, 40020 | Y | N |  | 0 | 52142 | 52141
57514 | Jeanetta Auto A1 Upgrade | Upgrade Jeanetta Auto A1 |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47300, 47310, 49024 | Y | N |  | 0 | 57515 | 57514
43284G | Baytown Area Upgrades | Upgrade Ckt.87 Cedar Bayou to Cedar Bayou tap to increase thermal ratings |  | Cedar Bayou | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 2.39 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40011, 40015 | Y | N |  | Overall cost for 2020 project included in 6585E | 56060 | 43284
52519C | Jones Creek Area Reconfigurations | Unbundle existing Ckt.02G Velasco to Jones Creek to create parallel circuits Ckt.02G and Ckt.36y Velasco to Jones Creek. This project entry is for Ckt.36y. Reconnect existing Jones Creek cap bank #2 to this line position (Should be installed as fixed 120MVAr cap bank #2). Reconnect existing Jones Creek cap bank #1 to the 48JCKCTZ line position at Jones Creek (Should be installed as switched 160MVAr cap bank #1). |  | Velasco | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42541, 42542, 42540, 42546, 42547, 43360 | Y | N |  | Cost included in Phase A. | 59983 | 52519
57642A | Hayes Ckt.09A Loop Upgrade | Upgrade Ckt.09A Britmoore to Hayes to increase thermal limits |  | Britmoore | Hayes | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 | 2021-08-11 | 138 | 0 | 0.1 | 0 |  |  |  | Tier 4 |  |  |  |  | 44120, 44310 | Y | N |  | 0 | 57644 | 57642
52197A | Jordan Auto A3 Addition (PLACID 138kV Sub) | Install 800 MVA Jordan Auto A3 |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-05-31 |  | 345 | 0 | 0 | 800 |  | Chambers | Chambers | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 49079, 40850, 40855 | Y | N |  | 0 | 57345 | 52197
55630 | Lobo: Install 345 kV terminal | Install terminal at Lobo to interconnect Corazon Solar, build 345 kV line from Lobo to Corazon Solar | IN-SERVICE | Lobo | Corazon Solar | In-Service | 1098 - 1214 | ETT | Adam Wells bcogan@aep.com 918-599-2857 | 3775 | 2021-05-31 | 2021-05-09 | 345 | 4.5 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 80599, 80219 | Y | Y |  | 0 | 55631 | 55630
57518B | Wortham 138kV Distribution Substation | New Ckt.76A Gertie tap to Wortham tap to Satsuma tap |  | Wortham | Gertie/Satsuma | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45102, 44900, 44910, 45500, 45610, 45802, 45811, 46301, 46302, 45515, 46312 | Y | N |  | Cost included in main entry | 57519 | 57518
4186D | University Area 138kV Conversions | Remove University Auto A1 from service |  | University |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2021-05-31 |  | 138 | 0 | 0 | 0 | -200,0 | Harris |  | Tier 4 |  |  |  |  | 49030, 47755, 47760 | Y | N |  | Cost included in 4186A | 57371 | 4186
57642B | Hayes Ckt.09A Loop Upgrade | Upgrade Ckt.09A Hayes to Alief to increase thermal limits |  | Hayes | Alief | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 01:00 | 2021-08-11 | 138 | 0 | 0.1 | 0 |  |  |  | Tier 4 |  |  |  |  | 44020, 44671, 44762, 44015, 44310, 44311 | Y | N |  | Cost included in main entry | 57643 | 57642
44944 | Burnet-Bertram-Andice 138kV Conversion | Rebuild Burnet to Bertram to Andice 69 kV line and convert to 138 kV. |  | Burnet | Andice | In-Service |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2021-06-01 |  | 138 | 0 | 21.9 | 0 |  | Burnet | Williamson | Tier 3 |  |  |  |  | 7520, 7521, 7097, 7100, 7522 | Y | N |  | 0 | 51770 | 44944
07TPIT0060 | Howard Lane to Techridge Reconductor | The project re-conductors Circuit 1004 (Techridge to Howard Lane) using 795 ACSS Drake conductors to increase the capacity to 3000 Amp. |  | Howard Lane | Techridge | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P067 PLAN_117_P194 | 2021-06-01 |  | 138 | 0 | 1.72 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9191, 9217 | Y | N |  |  | 8204 | 1028
52245 | CONSTRUCT OGALLALA TO BLACKWATER DRAW 345 KV LINE | REBUILD ABERNATHY SW AND RENAME BLACKWATER DRAW. CONSTRUCT OGALLALA TO BLACKWATER 345 KV LINE, LPL INTEGRATION |  | OGALLALA | BLACKWATER DRAW | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3002, R3003, R3005 | 2021-06-01 |  | 345 | 0 | 0 | 0 |  | Castro | Hale | Tier 1 |  | 2015-12-29 | 2016-06-09 |  | 23920, 23912 | Y |  |  | 0 | 52246 | 52245
08TPIT0033 | Gilleland to Techridge 138kV Circuit | Establish a new 138kV circuit from Gilleland to Techridge and maintain a normally close tie between AEN and LCRA's switchyard at Gilleland. |  | Gilleland Substation | Techridge Substation | In-Service |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_4276 PLAN_117_P207 | 2021-06-01 |  | 138 | 8 | 0 | 0 |  | Travis | Travis | Tier 2 |  |  | 2009-07-21 | 2009-07-21 | 9054, 9191, 7336, 9190 | Y | N |  |  | 8205 | 1029
5417 | Buckeye to LA_HTS Rebuild | Rebuild 1.8 mile 138 kV t-line from Buckeye to LA_Hts. Upgrade line terminal at Buckeye Station for Buckeye to LA_HTS t-line. |  | Buckeye | LA_Hts | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0266, S-0899a | 2021-06-01 |  | 138 | 0 | 1.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5050, 5285 | Y |  |  |  | 13105 | 5417
57052B | Adds Attwater Switching Station for Topaz POI | Attwater-Topaz POI transmission line |  | Attwater (Bus # 38745) | Topaz (Bus # 111971) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-06-01 |  | 138 | 1.03 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38745, 42015, 111971 | Y |  |  | 0 | 57231 | 57052
52258 | CONSTRUCT BLACKWATER DRAW TO FOLSOM POINT345 KV LINE | CONSTRUCT FOLSOM POINT SWITCH AND BLACKWATER DRAW TO FOLSOM POINT 345 KV LINE, LPL INTEGRATION |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3007, R3011 | 2021-06-02 |  | 345 | 23.3 | 0 | 0 |  | Hale | Lubbock | Tier 1 |  | 2015-12-29 | 2016-06-09 |  | 23920, 23926, 59156 | Y |  |  | 0 | 52259 | 52258
5286B | Fayette Area Upgrades | Upgrade existing Plum - Flatonia (T133) TL with a minimum rating of 380 MVA and with OPGW. Upgrade terminal equipment at Plum to achieve a planned static normal and emergency rating of 530 MVA on Piney Creek - Plum (T535). | Planning In-Service Date Change. Updated to a phased project, the original TPIT project number is 5286. | Flatonia | Plum | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1019026, 1019024 | 2021-06-03 | 2021-05-14 | 138 | 0 | 19.6 | 0 |  | Fayette | Fayette | Tier 4 | 17RPG011 | 2017-06-29 | 2017-07-28 |  | 7248, 7274, 7307 | Y | N |  |  | 14584 | 5286
52299 | CONSTRUCT BLACKWATER DRAW TO DOUBLE MOUNTAIN | CONSTRUCT DOUBLE MOUNTAIN SWITCH AND BLACKWATER DRAW TO DOUBLE MOUNTAIN 345 KV LINE, LPL INTEGRATION |  | BLACKWATER DRAW | DOUBLE MOUNTAIN | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3001, R3008 | 2021-06-03 |  | 345 | 33 | 0 | 0 |  | Hale | Lubbock | Tier 1 |  | 2015-12-29 | 2016-06-09 |  | 23920, 23928, 59178 | Y |  |  | 0 | 52300 | 52299
52307 | CONSTRUCT DOUBLE MOUNTAIN TO FIDDLEWOOD TO FARMLAND 345 KV L | CONSTRUCT FIDDLEWOOD SWITCH AND DOUBLE MOUNTAIN TO FIDDLEWOOD TO FARMLAND 345 KV LINE, LPL INTEGRATION |  | DOUBLE MOUNTAIN | FARMLAND | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3004, R3006, R3009, R3010 | 2021-06-04 |  | 345 | 49.3 | 0 | 0 |  | Lubbock | Lynn | Tier 1 |  | 2015-12-29 | 2016-06-09 |  | 23930, 59196 | Y |  |  | 0 | 52308 | 52307
6974 | New Bremen Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at New Bremen Substation. |  | New Bremen |  | In-Service | 1018919 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018919 | 2021-06-04 | 2021-05-14 | 138 | 0 | 0 | 0 |  | Austin |  | Tier 4 |  |  |  |  | 7271, 7270, 7273 | Y | N |  |  | 14791 | 6974
52587 | Fiddlewood 75MVAR Shunt Reactor | Install 75MVAR Reactor |  | Fiddlewood | Fiddlewood | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3017 | 2021-06-05 |  | 345 | 0 | 0 | 0 | -75,0 | Lubbock | Lubbock | Tier 4 |  |  |  |  | 23930 | Y |  |  | 0 | 52588 | 52587
52570 | Double Mountain 75 MVAR Reactor | Install 75 MVAR Reactor |  | Double Mountain | Double Mountain | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3016 | 2021-06-05 |  | 345 | 0 | 0 | 0 | -75,0 | Lubbock | Lubbock | Tier 4 |  |  |  |  | 23928 | Y |  |  | 0 | 52571 | 52570
6984 | Rim Rock - Turtle Creek Transmission Line Storm Hardening | Overhaul and upgrade the 138-kV Rim Rock - Turtle Creek transmission line supporting circuit T270 with single 795 ACSR capable structures, single 795 ACSR conductor, and OPGW static. The planned T270 circuit rating is (MVA): Rate A=220, Rate B=220, Rate C=220. |  | Rim Rock | Turtle Creek | In-Service | 1018968 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018968 | 2021-06-05 |  | 138 | 0 | 7.6 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7143, 7442 | Y | N |  |  | 14801 | 6984
54757 | This is related to GINR20INR0083 | This is a switching station to interconnect new generation project 20INR0083 Baird North Wind Project |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2021-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68008, 68006, 68010 | Y |  |  | 0 | 54758 | 54757
61281 | POI for AJAX Wind Generator | Install a 345 kV point-of-interconnection (POI) for Ajax Wind Generator at Byrd Road 345 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5316 | 2021-06-15 |  | 345 | 0 | 0 | 0 |  | Wichita | Wilbarger | Tier 4 |  |  |  |  | 1415, 1422, 6101 | Y |  |  | 0 | 61282 | 61281
48780 | Pantera: Construct New Distribution Station | Pantera: Construct New Distribution Station | IN-SERVICE | Wesmer | Weslaco SW | In-Service | 1027 - 1205 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3766 | 2021-06-17 | 2021-06-18 | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8033, 8347, 8348 | Y | N |  | 0 | 65535 | 48780
44372 | Geronimo T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Geronimo |  | In-Service |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-06-25 | 2021-07-14 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7606 | Y |  |  | 0 | 44373 | 44372
50452 | LCRATSC_Clear Springs AT1 | Replacing the failed Auto-transformer with like and kind Auto-transformer. |  | Clear Springs | Clear Springs | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-06-30 | 2021-03-31 | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 77683 | Y | N |  | 0 | 50453 | 50452
45573 | Hayter Ranch Substation Addition | Construct a new 138-kV Hayter Ranch substation. The Hayter Ranch Substation will be located on the Alamito Creek to Solstice 138-kV transmission line. The total length of the line is 68.12 miles and the Hayter Ranch substation will be approximately 8.5 miles from Solstice. |  | Alamito Creek | Solstice | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2021-06-30 | 2021-05-28 | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 78925, 60444 | Y | N |  | 0 | 45574 | 45573
5939 | Cooks Point Substation and Transmission Line Addition | Construct a load serving 138-kV substation in Northern Burleson County called Cooks Point. Construct a 16.7-mile single circuit 138-kV transmission line from Lyle Wolz to Cooks Point 138-kV transmission line with bundled 795 ACSR Drake (440 MVA). Bryan Texas Utilities will construct a 138-kV transmission line from Steele Store Substation to Cooks Point bundled 1033 ACSR Curlew (495 MVA). |  | Cooks Point | Lyle Wolz | In-Service | 6666 | LCRATSC/BBEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017348 | 2021-06-30 | 2021-06-30 | 138 | 16.7 | 0 | 0 |  | Burleson | Burleson | Tier 4 | 16RPG011 | 2016-07-07 |  |  | 7569, 7567 | Y | N |  |  | 13650 | 5939
6712 | Soda Lake Substation Addition | Construct a new substation named Soda Lake off the LCRA Crane to Rio Pecos (T451) transmission line to support a generation interconnection request (18INR0040). |  | LCRA Crane | Rio Pecos | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018761 | 2021-06-30 | 2021-06-03 | 138 | 0 | 0 | 0 |  | Crane | Crockett | Tier 4 |  |  |  |  | 76026, 6601, 60014 | Y | N |  |  | 14495 | 6712
52523A | Hayes to WA Parish Ckt.09A Upgrades | Upgrade Ckt.09A Hayes to Alief as a Clearance upgrade |  | Hayes | Alief | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-06-30 |  | 138 | 0 | 1.7 | 0 |  | Harris | Harris | Tier 3 | 19RPG024 | 2019-12-20 | 2020-01-16 |  | 44020, 44120, 44310 | Y | N |  | 0 | 57335 | 52523
57647 | Hillje 345kV Ramsey Solar (20INR0130) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Ramsey Solar. Reposition existing Ckt.72 Hillje to Bailey |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-06-30 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44200, 44040 | Y | N |  | 0 | 57648 | 57647
5274 | Camp Wood - Leakey Transmission Line Overhaul | Rebuild T269 Camp Wood to Leakey to be 138-kV capable with a nominal conductor rating of 223 MVA at 138-kV (Single Drake) with OPGW and operated at 69-kV. |  | Camp Wood | Leakey | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1016183 | 2021-06-30 |  | 69 | 0 | 17.3 | 0 |  | Real | Real | Tier 4 | 15RPG026 | 2015-12-16 | 2016-01-27 |  | 7426, 8633 | Y | N |  |  | 12950 | 5274
52523B | Hayes to WA Parish Ckt.09A Upgrades | Upgrade Ckt.09A Alief to Stafford as a Clearance upgrade |  | Alief | Stafford | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-06-30 01:00 |  | 138 | 0 | 4.67 | 0 |  | Harris | Harris | Tier 3 | 19RPG024 | 2019-12-20 | 2020-01-16 |  | 44020, 44671 | Y | N |  | Cost included in main entry | 57336 | 52523
52523C | Hayes to WA Parish Ckt.09A Upgrades | Upgrade Ckt.09A Stafford to WA Parish as a Clearance upgrade |  | Stafford | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-06-30 02:00 |  | 138 | 0 | 11.75 | 0 |  | Harris | Harris | Tier 3 | 19RPG024 | 2019-12-20 | 2020-01-16 |  | 44015, 44671 | Y | N |  | Cost included in main entry | 57337 | 52523
3821 | Pearsall to Palo Duro 138 kV line upgrade | Upgrade Pearsall to Palo Duro 138 kV line as recommended in 2013 RTP. Will investigate using a reconductor on existing structures with ACCC and other high temperature conductors. |  | Pearsall | Paloduro | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-07-15 | 2021-06-11 | 138 | 0 | 10.8 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5866, 5895 | Y | N |  |  | 11278 | 3821
48778 | Dustdevil: Construct New Distribution Station | Dustdevil: Construct New Distribution Station | Update schedule | Laredo VFT North | Lobo | In-Service | 1029 - 1207 | AEP TCC | Michael Richardson bcogan@aep.com 918-599-2857 | 3768 | 2021-07-15 | 2021-05-14 | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8038, 80013, 80221 | Y | N |  | 0 | 48779 | 48778
55789 | Big Foot to Moore SW: Rebuild 138 kV Line | Rebuild 138 kV line from Big Foot to Moore SW | IN-SERVICE | Big Foot | Moore | Planned | 1108 - 1286 | AEP TCC/STEC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3828 | 2021-07-15 | 2021-05-20 | 138 | 0 | 6.09 | 0 |  | Frio | Frio | Tier 2 |  | 2019-11-19 | 2020-04-19 |  | 8221, 5827 | Y | Y |  | 0 | 65577 | 55789
51645 | Sand Crab: Add New Distribution Station | Build new station on the Joslin to North Carbide138 kV line | IN-SERVICE | Joslin | North Carbide | In-Service | 1064 - 1237 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3799 | 2021-07-15 | 2021-04-15 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8155, 8135, 8140, 8190 | Y |  |  | 0 | 65557 | 51645
57882 | Add Vancourt POI for Vancourt Solar | Add Vancourt POI for Vancourt Solar at Luna | IN-SERVICE | Luna | Vancourt | In-Service | 1121 - 1299 | AEP TCC | J Randy Weaver jrweaver@aep.com 918-599-2253 | 3840 | 2021-07-15 | 2021-08-26 | 138 | 0.25 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 88657, 8656 | Y |  |  | 0 | 57883 | 57882
56098 | Turtle Creek Substation Upgrade | LCRA TSC will change the SB/SB configuration to a four-breaker ring bus and replace all three existing CBs (8810, 8820, and 8830) at Turtle Creek Substation. |  | Turtle Creek |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018970 | 2021-07-22 |  | 138 | 0 | 0 | 0 |  | Kerr |  | Tier 4 |  |  |  |  | 7442 | Y |  |  | 0 | 56099 | 56098
54118 | Rebuild Alvin-Mainland (795 ACSS) | Rebuild Alvin - Mainland 138 kV line with 795 ACSS conductor. |  | Freeway Park 138 kV Substation (Bus # 38820) | Alvin 138 kV Substation (Bus # 39030) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE09517 | 2021-08-15 |  | 138 | 0 | 17.3 | 0 |  | Galveston | Brazoria | Tier 4 |  |  |  |  | 38830, 39030 | Y |  |  | 0 | 54119 | 54118
60495 | Rebuild Wink-Kermit Tap with 795 ACSR | NOMCR ID # 68891-1 |  | Wink (bus # 37920) | Kermit Tap (bus # 38260) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-08-25 |  | 69 | 0 | 9.69 | 0 |  | Winkler | Winkler | Tier 4 |  |  |  |  | 37920, 38260 | Y |  |  | 0 | 60496 | 60495
57904 | Brightside Solar Interconnection | Interconnect Brightside Solar temporary tap on the Beeville to Three Rivers 69 kV line | IN-SERVICE | Beeville | Three Rivers | In-Service | 1113 - 1291 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2674 | 3832 | 2021-08-27 | 2021-11-11 | 138 | 0 | 0 | 0 |  | Bee | Live Oak | Tier 4 |  |  |  |  | 8142, 8199, 8400, 84006 | Y | N |  | 0 | 57905 | 57904
49812 |  |  |  | 5945059410 | 79601 |  |  | BPUB | Javier Martinez jamartinez@brownsville-pub.com 956-083-6530 |  | 2021-09-01 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 59410, 59450, 79601 | Y |  |  | 0 | 62164 | 49812
60489 | Adds Leon Creek Switching Station and Tarbush Tie | NOMCR ID# 68484-1 |  | Leon Creek (bus # 38355) | Tarbush (bus # 38295), Airport (bus # 38340) | Under Construction |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-09-01 |  | 138 | 0 | 22.38 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38355, 6630, 38295, 38340 | Y |  |  | 0 | 60490 | 60489
56372 | This is related to GINR19INR0117 | This is a brand new substation named Reata Station to accommodate GINR19INR0117 Roadrunner Crossing Wind project and Sheep Creek Wind Project later. |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2021-09-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68051, 68005, 68050 | Y |  |  | 0 | 56373 | 56372
52062 | Blackjack Creek Wind Interconnection | Interconnect Blackjack Creek Wind to the Grissom 345 kV station | IN-SERVICE | Grissom | Blackjack Creek | In-Service | 1075 - 1248 | AEP TCC | Darren O'Hare bcogan@aep.com 918-599-2857 | 3800 | 2021-09-15 | 2021-09-15 | 345 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 88670, 8624 | Y | Y |  | 0 | 52063 | 52062
61752 | This is to add Hubard Transmission Line | Transmission line is being built to interconnect Aquilla Lake Wind project 19INR0145 and 20INR0256 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2021-09-15 |  | 345 | 0 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 68090, 163273 | Y | N |  | 0 | 61753 | 61752
58292 | This is related to GINR21INR0031 | Jordan station will be interconnected project GINR 21INR0031 Indigo Solar Project |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2021-09-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68013, 68000, 68001 | Y |  |  | 0 | 58293 | 58292
58004 | Katoen: Build 345 kV station | Build 345 kV station Katoen to interconnect El Algodon, cut-in Katoen station to the Lon Hill to Goddard 345 kV line | IN-SERVICE | Katoen |  | In-Service | 1110 - 1288 | AEP TCC | Raza S Ansari bcogan@aep.com 918-599-2857 | 3829 | 2021-09-30 | 2021-10-15 | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8579, 88579, 8455, 8606 | Y |  |  | 0 | 58005 | 58004
58933 | This is related to GINR21INR0387 and GINR21INR0474-- Anchor Wind Project | Aspire station will be interconnected to GINR21INR0387 Anchor Wind and GINR21INR0474 Anchor BESS projects. |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2021-09-30 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68011, 68008, 68010 | Y |  |  | 0 | 58934 | 58933
48288B | BOGGY (BOG) 138kV Substation (SHELL Substation Replacement) | Install new customer-owned BOGGY 138kV substation. Loop from Ckt.85 to create new Ckt.85 DERICK to BOGGY to SHELL |  | BOGGY | DERICK/SHELL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-12 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41460, 40981, 41320, 41380, 41450, 41580, 40089, 41620, 110950, 110951, 110953, 110947, 110948, 110952 | Y | N |  | Cost Included in 48288A | 58108 | 48288
5277 | Glidden Area Transmission Line Upgrade | Convert existing 69-kV lines (T544) from Glidden to Altair and (T545) from Altair to Nada to 138-kV transmission lines. Relocate existing 45 MVA auto from Glidden to Altair. Add a second new 45 MVA auto at Altair substation. |  | Glidden | Nada | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1016219 | 2021-10-18 |  | 138 | 0 | 0.77 | 45 |  | Colorado | Colorado | Tier 4 |  |  |  |  | 78107, 78111, 78115, 78118, 78170, 78171, 78520, 5536, 7258, 78103, 78106 | Y | N |  | 0 | 46205 | 5277
43284D | Baytown Area Upgrades | Upgrade portions of reconfigured Ckt.87 SR Bertron to TEXAS to increase thermal ratings |  | SR Bertron | TEXAS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-28 |  | 138 | 0 | 0.99 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41405, 41540 | Y | N |  | Overall Cost included in phase F | 56065 | 43284
5838 | New Katz Auto to Benjamin 138 kV | Joint project with AEP to add autotransformer from Katz (bus# 774) to Katz8 (bus #798) and new line to Benjamin (bus # 6088) when AEP converts to 138 kV and builds line from the new Tardis switching station | [5 empty] | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 15016 | 2021-10-28 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | 16RPG002 | 2016-02-03 | 2016-05-30 |  | 790, 6088, 798, 33798 | Y |  |  |  | 14961 | 5838
52365I | Spillman Island Restoration Plan | Upgrade Ckt.83A Cedar Bayou to DECKER to increase thermal limits. |  | Cedar Bayou | DECKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Harris | Tier 4 |  |  |  |  | 40439, 40430 | Y | N |  | Cost included in Phase A. | 52375 | 52365
48281 | Angleton to West Columbia Ckt 04E Equipment Upgrades | Upgrade Ckt 04E Angleton to West Columbia to increase thermal limits | Now a GO project | Angleton | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-30 |  | 138 | 0 | 16.11 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 43381 | Y | N |  | 0 | 55974 | 48281
52197B | Jordan Auto A3 Addition (PLACID 138kV Sub) | Loop Ckt 97C-1 Chambers-King into Jordan 345kV |  | Chambers | King | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-10-30 |  | 345 | 0 | 0 | 0 |  | Chambers | Harris | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 40255, 40850, 40900 | Y | N |  | Cost included in Phase A | 57346 | 52197
52197C | Jordan Auto A3 Addition (PLACID 138kV Sub) | PLACID (PLA) Substation Looped into Ckt.86D RIGBY to Crosby |  | Rigby | Crosby | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-10-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Harris | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 40680, 40155, 40390, 40670, 40665 | Y | N |  | 0 | 57347 | 52197
50658 | Friendswood to Mustang Bayou Ckt.04A Upgrades | Upgrade 138kV Ckt.04A Friendswood tap to Mustang Bayou to increase thermal limits. |  | Friendswood Tap | Mustang Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-31 |  | 138 | 0 | 2.19 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42652, 42960 | Y | N |  | 0 | 50816 | 50658
5604 | Stewart Road: Construct 345 kV cut-in | Construct new 345 kV 4 breaker ring bus station at AEP Stewart Rd, with two 675 MVA 345/138 autotransformers connected to Stewart Rd 138 station. Hairpin the North Edinburg to SU Palmito 345 kV line into new Stewart Rd 345 station. The hairping will be constructed in a double circuit configuration, approximately 5 miles long. Also install 100 Mvar shunt reactor at the new Stewart Rd 345 kV station. |  | Stewart Road |  | In-Service | 792 - 0977 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 3582 | 2021-10-31 | 2021-10-18 | 345 | 0 | 0 | 1350 | -100,0 | Hidalgo | Hidalgo | Tier 2 | 15RPG016 | 2015-07-10 | 2016-05-19 | 2016-06-14 | 80137, 8966, 8974 | Y | N |  |  | 13334 | 5604
52555 | Wallis to East Bernard Ckt.65C Upgrades | Upgrade Ckt.65C Wallis to East Bernard to increase thermal limits. |  | East Bernard | Wallis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-31 |  | 138 | 0 | 8.17 | 0 |  | Wharton | Austin | Tier 4 |  |  |  |  | 44190, 44740 | Y | N |  | 0 | 52556 | 52555
62001 | Tex Gulf Customer Substation Bypass as Ckt.60C | Disconnect Tex Gulf customer substation. Convert New Gulf substation to loop service to create new Ckt.60C South Lane City to New Gulf to to Pledger tap to West Columbia |  | South Lane City/ New Gulf | Pledger tap/ West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-31 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 43010, 43011, 43012, 43120, 43340, 43341, 48253, 48254, 48281, 910461, 43380, 43190 | Y | N |  | 0 | 62002 | 62001
52365E | Spillman Island Restoration Plan | Upgrade equipment at SR Bertron substation on SRB-Alexander Island-CHORIN Ckt.87C (Future Option 3 to reconfigure as Ckt.xx SRB-Alexander Island-WALKER-QUANUM) |  | SRB | Chorin | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-31 01:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40320, 41391, 41400 | Y | N |  | Cost included in Phase A. | 52371 | 52365
52365H | Spillman Island Restoration Plan | Upgrade Relays at WARVUE substation on WARVUE to HOPSON Ckt.84D. Upgrade Relays at Cedar Bayou substation on Cedar Bayou to HOPSON Ckt.84D. |  | WARVUE | HOPSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-31 03:00 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 | [5 empty] | Y | N |  | Cost included in Phase A. | 52374 | 52365
55372 | Conversion of TNMP Gomez to 138kV service. |  |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE03020 | 2021-11-01 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38471, 60798 | Y |  |  | 0 | 55373 | 55372
47929 | Rising Star Area Rebuilds | Rising Star Area Rebuilds |  | Downing (281) | Nimrod (289) | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2021-11-01 |  | 69 | 0 | 50.04 | 60 |  | Comanche | Eastland | Tier 3 | 19RPG0007 | 2019-04-04 | 2019-04-30 |  | 281, 285, 289, 293, 277, 1649 | Y |  |  | 0 | 47930 | 47929
47936 | Pleasant Grove Rebuilds | Pleasant Grove Rebuilds |  | Midway (bus 185) | Calvert Switch (bus 73) | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2021-11-01 |  | 69 | 0 | 20.4 | 0 |  | Falls | Milam | Tier 4 |  |  |  |  | 73, 81, 185 | Y |  |  | 0 | 47937 | 47936
54568 | CPSE_New_Navistar_Substation | CPSE_New_Navistar_Substation |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2021-11-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5317, 5007, 5297 | Y |  |  | 0 | 54569 | 54568
59921 | Breaker Installation | Updating to a Ring Bus configuration at the Rosehill substation for increased reliability. |  | 6894 | 6894 | Planned |  | RYBRN |  |  | 2021-11-01 | 2021-11-01 | 138 | 0 | 0 | 0 |  | Kaufman | Kaufman | Tier 4 | [5 empty] | Y |  |  |  | 59922 | 59921
45032 | Brant: Build 69 kV station | Construct new 69 kV box bay on the Rock Springs to Sonora 69 kV line | IN-SERVICE | Brant |  | In-Service | 977 - 1155 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2762 | 2021-11-03 01:00 | 2021-11-03 | 69 | 0 | 0 | 0 |  | Sutton |  | Tier 4 |  |  |  |  | 60438, 6570, 60210 | Y | N |  | 0 | 65526 | 45032
6346 | Menard Phillips T to Junction 69 kV line: Rbld 69 kV line | Rehab Menard Phillips Tap to Junction 69 kV line | IN-SERVICE | Menard Phillips Tap | Junction | In-Service | 786 - 0971 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2712 | 2021-11-07 | 2021-11-07 | 69 | 0 | 12.2 | 0 |  | Kimble | Kimble | Tier 4 |  |  |  |  | 6400, 6401 | Y | N |  |  | 14090 | 6346
47537 | LCRATSC_Kempner_CB_Addition | LCRA TSC will add three 138kV, 3000A, 40kAIC circuit breakers in a ring bus configuration at Kempner Substation. |  | Kempner | Kempner | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-11-11 |  | 138 | 0 | 0 | 0 |  | Lampasas | Lampasas | Tier 4 |  |  |  |  | 7260, 260, 7061, 7064 | Y | N |  | 0 | 62635 | 47537
6972 | Dimmit Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Dimmit Substation. |  | Dimmit |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-11-12 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  |  | 78281 | Y | N |  |  | 14789 | 6972
59522 | Pebble Creek 138 kV Switch | Establish the new Pebble Creek 138 kV Switch |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4315 | 2021-11-15 | 2021-11-04 | 138 | 1.2 | 0 | 0 |  | Ellis |  | Tier 4 |  |  |  |  | 2229, 221, 2328 | Y |  |  | 0 | 59523 | 59522
55969 | Cedar Creek (CCK) Substation for Old 300 Solar (21INR0406) | New 138kV Cedar Creek substation for generator interconnection to Old 300 Solar. Loop Ckt.02 into substation to create new Ckt.72 BAILEY to Cedar Creek to WAP |  | Cedar Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-11-30 |  | 345 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 44090, 111865, 44005, 44040 | Y | N |  | 0 | 56664 | 55969
49550 | Port Isabel: Rebuild As GIS Station | Port Isabel: Rebuild As GIS Station |  | Port Isabel |  | Planned | 958 - 1136 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3716 | 2021-11-30 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  | 0 | 49551 | 49550
6668B | Freeport - Master Plan | New 345 kV double-circuit line from Bailey Substation to Jones Creek Substation | Accelerated Project Schedule | Bailey | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-11-30 |  | 345 | 55.2 | 0 | 0 |  | Wharton | Brazoria | Tier 1 | 17RPG005 | 2017-04-04 | 2017-06-05 | 2017-12-12 | 5568, 5915, 42150, 42195, 42199, 42400, 42500, 42530, 42540, 43011, 43120, 43211, 44000, 44005, 44040, 42210, 42215, 43212, 43221, 43222, 43380, 44200, 47531, 47532, 48006 | Y | N |  | 0 | 64156 | 6668
5891A | LUBZOL Substation Removal and Substation PATRIK Addition | Remove LUBZOL 138kV substation from CNP service |  | LUBZOL | TIDAL/TRAVIS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-11-30 00:01 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40980, 40070, 40470, 41210, 41380, 41580, 41590, 40089, 40530, 41370, 41415, 41450 | Y | N |  | 0 | 52118 | 5891
51216C | Ward Winkler RPG | Re-conductor Pecos to Cedarvale (both lines D & E). |  | Pecos (38091) | Cedarvale (38145) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-12-01 |  | 138 | 0 | 15.12 | 0 |  | Reeves | Ward | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 38091, 38145 | Y |  |  | 0 | 56658 | 51216
6569 | Aspermont: Replace the 138/69 kV autotransformer | Replace the 138/69 kV autotransformer at Aspermont with a 130 MVA autotransformer | IN-SERVICE | Aspermont |  | In-Service | 839 - 1023 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 2817 | 2021-12-01 | 2021-12-01 | 138 | 0 | 0 | 130 |  | Stonwall |  | Tier 4 |  |  |  |  | 6156, 6158 | Y | N |  | 0 | 65510 | 6569
6167 | Harlingen SS - Raymondville #2: Convert to 138 kV | Harlingen SS - Raymondville #2: Convert to 138 kV | IN-SERVICE | Harlingen SS | Raymondville #2 | Planned | 864 - 1042 | AEP TCC | Eric Scott bcogan@aep.com 918-599-2857 | 3650 | 2021-12-01 |  | 138 | 0 | 0 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  |  | 8300, 8700, 80436, 8302, 8325, 8327 | Y | N |  | 0 | 65504 | 6167
51742 | Pipeline Breaker Addition | Convert existing tap substation to ring bus |  | Pipeline |  | In-Service |  | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 |  | 2021-12-08 | 2021-12-01 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7390 | Y | N |  | 0 | 51751 | 51742
48335 | RGEC Ft. Stockton US 285 138-kV Substation Addition | Provide transmission service to new 25/30/35 MVA 138/24.9-kV substation to replace (transfer load from) Ft. Stockton 69-kV Substation. This is tied to AEP Project ID # 44361 |  | Fort Stockton | Fort Stockton | In-Service |  | RGEC/LCRATSC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2021-12-08 02:00 | 2021-09-01 | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 78926, 6645, 60717 | Y |  |  | 0 | 48340 | 48335
6273 | Saginaw-Eagle Mountain 138 kV DCKT | Upgrade the Saginaw - Eagle Mountain 138 kV Double Circuit Line |  | Saginaw | Eagle Mountain | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5274 | 2021-12-15 | 2021-12-21 | 138 | 0 | 28 | 0 |  | Tarrant | Tarrant | Tier 3 | 20RPG011 |  | 2020-07-24 |  | 1864, 2066, 2067, 2071, 2074, 1860, 2070, 2076, 11860 | Y | N |  | 0 | 63690 | 6273
6540 | LCRA Gonzales to GVEC Gonzales Transmission Line Upgrade | Replace 0.98 miles of 4/0 ACSR 69 kV T-line, with double circuit 138kV structures, 795 ACSR "Drake", initially operate one circuit at 69 kV; plus terminal improvements |  | LCRA Gonzales | GVEC Gonzales | In-Service |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-12-15 | 2022-01-03 | 69 | 0 | 0.98 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  |  | 7592, 7626 | Y | N |  |  | 14280 | 6540
57928 | Rebuild Midland East 138 kV Switch | Rebuild Midland East 138 kV Switch |  | Midland East | Midland East | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8538 | 2021-12-15 | 2021-12-15 | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 | 2021-03-12 |  | 1023 | Y |  |  | 0 | 57930 | 57928
52309 | Horseshoe Springs Switch - Riverton Switch 138 kV Second Circuit | Install a 2nd circuit on existing 138 kV structures |  | Horseshoe Springs | Riverton | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8526, R8452 | 2021-12-15 | 2021-12-17 | 138 | 0 | 55 | 0 |  | Culberson | Reeves | Tier 3 | 20RPG012 | 2020-07-07 | 2020-08-10 |  | 11266, 11267, 11268, 11269, 11271, 11272, 11083, 11090, 11112, 11183, 11190 | Y |  |  | 0 | 56599 | 52309
52251 | Mountain Creek Switch 138 kV Breaker Installation | install two 138 kV breakers |  | Mountain Creek |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4093 | 2021-12-15 | 2021-12-15 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 12457, 12458, 2411, 2412, 3014, 3015 | Y |  |  | 0 | 52252 | 52251
6833 | Vineyard 138 kV Switching Station | Establish new 138 kV switching station | Project Deferral | Vineyard Switch |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3211 | 2021-12-15 | 2021-12-18 | 138 | 4.2 | 0 | 0 |  | Tarrant | Tarrant | Tier 2 | 18RPG003 |  | 2018-08-17 |  | 2025, 555, 648, 2015, 12013, 2031 | Y | N |  |  | 14635 | 6833
5310 | Everman - Venus 345 kV Double-circuit line | Upgrade existing line |  | Everman | Venus | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1735 | 2021-12-15 | 2021-12-09 | 345 | 0 | 34.6 | 0 |  | Tarrant | Ellis | Tier 3 | 16RPG006 |  | 2016-08-22 |  | 1882, 1886, 1906, 1907 | Y | N |  |  | 12986 | 5310
57855 | Ennis Switch 138 kV Rebuild | Rebuild Ennis 138 kV Switch |  |  |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4302 | 2021-12-15 | 2021-12-16 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  | 0 | 57856 | 57855
52255 | Sand Lake Switch 138 kV Terminal Addition | Add 2-138 kV terminals at Sand Lake Switch |  | Sand Lake | Sand Lake | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8504 | 2021-12-15 | 2021-12-14 | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  | 2019-03-01 | 2019-09-01 | 2019-10-01 | 11097 | Y |  |  | 0 | 52256 | 52255
57915 | Tall City - Telephone Road 138 kV Line Rebuild | Tall City - Telephone Road 138 kV Line Rebuild |  | Tall City | Telephone Road | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8552 | 2021-12-15 | 2021-12-03 | 138 | 0 | 11.9 | 0 |  | Midland | Midland | Tier 3 | 20RPG016 | 2020-09-11 | 2020-10-21 |  | 23855, 23862 | Y |  |  | 0 | 57916 | 57915
57758 | Carrollton Northwest 345/138 kV Autotransformer | Carrollton Northwest 345/138 kV Autotransformer |  | Carrollton Northwest |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4247 | 2021-12-15 | 2021-12-21 | 345 | 0 | 0 | 600 |  |  |  | Tier 3 | 20RPG010 |  |  |  | 2360, 2362, 2363, 2361, 12360 | Y |  |  | 0 | 57759 | 57758
52153 | Upgrade Eustace SE - Mabank 138 kV Line | Upgrade Eustace SE - Mabank 138 kV Line |  | Eustace Southeast | Mabank | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6097 | 2021-12-15 | 2021-12-22 | 138 | 0 | 9.3 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  |  | 3176, 3177, 3179, 6951 | Y |  |  | 0 | 52154 | 52153
52234 | Calmont 138 kV Emergency Capacitors | Install new 55.2 Mvar capacitor bank |  | Calmont |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5134 | 2021-12-15 | 2021-12-30 | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1955 | Y |  |  | 0 | 52235 | 52234
57853 | Palmer and Rice 69 kV Substations Conversion to 138 kV | Convert Palmer and Rice 69 kV Substations to 138 kV |  | Palmer | Rice | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4317 | 2021-12-15 | 2021-12-22 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2344, 2345, 2346, 2347, 12344, 221, 2326, 2329, 2342, 3468 | Y |  |  | 0 | 57854 | 57853
7025 | Renner Sw. Sta. - Plano Tennyson Sw. Sta. 138 kV Line | Upgrade existing Renner Sw. Sta. - Plano Tennyson Sw. Sta. 138 kV Line |  | Renner Sw. Sta. | Plano Tennysson Sw. Sta. | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3047 | 2021-12-15 | 2021-12-16 | 138 | 0 | 10.6 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2352, 2353, 2521, 2523, 2524 | Y | N |  |  | 14847 | 7025
45517 | Waco West - Waco East 138 kV Line | Upgrade the Waco West Switch - Waco East Switch (Via Baylor Tap) 138 kV Line to 2569 A |  | Waco West | Waco East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R463 | 2021-12-15 | 2021-12-16 | 138 | 0 | 10.6 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3434, 3436, 3438, 3563 | Y | N |  | 0 | 45518 | 45517
52305 | Cedar Hill Switch-Cedar Hill 138 kV Line Upgrade | rebuild the existing Cedar Hill Switch-Cedar Hill 138 kV Line |  | Cedar Hill SW | Cedar Hill | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4131 | 2021-12-15 | 2021-12-27 | 138 | 5.9 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2422, 3049, 3051, 3052, 3050, 3055 | Y |  |  | 0 | 52306 | 52305
52149 | Upgrade Elm Mott - Bosque 138 kV Line | Upgrade Elm Mott - Bosque 138 kV Line |  | Elm Mott | Bosque | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1721 | 2021-12-15 | 2021-12-29 | 138 | 0 | 19.3 | 0 |  | McLennan | Bosque | Tier 4 |  |  |  |  | 249, 252, 3407 | Y |  |  | 0 | 52150 | 52149
52295 | Natural Dam 138 kV Switch | Upgrade the existing 138 kV Switch |  | Natural Dam | Natural Dam | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8308 | 2021-12-15 | 2021-12-22 | 138 | 0 | 0 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 11355, 11322, 11331, 23836 | Y |  |  | 0 | 52347 | 52295
52469 | Scout: Build 69 kV station | Construct new 69 kV box bay on the Abilene South to Steamboat 69 kV line | IN-SERVICE | Scout |  | In-Service | 1072 - 1245 | AEP TNC | William Lovelace mlforcum@aep.com 918-599-2674 | 2833 | 2021-12-15 | 2021-12-15 | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 60456, 6328, 6331 | Y | N |  | 0 | 52470 | 52469
49834 | Fullerton 138 kV Switch Terminal Addition | Fullerton 138 kV Switch Terminal Addition |  | Fullerton | Fullerton | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9037 | 2021-12-15 01:00 |  | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1274, 11275, 1272, 11274, 11277, 11284 | Y |  |  | 0 | 49835 | 49834
46259 | Big Spring - Buzzard Draw 69 kV Line Conversion | Big Spring - Buzzard Draw 69 kV Line Conversion |  | Big Spring | Buzzard Draw | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9015 | 2021-12-15 23:00 | 2021-12-17 | 138 | 0 | 21.3 | 0 |  | Howard | Howard | Tier 4 | 20RPG009 | 2020-06-03 | 2020-07-09 |  | 1357, 1358, 1359, 1361, 1365, 1322, 1323, 1355, 1356, 11324 | Y |  |  | 0 | 46262 | 46259
52239 | Lake Hubbard SW | Install two 138 kV breakers |  | Lake Hubbard |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4134 | 2021-12-16 | 2021-12-01 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 12401, 12402, 2401, 2402, 2441, 2939 | Y |  |  | 0 | 52240 | 52239
54088 | Hortontown Substation Upgrade | Increase the reliability of substation equipment at the Hortontown Substation. LCRA TSC will change the existing high-side configuration at Hortontown substation from Single Bus/Single Breaker to Ring Bus. |  | Hortontown Substation | Hortontown Substation | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-12-16 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7175 | Y | N |  | 0 | 54089 | 54088
5967 | Burma: Build new 69 kV station | Construct a new 69 kV station near the exsiting Grape Creek tap and reterminate the College Hills to Sterling City and Grape Creek to North San Angelo 69 kV lines into Burma | IN-SERVICE | Burma |  | In-Service | 845 - 1029 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2688 | 2021-12-16 | 2021-12-16 | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6416, 60411, 6437, 6460, 6468 | Y | N |  |  | 13682 | 5967
49841 | Fullerton_to_NorthAndrews_138_kV_Conversion_East | Fullerton_to_NorthAndrews_138_kV_Conversion_East |  | Fullerton | North Andrews | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9038 | 2021-12-16 |  | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1285, 1159, 1160, 11274, 11275 | Y |  |  | 0 | 49842 | 49841
49858 | Fullerton_to_NorthAndrews_138_kV_Conversion_West | Fullerton_to_NorthAndrews_138_kV_Conversion_West |  | Fullerton | North Andrews | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9039 | 2021-12-17 |  | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1160, 1267, 1270, 11274, 1159, 1272, 11275 | Y |  |  | 0 | 49859 | 49858
6786 | Schumansville T2 Replacement | Replace T2, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Schumansville |  | In-Service |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-12-17 | 2021-12-06 | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7609 | Y |  |  |  | 14580 | 6786
59550 | Relocate Exxon Means to Landfill 138 kV POD | Relocate Exxon Means to new Landfill 138 kV POD and remove 4.3 miles of 138 kV line |  | Andrews North | Means | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8563 | 2021-12-18 | 2021-12-20 | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1159, 1165, 1166, 1285 | Y |  |  | 0 | 59572 | 59550
07TPIT0050 | Dunlap to Techridge 138kV Circuit Relocation | This project will reroute the existing Ckt 975 Dunlap-Techridge from near the intersection of Howard Lane and Dessau Road to the Techridge substation. The reroute will use 3000 amp bundled 795 ACSS Drake conductor. |  | Dunlap Substation | Techridge Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P071 | 2021-12-18 |  | 138 | 0 | 2.7 | 0 |  | Travis | Travis | Tier 2 | 09RPG001 | 2009-01-26 | 2009-07-21 |  | 9045, 9190 | Y | N |  |  | 8189 | 1013
61604 | Add Tecumseh Creek 345 kV Switch | Add Tecumseh Creek 345 kV Switch |  | Coody Crossing | Willow Creek | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4023 | 2021-12-19 | 2021-12-20 | 345 | 0 | 0 | 0 |  | Throckmorton | Throckmorton | Tier 4 |  |  |  |  | 11418, 20104, 20105, 1421, 60514 | Y |  |  | 0 | 64011 | 61604
5965 | Benjamin Tap to Katz (BEC): Build new 138 kV line | Construct new 138 kV ring bus Tardis on the Munday to Paducah 138 kV line, rebuild existing Benjamin Tap to 138 kV, terminate into Tardis, convert Benjamin to 138 kV operation and build new 138 kV line from Benjamin to Katz (BEC) | IN-SERVICE | Benjamin Tap | Katz (BEC) | In-Service | 769-0954 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2685 | 2021-12-21 | 2021-12-21 | 138 | 17.7 | 9 | 0 |  | Knox | Knox | Tier 2 | 16RPG002 | 2016-02-03 | 2016-05-01 | 2016-05-01 | 6320 | Y | N |  |  | 13680 | 5965
54698 | Perigee: Build 345 kV station | Interconnect Apogee Wind on the Foxtail to Mulberry Creek 345 kV Line | IN-SERVICE | Perigee |  | In-Service | 1038 - 1265 | AEP TNC | Joseph E. Page mlforcum@aep.com 918-599-2674 | 1855 | 2021-12-28 | 2021-12-28 | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60791, 6076, 6235 | Y | N |  | 0 | 54699 | 54698
7027 | Barrilla Junction to Ft. Stockton SW: Rebuild 69 kV line | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138 kV, reterminate into Solstice, install 138 kV capacitor bank at Solstice, and build new Ft. Stockton Switch 138 kV station | IN-SERVICE | Solstice | Fort Stockton Switch | In-Service | 908 - 1086 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 2732 | 2021-12-30 | 2021-12-30 | 138 | 0 | 16.3 | 0 |  | Pecos | Pecos | Tier 3 | 17RPG018 | 2017-12-22 | 2018-02-02 |  | 6645, 60717, 60385, 6653, 38350, 38470 | Y | N |  | 0 | 66648 | 7027
52640 | HO Clarke Auto A3 Replacement | Replace existing HO Clarke Auto A3 with removed University Auto A1. Update 10/13/2021: Update project to reflect change in scope to replacing HOC-A3. This portion of the HOC Upgrades has been cancelled and the existing HOC-A3 (C-254515) will remain in service. |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-30 |  | 138 | 0 | 0 | 117 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  | 0 | 52641 | 52640
57586 | Cedar Bayou to Center Ckt.97D Upgrade | Upgrade Cedar Bayou to Center Ckt.97D |  | Cedar Bayou | CENTER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 345 | 0 | 0 | 0 |  | Chambers | Harris | Tier 4 |  |  |  |  | 40000, 40240 | Y | N |  | 0 | 57587 | 57586
52267C | SR Bertron 138/69kV Conversions | Remove SRB Auto A2 |  | SR Bertron | SR Bertron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 138 | 0 | 0 | -192 |  | Harris | Harris | Tier 4 |  |  |  |  | 41405, 41415, 40290, 40480, 40540, 41400, 41540 | Y | N |  | Cost Included in Phase A. | 59288 | 52267
64017 | Hockley Substation Reconfiguration | Reposition Hockley distribution transformers to increase reliability |  | Hockley |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 45884, 45885, 45886, 45880, 45675, 46564, 46511 | Y | N |  | 0 | 64018 | 64017
52197D | Jordan Auto A3 Addition (PLACID 138kV Sub) | Upgrade Ckt.86J Connor to Bender to increase thermal limits. |  | Connor | Bender | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 40155, 40665 | Y | N |  | 0 | 57348 | 52197
52197E | Jordan Auto A3 Addition (PLACID 138kV Sub) | Upgrade Ckt.86J Bender to Jordan to increase thermal limits. |  | Bender | Jordan | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 40155, 40390, 40856, 40857, 40340, 40670, 40855 | Y | N |  | 0 | 57349 | 52197
52553 | Wallis to Gebhardt Ckt.65C Upgrades | Upgrade Ckt.65C Wallis to Gebhardt to increase thermal limits. |  | Wallis | Gebhardt | Planned | 525535253359322 | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-12-31 |  | 138 | 0 | 9.58 | 0 |  | Austin | Austin | Tier 3 | 20RPG020 | 2020-10-27 | 2020-11-18 |  | 44700, 44740 | Y | N |  | 0 | 52554 | 52553
57582 | Cedar Bayou Auto A1 Upgrade | Upgrade Cedar Bayou auto A1 to increase thermal limits |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 345 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  |  | 40000, 40015, 49005 | Y | N |  | 0 | 57583 | 57582
46938 | McCreeAdds600MVAAuto2 | McCreeAdds600MVAAuto2 |  | McCree | McCree | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2021-12-31 |  | 345 | 0 | 0 | 600 |  | Dallas | Dallas | Tier 4 | 19RPG022 |  |  |  | 983, 901127, 973, 834 | Y | N |  | 0 | 46939 | 46938
45543 | Everman Switch - Marrs Switch 138 kV DCKT Line | Upgrade the Everman Switch - Marrs Switch 138 kV Double-Circuit Line |  | Everman Switch | Marrs Switch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5279 | 2021-12-31 | 2021-12-15 | 138 | 0 | 8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1883, 1884, 1969, 2211, 11967, 11968 | Y |  |  | 0 | 64343 | 45543
52267D | SR Bertron 138/69kV Conversions | Disconnect Ckt.16A and Ckt.23A at SRB and Reconnect to Create New Ckt.23A Deepwater to South Channel |  | South Channel | Deepwater | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 01:00 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 110005, 41400, 41415 | Y | N |  | Cost included in Phase A. | 59284 | 52267
52267A | SR Bertron 138/69kV Conversions | Deenergize 69kV SRB substation and connect 138kV Buses |  | SR Bertron | SR Bertron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 02:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 49004, 41400, 41410 | Y | N |  | 0 | 59285 | 52267
52267B | SR Bertron 138/69kV Conversions | Remove SRB Auto A1 |  | SR Berton | SR Berton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 03:00 |  | 138 | 0 | 0 | -200 |  | Harris | Harris | Tier 4 |  |  |  |  | 40089, 40470, 41380, 41410, 41415 | Y | N |  | Cost included in Phase A. | 59289 | 52267
52267G | SR Bertron 138/69kV Conversions | Install cap bank removed from HOC at SRB. |  |  | SR Bertron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 04:00 |  | 138 | 0 | 0 | 0 | 0,100 | Harris | Harris | Tier 4 |  |  |  |  | 41410, 41415, 41419, 40089, 40470, 41400, 49004, 110005 | Y | N |  | Cost included in Phase A | 59287 | 52267
52267E | SR Bertron 138/69kV Conversions | De-Energize Ckt.55D SRB to SRB |  | SR Bertron | SR Bertron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 05:00 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41400 | Y | N |  | Cost included in Phase A. | 59286 | 52267
61262B | Hunter to McCarty Lane Storm Hardening | Rebuild double-circuit section of Hunter to McCarty Lane 138 kV with single, circuit bundled 795 ACSR Conductor, 440 MVA. This project is in conjunction with LCRA TSC project of McCarty Lane - Ranch Road ( and ERCOT Project #54105). | For total project cost please see 61262A | McCarty Lane | Hunter | In-Service |  | PEC/LCRATSC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2022-01-01 | 2022-01-01 | 138 | 0 | 1.57 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7491 | Y | N |  | 0 | 63728 | 61262
52072 | Conan: Build new 69 kV box bay | Construct new 69 kV box bay on the Santa Anna to Cross Plains 69 kV line and install capacitor bank | IN-SERVICE | Conan |  | In-Service | 1066 - 1239 | AEP TNC | William Lovelace mlforcum@aep.com 918-599-2674 | 2827 | 2022-01-12 | 2022-01-12 | 69 | 0 | 0 | 0 | 0,7.2 | Callahan |  | Tier 4 |  |  |  |  | 6350, 6356, 60455, 6352, 6357 | Y | N |  | 0 | 52073 | 52072
52533 | Gebhardt to Sealy Ckt.65A Upgrades | Upgrade Ckt.65A Gebhardt to Sealy to increase thermal limits (Transmission Design Hardening Project) |  | Gebhardt | Sealy | Planned | 525535253359322 | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2022-01-22 |  | 138 | 0 | 2.46 | 0 |  | Austin | Austin | Tier 3 | 20RPG020 | 2020-10-27 | 2020-11-18 |  | 44640, 44700 | Y | N |  | 0 | 52534 | 52533
47442 | Graphite Mine Circuit Breaker Addition | LCRA TSC will increase the reliability of transmission facilities along T109 by adding three 138-kV, 3000A, 40kAIC circuit breakers in ring-bus configuration at the Graphite Mine Substation. |  | Graphite Mine | Graphite Mine | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-01-28 |  | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  |  | 7084 | Y | N |  | 0 | 47443 | 47442
44866 | Dilley - Jourdanton 69 kV Line | Rebuild Dilley - Jourdanton 69 kV Line | Update Schedule | Dilley | Jourdanton | Under Construction | 967 - 1145 | AEP TCC | Brian Oyster bcogan@aep.com 918-599-2857 | 3725 TP2018043 | 2022-01-30 |  | 69 | 0 | 44.8 | 0 |  | Frio | Atascosa | Tier 3 | 19RPG010 | 2019-05-23 | 2019-05-24 | 2019-06-17 | 8206, 8208, 8607 | Y | N |  | 0 | 66651 | 44866
62841 | Add TresBahias | Re-terminate the Dupont to Joslin line. Re-terminate the Formosa to Joslin line. Install one span to POI. Install a new 138 kV rung with double breakers. Install a 138 kV breaker on the new Formosa terminal. Install EPS metering on the Tres Bahias terminal |  | Joslin | Tres Bahias | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2019312 | 2022-01-31 |  | 138 | 0.05 | 0 | 0 |  | Calhoun | Calhoun | Tier 4 |  |  |  |  | 8661, 8140 | Y |  |  | 0 | 65597 | 62841
64161 | Addicks Auto A2 Replacement for Failed Auto | Replace failed Addicks auto A2 with 800MVA spare auto |  | Addicks |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 |  | 345 | 0 | 0 | 200 |  | Harris |  | Tier 4 |  |  |  |  | 45600, 45610, 49083 | Y | N |  | 0 | 64162 | 64161
57414 | BEARLE (BER) 138kV Customer Substation | BEARLE (BER) 138kV customer substation looped into Ckt.96C Philip to South Channel |  | BEARLE | Philip/South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41230, 41250, 41370 | Y | N |  | 0 | 57415 | 57414
52529 | Jordan to Cities to Dalton Ckt.86I | Upgrade Ckt.86I Jordan to Cities to Dalton to increase thermal limits. |  | Jordan | Dalton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40340, 40740, 40857 | Y | N |  | 0 | 52530 | 52529
60493 | Rebuild West-TI with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-01-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37060, 37080 | Y |  |  | 0 | 60494 | 60493
51216E | Ward Winkler RPG | Construct two 138kV tie-lines between TNMP Cedarvale and Oncor Sand Lake. |  | TNMP Cedarvale (38145) | Oncor Sand Lake (11097) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-01-31 |  | 138 | 1.56 | 0 | 0 |  | Ward | Ward | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 11097, 38145 | Y |  |  | 0 | 56660 | 51216
64150 | Smithers Sub Exp Braes Power - (20INR0221) | Expand Smithers 345kV substation and install one generator lead for new interconnection to Braes Power |  | Smithers |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 |  | 345 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 44650, 112419 | Y | N |  | 0 | 64151 | 64150

## CancelledTPIT020122NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2022
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
52089 | Red Creek: Build new 345 kV terminal | Interconnect Bravepost Solar at the Red Creek 345 kV station | CANCELLED | Red Creek |  | Planned | 1067 - 1240 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2828 | 2022-05-15 |  | 345 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6444 | N | N |  | 0 | 52090 | 52089
51243 | Keller Wall Price 138 kV Switch | Upgrade Roanoke - Keller Wall Price Switch 138 kV Double-Circuit Line |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5251 | 2022-05-16 |  | 138 | 0 | 0 | 0 |  | Denton | Tarrant | Tier 4 |  |  |  |  | 2037, 12038, 12307, 566, 679, 1852, 1854, 1856, 1857, 2027, 2033, 2034, 2036, 2038, 2058, 11857, 15100, 15101 | N |  |  | 0 | 51244 | 51243
5538 | Lynx: Build a 345 kV station | Construct two new 345 kV stations, Lynx and Solstice, and new 345 kV lines from Lynx to Solstice and Lynx to Bakersfield | CANCELLED | Lynx |  | Planned | 789 - 0974 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2650 | 2022-06-30 |  | 345 | 0 | 0 | 743 | -50,0 | Pecos |  | Tier 1 |  | 2016-04-01 |  |  | 60401, 60403, 60400 | N | Y |  |  | 13266 | 5538
50886 | Edna - Victoria: Rebuild 138 kV line | Rebuild El Campo to Victoria 138 kV line |  | Edna | Victoria | Planned | 1062 - 1235 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3796 | 2022-11-30 |  | 138 | 0 | 21.57 | 0 |  | Jackson | Victoria | Tier 3 |  |  |  |  | 8118, 8172 | N | N |  | 0 | 50887 | 50886
50884 | Ganado - Edna: Line Rebuild | El Campo - Victoria: Line Rebuild |  | Ganado | Edna | Planned | 1062 - 1235 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3795 | 2022-11-30 |  | 138 | 0 | 9.72 | 0 |  | Jackson | Jackson | Tier 3 |  |  |  |  | 8117, 8118 | N | N |  | 0 | 50885 | 50884
50888 | El Campo - Ganado: Line Rebuild | Rebuild El Campo to Victoria 138 kV line |  | El Campo | Ganado | Planned | 1062 - 1235 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3794 | 2022-11-30 |  | 138 | 0 | 20.02 | 0 |  | Wharton | Jackson | Tier 3 |  |  |  |  | 8102, 8117, 88099 | N | N |  | 0 | 50889 | 50888
15TPIT0008 | Triple R - New Substation (7627) | Build a 138-26.18kV. 40 MVA substation on the GVEC Wilson-Sutherland Springs (T549) 138 kV transmission line |  | Triple R | Wilson/Sutherland Springs | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 7627, 5418, 7615 | N | N |  |  | 11634 | 3367
5647 | Del Rio to Buena Vista, rebuild 138 kV line | Rebuild Del Rio to Buena Vista 138 kV line |  | Del Rio | Buena Vista | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-04-01 |  | 138 | 0 | 2.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8690 | N | N |  |  | 13381 | 5647
51243 | Keller Wall Price 138 kV Switch | Upgrade Roanoke - Keller Wall Price Switch 138 kV Double-Circuit Line |  | Keller Wall Price |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5251 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Denton | Tarrant | Tier 4 |  |  |  |  | 2037, 12038, 12307, 566, 1852, 1854, 1856, 1857, 2027, 2033, 2034, 2036, 2038, 2058, 11857, 15100, 15101 | N |  |  | 0 | 52845 | 51243
4804 | Wichita Falls South 345/138 kV autotransformer | Install autotransformer |  | Wichita Falls South |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4010 | 2023-05-15 |  | 345 | 0 | 0 | 600 |  | Archer |  | Tier 3 |  |  |  |  | 11464, 11465, 1422, 1425, 1464 | N | N |  |  | 12410 | 4804
50890 | Port Lavaca: Station Rebuild | Port Lavaca: Station Rebuild |  | Port Lavaca |  | Planned | 1057 - 1230 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3787 | 2023-05-30 |  | 69 | 0 | 37.81 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | 8135 | N | N |  | 0 | 50891 | 50890
45513 | Santo Nino - Wormser: 138 kV Line Rebuild | Rebuild Santo Nino - Wormser 138 kV line with 795 ACSS | CANCELLED | Santo Nino | Wormser | Conceptual | 991 - 1169 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3745 | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8295, 8649, 8653 | N | N |  | 0 | 45514 | 45513
5646 | Buena Vista to Picacho, rebuild 138 kV line | Rebuild Buena Vista to Picacho 138 kV line |  | Buena Vista | Picacho | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2023-08-01 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8186 | N | N |  |  | 13380 | 5646
6755 | Stratton: Add Cap Bank | Add 14.4Mvar Cap Bank at Stratton 138kV Substation | CANCELLED | Stratton |  | Planned | 903 - 1081 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3687 | 2023-12-31 |  | 138 | 0 | 0 | 0 | 0,14.4 | Nueces |  | Tier 4 |  |  |  |  | 8514 | N | N |  |  | 14548 | 6755
61467 | Merrilltown Substation Addition | New 138 kV station - Oncor load | [5 empty] | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-03-24 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson | Williamson | Tier 4 |  |  |  |  | 9230, 9231, 9223, 9224 | N |  |  | 0 | 61468 | 61467
5645 | Hamilton Road to Picacho, rebuild 138 kV line | Rebuild Hamilton Road to Picacho 138 kV line |  | Hamilton Road | Picacho | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-06-01 |  | 138 | 0 | 8.8 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8255, 8684 | N | N |  |  | 13379 | 5645
50876 | Port Lavaca - Victoria: Line Rebuild | Port Lavaca - Victoria: Line Rebuild | Update Schedule | Port Lavaca | Victoria | Planned | 1054 - 1227 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3782 | 2025-03-30 |  | 69 | 0 | 29 | 0 |  | Calhoun | Victoria | Tier 3 |  |  |  |  | 8135, 8136, 8169 | N | N |  | 0 | 50877 | 50876
61451 | La Vernia Substation | Replace T2, 20 MVA with a 40MVA dual high-dual low |  | La Vernia | La Vernia | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.or |  | 2025-05-16 |  | 138 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7614 | N | N |  | 0 | 61452 | 61451
48854 | Adds Annova and Port South Bus and lines | Adds Annova and Port South buses, lines to connect Annova to Port South, line from HWY 511 to Port South, and reconnects line from S Carbide to HWY 511 into Port South |  | Annova LNG | Port South | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2025-06-01 |  | 138 | 22.1 | 0 | 0 | 0,120 | Cameron | Cameron | Tier 4 |  |  |  |  | 5775, 5776, 5767, 8337 | N | N |  | 0 | 48855 | 48854
44870 | Charlotte 69 kV Station | Charlotte 69 kV Station: Add Cap Bank |  | Charlotte | - | Planned | 976 - 1154 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3734 | 2027-07-01 |  | 69 | 0 | 0 | 0 | 0,7.2 | Atascosa |  | Tier 3 | [5 empty] | N | N |  | 0 | 44871 | 44870
4490 | LaPalma: Add 2nd 345/138 kV autotransformer | Add 345/138 kV autotransformer capacity at LaPalma | CANCELLED | LaPalma |  |  | 710 - 0880 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 2904 | 2027-09-30 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 4 |  |  |  |  | 8356, 8317, 8314 | N | N |  |  | 12067 | 4490
6930 | New Paloma Substation | Adds new station and short line from Midstream |  | Midstream | Paloma | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2029-06-01 |  | 138 | 0.9 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5644, 5643 | N | N |  |  | 14749 | 6930
6743 | Magellan Tank Farm: LCRA Interconnect | Add 138kV Tie Line between Navigation 138kV substation and Magellan's 138kV substation. Add Metering at Magellan's Substation. | Cancelled | Navigation | Magellan |  | 905 - 1083 | AEP TCC/LCRA | Michael Glueck bcogan@aep.com 918-599-2857 | 3689 | 2029-07-01 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 78460 | N | Y |  |  | 14536 | 6743

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2021-E1 | Nacogdoches Southeast Switch - Redland Switch Project | Oncor | 2023
2016-N1 | Kiamichi Energy Facility (140077) 345-kV Reactor Addition | KIOWA POWER PARTNERS LLC (RE) | 2024 min
2021-N1 | Bowman 345/138-kV Transformer Upgrades | Oncor | 2023
2021-N2 | City View (1483) – Ceramic (1485) 138-kV Line Terminal Equipment Upgrade | Oncor | 2023
2021-N3 | Wichita Falls (1448) to Fisher Road (1427) 138-kV Line Upgrade | Oncor | 2023
2021-N4 | Ceramic (1485) - Pleasant Valley Switch (1450) 138-kV Line Upgrade | Oncor | 2023
2021-NC1 | Mcgregor Phillips Tap (3594) - MooreMill (3601) - Temple Elm Creek (13662) 138-kV Line Upgrades | Oncor | 2023
2021-NC2 | Pebble Creek Area Upgrade Project | Oncor | 2023
2021-NC3 | Kleberg Tap (3077) -Seagoville (3076) 138-kV Line Upgrades | Oncor | 2023
2021-NC4 | Cedarhill Switch (2422) - Fish Creek Switch (2491) 138-kV Line Upgrade | Oncor | 2024
2021-NC5 | Belton (3610) – Belton Southwest (13610) 138-kV Line Upgrade | Oncor | 2023
2021-NC6 | New Epco 345/138-kV Station | Oncor | 2023
2021-NC7 | Liggett (1926) to Norwood (2406) 138 to 345-kV Line Conversion | Oncor | 2023
2021-NC8 | Roanoke Area Upgrade Project | Oncor | 2023
2021-NC9 | Sargant (2941) – Saint Augustine (2951) 138-kV Line Upgrade | Oncor | 2023
2021-NC10 | Southlake (2020) 138-kV Capacitor Addition | Oncor | 2023
2020-NC15 | Sargant (2947) – East Levee (2482) 138-kV Line Upgrade | Oncor | 2023
2020-NC19 | Cedar Crest (2493) to Dealey (2842) to West Levee (2400) 138-kV Line Upgrades | Oncor | 2023
2020-NC25 | Royse Switch (2472) - Oates (831) 138-kV Line Upgrades | Oncor | 2023 | 2023-05-15 | Planned | 59745
2021-S1 | Rio Hondo (8319) - Val Verde (5769) and and Wesmer ( 8347) -> Pantera ( 8033) 138-kV Line Upgrades | STEC, AEP | 2023
2021-S2 | LA Palma (8314) – Haine Dr (8322) – Oleander (80022) 138-kV Line Upgrades | AEP | 2023
2021-S3 | Celanese Bishop ( 8714) - Kleberg ( 8615), Nelson Sharpe (85007) - Celanese Bishop ( 8516) 138-kV Line Upgrades | AEP | 2026
2021-S4 | Harlingen ( 8327) - North Mercedes ( 8358) 138-kV Line Terminal Equipment Upgrade | AEP, LCRA TSC | 2027
2021-S5 | Dupont Switch Area Line Upgrades | AEP | 2027
2021-SC1 | Hamwolf (5187) – Med_Ctr (5300) 138-kV Line Upgrades | CPS | 2026
2021-SC2 | Medinabs (5305) – 36th_st (5427) 138-kV Line Upgrades | CPS | 2026
2021-SC3 | Howard and Beck Road 345-kV Project | CPS, STEC | 2026
2021-FW1 | Barrila Loop 69-kV to 138-kV Line Conversion | AEP | 2023
2021-FW2 | Yucca - Wolfcamp - Courtney Creek 69-kV to 138-kV Line Conversion | Oncor | 2023
2021-FW3 | Spaberry - Midkiff 69-kV to 138-kV Line Conversion | Oncor | 2024
2021-FW4 | Rio Pecos - Rankin - Texon Tap - Atlantic Best Tap - Kemper Tap - Big Lake 69-kV to 138-kV Line Conversion | AEP | 2023
2021-FW5 | Caymus TNP - Gas Pad 138-kV Line and Caymus TNP - Caymus Compressor TNP Line Terminal Equipment Upgrade | AEP | 2023
2021-FW6 | TNMP Monument Draw to Monument Draw Gray Oak 138-kV Line Terminal Equipment Upgrade | TNMP | 2026
2021-FW7 | TNMP Flat Top 138/25-kV Transformer Upgrade | TNMP | 2023
2021-FW8 | TNMP Wink - TNMP California 69-kV to 138-kV Line Conversion | TNMP | 2026
2021-FW9 | Cap Bank (90 Mvar) Addition at New Load Bus 90021 | New | 2023
2021-FW10 | Cap Bank (90 Mvar) Addition at New Load Bus 90012 | New | 2024
2021-FW11 | Lynx to Tombstone 138-kV Line Upgrade | AEP | 2027
2021-FW12 | Moss Switch to Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2021-FW13 | TNMP Wink to AA Pipeline Tap to Monument Draw Tap 138-kV Line Upgrade | TNMP | 2026
2021-FW14 | Cap bank (90 Mvar) Addition at New Load Bus 90008 | New | 2026
2021-FW15 | Bearkat - North McCamey - Sand Lake 345-kV Double Circuit Line Addition | LCRA TSC, Oncor, WETT | 2026
2021-FW16 | 16th Street TNP - Fort Stockton TNP 69-kV Line Upgrade | TNMP | 2023
2021-FW17 | Fort Stocton Plant to Leon Creek 138-kV Line Upgrade | AEP, TNMP | 2027
2021-FW18 | Quail Switch - Odessa EHV Switch 345-kV Line Upgrade | Oncor | 2023
2021-FW19 | Morgan Creek SES - Longshore Switch 345-kV Line Upgrade | Oncor | 2027
2021-FW20 | Lamesa - Key Sub - Gail Sub - Willow Valley Switch 138-kV Line Upgrade | Oncor | 2023
2021-FW21 | Lamesa - Jim Payne POI 138-kV Line Upgrade | Oncor | 2024
2021-FW22 | IH20 345-kV Substation and New 345/138-kV Transformers Addition; and Solstice - Sand Lake 345-kV Existing Double-Circuit Line Loop in at the New IH20 345-kV Substation | TNMP, AEP, Oncor | 2027
2021-FW23 | Stanton East to Big Spring 138-kV Line Upgrade | Oncor | 2023
2021-FW24 | Adobe Meadow to Midland East 138-kV Line Upgrade | Oncor | 2023
2021-FW25 | Odessa EHV Switch to ONCOR New Tap 11121 138-kV Line Upgrade | Oncor | 2024
2021-FW26 | Holt Switch to Turnbaugh Corner Switch to Scharbauer POI 138-kV Line Upgrade | Oncor | 2024
2021-W1 | Cassava - San Angelo Concho 69-kV to 138-kV Line Conversion | AEP | 2024
2021-W2 | Morgan Creek - McDonald 138-kV Line Upgrade | Oncor | 2023
2021-W3 | Scurry - Kndrsacrc - Oncor 90041 Tap 138-kV Line Upgrade | Oncor | 2024
2021-W4 | Oncor 90041 Tap - Knapp - Bluff Creek Switch 138-kV Line Upgrade | Oncor | 2026
2021-W5 | Sacroc - Deep Creek Sub 138-kV Line Upgrade | Oncor | 2027
2021-W6 | Twin Buttes - Hargrove - Pumpjack - Jerry 138-kV Line Upgrade | AEP, LCRA TSC | 2023
2021-W7 | San Angelo Highland Street to San Angelo South Tap to San Angelo Power Station 138-kV Line Upgrade | AEP | 2026
2021-W8 | San Angelo Red Creek to San Angelo Ben Ficklin 138-kV Line Upgrade | AEP | 2027
2021-W9 | San Angelo Paulann to San Angelo North 138-kV Line Upgrade | AEP | 2026
2021-W10 | San Angelo Red Creek to San Angelo Coke Street to Rusthill 138-kV Line Upgrade | AEP | 2024
2021-W11 | Downie Switching Station to Reading 138-kV Line Upgrade | STEC, AEP | 2024
2021-W12 | Cap bank (28.8 Mvar) Addition at Hargrove Station | AEP | 2027
2021-WFW1 | Big Lake - Cassava 69-kV to 138-kV Line Conversion | AEP | 2026
2021-WFW2 | Midland County Northwest to Midland East to Falcon Seaboard to Morgan Creek to Tonkawaw Switch 345-kV Existing Circuit Rebuild and Second Circuit Addition | Oncor | 2023

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Cindy Miller | Camiller2@aep.com | Cindy Miller: 918 599 2891 | Glen Reed; David Kidd; Brad Myers; Mabel See; Mike Forcum; Doug Lee; Daniel Lyons; Bob Lager; Mina Turner; Lisa Kelso; Carole Myser | gareed@aep.com; dekidd@aep.com; blmyers@aep.com; msee@aep.com; mlforcum@aep.com; dnlyons@aep.com; dlee@aep.com; rjlager@aep.com; myturner@aep.com; lokelso@aep.com; camyser@aep.com | David Kidd: 918 599 2637 Glen Reed: 918 599 2664 Brad Myers: 918 599 2690
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Hunt, Dandy; Brion Ryan | dandy.hunt@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | Reza:512 322 6740 Dandy:512 322 6748 Brion: 512-322-6879
BPUB | Primary | Ramon Sanz | rsanz@brownsville-pub.com; | Ramon: 956 983 6203 | James McCann | jmccann@brownsville-pub.com; | James: 956 983 6204
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Dwight Beckman | dbeckman@brazoselectric.com | Dwight: 254 750 6373 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | Edward Lopez | elopez@btutilities.com | Edward: 979 821 5697 | David Hering | dhering@btutilities.com | David: 979 821 5652
CNP | Primary & Secondary | Wesley Woitt | wesley.woitt@centerpointenergy.com | Wesley Woitt: 713-207-2760 | Yingying Huang; Raja Sekhar Kakarla; Cody Mann | Yingying.Huang@centerpointenergy.com; rajasekhar.kakarla@centerpointenergy.com; cody.mann@centerpointenergy.com | Yingying Huang: 713-207-2831 Raja Sekhar Kakarla: 713-207-3614 Cody Mann: 713-207-3149
COCS | Primary | Wesley Gray | wgray@cstx.gov | Wesley: 979 764 3434 | Timothy Crabb, Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | Basileo Rocha, Sunil Dhakal | bdrocha@cpsenergy.com; SDhakal@cpsenergy.com | Basileo: 210 353 4933 Sunil: 210 353 2008 | Kenneth Bowen Trieu Vo | kbowen@cpsenergy.com; tvo@cpsenergy.com; | Kenneth: 210 353 4142 Trieu: 210 353 2127
CTT (Cross Texas Transmission) | Primary & Secondary | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310 | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310
DENTON | Primary & Secondary | Chuck Sears | Chuck.Sears@cityofdenton.com; | Chuck: 940 349 7111 | Brent Heath | brent.heath@cityofdenton.com; | Brent: 940 349 7180
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Grubbs, David; Juan Santos | Dgrubbs@gpltexas.org; Jsantos@gpltexas.org | David: 972 205 2664 Juan: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; BEC (Bandera); BBEC; CTEC; GVEC; NBU; PEC; SBEC; RGEC | Primary & Secondary | Dylan Preas | dylan.preas@lcra.org | Dylan: 512-578-4514 | Naved Khan | naved..khan@lcra.ord | Naved: 512-578-4176
Lone Star | Primary & Secondary | Chenyan Guo | chenyan.guo@fpl.com | Chenyan: 561-304-5692 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Charles Saker | charles.saker@oncor.com | Charles: 214-743-6896 | Paul Bell | paul.bell@oncor.com | Paul: 214-743-6676
Sharyland Utilities | Primary & Secondary | Brad Schwarz | bschwarz@huntpower.com | Brad: 512-289-7425 | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243
STEC | Primary & Secondary | Doug Evans | devans@stec.org | Doug: 361 485 6459 | Paul Person Loretta Gonzalez | pperson@stec.org; lgonzalez@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Ahmad Saboor | asaboor@texasmpa.org | Ahmad: 936 873 1104 | Frank Owens | fowens@texasmpa.org; | Frank: 936 873 1120
TNMP | Primary & Secondary | Robert Lona | Robert.Lona@tnmp.com | Robert: 281-581-4732 | Anthony, Hudson Ballay, Dustin Cloninger, Ross | Anthony.Hudson@tnmp.com; Dustin.Ballay@tnmp.com; Ross.Cloninger@tnmp.com; | Anthony: 281 581 4712 Dustin:281 581 4730 Ross:281 581 4733
Wind Energy Texas Transmission (WETT) | Primary | Chris Ramirez | cramirez@wettllc.com | Chris: 737-218-4525 | Christina Minchew | cminchew@wettllc.com | Christina: 737-218-4520