## ImprovementCostSummary02232016
| Project Cost |  |  |  |  | XFMR MVA
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total
2015 | 154360000 | 588826054 | 182173454 | 925359508 | 2015 | 5622 | 1657 | 240 | 7519 | For ROS and BOD Reports
2016 | 1119329687 | 877102607 | 197459865 | 2193892159 | 2016 | 7047 | 1550 | 90 | 8687 | ·All Projects (in engineering, routing, licensing and construction): |  |  |  | 6807247064
2017 | 296726667 | 1139172877 | 199111000 | 1635010544 | 2017 | 7482 | 870 | 330 | 8682 | ·Transmission Projects Energized in 2016: |  |  |  | 148997000
2018 | 788736061 | 967109000 | 148527000 | 1904372061 | 2018 | 4180 | 650 | 0 | 4830
2019 | 104866000 | 458465200 | 117465000 | 680796200 | 2019 | 814 | 288 | 0 | 1102
2020 | 76000000 | 150720000 | 51100000 | 277820000 | 2020 | 1800 | 45 | 0 | 1845
2021 | 28800000 | 137492000 | 5900000 | 172192000 | 2021 | 1200 | 0 | 0 | 1200
2022+ | 13000000 | 44050000 | 35111100 | 92161100 | 2022+ | 600 | 0 | 0 | 600
2016COM | 14700000 | 122897000 | 11400000 | 148997000 | 2016COM | 0 | 180 | 0 | 180
2016PLAN | 1104629687 | 754205607 | 186059865 | 2044895159 | 2016PLAN | 7047 | 1370 | 90 | 8507
2015-2022+ | 2581818415 | 4362937738 | 936847419 | 7881603572 | 2015-2022+ | 28745 | 5060 | 660 | 34465
2015-2016 | 1273689687 | 1465928661 | 379633319 | 3119251667 | 2015-2016 | 12669 | 3207 | 330 | 16206
2017-2022+ | 1308128728 | 2897009077 | 557214100 | 4762351905 | 2017-2022+ | 16076 | 1853 | 330 | 18259
| Circuit Miles New |  |  |  | Circuit Miles Rebuilt, Reconductored or Upgraded |  |  |  |  | Total
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total | 345 | 138 | 69 | Total
2015 | 44.3 | 120.34 | 2.8 | 167.44 | 2015 | 54.2 | 474.79 | 144.66 | 673.65 | 98.5 | 595.13 | 147.46 | 841.09
2016 | 360.138 | 326.6 | 15.9 | 702.638 | 2016 | 145.39 | 605.27 | 203.8 | 954.46 | 505.528 | 931.87 | 219.7 | 1657.098
2017 | 8 | 335.31 | 0.15 | 343.46 | 2017 | 62 | 831.891 | 178.93 | 1072.821 | 70 | 1167.201 | 179.08 | 1416.281
2018 | 299 | 163.92 | 0 | 462.92 | 2018 | 89 | 908.75 | 175.21 | 1172.96 | 388 | 1072.67 | 175.21 | 1635.88
2019 | 18 | 91.8 | 33.11 | 142.91 | 2019 | 32.8 | 233.59 | 65.42 | 331.81 | 50.8 | 325.39 | 98.53 | 474.72
2020 | 20 | 0.2 | 0 | 20.2 | 2020 | 0 | 106.77 | 49.8 | 156.57 | 20 | 106.97 | 49.8 | 176.77
2021 | 0 | 33.4 | 0 | 33.4 | 2021 | 0 | 132.11 | 15.8 | 147.91 | 0 | 165.51 | 15.8 | 181.31
2022+ | 4 | 14.8 | 9 | 27.8 | 2022+ | 67.96 | 32.3 | 14.6 | 114.86 | 71.96 | 47.1 | 23.6 | 142.66
2016COM | 0 | 88.8 | 0 | 88.8 | 2016COM | 0 | 114.2 | 6.1 | 120.3 | 0 | 203 | 6.1 | 209.1
2016PLAN | 360.138 | 237.8 | 15.9 | 613.838 | 2016PLAN | 145.39 | 491.07 | 197.7 | 834.16 | 505.528 | 728.87 | 213.6 | 1447.998
2015-2022+ | 753.438 | 1086.37 | 60.96 | 1900.768 | 2015-2022+ | 451.35 | 3325.471 | 848.22 | 4625.041 | 1204.788 | 4411.841 | 909.18 | 6525.809
2015-2016 | 404.438 | 446.94 | 18.7 | 870.078 | 2015-2016 | 199.59 | 1080.06 | 348.46 | 1628.11
2017-2022+ | 349 | 639.43 | 42.26 | 1030.69 | 2017-2022+ | 251.76 | 2245.411 | 499.76 | 2996.931

## FutureTPIT020116NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2016
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
15TPIT0035A | Velasco to West Columbia Upgrades and Conversion to 138kV | Remove 69kV facilities at Velasco. | Delay in project schedule | Velasco |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-02-03 |  | 138 | 0 | 0 | -93 |  | Brazoria |  | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43370, 42640, 43140, 49032, 43360 | Y | N |  |  | 2485 | 2388
17TPIT0007 | Gillespie to Pointer: Rebuild 69 kV line | Rebuild Gillespie to Pointer 69 kV line with 959.6 ACSR |  | Gillespie | Pointer | In-Service | 568 - 0742 | AEP TNC | Aaron Schwerman myturner@aep.com 918-599-2437 | 2579 | 2016-02-05 |  | 69 | 0 | 6.7 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 6113, 60382, 60346 | Y | N |  |  | 2912 | 2757
4798 | GSEC_4798_Add_Plains_Pandale_Sub |  |  |  |  | Planned |  | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2016-02-16 |  | 138 | 0 | 0 | 10 |  |  |  | Tier 4 |  |  |  | 60388, 60389 | N |  |  |  | 5224 | 4798
3868 | Butman Substation | Construct the new Butman substation on the existing LCRA TSC Abilene South to Eskota 138-kV transmission line (T470). |  | Butman | Abilene S / Eskota | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014313 | 2016-02-18 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  | 76318, 76317, 76319 | Y | N |  |  | 4156 | 3868
3938A | Angleton Area Ckt.26 & 82 Upgrades | Upgrade 138kV Ckt.26 Angleton to STRATT to increase thermal ratings. | Delay in Project Schedule | Angleton | STRATT | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1055 | 2016-02-26 |  | 138 | 0 | 13.8 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 42110, 43300 | Y | N |  |  | 4249 | 3938
3938B | Angleton Area Ckt.26 & 82 Upgrades | Upgrade 138kV Ckt.26 STRATT to SINTEK to increase thermal ratings. | Delay in Project Schedule | STRATT | SINTEK | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1055 | 2016-02-27 |  | 138 | 0 | 6.4 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43240, 43300 | Y | N |  |  | 4250 | 3938
3872 | MARINE 138kV Substation | Construct service to new 138kV MARINE customer-owned substation. Loop through Ckt.59 Surfside to Quintana. | Delay in project schedule | MARINE | Surfside/Quintana | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 55 | 2016-02-28 |  | 138 | 1.5 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  | 43155, 43360, 43315, 43435 | Y | N |  |  | 4160 | 3872
3938C | Angleton Area Ckt.26 & 82 Upgrades | Upgrade 138kV Ckt.82 Angleton to Richwood to increase thermal ratings. | Delay in Project Schedule | Angleton | Richwood | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1055 | 2016-02-28 |  | 138 | 0 | 14.2 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 42110, 43150 | Y | N |  | Cost Included in TPIT Project 3938A | 4251 | 3938
4183 | Jordan Cap Bank | Move existing Mont Belvieu cap bank #2 to Jordan 138kV substation | Change in project schedule | Jordan |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 95 | 2016-02-28 |  | 138 | 0 | 0 | 0 | 0,6.7 | Chambers |  | Tier 4 |  |  |  | 40856, 41114, 40155, 40855, 41111 | Y | N |  |  | 4538 | 4183
4525 | HO Clarke to Heights Ckt.34 | Upgrade 69kV Ckt.34 HO Clarke to Heights to increase thermal ratings | Accelerated project schedule | HO Clarke | Heights | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-02-28 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47165, 47680 | Y | N |  |  | 4922 | 4525
3938D | Angleton Area Ckt.26 & 82 Upgrades | Upgrade 138kV Ckt.82 Richwood to Cavern to increase thermal ratings. | Delay in Project Schedule | Richwood | Cavern | Under Construction |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1055 | 2016-02-29 |  | 138 | 0 | 5.4 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43150, 43330 | Y | N |  | Cost Included in TPIT Project 3938A | 4252 | 3938
4854 | Tunas Creek Substation Addition | Provide transmission service for a generator (15INR0070_1) off T449 138-kV line between Rio Pecos and Indian Mesa Substations. |  | RIO PECOS | INDIAN MESA | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014769 | 2016-03-08 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 76580, 6584, 6601 | Y | N |  |  | 5281 | 4854
4855 | Mesa View Circuit Breaker Addition | Add a new Long Loop Substation with circuit breakers adjacent to Mesa View Substation between Mesa View Switchyard and West Yates Switch Substations |  | Mesa View Switchyard | West Yates Switch | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014332 | 2016-03-17 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 76583, 6583, 76013, 76582 | Y | N |  |  | 5282 | 4855
14TPIT0050 | Lon Hill to North Edinburg: Reconductor 345kV Line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo | UPDATED INSV DATE | Lon Hill | North Edinburg | Under Construction | 071 - 0281 | AEP TCC | Michael Glueck dnlyons@aep.com 918-599-2698 | 3183 | 2016-03-31 |  | 345 | 0 | 122.88 | 0 |  | Nueces | Hidalgo | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 5660, 8455, 8452, 8905 | Y | N |  |  | 1420 | 1419
15TPIT0024 | Lon Hill to Nelson Sharpe: Reconductor 345kV Line | Reconductor Lon Hill to North Edinburg and Lon Hill to Rio Hondo 345kV lines, Replace Series Capacitors at North Edinburg and Rio Hondo | UPDATED INSV DATE | Lon Hill | Nelson Sharpe | Under Construction | 071 - 0281 | AEP TCC | Michael Glueck dnlyons@aep.com 918-599-2698 | 3180 | 2016-03-31 |  | 345 | 0 | 20.81 | 0 |  | Nueces | Kleberg | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-01 | 8455, 85000 | Y | N |  |  | 1422 | 1421
16TPIT0023 | South McAllen - Stewart Road: Rebuild 138kV Line | Rebuild South McAllen - Stewart Road 138kV Line |  | South McAllen | Stewart Road | Under Construction | 601 - 0763 | AEP TCC | Aaron Schwerman DNLYONS@AEP.COM 918-599-2698 | 3470 | 2016-03-31 |  | 138 | 0 | 9.8 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8371, 8758, 8951 | Y | N |  | 0 | 1945 | 1896
16TPIT0037 | Rebuild Orange Grove to Casa Blanca | Rebuild 4/0 ACSR 69 kV to 795 ACSR circuit on 138 kV capable structures. |  | Orange Grove | Casa Blanca | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-03-31 |  | 69 | 0 | 6.7 | 0 |  | Jim Wells | Jim Wells | Tier 1 | 2012-09-05 | 2013-01-31 | 2013-03-12 | 5662, 8166 | Y | N |  |  | 3116 | 2947
3676 | Foxtail: Build 345 kV station | Interconnect Green Pastures Wind Farm at Foxtail to connect Green Pastures and Vertigo to the Oklaunion to Mulberry Creek 345 kV line | Status Update | Foxtail |  | Under Construction | 648 - 0817 | AEP TNC | Gregory Gibbs myturner@aep.com 918-599-2437 | 1813 | 2016-03-31 |  | 345 | 0 | 0 | 0 |  | Baylor |  | Tier 4 |  |  |  | 6076, 6100, 6235 | Y | N |  |  | 3913 | 3676
3880 | GSEC_3880_Add_Butman_Sub |  | NA |  |  | Under Construction | NA | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2016-03-31 |  | 138 | 0 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 76318 | Y | N |  | Approximate energization date of 10/2015 | 4170 | 3880
3887 | Relocate Seguin Auto to Nixon | Relocate 138/69 kV Auto at Seguin to LCRA Nixon, associated GCBs, Bus |  | LCRA Nixon |  | Planned |  | LCRATSC/GVEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2016-03-31 |  | 138 | 0 | 0 | 40 |  | Gonzales |  | Tier 1 | 2012-09-01 | 2012-10-31 | 2013-03-10 | 7617, 7621 | Y | N |  |  | 4177 | 3887
3982 | EF 90 Corpus Tank Farm | EF 90 Corpus Tank Farm - Kepler 69kV substation: Costruct substation | New | Koch Upriver | Valero West | Planned | 615 - 0783 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3498 | 2016-03-31 |  | 69 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8217, 8240, 8469, 8477 | Y | N |  |  | 4307 | 3982
4180 | Cinnamon: Build 69 kV station | Construct new Cinnamon tap on the North San Angelo to San Angelo Grape Creek Tap 69 kV line | Schedule Update | Cinnamon |  | Under Construction | 695 - 0865 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2809 | 2016-03-31 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  | 60380, 6459, 6462 | Y | N |  |  | 4535 | 4180
4296 | Midkiff 138 kV Switching Station POI | Establish a 138 kV point of interconnection (POI) |  | Midkiff |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8273 | 2016-03-31 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | Y | N |  |  | 4677 | 4296
4748 | Corral: Build 138 kV station | Construct 138 kV POD box bay for customer interconnection between Comstock and Illinois #4 | Description and Schedule Update | Corral |  | Planned | 720 - 0902 | ETT | Eric Scott myturner@aep.com 918-599-2437 | 2611 | 2016-03-31 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 60388, 60389, 6564, 8683 | Y | N |  |  | 5168 | 4748
4722 | Tortuga: Temporary Hard Tap | Construct hardtap on the Gila - Upriver (Koch) 138 kV line |  | Gila | Upriver (Koch) | Planned | 719 - 0901 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3555 | 2016-03-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 81680, 8467, 80260 | Y |  |  |  | 5213 | 4722
15TPIT0051 | Kenedy Switch - Nixon - Seguin Transmission Line Upgrade | Upgrade the 54.2 mile Kenedy Switch (8184) - Nixon (78580) - Deer Creek (New) (7595) from 69kV to 138kV 795 ACSR Drake, 223 MVA. |  | Kenedy Switch | Deer Creek | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1012640 | 2016-04-01 |  | 138 | 0 | 54.2 | 0 |  | Karnes | Guadalupe | Tier 1 | 2012-09-01 | 2012-10-30 | 2013-03-31 | 78580 | Y | N |  |  | 3969 | 3725
4535 | Add new 138kV Natural Dam Station |  |  | Natural Dam | Natural Dam | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-04-01 |  | 138 | 0 | 0 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79509 | Y | N |  |  | 4937 | 4535
4697 | Adding Blue Acre station & load |  |  | Yosemite | South Midland | Planned |  | SLU | Bradley Schwarz 512-289-7425 |  | 2016-04-01 |  | 138 | 0.9 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 79609, 79610, 79615 | Y | N |  |  | 5107 | 4697
14TPIT0080 | Oran to Advance Rebuild | Rebuild Oran to Advance with 959 ACSS, 138 kV construction (operate at 69 kV) |  | Oran | Advance | Planned |  | BEPC | Dwight Beckman kdye@brazoselectric.com 254-750-6373 | 12010 | 2016-04-04 |  | 69 | 0 | 13.7 | 0 |  | Palo Pinto | Parker | Tier 4 |  |  |  | 518, 519, 785 | Y | N |  |  | 2311 | 2238
3267B | Rebuild ERioHondoTo Paredes to Central Avenue 138 kV line | Rebuild Paredes Switch to Central Avenue |  | Central Avenue | Paredes Switch | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-04-09 |  | 138 | 0 | 21 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  | 5761, 5766 | Y | N |  | Cost in other phase of project. | 4818 | 3267
4639 | Red Gate: Build new 138 kV temporary tap | Interconnect STEC Red Gate Power Plant at Temporary Tap on the Falfurrias to North Edinburg 138 kV line |  | Falfurrias | North Edinburg | Planned | 716 - 0897 | AEP TCC | Michael Tallon dnlyons@aep.com 918-599-2698 | 3551 | 2016-04-15 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 8380, 8510, 8896, 88380 | Y | Y |  |  | 5040 | 4639
4744 | Prairie View Substation 69 KV breaker replacement | Replace an oil breaker with a new 145 KV Siemens Breaker due to test results being marginal | Need to replace prior to next testing cycle | Prairie View | Sunnyside | Under Construction |  | SBEC | Don Roberts droberts@sbec.org | WO#15-5394 | 2016-04-15 |  | 69 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  | 7666 | Y | N |  | 69 KV oil Breaker testing results have deteriorated and requires replacing | 5164 | 4744
4555 | Gillette Substation | Construct the new 138-kV Gillette substation (78582) on the existing LCRA TSC Milton (78583) to Nixon AE (78580) 138-kV transmission line. |  | Gillette | Milton / NixonAE | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015955 | 2016-04-20 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 78582, 78580, 78583 | Y | N |  |  | 4959 | 4555
15TPIT0035G | Velasco to West Columbia Upgrades and Conversion to 138kV | Convert Retrieve substation to 138kV and energize with existing Ckt. 02 Lake Jackson to West Columbia. Upgrade Ckt. 02 Lake Jackson to Retrieve and parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | Lake Jackson | Retrieve | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-04-25 |  | 138 | 0 | 5.34 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43140, 43145, 42880, 43380, 43390 | Y | N |  | Cost included in project 15TPIT0035A. | 5538 | 2388
15TPIT0035B | Velasco to West Columbia Upgrades and Conversion to 138kV | Upgrade Ckt. 02 Retrieve to West Columbia. Parallel bundle a portion of the line with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | Retrieve | West Columbia | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-04-26 |  | 138 | 0 | 11.9 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43145, 43380 | Y | N |  | Cost included in project 15TPIT0035A. | 2486 | 2388
15TPIT0035C | Velasco to West Columbia Upgrades and Conversion to 138kV | Parallel bundle a portion of Ckt. 02 Hofman to Lake Jackson with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | Hofman | Lake Jackson | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-04-27 |  | 138 | 0 | 3.9 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42810, 42880 | Y | N |  | Cost included in project 15TPIT0035A. | 2487 | 2388
15TPIT0035D | Velasco to West Columbia Upgrades and Conversion to 138kV | Parallel bundle a portion of Ckt. 02 BASF to Hofman with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | BASF | Hofman | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-04-28 |  | 138 | 0 | 0.84 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42150, 42810 | Y | N |  | Cost included in project 15TPIT0035A. | 2488 | 2388
15TPIT0035E | Velasco to West Columbia Upgrades and Conversion to 138kV | Parallel bundle a portion of Ckt. 02 Brazosport to Velasco with converted 69kV Ckt.47 Velasco to West Columbia. | Delay in project schedule | Brazosport | Velasco | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-04-29 |  | 138 | 0 | 1.32 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42150, 42210, 42215, 43222, 43360 | Y | N |  | Cost included in project 15TPIT0035A. | 2489 | 2388
14TPIT0120 | Moore Road 138kV Substation | Build new 138kV Moore Road substation. Loop-Tap through Ckt.08 GBY to Uvalde. | Delay in project schedule | Moore Road | Greens Bayou/Uvalde | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-04-30 |  | 138 | 0.6 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40555, 40710, 40990, 41022, 41651 | Y | N |  |  | 3047 | 2873
3503 | Rebuild Seguin-Deer Creek to 138kV | Rebuild 6/1 miles (Capote to Deer Creek, back to Seguin is 138) single Ckt 69 to 138 kV, 795 ACSR, terminals at Seguin and Deer Creek. (This portion of the T-377 line segment will be out of service from Oct 1, 2015 - Mar 31, 2016) |  | Seguin | Deer Creek | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2016-04-30 |  | 138 | 0 | 6.1 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7228, 7595 | Y | N |  |  | 3710 | 3503
15TPIT0055 | Naval Base Station: Add 138/69 kV Auto | Construct new 138 kV line and add tranformation at Naval Base to remove contingency overloads during off-peak maintenance | In Service Update | NAVAL BASE |  | Under Construction | 607 - 0648 | AEP TCC | MICHAEL GLUECK DNLYONS@AEP.COM 918-599-2698 | 3485 | 2016-04-30 |  | 138 |  |  | 220 |  | Nueces |  | Tier 1 | 2012-07-15 | 2012-12-20 | 2013-01-04 | 8997, 8495 | Y | N |  |  | 3721 | 3514
3766 | Asherton Station: Replace 138/69 kV Autotransformer | Upgrade 138/69 kV Auto at Asherton Station | Changed Project Title, Project Description, Transmission Status, PM, Estimates and ISD | ASHERTON |  | Under Construction | 659-0828 | AEP TCC | Aaron Schwerman DNLYONS@AEP.COM 918-599-2698 | 3524 | 2016-04-30 |  | 138 |  |  | 130 |  | Dimmit |  | Tier 4 |  |  |  | 8280, 8283 | Y | N |  |  | 4011 | 3766
4428 | CAMDEN 138kV Substation | Loop Ckt.26 SINTEK to Velasco into new 138kV CAMDEN substation |  | CAMDEN | SINTEK/Velasco | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-04-30 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43365, 43240, 43360 | Y | N |  |  | 4812 | 4428
4522 | Hoefs Road: Build a 69 kV station | Construct new 69 kV in and out substation off the Barrilla Junction to Verhalen line |  | Hoefs Road |  | Planned | 690 - 0860 | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | 2607 | 2016-04-30 |  | 69 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 6654 | Y | N |  |  | 4919 | 4522
5030A | Flat Top Tie with AEP Pig Creek | Rebuild de-energized line from TNMP Flat Top-AEP's new Pig Creek station with 1926 ACSR/TW Cumberland. Convert Flat Top to 138 kV service and install circuit breakers. Switch line out of service from Barilla Draw Tap-Flat Top. |  | 60393 | 38070 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2016-04-30 |  | 138 | 0 | 8.85 | 0 |  | Pecos | Reeves | Tier 3 | 2015-01-13 | 2015-06-19 |  | 38070, 38060, 60393 | Y |  |  | Conductor changed from RPG submittal from 795 ACSR to 1926 ACSR/TW Cumberland. Flat Top station changed from RPG to include up to 5 breakers. | 5498 | 5030
11TPIT0032 | NW Carrollton - Collin second 138 kV circuit |  | Construction schedule change | NW Carrollton | Hebron | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M368 | 2016-04-30 |  | 138 | 21 | 21 | 0 |  | Dallas | Collin | Tier 4 |  |  |  | 12519, 663, 2362, 2363, 2519 | Y | N | 2009-R13 |  | 5719 | 1055
4398 | Razorback: Build new three breaker 138 kV station | Construct new Razorback station along the Uvalde to Castroville (STEC) 138 kV line |  | Uvalde | Castroville STEC | Planned | 611 - 0779 | ETT | Brent Smith dnlyons@aep.com 918-599-2698 | 3494 | 2016-05-01 |  | 138 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 8241, 80241, 5083, 8234 | Y | N |  |  | 4777 | 4398
4545 | Upgrade 138kV Brown - Vealmoor line |  |  | Brown | Vealmoor | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-05-01 |  | 138 | 0 | 15.3 | 0 |  | Martin | Borden | Tier 4 |  |  |  | 79551, 79553, 79600 | Y | N |  |  | 4947 | 4545
4977 | Georgetown East Circuit Breaker Addition | Install four 138-kV circuit breakers at Georgetown East in a ring bus configuration. |  | Georgetown East |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015108 | 2016-05-01 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  | 7528 | Y | N |  |  | 5437 | 4977
4980 | T326 - Wavetrap Upgrade | Replace Wavetrap at Blockhouse Substation on T326 |  | Blockhouse |  | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2016-05-01 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  | 7525, 7527 | Y | N |  |  | 5440 | 4980
4974 | Pleasant Farms Circuit Breaker Addition | Install three 138-kV circuit breakers at Pleasant Farms in a ring bus configuration. |  | Pleasant Farms |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014331 | 2016-05-09 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  | 71230 | Y | N |  |  | 5434 | 4974
3966 | Zorn to Seguin Transmission Line Upgrade | Upgrade the 13.2 miles Zorn (7180) - York Creek (7227) - Seguin (7228) 138kV transmission line to single 1433 Merrimack conductor (478 MVA). |  | Zorn | York Creek - Seguin | Planned | ERCOT RTP # 2013-R83 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014341 | 2016-05-12 |  | 138 | 0 | 13.2 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7180, 7227, 7228 | Y | N |  |  | 4287 | 3966
06TPIT0047 | Elkton - Tyler Northwest 138 kV line | Upgrade existing Elkton - Tyler West 138 kV line section |  | Elkton | Tyler West | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6023-E | 2016-05-15 |  | 138 | 0 | 4 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3106, 3139 | Y | N |  |  | 1434 | 1433
15TPIT0039 | Plano Tennyson Road - McDermott | Upgrade 138 kV line |  | Plano Tennyson Road | McDermott | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4103-E | 2016-05-15 |  | 138 | 0 | 5.3 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 2523, 10011, 2516 | Y | N |  |  | 2346 | 2273
13TPIT0113 | Renner 345/138 kV autotransformer | Replace existing 345/138 kV autotransformer with larger autotransformer |  | Renner |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3099B | 2016-05-15 |  | 345 | 0 | 0 | 600 |  | Collin |  | Tier 4 |  |  |  | 2359, 2358, 16358 | Y | N |  |  | 2826 | 1300
11TPIT0012 | Euless - Grapevine Ball St - Grapevine Jnct 138 kV Line | Reconductor existing double-circuit 138 kV line (Euless - Grapevine Ball Street east circuit and Euless - Grapevine Junction west circuit) | Construction schedule change | Euless | Grapevine Ball Street/Grapevine Junction | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5131-E | 2016-05-15 |  | 138 | 0 | 11.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2014, 2016, 2021, 12012, 12022, 12021, 12040 | Y | N |  | Euless - Highway 360 Substation section by 5/2014 | 3112 | 2943
14TPIT0012 | Mountain Creek - Norwood 138 kV line | Upgrade existing line |  | Mountain Creek | Norwood | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4074-E | 2016-05-15 |  | 138 | 0 | 7.2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2407, 2412, 2805, 12804 | Y | N |  |  | 3263 | 3094
16TPIT0065 | Gresham Road - Nacogdoches 138 kV line | Upgrade existing line |  | Gresham Road | Nacogdoches | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6035-E | 2016-05-15 |  | 138 | 0 | 21.3 | 0 |  | Cherokee | Nacogdoches | Tier 3 | 2015-06-15 | 2015-07-15 |  | 3299, 3300, 3301, 3303 | Y | N |  |  | 3284 | 3115
17TPIT0029 | Tyler Grande - Tyler East 138 kV Line | Upgrade existing line |  | Tyler Grande | Tyler East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6017-E | 2016-05-15 |  | 138 | 0 | 8.2 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3143, 3212, 3214, 3211, 3213 | Y | N |  |  | 3288 | 3119
15TPIT0082 | Collin - Custer (Brazos) 138 kV Line (Oncor's section) | Upgrade existing line |  | Collin | Custer (Brazos) | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R937-E | 2016-05-15 |  | 138 | 0 | 3.5 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 2364, 2365, 2566, 2567 | Y | N |  |  | 3378 | 3207
17TPIT0011 | Carroll Springs 69 kV capacitors | Install shunt capacitor |  | Carroll Springs |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6041-E | 2016-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Anderson | Anderson | Tier 4 |  |  |  | 3270 | Y | N |  |  | 3591 | 3393
14TPIT0011 | Midessa South - Windwood - Midland East 138 kV Line | Upgrade existing line |  | Midessa South | Midland East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8148-E | 2016-05-15 |  | 138 | 0 | 10.4 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1059, 1116, 1117 | Y | N |  |  | 3631 | 3431
4210 | Paris Switch 345/138 kV autotransformer | Replace existing autotransformer |  | Paris Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R959 | 2016-05-15 |  | 345 | 0 | 0 | 600 |  | Lamar |  | Tier 4 |  |  |  | 1692, 1693, 1686 | Y | N |  |  | 4571 | 4210
4216 | Odessa EHV - Spraberry 138 kV Line | Upgrade existing line |  | Odessa EHV | Spraberry | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8257 | 2016-05-15 |  | 138 | 0 | 21.5 | 0 |  | Ector | Midland | Tier 4 |  |  |  | 1027, 1137, 1139, 1329 | Y | N |  |  | 4578 | 4216
4220 | Screwbean 138 kV capacitors | Install shunt capacitors |  | Screwbean |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8224 | 2016-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Culberson |  | Tier 4 |  |  |  | 1095 | Y | N |  |  | 4590 | 4220
4237 | North Andrews - Andrews 69 kV Line | Rebuild existing Means - Fullerton 69 kV line section as a double-circuit line with a 69 kV circuit and a 138 kV circuit |  | Means | Fullerton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8161 | 2016-05-15 |  | 69 | 15.1 | 15.1 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1284, 1159, 1274, 1285 | Y | N |  |  | 4610 | 4237
4239 | Paul Davis - Paul Davis Tap 138 kV Line | Rebuild existing tap line as a double-circuit line |  | McKenzie Draw | Paul Davis Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8220 | 2016-05-15 |  | 138 | 12 | 12 | 0 |  | Dawson | Martin | Tier 4 |  |  |  | 1170, 1168, 1169, 18880 | Y | N |  |  | 4612 | 4239
4273 | Corsicana - Trinidad 69 kV Line | Upgrade existing line |  | Corsicana | Trinidad | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R794 | 2016-05-15 |  | 69 | 0 | 26.5 | 0 |  | Navarro | Henderson | Tier 3 | 2015-06-15 | 2015-08-15 |  | 3128, 3466, 3467, 3468, 3469 | Y | N |  |  | 4647 | 4273
4212 | Lamar Blossom 69 kV capacitors | Install shunt capacitors |  | Lamar Blossom |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R974 | 2016-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Lamar |  | Tier 4 |  |  |  | 1772 | Y | N |  |  | 4651 | 4212
4277 | Lott 69 kV capacitors | Install shunt capacitors |  | Lott |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R791 | 2016-05-15 |  | 69 | 0 | 0 | 0 | 0,9.2 | Falls |  | Tier 4 |  |  |  | 3642 | Y | N |  |  | 4652 | 4277
4527 | Fullerton Switching Station | Construct new switching station |  | Fullerton |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8277 | 2016-05-15 |  | 69 | 0 | 0 | 0 |  | Andrews |  | Tier 4 |  |  |  | 1272, 1274, 1284 | Y | N |  |  | 4927 | 4527
4529 | Fullerton - North Andrews 138 kV Line | Rebuild existing 69 kV line section as a double-circuit line with a 69 kV circuit and a 138 kV circuit |  | Fullerton | North Andrews | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8294 | 2016-05-15 |  | 138 | 21.7 | 6.9 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1277, 1159, 1160, 1267, 1272 | Y | N |  |  | 4929 | 4529
4737 | Wichita Fallls South | Upgrade terminal equipment on Wichita Falls South -Windthorst 138 kV Line |  | Wichita Falls S |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4003 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Archer |  | Tier 4 |  |  |  | 1464, 1474 | Y | N |  |  | 5156 | 4737
4738 | Pleasant Valley - Ceramic 138 kV Line | Upgrade terminal equipment on Pleasant Valley - Ceramic 138 kV Line |  | Pleasant Valley | Ceramic | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4004 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Wichita |  | Tier 4 |  |  |  | 1450, 1485 | Y | N |  |  | 5157 | 4738
4739 | Wichita Fallls South | Upgrade terminal equipment on Wichita Falls South - Lake Wichita 138 kV Line |  | Wichita Falls South |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4003 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Archer |  | Tier 4 |  |  |  | 1446, 1464 | Y | N |  |  | 5158 | 4739
4742 | Argyle Sw. Sta. | Upgrade terminal equipment on Argyle Sw. Sta. - Corinth 138 kV Line |  | Argyle Sw. Sta. |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3200 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  | 1984, 1985 | Y | N |  |  | 5161 | 4742
4750 | Belton | Upgrade terminal equipment on Belton - Killeen Switch 138 kV Line |  | Belton |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1703 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Bell |  | Tier 4 |  |  |  | 3610, 13610 | Y | N |  |  | 5170 | 4750
4754 | Walnut Springs 69 kV capacitors | Install shunt capacitors |  | Walnut Springs |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1723 | 2016-05-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Bosque |  | Tier 4 |  |  |  | 1647 | Y | N |  |  | 5174 | 4754
4769 | Lake Creek | Upgrade terminal equipment on Lake Creek - Rattlesnake Road 345 kV Line |  | Lake Creek |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R2006 | 2016-05-15 |  | 345 | 0 | 0 | 0 |  | McLennan |  | Tier 4 |  |  |  | 3399, 3409 | Y | N |  |  | 5191 | 4769
4770 | Temple Switch | Upgrade terminal equipment on the Temple Switch - Bell County 138 kV Line |  | Temple Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R2007 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Bell |  | Tier 4 |  |  |  | 3415, 3425 | Y | N |  |  | 5192 | 4770
4772 | Big Brown | Upgrade terminal equipment on Big Brown - Richland Chambers 345 kV Line |  | Big Brown |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R2011 | 2016-05-15 |  | 345 | 0 | 0 | 0 |  | Freestone |  | Tier 4 |  |  |  | 3134, 3380 | Y | N |  |  | 5195 | 4772
4778 | 800/900 Network Substation | Upgrade terminal equipment on 800/900 Network - West Levee double-circuit 138 kV Line |  | 800/900 Network Substation |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4210 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2808, 2809, 2857, 2858 | Y | N |  |  | 5203 | 4778
4779 | West Levee Sw. Sta. | Upgrade terminal equipment on West Levee Sw.Sta. - 800/900 Network 138 kV Line |  | West Levee Sw. Sta. |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4211 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2399, 2400, 12481, 12482 | Y | N |  |  | 5204 | 4779
4780 | Cedar Crest Sw. Sta. | Upgrade terminal equipment on Cedar Crest Sw.Sta. - Watermill 138 kV Line |  | Cedar Crest Sw. Sta. |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4209 | 2016-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 2493, 2494, 2495 | Y | N |  |  | 5207 | 4780
5130 | Establish Mitchell Bend 345 kV Switching Station |  |  |  |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5241 | 2016-05-15 |  | 345 | 0 | 0 | 0 |  | Hood |  | Tier 4 |  |  |  | 1877, 1878, 1879, 1876, 1890, 1880, 1900 | Y | N |  |  | 5608 | 5130
4975 | Rosita Creek Circuit Breaker Addition | Install two 138-kV circuit breakers at Rosita Creek in a single bus-single breaker configuration. |  | Rosita Creek |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015128 | 2016-05-26 |  | 138 | 0 | 0 | 0 |  | Maverick |  | Tier 4 |  |  |  | 78015 | Y | N |  |  | 5435 | 4975
3268 | AEP_McCampbell: New Substation Cut In | Customer to construct 138kV substation. Two 138kV circuits Cut-In to McCampbell substation. | Planned | Dupont SS | Whitepoint SS | Planned | 561 - 0729 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3435 | 2016-05-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 | 2000-01-01 | 2000-01-01 | 2000-01-01 | 80469, 8414, 8422, 8961, 80470 | Y | N |  | This project was previously referred to as 4578. Project 4578 was deleted and replaced by this project 3268. | 3444 | 3268
4421A | Rothwood Substation Upgrades | Add 2nd 800MVA autotransformer at Rothwood substation |  | Rothwood |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-05-30 |  | 345 | 0 | 0 | 800 |  | Harris |  | Tier 4 |  |  |  | 49045, 46290, 46295 | Y | N |  |  | 4801 | 4421
4451 | Plum to Flatonia Transmission Line Upgrade | Replace existing conductor and shield wire to achieve conductor rating of 221 MVA for the 0.45 mile portion of T133 and T122 between Flatonia substation and structure 1/3. |  | Plum | Flatonia | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015098 | 2016-05-30 |  | 138 | 0 | 0.45 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  | 7248, 7274 | Y | N |  |  | 4836 | 4451
4460 | Hidden Valley Substation Upgrade | Construct a new 138-kV bus with tie breaker to existing Austin Energy bus at the Hidden Valley substation. Cut McNeil (7334) to Marshall Ford (7356) 138-kV line into the LCRA TSC 138-kV bus at Hidden Valley. |  | Hidden Valley |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015119 | 2016-05-30 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 78207, 7356, 9207, 78220 | Y | N |  |  | 5283 | 4460
12TPIT0084 | Lookout 138 kV new substation and connections | Lookout 138 kV new substation and its connections to Apollo and to Firewheel | On Hold For Funding | Apollo | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2016-05-31 |  | 138 | 4.1 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 828, 12683, 802, 821 | Y | N |  |  | 765 | 764
3696 | Friend Ranch to Ozona: Rebuild 69 kV line | Rebuild Friend Ranch to Ozona line with 959.6 ACSS/TW |  | Friend Ranch | Ozona | Planned | 657 - 0826 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 1821 | 2016-05-31 |  | 69 | 0 | 3.4 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  | 6550, 6560 | Y | N |  |  | 3939 | 3696
3546 | Edroy 69 kV Station: Install Series Reactor | Construct a 15-ohm series reactor at Edroy on the terminal to Mathis 69 kV | Added ERCOT RPG estimate, changed Tier, ransmission status. | Edroy |  | Under Construction | 692-0862 | AEP TCC | Dave Goetz DNLYONS@AEP.COM 918-599-2698 | 3537 | 2016-05-31 |  | 69 |  |  |  | 15,0 | San Patricio |  | Tier 1 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8424, 8407, 8408 | Y | N |  |  | 4198 | 3546
4179 | Tanner 138kV Substation | Build new 138kV Tanner distribution substation. Double tap off Ckt.24 Satsuma - Addicks and Ckt.76 Satsuma - Addicks. |  | Tanner |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-05-31 |  | 138 | 1.9 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 46311, 46312, 45610, 45611, 46300, 46302 | Y | N |  |  | 4534 | 4179
4188 | Glenwood to Hardy Ckt.95 Upgrades | Upgrade 138kV Ckt.95 Glenwood to Hardy to increase thermal ratings. |  | Glenwood | Hardy | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1068 | 2016-05-31 |  | 138 | 0 | 7.5 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40180, 40620, 45840 | Y | N |  |  | 4543 | 4188
3665 | Texon Tap to Santa Rita: Rebuild 69kV line | Rebuild Texon Tap to Santa Rita 69 kV line with 959.6 ACSS/TW | Status and Schedule Update | Texon Tap | Santa Rita | Under Construction | 643 - 0812 | AEP TNC | Bill Clarke myturner@aep.com 918-599-2437 | 1460 | 2016-05-31 |  | 69 | 0.8 | 3.7 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 6504, 6542, 6541, 6555 | Y | N |  |  | 4736 | 3665
4421B | Rothwood Substation Upgrades | Reconfigure existing 138kV Rothwood circuits to create new Ckt.22 loop from Rothwood to Rayford to Springwood to Rothwood. |  | Rothwood | Rayford/Springwood/Rothwood | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-05-31 |  | 138 | 0.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 46051, 46261, 46270, 46295 | Y | N |  |  | 4802 | 4421
4462 | Clear Springs 345/138-kV Auto Transformer Addition | Energize the standby 345/138-kV 478 MVA auto transformer at Clear Springs substation. |  | Clear Springs |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2016-05-31 |  | 345 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7050, 7680, 77680 | Y | N |  |  | 4848 | 4462
4491 | Marconi: Build new 138 kV temporary tap | Interconnect San Roman Windfarm at Temporary Tap to connect San Roman to the Port Isabel to Laureles 138 kV line |  | Port Isabel | Laureles | Planned | 711 - 0882 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 2905 | 2016-05-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8262, 5756, 8338 | Y | N |  |  | 4885 | 4491
4857 | Hendrick: Build 138 kV temporary tap | Interconnect Alamo 7 solar farm at temporary tap to connect Alamo 7 to the Abilene Northwest to Paint Creek 138 kV line |  | Hendrick |  | Planned | 721 - 0903 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2612 | 2016-05-31 |  | 138 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  | 60387, 6169, 6228 | Y | N |  |  | 5285 | 4857
5018 | Pig Creek: Build 138 kV temporary tap | Construct new 138 kV temporary tap on the Barrilla Junction to Permian Basin line | Contact and Schedule Update | Pig Creek |  | Planned | 737 - 0920 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2617 | 2016-05-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60393, 6655, 6673 | Y | N |  |  | 5476 | 5018
5068 | Add Third Distribution Xer at OB by Tapping OB-FL Ckt73 | Add Third Distribution Transformer at OB by Tapping OB-FL Ckt73 |  |  |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 44511, 44512, 44513, 44230, 44510 | Y | N |  |  | 5547 | 5068
5077 | Add 3rd Distribution Transformer at Orchard | Add 3rd Distribution Transformer at Orchard |  |  |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 44541, 44190, 44540, 44615 | Y | N |  |  | 5557 | 5077
5190 | Gas Pad Tap: Build 138 kV temporary tap | Construct 138 kV POD box bay for customer interconnection | NEW | Gas Pad Tap |  | Planned | 755 - 0938 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2628 | 2016-05-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60397, 1010, 6656 | Y | N |  |  | 5674 | 5190
5241A | STP to DOW Ckt.18 & Ckt.27 Thermal Uprate | STP to DOW Ckt18 Thermal Uprate |  | South Texas Project | DOW | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-05-31 |  | 345 | 0 | 0 | 0 |  | Matagorda | Brazoria | Tier 4 |  |  |  | 5915, 42500 | Y | N |  |  | 5740 | 5241
5241B | STP to DOW Ckt.18 & Ckt.27 Thermal Uprate | STP to DOW Ckt27 Thermal Uprate |  | South Texas Project | DOW | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-05-31 |  | 345 | 0 | 0 | 0 |  | Matagorda | Brazoria | Tier 4 |  |  |  | 5915, 42500 | Y | N |  |  | 5741 | 5241
5244 | Hardy to Northside Ckt.91 Thermal Uprate | Upgrade Ckt.91 Hardy to Northside to increase thermal ratings |  | Hardy | Northside | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45840, 47711 | Y | N |  |  | 5744 | 5244
12TPIT0090 | Whitney 2nd Auto | Replace 60 MVA, 138-69 kV auto with 100 MVA auto |  | Whitney |  | Planned |  | BEPC | Dwight Beckman kdye@brazoselectric.com 254-750-6373 | 10048 | 2016-06-01 |  | 138 | 0 | 0 | 100 |  | Bosque |  | Tier 4 |  |  |  | 243, 3546 | Y | N |  |  | 883 | 882
09TPIT0012 | Hill Country to Skyline - 345 kV 2nd Circuit | Build second 345 kV line from Hillcountry to Skyline. The second circuit will be installed on existing transmission structures |  | Hill Country | Skyline | Planned | S-0470 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0052 | 2016-06-01 |  | 345 | 11 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5211, 5371 | Y | N |  | There are no transformers associated with this project | 1404 | 1403
10TPIT0095 | VH Braunig - Grandview 138kV Line Reroute | Reroute VH Braunig - Grandview to become VH Braunig - Coliseum Rd | Delayed due to Rail Road permit | VH Braunig | Grandview |  | S-0746 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0130 | 2016-06-01 |  | 138 | 2.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5030, 5095, 5175 | Y | N |  | There are no transformers associated with this project | 1465 | 1464
14TPIT0071 | Princeton South - New Substation | Build a new 138-12.47 kV substation to accommodate load growth in Princeton. |  |  |  | Planned | 16TPIT0005 | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE02815 | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 37295 | N | N |  |  | 2063 | 2011
15TPIT0030 | Mainland - New Substation | Build a new 138-12.47 kV substation to accommodate load growth along I45 between Texas City and Dickinson. Cut TNMP's Freeway Park - Alvin 138 kV line into the new substation. |  | Mainland |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38830, 38820, 39030 | Y | N |  |  | 2089 | 2025
16TPIT0030 | New 345kV line from Loma Alta to N Edinburgh | Construct a new 345 kV transmission line from N.Edinburg to Loma Alta (~106.5 mi) and station upgrades | New Changed Dollars to include the station costs associated with the project (Approved by RPG, see comments for breakout) | Loma Alta | N Edinburgh | Planned |  | SLU |  |  | 2016-06-01 |  | 345 | 106.5 | 0 | 0 |  | Cameron | Hidalgo | Tier 1 | 2011-05-03 | 2011-12-19 | 2012-01-17 | 5966, 8383, 5962 | Y | N |  |  | 2460 | 2371
15TPIT0045 | ETP Capacitor | Add 19.2 MVAR capacitor |  | ETP |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-06-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | Jackson |  | Tier 4 |  |  |  | 5523 | Y | N |  |  | 2659 | 2553
3394 | Add Long Road Station |  |  | North Denton | Arco | Planned |  | DME | Chuck Sears 940-349-7111 |  | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 925, 983, 985 | Y | N |  |  | 3592 | 3394
4086 | Dunlap-Austrop: Upgrade Ckt 920 | Upgrade conductor and termination equipment to a minimum rating of 3000 amps as part of AU-DP Corridor Upgrade |  | Dunlap | Austrop | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2016-06-01 |  | 138 | 0 | 3.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9045, 9328 | Y |  |  |  | 4436 | 4086
4087 | Dunlap-Decker Plant: Upgrade Ckt 1027 | Reconductor to 3000 amps as part of AU-DP Corridor Upgrade |  | Dunlap | Decker Plant | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2016-06-01 |  | 138 | 0 | 4.85 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9045, 9188 | Y |  |  |  | 4437 | 4087
4140 | DME_Ndenton_NLakes |  |  | N Denton | N Lakes | Planned | N/A | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2016-06-01 |  | 69 | 0 | 2 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 912, 915 | Y | N | N/A |  | 4485 | 4140
4363 | Miracle Lake 138 kV substation | Add new 138 kV substation between Cross and Pearsall |  | Miracle Lake |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5700, 5707, 5895 | Y | N |  |  | 4737 | 4363
4608 | Olsen-Walnut Springs Rebuild | Olsen-Clifton-Clifton Tap-Meridian Tap-Walnut Springs Rebuild with 795 ACSR. |  | 37470 | 37680 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE09517 | 2016-06-01 |  | 69 | 0 | 24.77 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  | 37470, 37600, 37620, 37650, 37680 | Y |  |  |  | 5015 | 4608
4882 | Rebuild North Calliham to South Calliham Switch | Rebuild North Calliham to South Calliham Switch from 4/0 to 795 ACSR 138 kV capable |  | South Calliham Switch | North Calliham | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-06-01 |  | 69 | 0 | 11.8 | 0 |  | McMullen | Live Oak | Tier 4 |  |  |  | 5696, 5698 | Y | N |  |  | 5318 | 4882
4906 | Addition of Calytonville station and 3-winding auto |  |  | West Shackelford | Scurry | Planned |  | LST | Don Le 713-366-6105 |  | 2016-06-01 |  | 345 | 0 | 0 | 250 |  | Fisher | Fisher | Tier 4 |  |  |  | 68001, 68002, 68003, 11318, 68000 | Y | N |  |  | 5345 | 4906
4908 | Addition of 200 MVAR reactors at West Shackelford |  |  | West Shackelford | West Shackelford | Planned |  | LST | Don Le 713-366-6105 |  | 2016-06-01 |  | 345 | 0 | 0 | 0 | 200,0 | Shackelford | Shackelford | Tier 4 |  |  |  | 68000 | Y | N |  |  | 5347 | 4908
4909 | Addition of 150 MVAR reactors at Claytonville |  |  | Claytonville | Claytonville | Planned |  | LST | Don Le 713-366-6105 |  | 2016-06-01 |  | 345 | 0 | 0 | 0 | 150,0 | Fisher | Fisher | Tier 4 |  |  |  | 68001 | Y | N |  |  | 5348 | 4909
5004 | Install second Wink Auto |  |  | 37900 | 37920 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2016-06-01 |  | 138 | 0 | 0 | 93 |  |  |  | Tier 4 |  |  |  | 37920, 37900 | Y |  |  |  | 5462 | 5004
4660 | GSEC_4660_Add_BG-Claytonville_Sub |  |  |  |  | Planned |  | GOLDENSPREAD | Chris Koenig ckoeng@gsec.coop 806-349-5201 |  | 2016-06-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 68002 | Y |  |  |  | 5062 | 4660
11TPIT0009 | Dunlap 138kV substation | Install one 30MVA Transformer at Dunlap Substation |  | Dunlap Substation | Dunlap Substation | Under Construction |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | 3230_117_2930 3230_117_2933 3240_117_4930 3240_117_4933 | 2016-06-17 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9045 | Y | N |  |  | 1021 | 1020
4424A | Gable Street Upgrades | Convert to 138kV and reconfigure existing Ckt.46 Gable Street to Blodgett tap to create new 138kV Ckt.70 Gable Street to East Side. | Delay in project schedule | Gable Street | East Side | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-06-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47522, 47600, 47630, 47640 | Y | N |  |  | 4805 | 4424
4424B | Gable Street Upgrades | Install 2nd autotransformer (200MVA) at Gable Street substation. | Delay in project schedule | Gable Street |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-06-29 |  | 138 | 0 | 0 | 200 |  | Harris |  | Tier 4 |  |  |  | 49056, 47630, 47640 | Y | N |  | Cost included in main project. | 4806 | 4424
11TPIT0002 | Lobo to North Edinburg: Construct 345 kV Line | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Lobo | North Edinburg | Under Construction | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3421 | 2016-06-30 |  | 345 | 156 | 0 | 0 |  | Webb | Hidalgo | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80220, 80225, 80307, 80355, 8383, 80219 | Y | N |  |  | 1325 | 1321
13TPIT0157 | Cactus to Ft. Lancaster: Rebuild 69 kV line | Rebuild Cactus to Ft. Lancaster 69 kV line with 959.6 ACSS |  | Cactus | Ft. Lancaster | Planned | 569 - 0743 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2573 | 2016-06-30 |  | 69 | 0 | 9.28 | 0 |  | Crockett | Pecos | Tier 4 |  |  |  | 6577, 6578, 6579 | Y | N |  |  | 1844 | 1801
14TPIT0062 | Kurten Substation Upgrade | Install (3) Breaker ring to support (2) existing 138 lines and (1) existing 138/12.5 transformer (No MOD changes necessary) |  |  |  | Planned |  | BRYN | James Tanneberger 979-821-5763 |  | 2016-06-30 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 3041 | 2867
16TPIT0040 | Del Sol: Add a 100 MVAR Shunt Reactor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Del Sol |  | Under Construction | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 629 | 2016-06-30 |  | 345 | 0 | 0 | 0 | -100,0 | Starr |  | Tier 4 |  |  |  | 80355 | Y | N |  |  | 3310 | 3141
16TPIT0041 | Cenizo: Add a 100 MVAR Shunt Reactor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Cenizo |  | Under Construction | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 630 | 2016-06-30 |  | 345 | 0 | 0 | 0 | -100,0 | Webb |  | Tier 4 |  |  |  | 80220 | Y | N |  |  | 3311 | 3142
16TPIT0000 | Del Sol: Add a 24 Ohm, 3600 A Series Capacitor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Del Sol |  | Under Construction | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 629 | 2016-06-30 |  | 345 | 0 | 0 | 0 | 0,933.1 | Starr |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80307, 80355 | Y | N |  | Modeling in 11TPIT0002 | 3312 | 3143
16TPIT0017 | Cenizo: Add a 24 Ohm 3600, A Series Capacitor | Construct 345 kV series compensated line from Lobo to Cenizo to Del Sol to North Edinburg |  | Cenizo |  | Under Construction | 065 - 0273 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 630 | 2016-06-30 |  | 345 | 0 | 0 | 0 | 0,933.1 | Webb |  | Tier 1 | 2011-03-10 | 2011-08-25 | 2011-09-20 | 80220, 80225 | Y | N |  | Modeled in 11TPIT0002 | 3313 | 3144
3745 | Del Sol: Add 345 kV breaker terminal for WF interconnect | Construct four 345 kV breaker ring exdable at Del Sol Station for the Generator Interconnect |  | DEL SOL |  | Under Construction | 666 - 0835 | AEP TCC | KENNETH 'RICH' HALEY DNLYONS@AEP.COM 918-599-2698 | 3530 | 2016-06-30 |  | 345 |  |  |  |  | Starr |  | Tier 4 |  |  |  | 80355 | Y | N |  |  | 3991 | 3745
3953 | Marfa to Alamito Creek: Rebuild 69 kV line | Rebuild Marfa to Alamito Creek 69 kV line with 959.6 ACSS/TW |  | Marfa | Alamito Creek | Planned | 669 - 0838 | AEP TNC | Greg Crane myturner@aep.com 918-599-2437 | 2805 | 2016-06-30 |  | 69 | 0 | 0.7 | 0 |  | Presidio | Presidio | Tier 4 |  |  |  | 6678, 6681 | Y | N |  |  | 4273 | 3953
4168 | PH Robinson Autotransformer A2 Upgrade | Replace existing 600MVA PH Robinson autotransformer A2 with 800MVA autotransformer. | Accelerated project schedule | P.H. Robinson |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 994 | 2016-06-30 |  | 345 | 0 | 0 | 200 |  | Galveston |  | Tier 4 |  |  |  | 42000, 42015, 49048 | Y | N |  |  | 4517 | 4168
4187 | LaMarque Substation Expansion & Circuit Reconfigurations | Expand LaMarque 138kV substation and loop Ckt.93 into LaMarque to create PHR - LaMarque and LaMarque - West Galveston circuits. Reconfigure circuits south of LaMarque. |  | LaMarque | Hitchcock/West Galv | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 859 | 2016-06-30 |  | 138 | 0.5 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 42860, 42861, 42080, 42600, 42670, 42800, 43290, 43355, 43400, 43505, 43401, 43500, 43507, 43510 | Y | N |  |  | 4542 | 4187
3666 | Atlantic Best Tap to Santa Rita: Rebuild & convert to 138 kV | Rebuild Atlantic Best Tap to Santa Rita 69 kV line with 959.6 ACSS/TW and convert Santa Rita to 138 kV by rerouting the Big Lake to North McCamey line through Santa Rita | Status and Schedule Update | Altantic Best Tap | Santa Rita | Under Construction | 644 - 0813 | AEP TNC | Bill Clarke myturner@aep.com 918-599-2437 | 1461 | 2016-06-30 |  | 138 | 0.7 | 5 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 6504, 6541, 6542, 6555, 60361, 6536, 6544, 6589, 76032 | Y | N |  |  | 4634 | 3666
4424C | Gable Street Upgrades | Install in-series reactor at Gable Street substation on Ckt.32 Gable Street to Downtown | Delay in project schedule | Gable Street | Downtown | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-06-30 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47510, 47640 | Y | N |  | Cost included in main project. | 4807 | 4424
4481 | Linterna: Build a 138 kV tap | Construct new 138 kV hard tap off the Barrilla Junction to Fort Stockton line |  | Linterna |  | Planned | 706 - 0876 | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | 2812 | 2016-06-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60383, 6630, 6655 | Y | N |  |  | 4871 | 4481
4542 | Add new 345/138kV Einstein station |  |  | Einstein | Einstein | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-06-30 |  | 345 | 0.038 | 0 | 675 |  | Glasscock | Glasscock | Tier 2 |  |  |  | 79565, 79632, 59903, 79617, 79625 | Y | N |  |  | 4944 | 4542
4702 | Britmoore to Sauer Ckts. 73 & 81 | Reconductor Circuits 73 & 81 Britmoore to Sauer |  | Britmoore | Sauer | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-06-30 |  | 138 | 0 | 3.5 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44120, 44620, 44621, 44622 | Y | N |  |  | 5114 | 4702
4851 | Del Sol to JackieHoward: New 345 kV Line | Build a double circuit capable 345 kV circuit from Del Sol station to JackiwHoward collector station for Los Vientos IV Windfarm Interconnect. |  | DEL SOL | JACKIEHOWARD | Under Construction | 722-0904 | AEP TCC | William Clark DNLYONS@AEP.COM 918-599-2698 | 3556 | 2016-06-30 |  | 345 | 10.8 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  | 80323, 80355 | Y | N |  |  | 5278 | 4851
4961 | Adding Pemkiff tap and 138 kV line to Midkiff |  |  | Pemkiff | Midkiff | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-06-30 |  | 138 | 0.3 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  | 79555, 1210, 79612, 79614 | Y | N |  |  | 5419 | 4961
4964 | Upgrade conductor on existing Grady to Brown 138 kV line |  |  | Grady | Brown | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-06-30 |  | 138 | 0 | 20.3 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79550, 79551 | Y | N |  |  | 5422 | 4964
5065 | WATSON 138kV Substation | Construct service to new 138kV WATSON customer-owned substation. Loop through Ckt.21 Witter to DAVSON. |  | WATSON |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-06-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 41720, 40420, 41712 | Y | N |  |  | 5543 | 5065
4411 | Transmission line upgrade | Upgrade and Reconductor 4.08 miles of transmission line from Switch Station Substation to Spring Creek Substation from 477 AAC to 1033 ACSS conductor. Replace 5.13 miles of static with OPGW. Replace and re-span poles as necessary. Project relieves contingency overload of Gibbons Creek (964) to Greens Prairie (32878), Switch Station (32000) to Post Oak (32001). |  | CSST | CSSC | Planned |  | COCS | Tony Mickalsky tmichalsky@cstx.gov 979-764-3438 |  | 2016-07-01 |  | 138 | 0 | 4.08 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32000, 32004 | Y | N |  |  | 4791 | 4411
4413 | Transmission line upgrade | Upgrade and Reconductor 2.11 miles of transmission line from Spring Creek Substation to Greens Prairie Substation from 477 AAC to 1033 ACSS conductor. Replace 3.81 miles of static with OPGW. Replace and re-span poles as necessary. Project relieves contingency overload conditions for loss of Gibbons Creek (964) to Greens Prairie (32878), Switch Station (32000) to Post Oak (32001). |  | CSSC | CSGP | Planned |  | COCS | Tony Mickalsky tmichalsky@cstx.gov 979-764-3438 |  | 2016-07-01 |  | 138 | 0 | 2.11 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32004, 32003 | Y |  |  |  | 4793 | 4413
4541 | Add new 345kV Abernathy station and 51 miles line from WR-AN |  |  | White River | Abernathy | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-07-01 |  | 345 | 51 | 0 | 0 |  | Floyd | Hale | Tier 4 |  |  |  | 79506, 79505, 141607 | Y | N |  |  | 4943 | 4541
4786 | Apollo-Lookout-Firewheel_LineUpgrade | Apollo to Lookout to Firewheel 138 kV lines upgrade to 495 MVA ratings as well as some load growths at Lookout |  | Apollo | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2016-07-01 |  | 138 | 0 | 4.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 828, 802, 821 | Y | N |  |  | 5211 | 4786
5249 | Gray_Railhead_Reactors_Relocation |  |  | Railhead | Railhead | Planned |  | CTT | Tim Cook 512-473-2700 |  | 2016-07-01 |  | 345 | 0 | 0 | 0 |  | Carson | Carson | Tier 4 |  |  |  | 79000, 79005 | Y | N |  | No inductive capability added since reactors moved from Gray to Railhead | 5749 | 5249
5288 | Add Pronghorn 138 kV station |  |  | Pronghorn | Pronghorn | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-07-01 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 79566, 79613, 79615 | Y | N |  |  | 5789 | 5288
5289 | Add Roughneck 138 kV station |  |  | Roughneck | Roughneck | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-07-01 |  | 138 | 0 | 0 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79567, 79610, 79627 | Y | N |  |  | 5790 | 5289
5317 | Gray_Reactors_Addition |  |  | Gray | Gray | Planned |  | CTT | Tim Cook 636-236-7197 |  | 2016-07-01 |  | 345 | 0 | 0 | 0 | 200,0 | Gray | Gray | Tier 4 |  |  |  | 79493, 79494, 79495, 79496, 79000 | Y |  |  |  | 5822 | 5317
5030B | Flat Top Tie with AEP Pig Creek | Rebuild line from Flat Top-Barilla Draw Tap station with 1926 ACSR/TW Cumberland. Convert Barilla Draw Tap and Barilla Draw to 138 kV service and install circuit breakers. Switch line out of service from Barilla Draw Tap-IH20. |  | 38060 | 38070 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2016-07-30 |  | 138 | 0 | 5.73 | 0 |  | Reeves | Reeves | Tier 3 | 2015-01-13 | 2015-06-19 |  | 38060, 38065, 38040, 38070 | Y |  |  | Conductor changed from RPG submittal from 795 ACSR to 1926 ACSR/TW Cumberland. Barilla Draw Tap station changed from RPG to include up to 6 breakers. | 5499 | 5030
13TPIT0121A | Tilden to Reveille 138 kV line | New station between Tilden and Reveille |  | Fowlerton |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-01 |  | 138 | 0 | 0 | 0 |  | McMullen | La Salle | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5705 | Y | N |  | project cost in last phase | 2355 | 2282
5247 | Addition_Allen_Creek_Station |  |  | Allen Creek | Allen Creek | Planned |  | CTT | Tim Cook 512-473-2700 |  | 2016-08-01 |  | 345 | 0 | 0 | 0 |  | Donley | Donley | Tier 4 |  |  |  | 79006 | Y | N |  |  | 5747 | 5247
5248 | Addition_Gray_Allen_Creek_Line |  |  | Gray | Allen Creek | Planned |  | CTT | Tim Cook 512-473-2700 |  | 2016-08-01 |  | 345 | 24.3 | 0 | 0 |  | Gray | Donley | Tier 4 |  |  |  | 79000, 79006 | Y | N |  |  | 5748 | 5248
5290 | Add Ringo 138 kV station |  |  | Ringo | Ringo | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2016-08-01 |  | 138 | 0 | 0 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 79568, 79555, 79614 | Y | N |  |  | 5791 | 5290
13TPIT0121B | Tilden to Reveille 138 kV line | Construct a new 138 kV double circuit capable line from Tilden to Fowlerton |  | Tilden | Fowlerton | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-02 |  | 138 | 19.4 | 0 | 0 |  | McMullen | La Salle | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5701, 5705 | Y | N |  | project cost in last phase | 2356 | 2282
13TPIT0121C | Tilden to Reveille 138 kV line | Construct a new 138 kV double circuit capable line from Fowlerton to Reveille |  | Fowlerton | Reveille | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-03 |  | 138 | 40 | 0 | 0 |  | McMullen | La Salle | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5705, 8612 | Y | N |  |  | 2357 | 2282
5078 | Add new station between Fowlerton and Reveille | Add a new 138 kV load serving station between Fowlerton and Reveille |  | Los Angeles |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-04 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 5723, 5705, 8612 | Y | N |  |  | 5558 | 5078
4310 | Long Draw Reactor Addition | Add three breakers and two 100 MVAR reactors at WETT's Long Draw substation |  | Long Draw |  | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2016-08-05 |  | 345 | 0 | 0 | 0 | 200,0 | Borden |  | Tier 4 |  |  |  | 59900 | Y | N |  |  | 4687 | 4310
14TPIT0100 | Tilden Capacitor | Add 19.2 MVAR capacitor |  | Tilden |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-08-15 |  | 138 | 0 | 0 | 0 | 0,19.2 | McMullen |  | Tier 4 |  |  |  | 5701 | Y | N |  |  | 2661 | 2555
5055 | Maxwell Tap: Build new 138 kV temporary tap | Temporary interconnect Val Verde Windfarm at Maxwell Tap via Fermi Collector station |  | Maxwell Tap |  | Under Construction | 735-0917 | AEP TCC | Rick McCracken dnlyons@aep.com 918-599-2698 | 3567 | 2016-08-31 |  | 138 | 0 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  | 88998, 8257, 8261 | Y | N |  |  | 5530 | 5055
15TPIT0013 |  | Rebuild Lake Kemp Switch to Seymour with 1033 acsr conductor |  | Seymour | Lake Kemp | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 10047 | 2016-09-01 |  | 69 | 0 | 6.9 | 0 |  |  |  | Tier 4 |  |  |  | 779, 782 | Y |  |  |  | 4136 | 3852
4785 | Lobo: Connect Torrecillas Generation | Lobo: Add IPP Equipment and breaker to accommodate Torrecillas |  | Lobo |  | Planned | 723 - 0905 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 3557 | 2016-09-01 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 80219, 80481, 89631 | Y |  |  |  | 5210 | 4785
4872 | Smoky Hill: Build 345 kV temporary tap | Interconnect Horse Creek wind farm at temporary tap to connect Horse Creek to the Clear Crossing to Edith Clarke 345 kV line |  | Smoky Hill |  | Planned | 726 - 0908 | ETT | Mike Tallon myturner@aep.com 918-599-2437 | 2908 | 2016-09-01 |  | 345 |  |  |  |  | Haskell |  | Tier 4 |  |  |  | 6104, 60515, 60701 | Y | N |  |  | 5308 | 4872
4968 | Pomelo Tap: Build new 345 kV temporary tap | Interconnect Hidalgo Windfarm at temporary tap to connect Hidalgo to the Del Sol to North Edinburg 345 kV line |  | Del Sol | North Edinburg | Planned | 729 - 0911 | ETT | Michael Tallon dnlyons@aep.com 918-599-2698 | 3560 | 2016-09-01 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 88574, 8383, 80355 | Y |  |  |  | 5428 | 4968
14TPIT0109 | Kenedy Switch to Tuleta: Build double circuit 138 kV line | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. |  | KENEDY SWITCHING STATION | TULETA | Under Construction | 603 - 0765 | AEP TCC | Eric Scott DNLYONS@AEP.COM 918-599-2698 | 3483 | 2016-09-30 |  | 138 | 16.9 | 16.9 | 0 |  | Karnes | Bee | Tier 4 |  |  |  | 8590, 8186 | Y | N | NA | NA | 3169 | 3000
3418 | Nelson Sharpe: Add 345 kV Terminal for WF Interconnect | Add a new 345 kV line terminal at Nelson Sharpe for the Patriot WF Interconnect | UPDATED INSV DATE | Nelson Sharpe |  | Under Construction | 515 - 0756 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3474 | 2016-09-30 |  | 345 | 0 | 0 | 0 |  | Kleberg |  | Tier 4 |  |  |  | 85000 | Y | N |  |  | 3618 | 3418
14TPIT0082 | Kenedy Switch to Pettus: Rebuild 69 kV line | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. | KENEDY SWITCHING STATION | PETTUS | Under Construction | 603-0765 | AEP TCC | Eric Scott DNLYONS@AEP.COM 918-599-2698 | 3473 | 2016-09-30 |  | 69 |  | 15.9 | 0 |  | Karnes | Bee | Tier 4 |  |  |  | 8184, 8188, 8593 | Y | N |  |  | 3669 | 3464
15TPIT0067 | Tuleta 138 kV Station: Construct a new station | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. |  | TULETA |  | Under Construction | 603-0765 | AEP TCC | Eric Scott DNLYONS@AEP.COM 918-599-2698 | 3552 | 2016-09-30 |  | 138 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  | 8590 | Y | N |  | NA | 3689 | 3482
3898 | Pleasanton: Replace 138/69 kV autotransformer | Add 138/69 kV autotranformer capacity at Pleasanton |  | Pleasanton |  | Under Construction | 676 - 0845 | AEP TCC | Michael Tallon dnlyons@aep.com 918-599-2698 | 2595 | 2016-09-30 |  | 138 | 0 | 0 | 90 |  | Atascosa |  | Tier 4 |  |  |  | 8200, 8203 | Y | N |  |  | 4193 | 3898
4461 | Moulton South Substation | Build a new 138-26.18 kV 18-24-30 MVA substation on the LCRA TSC Flatonia to Yoakum 138-kV transmission line. |  | Flatonia | Yoakum | Planned |  | LCRATSC/GVEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015113 | 2016-09-30 |  | 138 | 0 | 0 | 0 |  | Lavaca |  | Tier 4 |  |  |  | 7237, 7236, 7238 | Y | N |  |  | 4969 | 4461
4994 | Bunker Customer Owned 138 kV Station | Build new 138kV BUNKER customer-owned substation. Loop through Ckt.08 HO Clarke to Knight. |  | BUNKER | HO Clarke/Knight | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-09-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47340, 47150, 47331 | Y | N |  |  | 5452 | 4994
16TPIT0012 | Encino to Skyline - 138 kV Substation Equipment Upgrade | Upgrade terminals at Encino and Skyline to ensure a 2420 A rating and remove existing MLSE on Encino to Skyline 138 kV transmission line |  | Encino | Skyline | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0671 | 2016-10-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5140, 5369 | Y | N |  | There are no transformers associated with this project | 973 | 972
5230 | Sonne Substation Addition | Provide transmission service for a generator off T554 radial 138-kV line between North McCamey and Tippet Substations. |  | North McCamey | Tippet | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015963 | 2016-10-01 |  | 138 | 0 | 0 | 0 |  | Upton | Pecos | Tier 4 |  |  |  | 76020, 76001, 76595 | Y | N |  |  | 5728 | 5230
5233 | Lincoln Substation Addition | Construct a load serving substation (ring bus) at Lincoln. The station will be built off between Giddings and Lexington off T255. |  | Giddings | Lexington | Planned | 1015961 | LCRATSC/BBEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2016-10-01 |  | 138 | 0 | 0 | 0 |  | Lee | Lee | Tier 4 |  |  |  | 7568, 7302, 7571 | Y | N |  |  | 5731 | 5233
5243 | BAILEY - Colorado Bend Generator Interconnection (17INR0007) | New 345 kV, 4 breaker ring with two generator leads. Loop from 345kV Ckt.72 WA Parish to Hillje |  | BAILEY | WA Parish/Hillje | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-10-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 44040, 44005, 44200 | Y | N |  |  | 5743 | 5243
4311 | Sand Bluff Reactor Addition | Add three breakers and move one 50 MVAR shunt reactor from Cottonwood to Sand Bluff. |  | Sand Bluff |  | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2016-10-06 |  | 345 | 0 | 0 | 0 | 50,0 | Sterling |  | Tier 4 |  |  |  | 59902 | Y | N |  |  | 4688 | 4311
4402 | Cenizo: Build new four breaker 345 kV station | Interconnect Javalina Windfarm at Cenizo to connect Bordas on the Lobo SS to North Edinburg 345 kV line |  | Cenizo |  | Planned | 700 - 0870 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3544 | 2016-10-15 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 80646, 8295, 80230 | Y |  |  |  | 4781 | 4402
16TPIT0038 | Rebuild STEC Mathis to AEP Mathis | Rebuild 69 kV 4-0 to 795 ACSR on 138 kV capable structures. |  | Mathis | AEP Mathis | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-10-28 |  | 69 | 0 | 5.19 | 0 |  | Live Oak | San Patricio | Tier 1 | 2012-09-05 | 2013-01-31 | 2013-03-12 | 5668, 8407 | Y | N |  |  | 3117 | 2948
4319 | Cottonwood Reactor Addition | Add one new 100 MVAR reactor at Cottonwood. Move one existing 50 MVAR reactor to Sand Bluff |  | Cottonwood |  | Planned |  | WETT | Julius Horvath julius.horvath@windenergyoftexas.com 512-436-9585 |  | 2016-10-28 |  | 345 | 0 | 0 | 0 | 100,0 | Dickens |  | Tier 4 |  |  |  | 59904 | Y | N |  |  | 4696 | 4319
4876 | Riley: Build 345 kV terminal | Interconnect Electra wind farm at Riley |  | Riley |  | Planned | 727 - 0909 | ETT | Dave Goetz myturner@aep.com 918-599-2437 | 2910 | 2016-10-31 |  | 345 |  |  |  |  | Wilbarger |  | Tier 4 |  |  |  | 6101 | Y | N |  |  | 5312 | 4876
4933 | COPPER Substation | Loop new 138kV COPPER substation from Ckt.02 Brazosport to Seadoc tap |  | COPPER | Brazosport/Seadoc | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 42215, 42210, 43222 | Y |  |  |  | 5391 | 4933
3817 | George West autotransformer upgrade | Upgrade autotransformer at George West to 150 MVA as recommended in 2013 RTP. |  | George West Switch |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-11-01 |  | 138 | 0 | 0 | 150 |  | Live Oak |  | Tier 4 |  |  |  | 5686, 5688 | Y | N |  |  | 4099 | 3817
4501 | Trading Post Circuit Breaker Addition | Install Line Breakers at Trading Post on the Trading Post to Marshall Ford and the Trading Post to Cedar Valley 138kV lines (T315). |  | Trading Post |  | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2016-11-01 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7505 | Y | N |  |  | 4898 | 4501
4967 | Nelson Sharpe: Add 138 kV terminal for generator interconnec | Interconnect Chapman Ranch Windfarm at Nelson Sharpe and construct 138 kV line with 2-795 ACSR from Nelson Sharpe to Santa Cruz |  | Nelson Sharpe | Santa Cruz | Planned | 733 - 0915 | ETT | Dave Goetz dnlyons@aep.com 918-599-2698 | 3564 | 2016-11-01 |  | 138 | 6 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 80503, 85001 | Y |  |  |  | 5427 | 4967
4773B | Smithville to Rosanky Rebuild | Part 2: Upgrade Structures on Smithville to Rosanky Transmission Line |  | Smithville | Rosanky | Planned |  | BBEC | Thomas Ellis thomas.ellis@bluebonnet.coop |  | 2016-11-10 |  | 69 | 0 | 5.4 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  | 7315, 7558 | Y | N |  |  | 5197 | 4773
4422 | Stewart 10MVAr Reactor Bank | Install 10MVAR shunt reactor at Stewart substation. | Delay in project schedule | Stewart |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-11-30 |  | 138 | 0 | 0 | 0 | -10,0 | Galveston |  | Tier 4 |  |  |  | 43290 | Y | N |  |  | 4803 | 4422
5156 | Fort Stockton Plant: Build 138 kV terminal | Interconnect Oak Solar solar farm at Fort Stockton Plant | NEW | Fort Stockton |  | Planned | 752 - 0935 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2622 | 2016-11-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6630 | Y | N |  |  | 5637 | 5156
16TPIT0018 | Hicks Switch 345/138 kV autotransformer | Install 345/138 kV autotransformer and 138 kV bus | Construction schedule change | Hicks Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5145-E | 2016-12-01 |  | 345 | 0 | 0 | 600 |  | Tarrant |  | Tier 4 |  |  |  | 2082, 1860, 2075, 2076, 12065, 2081 | Y | N |  |  | 2700 | 2584
11TPIT0179 | Hicks Switch - Elizabeth Creek 138 kV line | Construct new double-circuit 138 kV line | Construction schedule change | Hicks Switch | Elizabeth Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M523-E | 2016-12-01 |  | 138 | 30.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 2 | 2013-02-01 | 2013-03-01 |  | 1866, 1867, 2082 | Y | N |  |  | 2786 | 2662
14TPIT0089 | North Main Switch third transmission source | Construct a third 138 kV line into North Main Switch | Construction schedule change | North Main Tap | North Main Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5161-E | 2016-12-01 |  | 138 | 4.4 | 4.4 | 0 |  | Tarrant | Tarrant | Tier 2 |  |  |  | 1961, 2158, 2105, 3011 | Y | N |  |  | 3110 | 2941
15TPIT0085 | Eagle Mountain - Wagley Robertson - Saginaw 138 kV Line | Upgrade the existing Eagle Mountain - Wagley Robertson line section |  | Eagle Mountain | Wagley Robertson | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5200-E | 2016-12-01 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1860, 2076, 11860, 2075, 12065 | Y | N |  |  | 3382 | 3209
4784A | Forest Hill - Cresson 69 kV Line Conversion | Rebuild existing 69 kV line section from Forest Hill to Crowley | Construction schedule and scope change | Forest Hill | Crowley | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5227 | 2016-12-01 |  | 69 | 0 | 12.1 | 0 |  | Tarrant | Tarrant | Tier 4 | 2015-05-07 | 2015-06-01 |  | 1968, 2205, 12209 | Y | N |  |  | 5484 | 4784
4548 | Yucca Drive Switching Station | Construct new switching station | Construction schedule change | Yucca Drive Switching Station |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8261 | 2016-12-14 |  | 138 | 0 | 0 | 300 |  | Ward |  | Tier 3 |  |  |  | 1009, 1015, 18110, 1010, 1019, 1074, 1105, 1146, 60397 | Y | N |  |  | 4950 | 4548
15TPIT0046 | Yucca Drive - Barstow NW 138 kV line | Construct new line. | Construction schedule change | Yucca Drive | Barstow NW | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8070-E | 2016-12-15 |  | 138 | 35 | 0 | 0 |  | Ward | Ward | Tier 4 | 2013-02-15 | 2013-02-15 |  | 1086, 1009, 38150 | Y | N |  |  | 2305 | 2232
15TPIT0070 | North Andrews - Andrews Switch 69 kV Line | Rebuild existing Andrews Switch - Fullerton 69 kV line section as a double-circuit line with a 69 kV circuit and a 138 kV circuit. Includes 16TPIT0046 Frankel City - Exxon Fullerton 69 kV Line. | Construction schedule change | Andrews Switch | Fullerton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8292 | 2016-12-15 |  | 69 | 0 | 14.8 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1267, 1270, 1271, 1274, 1275 | Y | N |  |  | 3327 | 3156
4215 | Midessa South - Spraberry 138 kV Line | Rebuild Spraberry - Odessa TI Tap 138 kV line section using double-circuit 138 kV structures. Install a second circuit from Midessa South to Spraberry | Construction schedule change | Midessa South | Spraberry | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8255 | 2016-12-15 |  | 138 | 16 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1124, 1329 | Y | N |  |  | 4576 | 4215
4243 | Holt - North Andrews 138 kV Line | Upgrade existing line | Construction schedule change | Holt | North Andrews | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8212 | 2016-12-15 |  | 138 | 0 | 22.1 | 0 |  | Ector | Andrews | Tier 4 |  |  |  | 1141, 1154, 1161, 1281, 1159, 1283 | Y | N |  |  | 4616 | 4243
4367 | Screwbean Tap - Culberson 138 kV Line | Rebuild existing 138 kV line | Construction schedule change | Screwbean Tap | Culberson | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8274 | 2016-12-15 |  | 138 | 0 | 19.6 | 0 |  | Culberson | Culberson | Tier 4 |  |  |  | 1095, 1096, 1097 | Y | N |  |  | 4741 | 4367
4518 | Midessa South 345/138 kV autotransformer | Install 345/138 kV autotransformer in the existing Midessa South Switching Station | Construction schedule change | Midessa South |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8259 | 2016-12-15 |  | 345 | 0 | 0 | 450 |  | Midland |  | Tier 4 |  |  |  | 1125, 1058, 11028, 1124 | Y | N |  |  | 4915 | 4518
4760 | Jewett 345/138 kV autotransformer | Jewett second 345/138 kV autotransformer |  | Jewett |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1914 | 2016-12-15 |  | 345 | 0 | 0 | 600 |  | Leon |  | Tier 3 | 2015-05-15 | 2015-06-15 |  | 13392, 3390, 3394 | Y | N |  |  | 5181 | 4760
4765 | Leon 69 kV Sw Sta | Upgrade switching station | Construction schedule change | Leon Sw. |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1725 | 2016-12-15 |  | 69 | 0 | 0 | 0 |  | Eastland |  | Tier 4 |  |  |  | 1625 | Y | N |  |  | 5188 | 4765
4973 | LCRATSC_BlewettSubstation | Provide transmission service for a new substation to be served off of the T570 Uvalde to Odlaw transmission line. |  | Odlaw | Asphalt Mines | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015146 | 2016-12-15 |  | 138 | 0 | 0 | 0 |  | Uvalde | Uvalde | Tier 4 |  |  |  | 78424, 7425, 8246 | Y | N |  |  | 5433 | 4973
4878 | Twin Buttes Auto Transformer | Install a new 345/138 kV 672 MVA auto transformer at Twin Buttes substation |  | Twin Buttes |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014328 | 2016-12-22 |  | 345 | 0 | 0 | 672 |  | Tom Green |  | Tier 4 |  |  |  | 77280, 76009, 76011, 77281 | Y | N |  |  | 5314 | 4878
4493 | Pharr 138 kV Loop | McColl Road & North McAllen to Pharr: Reroute 138 kV Line |  | MCCOLL ROAD & NORTH MCALLEN | PHARR | Under Construction | 704-0874 | AEP TCC | Michael Tallon DNLYONS@AEP.COM 918-599-2698 | 3548 | 2016-12-30 |  | 138 | 2.2 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8368, 8372, 8908 | Y |  |  |  | 5552 | 4493
3396 | Cedar Hill: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Cedar Hill | Schedule Update | Cedar Hill |  | Under Construction | 626 - 0794 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2584 | 2016-12-31 |  | 69 | 0 | 0 | 90 |  | Coke |  | Tier 4 |  |  |  | 6423, 6425 | Y | N |  |  | 3594 | 3396
3398 | Cedar Hill: Add 69 kV capacitor bank | Add one 7.2 Mvar capacitor bank at Cedar Hill | Schedule Update | Cedar Hill |  | Under Construction | 629 - 0797 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2587 | 2016-12-31 |  | 69 | 0 | 0 | 0 | 0,7.2 | Coke |  | Tier 4 |  |  |  | 6423 | Y | N |  |  | 3596 | 3398
3402 | Abilene Northwest to Ely Tap: Rebuild 69 kV line | Rebuild Abilene Northwest to Ely Tap 69 kV line with 959.6 ACSS/TW |  | Abilene Northwest | Ely Tap | Planned | 630 - 0798 | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | 2589 | 2016-12-31 |  | 69 | 0 | 8.2 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6225, 6241 | Y | N |  |  | 3600 | 3402
13TPIT0160 | Whitepoint: Add 138 kV breaker terminal for WF interconnect | Construct a 138 kV breaker terminal at Whitepoint for the Generator Interconnect |  | Whitepoint |  | Under Construction | 573-0750 | AEP TCC | Rick McCraken DNLYONS@AEP.COM 918-599-2698 | 3454 | 2016-12-31 |  | 138 |  |  |  |  | San Patricio |  | Tier 4 |  |  |  | 8961 | Y | N |  |  | 3976 | 3731
3767 | Three Rivers 138 kV: Replace 138/69 kV Autotransformer | Replace 138/69 kV Auto at Three Rivers 138 kV Station | Changed Super project ID, Transmission Status, ISD, PM, and Estimate | THREE RIVER |  | Under Construction | 660-0829 | AEP TCC | Rick McCraken DNLYONS@AEP.COM 918-599-2698 | 3525 | 2016-12-31 |  | 138 |  |  | 130 |  | Live Oak |  | Tier 4 |  |  |  | 8400, 8403 | Y | N |  |  | 4012 | 3767
3796 | FrioAEP 69 kV station | Add new station for AEP load on 69 kV |  | Frio |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-12-31 |  | 69 | 0 | 0 | 0 |  | Frio |  | Tier 4 |  |  |  | 5845, 5842, 5893 | Y | N |  |  | 4047 | 3796
3797 | Shropshire 69 kV station | Add new station for AEP load on 69 kV |  | Shropshire |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2016-12-31 |  | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  | 5555, 5549, 5554 | Y | N |  |  | 4048 | 3797
3824 | Dow: Install 2nd 800MVA Autotransformer | Install 2nd DOW-Velasco 800MVA autotransformer at DOW substation | Delay in project schedule | DOW |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 993 | 2016-12-31 |  | 345 | 0.5 | 1.7 | 800 |  | Brazoria |  | Tier 3 | 2014-03-21 | 2014-04-30 |  | 42511, 49069, 43360, 42500 | Y | N |  |  | 4106 | 3824
3825 | Jordan: Install 2nd 800MVA Autotransformer | Install 2nd 800MVA autotransformer at Jordan substation |  | Jordan |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 992 | 2016-12-31 |  | 345 | 0 | 0 | 800 |  | Chambers |  | Tier 4 |  |  |  | 49078, 40850, 40855 | Y | N |  |  | 4107 | 3825
3998 | Stewart Road to Weslaco Unit: Rebuild 138 kV line | Rebuild 138 kV line from Stewart Road to Weslaco Unit |  | STEWART ROAD | WESLACO UNIT | Planned | 680-0849 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3536 | 2016-12-31 |  | 138 |  | 15 |  |  | Hidalgo | Hidalgo | Tier 3 |  |  |  | 8348, 8951 | Y | N |  |  | 4324 | 3998
4200 | Sage: Build 69 kV station | Construct new 69 kV in and out substation off the Crane loop, and demolish Crane Gulf #1 |  | Sage |  | Planned | 697 - 0867 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2266 | 2016-12-31 |  | 69 | 0 | 0 | 0 |  | Crane |  | Tier 4 |  |  |  | 6604, 6608 | Y | N |  |  | 4556 | 4200
16TPIT0031 | Esmeralda: Build 138 kV station and add capacitor banks | Construct new Esmeralda station along the Big Lake to Friend Ranch 138 kV line, install one 14.4 Mvar and two 7.2 Mvar capacitor banks, and build a new 138 kV line from Esmeralda to Yucca with 795 ACSS |  | Esmeralda |  | Planned | 585 - 0738 | AEP TCC | Eric Scott myturner@aep.com 918-599-2437 | 2576 | 2016-12-31 |  | 138 | 0 | 0 | 0 | 0,28.8 | Crockett |  | Tier 4 |  |  |  | 6525, 6562, 60375 | Y | N |  |  | 4646 | 3241
4503 | BRYN_4503_Rayburn_Tabor_Upgrade | Reconductor Rayburn to Tabor Line with 1033 |  | 32861 | 32870 | Planned |  | BRYN |  |  | 2016-12-31 |  | 69 | 0 | 4.06 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32861, 32870 | Y |  |  |  | 4900 | 4503
4516 | City of Brady to North Brady: Reterminate 69 kV line | Rebuild the 69 kV line from the City of Brady Tap to North Brady double circuit with 959.6 ACSR/TW to allow retermination of the City of Brady Tap line into North Brady station with the addition of a breaker | Schedule and Cost Update | City of Brady | North Brady | Planned | 715 - 0881 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2813 | 2016-12-31 |  | 69 | 0 | 0.8 | 0 |  | McCulloch | McCulloch | Tier 4 |  |  |  | 6382, 6006, 6380, 6383 | Y | N |  |  | 4913 | 4516
4544 | Upgrade sections of 138kV Buffalo - Grady line |  |  | Buffalo | Grady | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-12-31 |  | 138 | 0 | 14.3 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79508, 79550, 79549, 79564 | Y | N |  |  | 4946 | 4544
4703 | Bellaire to San Felipe Ckt.09 | Reconductor Ckt.09 Bellaire to San Felipe | Delay in project schedule | Bellaire | San Felipe | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-12-31 |  | 138 | 0 | 2 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47010, 47380 | Y | N |  |  | 5115 | 4703
4705 | San Felipe to Eureka Ckt.09 | Reconductor a portion of San Felipe to Eureka Ckt.09 | Delay in Project Schedule | San Felipe | Eureka | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-12-31 |  | 138 | 0 | 3.3 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45750, 47382 | Y | N |  |  | 5117 | 4705
4709 | Install 100MVAr Capacitor Bank at Rothwood from EastSide | Remove East Side capacitor bank and move to Rothwood substation | Delay in project schedule | Rothwood |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47610, 47600, 47750, 46295 | Y | N |  |  | 5121 | 4709
4877 | Bakersfield: Build 345 kV terminal | Interconnect East Pecos solar farm at Bakersfield |  | Bakersfield |  | Planned | 728 - 0910 | ETT | Aaron Schwerman myturner@aep.com 918-599-2437 | 2911 | 2016-12-31 |  | 345 |  |  |  |  | Pecos |  | Tier 4 |  |  |  | 6101 | Y | N |  |  | 5313 | 4877
5175 | Albercas: Install RTU | Interconnect Albercas Windfarm at Cenizo to connect Albercas on the Cenizo to Bordas 345 kV line |  | Albercas | Bordas | Planned | 751 - 0934 | ETT | Dan Lyons dnlyons@aep.com 918-599-2698 | 2925 | 2016-12-31 |  | 345 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  | 80355 | Y | Y |  |  | 5659 | 5175
5194 | Weiss: Build 138 kV station | Construct new 138 kV box bay at the CRMWD tap #2 on the Red Creek to Ballinger 138 kV line | NEW | Weiss |  | Planned | 757 - 0941 | AEP TNC | Rick McCracken gareed@aep.com 918-599-2664 | 2632 | 2016-12-31 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  | 60399, 6340, 6442, 6458 | Y | N |  |  | 5678 | 5194
3911 | Cheniere LNG | Cheniere LNG |  | Hecker |  | Planned | 616 - 0784 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3534 | 2017-01-02 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8568, 8565, 8961, 80470 | Y | N |  |  | 4209 | 3911
3903 | Lobo 345 kV Station: Add 345/138 kV Auto | Add 2nd 345/138 kV Autotransformer at Lobo Switching Station |  | Lobo |  | Under Construction | 663 - 0832 | ETT | MICHAEL GLUECK DNLYONS@AEP.COM 918-599-2698 | 3538 | 2017-01-15 |  | 345 | 0 | 0 | 675 |  | Webb |  | Tier 4 |  |  |  | 80219, 80221 | Y | N |  |  | 4199 | 3903
5080 | Bronco: Build 69 kV temporary tap | Interconnect Solaire Holman solar farm at temporary tap to connect Solaire Holman to the Alpine to Fort Stockton Plant 69 kV line | NEW | Bronco |  | Planned | 740 - 0923 | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | 2620 | 2017-01-22 |  | 69 |  |  |  |  | Brewster |  | Tier 4 |  |  |  | 6674, 6666, 38490 | Y | N |  |  | 5560 | 5080
4895 | CPSE_Capitol Cement Transmission Reconfiguration | Re-configurate Capitol Cement by loop into the existing Dresden to Skyline 138 kV transmission line and removing the existing Captiol Cement to Tuttle 138 kV transmission line. |  | Capitol Cement | Dresden/Skyline | Planned | S-0767 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0246 | 2017-01-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5075, 5130, 5370, 5435 | Y | N |  |  | 5332 | 4895
05TPIT0065 | Highway 32-Wimberley | Construct a new 795 ACSR (220-MVA) 138-kV transmission line (approximately four miles) between the Highway 32(7546) and Wimberley(7496) substations. |  | Highway 32 | Wimberley | Planned |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2017-02-01 |  | 138 | 4 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  | 7496, 7545, 7546 | Y | N |  |  | 998 | 997
5140 | Friendswood Generation (13INR0049) Transmission Network | New 138 kV, 3 breaker ring with generator lead. Ckt. 05 WAP to HOC will be relocated FEGC @ HOC bus. |  | HO Clarke |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-02-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 47170, 44081, 47150 | Y | N |  |  | 5618 | 5140
3705 | Solstice: Build 138 kV station | Construct new Solstice station along the Barrilla Junction to Fort Stockton Plant 138 kV line |  | Solstice |  | Planned | 658 - 0827 | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | 1822 | 2017-02-28 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60383, 60385, 6630, 6655, 6680, 60393 | Y | N |  |  | 4870 | 3705
5172 | Laredo: Add two 138 kV breakers | Add two 138 kV breakers to the STATCOM yard and rebuild the Laredo to Laredo STATCOM 138 kV tie with 1026 ACCC/TW |  | Laredo | Laredo | Planned | 744 - 0927 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2918 | 2017-03-01 |  | 138 | 0 | 0.111 | 0 |  | Webb | Webb | Tier 4 |  |  |  | 8293, 80021 | Y | N |  |  | 5656 | 5172
5174 | Nelson Sharpe: Reconfigure PST | Relocate the PST at Nelson Sharpe from the Barney Davis to Nelson Sharpe 138 kV line to the Nelson Sharpe to Celanese Bishop 138 kV line |  | Nelson Sharpe |  | Planned | 747 - 0930 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2921 | 2017-03-01 |  | 138 | 0 | 0 | 150 |  | Nueces |  | Tier 4 |  |  |  | 85003, 8516, 85001 | Y | N |  |  | 5658 | 5174
3353 | Aransas Pass to Rockport: Convert 69 kV line to 138 kV | Expand Aransas Pass and Rockport 138 kV stations and add 138/69 kV autotransformer capacity at Rockport |  | Aransas Pass | Rockport | Planned | 624 - 0792 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3507 | 2017-03-14 |  | 138 | 0 | 0 | 90 |  | Medina |  | Tier 4 |  |  |  | 8427, 8430, 8432, 8434 | Y |  |  |  | 3542 | 3353
5145A | Rafter - New 138 kV Substation | Loop new 138 kV load serving substation into the existing Castroville to Texas Research 138 kV transmission line. |  | RAFTER | CASTROVILLE/TX_RSRCH | Planned | S-0837 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0261 | 2017-03-15 |  | 138 | 0.77 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5355, 5083, 5430 | Y |  |  |  | 5623 | 5145
16TPIT0032 | Esmeralda to Yucca: Build 138 kV line | Construct new Esmeralda station along Big Lake to Friend Ranch 138 kV line and build new 138 kV line from Esmeralda to Yucca with bundled 959.6 ACSS |  | Esmeralda | Yucca | Planned | 585 - 0745 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2577 | 2017-03-31 |  | 138 | 13 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  | 6034, 6035, 6036, 6531, 6525 | Y | N |  |  | 2761 | 2637
3760 | Asherton to Carrizo Springs: 69 kV Transmission Line Rebuild | Rebuild 69 kV line from Asherton to Carrizo Spring |  | ASHERTON | CARRIZO SPRING | Under Construction | 661-0830 | AEP TCC | Aaron Schwerman DNLYONS@AEP.COM 918-599-2698 | 3526 | 2017-03-31 |  | 69 |  | 8.3 |  |  | Dimmit | Dimmit | Tier 4 |  |  |  | 8244, 8280 | Y | N | NA |  | 4005 | 3760
4920 | Divot 138 kV Substation | Add new station between Palo Duro and Batesville |  | Divot |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-03-31 |  | 138 | 0 | 0 | 0 |  | Frio |  | Tier 4 |  |  |  | 5865, 5851, 5866 | Y | N |  |  | 5359 | 4920
4950 | Oyster Creek 138kV Substation - GINR - 16INR0003 | Loop new 138kV Oyster Creek substation from Ckt.82 Velasco to BIPORT | Accelerated Project Schedule | Oyster Creek | Velasco/BIPORT | Planned | 4710 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-03-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43335, 43336, 43337, 42190, 43360 | Y | N |  |  | 5408 | 4950
5232 | Castillo Substation Addition | Provide transmission service for a generator off T4521 138-kV line between North McCamey and LCRA Crane Substations. |  | North McCamey | LCRA Crane | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015822 | 2017-03-31 |  | 138 | 1.64 | 0 | 0 |  | Upton | Crane | Tier 4 |  |  |  | 76040, 76032, 76615 | Y | N |  |  | 5730 | 5232
4970 | Magic Valley Tap: Build new 345 kV temporary tap | Interconnect Magic Valley II Windfarm at temporary tap to connect Magic Valley II to the Ajo to Rio Hondo 345 kV line |  | Ajo | Rio Hondo | Planned | 731 - 0912 | AEP TCC | Michael Glueck dnlyons@aep.com 918-599-2698 | 3561 | 2017-04-01 |  | 345 | 0 | 0 | 0 |  | Willacy |  | Tier 4 |  |  |  | 80512, 8902, 80076 | Y |  |  |  | 5430 | 4970
4978 | Helena Circuit Breaker Addition | Install two 138-kV circuit breakers at Helena in a single bus-single breaker configuration. |  | Helena |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015114 | 2017-04-01 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  | 78584 | Y | N |  |  | 5438 | 4978
4979 | Upton Circuit Breaker Addition | Install two 138-kV circuit breakers at Upton in a single bus-single breaker configuration. |  | Upton |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015131 | 2017-04-01 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  | 71212, 1212, 1214, 71213 | Y | N |  |  | 5439 | 4979
3897 | Add New FM758 Sub | Construct a new 138-kV FM758 (7758) substation, which will cut into the LCRA TSC Clear Springs (7680) to Freiheit (7462) 138-kV transmission line |  | FM758 | Freiheit Road / Clear Springs | Planned |  | LCRATSC/NBU | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2017-04-27 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7758, 7462, 7680 | Y | N |  |  | 4847 | 3897
15TPIT0054 | Barney Davis To Naval Base Construct 138 kV line | Construct new 138 kV line and add tranformation at Naval Base to remove contingency overloads during off-peak maintenance |  | BARNEY DAVIS | NAVAL BASE | Under Construction | 607 - 0648 | AEP TCC | JOHN PULAY DNLYONS@AEP.COM 918-599-2698 | 3484 | 2017-04-30 |  | 138 | 7 |  |  |  | Nueces | Nueces | Tier 1 | 2013-07-15 | 2013-12-20 | 2013-01-24 | 8458, 8997 | Y | N |  |  | 3726 | 3519
3819 | Rebuild San Miguel to North Calliham | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Sam Miguel | North Calliham | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-04-30 |  | 69 | 0 | 21.3 | 0 |  | Atascosa | McMullen | Tier 4 |  |  |  | 5693, 5698, 5702 | Y | N |  |  | 4101 | 3819
4858 | Hendrick: Build 138 kV station | Interconnect Alamo 7 solar farm at Hendrick to connect Alamo 7 to the Abilene Northwest to Paint Creek 138 kV line | Contact and Cost Update | Hendrick |  | Planned | 721 - 0903 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2613 | 2017-04-30 |  | 138 | 0.9 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  | 60387, 6169, 6228 | Y | N |  |  | 5286 | 4858
5017 | Lotebush: Build 138 kV station | Construct new 138 kV ring bus on the Barrilla Junction to Permian Basin Line |  | Lotebush |  | Planned | 736 - 0919 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2616 | 2017-04-30 |  | 138 | 1 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60392, 1243, 1247, 6656, 6657, 60397 | Y | N |  |  | 5475 | 5017
5019 | Pig Creek: Build 138 kV station | Construct new 138 kV ring bus on the Barrilla Junction to Permian Basin Line | Contact Update | Pig Creek |  | Planned | 737 - 0920 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2618 | 2017-04-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 60385, 60393 | Y | N |  |  | 5477 | 5019
5191 | Gas Pad Tap: Build 138 kV station | Construct 138 kV POD box bay for customer interconnection | NEW | Gas Pad Tap |  | Planned | 755 - 0938 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2629 | 2017-04-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 60397 | Y | N |  |  | 5675 | 5191
4716 | Tortuga: Build new 3 breaker 138 kV station | Construct new Tortuga 138 kV line and cut it into the Gila - Upriver (Koch) 138 kV line |  | Gila | Upriver (Koch) | Planned | 717 - 0899 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3553 | 2017-05-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8168, 81680, 8467, 80260 | Y |  |  |  | 5214 | 4716
4873 | Smoky Hill: Build 345 kV station | Interconnect Horse Creek wind farm at Smoky Hill to connect Horse Creek to the Clear Crossing to Edith Clarke 345 kV line |  | Smoky Hill |  | Planned | 726 - 0908 | ETT | Mike Tallon myturner@aep.com 918-599-2437 | 2909 | 2017-05-01 |  | 345 |  |  |  |  | Haskell |  | Tier 4 |  |  |  | 6104, 60515, 60701 | Y | N |  |  | 5309 | 4873
5076 | Smoky Hill: Build 345 kV terminal | Interconnect Willow Springs wind farm at Smoky Hill to connect Willow Springs to the Clear Crossing to Edith Clarke 345 kV line | NEW | Smoky Hill |  | Planned | 734 - 0916 | AEP TNC | Mike Tallon myturner@aep.com 918-599-2437 | 2614 | 2017-05-01 |  | 345 |  |  |  |  | Haskell |  | Tier 4 |  |  |  | 6104 | Y | N |  |  | 5556 | 5076
09TPIT0122 | Shamburger - Tyler NW 138 kV line | Upgrade existing 138 kV line | Construction schedule change | Shamburger | Tyler NW | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6001-E | 2017-05-15 |  | 138 | 0 | 6.3 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3104, 3141 | Y | N | 2009-E6 |  | 1243 | 1240
1332 | Elm Mott - Waco West/Waco East 138 kV Line | Upgrade existing Elm Mott - Waco Northeast Tap line section |  | Elm Mott | Waco Northeast Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1719 | 2017-05-15 |  | 138 | 0 | 6.7 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  | 3407, 3550, 3551, 3575 | Y | N |  |  | 1336 | 1332
11TPIT0034 | Sargent Road 345/138 kV autotransformer | Install second 345/138 kV autotransformer |  | Sargent Road |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M486-E | 2017-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  | 2946, 2949 | Y | N |  |  | 1826 | 1784
16TPIT0054 | Dialville - Palestine South 138 kV Line | Upgrade existing Dialville - Palestine South line section |  | Dialville | Palestine South | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6019 | 2017-05-15 |  | 138 | 0 | 25 | 0 |  | Cherokee | Andrews | Tier 3 |  |  |  | 3160, 3271, 3296 | Y | N |  |  | 3283 | 3114
17TPIT0020 | Forest Grove - Trinidad 138 kV Line | Upgrade existing line |  | Forest Grove | Trinidad | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6034 | 2017-05-15 |  | 138 | 0 | 14.5 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  | 3127, 3131, 3276, 29266 | Y | N |  |  | 3322 | 3151
14TPIT0008 | Holt - Emma Tap - Andrews 69 kV Line | Upgrade existing line. |  | Holt | Andrews | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8144-E | 2017-05-15 |  | 69 | 0 | 16.2 | 0 |  | Ector | Andrews | Tier 4 |  |  |  | 1142, 1262, 1267 | Y | N | 2009-R5 |  | 3331 | 3160
06TPIT0042 | Lake Wichita Switch - Wichita Falls Switch 69 kV line | Upgrade existing 69 kV line and convert to 138 kV operation |  | Lake Wichita Switch | Wichitia Falls Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R933-E | 2017-05-15 |  | 138 | 0 | 6.3 | 0 |  | Archer | Wichita | Tier 4 |  |  |  | 1446, 1447, 1448, 1449 | Y | N |  |  | 3390 | 3217
4213 | Morgan Creek - Sun Switching Station 138 kV Line | Upgrade existing line |  | Morgan Creek | Sun Switching Station | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R9005 | 2017-05-15 |  | 138 | 0 | 33.9 | 0 |  | Mitchell | Scurry | Tier 3 |  |  |  | 1032, 1064 | Y | N |  |  | 4574 | 4213
4240 | McKenzie Draw - Texaco Mabee 138 kV Line | Construct new line. | Scope change | McKenzie Draw | Texaco Mabee | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8213 | 2017-05-15 |  | 138 | 10 | 0 | 0 |  | Martin | Andrews | Tier 4 | 2015-04-01 | 2015-05-22 |  | 1169, 1171, 1177 | Y | N |  |  | 4613 | 4240
4253 | Eagle Mountain - Calmont 138 kV Line | Upgrade existing double-circuit line | Construction schedule change | Eagle Mountain | Calmont | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5213 | 2017-05-15 |  | 138 | 0 | 40.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1860, 1865, 1955, 2085, 2086, 2087, 2088, 11860 | Y | N |  |  | 4624 | 4253
4263 | Tyler Northwest - Elkton 138 kV Line | Upgrade existing Tyler West - Tyler Northwest 138 kV line Section |  | Tyler West | Tyler Northwest | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6053 | 2017-05-15 |  | 138 | 0 | 3.7 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3139, 3141 | Y | N |  |  | 4636 | 4263
4267 | Andrews County South - North Andrews 138 kV Line | Upgrade existing line |  | Andrews County South | North Andrews | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8235 | 2017-05-15 |  | 138 | 0 | 18 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1153, 1155, 1157, 1159 | Y | N |  |  | 4640 | 4267
4268 | Breckenridge - Leon Switch 69 kV Line | Upgrade existing line | Construction schedule change | Breckenridge | Leon Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R783 | 2017-05-15 |  | 69 | 0 | 17 | 0 |  | Stephens | Eastland | Tier 3 |  |  |  | 271, 1622, 1615, 1625 | Y | N |  |  | 4641 | 4268
11TPIT0033 | Saginaw - North Main 138 kV Line | Upgrade existing 138 kV line | Construction schedule change | Saginaw | North Main | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5070-E | 2017-05-15 |  | 138 | 0 | 5.5 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1957, 1961, 2146, 2148 | Y | N |  |  | 4642 | 4269
4280 | Allen Switching Station 138 kV series reactor | Install series reactor on 345/138 kV autotransformer #2 |  | Allen Switching Station |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R961 | 2017-05-15 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 12514, 2512, 2514, 12512 | Y | N |  |  | 4655 | 4280
4285 | Prairie Creek - Parkdale 138 kV Line | Upgrade existing double-circuit line |  | Prairie Creek | Parkdale | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4132 | 2017-05-15 |  | 138 | 0 | 5.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2441, 2442, 2445, 2743, 2762, 2763 | Y | N |  |  | 4662 | 4285
4299 | Big Brown - Navarro Switch 345 kV Line | Upgrade existing double-circuit line |  | Big Brown | Navarro Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1705 | 2017-05-15 |  | 345 | 0 | 62 | 0 |  | Freestone | Navarro | Tier 4 | 2015-06-15 |  |  | 3380, 68091 | Y | N |  |  | 4680 | 4299
4523 | McKenzie Draw Switching Station | Construct new switching station | Construction schedule and scope change | McKenzie Draw |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8288 | 2017-05-15 |  | 138 | 0 | 0 | 0 | 0,73.6 | Martin |  | Tier 4 |  |  |  | 1169 | Y | N |  |  | 4920 | 4523
4524 | Culberson 138 kV Switching Station | Rebuild 138 kV bus | Construction schedule change | Culberson Switching station |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8070B | 2017-05-15 |  | 138 | 0 | 0 | 0 |  | Culberson |  | Tier 4 | 2013-02-15 | 2013-02-15 |  | 1097 | Y | N |  |  | 4921 | 4524
15TPIT0083B | Collin - Arco (TMPA) 138 kV Line (Oncor's section) | Add second circuit to existing line from Krugerville to Arco (TMPA) |  | Krugerville | Arco (TMPA) | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R929 | 2017-05-15 |  | 138 | 5.7 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | Y | N |  |  | 4926 | 3216
4734 | Chalk 69 kV Switching Station conversion | Convert existing 69 kV switching station into a 138 kV load serving substation |  | Chalk |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8219 | 2017-05-15 |  | 138 | 0 | 0 | 0 |  | Howard |  | Tier 4 |  |  |  | 1352, 11352, 1218, 1322, 1333, 1353, 6436 | Y | N |  |  | 5153 | 4734
4735 | Wink - Permian Basin 69 kV Line | Convert existing 69 kV line to 138 kV operation |  | Wink | Permian Basin | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8307 | 2017-05-15 |  | 138 | 0 | 20.3 | 0 |  | Winkler | Ward | Tier 3 |  |  |  | 1296, 1297, 11297, 1010, 1015, 1074, 1075, 1295 | Y | N |  |  | 5154 | 4735
4752 | Venus Sw Sta - Cedar Hill 138 kV line | Rebuild existing line | Construction schedule change | Venus Sw Sta | Cedar Hill | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4201 | 2017-05-15 |  | 138 | 0 | 20.6 | 0 |  | Ellis | Dallas | Tier 4 |  |  |  | 1908, 2300, 2310, 2311, 2313, 2314, 3053, 3054 | Y | N |  |  | 5172 | 4752
4761 | Trinidad - Jewett 138 kV Line | Upgrade Trinidad - Big Brown Tap line section | Construction schedule change | Trinidad | Big Brown Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R2004 | 2017-05-15 |  | 138 | 0 | 26.4 | 0 |  | Henderson | Leon | Tier 4 |  |  |  | 212, 3127, 3505 | Y | N |  |  | 5184 | 4761
16TPIT0062 | Hutto Sw Sta - Gilleland Creek (LCRA) 138 kV Line | Upgrade existing line |  | Hutto Sw Sta | Gilleland Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R773-E | 2017-05-15 |  | 138 | 0 | 22 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 3654, 3665, 3666, 7336 | Y | N |  |  | 5198 | 3079
4793 | East Levee - Industrial 138 kV Line | Upgrade existing line |  | East Levee | Industrial | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4213 | 2017-05-15 |  | 138 | 0 | 3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2482, 2875, 2976 | Y | N |  |  | 5219 | 4793
4801 | Wichita Falls Cogen - Bowman 138 kV Line | Upgrade existing Wichita Falls Cogen - Certainteed line section |  | Wichita Falls Cogen | Certainteed | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4001 | 2017-05-15 |  | 138 | 0 | 0.5 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  | 1496, 1498 | Y | N |  |  | 5232 | 4801
4937 | Wolf 138 kV Switching Station | Construct new 138 kV switching station |  | Monahans Switching Station |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8262 | 2017-05-15 |  | 138 | 0 | 0 | 0 |  | Ward |  | Tier 3 |  |  |  | 1013, 1009, 1010, 1105, 1087, 1103, 1107, 1292, 1015 | Y | N |  |  | 5395 | 4937
4784B | Forest Hill - Cresson 69 kV Line Conversion | Convert existing 69 kV line section from Forest Hill to Crowley to 138 kV operation and rebuild existing 69 kV line section from Crowley to Cresson to 138 kV operation | Construction schedule and scope change | Crowley | Cresson | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5227 | 2017-05-15 |  | 138 | 0 | 9.1 | 0 |  | Tarrant | Parker | Tier 4 | 2015-05-07 | 2015-06-01 |  | 2204, 2205, 12209, 1967, 1968 | Y | N |  |  | 5485 | 4784
4743 | Plano Tennyson - Collin/Northwest Carrollton 138 kV Line | Upgrade the Plano Tennyson - Austin Ranch Junction double-circuit line section | Construction schedule change | Plano Tennyson | Austin Ranch Junction | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M369 | 2017-05-16 |  | 138 | 0 | 8.2 | 0 |  | Collin | Denton | Tier 4 |  |  |  | 673, 676, 678, 2377, 2378, 2521, 2523, 2518, 2519, 2568, 2570 | Y | N |  |  | 5163 | 4743
4710A | Jones Creek Project | Build 345/138 kV Jones Creek Substation. Install first 800MVA autotransformer. |  | Jones Creek |  | Planned | 4950 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 926 | 2017-05-23 |  | 345 | 0 | 0 | 800 |  | Brazoria |  | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42530, 42540, 49036 | Y | N |  |  | 5122 | 4710
4710B | Jones Creek Project | Install second 800MVA autotransformer at Jones Creek substation. |  | Jones Creek |  | Planned | 4950 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 926 | 2017-05-24 |  | 345 | 0 | 0 | 800 |  | Brazoria |  | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 49037, 42530, 42540 | Y | N |  |  | 5123 | 4710
4710C | Jones Creek Project | Loop 345kV Ckt.18 into Jones Creek Substation |  | Jones Creek | DOW/STP | Planned | 4950 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 926 | 2017-05-25 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 5915, 42500, 42530 | Y | N |  |  | 5124 | 4710
3507 | Nopal Substation | Build a new 138-26.18 kV 18/24/30 MVA substation to be served by Gillett to Nopal 138 kV transmission line |  | Nopal |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-05-26 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7233 | Y | N |  |  | 3714 | 3507
4710D | Jones Creek Project | Loop 138kV circuits 02, 48, and 59 into Jones Creek Substation |  | Jones Creek | Velasco/Freeport | Planned | 4950 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 926 | 2017-05-26 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42540, 42645, 43360 | Y | N |  |  | 5125 | 4710
3509 | Gillett Sub (LCRA) to Nopal Sub 138 kV Transmission Line | Add 138 Terminal at LCRA Gillett Station; Build approx 9 miles of single ckt 138 kV t-line, 795 ACSR |  | Gillett | Nopal | Planned | 15TPIT0063 | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-05-27 |  | 138 | 8.5 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  | 7233, 78582 | Y | N |  |  | 3716 | 3509
4710E | Jones Creek Project | Reconfigure Freeport area circuits to create a loop with Ckt.59 from Velasco to Surfside to Freeport to Jones Creek and Ckt.02 Jones Creek to Velasco. |  | Velasco | Surfside/Freeport/Jones Creek/Velasco | Planned | 4950 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 926 | 2017-05-27 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42645, 43155, 43315, 43360 | Y | N |  |  | 5126 | 4710
4710F | Jones Creek Project | Reconfigure Freeport area circuits to create a Ckt.48 circuit from Velasco to MARINE to CORTEZ to Quintana to Jones Creek. |  | Jones Creek | MARINE/CORTEZ/Quintana/Jones Creek | Planned | 4950 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 926 | 2017-05-28 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42540, 42645, 43155, 43435, 43315, 43360 | Y | N |  |  | 5127 | 4710
4997A | Deepwater Area Conversion to 138kV | Convert MOCHEM sub to 138kV service. Loop from Ckt.70 Goodyear to Deepwater/Lydell. New substation name is BRANUM. |  | BRANUM | Goodyear/Deepwater | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-05-28 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40640, 41080, 40460, 40470, 40650, 41560 | Y | N |  |  | 5455 | 4997
3682A | Katy Area Upgrades | Convert Franz Substation to loop service from 138kV Ckt.09. Install new conductor and reconfigure/upgrade existing lines to create new Ckt.09 Zenith to Franz to Katy to Flewellen. |  | Zenith | Katy | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 860 | 2017-05-29 |  | 138 | 6.4 | 1.6 | 0 |  | Harris | Waller | Tier 2 | 2013-12-18 | 2014-05-15 |  | 44260, 44261, 44262, 44420, 44421, 44422, 44910, 45770 | Y | N |  |  | 3921 | 3682
15TPIT0043C | Fort Bend Area Upgrades | Remove Richmond substation from CNP transmission service | Delay in project schedule | Richmond |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 937 | 2017-05-29 |  | 69 | 0 | 0 | 0 |  | Fort Bend |  | Tier 3 | 2012-09-14 | 2012-10-29 |  | 44580, 44290 | Y | N |  | Cost included in project 15TPIT0043D. | 4569 | 4208
4710G | Jones Creek Project | Upgrade Quintana loop: Reconductor portions of Ckt.48 Velasco to MARINE to CORTEZ to Quintana to Jones Creek. |  | Velasco | Jones Creek | Planned | 4950 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 926 | 2017-05-29 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42540, 43155, 43435, 43360 | Y | N |  |  | 5128 | 4710
3682B | Katy Area Upgrades | Convert Katy substation ckt 09 tap to loop service to modify Ckt.09 Flewellen to Katy to Franz. |  | Katy |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 860 | 2017-05-30 |  | 138 | 0 | 0 | 0 |  | Waller |  | Tier 2 | 2013-12-18 | 2014-05-15 |  | 44420, 44421, 44230, 44422, 45770 | Y | N |  | Cost included in project 17TPIT3682A. | 3922 | 3682
4458 | Altair to Glidden Transmission Line Overhaul | Upgrade the 12.2 mile Altair (78106) - Stafford Hill (78520) - Columbus (78111) - Glidden (78107) 69-kV transmission line to 795 ACSR Drake (111 MVA), 138-kV capable with OPGE shield wire. |  | Altair | Glidden | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1011917 | 2017-05-30 |  | 69 | 0 | 12.2 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  | 78106, 78107, 78111, 78520 | Y | N |  |  | 4843 | 4458
4710H | Jones Creek Project | De-energize a portion of existing Ckt.02 Velasco to Franklins Camp and reconfigure create new Ckt.02 Jones Creek to Franklins Camp. |  | Jones Creek | Franklins Camp | Planned | 4950 | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 926 | 2017-05-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 2014-07-01 | 2014-11-13 | 2015-02-10 | 42195, 42540, 43360 | Y | N |  |  | 5129 | 4710
5042 | BRYN_5042_BRYN_TAMU_RP | Build and Loop in New TAMU Research Park Substation |  |  |  | Planned |  | BRYN |  |  | 2017-05-30 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32797, 32005, 32799 | Y |  |  |  | 5516 | 5042
15TPIT0057 | Wylie 138 kV new switchyard and connections | Wylie 138 kV switchyard and its connections to Olinger, to Firewheel, to Elm Grove, and to Nevada | On Hold For Funding | New switches at Wylie | Switches at Olinger, at Friewheel, at Elm Grove, and at Nevada | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2017-05-31 |  | 138 | 0 | 36.75 | 0 |  | Collin | Dallas | Tier 4 |  |  |  | 833, 811, 818, 821, 855 | Y | N |  |  | 2750 | 2629
3682C | Katy Area Upgrades | Install a second 800MVA autotransformer at Zenith Substation. |  | Zenith |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 860 | 2017-05-31 |  | 345 | 0 | 0 | 800 |  | Harris |  | Tier 2 | 2013-12-18 | 2014-05-15 |  | 49090, 44900, 44910 | Y | N |  | Cost included in project 17TPIT3682A. | 3923 | 3682
14TPIT0067 | Red Creek: Replace one of the 345/138 kV autotransformers | Replace both 345/138 kV autotransformers at Red Creek with 480 MVA autotransformers |  | Red Creek |  | Planned | 566 - 0740 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2570 | 2017-05-31 |  | 345 | 0 | 0 | 480 |  | Tom Green |  | Tier 4 |  |  |  | 6295, 6444, 6442 | Y | N |  |  | 4185 | 1824
3900 | LaPalma to Stewart Road: Rebuild 69 kV line | Rebuild La Palma to Stewart Road 69 kV line with 959.6 ACSS/TW and add 138/69 kV autotransformer capacity at Stewart Road |  | La Palma | Stewart Road | Conceptual | 678 - 0847 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2597 | 2017-05-31 |  | 69 | 0 | 40.9 | 130 |  | Cameron | Hidalgo | Tier 3 |  |  |  | 8310, 8748, 8751, 8949, 8951 | Y | N |  |  | 4195 | 3900
3681 | TH Wharton to Addicks Ckt.71 Sub Upgrade | Upgrade substation equipment at TH Wharton and Addicks to increase thermal ratings for 345kV Ckt.71. | Delay in Project Schedule | TH Wharton | Addicks | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45500, 45600 | Y | N |  |  | 4268 | 3681
3951 | TH Wharton to Fairbanks Ckt.81 | Reconductor 138kV Ckt.81 TH Wharton to Fairbanks and upgrade substation equipment at TH Wharton and Fairbanks to increase thermal ratings. | Delay in Project Schedule | TH Wharton | Fairbanks | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-05-31 |  | 138 | 0 | 3.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45511, 45760 | Y | N |  |  | 4271 | 3951
3963 | Lockhart to Luling Transmission Line Upgrade | Upgrade the 16.9 miles Lockhart to Luling City 138kV line from existing 136 MVA to 221 MVA. Replace existing 45 MVA auto with 70 MVA auto. Upgrade both Lockhart and Luling to breaker and a half configuration. |  | Lockhart | Luling | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014350 | 2017-05-31 |  | 138 | 0 | 16.9 | 70 |  | Caldwell | Caldwell | Tier 4 |  |  |  | 7216, 7224, 7215 | Y | N |  |  | 4284 | 3963
4426 | Aritek to Chorin Ckt 87 Thermal Uprate | Upgrade 138kV Ckt.87 ARITEK to CHORIN to increase thermal ratings. | Delay in project schedule | ARITEK | CHORIN | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40120, 40320 | Y | N |  |  | 4810 | 4426
4446 | Luling to Nixon Transmission Line Overhaul | Upgrade the 15.62 mile Luling (7223) - Malone - Darst Creek - Deer Creek (7597) 69kV transmission line to 795 ACSR Drake (111 MVA), 138kV capable with OPGW shield wire. |  | Luling | Deer Creek | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1012406 | 2017-05-31 |  | 69 | 0 | 15.62 | 0 |  | Caldwell | Guadalupe | Tier 4 | 2015-02-18 | 2015-03-23 |  | 7223, 7597, 78195, 78579 | Y | N |  |  | 4834 | 4446
4487 | Sagan: Build new 69 kV station | Construct new Sagan station along the Valero East to Valero West 69 kV line, add 138/69 kV autotransformer capacity at Sagan, and build new Sagan to Champlin 138 kV line with 959.6 ACSS/TW |  | Champlin | Valero West | Planned | 709 - 0879 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2903 | 2017-05-31 |  | 138 | 1 | 0 | 130 |  | Nueces |  | Tier 4 |  |  |  | 8859, 8477 | Y | N |  |  | 4881 | 4487
4489 | Eagle Pass to Escondido: Rebuild 138kV line | Rebuild Eagle Pass to Escondido Circuit #1 with 959.6 ACSS/TW |  | Eagle Pass | Escondido | Under Construction | 708 - 0878 | AEP TCC | Michael Tallon dnlyons@aep.com 918-599-2664 | 2902 | 2017-05-31 |  | 138 | 0 | 1.5 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  | 8270, 8260 | Y | N |  |  | 4883 | 4489
4492 | Marconi: Build new three breaker 138 kV station | Interconnect San Roman Windfarm at Marconi to connect San Roman to the Port Isabel to Laureles 138 kV line by building new 138 kV line from Marconi to San Roman with 959.6 ACSS/TW |  | Marconi | San Roman | Planned | 712 - 0883 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 2906 | 2017-05-31 |  | 138 | 0.6 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  | 8262, 8266, 5756, 8338 | Y | N |  |  | 4886 | 4492
4707 | Velasco Cap Bank | Install 120MVAR capacitor bank at Velasco substation. |  | Velasco |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 926 | 2017-05-31 |  | 138 | 0 | 0 | 0 | 0,120 | Brazoria |  | Tier 4 |  |  |  | 43360 | Y | N |  |  | 5119 | 4707
4708 | Meadow: Install 600MVA Autotransformer A2 | Install 600MVA autotransformer A2 at Meadow (from PH Robinson substation) | Delay in Project Schedule | Meadow |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1116 | 2017-05-31 |  | 345 | 0 | 0 | 600 |  | Brazoria |  | Tier 4 |  |  |  | 49051, 43030, 43031 | Y | N |  |  | 5120 | 4708
4995 | Sandy Point 138kV Distribution Substation | Build new 138kV Sandy Point distribution substation. Loop through Ckt.96 ALKANE to LaPorte. | Change in project schedule | Sandy Point | ALKANE/LaPorte | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40090, 40160, 40941 | Y |  |  |  | 5453 | 4995
5030C | Flat Top Tie with AEP Pig Creek | Expand IH20 station for new 138/69 kV Auto, and 138 kV circuit breakers/bus. Rebuild line from Barilla Draw Tap-IH20 138 kV bus with 1926 ACSR/TW Cumberland. |  | 38040 | 38060 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-05-31 |  | 138 | 0 | 11.57 | 150 |  | Reeves | Reeves | Tier 3 | 2015-01-13 | 2015-06-19 |  | 38045, 38040, 38060 | Y |  |  | Conductor changed from RPG submittal from 795 ACSR to 1926 ACSR/TW Cumberland. | 5500 | 5030
5266 | Cuero - Luling Transmission Line Overhaul | Rebuild T542 Luling to Hocheim Tap from Luling to vicinity of Harwood to be 138-kV capable with a nominal conductor rating of 223 MVA at 138-kV (Single Drake) with OPGW and operated at 69-kV. |  | Hocheim | Luling | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016221 | 2017-05-31 |  | 69 | 0 | 10 | 0 |  | DeWitt | Gonzales | Tier 4 |  |  |  | 7223, 78577 | N | N |  |  | 5767 | 5266
5281 | Mason (CTEC) Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Mason (CTEC). |  | Mason (CTEC) |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016196 | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Mason |  | Tier 4 |  |  |  | 7395 | N | N |  |  | 5782 | 5281
5283 | Starcke Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Starcke. |  | Starcke |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016206 | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Burnet |  | Tier 4 |  |  |  | 7351 | N | N |  |  | 5784 | 5283
5284 | Tahitian Village Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Tahitian Village Substation. |  | Tahitian Village |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016212 | 2017-05-31 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  | 7575 | N | N |  |  | 5785 | 5284
09TPIT0037 | Blossom - New 138 kV Substation | Loop new 138 kV substation into the existing 138kV Harmony Hills to Skyline line | Delayed due to budget constraint | Blossom | Harmony Hills-Skyline | Planned | T-0178 | CPS | Ulrich Skerhut UKSkerhut@cpsenergy.com 210-353-2923 | S-0602 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5022, 5195, 5368 | Y | N |  | There are no transformers associated with this project | 950 | 949
16TPIT0010 | Bulverde - New 138kV Substation | Loop new 138kV substation into the existing Green Mountain to Stonegate transmission line |  | Green Mountain | Stonegate | Planned | T-0189 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0665 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5051, 5180, 5415 | Y | N |  | There are no transformers associated with this project | 972 | 971
16TPIT0009 | Five Points to Westside - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from Five Points to Westside to be upgraded to 326 MVA, minimum |  | Five Points | Westside | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0195 | 2017-06-01 |  | 138 | 0 | 3.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5150, 5490 | Y | N |  | There are no transformers associated with this project | 974 | 973
10TPIT0025 | Rinard Creek 138kV substation | Establish 138kV Rinard Ck substation with (2) 30MVA transformers and will cut into existing Ckt 987 (Lytton Springs to Slaughter Lane). |  | Rinard Creek substation | Rinard Creek Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P151 PLAN_117_P152 | 2017-06-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9262, 9075, 9267 | Y | N |  |  | 1031 | 1030
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2017-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9077, 9238 | Y | N |  | Will add the ptoject to the base case. | 1032 | 1031
11TPIT0084 | Hidden Lakes - New Substation | Build a new 138-12.47 kV substation to accommodate new subdivision growth along the FM 517 and FM 646 corridors in Dickinson, Texas |  | Leave blank | Leave blank | Planned |  | TNMP | Anthony Hudson Anthony.Hudson@tnmp.com. 281-581-4712 | STE02416 | 2017-06-01 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  | 38900, 38890, 42015 | Y | N |  |  | 1264 | 1261
16TPIT0005 | Farmersville West to Princeton South - new 138 kV line. | Build approximately 7.5 miles of 138 kV transmission line from Farmersville West Substation to Princeton South Substation. |  | Farmersville West | Princeton South | Planned | New projects added on rows 18 and 19. Please add TPIT numbers here after they have been assigned. | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE08016 | 2017-06-01 |  | 138 | 7.5 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 37291, 37295 | Y | N |  |  | 2064 | 2012
16TPIT0003 | Longneck to Princeton South - new 138 kV line | Build 3.5 miles of 138kV transmission line from Longneck Substation to Princeton South Substation. | Budget | Longneck | Princeton South | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07317 | 2017-06-01 |  | 138 | 3.5 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 37250, 37280, 37295 | N | N |  |  | 2065 | 2013
17TPIT0002 | Hunt Lane to Pinn Road - 138 kV Transmission Line Rebuild | Rebuild approximately eight circuit miles of 138 kV transmission from Hunt Lane to Pinn Road |  | Hunt Lane | Pinn Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0190 | 2017-06-01 |  | 138 | 0 | 8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5054, 5305, 5345, 5427 | Y | N |  | There are no transformers associated with this project | 2383 | 2307
4081 | CPSE_Skyline to Marion Reconfiguration | Reconfigure 4 - 345 kV transmission lines. Skyline to Marion and Skyline to Elm Creek will become double circuit lines from Skyline to Elm Creek. Hill Country to Marion and Hill Country to Elm Creek become double circuit lines from Hill Country to Marion. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0231 | 2017-06-01 |  | 345 | 0 | 0 | 0 |  | Bexar | Guadalupe | Tier 1 | 2014-06-27 |  | 2015-04-14 | 5133, 5211, 5371, 7044 | Y | N |  |  | 4431 | 4081
4139 | DME_Locust-Spencer |  |  | Pockrus | Spencer | Planned | N/A | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2017-06-01 |  | 69 | 0 | 1.91 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 902, 904, 914, 981 | Y | N | N/A |  | 4484 | 4139
5131 | CPSE_Brooks to Chavaneaux Transmission Rebuild | Rebuild approximately 11 circuit miles of 138 kV transmission along the 410 corridor between Brooks and Chavaneaux. Included in the rebuild are segments of Harlandale to Sommers and Merida to Sommers 138 kV transmission lines. |  | Brooks/Sommers | Chavaneaux/Merida/Harlandale | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0230 | 2017-06-01 |  | 138 | 0 | 11 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5045, 5190, 5310, 5085, 5395 | Y | N |  |  | 5609 | 5131
5217 | Rebuild Cotulla to Big Wells 69 kV line | 2015 NERC rebuild 69 kV line with 138 kV capable 795 ACSR |  | Cotulla | Big Wells | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-06-01 |  | 69 | 0 | 15.8 | 0 |  | La Salle | Dimmit | Tier 4 |  |  |  | 5868, 5876 | Y | N |  |  | 5707 | 5217
5168 | Airline to Holly: Build new 138 kV line | Build new Airline to Holly 138 kV line by installing a 1926 ACCC/TW circuit on the existing Barney Davis to Holly 138 kV line |  | Airline | Holly | Planned | 745 - 0928 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2919 | 2017-06-01 |  | 138 | 1.7 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8486, 8490 | Y | N |  |  | 5735 | 5168
5242 | Clodine to Barker Ckt.73 Thermal Uprate | Upgrade Ckt.73 Clodine to Barker to increase thermal ratings |  | Clodine | Barker | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-06-01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44052, 44140 | Y | N |  |  | 5742 | 5242
5229 | Bow Wood Substation Addition | Provide transmission service for a generator off T424 345-kV line between Red Creek and Brown Switch Substations. |  | Red Creek | Brown Switch | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015828 | 2017-06-20 |  | 345 | 0 | 0 | 0 |  | Tom Green | Brown | Tier 4 |  |  |  | 76006, 1444, 6444 | Y | N |  |  | 5727 | 5229
4997B | Deepwater Area Conversion to 138kV | Convert CHANEL sub to 138kV service. Loop from Ckt.70 Goodyear to Deepwater/Lydell |  | CHANEL | Goodyear/Deepwater/Lydell | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-06-29 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 40270, 40275, 40460, 40470, 40640, 40800 | Y | N |  |  | 5720 | 4997
14TPIT0061 | Briarcrest to Atkins Upgrade | Upgrade to 795 ACSR to alleviate overload during double contingency situations. Add OPGW. Add new poles/structures. |  | Atkins | Briarcrest | Planned |  | BRYN |  |  | 2017-06-30 |  | 138 | 0 | 3.4 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32864, 32877 | Y |  |  |  | 2052 | 2001
3479 | Cassava: Build 69 kV station | Construct new Cassava station along the Big Lake to Mathis Field 69 kV line (at Barnhart Phillips Tap location) |  | Cassava |  | Planned | 635 - 0804 | AEP TNC | Jason Bryant myturner@aep.com 918-599-2437 | 2590 | 2017-06-30 |  | 69 | 0 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6003, 60359, 6035, 6526, 6532 | Y | N |  |  | 3686 | 3479
4496 | AEP_4496_Las Pulgas | Loop STEC radial 138kV Raymondville #2 to East Raymondville line into Las Pulgas. |  | Las Pulgas |  | Planned | 615 - 3446 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 516 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Willacy |  | Tier 4 |  |  |  | 80309 | Y | N |  |  | 4890 | 4496
4538 | Add new 138kV line from Tall City to Glass Ranch |  |  | Tall City | Glass Ranch | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2017-06-30 |  | 138 | 10 | 0 | 0 |  | Midland | Martin | Tier 2 |  |  |  | 79507, 79558 | Y | N |  |  | 4940 | 4538
4573 | Briarcrest to Atkins Cable Upgrade | Upgrade Briarcrest to Atkins Cable to match OH capacity |  | 32864 | 32877 | Planned |  | BRYN |  |  | 2017-06-30 |  | 69 | 0.15 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32864, 32877 | Y |  |  |  | 4980 | 4573
4711 | CORTEZ 138kV Substation | Construct service to new 138kV CORTEZ customer-owned substation. Loop through Ckt.48 MARINE to Quintana | Delay in project schedule | CORTEZ | MARINE/Quintana | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 55 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  | 43440, 43155, 43435 | Y | N |  |  | 5130 | 4711
4960 | Adding Nat Dam to Sales 17 miles 138 kV line |  |  | Sales Ranch | Natural Dam | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2017-06-30 |  | 138 | 17 | 0 | 0 |  | Martin | Howard | Tier 4 | 2015-06-29 | 2015-07-29 |  | 79508, 79509 | Y | N |  |  | 5418 | 4960
4962 | Adding second 345/138 kV auto at Vealmoor station |  |  | Vealmoor 345 | Vealmoor 138 | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2017-06-30 |  | 345 | 0 | 0 | 708 |  | Borden | Borden | Tier 4 |  |  |  | 79600, 79640 | Y | N |  |  | 5420 | 4962
5201 | MaGill 138 kV Station: Install 28.8 MVAR Cap Bank | Install a 28.8 MVAR Cap Bank at MaGill 138 kV station |  | MaGill |  | Conceptual | 766-0951 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3574 | 2017-06-30 |  | 138 | 0 | 0 | 0 | 28.8,0 | Matagorda |  | Tier 4 |  |  |  | 8111 | Y | N |  |  | 5685 | 5201
5207 | Goliad 138 kV Station: Upgrade 69 kV Station | Add 138 kV design box bay with two breakers, expandable to three breakers and operated at 69 kV. |  | Goliad |  | Under Construction | 763-0948 | AEP TCC | Wilbur Roberts dnlyons@aep.com 918-599-2664 | 3571 | 2017-06-30 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | Y | N |  |  | 5691 | 5207
4997C | Deepwater Area Conversion to 138kV | Disconnect Deepwater 138kV substation from Ckt.70 service |  | Deepwater |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-06-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 40460, 40275, 41000 | Y | N |  |  | 5721 | 4997
5267 | MLSE Upgrade: T152 Sim Gideon to Winchester | Upgrade terminal equipment at Sim Gideon and Winchester for a static normal and emergency rating of 193 MVA. |  | Sim Gideon | Winchester | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016216 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Bastrop | Fayette | Tier 4 |  |  |  | 7306, 7310 | N | N |  |  | 5768 | 5267
5268 | MLSE Upgrade: T231 Austrop to Bastrop City | Upgrade terminal equipment at Austrop and Bastrop City for a static normal and emergency rating of 221 MVA. |  | Austrop | Bastrop City | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016216 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Travis | Bastrop | Tier 4 |  |  |  | 7322, 7329, 9328 | N | N |  |  | 5769 | 5268
5269 | MLSE Upgrade: T147 Gilleland Creek to McNeil | Upgrade terminal equipment at Gilleland Creek and McNeil for a static normal and emergency rating of 493 MVA. |  | Gilleland Creek | McNeil | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016216 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 7334, 7336 | N | N |  |  | 5770 | 5269
5279 | Chappell Hill Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Chappell Hill. |  | Chappel Hill |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016181 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Washington |  | Tier 4 |  |  |  | 7574 | N | N |  |  | 5780 | 5279
5280 | Georgetown South Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Georgetown South. |  | Georgetown South |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016215 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  | 7532 | N | N |  |  | 5781 | 5280
5282 | Shadow Glen Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Shadow Glen. |  | Shadow Glen |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016205 | 2017-06-30 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7323 | N | N |  |  | 5783 | 5282
10TPIT0148 | Las Pulgas Tap - Renamed from Willacy Tap Switch 138kV | Move normally open 138kV connection to the AEP Raymondville #2 bus and add breakers at Las Pulgas to serve E Raymondville and La Sara from Las Pulgas. |  | Las Pulgas |  | Planned | 12TPIT0103 | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2017-07-01 |  | 138 | 0 | 0 | 0 |  | Willacy | Willacy | Tier 4 |  |  |  | 5745, 5790, 8302, 80309 | Y | N |  |  | 2407 | 2330
3463 | Shady Bus Split | Reconfigure 69kV bus |  |  |  | Planned |  | BRYN | James Tanneberger 979-821-5763 |  | 2017-07-01 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 3668 | 3463
4495 | AEP_4495_Champlin | Expand existing breaker and half configuration to a six (6) breaker ring bus configuration |  | Champlin | Champlin | Planned | 694 - 0864 | AEP TCC | John Pulay dnlyons@aep.com 918-599-2698 | 3541 | 2017-07-01 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8476 | Y | N |  |  | 4889 | 4495
4537 | Add new line to connect Rocky Rd to Coates station (new) |  |  | Rocky Rd | Coates | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2017-07-01 |  | 138 | 7 | 0 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 79563, 79562 | Y | N |  |  | 4939 | 4537
4584 | Addition of 2nd circuit on Pemkiff - Midkiff line |  |  | Pemkiff | Midkiff | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2017-07-01 |  | 138 | 0.3 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  | 1210, 79555 | Y | N |  |  | 4992 | 4584
4969 | Pomelo: Build new four breaker 345 kV station | Interconnect Hidalgo Windfarm at Pomelo to connect Hidalgo to the Del Sol to North Edinburg 345 kV line |  | Del Sol | North Edinburg | Planned | 733 - 0915 | ETT | Michael Tallon dnlyons@aep.com 918-599-2698 | 3564 | 2017-07-01 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  | 8574, 88574, 8383, 80355 | Y |  |  |  | 5429 | 4969
5154 | Holford 138 kV new load substation and connections | Holford 138 kV new substation and its connections to Lookout and to Firewheel as well as some load growths at Holford |  | Lookout | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2017-07-01 |  | 138 | 0 | 2.1 | 0 |  |  |  | Tier 4 |  |  |  | 835, 821, 828 | Y |  |  |  | 5635 | 5154
08TPIT0033 | Gilleland to Techridge 138kV Circuit | Establish a new 138kV circuit from Gilleland to Techridge and maintain a normally close tie between AEN and LCRA's switchyard at Gilleland. |  | Gilleland Substation | Techridge Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_4276 PLAN_117_P207 | 2017-07-07 |  | 345 | 8 | 0 | 0 |  | Travis | Travis | Tier 2 |  | 2009-07-21 | 2009-07-21 | 9054, 7336, 9190 | Y | N |  |  | 1030 | 1029
10TPIT0062 | Marion Power Transformer Addition (Formerly Weil Road) | Expand the Marion substation 138-kV bus. Install a 138-26.18 kV 40 MVA power transformer at Marion 138 kV bus. |  | Marion |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2017-07-28 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7178 | Y | N |  |  | 2473 | 2384
11TPIT0107 | Steamboat: Reterminate 69 kV Happy Valley tap | Reterminate the Happy Valley tap into Steamboat |  | Happy Valley | Steamboat | Planned | 341 - 0515 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2092 | 2017-07-31 |  | 69 | 0 | 0.6 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6332, 6328, 6330, 6331, 60332 | Y | N |  |  | 299 | 302
3636 | Welsh HVDC: Upgrade Station Svc and Install New Filter | Welsh HVDC Tie: Phase 2 Station Upgrades | PM, PVID, Prj Desc, In-Service Changes | WELSH HVDC Tie |  | Planned | 625 - 0793 | AEP TCC | Tommy Vannoy dnlyons@aep.com 918-599-2698 |  | 2017-08-31 |  | 345 | 0 | 0 | 0 | 100100 | Titus |  | Tier 4 |  |  |  | 5925 | Y | Y |  |  | 3866 | 3636
5056 | Maxwell: Build new three breaker 138 kV station | Permanent Interconnect Val Verde Windfarm at Maxwell via Fermi Collector station |  | MAXWELL |  | Under Construction | 735-0917 | AEP TCC | Rick McCracken dnlyons@aep.com 918-599-2698 | 3565 | 2017-08-31 |  | 138 | 0 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  | 8998 | Y | N |  |  | 5531 | 5056
4574 | Briarcrest to Nall Cable Upgrade | Upgrade Briarcrest to Nall Cable to match OH section |  | 32877 | 32872 | Planned |  | BRYN |  |  | 2017-09-01 |  | 69 | 0 | 0.5 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32872, 32877 | Y |  |  |  | 4981 | 4574
5048 | Falfurius SVC: Upgrade | Replace SVC at Falfurius station +/- 60 MVAR capability |  | Falfurrias |  | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2017-09-01 |  | 138 | 0 | 0 | 0 |  | Brooks |  | Tier 4 |  |  |  | 88508, 8508 | Y | N |  |  | 5524 | 5048
5177 | Tesla: Add 345 kV reactor | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley | NEW | Tesla |  | Planned | 754 - 0937 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2624 | 2017-09-02 |  | 345 | 0 | 0 | 0 | -100,0 | Wilbarger |  | Tier 4 |  |  |  | 60501 | Y | N |  |  | 5661 | 5177
4490 | LaPalma: Add 2nd 345/138 kV autotransformer | Add 345/138 kV autotransformer capacity at LaPalma |  | LaPalma |  | Under Construction | 710 - 0880 | AEP TCC | Teresa Trotman gareed@aep.com 918-599-2664 | 2904 | 2017-09-30 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 4 |  |  |  | 8356, 8317, 8314 | Y | N |  |  | 4892 | 4490
4504 | BRYN_4504_Rayburn_Nall_Upgrade | Reconductor Rayburn to Nall with 1033 |  | 32861 | 32872 | Planned |  | BRYN |  |  | 2017-09-30 |  | 69 | 0 | 1.06 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32861, 32872 | Y |  |  |  | 4901 | 4504
4577 | BRYN_4577_Dansby_Rebuild | Convert Dansby 69kV bus to Breaker and a Half configuration |  |  |  | Planned |  | BRYN |  |  | 2017-09-30 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  | 32875, 32897 | Y |  |  |  | 4984 | 4577
5045 | BRYN_5045_Nall_Relocation | Relocate Nall Lane Substation Across the Street |  |  |  | Planned |  | BRYN |  |  | 2017-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  |  | 5519 | 5045
3683 | Abilene South to Sawgrass: Rebuild 69 kV line | Rebuild Abilene South to Sawgrass with 795 ACSS | Title, Description, Location, Contact, Schedule, and Cost Update | Abilene South | Sawgrass | Planned | 651 - 0820 | AEP TNC | Mike Tallon myturner@aep.com 918-599-2437 | 1815 | 2017-09-30 |  | 69 |  | 2.15 |  |  | Taylor | Taylor | Tier 4 |  |  |  | 6284, 60394, 6258, 6283, 6285 | Y | N |  |  | 5629 | 3683
5188 | Quaint Station: Build 69 kV station | Construct new 69 kV ring bus on the Abilene Northwest to Anson 69 kV Line | NEW | Quaint |  | Planned | 753 - 0936 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2623 | 2017-09-30 |  | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  | 6237, 6249, 6388, 6224, 6236, 6238, 6243, 60335 | Y | N |  |  | 5672 | 5188
5193 | Ft. Griffin: Build 69 kV station and add capacitor bank | Construct new 69 kV ring bus near Albany and add one 14.4 Mvar capacitor bank | NEW | Ft. Griffin |  | Planned | 756 - 0940 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2631 | 2017-09-30 |  | 69 | 0 | 0 | 0 | 0,14.4 | Shackelford |  | Tier 4 |  |  |  | 6213, 60398, 6206, 6207, 6214 | Y | N |  |  | 5677 | 5193
5081 | Bronco: Build 69 kV station | Interconnect Solaire Holman solar farm at Bronco to connect Solaire Holman to the Alpine to Fort Stockton Plant 69 kV line | NEW | Bronco |  | Planned | 740 - 0923 | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | 2621 | 2017-10-22 |  | 69 |  |  |  |  | Brewster |  | Tier 4 |  |  |  | 6674 | Y | N |  |  | 5561 | 5081
4456 | Gilleland Creek Autotransformer | Install a new 345/138 kV 672 MVA auto transformer at Gilleland Creek substation. |  | Gilleland Creek |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015112 | 2017-10-31 |  | 345 | 0 | 0 | 672 |  | Travis |  | Tier 4 |  |  |  | 77341, 7340, 7336 | Y | N |  |  | 4841 | 4456
5195 | Rio Pecos: Build 138 kV terminal | Interconnect Pecos solar farm at Rio Pecos | NEW | Rio Pecos |  | Planned | 758 - 0942 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2633 | 2017-10-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  | 6601 | Y | N |  |  | 5679 | 5195
5278 | Arco Tap Circuit Breaker Addition | Add circuit breakers in a ring bus arrangement at Arco Tap. |  | Arco Tap |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016176 | 2017-10-31 |  | 138 | 0 | 0 | 0 |  | Crane |  | Tier 4 |  |  |  | 1199, 71199, 1201, 71230, 76615 | N | N |  |  | 5779 | 5278
4459 | Goldthwaite to Lampasas Transmission Line Upgrade | Convert the 18.2 mile Goldthwaite (7073) - San Saba (7078) 69-kV to 795 ACSR Drake 138-kV (223 MVA) and Convert the 33.3 mile San Saba (7078) - Lometa (7080) - Lampasas (7082) 69-kV to 795 ACSR Drake 138-kV (223 MVA). |  | Goldthwaite | Lampasas | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014204 | 2017-11-01 |  | 138 | 0 | 51.5 | 0 |  | Mills | Lampasas | Tier 4 | 2014-11-11 | 2015-06-25 |  | 7064, 7070 | Y | N |  |  | 4844 | 4459
4751 | Lufkin Sw Sta - Crockett 138 kV Line | Rebuild existing line | Construction schedule change | Lufkin | Crockett | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6004 | 2017-11-15 |  | 138 | 0 | 42.9 | 0 |  | Angelina | Houston | Tier 3 | 2015-06-15 | 2015-08-15 |  | 3118, 3349, 3351, 3354 | Y | N |  |  | 5171 | 4751
4931 | Yukon Switching Station | Construct new switching station |  | Yukon |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8346 | 2017-11-15 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 3 | 2015-06-15 | 2015-07-15 |  | 1250, 1019, 11140 | Y | N |  |  | 5389 | 4931
4932 | Wink - Yukon 138 kV Line | Construct new line |  | Wink | Yukon | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8346 | 2017-11-15 |  | 138 | 36 | 9 | 0 |  | Ector | Winkler | Tier 3 |  | 2015-07-15 |  | 1252, 1074, 1075, 1250, 1251, 1254, 1253, 1258 | Y | N |  |  | 5390 | 4932
17TPIT0005 | St. Jo Autos | Replace 40 MVA autos with 60 MVA autos |  | St. Jo | St. Jo | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12005 | 2017-12-01 |  | 138 | 0 | 0 | 60 |  | Cooke |  | Tier 4 |  |  |  | 750, 746 | Y | N |  |  | 2316 | 2243
4546 | Upgrade 138kV Vealmoor - Salt Mine line |  |  | Vealmoor | Salt Mine | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2017-12-01 |  | 138 | 0 | 54.5 | 0 |  | Borden | Mitchell | Tier 4 |  |  |  | 79559, 79603, 79604, 79600, 79605 | Y | N |  |  | 4948 | 4546
5178 | Edith Clarke: Add 345 kV reactor | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley | NEW | Edith Clarke |  | Planned | 754 - 0937 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2625 | 2017-12-02 |  | 345 | 0 | 0 | 0 | -100,0 | Foard |  | Tier 4 |  |  |  | 60500 | Y | N |  |  | 5662 | 5178
4755 | Barstow - Culberson 138 kV circuit | Add second circuit to existing line |  | Yucca Drive | Culberson | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8342 | 2017-12-14 |  | 138 | 45 | 0 | 0 |  | Ward | Culberson | Tier 4 |  |  |  | 1086, 1097 | Y | N |  |  | 5175 | 4755
5263 | Barstow NW - Culberson 138 kV line |  |  | Barstow NW | Culberson | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8070 | 2017-12-14 |  | 138 | 45 | 0 | 0 |  | Ward | Culberson | Tier 4 | 2013-02-15 | 2013-02-15 |  | 1086, 1097 | Y | N |  |  | 5763 | 5263
13TPIT0064 | Rocky Mound Switching Station series capacitors | Install series capacitors for Willow Creek - Clear Crossing - Dermott Switch (Central B) 345 kV line (Oncor Electric Delivery part) | Construction schedule change | Rocky Mound Switching Station |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | C079-E | 2017-12-15 |  | 345 | 0 | 0 | 0 |  | Haskell |  | CREZ |  |  |  | 17012, 17013, 17014, 17015, 1421, 60515 | Y | N |  | Project schedule details can be found in PUCT CREZ Oversight Monitor Report. | 2768 | 2644
11TPIT0050 | Roanoke Switch - Elizabeth Creek 138 kV line | Construct new double-circuit line. | Construction schedule change | Roanoke Switch | Elizabeth Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M509-E | 2017-12-15 |  | 138 | 3.8 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1867, 640, 1852, 1854, 1866 | Y | N |  |  | 3058 | 2884
14TPIT0057 | Cedar Hill Switch - Liggett 138 kV line | Upgrade Cedar Hill Switch - Dalworth existing line section | Construction schedule change | Cedar HIll Switch | Dalworth | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5041-E | 2017-12-15 |  | 138 | 0 | 8.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 1912, 2265, 2274, 2422 | Y | N |  |  | 3101 | 2926
4241 | Texaco Mabee Tap - Texaco Mabee 138 kV Line | Rebuild existing line as a double-circuit line | Construction schedule change | Texaco Mabee Tap | Texaco Mabee | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8221 | 2017-12-15 |  | 138 | 11.4 | 11.4 | 0 |  | Midland | Andrews | Tier 4 |  |  |  | 1171, 1175, 1177, 1179, 11175, 11179, 1174, 1184, 11177 | Y | N |  |  | 4614 | 4241
4251 | Everman - Wedgwood 138 kV Line | Upgrade existing double-circuit line | Construction schedule changed | Everman | Wedgwood | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5210 | 2017-12-15 |  | 138 | 0 | 18 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1883, 1967, 2184, 2185, 2190, 2191, 2192, 2193, 2194, 2195 | Y | N |  |  | 4622 | 4251
17TPIT0019 | Forney - Royse 138 kV Line | Upgrade existing line | Construction schedule change | Forney | Royse | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4111-E | 2017-12-15 |  | 138 | 0 | 18.32 | 0 |  | Kaufman | Rockwall | Tier 4 |  |  |  | 2438, 2471, 2710, 2711, 2712 | Y | N |  |  | 4664 | 3086
16TPIT0050 | Northaven - Renner 138 kV Line | Upgrade existing line | Construction schedule change | Northaven | Renner | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4108-E | 2017-12-15 |  | 138 | 0 | 8.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2357, 2597, 2614, 2616, 2659 | Y | N |  |  | 4670 | 3065
16TPIT0061 | Norwood - Record Crossing - East Levee 138 kV Line | Upgrade existing line | Construction schedule change | Norwood | East Levee | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4107-E | 2017-12-15 |  | 138 | 0 | 7.6 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  | 2405, 2811, 2813, 2815, 2819, 2482, 2814, 2823 | Y | N |  |  | 4671 | 3067
4756 | Wink - Culberson 138 kV circuit | Add second circuit to existing line |  | Wink | Culberson | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8337 | 2017-12-15 |  | 138 | 62 | 0 | 0 |  | Winkler | Culberson | Tier 3 |  |  |  | 1074, 1077, 1081, 1083, 1092, 1093, 1095, 1084, 1094, 1096, 1097 | Y | N |  |  | 5176 | 4756
4758 | Sand Lake 138 kV Switching Station | Construct new switching station |  | Sand Lake |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8340 | 2017-12-15 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 1011, 1009, 1086, 1097 | Y | N |  |  | 5178 | 4758
4837 | Everman - Cleburne Sw. Sta. 138 kV Line | Upgrade existing Everman - Burleson line section | Construction schedule change | Everman | Burleson | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5204 | 2017-12-15 |  | 138 | 0 | 16.6 | 0 |  | Tarrant | Johnson | Tier 4 |  |  |  | 1883, 2208, 2209 | Y | N |  |  | 5264 | 4837
5031 | Install 80 MVar Cap Bank at Barilla Draw Tap |  |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2017-12-15 |  | 138 | 0 | 0 | 0 | 0,80 |  |  | Tier 4 |  |  |  | 38065 | Y |  |  |  | 5501 | 5031
5231 | Schneeman Draw Substation Addition | Provide transmission service for a generator off T21421 345-kV STEC line between Big Hill and Bakersfield Substations. |  | Big Hill | Bakersfield | Planned |  | LCRATSC/STEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015884 | 2017-12-29 |  | 345 | 0 | 0 | 0 |  | Schleicher | Pecos | Tier 4 |  |  |  | 76005, 76002, 76003 | Y | N |  |  | 5729 | 5231
3480 | Cassava to Yucca: Rebuild 69 kV line | Rebuild 69 kV line as 138 kV from Cassava (Barnhart Phillips Tap) to Yucca with 795 ACSS and add 138/69 kV autotransformer capacity at Cassava |  | Cassava | Yucca | Planned | 635 - 0804 | AEP TNC | Jason Bryant myturner@aep.com 918-599-2437 | 2591 | 2017-12-31 |  | 138 | 12.3 | 0 | 90 |  | Taylor | Taylor | Tier 4 |  |  |  | 6034, 6035, 6531, 60360, 6036, 60359 | Y | N |  |  | 3687 | 3480
3774 | Olinger-Ben Davis Line Upgrade | Olinger to Ben Davis 138 kV line upgrade to 436 MVA ratings |  | Olinger | Ben Davis | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2017-12-31 |  | 138 | 0 | 17.25 | 0 |  | Collin | Dallas | Tier 4 |  |  |  | 818, 968 | Y | N |  |  | 4019 | 3774
3775 | Firewheel-WylieSW Line Upgrade | Firewheel to Wylie Switch 138 kV line upgrade to 436 MVA ratings |  | Firewheel | WylieSW | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2017-12-31 |  | 138 | 0 | 17.77 | 0 |  | Dallas | Collin | Tier 4 |  |  |  | 821, 833 | Y | N |  |  | 4020 | 3775
4231 | Creosote: Build 138 kV station | Construct 138 kV, six breaker ring bus on the existing 138 kV line from Barrilla Junction to Permian Basin |  | Creosote |  | Planned | 689 - 0859 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2606 | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 6657, 60377, 6656, 6673, 38375 | Y | N |  |  | 4602 | 4231
4453 | Henne to McCarty Lane Transmission Line Upgrade | Upgrade the 6.6 mile Henne (7172) - McCarty Lane (7182) 138-kV transmission line to single 959 ACSS Suwannee, 380 MVA. |  | Henne | McCarty Lane | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015117 | 2017-12-31 |  | 138 | 0 | 6.6 | 0 |  | Comal | Hays | Tier 4 |  |  |  | 7172, 7182 | Y | N |  |  | 4838 | 4453
4531 | Solstice to Clovis: Build 138 kV line | Construct new 138 kV line from Solstice to Clovis |  | Solstice | Clovis | Planned | 705 - 0875 | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | 2811 | 2017-12-31 |  | 138 | 4.5 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  | 60383, 60384, 6630, 6655, 60385 | Y | N |  |  | 4931 | 4531
4871 | Webster Breaker Addition | Install breaker at Webster 138kV substation to connect ring buses | Delay in project schedule | Webster |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2017-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 43505, 42651, 42970, 43082, 43500, 43507 | Y | N |  |  | 5306 | 4871
4875 | Red Gate: Build new 138 kV line | Rebuild a portion of the Falfurrias to North Edinburg 138 kV line with 959 ACSS/TW as double circuit to connect the Red Gate Power Plant |  | Falfurrias | North Edinburg | Planned | 724 - 0906 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3558 | 2017-12-31 |  | 138 | 7.5 | 7.5 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8380, 8896, 88380, 161031 | Y | Y |  |  | 5311 | 4875
5150 | Southwest Vernon: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Southwest Vernon |  | Southwest Vernon |  | Planned | 741 - 0924 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2913 | 2017-12-31 |  | 138 | 0 | 0 | 130 |  | Wilbarger |  | Tier 4 |  |  |  | 6064, 6066 | Y | N |  |  | 5630 | 5150
3848 | Bison to Powell Field: Rebuild 69 kV line | Rebuild Bison to Powell Field with 795 ACSS | Project Title, Project Description, Terminal, Contact, Schedule, Cost, Circuit Miles, and County Update | Bison | Powell Field | Planned | 670 - 0839 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2806 | 2017-12-31 |  | 69 | 0 | 12.32 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  | 6540, 6543, 6544, 6554, 60395, 60396, 6534, 6539, 6545, 6589 | Y | N |  |  | 5638 | 3848
5169 | Harlingen SS to Raymondville #2: Rebuild 69 kV line | Rebuild Harlingen SS to Raymondville #2 with 959.6 ACSS/TW & OPGW |  | Harlingen SS | Raymondville #2 | Planned | 749 - 0932 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2923 | 2017-12-31 |  | 138 | 0 | 22.8 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  | 8300, 8325, 8700 | Y | N |  |  | 5652 | 5169
5171 | Bates to Wormser: Raise structures increase MOT | Increase the MOT rating of the Bates to Wormser 138kV line by raising xx structures |  | Bates | Wormser | Planned | 750 - 0933 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2924 | 2017-12-31 |  | 138 | 0 | 126.48 | 0 |  | Hidalgo | Webb | Tier 4 |  |  |  | 8299, 8392, 8394, 8399, 8795, 8957, 8985, 80106, 80230, 8295 | Y | N |  |  | 5654 | 5171
5173 | Airline to Westside: Reconductor 138 kV line | Reconductor Airline to Westside with 1966 ACCC/TW |  | Airline | Westside | Planned | 746 - 0929 | AEP TCC | Dan Lyons dnlyons@aep.com 918-599-2698 | 2920 | 2017-12-31 |  | 138 | 0 | 6.1 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8485, 8490, 8882 | Y | N |  |  | 5657 | 5173
5197 | Abilene Northwest to Elm Creek: Rebuild 69 kV line | Rebuild Abilene Northwest to Elm Creek 69 kV line with 795 ACSS | NEW | Abilene Northwest | Elm Creek | Planned | 759 - 0943 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2634 | 2017-12-31 |  | 69 | 0 | 3.07 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6228, 6255 | Y | N |  |  | 5681 | 5197
5235 | Bakersfield Reactor Bank Addition(s) | Add two (2) 50 MVAR reactor banks at Bakersfield Substation |  | Bakersfield |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016061 | 2017-12-31 |  | 345 | 0 | 0 | 0 | 0,-100 | Pecos |  | Tier 4 |  |  |  | 76002 | Y | N |  |  | 5733 | 5235
5270 | Twin Buttes Autotransformer Addition | Replace the existing Twin Buttes AT1 autotransformer with a new 345/138-kV 672 MVA autotransformer. Remove the existing 36 MVAR Twin Buttes AT1 tertiary reactor. Install a new 345-kV 50 MVAR reactor at Divide Substation |  | Twin Buttes |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016213 | 2017-12-31 |  | 345 | 0 | 0 | 672 | 50,0 | Tom Green |  | Tier 4 |  |  |  | 76009, 76011, 77281, 76090 | N | N |  |  | 5771 | 5270
4883 | MCCOY 69 KV substation | Add a new load serving substation between Pleasanton and Tordillo |  | MCCOY |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-01-31 |  | 69 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5721, 5714, 5715 | Y | N |  |  | 5319 | 4883
5179 | Clear Crossing: Add 345 kV reactor | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley | NEW | Clear Crossing |  | Planned | 754 - 0937 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2626 | 2018-03-02 |  | 345 | 0 | 0 | 0 | -100,0 | Haskell |  | Tier 4 |  |  |  | 60515 | Y | N |  |  | 5663 | 5179
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-04-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  | 5601, 5600, 5602 | Y | N |  |  | 1554 | 1538
4485 | Add new 345kV Limestone - Gibbons Crk double circuit line |  |  | Limestone | Gibbons Creek | Planned |  | CTT | Tim cook Tcook@lspower.com 636-534-3250 |  | 2018-05-01 |  | 345 | 70 | 0 | 0 |  | Limestone | Grimes | Tier 1 | 2013-07-29 | 2014-02-20 | 2014-04-08 | 967, 46020 | Y | Y |  |  | 4879 | 4485
10TPIT0017 | Renner - Allen Switch/Plano Tennyson 138kV Line | Upgrade existing double-circuit 138 kV line | Construction schedule change | Allen Switch | Renner | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3047-E | 2018-05-15 |  | 138 | 0 | 15.2 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 2352, 2353, 2509, 2510, 2521, 2524, 2523, 2525, 2526 | Y | N |  |  | 1059 | 1058
12TPIT0080 | Forney Sw. Sta. Second 600 MVA, 345/138 kV Autotransformer | Add second 345/138 autotransformer | Construction schedule change | Forney Sw. Sta. |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4037 | 2018-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 4 | 2008-06-01 | 2008-07-01 |  | 2437, 2438 | Y | N | 2007-R2 |  | 2594 | 2489
14TPIT0055 | Seagoville - Wilmer 138 kV line | Upgrade existing line |  | Seagoville | Wilmer | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4081-E | 2018-05-15 |  | 138 | 0 | 10.9 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2434, 3076, 3077, 3079, 3083 | Y | N |  |  | 2599 | 2494
13TPIT0059 | Cedar Crest - Industrial 138 kV line | Upgrade existing line | Construction schedule change | Cedar Crest | Industrial | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4072-E | 2018-05-15 |  | 138 | 0 | 3.2 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2494, 2976, 2981 | Y | N | 2009-R23 |  | 2600 | 2495
07TPIT0236 | N. Terrell Tap - Rose Hill 138 kV line | Rebuild existing line |  | N. Terrell Tap | Rose Hill | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3059-E | 2018-05-15 |  | 138 | 0 | 8.7 | 0 |  | Kaufman | Kaufman | Tier 4 |  |  |  | 2714, 2715, 2719, 2717, 2723 | Y | N |  |  | 3100 | 2925
16TPIT0052 | Cedar Crest - South Oak Cliff 138 kV line | Upgrade existing line |  | Cedar Crest | South Oak Cliff | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4089-E | 2018-05-15 |  | 138 | 0 | 1.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2493, 2494, 3023, 3024 | Y | N |  |  | 3235 | 3066
16TPIT0057 | Hutto Switching Station - Taylor 138 kV Line | Upgrade existing line |  | Hutto Switching Station | Taylor | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R775 | 2018-05-15 |  | 138 | 0 | 15.6 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 3658, 3666, 3673 | Y | N |  |  | 3240 | 3071
17TPIT0021 | Liggett - Norwood 138 kV Line | Upgrade existing double-circuit line |  | Liggett | Norwood | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4109-E | 2018-05-15 |  | 138 | 0 | 12.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 1922, 1924, 2053, 2054, 2055, 2408 | Y | N |  |  | 3257 | 3088
17TPIT0023 | Northwest Carrollton - Norwood 138 kV Line | Upgrade existing double-circuit Northwest Carrollton - Carrollton line section |  | Northwest Carrollton | Carrollton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4110-E | 2018-05-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  | 2362, 2363, 2535, 2536, 2537, 2538, 2539 | Y | N |  |  | 3258 | 3089
19TPIT0001 | Sargent Road - Cedar Crest 138 kV Line | Upgrade existing Sargent Road - Saint Augustine Tap line section |  | Sargent Road | Saint Augustine Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4090-E | 2018-05-15 |  | 138 | 0 | 3.9 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2941, 2951 | Y | N |  |  | 3264 | 3095
16TPIT0058 | Lufkin Switch - Lufkin 138 kV line | Upgrade existing line |  | Lufkin Switch | Lufkin | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6038-E | 2018-05-15 |  | 138 | 0 | 2.8 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  | 3118, 3340 | Y | N |  |  | 3281 | 3112
17TPIT0022 | Nacogdoches - Nacogdoches Southeast 138 kV Line | Upgrade existing Nacogdoches - Nacogdoches Southeast Line |  | Nacogdoches | Nacogdoches North | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6037-E | 2018-05-15 |  | 138 | 0 | 3.9 | 0 |  | Nacogdoches | Nacogdoches | Tier 4 |  |  |  | 3303, 3310 | Y | N |  |  | 3323 | 3152
16TPIT0060 | Midland East - Spraberry 138 kV Line | Upgrade existing line |  | Midland East | Spraberry | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8147-E | 2018-05-15 |  | 138 | 0 | 18.8 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1132, 1133, 1329 | Y | N |  |  | 3343 | 3172
17TPIT0024 | Payne - Anna Switch 138 kV Line | Upgrade existing line |  | Payne | Anna Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R938-E | 2018-05-15 |  | 138 | 0 | 20.8 | 0 |  | Grayson | Collin | Tier 3 |  |  |  | 1713, 1748, 1754, 1758, 2374 | Y | N |  |  | 3386 | 3213
08TPIT0104 | Elgin Switching Station - Elgin 69 kV line conversion to 138 | Rebuild existing 69 kV line and convert to 138 kV operation |  | Elgin Switching Station | Elgin | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R471-E | 2018-05-15 |  | 138 | 0 | 5.9 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 3655, 3650, 3651, 3674, 13674 | Y | N |  |  | 3478 | 1335
16TPIT0048 | Trinidad - Athens 69 kV Line | Upgrade existing line |  | Trinidad SES | Athens | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6033-E | 2018-05-15 |  | 69 | 0 | 17.5 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  | 3128, 3239 | Y | N |  |  | 3590 | 3392
4207 | Bowman - Lake Wichita 138 kV Line | Upgrade existing line |  | Bowman | Lake Wichita | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R952 | 2018-05-15 |  | 138 | 0 | 5.6 | 0 |  | Archer | Wichita | Tier 4 |  |  |  | 1424, 1446 | Y | N |  |  | 4564 | 4207
4252 | Eagle Mountain - Saginaw 138 kV Line | Upgrade existing double-circuit line | Scope and construction schedule change | Eagle Mountain | Saginaw | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5211 | 2018-05-15 |  | 138 | 0 | 27.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1860, 1864, 1957, 2065, 2066, 2067, 2070, 11860 | Y | N |  |  | 4623 | 4252
4254 | DeSoto Switching Station - Sterrett 138 kV Line | Upgrade existing line |  | De Soto | Sterrett | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4122 | 2018-05-15 |  | 138 | 0 | 2.7 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  | 2317, 2424, 2426 | Y | N |  |  | 4625 | 4254
4255 | Odessa Basin 69 kV Switching Station | Upgrade existing switching station |  | Odessa Basin |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8247 | 2018-05-15 |  | 69 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  | 1123, 1254, 1258 | Y | N |  |  | 4626 | 4255
4257 | Stryker Creek - Gresham Road 138 kV line | Upgrade existing line |  | Stryker Creek | Gresham Road | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6054 | 2018-05-15 |  | 138 | 0 | 9.1 | 0 |  | Cherokee | Rusk | Tier 4 |  |  |  | 3110, 3301 | Y | N |  |  | 4628 | 4257
4258 | Centerville Switch - Lake Hubbard 138 kV Line | Upgrade existing double-circuit 138 kV line | Construction schedule change | Centerville Sw | Lake Hubbard | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4126 | 2018-05-15 |  | 138 | 0 | 13.5 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2401, 2402, 2439, 2450 | Y | N |  |  | 4629 | 4258
4259 | Wichita Falls second 138/69 kV autotransformer | Install 138/69 kV autotransformer |  | Wichita Falls |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R970 | 2018-05-15 |  | 138 | 0 | 0 | 150 |  | Wichita |  | Tier 4 |  |  |  | 1448, 1449 | Y | N |  |  | 4630 | 4259
4261 | Centerville Switch - Centerville - Lake Hubbard 138 kV Line | Upgrade existing double-circuit 138 kV line | Construction schedule change | Centerville Switch | Lake Hubbard | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4127 | 2018-05-15 |  | 138 | 0 | 26 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2401, 2402, 2439, 2450, 2917, 2918 | Y | N |  |  | 4632 | 4261
14TPIT0010 | Handley - Pantego - Sherry 138 kV line | Upgrade existing line | Construction schedule change | Handley | Sherry | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5155-E | 2018-05-15 |  | 138 | 0 | 8.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1919, 1950, 2245, 2247, 2250, 2251 | Y | N |  |  | 4638 | 2582
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line |  | Handley | Hemphill | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5214 | 2018-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 4643 | 4270
4274 | Navarro - Corsicana 69 kV Line | Upgrade existing line | Construction schedule change | Navarro | Corsicana | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R793 | 2018-05-15 |  | 69 | 0 | 12.5 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  | 3468, 3475, 3479, 3480, 13468 | Y | N |  |  | 4648 | 4274
4275 | Hutto Switching Station 138 kV capacitors | Install shunt capacitors |  | Hutto Switching Station |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R798 | 2018-05-15 |  | 138 | 0 | 0 | 0 | 0,18.4 | Williamson |  | Tier 4 |  |  |  | 3666 | Y | N |  |  | 4649 | 4275
17TPIT0028 | Temple Switch - Belton 138 kV Line | Upgrade existing line |  | Temple Switch | Belton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R784 | 2018-05-15 |  | 138 | 0 | 12.9 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3415, 3602, 3610, 3611, 3612 | Y | N |  |  | 4659 | 3182
4303 | Lake Creek - Tradinghouse 345 kV Line | Upgrade existing east line |  | Tradinghouse | Lake Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1717 | 2018-05-15 |  | 345 | 0 | 9 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  | 3402, 3405 | Y | N |  |  | 4684 | 4303
4304 | Tradinghouse - Sam Switch 345 kV Line | Upgrade existing double-circuit line | Construction schedule change | Tradinighouse | Sam Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1706 | 2018-05-15 |  | 345 | 0 | 45.4 | 0 |  | McLennan | Hill | Tier 4 |  |  |  | 3405, 13405, 68090 | Y | N |  |  | 4685 | 4304
4330 | Sargent Road - Industrial BLVD 138 kV Line | Upgrade existing line |  | Sargent Road | Industrial BLVD | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4128 | 2018-05-15 |  | 138 | 0 | 5.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2940, 2947, 2972, 2973, 2974, 2975 | Y | N |  |  | 4707 | 4330
4354 | Collin 138 kV series reactor | Install 138 kV series reactor on second 345/138 kV autotransformer |  | Collin |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R960 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 29556, 29555, 2372, 29578 | Y | N |  |  | 4727 | 4354
4355 | Cedar Hill Switch - Sorcey Rd - Cedar Hill Sub 138 kV Line | Upgrade existing line | Construction schedule change | Cedar Hill Switch | Cedar Hill Substation | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4131 | 2018-05-15 |  | 138 | 0 | 7.5 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2422, 3049, 3051, 3052, 3053, 3050, 3055 | Y | N |  |  | 4729 | 4355
4521 | Midkiff Switching Station | Upgrade switching station |  | Midkiff |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8276 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  | 1210 | Y | N |  |  | 4918 | 4521
4549 | Yucca Drive - Barilla Junction (AEP) 138 kV Line | Rebuild Oncor's section of the existing line |  | Yucca Drive | Barilla Junction (AEP) | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8272 | 2018-05-15 |  | 138 | 0 | 15 | 0 |  | Ward | Pecos | Tier 3 | 2015-12-15 |  |  | 1009, 60397 | Y | N |  |  | 4951 | 4549
4550 | China Grove - Snyder 69 kV Line | Convert existing line to 138 kV operation |  | China Grove | Snyder | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8311 | 2018-05-15 |  | 138 | 0 | 13.1 | 0 |  | Mitchell | Scurry | Tier 4 |  |  |  | 1376, 1305, 1306, 1318, 1319 | Y | N |  |  | 4952 | 4550
4551 | China Grove - Amoco 69 kV Line | Upgrade existing line and convert to 138 kV operation |  | China Grove | Amoco | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8310 | 2018-05-15 |  | 138 | 0 | 2.9 | 0 |  | Mitchell | Scurry | Tier 4 |  |  |  | 1373, 1374, 1375, 1318, 1319, 1376 | Y | N |  |  | 4953 | 4551
4552 | Yucca Drive - Barnsley/Royalty 69 kV Line conversion | Rebuild existing 69 kV line and convert to 138 kV operation |  | Permian Basin | Barnsley | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8305 | 2018-05-15 |  | 138 | 0 | 50 | 0 |  | Ward | Crane | Tier 3 |  |  |  | 1202, 1203, 1009, 1015, 1238 | Y | N |  |  | 4954 | 4552
4553 | Yucca Dr - Northern Natural 69 kV Line | Convert existing line to 138 kV operation | Construction schedule change | Permian Basin | Northern Natural | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8295 | 2018-05-15 |  | 138 | 0 | 50 | 0 |  | Ward | Pecos | Tier 3 |  |  |  | 1238, 1239, 1240, 1241, 1242, 1009, 1015 | Y | N |  |  | 4955 | 4553
4554 | Snyder - Ennis Creek - Cogdell 69 kV Line | Convert existing line to 138 kV operation |  | Snyder | Ennis Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8309 | 2018-05-15 |  | 138 | 0 | 19 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  | 1400, 1401, 1402, 1412, 1305, 1306, 1411, 11306 | Y | N |  |  | 4956 | 4554
4559 | Midkiff - Garden City - McDonald Road 138 kV Line | Rebuild existing Midkiff - Garden City 69 kV Line as a double-circuit line with a 69 kV circuit and a 138 kV circuit and add 138 kV circuit to McDonald Road - Garden City line section |  | Midkiff | McDonald Road | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8290 | 2018-05-15 |  | 138 | 50 | 26 | 0 |  | Upton | Glasscock | Tier 3 |  |  |  | 1210, 1218, 1333, 1352 | Y | N |  |  | 4965 | 4559
4732 | Big Spring West - Stanton East 138 kV Line | Upgrade existing line |  | Big Spring West | Stanton East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8303 | 2018-05-15 |  | 138 | 0 | 17.6 | 0 |  | Howard | Martin | Tier 4 |  |  |  | 1324, 1326 | Y | N |  |  | 5151 | 4732
4733 | Midland County Northwest Sw. Sta. - Midland East 138 kV Line | Upgrade existing double-circuit line |  | Midland County Northwest Sw. Sta. | Midland East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8304 | 2018-05-15 |  | 138 | 0 | 32.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1023, 1171, 1178, 1179, 1182, 1183, 1184 | Y | N |  |  | 5152 | 4733
4741 | Argyle Sw. Sta. - Highlands (TNMP) 138 kV Line | Upgrade existing line | Construction schedule change | Argyle Sw. Sta. | Highlands (TNMP) | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3201 | 2018-05-15 |  | 138 | 0 | 7.5 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 1974, 1984 | Y | N |  |  | 5160 | 4741
4757 | Riverton 138 kV Switching Station | Construct new switching station |  | Mason |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8338 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  | 1094 | Y | N |  |  | 5177 | 4757
4759 | Riverton - Sand Lake 138 kV Line | Construct new double-circuit line |  | Riverton | Sand Lake | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8341 | 2018-05-15 |  | 138 | 25 | 0 | 0 |  | Reeves | Reeves | Tier 2 |  |  |  | 1011, 1094 | Y | N |  |  | 5179 | 4759
09TPIT0116 | Gatesville Tap - Gatesville TDC 69 kV line | Upgrade existing 69 kV line |  | Gatesville Tap | Gatesville TDC | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R497-WA | 2018-05-15 |  | 69 | 0 | 4.4 | 0 |  | McLennan | Coryell | Tier 4 |  |  |  | 3583, 3587 | Y | N |  |  | 5183 | 466
4781 | Riverton dynamic reactive device | Install a dynamic reactive device in an existing switching station |  | Mason |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8339 | 2018-05-15 |  | 138 | 0 | 0 | 0 | -60,60 | Reeves |  | Tier 3 |  |  |  | 11083, 1084, 1094 | Y | N |  |  | 5208 | 4781
4787 | Venus - Sardis - Sterrett 138 kV Line | Upgrade existing line | Construction schedule change | Venus | Sterrett | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4203 | 2018-05-15 |  | 138 | 0 | 14.4 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  | 203, 1908, 2305, 2307, 2308, 2309, 2317 | Y | N |  |  | 5212 | 4787
4790 | Sterrett - Ennis West 138 kV Line | Upgrade existing line | Construction schedule change | Sterrett | Ennis West | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4200 | 2018-05-15 |  | 138 | 0 | 21.1 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  | 2241, 2315, 2316, 2320, 2317, 2319, 2321 | Y | N |  |  | 5217 | 4790
4794 | Kirkland Park - Greenville 138 kV Line | Upgrade existing double-circuit line | Construction schedule change | Kirkland Park | Greenville | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4214 | 2018-05-15 |  | 138 | 0 | 7.4 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2456, 2457, 2882, 2883, 2884, 2885, 2886, 2887 | Y | N |  |  | 5220 | 4794
4795 | Argyle Sw. Sta. - Spencer (TMPA) 138 kV Line | Upgrade Argyle Sw. Sta. - Corinth line section |  | Argyle Sw. Sta. | Corinth | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3202 | 2018-05-15 |  | 138 | 0 | 3 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 1984, 1985 | Y | N |  |  | 5221 | 4795
4796 | West Levee - Dealey - Cedar Crest 138 kV Line | Upgrade existing line | Construction schedule change | West Levee | Cedar Crest | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4212 | 2018-05-15 |  | 138 | 0 | 4.7 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2400, 2493, 2842 | Y | N |  |  | 5222 | 4796
4797 | Royse - Nevada 138 kV Line | Upgrade existing line | Construction schedule change | Royse | Nevada | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4207 | 2018-05-15 |  | 138 | 0 | 4.2 | 0 |  | Rockwall | Collin | Tier 4 |  |  |  | 811, 2471 | Y | N |  |  | 5223 | 4797
4800 | Pleasant Valley - Wichita Falls Cogen 138 kV Line | Upgrade existing line |  | Pleasant Valley | Wichita Falls Cogen | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4002 | 2018-05-15 |  | 138 | 0 | 5.6 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  | 1450, 1498 | Y | N |  |  | 5231 | 4800
4802 | Lake Wichita Sw. Sta. Holliday 69 kV Line conversion | Convert existing 69 kV line to 138 kV operation |  | Lake Wichita Sw. Sta. | Holliday | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4009 | 2018-05-15 |  | 138 | 0 | 10.1 | 0 |  | Wichita | Archer | Tier 4 |  |  |  | 1447, 11527, 1446, 1449, 1527 | Y | N |  |  | 5233 | 4802
4814 | Northwest Carrollton - Carrollton East 138 kV Line | Upgrade existing line |  | Northwest Carrollton | Carrollton East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4205 | 2018-05-15 |  | 138 | 0 | 5.9 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2363, 2555, 2576 | Y | N |  |  | 5245 | 4814
4815 | DeSoto Sw. Sta. - Ennis Sw. Sta. 138 kV Line | Upgrade existing line |  | DeSoto Sw. Sta. | Ennis Sw. Sta. | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4204 | 2018-05-15 |  | 138 | 0 | 17.8 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  | 221, 2328, 2329, 2424 | Y | N |  |  | 5246 | 4815
4816 | Liggett series reactors | Install series reactors on 345/138 kV autotransformers |  | Liggett |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4206 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  | 11928, 11929, 1922, 1923, 1924, 1925 | Y | N |  |  | 5247 | 4816
4817 | TI Dallas - Kirkland Park/Coit Road 138 kV Line | Upgrade existing TI Dallas - Schroeder Road line section |  | TI Dallas | Schroeder Road | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4202 | 2018-05-15 |  | 138 | 0 | 1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2607, 2633, 2636, 2637 | Y | N |  |  | 5248 | 4817
4820 | Forest Grove - Canton Tap Switch 138 kV Line | Upgrade existing Forest Grove - Mabank line section |  | Forest Grove | Mabank | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6014 | 2018-05-15 |  | 138 | 0 | 12 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  | 3131, 3176, 3177, 3178, 3179 | Y | N |  |  | 5251 | 4820
4821 | Nacogdoches Southeast - Herty North 138 kV Line | Upgrade existing line |  | Nacogdoches Southeast | Herty North | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6049 | 2018-05-15 |  | 138 | 0 | 13.4 | 0 |  | Nacogdoches | Angelina | Tier 4 |  |  |  | 3120, 3319 | Y | N |  |  | 5252 | 4821
4823 | Trinidad - Kaufman Northwest 138 kV Line | Upgrade existing line |  | Trinidad | Kaufman Northwest | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6048 | 2018-05-15 |  | 138 | 0 | 34.4 | 0 |  | Kaufman | Henderson | Tier 4 |  |  |  | 2724, 2725, 2726, 3127, 3260, 3262, 2728, 3264 | Y | N |  |  | 5255 | 4823
4824 | Paris Switch 138/69 kV autotransformer | Install 138/69 kV autotransformer |  | Paris Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4100 | 2018-05-15 |  | 138 | 0 | 0 | 100 |  | Lamar |  | Tier 4 |  |  |  | 1779, 11693, 1778, 1803, 1693 | Y | N |  |  | 5256 | 4824
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line |  | Cresson | Rocky Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5228 | 2018-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  | 1881, 2204 | Y | N |  |  | 5261 | 4834
4836 | Eagle Mountain - Weatherford 138 kV Line | Upgrade existing line |  | Eagle Mountain | Weatherford | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5217 | 2018-05-15 |  | 138 | 0 | 23.4 | 0 |  | Tarrant | Parker | Tier 4 |  |  |  | 1592, 1860, 2062, 15015 | Y | N |  |  | 5263 | 4836
4840 | Crockett 138 kV Sw. Sta | Upgrade existing station | Construction schedule change | Crockett |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6060 | 2018-05-15 |  | 138 | 0 | 0 | 0 |  | Houston |  | Tier 4 |  |  |  | 3351, 3354 | Y | N |  |  | 5267 | 4840
4841 | Rivercrest - Sulphur Springs Switch 138 kV Line | Upgrade existing line |  | Rivercrest | Sulphur Springs Switch | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R980 | 2018-05-15 |  | 138 | 0 | 35.7 | 0 |  | Red River | Hopkins | Tier 3 |  |  |  | 1698, 1780, 1793, 1794, 1796, 1797, 1800, 11797 | Y | N |  |  | 5268 | 4841
4843 | Hicks Sw. Sta. 345/138 kV autotransformer #2 | Install second 345/138 kV autotransformer |  | Hicks Sw. Sta. |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5229 | 2018-05-15 |  | 345 | 0 | 0 | 600 |  | Tarrant |  | Tier 4 |  |  |  | 2082, 2081 | Y | N |  |  | 5270 | 4843
5310 | Everman - Venus 345 kV Double-circuit line | Upgrade existing line |  | Everman | Venus | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 |  | 2018-05-15 |  | 345 | 0 | 34.6 | 0 |  |  |  | Tier 4 |  |  |  | 1882, 1886, 1906, 1907 | Y |  |  |  | 5811 | 5310
4407 | Potencia: Build new 345/138 kV station | Interconnect La Paloma Generation at Potencia along the La Palma to Rio Hondo 345 kV and 138 kV lines and add 345/138 kV autotransformer capacity at Potencia |  | Potencia |  | Planned | 701 - 0871 | AEP TCC | Jason Bryant dnlyons@aep.com 918-599-2698 | 3545 | 2018-05-19 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 3 |  |  |  | 8460, 8461, 8314, 8317, 8318, 8319 | Y |  |  |  | 4786 | 4407
3937 | Brazos Valley Connection | Construct 345kV double circuit from Gibbons Creek to Zenith. |  | Gibbons Creek | Zenith | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 717 | 2018-05-30 |  | 345 | 63 | 0 | 0 |  | Harris | Grimes | Tier 1 | 2013-07-25 | 2014-02-20 | 2014-04-08 | 967, 44900 | Y | Y |  |  | 4893 | 3937
18TPIT0002 | Martinez - New 138kV Substation | Loop new 138kV substation into the existing 138kV Deely to Skyline line |  | Deely | Skyline | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2018-05-31 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5294, 5110, 5368 | Y | N |  | There are no transformers associated with this project | 2336 | 2263
06TPIT0068 | Hamilton Road to Picacho, reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | HAMILTON ROAD | PICACHO | Conceptual | 774-0959 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 1544 | 2018-05-31 |  | 138 |  | 8.76 |  |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8255, 8684 | N | N |  |  | 3742 | 3535
3663 | College Hills: Replace 138/69 kV autotransformer | Add 138/69 kV autotranformer capacity at College Hills |  | College Hills |  | Planned | 641 - 0810 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 1805 | 2018-05-31 |  | 138 | 0 | 0 | 90 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6468, 6470 | Y | N |  |  | 3900 | 3663
3664 | San Angelo North: Replace 138/69 kV autotransformer | Add 138/69 kV autotranformer capacity at San Angelo North |  | San Angelo North |  | Planned | 642 - 0811 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 1806 | 2018-05-31 |  | 138 | 0 | 0 | 90 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6462, 6464 | Y | N |  |  | 3901 | 3664
3671 | Moran to Putnam: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line with 795 ACSS | Project Description Update | Moran | Putnam | Planned | 645 - 0814 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 1807 | 2018-05-31 |  | 69 | 0 | 12.86 | 0 |  | Shackelford | Callahan | Tier 4 |  |  |  | 6209, 6307 | Y | N |  |  | 3908 | 3671
4454 | Henne to Comal Transmission Line Upgrade | Upgrade the 7.6 mile Henne (7174) - Comal (7176) 138-kV transmission line from 159 MVA to 380 MVA using single 959 ACSS Suwannee conductors. |  | Henne | Comal | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015116 | 2018-05-31 |  | 138 | 0 | 7.6 | 0 |  | Comal | Comal | Tier 4 |  |  |  | 7174, 7176 | Y | N |  |  | 4839 | 4454
4488 | Campwood to Uvalde: Rebuild 69 kV line | Rebuild Campwood to Uvalde 69 kV line with 959.9 ACSS/TW and energize as 138 kV and add 138/69 kV autotransformer capacity at Campwood |  | Campwood | Uvalde | Planned | 707 - 0877 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2901 | 2018-05-31 |  | 138 | 0 | 37.1 | 90 |  | Real | Uvalde | Tier 2 |  |  |  | 8230, 8633, 8231 | Y | N |  |  | 4882 | 4488
5020 | Red Creek: Replace the other 345/138 kV autotransformer | Replace both 345/138 kV autotransformers at Red Creek with 480 MVA autotransformers |  | Red Creek |  | Planned | 566 - 0740 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2615 | 2018-05-31 |  | 345 | 0 | 0 | 480 |  | Tom Green |  | Tier 4 |  |  |  | 6769, 6444, 6442 | Y | N |  |  | 5478 | 5020
5198 | Albany to Albany Foundry: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line with 795 ACSS | NEW | Albany Foundry | Albany | Planned | 645 - 0814 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 1809 | 2018-05-31 |  | 69 | 0 | 5.4 | 0 |  | Shackelford | Shackelford | Tier 4 |  |  |  | 6202, 6213, 60398 | Y | N |  |  | 5682 | 5198
5271 | FPP Bus Tie Upgrades | Add a second bus tie between LCRA TSC FPP 345-kV Yard #1 and Yard #2 with a minimum 1793 MVA rating. Upgrade T405 to a minimum rating of 1793 MVA. |  | FPP #1 | FPP #2 | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016189 | 2018-05-31 |  | 345 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  | 7055, 7056 | N | N |  |  | 5772 | 5271
5272 | Smithville - Winchester Line Overhaul | Rebuild T175 Smithville to Winchester with 795 ACSR (Drake) and OPGW. |  | Smithville | Winchester | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016207 | 2018-05-31 |  | 138 | 0 | 14.6 | 0 |  | Bastrop | Fayette | Tier 4 |  |  |  | 7306, 7314 | N | N |  |  | 5773 | 5272
14TPIT0041 | Coliseum to Kirby - 138 kV Transmission Line Rebuild | Rebuild 4.2 miles of 138 kV transmission line from Coliseum to Holbrook to Kirby and ensure a minimum conductor rating of 331 MVA |  | Colesium | Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0164 | 2018-06-01 |  | 138 | 0 | 4.2 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5095, 5160, 5218, 5250, 5420 | Y | N |  | There are no transformers associated with this project | 956 | 955
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0196 | 2018-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 2384 | 2308
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  | 5705 | Y | N |  |  | 2660 | 2554
3272 | Potranco - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to AMD line. |  | Cagnon | AMD | Planned | S-0753 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0219 | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5346, 5002, 5053 | Y | N |  | There are no transformers associated with this project | 3448 | 3272
3273 | Southton - New 138kV Substation | A new 138kV substation from 138kV Braunig to Brooks. |  | Southton | Braunig-Brooks | Planned | S-0750 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0217 | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5394, 5030, 5045 | Y | N |  | There are no transformers associated with this project | 3449 | 3273
3276 | JT Deely to Martinez MLSE Upgrade | Upgrade terminal at JT Deely to ensure a rating of 2386 A (minimum). |  | JT Deely | Martinez | Planned | S-0759 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5294, 5110 | Y | N |  | There are no transformers associated with this project | 3452 | 3276
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 5626, 5634 | Y | N |  |  | 4100 | 3818
3820 | Rebuild Sandia to AEP Mathis | Rebuild 69 kV 4-0 to 795 ACSR on 138 kV capable structures. |  | Sandia | AEP Mathis | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 69 | 0 | 7.85 | 0 |  | Jim Wells | San Patricio | Tier 4 |  |  |  | 5666, 8407 | Y | N |  |  | 4102 | 3820
3821 | Pearsall to Palo Duro 138 kV line upgrade | Upgrade Pearsall to Palo Duro 138 kV line as recommended in 2013 RTP |  | Pearsall | Paloduro | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 138 | 0 | 10.8 | 0 |  | Frio | Frio | Tier 4 |  |  |  | 5866, 5895 | Y | N |  |  | 4103 | 3821
4082 | CPSE_Howard to Somerset Rebuild | Rebuild approximately seven miles of 138 kV transmission circuit from Howard to Somerset. The Howard to Somerset circuit should be upgraded to 469 MVA, minimum. |  | Howard | Somerset | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0232 | 2018-06-01 |  | 138 | 0 | 7.56 | 0 |  | Bexar | Bexar | Tier 2 | 2014-05-07 | 2014-09-04 |  | 5230, 5390 | Y | N |  |  | 4432 | 4082
4138 | DME_Hickory_Locust |  |  | Hickory | Locust | Planned | N/A | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2018-06-01 |  | 69 | 0 | 2.5 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 910, 914, 926 | Y | N | N/A |  | 4483 | 4138
4321 | Add Eagle Station |  |  | Hickory | Locust | Planned |  | DME | Chuck Sears 940-349-7111 |  | 2018-06-01 |  | 69 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  | 926, 910, 914 | Y | N |  |  | 4698 | 4321
5144 | CPSE_Pleasanton Rd Transmission Rebuild | Rebuild approximately seven circuit miles of 138 kV transmission on Pleasanton Road from Loop 410 to Harlandale Tap. This project includes partial rebuild of the Sommers to Harlandale and Sommers to Merida 138 kV transmission circuits. |  | Sommers | Harlandale/Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0192 | 2018-06-01 |  | 138 | 0 | 7 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5190, 5310, 5395 | Y | N |  |  | 5622 | 5144
5218 | San Miguel 345/138 kV autotransformer replacements | 2015 RTP replace 300 MVA autos with much larger autos |  | San Miguel |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 345 | 0 | 0 | 1200 |  | Atascosa |  | Tier 4 |  |  |  | 5901, 5902, 5908, 5909 | Y | N |  |  | 5708 | 5218
5220 | Move Orange Grove load to 138 kV bus | 2015 RTP move load to 138 instead of replacing auto |  | Orange Grove |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  | 5660 | Y | N |  |  | 5712 | 5220
5221 | Move Oaks load to 138 kV bus | 2015 RTP move load to 138 instead of replacing auto |  | Oaks |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 138 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  | 5713 | Y | N |  |  | 5713 | 5221
5223A | 2015 RTP rebuild 4 sections from George West through Mathis | 2015 RTP rebuild George West Switch through Kittie West |  | George West Switch | Kittie West | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-01 |  | 69 | 0 | 4.25 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  | 5683, 5685, 5686 | Y | N |  |  | 5715 | 5223
5176 | Riley: Add 345 kV reactors | Add reactors to Tesla, Edith Clarke, Clear Crossing, and Riley | NEW | Riley |  | Planned | 754 - 0937 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 2627 | 2018-06-02 |  | 345 | 0 | 0 | 0 | -200,0 | Wilbarger |  | Tier 4 |  |  |  | 6101 | Y | N |  |  | 5660 | 5176
5223B | 2015 RTP rebuild 4 sections from George West through Mathis | 2015 RTP rebuild George West Tap to George West Sub |  | GW Tap | GW Substation | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-02 |  | 69 | 0 | 6.44 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  | 5684, 5685 | Y | N |  |  | 5716 | 5223
5223C | 2015 RTP rebuild 4 sections from George West through Mathis | 2015 RTP rebuild George West Sub to Mathis |  | GW Substation | Mathis | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2018-06-03 |  | 69 | 0 | 18.44 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  | 5668, 5684 | Y | N |  |  | 5717 | 5223
11TPIT0011 | Northeast 138kV Substation | Establish a 138kV substation with (2) 30MVA transformers and 4 distribution circuits with underground get-a-ways. The station will cut into existing Gilleland - Techridge line. | Original Project title is "East Substation" | Northeast Substation | Northeast Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P142 PLAN_117_P143 PLAN_117_P144 | 2018-06-15 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9195, 9054, 9190 | Y | N |  |  | 1053 | 1052
14TPIT0056 | Northaven - Morrison 138 kV line | Upgrade existing double-circuit line | Construction schedule change | Northaven | Morrison | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4088-E | 2018-06-15 |  | 138 | 0 | 12 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2657, 2658, 2660, 2661, 2662, 2663, 2782, 2783 | Y | N |  |  | 2598 | 2493
5145B | Rafter - New 138 kV Substation | Build a new 138 kV transmission line from Cagnon to Rafter for voltage support under contingency. |  | CAGNON | RAFTER | Planned | S-0837 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0261 | 2018-06-15 |  | 138 | 8.06 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5055, 5355 | Y | N |  |  | 5624 | 5145
20TPIT0000 | Parkway Substation | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-06-29 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7611 | Y | N |  |  | 3504 | 3323
16TPIT0034 | Coleto Creek to Tuleta: New 138 kV Line | Build a double circuit capable 138 kV circuit from Coleto Creek station to new Tuleta station. |  | COLETO CREEK | TULETA | Under Construction | 606-0771 | AEP TCC | Dave Goetz DNLYONS@AEP.COM 918-2599-2698 | 3481 | 2018-06-29 |  | 138 | 56 | 0 | 0 |  | Goliad | Bee | Tier 1 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8595, 8162, 8590 | Y | N |  |  | 3702 | 3495
13TPIT0106 | Killeen SS to Ding Dong | Rebuild 477 ACSR line with 955 ACSS |  | Killeen SS | Ding Dong | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 11037 | 2018-06-30 |  | 138 | 0 | 5.8 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 115, 117, 136, 3423 | Y | N |  |  | 2726 | 2608
3761 | Victoria to Fannin: 69 kV Transmission Line Rebuild | Rebuild Victoria to Fannin 69 kV line | Add Super project, and transmission status, ISD | VICTORIA | FANNIN | Under Construction | 662-0831 | AEP TCC | Rick McCracken DNLYONS@AEP.COM 918-599-2698 | 3527 | 2018-06-30 |  | 69 |  | 13.5 |  |  | Victoria | Victoria | Tier 4 |  |  |  | 5736, 8169 | Y | N |  |  | 4006 | 3761
15TPIT0069 | AEP_Angstrom | Add 138 kV PST |  | RAYMONDVILLE #2 | LOYOLA | Planned | 592 - 0769 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3479 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Kenedy |  | Tier 4 |  |  |  | 8134, 8530, 5648, 8899 | Y | N | NA |  | 4385 | 3354
4185 | HO Clarke Partial Load Conversion (TR1) | Convert HO Clarke TR1 load to 138kV. Tap off of Ckt.09 HO Clarke to Brays | Delay in project schedule | HO Clarke |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1112 | 2018-06-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47151, 47050, 47150 | Y | N |  |  | 4540 | 4185
5199 | Vernon Main Street: Add 138 kV capacitor bank | Add one 28.8 Mvar capacitor bank at Vernon Main Street | NEW | Vernon Main Street |  | Planned | 760 - 0944 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2635 | 2018-06-30 |  | 138 | 0 | 0 | 0 | 0,28.8 | Wilbarger |  | Tier 4 |  |  |  | 6060 | Y | N |  |  | 5683 | 5199
5203 | Bessel 138 kV Station: Install 20 MVAR Cap Bank | Install a 24.4 MVAR Cap Bank at Bessel 138 kV station |  | Bessel |  | Conceptual | 764-0949 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3572 | 2018-06-30 |  | 138 | 0 | 0 | 0 | 0,24.4 | Nueces |  | Tier 4 |  |  |  | 8060 | Y | N |  |  | 5687 | 5203
5204 | Jourdanton to Pleasanton: 69 kV Transmission Line Rebuild | Rebuild 69 kV line from Jourdanton to Pleasanton. Install 7.2 MVAR Cap Bank at Jourdanton station |  | Jourdanton | Pleasanton | Conceptual | 765-0950 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3573 | 2018-06-30 |  | 69 | 0 | 6 | 0 | 0,7.2 | Atascosa | Atascosa | Tier 4 |  |  |  | 8607, 8200 | Y | N |  |  | 5688 | 5204
5285 | Milton Capacitor Bank Addition(s) | Add two 138-kV 15.6 MVAR capacitor banks at the Milton Substation. |  | Milton |  | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2018-06-30 |  | 138 | 0 | 0 | 0 | 0,31.2 | Karnes |  | Tier 4 |  |  |  | 78583 | N | N |  |  | 5786 | 5285
5299 | Red Creek to Coke Street: Rebuild 138 kV line | Rebuild Red Creek to Coke Street 138 kV line with 795 ACSS | NEW | Red Creek | Coke Street | Planned | 768 - 0953 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2639 | 2018-06-30 |  | 138 | 0 | 8.01 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 6442, 6449 | Y | N |  |  | 5800 | 5299
5180 | Add second circuit to SLU panhandle loop |  |  | Alibates | Tule Canyon | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-07-01 |  | 345 | 166 | 0 | 0 |  | Carson | Briscoe | Tier 1 |  |  |  | 79500, 79501, 79502, 79503, 79504 | Y | N |  |  | 5664 | 5180
5187 | Add 2nd Palmito Transfomer |  |  | Palmito | Loma Alta | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-07-01 |  | 345 | 0 | 0 | 450 |  | Cameron | Cameron | Tier 4 |  |  |  | 5962, 5966 | Y | N |  |  | 5671 | 5187
5208 | Addition of synchronous condensers at Alibates and Tule Cany |  |  | Alibates | Tule Canyon | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2018-07-01 |  | 345 | 0 | 0 | 175 | 150300 | Carson | Briscoe | Tier 1 |  |  |  | 79520, 79521, 79500, 79503 | Y | N |  |  | 5692 | 5208
4719 | AEP_Add_ Melon Creek 69kV | Construct Melon Creek 69kV Substation | New Project | Melon Creek |  | Planned | 718 - 0900 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3554 | 2018-07-31 |  | 69 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  | 80066, 8410, 8800 | Y | N |  |  | 5137 | 4719
17TPIT0008 | Marion to Cibolo T-Line (T-302) Circuit Addition | Add another 138 kV circuit, to existing Marion to Cibolo T-Line (T-302), 1192 ACSR, 4.81 miles |  | Marion | Cibolo | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-09-28 |  | 138 | 4.81 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7178, 7608 | Y | N |  |  | 2962 | 2792
4505 | BRYN_4505_New_Annex | Construction of a New Annex Substation at 138kV |  |  |  | Planned |  | BRYN |  |  | 2018-09-30 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32853 | Y |  |  |  | 4902 | 4505
4567 | BRYN_4567_New_Annex_Line | Loop in new Annex Substation at 138kV |  | 32897 | 32863 | Planned |  | BRYN |  |  | 2018-09-30 |  | 138 | 0.75 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32853, 32863, 32897 | Y |  |  |  | 4974 | 4567
4572 | Atkins Bus Work for Power Transformer addition | Atkins Bus Work for Power Transformer addition |  | 32864 |  | Planned |  | BRYN |  |  | 2018-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  | No MOD changes necessary | 4979 | 4572
13TPIT0045 | Blumenthal Substation | Construct a new 11.5 mile 138 kV transmission line from a tap point on the Kendall CTEC (7147) - Mountain Top (7148)138 kV transmission line to the new Blumenthal substation (7418) using 336 ACSR Linnet. | Delayed from initial May 2013 in-service date | Blumenthal | Kendall CTEC-Mountain Top | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1010656 | 2018-10-16 |  | 138 | 8.4 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7418, 7419, 7147, 7148 | Y | N |  |  | 991 | 990
18TPIT0001 | Wiederstein Substation | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Wiederstein |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-10-26 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7461 | Y | N |  |  | 3500 | 3319
5234 | Cibolo to Schertz T-Line (T303) | Add 138kV Breakers and associated relaying on both ends |  | Cibolo | Schertz | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2018-10-26 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7608, 7610 | Y | N |  |  | 5732 | 5234
17TPIT0026 | Stryker Creek - Lufkin 138 kV Line | Upgrade existing line |  | Stryker Creek | Lufkin | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6040-E | 2018-11-15 |  | 138 | 0 | 44.3 | 0 |  | Cherokee | Angelina | Tier 3 |  |  |  | 3110, 3340, 3341, 3342, 3343 | Y | N |  |  | 3324 | 3153
07TPIT0060 | Howard Lane to Techridge Reconductor | The project re-conductors Circuit 1004 (Techridge to Howard Lane) using 795 ACSS Drake conductors to increase the capacity to 4000 Amp. |  | Howard Lane | Techridge | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P067 PLAN_117_P194 | 2018-11-30 |  | 138 | 0 | 1.72 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9190, 9217 | Y | N |  |  | 1029 | 1028
4425 | New TR-JV Ckt 961 | Add 2nd Ckt from TR to HL to tie-in to HL-JV Ckt 961 bypassing HL and creating TR-JV Ckt. |  | Techridge | Jollyville | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2018-11-30 |  | 138 | 1.7 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9190, 9217, 9223 | Y | N |  |  | 4809 | 4425
07TPIT0050 | Dunlap to Techridge 138kV Circuit Relocation | This project will reroute the existing Ckt 975 Dunlap-Techridge from near the intersection of Howard Lane and Dessau Road to the Techridge substation. The reroute will use 3000 amp bundled 795 ACSS Drake conductor. |  | Dunlap Substation | Techridge Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P071 | 2018-12-13 |  | 138 | 0 | 2.7 | 0 |  | Travis | Travis | Tier 2 | 2009-01-26 | 2009-07-21 |  | 9045, 9190 | Y | N |  |  | 1014 | 1013
4065 | Add Graham Road Substation |  |  | BTU South | BTU Greens Prairie | Planned |  | COCS | Tony Mickalsky tmichalsky@cstx.gov 979-764-3438 |  | 2018-12-30 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  | 32007, 32878, 32880 | Y |  |  |  | 4415 | 4065
14TPIT0079 | Glen Rose to Meridian Rebuild | Rebuild Glen Rose to Meridian with 795 ACSR, 138 kV construction (operate at 69 kV) |  | Glen Rose | Meridian | Planned |  | BEPC | Dwight Beckman kdye@brazoselectric.com 254-750-6373 | 15024 | 2018-12-31 |  | 69 | 0 | 18.18 | 0 |  | Somervell | Bosque | Tier 4 |  |  |  | 315, 319 | Y | N |  |  | 2310 | 2237
3776 | Big Lake to Powell Field Junction Tap: Rebuild 69 kV line | Rebuild Big Lake to Powell Field Junction Tap 69 kV line with 959.6 ACSS/TW |  | Big Lake | Powell Field Junction Tap | Planned | 667 - 0836 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2594 | 2018-12-31 |  | 69 | 0 | 12.76 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  | 6533, 6546, 6547, 6548 | Y | N |  |  | 4021 | 3776
3948 | Steamboat to Tuscola: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola |  | Steamboat | Tuscola | Planned | 685 - 0855 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 1851 | 2018-12-31 |  | 69 | 0 | 9.856 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  | 6328, 6331, 60332 | Y | N |  |  | 4266 | 3948
3949 | Steamboat to Winters: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola |  | Steamboat | Winters | Planned | 685 - 0855 | ETT | Glen Reed gareed@aep.com 918-599-2664 | 1850 | 2018-12-31 |  | 69 | 0 | 9.944 | 0 |  | Taylor | Runnels | Tier 4 |  |  |  | 6333, 60332 | Y | N |  |  | 4267 | 3949
4706 | HO Clarke to Webster Ckt.05 | Thermal Uprate of HO Clarke to Webster Ckt.05 | Delay in project schedule | HO Clarke | Webster | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 44361, 47150, 43260 | Y | N |  |  | 5118 | 4706
4996 | HO Clarke Load Conversion | Convert HO Clarke TR2 & TR3 to 138kV service. Tap off of Ckt.25 HO Clarke to Fondren. | Delay in project schedule | HO Clarke | Fondren | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2018-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 47151, 47152, 47160, 47150, 47412 | Y |  |  |  | 5454 | 4996
5165 | Borglum: Build new 138/69 kV station | Construct new Borglum station near Beeville, add 138/69 kV autotransformer capacity at Borglum, rebuild Three Rivers to Beeville 69 kV line with 959.6 ACSS/TW and convert to 138 kV and terminate into Borglum, rebuild the Beeville to Kenedy Switch 69 kV line as double circuit 138/69 kV with 959.6 ACSS/TW from Tuleta and terminate into Borglum, cut-in Beeville to Sinton 69 kV line into Borglum, and cut-in Beeville to Mathis 69 kV line into Borglum |  | Borglum |  | Planned | 742 - 0925 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2914 | 2018-12-31 |  | 138 | 0 | 0 | 130 |  | Bee |  | Tier 1 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8196, 8197, 8107, 8198, 8904 | Y | N |  |  | 5648 | 5165
5166 | Beeville to Three Rivers: Rebuild 69 kV line | Construct new Borglum station near Beeville, add 138/69 kV autotransformer capacity at Borglum, rebuild Three Rivers to Beeville 69 kV line with 959.6 ACSS/TW and convert to 138 kV and terminate into Borglum, rebuild the Beeville to Kenedy Switch 69 kV line as double circuit 138/69 kV with 959.6 ACSS/TW from Tuleta and terminate into Borglum, cut-in Beeville to Sinton 69 kV line into Borglum, and cut-in Beeville to Mathis 69 kV line into Borglum |  | Borglum | Three Rivers | Planned | 742 - 0925 | AEP TCC | Dave Gotez dnlyons@aep.com 918-599-2698 | 2915 | 2018-12-31 |  | 138 | 6 | 22 | 0 |  | Bee | Live Oak | Tier 1 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8198, 8196, 8400, 8403 | Y | N |  |  | 5649 | 5166
5189 | Exxon Hawley Tap to Onyx Switch Station: Rebuild 69 kV line | Rebuild Hawley Tap to Onyx Switch Station with 795 ACSS | NEW | Hawley Tap | Onyx Switch Station | Planned | 753 - 0939 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2630 | 2018-12-31 |  | 69 | 0 | 6.57 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 6224, 6238, 6388 | Y | N |  |  | 5673 | 5189
5202 | Bay City 138 kV Station: Install 14.4 MVAR Cap Bank | Install a 14.4 MVAR Cap Bank at Bay City 138 kV station |  | Bay City |  | Conceptual | 767-0952 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3575 | 2018-12-31 |  | 138 | 0 | 0 | 0 | 0,14.4 | Matagorda |  | Tier 4 |  |  |  | 8113 | Y | N |  |  | 5686 | 5202
4464B | Comal to Loop 337 Transmission Line Upgrade | Upgrade/Replace underrated switches to 2000 Amp Switches | Switches may be dynamically rated during Winter peak conditions. | Comal | GPI Switchyard | Planned |  | NBU | Greg Baumbach gbaumbach@nbutexas.com 830-629-8441 |  | 2019-05-01 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  | 7176, 7456, 7459 | Y | N |  |  | 5206 | 4464
16TPIT0055 | Elkton - Stryker Creek 138 kV Line | Upgrade existing Elkton - Jacksonville 138 kV line section |  | Elkton | Jacksonville | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6029-E | 2019-05-15 |  | 138 | 0 | 20.2 | 0 |  | Smith | Cherokee | Tier 4 |  |  |  | 3106, 3251, 3253, 13253 | Y | N |  |  | 3279 | 3110
17TPIT0010 | Chandler 69 kV capacitors | Install shunt capacitor | Scope and construction schedule change | Chandler |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6025-E | 2019-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Henderson | Henderson | Tier 4 |  |  |  | 3235 | Y | N |  |  | 3285 | 3116
10TPIT0019 | Everman - Cleburne Switch 138 kV Line | Upgrade existing Everman - Mansfield line section |  | Everman | Mansfield | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5218 | 2019-05-15 |  | 138 | 0 | 7.7 | 0 |  | Tarrant | Johnson | Tier 4 |  |  |  | 1883, 2208 | Y | N |  |  | 4754 | 3092
4808 | Wickett - O'Brian 69 kV Line conversion | Convert existing 69 kV line to 138 kV operation |  | Wickett | O-Brian | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8316 | 2019-05-15 |  | 138 | 1 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  | 1294, 1295, 1088 | Y | N |  |  | 5239 | 4808
4822 | Bell County (BEC) - Gabriel (LCRA) 138 kV | Upgrade existing line |  | Bell County | Gabriel | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R2008 | 2019-05-15 |  | 138 | 0 | 35.2 | 0 |  | Bell | Williamson | Tier 3 |  |  |  | 121, 3425, 3640, 3688, 7346, 13640 | Y | N |  |  | 5253 | 4822
4825 | Crockett - Jewett 138kV Line | Upgrade existing line |  | Crockett | Jewett | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6061 | 2019-05-15 |  | 138 | 0 | 39.5 | 0 |  | Houston | Leon | Tier 3 |  |  |  | 3354, 3355, 3357, 3358, 3394 | Y | N |  |  | 5257 | 4825
4826 | Hutto Sw. Sta. - Gilleland Creek (LCRA) 138 kV Line | Upgrade existing line |  | Round Rock Southeast | Round Rock Southeast Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R2005 | 2019-05-15 |  | 138 | 0 | 7.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 3654, 3666, 7336 | Y | N |  |  | 5258 | 4826
4827 | Lufkin - Nacogdoches Southeast 138 kV Line | Upgrade existing line |  | Lufkin | Nacogdoches | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6062 | 2019-05-15 |  | 138 | 0 | 21.6 | 0 |  | Angelina | Nacogdoches | Tier 3 |  |  |  | 3120, 3314, 3316, 3315, 3340 | Y | N |  |  | 5259 | 4827
4835 | DeCordova - Cleburne Sw. Sta. 138 kV Line | Upgrade existing line |  | DeCordova | Cleburne Sw. Sta. | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5226 | 2019-05-15 |  | 138 | 0 | 22.6 | 0 |  | Hood | Johnson | Tier 3 |  |  |  | 1891, 2279, 2280, 2281, 2283 | Y | N |  |  | 5262 | 4835
4842 | Holt 138/69 kV autotransformer | Replace existing autotransformer |  | Holt |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8317 | 2019-05-15 |  | 138 | 0 | 0 | 150 |  | Ector |  | Tier 4 |  |  |  | 1142, 1141 | Y | N |  |  | 5269 | 4842
5312 | Mitchell Bend - Rocky Creek 345 kV line | Upgrade existing line |  | Mitchell Bend | Rocky Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 |  | 2019-05-15 |  | 345 | 0 | 32.8 | 0 |  |  |  | Tier 4 |  |  |  | 1877, 1880 | Y |  |  |  | 5813 | 5312
4445 | Kerrville Stadium to Harper Road Transmission Line Upgrade | Upgrade the 1.6 mile Kerrville Stadium (7138) - Harper Road (7140) 138-kV transmission line to bundled 795 ACSR Drake, 440 MVA. |  | Kerrville Stadium | Harper Road | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015115 | 2019-05-30 |  | 138 | 0 | 1.6 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  | 7138, 7140 | Y | N |  |  | 4833 | 4445
5167 | Borglum to Tuleta: Build new double circuit 138/69 kV line | Construct new Borglum station near Beeville, add 138/69 kV autotransformer capacity at Borglum, rebuild Three Rivers to Beeville 69 kV line with 959.6 ACSS/TW and convert to 138 kV and terminate into Borglum, rebuild the Beeville to Kenedy Switch 69 kV line as double circuit 138/69 kV with 959.6 ACSS/TW from Tuleta and terminate into Borglum, cut-in Beeville to Sinton 69 kV line into Borglum, and cut-in Beeville to Mathis 69 kV line into Borglum |  | Borglum | Tuleta | Planned | 742 - 0925 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 2916 | 2019-05-30 |  | 138 | 23.5 | 10.5 | 0 |  | Bee | Bee | Tier 1 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 88590, 8186, 8188, 8196, 8198, 8592, 8593, 8184, 8590 | Y | N |  |  | 5650 | 5167
3669 | Albany Foundry to Moran: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line with 795 ACSS | Project Description Update | Albany Foundry | Moran | Planned | 645 - 0814 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 1808 | 2019-05-31 |  | 69 | 0 | 10 | 0 |  | Shackelford | Shackelford | Tier 4 |  |  |  | 6202, 6209 | Y | N |  |  | 3906 | 3669
3777 | Ozona to Midway Lane: Rebuild 69 kV line | Rebuild Ozona to Midway Lane 69 kV line with 959.6 ACSS/TW |  | Ozona | Midway Lane | Planned | 667 - 0836 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2594 | 2019-05-31 |  | 69 | 0 | 16.96 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  | 6549, 6560 | Y | N |  |  | 4022 | 3777
4465 | Wirtz to FlatRock to Paleface Transmission Line Upgrade | Upgrade the 17.34 mile Wirtz (7104) - Flat Rock (7111) - Paleface (7477) 138-kV transmission line to single 795 ACSR Drake, 221 MVA. |  | Wirtz | Paleface | Conceptual |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2019-05-31 |  | 138 | 0 | 17.34 | 0 |  | Burnet | Travis | Tier 3 |  |  |  | 7104, 7111, 7477 | N | N |  |  | 4851 | 4465
4473 | Zorn to Marion 2nd 345-kV Transmission Line Addition | Add 345-kV Zorn (7042) to Marion (7044) 2nd circuit using bundled Suwannee. Portion of the CPS-Tie Project. |  | Zorn | Marion | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015208 | 2019-05-31 |  | 345 | 18 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 1 | 2014-06-29 | 2015-03-26 | 2015-04-14 | 7042, 7044 | Y | N |  |  | 4859 | 4473
4844 | 2nd Marion Autotransformer | Add a Second 345/138-kV Autotransformer at Marion. Part of the CPS Tie Project |  | Marion | Marion | Planned | 4473 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1015208 | 2019-05-31 |  | 345 | 0 | 0 | 478 |  | Guadalupe | Guadalupe | Tier 1 | 2014-06-29 | 2015-03-26 | 2015-04-14 | 77044, 7044, 7178 | Y | N |  |  | 5271 | 4844
5273 | Bergheim Substation Upgrade | Add a 345-kV bus and a 345/138-kV 336 MVA autotransformer at Bergheim Substation. |  | Bergheim |  | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016178 | 2019-05-31 |  | 345 | 0 | 0 | 336 |  | Comal |  | Tier 4 |  |  |  | 7770, 7771, 7043, 7046, 7170 | N | N |  |  | 5774 | 5273
5274 | Camp Wood - Leakey Transmission Line Overhaul | Rebuild T269 Camp Wood to Leakey to be 138-kV capable with a nominal conductor rating of 223 MVA at 138-kV (Single Drake) with OPGW and operated at 69-kV. |  | Camp Wood | Leakey | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016183 | 2019-05-31 |  | 69 | 0 | 17.3 | 0 |  | Real | Real | Tier 4 | 2015-12-16 | 2016-01-27 |  | 7426, 8633 | N |  |  |  | 5775 | 5274
11TPIT0008 | Rainey St 138kV substation | Establish a new 138kV Rainey St substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2019-06-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9261, 9118, 9132 | Y | N |  |  | 1033 | 1032
4083 | CPSE_Merida to Westside Rebuild | Rebuild approximately four miles of 138 kV transmission circuit from Merida to Westside. The Merida to Westside circuit should be upgraded to 349 MVA, minimum. |  | Merida | Westside | Planned | S-0773 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0235 | 2019-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5310, 5490 | Y | N |  |  | 4433 | 4083
4084 | Barton-Vega: Upgrade Ckt 928 | Reconductor to 2000 amps |  | Barton | Vega | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2019-06-01 |  | 138 | 0 | 4.05 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9158, 9285 | Y |  |  |  | 4434 | 4084
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0733 | 2019-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5045, 5085 | Y | Y |  |  | 4697 | 4320
4438 | BenDavis-Murphy 138kV Line Upgrade | BenDavis-Murphy 138kV Line Upgrade |  | Ben Davis | Murphy | Planned |  | GARLAND/GPL-TMPA and Oncor | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2019-06-01 |  | 138 | 0 | 4.3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 968, 2696 | Y | Y |  |  | 4824 | 4438
4652 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2019-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9276, 9077, 9238 | Y |  |  |  | 5053 | 4652
13TPIT0198 | Seawillow Substation | Construct 138kV-12.5kV distribution substation Seawillow (7559) on T-184 Lockhart and Luling. |  | Seawillow | Luling / Lockhart | Planned |  | LCRATSC/BBEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013521 | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  | 7559, 7216, 7224 | Y | N |  |  | 2772 | 2648
2979 | Melon Creek: Install 138/69kV Auto | Construct Melon Creek substation on Airco to Rincon 138kV line with 138/69kV, 93 MVA auto. |  | Melon Creek |  | Conceptual | 100 - 0100 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2021 | 2019-06-30 |  | 138 | 0 | 0 | 93 |  | Refugio |  | Tier 4 |  |  |  | 8144, 8418, 80065, 80066, 80067 | Y | N |  |  | 3148 | 2979
5024 | Crane Loop: Rebuild 69 kV line | Rebuild Crane Loop 69 kV line with 795 ACSS |  | Crane | Crane | Planned | 738 - 0921 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2619 | 2019-06-30 |  | 69 | 0 | 8.05 | 0 |  | Crane | Crane | Tier 4 |  |  |  | 6600, 6603, 6607, 6609, 6606, 6608, 6613 | Y | N |  |  | 5486 | 5024
5205 |  | Rebuild 69 kV line from Carrizo Spring to Crystal City |  | Carrizo Springs | Crystal City | Conceptual | 761-0945 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3569 | 2019-06-30 |  | 69 | 0 | 12 | 0 |  | Dimmit | Zavala | Tier 4 |  |  |  | 8244, 8242 | Y | N |  |  | 5689 | 5205
5206 | Brackettville to Escondido: Construct 138 kV line | Build a double circuit capable 138 kV circuit from Brakettville to Escondido station |  | Brackettville | Escondido | Conceptual | 762-0947 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3570 | 2019-06-30 |  | 138 | 45 | 0 | 0 |  | Kinney | Maverick | Tier 4 |  |  |  |  | Y | N |  |  | 5690 | 5206
5257 | Solstice to Permian Basin: Rebuild 138 kV line | Rebuild Solstice to Permian Basin 138 kV line with 2x795 ACSS and add dynamic reactive devices at Ft. Stockton and Lotebush | NEW | Solstice | Permian Basin | Planned | 713 - 0946 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2636 | 2019-06-30 |  | 138 | 0 | 37.5 | 0 |  | Pecos | Ward | Tier 1 | 2016-12-15 |  |  | 6656, 6673, 60385, 60392, 60377, 60393, 60397 | Y | Y |  |  | 5757 | 5257
5258 | Ft. Stockton: Add dynamic reactive device | Rebuild Solstice to Permian Basin 138 kV line with 2x795 ACSS and add dynamic reactive devices at Ft. Stockton and Lotebush | NEW | Ft. Stockton |  | Planned | 713 - 0946 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2637 | 2019-06-30 |  | 138 | 0 | 0 | 0 | -25100 | Pecos |  | Tier 1 | 2016-12-15 |  |  | 6630 | Y | N |  |  | 5758 | 5258
5259 | Lotebush: Add dynamic reactive device | Rebuild Solstice to Permian Basin 138 kV line with 2x795 ACSS and add dynamic reactive devices at Ft. Stockton and Lotebush | NEW | Lotebush |  | Planned | 713 - 0946 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 2638 | 2019-06-30 |  | 138 | 0 | 0 | 0 | -25100 | Reeves |  | Tier 1 | 2016-12-15 |  |  | 60392 | Y | N |  |  | 5759 | 5259
3877 | Meadow Lake Substation Addtion | Add a new load serving substation (ring-bus) at Meadow Lake. The station will be built between Cushman and Highway 123 off T572. |  | Cushman | Highway 123 | Planned |  | LCRATSC/GVEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7720, 7221, 7226 | N | N |  |  | 5765 | 3877
4606 | Moulton South Substation 138/69-kV Autotransformer | Add Moulton South Substation 138/69-kV Autotransformer |  | Moulton South | Moulton | Conceptual |  | LCRATSC/GVEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-07-01 |  | 138 | 0 | 0 | 45 |  | Lavaca |  | Tier 4 |  |  |  | 7588, 7237 | N | N |  |  | 5013 | 4606
3505 | Cibolo Substation | Add T3, 40 MVA 138-26.18 kV power transformer, CSW and low side |  | Cibolo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2019-09-27 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7608 | Y | N |  |  | 3712 | 3505
4575 | BRYN_4575_New_Steele_Store | Construct New Steele Store substation at 138kV. Project includes the wreck out of the existing Atkins to Annex to Steele Store 69kV line and removal of existing Annex and Steele Store 69kV substations. |  |  |  | Planned |  | BRYN |  |  | 2019-09-30 |  | 138 | 0 | 0 | 0 |  | Burleson |  | Tier 4 | 2015-10-09 | 2015-11-06 |  | 32852, 32868, 32864, 32866 | Y |  |  |  | 4982 | 4575
5041 | BRYN_5041_Snook_to_Steele_Store | Construct 138kV line from Snook to Steele Store as part of the reliability project to loop in Steele Store |  | 32857 | 32852 | Planned |  | BRYN |  |  | 2019-09-30 |  | 138 | 9.2 | 0 | 0 |  | Burleson | Brazos | Tier 4 | 2015-10-09 | 2015-11-06 |  | 32852, 32857 | Y |  |  |  | 5515 | 5041
3967 | Leander - Parmer - Round Rock Transmission Line Addition | Construct a new 138kV transmission line from Leander to Parmer (new substation) to Round Rock (approx 13 miles) using bundled 795 ACSR Drake (446 MVA) conductor. |  | Leander | Round Rock | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014352 | 2019-10-30 |  | 138 | 13 | 0 | 0 |  | Williamson | Williamson | Tier 2 | 2013-12-10 | 2014-05-22 | 2014-06-10 | 7367, 3668, 7525 | Y | N |  |  | 4288 | 3967
3754 | Heartland to Yellowjacket: Build 69 kV line | Build new 69 kV line from Heartland to Yellowjacket with 959.6 ACSR/TW | Contact Update | Heartland | Yellowjacket | Planned | 637 - 0806 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2592 | 2019-11-30 |  | 69 | 32 | 0 | 0 |  | Mason | McCulloch | Tier 2 | 2014-01-23 | 2014-11-17 |  | 6379, 60386, 6363, 6378, 6381, 6406 | Y | N |  |  | 4910 | 3754
4519 | Heartland: Build 69 kV station | Construct new 69 kV ring bus between MCEC Brady and Katemcy | Description Update | Heartland |  | Planned | 637 - 0806 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2609 | 2019-11-30 |  | 69 | 0 | 0 | 0 |  | McCulloch |  | Tier 2 | 2014-01-23 | 2014-11-17 |  | 60386 | Y | N |  |  | 4916 | 4519
4530 | Heartland to South Brady Tap: Rebuild existing & build new | Construct a new 69 kV line from Heartland to South Brady Tap and rebuild the existing line from Heartland to South Brady Tap |  | Heartland |  | Planned | 637 - 0806 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2610 | 2019-11-30 |  | 69 | 1.11 | 1.11 | 0 |  | McCulloch | McCulloch | Tier 2 | 2014-01-23 | 2014-11-17 |  | 6379, 60386, 6378, 6381, 6406 | Y | N |  |  | 4930 | 4530
4323 | CPSE_Braunig to Brooks_MLSE | Upgrade terminal at Brooks and ensure a rating of 1364 A (minimum) at both Braunig and Brooks terminals |  | Braunig | Brooks | In-Service |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0669 | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5030, 5045 | Y | Y |  |  | 4700 | 4323
5275 | Esperanza Substation Addition | Add a new load serving substation (ring bus) at Esperanza. The station will be built between Boerne an Fair Oaks Ranch off T503. |  | Boerne | Fair Oaks Ranch | Planned |  | LCRATSC/PEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016187 | 2019-12-01 |  | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7710, 5470, 7168 | N | N |  |  | 5776 | 5275
13TPIT0070 | Nash Creek Substation | Replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2019-12-20 |  | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7596 | Y | N |  |  | 3503 | 3322
4186 | University 138kV Load Conversion | Convert University TR2 & TR3 load to 138kV. | Delay in project schedule | University |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1123 | 2019-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 47750, 47752 | Y | N |  |  | 4541 | 4186
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing autotransformer |  | Elkton |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6032-E | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 4 |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 3326 | 3155
17TPIT0025 | Payne - South Sherman 138 kV Line | Upgrade existing line |  | Payne | South Sherman | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R945-E | 2020-05-15 |  | 138 | 0 | 3.5 | 0 |  | Grayson | Grayson | Tier 4 |  |  |  | 1740, 1753, 1750, 1758 | Y | N |  |  | 5228 | 3214
4818 | Watermill - Camp Wisdom 138 kV Line | Upgrade existing line |  | Watermill | Camp Wisdom | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4216 | 2020-05-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2430, 2988, 2989, 2990, 3068 | Y | N |  |  | 5249 | 4818
4819 | Temple Sw. Sta. - Bell County 138 kV Line | Upgrade existing line |  | Temple Sw. Sta. | Bell County | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1728 | 2020-05-15 |  | 138 | 0 | 8.4 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3415, 3425 | Y | N |  |  | 5250 | 4819
4829 | Hutto Sw. Sta. second 345/138 kV autotransformer | Install new autotransformer |  | Hutto |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R750 | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 4 |  |  |  | 13660, 3696, 3666 | Y | N |  |  | 5260 | 4829
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-05-29 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7611 | Y | N |  |  | 3505 | 3324
5276 | Flatonia - Hallettsville Transmission Line Upgrade | Upgrade T132 Hallettsville to Flatonia (18.7 mi) 138-kV transmission line to a minimum rating of 380 MVA with OPGW. |  | Flatonia | Hallettsville | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016188 | 2020-05-31 |  | 138 | 0 | 18.7 | 0 |  | Fayette | Lavaca | Tier 4 |  |  |  | 7246, 7248 | N | N |  |  | 5777 | 5276
5277 | Glidden Area Transmission Line Upgrade | Convert existing 69-kV lines (T544) from Glidden to Altair and (T545) from Altair to Nada to 138-kV transmission lines. Relocate existing 45 MVA auto from Glidden to Altair. Add a second new 45 MVA auto at Altair substation. |  | Glidden | Nada | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1016219 | 2020-05-31 |  | 138 | 0 | 0.77 | 45 |  | Colorado | Colorado | Tier 4 |  |  |  | 78107, 78111, 78118, 78520, 5536, 7258, 78103, 78106 | N | N |  |  | 5778 | 5277
5286 | Fayette Area Upgrades | Upgrade existing Fayette - Frelsburg - Mockingbird - Glidden (T176) TL with a minimum rating of 380 MVA and with OPGW. Upgrade existing Plum - Flatonia (T133) TL with a minimum rating of 380 MVA and with OPGW. |  | Fayette | Glidden | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Fayette | Colorado | Tier 3 |  |  |  | 7248, 7258, 7263, 7274, 7286, 78259 | N | N |  |  | 5787 | 5286
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into future 138kV Martinez to Skyline transmission line |  | Converse | Martinez-Skyline | Planned | T-0177 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0601 | 2020-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5098, 5294, 5368 | Y | N |  | There are no transformers associated with this project | 968 | 967
15TPIT0000 | Bird Pond Substation | Install (3) Breaker ring to include (2) 138 lines and (1) 138-12.5 transformer |  | Bird Pond | Bird Pond | Planned |  | BRYN | James Tanneberger 979-821-5763 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  | 32858, 962, 964 | Y | N |  |  | 1855 | 1812
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and-or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle-Weiderstein | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0645b | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5360, 5435 | Y | N |  | There are no transformers associated with this project | 2382 | 2306
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0385 | 2020-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5416, 5250, 5395 | Y | N |  | There are no transformers associated with this project | 3190 | 3021
3277 | Shepherd Road - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Valley line. |  | Shepherd Road | Cagnon-Valley | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5378, 5053, 5465 | Y | N |  | There are no transformers associated with this project | 3453 | 3277
3298 | Skyline - Install a Fourth 345kV Autotransformer. | Install one 600 MVA autotransformer at Skyline switchyard. |  |  |  | Planned | S-0670 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 345 | 0 | 0 | 600 |  | Bexar | Bexar | Tier 4 |  |  |  | 5372, 5371, 5368 | Y | N |  | There are no transmission line additions associated with this project | 3474 | 3298
3334 | Fort Sam to Kirby MLSE Upgrade | Upgrade terminals at Fort Sam and ensure a rating of 2000 A at both Fort Sam and Kirby terminals. |  | Fort Sam | Kirby | Planned | S-0747 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5160, 5250 | Y | N |  | There are no transformers associated with this project | 3517 | 3334
3297 | Tezel Road - New 138kV Substation | Loop new 138 kV substation into the existing 138 kV Helotes to Bandera line. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 5421, 5020, 5200 | Y |  |  | There are no transformers associated with this project | 3665 | 3297
3992 | Rebuild Dickinson - League City 138 kV line. | Rebuilding Dickinson to League City 138 kV (G138-09). *Project pushed back to 2020. |  | Dickinson Sub | League City Sub | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07215 | 2020-06-01 |  | 138 | 0 | 3.6 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 38850, 38920 | Y |  |  |  | 4318 | 3992
4010 | Rebuild Magnolia - Seminole 138 kV line. | *Project pushed back to 2020. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07216 | 2020-06-01 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  | 38950, 38990 | Y |  |  |  | 4355 | 4010
4443 | CPSE_Fort Sam to Tenth Street MLSE | Upgrade terminals at Fort Sam and ensure a rating of 2000 A at Fort Sam for the Fort Sam to Tenth Street transmission circuit. |  | Forth Sam | Tenth Street | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5160, 5420 | Y |  |  |  | 4830 | 4443
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-06-26 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  | 7239 | Y | N |  |  | 3519 | 3336
06TPIT0082 | Buena Vista to Picacho, reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | BUENA VISTA | PICACHO | Planned | 775-0960 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 1547 | 2020-06-30 |  | 138 |  | 3 |  |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8688 | N | N |  |  | 3745 | 3537
3901 | Lobo to Freer: Rebuild 69 kV line | Rebuild Lobo to Freer 69 kV line with 959.6 ACSS/TW |  | Lobo | Freer | Conceptual | 677 - 0846 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2596 | 2020-06-30 |  | 69 | 0 | 49.8 | 0 |  | Webb | Duval | Tier 3 |  |  |  | 8505, 80222 | Y | N |  |  | 4196 | 3901
4116 | FM-725 Substation | Build a new 138-26.18 kV, 40 MVA substation on the GVEC McQueeney(7606) - Schumansville(7609) 138 kV transmission line |  | FM 725 | McQueeney-Schumansville | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-07-31 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7725, 7606, 7609 | Y | N |  |  | 4462 | 4116
4971 | Bonilla: Build new four breaker 345 kV station | Interconnect Magic Valley II Windfarm at Bonilla to connect Magic Valley II to the North Edinburg to Rio Hondo 345 kV line and construct 345 kV line with 3-954 ACSR from Bonilla to Ladekidde |  | Bonilla | Ladekidde | Planned | 731 - 0913 | AEP TCC | Michael Glueck dnlyons@aep.com 918-599-2698 | 3562 | 2020-08-15 |  | 345 | 20 | 0 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  | 8573, 80506, 80512, 8318, 8383, 80076, 8902 | Y |  |  |  | 5546 | 4971
4571 | Atkins Substation Upgrade | Rebuild Atkins 69kV bus |  | 32864 |  | Planned |  | BRYN |  |  | 2020-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | Y |  |  | No MOD Changes Necessary | 4978 | 4571
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2020-11-20 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  | 7622 | Y | N |  |  | 3502 | 3321
16TPIT0024 | Hamilton Road to Escondido: Rebuild 138kV Line | Rebuild Hamilton Road to Escondido 138 kV line | Reformated project number to match other numbers | Hamilton Road | Escondido | Conceptual | 602 - 0764 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3471 | 2020-12-31 |  | 138 | 0 | 53.7 | 0 |  | Val Verde | Maverick | Tier 3 |  |  |  | 8255, 8260, 8264, 8692 | N | N |  | 0 | 2655 | 2550
4282 | Lewisville Sw - Lewisville Jones - Lakepointe 138 kV Line | Upgrade Oncor's section of the existing line |  | Lewisville Switch (Brazos) | Lakepointe (TNMP) | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R966 | 2021-05-15 |  | 138 | 0 | 1.6 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 645, 1973 | Y | N |  |  | 4657 | 4282
4803 | Wichita Falls South - Wichita Falls 138 kV Line | Upgrade existing line |  | Wichita Falls South | Wichita Falls | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4008 | 2021-05-15 |  | 138 | 0 | 7.8 | 0 |  | Archer | Archer | Tier 4 |  |  |  | 1448, 1464, 1478, 1480 | Y | N |  |  | 5234 | 4803
4804 | Wichita Falls South 345/138 kV autotransformer | Install autotransformer |  | Wichita Falls South |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4010 | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Archer |  | Tier 4 |  |  |  | 11464, 11465, 1422, 1425, 1464 | Y | N |  |  | 5235 | 4804
4805 | Wichita Falls South - Lake Wichita 138 kV Line | Upgrade existing line |  | Wichita Falls South | Lake Wichita | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R4011 | 2021-05-15 |  | 138 | 3.3 | 0 | 0 |  | Archer | Archer | Tier 4 |  |  |  | 1446, 1464 | Y | N |  |  | 5236 | 4805
4813 | Graham - Breckenridge/Leon 138 kV Line | Upgrade existing Graham - Breckenridge Tap line section |  | Graham | Breckenridge Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R1729 | 2021-05-15 |  | 138 | 0 | 27.8 | 0 |  | Young | Stephens | Tier 3 |  |  |  | 1431, 1613 | Y | N |  |  | 5244 | 4813
4845 | Salado - Gabriel - Hutto 138 kV Line Rebuild | Upgrade existing line |  | Salado Sw. Sta. | Hutto Sw. Sta. | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R2010 | 2021-05-15 |  | 138 | 0 | 69.6 | 0 |  | Bell | Williamson | Tier 3 |  |  |  | 3640, 3664, 3666, 3668, 3669, 3677, 7346, 7528, 3667, 3670, 7532 | Y | N |  |  | 5272 | 4845
4846 | Salado Sw. Sta. 345/138 kV autotransformer | Install new autotransformer |  | Salado Sw. Sta. |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R2009 | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Bell |  | Tier 4 |  |  |  | 113640, 3699, 3640 | Y | N |  |  | 5273 | 4846
4847 | Belton - Killeen Sw. Sta. 138 kV Line | Upgrade existing line |  | Belton | Killeen Sw. Sta. | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R902 | 2021-05-15 |  | 138 | 0 | 17.2 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 3423, 3610, 3633, 13610 | Y | N |  |  | 5274 | 4847
5287 | Buda to Turnersville Transmission Line Addition | Construct a second 138-kV transmission line between Buda and Turnersville Substations. |  | Buda | Turnersvile | Conceptual |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 3 |  |  |  | 7498, 7500 | N | N |  |  | 5788 | 5287
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Howard line. |  | Masterson Rd. | Cagnon-Howard | Planned | T-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0538 | 2021-06-01 |  | 138 | 20 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5296, 5054, 5230 | Y | N |  | There are no transformers associated with this project | 2291 | 2218
15TPIT0031 | Brooks to Chavaneaux - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from Brooks to Chavaneaux |  | Brooks | Chavaneaux | Conceptual |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0207 | 2021-06-01 |  | 138 | 0.1 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5045, 5085, 5330 | Y | N |  | There are no transformers associated with this project | 2380 | 2304
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 2000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2021-06-01 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 2548 | 2443
5222 | Rebuild Dilley to Cotulla 69 kV line | 2015 RTP rebuild 69 kV line with 138 kV capable 795 ACSR |  | Dilley | Cotulla | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-06-01 |  | 69 | 0 | 15.8 | 0 |  | La Salle | Frio | Tier 4 |  |  |  | 5863, 5876 | Y | N |  |  | 5714 | 5222
4576 | BRYN_4576_Annex_to_Steele_Store | Construct New 138kV line to new Steele Store substation as part of the reliability project to loop in Steele Store |  | 32853 | 32852 | Planned |  | BRYN |  |  | 2021-09-30 |  | 138 | 10 | 0 | 0 |  | Brazos | Burleson | Tier 4 | 2015-10-09 | 2015-11-06 |  | 32852, 32853 | Y |  |  |  | 4983 | 4576
08TPIT0132 | Melon Creek to Tatton: Build 69 KV Line | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Melon Creek | Tatton | Conceptual | 100 - 0100 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2028 | 2022-03-31 |  | 69 | 9 | 0 | 0 |  | Refugio | Aransas | Tier 2 |  |  |  | 80066, 8410, 8800 | Y | N |  |  | 1175 | 1172
4477 | Austrop to Sandow Double 345-kV Transmission Line Upgrade | Upgrade 33.98-mile Austrop (7040) to Sandow (13429) 345-kV double circuit transmission lines to bundled 959 Suwannee conductor (1921 MVA). |  | Austrop | Sandow | Conceptual |  | LCRATSC/Oncor | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2022-05-31 |  | 345 | 0 | 67.96 | 0 |  | Travis | Milam | Tier 1 |  |  |  | 7040, 13429 | N | N |  |  | 4863 | 4477
4479 | Cut T511 Gilleland Creek to Clear Springs into AEN Dunlap | Cut-In the existing Gilleland Creek (7340) to Clear Springs (7050) T511 345kV transmission line into Austin Energy's Dunlap (9044) substation. |  | Gilleland Creek | Clear Springs | Conceptual |  | LCRATSC/AEN | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2022-05-31 |  | 345 | 4 | 0 | 0 |  | Travis | Guadalupe | Tier 1 |  |  |  | 7050, 7340, 9044 | N | N |  |  | 4868 | 4479
3894 | Fowlerton 345 station and 345/138 autotransformer | Add 345 kV bus and autotransformer |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-06-01 |  | 345 | 0 | 0 | 600 |  | McMullen |  | Tier 4 |  |  |  | 5709, 5901, 80219, 5705 | Y | N |  |  | 4189 | 3894
06TPIT0083 | Del Rio to Buena Vista, reconductor 138 kV line | Reconductor Del Rio 138 kV System |  | DEL RIO | BUENA VISTA | Planned | 775-0960 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 1546 | 2022-06-30 |  | 138 |  | 3 |  |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8690 | N | N |  |  | 3748 | 3540
06TPIT0084 | Hamilton Road to Del Rio reconductor 138 kV line | Reconductor Del Rio 138 kV System | CHANGES | HAMILTON ROAD | DEL RIO | Conceptual | 775-0960 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 1545 | 2022-06-30 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8255 | N | N | NA | NA | 3749 | 3541
07TPIT0083 | Picacho to CFE, construct new 138 kV line | Convert Amistad to CFE Amistad 12.5 kV distribution to 138 kV line | CHANGES | PICACHO | CFE | Conceptual | 775-0960 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 1548 | 2022-06-30 |  | 138 | 8.8 | 0 | 0 |  | Val Verde | Val Verde | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8684 | N | N |  | NA | 3750 | 3542
07TPIT0252 | Greta: Install 1-7.2 MVAR 69 kV Cap Bank | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Greta |  | Conceptual | 100 - 0100 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2045 | 2022-07-31 |  | 69 | 0 | 0 | 0 | 0,7.2 | Refugio |  | Tier 4 |  |  |  | 8409 | Y | N |  |  | 1174 | 1171
15TPIT0008 | Triple R - New Substation (7627) | Build a 138-26.18kV. 40 MVA substation on the GVEC Wilson-Sutherland Springs (T549) 138 kV transmission line |  | Triple R | Wilson/Sutherland Springs | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  | 7627, 5418, 7615 | Y | N |  |  | 4459 | 3367
11TPIT0036 | Caddo - New Substation | Construct a new 69-13.09x26.18-kV 10 MVA substation on GVEC La Vernia-GVEC Nixon 69 kV transmission line |  | Caddo | La Vernia/GVEC Nixon | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 69 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  | 7628, 7614, 7616 | Y | N |  |  | 4460 | 3368
12TPIT0025 | Refugio - Tatton: Rebuild Irreparable 69 kV Line | Construct Melon Creek substation on Airco to Rincon 138 kV line with 138-69 kV, 93 MVA, auto. Build new 69 kV line from Melon Creek to Tatton. Rebuild 69 kV line from Refugio to Tatton. |  | Refugio | Tatton | Conceptual | 100 - 0100 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2027 | 2022-12-30 |  | 69 | 0 | 12.6 | 0 |  | Refugio | Aransas | Tier 4 |  |  |  | 8410, 8800 | Y | N |  |  | 1167 | 1164
13TPIT0133 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 5828, 5857 | Y | N |  |  | 1579 | 1549
13TPIT0149 | Oaks to Loxley | Build new 138 kV 795 ACSR circuit from Oaks to a new AEP switching station Loxley in the Leon Creek to Pleasanton line | Load forecasts have changed since project was RPG approved | Oaks | Loxley | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 138 | 6 | 0 | 0 |  | Atascosa | Atascosa | Tier 3 | 2011-12-16 | 2012-04-25 |  | 5713, 80491 | Y | N |  |  | 2233 | 2161
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits, as recommended in 2013 RTP. |  | Bevo | Carrizo Springs | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 1 | 2012-04-12 | 2012-08-12 | 2012-09-12 | 5871, 8244 | Y | N |  |  | 3809 | 3595
3822 | San Miguel to Sigmor 138 kV line upgrade | Upgrade San Miguel to Sigmor 138 kV line as recommended in 2013 RTP |  | San Miguel | Sigmor | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 138 | 0 | 26.3 | 0 |  | Atascosa | Live Oak | Tier 3 |  |  |  | 5689, 5706, 8404 | Y | N |  |  | 4104 | 3822

## CompletedTPIT020116NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2016
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
4238 | Hutto Switching Station - Round Rock 138 kV Line | Upgrade operating temperature of existing 138 kV line |  | Hutto | Round Rock | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 |  | 2015-01-10 |  | 138 | 0 | 9.1 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 3666, 3668, 3670 | Y | N |  |  | 4611 | 4238
3933 | Aruba 138 kV POI | Convert Aruba POI to 138 kV operation |  | Spraberry Tap | Aruba | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8239 | 2015-01-13 |  | 138 | 6.8 | 0.5 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1220, 1221, 1222, 1337, 1328 | Y | N |  |  | 4235 | 3933
4244 | Odessa North Switch - Odessa Basin Switch 69 kV Line | Upgrade existing line |  | Odessa North Switch | Odessa Basin Switch | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8223 | 2015-01-15 |  | 69 | 0 | 9.4 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1123, 1254 | Y | N |  |  | 4618 | 4244
15TPIT0043D | Fort Bend Area Upgrades | Convert 69kv Rosenberg substation to 138kv and reconfigure existing circuits to create new Ckt.60 Orchard - Rosenberg - Fort Bend. |  | Rosenberg | Orchard/Fort Bend | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 937 | 2015-01-30 | 2015-01-21 | 138 | 0 | 1.5 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 2012-09-14 | 2012-10-29 |  | 44610, 44615, 44010, 44070, 44171, 44230, 44250, 44280, 44290, 44300, 44540, 44580, 44341, 46220 | Y | N |  |  | 4567 | 4208
3580 | Cottulla STEC tap into AEP Line | Cotttulla STEC Substation tap into existing AEP Dilley SS to Reveille 138kV Line. |  | Jardin | Cotulla | Planned | 631 - 0800, 3719 | AEP TCC | Glen Reed 918-599-2664 | 3510 | 2015-01-30 |  | 138 | 0 | 0 | 0 |  | La Salle | La Salle | Tier 4 |  |  |  | 8520, 8610, 8611 | Y | N |  |  | 3794 | 3580
16TPIT0051 | Athens - Forest Grove 138 kV line | Upgrade existing line |  | Athens | Forest Grove | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6018-E | 2015-01-31 |  | 138 | 0 | 16.9 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  | 3131, 3238, 3247, 3248 | Y | N |  |  | 4140 | 3111
15TPIT0043E | Fort Bend Area Upgrades | Remove 69kv facilities at Flewellen substation and convert existing circuit to create new 138kV Ckt.60 Flewellen - Fort Bend. |  | Flewellen | Fort Bend | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 937 | 2015-01-31 | 2015-05-04 | 138 | 0 | 9.3 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 2012-09-14 | 2012-10-29 |  | 44240, 49013, 44250, 44610, 44230 | Y | N |  | Cost included in project 15TPIT0043D. | 4568 | 4208
4088 | McNeil-Dessau: Upgrade Ckt 904 | Reconductor last Mcneil span off MC-DE Ckt 904 to 3000 amps |  | McNeil | Dessau | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2015-02-09 |  | 138 | 0 | 3.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9079, 9193 | Y |  |  |  | 4438 | 4088
09TPIT0117 | Stryker Creek - Dialville 138 kV line | Upgrade existing 138 kV line |  | Stryker Creek | Dialville | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R664-E | 2015-02-15 |  | 138 | 0 | 15.2 | 0 |  | Cherokee | Cherokee | Tier 4 |  |  |  | 3110, 3111, 3160 | Y | N |  |  | 1244 | 1241
3905 | McNeil-Decker Plant: Upgrade Ckt 1013 | Reconductor to 3000 amps as part of DP-MC Corridor Upgrade |  | McNeil | Decker Plant | Under Construction |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2015-02-15 |  | 138 | 0 | 9.56 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9076, 9188 | Y |  |  |  | 4201 | 3905
3985 | Dessau-Sprinkle: Upgrade Ckt 906 | Reconductor to 3000 amps as part of DP-MC Corridor Upgrade |  | Dessau | Sprinkle | Under Construction |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2015-02-15 |  | 138 | 0 | 1.58 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9193, 9271 | Y |  |  |  | 4310 | 3985
14TPIT0059B | Bevo Station and Autotransformer | 138 kV and autotransformer by December 2014. |  | BEVO |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-02-20 | 2015-03-01 | 138 | 0 | 0 | 150 |  | Dimmit |  | Tier 1 | 2012-04-01 | 2012-08-01 | 2012-09-01 | 5871, 78280 | Y | N |  |  | 3440 | 3264
4005 | Salem Substation Upgrade | Install a 345/138/13.2-kV, 672 MVA autotransformer at Salem Substation. |  | Salem |  | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013110 | 2015-02-27 | 2015-02-27 | 345 | 0 | 0 | 672 |  | Washington |  | Tier 4 |  |  |  | 7058, 7289 | Y | N |  | The new 672 MVA autotransformer will be energized from the Salem 345-kV bus and circuit breakers will remain open on the 138-kV side. | 4350 | 4005
14TPIT0003 | Ranchtown - New 138 kV Substation | Loop new 138kV substation into the existing 138kV Helotes to Menger Creek line |  | Ranchtown | Helotes-Menger Creek | Planned | T-0175 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0567 | 2015-02-27 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5358, 5200, 7665 | Y | N |  | There are no transformers associated with this project. There is no transmission line additions associated with this project | 958 | 957
15TPIT0035F | Velasco to West Columbia Upgrades and Conversion to 138kV | Retire Velasco 138/69 kV Auto |  | Velasco |  | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-02-28 |  | 138 | 0 | 0 | -100 |  | Brazoria |  | Tier 3 | 2012-06-14 | 2012-07-24 |  | 49032, 43360, 43370 | Y | N |  | Cost included in project 15TPIT0035A. | 4291 | 2388
15TPIT3405 | New SECO station with load and line | Adds a new 138 kV line to a new load serving substation SECO |  | SECO | Razorback | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-03-02 | 2015-04-01 | 138 | 9.2 | 0 | 0 |  | Medina | Medina | Tier 4 |  |  |  | 5806, 80241 | Y | N |  |  | 3605 | 3405
14TPIT3346 | Clinton Conversion | Convert all Clinton load to 138kV. Convert Clinton 138kV from tap to loop service. | Delay in project schedule | Clinton | Ninth/Anbush | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-03-05 | 2015-01-06 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40350, 40351, 40352, 40235, 41160, 47540 | Y | N |  |  | 3534 | 3346
3968 | Ferguson - Sandy Creek - Pitsburg Transmission Line Upgrade | Increase ground clearance of Ferguson (7126) to Sandy Creek (7127) (approx 9 miles) and Sandy Creek to Pitsburg (7120) (approx 18.9 miles) transmission lines to obtain 221 MVA rating. |  | Ferguson | Sandy Creek - Pitsburg | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014206 | 2015-03-09 | 2015-03-04 | 138 | 0 | 27.9 | 0 |  | Llano | Llano | Tier 4 |  |  |  | 7120, 7126, 7127 | Y | N |  |  | 4289 | 3968
14TPIT0032 | Downing to Mountary | Existing 69 kV line. |  | Downing | Mountary | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 10044 | 2015-03-15 |  | 69 | 0 | 15 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  | 281, 294 | Y | N | 2009-R29 |  | 1065 | 1064
15TPIT0007 | Green Mountain to Stonegate - 138kV 2nd Circuit | Build second 138kV transmission line from Green Mountain to Stonegate on existing transmission structures |  | Green Mountain | Stonegate | Planned | S-0608 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0179 | 2015-03-31 |  | 138 | 11.5 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5093, 5180, 5415 | Y | N |  | There are no transformers associated with this project | 970 | 969
4609 | Flewellen Ckt.09 & 25 Swaps | Swap circuit positions at Flewellen substation for circuits 09 & 25. |  | Flewellen | Brazos Valley/Mason Road | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 937 | 2015-03-31 | 2015-04-01 | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44231, 44100, 44230, 44280, 44450 | Y | N |  |  | 5016 | 4609
3355 | Razorback: Build 138 kV Temp Tap | Construct new Razorback station along the Uvalde to Castroville (STEC) 138 kV line |  | Uvalde |  | Under Construction | 611 - 0779 | ETT | Brent Harris dnlyons@aep.com 918-599-2698 | 3550 | 2015-03-31 |  | 138 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  | 80241, 5083, 8234 | Y |  |  |  | 3544 | 3355
4279 | Mercers Gap 138 kV Switching Station | Construct new switching station |  | Mercers Gap |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R799 | 2015-04-15 |  | 138 | 0 | 0 | 0 |  | Comanche |  | Tier 4 |  |  |  | 1653, 1441, 1654 | Y | N |  |  | 4654 | 4279
4178 | Holt Switching Station Additions | Install 138 kV circuit breaker to create a POI |  | Holt |  | Planned |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8227 | 2015-04-15 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  | 1141 | Y | N |  |  | 4531 | 4178
3882 | GSEC_3882_Add_Horton_Sub |  | NA |  |  | In-Service | NA | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2015-04-15 |  | 138 | 0 | 0 | 0 |  | Jones | Jones | Tier 4 |  |  |  | 60353, 60366 | Y | N |  | Anticipated energization date of 03/2015 | 4172 | 3882
3399 | Bronte: Add 69 kV capacitor banks | Add two 7.2 Mvar capacitor banks at Bronte | IN SERVICE and Cost Update | Bronte |  | In-Service | 629 - 0797 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2588 | 2015-04-16 | 2015-04-16 | 69 | 0 | 0 | 0 | 0,14.4 | Coke |  | Tier 4 |  |  |  | 6414 | Y | N |  |  | 3597 | 3399
15TPIT0061 | Marshall Ford to Lago Vista Transmission Line Upgrade | Upgrade the 6.5 mile Marshall Ford (7356) - Lago Vista (7352) 138-kV transmission line to bundled 795 ACSR, 440 MVA. |  | Marshall Ford | Lago Vista | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013487 | 2015-04-20 | 2015-04-28 | 138 | 0 | 6.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 7352, 7356 | Y | N |  |  | 3406 | 3233
15TPIT0062 | McNeil - Marshall Ford Transmission Line Upgrade | Upgrade and convert the 14.5 mile McNeil (7334) - Marshall Ford (7356) 69-kV transmission line to 138-kV bundled 795 ACSR, 440 MVA. |  | McNeil | Marshall Ford | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013494 | 2015-04-28 | 2013-03-30 | 138 | 0 | 14.5 | 0 |  | Travis | Travis | Tier 3 | 2013-03-01 | 2013-03-30 |  | 78220, 78221, 7334, 7356 | Y | N |  |  | 3407 | 3234
4029 | Upgrade Sealy 10.8 MVAR cap bank to 12.6 MVAR | Upgrade Sealy 10.8 MVAR cap bank to 12.6 MVAR | Delay in project schedule | Sealy |  | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-04-30 |  | 138 | 0 | 0 | 0 | 0,1.8 | Austin |  | Tier 4 |  |  |  | 44640 | Y | N |  |  | 4374 | 4029
4500 | Humble to King Ckt94 | Upgrade Equipment at Humble substation |  | Humble | King | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-04-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 40830, 40911 | Y |  |  |  | 4897 | 4500
15TPIT0042 | FM 237 Yorktown Substation | Replace T1, 138kV-26.18 kV, 30 MVA PWT w/associated bus, structures, panels, etc. |  | FM 237 |  | In-Service |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2015-04-30 |  | 138 | 0 | 0 | 0 |  | DeWitt |  | Tier 4 |  |  |  | 78191 | Y | N |  |  | 3501 | 3320
14TPIT0078 | Advance Capacitor Bank | Install 15 MVAR at Advance substation |  | Advance | Advance | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12011 | 2015-05-01 |  | 69 | 0 | 0 | 0 | 0,15 | Parker |  | Tier 4 |  |  |  | 518 | Y | N |  |  | 2309 | 2236
4266 | Wolfberry: Build 138 kV station & add 138 kV caps | Construct 138 kV substation box bay for customer interconnection, and install two 14.4 Mvar capacitor banks | IN SERVICE and Cost Update | Wolfberry |  | In-Service | 687 - 0857 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2604 | 2015-05-01 | 2015-05-01 | 138 | 0 | 0 | 0 | 0,28.8 | Reagan |  | Tier 4 |  |  |  | 60375, 6535, 6562 | Y | N |  |  | 4639 | 4266
13TPIT0171 | Farmersville West - New Substation | Build a new 138-12.47 kV substation to accommodate load growth in Farmersville. Cut Oncor's Princeton - Royce City 138 kV line into the new substation. |  |  |  | Planned | 16TPIT0005 | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07214 | 2015-05-01 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 37291, 12527 | Y | N |  |  | 2062 | 2010
13TPIT0128 | Danevang Switch to Danevang Substaton Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. |  | Danevang Switch | Danevang Substation | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-05-01 | 2015-08-20 | 69 | 0 | 2.2 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  | 5544, 5548 | Y | N |  |  | 1578 | 1548
4177 | Holt 138 kV Switching Station | Rebuild station as a double bus |  | Holt |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8246 | 2015-05-15 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  | 1141 | Y | N |  |  | 4530 | 4177
3932 | McDonald Road - Garden City East 138 kV Line | Rebuild existing 69 kV line as a double-circuit 138 kV and 69 kV line and convert Garden City East Substation to 138 kV |  | McDonald Road | Garden City East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8238 | 2015-05-15 |  | 138 | 19 | 19 | 0 |  | Howard | Glasscock | Tier 4 |  |  |  | 1225, 1218, 1333, 1352 | Y | N |  |  | 4234 | 3932
11TPIT0015 | Sherry - Grand Prairie - Cedar Hill 138 kV Line | Upgrade existing Sherry - Fish Creek 138 kV line section (south circuit) |  | Sherry | Fish Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5121-E | 2015-05-15 |  | 138 | 0 | 6.2 | 0 |  | Tarrant | Dallas | Tier 4 |  |  |  | 1920, 2258, 2259, 2262, 2421, 12491 | Y | N |  |  | 4141 | 2570
06TPIT0043C | Sherry - Liggett 138 kV line and Liggett - International Air | Rebuild existing Watson - International Airport line section |  | Watson | International Airport | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5042-WA | 2015-05-15 |  | 138 | 0 | 2.8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2124, 2128 | Y | N |  | Sherry - GM section was completed in 2009. | 4211 | 2653
3924 | McDonald Road 138 kV Switching Station | Install 138 kV breakers |  | McDonald Road |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8237 | 2015-05-15 |  | 138 | 0 | 0 | 0 |  | Howard |  | Tier 4 |  |  |  | 1333 | Y |  |  |  | 4224 | 3924
3875 | Dermott Sw. Station - Ennis Creek Tap 138 kV Line | Convert existing 69 kV line to 138 kV line |  | Dermott Sw. Station | Ennis Creek Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R9004 | 2015-05-15 |  | 138 | 0 | 7.5 | 0 |  | Scurry | Scurry | Tier 4 |  |  |  | 11410, 1312, 1313, 1314, 1410, 11306 | Y | N |  |  | 4165 | 3875
3429 | Andrews County South 345/138 kV Switching Station | Construct new switching station with a 345/138 kV autotransformer |  | Andrews County South |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8200-E | 2015-05-15 |  | 345 | 0 | 0 | 600 | -75,0 | Andrews |  | Tier 3 | 2013-11-01 | 2014-08-01 |  | 1157, 1158, 1162, 1150, 1153 | Y | N |  |  | 3768 | 3429
15TPIT0088 | North Andrews #1 and #2 138/69 kV autotransformers | Replace existing autotransformers. This project now includes TPIT project 17TPIT0016. |  | North Andrews |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8149-E | 2015-05-15 |  | 138 | 0 | 0 | 300 |  | Andrews |  | Tier 4 |  |  |  | 1159, 1160 | Y | N |  |  | 3336 | 3165
15TPIT0091 | Midland Airport - Glenhaven 138 kV Line | Upgrade existing line |  | Odessa EHV | Midessa | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8137-E | 2015-05-15 |  | 138 | 0 | 5.5 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 1118, 1120, 1121 | Y | N |  |  | 3338 | 3167
15TPIT0092 | Odessa North - Westover 138 kV Line | Upgrade existing line |  | Odessa North | Westover | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8182-E | 2015-05-15 |  | 138 | 0 | 4.9 | 0 |  | Ector | Ector | Tier 4 |  |  |  | 1122, 1129, 1130 | Y | N |  |  | 3341 | 3170
15TPIT0080 | Big Springs Switch - Big Springs West 138 kV Line | Upgrade existing line |  | Big Springs Switch | Big Springs W | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8139-E | 2015-05-15 |  | 138 | 0 | 7.9 | 0 |  | Howard | Howard | Tier 4 |  |  |  | 1322, 1324 | Y | N |  |  | 3332 | 3161
15TPIT0076 | North Andrews - Means 69 kV line section | Rebuild existing North Andrews - Means 69 kV line section as a double-circuit line with a 69 kV circuit and a 138 kV circuit |  | North Andrews | Means | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8142-E | 2015-05-15 |  | 69 | 2.8 | 2.8 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1160, 1285 | Y | N |  |  | 3328 | 3157
3433 | Midland County Northwest 345/138 kV Switching Station | Construct new switching station with a 345/138 kV autotransformer |  | Midland County Northwest |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8199-E | 2015-05-15 |  | 345 | 0 | 0 | 600 |  | Midland |  | Tier 3 | 2013-11-01 | 2014-08-01 |  | 1183, 1185, 1186, 1018, 1022, 1176, 1182 | Y | N |  |  | 3633 | 3433
11TPIT0097 | Norwood Switch 345/138 kV autotransformer | Replace #1 345/138 kV autotransformer |  | Norwood Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4070-E | 2015-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  | 2410, 2404, 12404 | Y | N |  |  | 3233 | 3064
14TPIT0016 | East Mesquite - Prairie Creek 138 kV line | Upgrade existing line |  | East Mesquite | Prairie Creek | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4069-E | 2015-05-15 |  | 138 | 0 | 2.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2441, 2754, 2756, 2759 | Y | N | 2009-R19 |  | 1825 | 1783
15TPIT0084 | Commerce 138/69 kV autotransformer | Replace existing autotransformer |  | Commerce |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R941-E | 2015-05-15 |  | 138 | 0 | 0 | 100 |  | Hunt |  | Tier 4 |  |  |  | 1820, 1821, 11820 | Y | N |  |  | 3385 | 3212
4289 | City View 138 kV terminal equipment replacement | Replace terminal equipment in the Fisher Road - City View - Pleasant Vally 138 kV Line |  | City View |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R967 | 2015-05-15 |  | 138 | 0 | 0 | 0 |  | Wichita |  | Tier 4 |  |  |  | 1426, 1483, 17006, 17005, 17007 | Y | N |  |  | 4668 | 4289
15TPIT0095 | Tyler Northwest 138/69 kV autotransformer | Replace existing autotransformer |  | Tyler Northwest |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6020 | 2015-05-15 |  | 138 | 0 | 0 | 100 |  | Smith | Smith | Tier 4 |  |  |  | 3141, 3142, 3157 | Y | N |  |  | 3254 | 3085
3456 | Morgan Creek 138/69 kV autotransformer | Replace existing autotransformer |  | Morgan Creek Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8151-E | 2015-05-15 |  | 138 | 0 | 0 | 150 |  | Mitchell |  | Tier 4 |  |  |  | 1032, 1033, 11035 | Y | N |  |  | 3659 | 3456
14TPIT0092 | Temple Switch - Bell County East 345 kV line | Upgrade existing 345 kV line |  | Temple Switch | Bell County East | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R765 | 2015-05-15 |  | 345 | 0 | 10 | 0 |  | Bell | Bell | Tier 4 |  |  |  | 13434, 13435, 3414, 3687, 13429, 39950 | Y | N |  |  | 4605 | 2375
3977 | Cobb 345 kV Switching Station | Construct 345 kV switching station |  | Cobb Switch |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R949 | 2015-05-15 |  | 345 | 0 | 0 | 0 |  | Clay |  | Tier 4 |  |  |  | 1458, 1422, 1429 | Y | N |  |  | 4302 | 3977
4101 | China Grove terminal 138 kV equipment replacement | Replace terminal equipment on line to Bluff Creek |  | China Grove |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R9010 | 2015-05-15 |  | 138 | 0 | 0 | 0 |  | Mitchell |  | Tier 4 |  |  |  | 1309, 1318 | Y | N |  |  | 4450 | 4101
10TPIT0001 | Trumbo - New 138 kV Substation | Loop new 138 kV substation into the existing 138kV Leon Creek to Pleasanton Rd-Loxley (AEP) line | Accelarated by Disribution Planning | Trumbo | Leon Creek-Pleasanton Rd | Planned | T-0082 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0181 | 2015-05-21 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5429, 5260, 8203 | Y | N |  | There are no transformers associated with this project | 976 | 975
14TPIT0127 | Purgatory Road Substation Addition | Construct the new Purgatory Road Substation (7489) on the PEC Sattler (7488) - Hunter (7491) 138-kV transmission line |  | Sattler | Hunter | In-Service |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2015-05-22 |  | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 |  |  |  | 7489, 7488, 7491 | Y | N |  |  | 3205 | 3036
14TPIT0063 | Munday to BEC Munday: Rebuild 69 kV line | Rebuild Munday to BEC Munday 69 kV line with 959.6 ACSR | IN SERVICE | Munday | BEC Munday | Under Construction | 568 - 0742 | AEP TNC | Aaron Schwerman myturner@aep.com 918-599-2437 | 2572 | 2015-05-26 | 2015-05-26 | 69 | 0 | 2.4 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 764, 6107 | Y | N |  |  | 1847 | 1804
3888A | Ranger 138kV Substation | Construct service to new 138kV RANGER customer-owned substation. Loop through Ckt.84 Channelview - DEPOT. |  | Ranger | Channelview/Depot | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 55 | 2015-05-29 | 2015-05-14 | 138 | 0.2 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40380, 40280, 40282, 40410 | Y | N |  |  | 4178 | 3888
3888B | Ranger 138kV Substation | Loop existing Ckt.84 Crystal Bay to DOWLAP into SR Bertron. |  | SR Bertron | Crystal Bay/DOWLAP | Planned |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 55 | 2015-05-30 | 2015-05-15 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40290, 40490, 41400, 41405 | Y | N |  | Project is associated with the addition of Ranger 138kV substation. | 4179 | 3888
4557A | Brazoria-Old Ocean Construction and Reconfigurations | Construction of Sweeny 138kV Substation. Rebuild Brazoria-Sweeny line to 138 kV. |  | 39600 | 39700 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2015-05-30 |  | 138 | 0 | 7.09 | 0 |  | Brazoria | Brazoria | Tier 3 | 2015-01-16 |  |  | 39700, 39600 | Y |  |  |  | 4962 | 4557
15TPIT0032 | Fort Sam to Tenth Street - 138 kV Transmission Line Rebuild | Rebuild approximately three of the five circuit miles of 138 kV transmission of the Ft. Sam to Tenth Street transmission circuit from Tenth Street to Coliseum. |  | Fort Sam | Tenth St | Planned | S-0744 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0188 | 2015-05-31 |  | 138 | 0 | 3 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5160, 5420 | Y | N |  | There are no transformers associated with this project | 2381 | 2305
15TPIT3391 | Bellaire Autotransformer Upgrade | Replace existing 600MVA Bellaire autotransformer A4 with 800MVA autotransformer. |  | Bellaire |  | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 | 2015-04-24 | 345 | 0 | 0 | 200 |  | Harris |  | Tier 4 |  |  |  | 47000, 47010, 49002 | Y | N |  |  | 3589 | 3391
4007 | Pasadena to Spencer tap Ckt.06 Upgrades | Upgrade 138 kV Ckt.06 Pasadena to Spencer tap to increase thermal ratings. |  | Pasadena | Spencer/College | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1024 | 2015-05-31 | 2015-03-15 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42550, 43040, 43271 | Y | N |  |  | 4352 | 4007
4147 | WA Parish to Sienna Ckt.02 Substation Upgrade | Upgrade substation equipment at WA Parish to increase thermal ratings for 138kV Ckt.02. |  | WA Parish | Sienna | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1129 | 2015-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  | 44010, 44651 | Y | N |  |  | 4492 | 4147
14TPIT3390 | Alvin Auto Removal | Disconnect Alvin Autotransformer A1. | Delay in project schedule | Alvin Auto |  | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 | 2015-07-01 | 138 | 0 | 0 | -83 |  | Brazoria |  | Tier 4 |  |  |  | 42130, 42140, 42820, 48001, 49086, 42080, 42600, 42651, 43260, 43505 | Y | N |  |  | 3588 | 3390
16TPIT0019 | Lobo 138 kV station: install 3 additional CB | Construct 345 kV circuit from Lobo to Molina energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Molina 138kV stations. |  | LOBO |  | Under Construction | 206 - 0288 | AEP TCC | KENEATH 'RICH' HALEY DNLYONS@AEP.COM 918-599-2698 | 634 | 2015-05-31 |  | 138 |  |  |  |  | Webb |  | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 80221 | Y | N |  |  | 3727 | 3520
16TPIT0027 | Beeville to Sinton: Rebuild 69 kV Line | Rebuild Beeville - Sinton 69kV Line for future 138 kV operation |  | BEEVILLE | SINTON | Under Construction | 579-0737 | AEP TCC | Terry Weeks DNLYONS@AEP.COM 918-599-2698 | 3465 | 2015-05-31 |  | 69 | 0 | 29.4 | 0 |  | Bee | San Patricio | Tier 1 | 2012-08-31 | 2012-12-27 | 2013-04-05 | 8198, 8405, 8904, 8413 | Y | N |  |  | 3717 | 3510
15TPIT0053 | Molina to Zapata: Cut-In | Construct 345 kV circuit from Lobo to Molina energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Molina 138kV stations. |  | MOLINA | ZAPATA | Under Construction | 206 - 0288 | AEP TCC | KENNETH 'RICH' HALEY DNLYONS@AEP.COM 918-599-2698 | 3487 | 2015-05-31 |  | 138 | 2 |  | 0 |  | Webb | Webb | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 8299 | Y | N |  | NA | 3703 | 3496
3886 | Ckt.75 Rothwood Loop | Loop Ckt.75 King - Kuykendahl tap into Rothwood 345kV substation. |  | Rothwood | King/Kuykendal | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 989 | 2015-05-31 | 2015-07-02 | 345 | 0.1 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 40600, 40900, 45971, 45972, 44645, 46290, 46500 | Y | N |  |  | 4176 | 3886
15TPIT0052 | Molina to Wormser: Cut-In | Construct 345 kV circuit from Lobo to Molina energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Molina 138kV stations. |  | MOLINA | WORMSER | Under Construction | 206 - 0288 | AEP TCC | KENNETH 'RICH' HALEY DNLYONS@AEP.COM 918-599-2698 | 3486 | 2015-05-31 |  | 138 | 0.5 | 0 | 0 |  | Webb | Webb | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 8295 | Y | N |  | NA | 3704 | 3497
11TPIT0001 | Lobo to Molina, build 345 kV circuit energized at 138kV | Construct 345 kV circuit from Lobo to Molina energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and Molina 138kV stations. |  | Lobo | Rio Bravo | Under Construction | 206 - 0288 | ETT | Kenneth 'Rich' Haley DNLYONS@AEP.COM 918-599-2698 | 880 | 2015-05-31 |  | 138 | 26 | 0 | 0 |  | Webb | Webb | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 80230, 8295, 8646, 80221 | Y | N |  | NA | 1248 | 1245
3823 | Stewart Capacitor Bank | Install 7.2MVAR capacitor bank at Stewart substation. |  | Stewart |  | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 859 | 2015-05-31 | 2015-03-15 | 138 | 0 | 0 | 0 | 0,7.2 | Brazoria |  | Tier 4 |  |  |  | 43290 | Y | N |  |  | 4105 | 3823
16TPIT0020 | Constrcut: Molina 138 kV Station | Construct 345 kV circuit from Lobo to Molina energized at 138 kV on the open position of the Lobo to North Edinburg 345kV line. Upgrade Lobo and build Molina 138kV stations. |  | MOLINA |  | Under Construction | 206-0288 | AEP TCC | Kenneth 'Rich' Haley DNLYONS@AEP.COM 918-599-2698 | 900 | 2015-05-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 3 | 2012-03-12 | 2012-04-02 | 2012-04-27 | 80230 | Y | N |  | NA | 3673 | 3468
4399 | Crestonio to Lobo SS: Raise four 138 kV structures | Increase the MOT rating of the Lobo SS to Falfurrias 138kV line by raising 49 structures |  | Crestonio | Lobo SS | Planned | 702 - 0872 | AEP TCC | Mike Tallon dnlyons@aep.com 918-599-2698 | 3549 | 2015-05-31 |  | 138 | 0 | 32.1 | 0 |  | Duval | Webb | Tier 4 |  |  |  | 8297, 80221, 8695, 80439 | Y | N |  |  | 4778 | 4399
4162 | BARBUR Replacement 138kV Substation ALKANE | Replace existing customer-owned BARBUR substation with another nearby substation. |  | ALKANE | LaPorte/Morgans Point | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 | 2015-08-15 | 138 | 0.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40140, 40160, 40941, 41100 | Y | N |  |  | 4513 | 4162
4427 | Blodgett to Teco Ckt 37 Thermal Uprate | Upgrade 138kV Ckt.37 Blodgett to Teco to increase thermal ratings. |  | Blodgett | Teco | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 | 2015-04-20 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 47430, 47521 | Y | N |  |  | 4811 | 4427
14TPIT3257 | Smithers to Bellaire Ckt.98 | Upgrade 138kV Ckt.98 Smithers to Bellaire to increase thermal ratings. |  | Smithers | Bellaire | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-05-31 | 2015-01-05 | 345 | 0 | 25.4 | 0 |  | Fort Bend | Harris | Tier 4 |  |  |  | 44005, 44010, 44650, 47160, 44342, 44652, 47000, 47300, 47580 | Y | N |  |  | 3431 | 3257
14TPIT0068 | Future 69kV upgrades & North Denton Auto Upgrade |  |  |  |  | Planned |  | DME | Chuck Sears 940-349-7111 |  | 2015-06-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  | 905, 915, 912, 985 | Y |  |  |  | 1425 | 1424
15TPIT0023 | Seaton Auto | Upgrade 138-69 kV auto to 100 MVA |  | Seaton | Seaton | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 11036 | 2015-06-01 |  | 138 | 0 | 0 | 100 |  | Bell |  | Tier 4 |  |  |  | 131, 130 | Y | N |  |  | 1188 | 1185
4137 | DME_BBrae_NLakes |  |  | Bonnie Brae | North Lakes | Planned | N/A | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2015-06-01 |  | 69 | 0 | 1.2 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 905, 915 | Y | N | N/A |  | 4482 | 4137
4136 | DME_Pockrus_Spencer |  |  | Pockrus | Spencer | Planned | N/A | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2015-06-01 |  | 138 | 3.8 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 917, 982 | Y | N | N/A |  | 4481 | 4136
3417 | North Calliham Capacitor | Adds 9.6 MVAR capacitor to North Calliham |  | North Calliham |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-06-01 | 2015-09-30 | 69 | 0 | 0 | 0 | 0,9.6 | McMullen |  | Tier 4 |  |  |  | 5698 | Y | N |  |  | 3617 | 3417
4322 | Add McKinney Station - Tap Woodrow - Kingsrow line |  |  | Woodrow | Kingsrow | Planned |  | DME | Chuck Sears 940-349-7111 |  | 2015-06-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 907, 901, 909 | Y | N |  |  | 4699 | 4322
4077 |  |  |  | Katz |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 14006 | 2015-06-01 |  | 69 | 0 | 0 | 0 | 0,16 | King |  | Tier 4 |  |  |  | 774 | Y |  |  |  | 4427 | 4077
3265 | Paredes switch new switching station for wind farm | A new swtiching station in the E Rio Hondo to Central 138 kV line |  | Paredes |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-06-01 | 2015-08-01 | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  | 5761, 5764, 5766 | Y | N |  |  | 3441 | 3265
4012 | Daffin Gin-Austrop: Upgrade Ckt 974 | Reconductor to 3000 amps as part of AU-DP Corridor Upgrade |  | Daffin Gin | Austrop | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2015-06-01 |  | 138 | 0 | 9.16 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9184, 9328 | Y |  |  |  | 4357 | 4012
4745 | Marshall Ford 138kV Breaker Replacement and Wave Trap upgrad | Replace GCB-8020, GCB-9180, and GCB-9070 with 63kA breakers and upgrade wave trap on T315. |  | Marshall Ford |  | In-Service |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2015-06-01 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  | 7356, 7505 | Y | N |  |  | 5165 | 4745
3267A | Rebuild ERioHondoTo Paredes to Central Avenue 138 kV line | Rebuild Paredes Switch to East Rio Hondo |  | E Rio Hondo | Paredes Switch | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-06-02 | 2015-05-30 | 138 | 0 | 6 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  | 5761, 5764 | Y | N |  |  | 3443 | 3267
15TPIT0060 | Convert KenedySw - Guadalupe (Cuero) to 138kV | Convert the 42.3 miles Kenedy Switch (8186) - Guadalupe (7253) 69-kV line to 138-kV line, 220 MVA. Guadalupe is a new substation to be built near Cuero Hydro (78189). |  | Kenedy Switch | Guadalupe | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013403 | 2015-06-03 | 2015-06-29 | 138 | 0 | 42.3 | 0 |  | Karnes | DeWitt | Tier 1 | 2013-02-15 | 2013-02-15 | 2013-03-31 | 78188 | Y | N |  | Coordinate with AEP Coordinate with GVEC | 3968 | 3724
4436 | Wynn Joyce Phase2 Upgrade Project | Upgrade Wynn Joyce to a 138kV ring substation with 3 lines out to Miller, Rosehill, and Ben Davis substations |  | Wynn Joyce | Miller, Rosehill, Ben Davis | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2015-06-24 |  | 138 | 0 | 11.5 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 813, 817, 824, 968 | Y | N |  |  | 4822 | 4436
4001 | Cuero Hydro to Hochheim Transmission Line Overhaul | Upgrade the Cuero Hydro (78189) to Hochheim (78577) 69kV transmission line to 795 ACSR Drake (111 MVA), 138kV capable. |  | Cuero Hydro | Hochheim | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013683 | 2015-06-24 | 2015-06-26 | 69 | 0 | 10.67 | 0 |  | DeWitt | DeWitt | Tier 4 |  |  |  | 8578, 78189, 78577 | Y | N |  |  | 4327 | 4001
3851 | Russek Street: Add 138 kV capacitor banks | Add one 14.4 Mvar and two 7.2 Mvar capacitor banks at Russek Street | IN SERVICE | Russek Street |  | In-Service | 672 - 0841 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2807 | 2015-06-28 | 2015-06-28 | 138 | 0 | 0 | 0 | 0,28.8 | Reagan |  | Tier 4 |  |  |  | 6517 | Y | N |  |  | 4135 | 3851
3850 | Russek Street: Build 138 kV station | Construct the new Russek Street station along the Big Lake to Twin Buttes 138 kV line | IN SERVICE | Russek Street |  | In-Service | 673 - 0842 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2808 | 2015-06-28 | 2015-06-28 | 138 | 0 | 0 | 0 |  | Reagan |  | Tier 4 |  |  |  | 6517, 6535, 6559 | Y | N |  |  | 4134 | 3850
4013 | Hindes Temporary Tap: STEC Interconnect | Hindes Temporary Tap: STEC Interconnect |  | DILLEY SS | SAN MIGUEL | Planned | 682 - 0837 | AEP TCC | Mike Tallon dnlyons@aep.com 918-599-2698 | 3539 | 2015-06-30 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 88215, 5704, 8212 | Y | N |  |  | 4358 | 4013
15TPIT0068 | Add Hecker 138kV substation | Add Hecker 138kV substation | Changed Dollars | Dupont SS | Whitepoint SS | Planned | 608 - 0776 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3488 | 2015-06-30 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  | 8565, 8422, 8961 | Y | N |  |  | 3268 | 3099
14TPIT0140 | Bunsen: Build new four breaker 138 kV station | Construct new Bunsen station along the Lon Hill to Kingsville 138 kV line and build 0.8 miles of double circuit 138 kV line with 959.6 ACSS/TW from Bunsen to new customer station |  | Lon Hill | Kingsville | Under Construction | 610 - 0778 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3493 | 2015-06-30 |  | 138 | 1.6 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8459, 8452, 8518 | Y |  |  |  | 3221 | 3052
3680 | Decker-Exxon Ckt83 Thermal Uprate | Upgrade 138kV Ckt.83 Decker to Exxon to increase thermal ratings. |  | Decker | Exxon | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1055 | 2015-07-01 | 2015-07-01 | 138 | 0 | 1 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40430, 40570 | Y | N |  |  | 3918 | 3680
3950B | TH Wharton to White Oak Ckt.71 | Upgrade 345kV Ckt.71 Addicks to White Oak to increase thermal ratings. (Transmission upgrades only.) |  | Addicks | White Oak | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-07-01 | 2015-07-01 | 345 | 0 | 9.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45600, 46600 | Y | N |  |  | 4270 | 3950
4129 | SLU_GlassRanch_addition |  |  | Sales Ranch | Glass Ranch | Planned | N/A | SLU | Brad Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2015-07-01 |  | 138 | 10 | 0 | 0 | 0,48 | Martin | Martin | Tier 4 |  |  |  | 79507, 79508, 79558, 79510, 79616, 79550, 79618 | Y | N | N/A |  | 4474 | 4129
14TPIT0121 | Channelview to CONIAL Ckt.84 Thermal Uprate | Upgrade 138kV Ckt.84 Channelview to CONIAL to increase thermal ratings. |  | Channelview | CONIAL | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1055 | 2015-07-01 | 2015-07-01 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41675, 40280, 40330, 40370, 40580, 40590, 40610, 40611, 41171, 41260, 41670, 40720, 40780, 41010, 41172, 41250, 41530, 41712 | Y | N |  |  | 3048 | 2874
4132 | SLU_TelephoneRd_addition |  |  | Telephone Road | Amoco Tap | Planned | N/A | SLU | Brad Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2015-07-01 |  | 345 | 32.8 | 0 | 500 |  | Midland | Andrews | Tier 2 | 2013-12-20 | 2014-07-23 |  | 79630, 79650, 1158, 1185, 79618, 904532 | Y | N | N/A |  | 4477 | 4132
4131 | SLU_Pemkiff_addition |  |  | Pemkiff | Upton | Planned | N/A | SLU | Brad Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2015-07-01 |  | 138 | 0.3 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  | 79555, 1210, 79612, 79614 | Y | N | N/A |  | 4476 | 4131
3950A | TH Wharton to White Oak Ckt.71 | Upgrade 345kV Ckt.71 TH Wharton to Addicks to increase thermal ratings. (Transmission upgrades only.) |  | TH Wharton | Addicks | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-07-01 | 2015-07-01 | 345 | 0 | 9.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 45500, 45600 | Y | N |  |  | 4269 | 3950
14TPIT0031 | CPSE_New_Cagnon_4th_Auto_2-Winding | Install one 600 MVA autotransmformer |  |  |  | Planned | T-0176 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0588 | 2015-07-02 |  | 345 | 0 | 0 | 600 |  | Bexar | Bexar | Tier 4 |  |  |  |  | Y | N |  |  | 5025 | 4617
14TPIT0064 | West Yates to Dinny: Rebuild 69 kV line | Rebuild West Yates to Dinny (formerly Discovery Canyon) 69 kV line with 959.6 ACSS/TW | IN SERVICE | West Yates | Dinny | In-Service | 570 - 0744 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2574 | 2015-07-08 | 2015-07-08 | 69 | 0 | 2.28 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  | 6574, 6576, 6581, 60370, 60371, 60372, 6556, 6572, 6575, 6580, 6585 | Y | N |  |  | 4180 | 1803
3361 | Magill Station: New 138kV Station for STEC Interconnect | Build New 138kV Station to Accommodate STEC Interconnection to serve customer load |  | Bay City | Lane City | Planned | 609 - 0777 | AEP TCC | Dave Goetz dnlyons@aep.com 918-599-2698 | 3496 | 2015-07-15 |  | 138 | 0 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  | 8111, 8113, 8127 | Y | N |  |  | 3556 | 3361
3406 | Tenaris 138 kV station | Connects new load to new Magill station with 138 kV line |  | Magill | Tenaris | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-07-16 | 2015-08-31 | 138 | 4.5 | 4.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  | 5562, 5554, 5556, 5560, 8111 | Y | N |  |  | 3606 | 3406
3687 | Estes: Build 138 kV station | Construct new Estes station along the South Abilene to Putnam 138 kV line | IN SERVICE and Cost Update | Estes |  | In-Service | 655 - 0824 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 1819 | 2015-07-17 | 2015-07-17 | 138 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  | 60365, 6309, 6773 | Y | N |  |  | 3928 | 3687
14TPIT0065 | Rusthill: Build 138 kV station | Build new 138 kV four breaker ring bus station, Rusthill, reterminate the 138 kV lines from Concho into Rusthill and add 138/69 kV autotransformer capacity | IN SERVICE | Rusthill |  | In-Service | 567 - 0741 | AEP TNC | Eric Scott myturner@aep.com 918-599-2437 | 2571 | 2015-07-24 | 2015-07-24 | 138 | 0 | 0 | 130 |  | Tom Green |  | Tier 4 |  |  |  | 61010, 61011, 6448, 6449, 6450, 6452, 6453 | Y | N |  |  | 3948 | 1795
3040A | WA Parish to Fort Bend Ckt.09 | Upgrade 138kV Ckt.09 Fort Bend to Reading to increase thermal ratings. | Delay in Project Schedule | Fort Bend | Reading | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1055 | 2015-07-30 |  | 138 | 0 | 2.6 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44280, 44570 | Y | N |  |  | 4577 | 3040
4256 | Santa Rita: Build 69 kV station | Construct new 69 kV in and out substation off the Big Lake to McCamey line, and demolish Texon | IN SERVICE | Santa Rita |  | In-Service | 691 - 0861 | AEP TNC | Bill Clarke myturner@aep.com 918-599-2437 | 2608 | 2015-07-31 | 2015-08-09 | 69 | 0 | 0 | 0 |  | Reagan |  | Tier 4 |  |  |  | 6504, 6538, 6541, 6555 | Y | N |  |  | 4627 | 4256
3040C | WA Parish to Fort Bend Ckt.09 | Upgrade 138kV Ckt.09 Crabb River Road to WA Parish to increase thermal ratings. | Delay in Project Schedule | Crabb River Road | WA Parish | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 1055 | 2015-07-31 | 2015-03-16 | 138 | 0 | 9.5 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  | 44010, 44170, 44172 | Y | N |  |  | 3896 | 3040
4182B | Alexander Island 138kV Conversion | Convert Alexander Island from double-tap 69kv to double-tap 138kV service. Tap from Ckt.84 DOWLAP - SR Bertron (reconfigured in 2015). |  | Alexander Island | DOWLAP/SR Bertron | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-07-31 | 2015-06-30 | 138 | 0.1 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40082, 41392, 40480, 40490, 41090, 41383, 41400, 40290, 41405, 41410, 41480, 41490 | Y | N |  |  | 4596 | 4182
4182A | Alexander Island 138kV Conversion | Convert Alexander Island from double-tap 69kv to double-tap 138kV service. Tap existing Ckt.87 SR Bertron to ARITEK. |  | Alexander Island | SR Bertron/AIRTEK | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-07-31 | 2015-06-30 | 138 | 0.2 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40081, 41391, 40120, 41410, 41400, 41415 | Y | N |  |  | 4537 | 4182
3427 | Add Whiteriver Station |  |  | White River | White River | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2015-08-01 |  | 345 | 0 | 0 | 0 |  | Floyd | Floyd | CREZ |  |  |  | 79505, 59904, 79503 | Y | N |  |  | 3627 | 3427
4464A | Comal to Loop 337 Transmission Line Upgrade | Alter CTs to 2000:5 to remove CTs as MLSE elements. Utilize dynamic switch rating for Winter loading. | Switches may be dynamically rated during Winter peak conditions. | Comal | GPI Switchyard | In-Service |  | NBU | Greg Baumbach gbaumbach@nbutexas.com 830-629-8441 |  | 2015-08-01 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  | 7176, 7456, 7459 | Y | N |  |  | 5205 | 4464
3674 | Puncher: Build 69 kV station and add capacitor bank | Puncher: Build 69 kV station and add one 7.2 Mvar capacitor bank | IN SERVICE, Project Title, Project Description, and Cost Update | Puncher |  | In-Service | 647 - 0816 | AEP TNC | Michael Tallon myturner@aep.com 918-599-2437 | 1811 | 2015-08-21 | 2015-08-21 | 69 | 0 | 0 | 0 | 0,7.2 | Mason |  | Tier 4 |  |  |  | 6407 | Y | N |  |  | 3911 | 3674
4463 | Kendall Bus Tie Configuration | Close the Kendall bus tie between Kendall MB (7150) and (7152) |  | Kendall |  | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2015-08-27 | 2015-08-27 | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 |  |  |  | 7150, 7152 | Y | N |  |  | 4849 | 4463
3964 | Johnson City Cap Bank Addition | Add two (2) 69-kV 7.8 MVAR capacitor banks at PEC Johnson City (7516) substation. |  | Johnson City |  | In-Service |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2015-09-01 |  | 69 | 0 | 0 | 0 | 0,15.6 | Blanco |  | Tier 4 |  |  |  | 7516 | Y | N |  |  | 4285 | 3964
4494 | AEP_4494_Koch Upriver | Add 138kV breakers at Koch Upriver 138kV Substation |  | Koch Upriver | Koch Upriver | In-Service | 693 - 0863 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3540 | 2015-09-01 | 2015-09-01 | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  | 8467 | Y | N |  |  | 4888 | 4494
12TPIT0081 | 36th St - New 138kV Substation | Loop new 138kV substation into existing 138kV Merida to Medina Base line and replace exiting Kelly Field #3 138kV substation | Delayed due to Budget Constraints | Merida | Medina Base | Planned | T-0161 | CPS | Hector Torres HVTorres@cpsenergy.com 210-353-2404 | S-0578 | 2015-09-02 | 2015-10-01 | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5245, 5305, 5310, 5427 | Y | N |  | There are no transformers associated with this project | 952 | 951
12TPIT0143C | Danevang Switch to El Campo Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. |  | Danevang Switch | Plainview | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-09-09 | 2015-09-30 | 69 | 0 | 4.89 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  | 5540, 5544 | Y | N |  |  | 1549 | 1535
13TPIT0047 | Parkway to EC Mornhinweg | Construct a new 138 kV 795 ACSR transmission line between the new EC Mornhinweg substation (7463) and the Parkway substation (7611). |  | Parkway | EC Mornhinweg | In-Service | 13TPIT0066 | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1010634 | 2015-09-14 | 2015-06-17 | 138 | 8 | 0 | 0 |  | Comal | Guadalupe | Tier 2 | 2009-02-01 | 2009-06-15 |  | 7463, 7611 | Y | N |  |  | 1004 | 1003
3271 | Comal Street - New 138kV Substation | Loop new 138kV substation into the existing 138kV Ball Park to Olmos. |  | Comal St | Ball Park-Olmos | Planned | T-0216 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0721 | 2015-09-30 | 2015-08-26 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5096, 5011, 5325 | Y | N |  | There are no transformers associated with this project | 3447 | 3271
4603 | Replace both Heights Autos. | Upgrading both existing Heights 69/138 kV Autos. |  | TNHEIGHTS_1 | TNHEIGHTS_0 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE02315 | 2015-10-01 |  | 138 | 0 | 0 | 200 |  | Galveston | Galveston | Tier 4 |  |  |  | 38770, 38740 | Y |  |  |  | 5010 | 4603
4557C | Brazoria-Old Ocean Construction and Reconfigurations | Construction of FM524 Sub. Build Sweeny-FM524 138 kV and FM524-Old Ocean 69 kV lines. Remove Sweeny 69 kV Sub. |  | 39700 | 39750 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2015-10-01 |  | 138 | 3.85 | 0 | 167 |  | Brazoria | Brazoria | Tier 3 | 2015-01-16 |  |  | 39701, 39703, 39704, 39700, 39750 | Y |  |  |  | 5036 | 4557
4557B | Brazoria-Old Ocean Construction and Reconfigurations | Construct new 0.19 miles 795 ACSS to existing 0.81 miles of bundled 636 ACSR for line G69EZ 69kV. Convert to 138kV and reconfigure from Old Ocean 69 kV to FMF524 138 kV. |  | 39703 | 110505 | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2015-10-01 |  | 138 | 0.19 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 2015-01-16 |  |  | 39703, 39750, 110505, 110507 | Y |  |  |  | 4963 | 4557
4536 | Tap 138kV East Stiles - Stiles line to create Rocky Rd Stati |  |  | East Stiles | Stiles | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2015-10-01 |  | 138 | 0 | 0 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 79562, 79614, 79623 | Y | N |  |  | 4938 | 4536
4076 |  |  |  | Stephenville |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 13002 | 2015-10-01 |  | 138 | 0 | 0 | 60 |  | Erath |  | Tier 4 |  |  |  | 299, 295 | Y |  |  |  | 4426 | 4076
4133 | SLU_Vealmoor_addition |  |  | Vealmoor | Longdraw | Planned | N/A | SLU | Brad Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2015-10-01 |  | 345 | 11.4 | 0 | 450 |  | Borden | Borden | Tier 2 | 2013-12-20 | 2014-07-23 |  | 79640, 59900, 79600 | Y | N | N/A |  | 4478 | 4133
4539 | Tap 138kV Sales Ranch - Grady line to create Coronado statio |  |  | Sales Ranch | Grady | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2015-10-01 |  | 138 | 0 | 0 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79564, 79508, 79550 | Y | N |  |  | 4941 | 4539
14TPIT0044 | Helotes to Hill Country - 138 kV Substation Equipment Upgrad | Upgrade terminals at Helotes and Hill Country to ensure a 2420 A rating and remove existing MLSE on Helotes to Hill Country 138 kV transmission line |  | Helotes | Hill Country | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0651 | 2015-10-10 | 2015-10-08 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5200, 5210, 5461 | Y | N |  | There are no transformers associated with this project | 964 | 963
4704 | Rock Island Substation Expansion for Generator Interconnect | Extend 138 KV Bus to add two 138 KV taps for Sky Global Power One Interconnect |  | Rock Island |  | In-Service | 16INR0057 - Sky Global Power One - 51 MW Generator | SBEC | Don Roberts droberts@sbec.org | WO#14-5367:WO#15-6067 | 2015-10-15 | 2015-10-22 | 138 | 0 | 0 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  | 7640 | Y | N |  |  | 5162 | 4704
12TPIT0143B | Danevang Switch to El Campo Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. |  | Industrial Park | Plainview | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-10-21 | 2015-11-10 | 69 | 0 | 5.3 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  | 5540, 5543 | Y | N |  | cost in last phase of project | 1548 | 1535
13TPIT0148B | Cotulla 138 kV bus load and auto | Second phase installs 138 kV breakers and autotransformer in early 2016. |  | Cotulla |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-10-30 | 2015-02-14 | 69 | 0 | 0 | 150 |  | La Salle |  | Tier 1 | 2012-04-16 | 2012-08-30 | 2012-09-18 | 5876, 8520 | Y | N |  |  | 3650 | 3449
17TPIT0009 | East Munday: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at East Munday | IN-SERVICE and Cost Update | East Munday |  | In-Service | 588 - 0746 | AEP TNC | Aaron Schwerman myturner@aep.com 918-599-2437 | 2580 | 2015-10-30 | 2015-10-30 | 69 | 0 | 0 | 90 |  | Knox |  | Tier 4 |  |  |  | 6108, 6110 | Y | N |  |  | 3400 | 3227
15TPIT0029 | CMC Tap to CMC (SMI) 138kV Transmission Line | Build 2 miles of new double ckt 138kV t-line loop, 1192 ACSR between CMC Tap and CMC (SMI) substation. Add terminals at CMC plant substation |  | CMC Tap | CMC (SMI) | In-Service |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2015-10-30 |  | 138 | 2.2 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  | 7602, 7604, 7606 | Y | N |  |  | 3403 | 3230
3910 | Lobo: Replace 138/69 kV autotransformer | Add 138/69 kV autotransformer capacity at Lobo |  | Lobo |  | Planned | 681 - 0850 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 2599 | 2015-10-31 | 2015-12-16 | 138 | 0 | 0 | 91 |  | Webb |  | Tier 4 |  |  |  | 80222, 80221 | Y | N |  |  | 4208 | 3910
4773A | Smithville to Rosanky Rebuild | Part 1: Upgrade Structures on Smithville to Rosanky Transmission Line |  | Smithville | Rosanky | In-Service |  | BBEC | Thomas Ellis thomas.ellis@bluebonnet.coop |  | 2015-11-10 | 2015-11-10 | 69 | 0 | 5.4 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  | 7315, 7558 | Y | N |  |  | 5196 | 4773
15TPIT0059 | Avery Ranch - Jollyville Transmission Line Upgrade | Upgrade the 1.1 mile Avery Ranch (7534) - Jollyville (9223) 138-kV transmission line to bundled 959.6 ACSS/TW Suwanee, 660MVA. |  | Avery Ranch | Jollyville | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1013396 | 2015-11-11 | 2015-11-25 | 138 | 0 | 1.1 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  | 7534, 9223 | Y | N |  |  | 3404 | 3231
08TPIT0172 | Gunsight 138 kV Switching Station | Construct new switching station to connect a new wind farm | Construction schedule change | Gunsight Switching Station |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R829-WA | 2015-11-15 |  | 138 | 0 | 0 | 0 |  | Howard |  | Tier 4 |  |  |  | 1360, 1355, 1395 | Y | N |  |  | 2680 | 2564
3971 | Eskota second 138/69 kV autotransformer | Install second 138/69 kV autotransformer |  | Eskota |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R9008 | 2015-11-15 |  | 138 | 0 | 0 | 100 |  | Nolan |  | Tier 4 |  |  |  | 1340, 1339 | Y | N |  |  | 4295 | 3971
4169 | Sweetwater Creek 69 kV capacitor | Install shunt capacitor |  | Sweetwater Creek |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R9007 | 2015-11-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Nolan |  | Tier 4 |  |  |  | 1407 | Y | N |  |  | 4522 | 4169
3715 | Cottulla STEC 138kV Station | Cotulla STEC 138kV Substation | NEW | JARDIN | COTULLA (AEP) | Planned | 631 - 0800, 3719 | AEP TCC | Mike Tallon dnlyons@aep.com 918-599-2698 | 3528 | 2015-11-16 |  | 138 | 0 | 0 | 0 |  | La Salle | La Salle | Tier 4 |  |  |  | 8520, 8526, 8610, 8611 | Y | N |  |  | 3959 | 3715
12TPIT0143A | Danevang Switch to El Campo Rebuild | Rebuild 4-0 ACSR 69 kV to 138 capable 795 ACSR. |  | Industrial Park | El Campo | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2015-11-18 | 2015-12-16 | 69 | 0 | 2.2 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  | 5538, 5543 | Y | N |  | cost in last phase of project | 1547 | 1535
3969 | Bergheim Capacitor Bank | Add one (1) 138kV 31.2 MVAR capacitor bank at the Bergheim (7170) substation. |  | Bergheim |  | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014336 | 2015-11-23 | 2015-10-09 | 138 | 0 | 0 | 0 | 0,31.2 | Comal |  | Tier 4 |  |  |  | 7170 | Y | N |  |  | 4290 | 3969
3832 | Reconductor Heights - Whiteoak Ckt34 to Increase Thermal Rat | Reconductor Ckt.34 Heights to White Oak and upgrade substation equipment to increase thermal ratings. | Delay in Project Schedule | Heights | White Oak | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 823 | 2015-11-30 | 2015-12-15 | 69 | 0 | 4.35 | 0 |  | Harris |  | Tier 4 |  |  |  | 44657, 46620, 47165, 47580, 46611, 47680 | Y | N |  |  | 4115 | 3832
4976 | Paige Circuit Breaker Addition | Install three 138-kV circuit breakers at Paige in a ring bus configuration. |  | Paige |  | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014329 | 2015-11-30 | 2015-11-30 | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  | 7308 | Y | N |  |  | 5436 | 4976
4934 | Clodine Breaker Addition | Install breaker at Clodine 138kV substation (modeling change) |  | Clodine |  | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-11-30 | 2015-10-17 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 44140, 44141, 44145, 44150, 44051, 44510, 44511, 44512 | Y | N |  |  | 5392 | 4934
3764 | Brackettville 138 kV Station: Upgrade 138 kV Station | Construct a five breakers ring at the expanded Brackettville 138 kV Statio for the Generator Interconnect |  | BRACKETTVILLE |  | Under Construction | 665-0834 | AEP TCC | MICHAEL TALLON DNLYONS@AEP.COM 918-599-2698 | 3529 | 2015-12-01 |  | 138 |  |  |  |  | Kinney |  | Tier 4 |  |  |  | 8252 | Y | N |  |  | 4009 | 3764
4134 | DME_Wrow-KRow_update |  |  | Kingsrow | woodrow | Planned | N/A | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2015-12-01 |  | 69 | 0 | 4.2 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 901, 907, 909 | Y | N | N/A |  | 4479 | 4134
10TPIT0010 | Coppell to Roanoke Reconductor | Reconductor existing Coppell to Roanoke 138kv line with 959ACSS conductor |  | Coppell | Roanoke | Under Construction | 12TPIT0079 | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 2005 | 2015-12-01 |  | 138 | 0 | 17 | 0 |  | Tarrant | Dallas | Tier 4 |  |  |  | 555, 556, 661, 648, 1852 | Y | N |  | construction by Oncor | 230 | 233
4135 | DME_Krow-NDenton_Update |  |  | Kingsrow | N Denton | Planned | N/A | DME | Chuck Sears cxsears@cityofdenton.com 940-249-7111 |  | 2015-12-01 |  | 69 | 0 | 1.91 | 0 |  | Denton | Denton | Tier 4 |  |  |  | 909, 912 | Y | N | N/A |  | 4480 | 4135
4078 |  |  |  | Perch Hill |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 12012 | 2015-12-01 |  | 138 | 0 | 0 | 0 | 0,25 | Wise |  | Tier 4 |  |  |  | 590 | Y |  |  |  | 4428 | 4078
13TPIT0100 | Correction of Effective date for 13TPIT0100 to 12/1/2015 | Build Westminster 138 kV Substation and transmission line tap from Oncor's Anna Switch - Van Alstyne 138 kV line. | Budget |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07612 | 2015-12-01 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 37270, 37271, 12704 | Y | N |  |  | 3812 | 3598
16TPIT0035 | BEC Munday to Gillespie: Rebuild 69 kV line | Rebuild BEC Munday to Gillespie 69 kV line with 959.6 ACSR | IN-SERVICE | BEC Munday | Gillespie | In-Service | 568 - 0742 | AEP TNC | Aaron Schwerman myturner@aep.com 918-599-2437 | 2578 | 2015-12-04 | 2015-11-04 | 69 | 0 | 7.2 | 0 |  | Knox | Knox | Tier 4 |  |  |  | 764, 6112 | Y | N |  |  | 2911 | 2756
4170 | Midessa South 138 kV Switching Station | Construct new 138 kV switching station | Construction schedule change | Midessa South |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8252 | 2015-12-14 |  | 138 | 0 | 0 | 0 |  | Midland |  | Tier 4 |  |  |  | 1124, 1137, 1138 | Y | N |  |  | 4523 | 4170
15TPIT0011 | Shannon to Montague | Rebuild Shannon to Montague 69 kV line with 959 ACSS. |  | Shannon | Montague | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 10045 | 2015-12-15 |  | 69 | 0 | 23.36 | 0 |  | Clay | Montague | Tier 4 |  |  |  | 768, 769, 772, 1548 | Y | N |  |  | 2536 | 2431
15TPIT0040 | Temple Switch 345/138 kV autotransformer | Replace existing autotransformer |  | Temple Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R758-E | 2015-12-15 |  | 345 | 0 | 0 | 600 |  | Bell |  | Tier 4 |  |  |  | 3414, 13415, 13414 | Y | N |  |  | 2465 | 2376
15TPIT0072 | Eddy 69 kV capacitors | Install shunt capacitors |  | Eddy |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R769-E | 2015-12-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | McLennan |  | Tier 4 |  |  |  | 3580 | Y | N |  |  | 3252 | 3083
16TPIT0033 | Culberson - Mason 138 kV Line | Rebuild existing Mason - Screwbean Tap 138 kV line section |  | Screwbean Tap | Mason | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8173-E | 2015-12-15 |  | 138 | 0 | 15 | 0 |  | Reeves | Culberson | Tier 4 |  |  |  | 1083, 1084, 1094, 1095 | Y | N |  |  | 3010 | 2837
4324 | Beaver Creek 69 kV Substation | Construct new substation with shunt capacitors |  | Ringgold |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R969 | 2015-12-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Montague |  | Tier 4 |  |  |  | 1524, 11524, 1545, 11546 | Y | N |  |  | 4701 | 4324
4173 | Odessa 138 kV Switching Station | Rebuild station as a ring bus |  | Odessa |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8251 | 2015-12-15 |  | 138 | 0 | 0 | 0 |  | Ector |  | Tier 4 |  |  |  | 11126, 1122, 1126, 1127 | Y | N |  |  | 4526 | 4173
4172 | Odessa - Midessa South 138 kV Line | Rebuild the Odessa EHV - Odessa TI Tap and the Odessa TI Tap - Midessa South Sw. Sta. 138 kV line sections using double-circuit 138 kV structures. | Construction schedule change | Odessa | Midessa South | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8253 | 2015-12-15 |  | 138 | 10 | 0 | 0 |  | Ector | Midland | Tier 4 |  |  |  | 1027, 1124, 1127, 1126, 1128 | Y | N |  |  | 4525 | 4172
08TPIT0153 | Elkton - Athens 138 kV line | Upgrade existing 138 kV line |  | Elkton | Athens | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R651-E | 2015-12-15 |  | 138 | 0 | 27.9 | 0 |  | Henderson | Henderson | Tier 4 | 2007-11-26 |  |  | 3106, 3238 | Y | N |  |  | 1246 | 1243
3925 | Spraberry 138 kV Switching Station | Upgrade switching station and replace 138/69 kV autotransformer. |  | Spraberry |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8236 | 2015-12-15 |  | 138 | 0 | 0 | 100 |  | Midland |  | Tier 4 |  |  |  | 1329, 1330 | Y | N |  |  | 4225 | 3925
3926 | Lamesa 69 kV Switching Station | Rebuild station as a ring bus | Construction schedule change | Lamesa |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8245 | 2015-12-15 |  | 69 | 0 | 0 | 0 |  | Dawson |  | Tier 4 |  |  |  | 1164 | Y | N |  |  | 4226 | 3926
14TPIT0015 | Stryker - Troup - Tyler Grande 138 kV line | Upgrade existing line. This project also includes 16TPIT0066 (Stryker creek - Troup 138 kV Line section) | Construction schedule change | Stryker Creek | Tyler Grande | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6002 | 2015-12-15 |  | 138 | 0 | 28.9 | 0 |  | Cherokee | Smith | Tier 4 |  |  |  | 3110, 3143, 3147, 3156, 3227 | Y | N |  |  | 4139 | 1434
3923 | Morgan Creek 138 kV Bus | Re-arrange connections for combustion turbines | Construction schedule change | Morgan Creek |  | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R9006 | 2015-12-15 |  | 138 | 0 | 0 | 0 |  | Mitchell |  | Tier 4 |  |  |  | 1032 | Y | N |  |  | 4223 | 3923
4089 | Summit: Upgrade Ckt Breaker SU-950 | Upgrade SU-950 bus tie circuit breaker (connecting buses MB1 and MB2) and related switches to 3000 amps |  | Summit | Summit | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2015-12-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  | 9279, 9280 | Y |  |  |  | 4439 | 4089
15TPIT0034A | Freeport Area Upgrades and Conversion to 138kV | Upgrade Ckt.47 Velasco to Freeport | Delay in Project Schedule | Velasco | Freeport | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 637 | 2015-12-23 |  | 69 | 0 | 4.5 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42640, 43370 | Y | N |  | Substation Cost included in project 15TPIT0034B. | 2491 | 2389
15TPIT0034F | Freeport Area Upgrades and Conversion to 138kV | Upgrade Ckt.47 Surfside to Quintana | Delay in Project Schedule | Surfside | Quintana | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 637 | 2015-12-24 |  | 69 | 0 | 2.1 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43310, 43135 | Y |  |  | Substation Cost included in project 15TPIT0034B. | 3528 | 2389
15TPIT0034I | Freeport Area Upgrades and Conversion to 138kV | Convert Ckt.10 Velasco to Surfside to 138kV and rename to Ckt.59 | Delay in Project Schedule | Velasco | Surfside | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 637 | 2015-12-25 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43310, 43315, 43360, 43370 | Y |  |  | Substation Cost included in project 15TPIT0034B. | 3531 | 2389
15TPIT0034B | Freeport Area Upgrades and Conversion to 138kV | Convert Ckt.47 Velasco to Freeport to 138kV and rename to Ckt.59 | Delay in Project Schedule | Velasco | Freeport | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 637 | 2015-12-26 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42640, 42645, 43360 | Y | N |  |  | 2492 | 2389
15TPIT0034C | Freeport Area Upgrades and Conversion to 138kV | Upgrade Ckt.47 Freeport to Quintana | Delay in Project Schedule | Freeport | Quintana | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 637 | 2015-12-27 |  | 69 | 0 | 3.9 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42640, 43135 | Y | N |  | Substation Cost included in project 15TPIT0034B. | 2493 | 2389
15TPIT0034D | Freeport Area Upgrades and Conversion to 138kV | Convert Ckt.47 Freeport to Quintana to 138kV and rename to Ckt.59 | Delay in Project Schedule | Freeport | Quintana | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 637 | 2015-12-28 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43135, 43435, 42640, 42645, 43310 | Y | N |  | Substation Cost included in project 15TPIT0034B. | 2494 | 2389
15TPIT0034E | Freeport Area Upgrades and Conversion to 138kV | Convert Ckt.47 Freeport to Bryan to 138kV and rename to Ckt.59 | Delay in Project Schedule | Freeport | Bryan | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 637 | 2015-12-29 |  | 138 | 0 | 2.4 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 42200, 44205, 42640, 42645 | Y |  |  | Substation Cost included in project 15TPIT0034B. | 3527 | 2389
3936A | Fairmont to Webster Ckt.06 Upgrades | Upgrade 138kV Ckt.06 Fairmont to NASA to increase thermal ratings |  | Fairmont | NASA | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-12-30 | 2015-12-15 | 138 | 0 | 7.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42292, 42610, 41631, 42970, 43102 | Y | N |  |  | 4532 | 3936
15TPIT0034G | Freeport Area Upgrades and Conversion to 138kV | Convert Ckt.47 Surfside to Quintana to 138kV and rename to Ckt.59 | Delay in Project Schedule | Surfside | Quintana | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 637 | 2015-12-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 2012-06-14 | 2012-07-24 |  | 43310, 43315, 43135 | Y |  |  | Substation Cost included in project 15TPIT0034B. | 3529 | 2389
14TPIT0108 | Kenedy 138/69 kV Switching Station: Upgrade | Construct 138 double circuit line from Kenedy Switch Station to Tuleta and Pettus respectively. Kenedy Switching station to Pettus will be energized at 69 kV. Upgrade 138 kV site at Kenedy Switching Station and construct new Tuleta 138 kV Station. |  | KENEDY SWITCHING STATION |  | Under Construction | 603 - 0765 | AEP TCC | Eric Scott DNLYONS@AEP.COM 918-599-2698 | 3482 | 2015-12-30 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  | 8186 | Y | N |  |  | 3683 | 3477
4400 | Crestonio to Falfurrias: Raise forty-five 138 kV structures | Increase the MOT rating of the Lobo SS to Falfurrias 138kV line by raising 49 structures |  | Crestonio | Falfurrias | Planned | 702 - 0872 | AEP TCC | Mike Tallon dnlyons@aep.com 918-599-2698 | 3546 | 2015-12-31 |  | 138 | 0 | 43.9 | 0 |  | Duval | Brooks | Tier 4 |  |  |  | 8510, 8695 | Y |  |  |  | 4779 | 4400
4455 | Fayatte to Frelsburg Transmission Line Overhaul | Replace 10 full structures with OPGW capability. |  | Fayetteville | Frelsburg | In-Service |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 | 1014183 | 2015-12-31 | 2015-12-18 | 138 | 0 | 0 | 0 |  | Fayette | Colorado | Tier 4 |  |  |  | 7263, 7286 | Y | N |  |  | 4840 | 4455
3253 | Treaschwig to Humble Ckt. 66 | Upgrade 138kV Ckt. 66 Treaschwig to Humble to increase thermal ratings. | Delay in Project Schedule | Treaschwig | Humble | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 732 | 2015-12-31 | 2016-01-13 | 138 | 0 | 9.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40830, 46550 | Y | N |  |  | 3427 | 3253
14TPIT0099 | Treaschwig - Westfield Ckt.66 | Upgrade 138kV Ckt. 66 Treaschwig to Westfield to increase thermal ratings. | Delay in project schedule | Treaschwig | Westfield | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-12-31 | 2016-01-13 | 138 | 0 | 8.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 40900, 46550, 46290, 46570 | Y | N |  | Project is part of the 2012 ERCOT 5-Year Plan. | 2751 | 2630
3441 | Falfurrias: Replace 138/69 kV autotransformer | Add 138/69 kV autotranformer capacity at Falfurrias |  | Falfurias |  | Planned | 632 - 0801 | AEP TCC | Brent Harris dnlyons@aep.com 918-599-2698 | 3511 | 2015-12-31 |  | 138 | 0 | 0 | 92 |  | Brooks |  | Tier 4 |  |  |  | 8508, 8510 | Y |  |  |  | 3641 | 3441
4409 | Liston: Build new three breaker 138 kV station | Interconnect Los Vientos V Windfarm at Liston to connect LKHoward to the Bates to Garza 138 kV line |  | Liston |  | Planned | 698 - 0868 | AEP TCC | Bill Clarke dnlyons@aep.com 918-599-2698 | 2900 | 2015-12-31 | 2015-11-05 | 138 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  | 8394, 8392, 8835 | Y |  |  |  | 4788 | 4409
15TPIT0081 | Centerville Switch 138 kV Series Reactors | Increase size of series reactors |  | Centerville Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4105-E | 2015-12-31 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 902763, 906859, 2439, 2450, 12439, 12450 | Y | N |  |  | 3230 | 3061
3363A | Obrien Autotransformer Upgrade | Replace existing Obrien 600MVA autotransformer A1 with 800MVA auto. |  | Obrien |  | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 681 | 2015-12-31 | 2016-11-25 | 345 | 0 | 0 | 800 |  | Fort Bend |  | Tier 4 |  |  |  | 49031, 49065, 44500, 44510 | Y | N |  | TPIT Cost Reflected in project 15TPIT3363B | 4253 | 3363
14TPIT0119 | Mason Road to Obrien Ckt25 | Upgrade substation equipment at Mason Road and Obrien to increase Ckt.25 thermal ratings. | Delay in Project Schedule | Mason Road | Obrien | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-12-31 | 2015-12-18 | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  | 44450, 44510 | Y | N |  |  | 3049 | 2875
3936B | Fairmont to Webster Ckt.06 Upgrades | Upgrade 138kV Ckt.06 NASA to Webster to increase thermal ratings |  | NASA | Webster | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2015-12-31 | 2015-12-15 | 138 | 0 | 5.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 42970, 43102, 43500, 43501, 43503, 43505 | Y | N |  |  | 4533 | 3936
4184 | Fairmont to QUANAB Ckt.06 | Upgrade 138kV Ckt.06 Fairmont to QUANAB to increase thermal ratings. |  | Underwood | Fairmont/QUANAB | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 991 | 2015-12-31 | 2016-01-13 | 138 | 0 | 6.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  | 41310, 41631, 42610 | Y | N |  |  | 4539 | 4184
4401 | Javalina: Build 138 kV Temp Tap | Interconnect Javalina Windfarm at Javalina to connect Bordas to the Molina to Rio Bravo 138 kV line |  | Javalina |  | Planned | 699 - 0869 | ETT | Rich Haley dnlyons@aep.com 918-599-2698 | 3543 | 2016-01-01 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  | 80646, 80230, 8646 | Y |  |  |  | 4780 | 4401
3363B | Obrien Autotransformer Upgrade | Move existing 600MVA Obrien auto A1 and parallel with existing auto A2. Rename autos 2A & 2B. | Delay in Project Schedule | Obrien |  | In-Service |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 | 681 | 2016-01-01 | 2016-01-17 | 345 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  | 49064, 49065, 44500, 44510 | Y | N |  |  | 4254 | 3363
4540 | Tap 138kV St. Lawrence - Eiland line to create Carterville s |  |  | St. Lawrence | Eiland | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-01-01 |  | 138 | 0 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  | 79560, 79620, 79625 | Y | N |  |  | 4942 | 4540
4174 | Cosden 138 kV terminal equipment replacement | Replace terminal equipment on line to Morgan Creek |  | Cosden |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R9011 | 2016-01-14 |  | 138 | 0 | 0 | 0 |  | Howard |  | Tier 4 |  |  |  | 1032, 1332 | Y | N |  |  | 4527 | 4174
15TPIT0083A | Collin - Arco (TMPA) 138 kV Line (Oncor's section) | Add second circuit to existing line from Collin to Frisco (Brazos) |  | Collin | Frisco (Brazos) | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R929 | 2016-01-15 |  | 138 | 1.9 | 0 | 0 |  | Collin | Denton | Tier 4 |  |  |  |  | Y | N |  |  | 3389 | 3216
4347 | Renner 345 kV bus rearrangement | Convert 345 kV bus to a ring bus arrangement | Under construction | Renner |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3099A | 2016-01-15 |  | 345 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  | 2354, 2355, 2359, 2358, 2361, 2513 | Y | N |  |  | 4720 | 4347
13TPIT0060 | Cedar Hill Switch - Mountain Creek 138 kV line | Upgrade existing line |  | Cedar Hill Switch | Mountain Creek | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4068-E | 2016-01-15 |  | 138 | 0 | 11.4 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2411, 2412, 2421, 2422 | Y | N |  |  | 2593 | 2488
3454 | Braunig_to_Toyota_Rebuild | Rebuild an existing 138 kV transmissions line between the Toyota and Valley Road Substations. |  | Braunig-Alamo1_8-Mauerman-Valley | Alamo1_8-Mauerman-Toyota-Cagnon | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0181 | 2016-01-15 |  | 138 | 0 | 13.7 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5007, 5025, 5053, 5297, 5428, 5465 | Y | N |  | There are no transformers associated with this project | 3655 | 3454
15TPIT0058 | Permian Basin - Ward Gulf Tap - Wink 138 kV line | Upgrade existing 138 kV line |  | Permian Basin | Wink | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8189-E | 2016-01-15 |  | 138 | 0 | 16.5 | 0 |  | Ward | Winkler | Tier 4 |  |  |  | 1010, 1074, 1087 | Y | N |  |  | 3007 | 2834
3934 | Spraberry - Garden City East 138 kV Line | Rebuild existing 69 kV line as a double-circuit 138 kV and 69 kV line |  | Spraberry | Garden City East | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8241 | 2016-01-15 |  | 138 | 33 | 33 | 0 |  | Midland | Glasscock | Tier 3 | 2014-12-01 | 2015-01-01 |  | 1224, 1226, 1328, 1225, 1329, 1337 | Y | N |  |  | 4236 | 3934
09TPIT0044 | E. Richardson - Apollo 138kV line (Oncor' section) | Upgrade existing 138 kV line |  | E. Richardson | Apollo | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3033-WA | 2016-01-15 |  | 138 | 0 | 2.3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 802, 2690 | Y | N |  |  | 3239 | 3070
3874 | Morgan Creek - Cosden 138 kV Line | Rebuild existing aged 138 kV line | Construction schedule change | Morgan Creek | Cosden | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R9001 | 2016-01-15 |  | 138 | 32.5 | 0 | 0 |  | Mitchell | Howard | Tier 4 |  |  |  | 1032, 1332 | Y | N |  |  | 4164 | 3874
15TPIT0078 | Tyler Northwest - Tyler 69 kV Line | Upgrade existing line | Construction schedule change | Tyler Northwest | Tyler | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R6021-E | 2016-01-15 |  | 69 | 0 | 3 | 0 |  | Smith | Smith | Tier 4 |  |  |  | 3142, 3207 | Y | N |  |  | 3231 | 3062
15TPIT0079 | Roanoke Switch - Coppell Switch 138 kV Line Phase 2 | Rebuild existing double-circuit Southlake - Grapevine Junction line section | Construction schedule change | Southlake | Grapevine Junction | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M5001C-E | 2016-01-15 |  | 138 | 0 | 7.7 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  | 2014, 2019, 2020, 2023 | Y | N |  |  | 2690 | 2574
15TPIT0025B | Monticello SES - Monticello Tap 138 kV line | Rebuild existing Monticello SES - Monticello Mining 138 kV line section |  | Monticello SES | Monticello Mining | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R906-E | 2016-01-15 |  | 138 | 0 | 5.5 | 0 |  | Titus | Franklin | Tier 4 |  |  |  | 1791, 1795 | Y | N |  |  | 4521 | 2643
4204 | Wink 138 kV Switching Station | Upgrade 138 kV bus arrangement to breaker and a half and upgrade 69 kV bus arrangement to a ring bus and install a second 138/69 kV autotransformer. | Combined with project #4206 Construction schedule change | Wink |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8263 | 2016-01-15 |  | 138 | 0 | 0 | 50 |  | Winkler |  | Tier 4 |  |  |  | 1074, 1075 | Y | N |  |  | 4561 | 4204
4171 | Midessa - Midessa South 138 kV Line | Rebuild Midessa South - Midessa Sw. Sta. 138 kV Line on double-circuit 138 kV structures. Install a second circuit. |  | Midessa | Midessa South | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8254 | 2016-01-15 |  | 138 | 9.4 | 9.4 | 0 |  | Midland | Midland | Tier 4 |  |  |  | 11159, 1059, 1120, 1124, 1138 | Y | N |  |  | 4524 | 4171
15TPIT0025A | Monticello SES - Monticello Tap 138 kV line | Reconductor existing Monticello Tap - Monticello Mining line section |  | Monticello Mining | Monticello Tap | Under Construction |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R906-E | 2016-01-15 |  | 138 | 0 | 14.7 | 0 |  | Titus | Franklin | Tier 4 |  |  |  | 1791, 1794 | Y | N |  |  | 4520 | 2643
11TPIT0032 | NW Carrollton - Collin second 138 kV circuit |  |  | Collin | Hebron | In-Service |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M368 | 2016-01-15 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  | 2517, 12516, 33629, 902288, 902879, 629, 659, 663, 2362, 2363, 2370, 2377, 2378, 2518, 2519 | Y | N | 2009-R13 |  | 5718 | 1055
3970 | Paris 69 kV Capacitors | Install shunt capacitors |  | Paris Switch |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R975 | 2016-01-15 |  | 69 | 0 | 0 | 0 | 0,18.4 | Lamar |  | Tier 4 |  |  |  | 1778 | Y | N |  |  | 4294 | 3970
3397 | Sterling City: Add 69 kV capacitor banks | Add two 7.2 Mvar capacitor banks at Sterling City | IN-SERVICE and Cost Update | Sterling City |  | In-Service | 629 - 0797 | AEP TNC | Rick McCracken myturner@aep.com 918-599-2437 | 2586 | 2016-01-18 | 2016-01-18 | 69 | 0 | 0 | 0 | 0,14.4 | Sterling |  | Tier 4 |  |  |  | 6435 | Y | N |  |  | 3595 | 3397
3975 | Bessel 138 kV Station: Construct a new station | Construct four 138 kV breaker ring expandable to six breaker at Bessel 138 kV station | Updated In Service Date, Transmission Status | BESSEL |  | In-Service | 671-0840 | AEP TCC | DAVE GOETZ DNLYONS@AEP.COM 918-599-2698 | 3532 | 2016-01-18 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  | 8060, 80601, 8452, 8514 | Y | N |  |  | 4300 | 3975
4118 | GSEC_4118_Add_Carroll_K_Land_Sub |  |  |  |  | Under Construction | NA | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2016-01-19 |  | 69 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  | 60378, 6465, 60380 | Y | N |  | Anticipated in-service date of 12/15 | 4464 | 4118
3881 | GSEC_3881_Add_Church_Sub |  | NA |  |  | In-Service | NA | GOLDENSPREAD | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2016-01-19 |  | 138 | 0 | 0 | 0 |  | Callahan | Callahan | Tier 4 |  |  |  | 60367, 60365 | Y | N |  |  | 4171 | 3881
16TPIT0026 | Lon Hill to Smith: Rebuild 69kV line | Rebuild Lon Hill - Smith 69kV Line with 1533.3 ACSR/TW conductor | Reformated project number to match other numbers | Lon Hill | Smith | In-Service | 583 - 0739 | AEP TCC | William Clarke dnlyons@aep.com 918-599-2698 | 3462 | 2016-01-29 |  | 69 | 0 | 3.1 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  | 8448, 8866, 80479, 80480 | Y | N |  | 0 | 1821 | 1779
3845 | Hindes 138kV Substation: STEC Interconnect | Hindes 138kV Substation: STEC Interconnect |  | Dilley SS | San Miguel | Planned | 682 - 0837 | AEP TCC | Mike Tallon dnlyons@aep.com 918-599-2698 | 3531 | 2016-01-30 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  | 8215, 88215, 5704, 8212 | Y | N |  |  | 4129 | 3845
17TPIT0004 | Frisco to Krugerville Second Circuit | Add second circuit from Frisco to Krugerville |  | Frisco | Krugerville | Planned |  | BEPC | Dwight Beckman kdye@brazoselectric.com 254-750-6373 | 12042 | 2016-01-31 |  | 138 | 12 | 0 | 0 |  | Collin | Denton | Tier 4 |  |  |  | 623, 638, 654, 649, 662, 681, 1993, 1994, 2370 | Y | N |  |  | 2537 | 2432
16TPIT0042 | Uvalde Station: Replace138/69 kV Auto | Upgrade138/69 kV Auto at Uvalde Station | Transmission status, Contact and Cost Update | UVALDE | UVALDE | Under Construction | 739-0922 | AEP TCC | Rick McCraken GAREED@AEP.COM 918-599-2664 | 3566 | 2016-02-01 |  | 138 |  |  | 130 |  | Uvalde |  | Tier 4 |  |  |  | 8231, 8234 | Y | N |  |  | 3741 | 3534

## CancelledTPIT020116NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2016
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar, +Capacitor, -Reactor) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
4583 | Addition of 138kV Boyd station and Boyd-Stiles line |  |  | Boyd | Stiles | Planned |  | SLU | Brad Schwarz 512-289-7425 |  | 2016-04-01 |  | 138 | 6 | 0 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  | 79561, 79614 | N | N |  |  | 4991 | 4583
17TPIT0032 | Fisher Road 345/138 kV autotransformer | Install second autotransformer |  | Fisher Road |  | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R931-E | 2016-05-16 |  | 345 | 0 | 0 | 600 |  | Wichita |  | Tier 4 |  |  |  | 11426, 1425, 1426 | N | N |  |  | 3388 | 3215
4776 | Lyondell Transformer Addition | Add 3rd transformer at Lyondell substation. Tap from Ckt.03 BIGVUE to Channelview |  | Lyondell | BIGVUE/Channelview |  |  | CNP | Wayne E. Kemper wayne.kemper@CenterPointEnergy.com 713-207-2192 |  | 2016-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  | 41021, 41022, 41023, 40190, 40281 | N | N |  |  | 5201 | 4776
16TPIT0011 | JT Deely to Streich - 138 kV Substation Equipment Upgrade | Upgrade terminals at JT Deely and Streich Rd. to ensure a 2420 A rating and remove existing MLSE on JT Deely to Streich 138 kV transmission line |  | JT Deely | Streich Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0674 | 2016-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5110, 5417 | N | N |  | There are no transformers associated with this project | 977 | 976
14TPIT0096 | Nevada-Olinger 138 kV line upgrade | Nevada-Olinger 138 kV line upgrade | On Hold For Funding | A new switch at new Nevada | A switch at Olinger | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2016-06-01 |  | 138 | 0 | 9.5 | 0 |  | Dallas |  | Tier 4 |  |  |  | 811, 818 | N | N |  | This project is a new line for new load serving at Nevada | 2619 | 2514
4202 | Jackalope: Build 138 kV station | Construct new 138 kV in and out substation off the Big Lake to North McCamey line | Cancelled | Jackalope |  | Planned | 696 - 0866 | AEP TNC | Bill Clarke myturner@aep.com 918-599-2437 | 2810 | 2016-12-31 |  | 138 | 0 | 0 | 0 |  | Reagan |  | Tier 4 |  |  |  | 6595, 6536, 60361 | N | N |  |  | 4558 | 4202
5047 | Upgrade conductor for 138 kV line from Sales to Buffalo |  |  | Buffalo | Sales Ranch | Planned |  | SHRY | Brad Schwarz 512-289-7425 |  | 2017-05-01 |  | 138 | 0 | 6 | 0 |  | Martin | Martin | Tier 4 |  |  |  | 79508, 79549 | N | N |  |  | 5521 | 5047
16TPIT0046 | Frankel City - Exxon Fullerton 69 kV Line | Project included under 15TPIT0070 North Andrews - Andrews 69 kV Line |  | Frankel City | Exxon Fullerton | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8176-E | 2017-05-15 |  | 69 | 0 | 2.8 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  | 1270, 1275 | N | N |  |  | 3330 | 3159
3673 | TNC Mason to LCRA Ft. Mason: Rebuild 69 kV line | Rebuild TNC Mason to LCRA Ft. Mason 69 kV line with 959.6 ACSR/TW | Cancelled | TNC Mason | LCRA Ft. Mason | Planned | 646 - 0815 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 1810 | 2017-05-31 |  | 69 | 0 | 0.15 | 0 |  | Mason | Mason | Tier 4 |  |  |  | 6393, 76388 | N | N |  |  | 3910 | 3673
16TPIT0013 | Skyline to Spruce - 345 kV Substation Equipment Upgrade | Replace the Line MDS at Skyline and Spruce (both circuits) and ensure all terminals have a 2420 A rating and remove existing MLSE on Skyline to Spruce 345 kV transmission lines (both circuits) |  | Skyline | Spruce | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0468 | 2017-06-01 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  | 5371, 5400 | N | N |  | There are no transformers associated with this project | 971 | 970
15TPIT0020 | Braunig to Highland Hills-Brooks - 138 kV Substation Equipme | Replace Line and Bus Switches at Brooks and ensure a 1385 A rating and remove existing MLSE on the Brooks to Southton 138 kV transmission line |  | Braunig_W | Highland Hills-Brooks | Planned | T-0194 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2018-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  |  | 5030, 5045, 5175, 5205, 5394 | N | N |  | There are no transformers associated with this project | 2385 | 2309
10TPIT0027 | West Batesville, Install 138 kV ring bus | West Batesville: Construct bundled 2x795 ACSR 138 kV line, add 138 kV circuit breaker and convert to 4 breaker ring bus | CHANGES | WEST BATESVILLE |  | Conceptual | 383 - 0560 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2168 | 2019-03-31 |  | 138 | 0 | 0 | 0 |  | Zavala |  | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8236 | N | N |  | NA | 3751 | 3543
10TPIT0028 | Escondido to West Batesville, build 138 kV Line | West Batesville: Construct bundled 2x795 ACSR 138 kV line, add 138 kV circuit breaker and convert to 4 breaker ring bus | CHANGES | ESCONDIDO | WEST BATESVILLE | Conceptual | 383 - 0560 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 2169 | 2019-03-31 |  | 138 | 46.2 | 0 | 0 |  | Maverick | Zavala | Tier 1 | 2006-01-01 | 2006-08-01 | 2006-08-01 | 8260 | N | Y |  | NA | 3752 | 3544
4476 | Kendall to Comfort Transmission Line Upgrade | Upgrade the 1.09-mile Kendall (7152) - Comfort (7155) 138-kV transmission line to bundle 1590 Lapwing conductor (669 MVA). Part of CPS-Tie Project. |  | Kendall | Comfort | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-05-31 |  | 138 | 0 | 1.09 | 0 |  | Kendall | Kendall | Tier 1 | 2014-06-29 |  |  |  | N | N |  |  | 4862 | 4476
4474 | Kendall to Kerrville Stadium Transmission Line Upgrade | Upgrade 16.68-mile Kendall (7150) to Kerrville Stadium (7138) 138-kV transmission line to bundle Drake (440 MVA). |  | Kendall | Kerrville Stadium | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2019-05-31 |  | 138 | 0 | 16.68 | 0 |  | Kendall | Kerr | Tier 1 | 2014-06-29 |  |  |  | N | N |  |  | 4860 | 4474
3670 | Albany to Albany Foundry: Rebuild 69 kV line | Rebuild Albany to Putnam 69 kV line with 959.6 ACSR/TW | Cancelled | Albany | Albany Foundry | Planned | 645 - 0814 | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 | 1809 | 2020-05-31 |  | 69 | 0 | 5.13 | 0 |  | Shackelford | Shackelford | Tier 4 |  |  |  | 6202, 6207, 6213 | N | N |  |  | 3907 | 3670
13TPIT0104 | Jack County Auto | Install 345-138 kV, 700 MVA auto at Jack County |  | Jack County | Jack County | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 11038 | 2020-06-01 |  | 345 | 0 | 0 | 700 |  | Jack |  | Tier 4 |  |  |  | 575, 579 | N | N |  |  | 1184 | 1181
12TPIT0185 | Airline to Westside: Add 138kV Circuit | Add a Second 138kV Circuit between Airline and Westside | Change transmission status, ISD | AIRLINE | WESTSIDE | Planned | 587-0747 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3464 | 2020-12-31 |  | 138 | 6.22 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  | 8490 | N | N |  | NA | 3753 | 3545
3999 | Airline to Holly: Build new 138 kV line | Build a new 138 kV line from Airline to Holly using the existing structures | Change transmission status, ISD | AIRLINE | HOLLY | Planned | 548-0747 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3464 | 2020-12-31 |  | 138 | 1.69 |  |  |  | Nueces | Nueces | Tier 4 |  |  |  | 8486, 8490 | N | N |  |  | 4325 | 3999
11TPIT0037 | Add New Santa Clara Substation | Build a new 138-26.18 kV 40 MVA substation on the GVEC McQueeney(7606)-Cibolo(7608) 138 kV transmission line |  | Santa Clara | McQueeney/Cibolo | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7605, 7606, 7608 | N | N |  |  | 4461 | 3369
12TPIT0006 | Olmos(7613)- New Substation | Build a new 138-13.09 kV 20 MVA substation on the Olmos switching station site |  | Olmos | Olmos Switching Station | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-11-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  | 7239 | N | N |  |  | 3566 | 3371
08TPIT0007 | Austin Ranch - Hebron 138 kV line | Upgrade existing 138 kV line |  | Austin Ranch | Hebron | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3002-E | 2024-05-15 |  | 138 | 0 | 0.7 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | N | N |  |  | 3366 | 3195
09TPIT0046 | N. Midlothian - Midlothian TXI Tap 138 kV line | Upgrade existing 138 kV line |  | N. Midlothian | Midlothian TXI Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M3031-E | 2024-05-15 |  | 138 | 0 | 6.2 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | N | N |  |  | 3295 | 3126
15TPIT0049 | Permian Basin 345 kV Switching Station | Construct 345 kV switching station and install 345/138 kV autotransformer |  | Permian Basin |  | Conceptual | R8100C-E & R8100B-E | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | R8100B-E | 2024-07-15 |  | 345 | 0 | 0 | 600 |  | Ward |  | Tier 1 | 2013-02-15 |  | 2013-09-15 | 11010, 1010 | N | N |  | Estimated cost is included in total estimated cost for 15TPIT0047. | 3009 | 2836
07TPIT0069 | Sterrett - Sardis 138 kV line | Upgrade existing 138 kV line |  | Sterrett | Sardis | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M361-E | 2025-05-15 |  | 138 | 0 | 2 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | N | N |  |  | 3271 | 3102
16TPIT0064 | Simpson Stuart - Lancaster Witt 138 kV Line | Upgrade existing line |  | Simpson Stuart | Lancaster Witt | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4112-E | 2026-05-15 |  | 138 | 0 | 3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  | 2988, 3068 | N | N |  |  | 3241 | 3072
16TPIT0068 | Venus - Chaparral Steel Tap 138 kV Line | Upgrade existing line |  | Venus | Chaparral Steel Tap | Conceptual |  | ONCOR | Michael Juricek michael.juricek@oncor.com 214-743-6671 | M4113-E | 2026-05-15 |  | 138 | 0 | 5.5 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  | 1908, 2300 | N | N |  |  | 3251 | 3082

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2015-N1 | Kiamichi Energy Facility (140077) 345-kV reactor addition | KIOWA POWER PARTNERS LLC (RE, Facility Owner) | 2016
2015-NC1 | Gatesville Switch (3583)-Gatesville TDC Army (3587) 69-kV line upgrade | Oncor | 2016
2015-NC2 | Ranger Gulf (1627)-Thurber TNP (37850) 69-kV terminal equipment upgrade | TNMP | 2016
2015-NC3 | Ben Davis (968) - Murphy Road (2696) 138-kV line upgrade | Oncor / TMPA | 2016 | 2019-06-01 | Planned | 4438 | Under Study
2015-NC4 | Bosque Switch (252) - Olsen TNP (37460) 138-kV line terminal equipment upgrade | TNMP | 2021
2015-NC5 | Firewheel (821) - Apollo (802) 138-kV line upgrade | Garland | 2018 | 2016-05-31 | Planned | 12TPIT0084
2015-NC6 | Hicks Switch (2081-2082) 345/138-kV transformer addition | Oncor | 2021
2015-NC7 | Trinidad SES (3127) - Oak Grove Tap (2725) 138-kV line upgrade | Oncor | 2018 |  |  |  | Under Study
2015-NC8 | Seagoville Switch (2434) - Crandall POI (2732) 138-kV line upgrade | Oncor | 2018
2015-NC9 | Liggett Switch (1923-1925) - Hackberry (2388) 138-kV double circuit line upgrade | Oncor | 2016
2015-NC10 | Killeen Switch (3423) - Belton (3610) 138-kV circuit upgrade | Oncor | 2020
2015-NC11 | Whitney (241) 138-kV bus tie upgrade | Brazos | 2021
2015-NC12 | Breckenridge (1615) - Leon Switch (1625) 69-kV line upgrade | Oncor | 2016
2015-NC13 | Carrollton Northwest (2362) - Lakepointe TNP (37010) 138-kV line upgrade | Oncor / TNMP | 2016 |  |  |  | Under Study
2015-NC14 | Corinth (1985) - Highlands TNP (1974) 138-kV line upgrade | Oncor | 2018
2015-NC15 | Vernon (6060) 138-kV capacitor bank addition | AEP TNC | 2016 | 2018-06-30 | Planned | 5199
2015-NC16 | Cedar Crest Switch (2495,2493) 138-kV breaker upgrade | Oncor | 2016
2015-FW1 | TNMP Flat Top TNMP 138-kV Interconnection Project 1. Tap existing Barilla (6655)-Solstice (60385) 138-kV line 2. Convert Flat Top TNP (38070) - Barilla Draw Tap (38060) to 138-kV 3. Convert Barilla Draw Tap (38060) - TNMP IH 20 (38040) to 138-kV 4. New 138/69-kV transformer at TNMP IH 20 (38040) | American Electric Power/TNMP | 2016 | 2016-04-30 | RPG Approved | 5030 | Under Study
2015-FW2 | Holt Switch (1141) - North Andrews (1159) 138-kV Line upgrade | ONCOR | 2020 | 2016-12-15 | Planned | 4243
2015-FW3 | Add a Dynamic Reactive Device at Mason (1094) | ONCOR | 2018 | 2018-05-15 | Planned | 4781
2015- | Odessa EHV - Moss - Pecos 345/138-kV Project 1. Convert 69-kV Barstow NW (1086) substation to 138-kV 2. Build new 138-kV station called Pecos (1098) 3. Tap 138-kV Mentone (1011) - Permian (1009) circuit and move Barstow as well as newly built Pecos (1098) stations there 4. Build 345/138-kV transformer at Pecos and connect to Moss (1018) and ODEHV (1029) via new 345kV lines | ONCOR | 2018
2015-W1 | Campwood (8633)-Montell (8230)-Uvalde (8231) 69-kV line upgrade | American Electric Power | 2016 | 2018-05-31 | Planned | 4488
2015-W2 | Add a second 345/138-kV transformer at Twin Buttes (76009) | LCRA TSC | 2016 | 12/22/2016; 12/31/2017 | Planned; Planned Not in Case | 4878; 5270 | Under Study
2015-W3 | Install at a minimum of 50 MVAR Shunt Reactor at Claytonville 345KV station (68001) | Lonestar | 2016
2015-W4 | Abilene Northwest (6225) - Abilene Elm Creek (6253) 69-kV line upgrade | American Electric Power | 2016 | 2017-12-31 | Planned | 5197 | Under Study
2015-W5 | Add a second 345/138-kV transformer at Vealmoor - Sharyland Utilities station (79640) | Sharyland | 2018 | 2017-06-30 | Planned | 4962
2015-SC_1 | Luling (7223) - Deer Creek (7597) 69-kV line rebuild | LCRA TSC | 2020 | 2017-05-31 | Planned | 4446
2015-SC_2 | Fayette (7278) area upgrades | LCRA TSC | 2020 | 2020-05-31 | Planned Not in Case | 5286
2015-SC_3 | Flatonia (7248) - Hallettsville (7246) 138-kV line rebuild | LCRA TSC | 2020 | 2020-05-31 | Planned Not in Case | 5276
2015-SC_4 | Milton (78583) 138-kV capacitor bank addition | LCRA TSC | 2018 | 2018-06-30 | Planned Not in Case | 5285
2015-SC_5 | New 138-kV line addition parallel to the Buda (7498) - Turnersville (7500) 138-kV line | LCRA TSC | 2021 | 2021-05-31 | Planned Not in Case | 5287
2015-S1 | George West (5688-5686) 138/69-kV transformer upgrade | STEC | 2016 | 2016-11-01 | Planned | 3817
2015-S2 | New Barney Davis (8458) - North Padre (8856) 138-kV line addition | American Electric Power/ETT | 2018 |  |  |  | Under Study
2015-S3 | Crystal (8242) - Carrizo Springs (8244) 138-kV line upgrade | American Electric Power | 2020
2015-S4 | Cross Valley Project tap at South McAllen (8371) | American Electric Power | 2016
2015-S5 | Escondido (8260) - Eagle Pass (8270) 138-kV line upgrade | American Electric Power | 2016 | 2017-05-31 | Planned | 4489 | Under Study
2015-S6 | New Escondido (8260) - Brackettville (8252) 138-kV line addition | American Electric Power | 2016
2015-S7 | Melon Creek (80066) - Tatton (8800) line upgrades | American Electric Power | 2018 | 2022-03-31 | Planned | 08TPIT0132
2015-S8 | Valero (8477) area upgrades | American Electric Power/ETT | 2016 | 2017-05-31 | Planned | 4487
2015-S9 | W George West Switch (5685) - George West Switching Station (5686) 69-kV line upgrade | STEC | 2018 | 2018-06-01 | Planned | 5223 | Under Study
2015-S10 | Beeville (8198) area upgrades | American Electric Power | 2018
2015-S11 | Bessel (80600) 138-kV capacitor bank addition | American Electric Power | 2016
2015-S12 | New North Hill (98455) - Zia (9838) 345-kV line | American Electric Power | 2018
2015-S13 | Koch Up River Road (8469) 138/69-kV transformer upgrade | American Electric Power | 2020 |  |  |  | Under Study
2015-S14 | Pharr Magic Valley (5762) 138-kV statcom addition | American Electric Power/STEC | 2021 |  |  |  | Under Study
2015-S15 | BigFoot (8218) - Pearsall (8216) 69-kV line upgrade | American Electric Power | 2021 |  |  |  | Under Study
2015-S16 | Second South McAllen (8371) 345/138-kV transformer addition | American Electric Power | 2018
2015-S17 | Molina (80230) - Cenizo (80220) 345/138-kV transformer addition | American Electric Power/ETT | 2016 |  |  |  | Under Study
2015-S18 | Replace two Miguel (5901) 345/138-kV transformers and add 6.7-ohm series reactors on 138-kV side | STEC | 2018 | 2018-06-01 | Planned | 5218
2015-S19 | Second Palmito (5966) 345/138-kV transformer addition | Sharyland | 2018
2015-S20 | Oaks (5713) 138/69-kV transformer upgrade | STEC | 2018 | 2018-06-01 | Planned | 5221
2015-S21 | Dilley Switch (5863) - Cotulla (5876) 69-kV line upgrade | STEC | 2021 | 2021-06-01 | Planned | 5222
2015-S22 | Pleasanton (8200) - Jourdanton (8607) 69-kV line upgrade | American Electric Power | 2018
2015-C1 | Switched Shunt at Jones Creek (42540) | Centerpoint Energy | 2020
2015-C2 | Dunlavy (47580) - Heights (47680) 69-kV Line Upgrade | Centerpoint Energy | 2020 |  |  |  | There is no topology change needed for this project as the power factor improvement is handled on the distribution side and the same is reflected in the current set of cases with Southwyck load at unity PF on distribution side.
2015-C3 | Second Switched Shunt at Velasco (43360) | Centerpoint Energy | 2020 |  |  |  | The shunt addition is needed by summer of 2020; TP is still evaluating alternatives however, this project can be available (tentatively) by May 2019.
2015-C4 | Hardy (45840) - North Side (47711) 138-kV Line Upgrade | Centerpoint Energy | 2020
2015-C5 | O'Brien (44512) - Clodine (44140) 138-kV Line Uprate | Centerpoint Energy | 2020
2015-C6 | Clodine (44140) - Barker (44052) 138-kV Line Upgrade | Centerpoint Energy | 2020
2015-C7 | Place Holder - Transformer Addition at Zenith (44900/44910) | Centerpoint Energy | 2020
2015-C8 | Switched Shunts at MaGill (8111) and Bay City (8113) | American Electric Power | 2016 |  |  |  | A mitigation plan has been developed to address the needs in the near term. TP is still evaluating alternatives however, this project can be available (tentatively) by May 2017.
2015-E1 | Trinidad (3127) - Winkler (212) 138-kV Line Upgrade | Oncor | 2016
2015-E2 | Stryker Creek (3110) - Douglas (3343) 138-kV Line Upgrade | Oncor | 2020

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Bob Healey; Veronica Billings | bhealey@aep.com; vbillings@aep.com | Bob Healey: 918 599 2249; Veronica Billings: 918 599 2945 | Glen Reed; David Kidd; Brad Myers; Mabel See; Mike Forcum; Doug Lee; Daniel Lyons; Bob Lager; Mina Turner; Lisa Kelso; Carole Myser | gareed@aep.com; dekidd@aep.com; blmyers@aep.com; msee@aep.com; mlforcum@aep.com; dnlyons@aep.com; dlee@aep.com; rjlager@aep.com; myturner@aep.com; lokelso@aep.com; camyser@aep.com | David Kidd: 918 599 2637 Glen Reed: 918 599 2664 Brad Myers: 918 599 2690
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Armke, James; Hunt, Dandy; Ron Krautz; Brion Ryan | James.Armke@austinenergy.com; dandy.hunt@austinenergy.com; ron.krautz@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | James:512 322 6705 Biju:512 322 6381 Reza:512 322 6740 Dandy:512 322 6748 Ron:512 322 6835 Brion: 512-322-6879
Bandera Electric | Primary | David Baker | d.baker@banderaelectric.com | David: 830-796-6084
BPUB | Primary | Ramon Sanz | rsanz@brownsville-pub.com; | Ramon: 956 983 6203 | James McCann | jmccann@brownsville-pub.com; | James: 956 983 6204
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Dwight Beckman | dbeckman@brazoselectric.com | Dwight: 254 750 6373 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | James Tanneberger | jtanneberger@btutilities.com | James: 979 821 5763 | Shawndra Green | sgreen@btutilities.com | Shawndra: 979 821 5744
CNP | Primary & Secondary | Wayne Kemper | wayne.kemper@centerpointenergy.com | Wayne: 713 207 2192 | David Mercado; Yingying Huang; Cody Mann | david.mercado@centerpointenergy.com; yingying.huang@centerpointenergy.com; cody.mann@centerpointenergy.com | David Mercado: 713-207-2125 Yingying Huang: 713-207-2831 Cody Mann: 713-207-3149
COCS | Primary | Tony Michalsky | tmichalsky@cstx.gov; | Tony: 979 764 3438 | Timothy Crabb; Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | Basileo Rocha, Sunil Dhakal | bdrocha@cpsenergy.com; SDhakal@cpsenergy.com | Basileo: 210 353 4933 Sunil: 210 353 2008 | Kenneth Bowen Trieu Vo | kbowen@cpsenergy.com; tvo@cpsenergy.com; | Kenneth: 210 353 4142 Trieu: 210 353 2127
CTT (Cross Texas Transmission) | Primary & Secondary | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310 | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310
DENTON | Primary & Secondary | Chuck Sears | Chuck.Sears@cityofdenton.com; | Chuck: 940 349 7111 | Brent Heath | brent.heath@cityofdenton.com; | Brent: 940 349 7180
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Grubbs, David; Juan Santos | Dgrubbs@gpltexas.org; Jsantos@gpltexas.org | David: 972 205 2664 Juan: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; PEC; SBEC; GVEC; City of Georgetown; BBEC,CTEC, NBU | Primary & Secondary | Charles DeWitt | Charles.dewitt@lcra.org | Charlie: 512-578-4199 | Sergio Garza, Cris Urena, Ken Chui | sergio.garza@lcra.org; cris.urena@lcra.org; ken.chui@lcra.org | Sergio: 512 578 4149 Cris: 512 578 4525 Ken: 512 578 4510
Lone Star | Primary & Secondary | Don Le | don.le@lonestar-transmission.com | Don - 512-236-3144 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Mike Juricek | Michael.Juricek@oncor.com; | Mike: 214 743 6671 | Paul Bell | paul.bell@oncor.com | Paul: 214-743-6676
Sharyland Utilities | Primary & Secondary | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243 | Michael Glass, Dwight Yarbrough, Miguel Alvarado | mglass@sharyland.com; dyarbrough@sharyland.com; malvarado@sharyland.com | Michael: (956) 687-5600, Dwight: (432) 684-0321, Miguel: (214) 855-6103
STEC | Primary & Secondary | Doug Evans | devans@stec.org | Doug: 361 485 6459 | Paul Person Loretta Gallaga | pperson@stec.org; lgallaga@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Ahmad Saboor | asaboor@texasmpa.org | Ahmad: 936 873 1104 | Frank Owens | fowens@texasmpa.org; | Frank: 936 873 1120
TNMP | Primary & Secondary | Robert Lona | Robert.Lona@tnmp.com | Robert: 281-581-4732 | Anthony, Hudson Ballay, Dustin Cloninger, Ross | Anthony.Hudson@tnmp.com; Dustin.Ballay@tnmp.com; Ross.Cloninger@tnmp.com; | Anthony: 281 581 4712 Dustin:281 581 4730 Ross:281 581 4733
Wind Energy Texas Transmission (WETT) | Primary | Julius Horvath | julius.horvath@windenergyoftexas.com | Julius: 512 436 9585; cell: 512 496 9186 | Christina Minchew | christina.Minchew@windenergyoftexas.com | Christina: 512-436-9469