## ImprovementCostSummary03012021
| Project Cost |  |  |  |  | XFMR MVA
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total
2020 | 977081770 | 1009514928.38 | 347402880 | 2333999578.38 | 2020 | 10380 | 180 | 0 | 10560 | For ROS and BOD Reports
2021 | 1145513000 | 1382394102.56 | 433936482 | 2961843584.56 | 2021 | 5297 | 172 | 110 | 5579 | ·All Projects (in engineering, routing, licensing and construction): |  |  |  | 7317089159.56
2022 | 352474000 | 1587750107 | 354482000 | 2294706107 | 2022 | 2660 | 1141 | 300 | 4101 | ·Transmission Projects Energized in 2021: |  |  |  | 49446532
2023 | 133500000 | 399003000 | 268360000 | 800863000 | 2023 | 3900 | 40 | 0 | 3940
2024 | 356799000 | 273141000 | 250178000 | 880118000 | 2024 | 1950 | 60 | 0 | 2010
2025 | 0 | 183050000 | 0 | 183050000 | 2025 | 0 | 0 | 0 | 0
2026 | 0 | 78910000 | 0 | 78910000 | 2026 | 0 | 0 | 0 | 0
2027+ | 45600000 | 114345000 | 7100000 | 167045000 | 2027+ | 675 | 0 | 0 | 675
2021COM | 0 | 49446532 | 0 | 49446532 | 2021COM | 0 | 0 | 0 | 0
2021PLAN | 1145513000 | 1332947570.56 | 433936482 | 2912397052.56 | 2021PLAN | 5297 | 172 | 110 | 5579
2020-2027+ | 3010967770 | 5028108137.94 | 1661459362 | 9700535269.94 | 2020-2027+ | 24862 | 1593 | 410 | 26865
2020-2021 | 2122594770 | 2391909030.94 | 781339362 | 5295843162.94 | 2020-2021 | 15677 | 352 | 110 | 16139
2022-2027+ | 888373000 | 2636199107 | 880120000 | 4404692107 | 2022-2027+ | 9185 | 1241 | 300 | 10726
| Circuit Miles New |  |  |  | Circuit Miles Rebuilt, Reconductored or Upgraded |  |  |  |  | Total
| 345 | 138 | 69 | Total |  | 345 | 138 | 69 | Total | 345 | 138 | 69 | Total
2020 | 472.422 | 161.967 | 33.11 | 667.499 | 2020 | 116.79 | 283.77 | 258.173 | 658.733 | 589.212 | 445.737 | 291.283 | 1326.232
2021 | 173.15 | 91.33 | 1 | 265.48 | 2021 | 34.6 | 563.64 | 295.09 | 893.33 | 207.75 | 654.97 | 296.09 | 1158.81
2022 | 40.41 | 89.72 | 27.5 | 157.63 | 2022 | 27 | 387.17 | 186.84 | 601.01 | 67.41 | 476.89 | 214.34 | 758.64
2023 | 8.1 | 74.141 | 0 | 82.241 | 2023 | 26.9 | 163.901 | 193.181 | 383.982 | 35 | 238.042 | 193.181 | 466.223
2024 | 77 | 16.9 | 0 | 93.9 | 2024 | 132.1 | 159.308 | 173.06 | 464.468 | 209.1 | 176.208 | 173.06 | 558.368
2025 | 0 | 22.1 | 0 | 22.1 | 2025 | 0 | 11.6 | 0 | 11.6 | 0 | 33.7 | 0 | 33.7
2026 | 0 | 0 | 0 | 0 | 2026 | 0 | 60.24 | 0 | 60.24 | 0 | 60.24 | 0 | 60.24
2027+ | 0 | 18.9 | 0 | 18.9 | 2027+ | 11.2 | 51.75 | 8.26 | 71.21 | 11.2 | 70.65 | 8.26 | 90.11
2021COM | 0 | 0.8 | 0 | 0.8 | 2021COM | 0 | 11.5 | 0 | 11.5 | 0 | 12.3 | 0 | 12.3
2021PLAN | 173.15 | 90.53 | 1 | 264.68 | 2021PLAN | 34.6 | 552.14 | 295.09 | 881.83 | 207.75 | 642.67 | 296.09 | 1146.51
2020-2027+ | 771.082 | 475.058 | 61.61 | 1307.75 | 2020-2027+ | 348.59 | 1681.379 | 1114.604 | 3144.573 | 1119.672 | 2156.437 | 1176.214 | 4452.323
2020-2021 | 645.572 | 253.297 | 34.11 | 932.979 | 2020-2021 | 151.39 | 847.41 | 553.263 | 1552.063
2022-2027+ | 125.51 | 221.761 | 27.5 | 374.771 | 2022-2027+ | 197.2 | 833.969 | 561.341 | 1592.51

## FutureTPIT020121NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2021
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
59921 | Breaker Installation | Updating to a Ring Bus configuration at the Rosehill substation for increased reliability. | N/A | 6894 | 6894 | Planned | N/A | RYBRN | Stephen Geiger, sgeiger@rayburnelectric.com See above. (469)-402-2112 |  | 2021-02-11 |  | 138 | 0 | 0 | 0 |  | Kaufman | Kaufman | Tier 4 | N/A |  |  |  |  | Y |  | N/A |  | 59922 | 59921
50342 | Rebuild Shropshire to Saltdome | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment |  | Saltdome | Shropshire | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-02-13 |  | 69 | 0 | 5.4 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5551, 5555 | Y | N |  | 0 | 50343 | 50342
6019 | North Main - Denton Ave/Springdale Loop | Establish Northmain - Springdale Loop 138 kV line |  | North Main | Springdale | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5240 | 2021-02-15 |  | 138 | 0 | 4.6 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1965, 2102, 2148, 2156, 3010, 2092, 2099, 2101, 2157, 1961, 2146 | Y | N |  | 0 | 52337 | 6019
56581 | Kimbro Substation Addition | Provide transmission service to a generator by cutting -in a new substation between the LCRA TSC Gilleland Creek Substation and Oncor Elgin Switch. This is related to ERCOT Generation Interconnection or Change Request No. 15INR0090. |  | Kimbro |  | Under Construction |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017433 | 2021-02-19 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7337, 3650, 7336 | Y |  |  | 0 | 56582 | 56581
5024 | Crane Loop: Rebuild 69 kV line | Rebuild Crane Loop 69 kV line | Update Schedule | Crane | Crane | Planned | 738 - 0921 | AEP TNC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | 2619 | 2021-02-28 |  | 69 | 0 | 8.05 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 6600, 6603, 6607, 6609, 6606, 6608, 6613 | Y | N |  |  | 12661 | 5024
5356 | Bakersfield: Build 345 kV terminal | Interconnect Maplewood solar farm at Bakersfield | Update Schedule | Bakersfield |  | Under Construction | 780 - 0965 | ETT | Greg Crane mlforcum@aep.com 918-599-2674 | 2640 | 2021-02-28 |  | 345 | 2.35 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 135324, 76002 | Y | N |  |  | 13042 | 5356
6118 | Port Isabel - Causeway 138 kV Line | Rehab Port Isabel - Causeway 138 kV Line |  | Port Isabel | Causeway | Planned | 826 - 1010 | AEP TCC | Kenneth Haley bcogan@aep.com 918-599-2857 | 3626 | 2021-02-28 |  | 138 | 0 | 6.74 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  |  | 13844 | 6118
6345 | Yellowjckt to Menard Phillips T 69 kV line: Rebld 69 kV line | Rehab Yellowjacket to Menard Phillips Tap 69 kV line | Update Schedule | Yellowjacket | Menard Phillips Tap | Planned | 786 - 0971 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2711 | 2021-02-28 |  | 69 | 0 | 15.3 | 0 |  | Menard | Kimble | Tier 4 |  |  |  |  | 6363, 6401 | Y | N |  |  | 14089 | 6345
6352 | Crckett Hghts to Sonora Atlntic 69 kV line: Rbld 69 kV line | Rehab Crockett Heights to Sonora Atlantic 69 kV line | Update Schedule | Crockett Heights | Sonora Atlantic | Planned | 786 - 0971 | AEP TNC | Joseph Page mlforcum@aep.com 918-599-2674 | 2706 | 2021-02-28 |  | 69 | 0 | 16.8 | 0 |  | Crockett | Sutton | Tier 4 |  |  |  |  | 6511, 6552 | Y | N |  |  | 14096 | 6352
6573 | Reconductor Dunlavey to Heights Ckt. 31 | Reconductor the Dunlavy to Heights as identified in the 2015 RTP case |  | Dunlavy | Heights | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 69 | 0 | 2.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47581, 47682, 47580, 47680 | Y | N |  | 0 | 50777 | 6573
7129 | DeCordova 345/138kV_Sw. | Rebuild existing switching DeCordova station |  | DeCordova |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5066 | 2021-02-28 |  | 345 | 0 | 0 | 0 |  | Hood |  | Tier 3 | 20RPG006 | 2020-05-05 | 2020-05-29 |  | 1891, 2888, 11890, 2277, 2278, 2281, 2285, 150721, 150722, 150723, 150724, 12288 | Y | N |  | 0 | 59769 | 7129
43284D | Baytown Area Upgrades | Upgrade portions of reconfigured Ckt.87 SR Bertron to TEXAS to increase thermal ratings |  | SR Bertron | TEXAS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 0.99 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41405, 41540 | Y | N |  | Overall Cost included in phase F | 56065 | 43284
43284F | Baytown Area Upgrades | Upgrade Ckt.87 TEXAS to Cedar Bayou tap to increase thermal ratings |  | TEXAS | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 3.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40011, 40015, 41540 | Y | N |  | 0 | 56061 | 43284
43454 | Gable Street Reconfigurations | Add 69kV breaker at Gable Street to mitigate P2 contingency load loss |  | Gable Street | Gable Street | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47640 | Y |  |  | 0 | 51311 | 43454
48281 | Angleton to West Columbia Ckt 04E Upgrades | Upgrade Ckt 04E Angleton to West Columbia to increase thermal ratings | Now a GO project | Angleton | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 16.11 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 43381, 43380 | Y | N |  | 0 | 55974 | 48281
50896 | Garnet: Build new 138 kV station | Interconnect Norton solar farm on the Ballinger to Oak Creek 138 kV line |  | Garnet |  | Planned | 1049 - 1222 | AEP TNC | Bryan Oyster mlforcum@aep.com 918-599-2674 | 2824 | 2021-02-28 |  | 138 | 0 | 0 | 0 |  | Runnels |  | Tier 4 |  |  |  |  | 60451, 6325, 6340 | Y | N |  | 0 | 50897 | 50896
52365D | Spillman Island Restoration Plan | Upgrade Relays at QUANUM substation on QUANUM to WALKER to Cedar Bayou Ckt.85A (Future Option 3 to reconfigure as Ckt.xx QUANUM-WALKER-Alexander Island-SRB). |  | QUANUM | WALKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41330, 41440 | Y | N |  | Cost included in Phase A. | 52369 | 52365
52376 | MARICK (MCK) 138kV Customer Substation | MARICK (MCK) 138kV customer substation looped into Ckt.60A Orchard/Rosenberg |  | Orchard | Rosenberg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44520, 44540, 44541, 44615 | Y | N |  | 0 | 52377 | 52376
44426 | Foxtail: Add 345 kV reactor | Add new 345 kV reactor at Foxtail |  | Foxtail |  | Planned | 940 - 1118 | AEP TNC | Todd Siegert mlforcum@aep.com 918-599-2674 | 2754 | 2021-02-28 01:00 |  | 345 | 0 | 0 | 0 | -50,0 | Baylor |  | Tier 4 |  |  |  |  | 6076 | Y | N |  | 0 | 44427 | 44426
52365E | Spillman Island Restoration Plan | Upgrade equipment at SR Bertron substation on SRB-Alexander Island-CHORIN Ckt.87C (Future Option 3 to reconfigure as Ckt.xx SRB-Alexander Island-WALKER-QUANUM) |  | SRB | Chorin | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 01:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40320, 41391, 41400 | Y | N |  | Cost included in Phase A. | 52371 | 52365
52365F | Spillman Island Restoration Plan | Upgrade Relays at Cedar Bayou substation on Cedar Bayou-WALKER-QUANUM Ckt.85A. |  | Cedar Bayou | Quanum | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 02:00 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40010, 41440 | Y | N |  | Cost Included in Phase A. | 52372 | 52365
52365H | Spillman Island Restoration Plan | Upgrade Relays at WARVUE substation on WARVUE to HOPSON Ckt.84D. Upgrade Relays at Cedar Bayou substation on Cedar Bayou to HOPSON Ckt.84D. |  | WARVUE | HOPSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-02-28 03:00 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 | [5 empty] | Y | N |  | Cost included in Phase A. | 52374 | 52365
4488 | Campwood to Uvalde: Rebuild 69 kV line | Rebuild Campwood to Uvalde 69 kV line, built to 138 kV, but energized at 69 kV. |  | Campwood | Uvalde | Planned | 707 - 0877 | AEP TCC | Terry Weeks bcogan@aep.com 918-599-2857 | 2901 | 2021-03-01 |  | 138 | 0 | 37.1 | 0 |  | Real | Uvalde | Tier 3 |  | 2017-01-17 | 2017-03-20 | 2017-03-20 | 8230, 8633, 8231 | Y | N |  |  | 12057 | 4488
52284 | This adds a capacitor to Bell County |  |  | BellCounty | BellCounty | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2021-03-01 |  | 69 | 0 | 0 | 0 | 0,16 | Bell | Bell | Tier 4 |  |  |  |  | 133 | Y |  |  | 0 | 52285 | 52284
49812 |  |  |  | 5945059410 | 79689 |  |  | BPUB | Javier Martinez jamartinez@brownsville-pub.com 956-083-6530 |  | 2021-03-10 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 59410, 59450, 79689 | Y |  |  | 0 | 49813 | 49812
6255B | Rebuild BEVO to Brundage to Big Wells 69 kV lines. | Rebuild 69 kV line with 795 ACSR on 138 kV and double circuit capable structures 2015- NERC assessment |  | BEVO | Brundage | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-03-13 |  | 69 | 0 | 7.3 | 0 |  | Dimmit | Dimmit | Tier 4 |  |  |  |  | 5870, 5871 | Y | N |  | 0 | 45067 | 6255
57957 | Construct Copperhead 138 kV Switch | Construct Copperhead 138 kV Switch for new solar interconnection |  | Copperhead Switch |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5288 | 2021-03-15 01:00 |  | 138 | 0 | 0 | 0 |  | Fannin |  | Tier 4 |  |  |  |  | 11809, 1808, 11808, 143424 | Y | N |  | 0 | 57958 | 57957
47539 | Frelsburg Circuit Breaker Addition | Increase the reliability of transmission facilities on the T176 Fayetteville - Glidden 20.0-mile 138-kV transmission line. LCRA TSC will add three 138-kV, 3000A, 40kAIC circuit breakers in ring-bus configuration next to Frelsburg Substation. |  | Frelsburg Substation | Frelsburg Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-03-17 |  | 138 | 0 | 0 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  |  | 7263 | Y | N |  | 0 | 47540 | 47539
50344 | Rebuild MarkhamTap to Shropshire | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment and 2019 RTP |  | Markham Tap | Shropshire | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-03-20 |  | 69 | 0 | 1.87 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5554, 5555 | Y | N |  | 0 | 50345 | 50344
49548 | Esperanza: Construct New 138 kV Station | Esperanza: Construct New 138 kV Station | Update Schedule | Esperanza |  | Planned | 993 - 1171 | AEP | James Nivens bcogan@aep.com 918-599-2857 | 3742 | 2021-03-24 |  | 138 | 0.6 | 0 | 0 | 0,46.6 | Matagorda |  | Tier 4 |  |  |  |  | 8191, 8116, 8558 | Y | N |  | 0 | 49549 | 49548
5277 | Glidden Area Transmission Line Upgrade | Convert existing 69-kV lines (T544) from Glidden to Altair and (T545) from Altair to Nada to 138-kV transmission lines. Relocate existing 45 MVA auto from Glidden to Altair. Add a second new 45 MVA auto at Altair substation. |  | Glidden | Nada | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1016219 | 2021-03-26 |  | 138 | 0 | 0.77 | 45 |  | Colorado | Colorado | Tier 4 |  |  |  |  | 78107, 78111, 78115, 78118, 78170, 78171, 78520, 5536, 7258, 78103, 78106 | Y | N |  | 0 | 46205 | 5277
44395 | Dupont SW: Connect 138 kV Gen Tie Line | Connect 138 kV Victoria Port Generation Tie Line into Dupont SW |  | Dupont SW | Rupley | In-Service | 950 - 1128 | AEP TCC | Tommy Vannoy bcogan@aep.com 918-599-2857 | 3714 | 2021-03-30 |  | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 88142, 88143, 8143, 8172, 111343 | Y | N |  | 0 | 44396 | 44395
48109 | Dolan Creek: Construct 138 kV Box Bay | Dolan Creek: Construct 138 kV Box Bay |  | Dolan Creek |  | Planned | 930 - 1108 | AEP TCC/PEC | Alison Scribailo bcogan@aep.com 918-599-2857 | 3706 | 2021-03-30 |  | 138 | 0 | 0 | 0 |  | Val Verde | Sutton | Tier 4 |  |  |  |  | 8991, 88991, 8259, 8261, 72194 | Y | Y |  | 0 | 48147 | 48109
5205 | Carrizo Springs-Crystal City 69 kV Line: Rebuild | Rebuild Carrizo Spring to Crystal City 69 kV Line |  | Carrizo Springs | Crystal City | Under Construction | 761-0945 | AEP | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3569 | 2021-03-31 |  | 69 | 0 | 13.9 | 0 |  | Dimmit | Zavala | Tier 3 |  | 2017-07-12 | 2017-08-07 | 2017-08-21 | 8244, 8242 | Y | N |  |  | 12864 | 5205
5967 | Burma: Build new 69 kV station | Construct a new 69 kV station near the exsiting Grape Creek tap and reterminate the College Hills to Sterling City and Grape Creek to North San Angelo 69 kV lines into Burma |  | Burma |  | Planned | 845 - 1029 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 2688 | 2021-03-31 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6416, 60411, 6437, 6460, 6468 | Y | N |  |  | 13682 | 5967
44393 | Zapata: Add 138 kV Reactor | Add 138 kV Reactor at Zapata |  | Zapata |  | Under Construction | 949 - 1127 | ETT | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3713 | 2021-03-31 |  | 138 | 0 | 0 | 0 | -10,0 | Zapata |  | Tier 4 |  |  |  |  | 8299 | Y | N |  | 0 | 44394 | 44393
44485 | Pig Creek: Build 138 kV terminal | Interconnect 138 kV line to Tar Bush | Update Schedule | Pig Creek |  | Planned | 938 - 1116 | AEP TNC | Dave Baker mlforcum@aep.com 918-599-2674 | 2751 | 2021-03-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60393, 60436, 60385 | Y | N |  | 0 | 44486 | 44485
44858 | Luna 138 kV Station | Rayos Del Sol Solar interconnection |  | Mesquite | STEC Rangerville | Planned | 964 - 1142 | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | 3722 | 2021-03-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8656, 88656, 8554, 80103 | Y | N |  | 0 | 44859 | 44858
48778 | Dustdevil: Construct New Distribution Station | Dustdevil: Construct New Distribution Station | Update schedule | Laredo VFT North | Lobo | Planned | 1029 - 1207 | AEP | Michael Richardson bcogan@aep.com 918-599-2857 | 3768 | 2021-03-31 |  | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8038, 80013, 80221 | Y | N |  | 0 | 48779 | 48778
48782 | Progreso: Construct New Distribution Station | Progreso: Construct New Distribution Station | Update schedule | Rio Rico | Stewart Road | Planned | 1031 - 1209 | AEP | Brandon Cogan bcogan@aep.com 918-599-2857 | 3770 | 2021-03-31 |  | 69 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8040, 8751, 8949 | Y | N |  | 0 | 48783 | 48782
55270 | Stillman: Reterminate two AEP 138 kV lines | Stillman: Reterminate two AEP 138 kV lines |  | PUB Loma Alto | Stillman | Planned | 1036 - 1214 | AEP TCC | William Loveless bcogan@aep.com 918-599-2698 | 3775 | 2021-03-31 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 8333, 8337, 79689 | Y | Y |  | 0 | 55271 | 55270
55959 | Crosby to Highlands Ckt.08G Upgrades | Upgrade Crosby to Highlands Ckt.08G as a clearance project |  | Crosby | Highlands | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-03-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40390, 40811 | Y | N |  | 0 | 55960 | 55959
44804 | Tinsley: Build 138 kV station | Construct new 138 kV box bay on the Carver to Maxwell 138 kV line | Update Schedule | Tinsley |  | Planned | 957 - 1135 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 2761 | 2021-03-31 01:00 |  | 138 | 0 | 0 | 0 |  | Sutton |  | Tier 4 |  |  |  |  | 60440, 8259, 60412 | Y | N |  | 0 | 44805 | 44804
45032 | Brant: Build 69 kV station | Construct new 69 kV box bay on the Rock Springs to Sonora 69 kV line |  | Brant |  | Planned | 977 - 1155 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 2762 | 2021-03-31 01:00 |  | 69 | 0 | 0 | 0 |  | Sutton |  | Tier 4 |  |  |  |  | 60438, 6570, 8239 | Y | N |  | 0 | 45033 | 45032
45155 | Ollin: Build 138 kV station | Construct new Ollin 138 kV station |  | Ollin |  | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2752 | 2021-03-31 01:00 |  | 138 | 0.1 | 0 | 0 |  | Crane |  | Tier 4 |  |  |  |  | 6600, 6605, 6606, 6668, 6669, 60428, 60429, 60432, 60441, 6604, 6610, 6613, 6607, 6611, 60431, 76615 | Y | N |  | 0 | 45156 | 45155
45506 | Coulomb: Build 345 kV terminal | Interconnect TG East wind farm on the Clear Crossing to Edith Clarke 345 kV line | Update Schedule | Coulomb |  | Planned | 980 - 1158 | ETT | Michael Macias mlforcum@aep.com 918-599-2674 | 2821 | 2021-03-31 01:00 |  | 345 | 0 | 0 | 0 |  | Hardeman |  | Tier 4 |  |  |  |  | 60722 | Y | N |  | 0 | 45507 | 45506
50336 | Rebuild Pleasanton to Mccoy | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment and 2019 RTP |  | Pleasanton | McCoy | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-04-01 |  | 69 | 0 | 10.9 | 0 |  | Atascosa | Atascosa | Tier 4 |  |  |  |  | 5714, 5721 | Y | N |  | 0 | 50337 | 50336
57081 | Elara 138 bus and line to Palo Duro | Adds new Elara station to connect Elara Solar plant and a line to Palo Duro |  | Palo Duro | Elara | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-04-01 |  | 138 | 2.77 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5890, 5866 | Y | N |  | 0 | 57082 | 57081
6382 | Stewart Road: Construct 345 kV cut-in | Hairpin the North Edinburg to SU Palmito 345 kV line into new Stewart Rd 345 station. The hairpin will be constructed in a double circuit configuration, approximately 5 miles long. |  | Stewart Road | North Edinburg, SU Palmito | Planned | 874 - 1052 | ETT | Teresea Trotman bcogan@aep.com 918-599-2857 | 3661 | 2021-04-02 |  | 345 | 5 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 2 |  | 2015-07-10 | 2016-05-19 | 2016-06-14 | 80137, 5966, 8383 | Y | N |  |  | 14126 | 6382
6978 | Ranch Road 12 Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Ranch Road 12 Substation. |  | Ranch Road 12 |  | Planned | 1018923 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018923 | 2021-04-02 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7186 | Y | N |  |  | 14795 | 6978
51041 | Rio Pecos: Add bus breakers and bus differential | Add 138 kV bus tie circuit breakers | Update Schedule | Rio Pecos |  | Planned | 1043 - 1216 | AEP TNC | Thomas Neils mlforcum@aep.com 918-599-2674 | 2790 | 2021-04-06 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60452, 60453, 6601, 60014, 76595, 76600, 76615 | Y | N |  | 0 | 51042 | 51041
57882 | Add Vancourt POI for Vancourt Solar | Add Vancourt POI for Vancourt Solar at Luna |  | Luna | Vancourt | Planned | 1121 - 1299 | AEP | J Randy Weaver jrweaver@aep.com 918-599-2253 | 3840 | 2021-04-11 |  | 138 | 0.25 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 88657, 8656 | Y |  |  | 0 | 57883 | 57882
50340 | Rebuild Markham Tap to Van Vleck Sw | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment and 2019 RTP |  | Markham Tap | Van Vleck Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-04-15 |  | 69 | 0 | 4.65 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5554, 5556 | Y | N |  | 0 | 50341 | 50340
54436 | Kent Street Substation Upgrade | LCRA TSC will remove the capacitor bank at the Buttercup Substation, and add a new capacitor bank to the Kent Street Substation. |  | Kent Street |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-04-22 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7530, 7531 | Y | N |  | 0 | 54437 | 54436
57343 | Rosita Creek Substation 138-kV T2 Power Transformer Addition | Add second 138/12.47-kV power transformer bay with new 138-kV transmission switch and circuit switcher interconnected at LCRA Switch# 12669. New power transformer capacity will be 15/20/25 MVA. | No immediate projected load increase. Justification is to provide backup power source for critical medical center loads and to accommodate potential future load increases. | Pueblo | Escondido | Conceptual |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2021-04-25 |  | 138 | 0 | 0 | 0 |  | Maverick | Maverick | Tier 4 | [5 empty] | Y | N |  | 0 | 57344 | 57343
57731A | Hornsby Substation Addition | Cut-in a temporary 138-kV single-bus/single-breaker substation to the Austin Energy-owned Decker to Sand Hill 138-kV transmission line to initially serve the load via two modular stations, one mobile transformer and 24.9-kV bus work. | For total project cost please see 57731B | Decker | Sand Hill | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-04-27 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7916, 9187, 9216 | Y | N |  | 0 | 57732 | 57731
54086 | Fort Mason Circuit Breaker Addition | Provide transmission service to a generator. Upgrade 138-kV ring bus to accommodate new circuit termination. ERCOT Generation Interconnection or Change Request No. 21INR0365. |  | Fort Mason Substation | Fort Mason Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-04-29 |  | 138 | 0 | 0 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 76390 | Y | N |  | 0 | 54087 | 54086
5218B | San Miguel 345/138 kV autotransformer replacements | Replace T2 300 MVA autos with much larger autos |  | San Miguel |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-04-30 |  | 345 | 0 | 0 | 675 |  | Atascosa |  | Tier 4 |  |  |  |  | 5909, 5901, 5902 | Y | N |  | Delayed from 2018 to 2019 in the 2016 RTP. | 45091 | 5218
6201 | Alice - North Ella 69 kV Line | Rehab Alice - North Ella 69 kV Line |  | Alice | North Ella | Planned | 818 - 1002 | AEP TCC | Joe Yeagler bcogan@aep.com 918-599-2857 | 3614 | 2021-04-30 |  | 69 | 0 | 11.56 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 8500, 8878 | Y | N |  |  | 13926 | 6201
47432 | LULING - ZORN Transmission Line OverHaul | Increase the reliability of transmission facilities on the T158 Luling - Zorn 28.3-mile 138-kV transmission line. Increase the reliability and capacity of transmission facilities on the T158 Luling - Zorn 28.3-mile 138-kV transmission line. Tear down and rebuild all existing wood structures on the SC section from Seguin split to Luling and replace with 795 ACSR Drake conductor. Add OPGW. |  | Luling | Zorn | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-04-30 |  | 138 | 0 | 0 | 0 |  | Caldwell | Guadalupe | Tier 4 |  |  |  |  | 7180, 7222, 7224 | Y | N |  | 0 | 47433 | 47432
48784 | Rowe: Construct New Distribution Station | Rowe: Construct New Distribution Station |  | North McAllen | West McAllen | Planned | 1030 - 1208 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3769 | 2021-04-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8041, 8367, 8631 | Y | N |  | 0 | 48785 | 48784
50670 | Angstrom: Add new 345 kV Station | Angstrom: Add new 345 kV Station to serve SDI |  | Angstrom |  | Planned | 1050 - 1223 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 3776 | 2021-04-30 |  | 345 | 0.5 | 0 | 0 |  | San Patricio | Matagorda | Tier 4 |  |  |  |  | 8249, 88249, 5915, 8956 | Y | N |  |  | 50671 | 50670
51645 | Sand Crab: Add New Distribution Station | Sand Crab: Add New Distribution Station |  | Joslin | North Carbide | Planned | 1064 - 1237 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3799 | 2021-04-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8155, 8135, 8140, 8190 | Y |  |  | 0 | 51646 | 51645
52089 | Red Creek: Add new 345 kV terminal | Interconnect Bravepost Solar at the Red Creek 345 kV station |  | Red Creek |  | Planned | 1067 - 1240 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 2828 | 2021-04-30 |  | 345 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6444 | Y | N |  | 0 | 52090 | 52089
53953 | Eckert - Nebo Transmission Line Overhaul | LCRA TSC will perform an overhaul of T126 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T126 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  | Eckert | Nebo | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2021-04-30 |  | 69 | 0 | 0 | 0 |  | Gillespie | Gillespie | Tier 4 |  |  |  |  | 7122, 7124 | Y | N |  | 0 | 53954 | 53953
54115 | Lockhart Circuit Breaker Addition | Increase transmission service reliability to the Lockhart Substation. LCRA TSC will install two (2) 4000-A circuit breakers and associated terminal equipment such that Lockhart T2 has breakered connections to both 138-kV operating buses. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-04-30 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7216 | Y | N |  | 0 | 54116 | 54115
55596 | Clear Crossing: Install 345 kV terminal | Install 345 kV terminal at Clear Crossing to interconnect Azure Sky Solar & BESS | Update Contact | Clear Crossing |  | Planned | 1097 - 1275 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 1865 | 2021-04-30 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60464, 60515 | Y | N |  | 0 | 57651 | 55596
57645 | Hillje 345kV Danish Fields Solar (21INR0069) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Danish Fields Solar |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-04-30 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  | 0 | 57646 | 57645
57752 | West Columbia Roughneck Storage (19INR0176) | Install generator lead from CNP West Columbia substation to customer NORTCO substation for interconnection to Roughneck Battery Storage (19INR0176) |  | West Columbia |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-04-30 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 120321, 120322 | Y | N |  | 0 | 57753 | 57752
45174 | Ollin to LCRA Crane: Partial build, partial rebuild, and con | Build new Ollin 138 kV station; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage |  | Ollin | LCRA Crane | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2767 | 2021-04-30 01:00 |  | 138 | 0.52 | 0 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 6600, 6605, 6606, 6669, 60428, 60429, 60431, 60432, 60441, 6610, 6613, 6668, 76615 | Y | N |  | 0 | 45175 | 45174
45421 | McElroy to Sage: Rebuild 69 kV line | Build new Ollin 138 kV station with a 138/69 kV auto; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage |  | McElroy | Sage | Planned | 939 - 1117 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2768 | 2021-04-30 01:00 |  | 69 | 0 | 1.99 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 6604, 6607 | Y | N |  | 0 | 45422 | 45421
3463 | Shady Bus Split | Reconfigure 69kV bus |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.co 979-821-5763 |  | 2021-05-01 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 | [5 empty] | Y |  |  |  | 10843 | 3463
47936 | Pleasant Grove Rebuilds | Pleasant Grove Rebuilds |  | Midway (bus 185) | Calvert Switch (bus 73) | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2021-05-01 |  | 69 | 0 | 20.4 | 0 |  | Falls | Milam | Tier 4 |  |  |  |  | 73, 81, 185 | Y |  |  | 0 | 47937 | 47936
51744 | Buda Bus Upgrade | Upgrade the Buda bus from operate/transfer to breaker-and-a-half |  | Buda |  | Planned |  | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 |  | 2021-05-01 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7498 | Y | N |  | 0 | 51752 | 51744
51216D | Ward Winkler RPG | Re-conductor TNMP Wink - Oncor Wink 138kV line. Convert existing TNMP Wink - Oncor Wink 69kV line to 138kV. |  | TNMP Wink (37900) | Oncor Wink (1074) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-05-05 |  | 138 | 0 | 2.66 | 0 |  | Winkler | Winkler | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 1074, 1075, 37900, 37920 | Y |  |  | 0 | 56659 | 51216
5939 | Cooks Point Substation and Transmission Line Addition | Construct a load serving 138-kV substation in Northern Burleson County called Cooks Point. Construct a 16.7-mile single circuit 138-kV transmission line from Lyle Wolz to Cooks Point 138-kV transmission line with bundled 795 ACSR Drake (440 MVA). Bryan Texas Utilities will construct a 138-kV transmission line from Steele Store Substation to Cooks Point bundled 1033 ACSR Curlew (495 MVA). |  | Cooks Point | Lyle Wolz | Planned | 6666 | LCRATSC/BBEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017348 | 2021-05-07 |  | 138 | 16.7 | 0 | 0 |  | Burleson | Burleson | Tier 4 | 16RPG011 | 2016-07-07 |  |  | 7569, 7567 | Y | N |  |  | 13650 | 5939
58540 | Rebuild 16th St - Soaptree | NOMCR ID # 66719-1 |  | TNMP 16th Street (38310) | TNMP Soaptree (38450) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-05-12 |  | 138 | 0 | 31.83 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38310, 38450 | Y |  |  | 0 | 58541 | 58540
60459 | Rebuild Freeway Park-Mainland with 795 ACSS | Project previously associated with PMCR ID # 54118. NOMCR ID # 66716-1 | [5 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-05-12 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38820, 38830 | Y |  |  | 0 | 60460 | 60459
6984 | Rim Rock - Turtle Creek Transmission Line Storm Hardening | Overhaul and upgrade the 138-kV Rim Rock - Turtle Creek transmission line supporting circuit T270 with single 795 ACSR capable structures, single 795 ACSR conductor, and OPGW static. The planned T270 circuit rating is (MVA): Rate A=220, Rate B=220, Rate C=220. |  | Rim Rock | Turtle Creek | Planned | 1018968 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018968 | 2021-05-13 |  | 138 | 0 | 7.6 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7143, 7442 | Y | N |  |  | 14801 | 6984
5286B | Fayette Area Upgrades | Upgrade existing Plum - Flatonia (T133) TL with a minimum rating of 380 MVA and with OPGW. Upgrade terminal equipment at Plum to achieve a planned static normal and emergency rating of 530 MVA on Piney Creek - Plum (T535). | Planning In-Service Date Change. Updated to a phased project, the original TPIT project number is 5286. | Flatonia | Plum | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1019026, 1019024 | 2021-05-14 |  | 138 | 0 | 19.6 | 0 |  | Fayette | Fayette | Tier 4 | 17RPG011 | 2017-06-29 | 2017-07-28 |  | 7248, 7274, 7307 | Y | N |  |  | 14584 | 5286
6972 | Dimmit Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Dimmit Substation. |  | Dimmit |  |  |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-14 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  |  | 78281 | Y | N |  |  | 14789 | 6972
7115 | Quarry Field - Kyle Ranch 138 kV Line | Quarry Field - Kyle Ranch 138 kV Line |  | Quarry Field | Kyle Ranch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8384 | 2021-05-14 |  | 138 | 12 | 0 | 0 |  | Loving |  | Tier 4 |  |  |  |  | 11089, 11189 | Y |  |  |  | 14951 | 7115
44862 | Schottky: Build 69 kV Box bay | New Schottky 69 kV Station, replaces Hard Tap | Update Title and Schedule | Schottky |  | Planned | 971 - 1149 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3729 | 2021-05-14 |  | 69 | 0 | 0 | 0 |  | Live Oak |  | Tier 4 |  |  |  |  | 8507, 88507, 8400, 8406 | Y | N |  | 0 | 45151 | 44862
47034 | Gabriel- Rivery Transmission Line Storm Hardening | Overhaul and upgrade the 138-kV Gabriel - Rivery transmission line with bundled 795 ACSR capable structures, bundled 795 ACSR conductor (440 MVA), and OPGW static. |  | Gabriel | Rivery | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-14 |  | 138 | 2.4 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7346, 7347 | Y | N |  | 0 | 47035 | 47034
47440 | Rattler Substation Addition | Construct a new load-serving 138-kV substation. Rattler substation will be located on T262 transmission line between Redwood and McCarty Lane. |  | Rattler | Rattler | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-14 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7184, 7182, 7188 | Y | N |  | 0 | 47441 | 47440
47513 | Pooley Road Circuit Breaker Addition | LCRA TSC will convert Pooley Road Substation to ring bus configuration by installing three 138-kV, 3000A, 40kAIC circuit breakers. |  | Pooley Road Substation | Pooley Road Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-14 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7222 | Y | N |  | 0 | 47514 | 47513
54098 | Warda Winchester - Transmission Line Upgrade | Increase the transmission capacity of T170: Warda ¿ Winchester 138-kV transmission circuit. LCRA TSC will upgrade T170: Warda - Winchester transmission line to a minimum 105 degree F ambient temperature rating of 580 MVA at 138-kV using single 1433 Merrimack ACSS conductor with OPGW fiber addition. |  | Warda | Winchester | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-05-14 |  | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7306, 7312 | Y | N |  | 0 | 54099 | 54098
3821 | Pearsall to Palo Duro 138 kV line upgrade | Upgrade Pearsall to Palo Duro 138 kV line as recommended in 2013 RTP. Will investigate using a reconductor on existing structures with ACCC and other high temperature conductors. |  | Pearsall | Paloduro | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-05-15 |  | 138 | 0 | 10.8 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5866, 5895 | Y | N |  |  | 11278 | 3821
5408 | Herty N Sw. Sta. 138 kV Rebuild | Rebuild existing 138 kV switching station, it will be named Redland Switch after the completion of the project | Project Deferral | Herty North | Herty North | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6069 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3317, 3319 | Y | N |  |  | 13094 | 5408
6833 | Vineyard 138 kV Switching Station | Establish new 138 kV switching station | Project Deferral | Vineyard Switch |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3211 | 2021-05-15 |  | 138 | 4.2 | 0 | 0 |  | Tarrant | Tarrant | Tier 2 | 18RPG003 |  | 2018-08-17 |  | 2025, 555, 648, 2015, 12013, 2031 | Y | N |  |  | 14635 | 6833
47450 | Naruna Circuit Breaker Addition | LCRA TSC will increase the reliability of transmission facilities along T219 Burnet - Lampasas by adding three 138-kV, 3000A, 40kAIC circuit breakers in a ring bus configuration at Naruna Substation. |  | Naruna | Naruna | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Lampasas | Lampasas | Tier 4 |  |  |  |  | 7063 | Y | N |  | 0 | 47451 | 47450
50338 | Rebuild Van Vleck Sw to Bay City | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment |  | Van Vleck Switch | Bay City | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-05-15 |  | 69 | 0 | 1.23 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5556, 5560 | Y | N |  | 0 | 50339 | 50338
51228B | Construct Kennedale 138 kV Substation and Burleson 138 kV Sw | Construct Burleson 138 kV Sw |  | Burleson |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5294 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 1967, 1969, 2205, 2209, 12205 | Y |  |  | 0 | 52342 | 51228
52062 | Blackjack Creek POI | Blackjack Creek: Install POI for new Blackjack Creek WF |  | Grissom | Blackjack Creek | Planned | 1075 - 1248 | AEP TCC | Darren O'Hare bcogan@aep.com 918-599-2857 | 3800 | 2021-05-15 |  | 345 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 88670, 8624 | Y | Y |  | 0 | 52063 | 52062
52151 | Upgrade Elkton - Tyler Switch 138 kV Line | Upgrade Elkton - Tyler Switch 138 kV Line |  | Elkton | Tyler | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6079 | 2021-05-15 |  | 138 | 0 | 5.3 | 0 |  | Smith | Smith | Tier 4 |  |  |  |  | 3106, 3107, 3196, 3197 | Y |  |  | 0 | 52152 | 52151
52253 | Wink Switch 138 kV Terminal Addition | Add a 138 kV terminal at Wink Switch |  | Wink | Wink | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8503 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Winkler | Winkler | Tier 4 |  | 2019-03-01 | 2019-09-01 | 2019-10-01 | 1074 | Y |  |  | 0 | 52254 | 52253
52295 | Natural Dam 138 kV Switch | Upgrade the existing 138 kV Switch |  | Natural Dam | Natural Dam | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8308 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 11355, 11322, 11331, 23836 | Y |  |  | 0 | 52347 | 52295
52303 | Quarry Field 345/138 kV Switch | Construct a new 345/138 kV Switch |  | Quarry Field | Quarry Field | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8481 | 2021-05-15 |  | 345 | 0 | 0 | 600 |  | Loving | Loving | Tier 3 | 20RPG008 | 2020-05-18 | 2020-06-15 |  | 11188, 11194, 11216, 11010, 11084, 11189 | Y |  |  | 0 | 52494 | 52303
52309 | Horseshoe Springs Switch - Riverton Switch 138 kV Second Cir | Install a 2nd circuit on existing 138 kV structures |  | Horseshoe Springs | Riverton | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8526, R8452 | 2021-05-15 |  | 138 | 0 | 55 | 0 |  | Culberson | Reeves | Tier 3 | 20RPG012 | 2020-07-07 | 2020-08-10 |  | 11266, 11267, 11268, 11269, 11271, 11272, 11083, 11090, 11112, 11183, 11190 | Y |  |  | 0 | 56599 | 52309
52827 | Keller Wall Price 138 kV Capacitor Banks | Upgrade the existing 138 kV capacitor banks at Keller Wall Price |  | Keller Wall Price |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5223 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 2037, 2038 | Y |  |  | 0 | 52828 | 52827
57754 | Install Quinlan Tap 138/69 kV Autotransformer | Install Quinlan Tap 138/69 kV Autotransformer |  | Quinlan Tap |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3058 | 2021-05-15 |  | 138 | 0 | 0 | 47 |  |  |  | Tier 4 |  |  |  |  | 2729, 12729, 12730, 2471, 2730, 12470 | Y |  |  | 0 | 59517 | 57754
57857 | Ennis West Switch 138 kV Reconfiguration | Reconfigure existing 138 kV Switch |  | Ennis West |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4311 | 2021-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  | 0 | 57858 | 57857
6792 | Anna - Anna Tap 138 kV Line | Upgrade existing Anna Switch - Anna Tap 138 kV Line |  | Anna Switch | Anna Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4314 | 2021-05-15 01:00 |  | 138 | 8.3 | 8.3 | 0 |  | Collin | Collin | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 12705, 2340, 2374, 2520, 2528, 2704, 12704 | Y | N |  | 0 | 49821 | 6792
49834 | Fullerton 138 kV Switch Terminal Addition | Fullerton 138 kV Switch Terminal Addition |  | Fullerton | Fullerton | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9037 | 2021-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1274, 11275, 1272, 11274, 11277, 11284 | Y |  |  | 0 | 49835 | 49834
45541 | Watermill Switch - Camp Wisdom 138 kV Line | Upgrade the Camp Wisdom - Witt Road 138 kV Line Section |  | Camp Wisdom | Witt Road | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4216 | 2021-05-15 12:00 |  | 138 | 0 | 6.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2988, 2989, 2990, 3068 | Y |  |  | 0 | 52172 | 45541
45545 | Norwood Switch - Denton Drive 138 kV DCKT Line | Upgrade the Norwood Switch - Denton Drive 138 kV DCKT Line |  | Norwood Switch | Denton Drive Switch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | m4245 | 2021-05-15 12:00 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2405, 2407, 2488, 2796, 2797, 12487, 2487, 2800, 2801 | Y |  |  | 0 | 45546 | 45545
48822 | Carrollton East - Renner_Northaven Double-circuit Line | Upgrade existing line |  | Carollton East | Alpha Road And Knoll Trail | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4232 | 2021-05-15 12:00 |  | 138 | 0 | 13 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2571, 2575, 2582, 2583, 2584, 2596, 2578, 2598, 2613 | Y | N |  | 0 | 49080 | 48822
49841 | Fullerton_to_NorthAndrews_138_kV_Conversion_East | Fullerton_to_NorthAndrews_138_kV_Conversion_East |  | Fullerton | North Andrews | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9038 | 2021-05-16 |  | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1285, 1159, 1160, 11274, 11275 | Y |  |  | 0 | 49842 | 49841
47434 | Zorn Auto Replacement | Increase the reliability of substation equipment at Zorn Substation through replacement of the Zorn AT1 autotransformer. |  | Zorn | Zorn | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-05-17 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7042 | Y | N |  | 0 | 47435 | 47434
49858 | Fullerton_to_NorthAndrews_138_kV_Conversion_West | Fullerton_to_NorthAndrews_138_kV_Conversion_West |  | Fullerton | North Andrews | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9039 | 2021-05-17 |  | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1160, 1267, 1270, 11274, 1159, 1272, 11275 | Y |  |  | 0 | 49859 | 49858
6789 | Wirtz to Johnson City to Mountain Top Rebuild to 138kV | Rebuild the Wirtz to Johnson City to Mountain Top 69kV Line and convert to 138kV. Convert Johnson City Substation to 138kV. |  | Johnson City | Mountain Top | Under Construction |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2021-05-20 |  | 138 | 0 | 25 | 0 |  | Burnet | Blanco | Tier 4 | 17RPG015, 18RPG009 | 2017-10-01 | 2017-12-01 |  | 7104, 7107, 7110, 7514, 7516, 7148, 7480 | Y | N |  | 0 | 51771 | 6789
6974 | New Bremen Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at New Bremen Substation. |  | New Bremen |  | Planned | 1018919 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018919 | 2021-05-24 |  | 138 | 0 | 0 | 0 |  | Austin |  | Tier 4 |  |  |  |  | 7271, 7270, 7273 | Y | N |  |  | 14791 | 6974
56098 | Turtle Creek Substation Upgrade | LCRA TSC will change the SB/SB configuration to a four-breaker ring bus and replace all three existing CBs (8810, 8820, and 8830) at Turtle Creek Substation. |  | Turtle Creek |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018970 | 2021-05-25 |  | 138 | 0 | 0 | 0 |  | Kerr |  | Tier 4 |  |  |  |  | 7442 | Y |  |  | 0 | 56099 | 56098
50658 | Friendswood to Mustang Bayou Ckt.04A Upgrades | Upgrade 138kV Ckt.04A Friendswood tap to Mustang Bayou to increase thermal limits. |  | Friendswood Tap | Mustang Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-28 |  | 138 | 0 | 2.19 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42652, 42960 | Y | N |  | 0 | 50816 | 50658
4186F | University Area 138kV Conversions | Disconnect Ckt.12B and Ckt.30A at University and Reconnect 69kV circuits to create New Ckt.xx GENRAL to Garden Villas |  | Garden Villas | Genral | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2021-05-30 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47755, 42690, 47560, 47670, 47762 | Y | N |  | Cost included in Phase D | 57373 | 4186
6325 | Install two distribution transfomers at Jones Creek | Install two distribution transformers at Jones Creek. Tap Ckt.59 Jones Creek to Freeport/Surfside and Ckt.59 Jones Creek to CORTEZ |  | Jones Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42546, 42547, 42541, 42542, 42645, 43440 | Y | N |  | 0 | 51031 | 6325
6668A | Freeport - Master Plan | Upgrade Ckts. 18 & 27 DOW to Jones Creek to increase thermal limits |  | DOW | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 | 17RPG005 | 2017-04-04 | 2017-06-05 | 2017-12-12 | 42500, 42530 | Y | N |  | 0 | 58255 | 6668
43511 | Keystone Capbank in TNMP West Texas System | Transfer West Texas spare 69kV 10MVar capacitor bank to Keystone Substation. Project delayed. |  | East Toyah (Bus #38129) | Keystone (Bus #38290) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-05-30 |  | 69 | 0 | 0 | 0 | 0,10 | Reeves | Winkler | Tier 4 |  |  |  |  | 38290 | Y |  |  | 0 | 48418 | 43511
52181 | ENCO (ENC) 138kV Substation | Install new customer-owned 138kV ENCO (ENC) substation. Loop into existing Ckt.91A between PH Robinson and El Dorado |  | ENCO |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47780, 42015, 42561 | Y | N |  | 0 | 52182 | 52181
52197B | Jordan Auto A3 Addition (PLACID 138kV Sub) | Loop Ckt 97C-1 Chambers-King into Jordan 345kV |  | Chambers | King | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-05-30 |  | 345 | 0 | 0 | 0 |  | Chambers | Harris | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 40255, 40850, 40900 | Y | N |  | Cost included in Phase A | 57346 | 52197
52555 | Wallis to East Bernard Ckt.65C Upgrades | Upgrade Ckt.65C Wallis to East Bernard to increase thermal limits. |  | East Bernard | Wallis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-30 |  | 138 | 0 | 8.17 | 0 |  | Wharton | Austin | Tier 4 |  |  |  |  | 44190, 44740 | Y | N |  | 0 | 52556 | 52555
4186D | University Area 138kV Conversions | Remove University Auto A1 from service |  | University |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2021-05-30 |  | 138 | 0 | 0 | 0 | -200,0 | Harris |  | Tier 4 |  |  |  |  | 49030, 47755, 47760 | Y | N |  | Cost included in 4186A | 57371 | 4186
5717 | Waller 138kV Substation Reconfiguration | Convert Waller substation from single-circuit radial service to radial & tap service. Install new tap section from Ckt.65 Hockley to Peters. |  | Waller | Hockley/Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 2.4 | 0 | 0 |  | Harris | Austin | Tier 4 |  |  |  |  | 46564, 46560, 45880, 45885, 46220, 46511 | Y | N |  |  | 13459 | 5717
6022 | Stamford to Haskell Tap 1 69 kV line: Rebuild 69 kV line | Rehab Stamford to Haskell Tap 1 69 kV line |  | Stamford | Haskell Tap 1 | Planned | 786 - 0971 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2668 | 2021-05-31 |  | 69 | 0 | 12.22 | 0 |  | Jones | Haskell | Tier 4 |  |  |  |  | 6171, 6172 | Y | N |  |  | 13739 | 6022
6029 | Anson to Stamford 69 kV line: Rebuild 69 kV line | Rehab Anson to Stamford 69 kV line |  | Anson | Stamford | Planned | 786 - 0971 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2667 | 2021-05-31 |  | 69 | 0 | 16.08 | 0 |  | Jones | Jones | Tier 4 |  |  |  |  | 6173, 6175, 6172, 6180 | Y | N |  |  | 13753 | 6029
43284G | Baytown Area Upgrades | Upgrade Ckt.87 Cedar Bayou to Cedar Bayou tap to increase thermal ratings |  | Cedar Bayou | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 2.39 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40011, 40015 | Y | N |  | Overall cost for 2020 project included in 6585E | 56060 | 43284
44359 | Solstice: Install 138 kV PST and capacitor bank | Install PST on the Fort Stockton Plant to Solstice 138 kV line at Solstice, install capacitor bank on the Solstice 138 kV bus | Update Schedule | Solstice |  | Planned | 984 - 1162 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2734 | 2021-05-31 |  | 138 | 0 | 0 | 0 | 0,14.4 | Pecos |  | Tier 3 |  | 2017-12-22 | 2018-02-02 |  | 60384, 6645, 60717, 6630, 60385 | Y | N |  | 0 | 44360 | 44359
44872 | Asherton 138 kV Station | Add breaker at Asherton 138 kV Station to Accommodate Shakes Solar |  | Asherton | - | Planned | 966 - 1144 | AEP | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3724 | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  |  | 88283, 8283 | Y | N |  | 0 | 44873 | 44872
48774 | Fincas: Construct New Distribution Station | Fincas: Construct New Distribution Station |  | Gateway Tap West | Wormser | Planned | 1026 - 1204 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3765 | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8039, 8295, 8650 | Y | N |  | 0 | 48775 | 48774
48780 | Pantera: Construct New Distribution Station | Pantera: Construct New Distribution Station |  | Wesmer | Weslaco SW | Planned | 1027 - 1205 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3766 | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8033, 8347, 8348 | Y | N |  | 0 | 48781 | 48780
49576 | Hayter: Build 138 kV box bay | Construct new 138 kV box bay on the Alamito Creek to Solstcie 138 kV line |  | Hayter |  | Planned | 1025 - 1203 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 2788 | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 6680, 60385, 60444 | Y | N |  | 0 | 49577 | 49576
51216E | Ward Winkler RPG | Construct two 138kV tie-lines between TNMP Cedarvale and Oncor Sand Lake. |  | TNMP Cedarvale (38145) | Oncor Sand Lake (11097) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-05-31 |  | 138 | 1.56 | 0 | 0 |  | Ward | Ward | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 11097, 38145 | Y |  |  | 0 | 56660 | 51216
52068 | Pleasanton to Three Rivers: Rebuild 69 kV line | Rebuild Pleasanton to Three Rivers 69 kV line |  | Pleasanton | Three Rivers | Planned | 1077 - 1250 | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | 3802 | 2021-05-31 |  | 69 | 0 | 0.06 | 0 |  | Atascosa | Live Oak | Tier 4 |  |  |  |  | 8200, 8400, 8406, 8507, 8600 | Y | N |  | 0 | 52069 | 52068
52141 | Cedar Bayou 138kV - West Bus In-Series 10-Ohm Reactor | Cedar Bayou 138kV - West Bus In-Series 10-Ohm Reactor |  | Cedar Bayou | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40015, 40020 | Y | N |  | 0 | 52142 | 52141
52167B | El Dorado 10.8 MVar Cap Bank | Install old harrisburg cap bank at El Dorado (Electrically connected to Ckt.91) |  | El Dorado/Harrisburg |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 | 0,10.8 | Harris |  | Tier 4 |  |  |  |  | 42561 | Y | N |  | 0 | 55385 | 52167
52173 | Spencer 7.2MVar Cap Bank | Install Spencer 7.2MVar Distribution Cap Bank (Electrically connected to Ckt.91) |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 | 0,7.2 | Harris |  | Tier 4 |  |  |  |  | 43272 | Y | N |  | 0 | 52174 | 52173
52197A | Jordan Auto A3 Addition (PLACID 138kV Sub) | Install 800 MVA Jordan Auto A3 |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-05-31 |  | 345 | 0 | 0 | 800 |  | Chambers | Chambers | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 49079, 40850, 40855 | Y | N |  | 0 | 57345 | 52197
52197E | Jordan Auto A3 Addition (PLACID 138kV Sub) | Upgrade Ckt.86J Bender to Jordan to increase thermal limits. |  | Bender | Jordan | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 40155, 40390, 40856, 40670, 40855 | Y | N |  | 0 | 57349 | 52197
52365I | Spillman Island Restoration Plan | Upgrade Ckt.83A Cedar Bayou to DECKER to increase thermal limits. |  | Cedar Bayou | DECKER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Harris | Tier 4 |  |  |  |  | 40439, 40430 | Y | N |  | Cost included in Phase A. | 52375 | 52365
52519C | Jones Creek Area Reconfigurations | Unbundle existing Ckt.02G Velasco to Jones Creek to create parallel circuits Ckt.02G and Ckt.36y Velasco to Jones Creek. This project entry is for Ckt.36y. Reconnect existing Jones Creek cap bank #2 to this line position (Should be installed as fixed 120MVAr cap bank #2). Reconnect existing Jones Creek cap bank #1 to the 48JCKCTZ line position at Jones Creek (Should be installed as switched 160MVAr cap bank #1). |  | Velasco | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42541, 42542, 42540, 42546, 42547, 43360 | Y | N |  | Cost included in Phase A. | 59983 | 52519
52519B | Jones Creek Area Reconfigurations | Unbundle existing Ckt.02G Velasco to Jones Creek to create parallel circuits Ckt.02G and Ckt.36y Velasco to Jones Creek. This project entry is for Ckt.02G. Existing Jones Creek fixed cap bank #3 will remain on this line with no expected change in capacity. |  | Velasco | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42150, 42540, 42543, 43212, 43360, 42210, 43221, 43363 | Y | N |  | Cost Included in Phase A. | 59984 | 52519
52519A | Jones Creek Area Reconfigurations | Reconfigure existing Ckt.02H COPPER to Velasco to create new Ckt.36x COPPER to Jones Creek. |  | Copper | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42195, 42199, 42210, 42215, 42540, 43211, 43360, 43222, 48006 | Y | N |  | 0 | 59982 | 52519
52529 | Jordan to Cities to Dalton Ckt.86I | Upgrade Ckt.86I Jordan to Cities to Dalton to increase thermal limits. |  | Jordan | Dalton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40340, 40855, 40740, 40857 | Y | N |  | 0 | 52530 | 52529
53854 | Avenger: Build 69 kV station | Construct new 69 kV station on the Putnam to Cross Plains 69 kV line |  | Avenger |  | Planned | 1084 - 1257 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1854 | 2021-05-31 |  | 69 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  |  | 60457, 6312, 6357 | Y | N |  | 0 | 53855 | 53854
55628 | Rio Hondo: Upgrade 138 kV terminal | Upgrade 138 kV STEC East Rio Hondo terminal at Rio Hondo |  | Rio Hondo |  | Planned | 1103 - 1281 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3821 | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8319 | Y |  |  | 0 | 55629 | 55628
55630 | Lobo: Install 345 kV terminal | Install terminal at Lobo to interconnect Corazon Solar, build 345 kV line from Lobo to Corazon Solar |  | Lobo | Corazon Solar | Planned | 1098 - 1214 | ETT | Adam Wells bcogan@aep.com 918-599-2857 | 3775 | 2021-05-31 |  | 345 | 4.5 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 80599, 80219 | Y | Y |  | 0 | 55631 | 55630
55789 | Rebuild 138 kV line from Big Foot to Moore SW | Big Foot to Moore SW: Rebuild 138 kV line |  | Big Foot | Moore | Planned | 1108 - 1286 | AEP TCC/STEC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3828 | 2021-05-31 |  | 138 | 0 | 6.09 | 0 |  | Frio | Frio | Tier 2 |  | 2019-11-19 | 2020-04-19 |  | 8221, 5827 | Y | Y |  | 0 | 55790 | 55789
55957 | COUGAR to Gulfgate Ckt.91 Upgrades | Upgrade Ckt.91 COUGAR to Gulfgate tap to minimum 478MVA emergency rating |  | COUGAR | Gulfgate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42741, 47560 | Y | N |  | 0 | 55958 | 55957
55963 | Pearland 40 MVAr Cap Bank | Install Pearland 40 MVAr Cap Bank tapped on Ckt.06K |  | Pearland |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 | 0,40 | Brazoria |  | Tier 4 |  |  |  |  | 43051 | Y | N |  | 0 | 55964 | 55963
57514 | Jeanetta Auto A1 Upgrade | Upgrade Jeanetta Auto A1 |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47300, 47310, 49024 | Y | N |  | 0 | 57515 | 57514
57518A | Wortham 138kV Distribution Substation | New Ckt.21G CAMRON to Wortham tap to TH Wharton. |  | Wortham | CAMRON/TH Wharton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45101, 45515, 45700 | Y | N |  | 0 | 57520 | 57518
57518B | Wortham 138kV Distribution Substation | New Ckt.76A Gertie tap to Wortham tap to Satsuma tap |  | Wortham | Gertie/Satsuma | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45102, 44900, 44910, 45500, 45610, 45802, 45811, 46301, 46302, 45515, 46312 | Y | N |  | Cost included in main entry | 57519 | 57518
57534B | Heights and White Oak Upgrades | Upgrade Ckt.34A Heights - White Oak |  | Heights | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46620, 47680 | Y | N |  | 0 | 57536 | 57534
57534A | Heights and White Oak Upgrades | Install New 200MVA White Oak 138-69kV Auto A4. |  | White Oak |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 200 |  | Harris |  | Tier 4 |  |  |  |  | 49021, 46615, 46620 | Y | N |  | 0 | 57535 | 57534
57642A | Hayes Ckt.09A Loop Upgrade | Upgrade Ckt.09A Britmoore to Hayes to increase thermal limits |  | Britmoore | Hayes | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0.1 | 0 |  |  |  | Tier 4 |  |  |  |  | 44120, 44310 | Y | N |  | 0 | 57644 | 57642
57647 | Hillje 345kV Ramsey Solar (20INR0130) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Ramsey Solar. Reposition existing Ckt.72 Hillje to Bailey |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44200, 44040 | Y | N |  | 0 | 57648 | 57647
57859 | West Galveston New Distribution Transformer | Install 3rd distribution transformer at West Galveston substation. Tap from Ckt.01B to create new Galveston 26th Street to West Galveston tap to Webster |  | West Galveston | Galveston 26th Street/Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 43403, 42670, 43400, 43500, 43401 | Y | N |  | 0 | 57860 | 57859
59207 | Missouri City (MC) Distribution Transformer TR1 | Missouri City (MC) 3rd distribution transformer TR1 tapped on Ckt.02A Blueridge tap to Dewalt |  | Missouri City | Blueridge/Dewalt | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Harris | Tier 4 |  |  |  |  | 44481, 44482, 44483, 44081, 44082, 44180, 44342, 44652, 44672, 47150 | Y | N |  | 0 | 59208 | 59207
59585 | Avogadro: Build new 345 kV station | Interconnect Griffin Trail wind farm on the Clear Crossing to Edith Clarke 345 kV line | Update Schedule | Avogadro |  | Planned | 1017 - 1195 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 2778 | 2021-05-31 |  | 345 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 60420, 60506, 60500, 60700 | Y | N |  | 0 | 59586 | 59585
57642B | Hayes Ckt.09A Loop Upgrade | Upgrade Ckt.09A Hayes to Alief to increase thermal limits |  | Hayes | Alief | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-05-31 |  | 138 | 0 | 0.1 | 0 |  |  |  | Tier 4 |  |  |  |  | 44020, 44310 | Y | N |  | Cost included in main entry | 57643 | 57642
08TPIT0033 | Gilleland to Techridge 138kV Circuit | Establish a new 138kV circuit from Gilleland to Techridge and maintain a normally close tie between AEN and LCRA's switchyard at Gilleland. |  | Gilleland Substation | Techridge Substation | In-Service |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_4276 PLAN_117_P207 | 2021-06-01 |  | 138 | 8 | 0 | 0 |  | Travis | Travis | Tier 2 |  |  | 2009-07-21 | 2009-07-21 | 9054, 9191, 7336, 9190 | Y | N |  |  | 8205 | 1029
4323 | CPSE_Braunig to Brooks_MLSE | Upgrade terminal at Brooks and ensure a rating of 2000 A (minimum) at both Braunig and Brooks terminals |  | Braunig | Brooks | In-Service |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0669 | 2021-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5045 | Y | Y |  |  | 11875 | 4323
5417 | Buckeye to LA_HTS Rebuild | Rebuild 1.8 mile 138 kV t-line from Buckeye to LA_Hts. Upgrade line terminal at Buckeye Station for Buckeye to LA_HTS t-line. |  | Buckeye | LA_Hts | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0266, S-0899a | 2021-06-01 |  | 138 | 0 | 1.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5050, 5285 | Y |  |  |  | 13105 | 5417
6281 | CPSE_Harlandal_Sommers_MLSE | Upgrade terminals at Harlandale and Sommers Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0732 | 2021-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5395 | Y |  |  |  | 14013 | 6281
6931 | New Tres Lagos Substation | Adds new station and short line from W Edinburg-Alton line |  | West Edinburg | Alton | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-06-01 |  | 138 | 1.8 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5770, 5771, 5772 | Y | N |  |  | 14750 | 6931
44944 | Burnet-Bertram-Andice 138kV Conversion | Rebuild Burnet to Bertram to Andice 69 kV line and convert to 138 kV. |  | Burnet | Andice | Under Construction |  | PEC | Tony Perez jesus.perez@peci.com 830-868-5158 |  | 2021-06-01 |  | 138 | 0 | 21.9 | 0 |  | Burnet | Williamson | Tier 3 |  |  |  |  | 7520, 7521, 7097, 7100, 7522 | Y | N |  | 0 | 51770 | 44944
45573 | Hayter Ranch Substation Addition | Construct a new 138-kV Hayter Ranch substation. The Hayter Ranch Substation will be located on the Alamito Creek to Solstice 138-kV transmission line. The total length of the line is 68.12 miles and the Hayter Ranch substation will be approximately 8.5 miles from Solstice. |  | Alamito Creek | Solstice | Planned |  | LCRATSC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2021-06-01 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 78925, 60444 | Y | N |  | 0 | 45574 | 45573
50643 | CPSE_Spruce_Skyline MLSE | Upgrade terminals at Spruce and Skyline to ensure a 3000 A rating (minimum). |  | Skyline | Spruce | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0899b/S-0899c | 2021-06-01 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5371, 5400 | Y |  |  | 0 | 50644 | 50643
51216C | Ward Winkler RPG | Re-conductor Pecos to Cedarvale (both lines D & E). |  | Pecos (38091) | Cedarvale (38145) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-06-01 |  | 138 | 0 | 15.12 | 0 |  | Reeves | Ward | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 38091, 38145 | Y |  |  | 0 | 56658 | 51216
52245 | CONSTRUCT OGALLALA TO BLACKWATER DRAW 345 KV LINE | REBUILD ABERNATHY SW AND RENAME BLACKWATER DRAW. CONSTRUCT OGALLALA TO BLACKWATER 345 KV LINE, LPL INTEGRATION |  | OGALLALA | BLACKWATER DRAW | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3002, R3003, R3005 | 2021-06-01 |  | 345 | 0 | 0 | 0 |  | Castro | Hale | Tier 1 |  | 2015-12-29 | 2016-06-09 |  | 23920, 23912 | Y |  |  | 0 | 52246 | 52245
57052B | Adds Attwater Switching Station for Topaz POI | Attwater-Topaz POI transmission line |  | Attwater (Bus # 38745) | Topaz (Bus # 111971) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-06-01 |  | 138 | 1.03 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38745, 42015, 111971 | Y |  |  | 0 | 57231 | 57052
50672 | Black Cat: New 138 kV Distribution Station | Black Cat: In & Out capable bus with manual bus tie switch for double bank station |  | Bay City | Conoco | Planned |  | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 |  | 2021-06-02 |  | 138 | 0 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 80124, 8547, 8549, 8113, 8138 | Y | N |  |  | 50673 | 50672
52258 | CONSTRUCT BLACKWATER DRAW TO FOLSOM POINT345 KV LINE | CONSTRUCT FOLSOM POINT SWITCH AND BLACKWATER DRAW TO FOLSOM POINT 345 KV LINE, LPL INTEGRATION |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3007, R3011 | 2021-06-02 |  | 345 | 23.3 | 0 | 0 |  | Hale | Lubbock | Tier 1 |  | 2015-12-29 | 2016-06-09 |  | 23926, 23920, 59156 | Y |  |  | 0 | 52259 | 52258
52299 | CONSTRUCT BLACKWATER DRAW TO DOUBLE MOUNTAIN | CONSTRUCT DOUBLE MOUNTAIN SWITCH AND BLACKWATER DRAW TO DOUBLE MOUNTAIN 345 KV LINE, LPL INTEGRATION |  | BLACKWATER DRAW | DOUBLE MOUNTAIN | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3001, R3008 | 2021-06-03 |  | 345 | 33 | 0 | 0 |  | Hale | Lubbock | Tier 1 |  | 2015-12-29 | 2016-06-09 |  | 23928, 23920, 59178 | Y |  |  | 0 | 52300 | 52299
52307 | CONSTRUCT DOUBLE MOUNTAIN TO FIDDLEWOOD TO FARMLAND 345 KV L | CONSTRUCT FIDDLEWOOD SWITCH AND DOUBLE MOUNTAIN TO FIDDLEWOOD TO FARMLAND 345 KV LINE, LPL INTEGRATION |  | DOUBLE MOUNTAIN | FARMLAND | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R3004, R3006, R3009, R3010 | 2021-06-04 |  | 345 | 49.3 | 0 | 0 |  | Lubbock | Lynn | Tier 1 |  | 2015-12-29 | 2016-06-09 |  | 23930, 23924, 23928, 59196 | Y |  |  | 0 | 52308 | 52307
52570 | INSTALL 75MVAR REACTOR |  |  | DOUBLE MOUNTAIN | DOUBLE MOUNTAIN | Planned |  | ONCOR | CHARLES SAKER | R3016 | 2021-06-05 |  | 345 | 0 | 0 | 0 | -75,0 | Lubbock | Lubbock | Tier 4 |  |  |  |  | 23928 | Y |  |  | 0 | 52571 | 52570
52587 | INSTALL 75MVAR REACTOR |  |  | FIDDLEWOOD | FIDDLEWOOD | Planned |  | ONCOR | CHARLES SAKER | R3017 | 2021-06-05 |  | 345 | 0 | 0 | 0 | -75,0 | Lubbock | Lubbock | Tier 4 |  |  |  |  | 23930 | Y |  |  | 0 | 52588 | 52587
57165 | Red Gate138/69 autotransformer and lines to McCook and Faysv | Adds 69 kV bus at Red Gate, a 138/69 autotransformer at Red Gate, and connects 69 kV lines to McCook#1 and Faysville Switch. |  | Redgate | McCook and Faysville Switch | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-06-05 |  | 69 | 1 | 0 | 50 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5780, 5782, 5783, 8377, 161031 | Y | N |  | 0 | 57166 | 57165
57904 | Brightside Temporary Connection | Build Brightside Temporary Connection |  | Beeville | Three Rivers | Planned | 1113 - 1291 | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2674 | 3832 | 2021-06-11 |  | 138 | 0 | 0 | 0 |  | Bee | Live Oak | Tier 4 |  |  |  |  | 84006, 8199, 8400 | Y | N |  | 0 | 57905 | 57904
54757 | This is related to GINR20INR0083 | This is a switching station to interconnect new generation project 20INR0083 Baird North Wind Project |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2021-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68008, 68006, 68010 | Y |  |  | 0 | 54758 | 54757
44372 | Geronimo T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Geronimo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-06-25 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7606 | Y |  |  | 0 | 44373 | 44372
5838 | New Katz Auto to Benjamin 138 kV | Joint project with AEP to add autotransformer from Katz (bus# 774) to Katz8 (bus #798) and new line to Benjamin (bus # 6088) when AEP converts to 138 kV and builds line from the new Tardis switching station | [5 empty] | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 15016 | 2021-06-28 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | 16RPG002 | 2016-02-03 | 2016-05-30 |  | 790, 798, 33798, 745, 774, 6088, 6087 | Y |  |  |  | 14961 | 5838
5274 | Camp Wood - Leakey Transmission Line Overhaul | Rebuild T269 Camp Wood to Leakey to be 138-kV capable with a nominal conductor rating of 223 MVA at 138-kV (Single Drake) with OPGW and operated at 69-kV. |  | Camp Wood | Leakey | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1016183 | 2021-06-30 |  | 69 | 0 | 17.3 | 0 |  | Real | Real | Tier 4 | 15RPG026 | 2015-12-16 | 2016-01-27 |  | 7426, 8633 | Y | N |  |  | 12950 | 5274
5604 | Stewart Road: Construct 345 kV cut-in | Construct new 345 kV 4 breaker ring bus station at AEP Stewart Rd, with two 675 MVA 345/138 autotransformers connected to Stewart Rd 138 station. Hairpin the North Edinburg to SU Palmito 345 kV line into new Stewart Rd 345 station. The hairping will be constructed in a double circuit configuration, approximately 5 miles long. Also install 100 Mvar shunt reactor at the new Stewart Rd 345 kV station. |  | Stewart Road |  | Planned | 792 - 0977 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 3582 | 2021-06-30 |  | 345 | 0 | 0 | 1350 | -100,0 | Hidalgo | Hidalgo | Tier 2 |  | 2015-07-10 | 2016-05-19 | 2016-06-14 | 80137, 8951 | Y | N |  |  | 13334 | 5604
6121 | Sunchase - South Padre Island 138 kV Line | Rebuild Sunchase - South Padre Island 138 kV Line |  | Sunchase | South Padre Island | Planned | 826 - 1010 | AEP TCC | Kenneth Haley bcogan@aep.com 918-599-2857 | 3625 | 2021-06-30 |  | 138 | 0 | 3.33 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8335, 8917 | Y | N |  |  | 13847 | 6121
6712 | Soda Lake Substation Addition | Construct a new substation named Soda Lake off the LCRA Crane to Rio Pecos (T451) transmission line to support a generation interconnection request (18INR0040). |  | LCRA Crane | Rio Pecos | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018761 | 2021-06-30 |  | 138 | 0 | 0 | 0 |  | Crane | Crockett | Tier 4 |  |  |  |  | 76026, 6601, 60014 | Y | N |  |  | 14495 | 6712
7077 | Horse Crossing - Rio Pecos Transmission Line Addition | Construct a new 138-kV transmission line to a new radially connected generator-serving substation called Horse Crossing from Rio Pecos using double 795 26/7 ACSR Drake OPGW static. The planned transmission circuit rating will be (MVA): Rate A=439, Rate B=448, Rate C=448. |  | Horse Crossing | Rio Pecos | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018600 | 2021-06-30 |  | 138 | 0.9 | 0 | 0 |  | Crane | Crockett | Tier 4 |  |  |  |  | 76601, 76602, 6601 | Y | N |  |  | 14909 | 7077
50452 | LCRATSC_Clear Springs AT1 | Replacing the failed Auto-transformer with like and kind Auto-transformer. |  | Clear Springs | Clear Springs | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 77683 | Y | N |  | 0 | 50453 | 50452
52523A | Hayes to WA Parish Ckt.09A Upgrades | Upgrade Ckt.09A Hayes to Alief as a Clearance upgrade |  | Hayes | Alief | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-06-30 |  | 138 | 0 | 1.7 | 0 |  | Harris | Harris | Tier 3 | 19RPG024 | 2019-12-20 | 2020-01-16 |  | 44020, 44120, 44310 | Y | N |  | 0 | 57335 | 52523
52523B | Hayes to WA Parish Ckt.09A Upgrades | Upgrade Ckt.09A Alief to Stafford as a Clearance upgrade |  | Alief | Stafford | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-06-30 |  | 138 | 0 | 4.67 | 0 |  | Harris | Harris | Tier 3 | 19RPG024 | 2019-12-20 | 2020-01-16 |  | 44020, 44671 | Y | N |  | Cost included in main entry | 57336 | 52523
52523C | Hayes to WA Parish Ckt.09A Upgrades | Upgrade Ckt.09A Stafford to WA Parish as a Clearance upgrade |  | Stafford | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-06-30 |  | 138 | 0 | 11.75 | 0 |  | Harris | Harris | Tier 3 | 19RPG024 | 2019-12-20 | 2020-01-16 |  | 44015, 44671 | Y | N |  | Cost included in main entry | 57337 | 52523
6988 | Sheriff's Posse to Marion Transmission Line Upgrade | Replace existing T-340 795 ACSR with 959 ACSS. At Sheriff Posse - Upgrade/Replace underrated switches 2967, 2969, 2971 to 3,000 Amp Switches. Replace and increase fault interrupting rating of breaker 2970 to 63kA, and its continuous rating to 3,000 Amp. Replace CS 2965 and CS 2975 to 40kA units. |  | Sheriff's Posse | Marion | Planned |  | NBU | Gregory Thomas gthomas@nbutexas.com 830-608-8953 |  | 2021-07-01 |  | 138 | 0 | 3.35 | 0 |  | Comal | Guadalupe | Tier 4 | [5 empty] | Y | N |  |  | 14806 | 6988
47424 | Clear Fork - Lockhart Transmission Line Overhaul | Increase the reliability and capability of circuit T601 on the Clear Fork - Lockhart 3.0-mile 69-kV transmission line.Upgrade all structures to 138-kV class and bundled Suwannee capable. Upgrade conductor to bundled 959 ACSS Suwannee. Add OPGW. |  | ClearFork | Lockhart | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-07-30 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7195, 7215 | Y |  |  | 0 | 47425 | 47424
6540 | LCRA Gonzales to GVEC Gonzales Transmission Line Upgrade | Replace 0.98 miles of 4/0 ACSR 69 kV T-line, with double circuit 138kV structures, 795 ACSR "Drake", initially operate one circuit at 69 kV; plus terminal improvements |  | LCRA Gonzales | GVEC Gonzales | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-08-31 |  | 69 | 0 | 0.98 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  |  | 7592, 7626 | Y | N |  |  | 14280 | 6540
52638 | Solanum: Build 138 kV station | Construct new 138 kV box bay on the Abilene South to Putnam 138 kV line |  | Solanum |  | Planned | 1074 - 1247 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2835 | 2021-08-31 |  | 138 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  |  | 61015, 6309, 60365 | Y | N |  | 0 | 52639 | 52638
07TPIT0060 | Howard Lane to Techridge Reconductor | The project re-conductors Circuit 1004 (Techridge to Howard Lane) using 795 ACSS Drake conductors to increase the capacity to 3000 Amp. |  | Howard Lane | Techridge | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P067 PLAN_117_P194 | 2021-09-05 |  | 138 | 0 | 1.72 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9191, 9217 | Y | N |  |  | 8204 | 1028
56372 | This is related to GINR19INR0117 | This is a brand new substation named Reata Station to accommodate GINR19INR0117 Roadrunner Crossing Wind project and Sheep Creek Wind Project later. |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2021-09-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68051, 68005, 68050 | Y |  |  | 0 | 56373 | 56372
58292 | This is related to GINR21INR0031 | Jordan station will be interconnected project GINR 21INR0031 Indigo Solar Project |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2021-09-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68013, 68000, 68001 | Y |  |  | 0 | 58293 | 58292
07TPIT0050 | Dunlap to Techridge 138kV Circuit Relocation | This project will reroute the existing Ckt 975 Dunlap-Techridge from near the intersection of Howard Lane and Dessau Road to the Techridge substation. The reroute will use 3000 amp bundled 795 ACSS Drake conductor. |  | Dunlap Substation | Techridge Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P071 | 2021-09-30 |  | 138 | 0 | 2.7 | 0 |  | Travis | Travis | Tier 2 | 09RPG001 | 2009-01-26 | 2009-07-21 |  | 9045, 9190 | Y | N |  |  | 8189 | 1013
44868 | McKenzie - Westside 138 kV Line: Rebuild | Rebuild McKenzie - Westside 138 kV Line |  | McKenzie Road | Westside | Under Construction | 968 - 1146 | ETT | James Weaver bcogan@aep.com 918-599-2857 | 3726 | 2021-09-30 |  | 138 | 0 | 11.48 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8485, 8858 | Y | N |  | 0 | 44869 | 44868
52469 | Scout: Build 69 kV station | Construct new 69 kV box bay on the Abilene South to Steamboat 69 kV line |  | Scout |  | Planned | 1072 - 1245 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2833 | 2021-09-30 |  | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 60456, 6328, 6331 | Y | N |  | 0 | 52470 | 52469
58004 | Katoen: Build 345 kV station | Build 345 kV station Katoen to interconnect El Algodon, cut-in Katoen station to the Lon Hill to Goddard 345 kV line |  | Katoen |  | Planned | 1110 - 1288 | AEP TCC | Raza S Ansari bcogan@aep.com 918-599-2857 | 3829 | 2021-09-30 |  | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8579, 88579, 8455, 8606 | Y |  |  | 0 | 58005 | 58004
58933 | This is related to GINR21INR0387 and GINR21INR0474-- Anchor Wind Project | Aspire station will be interconnected to GINR21INR0387 Anchor Wind and GINR21INR0474 Anchor BESS projects. |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2021-09-30 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68011, 68008, 68010 | Y |  |  | 0 | 58934 | 58933
48288B | BOGGY (BOG) 138kV Substation (SHELL Substation Replacement) | Install new customer-owned BOGGY 138kV substation. Loop from Ckt.85 to create new Ckt.85 DERICK to BOGGY to SHELL |  | BOGGY | DERICK/SHELL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-12 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41460, 40981, 41320, 41380, 41450, 41580, 40089, 41620, 110941, 110942, 110943, 110944, 110950, 110951, 110953, 110947, 110948, 110952 | Y | N |  | Cost Included in 48288A | 58108 | 48288
52066 | Blessing to Bay City Pumps: Rebuild 69 kV Line | Rebuild Blessing to Markham Tap and retire the radial line servicing Bay City Pumps |  | Blessing | Markham Tap | Planned | 1076 - 1249 | AEP TCC | Marc E. Wilson bcogan@aep.com 918-599-2857 | 3801 | 2021-10-30 |  | 69 | 0 | 10.78 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 8546, 8547, 8549, 8119, 8550, 8984 | Y | N |  | 0 | 52067 | 52066
7027 | Barrilla Junction to Ft. Stockton SW: Rebuild 69 kV line | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138 kV, reterminate into Solstice, install 138 kV capacitor bank at Solstice, and build new Ft. Stockton Switch 138 kV station | Update Schedule | Solstice | Fort Stockton Switch | Planned | 908 - 1086 | AEP TNC | Darren O'Hare mlforcum@aep.com 918-599-2674 | 2732 | 2021-10-31 |  | 138 | 0 | 16.3 | 0 |  | Pecos | Pecos | Tier 3 |  | 2017-12-22 | 2018-02-02 |  | 6645, 60717, 60385, 6653, 38350, 38470 | Y | N |  |  | 14849 | 7027
7028 | Ft. Stockton SW to Rio Pecos: Rebuild 69 kV line | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138 kV, reterminate into Solstice, install 138 kV capacitor bank at Solstice, and build new Ft. Stockton Switch 138 kV station | Update Schedule | Fort Stockton Switch | Rio Pecos | Planned | 908 - 1086 | AEP TCC | Darren O'Hare mlforcum@aep.com 918-599-2674 | 2733 | 2021-10-31 |  | 138 | 0 | 0.42 | 0 |  | Pecos | Pecos | Tier 3 |  | 2017-12-22 | 2018-02-02 |  | 6641, 6642, 6643, 38470, 60717, 60718, 60719, 60720, 60798, 6598, 6601, 6645 | Y | N |  |  | 14850 | 7028
44361 | Ft. Stockton SW: Build 138 kV station | Rebuild Barrilla Junction to Ft. Stockton SW to Rio Pecos 69 kV line, convert to 138 kV, reterminate into Solstice, install 138 kV capacitor bank at Solstice, and build new Ft. Stockton Switch 138 kV station | Update Schedule | Fort Stockton Switch |  | Planned | 908 - 1086 | AEP TNC | Darren O'Hare mlforcum@aep.com 918-599-2674 | 2735 | 2021-10-31 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 3 |  | 2017-12-22 | 2018-02-02 |  | 60717 | Y | N |  | 0 | 44362 | 44361
49570 | Goodlett: Build 69 kV station | Build new Goodlett 69 kV station on the Childress to Quanah 69 kV line | Update Schedule | Goodlett |  | Planned | 1021 - 1199 | AEP TNC | Alison Scribailo mlforcum@aep.com 918-599-2674 | 2783 | 2021-10-31 |  | 69 | 0 | 0 | 0 |  | Hardeman |  | Tier 4 |  |  |  |  | 60446, 6052, 6053 | Y | N |  | 0 | 49571 | 49570
52197C | Jordan Auto A3 Addition (PLACID 138kV Sub) | PLACID (PLA) Substation Looped into Ckt.86D RIGBY to Crosby |  | Rigby | Crosby | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2021-10-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Harris | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 40680, 40155, 40390, 40670, 40665 | Y | N |  | 0 | 57347 | 52197
52688 | Angleton Substation Expansion | Expand Angleton substation for the Myrtle Solar generator interconnection (19INR0041). |  | Angleton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 111533 | Y | N |  | 0 | 55842 | 52688
55971 | Eagle Nest (EGL) Sub for Brazoria West Solar (20INR0101) | Install new 138kV Eagle Nest substation for generator interconnection to Brazoria West Solar. Loop Ckt.02 into Eagle Nest substation to create new Ckt.02 BURKE to Eagle Nest to West Columbia |  | Eagle Nest | BURKE/ West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42430, 42410, 43380 | Y | N |  | 0 | 56717 | 55971
48814 | Albany Foundry to Fort Griffin: Rebuild 69 kV line | Rebuild 69 kV line from Albany Foundry to Fort Griffin, install box bay at Salt Prong POD, install capacitor banks at Albany Foundry |  | Albany Foundry | Fort Griffin | Planned | 1014 - 1192 | AEP TNC | Nathan Cowan mlforcum@aep.com 918-599-2674 | 2775 | 2021-10-31 01:00 |  | 69 | 0 | 4.66 | 0 | 0,14.4 | Shackelford | Shackelford | Tier 4 |  |  |  |  | 6208, 6213, 60445, 6202, 6212, 60398, 6214 | Y | N |  | 0 | 48815 | 48814
6938 | Leonard Road Substation 69 | Construct Leonard Rd Substation with Dual Voltage Transformer. Will be served at 69kV until completion of Smetana to Leonard Rd 138kV line. | [5 empty] | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2021-11-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 32851, 32864, 32850 | Y |  |  |  | 14758 | 6938
47929 | Rising Star Area Rebuilds | Rising Star Area Rebuilds |  | Downing (281) | Nimrod (289) | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2021-11-01 |  | 69 | 0 | 50.04 | 60 |  | Comanche | Eastland | Tier 3 | 19RPG0007 | 2019-04-04 | 2019-04-30 |  | 281, 285, 289, 293, 277, 1649 | Y |  |  | 0 | 47930 | 47929
54568 | CPSE_New_Navistar_Substation | CPSE_New_Navistar_Substation |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2021-11-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5317, 5007, 5297 | Y |  |  | 0 | 54569 | 54568
55372 | Conversion of TNMP Gomez to 138kV service. |  |  |  |  | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE03020 | 2021-11-01 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38471, 60798 | Y |  |  | 0 | 55373 | 55372
48335 | RGEC Ft. Stockton US 285 138-kV Substation Addition | Provide transmission service to new 25/30/35 MVA 138/24.9-kV substation to replace (transfer load from) Ft. Stockton 69-kV Substation. This is tied to AEP Project ID # 44361 |  | Fort Stockton | Fort Stockton | Planned |  | RGEC/LCRATSC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2021-11-01 02:00 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 78926, 6645, 60717 | Y |  |  | 0 | 48340 | 48335
45334 | Corichi: Build 138 kV Box Bay | Build New Box Bay on El Campo - Victoria Line |  | Corichi |  | Planned | 986 - 1164 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3737 | 2021-11-08 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 8099, 88099, 8102, 8117 | Y | N |  | 0 | 45335 | 45334
51996 | Rebuild Markham Tap to AEP Markham Tap | Rebuild Markham Tap to AEP Markham Tap with 138 kV capable structures |  | Markham Tap | AEP MarkhamTap | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-11-13 |  | 69 | 0 | 1.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5554, 8984 | Y | N |  | 0 | 51997 | 51996
52255 | Sand Lake Switch 138 kV Terminal Addition | Add 2-138 kV terminals at Sand Lake Switch |  | Sand Lake | Sand Lake | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8504 | 2021-11-15 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  | 2019-03-01 | 2019-09-01 | 2019-10-01 | 11097 | Y |  |  | 0 | 52256 | 52255
59522 | Pebble Creek 138 kV Switch | Establish the new Pebble Creek 138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4315 | 2021-11-15 |  | 138 | 1.2 | 0 | 0 |  | Ellis |  | Tier 4 |  |  |  |  | 2229, 221, 2328 | Y |  |  | 0 | 59523 | 59522
59550 | Relocate Exxon Means to Landfill 138 kV POD | Relocate Exxon Means to new Landfill 138 kV POD and remove 4.3 miles of 138 kV line |  | Andrews North | Means | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8563 | 2021-11-15 |  | 138 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 1159, 1165, 1166, 1285 | Y |  |  | 0 | 59572 | 59550
5965 | Benjamin Tap to Katz (BEC): Build new 138 kV line | Construct new 138 kV ring bus Tardis on the Munday to Paducah 138 kV line, rebuild existing Benjamin Tap to 138 kV, terminate into Tardis, convert Benjamin to 138 kV operation and build new 138 kV line from Benjamin to Katz (BEC) | Update Schedule | Benjamin Tap | Katz (BEC) | Planned | 769-0954 | AEP | Dewey Peters mlforcum@aep.com 918-599-2674 | 2685 | 2021-11-30 |  | 138 | 17.7 | 9 | 0 |  | Knox | Knox | Tier 2 |  | 2016-02-03 | 2016-05-01 | 2016-05-01 | 6320 | Y | N |  |  | 13680 | 5965
6569 | Aspermont: Replace the 138/69 kV autotransformer | Replace the 138/69 kV autotransformer at Aspermont with a 130 MVA autotransformer | Update Schedule, Contact | Aspermont |  | Planned | 839 - 1023 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 2817 | 2021-11-30 |  | 138 | 0 | 0 | 130 |  | Stonwall |  | Tier 4 |  |  |  |  | 6156, 6158 | Y | N |  |  | 14320 | 6569
6668B | Freeport - Master Plan | New 345 kV double-circuit line from Bailey Substation to Jones Creek Substation | Accelerated Project Schedule | Bailey | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-11-30 |  | 345 | 55.2 | 0 | 0 |  | Wharton | Brazoria | Tier 1 | 17RPG005 | 2017-04-04 | 2017-06-05 | 2017-12-12 | 5568, 5915, 42400, 42500, 42530, 43011, 43120, 44000, 44005, 44040, 43221, 43380, 44200, 47531, 47532 | Y | N |  | 0 | 58254 | 6668
6749 | Rosata: Build 138kV Substation | Build new Rosata 138kV POD Switch on Coleto Creek to Kenedy 138kV Line |  | Rosata |  | Planned | 898 - 1076 | AEP TCC | James Lutz bcogan@aep.com 918-599-2857 | 3682 | 2021-11-30 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8153, 88153, 7241, 8162, 8186 | Y | Y |  |  | 14542 | 6749
46513 | Port Isabel: Rebuild As GIS Station | Rebuild Port Isabel as a GIS |  | Port Isabel |  | Planned | 958 - 1136 | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | 3716 | 2021-11-30 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  | 0 | 50322 | 46513
49556 | Ozona: Rebuild 69 kV station | Replace existing Ozona 69 kV station with a new 69 kV ring bus |  | Ozona |  | Planned | 1018 - 1196 | AEP TNC | Nathan Cowan mlforcum@aep.com 918-599-2674 | 2780 | 2021-11-30 |  | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6550, 6560 | Y | N |  | 0 | 49557 | 49556
50160 | Beeville - Goliad: Rebuild 69 kV Line | Beeville - Goliad: Rebuild 69 kV Line |  | Beeville | Goliad | Planned | 961 - 1139 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3719 | 2021-11-30 |  | 69 | 0 | 22.21 | 0 |  | Bee | Goliad | Tier 3 |  | 2019-04-30 | 2019-05-30 |  | 8584, 8586, 8587 | Y | N |  | 0 | 50161 | 50160
50878 | North Edinburg: 345 kV Reconfigure | North Edinburg: 345 kV Reconfigure |  | North Edinburg |  | Planned | 1056 - 1229 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3786 | 2021-11-30 |  | 345 | 0 | 0 | 0 | -100,0 | Hidalgo |  | Tier 4 |  |  |  |  | 8341, 8383 | Y | N |  | 0 | 50879 | 50878
50898 | Alamito Creek to Paisano to Alpine: Rebuild 69 kV line | Rehab Alamito Creek to Paisano to Alpine 69 kV line |  | Alamito Creek | Alpine | Planned | 1045 - 1218 | AEP TNC | Nathan Cowan mlforcum@aep.com 918-599-2674 | 2793 | 2021-11-30 |  | 69 | 0 | 22.26 | 0 |  | Presidio | Brewster | Tier 4 |  |  |  |  | 60449, 6666, 6667, 6672 | Y | N |  | 0 | 50899 | 50898
52100 | Bradshaw to Steamboat: Rebuild 69 kV line | Rebuild Bradshaw to Steamboat 69 kV line | Update Contact | Bradshaw | Steamboat | Planned | 1069 - 1242 | ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | 2830 | 2021-11-30 |  | 69 | 0 | 0.25 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6331, 60332, 6328, 60456 | Y | N |  | 0 | 52101 | 52100
55367 | Wolfcamp: Build 138 kV box bay | Build new 138 kV box bay on the Big Lake to North McCamey line |  | Wolfcamp |  | Planned | 1087 - 1270 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1860 | 2021-11-30 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | 60799, 60361, 60723 | Y | N |  | 0 | 55368 | 55367
57908 | North Edinburg: Station Work | North Edinburg: Station Work |  | North Edinburg |  | Planned | 1112 - 1290 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3831 | 2021-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 88381, 88382, 8380, 8383, 8341 | Y | N |  | 0 | 57909 | 57908
59095 | Athey: Build 138 kV Temporary Hard Tap | Build new 138 kV temporary tap on the Ft Stockton to Rio Pecos 138 kV line | NEW | Athey |  | Planned | 1123 - 1301 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 1868 | 2021-11-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60792, 60718, 60798 | Y | N |  | 0 | 59096 | 59095
59313 | Beasly (BEA) CNP-Owned Sub for Fort Bend Solar (18INR0053) | Loop new 138kV Beasly (BEA) substation for generator interconnection to Fort Bend Solar. Loop Ckt.60 into Beasly substation to create new Ckt.60 East Bernard to Beasly to Orchard |  | Beasly | East Bernard/Orchard | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-11-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 42420, 44190, 44541 | Y | N |  | 0 | 59314 | 59313
55969 | Cedar Creek (CCK) Substation for Old 300 Solar (21INR0406) | New 138kV Cedar Creek substation for generator interconnection to Old 300 Solar. Loop Ckt.02 into substation to create new Ckt.72 BAILEY to Cedar Creek to WAP |  | Cedar Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-11-30 |  | 345 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 44090, 44005, 44040 | Y | N |  | 0 | 56664 | 55969
5891A | LUBZOL Substation Removal and Substation PATRIK Addition | Remove LUBZOL 138kV substation from CNP service |  | LUBZOL | TIDAL/TRAVIS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-11-30 00:01 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40980, 40070, 40470, 41210, 41380, 41580, 41590, 40089, 40530, 41370, 41415, 41450 | Y | N |  | 0 | 52118 | 5891
17TPIT0005 | St. Jo Autos | Replace 40 MVA autos with 60 MVA autos |  | St. Jo | St. Jo | Planned |  | BEPC | Kenneth Dye kdye@brazoselectric.com 254-750-6353 | 12005 | 2021-12-01 |  | 138 | 0 | 0 | 60 |  | Cooke |  | Tier 4 |  |  |  |  | 750, 746 | Y | N |  |  | 9491 | 2243
51742 | Pipeline Breaker Addition | Convert existing tap substation to ring bus |  | Pipeline |  | Planned |  | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 |  | 2021-12-01 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7390 | Y | N |  | 0 | 51751 | 51742
51990 | AEN_21TPIT51990_New_Dunlap_345kV_Auto_AT2_PMCR | Second 345/138 kV autotransformer addition at Dunlap substation |  | 9044 | 9045 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2021-12-01 |  | 345 | 0 | 0 | 672 |  |  |  | Tier 4 |  |  |  |  | 90007, 9044, 9045 | Y |  |  | 0 | 59171 | 51990
60493 | Rebuild West-TI with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37060, 37080 | Y |  |  | 0 | 60494 | 60493
60495 | Rebuild Wink-Kermit Tap with 477 ACSR | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2021-12-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37920, 38260 | Y |  |  | 0 | 60496 | 60495
44854 | Lipton: Build 138 kV Box Bay | New Lipton 138 kV Station, replaces Lipton Hard Tap |  | Lipton |  | Planned | 973 - 1151 | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | 3731 | 2021-12-09 |  | 138 | 0 | 0 | 0 |  | Zavala |  | Tier 4 |  |  |  |  | 8285, 88285, 8236, 8283 | Y | N |  | 0 | 44855 | 44854
6873 | Support 69kV to 138kV East Loop Conversion Projects | Upgraded lines Apollo to Naaman to Walnut to Newman to support 69kV to 138kV East Loop Conversion Projects |  | Apollo | Newman | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2021-12-10 |  | 138 | 0 | 10.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 800, 814, 825, 826, 802, 849, 823, 806 | Y | N |  |  | 14682 | 6873
5310 | Everman - Venus 345 kV Double-circuit line | Upgrade existing line |  | Everman | Venus | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1735 | 2021-12-15 |  | 345 | 0 | 34.6 | 0 |  | Tarrant | Ellis | Tier 3 |  |  |  |  | 11886, 11888, 1906, 1907 | Y | N |  |  | 12986 | 5310
7025 | Renner Sw. Sta. - Plano Tennyson Sw. Sta. 138 kV Line | Upgrade existing Renner Sw. Sta. - Plano Tennyson Sw. Sta. 138 kV Line |  | Renner Sw. Sta. | Plano Tennysson Sw. Sta. | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3047 | 2021-12-15 |  | 138 | 0 | 10.6 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2352, 2353, 2521, 2523, 2524 | Y | N |  |  | 14847 | 7025
7118 | Everman 345 kV Sw. Sta. | Rebuild Everman 345 kV Sw. Sta. |  | Everman |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5278 | 2021-12-15 |  | 345 | 0 | 0 | 0 |  | Tarrant |  | Tier 3 | 20RPG013 | 2020-07-01 | 2020-09-10 |  | 1882, 1885, 1886, 1887, 11885, 11886, 11888, 1880, 1888, 1900, 1906, 1907, 1931, 1932, 1935, 2285, 11882, 11887, 11884, 24997 | Y |  |  | 0 | 60063 | 7118
45517 | Waco West - Waco East 138 kV Line | Upgrade the Waco West Switch - Waco East Switch (Via Baylor Tap) 138 kV Line to 2071 A |  | Waco West | Waco East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R463 | 2021-12-15 |  | 138 | 0 | 10.6 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3434, 3436, 3438, 3563 | Y | N |  | 0 | 45518 | 45517
52149 | Upgrade Elm Mott - Bosque 138 kV Line | Upgrade Elm Mott - Bosque 138 kV Line |  | Elm Mott | Bosque | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1721 | 2021-12-15 |  | 138 | 0 | 19.3 | 0 |  | McLennan | Bosque | Tier 4 |  |  |  |  | 249, 252, 3407 | Y |  |  | 0 | 52150 | 52149
52153 | Upgrade Eustace SE - Mabank 138 kV Line | Upgrade Eustace SE - Mabank 138 kV Line |  | Eustace Southeast | Mabank | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6097 | 2021-12-15 |  | 138 | 0 | 9.3 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  |  | 3176, 3177, 3179, 6951 | Y |  |  | 0 | 52154 | 52153
52234 | Calmont 138 kV Emergency Capacitors | Install new 55.2 Mvar capacitor bank |  | Calmont |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5134 | 2021-12-15 |  | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1955 | Y |  |  | 0 | 52235 | 52234
52247 | Marrs - Handley 69 kV Line Conversion to 138 kV | Convert the existing Marrs-Handley 69 kV line to 138 kV operation |  | Marrs SW | Handley | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5222 | 2021-12-15 |  | 138 | 2.2 | 13 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1952, 1968, 2158, 2159, 2160, 2161, 11952, 1951, 1969 | Y |  |  | 0 | 52248 | 52247
52251 | Mountain Creek Switch 138 kV Breaker Installation | install two 138 kV breakers |  | Mountain Creek |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4093 | 2021-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 12457, 12458, 2411, 2412, 3014, 3015 | Y |  |  | 0 | 52252 | 52251
52305 | Cedar Hill Switch-Cedar Hill 138 kV Line Upgrade | rebuild the existing Cedar Hill Switch-Cedar Hill 138 kV Line |  | Cedar Hill SW | Cedar Hill | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4131 | 2021-12-15 |  | 138 | 5.9 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2422, 3049, 3051, 3052, 3053, 3050, 3055 | Y |  |  | 0 | 52306 | 52305
52728 | Add NS Crane 138 kV Switch | Oncor's portion of AEP's Crane Area Transmission Project |  | LCRA Arco Crane | Navajo Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8502 | 2021-12-15 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  | 2019-06-01 | 2019-07-22 |  | 10002, 11202, 60448, 71199 | Y |  |  | 0 | 52730 | 52728
54118 | Rebuild Alvin-Mainland (795 ACSS) | Rebuild Alvin - Mainland 138 kV line with 795 ACSS conductor. |  | Freeway Park 138 kV Substation (Bus # 38820) | Alvin 138 kV Substation (Bus # 39030) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE09517 | 2021-12-15 |  | 138 | 0 | 17.3 | 0 |  | Galveston | Brazoria | Tier 4 |  |  |  |  | 38830, 39030 | Y |  |  | 0 | 54119 | 54118
57758 | Carrollton Northwest 345/138 kV Autotransformer | Carrollton Northwest 345/138 kV Autotransformer |  | Carrollton Northwest |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4247 | 2021-12-15 |  | 345 | 0 | 0 | 600 |  |  |  | Tier 3 | 20RPG010 |  |  |  | 2360, 2362, 2363, 2361, 12360 | Y |  |  | 0 | 57759 | 57758
57853 | Palmer and Rice 69 kV Substations Conversion to 138 kV | Convert Palmer and Rice 69 kV Substations to 138 kV |  | Palmer | Rice | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4317 | 2021-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2344, 2345, 2346, 2347, 221, 2326, 2329, 2342, 3468 | Y |  |  | 0 | 57854 | 57853
57855 | Ennis Switch 138 kV Rebuild | Rebuild Ennis 138 kV Switch |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4302 | 2021-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  | 0 | 57856 | 57855
57915 | Tall City - Telephone Road 138 kV Line Rebuild | Tall City - Telephone Road 138 kV Line Rebuild |  | Tall City | Telephone Road | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8552 | 2021-12-15 |  | 138 | 0 | 11.9 | 0 |  | Midland | Midland | Tier 3 | 20RPG016 | 2020-09-11 | 2020-10-21 |  | 23855, 23862 | Y |  |  | 0 | 57916 | 57915
52316 | Anna Tap - Princeton 138 kV Line | Upgrade the Anna Tap - Princeton 138 kV Line |  | Anna Tap | Princeton Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4275 | 2021-12-15 01:00 |  | 138 |  | 9.6 | 0 |  | Collin | Collin | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 2527, 2707, 2528, 2708 | Y |  |  | 0 | 52317 | 52316
45527 | Plano West - Richardson Collins 138 kV Line | Upgrade the Plano West - Richardson Collins 138 kV Line |  | Plano West Switch | Richardson Collins Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M364 | 2021-12-15 12:00 |  | 138 | 0 | 0 | 0 |  | Collin | Dallas | Tier 4 |  |  |  |  | 2685, 2628, 2673, 2683, 2684, 2686, 12684 | Y |  |  | 0 | 45528 | 45527
46259 | Big Spring - Buzzard Draw 69 kV Line Conversion | Big Spring - Buzzard Draw 69 kV Line Conversion |  | Big Spring | Buzzard Draw | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9015 | 2021-12-15 23:00 |  | 138 | 0 | 21.3 | 0 |  | Howard | Howard | Tier 4 | 20RPG009 | 2020-06-03 | 2020-07-09 |  | 1357, 1358, 1359, 1361, 1365, 1322, 1323, 1355, 1356, 11324 | Y |  |  | 0 | 46262 | 46259
52239 | Lake Hubbard SW | Install two 138 kV breakers |  | Lake Hubbard |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4134 | 2021-12-16 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 12401, 12402, 2401, 2402, 2441, 2939 | Y |  |  | 0 | 52240 | 52239
52322 | Establish Courtney Creek Switch | Establish Courtney Creek 138/69 kV Switch |  | Courtney Creek Switch | Athey (AEP) | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8479 | 2021-12-16 |  | 138 |  |  | 82 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 11242, 11258, 1240, 1242, 60792 | Y |  |  | 0 | 56445 | 52322
54088 | Hortontown Substation Upgrade | Increase the reliability of substation equipment at the Hortontown Substation. LCRA TSC will change the existing high-side configuration at Hortontown substation from Single Bus/Single Breaker to Ring Bus. |  | Hortontown Substation | Hortontown Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-12-16 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7175 | Y | N |  | 0 | 54089 | 54088
6786 | Schumansville T2 Replacement | Replace T2, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Schumansville |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2021-12-17 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7609 | Y |  |  |  | 14580 | 6786
55873 | Upgrade Moore to Hondo Creek 138 kV line | Replace the 336 ACSR with 1020 ACCC conductor while keeping the existing structures that still meet our standards. |  | Moore | Hondo Creek | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2021-12-18 |  | 138 | 0 | 13.5 | 0 |  | Medina | Frio | Tier 2 | 19RPG021 | 2019-11-20 | 2020-05-21 |  | 5819, 5827 | Y | N | Field engineering is still occurring due to short timeline for this upgrade. Details may change. | Current plan is to upgrade the line using mostly existing structures. Detailed field engineering is underway and could change the plan. | 55874 | 55873
3774 | Olinger-Ben Davis Line Upgrade | Olinger to Ben Davis 138 kV line upgrade to Cumberland conductor |  | Olinger | Ben Davis | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2021-12-25 |  | 138 | 0 | 17.25 | 0 |  | Collin | Dallas | Tier 4 |  |  |  |  | 818, 968 | Y | N |  |  | 11194 | 3774
54092 | Sheriff's Posse Substation Upgrade | Increase transmission service reliability to the Sheriff¿s Posse Substation. Increase the reliability of substation equipment at the Sheriff¿s Posse Substation. Note: NBU is adding a third power transformer at Sheriff¿s Posse and reconfiguring the substation to a ring bus arrangement. LCRA TSC will complete this project to support the NBU substation reconfiguration. LCRA TSC will ultimately own a section of the ring bus at Sheriff¿s Posse where an existing LCRA TSC transmission line terminates. |  | Sheriff's Posse | Sheriff's Posse | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2021-12-28 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7460 | Y | N |  | 0 | 54093 | 54092
7013 | NASA Substation Upgrades | Upgrade substation equipment at NASA substation to increase thermal limits |  | NASA | NASA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42970, 42610 | Y | N |  |  | 14835 | 7013
52565D | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Upgrade Ckt.90A HO Clarke to Kirby to Garrott to increase thermal limits |  | Kirby | HO Clarke/Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47151, 47175, 47322, 47660 | Y | N |  | 0 | 59282 | 52565
52640 | HO Clarke Auto A3 Replacement | Replace existing HO Clarke Auto A3 with removed University Auto A1 |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 49009, 47175, 47165 | Y | N |  | 0 | 52641 | 52640
6346 | Menard Phillips T to Junction 69 kV line: Rbld 69 kV line | Rehab Menard Phillips Tap to Junction 69 kV line | Update Schedule | Menard Phillips Tap | Junction | Planned | 786 - 0971 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2712 | 2021-12-31 |  | 69 | 0 | 12.2 | 0 |  | Kimble | Kimble | Tier 4 |  |  |  |  | 6400, 6401 | Y | N |  |  | 14090 | 6346
6572 | Ballinger to Eden 69 kV line: Rebuild taps | Ballinger to Eden 69 kV line: Rebuild taps |  | Ballinger | Eden | Planned | 890 - 1068 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2814 | 2021-12-31 |  | 69 | 0 | 2.8 | 0 |  | Runnels | Concho | Tier 4 |  |  |  |  | 6338, 6369, 6370, 6372, 6376 | Y | N |  |  | 14323 | 6572
45543 | Everman Switch - Marrs Switch 138 kV DCKT Line | Upgrade the Everman Switch - Marrs Switch 138 kV Double-Circuit Line |  | Everman Switch | Marrs Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5279 | 2021-12-31 |  | 138 | 0 | 8 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1883, 1884, 1969, 2211, 11968, 11967 | Y |  |  | 0 | 51248 | 45543
46938 | McCreeAdds600MVAAuto2 | McCreeAdds600MVAAuto2 |  | McCree | McCree | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2021-12-31 |  | 345 | 0 | 0 | 600 |  | Dallas | Dallas | Tier 4 | 19RPG022 |  |  |  | 983, 973, 834 | Y | N |  | 0 | 46939 | 46938
52267A | SR Bertron 138/69kV Conversions | Deenergize 69kV SRB substation and connect 138kV Buses |  | SR Bertron | SR Bertron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41405, 41415, 40290, 40480, 40540, 41400, 41540 | Y | N |  | 0 | 59288 | 52267
56012 | PSARCO Fault Duty Upgrade with Bus Reactors | Install (2) 10-Ohm Reactors at PSARCO by splitting PSARCO bus as a fault duty upgrade |  | PSARCO |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41300, 41305, 40190, 41021, 110579, 110571, 110572, 110573, 110574, 110577 | Y | N |  | 0 | 56103 | 56012
57582 | Cedar Bayou Auto A1 Upgrade | Upgrade Cedar Bayou auto A1 to increase thermal limits |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 345 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  |  | 40000, 40015, 49005 | Y | N |  | 0 | 57583 | 57582
57586 | Cedar Bayou to Center Ckt.97D Upgrade | Upgrade Cedar Bayou to Center Ckt.97D |  | Cedar Bayou | CENTER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 345 | 0 | 0 | 0 |  | Chambers | Harris | Tier 4 |  |  |  |  | 40000, 40240 | Y | N |  | 0 | 57587 | 57586
59363A | Hungerford (HUG) CNP-Owned Sub for SBranch Solar (22INR0205) | New 138kV Hungerford (HUG) substation for generator interconnection to SBranch Solar. Loop Ckt.60 into substation to create new Ckt.60 East Bernard to Hungerford to Caney tap. |  | Hungerford | East Bernard/Caney | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 44150, 44130, 44190 | Y | N |  | 0 | 59364 | 59363
59363B | Hungerford (HUG) CNP-Owned Sub for SBranch Solar (22INR0205) | Upgrade Ckt.60A Beasly to Orchard to Minimum 525/580 MVA to increase thermal limits |  | Beasly | Orchard | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 42420, 44541 | Y | N |  | 0 | 59365 | 59363
52267B | SR Bertron 138/69kV Conversions | Remove SRB Auto A1 |  | SR Berton | SR Berton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 01:00 |  | 138 | 0 | 0 | -200 |  | Harris | Harris | Tier 4 |  |  |  |  | 110005, 41400, 41415 | Y | N |  | Cost included in Phase A. | 59284 | 52267
52267C | SR Bertron 138/69kV Conversions | Remove SRB Auto A2 |  | SR Bertron | SR Bertron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 02:00 |  | 138 | 0 | 0 | -192 |  | Harris | Harris | Tier 4 |  |  |  |  | 49004, 41400, 41410 | Y | N |  | Cost Included in Phase A. | 59285 | 52267
52267D | SR Bertron 138/69kV Conversions | Disconnect Ckt.16A and Ckt.23A at SRB and Reconnect to Create New Ckt.23A Deepwater to South Channel |  | South Channel | Deepwater | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 03:00 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40089, 40470, 41380, 41410, 41415 | Y | N |  | Cost included in Phase A. | 59289 | 52267
52267E | SR Bertron 138/69kV Conversions | De-Energize Ckt.55D SRB to SRB |  | SR Bertron | SR Bertron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 04:00 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41410, 41415, 41419, 40089, 40470, 41400, 49004, 110005 | Y | N |  | Cost included in Phase A. | 59287 | 52267
52267G | SR Bertron 138/69kV Conversions | Install cap bank removed from HOC at SRB. |  |  | SR Bertron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2021-12-31 05:00 |  | 138 | 0 | 0 | 0 | 0,100 | Harris | Harris | Tier 4 |  |  |  |  | 41400 | Y | N |  | Cost included in Phase A | 59286 | 52267
54698 | Perigee: Build 345 kV station | Interconnect Apogee wind farm on the Foxtail to Mulberry Creek 345 kV line | Update Contact, Schedule | Perigee |  | Planned | 1038 - 1265 | AEP TNC | Benjamin Golnik mlforcum@aep.com 918-599-2674 | 1855 | 2022-01-01 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60791, 6076, 6235 | Y | N |  | 0 | 54699 | 54698
4505 | BRYN_4505_Smetana_Sub | Construction of a new Smetana Substation at 138kV |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.co 979-821-5763 |  | 2022-01-03 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32850, 32853, 32868 | Y |  |  | 0 | 58925 | 4505
4576 | BRYN_4576_Smetana_to_Steele_Store | Construct New 138kV line (Bundled 1033 ACSR - Curlew) to new Steele Store substation as part of the reliability project to loop in Steele Store |  | 32853 | 32852 | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2022-01-03 |  | 138 | 4.5 | 0 | 0 |  | Brazos | Burleson | Tier 4 |  | 2015-10-09 | 2015-11-06 |  | 32852, 32853 | Y |  |  |  | 12158 | 4576
47426 | Clear Fork - Robert Brown Transmission Line Overhaul | Increase the reliability and capability of circuit T519 on the Clear Fork - Robert Brown Jr 8.8-mile 69-kV transmission line. Upgrade all structures to 138-kV class and bundled Suwannee capable. Upgrade conductor to bundled 959 ACSS Suwannee. Add OPGW. |  | Clear Fork | Robert Brown Jr | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-01-12 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7194, 7195 | Y | N |  | 0 | 47427 | 47426
54105 | McCarty Lane - Ranch Road 12 Transmission Line Upgrade | Increase the reliability of transmission facilities on the T699 McCarty Lane ¿ Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | McCarty Lane | Ranch Road 12 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-01-14 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7186 | Y | N |  | 0 | 54106 | 54105
10TPIT0025 | Bluff Spring 138kV substation | Establish 138kV Bluff Spring substation with (2) 30MVA transformers and will cut into existing Ckt 987 (Lytton Springs to Slaughter Lane). | Changing name of substation from Rinard Creek to Bluff Springs | Lytton Springs substation | Bluff Springs Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P151 PLAN_117_P152 | 2022-01-26 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9262, 9075, 9267 | Y | N |  |  | 8206 | 1030
44511 | Aransas_Pass-Seawall: Rebuild and re-conductor with 795 ACSS | Rebuild and re-conductor Aransas Pass - Seawall with 795 ACSS (2000 A conductor). This will relieve overload seen in the 2025 SSWG Summer Peak case for loss of Naval Base- North Padre. |  | Aransas Pass | Seawall | Planned | 947 - 1125 | AEP | Michael Glueck bcogan@aep.com 918-599-2857 | 3711 | 2022-01-30 |  | 69 | 0 | 3.2 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8427, 8435 | Y | N |  | 0 | 44512 | 44511
44866 | Dilley - Jourdanton 69 kV Line | Rebuild Dilley - Jourdanton 69 kV Line |  | Dilley | Jourdanton | Under Construction | 967 - 1145 | AEP | Brian Oyster bcogan@aep.com 918-599-2857 | 3725 | 2022-01-30 |  | 69 | 0 | 44.8 | 0 |  | Frio | Atascosa | Tier 3 |  | 2019-05-23 | 2019-05-24 | 2019-06-17 | 8206, 8208, 8607 | Y | N |  | 0 | 44867 | 44866
4895 | CPSE_Capitol Cement Transmission Reconfiguration | Re-configurate Capitol Cement by loop into the existing Dresden to Skyline 138 kV transmission line and removing the existing Captiol Cement to Tuttle 138 kV transmission line. |  | Capitol Cement | Dresden/Skyline | Planned | S-0767 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0246 | 2022-01-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5075, 5130, 5370, 5435 | Y | N |  |  | 12507 | 4895
49546 | Resnik: Construct New Distribution Station | Resnik: Construct New Distribution Station |  | Resnik |  | Planned | 996 - 1174 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 3749 | 2022-01-31 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8580, 8422, 8565, 80470 | Y | N |  | 0 | 49547 | 49546
50950 | Whitepoint Area Improvements | Whitepoint Area Improvements |  | Whitepoint | Hecker | Planned | 1061 - 1234 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3792 | 2022-01-31 |  | 138 | 0 | 12 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8418, 8565, 8961 | Y | N |  | 0 | 50951 | 50950
50954 | Whitepoint: Add Second Auto | Whitepoint: Add Second Auto |  | Whitepoint |  | Planned | 1085 - 1258 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3805 | 2022-01-31 |  | 345 | 0 | 0 | 500 |  | San Patricio |  | Tier 4 |  |  |  |  | 8956, 8961 | Y | N |  | 0 | 50955 | 50954
52072 | Conan: Build new 69 kV box bay | Construct new 69 kV box bay on the Santa Anna to Cross Plains 69 kV line and install capacitor bank | Update Contact, Schedule, Cost | Conan |  | Planned | 1066 - 1239 | AEP TNC | William Lovelace mlforcum@aep.com 918-599-2674 | 2827 | 2022-01-31 |  | 69 | 0 | 0 | 0 | 0,7.2 | Callahan |  | Tier 4 |  |  |  |  | 6356, 60455, 6350, 6352, 6357 | Y | N |  | 0 | 52073 | 52072
57756 | WOLF 345kV for Fighting Jays Solar (21INR0278) | New 345kV CNP WOLF (WLF) substation for generator interconnection to Fighting Jays Solar. Loop Ckt.64C into substation to create new Ckt.64 Hillje to WOLF to WA Parish. |  | WOLF | Hillje/WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 44160, 44000, 44200 | Y | N |  | 0 | 57757 | 57756
59117 | Tres Bahias Solar Interconnection | Tres Bahias Solar Interconnection | NEW | Joslin |  | Planned |  | AEP TCC | bcogan@aep.com 918-599-2857 | TP2019312 | 2022-01-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8192, 8661, 8126, 8140, 8141, 8143, 8157, 80064 | Y |  |  | 0 | 59118 | 59117
59392 | Riverside (RVR) Sub for CHAMON Phase 2 (19INR0056) | Install new 138kV Riverside (RVR) CNP substation for generator interconnection to customer LIGNIN (LIG). Loop Ckt.94C into Riverside substation to create new Ckt.94 CHAMON to Riverside to Metals Switchrack |  | Riverside | CHAMON/Metals Switchrack | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-01-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 40270, 40260, 41050 | Y | N |  | 0 | 59393 | 59392
57161 | Rebuild Vanderbilt to VanHumble | Rebuild 4/0 ACSR with 795 ACSR on 138 kV capable poles |  | Vanderbilt | Van Humble Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-02-15 |  | 69 | 0 | 0.97 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 5580, 5582 | Y | N |  | 0 | 57162 | 57161
47537 | Kempner Circuit Breaker Addition | LCRA TSC will add three 138kV, 3000A, 40kAIC circuit breakers in a ring bus configuration at Kempner Substation. |  | Kempner Substation | Kempner Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-02-21 |  | 138 | 0 | 0 | 0 |  | Lampasas | Lampasas | Tier 4 |  |  |  |  | 260 | Y | N |  | 0 | 47538 | 47537
59119 | Sparta Solar Interconnection | Sparta Solar Interconnection | NEW | Tango |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020136 | 2022-02-28 |  | 345 | 0.01 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 88690, 163321, 8689 | Y |  |  | 0 | 59120 | 59119
59315 | BLUE (BLU) CNP-Owned Sub for Red-Tailed Hawk Solar (21INR0389) | New 345kV BLUE (BLU) substation for generator interconnection to Red-Tailed Hawk Solar. Loop Ckt.72 into substation to create new Ckt.72 Hillje to BLUE to Bailey |  | BLUE | Hillje/Bailey | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 44060, 44040, 44200 | Y | N |  | 0 | 59316 | 59315
59387 | DANBUR (DAB) 138kV Sub for Long Bow Solar (20INR0026) | Loop new CNP 138kV substation DANBUR (DAB) into Ckt.04C Angleton to Liverpool to create new Ckt.04 Angleton to DANBUR to Liverpool. Install one generator lead for new interconnection to Longbow Solar. |  | DANBUR | Angleton/Liverpool | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-02-28 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 42875, 42110, 42870 | Y | N |  | 0 | 59388 | 59387
58002 | Foxtrot: Construct new 345 kV Station |  |  |  |  | Planned | 1120 - 1298 | AEP | Glen Reed gareed@aep.com 918-599-2664 | 3839 | 2022-03-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8689, 88689, 5725, 8606 | Y |  |  | 0 | 58003 | 58002
58907 | AEN_22TPIT_NEW_GEN_BIGSTAR_CONNECTION_CISTERN_SUB | New 345 kV station to interconnect Big Star Solar and Storage generation interconnection |  | Holman | Lytton | Planned | 58907 | AEN | Reza Ebrahimian Reza.Ebrahimian@austinene 512-322-6740 |  | 2022-03-01 |  | 345 | 0 | 0 | 0 |  | Fayette | Caldwell | [5 empty] | 9043, 9073, 9074 | Y |  |  |  | 58908 | 58907
60491 | Rebuild 16th Street-Airport with 1926 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38310, 38340 | Y |  |  | 0 | 60492 | 60491
54084 | King Mountain Circuit Breaker Addition | Provide transmission service to a generator. Add a 138-kV bay and associated circuit breaker to the existing substation. ERCOT (ERCOT Generation Interconnection or Change Request No. 20INR0226) |  | King Mountain Sub | King Mountain Sub | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-03-11 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 76635 | Y | N |  | 0 | 54085 | 54084
43212B | Caymus Capbanks in TNMP West Texas System | Expands Caymus Capacitor bank by 1 block of 20 Mvar. |  | Caymus (Bus #38410) | Caymus (Bus #38410) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07819 | 2022-03-15 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38410 | Y |  |  | 0 | 48414 | 43212
48415B | TransPecos Capbank in TNMP West Texas System | Expands TransPecos Capacitor bank by 1 block of 20 Mvar. |  | TransPecos (Bus #38377) | TransPecos (Bus #38377) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE07919 | 2022-03-15 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38377 | Y |  |  | 0 | 48417 | 48415
59452 | Air Liquide Pass Through 138 kV Station | Air Liquide to construct 138 kV Ring Bus | NEW | Dupont SW Ingleside |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020197 | 2022-03-15 |  | 138 | 0.01 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8979, 8422, 8818, 8978 | Y | Y |  | 0 | 59453 | 59452
59959 | CPSE_New_Old_Hickory_Switchyard | Build a new Old Hickory 345 switchyard to connect Old Hickory Solar plant. |  | 5133 | 5915 | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0303; S-0940 | 2022-03-15 20:00 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5323, 5133, 5915 | Y |  |  | 0 | 59960 | 59959
5230 | Sonne Substation Addition | Provide transmission service for a generator off T554 radial 138-kV line between North McCamey and Tippet Substations. |  | North McCamey | Tippet | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1015964 | 2022-03-17 |  | 138 | 0 | 0 | 0 |  | Upton | Pecos | Tier 4 |  |  |  |  | 76020, 76021, 76595 | Y | N |  |  | 12903 | 5230
49574 | Tesla: Build 345 kV terminal | Interconnect Misae II solar farm at Tesla | Update Schedule | Tesla |  | Planned | 1023 - 1201 | ETT | Michael Glueck mlforcum@aep.com 918-599-2674 | 2785 | 2022-03-24 |  | 345 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501 | Y | N |  | 0 | 49575 | 49574
55464 | Adds new Morrow sub near Pearsall | Adds new Morrow substation and short line from Morrow to the Pearsall substation |  | Pearsall | Morrow | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-03-30 |  | 138 | 0.91 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5896, 5895 | Y | N |  | 0 | 55465 | 55464
4495 | Champlin: Station Reconfigure | Expand existing breaker configuration to a four (4) breaker ring bus expandable to a six (6) breaker ring bus configuration. |  | Champlin |  | Planned | 694 - 0864 | AEP | John Pulay bcogan@aep.com 918-599-2857 | 3541 | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8476 | Y | N |  |  | 12064 | 4495
11TPIT0011 | East_Village138kV Substation | East_Village 138kV Substation |  | Techridge | East_Village SUB |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9195, 9045, 9190 | Y |  |  |  | 13043 | 5357
6571 | Lake Pauline to Vernon 69 kV line: Rebuild taps | Lake Pauline to Vernon 69 kV line: Rebuild taps |  | Lake Pauline | Vernon Main | Planned | 891 - 1069 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2815 | 2022-03-31 |  | 69 | 0 | 2.5 | 0 |  | Hardeman | Wilbarger | Tier 4 |  |  |  |  | 6048, 6056, 6057, 6058 | Y | N |  |  | 14322 | 6571
6791 | Lake Pauline: Replace 138/69 kV Auto | Replace the 138/69 kV autotransformer at Lake Pauline with a 130 MVA autotransformer |  | Lake Pauline |  | Planned | 906 - 1084 | AEP TNC | Greg Crane mlforcum@aep.com 918-599-2674 | 2730 | 2022-03-31 |  | 138 | 0 | 0 | 130 |  | Hardeman |  | Tier 4 |  |  |  |  | 6048, 6050 | Y | N |  |  | 14589 | 6791
44399 | South Padre Island: Rebuild as GIS station | Rebuild South Padre Island as a GIS |  | South Padre Island | - | Planned | 948 - 1126 | AEP | James Nivens bcogan@aep.com 918-599-2857 | 3712 | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8335, 8917 | Y | N |  | 0 | 44400 | 44399
46456 | LookoutAddsSVC&Capbanks | Lookout adds SVC&Capbanks for voltage reliability |  | Lookout | Lookout | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-03-31 |  | 138 | 0 | 0 | 0 | 0,180 | Dallas | Dallas | Tier 4 | 20RPG003 |  |  |  | 828 | Y | N |  | 0 | 46457 | 46456
49948 | McCreeShilohLineUpgrades | McCree to Shiloh Line Upgrades to Cumberland |  | McCree | Shiloh | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-03-31 |  | 138 | 0 | 2.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 830, 834 | Y | N |  | 0 | 49949 | 49948
50843 | Heron: Build 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Update Cost, RPG Review Date | Heron |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2796 | 2022-03-31 |  | 138 | 0 | 0 | 90 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60447, 60448, 6610, 6611, 6614 | Y | N |  | 0 | 50844 | 50843
50845 | Kinnison: Expand 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line |  | Kinnison |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2797 | 2022-03-31 |  | 138 | 0 | 0 | 130 |  | Crane |  | Tier 3 |  |  |  |  | 60431, 60432 | Y | N |  | 0 | 50846 | 50845
50847 | Sage: Expand 69 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line |  | Sage |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2799 | 2022-03-31 |  | 69 | 0 | 0 | 0 |  | Crane |  | Tier 3 |  |  |  |  | 6604 | Y | N |  | 0 | 50848 | 50847
50892 | Seawall to Port Aransas: Replace 69 kV undersea cable | Replace Seawall to Port Aransas 69 kV undersea cable |  | Seawall | Port Aransas | Planned | 1058 - 1231 | AEP | Bill Roberts bcogan@aep.com 918-599-2857 | 3789 | 2022-03-31 |  | 69 | 0 | 0.5 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8435, 8442 | Y | N |  | 0 | 50893 | 50892
51010 | Heron to Ollin: Rebuild and convert to 138 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Update Cost, RPG Review Date | Heron | Ollin | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2798 | 2022-03-31 |  | 138 | 0 | 2 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60448, 60441 | Y | N |  | 0 | 51011 | 51010
51012 | Kinnison to Sage: Rebuild 69 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | Update RPG Date | Kinnison | Sage | Planned | 1048 - 1221 | AEP TNC | Gregory Crane mlforcum@aep.com 918-599-2674 | 2823 | 2022-03-31 |  | 69 | 0 | 0.25 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-17 |  | 60431, 6604 | Y | N |  | 0 | 51013 | 51012
59398A | San Bernard (SAN) Sub for Brazoria County Solar (20INR0098) | New 138kV San Bernard (SAN) substation for generator interconnection to Brazoria County Solar. Loop Ckt.04 into new substation to create new Ckt.04 West Columbia to San Bernard to Pledger tap |  | San Bernard | West Columbia/Pledger | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-03-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43110, 43120, 43380 | Y | N |  | 0 | 59767 | 59398
4487 | Nueces Area 69kV Reinforcement | Expand and add new 138/69kV Auto at Valero East 69kV substation. Add 5th breaker to Champlin 138kV substation. Construct Champlin to Valero East 138kV Line. |  | Champlin | Valero East | Planned | 709 - 0879 | AEP | John Pulay mlforcum@aep.com 918-599-2857 | 2903 | 2022-03-31 01:00 |  | 138 | 1.6 | 0 | 200 |  | Nueces |  | Tier 4 |  |  |  |  | 8528, 8476, 8859 | Y | N |  |  | 13570 | 4487
48818 | Ballinger: Replace the 138/69 kV autotransformer | Replace the 138/69 kV autotransformer at Ballinger with a 130 MVA autotransformer | Update Schedule | Ballinger |  | Planned | 1016 - 1194 | AEP | Dewey Peters mlforcum@aep.com 918-599-2674 | 2777 | 2022-03-31 01:00 |  | 138 | 0 | 0 | 130 |  | Runnels |  | Tier 4 |  |  |  |  | 6338, 6340 | Y | N |  | 0 | 48819 | 48818
5621 | South McAllen-Bentsen and North Edinburg-West Edinburg | Replace MLSE equipment at North Edinburg and South McAllen | Update Schedule | North Edinburg | North McAllen | Planned | 795 - 0980 | AEP TCC | Michael Richardson bcogan@aep.com 918-599-2857 | 3585 | 2022-04-07 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5771, 8367, 8371, 8368, 8380, 8758, 8822 | Y | N |  |  | 13351 | 5621
53956 | Coronado - Fairland Transmission Line Upgrade | Increase the reliability of transmission facilities on the T110 Coronado - Fairland 12.4-mile 138-kV transmission line by replacing the existing Condor conductor with Drake conductor. |  | Coronado | Fairland | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-04-07 |  | 138 | 0 | 0 | 0 |  | Burnet | Llano | Tier 4 |  |  |  |  | 7087, 7518 | Y | N |  | 0 | 53957 | 53956
52064 | Bay City - Lane City: 138 kV Line Rebuild | Rebuild the Bay City - Magill - Lane City 138 kV Line | Update Schedule, Dollars, Tier, Sponser | Bay City | Lane City | Planned | 1078 - 1251 | AEP | Marc E. Wilson bcogan@aep.com 918-599-2857 | 3803 | 2022-04-09 |  | 138 | 0 | 16 | 0 |  | Matagorda | Wharton | Tier 3 |  |  |  |  | 8111, 8113, 8127 | Y | N |  | 0 | 52065 | 52064
7161 | Naval_Base-North_Padre: Rebuild and re-conductor | For Naval Base-North Padre Tap: Rebuild line to 138 kV standards with 2000A conductor (795 ACSS). For North Padre Tap - North Padre station, double ckt. line is already built to 138 kV standards with 477 ACSR. Re-conductor both circuits with largest possible conductor to achieve maximum rating. The 2nd ckt. is part of the North Padre - Mustang Island branch |  | Naval Base | North Padre Tap | Planned | 909 - 1087 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3690 | 2022-04-30 |  | 69 | 0 | 12.7 | 0 |  | Nueces | Nueces | Tier 3 |  |  |  |  | 8495, 8847, 8856 | Y | N |  |  | 15002 | 7161
48776 | Tidehaven: Construct New Distribution Station | Tidehaven: Construct New Distribution Station |  | Blessing | Lolita | Planned | 1028 - 1206 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3767 | 2022-04-30 |  | 138 | 0 | 0 | 0 |  | Matagorda | Jackson | Tier 4 |  |  |  |  | 8044, 8121, 8125 | Y | N |  | 0 | 48777 | 48776
55217 | Putnam to Leon: Rebuild 138 kV line | Rehab Putnam to Leon 138 kV line | Update Contact, Cost, Tier | Putnam | Leon | Planned | 1042 - 1269 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1859 | 2022-04-30 |  | 138 | 0 | 21.93 | 0 |  | Callahan | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | N |  | 0 | 55218 | 55217
55421 | Ballinger to Concho: Rebuild 69 kV line | Rebuild 69 kV line from Ballinger to Concho, install POD box bay for Rowena, install CB at Miles, install POP switches for Harriett REA and Warbler | Update RPG Dates | Ballinger | Concho | Planned | 1088 - 1271 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1861 | 2022-04-30 |  | 69 | 0 | 20.45 | 0 |  | Runnels | Tom Green | Tier 3 |  | 2020-04-08 | 2020-04-30 |  | 6409, 60800, 6338, 6410, 6412, 6413, 6450, 6411 | Y | N |  | 0 | 55422 | 55421
57414 | BEARLE (BER) 138kV Customer Substation | BEARLE (BER) 138kV customer substation looped into Ckt.96C Philip to South Channel |  | BEARLE | Philip/South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-04-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41230, 41250, 41370 | Y | N |  | 0 | 57415 | 57414
59088 | Alice - Falfurrias: Line Rebuild | Alice - Falfurrias: Line Rebuild | NEW | Alice | Falfurrias | Planned |  | AEP | Glen Reed gareed@aep.com 918-599-2664 | TP2020088 | 2022-04-30 |  | 69 | 0 | 3.67 | 0 |  | Jim Wells | Brooks | Tier 2 |  |  |  |  | 8500, 8508, 8878, 8894 | Y |  |  | 0 | 59089 | 59088
44513 | Concho to Live Oak: Rebuild 69 kV line | Rebuild remaining portions of the Concho to Live Oak 69 kV line | Update Schedule | Concho | Live Oak | Planned | 941 - 1119 | AEP TNC | Jim Nivens mlforcum@aep.com 918-599-2674 | 2755 | 2022-04-30 01:00 |  | 69 | 0 | 3.3 | 0 |  | Tom Green | Schleicher | Tier 4 |  |  |  |  | 6450, 6494, 6495, 6496, 6497, 6498, 6527 | Y | N |  | 0 | 44514 | 44513
58542 | Texas City RPG | Texas City RPG |  | Cat Tail (38580), Cherokee (39075) & Greenbelt (38575) | Texas City Main (39140,39141) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-05-01 |  | 138 | 4.1 | 0 | 200 |  | Galveston | Galveston | Tier 2 |  | 2020-04-16 | 2020-09-16 |  | 38580, 39141, 38575, 39075, 39140 | Y |  |  | 0 | 58543 | 58542
4567 | BRYN_4567_Smetana_to_Leonard | Build Smetana to Leonard Rd 138 line in existing 69KV ROW of old Annex to Atkins line |  | 32897 | 32863 | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.co 979-821-5763 |  | 2022-05-05 |  | 138 | 0.75 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32853, 32851 | Y |  |  |  | 12149 | 4567
5792 | Leonard Road Substation 138 | Upgrade Leonard Rd from 69kV to 138kV and construct 138 from Leonard to Atkins |  |  |  | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2022-05-05 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32851, 32862, 32864 | Y |  |  | 0 | 53867 | 5792
47436 | ROBERT BROWN JR ¿ SAN MARCOS Transmission Line OverHaul | Increase the reliability and capability of circuit T220 on the Robert Brown Jr ¿ San Marcos 4.9-mile 69-kV transmission line. Upgrade all structures to 138-kV class and bundled Suwannee capable. Upgrade conductor to bundled 959 ACSS Suwannee. Add OPGW. |  | Robert Brown JR | San Marcos | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-06 |  | 138 | 0 | 0 | 0 |  | Hays | Caldwell | Tier 4 |  |  |  |  | 7191, 7194, 7196 | Y | N |  | 0 | 47437 | 47436
46968 | Gabriel Substation Upgrade | LCRA TSC will upgrade the configuration of the 138-kV bus from single bus/single breaker to a breaker and a half bus configuration and replace five existing CBs at Gabriel Substation and provide for future Georgetown PWT addition. |  | Gabriel | Gabriel | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-13 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y | N |  | 0 | 46969 | 46968
47541 | Crane Circuit Breaker Addition | Provide transmission service to American Electric Power at Crane Substation. Adding one (1) breaker and associated equipment needed to connect the AEP-owned Crane to Kinnison 138-kV transmission line. |  | Crane Substation | Crane Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-13 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 76615 | Y | N |  | 0 | 47542 | 47541
53965 | Red Rock - Tahitian Transmission Line Overhaul | LCRA TSC will perform an overhaul of T153 with replacement structures that are capable of operating at 138-kV and supporting a single 959 ACSR Suwannee conductor. The replacement conductor on T153 will be 595 ACSR Suwannee. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  | Red Rock | Tahitian Village | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-05-13 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7560, 7575, 7576 | Y | N |  | 0 | 53966 | 53965
54101 | Ranch Road - Hilltop Transmission Line Upgrade | Increase the reliability of transmission facilities on the T375: Hilltop-Ranch Road 12 3.95-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | Ranch Road 12 | Hilltop | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-05-13 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7186, 7190 | Y | N |  | 0 | 54102 | 54101
14TPIT0056 | Northaven - Morrison 138 kV line | Upgrade existing double-circuit line |  | Northaven | Morrison | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4088-E | 2022-05-15 |  | 138 | 0 | 12 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2655, 2656, 2660, 2661, 2662, 2663, 2782, 2783 | Y | N |  |  | 9773 | 2493
5467 | Nacogdoches Southeast_Redland 345kV Line | Establish a new 345kV Line between Nacogdoches Southeast Switch and Redland Switch |  | Nacogdoches Southeast | Redland | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6075 | 2022-05-15 |  | 345 | 13.4 | 0 | 0 |  | Nacogdoches | Angelina | Tier 2 | 20RPG019 | 2020-10-01 |  |  | 3119, 3321 | Y | N |  |  | 13171 | 5467
5491 | Whitestone - Leander 138kV Transmission Line Upgrade | Upgrade the Whitestone - Blockhouse (T469) and the Blockhouse - Leander (T326) 138kV Line to 441MVA. |  | Whitestone | Leander | Under Construction |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2022-05-15 |  | 138 | 0 | 5.4 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7525, 7527, 7529 | Y | N |  | 0 | 51769 | 5491
6273 | Saginaw-Eagle Mountain 138 kV DCKT | Upgrade the Saginaw - Eagle Mountain 138 kV Double Circuit Line |  | Saginaw | Eagle Mountain | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5274 | 2022-05-15 |  | 138 | 0 | 28 | 0 |  | Tarrant | Tarrant | Tier 3 | 20RPG011 |  | 2020-07-24 |  | 1864, 2066, 2067, 2071, 2074, 1860, 2069, 2070, 2076, 11860 | Y | N |  | 0 | 59961 | 6273
7020 | Cedar Hill - Camp Wisdom 138 kV Line | Upgrade existing Cedar Hill - Camp Wisdom 138 kV Line |  | Cedar Hill | Camp Wisdom | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4250 | 2022-05-15 |  | 138 | 0 | 9.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2421, 2990, 2993, 2994, 2992, 2999 | Y | N |  |  | 14842 | 7020
47428 | Bellville South - Prairie View Transmission Line Upgrade | The proposed project converts the existing 69-kV transmission line T283 from Bellville South - Quanex Switch - Sunnyside Prairie View Substation to 138-kV. The proposed project improves the reliability of transmission facilities on the 26.1-mile transmission line and increases the line capacity for long term system growth. |  | Bellville South | Prairie View | Conceptual |  | SBEC | James Jouett jjouett@sbec.org 979-413-7714 |  | 2022-05-15 |  | 69 | 0 | 0 | 0 |  | Austin | Waller | Tier 3 |  |  |  |  | 7269, 7660, 7664, 7666 | N | N |  | 0 | 47429 | 47428
56350A | Burnett-Ringgold Magnolia Tap 69 kV Line |  |  | Burnett | Ringgold Magnolia Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2022-05-15 |  | 69 | 0 | 21 | 100 |  | Wichita | Clay | Tier 3 |  |  |  |  | 1452, 1523, 1543, 1544, 1426, 1491, 1545 | Y | N |  | 0 | 56861 | 56350
57163 | Rebuild VanHumble to Olivia Switch | Rebuild 4/0 ACSR with 795 ACSR on 138 kV capable poles |  | Van Humble Switch | Olivia Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-05-15 |  | 69 | 0 | 14.4 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 5574, 5580 | Y | N |  | 0 | 57164 | 57163
57167 | Faysville substation conversion from 69 to 138 kV | The lines from North Edinburg to Faysville Switch to Faysville will be rebuilt to 138 kV. Faysville substation will be built to 138 kV. |  | Faysville | North Edinburg | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-05-15 |  | 138 | 0 | 8.46 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5782, 5786, 5787, 5788, 5780, 8380 | Y | N |  | 0 | 57168 | 57167
57731B | Hornsby Substation Addition | Construct a new 345-kV substation between Clear Springs to Gilliland Creek 345-kV transmission line to provide transmission service to a load-serving substation. Restore 138-kV transmission line from Decker to Sand Hill by removing temporary substation/arrangements made in first phase to serve load. |  | Clear Springs | Gilleland Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-15 |  | 345 | 0 | 0 | 960 |  | Travis | Travis | Tier 4 |  |  |  |  | 7047, 7916, 7050, 9187, 7340, 9216 | Y | N |  | 0 | 57740 | 57731
59406 | Tex Harvey 138 kV Capacitors | Add Tex Harvey 138 kV Capacitors |  | Tex Harvey | Tex Harvey | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8567 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Midland | Midland | Tier 4 |  |  |  |  | 1221 | Y |  |  | 0 | 59408 | 59406
59409 | Centralia 138 kV Capacitors | Add Centralia 138 kV Capacitors |  | Centralia | Centralia | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8568 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Upton | Upton | Tier 4 |  |  |  |  | 11209 | Y |  |  | 0 | 59534 | 59409
59412 | Grady 138 kV Capacitors | Add Grady 138 kV Capacitors |  | Grady | Grady | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8571 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Martin | Martin | Tier 4 |  |  |  |  | 23842 | Y |  |  | 0 | 59535 | 59412
59415 | Crane East 138 kV Capacitors | Add Crane East 138 kV Capacitors |  | Crane East | Crane East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8577 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Upton | Upton | Tier 4 |  |  |  |  | 1214 | Y |  |  | 0 | 59537 | 59415
59418 | Brown 138 kV Capacitors | Add Brown 138 kV Capacitors |  | Brown | Brown | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8551 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Martin | Martin | Tier 4 |  |  |  |  | 23838 | Y |  |  | 0 | 59538 | 59418
59421 | McIlvain 138 kV Capacitors | Add McIlvain 138 kV Capacitors |  | McIlvain | McIlvain | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8562 | 2022-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Reeves | Reeves | Tier 4 |  |  |  |  | 11182 | Y |  |  | 0 | 59533 | 59421
59525 | Cedar Crest Switch - Wall Street 69 kV Line Section Conversion To 138 kV | Convert existing 69 kV Line to 138 kV operation |  | Cedar Crest | Wall Street | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4071 | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2982, 2983, 2486, 2494, 2977 | Y |  |  | 0 | 59526 | 59525
59546 | Lamesa 138/69 kV Autotransformer #1 | Replace Lamesa 138/69 kV Autotransformer #1 |  | Lamesa | Lamesa | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8561 | 2022-05-15 |  | 138 | 0 | 0 | 86 |  | Dawson | Dawson | Tier 4 |  |  |  |  | 1163, 1355, 1164, 1356 | Y |  |  | 0 | 59548 | 59546
59552 | Rebuild Eskota - Sweetwater No.2 69 kV Line | Rebuild Eskota - Sweetwater No.2 69 kV Line |  | Eskota | Sweetwater No. 2 | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8570 | 2022-05-15 |  | 138 | 0 | 16.3 | 0 |  | Nolan | Nolan | Tier 4 |  |  |  |  | 1377, 1382, 1383, 1386, 1387, 11385, 1340, 1381, 1384, 1385, 11384 | Y |  |  | 0 | 59554 | 59552
59763 | Construct three terminal 138 kV capable switching station | Change Markham hard wire tap point to 3 way switching station |  | Cayce Switch |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-05-15 |  | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5554 | Y | N |  | 0 | 59764 | 59763
59839 | Duck Cove Tap #1 - Wills Point 69 kV Double Circuit Line | Rebuild the 3.1-mile Duck Cove Tap #1 - Wills Point 69 kV Double-Circuit Line Section, using 138 kV double-circuit structures with two circuits in place and loop through Wills Point. Use a conductor rated 1649 A or greater. |  | Edgewood | Iron Bridge | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6137 | 2022-05-15 |  | 69 | 0 | 3.1 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 3187, 3188, 3189 | Y |  |  | 0 | 59840 | 59839
60060 | Add Marlin South 69 kV Cap Bank | Add Marlin South 69 kV Cap Bank |  | Marlin South | Marlin South | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R468 | 2022-05-15 |  | 69 | 0 | 0 | 0 | 0,27.6 | Falls | Falls | Tier 4 |  |  |  |  | 3641 | Y |  |  | 0 | 60061 | 60060
60064 | Add McGregor 69 kV Capacitor | Add McGregor 69 kV Capacitor |  | McGregor | McGregor | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R790 | 2022-05-15 |  | 69 | 0 | 0 | 0 | 0,55.2 | McLennan | McLennan | Tier 4 |  |  |  |  | 3586 | Y |  |  | 0 | 60065 | 60064
57919 | Add Buzzard Draw 138 kV Terminal Additions | Add Buzzard Draw 138 kV Terminal Additions |  | Buzzard Draw | Buzzard Draw | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8555 | 2022-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 1355, 23829, 23838 | Y |  |  | 0 | 57921 | 57919
57925 | Midland County Northwest to Texaco Mabee Tap 138 kV Double-Circuit Line Section | Add Midland County NW - Texaco Mabee Tap 138 kV Double-Circuit Line Section Rebuild |  | Midland County Northwest | Texaco Mabee Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8558 | 2022-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 |  |  | 11299, 11300, 11301, 1178, 1179, 1182, 1183 | Y |  |  | 0 | 60059 | 57925
14TPIT0010 | Handley - Sherry 138 kV line | Upgrade existing line |  | Handley | Sherry | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5155-E | 2022-05-15 12:00 |  | 138 | 0 | 8.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1919, 1920, 1950, 1951, 2245, 2246, 2247, 2251, 2252 | Y | N |  | 0 | 59262 | 2582
6979 | Lexington Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Lexington Substation. |  | Lexington |  | In-Service | 1018928 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018928 | 2022-05-16 |  | 138 | 0 | 0 | 0 |  | Burleson |  | Tier 4 |  |  |  |  | 7571 | Y | N |  |  | 14796 | 6979
59389 | Johnson Draw POD - Flat Iron Substation 138 kV line | Johnson Draw POD - Flat Iron Substation 138 kV line |  | Johnson Draw POD | Flat Iron Substation | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8580 | 2022-05-16 |  | 138 | 3 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11217, 11344 | Y |  |  | 0 | 59391 | 59389
53962 | Turtle Creek - Verde Creek Transmission Line Overhaul | LCRA TSC will perform an overhaul of T221 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T221 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  | Turtle Creek | Verde Creek | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2022-05-25 |  | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7146, 7442 | Y | N |  | 0 | 53963 | 53962
6872 | Support 69kV to 138kV Conversion Projects | Removing of Lawler substation from system to support 69kV to 138kV conversion projects |  |  |  | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-05-27 |  | 69 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 815, 820, 803, 806 | Y | N |  |  | 14681 | 6872
48248 | BrandToCollegeLineUpgrade | Brand to College Line Upgrade to Cumberland |  | Brand | College | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-05-27 |  | 138 | 0 | 4.16 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 827, 829 | Y |  |  | 0 | 48249 | 48248
50880 | Medio Creek to Warburton (STEC) | Lon Hill - STEC Warburton: Line Rebuild |  | Medio Creek | STEC Warburton | Planned | 1055 - 1228 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3783 | 2022-05-30 |  | 138 | 0 | 32.7 | 0 |  | San Patricio | Refugio | Tier 3 |  | 2019-09-05 | 2019-10-07 |  | 5607, 8912 | Y | Y |  | 0 | 50881 | 50880
4010 | Rebuild Magnolia - Seminole 138 kV line. | *Project pushed back to 2022. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07216 | 2022-05-31 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38950, 38990 | Y |  |  |  | 11530 | 4010
4465 | Wirtz to FlatRock to Paleface Transmission Line Upgrade | Upgrade the 17.34 mile Wirtz (7104) - Flat Rock (7111) - Paleface (7477) 138-kV transmission line to bundled 795 ACSR Drake, 441 MVA. |  | Wirtz | Paleface | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com (830) 868-5041 |  | 2022-05-31 |  | 138 | 0 | 17.34 | 0 |  | Burnet | Travis | Tier 4 |  |  |  |  | 7104, 7111, 7477 | Y | N |  |  | 12026 | 4465
5244 | Hardy to Northside Ckt.91 Thermal Uprate | Upgrade Ckt.91 Hardy to Northside to increase thermal ratings | - Overall Date Update | Hardy | Northside | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45840, 47711 | N | N |  |  | 12919 | 5244
6980 | Weimar Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Weimar Substation. |  | Weimar |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Colorado |  | Tier 4 |  |  |  |  | 7254, 7258 | Y | N |  |  | 14797 | 6980
52197D | Jordan Auto A3 Addition (PLACID 138kV Sub) | Upgrade Ckt.86J Connor to Bender to increase thermal limits. |  | Connor | Bender | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 19RPG017 | 2019-10-25 | 2019-11-18 |  | 40155, 40665 | Y | N |  | 0 | 57348 | 52197
52218 | Alvin 69kV Substation Bypass | Alvin 69kV Substation Bypass |  | Webster | Manvel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 69 | 0 | 0 | 0 |  | Galveston | Brazoria | Tier 4 |  |  |  |  | 42080, 42600, 43510, 44440 | Y | N |  | 0 | 52225 | 52218
52533 | Gebhardt to Sealy Ckt.65A Upgrades | Upgrade Ckt.65A Gebhardt to Sealy to increase thermal limits (Transmission Design Hardening Project) |  | Gebhardt | Sealy | Planned | 525535253359322 | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 2.46 | 0 |  | Austin | Austin | Tier 3 | 20RPG020 | 2020-10-27 | 2020-11-18 |  | 44640, 44700 | Y | N |  | 0 | 52534 | 52533
52553 | Wallis to Gebhardt Ckt.65C Upgrades | Upgrade Ckt.65C Wallis to Gebhardt to increase thermal limits. |  | Wallis | Gebhardt | Planned | 525535253359322 | CNP | Wesley Woitt wesley.woitt@centerpointe 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 9.58 | 0 |  | Austin | Austin | Tier 3 | 20RPG020 | 2020-10-27 | 2020-11-18 |  | 44700, 44740 | Y | N |  | 0 | 52554 | 52553
54811 | Winecup: Build 69 kV station | Construct new 69 kV box bay on the North San Angelo to San Angelo Grape Creek Tap 69 kV line |  | Winecup |  | Planned | 1041 - 1268 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1858 | 2022-05-31 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 60796, 6459, 6465 | Y | N |  | 0 | 54812 | 54811
55550 | Brushline: Construct New Distribution Station | Brushline: Construct New Distribution Station |  |  |  | Planned | 1106 - 1284 | AEP TCC | Rick Garcia bcogan@aep.com 918-599-2857 | 3826 | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8972, 5754, 8963 | Y |  |  | 0 | 55551 | 55550
55961 | PSARCO to Highlands Ckt.08G Upgrades | Upgrade Ckt.08G PSARCO to Highlands with minimum 427MVA Continuous Rating |  | Highlands | PSARCO | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40811, 41300 | Y | N |  | 0 | 55962 | 55961
57584 | Cedar Bayou Auto A1 and A3 Position Swaps at 138kV | Swap Cedar Bayou Auto A1 and A3 Positions on the 138kV side to address fault concerns |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 345 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  |  | 40000, 40010, 40015, 49005, 49008 | Y | N |  | 0 | 57585 | 57584
57735A | Mykawa 138kV Switching Station | Install new CNP-owned 138kV switching station |  | Pearland |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42750 | Y | N |  | 0 | 57736 | 57735
57750 | Seabrook 138kV Distribution Substation | Build new 138kV Seabrook distribution substation. Double tap from Ckt.79F PH Robinson to Hanna and Ckt.96A PH Robinson to Bayou. |  | Seabrook |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 42851, 42852, 42013, 42014, 42160, 42780 | Y | N |  | 0 | 57751 | 57750
57912 | Champlin to Weil Tract: Rebuild 138 kV Line | Champlin to Weil Tract Line Rebuild |  | Champlin | Weil Tract | Planned | 1111 - 1289 | ETT | Nathan Cowan mlforcum@aep.com 918-599-2674 | 3830 | 2022-05-31 |  | 138 | 0 | 1.37 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8476, 8482 | Y | N |  | 0 | 57913 | 57912
58006 | Magnolia Cap Bank | Install Cap bank (14.4 Mvar ) at Magnolia |  | Kosciusko |  | Planned | 1115 - 1293 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3834 | 2022-05-31 |  | 138 | 0 | 0 | 0 | 0,14.4 |  |  | Tier 4 |  |  |  |  | 8583 | Y |  |  | 0 | 58007 | 58006
58008 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild 11.691 miles of the Laredo VFT North to North Laredo Switch 138 kV transmission line and upgrade any limiting elements. |  | Laredo | Laredo | Planned | 1116 - 1294 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3835 | 2022-05-31 |  | 138 | 11.68 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8112, 8643, 8909, 8918, 80013 | Y |  |  | 0 | 58009 | 58008
59086 | Edna to Victoria: Rebuild 138 kV line | Rebuild 138 kV line from Enda to Victoria | NEW | Edna | Victoria | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2020888 | 2022-05-31 |  | 138 | 0 | 26.35 | 0 |  | Jackson | Victoria | Tier 3 |  |  |  |  | 8118, 8172 | Y | N |  | 0 | 59087 | 59086
59322 | Sealy to Peters Ckt.65A Upgrades | Upgrade Ckt.65A Sealy to Peters to increase thermal limits |  | Sealy | Peters | Planned | 525535253359322 | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 5.07 | 0 |  |  |  | Tier 3 | 20RPG020 | 2020-10-27 | 2020-11-18 |  | 44640, 46220 | Y | N |  | 0 | 59323 | 59322
59342 | Greens Bayou to LYCHEM Ckt.08 Upgrade | Rebuild and reconductor a de-energized section of Ckt.38Z. Loop the rebuilt section into 138kV Ckt.08F between Moore Road and Uvalde tap. The reconfiguration creates additional conductor impedance on the line to increase the fault duty margin for future generation. |  | Moore Road | Uvalde | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 3.25 | 3.25 | 0 |  |  |  | Tier 4 |  |  |  |  | 40559, 40281, 40555, 41023, 41651 | Y | N |  | 0 | 59343 | 59342
59346 | Hillcroft to Dunvale Ckt.24B Upgrades | Upgrade Ckt.24B Hillcroft tap to Dunvale tap with minimum 340MVA Emergency Rating |  | Hillcroft | Dunvale | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 1.04 | 0 |  |  |  | Tier 4 |  |  |  |  | 47072, 47191 | Y | N |  | 0 | 59347 | 59346
59398B | San Bernard (SAN) Sub for Brazoria County Solar (20INR0098) | Upgrade San Bernard to West Columbia Ckt.04 to increase thermal limits. Increase fault duty at West Columbia to 63KA |  | San Bernard | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43110, 43120 | Y | N |  | 0 | 59768 | 59398
57735B | Mykawa 138kV Switching Station | Loop Ckt.06K into new CNP-owned 138kV switching station to create new Ckt.06 Gulfgate to Mykawa to Pearland |  | Mykawa | Gulfgate/Pearland | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42742, 42750, 43051 | Y | N |  | Cost include in main project | 57737 | 57735
59319A | Garrott to Midtown to Polk Ckt.90 Upgrades | Upgrade Ckt.90D Garrott to Midtown to increase thermal limits |  | Garrott | Midtown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 47660, 47706, 47661, 47705 | Y | N |  | 0 | 59320 | 59319
57735C | Mykawa 138kV Switching Station | Loop Ckt.91A into new CNP-owned 138kV switching station to create new Ckt.91 Gulfgate to Mykawa to Pearland |  | Mykawa | Gulfgate/Pearland | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42741, 42750, 43052 | Y | N |  | Cost include in main project | 57738 | 57735
59319B | Garrott to Midtown to Polk Ckt.90 Upgrades | Upgrade Ckt.90B Midtown to Polk to increase thermal limits |  | Midtown | Polk | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 47705, 47731, 47707, 47730 | Y | N |  | Cost included in main entry | 59321 | 59319
11TPIT0008 | RAINEY_ST 138kV substation | Establish a new 138kV Rainey St. Substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2022-06-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9261, 9118, 9132 | Y | N |  |  | 8208 | 1032
17TPIT0002 | Hunt Lane to Pinn Road - 138 kV Transmission Line Rebuild | Rebuild approximately eight circuit miles of 138 kV transmission from Hunt Lane to Pinn Road |  | Hunt Lane | Pinn Rd | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0190 | 2022-06-01 |  | 138 | 0 | 8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5054, 5305, 5324, 5345, 5427 | Y | N |  | There are no transformers associated with this project | 9558 | 2307
45136 | CPSE_New Midtown Substation | New Mid Town substation looped into Comal St to Olmos transmission line. |  |  |  |  | S-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0283 | 2022-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5311, 5096, 5325 | Y |  |  | 0 | 45137 | 45136
48327 | Reconductor 138kV ckt 972 Howard Lane to McNeil to 3000A. |  |  | 9079 | 9217 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinene (512) 322-6740 |  | 2022-06-01 |  | 138 | 0 | 2.81 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9079, 9217 | Y |  |  | 0 | 48328 | 48327
60522 | Rebuild Hidden Lakes-League City with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  | 0 | 60523 | 60522
6971 | Magnolia Mercer Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Magnolia Mercer Substation. |  | Magnolia Mercer |  | Planned | 1018915 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018915 | 2022-06-10 |  | 69 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7218, 7215, 7220 | Y | N |  |  | 14788 | 6971
59541 | Wolf 138 kV Terminal Addition | Add Wolf 138 kV Terminal Addition |  | Wolf Switch | Wolf Switch | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8505 | 2022-06-15 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 1013 | Y |  |  | 0 | 59543 | 59541
4577 | BRYN_4577_Dansby_Rebuild | Convert Dansby 69kV bus to Double Bus, Double Breaker configuration |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.co 979-821-5763 |  | 2022-06-29 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  |  | 32875, 32897 | Y |  |  | 0 | 45636 | 4577
3948 | Steamboat to Tuscola: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola | Update Contact, Schedule, Cost | Steamboat | Tuscola | Planned | 685 - 0855 | ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | 1851 | 2022-06-30 |  | 69 | 0 | 9.856 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6328, 6331, 60332 | Y | N |  |  | 11441 | 3948
3949 | Steamboat to Winters: Rebuild 69 kV line | Rebuild Winters to Steamboat and Steamboat to Tuscola | Update Contact, Schedule, Cost | Steamboat | Winters | Planned | 685 - 0855 | ETT | Curtis Brown mlforcum@aep.com 918-599-2674 | 1850 | 2022-06-30 |  | 69 | 0 | 9.944 | 0 |  | Taylor | Runnels | Tier 4 |  |  |  |  | 6333, 60332 | Y | N |  |  | 11442 | 3949
5154 | Holford 138 kV new load substation and connections | Holford 138 kV new substation and its connections to CampbellSW and to Firewheel as well as some load growths at Holford |  | CampbellSW | Firewheel | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-06-30 |  | 138 | 0 | 1.5 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 835, 821, 838 | Y |  |  |  | 12810 | 5154
50440 | Delhi Substation Addition | Add a new load serving substation 10 miles north of IH-10 along 304, w/30 MVA PWT. |  | Delhi | Delhi | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-06-30 |  | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7896 | Y | N |  | 0 | 50441 | 50440
51734 | Blue Stem to Delhi Transmission Line | Build new 9.5 mile 138/69 kV transmission. |  | BlueStem | Delhi | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-06-30 02:00 |  | 69 | 9.5 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7895, 7230, 7231, 7896 | Y | N |  | 0 | 51843 | 51734
5457 | Load serving | New station to aid in DME's load serving |  | Brinker |  | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2022-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 906, 907, 913, 921 | Y | N |  |  | 13160 | 5457
47442 | Graphite Mine Circuit Breaker Addition | LCRA TSC will increase the reliability of transmission facilities along T109 by adding three 138-kV, 3000A, 40kAIC circuit breakers in ring-bus configuration at the Graphite Mine Substation. |  | Graphite Mine | Graphite Mine | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2022-07-12 |  | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  |  | 7084 | Y | N |  | 0 | 47443 | 47442
6072 | Eldorado to Ft. McKavitt 69 kV line: Rebuild 69 kV line | Rehab Eldorado to Ft. McKavitt 69 kV line |  | Eldorado Tap | Ft. McKavitt | Planned | 786 - 0971 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2677 | 2022-07-31 |  | 69 | 0 | 19.41 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  |  | 6505, 6506, 6507, 6508 | Y | N |  |  | 13794 | 6072
5165 | Poesta: Construct a new 138/69 kV station | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. |  | Borglum |  | Under Construction | 742 - 0925 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 2914 | 2022-08-30 |  | 138 | 0 | 0 | 130 |  | Bee |  | Tier 1 |  | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8196, 8197, 8205, 8107, 8198, 8199, 8904 | Y | N |  |  | 13315 | 5165
5166 | Poesta to Three Rivers: Rebuild 69 kV line | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. |  | Borglum | Three Rivers | Under Construction | 742 - 0925 | AEP TCC | Dave Gotez bcogan@aep.com 918-599-2857 | 2915 | 2022-08-30 |  | 138 | 6 | 22 | 0 |  | Bee | Live Oak | Tier 1 |  | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8156, 84006, 8142, 8199, 8196, 8400, 8403 | Y | N |  | 0 | 57889 | 5166
5167 | Poesta to Tuleta: Build new double circuit 138/69 kV line | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. |  | Borglum | Tuleta | Under Construction | 742 - 0925 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 2916 | 2022-08-30 |  | 138 | 23.5 | 23.5 | 0 |  | Bee | Bee | Tier 1 |  | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8584, 8629, 88198, 8196, 8197, 8198, 8586, 8592, 85851, 8585, 8590, 8593 | Y | N |  |  | 13317 | 5167
59093 | Starr Solar Connection | Starr Solar Connection | NEW | Roma Tap |  | Planned |  | AEP | Glen Reed gareed@aep.com 918-599-2664 | TP2020209 | 2022-09-28 |  | 138 | 0.1 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 88795, 8795 | Y |  |  | 0 | 59094 | 59093
59099 | Rebuild Blessing to Celanese 138 kV Line | Rebuild Blessing to Celanese 138 kV Line | NEW | Matagorda |  | Planned |  | AEP | Glen Reed gareed@aep.com 918-599-2664 | TP2020227 | 2022-09-28 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8116, 8121, 8191, 8558 | Y |  |  | 0 | 59100 | 59099
45399 | Bearkat Loop - Bearkat to Longshore | Adds 345 KV line from Bearkat to Longshore. |  | Bearkat | Longshore | Planned |  | WETT/ONCOR | Christina Minchew christina.minchew@windene 512-436-9469 |  | 2022-09-30 |  | 345 | 27 | 0 | 0 |  | Glasscock | Howard | Tier 1 |  | 2017-08-15 | 2018-09-19 | 2018-10-09 | 1058, 59903 | Y | N |  | 0 | 45473 | 45399
59293 | Maddux: Build New 138 kV Station | Interconnect Concho Valley Solar to the SAPS to Treadwell AND the SAPS to Eldorado Live Oak 138 kV Lines | NEW | Maddux |  | Planned | 1125 - 1303 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 1870 | 2022-09-30 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6015, 6016, 6480, 6490, 60423 | Y | N |  | 0 | 59294 | 59293
3505 | Cibolo Substation, T3 transformer addition | Add T3, 40 MVA 138-26.18 kV power transformer, CSW and low side |  | Cibolo |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-10-14 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7608 | Y | N |  |  | 10887 | 3505
48288C | BOGGY (BOG) 138kV Substation (SHELL Substation Replacement) | Install new customer-owned BOGGY 138kV substation. Loop from Ckt.88 to create new Ckt.88 PAIR to BOGGY to ESBELT |  | BOGGY | PAIR/ESBELT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-10-18 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40530, 41210, 41350, 41370, 41460 | Y | N |  | Cost Included in 48288A | 57334 | 48288
49572 | Goodlett to Quanah: Build a new portion of 69 kV line | Build new section of 69 kV line between Goodlett and Quanah | Update Cost, RPG Review Dates, Tier | Goodlett | Quanah | Planned | 1022 - 1200 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2784 | 2022-10-31 |  | 69 | 6 | 0 | 0 |  | Hardeman |  | Tier 2 |  | 2019-11-01 | 2020-01-01 |  | 6052, 6051, 60446 | Y | N |  | 0 | 49573 | 49572
50952 | Whitepoint: Replace reactors | Replace the 10 ohm reactors with 19.08 ohm reactors at Whitepoint |  | Whitepoint |  | Planned | 1086 - 1259 | AEP | Michael Glueck bcogan@aep.com 918-599-2857 | 3806 | 2022-10-31 |  | 138 | 0 | 0 | 0 | -18.16,0 | San Patricio |  | Tier 4 |  |  |  |  | 8961, 80128, 80129 | Y | N |  | 0 | 50953 | 50952
49564 | Mantle: Construct New 345 kV Station | Mantle: Construct New 345 kV Station | Update Contact, Schedule | Bonilla | North Edinburg | Planned | 1035 - 1213 | AEP TCC | Joe Yeagler bcogan@aep.com 918-599-2857 | 3774 | 2022-10-31 20:00 |  | 345 | 0 | 0 | 0 |  | Cameron | Hidalgo | Tier 4 |  |  |  |  | 8059, 80598, 8383, 8573 | Y | N |  | 0 | 49565 | 49564
48288A | BOGGY (BOG) 138kV Substation (SHELL Substation Replacement) | Remove existing customer-owned SHELL (_SL) 138kV Substation |  | SHELL |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-11-03 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41450, 40070, 40530, 41460, 41210 | Y | N |  | 0 | 57332 | 48288
54109 | Fayetteville - Substation Upgrade | Increase the reliability of substation equipment at Fayetteville Substation through the replacement of the Fayetteville AT2 autotransformer and installation of two 138-kV shunt reactors. |  | Sayetteville Substation | Sayetteville Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-11-22 |  | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7057, 7286, 7853 | Y | N |  | 0 | 54110 | 54109
55603 | Big Foot to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley |  | Big Foot | Pearsall | Planned | 1104 - 1282 | AEP | Bill Roberts bcogan@aep.com 918-599-2857 | 3821 | 2022-11-30 |  | 69 | 0 | 14.79 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8218, 8216 | Y |  |  | 0 | 55604 | 55603
57797 | Athey: Build 138 kV Station | Build new 138 kV Station on the Ft Stockton to Rio Pecos 138 kV line | Update Description, Contact, Schedule, kV Level | Athey |  | Planned | 1109 - 1287 | AEP TNC | John Pulay mlforcum@aep.com 918-599-2674 | 1866 | 2022-11-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60792, 60718, 60798 | Y | N |  | 0 | 57798 | 57797
59324 | Creosote: Build 138 kV Station | Build new 138 kV Station on the Pig Creek to Lotebush 138 kV line | NEW | Creosote |  | Planned | 1124 - 1302 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 1869 | 2022-11-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 6657, 60377, 6673, 38376, 60392 | Y | N |  | 0 | 59325 | 59324
6685 | Van Vleck substation loop | Replaces single circuit radial line connected to a pole mounted switch with a double circuit transmission loop to the Van Vleck substation and upgrades the 4/0 ACSR to 795 ACSR on 138 kV capable poles. |  | Van Vleck Substation | Van Vleck Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-12-01 |  | 69 | 2 | 2 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5556, 5554, 5558, 5560 | Y | N |  |  | 14456 | 6685
6934B | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0873 | 2022-12-01 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  |  | 5133 | Y |  |  |  | 14754 | 6934
6934A | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0873 | 2022-12-01 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  |  | 5133 | Y |  |  |  | 14753 | 6934
57169 | Rebuilds Faysville Switch to Redgate 138 kV | Rebuilds Faysville SW to Redgate from 69 kV to 138 kV and opens the current Redgate tap |  | Redgate | Faysville Switch | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-12-01 |  | 138 | 0 | 3.45 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5787, 88380, 161031 | Y | N |  | 0 | 57170 | 57169
60524 | Rebuild Angleton-Retrieve with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39560, 43170 | Y |  |  | 0 | 60525 | 60524
60526 | Rebuild West Columbia Local-Angleton with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39530, 39560 | Y |  |  | 0 | 60527 | 60526
60528 | Rebuild West Columbia Main-West Columbia Local with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2022-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39500, 39530 | Y |  |  | 0 | 60529 | 60528
57890 | Brightside Permanent Connection | Construct Charter Station |  | Beeville | Three Rivers | Planned | 1114 - 1292 | AEP | Glen Reed gareed@aep.com 918-599-2664 | 3833 | 2022-12-11 |  | 138 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8156 | Y |  |  | 0 | 57891 | 57890
5466 | Redland Switch 345/138 kV Autotransformer | Install new 345/138 kV Autotransformer at Redland Switch previously known as Herty North |  | Redland | Redland | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6076 | 2022-12-15 |  | 345 | 0 | 0 | 600 |  | Angelina | Angelina | Tier 3 | 20RPG019 | 2020-10-01 |  |  | 3319, 3321, 3322 | Y | N |  |  | 13170 | 5466
5492 | Venus - Webb/Cedar Hill Sw. Sta. 345 kV DCKT Line | Upgrade existing Venus - Webb/Cedar Hill Sw. Sta. 345 kV Double Ckt Line |  | Ellis | Tarrant | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4230 | 2022-12-15 |  | 345 | 0 | 27 | 0 |  | Ellis | Tarrant | Tier 3 | 21RPG004 |  |  |  | 1904, 1906, 2420, 11901 | Y | N |  |  | 13230 | 5492
7126 | Renner TPL 138 kV Capacitors | Upgrade existing capacitor banks |  | RENNER SWITCH | RENNER SWITCH | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3048 | 2022-12-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas | Dallas | Tier 4 |  |  |  |  | 2352, 2353 | Y | N |  |  | 14964 | 7126
7127 | East Levee 138 kV Emergency Capacitors | Upgrade East Levee 138 kV Emergency Capacitors |  | EAST LEVEE | EAST LEVEE | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4290 | 2022-12-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas | Dallas | Tier 4 |  |  |  |  | 2481, 2482 | Y | N |  |  | 14965 | 7127
57928 | Rebuild Midland East 138 kV Switch | Rebuild Midland East 138 kV Switch |  | Midland East | Midland East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8538 | 2022-12-15 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 |  |  | 1023 | Y |  |  | 0 | 57930 | 57928
57934 | Midland East - Spraberry 138 kV Line Rebuild | Add Midland East - Spraberry 138 kV Line Rebuild |  | Midland East | Spraberry | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8147 | 2022-12-15 |  | 138 | 0 | 13.5 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 |  |  | 11294, 11295, 11296, 1023, 1132, 1329, 11123, 11134, 11361 | Y |  |  | 0 | 60082 | 57934
59265 | Hurst - International Airport 138 kV Double-Circuit Line Section | Upgrade existing 138 kV Line |  | Hurst | International Airport | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5216 | 2022-12-15 |  | 138 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 2115, 2116, 2117, 2121, 2125, 2243, 2244 | Y |  |  | 0 | 59266 | 59265
59402 | Add Midland East Switch 345138 kV Autotransformer #2 | Add a new 345/138 kV autotransformer to existing switch |  | Midland East | Midland East | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8258 | 2022-12-15 |  | 345 | 0 | 0 | 600 |  | Midland | Midland | Tier 3 | 21RPG003 | 2021-02-16 |  |  | 1014, 11298, 1021, 1023 | Y |  |  | 0 | 59404 | 59402
59518 | upgrade the Desoto-Sterrett 138 kV Line | upgrade the existing Desoto-Sterrett 138 kV Line |  | Desoto | Sterrett | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4122 | 2022-12-15 |  | 138 | 0 | 8.3 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  |  | 217, 2317, 2424 | Y |  |  | 0 | 59519 | 59518
59745 | ONCOR_MN_Royse Switch - Oates (GP&L) 138 kV Line | Upgrade existing 138 kV Line |  | Royse | Oates | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4236 | 2022-12-15 |  | 138 | 0 | 0 | 0 |  | Rockwall | Dallas | Tier 4 |  |  |  |  | 831, 2472, 2733, 2735, 2736, 2739, 12703, 12735 | Y |  |  | 0 | 59746 | 59745
59835 | Royse Switch-Terrell Switch 69 kV Line Conversion to 138 Kv | Convert the existing 69 kV Line to 138 kV |  | Royse | Terrell | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M3223 | 2022-12-15 |  | 69 | 0 | 0 | 0 |  | Rockwall | Rockwall | Tier 4 |  |  |  |  | 2722, 2729, 12722, 12730, 2463, 2472, 2721, 3188 | Y |  |  | 0 | 59836 | 59835
60094 | Convert Waco East - Elm Mott 69 kV Line to 138 kV | Convert Waco East - Elm Mott 69 kV Line to 138 kV and relocate the Waco East Substation to the double circuit line going towards Lake Creek/Waco West |  | Waco East | Elm Mott | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6147 | 2022-12-15 |  | 138 | 0 | 10 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3439, 3481, 3482, 3571, 3573, 13438, 3438, 3407, 3408, 3434, 3452 | Y |  |  | 0 | 60095 | 60094
52318 | Royse Switch - Greenbriar Switch 138 kV Line | Upgrade the Royse Switch - Greenbriar Switch 138 kV Line |  | Royse | Greenbriar | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4292 | 2022-12-15 01:00 |  | 138 | 0 | 0 | 0 |  | Collin | Rockwall | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 2472, 2707, 12527 | Y |  |  | 0 | 52319 | 52318
50446 | Santa Clara Substation Addition | Add a new load serving substation 10 miles west of City of Seguin, of IH-10, w/ twin 40 MVA PWTs. |  | Santa Clara Substation | Santa Clara Substation | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-16 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7891 | Y | N |  | 0 | 50447 | 50446
54103 | Hilltop - Strahan Transmission Line Upgrade | Increase the reliability of transmission facilities on the T445: Hilltop ¿ Strahan 1.25-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | Hilltop | Strahan | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2022-12-16 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7190, 7193 | Y | N |  | 0 | 54104 | 54103
6719 | Twelvemile Substation Addition | Construct a new substation named Twelvemile off the Bakersfield to Schneeman Draw transmission line to support a generation interconnection request (16INR0104). |  | Bakersfield | Schneeman Draw | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018769 | 2022-12-22 |  | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  |  | 76008, 7053, 76015 | Y | N |  | 0 | 58408 | 6719
51736 | Cibolo to McQueeney Transmission Line | Install 10.62 miles of 1192 Bunting to existing transmission structures, circuit to help with load flows per the TPA and will be source for Santa Clara Substation. |  | Cibolo | McQueency | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-23 |  | 138 | 10.62 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7608, 7606 | Y | N |  | 0 | 51737 | 51736
51841 | H-Pole to Santa Clara Transmission Line Addtition | Build 5 onmiles of new double circuit 138kV t-line loop, 1192 ACSR Bunting, from H-pole structure to Santa Clara Substation |  | H-pole ( Structure/Tap) | Santa Clara | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2022-12-23 |  | 69 | 10 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7890, 7892, 7606, 7608, 7891 | Y | N |  | 0 | 57331 | 51841
5940A | Mountain Home Substation and Transmission Line Addition | Construct new Mountain Home substation and construct a 138-kV transmission line from Hunt substation to Mountain Home substation. | For total project cost please see 5940_C | Hunt | Mountain Home | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017394 | 2022-12-27 |  | 138 | 7.5 | 0 | 0 |  | Kerr | Kerr | Tier 1 | 16RPG015 | 2016-11-18 |  |  | 7750, 7144 | Y | N |  | 0 | 46980 | 5940
5940B | Mountain Home Substation and Transmission Line Addition | Construct a 138-kV transmission line from Harper substation to Mountain Home substation. | For total project cost please see 5940_C | Mountain Home | Harper | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017394 | 2022-12-27 |  | 138 | 11.5 | 0 | 0 |  | Kerr | Gillespie | Tier 1 | 16RPG015 | 2016-11-18 |  |  | 74100, 7410, 7750 | Y | N |  | 0 | 46981 | 5940
5940C | Mountain Home Substation and Transmission Line Addition | Add one(1) 138/69-kV autotransformer at Harper substation |  | Harper | Live Oak | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017394 | 2022-12-27 00:10 |  | 138 | 0 | 21.7 | 45 |  | Gillespie | Gillespie | Tier 1 | 16RPG015 | 2016-11-18 |  |  | 7412, 7130, 7132, 7149, 7410, 7413, 74100 | Y | N |  | 0 | 46982 | 5940
43460 | Moody to Stewart Ckt.63 Upgrades | Upgrade Ckt.63 Moody to Stewart |  | Moody | Stewart | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-30 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42950, 43290 | Y |  |  | 0 | 43461 | 43460
52183 | EXTER 69kV Substation Removal | Remove EXTER 69kV Substation from Ckt.53B |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-30 |  | 138 | 0 | 0 | 0 |  | Galveston | Harris | Tier 4 |  |  |  |  | 42600, 42080, 43510, 44440 | Y | N |  | Cost included in MOD 52181 - ENCO new customer sub | 52184 | 52183
58917 | Horizon 138 bus and line to Pearsall | Adds new Horizon Switch station to connect Horizon solar generation and a line to Pearsall |  | Horizon Swttch | Pearsall | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2022-12-30 |  | 138 | 0.4 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5897, 5895 | Y | N |  | 0 | 58918 | 58917
6875 | Support 69kV to 138kV West Loop Conversion Projects | Upgraded line Apollo to Jupiter to support 69kV to 138kV West Loop Conversion Projects |  | Apollo | Jupiter | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-12-31 |  | 138 | 0 | 3.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 803, 806, 802, 815, 829 | Y | N |  |  | 14684 | 6875
6876 | Support 69kV to 138kV West Loop Conversion Projects | Upgraded line Jupiter to College to support 69kV to 138kV West Loop Conversion Projects |  | Jupiter | College | Planned |  | GARLAND | Danh Huynh dhuynh@garlandpower-light.org 972-205-3826 |  | 2022-12-31 |  | 138 | 0 | 2.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 806, 829 | Y |  |  |  | 14685 | 6876
56003A | Mont Belvieu Reliability Project | Expand Jordan and Mont Belvieu with new line positions |  | Jordan | Winfre | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40500, 40764, 40857, 40740, 40855 | Y | N |  | 0 | 56075 | 56003
57521A | Stone Lake New Sub Ckt66 | Install Stone Lake Distribution Substation AP2022 to create new Ckt..66 Hockley to Stone Lake to Tomball. |  | Stone Lake | Hockley/Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45880, 46511 | Y | N |  | 0 | 57530 | 57521
59317 | Deer Park Tap to Cardiff Ckt.96E Upgrades | Upgrade Deer Park Tap to Cardiff Ckt.96E to Minimum 300 MVA Emergency rating |  | Deer Park | Cardiff | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 5.8 | 0 |  |  |  | Tier 4 |  |  |  |  | 40442, 42240 | Y | N |  | 0 | 59318 | 59317
56003B | Mont Belvieu Reliability Project | Remove existing Jordan TR1 tap from Ckt.86I Jordan to Cities. Reconnect at new Ckt.52A Jordan to Winfre |  | Jordan | Cities | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40340, 40855, 40740, 40857 | Y | N |  | Cost included in main entry | 56076 | 56003
59804A | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86 Crosby to Newport to Jonte |  | Jonte | Crosby/Newport | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 45660, 41150, 46032 | Y | N |  | 0 | 59805 | 59804
56003C | Mont Belvieu Reliability Project | Reconfigure existing 86B/86H/86K to create new Ckt.52B Winfre to Eagle with minimum 360/440 MVA |  | Winfre | Eagle | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40220, 40300, 40500, 40764 | Y | N |  | Cost included in main entry | 56077 | 56003
59804B | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86 Jonte to Greens Road tap |  | Jonte | Greens Road | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 45821, 45660, 46331 | Y | N |  | Cost included in main project | 59806 | 59804
56003D | Mont Belvieu Reliability Project | Expand Jordan and Mont Belvieu with new line positions |  | Eagle | Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40500, 41111 | Y | N |  | Cost included in main entry | 56078 | 56003
59804C | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86 Jonte to Lockwood tap to Scenic Woods radial |  | Lockwood | Jonte/Scenic Woods | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 46331, 46032, 45660 | Y | N |  | Cost included in main project | 59807 | 59804
56003E | Mont Belvieu Reliability Project | Expand Jordan and Mont Belvieu with new line positions |  | Dalton | BRINE/Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40220, 40775, 40740, 41111, 41113 | Y | N |  | Cost included in main entry | 56079 | 56003
59804D | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90 North Belt to Greens Road tap to Jonte |  | Greens Road | North Belt/Jonte | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 45822, 45660, 46031 | Y | N |  | Cost included in main project | 59808 | 59804
56003F | Mont Belvieu Reliability Project | Reconfigure existing 86B/86H/86K to create new Ckt.86B Chevron to Langston with minimum 440/525 MVA |  | Chevron | Langston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40300, 40775 | Y | N |  | Cost included in main entry | 56080 | 56003
59804E | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90 Jonte to Lockwood tap to Lauder tap to Scenic Woods radial |  | Jonte | Lockwood/Lauder/Scenic Woods | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 46031, 45660 | Y | N |  | Cost included in main project | 59809 | 59804
56003G | Mont Belvieu Reliability Project | Upgrade Ckt.84D Cedar Bayou Plant to Cedar Bayou Tap to HOPSON with minimum 682MVA Emergency Rating |  | Cedar Bayou Plant | Cedar Bayou/HOPSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40012, 40015, 41690 | Y | N |  | Cost included in main entry | 56081 | 56003
56003H | Mont Belvieu Reliability Project | Upgrade Ckt.86A Cedar Bayou Plant to Chevron with minimum 669MVA Emergency Rating |  | Cedar Bayou Plant | Chevron | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2022-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Harris | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40015, 40300 | Y | N |  | Cost included in main entry | 56082 | 56003
50872 | Structure 25/7 - Medio Creek: Line Rebuild | Lon Hill - STEC Warburton: Line Rebuild |  | Haisley | Medio Creek | Planned | 1055 - 1228 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3784 | 2023-01-31 |  | 138 | 0 | 14.9 | 0 |  | San Patricio | Refugio | Tier 3 |  |  |  |  | 8912, 8920 | Y | N |  | 0 | 50873 | 50872
45397 | Lion: 138 kV Station & Transmission Line | Lion: 138 kV Station with new line to Stewart Road |  | Lion | Stewart Road | Planned | 885 - 1063 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3672 | 2023-02-23 |  | 138 | 2.71 | 0 | 40 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8969, 8758, 8951 | Y | N |  | 0 | 50139 | 45397
50870 | Coleto Creek - Rosata: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Coleto Creek | Rosata | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3778 | 2023-03-16 01:00 |  | 138 | 0 | 15.3 | 0 |  | Goliad | Goliad | Tier 3 | 20RPG014 |  |  |  | 8162, 8153 | Y | N |  | 0 | 50871 | 50870
6373 | Hamilton Road to Picacho ckt #2, rebuild 138 kV line | Rebuild Hamilton Road to Picacho 138 kV line ckt #2 |  | Hamilton Road | Picacho | Planned | 870-1051 | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | 3660 | 2023-03-30 |  | 138 | 0 | 8.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8186, 8255, 8690, 8688, 8684 | Y | N |  |  | 14117 | 6373
51005 | Rocksprings to Friess Ranch: Rebuild 69 kV line | Rebuild Rocksprings to Sonora 69 kV line |  | Rocksprings | Friess Ranch | Planned | 1044 - 1217 | AEP | Nathan Cowan mlforcum@aep.com 918-599-2674 | 2792 | 2023-03-31 |  | 69 | 0 | 22.6 | 0 |  | Edwards | Sutton | Tier 3 |  |  |  |  | 8238, 8239 | Y | N |  | 0 | 51006 | 51005
45015 | Barnhart to Cassava: Rebuild 69 kV line | Rebuild the Barnhart to Cassava 69 kV line | Update Schedule | Barnhart | Cassava | Planned | 942 - 1120 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2756 | 2023-03-31 01:00 |  | 69 | 0 | 6.021 | 0 |  | Irion | Irion | Tier 4 |  |  |  |  | 6532, 6530, 6537, 60359 | Y | N |  | 0 | 45016 | 45015
51001 | Friess Ranch to Sonora: Rebuild 69 kV line | Rebuild Rocksprings to Sonora 69 kV line |  | Friess Ranch | Sonora | Planned | 1044 - 1217 | AEP | Nathan Cowan mlforcum@aep.com 918-599-2674 | 2791 | 2023-03-31 12:00 |  | 69 | 0 | 24.3 | 0 |  | Sutton | Sutton | Tier 3 |  |  |  |  | 8238, 8239, 60438, 6513, 6570 | Y | N |  | 0 | 51002 | 51001
55622 | Dilley to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley |  | Dilley | Pearsal | Planned | 1104 - 1282 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3822 | 2023-05-01 |  | 69 | 0 | 17.7 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8216, 8208 | Y |  |  | 0 | 55623 | 55622
54080 | Lockhart - Lulig Transmission Line Overhaul | LCRA TSC will perform an overhaul of T184 (from Lockhart structure #301 to Luling) with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T184 will be 795 ACSR Drake. Note: Condor conductor replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-02 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7216, 7224 | Y | N |  | 0 | 54081 | 54080
54082 | Lockhart - Red Rock Transmission Line Overhaul | LCRA TSC will perform an overhaul of T578 (from Lockhart structure #301 to Red Rock) with replacement structures that are capable of operating at 138-kV and supporting a single 959 ACSR Suwannee conductor. The replacement conductor on T578 will be 959 ACSR Suwannee. This overhaul will include the installation of a 72-count optical ground wire (OPGW). Note: Condor conductor, new OPGW and any structure replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Red Rock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-09 |  | 138 | 0 | 0 | 0 |  | Caldwell | Bastrop | Tier 4 |  |  |  |  | 7216, 7560 | Y | N |  | 0 | 54083 | 54082
53958 | Fairland - Lago Vista Transmission Line Upgrade | Increase the reliability of transmission facilities on the T414 Fairland - Lago Vista 21-mile 138-kV transmission line by replacing the existing Condor conductor with Drake conductor. |  | Fairland | Lago Vista | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-12 |  | 138 | 0 | 0 | 0 |  | Burnet | Travis | Tier 4 |  |  |  |  | 7352, 7518 | Y | N |  | 0 | 53959 | 53958
12TPIT0080 | Forney Sw. Sta. Second 600 MVA, 345/138 kV Autotransformer | Add second 345/138 autotransformer | Project Deferral | Forney Sw. Sta. |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4037 | 2023-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 3 |  | 2008-06-01 | 2008-07-01 |  | 2437, 2438 | Y | N | 2007-R2 |  | 9769 | 2489
4804 | Wichita Falls South 345/138 kV autotransformer | Install autotransformer |  | Wichita Falls South |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4010 | 2023-05-15 |  | 345 | 0 | 0 | 600 |  | Archer |  | Tier 3 |  |  |  |  | 11464, 11465, 1422, 1425, 1464 | Y | N |  |  | 12410 | 4804
5436 | Morgan Creek - McDonald 138 kV Line | Upgrade existing line | Project Deferral | Morgan Creek | McDonald Rd | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8360 | 2023-05-15 |  | 138 | 0 | 31.8 | 0 |  | Howard | Mitchell | Tier 3 |  |  |  |  | 1032, 1333 | Y | N |  |  | 13139 | 5436
5475 | Lufkin Switch - Redland Switch 345 kV Line | Construct a new 345 kV Line from Lufkin Switch to Redland Switch |  | Lufkin Switch | Redland Switch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6077 | 2023-05-15 |  | 345 | 8.1 | 0 | 0 |  | Angelina | Angelina | Tier 2 | 20RPG019 | 2020-10-01 |  |  | 3117, 3321 | Y | N |  |  | 13180 | 5475
5525 | Forney - Lake Hubbard 345 kV Line | Construct new 345 kV line |  | Forney | Lake Hubbard | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4233 | 2023-05-15 |  | 345 | 0 | 7.5 | 0 |  | Kaufman | Dallas | Tier 2 |  |  |  |  | 2455, 2467 | Y | N |  |  | 13252 | 5525
5526 | Forney 345 kV Switching Station | Reconstruct existing 345 kV switching station |  | Forney |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4114 | 2023-05-15 |  | 345 | 0 | 0 | 0 |  | Kaufman |  | Tier 3 |  |  |  |  | 2467, 2433, 2437, 2470, 2478, 150189, 2438, 12438 | Y | N |  | 0 | 49916 | 5526
5624 | Killeen Sw. Sta. 345/138 kV Autotransformer Replacement | Replace existing autotransformer |  | Killeen Sw. Sta. | Killeen Sw. Sta | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R797 | 2023-05-15 |  | 345 | 0 | 0 | 600 | -75,0 | Bell | Bell | Tier 3 |  |  |  |  | 3422, 3423, 13423 | Y | N |  |  | 13354 | 5624
5981 | Shamburger North 345/138 kV Sw. Sta. | Establish Shamburger North 345/138 kV Sw. Sta. |  | Shamburger North | Shamburger North | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6083 | 2023-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 3217, 3223, 3226, 2478, 3103, 3201, 3206 | Y | N |  |  | 13696 | 5981
7023 | Hicks Sw. Sta. - Roanoke Sw. Sta. 345 kV Double-circuit Line | Upgrade existing Hicks Sw. Sta. - Roanoke Sw. Sta. 345 kV Double-circuit Line |  | Hicks Sw. Sta. | Roanoke Sw. Sta. | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5256 | 2023-05-15 |  | 345 | 0 | 19.4 | 0 |  | Tarrant | Denton | Tier 3 |  |  |  |  | 1855, 2081, 1845, 1851 | Y | N |  | 0 | 52815 | 7023
7125 | Greenville Ave 138 kV Capacitors | Upgrade existing capacitor banks |  | Greenville Ave | Greenville Ave | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4177 | 2023-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas | Dallas | Tier 4 |  |  |  |  | 2882, 2883 | Y | N |  |  | 14963 | 7125
51243 | Keller Wall Price 138 kV Switch | Upgrade Roanoke - Keller Wall Price Switch 138 kV Double-Circuit Line |  | Keller Wall Price |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5251 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Denton | Tarrant | Tier 4 |  |  |  |  | 2037, 12038, 12307, 566, 679, 1852, 1854, 1856, 1857, 2027, 2033, 2034, 2036, 2038, 2058, 11857, 15100, 15101 | Y |  |  | 0 | 52845 | 51243
51740 | Buttercup Bus Upgrade | Upgrade the Buttercup bus from operate/transfer to double-bus double-breaker |  | Buttercup |  | Planned |  | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 |  | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7531 | Y | N |  | 0 | 51750 | 51740
54204 | Gonzales - Hochheim Transmission Line Overhaul | Increase the reliability and capacity of transmission facilities on the T542 Luling ¿ Cuero 19.6-mile 69-kV transmission line from Gonzales (structure #33) to Hochheim Tap. LCRA TSC will perform an overhaul of T542 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T542 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 |  | 69 | 0 | 0 | 0 |  | Gonzales | DeWitt | Tier 4 |  |  |  |  | 7223, 78577 | Y | N |  | 0 | 54205 | 54204
56350B | Burnett-Ringgold Magnolia Tap 69 kV Line |  |  | Bowie | Ringgold Magnolia Tap | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4015 | 2023-05-15 |  | 69 | 0 | 21 | 0 |  | Montague | Clay | Tier 3 |  |  |  |  | 1540, 1545, 1547, 1548, 1550, 33770 | Y | N |  | 0 | 56862 | 56350
57726 | Commerce - Royse 69 kV Line Conversion to 138 kV | Convert existing 69 kV Line to 138 kV |  | Commerce Switch | Royse | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R985 | 2023-05-15 01:00 |  | 138 | 0 | 38.3 | 0 |  | Hunt | Rockwall | Tier 3 | 20RPG023 | 2020-12-23 | 2021-01-19 |  | 1818, 1821, 1824, 1826, 1827, 1828, 1829, 1830, 1831, 2463, 6944, 1816, 2472, 1820 | Y | N |  | 0 | 60030 | 57726
6777 | Cedar Hill - Liggett 138 kV Line | Loop Cedar Hill - Liggett 138 kV line in to Home Run Substation | Project Deferral | Grand Prairie West | Mayfield Tap | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4270 | 2023-05-15 02:01 |  | 138 | 7 | 0 | 0 |  | Dallas | Tarrant | Tier 4 |  |  |  |  | 2143, 1912, 1919, 2138, 2265 | Y | N |  | 0 | 51988 | 6777
7124 | Flat Iron - Barr Ranch 138 kV line | Flat Iron - Barr Ranch 138 kV line |  | Flat Iron | Barr Ranch | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8373 | 2023-05-16 |  | 138 | 6 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11235, 11217 | Y |  |  |  | 14962 | 7124
5522 | Lake Hubbard 345/138 kV Switching Station | Construct new 345/138 kV switching station |  | Lake Hubbard |  | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4139 | 2023-05-17 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 |  |  |  |  | 12455, 12456, 2401, 2402, 2455 | Y | N |  |  | 13249 | 5522
18TPIT0001 | Wiederstein Substation Transformer Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Wiederstein |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-05-26 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7461 | Y | N |  |  | 10675 | 3319
52464 | Alamito Creek to Ft. Davis: Rebuild 69 kV line | Rehab Alamito Creek to Ft. Davis 69 kV line |  | Alamito Creek | Ft Davis | Planned | 1070 - 1243 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2831 | 2023-05-31 |  | 69 | 0 | 20.5 | 0 |  | Presidio |  | Tier 4 |  |  |  |  | 6676, 6677, 6691, 6678, 6692 | Y | N |  | 0 | 52465 | 52464
57521D | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 57533 | 57521
57521B | Stone Lake New Sub Ckt66 | Upgrade Ckt.66 Hockley to Stone Lake BP2023 as a transmission project. |  | Stone Lake | Hockley/Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 15.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45880 | Y | N |  | Cost included in main entry | 57531 | 57521
57521C | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 57532 | 57521
57906 | Laredo to University: Rebuild 138 kV Line | Rebuild the 5.19 mile Laredo to University 138 kV transmission line and upgrade any limiting elements. |  | Laredo | University | Planned | 1119 - 1297 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3838 | 2023-05-31 |  | 138 | 0 | 5.19 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645, 8647 | Y | N |  | 0 | 57907 | 57906
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2023-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 5601, 5600, 5602 | Y | N |  |  | 8729 | 1538
6253 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2023-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9276, 9077, 9238 | Y |  |  |  | 13981 | 6253
44963 | USAA Rebuild 138 kV Station | CPSE_USAA 138 kV Substation Rebuild and Line Reconfiguration. |  |  |  | Planned | S-0896 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0285 | 2023-06-01 |  | 138 | 0.6 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-10 |  |  | 5450, 5451, 5452, 5125, 5170, 5208, 5300, 5453 | Y |  |  | 0 | 44964 | 44963
45101 | Chavaneaux_Chavaneaux Tap (Chavaneaux to Palo Alto)- 138 kV | CPSE_Chavaneaux_Chavaneaux 138 kV Tap Rebuild (Chavaneaux to Palo Alto). |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0256 | 2023-06-01 |  | 138 | 0 | 0.9 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5085, 5330 | Y |  |  | 0 | 45102 | 45101
50645 | CPSE_Rafter 138kV Cap Bank | [6 empty] | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2023-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5355 | Y |  |  | 0 | 50646 | 50645
51216F | Ward Winkler RPG | Convert & re-conductor existing TNMP Wickett - Oncor Yucca 69kV line to 138kV, construct line extension (~1.3 miles) and re-terminate line to Oncor Wolf 138kV station. |  | TNMP Wickett (37980 / 37981) | Oncor Wolf (1013) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-06-01 |  | 138 | 1.3 | 4.7 | 0 |  | Ward | Ward | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 1013, 1015, 37940, 37960, 37980, 37981 | Y |  |  | 0 | 56661 | 51216
20TPIT0000 | Parkway Substation T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-06-30 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10679 | 3323
5430I | Conversion to 138kV | Retire the existing 69kV North Lakes substation together with the transformer relocated from Denton North |  | North Lakes |  | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 915, 928 | Y | N | N/A | 0 | 55203 | 5430
5430G | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 905, 915 | Y | N | N/A | 0 | 55201 | 5430
5430J | Conversion to 138kV | Line already insulated for 138kV. Line will be terminated at the new 138kV Hickory substation |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 905, 910 | Y | N | N/A | 0 | 55204 | 5430
5430K | Conversion to 138kV | Construct new 138kV Hickory substation and terminate the existing Bonnie Brae - Hickory (which is already insulated for 138kV) at the new 138kV Hickory substation. |  | Bonnie Brae | Hickory | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 931 | Y | N | N/A | 0 | 55205 | 5430
5430H | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 0 | 1.521 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 928, 931 | Y | N | N/A | 0 | 55202 | 5430
5461 | Load serving |  |  | Puckrus | Mayhill | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 1.9 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 929, 917 | N | N |  |  | 13164 | 5461
5559 | Add new 138kV Bonnie Brae Substation and retire the 69kV sta |  |  | Bonnie Brae |  | Planned | N/A | DENTON | Charles Sears cxsears@cityofdenton.com 940-349-7111 |  | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  |  | 905, 931 | Y | N | N/A |  | 13291 | 5559
44416 | Add a 2nd circuit at Brinker - Denton Steam |  |  | Brinker | Denton Steam | Planned |  | DENTON | Chuck Sears |  | 2023-07-01 |  | 138 | 0.631 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 982 | Y | N |  | 0 | 44417 | 44416
45511 | Laredo - Del Mar: 138 kV Line Rebuild | Rebuild Laredo - Del Mar 138 kV Line with 795 ACSS |  | Laredo | Del Mar | Conceptual | 992 - 1170 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3746 | 2023-07-01 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645 | Y | N |  | 0 | 45512 | 45511
45513 | Santo Nino - Wormser: 138 kV Line Rebuild | Rebuild Santo Nino - Wormser 138 kV line with 795 ACSS |  | Santo Nino | Wormser | Conceptual | 991 - 1169 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3745 | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8295, 8649, 8653 | Y | N |  | 0 | 45514 | 45513
45566 | Holly - Southside: 138 kV Line Rating Increase | Increase MOT for Holly - Southside 138 kV Line |  | Holly | Southside | Planned | 994 - 1172 | AEP | Michael Glueck bcogan@aep.com 918-599-2857 | 3747 | 2023-07-01 |  | 138 | 0 | 1.8 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486, 8496 | Y | N |  | 0 | 45567 | 45566
5206 | Brackettville to Escondido: Construct 138 kV line | Build a single circuit capable 138 kV circuit from Brakettville to Escondido station |  | Brackettville | Escondido | Planned | 762-0947 | AEP | James Weaver bcogan@aep.com 918-599-2857 | 3570 | 2023-07-30 |  | 138 | 45 | 0 | 0 |  | Kinney | Maverick | Tier 2 |  | 2016-01-05 | 2017-01-20 | 2017-02-08 | 8252, 8260 | Y | N |  |  | 12865 | 5206
53999 | ElCampo - Ricebird Transmission Line Strom Hardening | Increase the reliability of transmission facilities on the T589 El Campo ¿ Ricebird 4.6-mile 138-kV transmission line. |  | El Campo | Ricebird | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2023-08-21 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8102, 78104 | Y | N |  | 0 | 54000 | 53999
52147 | Rising Star Area Conversions | Converts voltage to 138 KV from Holder to Nimrod to Rising Star. |  | Holder | Rising Star | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2023-09-01 |  | 138 | 0 | 0 | 0 |  | Brown | Comanche | Tier 4 |  |  |  |  | 285, 289, 293, 292, 281 | Y |  |  | 0 | 52148 | 52147
47422 | Homestead Substation Addition | Construct a new 138-kV Homestead substation.The Homestead substation will be located approximately ½ mile from the existing Tarbush substation (owned by TNMP) and will include three-PWTs with RGEC distribution (express feeders) to the load. |  | Homestead | Homestead | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-09-22 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 7868, 38295 | Y |  |  | 0 | 47423 | 47422
52169 | Rising Star Area Conversions | This converts the voltage to 138 following Rising Star Substation Voltage Conversion |  | Rising Star | Downing | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2023-10-01 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 281, 277, 285, 294 | Y |  |  | 0 | 52170 | 52169
5889 | MIRAGE - 138kV Substation Removal | Remove 138kV MIRAGE customer-owned substation from CNP service. |  | MIRAGE | MCCABE/BIMONT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42360, 40209, 42351, 40200 | Y | N |  |  | 13606 | 5889
57350 | Lyons to Gay Hill T-line pole change out and reconductor | Replace existing structure with upgraded structures and replace existing 336.4 ACSR Linnet with 795 ACSR Drake on Lyons to Gay Hill transmission line. |  | Lyons | Gay Hill | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet.coop curtis.fischer@bluebonnet (979) 716-0253 |  | 2023-10-31 |  | 138 | 0 | 11.51 | 0 |  | Burleson | Washington | Tier 4 |  |  |  |  | 7572, 7573 | Y |  |  | 0 | 57351 | 57350
55605 | New Barksdale to Rocksprings: Rebuild 69 kV line | Rebuild 69 kV line from Campwood to Rocksprings |  | New Barksdale | Rocksprings | Planned | 1102 - 1280 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3819 | 2023-11-01 |  | 69 | 0 | 19.51 | 0 |  | Edwards | Edwards | Tier 3 |  |  |  |  | 8365, 8238 | Y |  |  | 0 | 55606 | 55605
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-11-17 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7622 | Y | N |  |  | 10677 | 3321
50882 | Lon Hill - Structure 25/4: Line Rebuild | Lon Hill - STEC Warburton: Line Rebuild |  | Lon Hill | Haisley | Planned | 1055 - 1228 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3785 | 2023-11-30 |  | 138 | 0 | 10.2 | 0 |  | San Patricio | San Patricio | Tier 3 |  |  |  |  | 8027, 8452, 8920 | Y | N |  | 0 | 50883 | 50882
55299 | Munday to Throckmorton: Rebuild 69 kV line | Rehab 69 kV line from Munday to Throckmorton |  | Munday | Throckmorton | Planned | 1094 - 1272 | AEP TNC | Charity Kreher mlforcum@aep.com 918-599-2857 | 1862 | 2023-11-30 |  | 69 | 0 | 34.55 | 0 |  | Knox | Throckmorton | Tier 3 |  |  |  |  | 6107, 6204, 6205 | Y | N |  | 0 | 55300 | 55299
55470 | Bison to Ozona: Rebuild 69 kV line | Rehab 69 kV line from Bison to Ozona | Update Contact, Schedule, Cost | Bison | Ozona | Planned | 1095 - 1273 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1863 | 2023-11-30 |  | 69 | 0 | 27 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  |  | 6549, 6560, 60395 | Y | N |  | 0 | 55471 | 55470
48816 | Mulberry Creek: Rebuild 345 kV station | Rebuild Mulberry Creek 345 kV station | Update Schedule, Cost, Auto Capacity | Mulberry Creek |  | Planned | 1015 - 1193 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 2776 | 2023-11-30 01:00 |  | 345 | 0 | 0 | 900 |  | Jones |  | Tier 3 |  |  |  |  | 6230, 6232, 6287, 6288, 60788, 60789, 1435, 6228, 6231, 6235, 60040, 60772 | Y | N |  | 0 | 48817 | 48816
54120 | Rebuild Tejas-Commanche (Bundled 795 ACSS) | Rebuild Tejas - Commanche 138 kV line with Bundled 795 ACSS conductor. |  | Tejas 138 kV Substation (Bus # 38530) | Commanche 138 kV Substation (Bus # 38560) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | STE07318 | 2023-12-01 |  | 138 | 0 | 0.95 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38530, 38560 | Y |  |  | 0 | 54121 | 54120
60502 | Rebuild Apache-Amoco with bundled 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38620, 38720 | Y |  |  | 0 | 60503 | 60502
60504 | Rebuild Caddo-Apache with bundled 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2023-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38710, 38720 | Y |  |  | 0 | 60505 | 60504
44946 | CPSE_New_Scenic_Loop_138kV_Load_Serving_Station | The new Scenic Loop 138 kV load serving station will be looped into existing Ranchtown to LCRA (Menger Creek) 138 kV transmission line. The substation should be located south west of the existing Fair Oaks Ranch and north east of the existing Ranchtown substation. |  |  |  | Planned | S-0885 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0275 | 2023-12-01 20:00 |  | 138 | 9 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5363, 5358, 7665 | Y |  |  | 0 | 44947 | 44946
6755 | Stratton: Add Cap Bank | Add 14.4Mvar Cap Bank at Stratton 138kV Substation |  | Stratton |  | Planned | 903 - 1081 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3687 | 2023-12-31 |  | 138 | 0 | 0 | 0 | 0,14.4 | Nueces |  | Tier 4 |  |  |  |  | 8514 | Y | N |  |  | 14548 | 6755
52260 | India to DWU Rebuild | India to DWU Rebuild |  | India | Dallas Water Utilities | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-01-01 |  | 69 | 0 | 0 | 0 |  | Ellis | Dallas | Tier 4 |  |  |  |  | 230, 2351 | Y |  |  | 0 | 52261 | 52260
50868 | Rosata - Structure 31/8: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3780 | 2024-01-12 |  | 138 | 0 | 15.5 | 0 |  | Goliad | Karnes | Tier 3 | 20RPG014 |  |  |  | 8186, 8153 | Y | N |  | 0 | 50869 | 50868
6666 | BRYN_6666_Steele_Store_to_Cooks_Point | Construct 138kV line from BTU Steele Store to LCRA Cooks Point (Bundled 1033 ACSR - Curlew) |  | 32852 | 7569 | Planned |  | BRYN | James Tanneberger jtanneberger@btutilities.com 979-821-5763 |  | 2024-01-30 |  | 138 | 6 | 0 | 0 |  | Brazos | Burleson | Tier 4 |  | 2016-07-07 | 2017-07-07 |  | 32852, 7569 | Y |  |  |  | 14422 | 6666
52670 | BEPC_20TPITXXXX_DowningStephenville |  |  | Stephenville | Carlton Switch | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-02-05 |  | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 286, 299, 295, 297, 294 | Y |  |  | 0 | 52671 | 52670
50900 | Mason to North Brady: Rebuild 69 kV line | Rehab Mason to North Brady 69 kV line | Update Schedule | Mason | North Brady | Planned | 1046 - 1219 | AEP TNC | David Baker mlforcum@aep.com 918-599-2674 | 2794 | 2024-03-31 |  | 69 | 0 | 30.24 | 0 |  | Mason | McCulloch | Tier 3 |  | 2019-10-01 | 2019-11-01 |  | 6006, 6381, 6393, 6406, 60386 | Y | N |  | 0 | 50901 | 50900
45501 | Eldorado Live Oak to Sonora: Rebuild 69 kV line | Rehab Eldorado Live Oak to Sonora 69 kV line | Update Schedule | Eldorado Live Oak | Sonora | Planned | 982 - 1160 | AEP TNC | Dave Baker mlforcum@aep.com 918-599-2674 | 2769 | 2024-03-31 01:00 |  | 69 | 0 | 23.92 | 0 |  | Schleicher | Sutton | Tier 3 |  | 2018-12-18 | 2019-01-17 |  | 6498, 6505, 6509, 6510, 6513 | Y | N |  | 0 | 45502 | 45501
50948 | Angstrom - Grissom: Build New Line | Angstrom - Grissom: Build New Line |  | Angstrom | Grissom | Planned | 1063 - 1236 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3797 | 2024-04-01 |  | 345 | 17 | 0 | 0 |  | San Patricio | Bee | Tier 1 |  |  |  |  | 8249, 8624 | Y | N |  | 0 | 50949 | 50948
50966 | North Shore: 345 kV (Chienere LNG) RPG | Corpus North Shore RPG |  | Angstrom | Resnik | Planned | 1063 - 1236 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3798 | 2024-04-01 |  | 345 | 50 | 0 | 1350 |  | San Patricio | San Patricio | Tier 1 |  |  |  |  | 8659, 8660, 8249, 8580 | Y | N |  | 0 | 50970 | 50966
52175 | Rising Star Area Conversions | This continues the Rising Star Area Conversions with Carlton Switch to Downing | Carlton to Downing 138 kV Conversion | Carlton | Downing | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-04-01 |  | 138 | 0 | 0 | 0 |  | Erath | Comanche | Tier 4 |  |  |  |  | 294, 281, 286, 297 | Y |  |  | 0 | 52176 | 52175
53968 | Fayetteville - Salem Transmission Line Upgrade | Increase the reliability of transmission facilities on the T177 Fayetteville - Salem 138-kV and T211 FPP Yard #1 - Salem 345-kV 19.3-mile double-circuit transmission line by replacing the existing Condor conductor from Fayetteville Substation to Salem Substation. |  | Fayetteville | Salem | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-04-05 |  | 345 | 0 | 0 | 0 |  | Fayette | Washington | Tier 4 |  |  |  |  | 7056, 7286, 7058, 7289 | Y | N |  | 0 | 53969 | 53968
54892 | Eden to North Brady: Rebuild 69 kV line | Rehab Eden to North Brady 69 kV line | Update Contact, Cost | Eden | North Brady | Planned | 1039 - 1266 | AEP TNC | Larry Brown mlforcum@aep.com 918-599-2674 | 1856 | 2024-04-30 |  | 69 | 0 | 32.7 | 0 |  | Concho | McCulloch | Tier 3 |  |  |  |  | 6384, 60797, 6006, 6372, 6380, 6385 | Y | N |  | 0 | 54893 | 54892
59197 | Mason - Mason Switch: Rebuild 69 kV Line | Rebuild Mason to Mason Switch 69 kV Line | NEW | Mason | Mason Swicth | Planned | 1126 - 1304 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 1871 | 2024-04-30 |  | 69 | 0 | 10.3 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6394, 60458, 6393, 6396, 6407 | Y | N |  | 0 | 59198 | 59197
5496 | Forney - Royse 345 kV Line | Upgrade existing Royse - Forney 345 kV Line |  | Royse | Forney | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4235 | 2024-05-10 |  | 345 | 0 | 30 | 0 |  | Rockwall | Kaufman | Tier 3 |  |  |  |  | 2437, 2461, 2467, 2474, 2478 | Y | N |  | 0 | 59744 | 5496
50866 | Structure 31/8 - Kenedy SS: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3779 | 2024-05-13 01:00 |  | 138 | 0 | 14.3 | 0 |  | Karnes | Karnes | Tier 3 | 20RPG014 |  |  |  | 8186, 8153 | Y | N |  | 0 | 50867 | 50866
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing autotransformer |  | Elkton | Elkton | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6032-E | 2024-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 10501 | 3155
5479 | Trinidad_TriC_Watermill_345kV_DCKT | Upgrade existing DCKT line |  | Trinidad Sw. Sta | TriCorner/Watermill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4045 | 2024-05-15 |  | 345 | 0 | 92.1 | 0 |  | Henderson | Dallas | Tier 3 |  |  |  |  | 2432, 3123, 3124 | Y | N |  |  | 13184 | 5479
5982 | Relocate existing Shamburger North - Shamburger 138 kV Line | Establish 138 kV Line |  | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6084 | 2024-05-15 |  | 138 | 10 | 0 | 0 |  | Smith | Smith | Tier 4 |  |  |  |  | 3104, 3206, 3226 | Y | N |  |  | 13697 | 5982
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-05-24 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10680 | 3324
6304 | Shamburger North - Shamburger 345 kV Line | Upgrade existing 345 kV Line |  | Shamburger North | Shamburger | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6085 | 2024-05-28 |  | 345 | 10 | 10 | 0 |  | Smith | Smith | Tier 3 |  |  |  |  | 3103, 3223 | Y | N |  |  | 14033 | 6304
50874 | Smith - Mathis: Line Rebuild | Smith - Mathis: Line Rebuild | Update Schedule, Dollars | Smith | Mathis | Planned | 1053 - 1226 | AEP | Joseph Page bcogan@aep.com 918-599-2857 | 3781 | 2024-05-30 |  | 69 | 0 | 22.47 | 0 |  | San Patricio | San Patricio | Tier 3 |  |  |  |  | 8407, 8408, 8424, 8866 | Y | N |  | 0 | 50875 | 50874
55626 | Ganso to Hamilton Road: Rebuild 138 kV line | Rebuild 138 kV line from Ganso to Hamilton Road |  | Maverick | Hamilton Road | Planned | 1105 - 1283 | AEP | Bill Roberts bcogan@aep.com 918-599-2857 | 3824 | 2024-05-30 |  | 138 | 0 | 41.1 | 0 |  | Maverick | Val Verde | Tier 3 |  |  |  |  | 8267, 8692, 8255 | Y |  |  | 0 | 55627 | 55626
55572 | Burma to Sterling City: Rebuild 69 kV line | Rehab 69 kV line from Burma to Sterling City | Update Contact, Schedule, Cost, RPG Dates | Burma | Sterling City | Planned | 1096 - 1274 | AEP TNC | Forrest Farson mlforcum@aep.com 918-599-2674 | 1864 | 2024-05-31 |  | 69 | 0 | 32 | 0 |  | Tom Green | Sterling | Tier 3 |  | 2020-10-01 | 2020-11-01 |  | 6439, 6445, 6460, 61016, 61017, 6435, 6446, 6461, 60411 | Y | N |  | 0 | 55573 | 55572
57910 | Uvalde - West Batesville: Rebuild 138 kV Line | Rebuild the 20.61 mile Uvalde to West Batesville 138 kV line |  | Uvalde | West Batesville | Planned | 1117 - 1295 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3836 | 2024-05-31 |  | 138 | 0 | 20.6 | 0 |  | Uvalde | Zavala | Tier 4 |  |  |  |  | 8234, 8236 | Y | N |  | 0 | 57911 | 57910
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2024-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238 | Y | N |  | Will add the ptoject to the base case. | 8207 | 1031
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0196 | 2024-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 9559 | 2308
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  |  | 5705 | Y | N |  |  | 9835 | 2554
3297 | Tezel Road - New 138kV Substation | Loop new 138 kV substation into the existing 138 kV Helotes to Bandera line. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2024-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5421, 5020, 5200 | Y |  |  | There are no transformers associated with this project | 10840 | 3297
6687 | Rebuild Rio Hondo to East Rio Hondo | Rebuild the 138 kV line from Rio Hondo to East Rio Hondo. |  | Rio Hondo | East Rio Hondo | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-06-01 |  | 138 | 0 | 8.19 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5764, 8319 | Y | N |  |  | 14458 | 6687
45084A | Braunig to Highland Rebuild | Rebuild approximately six circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Highland Hills to Schillers Tap'. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0194, T-0238 | 2024-06-01 |  | 138 | 0 | 6 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  | 0 | 45085 | 45084
45084B | Braunig to Highland Rebuild | Rebuild approximately sixteen circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Schillers Tap to Braunig'. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0194, T-0238 | 2024-06-01 |  | 138 | 0 | 16 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  | 0 | 45086 | 45084
45125 | Quintana Rd to South San Rebuild | Rebuild 1.3 miles of 138 kV transmission line form Quintana Rd substation to South San substation. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0271 | 2024-06-01 |  | 138 | 0 | 1.29 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-15 |  |  | 5350, 5385 | Y |  |  | 0 | 45126 | 45125
13TPIT0070 | Nash Creek Substation | Replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-06-28 |  | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7596 | Y | N |  |  | 10678 | 3322
5430O | Conversion to 138kV | Reconnect the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 930 | Y | N | N/A | 0 | 55209 | 5430
5430Q | Conversion to 138kV | Retire the existing 69kV RD Wells substation together with the autotransformers |  | RD Wells |  | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 932, 930 | Y | N | N/A | 0 | 55211 | 5430
5430M | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line |  | Eagle |  | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 926, 924 | Y | N | N/A | 0 | 55207 | 5430
5430P | Conversion to 138kV | Transfer the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 910, 932 | Y | N | N/A | 0 | 55210 | 5430
5430N | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line |  | Eagle |  | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2024-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 926 | Y | N | N/A | 0 | 55208 | 5430
6930 | New Paloma Substation | Adds new station and short line from Midstream |  | Midstream | Paloma | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2024-08-30 |  | 138 | 0.9 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5644, 5643 | Y | N |  |  | 14749 | 6930
52179 | Rising Star Area Conversions | This converts Hasse to Downing to 138 KV |  | Downing | Hasse | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-10-01 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 277, 281, 1649 | Y |  |  | 0 | 52180 | 52179
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 2000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2024-10-07 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 9723 | 2443
55617 | Campwood to New Barksdale: Rebuild 69 kV line | Rebuild 69 kV line from Campwood to Rocksprings |  | New Barksdale | Campwood | Planned | 1102 - 1280 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3820 | 2024-11-01 |  | 69 | 0 | 7.73 | 0 |  | Edwards | Edwards | Tier 3 |  |  |  |  | 8633, 8365 | Y |  |  | 0 | 55618 | 55617
55624 | Escondido to Ganso: Rebuild 138 kV line | Rebuild 138 kV line from Escondido to Hamilton Road |  | Escondido | Ganso | Planned | 1105 - 1283 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3825 | 2024-11-30 |  | 138 | 0 | 10.198 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 8260, 8267 | Y |  |  | 0 | 55625 | 55624
59260 | Mason Phillips Tap - Mason Phillips: Rebuild 69 kV Line | Rebuild the Mason Phillips Tap to Mason Phillips 69 kV Line | NEW | Seaquist | Mason Phillips | Planned | 1127 - 1305 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 1872 | 2024-11-30 |  | 69 | 0 | 13.7 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6395, 6407, 60458 | Y | N |  | 0 | 59261 | 59260
59394 | Pointer to Rule 69 kV Line Rehab | Rebuild 69 kV Line from Pointer to Rule | NEW | Pointer | Rule | Planned | 1122 - 1300 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1867 | 2024-11-30 |  | 138 | 0 | 14.78 | 0 |  | Haskell | Knox | Tier 4 |  |  |  |  | 6014, 6115, 763, 6120, 60346 | Y | N |  | 0 | 59395 | 59394
3334 | Fort Sam to Kirby and Fort Sam to Tenth Street MLSE Upgrade | Upgrade entire bus and terminals at Fort Sam and ensure a rating of 2000 A. |  | Fort Sam | Kirby/Tenth Street | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0744 | 2024-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5160, 5250, 5420 | Y | N |  | There are no transformers associated with this project | 10692 | 3334
60530 | Rebuild TI-South with 795 ACSS | [6 empty] | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2024-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37080, 37100 | Y |  |  | 0 | 60531 | 60530
54521 | Weatherford_Peaster |  |  | Advance | Shady Grove | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2024-12-26 |  | 138 | 0 | 0 | 60 |  | Parker | Parker | Tier 4 |  |  |  |  | 510, 515, 517, 33517, 516, 518, 543, 1585, 1589 | Y |  |  | 0 | 54522 | 54521
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2024-12-28 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7239 | Y | N |  |  | 10694 | 3336
58010 | North McAllen: Rebuild 138 kV Station | North McAllen Station Rebuild |  | McAllen |  | Planned | 1118 - 1296 | AEP | Glen Reed gareed@aep.com 918-599-2664 | 3837 | 2025-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8368, 8631, 8632 | Y |  |  | 0 | 58011 | 58010
45029 | Grandview Highland Hills Rebuild | CPSE_Rebuild of 138 kV double circuit line Line between Grandview to Highland Hills. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0273 | 2025-06-01 |  | 138 | 0 | 11.6 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-11 |  |  | 5030, 5175, 5095, 5205 | Y |  |  | 0 | 45030 | 45029
48854 | Adds Annova and Port South Bus and lines | Adds Annova and Port South buses, lines to connect Annova to Port South, line from HWY 511 to Port South, and reconnects line from S Carbide to HWY 511 into Port South |  | Annova LNG | Port South | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2025-06-01 |  | 138 | 22.1 | 0 | 0 | 0,120 | Cameron | Cameron | Tier 4 |  |  |  |  | 5775, 5776, 5767, 8337 | Y | N |  | 0 | 48855 | 48854
52070 | Carver - Maxwell: Line Rebuild | Rebuild Carver to Maxwell 138 kV Line | Update Description, Schedule | Carver | Maxwell | Planned | 1079 - 1252 | AEP TNC | Charity Kreher bcogan@aep.com 918-599-2853 | 3804 | 2026-05-31 |  | 138 | 0 | 60.24 | 0 |  | Sutton | Val Verde | Tier 3 |  |  |  |  | 8259, 8261, 60412, 8991, 8998, 60440 | Y | N |  | 0 | 52071 | 52070
15TPIT0031 | Chavaneaux_Chavaneaux Tap Rebuild (Brooks to Chavaneaux ckt) | Rebuild 138 kV transmission from Chavaneaux to Chavaneaux Tap. This rebuild is for Brooks to Chavaneaux ckt. |  | Brooks | Chavaneaux | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0260 | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y |  |  | There are no transformers associated with this project | 9555 | 2304
50647 | CPSE_Merida to Westside MLSE | Upgrade terminal at Merida to ensure a 2000 A rating. |  | Merida | Westside | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0773 | 2026-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5490 | Y |  |  | 0 | 50648 | 50647
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0733 | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y | Y |  |  | 11872 | 4320
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line | Project Deferral | Handley | Hemphill | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5214 | 2027-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 11818 | 4270
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line |  | Cresson | Rocky Creek | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5228 | 2027-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  |  | 1881, 2202 | Y | N |  |  | 12436 | 4834
6287 | Sherry Sw. - Webb/Kennedale 345 kV DCKT Line | Upgrade the existing 345 kV Line |  | Sherry | Webb/Kennedale | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4252 | 2027-05-15 |  | 345 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 3 |  |  |  |  | 1911, 1918, 1930, 1929, 1932, 1934 | Y |  |  |  | 14016 | 6287
5524 | Royse South 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | Royse | Forney | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4234 | 2027-05-15 12:00 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 3 |  |  |  |  | 2469, 2470, 12471, 2437, 2467, 2471, 2478, 2702, 2472, 2474, 2710, 3223, 12702 | Y | N |  | 0 | 49918 | 5524
45068 | Merida to Harlandale Rebuild | CPSE_Merida to Harlandale Rebuild |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0233 | 2027-06-05 |  | 138 | 0 | 10 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5310, 5385, 5395 | Y |  |  | 0 | 45069 | 45068
4490 | LaPalma: Add 2nd 345/138 kV autotransformer | Add 345/138 kV autotransformer capacity at LaPalma |  | LaPalma |  | Planned | 710 - 0880 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 2904 | 2027-09-30 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 4 |  |  |  |  | 8356, 8317, 8314 | Y | N |  |  | 12067 | 4490
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2027-12-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5626, 5634 | Y | N |  |  | 11275 | 3818
6774 | Marina: Add New Distribution Station | Add New Marina Distribution Station |  | Highway 9 | Nueces Bay | Planned | 878 - 1056 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 3665 | 2028-01-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8026, 8441, 8470, 8474 | Y | N |  |  | 14780 | 6774
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into future 138kV Martinez to Skyline transmission line |  | Converse | Martinez-Skyline | Planned | T-0177 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0601 | 2028-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5098, 5294, 5368 | Y | N |  | There are no transformers associated with this project | 8143 | 967
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Howard line. |  | Masterson Rd. | Cagnon-Howard | Planned | T-0910 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0538 | 2028-06-01 |  | 138 | 8 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5296, 5054, 5230 | Y | N |  | There are no transformers associated with this project | 9466 | 2218
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0385 | 2028-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5416, 5250, 5395 | Y | N |  | There are no transformers associated with this project | 10365 | 3021
4084 | Barton-Vega: Upgrade Ckt 928 | Reconductor to 2000 amps |  | Barton | Vega | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-06-01 |  | 138 | 0 | 4.05 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9158, 9285 | Y |  |  |  | 11609 | 4084
4425 | New TR-AW Ckt 1032 AW-JV Ckt 961 | Old Description in Planbook Add 2nd Ckt from TR to HL to tie-in to HL-JV Ckt 961 bypassing HL and creating TR-JV Ckt. New description Ckt 1032 from TR-AW and CKT 961 from AW - JV |  | Techridge 9190 AshtonWoods 9224 | AshtonWoods 9226 Jollyville 9223 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-06-01 |  | 138 | 1.7 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9190, 9223, 9224, 9226 | Y | N |  |  | 11984 | 4425
45535 | Valley_to_ValleyTap_Rebuild | Rebuild an approximate four circuits miles of 138 kV Transmission line from Valley Tap to Valley Road substation. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0279 | 2028-06-01 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5025, 5053, 5465 | Y |  |  | 0 | 45536 | 45535
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and-or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle-Weiderstein | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0645b | 2028-06-01 12:00 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5360, 5435 | Y | N |  | There are no transformers associated with this project | 9557 | 2306
6743 | Magellan Tank Farm: LCRA Interconnect | Add 138kV Tie Line between Navigation 138kV substation and Magellan's 138kV substation. Add Metering at Magellan's Substation. |  | Navigation | Magellan | Planned | 905 - 1083 | AEP TCC/LCRA | Michael Glueck bcogan@aep.com 918-599-2857 | 3689 | 2028-07-01 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 78460 | Y | Y |  |  | 14536 | 6743
1549 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2029-06-01 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  |  | 5857, 58570 | N | N |  |  | 8754 | 1549
2161 | Oaks to Loxley | Build new 138 kV 795 ACSR circuit from Oaks to a new AEP switching station Loxley in the Trumbo to Pleasanton line | Load forecasts have changed since project was RPG approved | Oaks | Loxley | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2029-06-01 |  | 138 | 6 | 0 | 0 |  | Atascosa | Atascosa | Tier 3 |  | 2011-12-16 | 2012-04-25 |  | 5713, 80491 | N | N |  | This new line was part of Karnes Electric Cooperative Project that was approved in 2012. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 9408 | 2161
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits, as recommended in 2013 RTP. |  | Bevo | Carrizo Springs | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2029-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 1 |  | 2012-04-12 | 2012-08-12 | 2012-09-12 | 5871, 8244 | N | N |  | This new line was part of Karnes and Medina Electric Cooperatives Project that was approved in 2012. This also helped voltage on AEP transmission under contingencies. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 10984 | 3595
3822 | San Miguel to Sigmor 138 kV line upgrade | Upgrade San Miguel to Sigmor 138 kV line as recommended in 2013 RTP. Will investigate re-conductoring on existing structures with ACCC and other high temperature conductors. |  | San Miguel | Sigmor | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2029-06-01 |  | 138 | 0 | 26.3 | 0 |  | Atascosa | Live Oak | Tier 3 |  |  |  |  | 5689, 5902, 8404 | N | N |  | Studies after the 2013 RTP have shown that AEP's approved project to rebuild the 69 kV Beeville to Three Rivers to 138 kV, TPIT 5166, reduces the loading on this line. STEC believes that rebuilding San Miguel to Sigmor is likely to be justified in the future by load growth and or generation additions. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 11279 | 3822
5220 | Move Orange Grove load to 138 kV bus | Move load from the 69 KV to the 138 KV instead of replacing auto. 2015 RTP |  | Orange Grove |  | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 5660 | N | N |  |  | 12887 | 5220
5763C | CHORIN to STRANG Ckt.87 | STRANG to Cedar Bayou Ckt.87 |  | STRANG | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40010, 41500 | Y | N |  | 0 | 45414 | 5763

## CompletedTPIT020121NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2021
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
7172 | Refugio: Install 138/69 kV Auto | Install 90 MVA 138/69 kV autotransformer and a 138 kV breaker |  | Refugio |  | In-Service | 100-0100 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 2021 | 2020-01-01 | 2019-10-24 | 138 | 0 | 0 | 90 |  | Refugio |  | Tier 3 |  | 2017-03-31 | 2017-04-21 | 2017-06-01 | 8412, 89634, 8410 | Y | N |  |  | 15013 | 7172
44385 | Victoria: Connect 138 kV Generator | Connect 138 kV Victoria City generator tie line into new breakers at Victoria. |  | Victoria | Leupold | In-Service | 951 - 1129 | AEP TCC | Tommy Vannoy bcogan@aep.com 918-599-2857 | 3715 | 2020-01-01 | 2019-12-03 | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 8174, 8172, 111363 | Y | N |  | 0 | 44386 | 44385
50674 | Chocolate Bayou: Upgrade Distribution Transformer | Chocolate Bayou: Upgrade Distribution Transformer |  | Chocolate Bayou |  | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2020-01-01 |  | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 80064 | Y | N |  | 0 | 50675 | 50674
7036 | Forest Grove Sw. Sta. to Eustace SE 138 kV line section | Rebuild the Forest Grove Sw. Sta. to Eustace SE 138 kV line section |  | Forest Grove Sw. Sta. | Eustace SE | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6014 | 2020-01-01 |  | 138 | 0 | 4.3 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  |  | 3131, 6951 | Y | N |  |  | 14858 | 7036
6785 | Leakey Substation Upgrade | Replace 69/25 kV and 69/12.5 kV Power Transformers with dual-rated 138-69/25-12.5 kV Power Transformers and add one 138 kV Circuit Breaker to be operated at 69 kV. | Accelerating Schedule | Leakey |  | Planned |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-3372 Ext 6078 | 353985 | 2020-01-08 |  | 69 | 0 | 0 | 0 |  | Bandera |  | Tier 4 |  |  |  |  | 7426 | Y | N |  |  | 14579 | 6785
45053 | Schottky 69 kV Hard Tap | Schottky 69 kV Hard Tap |  | Sunniland | Three Rivers | Under Construction | 970 - 1148 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3728 | 2020-01-16 | 2019-08-16 | 69 | 0 | 0 | 0 |  | Live Oak | Live Oak | Tier 4 |  |  |  |  | 88507, 8400, 8406 | Y | N |  | 0 | 51801 | 45053
5195 | Rio Pecos: Build 138 kV terminal | Interconnect Pecos solar farm at Rio Pecos | IN SERVICE | Rio Pecos |  | In-Service | 758 - 0942 | AEP TNC | Randy Weaver mlforcum@aep.com 918-599-2674 | 2633 | 2020-01-24 | 2020-01-24 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 6601 | Y | N |  |  | 12854 | 5195
6985 | Gonzales - Harwood Transmission Line Overhaul | Overhaul and upgrade the 69-kV Gonzales - Harwood transmission line supporting circuit T542 with 138-kV capable structures, 795 ASCR Drake, and OPGW static. The planned T542 circuit rating will be (MVA): Rate A=28, Rate B=28, Rate C=28. |  | Luling | Hochheim | Planned | 1018965 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018965 | 2020-01-24 |  | 69 | 0 | 10 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  |  | 7223, 78577 | Y | N |  |  | 14802 | 6985
43452A | Angleton to MONSAN Ckt.04 Upgrades | Upgrade Ckt.04 PETSON to MONSAN to increase thermal limits |  | Petson | Monsan | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-01-29 | 2020-01-21 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | 18RPG007 | 2018-07-26 | 2018-08-17 |  | 42940, 43070 | Y | N |  | Cost included in 43452C | 51007 | 43452
43452B | Angleton to MONSAN Ckt.04 Upgrades | Upgrade Ckt.04 Liverpool to PETSON to increase thermal limits |  | Liverpool | Petson | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-01-30 00:01 | 2020-01-21 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | 18RPG007 | 2018-07-26 | 2018-08-17 |  | 42870, 43070 | Y | N |  | Cost included in 43452C | 51008 | 43452
50944 | Move Southwyck distribution 14.4MVAR to ckt 05 | Distribution 14.4 MVAR C1 moves from ckt 26 to ckt 05 |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-01-31 | 2020-03-31 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 43260, 43261 | Y |  |  | 0 | 50945 | 50944
6255A | Rebuild BEVO to Brundage to Big Wells 69 kV lines. | Rebuild 69 kV line with 795 ACSR on 138 kV and double circuit capable structures 2015- NERC assessment |  | Brundage | Big Wells | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-01-31 | 2020-02-14 | 69 | 0 | 11.05 | 0 |  | Dimmit | Dimmit | Tier 4 |  |  |  |  | 5868, 5870 | Y | N |  | 0 | 45066 | 6255
43284E | Baytown Area Upgrades | Upgrade Ckt.21 DIABOX to MOMENT to increase thermal ratings |  | DIABOX | MOMENT | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-01-31 00:01 | 2020-03-04 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40480, 41090 | Y |  |  | 0 | 56063 | 43284
43452C | Angleton to MONSAN Ckt.04 Upgrades | Upgrade Ckt.04 Angleton to Liverpool to increase thermal limits |  | Angleton | Liverpool | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-01-31 00:02 | 2020-01-21 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | 18RPG007 | 2018-07-26 | 2018-08-17 |  | 42110, 42870, 44561 | Y | N |  | 0 | 51009 | 43452
48750 | Gibbs: Construct New 138 kV Station | Gibbs: Construct New 138 kV Station |  | McCampbell | Portland | In-Service | 846 - 1030 | AEP TCC | Thomas Reynolds bcogan@aep.com 918-599-2857 | 3642 | 2020-02-01 | 2019-10-30 | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8173, 88790, 8414, 80470 | Y | N |  | 0 | 48751 | 48750
4530 | Heartland to South Brady Tap: Rebuild existing & build new | Construct a new 69 kV line from Heartland to South Brady Tap and rebuild the existing line from Heartland to South Brady Tap | IN SERVICE | Heartland | South Brady Tap | In-Service | 637 - 0806 | AEP TNC | Thomas Reynolds mlforcum@aep.com 918-599-2674 | 2610 | 2020-02-07 | 2020-02-07 | 69 | 1.11 | 1.11 | 0 |  | McCulloch | McCulloch | Tier 2 |  | 2014-01-23 | 2014-11-04 | 2014-11-17 | 6379, 60386, 6378, 6381, 6406 | Y | N |  |  | 12105 | 4530
4519 | Heartland: Build 69 kV station | Construct new 69 kV ring bus between MCEC Brady and Katemcy | IN SERVICE | Heartland |  | In-Service | 637 - 0806 | AEP TNC | Thomas Reynolds mlforcum@aep.com 918-599-2674 | 2609 | 2020-02-07 | 2020-02-07 | 69 | 0 | 0 | 0 |  | McCulloch |  | Tier 2 |  | 2014-01-23 | 2014-11-04 | 2014-11-17 | 60386 | Y | N |  |  | 12091 | 4519
5956 | Young: Build new distribution station | Young: Build new distribution station |  | Polk Avenue | Pharr | In-Service | 804 - 0989 | AEP TCC | Thomas Reynolds bcogan@aep.com 918-599-2857 | 3593 | 2020-02-08 | 2020-02-18 | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8030, 8372, 8373 | Y | N |  |  | 13669 | 5956
6077 | Bronte Atlantic to Miles 69 kV line: Rebuild 69 kV line | Rehab Bronte Atlantic to Miles 69 kV line | IN SERVICE | Bronte Atlantic | Miles | In-Service | 786 - 0971 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2691 | 2020-02-17 | 2020-02-17 | 69 | 0 | 17.44 | 0 |  | Coke | Runnels | Tier 4 |  |  |  |  | 6410, 6418 | Y | N |  |  | 13800 | 6077
7018 | Kleimann Substation Addition | Construct a 138-kV capable breakered substation, in a ring bus arrangement, between Columbus and Stafford Hill on circuit T544. The substation will provide transmission service to AEP load that will be transferred from Columbus Substation. Columbus Substation will be retired. ( Initially modelled at 69-kV until the completion of Glidden area upgrades project) |  | Columbus | Stafford Hill | Planned | 1018910 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018910 | 2020-02-26 |  | 138 | 0 | 0 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  |  | 78111, 78115, 78107, 78520 | Y | N |  | 0 | 45505 | 7018
6111 | Carancahua - Point Comfort 69 kV Line | Rehab Carancahua - Point Comfort 69 kV Line |  | Carancahua | Point Comfort | In-Service | 817 - 1001 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3613 | 2020-02-28 | 2019-12-13 | 69 | 0 | 9.18 | 0 |  | Jackson | Calhoun | Tier 4 |  |  |  |  | 8132, 8555 | Y | N |  |  | 13837 | 6111
6683 | Del Sol-Cabezon: Create Permanent Interconnection for Rio Br | Construct 2nd circuit on Cenizo-Del Sol 345 kV line from the Rio Bravo Windfarm Collector Station (Cabezon) to Del Sol. |  | Del Sol | Cabezon | In-Service | 896 - 1074 | ETT | Kenneth Haley bcogan@aep.com 918-599-2857 | 3680 | 2020-02-28 | 2019-12-17 | 345 | 26.5 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  |  | 80380, 80381, 80307, 80355, 80225, 161851, 161855 | Y | N |  |  | 14453 | 6683
52167A | El Dorado 10.8 MVar Cap Bank | Remove existing Harrisburg 10.8 MVAr cap bank CB2 |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-02-28 | 2020-01-28 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40800 | Y | N |  | 0 | 55384 | 52167
44381 | Causeway: Add 2nd Distribution Bank | Causeway: Add 2nd Distribution Bank |  | Causeway |  | Planned | 945 - 1123 | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | 3709 | 2020-02-28 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8744 | Y | N |  | 0 | 44382 | 44381
6673C | Freeport - Bridge the Gap | Loop Ckt.27 STP-DOW into Jones Creek to create new Ckt.27 Jones Creek to STP |  | Jones Creek | STP | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-02-28 00:03 | 2020-02-19 | 345 | 0.18 | 0 | 0 |  | Brazoria | Matagorda | Tier 1 |  |  |  | 2017-12-12 | 42400, 42500, 42530 | Y | N |  | 0 | 56736 | 6673
6673G | Freeport - Bridge the Gap | Install 7-Ohm in-series reactors at Jones Creek substation on Ckts.18 & 27 Jones Creek to STP |  | Jones Creek | STP | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-02-28 00:05 | 2020-02-19 | 345 | 0 | 0 | 0 |  | Brazoria | Matagorda | Tier 1 |  |  |  | 2017-12-12 | 47531, 47532, 5915, 42400, 42530 | Y | N |  | 0 | 56738 | 6673
6673D | Freeport - Bridge the Gap | Loop Ckt.27 STP-DOW into Jones Creek to create new Ckt.27 Jones Creek to DOW |  | Jones Creek | DOW | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-02-28 00:06 | 2020-02-19 | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 1 |  |  |  | 2017-12-12 | 42400, 42500, 47531, 5915, 42530 | Y | N |  | Cost included in Phase C. | 56732 | 6673
45116 | TNMP Elm First Substation | New Substation - Elm First |  | IH20 (Bus #38045) | Reeves Tap (Bus #38114) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2020-03-01 |  | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38049, 38090, 38040, 38045, 38114 | Y |  |  | 0 | 48424 | 45116
45344 | Pirate: Build 69 kV Station | Pirate: Build 69 kV Station on Beeville - Sinton Line |  | Skidmore | Sinton | In-Service | 882 - 1068 | AEP TCC | Terry Weeks bcogan@aep.com 918-599-2857 | 3669 | 2020-03-02 |  | 69 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8652, 8405, 8413 | Y | N |  | 0 | 45345 | 45344
44368 | Amos Creek Substation Addition | Construct a 345-kV breakered substation, in a ring bus arrangement, between Red Creek and Bow Wood on circuit T424. The substation will provide transmission service for a generation interconnection (20INR0045) request. |  | Red Creek | Bow Wood | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1020230 | 2020-03-05 |  | 345 | 0 | 0 | 0 |  | Tom Green | McCulloch | Tier 4 |  |  |  |  | 7077, 6444, 76006 | Y | N |  | 0 | 44369 | 44368
43487 | Cryo to Saragosa: Build 138 kV line | Build new Cryo 138 kV station, build Cryo to Saragosa new 138 kV line, add capacitor banks at Cryo | IN SERVICE | Cryo | Saragosa | In-Service | 926 - 1104 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2739 | 2020-03-05 | 2020-03-05 | 138 | 5 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 60721, 60716 | Y | N |  | 0 | 43488 | 43487
43485 | Cryo: Build 138 kV station | Build new Cryo 138 kV station, build Cryo to Saragosa new 138 kV line, add capacitor banks at Cryo | IN SERVICE | Cryo |  | In-Service | 926 - 1104 | AEP TNC | Tom Reynolds mlforcum@aep.com 918-599-2674 | 2740 | 2020-03-05 | 2020-03-05 | 138 | 0 | 0 | 0 | 0,28.8 | Reeves |  | Tier 4 |  |  |  |  | 60721, 60716 | Y | N |  | 0 | 43486 | 43485
51240 | Add Wolf to Moss 138 kV Line High Temperature Upgrade | Wolf to Moss 138 kV Line High Temperature Upgrade |  | Wolf | Moss | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8494 | 2020-03-15 |  | 138 | 0 | 34.5 | 0 |  | Ward | Ector | Tier 3 |  | 2019-07-12 | 2019-09-06 |  | 1019, 1292 | Y |  |  | 0 | 51242 | 51240
7159 | Ajo-Stella: Create Permanent Interconnection for Stella WF | Convert Stella Windfarm temporary tap interconnection to a permanent interconnection. ETT will construct an extension of the gen tie-line by adding a second circuit on the Ajo-Zorillo line, therefore creating a dedicated circuit terminating at the Ajo station. |  | Ajo | Stella | In-Service | 894 - 1072 | ETT | Teresa Trotman bcogan@aep.com 918-599-2857 | 3678 | 2020-03-17 | 2020-03-03 | 345 | 0 | 7.85 | 0 |  | Kenedy | Kenedy | Tier 4 |  |  |  |  | 80070, 80071, 80072, 80076, 161591 | Y | N |  |  | 15000 | 7159
3894 | Fowlerton 345 station and 345/138 autotransformer | Add 345 kV bus and autotransformer |  | Fowlerton |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-03-20 12:00 | 2020-04-09 | 345 | 0 | 0 | 675 |  | McMullen |  | Tier 4 |  |  |  |  | 5706, 5709, 5901, 80219, 5705 | Y | N |  | 2017 RTP moved project up to 2019. Still studying size needed and possible relocation of existing autotransformer. | 44403 | 3894
6075 | Veribest T to Harriett 69 kV line: Rebuild 69 kV line | Rehab Veribest Tap to Harriett CVEC REA 69 kV line | IN SERVICE | Veribest Tap | Harriett CVEC REA | In-Service | 786 - 0971 | AEP TNC | Darren O'Hare mlforcum@aep.com 918-599-2674 | 2690 | 2020-03-24 | 2020-03-24 | 69 | 0 | 8.4 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  |  | 6409, 6412 | Y | N |  |  | 13797 | 6075
44379 | Bonilla: Build new 345 kV Station | New Bonilla 345 kV Station to interconnect Raymond Wind |  | Bonilla |  | In-Service | 944 - 1122 | AEP TCC | Adam Wells bcogan@aep.com 918-599-2857 | 3708 | 2020-03-25 | 2020-01-27 | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8573, 88573, 8318, 8383 | Y | N |  | 0 | 44380 | 44379
7164 | T195 Granite Mountain - Marble Falls MLSE Upgrade | Upgrade terminal equipment at Granite Mountain and Marble Falls to achieve a planned static normal and emergency rating of 221 MVA on T195. |  | Granite Mountain | Marble Falls | Planned | 1019369 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1019369 | 2020-03-26 |  | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  |  | 7348, 7474 | Y | N |  |  | 15005 | 7164
6711 | Castle Mountain Substation Addition | Construct a new substation named Castle Mountain off the LCRA Crane to Rio Pecos (T451) transmission line to support a generation interconnection request (18INR0039). |  | LCRA Crane | Rio Pecos | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018758 | 2020-03-27 |  | 138 | 0 | 0 | 0 |  | Crane | Crockett | Tier 4 |  |  |  |  | 76025, 60014, 76615 | Y | N |  |  | 14494 | 6711
44852 | Kelvin: Build new 138 kV station | Interconnect Chalupa wind farm on the La Palma to Rio Hondo 138 kV line |  | La Palma | Rio Hondo | In-Service | 965 - 1143 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3723 | 2020-04-01 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8640, 88640, 8314, 8319 | Y | N |  | 0 | 44853 | 44852
6783 | Utopia-Tarpley Re-Termination | Re-Termination of existing T281 Transmission Line, related to reconfiguration of Utopia and Tarpley Substations. | Change in schedule | Utopia | Tarpley | In-Service |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-3372 Ext 6078 | 353985 | 2020-04-08 |  | 69 | 0 | 0.25 | 0 |  | Bandera | Bandera | Tier 4 |  |  |  |  | 7428, 7440 | Y | N |  |  | 14577 | 6783
5914 | Crosswinds Substation Addition | LCRA TSC will construct a new three breaker ring bus substation to provide transmission service to PEC's planned distribution substation facility. |  | Turnersville | Goforth | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017349 | 2020-04-13 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7503, 7500, 7501 | Y | N |  |  | 13622 | 5914
6973 | Welcome Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement,at Welcome Substation. |  | Welcome |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018929 | 2020-04-13 |  | 138 | 0 | 0 | 0 |  | Austin |  | Tier 4 |  |  |  |  | 7577 | Y | N |  |  | 14790 | 6973
4065 | Add Graham Road Substation |  |  | BTU South | BTU Greens Prairie | Planned |  | COCS | Tony Mickalsky tmichalsky@cstx.gov 979-764-3438 |  | 2020-04-15 10:00 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32007, 32878, 32880 | Y |  |  |  | 11590 | 4065
6347 | Ballinger to Paint Rock 69 kV line: Rebuild 69 kV line | Rehab Ballinger to Paint Rock 69 kV line | IN SERVICE | Ballinger | Paint Rock | In-Service | 786 - 0971 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2708 | 2020-04-20 | 2020-04-20 | 69 | 0 | 14.6 | 0 |  | Runnels | Concho | Tier 4 |  |  |  |  | 6338, 6369 | Y | N |  |  | 14091 | 6347
6353 | Kirkland to Acme Best Wall 69 kV line: Rebuild 69 kV line | Rehab Kirkland to Acme Best Wall 69 kV line | IN SERVICE | Kirkland | Acme Best Wall | In-Service | 786 - 0971 | AEP TNC | Joseph Page mlforcum@aep.com 918-599-2674 | 2717 | 2020-04-22 | 2020-04-22 | 69 | 0 | 14.6 | 0 |  | Childress | Hardeman | Tier 4 |  |  |  |  | 6052, 6053 | Y | N |  |  | 14097 | 6353
6983 | Fayetteville - Winchester Transmission Line Upgrade | Upgrade the 138-kV Fayetteville - Winchester transmission line supporting circuit T165 to single 1433 ACSS/TW conductor and OPGW static. The planned T165 circuit rating is (MVA): Rate A=470, Rate B=470, Rate C=470. |  | Fayetteville | Winchester | Planned | 1018933 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018933 | 2020-04-24 |  | 138 | 0 | 18.8 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7286, 7306 | Y | N |  |  | 14800 | 6983
45415 | Coulomb to Vera: Build new 345 kV line | Interconnect Vera wind farm on the Clear Crossing to Edith Clarke 345 kV line | IN-SERVICE | Coulomb | Vera | In-Service | 933 - 1111 | ETT | Eric Blind mlforcum@aep.com 918-599-2674 | 2745 | 2020-04-27 01:00 | 2020-04-27 | 345 | 4 | 0 | 0 |  | Knox | Knox | Tier 4 |  |  |  |  | 143015, 60722 | Y | N |  | 0 | 45416 | 45415
44812 | Coulomb: Build new 345 kV station | Interconnect Vera wind farm on the Clear Crossing to Edith Clarke 345 kV line | IN-SERVICE | Coulomb |  | In-Service | 933 - 1111 | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | 2744 | 2020-04-27 01:00 | 2020-04-27 | 345 | 4 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 60722, 60500, 60702 | Y | N |  | 0 | 44813 | 44812
6065 | Abilene Northwest to Anson 69 kV line: Rebuild 69 kV line | Rehab Abilene Northwest to Anson 69 kV line | IN SERVICE | Abilene Northwest | Anson | In-Service | 786 - 0971 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2673 | 2020-04-29 | 2020-04-29 | 69 | 0 | 14 | 0 |  | Taylor | Jones | Tier 4 |  |  |  |  | 6224, 6236 | Y | N |  |  | 13785 | 6065
5946 | Winchester Autotransformer Additions | Add two 672 MVA autotransformers at Winchester Substation. Cut the new 345-kV bus at Winchester into an existing Austin Energy owned 345-kV transmission line from FPP to Lost Pines. |  | FPP #1 | Lost Pines | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017413 | 2020-04-29 |  | 345 | 0 | 0 | 1344 |  | Fayette | Bastrop | Tier 3 | 17RPG002 | 2017-02-01 | 2017-03-20 |  | 77306, 77308, 77309, 7056, 9041, 7306 | Y | N |  |  | 13657 | 5946
4464A | Comal to Loop337 to GPI to Marion switchyard Transmission Up | Alter CTs to 2000:5 to remove CTs as MLSE elements. Utilize dynamic switch rating for Winter loading. | Switches may be dynamically rated during Winter peak conditions. | Comal | GPI Switchyard | In-Service |  | NBU | Gregory Thomas gthomas@nbutexas.com 830-608-8953 |  | 2020-04-30 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7176, 7456, 7459 | Y | N |  |  | 12380 | 4464
4464B | Comal to Loop337 to GPI to Marion switchyard Transmission Up | Upgrade/Replace underrated switches to 3000 Amp Switches. Replace and increase fault interrupting rating of breakers 430, 440, 3370, 3380, 5680, 5690, 5700, 2970, 5870 to 63kA. Replace and upgrade CS2965 and CS2975 to 3000 Amp 40kA. Replace and upgrade CS5395 and CS5405 to 40kA. | Switches may be dynamically rated during Winter peak conditions. | Comal | Marion | Planned |  | NBU | Gregory Thomas gthomas@nbutexas.com 830-608-8953 |  | 2020-04-30 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7176, 7178, 7456, 7459 | Y | N |  |  | 12381 | 4464
51746 | LagoVista Capacitor Switcher Upgrade | Upgrade interrupting capability of capacitor switcher from 8 kA to 40 kA and replace electromechanical relay panel with digital relay panel |  | Lago Vista |  | Planned |  | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 |  | 2020-05-01 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7352 | Y | N |  | 0 | 51753 | 51746
51748 | PEC Leander BusUpgrade | Upgrade the Leander bus from operate/transfer to breaker-and-a-half |  | Alamito Creek | Solstice | Planned |  | PEC | Charles Dewitt Charles.Dewitt@LCRA.org 512-578-4199 |  | 2020-05-01 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 7525 | Y | N |  | 0 | 51754 | 51748
6074 | Concho to Veribest Tap 69 kV line: Rebuild 69 kV line | Rehab Concho to Veribest Tap 69 kV line | IN SERVICE | Concho | Veribest Tap | In-Service | 786 - 0971 | AEP TNC | Darren O'Hare mlforcum@aep.com 918-599-2674 | 2689 | 2020-05-04 | 2020-05-04 | 69 | 0 | 1.86 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  |  | 6409, 6450 | Y | N |  |  | 13796 | 6074
5429A | Phase 3 of the conversion to 138kV | Add a new 138kV line from the new Locust station to Woodrow to Spencer Interchange via a three way tie at Woodrow. The section going from the 3way tie to Spencer Int. was added in phase 2. |  | Locust | Spencer Int. | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-05-05 | 2017-07-01 | 138 | 1.917 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 924, 99999, 921, 982 | Y | N | N/A | 0 | 45742 | 5429
5429C | Phase 3 of the conversion to 138kV | The three way tie will be retired and 138kV locust will tie directly to 138kV Woodrow. The Spencer Int. to the 3way tie will be reconfigured to terminate at the new 138kV Brinker substation. |  | Locust | Spencer Int. | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-05-05 | 2019-03-11 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 99999, 921, 924, 982 | Y | N | N/A | 0 | 45744 | 5429
5428D | Phase 2 of the conversion to 138kV | Line will be reconfigured to through a 3way tie |  | Woodrow | Spencer Int | Planned | N/A | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-05-05 | 2017-07-01 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 921, 982 | Y | N | N/A |  | 13116 | 5428
47444 | Divide Circuit Breaker Addition | Provide transmission service to a generator and add a 345-kV bay and circuit breaker at Divide Substation (19INR0156). |  | Divide | Divide | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2020-05-06 |  | 345 | 0 | 0 | 0 |  | Coke | Coke | Tier 4 |  |  |  |  | 76090 | Y | N |  | 0 | 47445 | 47444
6709 | Heines Substation Addition | Construct a new load-serving substation named Heines off the Airline to Naval Base (T476) transmission line. | [5 empty] | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018754 | 2020-05-07 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 78560, 8487, 8560 | Y |  |  | 0 | 45470 | 6709
6787 | Utopia Susbtation Upgrade | Add two 138 kV Circuit Breakers to Line Terminals to be operated at 69 kV. | Accelerating Schedule | Utopia |  | In-Service |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-3372 Ext 6078 | 353985 | 2020-05-08 | 2020-06-20 | 69 | 0 | 0 | 0 |  | Bandera |  | Tier 4 |  |  |  |  | 7428, 7439, 7440 | Y | N |  |  | 14581 | 6787
6982 | Boerne Cico - Comfort - Kendall Transmission Line Upgrade | Upgrade the 138-kV Boerne Cico - Comfort transmission line supporting circuit T148 to bundled 795 ACSR conductor. The planned T148 circuit rating is (MVA): Rate A=440, Rate B=440, Rate C=440. Upgrade the 138-kV Comfort - Kendall transmission line supporting circuit T243 to bundled 959 ACSS/TW conductor. The planned T243 circuit rating is (MVA): Rate A=760, Rate B=760, Rate C=760. |  | Boerne Cico | Kendall | Planned | 1019089 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1019089 | 2020-05-11 |  | 138 | 0 | 18.1 | 0 |  | Kendall | Kendall | Tier 4 |  |  |  |  | 7151, 7152, 7155 | Y | N |  |  | 14799 | 6982
6203 | Premont - Falfurrias 69 kV Line | Rehab Premont - Falfurrias 69 kV Line |  | Premont | Falfurrias | In-Service | 818 - 1002 | AEP TCC | Joe Yeagler bcogan@aep.com 918-599-2857 | 3616 | 2020-05-11 |  | 69 | 0 | 12.25 | 0 |  | Jim Wells | Brooks | Tier 4 |  |  |  |  | 8508, 8894 | Y | N |  |  | 13928 | 6203
44850 | Grissom: Build new 345 kV Station | Interconnect Cranell wind farm on the Coleto Creek to Lon Hill 345 kV line |  | Grissom |  | In-Service | 963 - 1141 | AEP TCC | Adam Wells bcogan@aep.com 918-599-2857 | 3721 | 2020-05-13 |  | 345 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8164, 8455, 8624, 88624 | Y | N |  | 0 | 51799 | 44850
16TPIT0050 | Northaven - Renner 138 kV Line | Upgrade existing line | Project Deferral | Northaven | Renner | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4108-E | 2020-05-14 |  | 138 | 0 | 8.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2356, 2357, 2596, 2597, 2613, 2614, 2615, 2616, 2657, 2658 | Y | N |  |  | 11845 | 3065
6778 | Tri Corner - Watermill 345 kV Line | Upgrade existing line |  | Watermill | Tri Corner | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4226 | 2020-05-14 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 12427, 2427, 2432 | Y | N |  | 0 | 49535 | 6778
5499 | Everman - Cedar Hill Sw. Sta. 345 kV Line | Upgrade existing Everman - Cedar Hill Sw. Sta. 345 kV Line | Construction schedule change | Everman | Cedar Hill | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5260 | 2020-05-14 11:52 |  | 345 | 0 | 39.14 | 0 |  | Tarrant | Dallas | Tier 4 |  | 2016-03-10 | 2016-07-22 |  | 1885, 1886, 1931, 1932, 2420 | Y | N |  |  | 13239 | 5499
51228A | Construct Kennedale 138 kV Substation and Burleson 138 kV Sw | Construct Kennedale 138 kV Substation |  | Kennedale | Burleson | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5294 | 2020-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1933, 1883, 2208 | Y |  |  | Cost included in phase B | 52341 | 51228
4829 | Hutto Switch second 345/138 kV autotransformer | Install new autotransformer |  | Hutto |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R750 | 2020-05-15 |  | 345 | 0 | 0 |  |  |  |  | Tier 4 |  |  |  |  | 13660, 3696, 3666 | Y |  |  | 0 | 49638 | 4829
17TPIT0023 | Northwest Carrollton - Norwood 138 kV Line | Upgrade existing double-circuit Northwest Carrollton - Carrollton line section | Project Deferral | Northwest Carrollton | Carrollton | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4110-E | 2020-05-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 4 |  |  | 2017-01-11 |  | 2362, 2363, 2409, 2535, 2536, 2537, 2540, 2541, 2542, 2545, 2550, 2551, 2552, 12552 | Y | N |  |  | 10433 | 3089
7021 | Collin 345/138 kV Autotransformer 2 Series Reactor | Install 2-ohm series reactor on Collin 345/138 kV Autotransformer 2 |  | Collin Sw. Sta. |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R960 | 2020-05-15 |  | 138 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  |  | 2370, 29555 | Y | N |  |  | 14843 | 7021
46094 | Add Wolf 345 kV Switch | Wolf 345 kV Switch | New route approved | Wolf | Wolf | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8289 | 2020-05-15 |  | 345 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 11007, 11008, 11010, 1018, 1029, 11028, 11084, 1013 | Y |  |  | 0 | 51215 | 46094
5286A | Fayette Area Upgrades | Upgrade existing Fayette - Frelsburg - Mockingbird - Glidden (T176) TL with a minimum rating of 380 MVA and with OPGW. | Planning In-Service Date Change. Updated to a phased project, the original TPIT project number is 5286. | Fayetteville | Glidden | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1019026, 1019024 | 2020-05-15 |  | 138 | 0 | 20 | 0 |  | Fayette | Colorado | Tier 4 | 17RPG011 | 2017-06-29 | 2017-07-28 |  | 7258, 7263, 7286, 78259 | Y | N |  |  | 14583 | 5286
6834D | IH20 STATCOM RPG | Install fifth and sixth 20 MVAR MSCs at Collie Capacitor Station (38035). |  | Collie Capacitor Station (38035) | Collie Capacitor Station (38035) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2020-05-15 |  | 138 | 0 | 0 | 0 | 0,40 | Reeves | Reeves | Tier 3 |  | 2017-10-10 | 2017-12-06 |  | 38035 | Y |  |  | 0 | 46209 | 6834
5648 | Hamilton Road to Picacho Ckt #2 138 kV Line: Rebuild | Rebuild Hamilton Road to Picacho 138 kV line ckt #1 |  | Hamilton Road | Del Rio | In-Service | 869-1050 | AEP TCC | Jeremy Brazeal bcogan@aep.com 918-599-2857 | 3659 | 2020-05-15 | 2020-05-15 | 138 | 0 | 8.7 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8255, 8684 | Y | N |  |  | 13382 | 5648
11TPIT0034 | Sargent Road 345/138 kV autotransformer | Install second 345/138 kV autotransformer |  | Sargent Road |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M486-E | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 4 |  |  |  |  | 2946, 2949 | Y | N |  |  | 9001 | 1784
44181 | 138kV Cooper Creek - Arco Line Reconstruction |  |  |  |  | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2020-05-15 | 2020-02-01 | 138 | 0 | 1.62 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 906, 923 | Y | N |  | Reconstruct 138kV Cooper Creek to Arco | 44182 | 44181
7171 | Andrews County South Switch - No Trees Switch 138 kV Line | Andrews County South Switch - No Trees Switch 138 kV Line |  | Andrews Co South | No Trees | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8407 | 2020-05-15 |  | 138 | 0 | 8.8 | 0 |  | Andrews | Winkler | Tier 4 |  |  | 2018-09-06 |  | 1149, 1150, 1157, 131853 | Y |  |  |  | 15012 | 7171
50510 | Add Doghouse 345 kV Switch | Add Doghouse 345 kV Switch for Prospero Solar POI |  | Clearfork Switch | Doghouse Switch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8482, R8284 | 2020-05-15 |  | 345 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 11270, 23876 | Y |  |  | 0 | 50512 | 50510
51245 | Add Andrews County South 345/138 kV Autotransformer #2 | Andrews County South 345/138 kV Autotransformer #2 |  | Andrews County South | Andrews County South | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8495 | 2020-05-15 |  | 345 | 0 | 0 | 600 |  | Andrews | Andrews | Tier 3 |  | 2019-07-12 | 2019-09-16 |  | 11207, 1158, 1157 | Y |  |  | 0 | 51247 | 51245
4817 | TI Dallas - Kirkland Park/Coit Road 138 kV Line | Upgrade existing TI Dallas - Schroeder Road line section | Project Deferral | TI Dallas | Schroeder Road | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4202 | 2020-05-15 01:00 |  | 138 | 0 | 1 | 0 |  | Dallas | Dallas | Tier 4 |  | 2018-04-05 | 2018-05-08 |  | 2607, 2633, 2636, 2637 | Y | N |  |  | 12423 | 4817
45537 | Lewisville - Lewisville Jones - Lakepointe 138 kV Line | Upgrade the Lewisville - Lewisville Jones - Lakepointe 138 kV Line |  | Lewisville Switch | Lake Point (TNMP) | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R966 | 2020-05-15 12:00 |  | 138 | 0 | 0 | 0 |  | Denton |  | Tier 4 |  |  |  |  | 645, 1972, 1973, 37010 | Y |  |  | 0 | 45538 | 45537
55609 | Permian Basin Area 138 kV Reconfiguration | Permian Basin Area 138 kV Reconfiguration |  | Aroya - Yucca | Wink - Aroya | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 |  | 2020-05-15 23:00 |  | 138 | 0 | 0 | 0 |  | Ward | Winkler | Tier 4 |  |  |  |  | 1001, 1009, 1013, 1074 | Y |  |  | 0 | 55611 | 55609
51236 | Add Wink to Andrews County South 138 kV Second Circuit | Wink to Andrews County South 138 kV Second Circuit |  | Wink | Andrews County South | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8493 | 2020-05-16 |  | 138 | 36.6 | 0 | 0 |  | Winkler | Andrews | Tier 3 |  | 2019-07-12 | 2019-09-06 |  | 131853, 1009, 1074, 1147, 1149, 1157, 11135 | Y |  |  | 0 | 52912 | 51236
6042 | Scott REA Tap to Eskota 69 kV line: Rebuild 69 kV line | Rehab Scott REA Tap to Eskota 69 kV line | IN-SERVICE | Scott REA Tap | Eskota | In-Service | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2671 | 2020-05-21 | 2020-05-21 | 69 | 0 | 11.73 | 0 |  | Taylor | Nolan | Tier 4 |  |  |  |  | 1340, 6246, 6247 | Y | N |  |  | 13761 | 6042
6041 | Ely Tap to Scott REA Tap 69 kV line: Rebuild 69 kV line | Rehab Ely Tap to Scott REA Tap 69 kV line | IN SERVICE | Ely Tap | Scott REA Tap | In-Service | 786 - 0971 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2670 | 2020-05-21 | 2020-05-21 | 69 | 0 | 8.79 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6242, 6246, 60405 | Y | N |  |  | 13760 | 6041
3754 | Heartland to Yellowjacket: Build 69 kV line | Build new 69 kV line from Heartland to Yellowjacket | IN SERVICE | Heartland | Yellowjacket | In-Service | 637 - 0806 | AEP TNC | Thomas Reynolds mlforcum@aep.com 918-599-2674 | 2592 | 2020-05-28 | 2020-05-28 | 69 | 32 | 0 | 0 |  | Mason | McCulloch | Tier 2 |  | 2014-01-23 | 2014-11-04 | 2014-11-17 | 6379, 60386, 6363, 6378, 6381, 6406, 6372 | Y | N |  |  | 12085 | 3754
7022 | Forney - Elkton 345 kV line termination at Tri Corner | Forney - Elkton 345 kV line termination at Tri Corner |  | Forney | Tri Corner | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4306 | 2020-05-30 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 13105, 2432, 2437, 3105 | Y | N |  | 0 | 49534 | 7022
52527 | Greens Bayou 345kV Reconfiguration - Ckt. 74F Deepwater to S | Disconnect existing circuits 68B & 74F at Greens Bayou and reconnect circuits to create new Ckt.74F Deepwater to Sheldon (Bypass GBY345). |  | Deepwater | Sheldon | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 | 2020-05-12 | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40450, 40700, 41430 | Y | N |  | 0 | 52528 | 52527
49554 | Cabaniss: Add Second Distribution Bank | Cabaniss: Add Second Distribution Bank |  | Cabaniss |  | In-Service | 1033 - 1211 | AEP TCC | Thomas Niels bcogan@aep.com 918-599-2857 | 3772 | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8882 | Y | N |  | 0 | 49555 | 49554
6744 | Picacho: Add Distribution | Add a new distribution bank at the existing Picacho station |  | Picacho |  | In-Service | 1100 - 1278 | AEP TCC | James Lutz dnlyons@aep.com 918-599-2698 | 3817 | 2020-05-31 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 4 |  |  |  |  | 8684 | Y | N |  |  | 14537 | 6744
44834 | LIMBRG (LIM) 138kV Distribution Substation | Build new 138kV LIMBRG distribution substation. Loop through Ckt.05 Southwyck to Friendswood tap. |  | Southwyck | Friendswood | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 | 2020-04-29 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43280, 42651, 43260, 47150, 43500, 44361 | Y |  |  | 0 | 50151 | 44834
7005 | Lake Houston (LAK) - 138kV Distribution Substation | Construct service to new 138kV Lake Houston distribution substation. Loop through Ckt.66 Kingwood to Atascocita. |  | Kingwood | Atascocita | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 | 2020-03-09 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40820, 40130, 40390, 40930, 40391, 40830 | Y |  |  | 0 | 50551 | 7005
6427 | Refugio-Rincon 69 line MLSE Upgrade | Refugio-Rincon 69 line MLSE Upgrade |  | Refugio | Rincon | In-Service | 962 - 1140 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3720 | 2020-05-31 | 2020-04-06 | 138 | 0 | 1 | 0 |  | San Patricio | Refugio | Tier 3 |  | 2017-03-28 | 2017-04-21 | 2017-05-08 | 8410, 8802, 8804, 8805, 8416 | Y | N |  |  | 14170 | 6427
6696A | Nash 138kV Loop Conversion | Convert Nash Substation to 138kV loop service. Loop from Ckt.02 WA Parish to West Columbia. Reconductor the loop sections to Nash. |  | Nash | WA Parish/West Columbia | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 | 2019-12-11 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42980, 42981, 43380, 43384, 44010, 44030, 44390, 44721, 44722 | Y | N |  |  | 14478 | 6696
6673B | Freeport - Bridge the Gap | Install 1st 138kV Automatically Switchable Capacitor Bank (Cap Bank #5 - 140 MVAR) at Jones Creek Substation |  | Jones Creek |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 00:01 | 2020-02-19 | 138 | 0 | 0 | 0 | 0,140 | Brazoria |  | Tier 1 |  |  |  | 2017-12-12 | 42535, 42540 | Y | N |  | 0 | 56734 | 6673
6696B | Nash 138kV Loop Conversion | Remove 69kV Nash tap from Ckt.45 Damon to West Columbia |  | Damon | West Columbia | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 00:01 | 2019-12-11 | 69 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42982, 42980, 42340, 43000, 44070, 44290, 43390 | Y | N |  | Cost included in Phase A | 14480 | 6696
6673E | Freeport - Bridge the Gap | Install 2nd 138kV Automatically Switchable Capacitor Bank (Cap Bank #6 - 140 MVAR) at Jones Creek Substation |  | Jones Creek |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 00:02 | 2020-02-19 | 138 | 0 | 0 | 0 | 0,140 | Brazoria |  | Tier 1 |  |  |  | 2017-12-12 | 42536, 42540 | Y | N |  | 0 | 56735 | 6673
6673F | Freeport - Bridge the Gap | Install 3rd 800MVA autotransformer (A3) at Jones Creek substation |  | Jones Creek |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 00:04 | 2020-02-19 | 345 | 0 | 0 | 800 |  | Brazoria |  | Tier 1 |  |  |  | 2017-12-12 | 49038, 42530, 42540 | Y | N |  | 0 | 56737 | 6673
44836 | BURKE (BKE) - Generator 138kV Substation (18INR0062) | New 138kV BURKE generator interconnection for Wagyu Solar. Loop substation to create new Ckt.02 WA Parish to BURKE to NASH. |  | West Columbia | Nash | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 00:05 | 2020-04-02 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42410, 42980, 43384, 44010, 43380 | Y |  |  | 0 | 46324 | 44836
7071 | West Columbia 138kV Load Conversion | Replace 69/12kV West Columbia power transformer with 138/12kV transformer |  | West Columbia |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-05-31 00:08 | 2020-02-25 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 43384, 43390, 43380, 42410 | Y |  |  |  | 14902 | 7071
51074 | This adds a capacitor to Annetta |  |  | Annetta Substation | Annetta Substation | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2020-06-01 |  | 138 | 0 | 0 | 0 | 0,37.8 | Parker | Parker | Tier 4 |  |  |  |  | 485 | Y |  |  | 0 | 51075 | 51074
4716 | Tortuga: Build new 3 breaker 138 kV station | Construct new Tortuga 138 kV line and cut it into the Gila - Upriver (Koch) 138 kV line |  | Gila | Upriver (Koch) | In-Service | 717 - 0899 | AEP TCC | John Pulay bcogan@aep.com 918-599-2857 | 3553 | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8168, 81680, 8467, 80136, 80141, 80260 | Y |  |  | New or Expand - New Telecom - Yes 345 kV CBs - 0 138 kV CBs - 3 69 kV CBs - 0 SCADA Additions - Yes | 12389 | 4716
5145C | Rafter - New 138 kV Substation | Build a new 138 kV transmission line from Cagnon to Rafter. |  | CAGNON | RAFTER | Planned | S-0837 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0261 | 2020-06-01 |  | 138 | 7.86 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5055, 5355 | Y | N |  |  | 14399 | 5145
3820 | Rebuild Casa Blanca to Sandia to AEP Mathis | Rebuild 69 kV 4-0 ACSR line sections to 795 ACSR on 138 kV capable structures. |  | Casa Blanca | AEP Mathis | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-06-01 | 2020-04-16 | 69 | 0 | 11.45 | 0 |  | Jim Wells | San Patricio | Tier 4 |  |  |  |  | 5666, 8166, 8407 | Y | N |  |  | 11277 | 3820
3273B | Southton - New 138kV Substation |  |  | Southton | Braunig-Brooks | Under Construction | S-0750 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0217 | 2020-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5394, 5030, 5045, 5190, 5310, 5395 | Y | N |  | There are no transformers associated with this project | 10624 | 3273
44874 | Resaca 69 kV Station | New Resaca 69 kV Station |  | Brownsville | La Palma | In-Service | 974 - 1152 | AEP TCC | Thomas Niels bcogan@aep.com 918-599-2857 | 3732 | 2020-06-02 |  | 69 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8626, 8310, 8332 | Y | N |  | 0 | 44875 | 44874
3967 | Leander - Round Rock Transmission Line Addition | Construct a new 138kV transmission line from Leander to Ridgmar (new substation) to Spanish Oak (new substation) to Round Rock (approximately 13 miles) using bundled 795 ACSR Drake (446 MVA) conductor. | Substation name change from Hero Way to Ridgmar and Parmer to Spanish Oak | Leander | Round Rock | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1014352 | 2020-06-24 | 2020-06-04 | 138 | 13 | 0 | 0 |  | Williamson | Williamson | Tier 2 |  | 2013-12-10 | 2014-05-22 | 2014-06-10 | 7367, 7368, 3668, 7525 | Y | N |  |  | 11463 | 3967
13TPIT0106 | Killeen SS to Ding Dong | Rebuild 477 ACSR line with 955 ACSS |  | Killeen SS | Ding Dong | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 11037 | 2020-06-30 |  | 138 | 0 | 5.8 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 115, 117, 136, 3423 | Y | N |  |  | 9901 | 2608
6742 | Heines Sub: New Distribution Station | Add New Heines Sub Distribution Station |  | Airline | Naval Base | In-Service | 877 - 1055 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 3664 | 2020-06-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8490, 8997, 78560 | Y | Y |  |  | 14535 | 6742
44860 | Primera 138 kV Station | New Primera 138 kV Station |  | Harlingen SW | South Santa Rosa | In-Service | 975 - 1153 | AEP TCC | Michael Richardson bcogan@aep.com 918-599-2857 | 3733 | 2020-06-30 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 8638, 8327, 8359 | Y | N |  | 0 | 44861 | 44860
6005 | Airline: Convert 69 kV Station | Upgrade Airline 69 kV station and lines to 138 kV |  | Airline | Naval Base | In-Service | 808 - 0993 | AEP TCC/LCRA | Dave Goetz bcogan@aep.com 918-599-2857 | 3597 | 2020-06-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8487, 8494, 8548, 8560, 8561, 78560, 8490, 8495, 8997, 8562, 8856 | Y | Y |  |  | 13771 | 6005
5430L | Conversion to 138kV | Switch the Hickory - Locust line on to the 138kV substations |  | Hickory | Locust | Planned | N/A | DENTON | Chuck Sears Chuck.Sears@cityofdenton.com 940-349-7111 |  | 2020-07-01 | 2019-07-01 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 914, 910 | Y | N | N/A | 0 | 55206 | 5430
6788 | Tarpley Substation Upgrade | Add two 138 kV Circuit Breakers to Line Terminals to be operated at 69 kV. | Change in schedule | Tarpley |  | Under Construction |  | BANDERA | Tyler Pansing t.pansing@banderaelectric.com 866-226-3372 Ext 6078 | 353985 | 2020-07-01 |  | 69 | 0 | 0 | 0 |  | Bandera |  | Tier 4 |  |  |  |  | 7439, 7440 | Y | N |  |  | 14582 | 6788
3298 | Skyline - Install a Fourth 345kV Autotransformer. | Install one 600 MVA autotransformer at Skyline switchyard. |  |  |  | Planned |  | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | S-0670 | 2020-07-09 |  | 345 | 0 | 0 | 600 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5372, 5371, 5368 | Y | N |  | There are no transmission line additions associated with this project | 10649 | 3298
52098 | Rio Pecos: Replace 138/69 kV Auto | Replace 138/69 kV autotransformer #1 at Rio Pecos with a 90 MVA autotransformer | IN SERVICE | Rio Pecos |  | In-Service | 1068 - 1241 | AEP TNC | Thomas Neils mlforcum@aep.com 918-599-2674 | 2829 | 2020-07-12 | 2020-07-12 | 138 | 0 | 0 | 90 |  | Pecos |  | Tier 4 |  |  |  |  | 6598, 6601 | Y | N |  | 0 | 52099 | 52098
52275 | Bowie Autotransformer replacement | Bowie Autotransformer replacement |  | Bowie | Bowie | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 |  | 2020-07-13 |  | 138 | 0 | 0 | 0 |  | Montague | Montague | Tier 4 |  |  |  |  | 621, 620 | Y |  |  | 0 | 52276 | 52275
5276 | Flatonia - Hallettsville Transmission Line Upgrade | Upgrade T132 Hallettsville to Flatonia (18.7 mi) 138-kV transmission line to a minimum rating of 380 MVA with OPGW. |  | Flatonia | Hallettsville | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1016188 | 2020-08-01 |  | 138 | 0 | 18.7 | 0 |  | Fayette | Lavaca | Tier 4 |  |  |  |  | 7246, 7248 | Y | N |  |  | 12952 | 5276
45508 | Pig Creek: Build 138 kV terminal | Interconnect Taygete I solar farm at the Pig Creek 138 kV station | IN-SERVICE | Pig Creek |  | In-Service | 981 - 1159 | AEP TNC | Dave Baker mlforcum@aep.com 918-599-2674 | 2822 | 2020-08-03 | 2020-08-03 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60393 | Y | N |  | 0 | 45509 | 45508
49562 | Pig Creek: Build 138 kV terminal | Interconnect Taygete II solar farm at the Pig Creek 138 kV station | IN-SERVICE | Pig Creek |  | In-Service | 1020 - 1198 | AEP TNC | David Baker mlforcum@aep.com 918-599-2674 | 2782 | 2020-08-04 02:00 | 2020-08-04 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60393 | Y | N |  | 0 | 49563 | 49562
48533 | BPUB Rio Grande Susbtation | BPUB has updated effective date for Rio Grande Substation. |  |  |  | Planned |  | BPUB | Javier Martinez jamartinez@brownsville-pub.com 956-083-6530 |  | 2020-08-05 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 59550, 59300, 59480 | Y |  |  | Project has been delayed until 7/1/2020. | 52532 | 52531
5964 | Belknap: Build new 69 kV station | Construct new 69 kV ring bus on the Albany to Rainey Creek 69 kV line, remove existing Spillway SW, reterminate Albany to Rainey Creek and Ft Phantom Pump to Onyx lines into Belknap | IN-SERVICE | Belknap |  | In-Service | 843 - 1027 | AEP TNC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | 2684 | 2020-08-20 | 2020-08-20 | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6211, 60409, 6178, 6219, 6220, 6243 | Y | N |  |  | 13679 | 5964
51642 | Figaro to Amadeus: Build new 345 kV line | Interconnect Amadeus wind farm on the Clear Crossing to Dermott 345 kV line | IN-SERVICE | Figaro | Amadeus | In-Service | 907 - 1085 | ETT | Jake Tucker mlforcum@aep.com 918-599-2674 | 2825 | 2020-08-21 | 2020-08-21 | 345 | 0.742 | 0 | 0 |  | Fisher | Fisher | Tier 4 |  |  |  |  | 60715, 182405 | Y | N |  | 0 | 51643 | 51642
6117 | Pleasanton - Coy City Tap 69 kV Line | Rehab Pleasanton - Coy City Tap 69 kV Line |  | Pleasanton | Coy City Tap | In-Service | 814 - 0998 | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | 3604 | 2020-08-30 | 2019-12-13 | 69 | 0 | 16.79 | 0 |  | Atascosa |  | Tier 4 |  |  |  |  | 8200, 8600 | Y | N |  |  | 13843 | 6117
4186C | University Area 138kV Conversions | Convert Blodgett substation from double-tap service to 138kV Ckt.37 loop service. Convert Blodgett TR1 load to 138kV. |  | Blodgett | TECO/Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 | 1123 | 2020-08-30 | 2020-07-23 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47520, 47521, 47522, 42690, 47430, 47660 | Y | N |  | Cost included in 4186A | 57372 | 4186
6114 | La Pryor - Uvalde 69 kV Line | Rehab La Pryor - Uvalde 69 kV Line |  | La Pryor | Uvalde | In-Service | 810 - 0995 | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | 3600 | 2020-08-30 | 2020-03-30 | 69 | 0 | 17.603 | 0 |  | Zavala | Uvalde | Tier 4 |  |  |  |  | 8231, 8672 | Y | N |  |  | 13840 | 6114
6822 | Figaro: Build new 345 kV station | Interconnect Amadeus wind farm on the Clear Crossing to Dermott 345 kV line |  | Figaro |  | In-Service | 907 - 1085 | ETT | Jake Tucker mlforcum@aep.com 918-599-2674 | 2731 | 2020-08-30 | 2020-08-21 | 345 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 60715, 11305, 60704, 60706 | Y | N |  |  | 14623 | 6822
55632 | North Padre Tap to Port Aransas: Replace shield wire | Replace shield wire from North Padre Tap to Port Aransas |  | North Padre Tap | Port Aransas | In-Service | 1101 1279 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3818 | 2020-08-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  | 0 | 55633 | 55632
51968 | Pinnacle Circuit Breaker Addition | Provide transmission service to a generator. Add circuit breakers in a ring-bus configuration to the existing substation.(ERCOT Generation Interconnection or Change Request No. 20INR0032) |  | Pinnacle Substation | Culberson Substation | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2020-09-25 |  | 138 | 0 | 0 | 0 |  | Culberson | Culberson | Tier 4 | [5 empty] | Y | N |  | 0 | 51969 | 51968
5041 | BRYN_5041_Snook_to_Steele_Store | Construct 138kV line from Snook to Steele Store (Bundled 1033 ACSR - Curlew) as part of the reliability project to loop in Steele Store |  | 32857 | 32852 | Planned |  | BRYN |  |  | 2020-09-28 |  | 138 | 9.2 | 0 | 0 |  | Burleson | Brazos | Tier 4 |  | 2015-10-09 | 2015-11-06 |  | 32852, 32857 | Y |  |  | 0 | 53866 | 5041
4575 | BRYN_4575_Steele_Store_138 | Construct Steele Store substation 138kV bus with 138/69kV auto. |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.co 979-821-5763 |  | 2020-09-28 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  | 2015-10-09 | 2015-11-06 |  | 32852, 32866, 32868 | Y |  |  | 0 | 45782 | 4575
50894 | Bonilla: Add new terminal for West Raymond Wind | Bonilla: Add new terminal for West Raymond Wind |  | Bonilla |  | In-Service | 1059 - 1232 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3790 | 2020-09-30 |  | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 88574, 8573 | Y | Y |  | 0 | 50895 | 50894
5218A | San Miguel 345/138 kV autotransformer replacements | Replace T1 300 MVA auto with much larger auto and open T2 for construction |  | San Miguel |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-09-30 | 2020-12-07 | 345 | 0 | 0 | 675 |  | Atascosa |  | Tier 4 |  |  |  |  | 5908, 5909, 5901, 5902 | Y | N |  | Delayed from 2018 to 2019 in the 2016 RTP. | 45090 | 5218
4571 | Atkins Substation Upgrade | Rebuild Atkins 69kV bus |  | 32864 |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.co 979-821-5763 |  | 2020-09-30 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 | [5 empty] | Y |  |  | No MOD Changes Necessary | 12153 | 4571
4883 | McCoy 69 KV substation | Add a new load serving substation between Pleasanton and Tordillo |  | McCoy |  | Under Construction |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-09-30 |  | 69 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  |  | 5721, 5714, 5715 | Y | N |  |  | 12494 | 4883
48748 | Oklaunion: Install 345 kV reactor | Install reactor on the Oklaunion 345 kV bus |  | Oklaunion |  | Planned | 1013 - 1191 | ETT | Dave Goetz mlforcum@aep.com 918-599-2674 | 2774 | 2020-09-30 01:00 |  | 345 | 0 | 0 | 0 | -50,0 | Wilbarger |  | Tier 4 |  |  |  |  | 6100 | Y | N |  | 0 | 48749 | 48748
48802 | Gillet: Build New Distribution Station | Gillet: Build New Distribution Station | IN-SERVICE | Magnolia Tap | Nixon | Planned | 1032 - 1210 | AEP/LCRA | Brandon Cogan bcogan@aep.com 918-599-2857 | 3771 | 2020-10-07 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  |  | 8583 | Y | Y |  | 0 | 48803 | 48802
6348 | Paint Rock to CRMWD Tap #1 69 kV line: Rebuild 69 kV line | Rehab Paint Rock to CRMWD Tap #1 69 kV line | update schedule | Paint Rock | CRMWD Tap #1 | In-Service | 786 - 0971 | AEP TNC | Andrew Garlick mlforcum@aep.com 918-599-2674 | 2709 | 2020-10-07 | 2020-10-07 | 69 | 0 | 6.09 | 0 |  | Concho | Concho | Tier 4 |  |  |  |  | 6369, 6370, 6376 | Y | N |  |  | 14092 | 6348
6718 | Pinnacle Substation Addition | Construct a new substation named Pinnacle off the Culberson to Kunitz transmission line to support a generation interconnection request (19INR0088). Upgrade 8.8 miles of Culberson - Kunitz 138-kV trasnmission line to a minimum 480 MVA rating (Merrimack conductor). |  | Culberson | Kunitz | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2020-10-14 |  | 138 | 0 | 0 | 0 |  | Culberson | Culberson | Tier 4 |  |  |  |  | 7389, 7387, 71097 | Y | N |  |  | 14501 | 6718
5834 | Salt Creek to Cogdell | RPG Project for Salt Creek (Bus# 743) to Clairmont (Bus# 752) to ONCOR's Cogdell (Bus# 1402) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 14032 | 2020-10-15 |  | 138 | 20 | 0 | 0 |  | Kent | Scurry | Tier 2 |  | 2015-12-21 | 2016-06-27 |  | 731, 752, 720, 729, 743, 6198 | Y |  |  |  | 13576 | 5834
6976 | Riverside Circuit Breaker Addition | Add circuit breakers, in a ring bus arrangement, at Riverside Substation. |  | Riverside |  | Planned | 1018925 | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018925 | 2020-10-16 |  | 138 | 0 | 0 | 0 |  | Fayette |  | Tier 4 |  |  |  |  | 7275 | Y | N |  |  | 14793 | 6976
50444 | Adds load to new Escobares Station | LCRA is building the high side and STEC is building the low side of the Escobares station |  | Escobares |  | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-10-16 | 2021-02-28 | 138 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 7870 | Y | N |  | 0 | 50445 | 50444
51960 | LCRATSC T137 Warda Giddings TL ADD | Tear down and rebuild the de-energized 69-kV transmission line between Giddings and Warda substations (T137) with 138-kV class structures capable of supporting bundled Drake conductor and OPGW fiber. |  | Giddings | Warda | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2020-10-16 |  | 138 | 0 | 0 | 0 |  | Lee | Fayette | Tier 4 |  |  |  |  | 7302, 7312 | Y | N |  | 0 | 51961 | 51960
51958 | LCRATSC Lincoln Sub UPG Cap Relocate | Construct a new approximately 0.35 mile 138-kV transmission line from Lincoln Substation to a new point of interconnection at the Enterprise Energy Substation. |  | Lincoln | Enterprise Energy Substation | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2020-10-30 |  | 138 | 0 | 0 | 0 |  | Burleson | Washington | Tier 4 |  |  |  |  | 7302, 7568 | Y | N |  | 0 | 51959 | 51958
50820A | Deepwater 345/138 kV 800 MVA A1 and loop ckt 70 | Install Deepwater 345/138kV 800MVA Autotransformer A1 | Accelerated project schedule | Deepwater |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-10-30 |  | 345 | 0 | 0 | 800 |  | Harris |  | Tier 4 | 19RPG012 | 2019-06-07 | 2019-07-01 |  | 40460, 49054, 40450 | Y | N |  | 0 | 53435 | 50820
50820B | Deepwater 345/138 kV 800 MVA A1 and loop ckt 70 | Re-energize the Deepwater 138kV substation. Loop existing Ckt.70 LYDELL to CHANEL into DPW138 to create new Ckt.70 LYDELL to DPW to CHANEL. | Accelerated project schedule | Deepwater | LYDELL/CHANEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-10-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | 19RPG012 | 2019-06-07 | 2019-07-01 |  | 905588, 905695, 40275, 40460, 40640, 41000, 41009 | Y | N |  | Cost included in Phase A | 53436 | 50820
49566 | Revilla: Construct New 138 kV Station | Revilla: Construct New 138 kV Station |  | Falcon SS | Lopeno | In-Service | 1034 - 1212 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3773 | 2020-10-30 20:00 |  | 138 | 0 | 0 | 0 |  | Starr | Zapata | Tier 4 |  |  |  |  | 8004, 80084, 8957, 80106 | Y | Y |  | 0 | 49567 | 49566
49540 | Avogadro: Build new 345 kV station | Interconnect Griffin Trail wind farm on the Clear Crossing to Edith Clarke 345 kV line |  | Avogadro |  | Planned | 1017 - 1195 | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | 2778 | 2020-10-31 |  | 345 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 60506, 60500, 60700 | Y | N |  | 0 | 49541 | 49540
57352 | Max Zuehlke to Gay Hill T-line structure change | Replace existing structure with upgraded structures on Max Zuehlke to Gay Hill transmission line |  | Max Zuehlke | Gay Hill | Under Construction |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet.coop curtis.fischer@bluebonnet (979) 716-0253 |  | 2020-10-31 |  | 138 | 0 | 9.07 | 0 |  | Washington | Washington | Tier 4 | [5 empty] | Y |  |  | 0 | 57353 | 57352
52565A | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Expand existing HO Clarke substation [47170] to five-breaker ring bus. Connect expanded HO Clarke bus to new customer-owned PRERGY (PRO) substation. |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-10-31 | 2020-10-09 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47170, 111797 | Y | N |  | 0 | 59279 | 52565
52565B | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Reposition existing Ckt.05A HOC to WAP at HOC bus 47170 |  | HO Clarke | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-10-31 | 2020-10-30 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  | Cost included in Ckt.26A relocation | 59280 | 52565
52565C | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Reposition existing Ckt.26A HOC to Karsten from HOC bus 47175 to 47170 |  | HO Clarke | Karsten | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-10-31 | 2020-10-30 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 42041, 47170, 47175 | Y | N |  | 0 | 59281 | 52565
4501 | Trading Post Circuit Breaker Addition | Install Line Breakers at Trading Post on the Trading Post to Marshall Ford and the Trading Post to Cedar Valley 138kV lines (T315). |  | Trading Post |  | Under Construction |  | PEC | Ryan Morlino ryan.morlino@peci.com 830-868-5166 |  | 2020-11-01 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7505 | Y | N |  |  | 12073 | 4501
6044 | Big Lake to Barnhart 69 kV line: Rebuild 69 kV line | Rehab Big Lake to Barnhart 69 kV line | IN-SERVICE | Big Lake | Barnhart | In-Service | 786 - 0971 | AEP TNC | James Weaver mlforcum@aep.com 918-599-2674 | 2672 | 2020-11-11 | 2020-11-11 | 69 | 0 | 17.71 | 0 |  | Reagan | Irion | Tier 4 |  |  |  |  | 6530, 6534 | Y | N |  |  | 13763 | 6044
6079 | Childress to Kirkland 69 kV line: Rebuild 69 kV line | Rehab Childress to Kirkland 69 kV line | IN-SERVICE | Childress | Kirkland | In-Service | 786 - 0971 | AEP TNC | Joseph Page mlforcum@aep.com 918-599-2674 | 2693 | 2020-11-17 | 2020-11-17 | 69 | 0 | 5.61 | 0 |  | Childress | Childress | Tier 4 |  |  |  |  | 6032, 6053 | Y | N |  |  | 13803 | 6079
6083 | Wolfgang: Build 69 kV station | Construct new 69 kV ring bus at Wolfgang | IN-SERVICE | Wolfgang |  | In-Service | 842 - 1026 | AEP TNC | Dewey Peters mlforcum@aep.com 918-599-2674 | 2682 | 2020-11-22 | 2020-11-22 | 69 | 0 | 0 | 0 |  | Kent |  | Tier 4 |  |  |  |  | 6162 | Y | N |  |  | 13807 | 6083
51788 | Amos Creek Circuit Breaker Addition | Provide transmission service to a generator. Add a 345-kV bay and associated circuit breakers to the Amos Creek substation.Cut-in Twin Buttes - Brown 345-kV transmission line to the Amos Creek substation. Associated with GINR # 19INR0121 |  | Amos Creek | Amos Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1021517 | 2020-11-24 |  | 345 | 0 | 0 | 0 |  | Concho | Concho | Tier 4 |  |  |  |  | 1444, 7077, 76009 | Y | N |  | 0 | 51789 | 51788
50902 | Zygon: Build new 138 kV station | Interconnect Kaiser Creek wind farm on the East Abilene to Putnam 138 kV line | CANCELLED | Zygon |  | Planned | 1047 - 1220 | ETT | Eric Blind mlforcum@aep.com 918-599-2674 | 2795 | 2020-11-30 |  | 138 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  |  | 60450, 6275, 6670 | Y | N |  | 0 | 50903 | 50902
44383 | Rio Hondo: Wind Farm Interconnection | Interconnect Las Majadas Wind Farm at Rio Hondo |  | Rio Hondo | Majadas | In-Service | 943 - 1121 | AEP TCC | Kenneth Haley bcogan@aep.com 918-599-2857 | 3707 | 2020-11-30 |  | 345 | 9 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 8318 | Y | N |  | 0 | 44384 | 44383
53971 | Sandstone Mountain System Upgrade | To facilitate closing of normally open switch at Sandstone Mountain Substation. |  | Sandstone Mountain |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1023641 | 2020-11-30 |  | 69 | 0 | 0 | 0 |  | Llano |  | Tier 4 |  |  |  |  | 7116, 7101 | Y | N |  | 0 | 53972 | 53971
4971 | Magic Valley II: Build new four breaker 345 kV station | Interconnect Magic Valley II Windfarm at Magic Valley II to connect Magic Valley II to the Ajo to Rio Hondo 345 kV line and connect the generator's line to the Cebolla station. |  | Cebolla | Ladekidde | In-Service | 731 - 0913 | AEP TCC | William Loveless bcogan@aep.com 918-599-2857 | 3562 | 2020-11-30 11:00 |  | 345 | 0 | 0 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  |  | 8601, 80509, 80512, 80076, 8902, 161753 | Y |  |  |  | 12721 | 4971
5045 | BRYN_5045_Rodgers_Sub | Construct new Rodgers Substation and remove Nall Lane Substation |  |  |  | Planned |  | BRYN |  |  | 2020-12-01 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32849, 32872, 32874, 32877 | Y |  |  | 0 | 57318 | 5045
51953 | LCRATSC KENDALL MOST LIMITING SERIES ELEMENT | Increase the rating of T459 transmission line between Kendall and Cagnon Road substations to a minimum of 3000A at 105 degree F ambient temperature by upgrading the Most Limiting Series Element (MLSE) at Kendall Substation. |  | Kendall | Cagnon | Planned |  | LCRATSC | Dylan Rreas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2020-12-01 |  | 345 | 0 | 0 | 0 |  | Medina | Bexar | Tier 4 |  |  |  |  | 5056, 7046 | Y | N |  | 0 | 51954 | 51953
49817 | 4x20 MVAR Pecos Capacitor Bank | Install 80 MVAR Capacitor Bank at Pecos 138 kV switching station. |  | Pecos (Bus # 38090) | Pecos (Bus # 38090) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2020-12-01 |  | 138 | 0 | 0 | 0 | 0,80 | Reeves | Reeves | Tier 4 |  |  |  |  | 38091 | Y |  |  | 0 | 49818 | 49817
50334 | Rebuild Mccoy to Tordillo | Rebuilds 4/0 ACSR to 795 ACSR on double circuit 138 kV capable poles. NERC assessment and 2019 RTP. |  | McCoy | Tordillo | In-Service |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2020-12-01 | 2020-12-15 | 69 | 0 | 7.9 | 0 |  | Atascosa | Atascosa | Tier 4 |  |  |  |  | 5715, 5721 | Y | N |  | 0 | 50335 | 50334
57052A | Adds Attwater Switching Station for Topaz POI | Attwater Switching Station and rebuild of Heights-Attwater, Attwater-Freeway Park, and TNMP's owner share of Attwater-PH Robinson circuits 1 and 2. |  | Heights, Attwater, Attwater | Attwater, Freeway Park, PH Robinson | In-Service |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2020-12-01 |  | 138 | 0 | 16.21 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38745, 38740, 38820, 42015 | Y |  |  | 0 | 57230 | 57052
3277 | Shepherd Road - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Valley line. |  | Shepherd Road | Cagnon-Valley | Planned | S-0774 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 | T-0236 | 2020-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5378, 5053, 5465 | Y | N |  | There are no transformers associated with this project | 10628 | 3277
54255 | Rebuild Rio Pecos-Lynx Ckt 2 (1926 ACSS) | Rebuild AEP Rio Pecos to TNMP Woodward Tap 138kV line and re-terminate Woodward Tap end over to AEP Lynx. |  | AEP Rio Pecos (Bus # 6601) | AEP Lynx (Bus # 60400) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 | NTE08314 & NTE08414 | 2020-12-01 |  | 138 | 0.72 | 1.98 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 6601, 38310, 60400 | Y |  |  | 0 | 54256 | 54255
4504 | BRYN_4504_Rayburn_Rodgers_Upgrade | Reconductor Rayburn to Rodgers with 1033ACSR |  | 32861 | 32849 | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.co 979-821-5763 |  | 2020-12-01 |  | 69 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32861, 32849, 32872 | Y |  |  | 0 | 57319 | 4504
45023 | Pershing: Build 138 kV station | Construct new 138 kV box bay on the Abilene Northwest to Oak Creek 138 kV line | IN-SERVICE | Pershing |  | In-Service | 979 - 1157 | AEP TNC | Michael Glueck mlforcum@aep.com 918-599-2674 | 2764 | 2020-12-02 01:00 | 2020-12-02 | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 60724, 6229, 6335 | Y | N |  | 0 | 45024 | 45023
57173 | TNMP Soaptree Switching Station | NOMCR IDs: 64303-1 & 64608-1 |  | Rio Pecos (6601), Lynx (60400) & 16th Street (38310) | Soaptree (38450) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2020-12-03 |  | 138 | 0.76 | 1.93 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38450, 6601, 38310, 60400 | Y |  |  | 0 | 57174 | 57173
6349 | CRMWD Tap #1 to Eden 69 kV line: Rebuild 69 kV line | Rehab CRMWD Tap #1 to Eden 69 kV line | IN-SERVICE | CRMWD Tap #1 | Eden | In-Service | 786 - 0971 | AEP TNC | Brian Oyster mlforcum@aep.com 918-599-2674 | 2710 | 2020-12-03 | 2020-12-03 | 69 | 0 | 13.6 | 0 |  | Concho | Concho | Tier 4 |  |  |  |  | 6372, 6376 | Y | N |  |  | 14093 | 6349
45503 | Lynx: Expand 138 kV station | Terminate the TNMP 16th Street to Rio Pecos 138 kV line into Lynx station | IN-SERVICE | Lynx |  | In-Service | 983 - 1161 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2770 | 2020-12-08 | 2020-12-08 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 38330, 6601, 38310, 60400, 130533 | Y | N |  | 0 | 49830 | 45503
51216B | Ward Winkler RPG | Re-terminate existing IH20-Pecos 69kV line to 138kV buses. |  | TNMP IH20 (38040 / 38045) | TNMP Pecos (38090 /38091) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2020-12-11 |  | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 38045, 38091 | Y |  |  | 0 | 56657 | 51216
45346 | Trade Zone: Build 138 kV Station | Trade Zone: Build 138 kV Station on South McAllen - Stewart Road Line |  | South McAllen | Las Milpas | In-Service | 886 - 1064 | AEP TCC | Todd Siegert bcogan@aep.com 918-599-2857 | 3673 | 2020-12-12 |  | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8644, 8371, 8758 | Y | N |  | 0 | 45347 | 45346
4825 | Crockett - Jewett 138kV Line | Upgrade existing line | Project Deferral | Crockett | Jewett | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6061 | 2020-12-15 |  | 138 | 0 | 39.5 | 0 |  | Houston | Leon | Tier 3 | 17RPG014 | 2017-09-11 | 2017-12-04 | 2017-12-04 | 3354, 3355, 3357, 3358, 13354, 3345, 3394 | Y | N |  |  | 12432 | 4825
6790 | Sargent Road-East Network 138 kV Line | Construct the new Sargent Road-East Network 138 kV Line | Project Deferral | Sargent Road | Oakland | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4268 | 2020-12-15 |  | 138 | 2.5 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2905, 2949, 2969, 2970, 2971, 12447 | Y | N |  |  | 14588 | 6790
45471 | Lake Creek - Waco East 138 kV Line | Upgrade the Lake Creek Switch - Waco East Switch 138 kV Line to 2071A |  | Lake Creek | Waco East | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R470 | 2020-12-15 |  | 138 | 0 | 9.8 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3410, 3438, 3452 | Y | N |  | 0 | 45472 | 45471
7119 | Sand Lake 345 kV Sw. Sta. | Sand Lake 345 kV Sw. Sta. |  | Sand Lake | Sand Lake | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8420 | 2020-12-15 |  | 345 | 0 | 0 | 1400 |  | Ward | Ward | Tier 1 |  | 2018-02-02 | 2018-05-22 |  | 11098, 11099, 11109, 11097 | Y |  |  |  | 14955 | 7119
7104 | Owl Hills - Tunstill POD 138 kV Line | Owl Hills - Tunstill POD 138 kV Line |  | Owl Hills | Tunstill | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8428 | 2020-12-15 |  | 138 | 12 | 0 | 0 |  | Culberson | Reeves | Tier 1 |  | 2018-02-02 | 2018-05-22 |  | 11090, 11183 | Y |  |  |  | 14938 | 7104
5974 | Saginaw - Denton Ave/Springdale 138 kV DCKT Line | Rebuild existing 69 kV Lines | Construction schedule change | SAGINAW | DENTON AVE | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5245 | 2020-12-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1957, 2101, 2146, 2157, 11966 | Y | N |  |  | 13689 | 5974
45498 | Shipwreck Substation - Midkiff Switch 138 kV Line | Construct Shipwreck Substation to Midkiff Switch 138 kV Line |  | Shipwreck Substation | Midkiff Switch | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8462 | 2020-12-15 |  | 138 | 0 | 10.3 | 0 |  | Glasscock | Reagan | Tier 4 |  |  |  |  | 1210, 1211, 1213, 1217, 1219, 11218 | Y |  |  | 0 | 45500 | 45498
5440 | Riverton 345 kV Switching Station | Construct new 345 kV switching station |  | Riverton | Riverton | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8351 | 2020-12-15 |  | 345 | 0 | 0 | 1400 |  | Reeves | Reeves | Tier 1 |  | 2016-04-20 | 2017-05-23 | 2017-06-13 | 11075, 11084, 11085, 11083 | Y | N |  |  | 13143 | 5440
52311 | Add Gardendale 345 kV Switch | Add Gardendale 345 kV Switch for 2W Permian Solar |  | Clearfork | Telephone Road | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8506 | 2020-12-15 |  | 345 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 4 |  |  |  |  | 11157, 23873, 23876 | Y |  |  | 0 | 52313 | 52311
5312 | Mitchell Bend - Rocky Creek 345 kV line | Upgrade existing line | Project Deferral | Mitchell Bend | Rocky Creek | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R1736 | 2020-12-15 |  | 345 | 0 | 32.8 | 0 |  | Hood | Tarrant | Tier 3 |  |  | 2016-07-22 | 2016-08-22 | 1877, 1880 | Y |  |  |  | 12988 | 5312
6302 | Black Fork-Tyler West 69 kV to 138 kV Line Conversion | Rebuild existing 69 kV line and convert to 138 kV operation |  | Black Fork | Tyler West | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R6071 | 2020-12-15 |  | 138 | 0 | 4.9 | 0 |  | Smith | Smith | Tier 4 |  |  |  |  | 3121, 3132, 3138, 3140, 3142, 3198, 3207, 3139, 3197, 13235, 3141 | Y |  |  | 0 | 56108 | 6302
58063 | Construct Cedar Elm 345 kV Switch | Construct Cedar Elm 345 kV Switch to Interconnect Wildwind |  | Cedar Elm |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5313 | 2020-12-15 01:00 |  | 345 | 0 | 0 | 0 |  | Cooke |  | Tier 4 |  |  |  |  | 11735, 1730, 2373 | Y | N |  | 0 | 58064 | 58063
14TPIT0057 | Cedar Hill Switch - Liggett 138 kV line | Upgrade Cedar Hill Switch - Dalworth existing line section |  | Cedar HIll Switch | Dalworth | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5041-E | 2020-12-15 02:02 |  | 138 | 0 | 8.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 1912, 1922, 2265, 2270, 2271, 2274, 2422 | Y | N |  |  | 10276 | 2926
6269 | Ennis Creek 138 kV Switching Station | Rebuild existing Ennis Creek 138 kV Switching Station | Project Deferral | Ennis Creek | Ennis Creek | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9026 | 2020-12-15 22:00 |  | 138 | 0 | 0 | 0 |  | Scurry |  | Tier 4 |  | 2015-12-21 | 2016-10-11 |  | 1410 | Y | N |  |  | 13999 | 6269
5445 | Riverton-Odessa EHV/Moss 345 kV Line | Riverton-Odessa EHV/Moss 345 kV Line |  | Riverton | Odessa EHV | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8356 | 2020-12-16 |  | 345 | 186 | 16 | 0 |  | Reeves | Ector | Tier 1 |  | 2016-04-20 | 2017-05-23 | 2017-06-13 | 1018, 11010, 11028, 11084 | Y |  |  | 0 | 51212 | 5445
7121 | Sand Lake Sw. Sta. - Solstice 345 kV Line | Sand Lake Sw. Sta. - Solstice 345 kV Line |  | Sand Lake | Solstice | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8380 | 2020-12-16 |  | 345 | 80 | 0 | 0 |  | Ward | Ward | Tier 1 |  | 2018-02-02 | 2018-05-22 |  | 11098, 60404 | Y |  |  |  | 14957 | 7121
7120 | Riverton Sw. Sta. - Sand Lake Sw. Sta. 345 kV Line | Riverton Sw. Sta. - Sand Lake Sw. Sta. 345 kV Line |  | Riverton | Sand Lake | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8443 | 2020-12-16 |  | 345 | 26 | 0 | 0 |  | Reeves | Ward | Tier 1 |  | 2018-02-02 | 2018-05-22 |  | 11084, 11098 | Y |  |  |  | 14956 | 7120
52825 | Woodard 345 kV Switch | Establish Woodard 345 kV Switch |  | Woodard |  | In-Service |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5291 | 2020-12-16 |  | 345 | 0 | 0 | 0 |  | Lamar |  | Tier 4 |  |  |  |  | 11699, 1692, 1695, 143062 | Y |  |  | 0 | 52826 | 52825
52636 | Solanum: Build 138 kV temporary tap | Construct new 138 kV temporary hard tap on the Abilene South to Putnam 138 kV line | update schedule | Solanum |  | In-Service | 1073 - 1246 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 2834 | 2020-12-17 | 2020-12-17 | 138 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  |  | 61015, 6309, 60365 | Y | N |  | 0 | 52637 | 52636
7116 | Riverton Sw. Sta.- Kyle Ranch 138 kV Line | Riverton Sw. Sta.- Kyle Ranch 138 kV Line |  | Riverton | Kyle Ranch | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R8427 | 2020-12-18 |  | 138 | 15 | 0 | 0 |  | Reeves | Loving | Tier 2 |  | 2018-02-02 | 2018-05-22 |  | 11089, 11083 | Y |  |  |  | 14952 | 7116
48407 | Chaparrosa: Construct New 69 kV Box Bay | Chaparrosa: Construct New 69 kV Box Bay |  | Chaparrosa |  | Planned | 929 - 1107 | AEP TCC | James Nivens bcogan@aep.com 918-599-2857 | 3705 | 2020-12-18 |  | 69 | 0 | 0 | 0 |  | Zavala |  | Tier 4 |  |  |  |  | 8284, 88284, 8243, 8672, 7867 | Y | N |  | 0 | 48408 | 48407
6594 | Solstice: Add 345 kV reactor | Construct new 345 kV station with two 345/138 kV autotransformers, reactor, and build new 345 kV line from Solstice to Bakersfield | IN-SERVICE | Solstice |  | In-Service | 789 - 0974 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2729 | 2020-12-19 | 2020-12-19 | 345 | 0 | 0 | 0 | -50,0 | Pecos |  | Tier 1 |  | 2016-04-01 | 2017-05-01 | 2017-06-01 | 60404 | Y | N |  |  | 14356 | 6594
5539 | Solstice to Bakersfield: Build 345 kV line | Construct new 345 kV station with two 345/138 kV autotransformers, reactor, and build two new 345 kV lines from Solstice to Bakersfield | IN-SERVICE | Solstice | Bakersfield | In-Service | 789 - 0974 | AEP TNC/LCRATSC | Brent Harris mlforcum@aep.com 918-599-2674 | 2651 | 2020-12-19 | 2020-12-19 | 345 | 136 | 0 | 0 |  | Pecos | Pecos | Tier 1 |  | 2016-04-01 | 2017-05-23 | 2017-06-21 | 60404, 76002 | Y | Y |  |  | 13267 | 5539
45575 | Solstice: Add second 345 kV reactor | Add a second 345 kV reactor at Solstice | IN-SERVICE | Solstice |  | In-Service | 997 - 1175 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2771 | 2020-12-19 | 2020-12-19 | 345 | 0 | 0 | 0 | -50,0 | Pecos |  | Tier 4 |  |  |  |  | 60404 | Y | N |  | 0 | 45576 | 45575
50864 | Cenizo - Del Sol: Install Double CKT to Reloj del Sol | Cenizo - Del Sol: Install Double CKT to Reloj del Sol to connect generator into Cenizo |  | Cenizo | Reloj POI | Planned | 1051 - 1224 | ETT | Adam Wells bcogan@aep.com 918-599-2857 | 3777 | 2020-12-21 |  | 345 | 0 | 21 | 0 |  | Webb | Zapata | Tier 4 |  |  |  |  | 80226, 80220, 162491 | Y | Y |  | 0 | 50865 | 50864
4554 | Ennis Creek - Cogdell 69 kV Line | Convert existing line to 138 kV operation |  | Ennis Creek | Cogdell | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R9025 | 2020-12-23 |  | 138 | 0 | 8.6 | 0 |  | Scurry | Scurry | Tier 3 |  | 2015-12-21 | 2016-10-11 |  | 1400, 1401, 1402, 1411, 1412, 11402, 752, 1410 | Y |  |  | 0 | 49764 | 4554
44818A | Fort Bend to West Columbia 138kV Conversion | Remove Fort Bend 138/69kV Auto A1 from CNP service |  | Ft Bend | Ft Bend | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-29 | 2020-10-26 | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 18RPG011 | 2018-10-30 | 2018-11-26 |  | 44290, 49014, 44280 | Y |  |  | 0 | 52190 | 44818
5530 | Solstice: Build 345 kV station | Construct new 345 kV station with two 345/138 kV autotransformers, reactor, and build new 345 kV line from Solstice to Bakersfield | IN-SERVICE | Solstice |  | In-Service | 789 - 0974 | AEP TNC | Brent Harris mlforcum@aep.com 918-599-2674 | 2649 | 2020-12-29 | 2020-12-29 | 345 | 0 | 0 | 1486 |  | Pecos |  | Tier 1 |  | 2016-04-01 | 2017-05-23 | 2017-06-21 | 60402, 60404, 60418, 60385 | Y | Y |  |  | 13257 | 5530
43456A | Greens Bayou 138kV Reconfigurations | Connect Greens Bayou 'East' and 'West' buses with (1) 8-Ohm Reactor. |  | Greens Bayou | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-29 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40710, 40715 | Y | N |  | 0 | 50813 | 43456
44818B | Fort Bend to West Columbia 138kV Conversion | Convert existing 69kV Ckt.45 Fort Bend to Big Creek to 138kV service as Ckt.89. Convert Big Creek substation from tap to loop service. |  | Ft Bend | Big Creek | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-29 00:01 | 2020-10-26 | 138 | 7.4 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 18RPG011 | 2018-10-30 | 2018-11-26 |  | 42390, 44070, 44280, 44290 | Y |  |  | Cost Included in 44818A | 52192 | 44818
44818C | Fort Bend to West Columbia 138kV Conversion | Convert existing 69kV Ckt.45 Big Creek to Needville to 138kV service as Ckt.89. Convert Big Creek substation from tap to loop service. |  | Big Creek | Needville | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-29 00:02 | 2020-10-26 | 138 | 8.2 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 18RPG011 | 2018-10-30 | 2018-11-26 |  | 42380, 43000, 44070, 42390 | Y |  |  | Cost Included in 44818A | 52191 | 44818
44818D | Fort Bend to West Columbia 138kV Conversion | Convert existing 69kV Ckt.45 Needville to Damon to 138kV service as Ckt.89 |  | Needville | Damon | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-29 00:03 | 2020-10-26 | 138 | 10.8 | 0 | 0 |  | Fort Bend | Brazoria | Tier 3 | 18RPG011 | 2018-10-30 | 2018-11-26 |  | 42340, 42370, 43000, 42380 | Y |  |  | Cost Included in 44818A | 52195 | 44818
44818E | Fort Bend to West Columbia 138kV Conversion | Convert existing 69kV Ckt.45 Damon to West Columbia to 138kV service as Ckt.89 |  | Damon | West Columbia | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-29 00:04 | 2020-10-26 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 18RPG011 | 2018-10-30 | 2018-11-26 |  | 43384, 42370, 42410, 43380, 43390, 44010, 42340, 42980 | Y |  |  | Cost Included in 44818A | 52193 | 44818
44818F | Fort Bend to West Columbia 138kV Conversion | Remove West Columbia 138/69kV Auto A2 from CNP service |  | West Columbia | West Columbia | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-29 00:05 | 2020-10-26 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 18RPG011 | 2018-10-30 | 2018-11-26 |  | 43390, 49034, 43380 | Y |  |  | Cost Included in 44818A | 52194 | 44818
44818H | Fort Bend to West Columbia 138kV Conversion | Remove 7.2 MVAR cap bank from West Columbia Auto A2 tertiary bus |  | West Columbia | West Columbia | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-29 00:07 | 2020-10-26 | 69 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 18RPG011 | 2018-10-30 | 2018-11-26 |  | 49034 | Y |  |  | Cost Included in 44818A | 52189 | 44818
50904B | Install two 14.4 MVAR cap banks at Village Creek substation | Cap Bank #2: Install one 14.4 MVAR cap bank at Village Creek substation |  | Village Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-30 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris | Harris | Tier 4 |  |  |  |  | 44270 | Y | N |  | Cost included in 50904A | 50906 | 50904
6202 | North Ella - Premont 69 kV Line | Rehab North Ella - Premont 69 kV Line |  | North Ella | Premont | Planned | 818 - 1002 | AEP TCC | Joe Yeagler bcogan@aep.com 918-599-2857 | 3615 | 2020-12-30 |  | 69 | 0 | 10.7 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 8878, 8894 | Y | N |  |  | 13927 | 6202
50904A | Install two 14.4 MVAR cap banks at Village Creek substation | Cap Bank #1: Install one 14.4 MVAR cap bank at Village Creek substation |  | Village Creek |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-30 |  | 138 | 0 | 0 | 0 | 0,14.4 | Harris | Harris | Tier 4 |  |  |  |  | 44270 | Y | N |  | 0 | 50905 | 50904
44940 | Henne and TXI Switch Upgrades/Replacement | Replace and increase fault interrupting rating of breaker 5870 to 63kA, and its continuous rating to 3,000 Amp. Replace CS 5395 and CS 5405 to 40kA units. |  | Henne | TXI | Planned |  | NBU | Gregory Thomas gthomas@nbutexas.com 830-608-8953 |  | 2020-12-30 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7174 | Y | N |  | 0 | 44941 | 44940
43456B | Greens Bayou 138kV Reconfigurations | Reposition Ckt.94A (GBY to Humble) to connect to GBY 'West' bus |  | Greens Bayou | Humble | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40710, 40715, 41222 | Y |  |  | Cost Included in 43456A | 50814 | 43456
48830 | Pavlov: Construct New 138 kV Station | Pavlov: Construct New 138 kV Station |  | Blessing | Lane City | Planned | 995 - 1173 | AEP TCC | James Ball bcogan@aep.com 918-599-2857 | 3748 | 2020-12-31 |  | 138 | 0 | 0 | 0 |  | Matagorda | Wharton | Tier 4 |  |  |  |  | 8608, 8614, 8121, 8127 | Y | N |  | 0 | 48831 | 48830
5500 | Lamar Blossom - Paris East Tap 138 kV Line | Construct new 138 kV line and ring bus | Project Deferral | Lamar Blossom | Paris East Tap | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R4103 | 2020-12-31 |  | 138 | 10 | 0 | 0 |  | Lamar | Lamar | Tier 4 |  |  |  |  | 1769, 1770, 1771 | Y | N |  |  | 13240 | 5500
6112 | Causeway - Sunchase 138 kV Line | Rehab Causeway - Sunchase 138 kV Line |  | Causeway | Sunchase | Planned | 826 - 1010 | AEP TCC | Kenneth Haley bcogan@aep.com 918-599-2857 | 3627 | 2020-12-31 |  | 138 | 0 | 3.56 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8744, 8917 | Y | N |  |  | 13838 | 6112
5835 | Rebuild Sardis to Reagor Springs | Rebuild Sardis (Bus #202) to Reagor Springs (Bus #210) |  |  |  | Planned |  | BEPC | Dwight Beckman dbeckman@brazoselectric.com 254-750-6373 | 16027 | 2020-12-31 |  | 69 | 0 | 15.46 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 202, 210 | Y |  |  |  | 13577 | 5835
52565E | PRERGY (PRO) - Generator at HO Clarke Substation (20INR0206) | Remove HOC cap bank CB2 from Ckt.90A |  | HO Clarke |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-31 | 2020-12-03 | 138 | 0 | 0 | 0 | -100,0 | Harris |  | Tier 4 |  |  |  |  | 47155, 47151, 47175 | Y | N |  | Cost included in main entry | 59283 | 52565
54755 | This is related to GINR19INR0081 | This is a switching station to interconnect new generation project 19INR0081 Anson Solar Project. |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2020-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68004, 68000, 68001 | Y |  |  | 0 | 54756 | 54755
56109 | McDonough Substation Removal | Remove 69kV McDonough substation from CNP service |  | McDonough |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-31 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 41040, 40352, 40800 | Y | N |  | 0 | 56110 | 56109
52365A | Spillman Island Restoration Plan | Upgrade Relays at STRANG substation on STRANG to Cedar Bayou Ckt.87A (Future Option 3 to reconfigure as Ckt.xx STRANG to SYLVAN to BAYOU). |  | STRANG | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Chambers | Tier 4 | [5 empty] | Y | N |  | 0 | 52366 | 52365
43456C | Greens Bayou 138kV Reconfigurations | Reposition Ckt.95C (GBY to Glenwood) to connect to GBY 'West' bus |  | Greens Bayou | Glenwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40260, 40352, 40420, 40475, 40611, 40620, 40700, 40710, 40715, 40725, 40830, 40900, 40911, 40720, 40831, 40912, 41221, 41222, 41570, 41651, 41681, 41712, 46290, 49018 | Y |  |  | Cost Included in 43456A | 50815 | 43456
51216A | Ward Winkler RPG | Conversion of TNMP Wink to Pecos 138kV. |  | TNMP Wink (37920 / 37900) | TNMP Pecos (38090) | Planned |  | TNMP | Robert Lona Robert.Lona@tnmp.com 281-581-4732 |  | 2020-12-31 |  | 138 | 1.01 | 0 | 0 |  | Winkler | Reeves | Tier 2 |  | 2019-03-19 | 2019-10-10 |  | 38040, 38090, 38091, 38135, 38136, 38137, 38140, 38141, 38142, 38145, 38150, 38151, 38152, 38160, 38165, 38166, 38167, 38170, 38175, 38180, 38190, 38195, 38200, 38210, 38211, 38212, 38230, 38231, 38232, 37900, 37920, 38049, 38114, 38045 | Y |  |  | 0 | 56656 | 51216
57422 | Brown Substation Removal | Remove 69kV Brown substation from CNP service |  | Brown |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-31 |  | 69 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47550, 47540, 47670 | Y | N |  | 0 | 57423 | 57422
7007 | CNP_18TPIT7007_WAP_Reactor_Upgrades | Install (2) 5-Ohm Reactors at WA Parish as a fault duty upgrade |  | WAP | WAP | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-31 | 2020-03-18 | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44010, 44015, 44170, 44173, 44651, 44671, 44172, 110013, 110014 | Y |  |  | 0 | 51161 | 7007
52365C | Spillman Island Restoration Plan | Upgrade Relays at Morgans Point substation on Morgans Point to BAYOU Ckt.79B (Future Option 3 to reconfigure as Ckt.xx Morgans Point to CHORIN). |  | Morgans Point | BAYOU | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | Cost included in Phase A. | 52368 | 52365
52365B | Spillman Island Restoration Plan | Upgrade Relays at BAYOU substation on BAYOU to Morgans Point Ckt.79B (Future Option 3 to reconfigure as Ckt.xx STRANG to SYLVAN to BAYOU) |  | BAYOU | Morgans Point | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | Cost included in Phase A. | 52367 | 52365
52365G | Spillman Island Restoration Plan | Upgrade Relays at Cedar Bayou substation on Cedar Bayou to STRANG Ckt.87A. |  | Cedar Bayou | STRANG | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2020-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | Cost included in phaseA. | 52373 | 52365
59263 | Oncor_MW_XXX_WeatherfordSw-Azle_138kVLine | Upgrade existing 138 kV Line |  | Weatherford | Azle | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5172 | 2021-01-19 |  | 138 | 0 | 11.5 | 0 |  | Parker | Tarrant | Tier 4 |  |  |  |  | 1592, 2062, 15015 | Y |  |  | 0 | 59524 | 59263
59765 | ONCOR_MN_Loy Lake 138 kV Capacitors | Install new 138 kV Capacitors | [5 empty] | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | R989 | 2021-01-19 |  | 138 | 0 | 0 | 0 | 0,55.2 | Grayson |  | Tier 4 |  |  |  |  | 1834, 1745, 1746 | Y |  |  | 0 | 59770 | 59765
45340 | Lemay: Build 138 kV Box Bay | Lemay: Build 138 kV Box Bay on North Laredo SS - Reveille Line |  | Lemay |  | Planned | 988 - 1166 | AEP TCC | William Lovelace bcogan@aep.com 918-599-2857 | 3739 | 2021-01-26 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  |  | 8627, 88627, 8612, 8619 | Y | N |  | 0 | 45341 | 45340
3877 | Meadow Lake Substation Addtion | Add a new load serving substation (ring-bus) at Meadow Lake. The station will be built between Cushman and Highway 123 off T572. | Customer Schedule Change | Cushman | Highway 123 | In-Service |  | LCRATSC/GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1016198 | 2021-01-28 | 2020-12-18 | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7720, 7221, 7226 | Y | N |  |  | 12940 | 3877
50450 | LCRATSC_Escobares Substation Addition | Construct a new 138-kV Escobares substation.The Escobares substation will be located approximately 2 miles east of Roma (AEP) Substation and approximately 3.5 miles west of Garceno (AEP) Substation. |  | Escobares | Escobares | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2021-01-28 |  | 138 | 0 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  |  | 7870, 8796, 8923 | Y | N |  | 0 | 50451 | 50450
6167 | Harlingen SS - Raymondville #2: Convert to 138 kV | Harlingen SS - Raymondville #2: Convert to 138 kV |  | Harlingen SS | Raymondville #2 | Planned | 864 - 1042 | AEP TCC | Eric Scott bcogan@aep.com 918-599-2857 | 3650 | 2021-01-28 |  | 138 | 0 | 0 | 0 |  | Cameron | Willacy | Tier 4 |  |  |  |  | 8300, 8700, 80436, 8302, 8325, 8327 | Y | N |  |  | 13892 | 6167
6753 | Quihi: Build 138kV Station | Build new Quihi 138kV In and Out Station on Razorback to Castroville 138kV Line |  | Quihi |  | Planned | 900 -1078 | ETT/STEC | James Weaver bcogan@aep.com 918-599-2857 | 3684 | 2021-01-31 |  | 138 | 0.8 | 0 | 0 |  | Medina |  | Tier 4 |  |  |  |  | 8248, 88248, 5083, 8241 | Y | Y |  |  | 14546 | 6753
6780 | Deen 138 kV Switching Station | Rebuild existing Saginaw 138 kV Switching Station |  | Deen |  | Under Construction |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5277 | 2021-01-31 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 1957, 2074, 2043, 2047, 2048, 2049, 2067, 2070, 2071, 2077, 2146, 2157 | Y |  |  | 0 | 57900 | 6780

## CancelledTPIT020121NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2021
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number
6288 | Watermill - Trinidad 345 kV Line | Install a breaker at Watermill Sw. on the Watermill - Trinidad 345 kV Line to establish double-breaker configuration |  | Watermill | Trinidad | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4249 | 2021-05-15 |  | 345 | 0 | 0 | 0 |  | Dallas | Henderson | Tier 3 |  |  |  |  | 2996, 2427, 2428, 2432 | N |  |  |  | 14017 | 6288
50876 | Port Lavaca - Victoria: Line Rebuild | Port Lavaca - Victoria: Line Rebuild |  | Port Lavaca | Victoria | Planned | 1054 - 1227 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3782 | 2021-11-30 |  | 69 | 0 | 29 | 0 |  | Calhoun | Victoria | Tier 3 |  |  |  |  | 8135, 8136, 8169 | N | N |  | 0 | 50877 | 50876
4875 | Red Gate: Build new 138 kV line | Interconnect STEC Red Gate Power Plant at Permanent with a new 138 kV line into North Edinburg |  | Falfurrias | North Edinburg | Planned | 724 - 0906 | AEP TCC | Teresa Trotman dnlyons@aep.com 918-599-2698 | 3558 | 2021-12-01 12:00 |  | 138 | 7.5 | 7.5 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 88380, 8380, 8896, 83809, 161031 | N | Y |  |  | 12486 | 4875
5490 | Liggett - North Irving138 kV DCKT Line | Upgrade existing Liggett - North Irving138 KV Double Ckt Line |  | Liggett | Hackberry | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4222 | 2021-12-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 11923, 11925, 1922, 1924, 2001, 2002, 15002, 15020, 15021, 2010, 15025, 15026, 15045 | N | N |  | 0 | 45577 | 5490
5490 | Liggett - North Irving138 kV DCKT Line | Upgrade existing Liggett - North Irving138 KV Double Ckt Line |  | Liggett | Hackberry | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4222 | 2021-12-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 11923, 11925, 1922, 1924, 2001, 2002, 15002, 15020, 15021, 2010, 15025, 15026, 15045 | N | N |  | 0 | 52266 | 5490
5490 | Liggett - North Irving138 kV DCKT Line | Upgrade existing Liggett - North Irving138 KV Double Ckt Line |  | Liggett | Hackberry | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4222 | 2021-12-15 |  | 138 | 0 | 11.8 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 2001, 11923, 11925, 12002, 15022, 15023, 1922, 1924, 2002, 2010, 15002, 15020, 15021, 15025, 15026, 15045 | N | N |  | 0 | 52807 | 5490
50989 | Blessing - El Campo: Line Rebuild | Blessing - El Campo: Line Rebuild |  | Blessing | El Campo | Planned | 1060 - 1233 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3791 | 2022-01-31 |  | 69 | 0 | 27.23 | 0 |  | Matagorda | Wharton | Tier 3 |  |  |  |  | 8100, 8119, 8552, 8556 | N | Y |  | 0 | 50990 | 50989
52293 | Hackberry - North Irving138 kV DCKT Line | Upgrade the Hackberry - North Irving |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4291 | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 1996, 1997, 2010, 2388, 15045, 15046, 2001, 15020 | N |  |  | 0 | 52294 | 52293
52293 | Hackberry - North Irving138 kV DCKT Line | Upgrade the Hackberry - North Irving |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4291 | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 1996, 1997, 2001, 2010, 15020, 15023, 2388, 15022, 15045, 15046 | N |  |  | 0 | 52809 | 52293
52293 | Hackberry - North Irving138 kV DCKT Line | Upgrade the Hackberry - North Irving |  |  |  | Planned |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4291 | 2022-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 1996, 1997, 2010, 15023, 2388, 15022, 15045, 15046 | N |  |  | 0 | 52810 | 52293
50888 | El Campo - Ganado: Line Rebuild | Rebuild El Campo to Victoria 138 kV line |  | El Campo | Ganado | Planned | 1062 - 1235 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3794 | 2022-11-30 |  | 138 | 0 | 20.02 | 0 |  | Wharton | Jackson | Tier 3 |  |  |  |  | 8102, 8117, 88099 | N | N |  | 0 | 50889 | 50888
50884 | Ganado - Edna: Line Rebuild | El Campo - Victoria: Line Rebuild |  | Ganado | Edna | Planned | 1062 - 1235 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3795 | 2022-11-30 |  | 138 | 0 | 9.72 | 0 |  | Jackson | Jackson | Tier 3 |  |  |  |  | 8117, 8118 | N | N |  | 0 | 50885 | 50884
50886 | Edna - Victoria: Rebuild 138 kV line | Rebuild El Campo to Victoria 138 kV line |  | Edna | Victoria | Planned | 1062 - 1235 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3796 | 2022-11-30 |  | 138 | 0 | 21.57 | 0 |  | Jackson | Victoria | Tier 3 |  |  |  |  | 8118, 8172 | N | N |  | 0 | 50887 | 50886
6282 | Everman - Benbrook 345 kv line | Upgrade the existing 345 kV Line |  | Everman | Benbrook | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M5273 | 2023-05-15 |  | 345 |  | 29 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1870, 1886, 1935 | N |  |  |  | 14014 | 6282
6291 | Royse Sw. Sta. - Farmersville Sw. Sta. 345 kV DCKT Line | Rebuild existing 345 kV Line |  | Royse | Farmersville | Conceptual |  | ONCOR | Charles Saker charles.saker@oncor.com 214-743-6896 | M4255 | 2023-05-15 |  | 345 | 0 | 30.4 | 0 |  | Rockwall | Collin | Tier 3 |  |  |  |  | 1685, 2461, 2478 | N |  |  |  | 14020 | 6291
50890 | Port Lavaca: Station Rebuild | Port Lavaca: Station Rebuild |  | Port Lavaca |  | Planned | 1057 - 1230 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3787 | 2023-05-30 |  | 69 | 0 | 37.81 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | 8135 | N | N |  | 0 | 50891 | 50890
3901 | Lobo to Freer: Rebuild 69 kV line | Rebuild Lobo to Freer 69 kV line with 795 ACSS | Description Update | Lobo | Freer | Planned | 677 - 0846 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 2596 | 2024-06-30 |  | 69 | 0 | 49.8 | 0 |  | Webb | Duval | Tier 3 |  |  |  |  | 8505, 80222 | N | N |  |  | 11371 | 3901
44419 | Load serving |  |  | Mayhill | Denton Steam/Brinker | Planned |  | DENTON | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2024-07-01 | 2024-07-01 | 138 | 5.1 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 929, 982 | N | N |  | 0 | 44420 | 44419
3276 | JT Deely to Martinez MLSE Upgrade | Upgrade terminal at JT Deely to ensure a rating of 2386 A (minimum). |  | JT Deely | Martinez | Planned | S-0759 | CPS | Basilio Rocha bdrocha@cpsenergy.com 210-353-4933 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5110, 5294 | N | N |  | There are no transformers associated with this project | 10627 | 3276
50282 | Adds new Jaguar sub near Twin Pines Switch | Adds new Jaguar sub between Twin Pines Switch and Highlands Sub. For AEP load. | AEP is looking at another location to serve the load. | Highlands Sub | Twin Pines Switch | Conceptual |  | STEC | Doug Evans devans@stec.org 361-485-6459 |  | 2027-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5609, 5602, 5604 | N | N |  | 0 | 50283 | 50282
44870 | Charlotte 69 kV Station | Charlotte 69 kV Station: Add Cap Bank |  | Charlotte | - | Planned | 976 - 1154 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3734 | 2027-07-01 |  | 69 | 0 | 0 | 0 | 0,7.2 | Atascosa |  | Tier 3 | [5 empty] | N | N |  | 0 | 44871 | 44870

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2020-C1 | Blessing to STP River Pump to Esperanza 138-kV Upgrade | AEP | 2023
2020-C2 | Vanderbilt Switching Station to VanHumble Switch to Olivia Switch 69-kV Upgrade | STEC | 2022 | 2/15/2022; 5/15/2022 | Planned; Planned | 57161; 57163
2020-C3 | Brookhollow to Port Lavaca and Port Lavaca Tap to North Carbide 69-kV Upgrade | AEP | 2022
2020-C4 | Mykawa 138-kV Substation Addition and Pearland Area Reconfiguration | CNP | 2022
2020-C5 | Lolita to Tidehaven to Blessing 138-kV Upgrade | AEP | 2022
2020-E1 | Nacogdoches SE to Herty North Switch to Lufkin Switch 345-kV Loop | Oncor | 2022
2020-NC1 | Firewheel-Wylie 138-kV Line Terminal Equipment Upgrade | GPL | 2022
2019-NC17 | Carrollton Northwest 345/138-kV Transformer Upgrade | Oncor | 2023
2020-NC3 | Royse to Princeton 138-kV Line Upgrade | Oncor | 2022
2020-NC4 | Witt Rd to Simpson-Stuart 138-KV Line Upgrade | Oncor | 2023
2020-NC5 | Commerce-Royse-Terrell 69-kV to 138-KV Line Conversion | Oncor | 2023
2016-N1 | Kiamichi Energy Facility (140077) 345-kV Reactor Addition | KIOWA POWER PARTNERS LLC (RE) | 2023
2020-NC6 | Bosque Switch (252) - Olsen TNP (37460) 138-kV Line Terminal Equipment Upgrade | TNMP | 2023
2020-NC7 | McCree (834) 138-kV Improvement Project | GPL | 2023 | 2021-12-31 | Planned | 46938
2020-NC8 | Hurst (2116) - Euless South (2121) - Euless Trinity (2244) 138-kV Line Upgrades | Oncor | 2025
2020-NC9 | Eagle Mountain (11860) - Saginaw (1957) 138-kV Double Circuit Line Upgrade | Oncor | 2025
2020-NC10 | Trinidad SES (3127) - Nipak Tap (3260) - Oak Grove Tap (2725) - Kaufman (2724) 138-kV Line Upgrades | Oncor | 2026
2020-NC11 | Dallas - Fort Worth Import Project | Oncor | 2023
2020-NC12 | Anna Southeast (2704) 55.2 MVAr 138-kV Cap Bank Addition | Oncor | 2025
2019-NC1 | Irving Valley (2389) - Hackberry (2387) 345-kV Terminal Equipment Upgrade | Oncor | 2026
2019-NC15 | Venus Switch (1907,1906) - Navarro (68091) 345-kV Line Upgrade | Oncor | 2026
2020-NC13 | Eagle Mountain 345/138-kV Transformer Upgrades | Oncor | 2025
2020-NC14 | Brand (827) - Ben Davis (968) 138-kV Line Upgrade | GPL | 2026
2020-NC15 | Sargant (2947) to East Levee (2482) 138-kV Line Upgrade | Oncor | 2022
2020-NC16 | Ceramic (1485) - PPG (1484) 138-kV Line Terminal Equipment Upgrade | Oncor | 2022
2020-NC17 | Venus 345/138-kV Transformer Addition | Oncor | 2022
2020-NC18 | New Roanoke (1850) to Alliance (502) 138-kV Line | Oncor | 2023
2020-NC19 | Cedar Crest (2493) to Dealey (2842)to West Levee (2400) 138-kV Line Upgrades | Oncor | 2022
2020-NC20 | New Epco 345/138-kV Station | Oncor | 2025
2020-NC21 | West Denton Transformer Addition | TMPA | 2025
2020-NC23 | Cedar Hill (3053) to Sorcey (3051) 138-kV Line Upgrade | Oncor | 2022
2020-NC24 | Liggett (1916) to Hackberry (2387) 138-kV to 345-kV Line Conversion | Oncor | 2022
2020-NC25 | Royse Switch (2472) - Oates (831) 138-kV Line Upgrades | Oncor | 2023
2020-NC26 | Mesquite Forney Rd (2752) - Buckner home (12747) - Thorton East tap (2747) - Mesquite North Tap (2742) 138-kV Line Upgrades | Oncor | 2023
2020-NC27 | Carrolton Northwest (2363) - Carrolton Josey Lane (2555) - Carrolton Tarpley Road (2558) - Carrolton East (2577) 138-kV Line Upgrades | Oncor | 2026
2020-W1 | Sandstone Mountain System Upgrade | LCRA TSC | 2023
2020-FW1 | Rebuild Telephone Road to Tall City 138-kV Line | Oncor | 2022
2020-FW2 | Construct an Additional Terminal at Buzzard Draw Switch Substation; and Re-route the 138-kV Line from Koch Tap to Brown Sub via the New Terminal | Oncor | 2025
2020-FW3 | Establish a New 138-kV Howard Switch Substation; Reconfigure and Upgrade the 138-kV Lines Around This New Substation | Oncor | 2022
2020-FW4 | Add New 138-kV 55.2-MVAr Capacitor Bank at Tex Harvey Substation | Oncor | 2022
2020-FW5 | Add New 138-kV 55.2-MVAr Capacitor Bank at Shipwreck Substation | Oncor | 2022
2020-FW6 | Midland County Northwest to Mockingbird 138-kV Line Upgrade | Oncor | 2022
2020-FW7 | Add 138-kV 110.4-MVAr Capacitor Bank at McLlvain Pod Substation in the Culberson Loop | Oncor | 2023
2020-FW8 | Addition of the Horseshoe Springs - Riverton 138-kV Second Circuit | Oncor | 2022
2020-FW9 | Mockingbird to Adobe Meadows to Midlland East 138-kV Line Rebuild | Oncor | 2022
2020-FW10 | Midland East to Midland Downtown 138-kV Line Rebuild | Oncor | 2022
2020-FW11 | Cotton Field to Cloverdale POD 138-kV Line Rebuild | Oncor | 2023
2020-FW12 | Midland Area Transmission Improvement | Oncor | 2025
2020-SC1 | Hutto-Round Rock NE 138-kV Line Upgrade | Oncor | 2025
2020-S1 | Pleasanton-ThreeRiver Line Conversion | AEP | 2022

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Cindy Miller | Camiller2@aep.com | Cindy Miller: 918 599 2891 | Glen Reed; David Kidd; Brad Myers; Mabel See; Mike Forcum; Doug Lee; Daniel Lyons; Bob Lager; Mina Turner; Lisa Kelso; Carole Myser | gareed@aep.com; dekidd@aep.com; blmyers@aep.com; msee@aep.com; mlforcum@aep.com; dnlyons@aep.com; dlee@aep.com; rjlager@aep.com; myturner@aep.com; lokelso@aep.com; camyser@aep.com | David Kidd: 918 599 2637 Glen Reed: 918 599 2664 Brad Myers: 918 599 2690
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Hunt, Dandy; Ron Krautz; Brion Ryan | dandy.hunt@austinenergy.com; ron.krautz@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | Reza:512 322 6740 Dandy:512 322 6748 Ron:512 322 6835 Brion: 512-322-6879
BPUB | Primary | Ramon Sanz | rsanz@brownsville-pub.com; | Ramon: 956 983 6203 | James McCann | jmccann@brownsville-pub.com; | James: 956 983 6204
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Dwight Beckman | dbeckman@brazoselectric.com | Dwight: 254 750 6373 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | Edward Lopez | elopez@btutilities.com | Edward: 979 821 5697 | David Hering | dhering@btutilities.com | David: 979 821 5652
CNP | Primary & Secondary | Wesley Woitt | wesley.woitt@centerpointenergy.com | Wesley Woitt: 713-207-2760 | Yingying Huang; Raja Sekhar Kakarla; Cody Mann | Yingying.Huang@centerpointenergy.com; rajasekhar.kakarla@centerpointenergy.com; cody.mann@centerpointenergy.com | Yingying Huang: 713-207-2831 Raja Sekhar Kakarla: 713-207-3614 Cody Mann: 713-207-3149
COCS | Primary | Wesley Gray | wgray@cstx.gov | Wesley: 979 764 3434 | Timothy Crabb, Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | Basileo Rocha, Sunil Dhakal | bdrocha@cpsenergy.com; SDhakal@cpsenergy.com | Basileo: 210 353 4933 Sunil: 210 353 2008 | Kenneth Bowen Trieu Vo | kbowen@cpsenergy.com; tvo@cpsenergy.com; | Kenneth: 210 353 4142 Trieu: 210 353 2127
CTT (Cross Texas Transmission) | Primary & Secondary | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310 | Tim Cook | Tcook@LSPower.com | Tim 636 534 3310
DENTON | Primary & Secondary | Chuck Sears | Chuck.Sears@cityofdenton.com; | Chuck: 940 349 7111 | Brent Heath | brent.heath@cityofdenton.com; | Brent: 940 349 7180
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Grubbs, David; Juan Santos | Dgrubbs@gpltexas.org; Jsantos@gpltexas.org | David: 972 205 2664 Juan: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; BEC (Bandera); BBEC; CTEC; GVEC; NBU; PEC; SBEC; RGEC | Primary & Secondary | Dylan Preas | dylan.preas@lcra.org | Dylan: 512-578-4514 | Naved Khan | naved..khan@lcra.ord | Naved: 512-578-4176
Lone Star | Primary & Secondary | Chenyan Guo | chenyan.guo@fpl.com | Chenyan: 561-304-5692 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Charles Saker | charles.saker@oncor.com | Charles: 214-743-6896 | Paul Bell | paul.bell@oncor.com | Paul: 214-743-6676
Sharyland Utilities | Primary & Secondary | Brad Schwarz | bschwarz@huntpower.com | Brad: 512-289-7425 | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243
STEC | Primary & Secondary | Doug Evans | devans@stec.org | Doug: 361 485 6459 | Paul Person Loretta Gonzalez | pperson@stec.org; lgonzalez@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Ahmad Saboor | asaboor@texasmpa.org | Ahmad: 936 873 1104 | Frank Owens | fowens@texasmpa.org; | Frank: 936 873 1120
TNMP | Primary & Secondary | Robert Lona | Robert.Lona@tnmp.com | Robert: 281-581-4732 | Anthony, Hudson Ballay, Dustin Cloninger, Ross | Anthony.Hudson@tnmp.com; Dustin.Ballay@tnmp.com; Ross.Cloninger@tnmp.com; | Anthony: 281 581 4712 Dustin:281 581 4730 Ross:281 581 4733
Wind Energy Texas Transmission (WETT) | Primary | Julius Horvath | julius.horvath@windenergyoftexas.com | Julius: 512 436 9585; cell: 512 496 9186 | Christina Minchew | christina.Minchew@windenergyoftexas.com | Christina: 512-436-9469