## Slide 1
Resource Integration Topics
Jay Teixeira
ERCOT
Resource Integration Working Group
October 26, 2021

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
PSCAD Model Quality Test and Unit Model Validation required for November 1, 2021 QSA
TSAT Model Required – If PSSE model is UDM, then TSAT model should be UDM by November 1, 2021.

## Slide 7: Dispatchable Resources Potential Prioritization
ERCOT considering ways to prioritize generation considered to be “dispatchable” in the interconnection process under current rules
  Submissions of application and processing
  Screening studies completions
  FIS Kickoff meetings
  Reviews of TSP studies
  RARF and Model Submissions
  Commissioning Checklist and Testing reviews
http://interchange.puc.texas.gov/search/documents/?controlNumber=52373&itemNumber=173

## Slide 8: Active RR’s
NOGRR223, Add Phasor Measurement Recording Equipment Requirement to Modified Generating Facilities in Interconnection Process. PUCT approved 10/7/2021.
NOGRR227, Add Phasor Measurement Recording Equipment Location for Main Power Transformer for Intermittent Renewable Resource (IRR). PUCT approved 10/7/2021.

## Slide 9: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department
Mailing List
  RESOURCE_INTEGRATION@LISTS.ERCOT.COM

## Slide 10: Questions?
Thank you!