## Slide 1
Item 12: Securitization Update
Mark Ruane
Senior Director, Settlements, Retail and Credit
TAC
ERCOT Public
November 10, 2021

## Slide 2: Securitization Update
The PUC issued the Debt Obligation Orders for Securitization Subchapter M and Subchapter N on October 13th.
ERCOT has received the Subchapter M funds and the disbursement process is ongoing
NPRR 1103, the Subchapter M implementation NPRR, is expected to be at the Board and PUCT in December.
The implementation NPRR for Subchapter N will be posted in December.
A securitization landing page on Ercot.com will be implemented shortly.

## Slide 3: Securitization Update
The following slides lay out the sequence of key activities for M and N.
Many securitization dates are subject to change due to:
  Timing of when debt funding is received (outside of ERCOT’s control)
  ERCOT’s ability to rapidly develop and validate manual activities
  ERCOT’s ability to expedite the securitization project work in conjunction with the in-flight FFR go-live December & DGR go-live Feb 2022.
ERCOT will provide updates to TAC and Market Notices will be issued as applicable throughout the process.
ERCOT expects Board and PUCT approval for M in December 2021 and for N in February 2022.
Next Steps and Timeline

## Slide 4: Securitization Update
Subchapter M Securitization Default Charge Milestones
Item | Target Dates
NPRR 1103 WMS presentation | November 3, 2021
NPRR 1103 PRS review | November 10, 2021
NPRR 1103 CWG/MCWG review | November 11, 2021
Closing of $800m M funding | November 12, 2021
Disbursement of M funds commenced | November 15, 2021
NPRR 1103 TAC review | November 29, 2021
NPRR 1103 Board review | December 9-10, 2021
(Continued on next slide)
Next Steps and Timeline

## Slide 5: Securitization Update
Subchapter M Securitization Default Charge Milestones
Item | Target Dates
NPRR 1103 PUCT review | December 16, 2021
Market notice with implementation details | December 17, 2021
M escrow deposit requirement estimates available (manual process) | Late December 2021
M escrow deposit requests | January 3, 2022
Initial Default Charge Miscellaneous Invoices issued (manual process) | January 11, 2022
Initial invoicing of non-Period of Emergency Uplift (manual process) | Late January 2022
Project for M automation to automate manual processes | TBD 2022
Next Steps and Timeline

## Slide 6: Securitization Update
Subchapter N Securitization Uplift Balance Milestones
Item | Target Dates
Opt-out deadline (45 days after Order) | November 29, 2021
REPs provide ERCOT Period of Emergency interval-level meter data for opted-out transmission voltage customers. | December 1, 2021
Deadline for ERCOT to file its calculation of total exposure and LRS (one-time manual calculation) (55 days after Order) | December 7, 2021
Urgent N NPRR posted | ~December 20, 2021
Deadline for LSEs to verify ERCOT’s exposure calculation (70 days after Order) | December 22, 2021
(Continued on next slide)
Next Steps and Timeline

## Slide 7: Securitization Update
Subchapter N Securitization Uplift Balance Milestones
Item | Target Dates
N NPRR WMS presentation | January 5, 2022
Urgent N NPRR PRS review | January 13, 2022
N NPRR CWG / MCWG review | January 19, 2022
N NPRR TAC review | January 26, 2022
N NPRR Board review | February 8, 2022
N NPRR PUCT review | February 10, 2022
* N release date has interdependencies and constraints related to completion of FFR and DGR release activities (people and system environment constraint risks).
Next Steps and Timeline

## Slide 8: Securitization Update
Subchapter N Securitization Uplift Balance Milestones
Item | Target Dates
N Closing to secure funds (up to $2.1B) | Q1 2022
Disbursement of N funds (one-time manual process) | Q1 2022
System go-live for daily N invoicing* | March 14, 2022
N escrow deposit requirement notifications | TBD 2022
Initial N invoicing | TBD 2022
* N release date has interdependencies and constraints related to completion of FFR and DGR release activities (people and system environment constraint risks).
Next Steps and Timeline

## Slide 9: Securitization Update
Questions