## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2021-10-21
Agenda Item: | Decision / Resolution | Action Items :
September Meeting Notes
| Texas SET approve the September meeting notes. | The Texas SET Vice Chair will have the notes posted to the ERCOT September meeting page key documents.
Retail Market Subcommittee (RMS) Update
1095NPRR-01_Texas_SET_V5.0_Changes | RMS and PRS approved this as written
169RMGRR-01_Texas_SET_V5.0_Changes | RMS and PRS approved this as written
Change Control 2021-835: Update code 26 of the BIG07 in the 810_02 to support miscellaneous credits. | RMS approved this Change Control
Change Control 2021-836: This change control will implement logic to reject Texas SET transactions that contain only a comma in the name field | RMS approved this Change Control
ERCOT Update
Flight 1021 | The Texas SET Chair presented the flight update as provided by ERCOT.
The ONCOR Texas SET member inquired if there would be value to include the statistics on new entries into the market. It was suggested that a summary be included in the Accomplishments line on testing.
ERCOT | ERCOT stated that they will do their best to get the Impact Analysis (IA) for NPRR1095 to Texas SET Leadership for review prior to the November RMS meeting.
Discussion Items
Retail Emergency Conditions Task Force (RECTF)
CBCI File | The Texas SET Chair conducted an initial review of the current Retail Market Guide (RMG)Section 7.11.3 Customer Billing Contact Information (CBCI) File including some updates. TXU Energy asked if ERCOT could contact a REP when they do not send the monthly file. ERCOT stated that they do not now but would invite anyone to submit the request along with requirements, so the request could be vetted through the Stakeholder process. ERCOT also stated that the RMG should be used to make the request. | The Texas SET Chair will send the document to TXU Energy; then language will be added to request ERCOT to let a CR know if they do not send files or files that contain beneficial data in their file. The updated document will be reviewed at the next meeting.
Transmission Distribution Service Provider (TDSP) Data Practices PowerPoint | The RMS Chair reviewed the history behind the matrix and stated that it will be posted to the RMS home page key documents.
Other Business
Transaction Names Inventory--Correction to 814_27 transaction directions. | The corrections were reviewed at the last meeting. | The Texas SET vice-Chair will send the corrected document to ERCOT for posting.
650_04 MVO Request Cancel Discussion | The Texas SET Chair, TXU Energy and ONCOR reviewed a scenario where a TDSP sent the 650_04 with the R8 permanent suspension code to the CR in error and that the automated process for the CR immediately sent the Move out. The customer was inadvertently left in a lights out situation. It was noted that there is no way to cancel a 650_04 Permanent Suspension and even if there was that the CRs with automated responses happen to fast to allow a cancel to come through. It was determined that this scenario happens rarely and that the TDSP could develop a process to Un-execute the Move Out to prevent the lights out situation. It was also noted that language in the Implementation Guide could be updated to show that the requests with the R8 permanent suspension code cannot be cancelled. | TXU will update the language and add to an existing approved Change Control; then submit it to ERCOT to review on a Texas SET Change Control call. If consensus is reached, it will be submitted to RMS for approval.
2022 Meetings | The Texas SET Chair conducted a discussion on the meeting dates for next year. | Texas SET Leadership will coordinate dates with TDTMS Leadership to have them scheduled for the same week, back-to-back; then determine which can be held in Austin.
Next Meeting--WebEx Only | 2021-12-08
Attendees F-T-F
Attendees Webex
Birdie Cobb Centerpoint Energy | Kathy Scott Centerpoint Energy
Carolyn Reed Centerpoint Energy | Kim Wall Hansen Technologies
Dave Michelsen ERCOT | Kyle Patrick NRG
Deb Belin MarketWise | Mary Do Agility CIS
Diana Rehfeldt TNMP | Michael Heselton
Eric Lotter GridMonitor | Paul Shadle NEC
Frank Nunes EC InfoSystems | Sam Pak ONCOR
Jim Lee AEP | Stephen Wilson TXU Energy
Jordan Troublefield ERCOT | Tyler Krueger Big Data Energy
Kathryn Thurman ERCOT