## Slide 1
Project Update
December 14, 2021
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2021 Release Targets
  2022 Release Targets
  TAC Priority / Rank Recommendations
    NPRR1091 – Changes to Address Market Impacts of Add’l Non-Spin Procurement
    NPRR1105 – Option to Deploy Distribution Voltage Reduction Measures Prior to EEA
  In-Flight Strategic Projects
    Fast-Frequency Response (FFR) Advancement
    DGR/DESR Implementation
    BES Combo Model Implementation
  Securitization Update
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1095 – Texas SET V5.0 Changes
    SCR817 – Related to NPRR1095, MarkeTrak Validation Revisions Aligning with Texas SET V5.0
    NPRR1098 – DC Tie Reactive Power Capability Requirements
    SCR816 – CRR Auction Bid Credit Enhancement
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 February Release – 2/1/2022-2/3/2022 In Flight
  NPRR917 – Nodal Pricing for SODGs and SOTGs
  NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
  NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
  NPRR1065 – Implementation Adjustment for NPRR917
  PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
  NOGRR212 – Related to NPRR1016
  RRGRR026 – Related to NPRR1016
  LPGRR068 – Add BUSLRG and BUSLRGDG Profile Types
2022 March Release – 3/29/2022-3/31/2022 In Flight
  SCR800 – Addition of DC Tie Ramp to GTBD Calculation
  SCR809 – Changes to External Telemetry Validations in Resource Limit Calculator
2022 May Release – 5/24/2022-5/26/2022 In Flight
  NPRR939 – Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions
  NPRR1093 – Load Resource Participation in Non-Spinning Reserve
  NPRR1101 – Create Non-Spin Deployment Groups made up of Generation Resources Providing Off-Line Non-Spinning Reserve and Load Resources that are Not Controllable Load Resources Providing Non-Spinning Reserve
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/2 – 2/4 | April 3/30 – 4/1 | May 5/25 – 5/27 | July 7/27 – 7/29 | October 10/5 – 10/7 | December 12/7 – 12/9
NPRR902(a) NOGRR195 NPRR1055 OBDRR023(a) NPRR1020 SCR804 | NPRR971 NPRR986 NPRR998 NPRR1024 NPRR1043 NOGRR213 VCMRR027 PGRR070 NPRR1060 | NPRR974 NPRR978(c) NPRR1048 NPRR1051 SCR811 ECMS ECMS NPRR1080 OBDRR030 NPRR1081(a) | NPRR902(b) NPRR905 SCR789 NPRR1062 RMGRR164 NPRR1031 NPRR867 NPRR1081(b) | None NPRR984 OBDRR023(b) | None SCR781
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR902(a) – ECEII Market Participant MPIM role
NPRR902(b) – MIS links updated for ECEII reports
NPRR978(c) – Forecast Zone scope
NPRR1081(a) – Manual implementation
NPRR1081(b) – Automated solution
OBDRR023(a) – ERS Expenditure Limit
OBDRR023(b) – 4 Standard Contract Terms/Year
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 879, 885, 904, 918, 930, 935(b), 936, 941, 945, 962, 965, 1004, 1006, 1019, 1023, 1030, 1032, 1034, 1040, 1057 SCRs: 799, 805, 809, 812 Market Guides: PGRR066, PGRR076 Other Binding Docs: OBDRR009
E
Replace NoticeBuilder
ECMS
11/17 – 11/20
New navigation
1/1
ü
ü
ü
2/1
10/1
5/1
3/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
4/22
ü
6/1
ü
RIOO – 12/20
Interconnection requests of less than 10MWs and DGRs
6/25
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
New public version of ERCOT.com homepage
ü
7/1
9/16
7/14
7/23
8/1
ü
ü
ü
ü
ü
ü
9/10
ü
ü
ü
ü
ü

## Slide 5: 2022 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/1 – 2/3 | March 3/29 – 3/31 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 DGR/DESR NPRR917 NPRR1016 NPRR1052 NPRR1065 NOGRR212 PGRR082 RRGRR026 | SCR800 SCR809 | NPRR939 NPRR1093 NPRR1101 | TBD | TBD | TBD
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
I
P
P
P
P
E
E
E
E
E
E
E
E
Securitization Subchapter N – March Go-Live

## Slide 6: TAC Priority / Rank Recommendations
NPRR1091 – Changes to Address Market Impacts of Additional Non-Spin Procurement
  IA Summary
    Cost $120k-$160k
    Duration 7-10 months
  Recommended Priority 2022 Recommended Rank 3195
  Priority / Rank Logic: 2022 start with same rank as NPRR1093 (per submitter’s request)
  Additional comments
    Combining with NPRR1093 will depend on any impact to the 2022 R3 target of NPRR1093
NPRR1105 – Option to Deploy Distribution Voltage Reduction Measures Prior to EEA
  IA Summary
    Cost $80k-$120k (for Phase 2)
    Duration Phase 1 – Effective on PUCT approval (sections 6.5.9.4.1 and 6.5.9.4.2)
    Phase 2 – 6-9 months (section 6.5.7.3.1)
  Recommended Priority 2022 Recommended Rank 3020
  Priority / Rank Logic: 2022 start with same rank as NPRR1006 (per market Comments)
  Additional comments
    Further discussion needed – ERCOT believes NPRR1105 may require revisions which could impact the potential to bundle with NPRR1006

## Slide 7: In-Flight Strategic Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on 6/22/2021)
    Planned go-live for 2021-R6 (December 2021)
    NPRR863, NPRR1015, NPRR1079, NOGRR187
  PR354-01 DGR/DESR Implementation (Gated to Execution phase on 7/30/2021)
    Target go-live 2022-R1 (February 2022)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
  PR353-01 BES Combo Model Implementation – potential for multiple go-lives
    Target go-live TBD (core project On Hold until resources are available after FFR and DGR/DESR)
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
ESR: Energy Storage Resource
DGR: Distributed Generation Resource
BES: Battery Energy Storage
Blue text: ERCOT considering removing from project for earlier delivery
Revised go-live target TBD

## Slide 8: Securitization Update
For latest information, see presentation posted with 11/29/2021 TAC materials
NPRR1103 Securitization – PURA Subchapter M Default Charges approved by Board of Directors on 12/10/2021
After PUCT approval, ERCOT will issue a Market Notice with implementation details

## Slide 9: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1095 | Texas SET V5.0 Changes | 2023 | 3700 | $1.0M-$1.5M, 16-20 months Impacted Systems: Registration, Retail, Integration, Data Management & Analytics Expected to be bundled with SCR817
SCR817 | Related to NPRR1095, MarkeTrak Validation Revisions Aligning with Texas SET V5.0 | 2023 | 3700 | $400k-$600k, 10-15 months Impacted Systems: Retail, Registration, Integration Expected to be bundled with NPRR1095
NPRR1098 | DC Tie Reactive Power Capability Requirements | 2022 | 2530 | $10k-$20k, 3-5 months (Southern Cross funding) Impacted Systems: Grid Decision Support Systems ERCOT suggests bundling with previously-approved Southern Cross Revision Request: NPRR857
SCR816 | CRR Auction Bid Credit Enhancement | 2022 | 2855 | $50k-$80, 4-6 months Impacted Systems: CRR ERCOT suggests bundling with SCR807 to save on testing hours and address the risk related to CRR transaction limits
PPL Rank Information
Next available 2022 Rank in Business Strategy = 3560
Next available Rank in Regulatory = 330
Options for…