## Issues
Item # | Category | Sub-Category | Item Number | Originating Entity | Item Description | Timing | Owner | TAC Priority | Status | PUCT Project | ROS Notes | Memo from Magness | WMS Notes | RMS Notes | Other Notes | WMS 12/1 Comments
111 | Communication |  | 1 | ERCOT | Work with applicable government and private entities to improve ERCOT emergency public safety communications (e.g., AMBER Alert and TxDOT digital highway signs) for anticipated and actual Energy Emergency Alert (EEA) events, including Load shed in the ERCOT Region. Incorporate public safety communications strategy into all communication channels such as traditional news media, the ERCOT website, and social media platforms. | Awaiting Commission Direction |  |  | Awaiting Commission Project | Project No . 51888, Review of Critical Load Standards and Processes Project No. 51889, Review of Communications for the Electric Market |  |  |  |  | SB3
112 | Communication |  | 2 | ERCOT | Increase coordination through the Texas Energy Reliability Council (TERC) and ERCOT’s Gas Electric Working Group (GEWG) to identify critical gas facilities for Transmission and/or Distribution Service Providers to avoid disconnection during EEA events. | Awaiting Commission Direction |  |  | Awaiting Commission Project | Project No . 51839, Electric - Gas Coordination Project No . 51888, Review of Critical Load Standards and Processes |  |  |  |  | SB3
114 | Credit |  | 3 | ERCOT | Comprehensive evaluation of Settlement and Creditworthiness requirements and ERCOT discretion practices during the Event. Consider changes such as: Settlement at Counter-Party level versus Qualified Scheduling Entity level, use of Unsecured Credit and certain Financial Security (e.g., surety bond and guarantees), and creation of Counter-Party financial dashboard. | Near-Term Stakeholder Items | WMS | High | Completed |  |  |  | MCWG |  |  | Ongoing work at MCWG
93 |  | ROS Load-Related Items | 4 | ERCOT/ROS | Load Shed Practices: Coordinate with Transmission Operators to understand the practical and operational limitations of Transmission Operators and related Distribution Service Providers to facilitate rotating Load shed practices when faced with an extreme magnitude of firm Load shed instructions. The extraordinary amount of Load shed, which resulted in outages that could not rotate from one area to another, was an extremely difficult issue during February 15-19. Upon feedback, consider adjusting operational practices between ERCOT and Transmission Operators to achieve effective rotating Load shed objectives. This objective will likely require industry-wide commitment to develop solutions, but after what occurred here, that effort must begin immediately.* | Long-Term Stakeholder Items | ROS |  | Completed | Project No . 51888, Review of Critical Load Standards and Processes | OWG - Contact Blake Gross NPRR1094; NOGRR233 | Item 1
98 |  | ROS Generation-Related Items | 5 | ERCOT/ROS | Outage Scheduler: Explore overall reporting and timing requirement changes to the ERCOT Outage Scheduler to ensure more specific, complete, and accurate information for Forced Outages of Resources during Real-Time operational conditions. Make appropriate system changes to the ERCOT Outage Scheduler to achieve enhanced situational awareness objective. What's the scope of the change? Does this apply to transmission and distribution? | Near-Term Stakeholder Items | ROS |  | Completed |  | OWG - Contact Ian Haley | Item 5 |  |  | NPRR1084
99 |  | ROS Generation-Related Items | 6 | ERCOT/ROS | Resource Telemetry: Ensure accurate exchange of Resource telemetry information related to Physical Responsive Capability (available operating reserves in real time) to enhance situational awareness during EEA events.* | Near-Term Stakeholder Items | ROS |  | Completed |  | OWG/PDCWG - Contact Lori Simpson | Item 6 |  |  | NPRR1085
100 |  | ROS Generation-Related Items | 7 | ERCOT/ROS | DER Registration: Expand registration and Real-Time data requirements for all types of resources beyond current modeling requirements (e.g., distribution-level resources) to enhance situational awareness for planning and operational purposes.* | Near-Term Stakeholder Items | ROS/WMS |  | Completed |  | OWG | Item 7 | WMWG |  | NPRR1077 - Workshop held on 7/22 PGRR092, RRGRR029
20 | Procedural | Seaonal Preparation | 8 | RMS | Have RMS preparation discussions twice a year to cover summer and winter | Near Term Stakeholder Items | RMS |  | Not Started | Communications and Governance |  |  |  | RECTF 6/23 - RMS will hold Weather Preparedness workshops 2x per year -- March/April for Summer, Oct/Nov for Winter. 2021 Winter Preparedness Workshop scheduled for November 2nd @ 1:30PM following RMS
5 | Communication | Customer | 9 | RMS | Outage alerts pushed to end-use Customers from TDUs | Outside the Stakeholder Purview |  |  | Not Started | Communications and Governance
3 | Communication | Customer | 10 | RMS | Review limitations on the ability of a REP/LSE to communicate to customers regardless of communications coming from ERCOT | Awaiting Commission Direction | RMS |  | Not Started | Project No. 51889, Review of Communications for the Electric Market |  |  |  | RECTF
6 | Communication | Customer | 11 | RMS | Consistency in delivery and content of messaging in communications from the TDUs | Awaiting Commission Direction | ROS/WMS/RMS |  | Completed | Project No. 51889, Review of Communications for the Electric Market |  |  |  |  | TAC note - PUC Staff meeting with the TDUs to discuss. | No stakeholder action at this time; monitor PUC project and can revisit upon completion of 51889
12 | Communication | Uplift | 12 | RMS | Concerns with the high uplift and impacts to a residential customer, how to communicate what uplift is, how it works, including refunds to customers | Awaiting Commission Direction | WMS |  | Completed | Project No. 51889, Review of Communications for the Electric Market |  |  | Reassigned to WMS on 6/23 | RECTF RMS requested TAC approval to re-assign item #12 to WMS. WMS possesses the subject matter expertise to appropriately address Uplift. |  | No stakeholder action at this time; monitor PUC project and can revisit upon completion of 51889
16 | Data | ERCOT Website | 13 | RMS | ERCOT website display, develop and improve the conditions on the grid numbers. The supply/demand chart was not helpful because it was not accurate. Current system conditions and forecasts are not clear. | Long-Term Stakeholder Items | ERCOT |  | Completed | Project No. 51889, Review of Communications for the Electric Market |  |  |  |  | New dashboard fullfills this item
1 | Communication | ERCOT listserv | 14 | RMS | The ERCOT listserv was down for much of the event, how can there be a backup for that, and what can ERCOT and stakeholders identify for communication if the listserv is unavailable. Evaluate if current listserv set up and ERCOT SLA w/ Vendor is adequate. ERCOT to determine if Listserv functionality can be brought in-house. Combine with Item 24 | Near-Term Stakeholder Items | RMS |  | Completed | Project No. 51889, Review of Communications for the Electric Market |  |  |  | TDTMS ERCOT has initiated an internal project to bring the Listserv functionality "on premise". Final testing of migration is expected to complete by end of June 2021. | ERCOT listserv brought in house
9 | Communication | Market Participant | 15 | RMS | Modifications to ERCOT Corporate Communication Handbook to include information to RMS | Near-Term Stakeholder Items | ERCOT |  | Not Started | Project No. 51889, Review of Communications for the Electric Market
11 | Communication | Market Participant | 16 | RMS | Should ERCOT Summer Preparedness communications begin to include Winter preparedness | Near-Term Stakeholder Items | ROS/WMS/RMS |  | Completed | Project No. 51889, Review of Communications for the Electric Market |  |  | Addressed by RECTF | RECTF See Item 8
8 | Communication | Customer | 17 | RMS | Possibility to leverage TDU CRIP sites (Competitive Retail Information Portal) for customer communications | Outside the Stakeholder Purview |  |  | Not Started | Project No. 51889, Review of Communications for the Electric Market
13 | Data | Metering | 18 | RMS | Evaluate the establishment of expectations regarding meter data and the use of estimates during prolonged, wide-spread customer outages | Long-Term Stakeholder Items | RMS |  | Not Started | Retail Market |  |  |  | RECTF RECTF finalizing the addendum to "TDSP AMS Data Practices Matrix" which provides further clarity of TDSP meter data expectations during a prolonged, wide-spread outage events.
14 | Data | Metering | 19 | RMS | Subset of C&I customers using medium and large profiles, high initial estimates cause large impacts to large C&I. C&I to receive similar treatment as the mass market residential segment. Specific to LC&I customers | Long-Term Stakeholder Items | RMS |  | Not Started | Retail Market |  |  |  | RECTF/PWG If an IDR Meter is changed to an AMS meter, the corresponding meter data will be delivered via daily LSE files to ERCOT for Settlement purposes and to Smart Meter Texas for Customer and REP access. Hight initial estimates will be reduced significantly when a meter is changed from IDR to AMS; and impacts to the market will be discussed at the October 13th IDR/AMS workshop
15 | Data | Metering | 20 | RMS | Should there be modifications for Validation, Editing and Estimation of meter data? What is the extend of billing error caused by this? Combine with Item 18 | Long-Term Stakeholder Items | RMS |  | Not Started | Retail Market |  |  |  | RECTF RECTF discussed options to mitigate MP credit risk and explored option of "Pre-VEE" meter data. End result: no changes to current VEE processes warranted. Other options that could positivity impact credit risk could include combining (netting) the DAM & RTM invoices -- to be raised at WMS. Additional concern that TDSP data is "routinely late" in delivery to ERCOT; however ERCOT data shows that data delivery timeliness is greater than 99.5% on time
17 | Default | Transparency | 21 | RMS | Not enough transparency in ERCOT default and acquisition processes – more transparency into default and acquisitions to pass on to customers (when happening and how impacts customers) Combine with Items 22 and 23 | Long-Term Stakeholder Items | RMS |  | In Progress | Retail Market |  |  |  | RECTF/TXSET/RMTTF RMGRR165 passed through Stakeholder process which improve market transparency and information to market re: Mass Transition events.
18 | Default | Mass Transition | 22 | RMS | Mass Transition expectations and scenarios for customers Combine with Items 21 and 23 | Long-Term Stakeholder Items | RMS |  | Not Started | Project No. 51889, Review of Communications for the Electric Market |  |  |  | RECTF/TXSET Draft RMGRR submitted to modify ERCOT system logic when handling Switches within 60 days of Mass Transition event.
19 | Default | Acquisition Transfer | 23 | RMS | Acquisition transfer process and expectations for customers Combine with Items 21 and 22 | Long-Term Stakeholder Items | RMS |  | Not Started | Project No. 51889, Review of Communications for the Electric Market |  |  |  | RECTF/RMTTF RMTTF updating Mass Transition training module.
2 | Communication | ERCOT listserv | 24 | RMS | Review of SLA language for after-hour issues Combine with Item 14 | Near-Term Stakeholder Items | RMS |  | Not Started |  |  |  |  | RECTF/TDTMS Working with ERCOT Staff to incorporate ListServ performance metrics into a SLA document.
10 | Communication | Market Participant | 25 | RMS | ERCOT FAQs were excellent but could benefit from more timely dissemination | Near-Term Stakeholder Items | ERCOT |  | Not Started
7 | Communication | Customer | 26 | RMS | Timeliness of messaging (e.g. customer may be out all day, after they were already out) | Outside the Stakeholder Purview |  |  | Not Started
4 | Communication | Customer | 27 | RMS | Outage websites (media directs Customers to those) | Outside the Stakeholder Purview |  |  | Not Started
85 |  | ROS Items | 28 | ROS | Governance: Review ERCOT’s governance structure and identify potential process improvements in the ERCOT Bylaws and ERCOT stakeholder processes. | Outside the Stakeholder Purview |  |  | Not Started | Communications and Governance |  |  |  |  | SB2
95 |  | ROS Load-Related Items | 29 | ROS | Load Impact to GTCs: Determine the impact of load shed on generation curtailments for generation tied to a GTC. | Long-Term Stakeholder Items | ROS |  | Completed | Project No . 51888, Review of Critical Load Standards and Processes | PLWG Joint OWG/CMWG discussion at 6/14 CMWG meeting |  |  |  | ERCOT presented summary of generation curtailment by constraints during 2021 February Winter Event at the June 2021 CMWG meeting
106 |  | ROS Generation-Related Items | 30 | ROS | Frequency Relay Points: Analyze load shed responsibilities related to frequencies for generation and load and ensure alignment | Near-Term Stakeholder Items | ROS |  | Completed | Project No . 51888, Review of Critical Load Standards and Processes | PDCWG to lead review; coordinate with SPWG and DWG. Allow NOGRR226 to work through stakeholder process
88 |  | ROS General Items | 31 | ROS | ERCOT Training Program: Review existing ERCOT training program, including system operator and communications training relevant to ERCOT emergency events and identify opportunities for enhancements to existing training and development of new training modules to consider load shed events of various levels of magnitude. | Long-Term Stakeholder Items | ROS | Medium | Not Started | Project No . 51888, Review of Critical Load Standards and Processes Project No. 51889, Review of Communications for the Electric Market | OTWG
86 |  | ROS Items | 32 | ROS | ERCOT Communications: Review ERCOT communications to the public and market participants before, during, and after the event and identify potential process improvements and recommendations for ERCOT and market participant communications plans for future ERCOT emergency events, including extreme load shed scenarios. | Near-Term Stakeholder Items | ROS/WMS/RMS |  | Completed | Project No . 51888, Review of Critical Load Standards and Processes Project No. 51889, Review of Communications for the Electric Market |  | Item 2 |  |  | TAC note - This isn't really a standalone item, but is addressed with PUCT-ERCOT regular communications. Currently several sets of PUCT-ERCOT partners meeting weekly. | No stakeholder action at this time; monitor PUC project and consider under normal course of business if/when necessary
94 |  | ROS Load-Related Items | 33 | ROS | Load Shed Table: Review the methodology currently used for determining load shed obligations for each Transmission Operator and consider modifications to ensure fair and equitable allocation that prioritizes maintaining service for critical load circuits and enables the ability to rotate outages in future extreme weather events. This review should consider constraints created by requirements for under-frequency relaying. | Long-Term Stakeholder Items | ROS |  | Awaiting Commission Project | Project No . 51888, Review of Critical Load Standards and Processes | OWG - Contact Blake Gross |  |  |  | This review should also consider creating separate Load shed tables for winter and summer. There is also calrity needed to ensure only one DSP is counting the Load for meeting the required allocation. Consider excluding auxilary Load from generation within NOIE territory from Load shed obligation. (GSEC/Katie Rich) SB3
105 |  | ROS Generation-Related Items | 34 | ROS | Blackstart: Review availability of blackstart units during February 2021 winter weather event and potential process improvements, including priority for non-curtailment of gas supply, to ensure availability during extreme weather events. Evaluate options to improve restoration process following blackout event. | Near-Term Stakeholder Items | ROS |  | In Progress | Project No . 51839 , Electric - Gas Coordination | BSWG Reviewed Black Start Resource availability during winter storm; proposed rule changes discussed | Item 3 |  |  | Consider/discuss possible Protocol requirement for blackstart units to have onsite fuel specifically reserved for blackstart operations. (Oncor/Collin Martin)
90 |  | ROS General Items | 35 | ROS | Procedures during Natural Gas Supply Emergency: Review current procedures and communication requirements between ERCOT, TOs, QSEs, and REs during a natural gas supply failure and assess if changes are warranted. | Near-Term Stakeholder Items | ROS/WMS |  | Completed | Project No . 51839 , Electric - Gas Coordination Project No. 51889, Review of Communications for the Electric Market | GEWG |  | WMWG |  | Discussed at 9/24/21 GEWG working group; determined no action needed at this time, pending outcomes of PUC, RRC activities
102 |  | ROS Generation-Related Items | 36 | ROS | Resource Outage Information during Event: Review units that were unavailable or did not bid into market by county and assess potential regional weatherization standards. | Awaiting Commission Direction |  |  | Awaiting Commission Project | Project No . 51840 , Rulemaking to Establish Weatherization Standards |  |  |  |  | SB3
87 |  | ROS Items | 37 | ROS | Benchmarking: Conduct benchmarking with other regional transmission organizations (RTOs) and independent system operators (ISO) in North America to identify best practices and opportunities for improvement in topics to be reviewed in the post February 2021 winter weather event assessment including policies, requirements, and processes related to communications, emergency preparedness and response, winter weatherization, wholesale market design to ensure resource adequacy during winter months and extreme winter weather events, load shed protocols and obligations, electric-gas coordination, and training. | Outside the Stakeholder Purview | ROS/WMS |  | Awaiting Commission Project | Project No . 51840 , Rulemaking to Establish Weatherization Standards Project No . 51839 , Electric - Gas Coordination Project No . 51888, Review of Critical Load Standards and Processes Project No. 51889, Review of Communications for the Electric Market
101 |  | ROS Generation-Related Items | 38 | ROS | Winter Weatherization Preparations: Review existing ERCOT requirements, including Section 3.21 of the ERCOT Protocols, and associated processes related to winter weatherization preparations, findings from ERCOT’s review of the most recent submissions of Emergency Operations Plan, Weatherization Plans, and Declarations of Summer and Winter Weather Preparedness, and identify potential gaps and process improvements, including consideration of standardized requirements. | Awaiting Commission Direction |  |  | Awaiting Commission Project | Project No . 51840 , Rulemaking to Establish Weatherization Standards Project No . 51841 , Review of 16 TAC § 25.53 Relating to Electric Service Emergency Operations Plans |  |  |  |  | SB3
83 |  | ROS Items | 39 | ROS | Overall Assessment and Root Cause Analysis: Perform an independent overall assessment of the February 2021 Winter Weather Event, including root cause analysis, with recommendations for future market and reliability enhancements in advance of summer 2021 and winter 2021-2022 to the extent feasible | Outside the Stakeholder Purview |  |  | Not Started | Project No. 51841, Review of 16 TAC § 25.53 Relating to Electric Service Emergency Operations Plans |  |  |  |  | Independent analysis puts this outside of stakeholder purview
84 |  | ROS Items | 40 | ROS | Emergency Preparedness and Response: Review ERCOT’s emergency response plan and ERCOT’s role in emergency preparedness and response leading up to, during, and after the February 2021 winter weather event and consider process improvements and enhanced coordination among market participants and State and local emergency preparedness and response organizations. | Awaiting Commission Direction |  |  | Not Started | Project No. 51841, Review of 16 TAC § 25.53 Relating to Electric Service Emergency Operations Plans
89 |  | ROS General Items | 41 | ROS | DC Ties: Review performance of DC ties during the event and consideration of how this impacts planning assumptions and other policies related to DC ties. | Long-Term Stakeholder Items | ROS/WMS | Medium | Completed |  | PLWG, OWG - Contact Chad Thompson DC Ties available but schedules curtailed during Uri. OWG recommends no changes; PLWG recommendations include: (1) update specific study scope document to include specific assumptions for DC Tie contributions, (2) study scenarios should include scenarios with 0 DC tie contributions, and (3) no Planning Guide revisions are recommended |  | SAWG Review complete; per protocol methodology, future winter DC tie capacity contribution will use Uri DC tie performance as a basis
96 |  | ROS Load-Related Items | 42 | ROS | Modify under-frequency relay (UFR) process to understand whether they can be used in smaller areas. Create a comparison among Transmission Operators and related Distribution Service Providers with how the UFRs performed with different types of load. Review under-frequency relay requirements to determine if changes are needed to improve Transmission and / or Distribution Service Providers' abilities to shed and rotate load. | Long-Term Stakeholder Items | ROS |  | In Progress |  | PDCWG Allow NPRR1094 and NOGRR233 to work through stakeholder process
103 |  | ROS Generation-Related Items | 43 | ROS | Reliability Studies for Proposed Resource Retirements: Review existing reliability must run (RMR) and must-run alternative (MRA) study and processes and determine if any changes to study parameters are needed, including winter peak and planned and forced outage scenarios and generation resource dispatch. Consider extension of RMR process to units proposed for seasonal mothball. | Long-Term Stakeholder Items | ROS/WMS |  | Completed |  |  |  | WMWG |  |  | long term item; future discussions can be taken up at WMWG
104 |  | ROS Generation-Related Items | 44 | ROS | Ancillary Service Products: Review existing ancillary service products and determine if existing suite of products and amounts is adequate based on lessons learned from the February 2021 winter weather event. Need to understand how generators offering AS performed: PDCWG to review what happened; Joint meeting with WMWG to discuss market impacts; | Awaiting Commission Direction | ROS/WMS |  | Completed |  | PDCWG PDCWG recommends creation of a temporary task force to review ERCOT's Ancillary Services Methodology |  | WMWG Planning for joint meeting with PDCWG in July |  | SB3 NPRR1096, NPRR1093, NOGRR232, OBDRR032, OBDRR033
107 |  | ROS Generation-Related Items | 45 | ROS | Frequency: Analyze system frequency leading up to Energy Emergency Alert conditions and determine impact of low frequency on generation and load tripping. Combine with Item 30 | Long-Term Stakeholder Items | ROS |  | Completed |  | PDCWG Allow NOGRR226 to work through stakeholder process. PDCWG recommends creation of a temporary task force to review ERCOT's Ancillary Services Methodology
108 |  | ROS Generation-Related Items | 46 | ROS | Station Service: Consider rule changes for turning off station service load at resources that are unavailable during EEA conditions. | Long-Term Stakeholder Items | ROS/WMS |  | Completed |  |  |  | WMWG |  |  | Was discussed at WMWG; No recommended changes, no further action requested
109 |  | ROS Transmission-Related Items | 47 | ROS | Transmission Planning Studies: Review existing transmission planning study assumptions and processes and determine if any adjustments are needed to adequately prepare for future extreme weather events including changes in assumptions for demand, generation, dispatch, and system constraints. | Long-Term Stakeholder Items | ROS |  | In Progress |  | PLWG PLWG continuing review (common mode failures, potential planning criteria updates, definitions for extreme events, timing of studies)
91 |  | ROS General Items | 48 | ROS | Emergency Response Service (ERS) Program: Review performance of ERCOT’s ERS Program during the February 2021 Winter Weather Event and determine if any adjustments to the program is needed based on those findings. Request ERCOT provide report on ERS performance to DSWG. Report/presentation should include: - ERS contract term procurement results specifics (and add amounts offered but not procured for SCT) - Deployment specifics (times, amounts, self-deployments, entirety of EEA event and recovery, weather-sensitive vs. Non-weather sensitive, connectivity details (Transmission vs. Distribution), problems in deploying, initial observations/quick changes needed, % of ERS allotment spent, effect on remaining SCTs for 2021, etc.) 2. Direct DSWG to review the information presented by ERCOT. Develop list of lessons learned. Assign champions for additional discussion and recommendations to WMS. Report to WMS on both the ERCOT findings and DSWG recommendations. | Near-Term Stakeholder Items | ROS/WMS |  | Completed |  |  |  | DSWG ERCOT has established a lessons learned list PRS recommended approval of NPRR1090 with Urgency; DSWG to determine if any additional action is needed
92 |  | ROS General Items | 49 | ROS | Energy Emergency Alert: Review EEA rules and assess if any changes are warranted. Look into issues going into and out of EEA and whether directives were appropriate. | Near-Term Stakeholder Items | ROS/WMS |  | Completed |  | OWG, PLWG |  | WMWG |  | NPRR1094, NPRR1105, NPRR1106 | See NPRRs that have been submitted WMS will consider market impacts of any future changes
97 |  | ROS Load-Related Items | 50 | ROS | Demand Response: Review demand response performance during the event. Request ERCOT to provide report/presentation on Demand Response over the event. Would include both REP and NOIE area data. Would be limited to existing data. Direct DSWG to review the information presented by ERCOT. Develop list of lessons learned. Assign champions for additional discussion and recommendations to WMS. Report to WMS on both the ERCOT findings and DSWG recommendations. | Near-Term Stakeholder Items | ROS/WMS |  | Completed |  |  |  | DSWG Have reviewed DR performance during Uri for REP and NOIE areas; education session on LR providing RRS planned for future DSWG meeting; NPRR1087 recommended for approval with urgency; DSWG to determine if any additional action is needed
110 |  | ROS Transmission-Related Items | 51 | ROS | Review GTC Management Process during EEA3: Analyze how much generation was curtailed behind GTCs during EEA3 and assess if changes are warranted around GTC management during emergency conditions. Tied to Items 29 and 86; Combine with #86 | Near-Term Stakeholder Items | ROS |  | Not Started |  | OWG, PLWG |  |  |  | Combined with item 86
54 | Credit |  | 52 | WMS | Should Collateral and Settlement be netted at CP level? | Near-Term Stakeholder Items | WMS | High | Completed | Market Settlements |  | Item 8 | MCWG |  |  | Ongoing work at MCWG
66 |  | Other Items from WMS | 53 | WMS | Should DSP circuits be granular enough to allow for rotating outages? Compare how different utilities managed load shed. What amount of load loss prohibits rolling black out? | Outside the Stakeholder Purview |  |  | Not Started | Project No . 51888, Review of Critical Load Standards and Processes
30 | Pricing |  | 54 | WMS | Shouldn’t protocols be changed to include firm load shed in RDPA to reflect commission order ? | Near-Term Stakeholder Items | WMS |  | Completed | Project No . 51888, Review of Critical Load Standards and Processes |  |  | NPRR1081 addressed this item
77 |  | Other Items from WMS | 55 | WMS | Should critical infrastructure be prohibited from participating in demand response programs, at least during severe weather events? | Awaiting Commission Direction |  |  | Completed | Project No . 51888, Review of Critical Load Standards and Processes |  |  |  |  | NPRR1087
42 | Planning & Operating Reserves |  | 56 | WMS | Improve situational awareness by identifying all NG infrastructure that is critical for power plants, Identifying firm and non-firm supply power plants. Should payments for NG storage closer to NG plants be considered to avoid counting a major supply on long haul transport? | Outside the Stakeholder Purview |  |  | Not Started | Project No . 51888, Review of Critical Load Standards and Processes |  |  | RCWG/WMWG
70 |  | Other Items from WMS | 57 | WMS | Should products that directly expose residential consumers to wholesale market prices be allowed? | Awaiting Commission Direction |  |  | Awaiting Commission Project | Project No . 51830 : Review of Wholesale - Indexed Products for Compliance with Customer Protection Rules for Retail Electric Service |  |  |  |  | HB16
74 |  | Other Items from WMS | 58 | WMS | Should there be enhancements to the Gas Electric Working Group scope and activities to improve participation and effectiveness? Are the protocol 3.21.1 requirements regarding gas pipeline coordination for summer preparedness effective and are similar requirements for winter preparedness needed? | Awaiting Commission Direction |  |  | Not Started | Project No . 51839 , Electric - Gas Coordination |  | Item 3 |  |  | SB3
67 |  | Other Items from WMS | 59 | WMS | Should there be a formal coordination process between the entities responsible for regulating electricity, water, and natural gas? | Awaiting Commission Direction |  |  | Awaiting Commission Project | Project No . 51839 , Electric - Gas Coordination |  |  |  |  | SB3
76 |  | Other Items from WMS | 60 | WMS | Request to review the availability of blackstart units and consider potential process improvements including priority for non-curtailment of gas supply to ensure availability during extreme weather events | Awaiting Legislative Direction |  |  | Not Started | Project No . 51839 , Electric - Gas Coordination |  | Item 3 |  |  | Combined with Item 34
40 | Planning & Operating Reserves |  | 61 | WMS | How should capacity reports be modified to include gas market coincident and offsetting risks with electric system? | Long-Term Stakeholder Items | WMS | Medium | Completed | Project No . 51839 , Electric - Gas Coordination |  |  | SAWG Caitlin Smith, Lori Simpson assigned as leads This will continue to be discussed as part of ongoing SAWG work
48 | ERS / Demand Response | ERS | 62 | WMS | Should all prospective (and existing) Load Resources and ERS loads that are classified as essential to the transportation, compression, processing, and delivery of natural gas or any other power generation fuel not be allowed to participate as LR or ESR? | Near-Term Stakeholder Items | WMS |  | Completed | Project No . 51839 , Electric - Gas Coordination |  |  | DSWG Did we place conflicting risks on any ERS loads? DSWG to discuss with participants any conflicts that arose regarding ERS performance with input from ERCOT, and provide details to WMS. NPRR1087 approved by PRS DSWG to determine if any additional action is needed |  | NPRR1087
68 |  | Other Items from WMS | 63 | WMS | Should there be a uniform process for identifying and updating critical infrastructure across all industries that are needed in producing electricity, gas, and water? | Awaiting Commission Direction |  |  | Not Started | Project No . 51839 , Electric - Gas Coordination Project No . 51888, Review of Critical Load Standards and Processes
82 |  | Other Items from WMS | 64 | WMS | To harden critical infrastructure should - ERS be expanded - new program like ERS be created to support DERs - encourage stand-alone self-contained microgrids. - encourage installation of fuel storage at or near gas plants - Install backup batteries/DG at critical facilities | Outside the Stakeholder Purview | WMS |  | Awaiting Commission Project | Project No . 51839 , Electric - Gas Coordination Project No . 51888, Review of Critical Load Standards and Processes |  |  | DSWG Awaiting commission direction before addressing |  | SB3 Not all items in this topic are covered by legislative action
64 |  | Other Items from WMS | 65 | WMS | Should there be enforceable standards for summer and winter weatherization to account for extreme temperatures in both seasons? | Awaiting Commission Direction |  |  | Not Started | Project No . 51840 , Rulemaking to Establish Weatherization Standards |  |  |  |  | SB3
75 |  | Other Items from WMS | 66 | WMS | Are existing winter weatherization related ERCOT requirements, preparations, and processes, including protocol 3.21, sufficient and are there any gaps or improvements that should be considered, including standardized requirements? | Awaiting Commission Direction |  |  | Not Started | Project No . 51840 , Rulemaking to Establish Weatherization Standards |  |  |  |  | SB3
22 | Pricing |  | 67 | WMS | Should DAM design for pricing AS be changed? Should ASDC be implemented in DAM. If not, should AS price be capped at $9,000/MW/hr? If not, should there be market participant training developed and notice sent explaining how maximum A/S MCPC can be $27k versus $9k. | Near-Term Stakeholder Items | WMS |  | Completed | Project No. 51871, Review of the ERCOT Scarcity Pricing Mechanism |  |  | NPRR1080 addressed AS capping; review of ASDC in DAM remains open |  | NPRR1080 addressed AS capping | NPRR1080; monitor 51871 and can revisit upon completion of 51871
78 |  | Other Items from WMS | 68 | WMS | Should LCAP be capped at $9k? | Near-Term Stakeholder Items | WMS |  | Completed | Project No. 51871, Review of the ERCOT Scarcity Pricing Mechanism |  |  | NPRR1086 addressing this item received PUC approval 8/19/21 |  | NPRR1086
55 | Settlement | Default Uplift | 69 | WMS | Should $2.5M/monthly default uplift be revisited? How should the $2.5M cap of default uplift per month be changed? | Near-Term Stakeholder Items | WMS | High | Completed | Project No. 51871, Review of the ERCOT Scarcity Pricing Mechanism |  |  | MCWG |  | SB1580 and HB4492 addressed instant defaults. Should be able to address remaining items in the stakeholder process. | Ongoing work at MCWG
57 | Settlement | Default Uplift | 70 | WMS | What changes to ERCOT settlements and market uplift processes are needed as a result of this event? | Near-Term Stakeholder Items | WMS |  | Completed | Project No. 51871, Review of the ERCOT Scarcity Pricing Mechanism |  | Item 8 |  |  | Not addressed by the Legislature and don't believe we need a Commission project to be completed to start. | Within MSWG scope, can be taken up in the future
59 | Settlement | Fuel Costs | 71 | WMS | Should there be make whole payments for extremely high fuel costs during EEA3? | Near-Term Stakeholder Items | WMS |  | Completed | Project No. 51871, Review of the ERCOT Scarcity Pricing Mechanism |  |  | RCWG/WMWG NPRR1086 partially addressed |  | NPRR1086 | NPRR1086 addressed this scenario during LCAP events No additional recommendations or work offered
62 | Settlement | Fuel Costs | 72 | WMS | How do we ensure that generation resources are being compensated for firm fuel arrangements? | Outside the Stakeholder Purview | WMS |  | Awaiting Commission Project | Project No. 51871, Review of the ERCOT Scarcity Pricing Mechanism |  |  | RCWG/WMWG |  | SB3
79 |  | Other Items from WMS | 73 | WMS | Should there be different PRC EEA trigger point & ORDC minimum reserves levels for winter and summer given potential for different events? | Near-Term Stakeholder Items | ROS/WMS |  | Completed | Project No. 51871, Review of the ERCOT Scarcity Pricing Mechanism | OWG |  | WMWG |  |  | Can revisit upon completion of 51871
81 |  | Other Items from WMS | 74 | WMS | Should ERCOT’s conservation appeal during winter-time include a defined period for conservation, instead of a blanket request to appeal without a defined time period for conservation? | Awaiting Commission Direction |  |  | Awaiting Commission Project | Project No . 51871 , Review of the ERCOT Sccircity Pricing Mechanism Project No . 51889, Review of Communications for the Electric Market |  |  | DSWG
69 |  | Other Items from WMS | 75 | WMS | Should there be a statewide communication mechanism to provide information in easy-to-understand terms for consumers before and during emergency event. | Awaiting Commission Direction |  |  | Awaiting Commission Project | Project No. 51889, Review of Communications for the Electric Market |  | Item 2 |  |  | SB3
72 |  | Other Items from WMS | 76 | WMS | Request for Review of: - ERCOT governance structure and identification of potential improvements to ERCOT bylaws and stakeholder process - ERCOT communications to the public and to stakeholders before, during, and after the event and identification of communication plan improvements - ERCOT’s emergency response plan and role in emergency preparedness and response before, during, and after the event; identification of process improvements | Outside the Stakeholder Purview |  |  | Not Started | Project No. 51889, Review of Communications for the Electric Market |  |  |  |  | SB2 and SB3
65 |  | Other Items from WMS | 77 | WMS | Should there be a set reliability requirement? | Awaiting Commission Direction |  |  | Awaiting Commission Project | Project No. 51841, Review of 16 TAC § 25.53 Relating to Electric Service Emergency Operations Plans |  |  |  |  | SB3
71 |  | Other Items from WMS | 78 | WMS | Request for an overall assessment and root cause analysis of this event (submitter provided comments and questions regarding the process and content for the assessment) | Outside the Stakeholder Purview |  |  | Not Started | Project No. 51841, Review of 16 TAC § 25.53 Relating to Electric Service Emergency Operations Plans |  |  |  |  | This is such a broad item. I suggest we close it out since there are so many entities doing this review that it makes it inappropriate for stakeholders to step into it.
73 |  | Other Items from WMS | 79 | WMS | Request for benchmarking effort with other North American RTOs and ISOs to identify best practices and improvement opportunities in topics from post-event assessment | Outside the Stakeholder Purview |  |  | Not Started | Project No. 51841, Review of 16 TAC § 25.53 Relating to Electric Service Emergency Operations Plans |  |  |  |  | Overly Broad
28 | Pricing |  | 80 | WMS | How did the resource adequacy incentives, including scarcity pricing mechanism, perform for promoting resource adequacy? Are alternative market design approaches necessary to promote/ensure resource adequacy? | Outside the Stakeholder Purview | WMS |  | Awaiting Commission Project | Project No. 51871, Review of the ERCOT Scarcity Pricing Mechanism |  |  |  |  | Project 52373
29 | Pricing |  | 81 | WMS | What is the best way to ensure prices are consistent with market design during load shed? | Awaiting Commission Direction | WMS |  | Completed | Project No. 51871, Review of the ERCOT Scarcity Pricing Mechanism | [5 empty] | No stakeholder action at this time; monitor PUC project and consider under normal course of business if/when necessary Allow market design changes to be finalized before considering further action
80 |  | Other Items from WMS | 82 | WMS | How should intermittent nature of renewable resources be accounted for to ensure proper dispatchable capacity is available to meet energy demands | Awaiting Commission Direction |  |  | Awaiting Commission Project | [5 empty] | SB3
21 | Pricing |  | 83 | WMS | Should there be a minimum market notice & timeline for design changes that impact prices so as to allow MPs time for hedging? | Long-Term Stakeholder Items | WMS |  | Completed |  |  |  | WMWG |  |  | Long term item, can be taken up under existing working group scope
24 | Pricing |  | 84 | WMS | Should TCEQ exempt MWs be priced at a floor of $1500/MWh or higher? If ERCOT RUCs the resource, how is the resource compensated for lost opportunity of using the emissions limit during other scarcity time Vs the RUCed time? | Long-Term Stakeholder Items | WMS |  | Completed |  |  |  | RCWG/WMWG |  |  | Long term item, can be taken up under existing working group scope
26 | Pricing |  | 85 | WMS | How did exceptional fuel price process work? | Long-Term Stakeholder Items | WMS |  | Not Started |  |  |  | RCWG/WMWG
27 | Pricing |  | 86 | WMS | Review constraint management process during EEA3 and assess if changes are warranted: How much generation was curtailed for congestion including GTC during EEA3? | Long-Term Stakeholder Items | ROS/WMS | Medium | Completed |  | OWG, PLWG Joint OWG/CMWG discussions at 6/14, 7/19, 8/16 CMWG meetings |  | CMWG |  | Current procedures outline when ERCOT constraint management actions are taken; NSA Inactive & Active Constraints reports provide market visibility
31 | Planning & Operating Reserves |  | 87 | WMS | What changes are needed to the reserve margin target, reserve margin calculation methodologies used for the CDR and SARA, and planning reserve margin studies including EORM and MERM to account for impacts from this event? Should CDR be changed to better reflect climate change and extremes such as the 2011 heat events and the 2021 Polar Vortex. – average Vs extreme sensitivities Vs worst case scenarios? How to reflect reliability risk in CDR and SARA? Coordinate with Item 88 | Long-Term Stakeholder Items | WMS | High | Completed |  |  | Item 4 | SAWG Ongoing work for winter SARA This will continue to be discussed as part of ongoing SAWG work
32 | Planning & Operating Reserves |  | 88 | WMS | Request to accelerate ongoing efforts to improve the CDR and SARA and incorporate probabilistic modeling approach to evaluate the risk of various magnitudes of ERCOT emergency events. If existing deterministic scenario is retained, consider revisions to account for more extreme and overlapping events. Consider actions to be taken based on resource adequacy report results. Coordinate with Item 87 | Long-Term Stakeholder Items | WMS | High | Completed |  |  | Item 4 | SAWG Working is ongoing for summer 2021 probabilistic model This will continue to be discussed as part of ongoing SAWG work
33 | Planning & Operating Reserves |  | 89 | WMS | Should there be different PRC EEA trigger point for winter and summer given potential for different events? | Long-Term Stakeholder Items | ROS/WMS |  | Not Started |  |  |  | WMWG
34 | Planning & Operating Reserves |  | 90 | WMS | Are the existing suite of Ancillary Service products and quantities adequate to ensure reliability or are changes needed? Combine with #44 | Long-Term Stakeholder Items | WMS |  | Not Started |  |  |  | WMWG |  | Combined with Item 44
35 | Planning & Operating Reserves |  | 91 | WMS | Could fast frequency response play a bigger role? | Long-Term Stakeholder Items | ROS/WMS |  | Completed |  | PDCWG Allow NOGRR226 to work through stakeholder process. PDCWG recommends creation of a temporary task force to review ERCOT's Ancillary Services Methodology. |  | WMWG Proposals to increase participation from ESRs (set FFR offer floor $0.01 below LR_RRS floor in DAM engine; enable batteries to provide RRS using ONSC status) were presented and an opinion paper concluding that underprocurement of a single AS product was not an issue during URI was discussed; further discussions to be held at PDCWG
37 | Planning & Operating Reserves |  | 92 | WMS | Should the Reliability Must Run (RMR) processes be extended to units proposed for seasonal mothball? Are the RMR and Must Run Alternative study and processes sufficient or are changes to study parameters, such as winter peak-, planned/forced outage-, or resource dispatch-scenarios, needed? Combine with Item 43 | Long-Term Stakeholder Items | ROS/WMS |  | Not Started |  |  |  | WMWG |  | Combined with Item 43
38 | Planning & Operating Reserves |  | 93 | WMS | Are adjustments to the load forecasting methodology, scenario analysis and trend analysis needed in light of this event? | Long-Term Stakeholder Items | ROS/WMS | High | Completed |  | PLWG/SSWG |  | SAWG |  |  | was addressed in a joint SAWG/PLWG meeting; long term item and will continue to be taken up in future meetings
39 | Planning & Operating Reserves |  | 94 | WMS | How should we revise extreme winter cases for planning assessments? Would like to start with review of changes made to March SARA | Long-Term Stakeholder Items | ROS/WMS | High | Completed |  | PLWG/SSWG |  | SAWG |  |  | taken up within ongoing SAWG work; should continue to be discussed by ERCOT staff in coordination with/direction from PUC
41 | Planning & Operating Reserves |  | 95 | WMS | What were the costs, benefits, and constraints of dual fuel and fuel storage? Are there potential market incentives based on lessons learned from this event? | Long-Term Stakeholder Items | WMS |  | Completed |  |  |  | WMWG |  |  | Long term item; can be taken up under normal WMWG scope
47 | ERS / Demand Response | DR | 96 | WMS | How did DR perform? Should UFR deployed beyond the period of it obligation be compensated for the deployment? Should A/S Imbalance Charge to deployed Load Resources be revisited? | Long-Term Stakeholder Items | WMS |  | Completed |  |  |  | DSWG/WMWG/SAWG DSWG has completed DR performance review; AS items to be worked with WMWG (Mike Hourihan, Holly O'Neill leads for DSWG)
49 | ERS / Demand Response | ERS | 97 | WMS | Did we place conflicting risks on any ERS loads? DSWG to discuss with participants any conflicts that arose regarding ERS performance with input from ERCOT, and provide details to WMS. | Long-Term Stakeholder Items | WMS |  | Completed |  |  |  | DSWG |  | Combined with Item 62
50 | Distributed Generation | DER | 98 | WMS | Could more DERs have helped? In addition to settlement-only DERs (between 1 and 10 MWs) is more needed to be done for a heavy-version of DERs so they can compete in energy and ancillary market more directly or is the current DER-light approach good enough? | Long-Term Stakeholder Items | WMS |  | Completed |  |  |  | DSWG SODG RFI summary provided by ERCOT; DGR will be a future topic with completion targeted for Q1-2022
25 | Pricing |  | 99 | WMS | Review converge of ORDC & PRC during the event. | Near-Term Stakeholder Items | WMS |  | Completed |  |  |  | WMWG Review complete; recommends to account load curtailment in ORDC calculation; ERCOT has submitted NPRR1081; item will remain open while longer term items continue to be reviewed
36 | Planning & Operating Reserves |  | 100 | WMS | How did batteries providing FFR perform? Were FFR providers allowed to charge and if not, what penalties did they get charged? | Near-Term Stakeholder Items | ROS/WMS |  | Completed |  | PDCWG No ESR bid for FFR during time of Feb 14/15 winter event |  | WMWG WMWG to determine if any additional review is needed
43 | ERS / Demand Response | ERS | 101 | WMS | What % of $50M for ERS was used during winter period? Combine with Item 48 | Near-Term Stakeholder Items | ERCOT |  | Completed |  |  |  | DSWG Spend $12,455,453 for Feb1-23 and Spend $7,675,163 for Feb 24- May
44 | ERS / Demand Response | ERS | 102 | WMS | Did ERS work well during crisis? Are any modifications needed? Combine with Item 48 | Near-Term Stakeholder Items | ERCOT |  | Completed |  |  |  | DSWG ERS Loads generally over-provided 30%-35% above the combined fleet-level obligation during the Winter Event. ERS Generators generally failed to meet their combined obligation during the Winter Event - 50%-55% below the combined fleet-level obligation due to forced outage
45 | ERS / Demand Response | ERS | 103 | WMS | How much of the ERS load is from transmission connected load vs distribution connected and how much transmission connected load self-curtailed? Combine with Item 48 | Near-Term Stakeholder Items | WMS |  | Completed |  |  |  | DSWG ERCOT findings presented at 8/4/21 WMS meeting
46 | ERS / Demand Response | ERS | 104 | WMS | If ERCOT had more flexibility to increase ERS resources would it have helped? Combine with Item 48 | Near-Term Stakeholder Items | WMS |  | Completed |  |  |  | DSWG DSWG generally believes more response, including ERS, as well as more generation, would have helped; Any additional data/findings will be reported to WMS
51 | Distributed Generation | SODG | 105 | WMS | How did SODG perform? | Near-Term Stakeholder Items | ERCOT |  | Not Started |  | PLWG |  | SAWG
52 | DC Ties | DC Ties | 106 | WMS | How did DC ties perform during the event? Are there any impacts to planning assumptions and other DC tie policies as a result of this event? Combine with #41 | Near-Term Stakeholder Items | ROS/WMS | Medium | Not Started |  | PLWG, OWG |  | SAWG |  | Combined with Item 41
53 | Credit |  | 107 | WMS | What enhancements to the existing credit/collateral requirements and overall credit risk management policies are needed as a result of this event? | Near-Term Stakeholder Items | WMS | Medium | Completed |  |  | Item 8 | MCWG |  |  | Ongoing MCWG work
56 | Settlement | DC Ties | 108 | WMS | Should correct credit calcs for DC Tie import/export during EEA be corrected as RTLE is based on history of value which could be exporting power while during EEA it would be importing? | Near-Term Stakeholder Items | WMS |  | Completed |  |  |  | MCWG |  |  | Ongoing MCWG work
58 | Settlement | Default Uplift | 109 | WMS | What is the potential default uplift exposure for different entities? - MMARS of all counterparties that have defaulted, for Municipalities, for Coops, for other entities with short pay but not defaulted. - Total Accumulated Short Pay for defaulted Counterparties, for Municipalities or coops that have not yet defaulted, for other Counterparties that have not yet defaulted - Total credit instruments exercised and unexercised | Near-Term Stakeholder Items | ERCOT | High | In Progress |  |  | Item 8 | MCWG
61 | Settlement | Default Uplift | 110 | WMS | Should money pulled from CARD revenue be included in determining default uplift? | Near-Term Stakeholder Items | WMS | Medium | Completed |  |  |  | MCWG |  |  | Ongoing MCWG work
63 | Settlement |  | 111 | WMS | Should credit exposure calculations be based on net DA and RT activity using preliminary RT pricing and net DART daily invoices, instead of extrapolations from recent activity exposure with RT and DA activity invoiced separately on the staggered timeline they are now invoiced on? Compare with how it is done in other ISOs. | Near-Term Stakeholder Items | WMS | Medium | Completed |  |  |  | MCWG Reviewed default uplift practices in ISO NE, MISO, CAISO, PJM |  |  | Ongoing MCWG work
23 | Pricing |  | 112 | WMS | Are changes to the use/applicability of Peaker Net Margin methodology needed to protect ratepayers during extended scarcity events? | Outside the Stakeholder Purview | WMS |  | Awaiting Commission Project |  |  |  | SAWG WMS will assign this upon receiving commission direction |  | SB3 Emergency Pricing Rule
|  |  | 113 | Summer Assessment | Switchable Generation Resources (SWGRs): o Make sure settlement, operator interaction and offers align with the intent of the Protocols and intended market design. o If necessary, propose changes to the Protocols o Exelon Items | Near-Term Stakeholder Items | WMS |  | Completed | [6 empty] | No WMS Recommendation; can be taken up under normal stakeholder process in the future if necessary
|  |  | 114 | Summer Assessment | Emergency Response Service (ERS): o Crossover between procurement time periods and calculation of the adder. o Self-deployment of ERS. | Near-Term Stakeholder Items | WMS |  | Completed | [6 empty] | Ongoing work at DSWG
|  |  | 115 | Summer Assessment | Credit/Collateral for QSE representing Resource only. o The potential default of a QSE representing a Resource instead of a trader only or Customer Load has raised some potential gaps/policy considerations for improvement. (e.g. should a generator be taken out of markets during tight conditions?) | Near-Term Stakeholder Items | CWG/MCWG |  | Completed | [6 empty] | Ongoing work at MCWG
|  |  | 116 | Summer Assessment | Evaluate current TCEQ enforcement discretion process and look for improvements with managing potential emission limitation issues. | Long-Term Stakeholder Items | WMS |  | Completed | [6 empty] | No WMS Recommendation; can be taken up under normal stakeholder process in the future if necessary
|  |  | 117 | Summer Assessment | Development of probabilistic SARA and net load forecast. Review of Resource Adequacy forecasts with evaluation and possible implementation of probabilistic SARA and net load forecast as supplements to current Resource Adequacy reports. | Long-Term Stakeholder Items | WMS |  | Completed |  |  |  | SAWG Working is ongoing for summer 2021 probabilistic model This will continue to be discussed as part of ongoing SAWG work
|  |  | 118 | Stakeholder | Can a new REP be formed by individuals associated with a defaulted REP? Will the default amount caused by market participants leaving the market (e.g. default/bankruptcy) from the February event be allocated to new and existing market participants? | Outside the Stakeholder Purview | RMS/WMS | Medium | Not Started |  |  |  | MCWG NPRR1073 received PUCT approval 8/19/2021 and partially addresses this item | Outside Stakeholder purview REP Certification Rule addressed by NPRR1073 & 1067. Commission Staff reviewing 25.107 for policy considerations for "mass transition event" as it does not address "default" HB4492, Subchapter M clarifies Uplift process allocated to new MPs.
|  |  | 119 | WMS | Develop and implement updated methodology used to determine cost of new entry (CONE) ERCOT to file NPRR based on Aug 2020 SAWG consensus ahead of April PRS; planning on April SAWG | Near-Term Stakeholder Items | WMS | High | Completed |  |  |  | SAWG Developed draft NPRR with study timeline for developing new CONE values; on hold pending PUC action; if needed for EORM or MERM, methodology will be brought to SAWG
|  |  | 120 | Lori Simpson (Constellation) | How batteries qualify for AS and the impact of their duration limits. | Near-Term Stakeholder Items | ROS |  | Completed |  | PDCWG ESR qualifications for AS and duration/charging requirements were defined by a set of 9 NPRRs that stakeholders developed in the Battery Energy Storage Task Force
|  |  | 121 | Eric Easton (CNP) | Assessment of dynamic stability had the underfrequency relays asserted during the winter storm event. Given the amount of non-underfrequency load shed, the percentage of underfrequency load in-service had increased. If the increased percentage of underfrequency load had been shed would generation remain stable? | Long-Term Stakeholder Items | ROS |  | Not Started |  | PDCWG, DWG
|  |  | 122 | Eric Easton (CNP) | Review the use of dynamic load shed ratios which more closely align with the specific event and changes in load density by comparing the static load shed table to the dynamic (actual) load ratio shares during the winter event. | Long-Term Stakeholder Items | ROS |  | Completed |  | OWG SB3 requires seasonal load shed obligations. Concern about complexity of calculating / communicating load shed obligations in real-time. No recommended changes.
|  |  | 123 |  | Review UFE outcomes from Winter Storm Uri - Initial UFE, then running UFE during days of storm, any solutions; allocation of UFE; request ERCOT present February UFE Report to WMS | Near-Term Stakeholder Items | WMS |  | Completed |  |  |  | MSWG, WMWG (invite PWG) February UFE analysis presented at June WMS
|  |  | 124 |  | Summer Assessment Item: Non-Frequency Responsive Capacity (NFRC) versus Physical Responsive Capability (PRC) reserves when Gen RRS is released | Near-Term Stakeholder Items | ROS |  | Not Started |  | PDCWG
|  |  | 125 |  | Demand Billing Considerations for C&I customers | Near-Term Stakeholder Items | RMS |  | Not Started |  |  |  |  | Added 6/23 Currently, TDSPs do not cancel & rebill Demand for C&I customers unless otherwise directed by the PUCT. Addressed this topic via Addendum for Prolonged, Widespread Outage matrix.
|  |  | 126 |  | Do the TDSPs utilize other data practices during prolonged, wide-spread outages which may deviate from normal VEE processes? (major outage events) | Near-Term Stakeholder Items | RMS |  | In Progress |  |  |  |  | Added 6/23 Combined with #18 -- Addendum for Prolonged, Widespread Outage matrix.
|  |  | 127 |  | Clarify Protocol language addressing processes for payment plans | Near-Term Stakeholder Items | ERCOT |  | In Progress |  |  |  | MCWG/CWG New Item added at 6/23 TAC
|  |  | 128 |  | Emergency Operational Communications: Evaluate opportunities to improve emergency operational communications between ERCOT and market participants. Consider Instant Messaging communication system similar to SPP’s R-COMM to reduce reliance on voice communications during emergency events. | Near-Term Stakeholder Items | ROS |  | In Progress |  | OWG 7/8/21 ROS - created new item that focuses on improving emergency operational communication between ERCOT and market participants
Note on B1: Boren, Ann: Should we come up with more general categories for this column?
Note on C1: Boren, Ann: This might columnn may be overkill - we may just want to take this out.

## RefTables
Owners
ERCOT
PRS
RMS
ROS
TAC
WMS
ROS/WMS/RMS
CWG/MCWG
RMS/WMS
ROS/WMS
TACPriority
High
Medium
Low
Status
Not Started
In Progress
Awaiting Commission Project
On Hold
Completed
Timing
Awaiting Legislative Direction
Near-Term Stakeholder Items
Long-Term Stakeholder Items
Awaiting Commission Direction
Outside the Stakeholder Purview
Category
Communication
Data
Default
Procedural
Pricing
Planning & Operating Reserves
ERS / Demand Response
Distributed Generation
DC Ties
Credit
Settlement

## Process
Process for modification of Emergency Conditions List
• Most recent spreadsheet will be posted on the TAC Landing Page
• Working Group edits on the List will be taken to Subcommittee for review
• Subcommittees will review and incorporate WG and other suggested edits as “Subcommittee Comments” to present to TAC - Comments should be made in the applicable color-coded column
• TAC will review Subcommittee comments and incorporate changes into the master spreadsheet
• Independent edits can be sent to RevisionRequest@ercot.com – these will be referred to a subcommittee/TAC for review as applicable