## Slide 1
Project Update
January 13, 2022
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2021 Release Targets (final)
  2022 Release Targets
  In-Flight Strategic Projects
    Fast-Frequency Response (FFR) Advancement
    DGR/DESR Implementation
    BES Combo Model Implementation
  Securitization Update
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1112 – Elimination of Unsecured Credit Limits
    NPRR1114 – Securitization – PURA Subchapter N Uplift Charges
    SCR818 – Changes to Incorporate GIC Modeling Data into Existing Modeling Applications
    PGRR099 – Revise GIM Process to Ensure Compliance w/Lone Star Infrastructure Protection Act
  ERCOT Technology Working Group – Venkat Tirupati
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 January Go-live – 1/1/2022 Complete
  NPRR1073 – Market Entry/Participation by Principals of Counter-Parties with Financial Obligations
  NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
  PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
  NOGRR212 – Related to NPRR1016
2022 February Release – 2/1/2022-2/3/2022 In Flight
  NPRR917 – Nodal Pricing for SODGs and SOTGs
  NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
  NPRR1065 – Implementation Adjustment for NPRR917
  NPRR1005 – Clarify Definition of Point of Interconnection (POI) and Add Definition Point of Interconnection Bus (POIB)
  NOGRR210 – Related to NPRR1005
  RRGRR025 – Related to NPRR1005
  NPRR1054 – Removal of Oklaunion Exemption Language
    Partial implementation
  LPGRR068 – Add BUSLRG and BUSLRGDG Profile Types
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Recent / Upcoming Project Highlights
2022 March Release – 3/29/2022-3/31/2022 In Flight
  SCR814 – Point-to-Point (PTP) Obligation Bid Interval Limit
2022 May Release – 5/24/2022-5/26/2022 In Flight
  NPRR939 – Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions
  NPRR1093 – Load Resource Participation in Non-Spinning Reserve
  NPRR1101 – Create Non-Spin Deployment Groups made up of Generation Resources Providing Off-Line Non- Spinning Reserve and Load Resources that are Not Controllable Load Resources Providing Non-Spinning Reserve
  SCR800 – Addition of DC Tie Ramp to GTBD Calculation
  SCR809 – Changes to External Telemetry Validations in Resource Limit Calculator
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 5: 2021 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/2 – 2/4 | April 3/30 – 4/1 | May 5/25 – 5/27 | July 7/27 – 7/29 | October 10/5 – 10/7 | December 12/7 – 12/9
NPRR902(a) NOGRR195 NPRR1055 OBDRR023(a) NPRR1020 SCR804 | NPRR971 NPRR986 NPRR998 NPRR1024 NPRR1043 NOGRR213 VCMRR027 PGRR070 NPRR1060 | NPRR974 NPRR978(c) NPRR1048 NPRR1051 SCR811 ECMS ECMS NPRR1080 OBDRR030 NPRR1081(a) | NPRR902(b) NPRR905 SCR789 NPRR1062 RMGRR164 NPRR1031 RRGRR026 NPRR867 NPRR1081(b) | None NPRR984 OBDRR023(b) | None SCR781
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR902(a) – ECEII Market Participant MPIM role
NPRR902(b) – MIS links updated for ECEII reports
NPRR978(c) – Forecast Zone scope
NPRR1081(a) – Manual implementation
NPRR1081(b) – Automated solution
OBDRR023(a) – ERS Expenditure Limit
OBDRR023(b) – 4 Standard Contract Terms/Year
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 879, 885, 904, 918, 930, 935(b), 936, 941, 945, 962, 965, 1004, 1006, 1019, 1023, 1030, 1032, 1034, 1040, 1057 SCRs: 799, 805, 809, 812 Market Guides: PGRR066, PGRR076 Other Binding Docs: OBDRR009
E
Replace NoticeBuilder
ECMS
11/17 – 11/20
New navigation
1/1
ü
ü
ü
2/1
10/1
5/1
3/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
4/22
ü
6/1
ü
RIOO – 12/20
Interconnection requests of less than 10MWs and DGRs
6/25
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
New public version of ERCOT.com homepage
ü
7/1
7/14
7/23
8/1
ü
ü
ü
ü
ü
ü
September
Various Dates
ü
ü
ü
ü
ü
ü

## Slide 6: 2022 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/1 – 2/3 | March 3/29 – 3/31 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NPRR917 NPRR1016 NPRR1052 NPRR1065 NOGRR212 PGRR082 NPRR1073 NPRR1016 PGRR082 NOGRR212 | SCR800 SCR809 SCR814 | NPRR939 NPRR1093 NPRR1101 SCR800 SCR809 | TBD | FFR Advancement (NPRR863 FFR) | TBD
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
P
P
P
P
P
E
E
E
E
E
E
Securitization Subchapter N March Go-Live
ECRS project starts in 1/2022 with a go-live target prior to the EMS Freeze
1/1
P
EMS Freeze
Mid-2023 – Mid-2024
E
ü
ü
ü
ü
DGR/DESR
NPRR1054(a) – Portion of gray box

## Slide 7: In-Flight Strategic Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on 6/22/2021)
    Planned go-live for 2021-R6 (December 2021)
    NPRR863, NPRR1015, NPRR1079, NOGRR187
  PR354-01 DGR/DESR Implementation (Gated to Execution phase on 7/30/2021)
    Target go-live 2022-R1 (February 2022)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
  PR353-01 BES Combo Model Implementation – potential for multiple go-lives
    Target go-live TBD (core project On Hold until resources are available)
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
ESR: Energy Storage Resource
DGR: Distributed Generation Resource
BES: Battery Energy Storage
Blue text: ERCOT considering removing from project for earlier delivery
Revised go-live target = 2022-R5
Orange text: 1/1/2022 go-live for DGR/DESR registration purposes

## Slide 8: Securitization Update
For latest information, see presentation posted with 1/5/2022 WMS materials
NPRR1103 Securitization – PURA Subchapter M Default Charges
  Approved by Board of Directors on 12/10/2021
  Approved by PUCT on 12/16/2021
NPRR1114 Securitization – PURA Subchapter N Uplift Charges
  Posted on 12/29/2021
  On 1/13/2022 PRS agenda

## Slide 9: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1112 | Elimination of Unsecured Credit Limits | 2022 | 3560 | $10k-$20k, 3-5 months Impacted Systems: CMM Seeking to implement by summer 2022
NPRR1114 | Securitization – PURA Subchapter N Uplift Charges | 2022 | 320 | $1.8M-$2.4M, 18-24 months REGULATORY Impacted Systems: CMM, Settlements, Reporting, Registration, Integration, ERCOT.com, MIS
SCR818 | Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | TBD | TBD | IA in progress (vendor estimate needed)
SCR819 | Improving IRR Control to Manage GTC Stability Limits | 2022 | 3570 | $40k-$60k, 4-6 months Impacted Systems: EMS, MMS Attempt to deliver by fall 2022 if we can find a window that doesn’t impact other critical items
PGRR099 | Revise GIM Process to Ensure Compliance with the Lone Star Infrastructure Protection Act | 2022 | 310 | $20k-$30k, 3-5 months REGULATORY Impacted Systems: RIOO
PPL Rank Information
Next available 2022 Rank in Business Strategy = 3560
Next available Rank in Regulatory = 330
Options for…

## Slide 10
ERCOT Technology Working Group (TWG)
Venkat Tirupati
January 13, 2022

## Slide 11: ERCOT Technology Working Group (TWG)
Information sharing about IT/OT Systems/Apps between MP's and ERCOT
Part of “Other Groups” family of Committees & Groups
Rollover EMSWG to TWG (January 20th)
Membership to include MPs IT/OT representatives and vendors
Leadership (Chair from ERCOT/ Vice-Chair from MPs)
Open Session - complementary to existing committees and groups
Meets every two months to start with and as deemed necessary
Reach out & soliciting feedback on charter in progress
First meeting will be in February