## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2021-12-08
Agenda Item: | Decision / Resolution | Action Items :
October Meeting Notes
| No Changes were made to the notes. | The Texas SET Vice Chair will have the final version posted to the October meeting page.
Retail Market Subcommittee (RMS) Update
Retail Emergency Conditions Task Force (RECTF)-Sunset
NPRR1095 with an Impact Analysis priority of 2023 and rank of 3700 was approved. The NPRR will be reviewed at the Protocol Revision Subcommittee (PRS) on Tuesday 12/14 for approval. | Vistra has a concerned about PRS pushing back on the cost. The RMS Chair stated that there should not be too much push back. Centerpoint Energy suggested that Texas SET Leadership and anyone else interested in moving the changes along, be on the call to justify the cost if there are questions.
RMGRR169 with an Impact Analysis cost that is included in NPRR1095 was approved.
ERCOT Update
Flight | No changes since Flight 1021 wrapped up.
MarkeTrak Refresh | This will be discussed at TDTMS, but is looking to migrate the first part of the project on June 4, 2022
Discussion Items
CBCI File assignment from RECTF | Vistra provided an update on the RMGRR draft Vistra explained that delaying some of the language changes related to quoting the Substantive Rule 25.43, Provider of Last Resort (POLR) allows enough time for the Public Utility Commission of Texas (PUCT) Staff and Commissioners time to complete their review of the rules. Specific changes being considered by the PUCT Staff and Comissioners can be found in Project 51830 Review of Certain Retail Electric Customer Protection Rules Texas SET members agreed to delay more discussion until the Janaury meeting.
Texas SET V5.0 Matrix Review | The Texas SET Chair conducted a final review of the matrix, then made changes where needed. | The Texas SET Chair will send the updated version to the TX SET email distribution list.
Other Business
2022 Goals / 2021 Accomplishments | The Texas SET Chair conducted a discussion on the 2021 Accomplishments and the 2022 Goals, then created a draft of each. | The Texas SET Chair will complete the draft, then send out to the membership to review. The final version will be completed at the Janaury member.
Next Meeting--WebEx Only | 2022-01-19
Attendees F-T-F
Attendees Webex
Carolyn Reed Centerpoint Energy | Kathy Scott Centerpoint Energy
Dave Michaelson ERCOT | Kyle Patrick NRG
Deb Belin MarketWise | Mark Pepdjonovic ESG
Diana Rehfeldt TNMP | Mary Do Agility CIS
Eric Lotter GridMonitor | Sam Pak ONCOR
Frank Nunes EC InfoSystems | Sheri Wiegand Vistra
Jim Lee AEP | Stepen Wilson TXU Energy
Jordan Troublefield ERCOT | Steve Pliler Vistra
Kathryn Thurman ERCOT