## 5.0
No | Enhancement | System Change | Notes | Consensus | Transactions | Recommended Version | Change Control (Approved) | TXSET Issue | RMGRR (Approved) | NPRR (Approved) | Author
2 | Updating the 814_24 to allow only the CSA CR to submit the REF~2W and create new reject reason for ERCOT | ERCOT | July 21, 2021: Language incorporated into NPRR was reviewed at TEXAS SET. June 16, 2021: Patrick to have draft ready for July TEXAS SET. Will have to be blended with #4. May 19, 2021: Diana provided draft NPRR for this change. Kyle and Kathryn to review. Adding validation at ERCOT for CSA CR | Y | 814_24 | 5.0 | 798 | TXSET134 | RMGRR124 | NPR1095 | Diana Rehfeldt/Kathy Scott
3 | Make the "Unmetered Service Type" found in the REF~PRT segment "Optional" for the TDSP when the information is available at the time the 814_20 Create transaction is established and communicated to ERCOT. | ERCOT, TDSP | Submitted in 2011 | Y | 814_20 | 5.0 | 794 |  | No | No
4 | Revise current CSA validation process for MVO process to be separated from CSA CR switch. Two days prior to the scheduled MVO date ERCOT would validate if a CSA was associated to ESIID and drop trxs to TDSP and CSA CR. | ERCOT | July 21, 2021: Language incorporated into NPRR was reviewed at TEXAS SET. June 16, 2021: Patrick to have draft ready for July TEXAS SET. It will have to be blended with #2. May 19, 2021: Kyle presented NPRR languge which TEXAS SET reviewed. Kyle and Kathryn will work in Solution to Stacking for any RMGRR edits. http://www.ercot.com/content/wcm/key_documents_lists/187801/2019_I149.docx Workflow attached to Issue 149 UPDATE 9/16/20: Kyle Patrick to add REF~TD for reason for change. UPDATE: Kyle Patrick to submit for March CC Call UPDATE 7/22/2020: Kyle Patrick to submit CSA Change Control with 150/151 DTMS for August 2020 CCC. 3/24/21: Add language to CC for Change greybox. Add language to protocls for ERCOT handling of start and end dates. | Y | 814_18, 814_19 | 5.0 | 828, 833 | TXSET149 | RMGRR169 | NPR1095 | Kyle Patrick
5 | Harvey Lesson Learned 1) 650_04 BGN08~R8 requesting CR to send MVO with B44 | TDSP, CR, Service Provider | Revise BGN08 Greybox description for R8: TDSP will use this code to indicate that the ESI ID is being permanently suspended and that the CR needs to submit an 814_24 (Move Out) transaction REF~1P=B44 so this ESI ID may be Retired. (2/19/20) | Y | 650_04 | 5.0 | 817 |  | No | No
6 | Harvey Lesson Learned 4) Clarify greybox language of the usage of the RC003 code in 650_01 | N | Greybox language currently used for RC003: 1) RCN after DNP; 2) RCN for Customer Req. Clearance; 3) RCN after DC due to Tampering Clarify greybox language: "Used by CR to reconnect premise when CR did not send disconnect" Also to remove the examples above (1, 2, 3) | Y | 650_01 | 5.0 | 815 |  | No | No
7 | Harvey Lesson Learned 3) Bi-Directional Turn On/Off Notification | TDSP, CR, Service Provider | Used by TDSP (650_04) and CR (650_01) to DC/RC from direct customer request Reconnect does not need to reference the Disconnect o New codes for bidirectional DC/RC due to floods, Force Majeure events, etc. • 650_01 BGN07 = 72, Purpose Code = DC006 for disconnects Turn Off at Customer Request • 650_01 BGN07 = 79, Purpose Code = RC006 for reconnects Turn On at Customer Request • 650_04 BGN07 = 8S, Purpose Code = DC006 for disconnects Turn Off at Customer Request • 650_04 BGN07 = 79, Purpose Code = RC006 for reconnects Turn On at Customer Request o Add new DC006 / RC006 purpose codes to the 650_01, 650_02 and 650_04 that allows either the TDSP or the CR to disconnect or reconnect due to Potential Hazardous Conditions. Need to clarify the difference between the 650_04 DC001 and DC006 | Y | 650_01, 650_02, 650_04 | 5.0 | 815, 816, 817 |  | No | No
9 | Harvey Lesson Learned 6) Review the 814_20 process for meter removal without an 814_24 to allow the TDSPs to use the meter asset at another location. | ERCOT, TDSP, CR, Service Provider | Proposal to utilize meter exchange with a “NONE” in new meter number field so the TDSP can physically use the meter that was there in another location. (814_20) Implementation Guide Gray Box would need to be modified to make OPTIONAL the number of dials and meter multiplier. Kathy Scott to submit draft of CC for TEXAS SET review for March. | Y | 814_20 | 5.0 | 819 |  | No | No
10 | Harvey Lesson Learned 8) Add ESI ID Attributes | ERCOT, CR, TDSP, Service Provider | July 21, 2021: Language incorporated into NPRR was reviewed at TEXAS SET. June 16, 2021: Patrick to incorporate this NPRR language into a larger NPRR. May 19, 2021: Kyle presented NPRR for review and no comments or changes were made at the meeting. TDSPs would add premise attributes as a code to describe the type of premise. This would be an optional segment and if used would be populated on a going forward basis. (primary residence vs temporary mobile trailer meter vs boat house vs workshop garage vs barn vs Master Metered) UPDATE 11.17.20: Reviewed list of Meter Sevice Types. TDSPs to have a call to finalize on December 7th. REF segment to be identifed and then Kathy Scott to write up change control and submit. UPDATE: Jim Lee to submit CC for March CC Call. UPDATE 7/22/2020: TDSPs planning to submit CC in August or September. They are additionally giving consideration to adding attribute for Electric Vehicle. 1) Forward-going basis. 2) To be displayed on ERCOT MIS and TDSP ESIID Extract for CR consumption. 3) TDSPs currently have lists, and will collaborate to create master list for market use. From Kim Wall: I would recommend using a REF segment within the N1*8R to provide the type of premise (e.g., Garage, etc.). REF02 would have whatever list of codes the TDSPs want to create and REF03 can optionally be used for additional text. I can’t add the notes for the gray boxes without getting on a different computer but the basic X12 structure is below. It would be a new REF segment at this position, not currently used for any reason today in this N1 loop. ST*814*78001 BGN*11*878862304201911091858330781111*20191109***201911090000465335100006312222**5 N1*8S*CENTERPOINT ENERGY*1*957877905 N1*AY*ERCOT*1*183529049**41 N1*SJ*X ENERGY*9*0787031111000**40 N1*8R*BONNIE SMITH N3*104 SHAWNEE PL N4*MISSOURI CITY*TX*77459 REF*JR*GRG*GARAGE LIN* TDSPs to create list of REF~02 premise details. TXSET suggested that this REF~JR be located between the AMS Indicator and Status Reason. UPDATE 9/16/2020: List being accumulated by TDSPs. | Y | 814_04, 814_05, 814_14, 814_20, 814_22 | 5.0 | 831 |  | No | NPR1095 | Kyle Patrick
15 | Add Counties to the N4 of the N1~8R Customer address of the 814_transactions (required field) | ERCOT, CR, TDSP, Service Provider | June 16, 2021: Patrick to incorporate this NPRR language into a larger NPRR. May 19, 2021: Kyle presented NPRR for TEXAS SET review and no comments or changes were made at the meeting. Draft ready for Submission. Added N405 and N406 CO and County free form field. | Y | 814_04, 814_05, 814_14, 814_20, 814_22 | 5.0 | 821 |  | No | NPR1095 | Kyle Patrick
16 | Need Unexecutable code added to 650_02 and 814_28 to address instances where a customer has installed Distributed Generation without an Automatic Transfer Switch (ATS) and/or a signed interconnection agreement with the TDSP | ERCOT, CR, TDSP, Service Provider | Add code J009—"DG Customer Requires Automatic Transfer Switch (ATS) installation and/or signed Interconnection Agreement" Add code U007-Service Standards Clearance Violations Add code S004-Service Standards Clearance Violations | Y | 650_02, 814_28 | 5.0 | 816, 818 |  | No | No
17 | Need Unexecutable code added to 650_01, 650_02, 650_04 and 814_28 for a code clearance violation | ERCOT, CR, TDSP, Service Provider | Add Required element for code "00x–Code Clearance Violation" (create within Change Control) Possibly add a comment in the REF03 that contains the service standards code for the specific violation. | Y | 650_01, 650_02, 650_04, 814_28 | 5.0 | 815, 816, 817, 818 |  | No | No
18 | Construction Hold | ERCOT, CR, TDSP, Service Provider | Use "CHP" when TDSP identifies Construction Hold needed to add transparency for CRs | Y | 814_04, 814_05 | 5.0 | 809 |  | No | No
19 | IAS/IAG Solution | TBD | July 21, 2021: TEXAS SET reviewed the IAS RMGRR. Additional language was presented for greater than 150 days in the past rejection reason. June 16th, 2021: TEXAS SET reviewed IAS RMGRR. Document will be sent to TXSET listserv and reviewed again at July meeting before submitted for RMS consideration. May 19, 2021: Jim, Kathy, Diana to work on IAG RMGRR for review at TEXAS SET in June/July. Automation to replace the MarkeTrak portion for CRs. TDSPs to evaluate how to automate TDSP portion for cancel/rebilling process. TDSPs will discuss further. UPDATE: Jim Lee to submit CC for March CC call. Bring back more for TXSET discussions. Update 11.17.20: Jim Lee will begin drafting CC for IAS enhancements to current process. This would include adding BGN~07 to the 814_16, 814_05, and 814_06. The BGN~07 will be enhanced to include IA and CR codes. IA=Inadvertent Switch in Grey Box and CR=Customer Recission in Grey Box. TEXAS SET discussed if 867s and 810s needed enhancement and decide that it was not. | Y | 814_16, 814_03, 814_04, 814_05, 814_06 | 5.0 | 829, 832 |  | RMGRR169 | No | Jim Lee
12b | Customer contact information: Adding direct customer authorization from Customer via CRs to sign up customer for TDSP Outage notifications | TBD | Update 7/22/2020: Sam Pak to submit change control adding Email to PER~PO segment. This will be submitted on a subsequent change control call. UPDATE 9/16/20: Change control drafted to add PER~PO to trxs. UPDATE 11/17/20: Sam Pak to submit CC to ERCOT. Each TDSP has different criteria needed, which will be discussed among the TDSPs. | Y | 814_01, 814_03, 814_16 | 5.0 | 827 |  | No | No
| A13 Cleanup |  | Issue 150. Clean up A13 codes use and add any new codes if necessary. Update 11.17.20: Reviewed list of possible new reject codes to be added to the 814 series. TDSPs to consolidate and provide a list at the January meeting. Then it will be added to a change control. UPDATE: Kathryn Thurman to submit CC for March CC Call. | Y | 814_04, 815_05, 814_02, 814_17, 814_09, 814_13, 814_27, 814_25, 814_19, 814_21 | 5.0 | 830 |  | No | No
| Standard Switch effectuating after MVO |  | May 19, 2021: Kathryn completed this change. Currently ERCOT does not reject a Standard Switch if there is a MVO pending. TEXAS SET discussed this and determined it would be best for the Standard Switch in this scenario to be rejected with "SBD: Scheduled to be Deenergized" code. This will mirror the currently logic ERCOT has in place for self selected switches that are rejected. This will be a Retail Market Guide Revision Request. | Y | 814_02 | 5.0 | No |  | RMGRR169 | No | Kathryn Thurman
15 | CW1 for TDSP |  | 3/25/21: Modify grey box for use by TDSP and ERCOT. Add CW1 Reject code logic on 814_12/814_13 for TDSP and Add CW1 Reject code logic on 814_08/814_09 RD cancel (B40, A13). Remove "ERCOT ONLY". | Y | 814_13 and 814_09 | 5.0 | 830 |  | No | No
20 | To provide the Market with a transactional solution for future, CNP is recommending adding additional codes to the 650_01, 650_02, 650_04 and 814_28. See Change Control for a full list of the new codes. |  | SET change control was approved: Add specific Unexecutable codes to provide detailed explanations rather than just "T018" for turndowns associated with unapproved Distributed Generation equipment or Auto Transfer Switch and/or no signed Interconnection Agreement received by TDSP. Due to the increased volumes of Complete Unexecutable, also known as Turndowns, that are currently being sent to the market with Complete Unexecutable code of T018 (Other) and majority of these are associated with unapproved Distributed Generation equipment or Auto Transfer Switch and/or no signed Interconnection Agreement received by TDSP. CNP foresees a need for more specific Complete Unexecutable codes to eliminate the numerous email inquiries or calls directly to CNP from Customer(s) and/or CR(s) looking for more detailed explanations than just the “T018” Other with comments type response | Y | 650_01, 650_02, 650_04 and 814_28 | 5.0 | 834 |  | No | No
21 | The 810_02 graybox states: “A second 810 for the same ESI ID may be sent for a Late Payment Charge, Service Order Charge, Meter Tampering Discretionary Invoice or Interest Credit.” |  | However, there is no existing BIG07 Code that supports a standalone Interest Credit or Credit of any type, even those credits that may be processed after a final bill was produced. This change control provides clarifications to the current BIG07 code “26” to change the graybox to match the name identified into the TX SET Guide as a “Miscellaneous Services Invoice” instead of creating a new BIG07 code dedicated to miscellaneous credits. | Y | 810_02 | 5.0 | 835 |  | No | No
22 | There have been instances where a customer name was submitted containing nothing but a comma in the EDI transaction. Because the Texas SET Guide describes the name field as being free-form Alpha numeric and between 1 and 60 characters, a value of a comma was accepted and passed to downstream market participants. |  | This change control adds clarification to all name fields that the use of a comma is only valid when associated with a Customer name. After implementation of this change control name fields populated with only a comma will be considered invalid and will be rejected by ERCOT and the TDSP. Also included are updates to Change Control 2020-827 to add comma language to the new Power Outage Contact PER~PO | Y | 814_01, 814_03, 814_04, 814_05, 814_08, 814_12, 814_14, 814_16, 814_18, 814_20, 814_22, 814_24, 814_26, 814_28, 814_PC, 650_01 | 5.0 | 836 |  | No | No

## 4.0A
No | Enhancement2 | System Change | Notes | Consensus | Transactions | Recommended Version | Change Control (Approved) | TXSET Issue | RMGRR (Approved) | NPRR (Approved)
4.0A | Muni-Coop guidelines are different than the IOU guidelines for meter removal | N | Muni-Coop guidelines are different than the IOU guidelines for meter removal (Update 6/17/20) TEXAS SET recommended this CC be withdrawn because CC 810 incorporated the same changes. | Y | 650_04 (MOU/EC) | 4.0A | 800 |  | No | No
4.0A | Sync the language in the Implementation Guide for "CW1" Reject Reason in the 814_09 and 814_13 transaction to support NPRR778 | N | already implemented, sync language in guide | Y | 814_09, 814_13 | 4.0A | 807 |  | No | NPRR778
4.0A | Sync the Texas SET Implementation Guides with ERCOT Protocols in the way the Muni-Coop is abbreviated | N | MC TDSP --> "MOU/EC TDSP" | Y | N/A | 4.0A | 806 |  | No | No
4.0A | Update all of the TX SET Implementation Guides to allow the receiver of the transaction containing Special Characters to determine to either accept the transaction or to respond with a valid rejection. | N | 11/14/19 discussion: 2 phase approach: 1) implement table of unacceptable special characters within the TXSET guides (Update 6/17/20) TEXAS SET will recommend on July CC call to withdraw this CC. CC820 is the preffered pat and has already been approved. | Y | All | 4.0A | 805 | TXSET143
4.0A | Update Greybox explanation to clarify that tenant-based permit must be sent to TDSP by the Applicable Legal Authority (ALA) -- city, county, etc. | N | Revise current greybox language to read: Required if a move-in request is for an ESI ID, which requires an occupancy permit. The Applicable Legal Authority (ALA) will notify the TDSP directly of the completed permit. The name provided in the PER02 must match the name on the occupancy permit. |  | 814_16, 814_03 | 4.0A | 811 |  | No | No
4.0A | Clarifies the current description shown in the REF~8X~TE003 of "PCB" Purpose Code to show it as "Investigate Transformer Leaking" in the 650_01 and 650_02. | N | Correcting description of TE003 | Y | 650_01/02 | 4.0A | 799 |  | No | No
4.0A | <ESIID>, <Membership ID>, <Special Needs Indicator>,etc | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Max Use: >1 Current ERCOT: last provided Notes: 814 ANSI > 1 ERCOT Rec: add Notes to restrict to 1 use TXSET Rec: Add "only one allowed" to gray box |  | All | 4.0A | 811 |  | No | No
4.0A | REF~PH (Priority Code) | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: REQ on standard Move In Current ERCOT: optional Notes: even split on LSE compliance ERCOT Rec: change guide to Optional TXSET Rec: 08/16/2019: Homework for T/X SET members to determine if "Optional" vs "Required" TX SET members to provide consensus or not at the September 2019 meeting. 09172019: TX SET members agreed that the 814-_16 language should be changed to make the requirment optional. |  |  | 4.0A | 811 |  | No | No
4.0A | Populating N3 and N401 and N402 in the N18R loop. | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Only N403 is valid in the N18R loop. N3 is not valid in the N18R loop. N401 and N402 are marked not used for the N4. Current ERCOT: optional Notes: Example: N1*8R*CUSTOMER NAME~ N3*CUSTOMER ADDRESS~ N4*CITY*TX*760536829~ ERCOT Rec: Market Participants to make updates to follow TX SET Guides TXSET Rec: Texas SET agrees with the ERCOT recommendation to reject. |  |  | 4.0A | 811 |  | No | No
4.0A | PER~IC located in the wrong N1 Loop | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Should be located in the N1~8R loop Current ERCOT: optional Notes: Example: N1*N1*CUSTOMER NOTIFICATION~ N3*STREET ADDRESS~ N4*CITY*TX*784043867~ PER*IC*CONTACT NAME~ ERCOT Rec: Market Participants to make updates to follow TX SET Guides TXSET Rec: Texas SET agrees with the ERCOT recommendation to reject. |  |  | 4.0A | 811 |  | No | No
4.0A | REF~2W located in the wrong N1 loop | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Should be located in the N1~SJ loop Current ERCOT: optional Notes: Example: N1*8R*CUSTOMER NAME~ N4***770604210~ REF*2W*MVO~ ERCOT Rec: Market Participants to make updates to follow TX SET Guides TXSET Rec: Texas SET agrees with the ERCOT recommendation to reject. |  |  | 4.0A | 811 |  | No | No
4.0A | PER~IC located in the wrong N1 Loop (No N1~BT was used in the transaction and it was not a Muni ESI) | CR, Service Provider | PR288-01 (EDI Translator upgrade) Current SET: Should be located in the N1~BT loop Current ERCOT: optional Notes: Example: N1*8R*CUSTOMER NAME~ N4***78362~ PER*IC*CUSTOMER NAME*TE*1234567890~ N1*AY*ERCOT*1*183529049**40~ ERCOT Rec: Market Participants to make updates to follow TX SET Guides TXSET Rec: Texas SET agrees with the ERCOT recommendation to reject. |  |  | 4.0A | 811
1 | Update all of the TX SET Implementation Guides to allow the receiver of the transaction containing Special Characters to determine to either accept the transaction or to respond with a valid rejection. | ERCOT, TDSP, CR, Service Provider | Need to create a new reject code. Upon implementation of TXSET 5.0, ERCOT & TDSPs would code to Reject any inappropriate special characters used. 11/14/19 discussion: Part 2) implement the reject code as part of 5.0 release (new change control needed to specify reject code). 3/26/20 discussion: TEXAS SET discussed possibly using "A83" instead of a new code along with a REF~03 explanation. Members thought further discussion was preferred. Review next meeting. 4/15/20 discussion: Update from ERCOT:3/26/20 discussion no longer applies and A83 no longer a preferred option. Proposal is to perform Special character validation is performed at the ANSI level. Any rejects for special characters would be contained within the 997. First point of contact for a transaction is where the validation would be performed. Ex 814s for ERCOT and 650s for TDSP (may reject). | Y | All | 4.0A | 820 |  | No | NPRR796
8 | Review 650_04 BGN~08 and REF~5H segments. Clarify usage by CRs and move "MOU/EC TDSP" language | TBD | Review and add new codes if needed. 1/22/20: Clarify 814_24 off of BGN08 not REF~5H. Review REF~5H Notes Section and add comments relating to the BGN~08. Move all references in REF~5H for "MOU/EC TDSP ONLY" to the top of the gray box. Ex: CR002 No coding changes -- Greybox clarification is needed |  | 650_04 | 4.0A | 810 |  | No | No

## Withdrawn
No | Enhancement2 | System Change | Notes | Consensus | Transactions | Recommended Version | Change Control (Approved) | TXSET Issue | RMGRR (Approved) | NPRR (Approved)
11 | Customer contact information: TDSP Request Contact Information | TBD | TDSP-initiated 814_PC? Can TDSPs leverage CBCI files that are already sent by CRs? Each TDSP would filter for own ESIIDs from master file Idea: CRs submit CBCI files monthly to ERCOT. ERCOT would create report/extract and post on MIS by TDSP DUNS. |  | TBD | TBD | Jim Lee
12a | Customer contact information: Add Optional E-mail field on the 814_01, 814_03, & 814_16 | TBD | Add optional email field on enrollment transactions Possibly rearrange location of the Email field on the 814_PC?? No longer needed. 12b will take the place of this enhancement. |  | 814_01, 814_03, 814_16 | 5.0 | Kyle Patrick/Sam Pak
6 | Harvey Lesson Learned 2) TDSPs to use 650_04 to notify CRs when power is restored/reactivated for premises that were de-activated | TDSP, CR, Service Provider | TDSPs to communicate reactivation to CRs by sending BGN08~79 with REF~5H=RC002 (RC002 does not exist today, will need to create new code, description and new DTM segment) This was addressed in a further CC and will utilize RC006 and RC007 as means vs what this orginal enhancement requested to use. |  | 650_04 | 5.0 | Kathy Scott |  |  | No
14 | If known by TDSP, communicate to CRs if meter set is required | TBD | If TDSP knows that a meter does not exist at the location, how to communicate to market that a meter set will be needed. Unless it is a brand new meter set (new construction), difficult for TDSPs to know on front end when meter set is needed. Generally won't know until field personnel has been dispatched. MORE DISCUSSION NEEDED. |  |  | 5.0 | TBD