## ProjectCenter
Project Category | Target Start Year (Priority) | Rank | Revision Request | Project Name | Project Status | Impact Analysis Estimated Cost | Impact Analysis Estimated Time | Impacted Systems | Target Start Date | Target End Date | Target Release
Base Operations | 2019 | 230 | PGRR070 | PGRR070 Revised Responsibilities for Performing Geomagnetic Disturbance (GMD) Vulnerability Assessments | Complete | $100k - $150k | 12 - 18 months | Data Management & Analytic Systems | 5/1/2020 | 12/31/2021 | 2021-R6
Base Operations | 2023 | 2580 | PGRR066 | PGRR066 Interconnection Request Cancellation and Creation of Inactive Status | Complete | $100k - $150k | 4 - 6 months | Grid Modeling Systems, Resource Integration and Ongoing Operations | 10/1/2024 | 4/1/2025
Base Operations | 2021 | 2705 | NPRR1051 | NPRR1051 Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices | Complete | $10k - $20k | 3 - 5 months | Market Operation Systems | 4/13/2021 | 5/31/2021 | 2021-R3
Base Operations | 2021 | 3320 | LPGRR068 | LPGRR068 Add BUSLRG and BUSLRGDG Profile Types | Complete | $20k - $40k | 3 - 6 months | Data Management & Analytic Systems | 10/1/2021 | 2/1/2022 | 2022-R1
Base Operations | 2021 | 3350 | SCR814 | SCR814 Point-to-Point (PTP) Obligation Bid Interval Limit | Complete | $10k - $25k | 3 - 5 months | Market Operation Systems | 1/1/2022 | 7/27/2022 | 2022-R2
Regulatory | 2019 | 220 | NPRR885 | 324-01 NPRR885 Must-Run Alternative (MRA) Details and Revisions Resulting from PUCT Project No_ 46369, Rulemaking Relating to Reliability Must-Run Service | On Hold | $500k - $700k | 8 - 12 months | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems | 7/1/2027 | 8/1/2028
Regulatory | 2022 | 235 | NPRR863, NPRR1085, NPRR1096, NPRR1148 | 386-01 Creation of ERCOT Contingency Reserve Service (ECRS) | Complete | $1M - $1.5M | 12 - 18 months | Credit Management Systems (CMM), CRM & Registration Systems, Data and Information Products, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Network Management Systems | 1/12/2022 | 7/1/2023 | 2023-R3
Regulatory | 2023 | 235 | NPRR1007-1014NPRR, NPRR1204 | 447-00 RTC-B Program Control | Execution | $12M - $16M | 2.5 - 3.5 years | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Energy Management Systems, ERCOT Website and MIS Systems, Forecasting Systems, Grid Modeling Systems, Grid Planning Systems, Infrastructure Systems, Market Operation Systems | 6/1/2023 | 12/1/2026
Regulatory | 2023 | 235 | NPRR1007-1014NPRR, NPRR1204 | 447-01 RTC-B Grid & Markets | Complete | $22.0M - $28.0M | 30 - 42 months | Energy Management Systems, ERCOT Website and MIS Systems, Forecasting Systems, Grid Modeling Systems, Grid Operations Support Systems, Grid Planning Systems, Infrastructure Systems, Market Operation Systems, Model Administration, Network Management Systems, Outage Management Systems | 6/1/2023 | 3/31/2026 | 2025-R11
Regulatory | 2023 | 235 | NPRR1007-1014NPRR, NPRR1204 | 447-02 RTC-B Commercial Applications | Complete | $5.0M - $7.0M | 30 - 42 months | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Energy Management Systems, ERCOT Website and MIS Systems, Forecasting Systems, Grid Modeling Systems, Grid Planning Systems, Infrastructure Systems, Market Operation Systems | 7/1/2023 | 12/1/2026 | 2025-R11
Regulatory | 2023 | 235 | NPRR1007-1014NPRR, NPRR1204 | 447-03 RTC-B Integration & Information | Execution | $4.0M - $6.0M | 30 - 42 months | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Energy Management Systems, ERCOT Website and MIS Systems, Forecasting Systems, Grid Modeling Systems, Grid Planning Systems, Infrastructure Systems, Market Operation Systems | 11/1/2023 | 7/31/2026 | 2025-R11
Regulatory | 2020 | 240 | NPRR974, NPRR978, NPRR1048, SCR806 | 345-01 NPRR974 NPRR978 NPRR1048 SCR806 - Alignmt w Amndmnt PUCT SubsRule 25_505_Schedule | Complete | $200k - $300k | 8 - 10 months | Data Management & Analytic Systems, Market Operation Systems | 7/1/2020 | 10/5/2021 | 2021-R3 Off Cycle
Regulatory | 2020 | 300 | NOGRR195 | 334-04 NOGRR195 Generator Voltage Control Tolerance Band | Complete | $30k - $50k | 4 - 6 months | Data Management & Analytic Systems, Energy Management Systems | 11/1/2020 | 4/1/2021 | 2021-R1
Regulatory | 2022 | 315 | NPRR1108 | 388-01 NPRR1108 ERCOT Shall Approve or Deny All Resource Outage Requests | Complete | $300k - $400k | 8 - 12 months | Content Delivery Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Outage Management Systems | 12/1/2021 | 8/1/2022 | 2022-R4
Regulatory | 2022 | 325 | NPRR1097 | 400-01 NPRR1097 Create Resource Forced Outage Report | Complete | $20k - $40k | 3 - 5 months | Data Management & Analytic Systems, ERCOT Website and MIS Systems | 7/1/2022 | 1/25/2023 | 2022-R6
Regulatory | 2022 | 330 | NPRR1120 | 394-01 NPRR1120 Create Firm Fuel Supply Service | Complete | $250k - $400k | 9 - 12 months | Channel Management Systems, Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems | 3/10/2022 | 4/12/2023 | 2022-R5 Off Cycle
Regulatory | 2023 | 360 | NOGRR249 | 444-01 NERC FAC Standard Changes Alignment | Complete | $100k - $150k | 5 - 7 months | Channel Management Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Grid Modeling Systems, Integration Systems | 7/3/2023 | 11/30/2023
Regulatory | 2025 | 390 | NPRR1188 NPRR1244 | 539-01 NPRR1188 NPRR1244 Controllable Load Resources | Execution | $1.8M - $2.6M | 18 - 29 months | Channel Management Systems, Credit Management Systems (CMM), Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Integration Systems, Market Operation Systems, Resource Integration and Ongoing Operations | 12/1/2025 | 3/1/2027
Regulatory | 2026 | 395 | NPRR1238 | 544-01 Large Load Curtailment Manager (LLCM) and NPRR1238 | Planning | $700k - $1.0M | 10 - 15 months | Data and Information Products, Data Management & Analytic Systems, Energy Management Systems, Network Management Systems | 1/1/2026 | 2/9/2027
Revision Requests | 2026 |  | NPRR1309 | 575-01 NPRR1309 Dispatchable Reliability Reserve Service Ancillary Service | Not Started | $3.0M - $5.0M | 20 - 30 months | Credit Management Systems (CMM), Data and Information Products, Energy Management Systems | 7/1/2026 | 11/30/2028
Revision Requests | 2026 |  | NPRR1328 | 576-01 NPRR1328 Establishment of Generation Firming Program | Not Started | $1.0 - $1.5M | 18 - 24 months | Data and Information Products, Data Management & Analytic Systems | 7/1/2026 | 1/1/2028
Revision Requests | 2013 | 440 | SCR781, RRGRR016, RRGRR019 | 106-01 RARF Replacement | Complete | N/A | N/A | CRM & Registration Systems, Grid Modeling Systems | 3/1/2017 | 11/1/2022 | 2021-R6 Off Cycle
Revision Requests | 2017 | 1820 | SCR789 | 250-01 SCR789 Update NMMS Topology Processor to PSS_E 34 (35) Capability - Phase 1 Only | Complete | $150k - $250k | 8 - 12 months | Grid Modeling Systems | 12/1/2020 | 2/1/2022 | 2021-R4 Off Cycle
Revision Requests | 2017 | 1820 | SCR789 | 391-01 SCR789 Update NMMS Topology Processor to PSS_E 34 (35) Capability – Phase 2 | Complete | $550k - $750k | 12 - 18 months | Grid Modeling Systems | 2/1/2022 | 11/21/2023
Revision Requests | 2020 | 2020 | NPRR918 | NPRR918 Validation for PTP Obligations with Links to an Option | Not Started | $30k - $50k | 4 - 6 months | Data Management & Analytic Systems, Market Operation Systems | 4/1/2027 | 9/24/2027
Revision Requests | 2018 | 2090 | NPRR825 | NPRR825 Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Not Started | $200k - $300k | 8 - 12 months | Data Management & Analytic Systems, Integration Systems, Market Operation Systems | 7/1/2027 | 7/1/2028
Revision Requests | 2019 | 2510 | NPRR829 | 351-01 NPRR829 Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL | On Hold | $200k - $300k | 5 - 10 months | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, Grid Modeling Systems, Integration Systems | TBD | TBD
Revision Requests | 2020 | 2515 | NPRR1030 | NPRR1030 Modify Allocator for CRR Auction Revenue Distribution | Not Started | $175k - $225k | 8 - 12 months | Credit Settlements & Billing Systems | TBD | TBD
Revision Requests | 2019 | 2520 | NPRR841 | NPRR841 Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | Not Started | $60k - $80k | 4 - 6 months | Credit Settlements & Billing Systems | TBD | TBD
Revision Requests | 2022 | 2530 | NPRR1098 | NPRR1098 DC Tie Reactive Power Capability Requirements | Not Started | $10k - $20k | 3 - 5 months | Grid Decision Support Systems | 7/1/2028 | 11/30/2028
Revision Requests | 2024 | 2530 | NPRR857 | NPRR857 Creation of Direct Current Tie Operator Market Participant Role | Not Started | $500k - $700k | 12 - 18 months | CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Grid Modeling Systems, Outage Management Systems, Telecom Management Systems | 7/1/2028 | 12/31/2029
Revision Requests | 2020 | 2630 | NPRR905 | 339-01 NPRR905 CRR Balancing Account Resettlement | Complete | $60k - $80k | 4 - 6 months | Credit Settlements & Billing Systems | 3/1/2020 | 11/3/2021 | 2021-R4
Revision Requests | 2019 | 2650 | NPRR863, NPRR1015, NPRR1079, NOGRR187 | 325-01 NPRR863 FFR Advancement | Complete | $1.5M - $2.5M | 16 - 24 months | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems, Outage Management Systems | 1/1/2020 | 4/26/2023 | 2022-R5 Off Cycle
Revision Requests | 2019 | 2710 | SCR799 | 486-01 SCR799 ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Complete | $150k - $250k | 5 - 7 months | Data Management & Analytic Systems, Outage Management Systems | 6/1/2024 | 2/4/2025 | 2024-R10
Revision Requests | 2019 | 2720 | NPRR904, OBDRR009, NPRR1006 | 347-01 NPRR904 Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | On Hold | $370k - $530k | 7 - 10 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 10/1/2026 | 10/1/2027
Revision Requests | 2020 | 2765 | NPRR986, NPRR971, NPRR1043 | 338-01 Implementation of NPRR986 BESTF-2 and NPRR971 | Complete | $260k - $390k | 9 - 12 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems | 3/1/2020 | 8/3/2021 | 2021-R2 Off Cycle
Revision Requests | 2019 | 2770 | NPRR939 | 358-01 NPRR939 Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions | Complete | $70k - $100k | 5 - 7 months | Data Management & Analytic Systems, Integration Systems, Market Operation Systems | 11/2/2021 | 8/4/2022 | 2022-R3
Revision Requests | 2020 | 2800 | NPRR879 | NPRR879 SCED Base Point Base Point Deviation and Performance Evaluation Changes for IRRs that Carry Ancillary Services | Not Started | $200k - $250k | 6 - 9 months | Data Management & Analytic Systems, Energy Management Systems, Grid Modeling Systems, Integration Systems | 1/1/2028 | 12/31/2028
Revision Requests | 2020 | 2850 | NPRR936, NPRR1288 | 543-01 NPRR936 NPRR1288 CRR Enhancements | Planning | NPRR936 $202,937 + NPRR1288 $564,525 = $767,462 | 8 - 10 months | Congestion Revenue Rights (CRR), Data Management & Analytic Systems, Market Operation Systems | 1/1/2026 | 2/1/2027
Revision Requests | 2022 | 2855 | SCR807, SCR816 | 414-01 SCR807 and SCR816 implementation | Complete | $100k - $180k | 5 - 7 months | Congestion Revenue Rights (CRR), Integration Systems | 10/1/2022 | 4/10/2024
Revision Requests | 2020 | 2860 | NPRR941 | NPRR941 Create a Lower Rio Grande Valley Hub | Not Started | $250k - $350k | 6 - 8 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 4/1/2027 | 9/24/2027
Revision Requests | 2020 | 2880 | SCR804 | 209-06 SCR804 ERCOT GridGeo Access for Transmission Operators | Complete | $400k - $600k | 6 - 12 months | Grid Decision Support Systems | 1/1/2020 | 9/1/2021 | 2021-R2 Off Cycle
Revision Requests | 2020 | 2890 | NPRR930 | 348-01 NPRR930 Process Pricing and Cost Recovery for Delayed Resource Outages | On Hold | $100k - $200k | 5 - 7 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Market Operation Systems, Outage Management Systems | 7/1/2027 | 6/30/2028
Revision Requests | 2020 | 2910 | SCR800, SCR809 | 382-01 SCR800 and SCR809 Implementation | Complete | $70k - $110k | 6 - 9 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 10/1/2021 | 7/1/2022 | 2022-R3
Revision Requests | 2020 | 2920 | SCR805 | SCR805 Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | $40k - $60k | 4 - 6 months | Data Management & Analytic Systems | 10/1/2026 | 3/1/2027
Revision Requests | 2020 | 2930 | NPRR902 | 337-01 NPRR902 ERCOT Critical Energy Infrastructure Information | Complete | $150k - $225k | 6 - 9 months | Corporate Systems, Data Management & Analytic Systems | 3/1/2020 | 12/1/2021 | 2021-R4
Revision Requests | 2020 | 2970 | NPRR826 | NPRR826 Mitigated Offer Caps for RMR Resources | Not Started | $100k - $200k | 6 - 8 months | Market Operation Systems | 1/15/2027 | 2/1/2028
Revision Requests | 2020 | 2990 | NPRR998 | 334-03 NPRR998 ERS Deployment and Recall Messages | Complete | $15k - $25k | 3 - 5 months | Integration Systems | 5/1/2020 | 7/1/2021 | 2021-R2
Revision Requests | 2022 | 3000 | NPRR975 | NPRR975 Load Forecast Model Transparency | Not Started | $75k - $100k | 6 - 9 months | Data and Information Products, Data Management & Analytic Systems, Energy Management Systems | TBD | TBD
Revision Requests | 2022 | 3005 | NPRR1092 | 440-01 NPRR1092 Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | Complete | $50k - $100k | 4 - 6 months | Channel Management Systems, Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Market Operation Systems | 7/1/2023 | 2/1/2024 | 2024-R01
Revision Requests | 2023 | 3010 | NPRR1026 | 454-01 NPRR1026 BESTF-7 Self-Limiting Facilities | Complete | $100k-$200k | 5 - 8 months | Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Resource Integration and Ongoing Operations | 7/3/2023 | 2/1/2024 | 2024-R01
Revision Requests | 2020 | 3015 | NPRR1029 | NPRR1029 BESTF-6 DC-Coupled Resources | Not Started | $800k - $1.2M | 16 - 24 months | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Network Management Systems, Outage Management Systems, Resource Integration and Ongoing Operations | TBD | TBD
Revision Requests | 2022 | 3020 | NPRR1105 | NPRR1105 Option to Deploy Distribution Voltage Reduction Measures Prior to Energy Emergency Alert (EEA) - Phase 2 | Not Started | $80k - $120k | 6 - 9 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 1/1/2027 | 8/1/2027
Revision Requests | 2020 | 3030 | NPRR1019 | 349-01 NPRR1019 Pricing and Settlement Changes for Switchable Generation Resources (SWGRs) Instructed to Switch to ERCOT | On Hold | $100k - $140k | 5 - 7 months | Data Management & Analytic Systems, Market Operation Systems | 7/1/2027 | 12/31/2027
Revision Requests | 2023 | 3050 | NPRR1002,NPRR1132,NPRR1153 | 456-01 RIOO-IS_RS ESR-Single Model & Validation Rules Update | Complete | $400k - $700k | 9 - 12 months | Grid Modeling Systems | 7/1/2023 | 11/6/2024 | 2024-R07
Revision Requests | 2020 | 3050 | SCR810 | SCR810 EMS System Change to Count DC Ties towards the 2 Percent Constraint Activation Criterion | Not Started | $15k - $25k | 3 - 5 months | Energy Management Systems | 7/1/2027 | 12/1/2027
Revision Requests | 2020 | 3070 | NPRR917, NPRR1016, NPRR1052, NPRR1065, NOGRR212, PGRR082, RRGRR026 | 354-01 DGR DESR Implementation Strategy | Complete | $1.1M - $1.45M | N/A | Credit Management Systems (CMM), Credit Settlements & Billing Systems, Energy Management Systems, Market Operation Systems | 10/1/2020 | 9/1/2022 | 2022-R1
Revision Requests | 2020 | 3080 | SCR811 | 360-01 Integrate Solar Forecasts and SCR811 Implementation | Complete | $120k - $180k | 5 - 7 months | Data Management & Analytic Systems, Energy Management Systems, Forecasting Systems, Market Operation Systems | 1/13/2021 | 8/24/2021 | 2021-R3 Off Cycle
Revision Requests | 2021 | 3125 | NPRR1093, NPRR1101 | 384-01 NPRR1093 Load Resource Participation in Non-Spinning Reserve | Complete | $480k - $700k | 10 - 14 months | Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Integration Systems, Market Operation Systems | 10/13/2021 | 8/24/2022 | 2022-R3
Revision Requests | 2024 | 3195 | NPRR1091 | NPRR1091 Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | $120k - $160k | 7 - 10 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 10/1/2026 | 7/1/2027
Revision Requests | 2021 | 3210 | NPRR1004 | 497-01 NPRR1004 Load Distribution Factor Process Update | Not Started | $45k - $65k | 5 - 7 months | Data Management & Analytic Systems, Integration Systems, Market Operation Systems | 7/1/2026 | 12/1/2026
Revision Requests | 2022 | 3220 | NPRR1020 | 393-01 NPRR1020 - EPS Metering - Allow Some Integrated Energy Storage Designs to Calculate Internal Loads | Complete | $175k - $225k | 8 - 12 months | Credit Settlements & Billing Systems | 3/21/2022 | 1/18/2023 | 2023-R1
Revision Requests | 2021 | 3230 | NPRR1035 | NPRR1035 DC Tie Schedules Protected Information Expiry and Posting | Not Started | $20k - $40k | 3 - 5 months | Data Management & Analytic Systems | 10/1/2026 | 3/1/2027
Revision Requests | 2021 | 3250 | SCR812 | 410-01 SCR812 Create Intermittent Renewable Generation Integration Report | Complete | $30k - $60k | 5 - 7 months | Data Management & Analytic Systems | 7/1/2022 | 2/1/2023 | 2022-R6
Revision Requests | 2021 | 3260 | NPRR1032 | NPRR1032 Consideration of Physical Limits of DC Ties in RUC Optimization and Settlements | Not Started | $100k - $150k | 5 - 8 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems | TBD | TBD
Revision Requests | 2021 | 3280 | NPRR1034 | NPRR1034 Frequency-Based Limits on DC Tie Imports or Exports | Not Started | $50k - $70k | 5 - 7 months | Content Delivery Systems, Data Management & Analytic Systems, Market Operation Systems | 7/1/2028 | 1/31/2029
Revision Requests | 2021 | 3290 | NPRR1040 | 411-01 NPRR1040 Compliance Metrics for Ancillary Service Supply Responsibility | Complete | $20k - $30k | 3 - 5 months | Data Management & Analytic Systems | 9/1/2022 | 12/5/2023 | 2023-R6
Revision Requests | 2024 | 3310 | NPRR1057 | NPRR1057 Modification to Real-Time Hub Price Formulas for Fully De-Energized Hubs | Not Started | $20k - $30k | 3 - 5 months | Market Operation Systems | 7/1/2027 | 12/29/2027
Revision Requests | 2021 | 3330 | NPRR1063 | NPRR1063 Dynamic Rating Transparency | Complete | $15k - $25k | 3 - 4 months | ERCOT Website and MIS Systems | 8/1/2022 | 12/1/2022
Revision Requests | 2021 | 3340 | NPRR1081 | 377-01 NPRR1081 Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed | Complete | $25k - $45k | 2 - 3 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 7/26/2021 | 11/1/2021 | 2021-R5 Off Cycle
Revision Requests | 2022 | 3500 | NPRR1023 | 460-01 NPRR1023 Change to CRR Repossession Process | On Hold | $250k - $350k | 10 - 14 months | Congestion Revenue Rights (CRR) | TBD | TBD | 2026-R02
Revision Requests | 2025 | 3515 | NOGRR245 | 507-01 NOGRR245 Inverter-Based Resource (IBR) Ride-Through Requirements | Complete | $150k - $250k | 6 - 9 months | Resource Integration and Ongoing Operations | 12/3/2024 | 1/20/2026 | 2025-R10 Off Cycle
Revision Requests | 2022 | 3520 | RRGRR028 | RRGRR028 Transformer Impedance Clarifications | Not Started | $100k - $150k | 7 - 10 months | Data Management & Analytic Systems, Resource Integration and Ongoing Operations | 3/1/2027 | 11/1/2027
Revision Requests | 2022 | 3550 | NPRR1077 | NPRR1077 Extension of Self-Limiting Facility Concept to Settlement Only Generators (SOGs) and Telemetry Requirements for SOGs | Not Started | $100k - $160k | 7 - 10 months | Energy Management Systems, Grid Modeling Systems, Resource Integration and Ongoing Operations | 2/1/2027 | 1/1/2028
Revision Requests | 2024 | 3570 | SCR819, NPRR1111 | 415-01 SCR819 Improving IRR Control to Manage GTC Stability Limits | Complete | $40k - $60k | 4 - 6 months | Energy Management Systems, Market Operation Systems | 12/1/2023 | 6/1/2024 | 2024-R05
Revision Requests | 2023 | 3595 | NPRR1186 | 453-01 Implement consideration of ESR SOC in ERCOT tools and studies | Complete | $500k - $700k | 7 - 10months | Energy Management Systems | 7/1/2023 | 9/24/2024 | 2024-R06
Revision Requests | 2022 | 3610 | NPRR1135 | NPRR1135 Add On-Line Status Check for Resources Telemetering OFFNS for Ancillary Service Imbalance Settlements | Complete | $15k - $25k | 3 - 4 months | Energy Management Systems | 1/1/2023 | 7/1/2023
Revision Requests | 2023 | 3620 | SCR822 | 449-01 SCR822 Create Daily Energy Storage Integration Report and Dashboard | Complete | $60k - $90k | 4 - 6 months | Channel Management Systems, Content Delivery Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems | 8/1/2023 | 2/1/2024 | 2023-R6
Revision Requests | 2023 | 3700 | NPRR1095, SCR817 | 409-01 TX SET 5_0 and SCR817 | Complete | $1.4M - $2.1M | 16 - 20 months | CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Retail Systems | 7/19/2022 | 2/11/2025 | 2024-R11
Revision Requests | 2023 | 3710 | SCR818, SCR831 | 558-01 SCR818 Phase 2 Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | Not Started | $300k - $500k | 9 - 12 months | Grid Modeling Systems | 2/1/2027 | 10/1/2027
Revision Requests | 2023 | 3720 | NPRR1131 + NPRR1058 | 476-01 NPRR1131 Controllable Load Resource Participation in Non-Spin | Complete | $100k - $150k | 6 - 9 months | Credit Settlements & Billing Systems, Energy Management Systems, Grid Decision Support Systems, Market Operation Systems | 4/1/2024 | 12/4/2024 | 2024-R08
Revision Requests | 2023 | 3730 | SCR820 | 430-01 SCR820 Operator Real-Time Messaging During Emergency | Execution | $750k - $1.2M | 18 - 24 months | Channel Management Systems, ERCOT Website and MIS Systems, Grid Operations Support Systems | 4/3/2023 | 12/16/2026
Revision Requests | 2023 | 3740 | NPRR1139 | 475-01 NPRR1139 Adjustments to Capacity Shortfall Ratio Share for IRRs | Complete | $15k - $30k | 3 - 5 months | Credit Settlements & Billing Systems | 4/1/2024 | 9/24/2024 | 2024-R06
Revision Requests | 2023 | 3750 | NPRR1140 | NPRR1140 Recovering Fuel Costs for Generation Above LSL During RUC-Committed Hours | Not Started | $20k - $30k | 3 - 4 months | Credit Settlements & Billing Systems | 3/1/2027 | 8/23/2027
Revision Requests | 2024 | 3760 | NPRR1128 | 496-01 NPRR1128 Allow FFR Procurement up to FFR Limit Without Proration | On Hold | $30k - $50k | 3 - 5 months |  | 9/1/2026 | 10/1/2026
Revision Requests | 2023 | 3770 | NPRR1154 | 431-01 NPRR1154 Include Alternate Resource in the Availability Plan for the Firm Fuel Supply Service | Complete | $40k - $70k | 5 - 7 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems | 4/3/2023 | 8/1/2023
Revision Requests | 2023 | 3780 | NPRR1149, NPRR1121, NPRR1090, NPRR962 | 451-01 NPRR1149, NPRR1121, NPRR1090, NPRR962 | Complete | $120k - $160k | 6 - 8 months | Credit Settlements & Billing Systems, Data Management & Analytic Systems, Market Operation Systems | 6/21/2023 | 4/9/2025
Revision Requests | 2024 | 4010 | NPRR1145 | 498-01 NPRR1145 Use of EMS Calculated ERCOT-Wide TLFs in Lieu of Seasonal Base Case ERCOT-Wide TLFs for Settlement | Complete | $50k - $80k | 3 - 6 months | Channel Management Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems | 9/1/2024 | 5/5/2025 | 2025-R03
Revision Requests | 2024 | 4020 | PGRR103 | PGRR103 Establish Time Limit for Generator Commissioning Following Approval to Synchronize | Not Started | $40k - $60k | 4 - 6 months | Data Management & Analytic Systems, Resource Integration and Ongoing Operations | TBD | TBD
Revision Requests | 2024 | 4030 | NPRR1182 | NPRR1182 Inclusion of Controllable Load Resources and Energy Storage Resources in the Constraint Competitiveness Test Process | Not Started | $60k - $90k | 5 - 7 months | Market Operation Systems | 4/1/2027 | 5/3/2028
Revision Requests | 2024 | 4040 | NPRR1183 | 488-01 NPRR1183 ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without ECEII | Complete | $50k - $75k | 4 - 6 months |  | 6/10/2024 | 1/29/2025 | 2024-R11
Revision Requests | 2024 | 4050 | NPRR1171 | NPRR1171 Requirements for DGRs and DESRs on Circuits Subject to Load Shedding | Not Started | $350k - $550k | 9 - 12 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems, Resource Integration and Ongoing Operations | 10/1/2027 | 10/31/2028
Revision Requests | 2024 | 4050 | NPRR1213 | NPRR1213 Allow DGRs and DESRs on Circuits Subject to Load Shed to Provide ECRS and Clarify Language Regarding DGRs and DESRs Providing Non-Spin | Not Started | $350k - $450k | 8 - 12 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 10/1/2027 | 10/31/2027
Revision Requests | 2024 | 4080 | NPRR1201 | 574-01 NPRR1201 Limitations on Resettlement Timeline and Default Uplift Exposure Adjustments | Not Started | $40k - $70k | 4 - 6 months | Credit Management Systems (CMM), Credit Settlements & Billing Systems | 7/1/2026 | 12/31/2026
Revision Requests | 2024 | 4090 | NPRR1208 | NPRR1208 Creation of Invoice Report | Not Started | $40k - $60k | 4 - 6 months | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems | 10/1/2026 | 3/1/2027
Revision Requests | 2025 | 4500 | NPRR995 | NPRR995 RTF-6 Create Definition and Terms for Settlement Only Energy Storage | Not Started | $800k - $1.2M | 20 - 30 months | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Network Management Systems, Resource Integration and Ongoing Operations | TBD | TBD
Revision Requests | 2025 | 4510 | SCR825 | SCR825 ERCOT Voice Communications Aggregation | Not Started | $150k - $250k | 7 - 10 months | CRM & Registration Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Telecom Management Systems | 10/1/2026 | 12/13/2027
Revision Requests | 2025 | 4520 | NPRR1198 | 559-01 NPRR1198 Congestion Mitigation Using Topology Reconfigurations | Planning | $50k - $80k | 4 - 7 months | Channel Management Systems, Energy Management Systems, ERCOT Website and MIS Systems | 4/1/2026 | 2/1/2027 | 2026-R10
Revision Requests | 2026 | 4560 | SCR829 | 569-01 SCR829 API for the NDCRC Application | Planning | $100k - $200k | 7 - 10 months | Software Development Systems | 6/2/2026 | 2/1/2027
Revision Requests | 2026 | 4700 | NOGRR215 | NOGRR215 Limit Use of Remedial Action Schemes | Not Started | $1.0M - $1.5M | 12 - 18 months | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 10/1/2026 | 3/31/2028
Revision Requests | 2028 | 4720 | VCMRR042 | VCMRR042 SO2 and NOx Emission Index Prices Used in Verifiable Cost Calculations | Not Started | $90k - $140k | 6 - 9 months | Credit Settlements & Billing Systems | 1/1/2028 | 2/1/2029
Revision Requests | 2026 | 4730 | NPRR1234 | NPRR1234 Interconnection Requirements for Large Loads and Modeling Standards for Loads 25 MW or Greater | Not Started | $600k - $800k | 12 - 18 months | Energy Management Systems, Market Operation Systems, Resource Integration and Ongoing Operations | 2/1/2027 | 2/1/2028
Revision Requests | 2026 | 4750 | SCR830 | SCR830 Expose Limited API Endpoints Using Machine-to-Machine Authentication | Not Started | $100k - $200k | 6 - 9 months | Resource Integration and Ongoing Operations | 10/1/2026 | 11/1/2027
Revision Requests | 2026 | 4760 | NPRR1267 | NPRR1267 Large Load Interconnection Status Report | Not Started | $100k - $150k | 5 - 8 months | Content Delivery Systems, Data and Information Products, Resource Integration and Ongoing Operations | 10/1/2026 | 11/1/2027
Revision Requests | 2026 | 4770 | NPRR1226 | NPRR1226 Estimated Demand Response Data | Not Started | $100K - $150K | 5 - 7 months | Content Delivery Systems, Data and Information Products, Energy Management Systems | 1/15/2027 | 2/1/2028
Revision Requests | 2026 | 4780 | NPRR1281 | 547-01 NPRR1281 Improvements to Alternate FFSS Resource Designation | Execution | $75k - $100k | 6 - 8 months | Database Management Systems | 2/1/2026 | 2/1/2027
Revision Requests | 2026 | 4800 | NPRR1290, NPRR1323 | 566-01 NPRR1290 Gap Resolutions and Clarifications for the Implementation of RTC-B, Including NPRR1323 | Execution | $75k - $100k | 5 - 7 months | Data and Information Products, Database Management Systems, Market Operation Systems | 4/1/2026 | 5/1/2027
Revision Requests | 2027 | 4800 | NPRR1256 | NPRR1256 Settlement of MRA of ESRs | Not Started | $25k - $50k | 3 - 5 months | Credit Settlements & Billing Systems | 7/1/2027 | 8/2/2028
Revision Requests | 2028 | 5100 | NPRR1229 | NPRR1229 Real-Time Constraint Management Plan Cost Recovery Payment | Not Started | $100K - $200K | 8 - 10 months | Market Operation Systems, Retail Systems | 4/1/2028 | 5/9/2029
Securitization | 2021 | 330 | NPRR1103, NPRR1114 | 379-01 Securitization - Subchapter N | Complete | $700k - $1M | 9 - 12 months | Channel Management Systems, Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems | 8/1/2021 | 10/7/2022 | 2022-R6
Securitization | 2022 | 340 | NPRR1103, NPRR1114 | 421-01 Securitization Phase 2A- Maine Invoice and Credit Exposure | Complete | $300k - $500k | 8 - 12 months | Channel Management Systems, Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems | 11/1/2022 | 10/25/2023 | 2023-R4
Technical Health | 2021 | 1440 | SCR815 | 376-01 MarkeTrak Upgrade & Enhancements | Complete | $350k - $550k | 15 - 20 months | Database Management Systems, ERCOT Website and MIS Systems, Infrastructure Systems, Integration Systems, Retail Systems | 9/1/2021 | 4/1/2023 | 2022-R6
Technical Health | 2022 | 3000 | SCR813 | 450-01 NMMS IMM Schema upgrade to CIM 16 | Execution | $1.0M - $1.5M | 18 - 24 months | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Grid Modeling Systems | 8/1/2023 | 9/1/2027