## Slide 1
Project Update
February 9, 2022
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2022 Release Targets
  In-Flight Strategic Projects
    Fast-Frequency Response (FFR) Advancement
    DGR/DESR Implementation
    BES Combo Model Implementation
  Securitization Update
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1092 – Reduce RUC Offer Floor and Remove RUC Opt-Out Provision
    NPRR1120 – Create Firm Fuel Supply Service
    SCR818 – Changes to Incorporate GIC Modeling Data into Existing Modeling Applications
  Technology Working Group
    Meeting on 2/10/2022
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 February Release – R1 – 2/1/2022-2/3/2022 Various dates
  NPRR1005 – Clarify Definition of Point of Interconnection (POI) and Add Definition Point of Interconnection Bus (POIB)
  NOGRR210 / RRGRR025 – Related to NPRR1005
  LPGRR068 – Add BUSLRG and BUSLRGDG Profile Types
  NPRR917 – Nodal Pricing for SODGs and SOTGs
  NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
  NPRR1065 – Implementation Adjustment for NPRR917
  NPRR1054 – Removal of Oklaunion Exemption Language (partial implementation)
2022 March Release – R2 – 3/29/2022-3/31/2022 In Flight
  SCR814 – Point-to-Point (PTP) Obligation Bid Interval Limit
2022 May Release – R3 – 5/24/2022-5/26/2022 In Flight
  NPRR939 – Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions
  NPRR1093 – Load Resource Participation in Non-Spinning Reserve
  NPRR1101 – Create Non-Spin Deployment Groups made up of Generation Resources Providing Off-Line Non- Spinning Reserve and Load Resources that are Not Controllable Load Resources Providing Non-Spinning Reserve
  SCR800 – Addition of DC Tie Ramp to GTBD Calculation
  SCR809 – Changes to External Telemetry Validations in Resource Limit Calculator
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.
2/1/2022
2/4/2022
2/10/2022-2/11/2022

## Slide 4: 2022 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Various | March 3/29 – 3/31 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NOGRR210 RRGRR025 NPRR917 NPRR1052 NPRR1065 NPRR1073 NPRR1016 PGRR082 NOGRR212 | SCR814 | NPRR939 NPRR1093 NPRR1101 SCR800 SCR809 | NPRR1108 | FFR Advancement (NPRR863 FFR) | TBD
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
P
E
E
P
P
E
E
E
E
Securitization Subchapter N March Go-Live
ECRS project starts in 1/2022 with a go-live target prior to the EMS Freeze
1/1
E
EMS Freeze
Mid-2023 – Mid-2024
E
ü
ü
ü
ü
DGR/DESR
NPRR1054(a) – Portion of gray box
SCR789 Ph2
Late 2022
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 879, 885, 904, 918, 930, 935(b), 936, 941, 945, 962, 965, 1004, 1006, 1019, 1023, 1030, 1032, 1034, 1040, 1057 SCRs: 799, 805, 812 Market Guides: PGRR066, PGRR076 Other Binding Docs: OBDRR009
P
ü
ü
ü
ü

## Slide 5: In-Flight Strategic Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on 6/22/2021)
    Planned go-live for 2021-R6 (December 2021)
    NPRR863, NPRR1015, NPRR1079, NOGRR187
  PR354-01 DGR/DESR Implementation (Gated to Execution phase on 7/30/2021)
    Target go-live 2022-R1 (February 2022)
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
  PR353-01 BES Combo Model Implementation – potential for multiple go-lives
    Target go-live TBD (core project On Hold until resources are available)
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
ESR: Energy Storage Resource
DGR: Distributed Generation Resource
BES: Battery Energy Storage
Blue text: ERCOT considering removing from project for earlier delivery
Revised go-live target = 2022-R5
Orange text: 1/1/2022 go-live for DGR/DESR registration purposes

## Slide 6: Securitization Update
NPRR1103 Securitization – PURA Subchapter M Default Charges
  Approved by Board of Directors on 12/10/2021
  Approved by PUCT on 12/16/2021
NPRR1114 Securitization – PURA Subchapter N Uplift Charges
  Approved by PRS on 1/13/2022
  Approved by TAC on 1/31/2022
  Pending Board and PUCT consideration in March

## Slide 7: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1092 | Reduce RUC Offer Floor and Remove RUC Opt-Out Provision | 2022 | 3005 | $150k-$250k, 8-12 months Impacted Systems: S&B, EMS, MMS, Reporting 3 phases expected in order to deploy critical elements as quickly as possible Suggested Rank puts this NPRR on a timeline similar to the BES restart
NPRR1120 | Create Firm Fuel Supply Service | 2022 | 330 | $250k-$400k, 9-12 months REGULATORY Impacted Systems: S&B, MMS, Registration, Reporting Targeting completion in Q4 2022
SCR818 | Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | 2023 | 3710 | $300k-$500k, 9-12 months Impacted Systems: Network Model Systems Likely approach: Deliver this project after completion of the in-flight SCR789 Phase 2 project
SCR820 | Operator Real-Time Messaging During Emergency | TBD | TBD | Additional time requested to complete IA Targeting IA for 4/14/2022 PRS meeting
PPL Rank Information
Next available 2022 Rank in Business Strategy = 3580
Next available Rank in Regulatory = 330
Options for…

## Slide 8: ERCOT Technology Working Group (TWG)
First meeting scheduled for February 10th, Thursday 2:00 PM – 4:00 PM
Open Meeting – WebEx information posted on ERCOT meetings site
Agenda includes –
  Review of charter & vice-chair nomination/selection
  Project Update
  Discussion on projects with interface change requirements
    NPRR1093 / FFRA / ECRS
  WAN refresh and encryption update
  NERC EMSWG update
  Information only topics
    MMS UI/OS UI IE support update/ MOTE enhancements/SCR820