## Slide 1
Item 9: Update on Securitization Subchapter N
Mark Ruane
Senior Director, Settlements, Retail and Credit
TAC
ERCOT Public
February 23, 2022

## Slide 2: Securitization Update
ERCOT will be posting clarification NPRRs for both M and N
  Provides for initial assessment of escrow deposits to avoid timing mismatches for new market entrants.
  Clarifies that escrow deposit funds must be sent to the correct account.
  For N, adds process for an LSE to return proceeds due to the outcome of a judicial review of pricing or uplift actions in connection with the period of emergency.
  Requesting urgency for both NPRRs.

## Slide 3: Securitization Update
The following slides lay out the sequence of key activities for N.
Timeline dates are estimates and are subject to change due to dependencies on multiple outside parties, viz. underwriters, SEC and ratings agencies.
ERCOT will provide updates to TAC and Market Notices will be issued as applicable throughout the process.
Next Steps and Draft Timeline

## Slide 4: Securitization Update
Completed Subchapter N Securitization Uplift Balance Milestones
Item | Dates
Opt-out deadline (45 days after Order) | November 29, 2021
REPs provide ERCOT Period of Emergency interval-level meter data for opted-out transmission voltage customers. | December 1, 2021
Deadline for ERCOT to file its calculation of total exposure and LRS (one-time manual calculation) (55 days after Order) | December 7, 2021
Urgent NPRR 1114 posted | December 29, 2021
Deadline for LSEs to verify ERCOT’s exposure calculation (70 days after Order) | December 22, 2021
(Continued on next slide)
Next Steps and Draft Timeline

## Slide 5: Securitization Update
Completed Subchapter N Securitization Uplift Balance Milestones
Item | Dates
NPRR 1114 WMS presentation | January 5, 2022
NPRR 1114 PRS review | January 13, 2022
NPRR 1114 CWG / MCWG review | January 19, 2022
NPRR 1114 TAC review | January 26, 2022
* N release date has interdependencies and constraints related to completion of FFR and DGR release activities (people and system environment constraint risks).
Next Steps and Draft Timeline

## Slide 6: Securitization Update
Upcoming Subchapter N Securitization Uplift Balance Milestones
Item | Estimated Dates
Clarification NPRRs filed | February 24, 2022
NPRR 1114 Board review | March 7, 2022
Board review of registration statement | March 7, 2022
Clarification NPRRs PRS review – urgency and language | March 9, 2022
NPRR 1114 PUCT review | TBD March 2022
Next Steps and Draft Timeline

## Slide 7: Securitization Update
Upcoming Subchapter N Securitization Uplift Balance Milestones
Item | Estimated Dates
Clarification NPRRs CWG/MCWG review | March 14, 2022
Clarification NPRRs TAC review | March 23, 2022
N system go-live | March 29, 2022
Clarification NPRRs Board review | April 12, 2022
Clarification NPRRs PUCT review | TBD April 2022
Next Steps and Draft Timeline

## Slide 8: Securitization Update
Upcoming Subchapter N Securitization Uplift Balance Milestones
Item | Estimated Dates
Initial N escrow deposit estimates provided (30 days before expected closing date) | May 2022
Registration statement completed | May 2022
Announce transaction | May 2022
Price transaction | May 2022
Escrow deposits due (at least one week before target closing date) | Late May 2022
Next Steps and Draft Timeline

## Slide 9: Securitization Update
Upcoming Subchapter N Securitization Uplift Balance Milestones
Item | Estimated Dates
Transaction close and funds received | June 2022
Market Notice: disbursement and invoicing schedule, payment information | June 2022
Disbursements commence | 2-3 days after closing
Invoicing begins (no sooner than 30 days after funding) | July 2022
Next Steps and Draft Timeline

## Slide 10: Securitization Update
Questions