## ImprovementCostSummary01262026
| Project Cost | [6 empty] | XFMR MVA
| 765 | 345 | 138 | 115 | 69 | Total |  | 765 | 345 | 138 | 115 | 69 | Total
2025 Completed | 0 | 1110737000 | 1429944000 | 0 | 248121000 | 2788802000 | 2025 Completed | 0 | 6700 | 0 | 0 | 40 | 6740 |  | For ROS and BOD Reports
2026 Completed | 0 | 0 | 8900000 | 0 | 0 | 8900000 | 2026 Completed | 0 | 0 | 0 | 0 | 0 | 0 |  | ·All Projects (in engineering, routing, licensing and construction): |  |  |  | 32631622485
2026 Planned | 0 | 3607924772 | 3060021003 | 0 | 857837000 | 7525782775 | 2026 Planned | 0 | 8656 | 1570 | 0 | 180 | 10406 |  | ·Transmission Projects Energized in 2026: |  |  |  | 8900000
2027 | 0 | 3078903000 | 2693014280 | 15000000 | 563083000 | 6350500280 | 2027 | 0 | 8472 | 1320 | 0 | 325 | 10117 |  | ·Transmission Projects Planned to Energize in 2026: |  |  |  | 7525782775
2028 | 1632100000 | 2370780000 | 2762331430 | 0 | 484223000 | 7249434430 | 2028 | 4500 | 6912 | 275 | 0 | 0 | 11687
2029 | 1863200000 | 2746365000 | 885633000 | 0 | 123787000 | 5668985000 | 2029 | 9000 | 6825 | 290 | 0 | 0 | 16115
2030 | 3649100000 | 791380000 | 197364000 | 0 | 43413000 | 4681257000 | 2030 | 16056 | 4200 | 0 | 0 | 0 | 20256
2031 | 820000000 | 26000000 | 205920000 | 0 | 58353000 | 1110273000 | 2031 | 0 | 0 | 0 | 0 | 0 | 0
2032 | 0 | 9000000 | 12690000 | 0 | 18700000 | 40390000 | 2032 | 0 | 600 | 0 | 0 | 0 | 600
2033 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 2033 | 0 | 0 | 0 | 0 | 0 | 0
2026 Completed | 0 | 0 | 8900000 | 0 | 0 | 8900000 | 2026 Completed | 0 | 0 | 0 | 0 | 0 | 0
2026 Planned | 0 | 3276992772 | 2805683003 | 0 | 720576000 | 6803251775 | 2026 Planned | 0 | 8056 | 1440 | 0 | 80 | 9576
2025-2033 | 7964400000 | 13741089772 | 11255817713 | 15000000 | 2402517000 | 35429324485 | 2025-2033 | 29556 | 42365 | 3455 | 0 | 545 | 75921
2025-2026 | 0 | 4718661772 | 4498865003 | 0 | 1105958000 | 10323484775 | 2025-2026 | 0 | 15356 | 1570 | 0 | 220 | 17146
2027-2033 | 7964400000 | 9022428000 | 6756952710 | 15000000 | 1296559000 | 25105839710 | 2027-2033 | 29556 | 27009 | 1885 | 0 | 325 | 58775
| Circuit Miles New | [6 empty] | Circuit Miles Rebuilt, Reconductored or Upgraded | [6 empty] | Total Circuit Miles New, Rebuilt, Reconductored or Upgraded
| 765 | 345 | 138 | 115 | 69 | Total |  | 765 | 345 | 138 | 115 | 69 | Total |  | 765 | 345 | 138 | 115 | 69 | Total
2025 Completed | 0 | 16.95 | 122.15 | 0 | 0 | 139.1 | 2025 Completed | 0 | 11.3 | 246.66 | 0 | 108.85 | 366.81 | 2025 Completed | 0 | 28.25 | 368.81 | 0 | 108.85 | 505.91
2026 Completed | 0 | 0 | 0 | 0 | 0 | 0 | 2026 Completed | 0 | 0 | 8.8 | 0 | 0 | 8.8 | 2026 Completed | 0 | 0 | 8.8 | 0 | 0 | 8.8
2026 Planned | 0 | 959.79 | 132.559 | 0 | 21.83 | 1114.179 | 2026 Planned | 0 | 131.06 | 625.66 | 0 | 376.18 | 1132.9 | 2026 Planned | 0 | 1086.35 | 757.389 | 0 | 398.01 | 2241.749
2027 | 0 | 151.78 | 115.87 | 3 | 16.93 | 287.58 | 2027 | 0 | 250.93 | 486.142 | 0 | 236.66 | 973.732 | 2027 | 0 | 402.71 | 602.012 | 3 | 253.59 | 1261.312
2028 | 184.8 | 445.54 | 244 | 0 | 1.5 | 875.84 | 2028 | 0 | 380.22 | 825.728 | 0 | 273.82 | 1479.768 | 2028 | 184.8 | 825.76 | 1064.228 | 0 | 275.32 | 2350.108
2029 | 257.45 | 383.2 | 57.94 | 0 | 2 | 700.59 | 2029 | 0 | 255.2 | 149.51 | 0 | 70.47 | 483.88 | 2029 | 257.45 | 638.4 | 207.45 | 0 | 72.47 | 1184.47
2030 | 629.6 | 271.01 | 39.4 | 0 | 0 | 940.01 | 2030 | 0 | 102.48 | 131.81 | 0 | 59.091 | 293.381 | 2030 | 629.6 | 373.49 | 171.21 | 0 | 59.091 | 1233.391
2031 | 185 | 0 | 13.44 | 0 | 1.2 | 199.64 | 2031 | 0 | 92.1 | 89.17 | 0 | 38.18 | 219.45 | 2031 | 185 | 92.1 | 102.61 | 0 | 39.38 | 419.09
2032 | 0 | 0 | 1.7 | 0 | 0 | 1.7 | 2032 | 0 | 0 | 4.05 | 0 | 0 | 4.05 | 2032 | 0 | 0 | 5.75 | 0 | 0 | 5.75
2033 | 0 | 0 | 0 | 0 | 0 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0
2026 Completed | 0 | 0 | 0 | 0 | 0 | 0 | 2026 Completed | 0 | 0 | 8.8 | 0 | 0 | 8.8 | 2026 Completed | 0 | 0 | 8.8 | 0 | 0 | 8.8
2026 Planned | 0 | 952.69 | 118.149 | 0 | 21.83 | 1092.669 | 2026 Planned | 0 | 131.06 | 553.97 | 0 | 311.69 | 996.72 | 2026 Planned | 0 | 1079.25 | 672.119 | 0 | 333.52 | 2084.889
2025-2033 | 1256.85 | 2228.27 | 727.059 | 3 | 43.46 | 4258.639 | 2025-2033 | 0 | 1223.29 | 2567.53 | 0 | 1163.251 | 4962.771 | 2025-2033 | 1256.85 | 3447.06 | 3288.259 | 3 | 1206.711 | 9210.58
2025-2026 | 0 | 976.74 | 254.709 | 0 | 21.83 | 1253.279 | 2025-2026 | 0 | 142.36 | 881.12 | 0 | 485.03 | 1508.51 | 2025-2026 | 0 | 1114.6 | 1134.999 | 0 | 506.86 | 2756.459
2027-2033 | 1256.85 | 1251.53 | 472.35 | 3 | 21.63 | 3005.36 | 2027-2033 | 0 | 1080.93 | 1686.41 | 0 | 678.221 | 3454.261 | 2027-2033 | 1256.85 | 2332.46 | 2153.26 | 3 | 699.851 | 6454.121

## FutureTPIT020126NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2026
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
81590 | Rio Medina substation | Adds Rio Medina Load serving station |  | Rio Medina |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-01-01 |  | 138 | 4.5 | 0 | 0 |  | Medina |  | Tier 2 |  |  | 2024-02-01 |  | 5804, 5805 | Y | N |  |  | 81591 | 81590
61232 | RGEC Persimmon Gap Substation 69-kV Transmission Line Extension and Substation Expansion | Extend Alpine-Persimmon Gap 69-kV Transmission Line at Switch# 6669 and Install Circuit Switcher to accommodate new substation power transformer and distribution bays. New power transformer capacity will be 12/16/20 MVA. | Scheduled RUS Construction Work Plan Project | Persimmon Gap | Persimmon Gap | Planned | 85965 | RGEC | Ruben Quiroga rquiroga@rgec.coop 830-291-4203 |  | 2027-01-01 |  | 69 | 0 | 0 | 0 |  | Brewster | Brewster | Tier 4 | [5 empty] | Y | N |  |  | 61233 | 61232
80404 |  | Reroute East to Rodgers 69kV line to create East to Rayburn 69kV line to accommodate the TXDOT SH6 project. |  | BRYN EAST | RAYBURN | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-01-01 |  | 69 | 1 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32849, 32861, 32874 | Y |  |  |  | 90442 | 80404
87514 | RCEC_BranchChanges_Kaufman_Update5 | Updating line info between Boze and CombineRC1 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-01-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6903, 6904 | Y |  |  |  | 87515 | 87514
81895 | BPUB Branch Changes | Removing branch Price to Loma, adding Price to Stillman, adding another branch Loma Alta to Stillman. |  | 59410, 5962 | 79601, 79601 | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2027-01-01 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 59410, 79601 | Y |  |  |  | 81896 | 81895
81415 | Hermleigh Synchronous Condenser | Add Hermleigh Syncrhonous Condenser |  | Tonkawa | Tonkawa | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | D20232 | 2027-01-14 |  | 345 | 0 | 0 | 0 | 0,350 | Scurry | Scurry | Tier 1 |  |  |  |  | 1048, 18556, 18557 | Y |  |  |  | 100033 | 81415
81410 | Averitt Synchronous Condenser | Add Averitt Switch Synchronous Condenser | [5 empty] | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | D20231 | 2027-01-15 |  | 345 | 0 | 0 | 0 | -175350 | Ector | Ector | Tier 1 |  |  |  |  | 18544, 18553, 18554 | Y |  |  |  | 100032 | 81410
100305 | Cross Expansion: Modify existing 345 kV Station | Expand Cross station to connect a large load |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Hall |  | Tier 4 |  |  |  |  | 60501, 79002, 79004, 79010 | Y |  |  |  | 100306 | 100305
70305 | Camp Elizabeth: Build new 69 kV station | Construct new 69 kV box bay station with capacitor bank on the College Hills West to Sterling City 69 kV line | Company Contact and In-Service Date Update | Camp Elizabeth |  | Planned |  | AEP TNC | Bradley Case myturner@aep.com 918-599-2437 |  | 2027-01-31 |  | 69 | 0 | 0 | 0 | 0,7.7 | Sterling |  | Tier 4 |  |  |  |  | 6417, 6435, 6436, 6641, 11352 | Y | N |  |  | 70306 | 70305
65837 | New Cachena Substation |  |  | 5133 | 5323 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 5068, 5133, 5323 | Y |  |  |  | 65838 | 65837
69902B | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | Upgrade Ckt.71C TH Wharton to Zenith in order to increase thermal limits |  | TH Wharton | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44900, 45500 | Y | N |  |  | 98394 | 69902
67422F | Greens Bayou to Clinton 138kV Conversion | Remove Wallisville substation from Ckt.10A service… Resulting in Ckt.10A Clinton to Greens Bayou |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40250, 40251, 40352, 40720, 41680, 41682, 48299 | Y | N |  |  | 87579 | 67422
86800 | Pendulo: Construct New 345 kV Terminal | Interconnect Rubicon Alpha Wind to the Pendulo 345 kV station |  | Pendulo |  | Planned | TP2024057 | ETT | Robert Doughterty myturner@aep.com 918-599-2437 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60507 | Y | N |  |  | 86801 | 86800
99000A | Install (2) 14.4 MVAR distribution cap banks at Twinwood substation. Install (2) 14.4 MVAR distribution cap banks at Fulshear substation. Install (2) 55 MVAR transmission cap bank at Peters substation. | Install (2) 14.4 MVAR distribution cap banks at Twinwood substation. Install (2) 14.4 MVAR distribution cap banks at Fulshear substation. |  | Twinwood / Fulshear |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 |  | 138 | 0 | 0 | 0 | 0,57.6 | Fort Bend |  | Tier 4 |  |  |  |  | 44750, 44860 | Y | N |  |  | 99001 | 99000
73496 | Nelson Sharpe: Construct New 345 kV Terminal | Interconnect Noria Hondo Solar and BESS to the Nelson Sharpe 345 kV station |  | Nelson Sharpe |  | Planned |  | AEP TCC | Robert Dougherty deevans@aep.com 918-599-2938 |  | 2027-01-31 |  | 345 | 1 | 0 | 0 |  | Nueces |  | Tier 4 | [5 empty] | Y |  |  |  | 73497 | 73496
44399 | South Padre Island: Rebuild as GIS station | Rebuild South Padre Island as a GIS |  | South Padre Island | - | Planned | 948 - 1126 | AEP TCC | Ali Abukar deevans@aep.com 918-599-2938 | 3712 | 2027-01-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 | 24RPG036 | 2024-11-25 | 2024-12-27 |  | 8335, 8917 | Y | N |  |  | 44400 | 44399
67422G | Greens Bayou to Clinton 138kV Conversion | Convert Wallisville substation from Ckt.10A service to 138kV loop service on 138kV TEXWAL to Clinton Ckt.13 to create new Ckt.13 Greens Bayou to TEXWAL to Wallisville to Clinton. |  | Greens Bayou | Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 00:01 |  | 138 | 2.17 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40250, 40350, 41575, 41660, 41680 | Y | N |  |  | 87580 | 67422
49564 | Mantle: Construct New 345 kV Station | Mantle: Construct New 345 kV Station |  | Mantle |  | Planned | 1035 - 1213 | AEP TCC | Tom Reynolds jlsolis@aep.com 361-881-5574 | 3774 TP2018166 | 2027-01-31 20:00 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8059, 8383, 8573 | Y | N |  |  | 49565 | 49564
20TPIT0000 | Parkway Substation T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2027-02-04 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10679 | 3323
87413 | Establish Fallstown Switch – Pleasant Valley/Fisher Road 138 kV Double-Circuit Line and Fallstown Switch – Ceramic/Wichita Falls PPG 138 kV Double-Circuit Line | Establish Fallstown Switch – Pleasant Valley/Fisher Road 138 kV Double-Circuit Line and Fallstown Switch – Ceramic/Wichita Falls PPG 138 kV Double-Circuit Line |  | Fallstown Switch | Pleasant Valley/Fisher Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4024 | 2027-02-05 |  | 138 | 0 | 10.7 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1450, 1483, 1484, 1485, 1488, 17005 | Y |  |  |  | 87414 | 87413
51005 | Rocksprings to Friess Ranch: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line |  | Rocksprings | Friess Ranch | Planned | 1044 - 1217 | AEP TCC/AEP TNC, ETT | Greg Crane deevans@aep.com 918-599-2938 | 2792 | 2027-02-28 |  | 69 | 0 | 22.6 | 0 |  | Edwards | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 8238, 60210 | Y | N |  |  | 51006 | 51005
72213 | Cedar Hill: Upgrade Relays | Upgrade relays for the Sterling City terminal and Miles terminal at the Cedar Hill 138 kV station | Company Contact and In-Service Date Update | Cedar Hill |  | Planned |  | AEP TNC | Chase Stevens myturner@aep.com 918-599-2437 | TP2022739 | 2027-02-28 |  | 69 | 0 | 0 | 0 |  | Lee |  | Tier 4 |  |  |  |  | 6422, 6423, 6431 | Y | N |  |  | 72214 | 72213
73067 | Marina: Construct New Station | Construct new network station on the Highway 9 to Morris St and Nueces Bay 138 kV lines | In-Service Date Update | Marina |  | Planned |  | AEP TCC | Marc Wilson deevans@aep.com 918-599-2938 |  | 2027-02-28 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8064, 8441, 8470, 8474, 8620, 8623, 8733 | Y |  |  |  | 73068 | 73067
92651 | Oncor_MNE_92651_Barnett138 kV Switch |  |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2027-02-28 |  | 138 | 0 | 0 | 0 |  | Delta | Delta | Tier 4 |  |  |  |  | 1802, 1820, 2932 | Y |  |  |  | 92652 | 92651
89961 | RCEC_Horton_Load | Added Horton bus, along with load and branches |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1820, 6869 | Y |  |  |  | 89962 | 89961
76816 | Upgrade Loyola Auto | Upgrade Loyola Auto |  | Loyola | Loyola | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5648, 5650 | Y |  |  |  | 76817 | 76816
81229 | Upgrade Oaks Auto | Upgrade Oaks Auto to 150MVA |  | Oaks | Oaks | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-03-01 |  | 138 | 0 | 0 | 150 |  |  |  | Tier 4 |  |  |  |  | 5712, 5713 | Y |  |  |  | 81230 | 81229
90476 |  |  |  | Sivells Bend Tap | Sivells Bend | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-01 |  | 69 | 1.5 | 0 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 716, 725, 727 | Y |  |  |  | 90477 | 90476
99391B | Stanton East - Midland Basin - Spraberry 69 kV Line Conversion to 138 kV | Add part of Permian Basin Reliability Plan Upgrade ID L18. Decommissions Midland Basin, Midland Gulf, Spraberry, Martin, and Stanton East 69 kV Stations. |  | Spraberry | Stanton East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L18_A | 2027-03-01 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 1230, 1231, 1326, 1329, 1330 | Y |  |  |  | 99393 | 99391
80336 |  |  |  | WESTLOOP | BROCK | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 2.23 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 480, 487 | Y |  |  |  | 80337 | 80336 | 2023-NC26
72568 | Friendship to Rutherford Storm Hardening | Rebuild single circuit section of Friendship to Rutherford and reconductor with bundled 795 ACSR Conductor, 440 MVA. Replaces Project ID 61270. |  | Friendship | Rutherford | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-03-15 |  | 138 | 0 | 4.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70507, 70509 | Y | N |  |  | 72569 | 72568
78179 |  |  |  | Ding Dong | Ding Dong | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 0 | 0 | 0,12 | Bell | Bell | Tier 4 |  |  |  |  | 115 | Y |  |  |  | 78180 | 78179
91570 |  |  |  | Gustine | Pottsville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-19 |  | 69 | 0 | 0 | 0 |  | Hamilton | Hamilton | Tier 4 |  |  |  |  | 178, 272, 273 | Y |  |  |  | 91571 | 91570
80852 | Lolita: Construct New 138 kV Terminal | Interconnect Third Coast BESS to the Lolita 138 kV station | In-Service Date Update | Lolita |  | Planned | TP2023138 | AEP TCC | Sally Matthews deevans@aep.com 918-599-2938 |  | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 8125 | Y | N |  |  | 80853 | 80852
81368 | Rio Pecos: Upgrade 138 kV Terminals | Upgrade the Soaptree and Whitebaker 138 kV terminals at the Rio Pecos 138 kV station |  | Rio Pecos |  | Planned | TP2023625 | AEP TNC | Brooks Dow twang1@aep.com 918-599-2635 |  | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6601, 38445 | Y | N |  |  | 81369 | 81368
100478 | Establish Woodfin 138 kV Switch | Establish Woodfin 138 kV Switch |  | Woodfin 345 kV Switch |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3341 | 2027-03-31 | 2025-05-15 | 345 | 0 | 0 | 0 |  | Lamar | Lamar | Tier 4 |  |  |  |  | 1465, 1690, 11683 | Y |  |  |  | 100479 | 100478
90053 | Dokmai: Construct New 138 kV Station | Interconnect Hyfuels Western Farmland Wind to the new Dokmai 138 kV station on the Cangrejo to Dacosta 138 kV line between Beecher and Cangrejo |  | Dokmai |  | Planned |  | AEP TCC | Lance Price deevans@aep.com 918-599-2938 | TP2024120 | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | 8721, 8723, 80090 | Y | N |  |  | 90054 | 90053
91537 | Starlite_Substation_Addition | LCRA TSC will construct the 138-kV Starlite Substation to facilitate the Generation Interconnection Request (GINR) submitted for by the Interconnecting Entity, "Blanquilla BESS LLC" (Generator). |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-03-31 | 2027-03-31 | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8452, 78568, 78570 | Y |  |  |  | 91538 | 91537
90059 | Cascabel: Construct New 345 kV Station | Interconnect Moccasin Solar to the new Cascabel 345 kV station on the Clear Crossing to Figaro 345 kV line between Clear Crossing and Kirchoff | Company Contact and In-Service Date Update | Cascabel |  | Planned |  | ETT | Charles Burks myturner@aep.com 918-599-2437 | TP2024121 | 2027-03-31 |  | 345 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 60124, 60515, 60705 | Y | N |  |  | 90060 | 90059
80824 | Zenaida: Construct New 138 kV Station | Interconnect Dove Run Solar to the new Zenaida 138 kV station on the Crestonio to Falfurrias 138 kV line | Company Contact and In-Service Date Update | Zenaida |  | Planned | TP2023843 | AEP TCC | Andrew Garlick jlsolis@aep.com 361-881-5574 |  | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Duval |  | Tier 4 |  |  |  |  | 8510, 8695, 80043 | Y | N |  |  | 80825 | 80824
80830 | Zenaida: Construct New 138 kV Station | Interconnect Sun Cactus Solar to the new Zenaida 138 kV station on the Crestonio to Falfurrias 138 kV line | Company Contact and In-Service Date Update | Zenaida |  | Planned | TP2023851 | AEP TCC | Andrew Garlick jlsolis@aep.com 361-881-5574 |  | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Duval |  | Tier 4 |  |  |  |  | 80043 | Y | N |  |  | 80831 | 80830
80502 | Lon Hill: Construct New 345 kV Terminal | Interconnect the Tom Cruise load to the Lon Hill 345 kV station | In-Service Date Update | Lon Hill |  | Planned | TP2023885 | AEP TCC | LaRissa Lundry deevans@aep.com 918-599-2938 |  | 2027-03-31 |  | 345 | 0.1 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8455, 80037 | Y |  |  |  | 80503 | 80502
92890 | Add Fresa load serving substation |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-04-01 |  | 69 | 0 | 0 | 0 |  | Atascosa | Atascosa | Tier 4 |  |  | 2024-02-01 |  | 5710, 5714, 5733 | Y | N |  |  | 92891 | 92890
73663 | New transformer (T1) at BPUB Waterport Substation | BPUB new load T1 at bus 59450 |  | Waterport Substation (59450) |  | Planned |  | BPUB/BROWNSVILLE PUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2027-04-02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 59450 | Y | N |  |  | 80507 | 73663
91289 | LCRATSC_Settlers Substation Upgrade | Settlers Substation Addition project will construct a new substation connecting to LCRA TSC owned 138-kV transmission lines T171 Austrop to Sim Gideon and T231 Bastrop to Webberville via a hard tap installation. In this project, LCRA TSC will upgrade the hard tap installation to a breakered facility. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-6691 | 2027-04-06 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 3 |  |  |  |  | 7322, 7327, 7328, 7329 | Y |  |  |  | 91959 | 91289
91549 | Gabriel - Split Transmission Line Upgrade | LCRA TSC will upgrade T223 Gabriel to Georgetown East & T224 Gabriel to Jarrell 138-kV double-circuit transmission line from Gabriel to Split to obtain a higher operational rating. This 1.1-mile transmission line is owned by LCRA TSC. The remaining portions of T223 and T224 from Split to Georgetown East and from Split to Jarrell, respectively, are owned by Oncor. Line ratings and impedances being updated on ONCOR's PMCR 80546, phase #87647. | [5 empty] | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7996 | 2027-04-07 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y |  |  |  | 91550 | 91549
80295 | Add 2nd transformer at Ponder | Add 2nd transformer at Ponder |  | Ponder | Ponder | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-04-15 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 642 | Y |  |  |  | 80296 | 80295
82840 |  |  |  | HYDRA | Hydroponic | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-04-16 |  | 115 | 3 | 0 | 0 |  | Lubbock | Lubbock | Tier 4 |  |  |  |  | 700, 59122 | Y |  |  |  | 82841 | 82840
91108 | Fisk 345 kV Switch | Construct a new 345 kV Switch. |  | Brown Switch | Central Bluff | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6328 | 2027-04-17 |  | 345 | 0 | 0 | 0 |  | Coleman | Coleman | Tier 4 |  |  |  |  | 1444, 11263, 11406 | Y |  |  |  | 91109 | 91108
80858 | Sterling City: Upgrade 69 kV Relays | Upgrade relays at the Sterling City 69 kV station on the Angora 69 kV terminal | In-Service Date Update | Sterling City |  | Planned | TP2023887 | AEP TNC | Chase Stevens myturner@aep.com 918-599-2437 |  | 2027-04-30 |  | 69 | 0 | 0 | 0 |  | Sterling |  | Tier 4 |  |  |  |  | 6435, 6484 | Y | N |  |  | 80859 | 80858
73032 | Mulberry Creek: Rebuild 138 kV Station | Rebuild Mulberry Creek 138 kV station | Company Contact, Dollars, Tier, and RPG Dates Update | Mulberry Creek |  | Planned |  | AEP TNC | Forrest Farson myturner@aep.com 918-599-2437 |  | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Jones |  | Tier 3 | 25RPG034 | 2025-09-22 | 2025-10-16 |  | 6231, 6232, 6235, 6288 | Y | N |  |  | 73033 | 73032
90049 | Yellowjacket: Construct New 138 kV Terminal | Interconnect Black and Gold Energy Storage to the Yellowjacket 138 kV station |  | Yellowjacket |  | Planned |  | ETT | Christopher Carroll myturner@aep.com 918-599-2437 | TP2024115 | 2027-04-30 |  | 138 | 0.2 | 0 | 0 |  | Menard |  | Tier 4 | [5 empty] | Y |  |  |  | 90050 | 90049
90006 | Oklaunion: Construct New 345 kV Terminal | Interconnect the OPS load to the existing Oklaunion 345 kV station |  | Oklaunion |  | Planned |  | AEP TNC | Randy Weaver myturner@aep.com 918-599-2437 | TP2024106 | 2027-04-30 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6100 | Y |  |  |  | 90007 | 90006
86802 | Saragosa: Construct New 138 kV Terminal | Interconnect Cantaloupe Solar to the Saragosa 138 kV station |  | Saragosa |  | Planned | TP2024067 | AEP TNC | Damian Raab twang1@aep.com 918-599-2635 |  | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60716 | Y | N |  |  | 86803 | 86802
87019 | Rincon: Upgrade 138 kV Bus | Upgrade the Rincon 138 kV bus |  | Rincon |  | Planned |  | AEP TCC | Wade Weller deevans@aep.com 918-599-2938 | TP2024029 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8418, 8437, 8961 | Y |  |  |  | 87020 | 87019
87027 | Black Bayou: Construct New 138 kV Terminal | Interconnect Two Brothers BESS to the Black Bayou 138 kV station |  | Black Bayou |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | TP2024060 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 8911 | Y |  |  |  | 87028 | 87027
58010 | North McAllen: Rebuild 138 kV Station | Rehab the North McAllen 138 kV station |  | McAllen |  | Planned | 1118 - 1296 | AEP TCC | Thomas Neils jlsolis@aep.com 361-881-5574 | 3837 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8368, 8631, 8632 | Y |  |  |  | 65583 | 58010
76569 | Asherton: Rebuild 138 kV station | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | In-Service Date Update | Asherton |  | Planned |  | AEP TCC | Chris Carroll jlsolis@aep.com 361-881-5574 |  | 2027-04-30 02:00 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 8005, 8242, 8244, 8280, 8283 | Y |  |  |  | 76570 | 76569
76580 | Poblano: Build new 138 kV station | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | In-Service Date Update | Poblano |  | Planned |  | AEP TCC | Chris Carroll jlsolis@aep.com 361-881-5574 |  | 2027-04-30 02:00 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 8008, 8009, 8234, 8236 | Y |  |  |  | 76581 | 76580
75255D | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5056, 5231 | Y |  |  |  | 75850 | 75255
75255E | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5056, 5231 | Y |  |  |  | 75851 | 75255
99266 | Big Spring - Steer 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L21B. Upgrade the existing Big Spring - Steer 138-kV line. |  | Big Spring | Steer | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L21_B | 2027-05-01 |  | 138 | 0 | 5.8 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 1322, 10044 | Y |  |  |  | 99267 | 99266
91463 | New Station tapping Oak Grove to Rand 138kV line. | New Station tapping Oak Grove to Rand 138kV line. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6896, 6906, 6913 | Y |  |  |  | 91464 | 91463
99596 | Add Mosquito Lake Gen POI |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38043, 38053, 38055 | Y |  |  |  | 99597 | 99596
84892 | New transmission line between Tally and Ranchtown |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5358, 5422 | Y |  |  |  | 84893 | 84892
84894 | Upgrade transmission line between Tally and Texas Research |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5422, 5430 | Y |  |  |  | 84895 | 84894
88041 | Rebuild Leon Creek to Pearsal |  |  |  |  | Planned | T-0396 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5260, 5335 | Y |  |  |  | 88042 | 88041
99341 | ONCOR_FW_Horntoad 345 kV Switch | Add Horntoad 345 kV Switch |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8911 | 2027-05-06 |  | 345 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 11084, 11098, 18740 | Y |  |  |  | 99342 | 99341
100076 | Establish Maxdale 138 kV Switch | Establish Maxdale 138 kV Switch for Cosper Solar |  | Maxdale | Maxdale | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6468 | 2027-05-13 |  | 138 | 0 | 0 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 115, 3785, 3812 | Y |  |  |  | 100077 | 100076
99532 | Establish Guthrie 138 kV Switch | Establish 138 kV Switch |  | Big Springs Switch | Tributary | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8916 | 2027-05-13 |  | 138 | 0 | 0 | 0 |  | Howard | Mitchell | Tier 4 |  |  |  |  | 1322, 10119, 10206 | Y |  |  |  | 99533 | 99532
78044 | Hays Hill (fka Rock Draw) 345 kV Switch | Adding Oncor's portion of TNMP Silverleaf and Cowpen 345/138-kV Stations Project (23RPG013) |  | Sand Lake | North McCamey | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8716 | 2027-05-14 |  | 345 | 0 | 0 | 0 |  | Ward | Upton | Tier 1 | 23RPG013 | 2023-05-18 | 2023-06-09 |  | 11098, 18668, 76000 | Y |  |  |  | 78048 | 78044
92743 | Rebuild ~3 miles of double-ckt from VLSI to Grissom transmission line with normal and emergency ratings of at least 478MVA |  |  | 5467 | 5185 | Planned | T-0377 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-14 |  | 138 | 0 | 3.03 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5185, 5467 | Y |  |  |  | 92744 | 92743
100257 | Hill Country Auto #4 will be replaced Summer 2027 to a 10% impedance auto. |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-14 |  | 345 | 0 | 0 | 600 |  | Bexar |  | Tier 4 |  |  |  |  | 5208, 5211, 5215 | Y |  |  |  | 100258 | 100257
93250A | Utley_Substation_and_Transmission_Line_Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8065 | 2027-05-14 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 3 |  |  |  |  | 7316, 7317, 7322, 7327 | Y |  |  |  | 93251 | 93250
102788 | Overland_Substation_Addition | Construct a new 345-kV Overland substation and cut-in the double circuit Bakersfield Substation to Solstice Substation 345-kV transmission line (T718 and T683) to provide two (2) Points of Interconnection |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 60404, 76002, 76007 | Y |  |  |  | 102789 | 102788
92622 | Elroy_Wolf_Lane_Transmission_Line_Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee |  |  |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6950 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Travis | Tier 4 |  |  |  |  | 7209, 7212 | Y |  |  |  | 92623 | 92622 | 2024-SC20
92627 | Colton_Mendoza_Transmission_Line_Upgrade | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7994 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Travis | Tier 4 |  |  |  |  | 7208, 7325 | Y |  |  |  | 92628 | 92627 | 2024-SC20
93274 | Bastrop_Mesquite_Substation_Addition | Construct a new 138-kV substation in a ring bus configuration to serve BBEC customer load |  | 7320 | 7320 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-4500 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7310, 7316, 7320, 7322 | Y |  |  |  | 93305 | 93274
99367 | China Grove - 900126 (towards Barber Lake) 138 kV Line Section Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22F. Upgrade the existing China Grove - 900126 138-kV line |  | China Grove | Barber Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_F | 2027-05-15 |  | 138 | 0 | 0.1 | 0 |  | Mitchell | Mitchell | Tier 4 |  |  |  |  | 1190, 19521 | Y |  |  |  | 99368 | 99367
76312 | Establish Ramhorn 138kV Switch | Establish Ramhorn 138kV Switch and Ramhorn -Dunham 138 kV Line |  | Ramhorn | Dunham | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5007 | 2027-05-15 |  | 138 | 19 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 568, 1570, 1840, 1842 | Y |  |  |  | 82052 | 76312
99321 | Austin Ranch 138kV Capacitor Bank | Austin Ranch 138kV Capacitor Bank |  | Austin Ranch | Austin Ranch | Planned | M3222 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 | 0,110 | Denton | Denton | Tier 4 |  |  |  |  | 2378 | Y |  |  |  | 99322 | 99321
92778 | Dunham 345-138 kV Switch and Dunham - Burger Lake 138 kV Line Section | Establish Dunham 345/138 kV Switch and Dunham - Burger Lake 138 kV Line Section |  | Dunham | Dunham | Planned | M5007 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Denton | Denton | Tier 3 |  |  |  |  | 1840, 11840, 15114, 21851 | Y |  |  |  | 92779 | 92778
78369 | Rebuild Sam Switch - Venus Switch 345 kV DCKT | Rebuild Sam Switch - Venus Switch 345 kV DCKT |  | Venus | Sam | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6293 | 2027-05-15 |  | 345 | 0 | 76 | 0 |  | Ellis | Hill | Tier 1 | 24RPG017 | 2024-06-07 | 2024-07-02 |  | 1906, 1907, 3374, 3389, 68090 | Y |  |  |  | 78370 | 78369
76728 | Skyview 345/138 kV Switch | Establish Skyview 345/138 kV Switch |  | Skyview |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4350 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 1922, 1924, 1927, 2119, 2120, 2123, 2124, 2125, 2127, 2128, 2129, 2130, 2131, 2132, 2134, 2231, 2243, 2244, 11938 | Y |  |  |  | 76831 | 76728
99685 | Oncor_ME_99685_Nimbus 345 kV Switch | Establish Nimbus 345 kV Switch |  |  |  | Planned |  | ONCOR | Zagros Shahooei | M4475 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2217, 2249, 2466 | Y |  |  |  | 99686 | 99685
81440 | Wolf - Yarbrough 138 kV Line Rebuild | Rebuild the existing 138 kV line section from Wolf to Yarbrough. |  | Wolf | Yarbrough | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8527 | 2027-05-15 |  | 138 | 0 | 9.4 | 0 |  | Ward | Ector | Tier 3 |  |  |  |  | 1013, 1107, 10006, 11111, 11117 | Y |  |  |  | 81441 | 81440
91397 | Wolf_Lane_Wyldwood_Transmission_Line_Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee |  | Wyldwood | Wolf Lane | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6945 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7210, 7212 | Y |  |  |  | 91398 | 91397 | 2024-SC20
91404 | Howard Lane_Wells Branch_TL_Upgrade | LCRA TSC will upgrade T387 Howard Lane - Wells Branch 138-kV transmission line to achieve a higher operational rating. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7655 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7288, 7335 | Y |  |  |  | 91405 | 91404
98875 | Redberry (fka Elbow) - Prong Moss 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L20C Upgrade the existing Redberry (fka Elbow) - Prong Moss 138-kV line |  | Elbow | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L20_C | 2027-05-15 |  | 138 | 0 | 5.782 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 10066, 10080 | Y |  |  |  | 98952 | 98875
99353 | Oak Spring (fka Roscoe, Plowboy) 345/138 kV | Add Permian Basin Reliability Plan Upgrade ID L25A and L25B. Establish a new Roscoe 345/138-kV substation near the Sweetwater Tap (1341) and install two new 345/138-kV transformers. Loop the existing Sweetwater East - Champion Creek/Bitter Creek - Cattleman 345-kV double-circuit line into Roscoe. |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8613 | 2027-05-15 |  | 345 | 0.1 | 0 | 1200 |  | Nolan | Nolan | Tier 3 |  |  |  |  | 1341, 1414, 10053, 10100, 10101, 10104, 10105, 11342, 11420, 71050 | Y |  |  |  | 99354 | 99353
92347 |  |  |  | New station Walston | Butler | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 104, 105, 3283 | Y |  |  |  | 92348 | 92347
91626 | Upgrading Buda to Manchaca | Upgrading Buda to Manchaca branch to minimum of 379 MVA. | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70498, 70504 | Y |  |  |  | 91627 | 91626
72011B | Tonkawa - Ranger Camp 345 kV Line Rebuild | Tonkawa - Ranger Camp 345 kV Line Rebuild |  | Tonkawa | Ranger Camp | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2027-05-15 |  | 345 | 0 | 21.3 | 0 |  | Mitchell | Scurry | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 11048 | Y |  |  |  | 99962 | 72011
81152 | China Grove to Tributary 138 kV Line Rebuild | Rebuild China_Grove - Tributary 138 kV Line |  | China Grove | Tributary Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8656 | 2027-05-15 |  | 138 | 0 | 23.7 | 0 |  | Mitchell | Howard | Tier 3 |  |  |  |  | 1318, 10119 | Y |  |  |  | 87650 | 81152
98873 | Prong Moss 345-138 kV auto-transformers and 138 kV Switch | Add Permian Basin Reliability Plan Upgrade ID L20A, L20B and L20D Establish a new Prong Moss 345/138-kV substation and install two new 345/138-kV transformers. Loop the existing Elbow - Bulldog 138-kV line into Prong Moss. Loop the existing Hill Crest - McDonald Road 138-kV line into Prong Moss |  | Prong Moss | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8661 | 2027-05-15 |  | 138 | 0 | 0 | 600 |  | Howard | Howard | Tier 3 |  |  |  |  | 1333, 10057, 10066, 10067, 10068, 10080, 11351, 23833 | Y |  |  |  | 98874 | 98873
71912A | Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Fort Hood - Killeen Park Street Tap 138 kV Line |  | Killeen Fort Hood | Killeen Park Street Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6245 | 2027-05-15 |  | 138 | 0 | 3.95 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3626, 3627, 3635, 13626 | Y |  |  |  | 71913 | 71912
71912B | Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Park Street Tap - Killeen Taft 138 kV Line |  | Killeen Park Street Tap | Killeen Taft | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6245 | 2027-05-15 |  | 138 | 0 | 3.95 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3367, 3619, 3621, 3622, 3623, 3635 | Y |  |  |  | 71914 | 71912
87673 | Rebuild the Salado - Bell County 138 kV Line | Rebuild the Salado - Bell County 138 kV Line on new structures |  | Salado | Bell County | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6280 | 2027-05-15 |  | 138 | 7.8 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 132, 3640 | Y |  |  |  | 87674 | 87673
87675 | Rebuild the Bell County - Fryers Creek 138 kV Line | Rebuild the Bell County - Fryers Creek 138 kV Line on new structures |  | Bell County | Fryers Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6336 | 2027-05-15 |  | 138 | 3.2 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 132, 3493 | Y |  |  |  | 87676 | 87675
80546D | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild and double-circuit the Sonterra - Salado 138 kV Line Section. Establish Salado 138 kV Switch and the Salado Switch - Round Rock Switch 138 kV Line |  | Sonterra | Salado Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 121, 3640, 3664, 3668, 3677, 3730, 3764, 3777, 13640, 13641 | Y |  |  |  | 87642 | 80546 | 2023-SC17
82826 | Sunflower 138 kV Switch | Establish Sunflower 138 kV Switch |  | Sunflower Switch | Sunflower Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6322 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 170, 3592, 3722 | Y |  |  |  | 82827 | 82826
87707 | Salado 345/138 kV Autotransformer #1 and #2 | Install Salado 345/138 kV Autotransformer #1 and #2 |  | Salado | Salado | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6354 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3640, 3699, 3745, 3746 | Y |  |  |  | 87708 | 87707
99271 | Upgrade Hutto 138 kV terminal equipment | Upgrade Hutto 138 kV terminal equipment for the Hutto - Teal 138 kV Line |  | Hutto | Hutto | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6205 | 2027-05-15 |  |  | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3362, 3666 | Y |  |  |  | 99272 | 99271
92561 | LCRATSC_Colton_Elroy_Transmission_Line_Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. |  | 7208 | 7209 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org | PLC-6951 | 2027-05-15 |  | 138 | 0 | 3.27 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7208, 7209 | Y |  |  |  | 92562 | 92561 | 2024-SC20
99821 | LCRATSC_Copperas_Cove-Kempner_Transmission_Line_Overhaul | Perform an overhaul on the 5.6 mile T721 Kempner - Copperas Cove 138-kV transmission line. |  | 7323 | 7330 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-05-15 |  | 138 | 0 | 5.62 | 0 |  | Lampasas | Lampasas | Tier 4 |  |  |  |  | 7061, 7260 | Y |  |  |  | 99822 | 99821
68681 | Lamar Blossom Switch - Clarksville 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Lamar | River Crest | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5325 | 2027-05-15 |  | 69 | 0 | 0 | 0 |  | Lamar | Red River | Tier 4 |  |  |  |  | 1772, 1785, 11784 | Y |  |  |  | 68682 | 68681
99687 | Oncor_MNE_99687_Paradise Lake 345 kV Switch | Establish Paradise Lake 345 kV Switch |  | Franklin | Franklin |  |  | ONCOR | Zagros Shahooei | M3340 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1695, 2449, 11699 | Y |  |  |  | 99696 | 99687
99064 | Clarksville 69 kV Capacitor Bank | Clarksville 69 kV Capacitor Bank |  | Clarksville |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5350 | 2027-05-15 |  | 69 | 0 | 0 | 0 | 0,13.8 | Red River |  | Tier 4 |  |  |  |  | 1784 | Y | N |  |  | 99065 | 99064
100291 | Most_Limiting_Series_Element_FY2025_Substation_Upgrade | Increase the capacity of transmission circuits by upgrading the limiting elements at various substations. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7560, 7575, 7576, 78103, 78104 | Y |  |  |  | 100292 | 100291
99919 | Georgetown Power Transformer Upgrade | Upgrade the Georgetown 138-kV transmission bus to a four circuit breaker improved bus with Gas Insulated Switchgear (GIS). The new switchgear and all 138-kV series equipment should be rated at 4000 continuous amps. Upgrade Georgetown T1 and Georgetown T2. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 99920 | 99919
99542 | Establish Axtell 345 kV Switch | Establish Axtell 345 kV Switch for Pepper Solar |  | Axtell 345 kV Switch | Axtell 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6469 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3405, 3406, 3806 | Y |  |  |  | 99543 | 99542
99610 | Upgrade Jacksonville Switch 138/69 kV Auto | Upgrade Jacksonville Switch 138/69 kV Auto |  | Jacksonville 69 kV Switch | Jacksonville 69 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6399 | 2027-05-15 |  | 69 | 0 | 0 | 125 |  | Cherokee | Cherokee | Tier 4 |  |  |  |  | 3253, 3254 | Y |  |  |  | 99611 | 99610
99624 | Upgrade Redland Switch - Herty Tap 138 kV Line Section | Upgrade Redland Switch - Herty Tap 138 kV Line Section |  | Redland 138 kV Switch | Herty Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6291 | 2027-05-15 |  | 138 | 0 | 6.9 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3306, 3318 | Y |  |  |  | 99625 | 99624
78046 | Blue Goose (fka Toyah Creek) 345 kV Switch | Adding Oncor's portion of TNMP Silverleaf and Cowpen 345/138-kV Stations Project (23RPG013) |  | Sand Lake | Solstice | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8715 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Ward | Pecos | Tier 1 | 23RPG013 | 2023-05-18 | 2023-06-09 |  | 11098, 18669, 60404 | Y |  |  |  | 78049 | 78046
5526 | Three Creek 345/138 kV Switch (fka Forney) | Rebuild existing 345/138 kV switching |  | Forney |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4114 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 1 | 24RPG021 | 2024-07-02 | 2024-07-29 |  | 2432, 2437, 2438, 12438, 22438 | Y | N |  |  | 78356 | 5526
71156 | Ennis West Switch-Waxahachie Switch 138 kV Line Rebuild | Rebuild the Ennis West-Waxahachie 138 kV Line |  | Ennis West | Waxahachie | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4200 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2241, 2321, 12320 | Y |  |  |  | 71160 | 71156
85977A | Cedar Hill - Swiftex Transmission Line Upgrade | Upgrade the existing T367 Cedar Hill - Swiftex 138-kV transmission line from Cedar Hill to Str 181 (Elgin Tap) |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 3674, 7326, 7331 | Y |  |  |  | 85978 | 85977 | 2023-SC15
85977B | Cedar Hill - Swiftex Transmission Line Upgrade | Corrects topology for Elgin Tap and its associated branches |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 7310, 7319, 7326, 7331, 7674, 13674 | Y |  |  |  | 90939 | 85977 | 2023-SC15
80870 | Bakersfield Dynamic Reactive Substation Upgrade | Add a 350 MVAR synchronous condenser at Bakersfield substation based on ERCOT recommendation. |  | Bakersfield (BAKESW) | Bakersfield (BAKESW) | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | 1030378 | 2027-05-15 |  | 345 | 0 | 0 | 0 | -350350 | Pecos | Pecos | Tier 1 | 23RPG027 | 2023-09-07 | 2023-09-28 |  | 76002, 76101, 76102 | Y |  |  |  | 80926 | 80870 | 2023-FW10
85979 | Elgin - Elgin Tap Transmission Line Overhaul | Perform an overhaul on the 2.2 mile T728 Elgin (structure #17/7) - Elgin Tap 138-kV transmission line. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 | 2958101 | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 3674, 7326, 7331, 13674 | Y |  |  |  | 85980 | 85979 | 2023-SC15
100184 | LyttonSprings_Mendoza_Transmission_Line_Upgrade | LCRA TSC will upgrade T534 Lytton Springs - Mendoza 138-kV transmission line to obtain a higher operational rating. |  | Lytton Springs | Mendoza | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7325, 9075 | Y |  |  |  | 100185 | 100184
87695 | Hartrick 138 kV Switch | Establish Hartrick 138 kV Switch |  | Bell County | Bell County | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6363 | 2027-05-16 |  | 138 | 0 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 132, 3493, 3598, 3640 | Y |  |  |  | 87696 | 87695
99136 | Wilke 138 kV Capacitors | Install 110.4 MVAR capacitor bank at Wilke 138 kV Substation |  | Wilke | Wilke | Planned | R6457 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2027-05-16 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3734 | Y |  |  |  | 99137 | 99136
89889 | Three Creek 138 kV Capacitor Bank |  |  | Three Creek |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4114 | 2027-05-16 |  | 138 | 0 | 0 | 0 | 0,110.4 | Kaufman |  | Tier 4 |  |  |  |  | 2438 | Y | N |  |  | 89891 | 89889
87701 | Establish the Roberts 138 kV Switch | Establish the Roberts 138 kV Switch |  | Watercrest | Watercrest | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6353 | 2027-05-16 |  | 138 | 0 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3626, 3627, 3744, 13628 | Y |  |  |  | 87702 | 87701 | 2023-NC57
91293 | LCRATSC_Gabriel-Schwertner TL conversion | This project is needed to meet a request from BEPC to voltage convert (69-138-kV) and increase the capacity of the BEPC-owned Gabriel - Schwertner circuit on the TSC-owned 138-kV T359 transmission line. As part of this upgrade, LCRA TSC will upgrade conductor on T359 from Gabriel to Str. 21R. |  |  |  | Planned |  | LCRATSC | dylan.preas@lcra.org 512-578-4514 | PLC-8197 | 2027-05-17 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7345, 7346, 7523 | Y |  |  |  | 91970 | 91293
86912 |  |  |  | Gabriel | Schwertner | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-05-21 |  | 138 | 0 | 12.6 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 122, 7346 | Y |  |  |  | 86913 | 86912
78173 |  |  |  | Trimmier | Trimmier | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-05-28 |  | 138 | 0 | 0 | 0 | 0,12 | Bell | Bell | Tier 4 |  |  |  |  | 136 | Y |  |  |  | 78174 | 78173
75835C | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Phase Three of overall approved upgrades. |  | Stone Lake | Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-30 |  | 138 | 0 | 2.45 | 0 |  | Harris | Harris | Tier 3 | 23RPG012 | 2023-05-04 | 2023-05-26 | 2023-05-26 | 44840, 48348 | Y | N |  | Cost included in main entry | 98430 | 75835
90255E | Jordan / Mont Belvieu Area Improvement Project | Apply 110% Emergency rating for the EAGLE customer substation 2000A equipment to increase thermal limits on Ckts 52B / 52C. Upgrade existing 515 / 515 MVA Mont Belvieu relay system limits on Ckt.52C line position. |  | EAGLE | WINFRE/Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40500, 40764, 41111 | Y | N |  |  | 92979 | 90255
90255D | Jordan / Mont Belvieu Area Improvement Project | Upgrade Ckt.86H BRINE to Mont Belvieu to increase thermal limits. |  | BRINE | Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-30 |  | 138 | 0 | 2.8 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40220, 41111 | Y | N |  |  | 92981 | 90255
90255C | Jordan / Mont Belvieu Area Improvement Project | Upgrade Ckt.86A Cedar Bayou to CHEVRON to increase thermal limits. |  | Cedar Bayou | CHEVRON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Harris | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40015, 40300 | Y | N |  |  | 92982 | 90255
90255B | Jordan / Mont Belvieu Area Improvement Project | Upgrade Ckt.84D Cedar Bayou to CD/HOPSON to increase thermal limits. |  | Cedar Bayou | Cedar Bayou Distribution | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40015, 48065 | Y | N |  |  | 92980 | 90255
76082 | Union Carbide: Rebuild 138 kV Station | Rebuild Union Carbide as new AIS station Chalybe |  | Union Carbide |  | Planned |  | AEP TCC | Charity Kreher jlsolis@aep.com 361-881-5574 |  | 2027-05-31 | 2958101 | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 5767, 5963, 5965, 8337, 8338, 8535, 8735, 79601 | Y |  |  |  | 76083 | 76082
86791 | Crane to Rio Pecos: Rebuild 138 kV Line | Rebuild the Crane to Rio Pecos 138 kV line |  | Crane | Rio Pecos | Planned | TP2024050 | AEP TNC | Brooks Dow twang1@aep.com 918-599-2635 |  | 2027-05-31 |  | 138 | 0 | 23.65 | 0 |  | Crane | Crockett | Tier 1 | 23RPG023 | 2023-08-11 | 2024-01-18 | 2024-01-24 | 6601, 76615 | Y | N |  |  | 86792 | 86791
93163 | Diablo: Construct New Distribution Station | Construct new distribution station on the North McCamey to Palouse 138 kV line between Crossover and Palouse |  | Diablo |  | Planned |  | AEP TNC | Lance Price myturner@aep.com 918-599-2437 | DR24N0002 | 2027-05-31 |  | 138 | 8.4 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | 60115, 60723, 60728 | Y | N |  |  | 93164 | 93163
99648 | Pecan Bayou: 138 kV Circuit Breaker Addition | Install two 138 kV circuit breakers at the Pecan Bayou 138 kV station |  | Pecan Bayou |  | Planned |  | AEP TNC | Jennifer Kates myturner@aep.com 918-599-2437 | TP2023323 | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 | [5 empty] | Y | N |  |  | 99649 | 99648
91843 | East Munday: Rebuild 138 kV Station | Rebuild the East Munday 138 kV station |  | East Munday |  | Planned |  | AEP TNC | Bill Edwards myturner@aep.com 918-599-2437 | TP2023800 | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Knox |  | Tier 3 | 25RPG002 | 2025-01-20 | 2025-02-12 |  | 6110, 6117, 6161, 6320 | Y | N |  |  | 91844 | 91843
76369 | BRINE Substation Upgrades | Upgrade substation equipment at BRINE on Ckt.86H DALTON to BRINE to Mont Belvieu. |  | BRINE | DALTON/Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40220, 41111, 41740 | Y | N |  |  | 98395 | 76369
89924 | Weinbrenner 138kV Substation Expansion for SWITCH (SWG)/Elio BESS (25INR0103) | Expand 138kV Weinbrenner substation for SWITCH (SWG)/Elio BESS (25INR0103). Install one new generator lead from Weinbrenner to SWITCH/Elio BESS |  | Weinbrenner |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42990, 114681 | Y | N |  |  | 89925 | 89924
90134A | Elvis (EVS) 138kV CEHE Substation for ROCK N ROLL Storage (24INR0234) | Install new Elvis (EVS) 138kV CEHE Substation for generator interconnection to Rock N Roll Storage. Connect to Ckt.26B WINMIL to Rosharon to create new Ckt.26 WINMIL to Elvis to Rosharon. |  | Elvis | WINMIL/ Rosharon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 44531, 44560, 44600 | Y | N |  |  | 90847 | 90134
90134B | Elvis (EVS) 138kV CEHE Substation for ROCK N ROLL Storage (24INR0234) | Install one generator lead from Elvis (EVS) 138kV CEHE Substation to customer-owned ROCK_N (RNR) for ROCK N ROLL Storage (24INR0234) customer substation. |  | ROCK_N |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | Costs included in main entry | 90848 | 90134
90191 | Bromine 138/35kV Distribution Substation | Install Bromine 138/35kV Distribution Substation. Loop on Ckt.66A to create new Ckt.66A Katy tap to Bromine to Freeman. |  | Bromine | Katy/Freeman | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 45040, 45770, 48203 | Y | N |  |  | 90759 | 90191
90242A | Clute to Velasco Ckt.82 Upgrades RPG | Upgrade Ckt.26E SINTEK to CAMDEN to increase thermal limits. |  | SINTEK | CAMDEN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0.62 | 0 |  | Brazoria | Brazoria | Tier 4 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 43240, 43365 | Y | N |  |  | 102648 | 90242
90242B | Clute to Velasco Ckt.82 Upgrades RPG | Upgrade Ckt.82F RIWOOD to CAVERN to BIPORT to increase thermal limits. (Expect partial reconductor to Ckt.86F RIWOOD to CAVERN with 1-795ACSR limiting conductor and full 2-959ACSS reconductor to Ckt.86F CAVERN to BIPORT) |  | CAVERN | Clute/BIPORT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0.31 | 0 |  | Brazoria | Brazoria | Tier 4 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 42050, 42190, 43150, 43330 | Y | N |  |  | 102649 | 90242
90242C | Clute to Velasco Ckt.82 Upgrades RPG | Upgrade Ckt.82G BIPORT to OYSTER CREEK to increase thermal limits. |  | BIPORT | OYSTER CREEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0.21 | 0 |  | Brazoria | Brazoria | Tier 4 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 42190, 43335 | Y | N |  |  | 102650 | 90242
90242D | Clute to Velasco Ckt.82 Upgrades RPG | Upgrade Ckt.82D GLOBAL to Velasco to increase thermal limits. |  | GLOBAL | Velasco | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 1.06 | 0 |  | Brazoria | Brazoria | Tier 4 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 43345, 43360 | Y | N |  |  | 102651 | 90242
90255F | Jordan / Mont Belvieu Area Improvement Project | Install new CEHE-owned Sjolander substation. Reconfigure existing Ckt.84D Cedar Bayou to CD/HOPSON and loop into Sjolander substation to create new Ckt.84 Cedar Bayou to Cedar Bayou tap to Sjolander to HOPSON. |  | Sjolander | Cedar Bayou/ HOPSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 2 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40012, 40015, 40050, 41690, 48065 | Y | N |  |  | 92983 | 90255
90255A | Jordan / Mont Belvieu Area Improvement Project | Install 120 MVAr cap bank at Mont Belvieu Ckt.84E to WARVUE. |  | Mont Belvieu | WARVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 41111, 41700 | Y | N |  |  | 92984 | 90255
80576 | Chalmers: Construct New Distribution Station | Construct new distribution station on the Lane City to Magill 138 kV line |  | Chalmers |  | Planned | DP23X0014 | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8111, 8127, 8668, 8750, 89500 | Y |  |  |  | 80577 | 80576
55421 | Ballinger to Concho: Rebuild 69 kV line | Rebuild Ballinger to Concho 69 kV line, install POP switch for Rowena, install CB at Miles, install POP switch for Harriett REA |  | Ballinger | San Angelo Concho | Planned | 1088 - 1271 | AEP TNC | William Lovelace myturner@aep.com 918-599-2437 | 1861 | 2027-05-31 |  | 69 | 0 | 20.45 | 0 |  | Runnels | Tom Green | Tier 3 | 20RPG004 | 2020-04-08 | 2020-04-30 | 2020-05-08 | 6338, 6409, 6410, 6411, 6412, 6413, 6450 | Y | N |  |  | 55422 | 55421
6072 | Eldorado to Ft. McKavitt: Rebuild 69 kV Line | Rehab Eldorado to Ft. McKavitt 69 kV line |  | Eldorado Tap | Ft. McKavitt | Planned | 786 - 0971 | AEP TNC | William Lovelace myturner@aep.com 918-599-2437 | 2677 | 2027-05-31 |  | 69 | 0 | 19.41 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  |  | 6505, 6506, 6507, 6508 | Y | N |  |  | 13794 | 6072
87423 | Reconfigure TNMP Pyote 138kV Substation. |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-05-31 |  | 138 | 0.92 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37990, 38001, 38005 | Y |  |  |  | 87424 | 87423
76196 | Lobo: 138 kV Breaker Replacement | Replace 138 kV breakers at the Lobo 138 kV station | In-Service Date Update | Lobo |  | Planned |  | AEP TCC | Lance Price jlsolis@aep.com 361-881-5574 | TP2023015 | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80221 | Y |  |  |  | 76197 | 76196
90063 | Elm Creek to Mulberry Creek: Rebuild 138 kV Line | Rebuild the Elm Creek to Mulberry Creek 138 kV line |  | Elm Creek | Mulberry Creek | Planned |  | AEP TNC | Charles Burks twang1@aep.com 918-599-2635 | TP2023600 | 2027-05-31 |  | 138 | 0 | 5.7 | 0 |  | Taylor | Jones | Tier 4 |  |  |  |  | 6255, 60772 | Y | N |  |  | 90064 | 90063
90020 | Firerock: Install New 138/69 kV Autotransformer | Install new 138/69 kV autotransformer at the Firerock 138/69 kV station |  | Firerock |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TP2022133 | 2027-05-31 |  | 138 | 0 | 0 | 130 |  | Coleman |  | Tier 4 | [5 empty] | Y |  |  |  | 90021 | 90020
90047 | Big Hill to Rockefeller Storage: Construct New 345 kV Line | Interconnect Rockefeller Storage to the existing Big Hill 345 kV station | Company Contact Update | Big Hill | Rockefeller Storage | Planned |  | AEP TNC | Lance Price twang1@aep.com 918-599-2635 | TP2024144 | 2027-05-31 |  | 345 | 0.2 | 0 | 0 |  | Schleicher | Schleicher | Tier 4 | [5 empty] | Y |  |  |  | 90048 | 90047
84902 | Rebuild Spruce to Pawnee into a double circuit |  |  | 5400 | 5725 | Planned |  | CPS/STEC | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-31 |  | 345 | 45.83 | 45.83 | 0 |  |  |  | Tier 1 |  |  |  |  | 5400, 5725 | Y |  |  |  | 84903 | 84902
85987A | Upgrade Ckt.26 STRATT to SINTEK to increase thermal limits. Upgrade Ckt.26F Velasco to CAMDEN to increase thermal limits. | Upgrade Ckt.26D Clute STRATT Clute to SINTEK to increase thermal limits. (Expect a full 2-959ACSS reconductor Ckt.26 Clute to SINTEK and a 1-795AAC conductor limitation Ckt.26 STRATT to Clute) |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 5.26 | 0 |  | Brazoria | Brazoria | Tier 3 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 43240, 43300 | Y | N |  |  | 102652 | 85987
75810A | Install new 345kV Speedway substation for interconnection to Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. Install generator lead from Speedway to CRADLE solar | Install new 345kV Speedway (SPD) substation for generator interconnection to CRADLE/ Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. |  | Speedway | DOW/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 43035, 43060 | Y | N |  |  | 87165 | 75810
67427A | MINING 138kV Conversion and BENTON customer substation removal(24RPG033). | Rebuild/Repurpose existing 69kV Ckt.16C MINING Switchrack to MINING tap section. Retire MINING Switchrack from Ckt.16C to create new Ckt.16C Deepwater to South Channel. Remove customer-owned BENTON substation from CEHE service. Retire MINING 69kV substation. |  | Deepwater | South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | 24RPG033 | 2024-11-07 | 2024-12-02 | 2024-12-02 | 40470, 41380 | Y | N |  |  | 91250 | 67427
67427B | MINING 138kV Conversion and BENTON customer substation removal(24RPG033). | Install new customer-owned MINING 138kV substation. Loop substation on existing Ckt.06G to create new Ckt.06 Pasadena to College tap to MINING to Jefferson. |  | MINING-138 | College/ Jefferson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | 24RPG033 | 2024-11-07 | 2024-12-02 | 2024-12-02 | 40470, 41030, 41061, 41071, 41240, 41380, 48171, 48177, 48274, 111102 | Y | N |  | Costs included in main entry | 91249 | 67427
102779 | Fairbanks (FB) Substation Expansion | Expand existing 138kV Fairbanks substation with in-series breakers. |  | Fairbanks | TH Wharton/Deihl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 102781 | 102779
100503D | Webster Distribution Upgrades | Expand Webster with new TR4 distribution transformer and connect to Ckt.95F Polaris to Webster TR4 to Kemah. |  | Webster | Polaris/Kemah | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 43504, 48194, 48289 | Y | N |  |  | 100519 | 100503
100503C | Webster Distribution Upgrades | Disconnect Webster TR2 from Ckt.92A service and reconnect as Ckt.93A PH Robinson to Webster TR1/TR2 to Webster main bus. |  | Webster | PH Robinson/Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 43501, 43502 | Y | N |  | Cost included in main entry | 100518 | 100503
100503B | Webster Distribution Upgrades | Disconnect Webster TR2 from Ckt.92A service and reconnect at other circuit location (see other entry for TR2). Reconnect Webster TR3 as Ckt.92A El Dorado to WEB-TR3 to Kemah. |  | Webster | El Dorado/Kemah | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 43503, 48393, 48394 | Y | N |  | Cost included in main entry | 100517 | 100503
100503A | Webster Distribution Upgrades | Remove existing Webster TR3 tap from Ckt.35A Polaris to PH Robinson. Reconfigure tap section and reconnect to another circuit. |  | Polaris | PH Robinson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 42010, 43503, 48288, 48394 | Y | N |  |  | 100516 | 100503
102538 | Install distribution transformers at Intercontinental distribution substation. |  |  | Intercontinental |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 45910 | Y | N |  |  | 102539 | 102538
102540 | Upgrade Ckt.67B North Belt to DRILCO to increase thermal limits. |  |  | North Belt | DRILCO | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45740, 46110 | Y | N |  |  | 102541 | 102540
102542 | Expand Peters 138kV Substation from ring bus to Breaker-and-Half configuration. Connect two circuits from Peters to TRENCH (TRE) customer owned substation |  |  | Peters | TRENCH | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Austin |  | Tier 4 |  |  |  |  | 46210, 46220 | Y | N |  |  | 102543 | 102542
98994B | Replace Harrisburg with new Manchester Subsation | Upgrade existing Ckt.70B GOODYEAR to Magnolia Park to increase thermal limits. Loop new Manchester distribution substation on existing Ckt.70B to create new Ckt.70B GOODYEAR to Manchester to Magnolia Park. No Transmission Breakers expected |  | Manchester | GOODYEAR / Magnolia Park | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40650, 44930, 47700, 740800 | Y | N |  | Cost included in main entry | 98996 | 98994
99009A | 138kV Flewellen to Fort Bend Ckt 09G-60E Upgrades | Upgrade Ckt.09G Flewellen to Brazos Valley to increase thermal limits. Expect 2-959ACSS reconductor as first phase of Ckt.09G upgrade. |  | Flewellen | Brazos Valley | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 5.03 | 0 |  | Fort Bend | Fort Bend | Tier 4 | 25RPG010 | 2025-03-26 | 2025-04-18 | 2025-04-18 | 44100, 44230 | Y | N |  |  | 99010 | 99009
99009C | 138kV Flewellen to Fort Bend Ckt 09G-60E Upgrades | Upgrade Ckt.60E Flewellen to Fort Bend to increase thermal limits. Expect 2-959ACSS reconductor as first phase of Ckt.60E upgrade |  | Flewellen | Fort Bend | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 8.63 | 0 |  | Fort Bend | Fort Bend | Tier 4 | 25RPG010 | 2025-03-26 | 2025-04-18 | 2025-04-18 | 44230, 44280 | Y | N |  | Cost included in main entry | 99012 | 99009
102777 | Prairieland 138/35kV Distribution Substation | Install Prairieland (PRL) 138/35kV Distribution Substation. Loop on Ckt.66B Hockley to Stone Lake to create new Ckt.66B Hockley to Prairieland to Stone Lake. |  | Prairieland | Hockley/Stone Lake | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 102778 | 102777
99134 | Install generator lead at existing GBY Substation for new interconnection to NRG customer substation. Previously known as GBY-6 |  |  | Greens Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 99135 | 99134
99453U | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.98I Zenith to TH Wharton to increase thermal limits as part of FRM2 upgrades. |  | Zenith | TH Wharton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44900, 45500 | Y | N |  |  | 102613 | 99453
99453Z | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.99 Singleton to Gibbons Creek to increase thermal limits as part of FRM2 upgrades. |  | Singleton | Gibbons Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 967, 44645 | Y | N |  |  | 102620 | 99453
99453N | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.18D DOW to Jones Creek to increase thermal limits as part of FRM2 upgrades. |  | DOW | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 42530 | Y | N |  |  | 102626 | 99453
99453Y | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.75 Singleton to Gibbons Creek to increase thermal limits as part of FRM2 upgrades. |  | Singleton | Gibbons Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 967, 44645 | Y | N |  |  | 102627 | 99453
75810B | Install new 345kV Speedway substation for interconnection to Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. Install generator lead from Speedway to CRADLE solar | Install generator lead from Speedway (SPD) substation to CRADLE (CDL) customer substation (23INR0150). |  | Speedway | CRADLE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43060, 114633 | Y | N |  |  | 87164 | 75810
85987B | Upgrade Ckt.26 STRATT to SINTEK to increase thermal limits. Upgrade Ckt.26F Velasco to CAMDEN to increase thermal limits. | Upgrade Ckt.26F CAMDEN to Velasco to increase thermal limits. |  | CAMDEN | Velasco | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 00:01 |  | 138 | 0 | 0.28 | 0 |  | Brazoria | Brazoria | Tier 3 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 43360, 43365 | Y | N |  |  | 102653 | 85987
98994A | Replace Harrisburg with new Manchester Subsation | Remove Harrisburg from Ckts. 33B & 33C service to create new Ckt.33 TEXPET to Clinton. |  | Deepwater | TEXPET | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40352, 40800, 41560, 740800 | Y | N |  |  | 98995 | 98994
90255H | Jordan / Mont Belvieu Area Improvement Project | Install new CEHE-owned Sjolander substation. Reconfigure existing Ckt.86 CHEVRON to Kilgore to LANGSTON and loop into Sjolander substation to create new Ckt.86 Sjolander to Kilgore to LANGSTON. |  | Kilgore | Sjolander/ LANGSTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40050, 44830 | Y | N |  |  | 92986 | 90255
90255G | Jordan / Mont Belvieu Area Improvement Project | Install new CEHE-owned Sjolander substation. Reconfigure existing Ckt.86A Cedar Bayou to CHEVRON and loop into Sjolander substation to create new Ckt.86 Cedar Bayou to Sjolander to Kilgore to Langston. |  | Cedar Bayou | Sjolander | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40015, 40050, 40300 | Y | N |  |  | 92985 | 90255
90255I | Jordan / Mont Belvieu Area Improvement Project | Install new CEHE-owned Sjolander substation. Disconnect existing circuits 86A and 86B from CHEVRON customer substation. Reconnect CHEVRON substation to Sjolander substation as Ckt.13 Sjolander to CHEVRON and Ckt.23 Sjolander to CHEVRON. |  | Sjolander | CHEVRON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 00:02 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40050, 40300, 44830 | Y | N |  |  | 92987 | 90255
86321 | AEN_Lakeshore_Northland_Ckt_916_Reconductor |  |  | 9128 | 9228 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9228 | Y |  |  |  | 86322 | 86321
99100B | BRYN_99100_RELLIS_CAPS | Install second 54 MVAr (in three 18 MVAr stages) 138-kV capacitor bank at RELLIS |  | RELLIS |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 | 0,54 | Brazos |  | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32780 | Y |  |  |  | 99153 | 99100
86331 | AEN_Wheless_Mueller_Ckt_1016_Reconductor |  |  | 9291 | 9342 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9291, 9342 | Y |  |  |  | 86332 | 86331
86313 | AEN_345kV_CRASCO_SWYD_Addition | Crasco Switchyard will serve Bottom Grass BESS..The new the switchyard will be cut-in to345Kv CKT 3123 Holman - Hillje. |  |  |  | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 345 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 9067, 9073, 44200 | Y |  |  |  | 86314 | 86313
81299 | Ranger Camp – Prong Moss 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Ranger Camp | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2027-06-01 |  | 345 | 0 | 61.4 | 0 |  | Mitchell | Howard | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 10049, 10057 | Y |  |  |  | 81300 | 81299
67091 | Second 138 kV transmission Line from DL-DP CKT1034 | Second 138 kV transmission Line from Dunlap to Decker CKT1034 |  | 9045 | 9188 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 138 | 5.22 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9045, 9188 | Y |  |  |  | 67092 | 67091
93685 | New Transformer will be added at Titan Substation. |  |  | Titan | Titan | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5963 | Y |  |  |  | 93686 | 93685
70550 | Create_GP_Solar_POI_Bus | Created GP Solar POI bus. |  | Glen Pine | Explorer | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 6802, 6829, 6833 | Y |  |  |  | 72028 | 70550
99369 | Union (fka Sun) - Golden Switch - Dermott 138 kV line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22C. Upgrade the existing Union (fka Sun) - Golden Switch - Dermott 138-kV line |  | Union | Dermott | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_C | 2027-06-01 |  | 138 | 0 | 13.6 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  |  | 729, 1064, 1067, 1304, 1310, 1311, 1312, 1313, 1314, 10050, 18555, 180256 | Y |  |  |  | 99370 | 99369
70307 | BRYN_Standard_PMCR_Dansby_Rebuild_fix | Reference Project 4577 Dansby Rebuild. Project 4577 was added to convert Dansby 69kV bus to Breaker and a Half configuration. |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-06-01 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  |  | 32875, 32897 | Y |  |  |  | 75508 | 70307
80424 |  | Rebuild / Reconductor Dansby to Business Park 69kV for Rail Spur |  | Dansby | Bryn Business Park | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-06-01 |  | 69 | 0 | 3.3 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32871, 32875 | Y |  |  |  | 80425 | 80424
80420 |  | Rebuild / Reconductor Greens Prairie to South Switch 138kV Line |  | Bryn South Switch | Greens Pairie | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-06-01 |  | 138 | 0 | 4.5 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32007, 32878, 32880, 32893 | Y |  |  |  | 80421 | 80420
99100A | BRYN_99100_RELLIS_CAPS | Install first 54 MVAr (in three 18 MVAr stages) 138-kV capacitor bank at RELLIS |  | RELLIS |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 | 0,54 | Brazos |  | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32780 | Y |  |  |  | 99152 | 99100
102484 |  |  |  | Silver City | Branchville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-06-04 |  | 69 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 61, 63, 65 | Y |  |  |  | 102485 | 102484
91062 | Add Boles Station which taps the Quinlan North to Magness line | Adding Boles Bus and updating the line information |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-06-11 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6817, 6823, 6883 | Y |  |  |  | 91063 | 91062
75255B | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5230, 5231 | Y |  |  |  | 75848 | 75255
75255A | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5231, 5901 | Y |  |  |  | 75256 | 75255
75255C | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5230, 5260 | Y |  |  |  | 75849 | 75255
91596 | Addition of PEC CementPlant_Substation | Adding PEC CementPlant_Substation substation. Adding bus, branch, and load. | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-06-29 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70002, 70198, 70498 | Y |  |  |  | 91597 | 91596
72884 | Gonzales: Build 69 kV STATCOM | Build new 69 kV STATCOM at the Gonzales 69 kV station | Company Contact and In-Service Date Update | Gonzales |  | Planned |  | ETT | Bradley Case myturner@aep.com 918-599-2437 | TP2022130 | 2027-06-30 |  | 69 | 0 | 0 | 0 | -25,25 | Presidio |  | Tier 4 |  |  |  |  | 6675, 60203 | Y | N |  |  | 72885 | 72884
90173C | Cedar Bayou 5 Generator Interconnection (23INR0029) | Upgrade Ckt.84K HOPSON to WARVUE to increase thermal limits. |  | HOPSON | WARVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 41690, 41700 | Y | N |  |  | 90209 | 90173
49556 | Ozona: Rebuild 69 kV station | Replace existing Ozona 69 kV station with a new 69 kV ring bus |  | Ozona |  | Planned | 1018 - 1196 | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 | 2780 | 2027-06-30 |  | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6550, 6551, 6560, 60194 | Y | N |  |  | 65538 | 49556
90055 | Ursidae: Construct New 138 kV Station | Interconnect Northington Solar to the new Ursidae 138 kV station on the El Campo to Victoria 138 kV line between Corichi and El Campo |  | Ursidae |  | Planned |  | AEP TCC | Brooks Dow deevans@aep.com 918-599-2938 | TP2024151 | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 8099, 8102, 80101 | Y | N |  |  | 90056 | 90055
76576 | Asherton to Uvalde: Convert to 138 kV | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | In-Service Date Update | Asherton | Uvalde | Planned |  | AEP TCC | Chris Carroll jlsolis@aep.com 361-881-5574 |  | 2027-06-30 |  | 138 | 0 | 59.74 | 0 |  | Dimmit | Uvalde | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 7867, 8005, 8006, 8007, 8008, 8231, 8242, 8243, 8244, 8280, 8283, 8284, 8672 | Y | N |  |  | 78243 | 76576
93117 | Gibson: Construct New Distribution Station | Construct new distribution station on the Abilene South to Putnam 138 kV line between Abilene South and Vinson | In-Service Date Update | Gibson |  | Planned |  | AEP TNC | Nelson Carroll myturner@aep.com 918-599-2437 | DR24N0009 | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6260, 60080, 60355 | Y | N |  |  | 93118 | 93117
90173B | Cedar Bayou 5 Generator Interconnection (23INR0029) | Upgrade Ckt.97E Cedar Bayou to Chambers to increase thermal limits. |  | Cedar Bayou | Chambers | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-06-30 |  | 345 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40000, 40255 | Y | N |  |  | 90208 | 90173
81227 | Cattleman – Gascondades 345 kV Reroute | Terminate Morgan Creek – Gascondades 345 kV Line into Cattleman 345 kV Switch |  | Cattleman | Gascondades | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8647 | 2027-06-30 |  | 345 | 0 | 2.5 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 10053, 11032, 11033, 11034, 76030 | Y |  |  |  | 81664 | 81227
87328 | Sunstone: Construct New 138 kV Station | Interconnect the Inner Harbor Desalination Plant load to the new Sunstone 138 kV station on the Morris Street to Nueces Bay 138 kV line |  | Sunstone |  | Planned |  | AEP TCC/ETT | LaRissa Lundry deevans@aep.com 918-599-2938 | TP2022754 | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8022, 8441, 8733 | Y | Y |  |  | 87329 | 87328
90173A | Cedar Bayou 5 Generator Interconnection (23INR0029) | Connect new generation facility to Cedar Bayou 345kV substation with 721 MW combined cycle natural gas-fired units. |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-06-30 |  | 345 | 0 | 0 | 0 |  | Chambers |  | Tier 4 | [5 empty] | Y | N |  |  | 90207 | 90173
99924 | Pine Path Substation Addition | Construct a new 138-kV substation to cut-in on T670 to serve new customer load in the BBEC service territory. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  |  | 7310, 7311, 7324 | Y |  |  |  | 99937 | 99924
80970 | Joule: Construct New 345 kV Station | Interconnect Zeissel Solar and Storage to the new Joule 345 kV station on the Clear Crossing to Coulomb 345 kV line |  | Joule |  | Planned | TP2024020 | ETT | Brandon Clarke twang1@aep.com 918-599-2635 |  | 2027-06-30 |  | 345 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 60094, 60702, 60722 | Y | Y |  |  | 80971 | 80970
91382 | Henne_Kohlenberg_Transmission_Line_Addition | New Braunfels Utilities will be building a new substation to serve new customer load near Kohlenberg Rd. LCRA TSC will build a new transmission line from Henne Substation to the new Kohlenberg substation and provide transmission service via a new transmission level bus. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.prease@lcra.org 512-578-4514 | PLC-6682 | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7174, 7464 | Y |  |  |  | 91383 | 91382
90033 | Reveille to Navitas: Construct New 138 kV Line | Interconnect the new Navitas load station to the existing Reveille 138 kV station |  | Reveille | Navitas | Planned |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 | TP2024157 | 2027-06-30 |  | 138 | 0.15 | 0 | 0 | 0,37.4 | La Salle | La Salle | Tier 4 |  |  |  |  | 8612, 80095 | Y | N |  |  | 90034 | 90033
71881 | Install 31.3 Mvar capacitor bank at Andice. | Install 31.3 Mvar capacitor bank at Andice. Formerly TPIT project number 70365. |  | Andice |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-07-01 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson |  | Tier 4 |  |  |  |  | 70522 | Y | Y |  |  | 71882 | 71881
84896 | New Legend Falls Substation looped into the existing Tally to Texas Research transmission line. This station supports the RPG approved Rio Medina project |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-07-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5259, 5422, 5430 | Y |  |  |  | 84897 | 84896
91708 | New San Geronimo Substation | adds new San Geronimo station on STEC Rio Medina - CPS Legend Falls line |  | Rio Medina | Legend Falls | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-07-01 00:20 |  | 138 | 0 | 0 | 0 |  | Medina | Medina | Tier 4 |  |  |  |  | 5259, 5805, 5808 | Y | N |  |  | 91709 | 91708
85008 | Add Rio Medina - Legend Falls Tline | Add Rio Medina - Legend Falls Tline as part of the Rio Medina RPG Project |  | Rio Medina |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-07-01 12:01 |  | 138 | 5.6 | 0 | 0 |  | Medina | Medina | Tier 2 |  |  | 2024-02-01 |  | 5259, 5805 | Y | N |  |  | 85009 | 85008
70012 | West Weatherford to Oran Voltage Conversion | West Weatherford to Oran Voltage Conversion |  | West Weatherford | Oran | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-07-03 |  | 138 | 0 | 0.1 | 0 |  | Palo Pinto | Parker | Tier 4 |  |  |  |  | 515, 518, 519, 785, 1569, 1585, 1589 | Y |  |  |  | 70013 | 70012
98601 | Riley: Expand 345 kV Station | Interconnect Dundee Wind and Felix Solar to the existing Riley 345 kV station |  | Riley |  | Planned | TP2025169 | ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-07-11 |  | 345 | 0.25 | 0 | 0 |  | Wilbarger |  | Tier 4 | [5 empty] | Y | N |  |  | 98602 | 98601
73436 | Rockhound - Connell 345 kV Double-Circuit Line | Construct a new 345 kV Double-Circuit Line and establish a 345/138 kV Switch |  | Rockhound | Connell | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8718, R8807 | 2027-07-24 |  | 345 | 10 | 0 | 1200 |  | Martin | Midland | Tier 1 |  |  |  |  | 10036, 10062, 10085, 10086, 10087, 10088, 10089, 10175, 10176, 11371, 23840, 23841, 23855 | Y |  |  |  | 93058 | 73436
61449 | Clark Church/Birdhouse (Ottine New) Substation | Build New 138 Substation adjacent to LCRA Birdhouse station; replaces existing Ottine station, add 20MVA |  | Ottine | Ottine | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2027-07-30 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7594 | Y | N |  |  | 61450 | 61449
87633 | WETT Buck Canyon Synchronous Condenser |  |  | Long Draw | Buck Canyon | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2027-07-30 |  | 345 | 0.25 | 0 | 0 |  | Borden | Borden | Tier 1 | 23RPG026 | 2023-09-01 | 2023-09-28 |  | 59900, 59916, 59917, 59918 | Y |  |  |  | 87634 | 87633
6572 | Ballinger to Eden 69 kV line: Rebuild taps | Rebuild Taps on the Ballinger to Eden 69 kV line | Company Contact and In-Service Date Update | Ballinger | Eden | Planned | 890 - 1068 | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 | 2814 | 2027-07-31 |  | 69 | 0 | 2.8 | 0 |  | Runnels | Concho | Tier 4 |  |  |  |  | 6338, 6369, 6370, 6372, 6376 | Y | N |  |  | 65513 | 6572
90057 | Volar: Construct New 138 kV Station | Interconnect XE Flying Kite Solar to the new Volar 138 kV station on the Crystal City to Poblano 138 kV line between La Pryor and Poblano |  | Volar | XE Flying Kite Solar | Planned |  | AEP TCC | Nathan Cowan jlsolis@aep.com 361-881-5574 | TP2024145 | 2027-07-31 |  | 138 | 2 | 0 | 0 |  | Zavala | Zavala | Tier 4 | [5 empty] | Y |  |  |  | 90058 | 90057
90035 | Edith Clarke to Seine BESS: Construct New 345 kV Line | Interconnect Seine BESS to the existing Edith Clarke 345 kV station |  | Edith Clarke | Seine BESS | Planned |  | AEP TNC | Lance Price myturner@aep.com 918-599-2437 | TP2024193 | 2027-07-31 |  | 345 | 0.3 | 0 | 0 |  | Foard | Foard | Tier 4 | [5 empty] | Y | N |  |  | 91677 | 90035
48818 | Ballinger: Rebuild 138 kV Station | Rehab the 138/69 kV autotransformer at Ballinger | Company Contact and In-Service Date Update | Ballinger |  | Planned | 1016 - 1194 | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 | 2777 | 2027-07-31 01:00 |  | 138 | 0 | 0 | 130 |  | Runnels |  | Tier 4 |  |  |  |  | 6338, 6340 | Y | N |  |  | 65537 | 48818
102879 | Add Zella Station for GINR on San Miguel to Fowlerton |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-08-01 |  | 345 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 | [5 empty] | Y | N |  |  | 102880 | 102879
81373 |  |  |  | Longstreet | Buckholts | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-08-13 |  | 138 | 0 | 1.5 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 65, 108, 110, 3749 | Y |  |  |  | 81374 | 81373
69471 | Villa Cavazos: Construct New 138 kV Terminal | Interconnect Eval BESS to the Villa Cavazos 138 kV station |  | Villa Cavazos |  | Planned |  | AEP TCC | Robert Dougherty jlsolis@aep.com 361-881-5574 |  | 2027-08-31 |  | 138 | 0.35 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 80229 | Y |  |  |  | 69472 | 69471
91611 |  |  |  | Spring | Rector | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-01 |  | 138 | 0 | 11.4 | 0 |  | Cooke | Denton | Tier 4 |  |  |  |  | 672, 680, 684 | Y |  |  |  | 91612 | 91611
86327 | AEN_New_138kV_Southshore_Substation_Addition |  |  | 9179 | 9132 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-09-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9132, 9134, 9179 | Y |  |  |  | 86328 | 86327
90111 |  |  |  | Gainesville | Red River | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-01 |  | 69 | 1.2 | 0 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 719, 726, 735 | Y |  |  |  | 90112 | 90111
86317 | AEN_DP_OnionCreek_Ckt_924_Reconductor |  |  | 9187 | 9251 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-09-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9187, 9251 | Y |  |  |  | 86318 | 86317
86333 | AEN_OnionCreek_StoneyRidge_Ckt_1026_Reconductor |  |  | 9237 | 9251 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-09-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9237, 9251 | Y |  |  |  | 86334 | 86333
102665 | BEPC_TPIT102665_Greyfox |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-03 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 468, 469, 477, 478, 479, 482, 484, 33478 | Y |  |  |  | 102666 | 102665
102757 | BEPC_TPIT102757_Paluxy |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-06 |  | 69 | 0 | 0 | 0 |  | Somervell |  | Tier 4 |  |  |  |  | 311, 315, 317 | Y |  |  |  | 102758 | 102757
102765 | BEPC_TPIT102765_Mahogany |  |  | Nolan | Tenaska | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-06 |  | 138 | 0 | 0 | 0 |  | Johnson |  | Tier 4 |  |  |  |  | 370, 401, 410 | Y |  |  |  | 102766 | 102765
66202C | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Grapeland - Crockett 69 kV Line |  | Grapeland | Crockett | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6182 | 2027-09-15 |  | 69 | 0 | 8.5 | 0 |  | Houston | Houston | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3286, 3289 | Y |  |  |  | 99515 | 66202
66492C | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Jacksboro Amoco - Chico City Services 69 kV Line |  | Jacksboro Amoco | Chico City Services | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3006 | 2027-09-15 |  | 69 | 0 | 7.3 | 0 |  | Jack | Wise | Tier 4 |  |  |  |  | 1554, 1555, 11557 | Y |  |  |  | 72963 | 66492
66206B | Upgrade Temple - Minerva 69 kV Line | Upgrade Marak - Minerva 69 kV Line |  | Marak | Minerva | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6186 | 2027-09-15 |  | 69 | 13.1 | 0 | 0 |  | Milam | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3682, 3684, 3685, 3689 | Y |  |  |  | 68924 | 66206
91496 |  |  |  | Perry | Ben Hur | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-16 |  | 138 | 0 | 0 | 100 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 85, 91, 92, 97, 98, 99, 103, 154691 | Y |  |  |  | 102790 | 91496
99950 | Expansion of Stillman to accomodate interconnection of Resaca Oasis Storage BESS | Interconnection of GINR #27INR0399 Resaca Oasis Storage to Sharyland's Stillman Station. Planned COD is 09/20/2027 | NEW - IA Signed |  |  | Planned |  | SLU | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2027-09-20 |  | 138 | 0.02 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 1571, 1572, 11571 | Y | Y |  |  | 99951 | 99950
70891 | Eola Tap: Rebuild 69 kV Line | Rehab Eola Tap 69 kV Line | Company Contact and In-Service Date Update | Eola Tap | Eola | Planned |  | AEP TNC | Sally Matthews myturner@aep.com 918-599-2437 |  | 2027-09-30 |  | 69 | 0 | 11.69 | 0 |  | Concho | Concho | Tier 4 |  |  |  |  | 6370, 6371 | Y | N |  |  | 70892 | 70891
87635 | WETT Pitchfork Synchronous Condenser |  |  | Cottonwood | Pitchfork | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2027-09-30 |  | 345 | 0 | 0 | 0 |  | Dickens | Dickens | Tier 1 | 23RPG026 | 2023-09-01 | 2023-09-28 |  | 59904, 59908, 59913, 59914, 59915 | Y |  |  |  | 87636 | 87635
90040 | Del Sol: Construct New 345 kV Terminal | Interconnect Diamondback Solar to the Del Sol 345 kV station | In-Service Date Update | Del Sol |  | Planned |  | ETT | Jarrod Evans 361-881-5574 | TP2024116 | 2027-09-30 |  | 345 | 0 | 0 | 0 |  | Starr |  | Tier 4 | [5 empty] | Y |  |  |  | 90041 | 90040
52464 | Alamito Creek to Ft. Davis: Rebuild 69 kV Line | Alamito Creek to Ft. Davis: Rebuild 69 kV line |  | Alamito Creek | Ft Davis | Planned | 1070 - 1243 | AEP TNC | William Lovelace myturner@aep.com 918-599-2437 | 2831 | 2027-09-30 |  | 69 | 0 | 20.5 | 0 |  | Presidio |  | Tier 4 |  |  |  |  | 6676, 6677, 6678, 6691, 6692 | Y | N |  |  | 65564 | 52464
80327 | RTP projects included the addition of 18.4 MVAR capacitor at Whitesboro SW | RTP projects included the addition of 18.4 MVAR capacitor at Whitesboro SW |  | Whitesboro SW | Whitesboro SW | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-30 |  | 138 | 0 | 0 | 0 | 0,18.4 | Grayson | Grayson | Tier 4 |  |  |  |  | 718 | Y |  |  |  | 80328 | 80327 | 2023-N14
91481 | RCEC_Kemp_RC_station | New TVEC substation by tapping Oncor's line Kemp to Seven Points 138kV. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2726, 3264, 6901 | Y |  |  |  | 91482 | 91481
98610 | Riley: Expand 345 kV Station | Interconnect the OPS load to the existing Riley 345 kV station |  | Riley |  | Planned | TP2025219 | ETT | Mina Turner myturner@aep.com 918-599-2437 |  | 2027-10-15 |  | 345 | 6 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6111, 60188, 60189 | Y |  |  |  | 98611 | 98610
73366 | CPSE_New_Wiseman_Substation | Loop new 138 kV substation into existing 138kV Cagnon to Helotes Transmission Line. | [5 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-10-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5055, 5200, 5487 | Y |  |  |  | 73367 | 73366
87677 | Rebuild the Fryers Creek - Temple 138 kV Line | Rebuild the Fryers Creek - Temple 138 kV Line on new structures |  | Fryers Creek | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6335 | 2027-10-15 |  | 138 | 4.5 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3415, 3493 | Y |  |  |  | 87678 | 87677
43434 | This is the POI for High Noon Solar and Storage |  |  | Boot Hill | Boot Hill | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-10-21 |  | 138 | 0 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 444, 445, 446 | Y |  |  |  | 43435 | 43434
102632 | BEPC_TPIT102632_BLACKTHORN |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-10-22 |  | 69 | 0 | 0 | 0 |  | Ellis |  | Tier 4 |  |  |  |  | 193, 202, 204, 210, 214, 215, 1571, 1572, 11571 | Y |  |  |  | 102656 | 102632
100537 | Add new Iron Horse station for 25INR0230 |  |  | Limestone | Gibbons Creek | Planned |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2027-10-23 |  | 345 | 0 | 0 | 0 |  | Leon |  | Tier 4 |  |  |  |  | 967, 46020, 79011 | Y | N |  |  | 100538 | 100537
99910 | County Line Substation Addition | Provide transformation service to a BBEC-member load in close proximity of existing Wolf Lane Substation. The 138-kV County Line Substation will be cut-in on T582 Elroy-Wolf Lane transmission line. |  | Elroy | Wolf Lane | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2027-10-24 |  | 138 | 0 | 0 | 0 | 0,62.4 | Bastrop | Bastrop | Tier 3 |  |  |  |  | 7209, 7211, 7212 | Y |  |  |  | 99911 | 99910
80850 | Lon Hill to Sinton: Bypass Waterworks 69 kV station | Relocate portion of 69 kV line between Odem and Stevens Tap to bypass Waterworks 69 kV station | In-Service Date Update | Odem | Stevens Tap | Planned | TA2022133 | AEP TCC | Travis Coody deevans@aep.com 918-599-2938 |  | 2027-10-30 |  | 69 | 0 | 0.45 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8810, 8865, 8867 | Y | N |  |  | 80851 | 80850
70675 | Aransas Pass to Rincon: Rebuild 69 kV Line | Rebuild the Aransas Pass to Gregory to Rincon 69 kV line | In-Service Date Update | Aransas Pass | Rincon | Planned |  | AEP TCC | LaRissa Lundry deevans@aep.com 918-599-2938 | TP2022132 | 2027-10-31 |  | 69 | 0 | 8.5 | 0 |  | San Patricio | San Patricio | Tier 2 | 24RPG035 | 2024-11-11 |  |  | 8416, 8421, 8427 | Y |  |  |  | 70676 | 70675
90014 | Palafox: Construct New 138 kV Station | Construct new STEC distribution station on the North Laredo Switch to Reveille 138 kV line between Barrera and North Laredo Switch |  | Palafox |  | Planned |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 | TP2024132 | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8053, 8717, 8909, 88000 | Y |  |  |  | 90037 | 90014
98802 | Claror: Construct New 345 kV Station | Interconnect Bigway Solar I and II to the new Claror 345 kV station on the Edith Clarke to Cottonwood 345 kV line | Company Contact and In-Service Date Update | Claror |  | Planned |  | ETT | Ali Barkat 918-599-2437 | TP2025175 | 2027-10-31 |  | 345 | 0 | 0 | 0 |  | King |  | Tier 4 |  |  |  |  | 59904, 60154, 60500 | Y |  |  |  | 98803 | 98802
73332 | Install Hermann (HER) Distribution Substation | Install Hermann (HER) Distribution Substation. Loop on Ckt.08I to create new Ckt.08 Plaza to Hermann to Grant. |  | Hermann | Plaza/Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45120, 47110, 47350 | Y | N |  |  | 87181 | 73332
89939A | Install new Skains (SKA) 345kV Substation for generator interconnection to Hollow Branch Creek Solar (24INR0422) | Install new Skains (SKA) 345kV Substation for generator interconnection to Hollow Branch Creek Solar (24INR0422). Loop into existing Ckt.74 Singleton to Jewett (ONCOR) to create new Ckt.74 Singleton to Skains to Jewett. |  | Skains | Singleton/Jewett | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Leon | Tier 4 |  |  |  |  | 3391, 44645, 44660 | Y | N |  |  | 90853 | 89939
102544 | Expand Sjolander 9-breaker BAAH substation to 12-breaker BAAH for a total of four line positions to Chevron. Relocate existing Sjolander Ckt.84 to Cedar Bayou to new line position. |  |  | Sjolander | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 102545 | 102544
89922 | Whaley 345kV Substation Expansion for ROSE/Rock Rose Energy BESS (26INR0201) | Expand Whaley 345kV Substation for ROSE / Rock Rose Energy BESS (26INR0201). Connect generator through one new generator lead. |  | Waterhole |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 345 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y | N |  |  | 89923 | 89922
91259A | Phelps (PHE) CEHE Station for SKIPJA (SKP) / Skipjack Energy Storage (26INR0189) | Install new Phelps (PHE) 138kV Substation for generator interconnection to SKIPJA (SKP) - Skipjack Energy Storage (26INR0189). Loop into existing Ckt.02B WA Parish to Nash to create new Ckt.02 WA Parish to Phelps to Nash. |  | Phelps | WA Parish / Nash | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42460, 42980, 44010 | Y |  |  |  | 100299 | 91259
90031 | LLaves: Construct New 345 kV Station | Interconnect Keys Hollow Solar & Storage to the new Llaves 345 kV station on the Coleto Creek to Raptor 345 kV line |  | Llaves |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2024167 | 2027-10-31 |  | 345 | 0 | 0 | 0 |  | Goliad |  | Tier 4 | [5 empty] | Y | N |  |  | 90032 | 90031
100333 | Ghost Town: Add new 345 kV Station | Add new substation to serve 25INR0080 & 26INR0113 |  | Gray | Ghost Town | Planned |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2027-10-31 |  | 345 | 14.3 | 0 | 0 |  | Gray |  | Tier 4 |  |  |  |  | 79000, 79008 | Y |  |  |  | 100334 | 100333
49550 | Port Isabel: Rebuild As GIS Station | Rebuild Port Isabel as a GIS |  | Port Isabel |  | Planned | 958 - 1136 | AEP TCC | Ali Abukar deevans@aep.com 918-599-2938 | 3716 | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  |  | 49551 | 49550
91259B | Phelps (PHE) CEHE Station for SKIPJA (SKP) / Skipjack Energy Storage (26INR0189) | Install one generator lead from Phelps (PHE) 138kV Substation to SKIPJA (SKP) / Skipjack Energy Storage (26INR0189) |  | Phelps | SJIPJA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y |  |  | Costs included in main entry. | 100300 | 91259
89939B | Install new Skains (SKA) 345kV Substation for generator interconnection to Hollow Branch Creek Solar (24INR0422) | Install one generator lead from Skains (SKA) 345kV CEHE Substation to HOLLOW (HLW) / Hollow Branch Solar (24INR0422) |  | Skains | HOLLOW | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 00:01 |  | 345 | 0 | 0 | 0 |  | Grimes |  | Tier 4 | [5 empty] | Y | N |  | Costs included in main entry | 90854 | 89939
91135 | Add the Frankston station which taps the Coffee to Blackburn line | Adding the Frankston station, tapping Rayburn's Coffee and Oncor's Blackburn stations. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-11-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 3325, 6855, 6871 | Y |  |  |  | 91136 | 91135
102559 | BEPC_TPIT_KosseSW_Kosse |  |  | 85 | 89 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-11-05 |  | 69 | 0 | 5.5 | 0 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 85, 89 | Y |  |  |  | 102560 | 102559
91986 | Establish the Wofford/Berryville POI | Establish the Wofford/Berryville POI |  | Frankston | Berryville | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6332 | 2027-11-06 |  | 138 | 2 | 0 | 0 |  | Anderson | Anderson | Tier 4 |  |  |  |  | 3782, 3783, 6871 | Y |  |  |  | 91987 | 91986
80340 |  |  |  | Keith Switch | Iola | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-11-26 |  | 138 | 0 | 6.1 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 2, 4 | Y |  |  |  | 80341 | 80340
92354 | Wren: Construct New 345 kV Station | Interconnect the Eolic load to the new Wren 345 kV station on the Gulch to Kelvin 345 kV line |  | Wren |  | Planned |  | AEP TCC | Robert Younger jlsolis@aep.com 361-881-5574 | TP2025127 | 2027-11-30 |  | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8013, 8704, 8759 | Y | N |  |  | 92355 | 92354
73423 | Buddy Owens: Build new 138 kV Substation | Build new 138 kV substation on Key Switch to North McAllen 138 kV line | Company Contact and In-Service Date Update | Buddy Owens |  | Conceptual |  | AEP TCC | Victoria Diaz jlsolis@aep.com 361-881-5574 |  | 2027-11-30 |  | 138 | 0 | 0 | 80 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8632, 8773, 8973 | Y |  |  |  | 73424 | 73423
77031 | Las Lomas: Construct New Distribution Station | Construct new distribution station on the La Grulla to Rio Grande City 138 kV line | Company Contact and In-Service Date Update | Las Lomas |  | Planned |  | AEP TCC | Morris Everroad jlsolis@aep.com 361-881-5574 | DP24X0003 | 2027-11-30 |  | 138 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 8793, 8798, 8806 | Y |  |  |  | 77032 | 77031
90043 | Kelvin to Eneus: Construct New 345 kV Line | Interconnect the new Eneus load station to the expanded Kelvin 345 kV station on the Gulch to La Palma 345 kV line | Company Contact and In-Service Date Update | Kelvin | Eneus | Planned |  | AEP TCC | Forrest Farson jlsolis@aep.com 361-881-5574 | TP2024073 | 2027-11-30 |  | 345 | 1 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 8013, 8317, 8704, 80113 | Y |  |  |  | 90044 | 90043
87629 | WETT Binturong Synchronous Condenser |  |  | Bearkat | Binturong | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2027-11-30 | 2958101 | 345 | 0.25 | 0 | 0 |  | Glasscock | Glasscock | Tier 1 | 23RPG026 | 2023-09-01 | 2023-09-28 |  | 59903, 59919, 59920, 59921 | Y |  |  |  | 87630 | 87629
45397 | Lion: 138 kV Station & Transmission Line | Lion: 138 kV Station with new line to Stewart Road | In-Service Date Update | Lion | Stewart Road | Planned | 885 - 1063 | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 | 3672 TP2018218 | 2027-11-30 |  | 138 | 2.71 | 0 | 40 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8758, 8951, 8969 | Y | N |  |  | 65528 | 45397
80907 | Fort Stockton Plant: Rebuild 138/69 kV Station | Rebuild the Fort Stockton Plant 138/69 kV station | Company Contact and In-Service Date Update | Fort Stockton Plant |  | Planned | TP2023319 | AEP TNC | Damian P Raab myturner@aep.com 918-599-2437 |  | 2027-11-30 |  | 138 | 0 | 0 | 90 |  | Pecos |  | Tier 4 |  |  |  |  | 6630, 38355 | Y | N |  |  | 80908 | 80907
70710 | Eden to Yellowjacket: Rebuild 69 kV Line | Rehab the Eden to Yellowjacket 69 kV line |  | Eden | Yellowjacket | Planned |  | AEP TNC | Damian Raab twang1@aep.com 918-599-2635 | TA2021119 | 2027-11-30 |  | 69 | 0 | 0 | 0 |  | Concho | Menard | Tier 3 |  |  |  |  | 6363, 6372 | Y |  |  |  | 70711 | 70710
72999 | Haskell to Munday: Rebuild 69 kV Line | Rehab Haskell to Munday 69 kV Line |  | Haskell | Munday | Planned |  | AEP TNC | Bill Edwards twang1@aep.com 918-599-2635 |  | 2027-11-30 |  | 69 | 0 | 21.71 | 0 |  | Haskell | Knox | Tier 4 | 22RPG043 | 2022-12-15 | 2023-01-11 |  | 6107, 6122, 6123, 6124, 6125, 6126, 60021 | Y | N |  |  | 73000 | 72999
99808 | Cesium: Construct New 345 kV Station | Interconnect the Castle load to the new Cesium 345 kV station on the Clear Crossing to Figaro 345 kV line between Figaro and Kirchoff |  | Cesium |  | Planned | TP2025188 | ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-11-30 |  | 345 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 60198, 60704, 60715 | Y |  |  |  | 99809 | 99808
99728 | Kilby: Expand 345 kV Station | Interconnect Briggs Solar to the existing Kilby 345 kV station |  | Kilby |  | Planned | TP2025196 | ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-11-30 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 | [5 empty] | Y |  |  |  | 99729 | 99728
90340B | South Lane City substation expansion for BRP Diran BESS (23INR0137) | Relocate existing Ckt.60D South Lane City to Dyann with expansion of South Lane City to BAAH configuration. |  | South Lane City | Dyann | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-11-30 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 | [5 empty] | Y | N |  | Costs included in main entry | 90342 | 90340
90340A | South Lane City substation expansion for BRP Diran BESS (23INR0137) | Expand South Lane City substation for generator interconnection to BRP Diran BESS. Convert South Lane City to BAAH configuration. |  | South Lane City | BRP Diran BESS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-11-30 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 90341 | 90340
54892 | Eden to North Brady: Rebuild 69 kV line | Rehab Eden to North Brady 69 kV line | Company Contact and In-Service Date Update | Eden | North Brady | Planned | 1039 - 1266 | AEP TNC | Bradley Case myturner@aep.com 918-599-2437 | 1856 | 2027-11-30 |  | 69 | 0 | 32.7 | 0 |  | Concho | McCulloch | Tier 3 | 22RPG009 | 2022-03-23 | 2022-04-14 |  | 6006, 6372, 6380, 6384, 6385, 60005, 60797 | Y | N |  |  | 65568 | 54892
99280 | Natural Dam - Beals Creek 138 kV Line | Add Permian Basin Reliability Plan Upgrade ID L21A. Upgrade the existing Natural Dam - Beals Creek 138-kV line |  | Natural Dam | Bealscreek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L21_A | 2027-12-01 |  | 138 | 0 | 7.4 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 11325, 11331, 23836 | Y |  |  |  | 99281 | 99280
99479B | Snyder - China Grove 69 kV Loop Converstion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L23. Convert the existing Snyder - Scurry - China Grove and Snyder - Amoco Tap - China Grove 69-kV lines to 138-kV. This converts the Snyder - Ira - China Grove 69 kV Line into 138 kV and reterminates into the new Bluff Creek 138 kV Switch. |  | China Grove | Bluff Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L23 | 2027-12-01 |  | 138 | 0 | 12.8 | 0 |  | Scurry | Scurry | Tier 1 |  |  |  |  | 1318, 1319, 1367, 10191, 10201 | Y |  |  |  | 99481 | 99479
89991 | Upgrade Sargent - Bay City | Upgrade Sargent - Bay City line to 795ACSR. 2024 RTP; 2025 RTP |  | Sargent | Bay City | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 69 | 0 | 18.5 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5560, 5564 | Y |  |  |  | 89992 | 89991
99391C | Stanton East - Midland Basin - Spraberry 69 kV Line Conversion to 138 kV | Add part of Permian Basin Reliability Plan Upgrade ID L18. Convert the existing Stanton East - Midland Basin - Spraberry 69-kV line to 138-kV and cut into Rockhound and Stanton East 138 kV Switches to establish the Consavvy - Rockhound - Stanton East 138 kV Line. |  | Consavvy | Stanton East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L18_A | 2027-12-01 |  | 138 | 0 | 26.8 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 1326, 10063, 11134, 11388 | Y |  |  |  | 99394 | 99391
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  |  | 5705 | Y | N |  |  | 9835 | 2554
102865 | Add Moursund load serving station |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 138 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 | [5 empty] | Y | N |  |  | 102866 | 102865
91553 | RCEC_Union_Valley | 180MW load connecting to a new load serving station from RCEC's Union Valley Station to Blackland RC |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 6860, 6886, 6981 | Y |  |  |  | 91554 | 91553
93048 | Add Liendo load serving substation |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 138 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  | 2024-02-01 |  | 7272, 57668, 57674 | Y | N |  |  | 93049 | 93048
102867 | Upgrade Sargent to Franklins Camp |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y | N |  |  | 102868 | 102867
99016 | Drill Hole - El Capitan (fka Culberson) 345 kV double-circuit line | Add Permian Basin Reliability Plan Upgrade ID L5D Add a new Drill Hole - El Capitan (fka Culberson) 345-kV double-circuit line |  | Drill Hole | El Capitan | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L5_D | 2027-12-01 |  | 345 | 36.2 | 0 | 0 |  | Culberson | Culberson | Tier 2 |  |  |  |  | 10073, 10180 | Y |  |  |  | 99017 | 99016
99006 | Establish El Capitan 345/138 kV Switch | Add Permian Basin Reliability Plan Upgrade ID L5A Establish a new Culberson 345/138-kV substation at the existing Culberson Switch and install two new 345/138-kV transformers |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L5_A | 2027-12-01 |  | 345 | 0 | 0 | 1200 | 75,0 | Culberson | Culberson | Tier 3 |  |  |  |  | 1096, 1097, 10179, 10180, 10181, 10182, 11082, 11191, 18726 | Y |  |  |  | 99007 | 99006
6777 | Establish Division Sub Cedar Hill - Liggett 138 kV Line | Establish Division Sub and Loop Cedar Hill - Liggett 138 kV line in to Great Southwest / General Motors | Project Deferral | Grand Prairie West | Mayfield Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5280 | 2027-12-14 02:01 |  | 138 | 6 | 0 | 0 |  | Dallas | Tarrant | Tier 2 |  |  |  |  | 1919, 2137, 2138, 2140, 2143, 2265, 2274, 12265 | Y | N |  |  | 72912 | 6777
81067 | Balch Springs Tap – Balch Springs 138 kV Line Section | Rebuild Balch Springs Tap – Balch Springs 138 kV Line Section |  | Balch Springs Tap | Balch Springs | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4194 | 2027-12-15 |  | 138 | 0 | 3.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2775, 2776, 2777, 2778 | Y |  |  |  | 81068 | 81067
68706 | Edgewood Switch – Royse Switch 138 kV Line | Rebuild and convert the Edgewood-Iron Bridge 69 kV to 138 kV operation |  | Edgewood | Able Springs | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3227 | 2027-12-15 |  | 69 | 0 | 0 | 0 |  | Van Zandt | Kaufman | Tier 4 |  |  |  |  | 2471, 2721, 3163, 3165, 3167, 3168, 3169, 3181, 3182, 3185, 3188, 3189, 3191, 3192, 3193, 6920, 6922, 12467, 12469, 12470, 12472, 13188, 13191 | Y |  |  |  | 68707 | 68706
87010 | Establish Drill Hole 345/138 kV Switch | Establish Drill Hole 345/138 kV Switch |  | Drill Hole Switch | Drill Hole Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8725 | 2027-12-15 |  | 345 | 0 | 0 | 1200 |  | Culberson | Culberson | Tier 1 | 24RPG010 | 2024-03-18 |  |  | 10073, 10074, 10075, 10076, 11090, 11271, 11272, 18709 | Y |  |  |  | 87735 | 87010
91459 | Establish Mosher 345 kV Switch | Establish Mosher 345 kV Switch for Glasgow Solar |  | Mosher 345 kV Switch | Mosher 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6321 | 2027-12-15 |  | 345 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 2466, 3763, 68091 | Y |  |  |  | 91460 | 91459
71910B | Rebuild the Hillsboro - Elm Mott 69 kV Line | Rebuild the West - Abbott 69 kV Line Section |  | West 69 kV Substation | Abbott 69 kV Substation | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6221 | 2027-12-15 |  | 69 | 0 | 6.3 | 0 |  | McLennan | Hill | Tier 3 |  |  |  |  | 3524, 3525 | Y |  |  |  | 91606 | 71910
99066 | ONCOR_MNE_99066_Royse Switch – Farmersville Switch 345 kV Double-Circuit Line | Upgrade Royse Switch – Farmersville Switch 345 kV Double-Circuit Line |  | Farmersville Switch | Royse Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4255 | 2027-12-15 |  | 345 | 0 | 0 | 0 |  | Collin | Rockwall | Tier 3 |  |  |  |  | 1685, 2461, 2478 | Y |  |  |  | 99067 | 99066
91945 | Establish Alder 138 kV Switch | Establish Alder 138 kV Switch |  | Alder | Alder | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6329 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Van Zandt | Van Zandt | Tier 2 | 24RPG007 |  |  |  | 3173, 3175, 3184 | Y |  |  |  | 91946 | 91945
92852A | Oncor_92852_MNE_Monticello_Paris_Line_Upgrade | Upgrade Monticello - Woodard 345 kV Line |  | Monticello | Woodard | Planned | R986 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R986 | 2027-12-15 |  | 345 | 0 | 33.3 | 0 |  | Titus | Lamar | Tier 1 | 25RPG026 |  |  |  | 1695, 11699 | Y |  |  |  | 93063 | 92852
87705 | Pepper Creek - Temple Elm Creek 138 kV Double-Circuit Line | Reconductor the Pepper Creek - Temple Elm Creek 138 kV Double-Circuit Line |  | Pepper Creek | Temple Elm Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6198 | 2027-12-15 |  | 138 | 0 | 6.2 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3484, 3608, 13608, 13662 | Y |  |  |  | 87706 | 87705 | 2023-NC51
76654 | Establish Voss Lake 345/138 kV Switch | Establish Voss Lake 345/138 kV Switch |  | Voss Lake | Voss Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6278 | 2027-12-15 |  | 345 | 0 | 5.6 | 600 | 0,110.4 | Milam | Milam | Tier 1 | 25RPG009 |  |  |  | 3687, 3717, 3740, 3749, 3750, 3751, 3752, 3761, 13429, 13430 | Y |  |  |  | 76655 | 76654 | 2023-SC9
87709 | Belton - Temple 138 kV Line | Rebuild the Belton - Temple 138 kV Line |  | Belton | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6199 | 2027-12-15 |  | 138 | 0 | 9.6 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3415, 3602, 3610, 3611, 3612, 3759 | Y |  |  |  | 87710 | 87709 | 2023-NC5, 2023-NC17
99407 | Sun - Sacroc - Union 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22D. Upgrade the existing Sun - Sacroc - Union 138 kV Line Rebuild. |  | Sun | Union | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_D | 2027-12-15 |  | 138 | 0 | 1.3 | 0 |  | Scurry | Scurry | Tier 4 |  |  |  |  | 1064, 1311 | Y |  |  |  | 99408 | 99407
99284 | Ranger Camp Switch - Barber Lake Switch 138 kV Line (East Circuit, 2nd Circuit) | Add Permian Basin Reliability Plan Upgrade ID L22A. Install a new 3.68-mile, 138 kV second conductor on existing double-circuit structures from Ranger Camp to Barber Lake (via Frontier) |  | Ranger Camp | Barber Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_A | 2027-12-15 |  | 138 | 3.68 | 0 | 0 |  | Mitchell | Mitchell | Tier 3 |  |  |  |  | 1189, 10050 | Y |  |  |  | 99285 | 99284
81232 | Cattleman – Bitter Creek/Champion Creek 345 kV Reroute | Terminate Morgan Creek – Bitter Creek/Champion Creek Double-Circuit 345 kV Line into Cattleman 345 kV Switch |  | Cattleman | Bitter Creek and Champion Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8647 | 2027-12-15 |  | 345 | 0 | 5 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 1414, 10053, 71050 | Y |  |  |  | 81665 | 81232
81225 | Cattleman - Range Rider 138 kV Double-Circuit Line | Construct a new 138 kV double-circuit line from Cattleman to Range Rider Switch |  | Cattleman | Range Rider | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8722 | 2027-12-15 |  | 138 | 0 | 6.6 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10054, 10183 | Y |  |  |  | 81226 | 81225
98953 | McDonald Road - Polecat Creek 138 kV Rebuild | Rebuild the 13.75 mile McDonald Road Switch - Polecat Creek Switch 138 kV Line |  | McDonald Road | Polecat Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8207 | 2027-12-15 |  | 138 | 0 | 13.75 | 0 |  | Glasscock | Glasscock | Tier 3 |  |  |  |  | 1333, 1334, 1335, 11337 | Y |  |  |  | 98954 | 98953
93466 | Rebuild Odessa EHV - Reiter 138 kV Double Circuit Line | Add Permian Basin Reliability Plan Upgrade ID L17 Upgrade Odessa - Reiter 138kV double-circuit line |  | Odessa EHV | Reiter | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB L17 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Ector | Ector | Tier 3 |  |  |  |  | 1027, 18545 | Y |  |  |  | 93467 | 93466
87021 | Construct Drill Hole – Riverton 345 kV Double-Circuit | Construct Drill Hole – Riverton 345 kV Double-Circuit |  | Drill Hole Switch | Riverton Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8748 | 2027-12-16 |  | 345 | 36 | 0 | 0 |  | Culberson | Reeves | Tier 1 | 24RPG010 | 2024-03-18 |  |  | 10073, 11084 | Y |  |  |  | 87022 | 87021
102661 | BEPC_TPIT102661_Pursley |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-12-17 |  | 69 | 0.13 | 0 | 0 |  | Navarro |  | Tier 4 |  |  |  |  | 190, 191, 194, 199 | Y |  |  |  | 102662 | 102661
102755 | BEPC_TPIT102755_Dennis |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-12-17 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 489, 494, 507 | Y |  |  |  | 102756 | 102755
90061 | Poisson: Construct New 345 kV Station | Interconnect Short Creek Solar to the new Poisson 345 kV station on the Riley to Fisher Road 345 kV line |  | Poisson |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TP2024154 | 2027-12-27 |  | 345 | 0 | 0 | 0 |  | Wichita |  | Tier 4 |  |  |  |  | 1425, 6101, 60136 | Y | N |  |  | 91151 | 90061
65154 | Mason Switch to Yellowjacket: Rebuild 69 kV Line | Rehab the Mason Switch to Yellowjacket 69 kV Line | Company Contact and In-Service Date Update | Mason Switch | Yellowjacket | Planned | 1142 - 1320 | AEP TNC | Carol Matheny myturner@aep.com 918-599-2437 | 2836 | 2027-12-31 |  | 69 | 0 | 26.45 | 0 |  | Menard | Mason | Tier 4 | 21RPG014 | 2021-08-01 | 2021-09-01 |  | 6363, 6396, 23824 | Y | N |  |  | 65155 | 65154
78404 | BBEC Bastrop Colony Substation Addition (formerly Bastrop Village) |  |  | Bastrop Colony |  | Planned |  | BBEC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8067 | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7555, 7556, 7561 | Y | N |  |  | 92458 | 78404
73065 | Magana Hein: Build new 138 kV distribution station | Construct new distribution station on the Molina to Wormser Road 138 kV line |  | Magana Hein |  | Planned |  | AEP TCC | Travis Coody jlsolis@aep.com 361-881-5574 |  | 2027-12-31 |  | 138 | 2.6 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8295, 8641, 8646, 8801, 80230 | Y |  |  |  | 73066 | 73065
99796 | Ganado: Expand 138 kV Station | Interconnect Dios BESS to the existing Ganado 138 kV station |  | Ganado |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2025221 | 2027-12-31 |  | 138 | 0.1 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 8117 | Y |  |  |  | 99797 | 99796
78461A | West Columbia to Damon and Needville to Big Creek Ckt.89A Upgrades | Rebuild/reconductor portions of West Columbia to Damon Ckt.89A as a Hardening upgrade. |  | West Columbia | Damon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 6.6 | 0 |  | Brazoria | Brazoria | Tier 4 | 23RPG021 | 2023-08-10 | 2023-08-31 | 2023-08-31 | 42370, 43380, 49914 | Y | N |  |  | 78462 | 78461
91394 | Mendoza_Substation_Upgrade | Increase the transformation capacity at Mendoza Substation by installing an additional power transformer and upgrade the existing bus configuration to an improved bus arrangement. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8202 | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7325 | Y |  |  |  | 91395 | 91394
73100 | Asherton to Piloncillo: Rebuild 138 kV Line | Rehab the Asherton to Piloncillo 138 kV line |  | Asherton | Piloncillo | Planned | TA2021030 | AEP TCC | William Simmons jlsolis@aep.com 361-881-5574 |  | 2027-12-31 | 2958101 | 138 | 0 | 13.43 | 0 |  | Dimmit | Dimmit | Tier 4 |  |  |  |  | 8283, 8970, 80481 | Y |  |  |  | 73101 | 73100
80315 | Big Foot to Pearsall: Convert to 138 kV | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch |  | Big Foot | Pearsall | Planned | 1104 - 1282 | AEP TCC | Will Simmons mlforcum@aep.com 918-599-2674 | 3821 | 2027-12-31 |  | 138 | 0 | 14.79 | 0 |  | Frio | Frio | Tier 4 | 23RPG024 | 2023-08-29 | 2023-09-28 |  | 8216, 8218, 8221, 8752 | Y |  |  |  | 80316 | 80315
80317 | Dilley Switch to Pearsall: Convert to 138 kV, Reroute from Dilley to Dilley Switch, Rebuild Dilley to Dilley Switch 69 kV, and Double Circuit Dilley Switch to Pearsall with Dilley to Dilley Switch | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch |  | Dilley Switch | Pearsall | Planned | 1104 - 1282 | AEP TCC | Will Simmons jlsolis@aep.com 361-881-5574 | 3822 | 2027-12-31 |  | 138 | 0 | 19.8 | 0 |  | Frio | Frio | Tier 4 | 23RPG024 | 2023-08-29 | 2023-09-28 |  | 8208, 8210, 8212, 8216, 8752 | Y |  |  |  | 80318 | 80317
90189 | Meadow 345kV Substation Expansion for Aldrin 345 BESS(25INR0425). | Expand 345kV Meadow (MDO) substation for ALDRIN (ALD) / Aldrin 345 BESS (25INR0425). |  | Meadow |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  |  | 90190 | 90189
72032 | Stewart to West Bay Ckts 48A & 59A Upgrades | Reconductor Ckts. 48A & 59A Stewart to West Bay as a Hardening upgrade. |  | Stewart | West Bay | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 40 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 43290, 43520, 43521 | N |  |  |  | 72033 | 72032
98878 | Chalk 69 kV Substation Conversion to 138 kV | Add Permian Basin Reliability Plan Upgrade ID L20G. Construct a new Chalk 138-kV substation at the existing Chalk 69-kV substation and loop the existing McDonald Road – Navigation 138-kV line into Chalk |  | Prong Moss | McDonald Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L20_G | 2027-12-31 |  | 138 | 1 | 0 | 0 |  | Howard | Glasscock | Tier 3 |  |  |  |  | 1333, 1352, 10066, 10112, 10186, 10187, 10188 | Y |  |  |  | 98883 | 98878
78495 | Hillje 345kV Substation Expansion for Space City Solar - Generator Interconnection (21INR0341) | Expand Hillje 345kV substation and install one generator lead for new interconnection to MIDANE customer substation for Space City Solar |  | Hillje | MIDANE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44200, 112261 | Y | N |  |  | 78496 | 78495
55550 | Brushline: Construct New Distribution Station | Construct new 138/13 kV station Brushline | Company Contact and In-Service Date Update | Brushline |  | Planned | 1106 - 1284 | AEP TCC | Julkarnain Chowdhury myturner@aep.com 918-599-2437 | 3826 | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 5754, 8963, 8972 | Y |  |  |  | 55551 | 55550
92280 | Alamo St - Bottlebrush 138kV - Upgrade L12 2024 Permian Basin Study | Alamo St - Bottlebrush 138kV - Upgrade L12 2024 Permian Basin Study |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-12-31 |  | 138 | 31.75 | 28.7 | 0 |  | Pecos | Pecos | Tier 2 |  |  |  |  | 38310, 38320, 38331, 38360, 38365, 38381, 38383, 38439 | Y |  |  |  | 92281 | 92280
73352A | PH Robinson Area 138kV Upgrades | Reposition existing PH Robinson to BACLIF generator lead from the PHR_South bus to the PHR_North bus. |  | PH Robinson | BACLIF | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42010, 42015, 111131 | Y | N |  |  | 73353 | 73352
76237 | Lobo: Construct New 345 kV Terminal | Interconnect Cuchillas Solar to the Lobo 345 kV station |  | Lobo |  | Planned |  | ETT | John Solis jlsolis@aep.com 361-881-5574 | TP2023320 | 2027-12-31 | 2025-06-01 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219 | Y |  |  |  | 76238 | 76237
91392 | Bergheim_Autotransformer_Upgrade | To improve efficiency and reliability of the transmission system, LCRA TSC will replace the existing Bergheim AT1 autotransformer with a higher capacity unit and install a second autotransformer at Bergheim Substation. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7662 | 2027-12-31 |  | 345 | 0 | 0 | 672 |  | Comal | Comal | Tier 3 |  |  |  |  | 7170, 7770, 7771, 7772, 70170, 70493 | Y |  |  |  | 91408 | 91392
75830A | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). Loop Ckt.27 into Savannah substation to create new Ckt.27 Seabreeze to Savannah to Oasis. |  | Savannah | Seabreeze/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 42590, 43020, 43035, 43180 | Y | N |  |  | 102674 | 75830
99141 | Rebuild Flower Grove - Vincent 138 kV Line Rebuild | Upgrade the existing Flower Grove - Vincent 138 kV Line Section |  | Flower Grove | Vincent | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8736 | 2027-12-31 |  | 138 | 0 | 20.3 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 1355, 1360, 1396, 10047, 11149, 11362 | Y |  |  |  | 99238 | 99141
75830B | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). | Install generator lead from Savannah (SAV) substation to CASCAD (CSC) customer substation (23INR0091). |  | Savannah | CASCAD | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43180, 113751 | Y | N |  |  | 102675 | 75830
72059 | Hillje 345kV Substation Expansion for Ramsey Storage - Generator Interconnection to FLATLA (FLA) (21INR0505) | Expand Hillje 345kV substation and install one generator lead for new interconnection to FLATLA (FLA) customer substation for Ramsey Storage |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44200, 113595 | Y | N |  |  | 90911 | 72059
73352D | PH Robinson Area 138kV Upgrades | Upgrade PH Robinson 'North' Bus fault duty to 80KA |  | PH Robinson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 00:03 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 | [5 empty] | Y | N |  |  | 73356 | 73352
80342 |  |  |  | HILLTOP LAKES | HILLTOP LAKES | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-01-06 |  | 138 | 0 | 0 | 60 |  | Leon | Leon | Tier 4 |  |  |  |  | 47, 48 | Y |  |  |  | 80343 | 80342
102659 | BEPC_TPIT102659_KellerUpgrade |  |  | 565 | 1856 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-01-07 |  | 138 | 0 | 0.27 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 565, 1856 | Y |  |  |  | 102660 | 102659
87367 |  |  |  | Temple Switch | Poage | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-01-28 |  | 138 | 0 | 2 | 75 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 126, 130, 133, 3415, 33126 | Y |  |  |  | 87368 | 87367
72479 | Cobia: Build new 138 kV Station | Build new 138 kV station along the Carbide to Joslin 138 kV line | In-Service Date Update | Cobia |  | Planned |  | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 |  | 2028-01-31 |  | 138 | 0.1 | 0 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | 8132, 8133, 8140, 8155, 8685, 8720, 8741, 8742, 88742, 708133 | Y |  |  |  | 72482 | 72479
64067 | Bessel to King Ranch: 138 kV Line Rebuild | Rehab the Bessel to King Ranch 138 kV line |  | Bessel | Stratton | Planned |  | AEP TCC | Robert Dougherty deevans@aep.com 918-599-2938 | TA2020081 | 2028-01-31 |  | 138 | 0 | 26.59 | 0 |  | Nueces | Kleberg | Tier 4 | 23RPG001 | 2023-01-25 | 2023-02-24 |  | 8060, 8498, 8512, 8514, 8665, 80228 | Y |  |  |  | 64068 | 64067
86933 | Paladio: Construct New 345 kV Station | Interconnect Argenta Solar and Storage to the new Paladio 345 kV station on the Goddard to Tango 345 kV line | Company Contact and In-Service Date Update | Paladio |  | Planned |  | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2024012 | 2028-01-31 |  | 345 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8012, 8606, 8689 | Y |  |  |  | 86934 | 86933
73055 | Hamlin to Roby: Rebuild 69 kV line | Rehab Hamlin to Roby 69 kV line | Company Contact and In-Service Date Update | Hamlin | Roby | Planned |  | AEP TNC | Bill Edwards myturner@aep.com 918-599-2437 |  | 2028-01-31 |  | 69 | 0 | 25.23 | 0 |  | Fisher | Jones | Tier 4 | 23RPG002 | 2023-02-01 | 2023-02-28 |  | 6185, 6192, 6193, 6194, 6195, 6638 | Y | N |  |  | 73056 | 73055
77144 | Pompano: New 138 kV Station | New station for Next Decade/ Rio Grande LNG | In-Service Date and Cost Update | Pompano |  | Planned |  | AEP TCC | Robert Younger jlsolis@aep.com 361-881-5574 | TP2015151 | 2028-01-31 |  | 138 | 0 | 20.4 | 0 | 0,276.4 | Cameron |  | Tier 4 |  |  |  |  | 8337, 8535, 79601 | Y |  |  |  | 77145 | 77144
98798 | Beecher: Expand 138 kV Station | Interconnect Leopard BESS to the existing Beecher 138 kV station |  | Beecher |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2025255 | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 8088, 8721 | Y |  |  |  | 98799 | 98798
55626 | Ganso to Hamilton Road: Rebuild 138 kV line | Rebuild 138 kV line from Ganso to Hamilton Road |  | Maverick | Hamilton Road | Planned | 1105 - 1283 | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 | 3824 | 2028-02-28 |  | 138 | 0 | 41.1 | 0 |  | Maverick | Val Verde | Tier 3 | 22RPG044 | 2022-12-15 | 2023-01-17 |  | 8255, 8267, 8692 | Y |  |  |  | 65576 | 55626
55624 | Escondido to Ganso: Rebuild 138 kV line | Rebuild 138 kV line from Escondido to Ganso |  | Escondido | Ganso | Planned | 1105 - 1283 | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 | 3825 | 2028-02-28 |  | 138 | 0 | 10.198 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 8260, 8267 | Y |  |  |  | 65575 | 55624
99132 | Expand Channelview 138kV substation for Brookview Road BESS (27INR0243) |  |  | Channelview |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 99133 | 99132
91744B | New 138kV CEHE Station Grassland for OCI SunRoper (24INR0257) | Install one generator lead from Grassland (GRS) CEHE 138kV substation to SUNROP (SUN) / OCI SunRoper |  | Grassland |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y |  |  |  | 92898 | 91744
91744A | New 138kV CEHE Station Grassland for OCI SunRoper (24INR0257) | Loop new Grassland (GRS) CEHE 138kV substation into Ckt.60D Dyann to South Lane City to create new Ckt.60 Dyann to Grassland to South Lane City. |  | Grassland | Dyann/South Lane City | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 42730, 42985, 43190 | Y | N |  |  | 92897 | 91744
100054 | Luna to Mesquite: Rebuild 138 kV Line | Rebuild the Luna to Mesquite 138 kV line | Company Contact and In-Service Date Update | Luna | Mesquite | Planned |  | AEP TCC | Craig Tabor jlsolis@aep.com 361-881-5574 | TP2025785 | 2028-02-28 |  | 138 | 0 | 1.25 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 8554, 8656 | Y |  |  |  | 100055 | 100054
90002 | Salvare: Install New 345 kV Capacitor Bank | Install a new capacitor bank at the Salvare 345 kV station | Company Contact and In-Service Date Update | Salvare |  | Planned |  | ETT | Matthew McLauchlin myturner@aep.com 918-599-2437 | TP2024109 | 2028-02-28 |  | 345 | 0 | 0 | 0 | 0,46.1 | Childress |  | Tier 4 |  |  |  |  | 60511 | Y | N |  |  | 91298 | 90002
90051 | Riley: Construct New 345 kV Terminal | Interconnect the Sabey Data Center load to the existing Riley 345 kV station | In-Service Date Update | Riley |  | Planned |  | AEP TNC/ETT | Jim Nivens myturner@aep.com 918-599-2437 | TP2024133 | 2028-02-28 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6101, 60150, 60151 | Y |  |  |  | 90052 | 90051
73441 | Dupont Switch to Joslin: Rebuild 138 kV Line | Rehab the Dupont Switch to Joslin 138 kV Line | Company Contact and In-Service Date Update | Dupont | Joslin | Planned |  | AEP TCC | Travis Coody myturner@aep.com 918-599-2437 |  | 2028-02-28 |  | 138 | 0 | 32.6 | 0 |  | Victoria | Calhoun | Tier 4 | 22RPG040 | 2022-11-01 | 2022-12-01 |  | 8140, 8141, 8143, 8722, 80064 | Y |  |  |  | 73442 | 73441
70712 | SAPS to Red Creek: Rebuild 138 kV Line | Rehab the SAPS to Red Creek 138 kV line |  | SAPS | Red Creek | Planned |  | AEP TNC | Sally Matthews myturner@aep.com 918-599-2437 | TA2020210 | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 3 |  |  |  |  | 6442, 6473, 6480, 60008 | Y |  |  |  | 70713 | 70712
99800 | Marconi: Expand 138 kV Station | Interconnect Pajarita BESS to the existing Marconi 138 kV station |  | Marconi |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025326 | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8266 | Y |  |  |  | 99801 | 99800
99833 | LCRATSC_Kempner-Lampasas_Transmission_Line_Overhaul | Perform an overhaul on the 7.7 mile T154 Kempner - Lampasas 138-kV transmission line. |  | 7061 Copperas Cove | 7260 Kempner | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-03-20 |  | 138 | 0 | 5.62 | 0 |  | Lampasas | Lampasas | Tier 4 |  |  |  |  | 7064, 7260 | Y |  |  |  | 99834 | 99833
98618 | Chalybe: Expand 345 kV Station | Install two 345/138 kV autotransformers at the Chalybe 345/138 kV station |  | Chalybe |  | Planned | TP2025010 | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-03-27 |  | 345 | 0 | 0 | 1350 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2025-03-24 | 2025-09-24 | 2025-12-24 | 8735, 88337 | Y |  |  |  | 98837 | 98618
98622 | Chalybe to Palmito: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Chalybe to Palmito | Transmission Owner, Owner Project Number, and RPG Dates Update | Chalybe | Palmito | Planned |  | AEP TCC/AEP TCC/SLU | John Solis jlsolis@aep.com 361-881-5574 | TP2025010 | 2028-03-31 |  | 345 | 2 | 0 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 79500, 88337 | Y |  |  |  | 98839 | 98622
77172 | Caravel: Construct New 138 kV Station | Interconnect the 1PointFive USA load to the new Caravel 138 kV station on the Barney Davis to Nelson Sharpe 138 kV line between Alazan and Barney Davis | In-Service Date and Cost Update | Caravel |  | Planned |  | AEP TCC/ETT | LaRissa Lundry jlsolis@aep.com 361-881-5574 | TP2024088 | 2028-03-31 |  | 138 | 0 | 0 | 0 |  | Kleberg |  | Tier 4 |  |  |  |  | 8458, 8515, 80099 | Y |  |  |  | 77173 | 77172
99794 | Frontera: Install 138 kV Series Reactors | Install two 15-ohm series reactors at the Frontera 138 kV station |  | Frontera |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025213 | 2028-03-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8980, 80004, 80005, 80119, 80295, 80296 | Y |  |  |  | 99795 | 99794
81686 | Chalcedony: Construct New 345 kV Station | Interconnect the Monarch load to the new Chalcedony 345 kV station on the Lon Hill to Nelson Sharpe 345 kV line |  | Chalcedony |  | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2028-03-31 |  | 345 | 1.5 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8455, 80078, 84555, 85000 | Y | N |  |  | 81687 | 81686
98637 | Chalybe to Stillman: Construct New 138 kV Line | Construct a new 138 kV single circuit line from Chalybe to Stillman | Transmission Owner Project Number and RPG Dates Update | Chalybe | Stillman | Planned |  | AEP TCC/AEP TCC/SLU | John Solis jlsolis@aep.com 361-881-5574 | TP2025010 | 2028-03-31 |  | 138 | 1 | 0 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 8735, 79601 | Y |  |  |  | 98844 | 98637
100073 | Rio Pecos: Expand 138 kV Station | Interconnect Midnight Sun BESS to the existing Rio Pecos 138 kV station |  | Rio Pecos |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2025332 | 2028-03-31 |  | 138 | 0.1 | 0 | 0 |  | Crockett |  | Tier 4 | [5 empty] | Y |  |  |  | 100074 | 100073
98632 | Chalybe: Install two STATCOMs at the 138 kV Station | Install two 150 MVAR STATCOMs at the Chalybe 138 kV station | Transmission Owner Project Number and RPG Dates Update | Chalybe |  | Planned |  | AEP TCC/AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025010 | 2028-03-31 |  | 138 | 0 | 0 | 0 | -300300 | Cameron |  | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 8735, 80282, 80283 | Y |  |  |  | 98842 | 98632
98620 | Chalybe to Kingfisher: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Chalybe to Kingfisher | Transmission Owner, Owner Project Number, and RPG Dates Update | Chalybe | Kingfisher | Planned |  | AEP TCC/AEP TCC/SLU | John Solis jlsolis@aep.com 361-881-5574 | TP2025010 | 2028-03-31 |  | 345 | 22 | 0 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 79501, 88337 | Y |  |  |  | 98838 | 98620
51001 | Friess Ranch to Sonora: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line |  | Friess Ranch | Sonora | Planned | 1044 - 1217 | AEP TNC/AEP TCC | Greg Crane twang1@aep.com 918-599-2635 | 2791 | 2028-03-31 12:00 |  | 69 | 0 | 24.3 | 0 |  | Sutton | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 6513, 6570, 8238, 8239, 60210, 60438 | Y | N |  |  | 65554 | 51001
102634 | BEPC_TPIT10264_Egan_HappyHill_Improvement |  |  | 438 | 412 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-04-03 |  | 138 | 0 | 2 | 36 |  | Johnson |  | Tier 4 |  |  |  |  | 405, 412, 419, 432, 438, 439, 33405 | Y |  |  |  | 102635 | 102634
102670 | BEPC_TPIT102670_Rockett |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-04-03 |  | 69 | 0 | 6.5 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 214, 218 | Y |  |  |  | 102671 | 102670
73061 | Falfurrias to King Ranch: 138 kV Line Rebuild | Rehab the Falfurrias to King Ranch 138 kV line |  | Falfurrias | King Ranch | Conceptual |  | AEP TCC | Sally Matthews deevans@aep.com 918-599-2938 |  | 2028-04-30 |  | 138 | 0 | 20.5 | 0 |  | Brooks | Kleberg | Tier 4 |  | 2023-01-24 | 2023-02-24 |  | 8510, 80228 | Y | N |  |  | 73062 | 73061
70706 | Tungsten (Carbide): Rebuild 138/69 kV Station | Rehab the Tungsten (Carbide) 138/69 kV station |  | Tungsten |  | Planned |  | AEP TCC | Robert Dougherty deevans@aep.com 918-599-2938 |  | 2028-04-30 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 | 21RPG024 | 2021-12-16 | 2022-01-18 |  | 5598, 8144, 8149, 8152, 8154, 8159, 8161, 8189, 8190, 8536, 8723, 80135, 110331, 110332, 110334, 110335, 110336 | Y |  |  |  | 78605 | 70706
98737 | Agrios: Construct New 345 kV Station | Interconnect Grapefruit Solar to the new Agrios 345 kV station on the North Edinburg to Reforzar 345 kV line |  | Agrios |  | Planned |  | AEP TCC | John Solis jsolis@aep.com 361-881-5574 | TP2025218 | 2028-04-30 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8098, 8905, 80078, 80233 | Y |  |  |  | 98738 | 98737
99551 | Chalice: Construct New 345 kV Station | Interconnect Corvus Solar to the new Chalice 345 kV station on the Cenizo to Lobo 345 kV line | Owner and In-Service Date Update | Chalice |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025348 | 2028-04-30 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80217, 80219, 80220 | Y |  |  |  | 99552 | 99551
91747 | Install (1) 50 MVAr switchable cap bank at Willow substation. Connect CB1 at the Willow breaker position with Willow TR3 distribution transformer |  |  | Willow |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-30 |  | 138 | 0 | 0 | 0 | 0,50 | Harris |  | Tier 4 |  |  |  |  | 46660 | Y | N |  |  | 99881 | 91747
93461A | Willow Substation Load Addition Upgrades | Install (1) 50 MVAr switchable cap bank at Willow substation. |  | Willow |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-30 |  | 138 | 0 | 0 | 0 | 0,50 | Harris |  | Tier 4 |  |  |  |  | 46660 | Y | N |  |  | 98389 | 93461
93461B | Willow Substation Load Addition Upgrades | Install (1) 50 MVAr cap bank at Klein substation. Tap the cap bank on Ckt.81F Klein to Kluge. |  | Klein |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-30 |  | 138 | 0 | 0 | 0 | 0,50 | Harris |  | Tier 4 |  |  |  |  | 45940 | Y | N |  |  | 98390 | 93461
93461C | Willow Substation Load Addition Upgrades | Install (3) 14.4 MVAr switchable cap banks at Klein substation. Connect cap banks at the 35kV distribution level. |  | Klein |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-30 |  | 138 | 0 | 0 | 0 | 0,43.2 | Harris |  | Tier 4 |  |  |  |  | 45940 | Y | N |  |  | 98391 | 93461
45125 | Quintana Rd to South San Rebuild | Rebuild 1.3 miles of 138 kV transmission line form Quintana Rd substation to South San substation. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0271 | 2028-05-01 |  | 138 | 0 | 1.29 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-15 |  |  | 5350, 5385 | Y |  |  |  | 45126 | 45125
88049 | Loop in Cagnon to Howard into Omicron |  |  |  |  | Planned | T-0394 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5054, 5230, 5326 | Y |  |  |  | 88050 | 88049
99207 | Rebuild (5.4 miles) Cagnon to VLSI transmission line to at least 698MVA | Rebuild (5.4 miles) Cagnon to VLSI transmission line to at least 698MVA |  | 5055 | 5467 | Planned | T-0397, S-1060 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-05-01 |  | 138 | 0 | 8.74 | 0 |  | Bexar | Bexar | Tier 1 |  |  |  |  | 5055, 5467 | Y |  |  |  | 99208 | 99207
1549 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 | [5 empty] | Y | N |  |  | 8754 | 1549
102875 | Upgrade Franklins Camp Auto |  |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | N | N |  |  | 102876 | 102875
76768 | Upgrade Pearson -Pearsall | Upgrade the Pearson-Natalia-Devine-Moore-Pearsall to 795 ACSR |  | Pearson | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 34.62 | 0 |  | Frio | Medina | Tier 4 |  |  |  |  | 5811, 5828, 5830, 5857, 5858, 5893, 58570 | Y |  |  |  | 76769 | 76768
76777 | Rebuild Nursery-El Toro | Rebuild Nursery- Fordtran Sw- Inez - El Toro Sw Station to 795 ACSR |  | Nursery | El Toro | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 24.8 | 0 |  | Victoria | Jackson | Tier 4 |  |  |  |  | 5504, 5510, 5514, 5516 | Y |  |  |  | 76778 | 76777
76107 | Riverside Capacitor | Add a new cap bank at Riverside sub with 2 9.6 MVAR steps |  | Riverside |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5632 | Y | N |  |  | 76108 | 76107
72956 | Bellville South - Prairie View Transmission Line Upgrade | the proposed project converts the existing 69kV transmission line T283 from Bellville South- Quanex Sw - Sunnyside - Prarie View substation to 138kV. The proposed project improves the reliabiltiy of transmission facilities on the 26.1 mile transmission line and increases the line capacity for long term system growth. |  | Bellville South | Prairie View | Conceptual | Project transitioned to STEC from LCRA . Previous Mod Project #47428 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 0 | 0 |  | Austin | Waller | Tier 3 |  |  |  |  | 7269, 57660, 57664, 57666 | N | N |  |  | 72957 | 72956
92572 | Lockhart Mendoza Transmission Line Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8191 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7206, 7215, 7216, 7325 | Y |  |  |  | 92573 | 92572 | 2024-SC20
100279 | Alford_Benedum_Transmission_Line_Upgrade | LCRA TSC will upgrade T611 Alford (Midkiff) - Benedum 138-kV transmission line to obtain a higher operational rating. |  | Alford | Benedum | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 71211, 71213 | Y |  |  |  | 100280 | 100279
100281 | Benedum_Autotransformer_Addition | Benedum Substation will be cut-in to the PUCT-approved Bearkat to North McCamey 345-kV transmission line and two 345/138-kV autotransformers will be installed at Benedum Substation |  | Benedum |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | Upton | Upton | Tier 2 |  |  |  |  | 59903, 71213, 76000, 76200, 76201, 76202 | Y |  |  |  | 100282 | 100281
99827A | LCRATSC_Canyon-Gofort_Transmission_Line_Overhaul |  |  | 7200 Canyon | 7515 Rohr | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-05-15 |  | 138 | 0 | 4.5 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7200, 7515 | Y |  |  |  | 99828 | 99827
99827B | LCRATSC_Canyon-Gofort_Transmission_Line_Overhaul |  |  | 7515 Rohr | 7514 Yarrington | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-05-15 |  | 138 | 0 | 0.51 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7514, 7515 | Y |  |  |  | 99829 | 99827
99827C | LCRATSC_Canyon-Gofort_Transmission_Line_Overhaul |  |  | 7514 Yarrington | 7501 Goforth | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-05-15 |  | 138 | 0 | 4.16 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7501, 7514 | Y |  |  |  | 99830 | 99827
92565 | Sim_Gideon_Winchester_Transmission_Line_Upgrade | LCRA TSC will upgrade Sim Gideon - Winchester 138-kV transmission line to achieve a higher operational rating |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7654 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7306, 7310 | Y |  |  |  | 92566 | 92565 | 2023-SC15
92602 | Bastrop West - Bluebonnet Transmission Line Upgrade | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee. |  | 7555 | 7556 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org | PLC-8101 | 2028-05-15 |  | 138 | 0 | 6.1 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7555, 7556, 7561 | Y |  |  |  | 92603 | 92602 | 2024-SC20
99357 | Add Permian Basin Reliability Plan Upgrade ID L25D and L25E. | Add Permian Basin Reliability Plan Upgrade ID L25D and L25E. Convert the existing Plowboy - Eskota 69-kV line to 138-kV. Loop the converted Plowboy - Eskota 138-kV line into Roscoe near the Sweetwater. Move the Eskota 138/69-kV transformer 1 to Plowboy. |  | Oak Spring | Plowboy | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8805 | 2028-05-15 |  | 138 | 2.4 | 0 | 0 |  | Nolan | Nolan | Tier 2 |  |  |  |  | 1339, 1340, 1378, 1380, 1381, 10103, 10104, 11380, 701380 | Y |  |  |  | 99676 | 99357
99479C | Snyder - China Grove 69 kV Loop Converstion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L23. Convert the existing Snyder - Scurry - China Grove and Snyder - Amoco Tap - China Grove 69-kV lines to 138-kV. This converts the China Grove - Snyder 69 kV Line into 138 kV and reterminates into the new Snyder 138 kV Switch. |  | China Grove | Snyder | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L23 | 2028-05-15 |  | 138 | 0 | 10.2 | 0 |  | Scurry | Scurry | Tier 1 |  |  |  |  | 1304, 1305, 1306, 1318, 1319, 1376, 10203, 11375 | Y |  |  |  | 99482 | 99479
99530 | Deep Creek - Snyder - China Grove 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22E. Upgrade the existing Deep Creek - China Grove 138-kV line |  | Deep Creek | China Grove | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_E | 2028-05-15 |  | 138 | 0 | 14.56 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  |  | 1304, 1318, 10203 | Y |  |  |  | 99531 | 99530
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line | Project Deferral | Handley | Hemphill | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5214 | 2028-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 11818 | 4270
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0196 | 2028-05-15 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 9559 | 2308
81236 | Cattleman – Longshore 345 kV Double-Circuit Line Rebuild | Rebuild the existing 345 kV Double Circuit Line |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 R8719 | 2028-05-15 |  | 345 | 0 | 66.8 | 0 |  | Howard | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1058, 10053 | Y |  |  |  | 81385 | 81236
99522 | Upgrading line | Upgrading conductor to 1xSuwannee | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70489, 70491 | Y |  |  |  | 99523 | 99522
73570 | Steger Substation Addition | Substation addition to provide Point of Interconnection for Oncor New Sweden substation addition. |  | Steger |  | Conceptual |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7336, 7337, 7339 | Y | N |  |  | 73571 | 73570
73762 | Peppergrass Substation Addition | American Electric Power (AEP) is building a new load serving substation and needs transmission service from the LCRA TSC owned 138-kV T470 Abilene South to McElmurray transmission line. LCRA TSC will install a new 138-kV bus and provide transmission service to the new AEP substation. |  | Peppergrass |  | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org | PLC-4477 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6260, 76316, 76317 | Y | N |  |  | 73763 | 73762
100178 | HarrisBranch_McNeil_Transmission_Line_Upgrade | LCRA TSC will upgrade T146 Harris Branch - McNeil 138-kV transmission line to achieve a higher operational rating. |  | Harris Branch | Mcneil | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7333, 7334 | Y |  |  |  | 100179 | 100178
100180 | HarrisBranch_ShadowGlen_Transmission_Line_Upgrade | LCRA TSC will upgrade T574 Harris Branch - Shadow Glen 138-kV transmission line to achieve a higher operational rating. |  | Harris Branch | Shadow Glen | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7323, 7333 | Y |  |  |  | 100181 | 100180
100182 | Henne_Zorn_Transmission_Line_Upgrade | LCRA TSC will upgrade T204 Henne - Zorn 138-kV transmission line to achieve a higher operational rating. |  | Henne | Zorn | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Hays | Tier 4 |  |  |  |  | 7174, 7180 | Y |  |  |  | 100183 | 100182
100283 | Comfort_Cypress_Creek_Transmission_Line_Upgrade | LCRA TSC will upgrade T121 Comfort - Cypress Creek 138-kV transmission line to achieve a higher operational rating. |  | Comfort | Cypress Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Kendall | Kendall | Tier 4 |  |  |  |  | 7155, 7156 | Y |  |  |  | 100284 | 100283
100285A | Comfort_Kendall_Transmission_Line_Upgrade |  |  | Comfort | Kendall | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Kendall | Kendall | Tier 3 |  |  |  |  | 7138, 7150, 7155 | Y |  |  |  | 100286 | 100285
100285B | Comfort_Kendall_Transmission_Line_Upgrade |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | [5 empty] | Y |  |  |  | 102393 | 100285
100287 | Comfort_Raymond_Barker_Transmission_Line_Upgrade | LCRA TSC will upgrade T122 Comfort - Raymond F. Barker 138-kV transmission line to achieve a higher operational rating. |  | Comfort | Raymond Barker | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Kendall | Kerr | Tier 4 |  |  |  |  | 7155, 7158 | Y |  |  |  | 100288 | 100287
100289 | CypressCreek_Raymond_Barker_Transmission_Line_Upgrade | LCRA TSC will upgrade T662 Cypress Creek - Raymond F. Barker 138-kV transmission line to achieve a higher operational rating. |  | Cypress Creek | Raymond Barker | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kendall | Tier 4 |  |  |  |  | 7156, 7158 | Y |  |  |  | 100290 | 100289
99818 | LCRATSC_Manor_Shadow_Glen_Transmission_Line_Upgrade | Upgrade the existing T649 Manor - Shadow Glen 138-kV transmission line to a minimum 105 deg. F ambient temperature rating of 700 MVA |  | 7323 | 7330 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-05-15 |  | 138 | 0 | 1.74 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7323, 7330 | Y |  |  |  | 99819 | 99818
99774 | Butler_Elgin_Transmission_Line_Overhaul | Perform an overhaul on the 2.8-mile T260 Butler - Elgin 138-kV transmission line. |  | Butler | Elgin | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Williamson | Tier 4 |  |  |  |  | 7321, 7324 | Y |  |  |  | 99775 | 99774
100155 | Establish Mormino 345 kV Switch for customer POD | Establish Mormino 345 kV Switch for customer POD |  | Mormino | Mormino | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6370 | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3403, 3779, 3791 | Y |  |  |  | 100156 | 100155
99344 | Rebuild the MInerva - Cannon 138 kV Line | Rebuild the MInerva - Cannon 138 kV Line |  | Minerva | Cannon | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6414 | 2028-05-15 |  | 138 | 0 | 10.2 | 0 |  | Milam | Milam | Tier 1 |  |  |  |  | 64, 3683, 3707 | Y |  |  |  | 99345 | 99344
100078 | Provide 345 kV POD to customer via POI from LCRA's Bow Wood 345 kV Switch | Provide 345 kV POD to customer via POI from LCRA's Bow Wood 345 kV Switch |  | Mikeska | Bow Wood | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6476 | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | McCulloch | McCulloch | Tier 4 |  |  |  |  | 3811, 76006 | Y |  |  |  | 100079 | 100078
100293 | Zorn_Load_Circuit_Breaker_Addition | Install a new 345-kV transmission point of interconnection to serve GVEC member load |  | Zorn |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7042 | Y |  |  |  | 100294 | 100293
91312A | Austrop - Zorn Transmission Line Upgrade | Upgrade the existing Austrop - Zorn 345-kV double-circuit transmission line between Austrop and Garfield substations to achieve a higher operational rating. |  | 7040 | 7048 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8063, PLC-8139, PLC-8140 | 2028-05-15 |  | 345 | 0 | 16.8 | 0 |  | Travis | Bastrop | Tier 1 |  |  |  |  | 7040, 7042, 7048 | Y |  |  |  | 91313 | 91312 | 2024-SC19
91312B | Austrop - Zorn Transmission Line Upgrade | Upgrade the existing Austrop - Zorn 345-kV double-circuit transmission line between Garfield and Lytton Springs substations to achieve a higher operational rating |  | 7048 | 9074 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8063, PLC-8139, PLC-8140 | 2028-05-15 |  | 345 | 0 | 24.7 | 0 |  | Bastrop | Caldwell | Tier 1 |  |  |  |  | 7040, 7042, 7048, 9074 | Y |  |  |  | 91314 | 91312 | 2024-SC19
91628 | Upgrading Buda to Rutherford | Upgrading Buda to Rutherford branch to minimum 379 MVA. | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70498, 70509 | Y |  |  |  | 91629 | 91628
81268 | Longshore – Consavvy 345 kV Double-Circuit Line Rebuild | Rebuild existing 345 kV Double-Circuit Line |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 | 2028-05-15 |  | 345 | 0 | 66.8 | 0 |  | Howard | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1058, 11387, 18548 | Y |  |  |  | 81388 | 81268
87697 | Bell County - Poage - Seaton 69 kV Line Conversion to 138 kV | Bell County - Poage - Seaton 69 kV Line Conversion to 138 kV |  | Bell County | Seaton | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6367 | 2028-05-16 |  | 138 | 0 | 17.8 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 126, 130, 131, 133, 3598, 3636, 3735, 33126 | Y |  |  |  | 87698 | 87697
91531 |  |  |  | Schwertner | Gabriel | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-05-19 |  | 138 | 0.3 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 122, 124, 7345, 7346 | Y |  |  |  | 91532 | 91531
93679 | New BPUB substation |  |  | Loma Alta/CRONUS | NIMZO | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2028-05-25 |  | 138 | 24 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5962, 59551 | Y |  |  |  | 93680 | 93679
99274C | Cedar Bayou RPG - Substation Upgrades (25RPG014) | Install 2.5-Ohm reactor in-series with existing Cedar Bayou A3 on the 138kV side of the autotransformer. |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers |  | Tier 3 | 25RPG014 | 2025-05-22 | 2025-06-13 | 2025-06-16 | 40000, 40015, 40020, 49008 | Y | N |  | Cost included in main entry | 99277 | 99274
99000B | Install (2) 14.4 MVAR distribution cap banks at Twinwood substation. Install (2) 14.4 MVAR distribution cap banks at Fulshear substation. Install (2) 55 MVAR transmission cap bank at Peters substation. | Install (1) 55 MVAR transmission cap bank at Peters substation. (first of two) |  | Twinwood / Fulshear |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,55 | Fort Bend |  | Tier 4 |  |  |  |  | 46220 | Y | N |  |  | 99002 | 99000
99791B | Additional Facility Ratings Methodology Phase 2 (FRM2) Substation Upgrades. | Upgrade Ckt.79C BIGBAY to BAYOU to increase thermal limits as part of FRM2 upgrades. |  | BIGBAY | BAYOU | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42160, 42180 | Y | N |  |  | 99807 | 99791
99409 | Hockley Cap Bank Addition | Hockley Cap Bank Addition, originally added to cases as part of Project 91713 |  | Hockley |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,40 | Harris |  | Tier 4 |  |  |  |  | 45880 | Y | N |  |  | 99410 | 99409
80579 | La Palma to Stewart Road: Convert to 138 kV | Convert the La Palma to Stewart Road 69 kV line to 138 kV |  | La Palma | Stewart Road | Planned | TA2020071 | AEP TCC | Robert Younger deevans@aep.com 918-599-2938 |  | 2028-05-31 |  | 138 | 0 | 37.5 | 0 |  | Cameron | Hidalgo | Tier 3 | 23RPG005 | 2023-03-01 | 2023-03-23 |  | 5778, 8040, 8310, 8314, 8701, 8703, 8748, 8751, 8949, 8951, 80104, 80229 | Y | N |  |  | 80580 | 80579
99863 | Doffing: Construct New Distribution Station | Construct new distribution station on the Stewart Road to Hi-Line 138 kV line |  | Doffing |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 5778, 8951, 80294, 80298 | Y |  |  |  | 99864 | 99863
86829 | Fort Stockton Plant to Lynx: Rebuild 138 kV Line | Rehab the Fort Stockton Plant to Lynx 138 kV line | Company Contact and In-Service Date Update | Fort Stockton Plant | Lynx | Planned | TA2020218 | AEP TNC | Damian Raab myturner@aep.com 918-599-2437 |  | 2028-05-31 |  | 138 | 0 | 37 | 0 |  | Pecos | Pecos | Tier 4 | 23RPG008 | 2023-04-14 | 2023-05-05 |  | 6630, 6671, 60400 | Y | N |  |  | 86830 | 86829
98561 | Solstice to Hayter Tap: Rebuild 138 kV Line Double Circuit | Rebuild the Solstice to Hayter Tap 138 kV line as a double circuit | Company Contact, Transmission Owner Project Number, and In-Service Date Update | Solstice | Hayter Tap | Planned |  | AEP TNC | Brooks Dow myturner@aep.com 918-599-2437 |  | 2028-05-31 |  | 138 | 1.7 | 1.7 | 0 |  | Pecos | Pecos | Tier 2 |  |  |  |  | 6680, 60444, 60802, 78925 | Y |  |  |  | 98562 | 98561
52070 | Carver to Maxwell: Rebuild 138 kV line | Rehab Carver to Maxwell 138 kV Line |  | Carver | Maxwell | Planned | 1079 - 1252 | AEP TCC/AEP TNC | Damian Raab twang1@aep.com 918-599-2635 | 3804 | 2028-05-31 | 2958101 | 138 | 0 | 60.24 | 0 |  | Sutton | Val Verde | Tier 3 | 22RPG042 | 2022-12-02 | 2022-12-28 |  | 8259, 8261, 8991, 8998, 60412, 60440 | Y | N |  |  | 65562 | 52070
91896 | La Palma to Military Highway: Rebuild 138 kV Line | Rebuild the La Palma to Military Highway 138 kV line |  | La Palma | Military Highway | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025011 | 2028-05-31 |  | 138 | 0 | 22.2 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 8314, 8339, 80229 | Y |  |  |  | 91897 | 91896
93224 | Eastpoint: Construct New Distribution Station | Construct new distribution station on the North Laredo Switch to Wormser Road 138 kV line between Gateway West Tap and Unitec |  | Eastpoint |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-05-31 |  | 138 | 7.2 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8080, 8134, 8650 | Y |  |  |  | 93225 | 93224
91883 | La Palma to Stillman: Rebuild 138 kV Line | Rebuild the La Palma to Stillman 138 kV line |  | La Palma | Stillman | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025011 | 2028-05-31 |  | 138 | 0 | 22.3 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 8314, 8333, 79601 | Y |  |  |  | 91884 | 91883
100534 | Misty Substation Addition | LCRA TSC will construct a new load-serving Misty Substation cut-in to T185 Austrop - Zorn & T246 Lytton Springs - Zorn 345-kV double-circuit transmission line. |  | Misty |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8282 | 2028-05-31 |  | 345 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7040, 7042, 7051, 9074 | Y |  |  |  | 100535 | 100534
93250B | Utley_Substation_and_Transmission_Line_Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8065 | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 3 |  |  |  |  | 7310, 7316, 7327 | Y |  |  |  | 93252 | 93250
90025 | Festin: Construct New 345 kV Station | Interconnect Sunscape Renewable Solar and Storage to the new Festin 345 kV station on the Lon Hill to Reforzar 345 kV line |  | Festin |  | Planned |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2024111 | 2028-05-31 |  | 345 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8455, 80078, 80085 | Y |  |  |  | 90026 | 90025
86857 | Blessing: Install New 345 kV Cap Bank | Install new capacitor bank at the Blessing 345 kV station | In-Service Date Update | Blessing |  | Planned |  | AEP TCC | LaRissa Lundry deevans@aep.com 918-599-2938 | TP2023803 | 2028-05-31 |  | 345 | 0 | 0 | 0 | 0,130.9 | Matagorda |  | Tier 4 |  |  |  |  | 8123 | Y |  |  |  | 86858 | 86857
81238 | Zoisite: Construct New 345 kV Station and 345 kV Lines to STP | Interconnect the HIF load to the new Zoisite 345 kV station and construct two new STP to Zoisite 345 kV lines | In-Service Date Update | STP | Zoisite | Planned |  | AEP TCC | LaRissa Lundry deevans@aep.com 918-599-2938 | TP2023803 | 2028-05-31 |  | 345 | 1.6 | 0 | 0 | 0,261.8 | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5915, 8754 | Y |  |  |  | 81239 | 81238
99933 | La Plaza: Construct New Distribution Station | Construct new distribution station on the Polk Avenue to South McAllen 138 kV line between Hall Acres and South McAllen |  | La Plaza |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | DP25X0035 | 2028-05-31 |  | 138 | 0.6 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8371, 8760, 80300 | Y |  |  |  | 99934 | 99933
99274B | Cedar Bayou RPG - Substation Upgrades (25RPG014) | Replace existing Cedar Bayou parallel 345/138kV autotransformers 2A/2B with new 800 MVA autotransformer as CBY-A2. Remove existing 10-Ohm reactor from the 138kV side of the 2A/2B parallel autotransformers. Replace with 2.5-Ohm reactor in-series with new CBY-A2 on the 138kV side of the autotransformer. |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 345 | 0 | 0 | 0 |  | Chambers |  | Tier 3 | 25RPG014 | 2025-05-22 | 2025-06-13 | 2025-06-16 | 40000, 40005, 40015, 40030, 49006, 49007 | Y | N |  | Cost included in main entry | 99276 | 99274
99802 | Aetos: Construct New 138 kV Station | Interconnect Paradiso BESS to the new Aetos 138 kV station on the Big Foot to Pleasanton 138 kV line | Company Contact and In-Service Date Update | Aetos |  | Planned |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 | TP2025254 | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  |  | 8203, 8221, 80297 | Y |  |  |  | 99803 | 99802
98997 | Rebuild/reconductor Ckt.89A West Columbia to Damon and Ckt.89A Damon to Needville to increase thermal limits. Upgrade Ckt.89A West Columbia equipment to increase thermal limits. | Rebuild/reconductor Ckt.89A West Columbia to Damon (3.74 miles) and Ckt.89A Damon to Needville (10.1 miles) to increase thermal limits. Upgrade Ckt.89A West Columbia equipment to increase thermal limits. |  | West Columbia | Needville | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 13.84 | 0 |  | Brazoria | Brazoria | Tier 3 | 25RPG011 | 2025-05-05 | 2025-05-28 | 2025-05-28 | 42370, 42380, 43380, 49914 | Y | N |  | Cost included in main entry | 98998 | 98997
99274A | Cedar Bayou RPG - Substation Upgrades (25RPG014) | Replace existing 600 MVA 345/138kV Cedar Bayou Auto A1 with new 800 MVA autotransformer. Install 2.5-Ohm reactor in-series with new CBY-A1 on the 138kV side of the autotransformer. |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 345 | 0 | 0 | 200 |  | Chambers |  | Tier 3 | 25RPG014 | 2025-05-22 | 2025-06-13 | 2025-06-16 | 40000, 40010, 40040, 49005 | Y | N |  |  | 99275 | 99274
92734 | Construct Clearfork - Border - Drill Hole 345 kV DCKT Line | Construct Clearfork - Border - Drill Hole 345 kV DCKT Line |  | Clearfork | Drill Hole | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8792 R8802 R8803 | 2028-06-01 |  | 345 | 196.8 | 0 | 0 |  | Andrews | Culberson | Tier 1 | 24RPG015 | 2024-05-17 | 2025-06-26 |  | 10073, 18718, 23876 | Y |  |  |  | 92735 | 92734
99022 | Border - Quarry Field 345 kV double-circuit line | Add Permian Basin Reliability Plan Upgrade ID L2C Add a new Border - Quarry Field 345-kV double-circuit line |  | Border | Quarry Field | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L2_C | 2028-06-01 |  | 345 | 23.6 | 0 | 0 |  | Loving | Loving | Tier 2 |  |  |  |  | 11188, 18718 | Y |  |  |  | 99023 | 99022
86240 | AEN_REPLACE_LYTTON__345kV_LYAT1_and_LYAT2_AUTOS_WITH__New_672_MVAs | Replace the two existing 345kV Lytton Autos with two new 672 MVA/345kV autos |  | Lytton 9074 | Lytton 9075 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-06-01 |  | 345 | 0 | 0 | 762 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 9074, 9075, 9078, 9081 | Y |  |  |  | 86241 | 86240
86315 | AEN_Barton_Vega_Ckt_928_Reconductor |  |  | 9158 | 9285 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9158, 9285 | Y |  |  |  | 86316 | 86315
99520 | Union (fka Sun) - Ranger Camp 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22B. Upgrade the existing Union (fka Sun) - Ranger Camp 138-kV line. |  | Union | Dermott | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_B | 2028-06-01 |  | 138 | 0 | 32.88 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  |  | 10050, 18555 | Y |  |  |  | 99521 | 99520
100672 | Install a 50MVAr Capacitor Bank at Castroville Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5083 | Y |  |  |  | 100673 | 100672
100678 | Install a 50MVAr Capacitor Bank at Fratt Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5165 | Y |  |  |  | 100679 | 100678
100647 | Install a 50MVAr Capacitor Bank at Anderson Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5003 | Y |  |  |  | 100648 | 100647
100689 | Install a 50MVAr Capacitor Bank at Hill Country Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5210 | Y |  |  |  | 100690 | 100689
100691 | Install a 50MVAr Capacitor Bank at Howard Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5230 | Y |  |  |  | 100692 | 100691
100684 | Install a 50MVAr Capacitor Bank at Grissom Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5185 | Y |  |  |  | 100685 | 100684
100670 | Install a 50MVAr Capacitor Bank at Cagnon Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5055 | Y |  |  |  | 100671 | 100670
100693 | Install a 35.72MVAr Capacitor Bank at Legend Falls Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5259 | Y |  |  |  | 100694 | 100693
100698 | Install a 35.72MVAr Capacitor Bank at Potranco Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5346 | Y |  |  |  | 100699 | 100698
100700 | Install a 28.57MVAr Capacitor Bank at Ranchtown Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5358 | Y |  |  |  | 100701 | 100700
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 3000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2028-06-01 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 9723 | 2443
71408 | Upgrade CKT943 to 3000 amperes | Replace existing 2-795ACSR conductors with 2-795 ACSS conductors and the upgrade the terminal equipment to 3000 amperes. |  | Lytton Springs | Pilot Knob | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-06-01 |  | 138 | 0 | 11.13 | 0 |  | Caldwell | Travis | Tier 4 |  |  |  |  | 9075, 9259 | Y |  |  |  | 71409 | 71408
99516 | Upgrading line to bundled drake | [6 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70524, 70525 | Y |  |  |  | 99517 | 99516
91621 | Adding Highway 71 between Wirtz and Johnson city | Adding highway 71 into the model Summer 2028 | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7104, 70003, 70516 | Y |  |  |  | 91622 | 91621
86838 | AEN_JustinLane_KoenigLane_Ckt__conversion_to_138kV | Justin Lane Koenig Lane convert to 138kV |  | 9225 | 9227 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9225, 9227 | Y |  |  |  | 86839 | 86838
99825 | Boykin: Construct New 345 kV Station | Interconnect data center load to the new Boykin 345 kV station on the Tesla to Tule Canyon 345 kV line | Project Title, Project Description, Terminal, Transmission Status, Transmission Owner Project Number, In-Service Date, Dollars, and Reactive Capacity Update |  |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2025947 | 2028-06-30 |  | 345 | 0.2 | 0 | 0 | 0,225 | Hall |  | Tier 4 |  |  |  |  | 60501, 60518, 79002, 79004, 79010 | Y |  |  |  | 99826 | 99825
91386 | Smithville_Substation_Upgrade | Increase the reliability of the Smithville substation by replacing assets identified as a high failure risk, removing the 138x69-kV auto transformer, and converting T344 New Rosanky - Smithville to 138-kV |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7727 | 2028-06-30 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7314, 7315, 7558 | Y |  |  |  | 91387 | 91386
100108 | Weil Tract: Expand 138 kV Station | Interconnect data center load to the existing Weil Tract 138 kV station |  |  |  | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2028-06-30 |  | 138 | 0 | 0 | 0 | 0,57.6 | Nueces |  | Tier 4 |  |  |  |  | 8482 | Y |  |  |  | 100109 | 100108
59086 | Corichi to Victoria: Rebuild 138 kV Line | Rebuild the Corichi to Victoria 138 kV line | Company Contact and In-Service Date Update | Corichi | Victoria | Planned |  | AEP TCC | Travis Coody deevans@aep.com 918-599-2938 | TP2020888 | 2028-08-31 |  | 138 | 0 | 42.76 | 0 |  | Jackson | Victoria | Tier 3 |  | 2022-02-22 | 2022-03-01 |  | 8118, 8172 | Y | N |  |  | 65585 | 59086
61224 | AEN_Decker_SH_ckt_1008__reconductor | Upgrade the 7.04 mile Decker to Sand Hill 138 kV transmission line (Ckt 1008) with bundled 795 ACSS Drake conductor rated for 3000 amps |  | Decker [9187] | Sandhill [9216] | Planned |  | AEN | Shirley Mathew shirley.mathew@austinener 512-322-6103 |  | 2028-09-01 |  | 138 | 0 | 7.04 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9187, 9216 | Y |  |  |  | 61225 | 61224
91615 |  |  |  | Concord | Crowley | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-09-01 |  | 138 | 0 | 9.3 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 394, 398, 399 | Y |  |  |  | 91616 | 91615
102685 | BEPC_TPIT102685_Add_Delia |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-09-01 |  | 69 | 1.5 | 0 | 0 | 0,10 | Limestone |  | Tier 4 |  |  |  |  | 107, 112, 186 | Y |  |  |  | 102686 | 102685
66492D | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Chico West - Chico City Services 69 kV Line |  | Chico City Services | Chico West | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3006 | 2028-09-15 |  | 69 | 0 | 6 | 0 |  | Jack | Jack | Tier 4 |  |  |  |  | 1553, 1554 | Y |  |  |  | 76368 | 66492
91545 | Birdhouse Substation Upgrade | Upgrade Birdhouse substation to provide a new POI for GVEC PWT. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | PLC-6656 | 2028-09-28 |  | 138 | 0 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  |  | 7255 | Y |  |  |  | 91546 | 91545
70630 | Ballinger to Santa Anna: Rebuild 69 kV line | Rebuild 69 kV line and rebuild taps on the Ballinger to Santa Anna 69 kV line. | Company Contact and In-Service Date Update | Ballinger | Santa Anna | Planned |  | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 | TA2021193 | 2028-09-30 |  | 69 | 0 | 0 | 0 |  | Runnels | Coleman | Tier 3 | 22RPG028 | 2022-08-01 | 2022-09-01 |  | 6329, 6338, 6341, 6342, 6343, 6344, 6345, 6346, 6349, 6353, 60019, 60024, 60029 | Y |  |  |  | 70664 | 70630
99644 | Victoria to Warburton: Rebuild 138 kV Line | Rebuild the Victoria to Warburton 138 kV line |  |  |  | Planned |  | AEP TCC | Charity Kreher deevans@aep.com 918-599-2938 | TA2022330 | 2028-09-30 |  | 138 | 0 | 14.64 | 0 |  | Victoria | Victoria | Tier 3 | 25RPG021 | 2025-06-27 | 2025-07-22 |  | 5607, 8172 | Y |  |  |  | 99645 | 99644
99111A | Loop new CEHE 138kV substation Persimmon (PER) into Ckt.04A Mustang Bayou to HUDSON to create new Ckt.04 Mustang Bayou to Persimmon to HUDSON. Install one generator lead from CEHE 138kV substation Persimmon (PER) to KINETIC (KIN) / Willow Beach Wind. | Loop new CEHE 138kV substation Persimmon (PER) into Ckt.04A Mustang Bayou to HUDSON to create new Ckt.04 Mustang Bayou to Persimmon to HUDSON. |  | Persimmon | Mustang Bayou/HUDSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-09-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42960, 43550, 111321 | Y | N |  | Cost included in main entry | 99112 | 99111
99111B | Loop new CEHE 138kV substation Persimmon (PER) into Ckt.04A Mustang Bayou to HUDSON to create new Ckt.04 Mustang Bayou to Persimmon to HUDSON. Install one generator lead from CEHE 138kV substation Persimmon (PER) to KINETIC (KIN) / Willow Beach Wind. | Install one generator lead from CEHE 138kV substation Persimmon (PER) to KINETIC (KIN) / Willow Beach Wind. |  | Persimmon | KINETIC | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-09-30 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | Cost included in main entry | 99113 | 99111
91483 | RCEC_Rand_Station | New REC station cutting into Ray Raymond to Explorer line and new 12.35 mile from new REC station to Rand |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2028-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 6802, 6833, 6906, 6907 | Y |  |  |  | 91484 | 91483
93831 | New substation to replace Loma Alta |  |  | Stillman, Waterport, and also future Nimzo Substations | Cipher (Loma Alta) | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2028-10-02 |  | 138 | 0 | 0 | 0 | 0,50 |  |  | Tier 3 |  |  |  |  | 5943, 5944, 5962, 59450, 59510, 59551, 79601 | Y |  |  |  | 93832 | 93831
99913 | Eagle Lake - El Campo Transmission Line Overhaul | Perform an overhaul on the 38.2 mile T548 Eagle Lake - El Campo (including all tap lines) 69-kV transmission line. Per LCRA TSC Transmission System Planning procedure, replacement structures will be capable of operating at 138-kV. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2028-10-24 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 3 |  |  |  |  | 8100, 8541, 78105, 78538, 78539, 78542, 78543 | Y |  |  |  | 99914 | 99913
76131 | Pendulo: Build New 345 kV terminal | Interconnect Inertia Solar and BESS 2 to the Pendulo 345 kV Station on the Clear Crossing to Smoky Hill line |  | Pendulo |  | Planned |  | ETT | Lance Price twang1@aep.com 918-599-2635 |  | 2028-10-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60507 | Y | N |  |  | 76132 | 76131
70673 | Clairmont Sun Oil Tap: Rebuild 69 kV Line | Rehab Clairmont Sun Oil Tap 69 kV Line |  | Clairmont | Sun Clairmont | Planned |  | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | TA2021233 | 2028-10-31 |  | 69 | 0 | 0 | 0 |  | Kent | Kent | Tier 4 |  |  |  |  | 6197, 6198 | Y |  |  |  | 70674 | 70673
91903 | Iowa: Construct New Distribution Station | Construct new distribution station on the Bates to Liston 138 kV line | Company Contact and In-Service Date Update | Iowa |  | Planned |  | AEP TCC | Jessica Huycke jlsolis@aep.com 361-881-5574 |  | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8392, 8394, 80180 | Y | N |  |  | 91904 | 91903
5889 | MIRAGE - 138kV Substation Removal | Remove 138kV MIRAGE customer-owned substation from CEHE service. |  | MIRAGE | MCCABE/BIMONT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40200, 40209, 42351, 42360 | N | N |  |  | 13606 | 5889
102774A | Twinwood (TWN) 138kV CEHE Substation RHEMAN (RHE) / Twinwood Solar (26INR0425) and Maderagemela BESS (26INR0426) | Install new Twinwood (TWN) 138kV Substation for generator interconnection to RHEMAN (RHE) / Twinwood Solar (26INR0425) and Maderagemela BESS (26INR0426). Loop into existing Ckt.25E to create new Ckt.25 Fulshear to Twinwood (new) to Twinwood (distribution loop) to Peters. |  | Twinwood(new) | Fulshear/Twinwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-11-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 | [5 empty] | Y | N |  |  | 102775 | 102774
55470 | Bison to Ozona: Rebuild 69 kV Line | Rehab 69 kV line from Bison to Ozona |  | Bison | Ozona | Planned | 1095 - 1273 | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 | 1863 | 2028-11-30 |  | 69 | 0 | 27 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  |  | 6549, 6560, 60395 | Y | N |  |  | 65570 | 55470
50876 | Victoria to Port Lavaca: Retire 69 kV Line | Retire 69 kV Line on Victoria to Port Lavaca |  | Port Lavaca | Victoria | Planned | 1054 - 1227 | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 | 3782 | 2028-11-30 |  | 69 | 0 | 29 | 0 |  | Calhoun | Victoria | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8135, 8136, 8169 | Y | N |  |  | 50877 | 50876
55617 | Campwood to New Barksdale: Rebuild 69 kV Line | Rebuild the Campwood to Rocksprings 69 kV line |  | Campwood | New Barksdale | Planned | 1102 - 1280 | AEP TCC/ETT | Greg Crane jlsolis@aep.com 361-881-5574 | 3820 | 2028-11-30 |  | 69 | 0 | 7.73 | 0 |  | Edwards | Edwards | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 8365, 8633 | Y |  |  |  | 65573 | 55617
90016 | Dupont Switch to Dupont PP1 Circuit 1: Rebuild 138 kV Line | Rebuild the Dupont Switch to Dupont PP1 Circuit 1 138 kV line | Company Contact and In-Service Date Update | Dupont Switch | Dupont PP1 | Planned |  | AEP TCC | Remington Hajdik deevans@aep.com 918-599-2938 | TP2024138 | 2028-11-30 |  | 138 | 0 | 1.46 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8422, 8817, 8819 | Y |  |  |  | 90017 | 90016
55605 | New Barksdale to Rocksprings: Rebuild 69 kV Line | Rebuild the Campwood to Rocksprings 69 kV line |  | New Barksdale | Rocksprings | Planned | 1102 - 1280 | AEP TCC/ETT | Greg Crane jlsolis@aep.com 361-881-5574 | 3819 | 2028-11-30 |  | 69 | 0 | 19.51 | 0 |  | Edwards | Edwards | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 8238, 8365 | Y |  |  |  | 65572 | 55605
69277 | Cangrejo to Carbide: Rebuild 138 kV Line | Rebuild 138 kV Line from Cangrejo to Carbide |  | Cangrejo | Carbide | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2028-11-30 |  | 138 | 0 | 11 | 0 |  | Calhoun | Calhoun | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8140, 8155, 8190, 8723 | Y |  |  |  | 69278 | 69277
78545 | Brookhollow to Cangrejo: Rebuild 69 kV Line | Rebuild 69 kV line from Brookhollow to Cangrejo |  | Brookhollow | Cangrejo | Planned |  | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 |  | 2028-11-30 |  | 69 | 0 | 2.15 | 0 |  | Calhoun | Calhoun | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8133, 8135, 8720, 8723, 8756, 88133 | Y |  |  |  | 78546 | 78545 | 2019-C2
90029 | Dupont Switch to Dupont PP1 Circuit 2: Rebuild 138 kV Line | Rebuild the Dupont Switch to Dupont PP1 Circuit 2 138 kV line | Company Contact and In-Service Date Update | Dupont Switch | Dupont PP1 | Planned |  | AEP TCC | Remington Hajdik deevans@aep.com 918-599-2938 | TP2024138 | 2028-11-30 |  | 138 | 0 | 1.52 | 0 |  | San Patricio | San Patricio | Tier 4 | [5 empty] | Y |  |  |  | 90030 | 90029
102774B | Twinwood (TWN) 138kV CEHE Substation RHEMAN (RHE) / Twinwood Solar (26INR0425) and Maderagemela BESS (26INR0426) | Install one generator lead from Twinwood (TWN) 138kV Substation to RHEMAN (RHE) / Twinwood Solar (26INR0425) and Maderagemela BESS (26INR0426) |  | Twinwood(new) | RHEMAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-11-30 00:01 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y | N |  | Cost included in main entry | 102776 | 102774
92278 | Faulkner 345kV - Part of Upgrade L5 2024 Permian Basin Study |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2028-12-01 |  | 345 | 79.28 | 0 | 1500 |  | Pecos | Reeves | Tier 1 |  |  |  |  | 38124, 38125, 38126, 38127, 60404 | Y |  |  |  | 92279 | 92278
99020 | Border 345/138 kV Switch and two new 345/138 kV Autotransformers | Add Permian Basin Reliability Plan Upgrade ID L2A Establish a new Border 345/138-kV substation and install two new 345/138-kV transformers |  | Border | Border | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L2_A_B | 2028-12-01 |  | 345 | 0 | 0 | 1200 | 75,0 | Loving | Loving | Tier 3 |  |  |  |  | 18672, 18718, 18720, 18721 | Y |  |  |  | 99021 | 99020
93088 | Cattleman - Champion Creek/Bitter Creek - Sweetwater East 345-kV Double-Circuit Line Rebuild 345 kV Double-Circuit Line Rebuild | LCRA and Oncor joint project to add L24A Upgrade the existing Cattleman - Champion Creek/Bitter Creek - Sweetwater East 345-kV double-circuit line |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L24_A | 2028-12-01 |  | 345 | 0 | 83.22 | 0 |  | Nolan | Mitchell | Tier 1 |  | 2023-09-29 |  |  | 1414, 10053, 10105, 11420, 71050 | Y |  |  |  | 99405 | 93088
99018 | Dry Lake 345/138 kV Switch (fka ONC900005_TAP 11610) and two new 345/138 kV autotransformers | Add Permian Basin Reliability Plan Upgrade ID L5B and L5E Establish a new ONC900005_TAP 345/138-kV substation and install two new 345/138-kV transformers and Add a new El Capitan - Dry Lake (fka 900005Tap) 345-kV double-circuit line |  | El Capitan | Dry Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L5_B_E | 2028-12-01 |  | 345 | 50 | 0 | 1200 | 75,0 | Culberson | Reeves | Tier 1 |  |  |  |  | 10179, 10180, 11082, 18723, 18724, 18725, 18726, 18732 | Y |  |  |  | 99019 | 99018
99513 | Dry Lake (fka 900005Tap) - Faulkner (TNMP) 345 kV double-circuit line | Joint Oncor and TNMP project to Add Permian Basin Reliability Plan Upgrade ID L5F Add a new 900005Tap - Faulkner 345-kV double-circuit line |  | Dry Lake (ONCOR) | Faulkner (TNMP) | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L5_F | 2028-12-01 |  | 345 | 63.36 | 0 | 0 |  | Reeves | Reeves | Tier 2 |  |  |  |  | 18723, 38125 | Y |  |  |  | 99514 | 99513
99479D | Snyder - China Grove 69 kV Loop Converstion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L23. Convert the existing Snyder - Scurry - China Grove and Snyder - Amoco Tap - China Grove 69-kV lines to 138-kV. This converts the Snyder - Scurry 69 kV Line into 138 kV and reterminates into the new Bluff Creek and Snyder 138 kV Switches. |  | Snyder | Bluff Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L23 | 2028-12-01 |  | 138 | 0 | 13.2 | 0 |  | Scurry | Scurry | Tier 1 |  |  |  |  | 1306, 1370, 1372, 10199, 10203, 10204, 10205 | Y |  |  |  | 99484 | 99479
99518 | Dry Lake (ONC900005_TAP 11610) - Faulkner (TNMP) 138 kV double-circuit line | Joint Oncor and TNMP project to Add Permian Basin Reliability Plan Upgrade ID L3 Connect new load buses to ONC900005_TAP (11610) and Faulkner and form a 138-kV double-circuit loop: 11610 - 900005 - 900111 - 900023 - 900012 - 900021 - 900038 - 38124 |  | Dry Lake (ONCOR) | FAULKNER (TNMP) | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L3_A | 2028-12-01 |  | 138 | 120 | 0 | 0 |  | Reeves | Reeves | Tier 2 |  |  |  |  | 18732, 38124 | Y |  |  |  | 99519 | 99518
98991A | Kinnebrew POI - Chalk 69 kV to 138 kV Line Conversion | Oncor's portion of the Permian Basin Reliability Plan Upgrade ID L27B. Convert the existing Chalk - Kinnebrew POI 69-kV line to 138-kV. |  | Kinnebrew | Chalk | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L27_B | 2028-12-01 |  | 138 | 13.6 | 0 | 0 |  | Sterling | Sterling | Tier 3 |  |  |  |  | 1333, 6641, 9429, 10189, 11352 | Y |  |  |  | 98993 | 98991
92911 | Adds Capacitor Bank at Wildhorse POD | Adds Capacitor Bank at Wildhorse POD |  | Wildhorse POD | Wildhorse POD | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8664 | 2028-12-06 | 2027-05-15 | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 1397 | Y |  |  |  | 92912 | 92911
102561 | BEPC_TPIT_FortGatesSW_FortGates |  |  | 250 | 254 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-12-08 |  | 69 | 0 | 2 | 0 |  | Coryell | Coryell | Tier 4 |  |  |  |  | 250, 254 | Y |  |  |  | 102562 | 102561
99605 | Establish Belltown 138 kV Switch | Establish Belltown 138 kV Switch |  | Belltown 138 kV Switch | Belltown 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6414 | 2028-12-15 |  | 138 | 0 | 0 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 3197, 3773, 3786 | Y |  |  |  | 99606 | 99605
100599 | Establish Hillsboro Switch 138/69 kV Auto #2 | Establish Hillsboro Switch 138/69 kV Auto #2 |  | Hillsboro 138 kV Switch | Hillsboro 69 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2028-12-15 |  | 138 | 0 | 0 | 104 |  | Hill | Hill | Tier 4 |  |  |  |  | 3522, 3523, 3814 | Y |  |  |  | 100600 | 100599
71910C | Rebuild the Hillsboro - Elm Mott 69 kV Line | Rebuild the Abbott - Hillsboro Switch 69 kV Line |  | Abbott 69 kV Substation | Hillsboro 69 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6221 | 2028-12-15 |  | 69 | 0 | 10.1 | 0 |  | Hill | Hill | Tier 3 |  |  |  |  | 3523, 3524, 3525, 13525 | Y |  |  |  | 91607 | 71910
92852B | Oncor_92852_MNE_Monticello_Paris_Line_Upgrade | Upgrade Woodard - Paris 345 kV Line |  | Woodard | Paris | Planned | R986 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R986 | 2028-12-15 |  | 345 | 0 | 16.8 | 0 |  | Lamar | Lamar | Tier 1 | 25RPG026 |  |  |  | 1692, 11699 | Y |  |  |  | 93064 | 92852
68700 | ONCOR_MNE_68700_Bonham - Toco Switch 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Bonham | Toco | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3016 | 2028-12-15 |  | 69 | 0 | 35 | 0 |  | Fannin | Lamar | Tier 4 |  |  |  |  | 1703, 1761, 1788, 1789, 1790, 11789 | Y |  |  |  | 68701 | 68700
85955 | Olmos to LaVernia TL, T533 | Olmos to LaVernia TL, Rebuild 5.1 miles of 69 kV line to 138 kV transmission line |  | Olmos | LaVernia | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2028-12-15 | 2958101 | 69 | 0 | 5.1 | 0 |  | Wilson | Wilson | Tier 4 | [5 empty] | Y |  |  |  | 85956 | 85955
99359 | Sweetwater Creek POI - Eskota 69 kV line and convert to 138 kV | Rebuild the Sweetwater Creek POI - Eskota 69 kV line and convert to 138 kV approved as part of the 24RPG040 Oncor Roscoe Area Upgrades Project. |  | Eskota | Oak Spring | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2028-12-15 |  | 138 | 0 | 24.6 | 0 |  | Nolan | Nolan | Tier 2 | 24RPG040 | 2024-12-23 | 2025-05-30 |  | 1339, 1340, 1406, 1407, 1408, 1409, 1413, 9451 | Y |  |  |  | 99360 | 99359
100157 | Construct the Teal - Pintail 138 kV DCKT Line | Construct the Teal - Pintail 138 kV DCKT Line |  | Teal | Pintail | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6366 | 2028-12-15 |  | 138 | 4.5 | 0 | 0 |  | Williamson | Williamson | Tier 2 |  |  |  |  | 3362, 3692 | Y |  |  |  | 100158 | 100157
99350 | Rebuild the Bell County East - Voss Lake 345 kV DCKT Line | Rebuild the Bell County East - Voss Lake 345 kV DCKT Line |  | Bell County East | Voss Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6401 | 2028-12-15 |  | 345 | 0 | 29.6 | 0 |  | Bell | Milam | Tier 1 |  |  |  |  | 3687, 3751, 3761 | Y |  |  |  | 99351 | 99350
99383 | Establish Tower 345 kV Switch | Establish Tower 345 kV Switch |  | Tower | Tower | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6454 | 2028-12-15 |  | 345 | 1.2 | 0 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3413, 3414, 3699, 3780 | Y |  |  |  | 99384 | 99383
87703 | Belton - Killeen 138 kV Line via Nolanville | Reconductor the Belton - Killeen 138 kV Line via Nolanville |  | Belton | Killeen | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6347 | 2028-12-15 |  | 138 | 0 | 24.8 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3366, 3423, 3429, 3444, 3610, 3616, 3617, 3618, 3619, 13426, 13427 | Y |  |  |  | 87704 | 87703 | 2023-NC22, 2023-NC36, 2023-NC50
87699 | Belton - Killeen 138 kV Line via Belton Southwest | Upgrade Belton - Killeen 138 kV Line via Belton Southwest |  | Belton | Killeen | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R902 | 2028-12-15 |  | 138 | 0 | 17.2 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3423, 3610, 3633, 3776, 13610 | Y |  |  |  | 87700 | 87699 | 2023-NC36
87711 | Watercrest - Killeen 138 kV Line | Upgrade the Watercrest - Killeen 138 kV Line |  | Watercrest | Killeen | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6355 | 2028-12-15 |  | 138 | 0 | 7 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3423, 3428, 13628 | Y |  |  |  | 87712 | 87711
81296A | Prong Moss – Rockhound 345 kV Line Rebuild | Prong Moss – Rockhound 345 kV Line Rebuild |  | Prong Moss | Rockhound | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2028-12-15 |  | 345 | 0 | 60.2 | 0 |  | Midland | Howard | Tier 1 | 23RPG029 |  |  |  | 10057, 10062 | Y |  |  |  | 81297 | 81296
99361 | Permian Basin Reliability Plan Upgrade ID L25C | Add Permian Basin Reliability Plan Upgrade ID L25C. Convert the existing Plowboy - Eskota 69-kV line to 138-Kv. Move the Eskota 138/69-kV transformer 1 to Plowboy. Rebuild the Eskota 138/69 kV Switch approved as part of the part of Permian Basin Reliability Plan Upgrade ID L25C. Required to convert the existing Plowboy - Eskota 69-kV line to 138-Kv |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8805 R8806 R8823 | 2028-12-15 |  | 138 | 0 | 10.88 | 0 |  |  |  | Tier 3 |  |  |  |  | 1339, 1340, 1380, 1381, 1382, 1384, 1386, 1387, 1409, 10091, 10103, 10198, 11341, 11384, 76319, 180052, 180054 | Y |  |  |  | 99404 | 99361
99239A | Establish Muscovy 345/138 kV Switch | Establish the Muscovy 345/138 kV Switch |  | Muscovy | Muscovy | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6212, R6342, R6362 | 2028-12-15 |  | 345 | 0 | 0 | 700 |  | Williamson | Williamson | Tier 1 |  |  |  |  | 3673, 3692, 3700, 3787, 13673, 13692, 13695 | Y |  |  |  | 99240 | 99239
100159 | Establish Teal East 138 kV Switch for a customer POD | Establish Teal East 138 kV Switch for a customer POD |  | Teal East | Teal East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6477 | 2028-12-16 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3362, 3692, 3784 | Y |  |  |  | 100160 | 100159
99239C | Establish Muscovy 345/138 kV Switch | Construct the Muscovy - Limmer (LCRA TSC) 345 kV Double-Circuit Line |  | Muscovy | Limmer (LCRA TSC) | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6212, R6342, R6362 | 2028-12-16 |  | 345 | 4 | 0 | 0 |  | Williamson | Williamson | Tier 1 |  |  |  |  | 3700, 7341 | Y |  |  |  | 99268 | 99239
99387 | Rebuild the Tower - Salado 345 kV DCKT Line | Rebuild the Tower - Salado 345 kV DCKT Line |  | Tower | Salado | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6358 | 2028-12-16 |  | 345 | 0 | 12.4 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3699, 3780 | Y |  |  |  | 99388 | 99387
99389 | Rebuild the Tower - Temple 345 kV DCKT Line | Rebuild the Tower - Temple 345 kV DCKT Line |  | Tower | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6402 | 2028-12-16 |  | 345 | 0 | 2.9 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3414, 3780 | Y |  |  |  | 99390 | 99389
87648 | Carver to Poblano: Convert 69 kV Line to 138 kV | Convert the Sonora to Uvalde 69 kV line to 138 kV and reterminate at Carver and Poblano |  | Carver | Poblano | Planned |  | AEP TCC/AEP TNC, ETT | Charity Kreher deevans@aep.com 918-599-2938 | TP2024058 | 2028-12-29 |  | 138 | 1 | 107.5 | 0 |  | Sutton | Uvalde | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 6513, 6570, 8009, 8230, 8231, 8238, 8365, 8633, 60039, 60119, 60120, 60121, 60210, 60412, 80073, 80074, 80075, 80081 | Y | Y |  |  | 87649 | 87648
80373 |  |  |  | IOLA | CRUTCHFIELD | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-12-29 |  | 138 | 0 | 5.5 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 4, 8 | Y |  |  |  | 80374 | 80373
91623 |  |  |  | Lillian | Highpoint | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-12-29 |  | 138 |  | 5.5 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 419, 439 | Y |  |  |  | 91624 | 91623
85953 | Camp Wood - Leakey Transmission Line Conversion | LCRATSC will perform a voltage conversion on Camp Wood – Leakey (T269) 69-kV transmission line. This project will increase the reliability of transmission facilities by converting the substation equipment at Camp Wood and Leakey substation to operate at 138-kV. |  | Bandera 7438 | Leakey 7426 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-12-30 | 2958101 | 138 | 0 | 0 | 0 |  | Bandera | Real | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 7426, 7428, 7438, 7439, 7440, 8633, 80074 | Y |  |  |  | 87789 | 85953 | 2023-W14
81783 | Ingleside to Seabird: Construct New 138 kV Line | Interconnect the Mu load to the new Seabird 138 kV station on the Homeport to Ingleside 138 kV line, construct a new 138 kV line from Ingleside to Seabird, and add capacitors |  | Ingleside | Seabird | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2028-12-31 |  | 138 | 2.9 | 0 | 0 | 0,69.1 | San Patricio | Nueces | Tier 4 |  |  |  |  | 8425, 8808, 84250 | Y | N |  |  | 81784 | 81783
81724 | Calabaza: Construct New 138 kV Station | Interconnect the Omicron load to the new Calabaza 138 kV station on the Gila to Tortuga and Nueces Bay to Saxet 138 kV lines |  | Calabaza |  | Conceptual |  | AEP TCC/LCRA | Doug Evans deevans@aep.com 918-599-2938 |  | 2028-12-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8168, 8441, 78568, 80260, 80380 | Y |  |  |  | 81725 | 81724
59394 | Pointer to Rule: Rebuild 69 kV Line | Rehab the Pointer to Rule 69 kV Line |  | Pointer | Rule | Planned | 1122 - 1300 | AEP TNC | Sally Matthews myturner@aep.com 918-599-2437 | 1867 | 2028-12-31 |  | 69 | 0 | 14.78 | 0 |  | Haskell | Knox | Tier 4 |  |  |  |  | 763, 6014, 6115, 6120, 60346 | Y | N |  |  | 59395 | 59394
55217 | Putnam to Leon: Rebuild 138 kV line | Rehab the Putnam to Leon (Oncor) 138 kV line |  | Putnam | Leon | Planned | 1042 - 1269 | AEP TNC | LaRissa Lundry twang1@aep.com 918-599-2635 | 1859 | 2028-12-31 |  | 138 | 0 | 20.81 | 0 |  | Callahan | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | N |  |  | 55218 | 55217
91487A | Austrop - Sim Gideon Transmission Line Upgrade |  |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8100 | 2028-12-31 |  | 138 | 0 | 0 | 0 |  | Travis | Bastrop | Tier 4 |  |  |  |  | 7310, 7322, 7327, 7328, 7329, 9328 | Y |  |  |  | 91488 | 91487
45566 | Holly to Southside: Upgrade 138 kV Line | Upgrade the Holly to Southside 138 kV line | Company Contact and In-Service Date Update | Holly | Southside | Planned | 994 - 1172 | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | 3747 TP-2019-065 | 2028-12-31 |  | 138 | 0 | 1.8 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486 | Y | N |  |  | 65532 | 45566
76696 | Border - Shifting Sands 138 kV Line and add Wink - Shifting Sands 138 kV second circuit | Add Permian Basin Reliability Plan Upgrade ID L1B and L1C Construct a new Border – Shifting Sands 138 kV Line and Add Wink - Shifting Sands 138-kV second circuit |  | Atchison | Wink | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8628 | 2028-12-31 |  | 138 | 64.6 | 0 | 0 |  | Loving | Winkler | Tier 2 |  |  |  |  | 1074, 10157, 11089, 11391, 18672, 18705 | Y |  |  |  | 102819 | 76696
99122 | Drill Hole 765/345 kV Autotransformer #1 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1C. Establish the Drill Hole 765/345 kV Switch with one 765/345 kV autotransformer |  | Drill Hole | Drill Hole | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_C | 2028-12-31 |  | 765 | 0 | 0 | 2250 | -675,0 | Culberson | Culberson | Tier 1 |  |  |  |  | 10073, 18733, 18734 | Y |  |  |  | 99123 | 99122
99126 | Drill Hole - Longshore 765 kV Line | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1E. Add a new Longshore – Drill Hole 765-kV single-circuit line |  | Drill Hole | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_E | 2028-12-31 |  | 765 | 184.8 | 0 | 0 |  | Culberson | Howard | Tier 1 |  |  |  |  | 18112, 18733 | Y |  |  |  | 99127 | 99126
87092 | Arcadia to Southside: Upgrade 138 kV Line | Upgrade the Arcadia to Southside 138 kV line | Company Contact and In-Service Date Update | Arcadia | Southside | Planned | 994 - 1172 | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | 3747 TP-2019-065 | 2028-12-31 |  | 138 | 0 | 2.59 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486, 8496, 8609, 8617, 8618 | Y | N |  |  | 87093 | 87092
99922 | Green Valley Substation Addition | Provide a transmission point of interconnection at the new Green Valley Substation. A new GVEC customer has requested 500 MW of load on LCRA TSC-owned 345-kV double-circuit line, T248 Marion -Zorn and T419 Clear Springs - Marion. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-762-3658 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  | Guadalupe |  | Tier 1 |  |  |  |  | 7044, 7050, 7052, 7054 | Y |  |  |  | 99923 | 99922
99823 | LCRATSC_Flatonia-Luling_Transmission_Line_Conversion | LCRA TSC will upgrade terminal facilities at Luling, Harwood, Bluestem, Thompsonville, Waelder, and Flatonia substations along the Flatonia - Luling 69-kV transmission line to operate at 138-kV. |  | 7248 Flatonia | 7224 Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-12-31 |  | 138 | 0 | 0 | 0 |  | Fayette | Caldwell | Tier 4 |  |  |  |  | 7223, 7224, 7230, 7231, 7232, 7247, 7248, 7895, 7896 | Y |  |  |  | 99824 | 99823
99928 | Three Lakes Substation Addition | Provide a transmission point of interconnection at the new Three Lakes Substation. A new PEC customer has requested 800 MW of load on LCRA TSC-owned 345-kV T775 John Dumas - Hornsby |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  | Caldwell |  | Tier 1 |  |  |  |  | 7041, 7047, 7059 | Y |  |  |  | 99929 | 99928
99124 | Longshore 765/345 kV Autotransformer #1 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1B. Establish the Longshore 765/345 kV Switch with one 765/345 kV autotransformer |  | Longshore | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_B | 2028-12-31 |  | 765 | 0 | 0 | 2250 | -675,0 | Howard | Howard | Tier 1 |  |  |  |  | 1058, 18112, 18113 | Y |  |  |  | 99125 | 99124
81659 | Lytle: Construct New 138 kV Terminal | Interconnect the Cinco II load to the existing Lytle 138 kV station and add capacitors |  | Lytle |  | Conceptual |  | AEP TCC/ETT | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-12-31 |  | 138 | 0 | 0 | 0 | 0,34.5 | Medina |  | Tier 4 |  |  |  |  | 8962 | Y |  |  |  | 81660 | 81659
87901 | Kallisto: Construct New 138 kV Station | Interconnect the Beta load to the new Kallisto 138 kV station on the Falfurrias to King Ranch Gas Plant 138 kV line |  | Kallisto |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-12-31 |  | 138 | 0 | 0 | 0 |  | Kleberg |  | Tier 4 |  |  |  |  | 80228 | Y |  |  |  | 87902 | 87901
91487B | Austrop - Sim Gideon Transmission Line Upgrade |  |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8100 | 2029-01-01 |  | 138 | 0 | 0 | 0 |  | Travis | Bastrop | Tier 4 |  |  |  |  | 7310, 7316, 7320, 7327, 7329 | Y |  |  |  | 93482 | 91487
80330 |  |  |  | DWU Southside | McCree | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-01-05 |  | 69 | 0 | 7.45 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 230, 832 | Y |  |  |  | 80331 | 80330 | 2023-NC24
80334 |  |  |  | CONCORD | WILDCAT TAP | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-01-05 |  | 138 | 0 | 4.9 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 388, 394 | Y |  |  |  | 80335 | 80334 | 2023-NC25
91937 | Cryo to Faulkner: Construct New 138 kV Line | Construct a new 138 kV single circuit line from Cryo to Faulkner |  | Cryo | Faulkner | Planned |  | AEP TNC/TNMP | Mina Turner myturner@aep.com 918-599-2437 | TP2025146 | 2029-01-31 |  | 138 | 11.5 | 0 | 0 |  | Reeves | Reeves | Tier 2 | [5 empty] | Y | N |  |  | 91938 | 91937
76133 | West Childress: Station Rehab | Rehab the West Childress station |  | West Childress |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2020223 | 2029-01-31 |  | 138 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 6030, 6135 | Y | N |  |  | 76134 | 76133
99726 | Dulce: Construct New 345 kV Station | Interconnect Iguala Solar to the new Dulce 345 kV station on the Static to STP 345 kV line |  | Dulce |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2025344 | 2029-01-31 |  | 345 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 5915, 8676, 80286 | Y |  |  |  | 99727 | 99726
73116 | Install new Cedar Port Mobile (CDM) 138kV Distribution Substation | Install new Cedar Port Mobile (CDM) 138kV Distribution Substation. Loop from existing Ckt.03B to create new Ckt.03B Trinity Bay to Cedar Port Mobile to KENNY tap. |  | Cedar Port Mobile | Trinity | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-01-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40921, 41610, 48360 | N | N |  |  | 73120 | 73116
72502 | Tarpley Substation Upgrade | Provide transmission point of interconnection to Battery energy storage system near the Tarpley Substation. Add a 138kV bay and associated circuit breaker to existing substation (25INR0196) |  | Tarpley |  | Planned |  | BEC | Jhonatan Guerrero Rivera j.rivera@banderaelectric. 830-612-0048 |  | 2029-02-28 |  | 138 | 0.1 | 0 | 0 |  | Bandera |  | Tier 4 | [5 empty] | Y | N |  |  | 72503 | 72502
99629 | BEPC_TPIT_HAMILTONGTC_GUSTINETOINDIANGAP |  |  | Gustine | Indian Gap | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-01 |  | 69 | 0 | 12.8 | 0 |  | Comanche | Hamilton | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 262, 265, 268, 269, 273 | Y |  |  |  | 99630 | 99629
99639 | BEPC_TPIT_HAMILTONGTC_PancakeSyrup |  |  | Pancake | Pancake | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-15 |  | 138 | 0 | 0 | 200 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 158, 159 | Y |  |  |  | 99640 | 99639
99652 | BEPC_TPIT_HAMILTONGTC_Energize_Odell |  |  | Hasse | Odell | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-22 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 273, 277, 278, 33273 | Y |  |  |  | 99653 | 99652
99674 | BEPC_TPIT_HAMILTONGTC_Energize_IndianGap |  |  | Odell | Indian Gap | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-29 |  | 138 | 0 | 0 | 0 |  | Comanche | Hamilton | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 262, 268, 273, 33262, 33273 | Y |  |  |  | 99675 | 99674
91562 |  |  |  | Gainesville | Sivells Bend | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-01 |  | 138 | 0 | 7.3 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 716, 719, 721, 725, 726, 727, 735, 11722, 33726 | Y |  |  |  | 91563 | 91562
102667 | BEPC_TPIT102667_Bream |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-02 |  | 138 | 0 | 0 | 0 |  | Robertson |  | Tier 4 |  |  |  |  | 26, 30, 32, 37, 79, 3707 | Y |  |  |  | 102669 | 102667
99679 | BEPC_TPIT_HAMILTONGTC_Energize_Waring |  |  | Indian Gap | Waring | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-05 |  | 138 | 0 | 0 | 0 |  | Hamilton | Comanche | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 268, 269, 273, 33262, 33268, 33273 | Y |  |  |  | 99680 | 99679
99683 | BEPC_TPIT_HAMILTONGTC_Energize_Gustine |  |  | Odell | Gustine | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-12 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 272, 273, 33263 | Y |  |  |  | 99684 | 99683
99689 | BEPC_TPIT_HAMILTONGTC_Energize_Resley |  |  | Gustine | Resley | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-19 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 178, 272, 33263, 199942 | Y |  |  |  | 99690 | 99689
99691 | BEPC_TPIT_HAMILTONGTC_Energize_Potsville |  |  | Resley | Potsville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-26 |  | 138 | 0 | 0 | 0 |  | Comanche | Hamilton | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 178, 258, 272, 151971, 151973 | Y |  |  |  | 99692 | 99691
86884 | Saragosa: Construct New 138 kV Terminal | Interconnect Bracero Pecan Storage to the Saragosa 138 kV station | Company Contact and In-Service Date Update | Saragosa | Bracero Pecan | Planned | TP2024091 | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 |  | 2029-04-30 |  | 138 | 0.5 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  | 2024-03-21 | 2024-04-12 |  | 60716 | Y | N |  |  | 86885 | 86884
93226 | Fort Stockton Switch: Expand 345 kV Station | Install three 345/138 kV autotransformers at the Fort Stockton Switch 345/138 kV station | In-Service Date Update | Fort Stockton Switch |  | Planned |  | AEP TNC | Brooks Dow myturner@aep.com 918-599-2437 | TP2025141 | 2029-04-30 |  | 345 | 0 | 0 | 2250 |  | Pecos |  | Tier 1 |  |  |  |  | 60146, 60147, 60148, 60149, 60152, 60153, 60404, 60717, 76002, 78926 | Y |  |  |  | 93227 | 93226
91567 |  |  |  | New station Rhew | New station Rhew | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-01 |  | 345 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 3, 5133, 5901 | Y |  |  |  | 91568 | 91567
99549 | Long Creek - Sweetwater East 345 kV Double Circuit Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L24B. Upgrade the existing Long Creek - Mulberry Creek (Oncor) - Sweetwater East 345-kV double-circuit line |  | Sweetwater East | Long Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L24_B | 2029-05-01 |  | 345 | 0 | 84.6 | 0 |  | Nolan | Shackelford | Tier 1 |  |  |  |  | 1435, 1459, 11420 | Y |  |  |  | 99550 | 99549
90000 | Upgrade San Diego - Orange Grove SW | Upgrade San Diego - Orange Grove SW to 795 ACSR. 2024 RTP |  | San Diego | Orange Grove SW | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-05-01 |  | 69 | 0 | 21.56 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5654, 5658 | Y |  |  |  | 90001 | 90000
99693 | BEPC_TPIT_HAMILTONGTC_Energize_HamiltonSyrup |  |  | Potsville | Syrup | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-03 |  | 138 | 0 | 0 | 0 |  | Hamilton | Cooke | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 158, 159, 178, 258, 33258 | Y |  |  |  | 99694 | 99693
99718 | BEPC_TPIT_HAMILTONGTC_Energize_Gatesville |  |  | Syrup | Gatesville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-10 |  | 138 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 157, 158, 159, 250, 33157 | Y |  |  |  | 99719 | 99718
99318 | Clearfork - Lamesa 345 kV Double Circuit Line | Construct Clearfork - Lamesa 345 kV DCKT Line approved as part of 24RPG015 |  | Clearfork 345 kV Switch | Lamesa 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8792 | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Andrews | Dawson | Tier 1 | 24RPG015 | 2024-05-02 |  |  | 10082, 23876 | Y |  |  |  | 99319 | 99318
99524 | Upgrading line | Upgrade conductor to 1xSuwannee | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70489, 70491 | Y |  |  |  | 99525 | 99524
93306 | Bastrop_Mesquite_Utley_Transmission_Line_Addition | Provide looped transmission service for BBEC-member load at 138-kV Utley Substation |  | 7320 | 7317 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 3 |  |  |  |  | 7317, 7320 | Y |  |  |  | 93307 | 93306
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0385 | 2029-05-15 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5250, 5395, 5416 | Y | N |  | There are no transformers associated with this project | 10365 | 3021
99417 | Establish Lamesa 345/138 kV Switch | Construct Lamesa 345/138 kV Switch approved as part of 24RPG015 |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8800 | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Dawson | Dawson | Tier 1 | 24RPG015 | 2024-05-02 |  |  | 1163, 10082, 10083, 10084 | Y |  |  |  | 99418 | 99417
99243 | Big Spring - Signal Mountain 69 kV Conversion to 138 kV | Add Permian Basin Reliability Plan Upgrade ID L20E and L20F. Convert the existing Big Spring - Signal Mountain 69-kV line to 138-kV. Connect Signal Mountain to Prong Moss. |  | Big Spring | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L20_E_F | 2029-05-15 |  |  | 0 | 8.7 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 1322, 1323, 1351, 1353, 10066, 10190 | Y |  |  |  | 99244 | 99243
81296B | Prong Moss – Rockhound 345 kV Line Rebuild | Prong Moss – Rockhound 345 kV Second Circuit Addition |  | Prong Moss | Rockhound | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2029-05-15 |  | 345 | 0 | 60.2 | 0 |  | Midland | Howard | Tier 1 | 23RPG029 |  |  |  | 10057, 10062 | Y |  |  |  | 102848 | 81296
91312C | Austrop - Zorn Transmission Line Upgrade | Upgrade the existing Austrop - Zorn 345-kV double-circuit transmission line between Lytton Springs and Zorn substations to achieve a higher operational rating |  | 9074 | 7042 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8063, PLC-8139, PLC-8140 | 2029-05-15 |  | 345 | 0 | 46.2 | 0 |  | Caldwell | Guadalupe | Tier 1 |  |  |  |  | 7040, 7042, 7051, 9074 | Y |  |  |  | 91315 | 91312 | 2024-SC19
99239B | Establish Muscovy 345/138 kV Switch | Construct the Muscovy - Voss Lake 345 kV Double-Circuit Line |  | Muscovy | Voss Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6212, R6342, R6362 | 2029-05-15 |  | 345 | 30 | 0 | 0 |  | Williamson | Milam | Tier 1 |  |  |  |  | 3700, 3751 | Y |  |  |  | 99265 | 99239
81551 | Dos Rios 138 kV Switch | Establish Dos Rios 138 kV Switch |  | Dos Rios Switch | Dos Rios Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6231 | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 32, 3707, 3725 | Y |  |  |  | 81552 | 81551
92874 | Oncor_MNE_92874_Bear_Pen 345 kV Switch | Establish Bear pen 345 kV Switch |  | Bear Pen 345 kV Switch |  | Planned |  | ONCOR | Zagros Shahooei | M3063 | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Franklin | Franklin | Tier 4 |  |  |  |  | 1695, 2449, 11702 | Y |  |  |  | 92875 | 92874
99831 | LCRATSC_Cedar_Hill_Manor_Transmission_Line_Upgrade | LCRA TSC will upgrade T495 Cedar Hill - Manor 138-kV transmission line to achieve a higher operational rating. |  | 7330 Manor | 7331 Cedar Hill | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2029-05-15 |  | 138 | 0 | 8.2 | 0 |  | Travis | Bastrop | Tier 3 |  |  |  |  | 7330, 7331 | Y |  |  |  | 99832 | 99831
66023 | T340 T-Line Upgrade | Upgrading the Marion to Sheriff's Posse Transmission Line T340 from 795 ACSR to 959 ACSS conductor. Upgrades to conductor and structures are included. Structures designed for ultimate build-out of double-circuit bundled 959 ACSS in preparation for additional future capacity. | Contracting has taken longer than originally expected. | Marion | Sheriff's Posse | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2029-05-15 |  | 138 | 0 | 3.4 | 0 |  | Guadalupe | Comal | Tier 4 |  |  |  |  | 7178, 7460 | Y | N |  |  | 78403 | 66023
99419 | Lamesa - Faraday 345 kV Double Circuit Line | Oncor and WETT joint project to construct the Lamesa (Oncor) - Faraday (WETT) 345 kV DCKT Line approved as part of 24RPG015 |  | Lamesa | Faraday | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8792 | 2029-05-15 |  | 345 | 154 | 0 | 0 |  | Dawson | Borden | Tier 1 | 24RPG015 | 2024-05-02 |  |  | 10082, 59905 | Y |  |  |  | 99420 | 99419
100165 | Gristmill_Substation_Addition | LCRA TSC will construct a new Gristmill Substation to provide transformation service to a PEC-member load |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 3 |  |  |  |  | 7174, 7180, 7181, 7182 | Y |  |  |  | 100259 | 100165
99720 | BEPC_TPIT_HAMILTONGTC_Energize_FortGates |  |  | Gatesville | Fort Gates | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-17 |  | 138 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 149, 250, 254, 33157, 33254 | Y |  |  |  | 99721 | 99720
99722 | BEPC_TPIT_HAMILTONGTC_Energize_Snelling |  |  | Fort Gates | Snelling | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-24 |  | 138 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 149, 33254, 33266, 33267 | Y |  |  |  | 99723 | 99722
93661 | New BPUB substation needed to service new load. Will require 6 miles of 138kV transmission line. |  |  | Nimzo | DEMETER | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2029-05-29 |  | 138 | 12 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 59551, 59555 | Y |  |  |  | 93662 | 93661
72051 | Twinwood Mobile (TWM) 138kV Distribution Substation | Install new Twinwood Mobile (TWM) 138kV Distribution Substation. Loop from existing Ckt.25E to create new Ckt.25E Foster to Twinwood Mobile to Peters |  | Twinwood | Foster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44256, 44861, 46220 | N | N |  |  | 72052 | 72051
70796 | El Campo to Corichi: Rebuild 138 kV Line | Rehab the El Campo to Corichi 138 kV line |  | El Campo | Corichi | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TA2018020 | 2029-05-31 |  | 138 | 0 | 13.26 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8099, 8102 | Y |  |  |  | 70797 | 70796
93134 | Minnesota: Construct New Distribution Station | Construct new distribution station on the North Edinburg to Pharr 138 kV line between McColl Road and Pharr |  | Minnesota |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8085, 8372, 8908 | Y |  |  |  | 93135 | 93134
90027 | Cross Plains to Rising Star: Rebuild 69 kV Line | Rehab the Cross Plains to Rising Star 69 kV line | Company Contact and In-Service Date Update | Cross Plains | Rising Star | Planned | TA2024101 | AEP TNC | Craig Tabor myturner@aep.com 918-599-2437 |  | 2029-05-31 |  | 69 | 0 | 12.96 | 0 |  | Callahan | Eastland | Tier 4 |  |  |  |  | 6357, 6358 | Y | N |  |  | 92899 | 90027
60522 | Rebuild Hidden Lakes-League City with 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  |  | 60523 | 60522
60526 | Rebuild West Columbia Local-Angleton with 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39530, 39560 | Y |  |  |  | 60527 | 60526
54120 | Rebuild Tejas-Commanche (Bundled 795 ACSS) | Rebuild Tejas - Commanche 138 kV line with Bundled 795 ACSS conductor. |  | Tejas 138 kV Substation (Bus # 38530) | Commanche 138 kV Substation (Bus # 38560) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | STE07318 | 2029-05-31 |  | 138 | 0 | 0.95 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38530, 38560 | Y |  |  |  | 54121 | 54120
93217 | Update Topology in Brownsville Area per Approved RPG Project | Adding in 345 kV topology for LRGV Brownsville area (new 345 kV Chalybe station with two (2) 675 MVA autos being fed from Sharyland's Kingfisher and Palmito stations) per the BOD approved RPG project. Also added additional 138 kV feed from Stillman to AEP's Chalybe 138 kV | Added two (2) 675 MVA Autotransformers to serve load on 138 kV system | Chalybe |  | Planned | 77144 | SLU | Charles Aleman caleman@huntutility.com 682-406-9656 |  | 2029-05-31 |  | 345 | 47 | 0 | 1350 |  | Cameron |  | Tier 1 | 24RPG008 | 2024-06-11 | 2024-09-25 | 2024-12-03 | 8735, 79500, 79501, 79502, 79596, 79597, 79601 | Y | N |  |  | 94231 | 93217
100071 | Taurus: Construct New 345 kV Station | Interconnect TNMP data center load to the new Taurus 345 kV station on the Solstice to Sand Lake 345 kV line | Project Description and In-Service Date Update | Taurus |  | Conceptual |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-05-31 |  | 345 | 0.2 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 18669, 60404, 60462 | Y |  |  |  | 100072 | 100071
98569 | Oso Creek to Westside: Construct New 138 kV Line | Construct a new 138 kV single circuit line from Oso Creek to Westside | Company Contact and In-Service Date Update | Oso Creek | Westside | Planned |  | AEP TCC | Brooks Dow deevans@aep.com 918-599-2938 | TP2025225 | 2029-05-31 |  | 138 | 6 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8089, 8485, 8515 | Y |  |  |  | 98570 | 98569
99009D | 138kV Flewellen to Fort Bend Ckt 09G-60E Upgrades | Upgrade Ckt.60E Flewellen to Fort Bend to increase thermal limits. Expect Flewellen equipment upgrades and Fort Bend equipment/Relay upgrades to reach the Minimum ratings as second phase of upgrade |  | Flewellen | Fort Bend | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 | 25RPG010 | 2025-03-26 | 2025-04-18 | 2025-04-18 | 44230, 44280 | Y | N |  |  | 99013 | 99009
99009B | 138kV Flewellen to Fort Bend Ckt 09G-60E Upgrades | Upgrade Ckt.09G Flewellen to Brazos Valley to increase thermal limits. Expect FL/BV equipment upgrade as second phase of Ckt.09G upgrade. |  | Flewellen | Brazos Valley | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 | 25RPG010 | 2025-03-26 | 2025-04-18 | 2025-04-18 | 44100, 44230 | Y | N |  |  | 99011 | 99009
99000C | Install (2) 14.4 MVAR distribution cap banks at Twinwood substation. Install (2) 14.4 MVAR distribution cap banks at Fulshear substation. Install (2) 55 MVAR transmission cap bank at Peters substation. | Install (1) additional 55 MVAR transmission cap bank at Peters substation. (second of two) |  | Twinwood / Fulshear |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 | 0,55 | Fort Bend |  | Tier 4 |  |  |  |  | 46220 | Y | N |  |  | 99003 | 99000
99724 | BEPC_TPIT_HAMILTONGTC_Energize_LeonCrusader |  |  | Snelling | Crusader | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 126, 142, 145, 149, 33126, 33145, 33266 | Y |  |  |  | 99725 | 99724
87427 | Rebuild Magnolia to Seminole 138kV line. | Replacement for recently committed PMCR # 4010. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38950, 38990 | Y |  |  |  | 87428 | 87427
76348 | Reconductor Foxtail-PIGCreek-1926ACSS-138KV |  |  | Foxtail | PIG Creek | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0.68 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38294, 60393 | Y |  |  |  | 76349 | 76348
66204 | Rebuild Hidden Lakes-PH Robinson with bundled 795 ACSS |  |  | TNMP Hidden Lakes (bus # 38900) | CenterPoint PH Robinson (bus # 42015) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 3.15 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 42015 | Y |  |  |  | 66205 | 66204
60502 | Rebuild Apache-Amoco with bundled 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38620, 38720 | Y |  |  |  | 60503 | 60502
60504 | Rebuild Caddo-Apache with bundled 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38710, 38720 | Y |  |  |  | 60505 | 60504
84898 | New Eastside Switching Station |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5035, 5110, 5136, 5137, 5250, 5294, 5371, 5400, 5416, 5485 | Y |  |  |  | 84899 | 84898
100674 | Install a 50MVAr Capacitor Bank at Crossroads Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5102 | Y |  |  |  | 100675 | 100674
86836 | AEN_Northland_KoenigLane_Ckt__conversion_to_138kV | Northland to Koenig Lane convert_to_138kV |  | 9129 | 9227 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9129, 9227 | Y |  |  |  | 86837 | 86836
86273 | AEN_REPLACE_AUSTROP_345kV_AUAT1_and_AUAT2_AUTOS_WITH__New_672_MVAs_PMCR | Autos to be upgraded to 672 MVAs |  | 7040 | 9328 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 345 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7040, 9328, 9329, 9330 | Y |  |  |  | 86274 | 86273
86329 | AEN_PilotKnob_CarsonCreek_Ckt_944_RECONDUCTOR |  |  | 9175 | 9259 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9175, 9259 | Y |  |  |  | 86330 | 86329
6687 | Rebuild Rio Hondo to East Rio Hondo | Rebuild the 138 kV line from Rio Hondo to East Rio Hondo. |  | Rio Hondo | East Rio Hondo | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-06-01 |  | 138 | 0 | 8.19 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5764, 8319 | N | N |  |  | 14458 | 6687
50645 | CPSE_Rafter 138kV Cap Bank |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5355 | Y |  |  |  | 50646 | 50645
100676 | Install a 50MVAr Capacitor Bank at the future Eastside Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5136 | Y |  |  |  | 100677 | 100676
87693 | Rebuild Spruce to Eastside Double Circuit |  |  |  |  | Planned | T-0398 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 3 |  |  |  |  | 5137, 5400 | Y |  |  |  | 87694 | 87693
100680 | Install a 50MVAr Capacitor Bank at Grandview Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5175 | Y |  |  |  | 100681 | 100680
100687 | Install a 50MVAr Capacitor Bank at Helotes Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5200 | Y |  |  |  | 100688 | 100687
100665 | Install a 21.42MVAr Capacitor Bank at Bulverde Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5051 | Y |  |  |  | 100666 | 100665
100695 | Install a 50MVAr Capacitor Bank at Omicron Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5326 | Y |  |  |  | 100696 | 100695
100702 | Install a 28.57MVAr Capacitor Bank at Tallly Rd Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5422 | Y |  |  |  | 100703 | 100702
93624 | L7C Add a new Creosote - Blue Goose (fka Toyah Creek) 345-kV double-circuit line | AEP and Oncor joint project to add the 23-mile L7C Creosote - Blue Goose (fka Toyah Creek) 345-kV double-circuit transmission line part of the local common projects approved as part of the Permian Basin Reliability Plan |  | Creosote | Blue Goose | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L7C | 2029-06-21 |  | 345 | 46 | 0 | 0 |  | Ward | Pecos | Tier 1 |  | 2023-05-18 | 2023-06-09 |  | 18669, 60141, 60145 | Y |  |  |  | 93625 | 93624
99908 | Altair - Eagle Lake Transmission Line Overhaul | Perform an overhaul on the 11.4 mile T547 Altair - Eagle Lake (including all tap lines) 69-kV transmission line. Per LCRA TSC Transmission System Planning procedure, replacement structures will be capable of operating at 138-kV. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-762-3658 |  | 2029-06-30 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8523, 8527, 8529, 78105, 78106, 78524, 78526, 78528 | Y |  |  |  | 99909 | 99908
76818 | Upgrade Rayburn Auto Station | Upgrade Rayburn Auto |  | Rayburn | Rayburn | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-07-01 |  | 138 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5500, 5502 | N |  |  |  | 76819 | 76818
73053A | Wimberley Loop to New Substation | Adds new 138 kV branch (219 MVA) from Wimberley to a new three terminal ring bus substation between Dripping Springs and Rutherford. |  | Wimberley | Cebolla Creek | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2029-08-01 |  | 138 | 13.44 | 0 | 0 |  | Hays | Hays | Tier 2 | 22RPG026 | 2022-08-29 | 2023-02-03 |  | 70509, 70511, 70512 | Y | N |  |  | 73054 | 73053
6666 | BRYN_6666_Steele_Store_to_Cooks_Point | Construct 138kV line from BTU Steele Store to LCRA Cooks Point (Bundled 1033 ACSR - Curlew & 959 ACSS Suwannee) |  | 32852 | 7569 | Planned |  | BRYN/BTU AND LCRA TSC | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-10-01 |  | 138 | 7.2 | 0 | 0 |  | Brazos | Burleson | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 7569, 32852 | Y |  |  |  | 91617 | 6666
99105A | BRYN_99105_RIVERSIDE | Construct Riverside 138-kV switching station by cutting into the existing Dansby to Thompson Creek 138-kV transmission line. |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32858, 32863, 32897 | Y |  |  |  | 99183 | 99105
99103 | BRYN_99103_RELLIS_TNPONE_DC345KV | Expand the existing RELLIS 138 kV Substation to establish the BTU RELLIS 345/138 kV Switchyard. Install at RELLIS Switchyard two 345/138 kV autotransformers with a nameplate rating of 600 MVA. Expand the TNP One Substation to accommodate two additional 345 kV line terminals. Construct a 40-mile, 345 kV double-circuit line from BTU RELLIS to TNMP TNP One. |  | RELLIS | TNP One | Planned |  | BRYN/BTU AND TNMP | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-10-01 |  | 345 | 43 | 0 | 1200 |  | Brazos | Robertson | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32780, 32781, 32782, 32783, 39950 | Y |  |  |  | 99539 | 99103
99117 | BRYN_99117_ATK-TAMU_UPGRADE | Re-build the existing Atkins to TAMU 138-kV single-circuit transmission line on double-circuit capable structures with one circuit in place with normal and emergency ratings of at least 495 MVA and 521 MVA, respectively, approximately 3.3-mile. |  | Atkins | TAMU | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-10-01 |  | 138 | 0 | 3.3 | 0 |  | Brazos | Brazos | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32799, 32862 | Y |  |  |  | 99118 | 99117
99105B | BRYN_99105_RIVERSIDE | Construct RELLIS to Riverside 138-kV transmission line on double-circuit capable structures. |  | RELLIS | Riverside | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-10-01 |  | 138 | 6.1 | 0 | 0 |  | Brazos | Brazos | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32780, 32858 | Y |  |  |  | 99184 | 99105
91941 | Solstice to Faulkner: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Solstice to Faulkner | Company Contact and In-Service Date Update | Solstice | Faulkner | Planned |  | AEP TNC/TNMP | Brent Harris myturner@aep.com 918-599-2437 | TP2024165 | 2029-10-30 |  | 345 | 40 | 0 | 0 |  | Pecos | Reeves | Tier 1 | [5 empty] | Y | N |  |  | 91942 | 91941
99453T | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.74C Tomball to Singleton to increase thermal limits as part of FRM2 upgrades. |  | Tomball | Singleton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Harris | Grimes | Tier 4 |  |  |  |  | 44645, 46500 | Y | N |  |  | 102625 | 99453
99453Q | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.98G Smithers to WA Parish to increase thermal limits as part of FRM2 upgrades. |  | Smithers | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44005, 44650 | Y | N |  |  | 102622 | 99453
99791A | Additional Facility Ratings Methodology Phase 2 (FRM2) Substation Upgrades. | Upgrade Ckt.50B Zenith to Gibbons Creek to increase thermal limits as part of FRM2 upgrades. |  | Zenith | Gibbons Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Harris | Tier 4 |  |  |  |  | 967, 44900 | Y | N |  |  | 99806 | 99791
102771A | Aquila (AQU) CEHE-Owned 345kV Substation for TALON (TAL) / Eagle Claw Energy Storage (27INR0085) | Install new 345kV Aquila (AQU) substation for generator interconnection to TALON (TAL) / Eagle Claw Energy Storage (27INR0085). Loop Ckt.99D Singleton to Zenith to create new Ckt.99 Singleton to Aquila to Zenith. |  | Aquila | Zenith/Singleton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Harris | Tier 4 | [5 empty] | Y | N |  |  | 102772 | 102771
99453F | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.75D Roans Prairie to Singleton increase thermal limits as part of FRM2 upgrades. |  | Roans Prairie | Singleton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 40600, 44645 | Y | N |  |  | 102619 | 99453
99453G | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.75B Kuykendahl to Roans Prairie to increase thermal limits as part of FRM2 upgrades. |  | Kuykendahl | Roans Prairie | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Harris | Grimes | Tier 4 |  |  |  |  | 40600, 48205 | Y | N |  |  | 102621 | 99453
102771B | Aquila (AQU) CEHE-Owned 345kV Substation for TALON (TAL) / Eagle Claw Energy Storage (27INR0085) | Install generator lead from Aquila (AQU) substation to TALON (TAL) customer substation (27INR0085). |  | Aquila | TALON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 00:01 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | Cost included in main entry | 102773 | 102771
92432 |  |  |  | Reno | New Station Nofoul | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-11-15 |  | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 534, 541, 542 | Y |  |  |  | 92433 | 92432
99749 | Friend Ranch to Illinois #4: Convert to 138 kV | Convert the Friend Ranch to Illinois #4 69 kV line to 138 kV | Company Contact, Transmission Owner Project Number, In-Service Date, and RPG Dates Update | Friend Ranch | Illinois #4 | Planned | TP2025183 | AEP | Craig Tabor myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0 | 23.8 | 0 |  | Crockett | Crockett | Tier 2 | H.B. 5066 |  |  | 2024-10-31 | 6550, 6551, 6560, 6562, 6564, 6565, 6567, 60190, 60191, 60192, 60194 | Y |  |  |  | 99750 | 99749
93453 | Creosote: Expand 345 kV Station | Install three 345/138 kV autotransformers at the Creosote 345/138 kV station | Company Contact and In-Service Date Update | Creosote |  | Planned |  | AEP TNC | Glen Reed gareed@aep.com 918-599-2664 |  | 2029-11-30 |  | 345 | 0 | 0 | 2025 |  | Reeves |  | Tier 1 | [5 empty] | Y |  |  |  | 93454 | 93453
98559 | Sterling City to Chalk: Convert to 138 kV | Convert the Sterling City to Chalk 69 kV line to 138 kV | Company Contact, Transmission Owner Project Number, In-Service Date, and RPG Dates Update | Sterling City | Chalk | Planned | TP2025199 | AEP TNC | Craig Tabor myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0 | 1.6 | 0 |  | Sterling | Sterling | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 6417, 6435, 6436, 11352, 60167, 60168, 60171 | Y |  |  |  | 98560 | 98559
91853 | Fort Stockton Plant to Solstice: Rebuild 138 kV Line | Rebuild the Fort Stockton Plant to Solstice 138 kV line and retire the PST at Solstice | In-Service Date and RPG Dates Update | Fort Stockton Plant | Solstice | Planned |  | AEP TNC | Brooks Dow myturner@aep.com 918-599-2437 | TP2025145 | 2029-11-30 |  | 138 | 0 | 25 | 0 |  | Pecos | Pecos | Tier 3 | H.B. 5066 |  |  | 2024-10-31 | 6630, 60384, 60385 | Y | N |  |  | 91854 | 91853
93428 | Creosote to Toyah Creek: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Creosote to Toyah Creek | Company Contact and In-Service Date Update | Creosote | Toyah Creek | Planned |  | AEP TNC | Charity Kreher myturner@aep.com 918-599-2437 | TP2024162 | 2029-11-30 |  | 345 | 23 | 0 | 0 |  | Reeves | Reeves | Tier 1 |  |  |  |  | 38376, 38380, 60140, 60141, 60142, 60143, 60144, 60145, 60377 | Y |  |  |  | 93429 | 93428
98556 | Cedar Hill to Sterling City: Convert to 138 kV | Convert the Cedar Hill to Sterling City 69 kV line to 138 kV | Company Contact, Transmission Owner Project Number, In-Service Date, and RPG Dates Update | Cedar Hill | Sterling City | Planned | TP2025199 | AEP TNC | Craig Tabor myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0 | 36.5 | 90 |  | Coke | Sterling | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 6423, 6425, 6427, 6428, 6429, 6430, 6431, 6432, 6433, 6434, 6435, 6484, 6488, 60162, 60166, 60169, 60170, 60171, 60172, 60173, 60174, 60175, 60185, 60187 | Y |  |  |  | 98558 | 98556
98628 | Ballinger to Oak Creek: Reterminate 138 kV Line Into Nicole | Reterminate the Ballinger to Oak Creek 138 kV line from Oak Creek into the existing Nicole 138 kV station | Company Contact, Transmission Owner Project Number, In-Service Date, and RPG Date Update | Ballinger | Nicole | Planned | TP2025197 | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0.25 | 0 | 0 |  | Runnels | Coke | Tier 1 | H.B. 5066 |  |  | 2024-10-31 |  | Y | N |  |  | 98629 | 98628
98626 | Abilene Northwest to Oak Creek: Reterminate 138 kV Line Into Nicole | Reterminate the Abilene Northwest to Oak Creek 138 kV line from Oak Creek into the existing Nicole 138 kV station | Company Contact, Transmission Owner Project Number, In-Service Date, and RPG Date Update | Abilene Northwest | Nicole | Planned | TP2025197 | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0.75 | 0 | 0 |  | Taylor | Coke | Tier 1 | H.B. 5066 |  |  | 2024-10-31 |  | Y | N |  |  | 98627 | 98626
6685 | Van Vleck substation loop | Replaces single circuit radial line connected to a pole mounted switch with a double circuit transmission loop to the Van Vleck substation and upgrades the 4/0 ACSR to 795 ACSR on 138 kV capable poles. |  | Van Vleck Substation | Van Vleck Switch | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-12-01 |  | 69 | 2 | 2 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5556, 5557, 5558, 5560 | N | N |  |  | 14456 | 6685
100136 | WETT project to loop Faraday station in the existing Long Draw to Scurry 345 kV double circuit transmission line approved as part of 24RPG015. |  |  | Faraday | Faraday | Planned |  | WETT | Christopher Ramirez cramirez@wettllc.com |  | 2029-12-01 |  | 345 | 0 | 0 | 0 |  | Borden | Borden | Tier 1 | 24RPG015 | 2024-05-03 | 2024-05-28 | 2025-05-16 | 59905, 59912, 59922 | Y |  |  |  | 100137 | 100136
59260 | Mason Phillips Tap to Mason Phillips: Rebuild 69 kV Line | Rehab the Mason Phillips Tap to Mason Phillips 69 kV Line |  | Seaquist | Mason Phillips | Planned | 1127 - 1305 | AEP TNC | Christopher Carroll twang1@aep.com 918-599-2635 | 1872 | 2029-12-01 |  | 69 | 0 | 13.7 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6395, 6407, 60458 | Y | N |  |  | 65588 | 59260
84900 | Rebuild Pawnee to Tango into a double circuit |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5725, 8689 | Y |  |  |  | 84901 | 84900
99314 | Establish Dinosaur 765/345 kV Switch | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1A. Establish the Dinosaur 765/345 kV Switch with two 765/345 kV autotransformers |  | Dinosaur | Dinosaur | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_A | 2029-12-15 |  | 765 | 0 | 0 | 4500 | -900,0 | Somervell | Somervell | Tier 1 |  |  |  |  | 1899, 1900, 1902, 1981, 11886, 15207, 15208, 15209, 15210 | Y |  |  |  | 99315 | 99314
81240 | Consavvy – Odessa EHV 345 kV Double Circuit Line Rebuild | Rebuild the existing 345 kV Double-Circuit Line |  | Consavvy | Odessa EHV | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 | 2029-12-15 |  | 345 | 0 | 40 | 0 |  | Midland | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1125, 11016, 11028, 11387, 18540, 18548 | Y |  |  |  | 81241 | 81240
89918 | GVEC Gonzales substation | Rebuild existing substation, 138 kV bus, new PWT, new Control House, new HV and LV structures, containment foundations, bus, panels, etc |  | Gonzales |  |  |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2029-12-15 | 2958101 | 138 | 0 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 | [5 empty] | Y |  |  |  | 89919 | 89918
81302 | Rockhound - Midland East 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Rockhound | Midland East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2029-12-15 |  | 345 | 0 | 24.2 | 0 |  | Midland | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1021, 10062 | Y |  |  |  | 81303 | 81302
80346 |  |  |  | SANDY SWITCH | CRUTCHFIELD | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-12-21 |  | 138 | 0 | 3.2 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 5, 8 | Y |  |  |  | 80347 | 80346
99128 | Longshore 765/345 kV Autotransformer #2 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1B. Add a second 765/345 kV autotransformer at Longshore |  | Longshore | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_B | 2029-12-31 |  | 765 | 0 | 0 | 2250 | -225,0 | Howard | Howard | Tier 1 |  |  |  |  | 1058, 18112, 18114 | Y |  |  |  | 99129 | 99128
99130 | Drill Hole 765/345 kV Autotransformer #2 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1C. Add a second 765/345 kV autotransformer at Drill Hole |  | Drill Hole | Drill Hole | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_C | 2029-12-31 |  | 765 | 0 | 0 | 2250 | -225,0 | Culberson | Culberson | Tier 1 |  |  |  |  | 10073, 18733, 18735 | Y |  |  |  | 99131 | 99130
66118 | Reconductor TI-Lakepointe with 959 ACSS/TW | Project ISD anticipated in 2025. |  | Lakepoint (bus # 37010) | TI (bus # 37080) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-12-31 |  | 138 | 0 | 2.78 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 37010, 37080 | Y |  |  |  | 66119 | 66118
100163 | BowWood_Load_Circuit_Breaker_Addition | Install a new transmission point of interconnection for a large load at Bow Wood Substation. |  | Bow Wood | Bow Wood | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-12-31 |  | 345 | 0 | 0 | 0 |  | McCulloch | McCulloch | Tier 4 |  |  |  |  | 76006 | Y |  |  |  | 100164 | 100163
99323 | Longshore - Dinosaur 765 kV Line | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1D. Add a new New Substation 2 – Longshore 765-kV single-circuit line |  | Longshore | Dinosaur | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_D | 2029-12-31 |  | 765 | 257.45 | 0 | 0 | -450,0 | Howard | Somervell | Tier 1 |  |  |  |  | 15207, 18112 | Y |  |  |  | 99324 | 99323
99857 | LCRATSC_Gooseneck_Substation_Addition | Add Gooseneck substation cut into LCRA TSC-owned 345-kV double-circuit line, T248 Marion -Zorn and T250 Clear Springs - Zorn. |  | 7052 Gooseneck |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2029-12-31 |  | 345 | 0 | 0 | 0 |  | Guadalupe |  | Tier 1 |  |  |  |  | 7042, 7044, 7050, 7052 | Y |  |  |  | 99858 | 99857
100025 | Naismith: Expand 138 kV Station | Interconnect green hydrogen load to the existing Naismith 138 kV station |  | Naismith |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2029-12-31 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8660 | Y |  |  |  | 100026 | 100025
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0733 | 2030-01-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y | Y |  |  | 11872 | 4320
15TPIT0031 | Chavaneaux_Chavaneaux Tap Rebuild (Brooks to Chavaneaux ckt) | Rebuild 138 kV transmission from Chavaneaux to Chavaneaux Tap. This rebuild is for Brooks to Chavaneaux ckt. |  | Brooks | Chavaneaux | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0260 | 2030-01-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y |  |  | There are no transformers associated with this project | 9555 | 2304
98582 | Rapido: Expand 345 kV Station | Interconnect Barrosos Creek to the existing Rapido 345 kV station |  | Rapido |  | Planned |  | AEP TCC/ETT TCC | Charity Kreher jlsolis@aep.com 361-881-5574 | TP2025226 | 2030-01-30 |  | 345 | 0 | 0 | 0 |  | Starr |  | Tier 4 | [5 empty] | Y |  |  |  | 98583 | 98582
102762 | BEPC_TPIT102762_Whitney_Itasca |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-03-01 |  | 69 | 0 | 16.1 | 0 |  | Bosque |  | Tier 4 |  |  |  |  | 224, 228, 243 | Y |  |  |  | 102763 | 102762
98584 | Tiempo: Expand 345 kV Station | Interconnect Corralitos Wind 1 and 2 to the existing Tiempo 345 kV station | Owner, Transmission Owner Project Number, and Company Contact Update | Tiempo |  | Planned |  | AEP TCC/ETT TCC | Charity Kreher jlsolis@aep.com 361-881-5574 | TP2025252 | 2030-04-30 |  | 345 | 0 | 0 | 0 |  | Zapata |  | Tier 4 | [5 empty] | Y |  |  |  | 98585 | 98584
61550 | East Munday to Lake Pauline: Rebuild 138 kV Line | Rehab East Munday to Lake Pauline 138 kV line |  | East Munday | Lake Pauline | Planned | 1129 - 1307 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 1874 | 2030-04-30 |  | 138 | 0 | 59.97 | 0 |  | Knox | Hardeman | Tier 4 | 20RPG018 |  |  |  | 6037, 6050, 6110 | Y | N |  |  | 65594 | 61550
102877 | Upgrade Bakersfield to Schneeman Draw | Upgrade Bakersfield - Cedar Canyon - Noelke - Schneeman Draw as part of the Permian Basin Reliability plan (project L15) |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y | N |  |  | 102878 | 102877
102873 | Upgrade Aloe to Warburton |  |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 69 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 | [5 empty] | N | N |  |  | 102874 | 102873
90022 | Upgrade Sam Rayburn to Aloe | Upgrade Sam Rayburn to Aloe to 795 ACSR conductor. 2025 RTP. |  | Sam Rayburn | Aloe | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 138 | 0 | 9.6 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5500, 5606 | Y |  |  |  | 90023 | 90022
76123 | D'Hanis Capacitor 2nd step addition | D'Hanis Capacitor 2nd step addition 9.6 MVAR |  | D'Hanis |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5814 | N | N |  |  | 76124 | 76123
75989 | Rebuild Vanderbilt -Pt Lavaca | Rebuild Vanderbilt - Placedo - Kamey -Pt Lavaca 69kV to 795 ACSR |  | Vanderbilt | Port Lavaca | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 69 | 0 | 26.47 | 0 |  | Victoria | Calhoun | Tier 4 |  |  |  |  | 5582, 5586, 5590, 5591, 5592 | N |  |  |  | 75990 | 75989
102663 | BEPC_TPIT102663_Pursley_Emmett |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-05-10 |  | 69 | 0 | 10.5 | 0 |  | Navarro |  | Tier 4 |  |  |  |  | 191, 198, 199 | Y |  |  |  | 102759 | 102663
102395 | Bakersfield_SchneemanDraw_Transmission_Line_Upgrade | Upgrade substation equipment at Bakersfield, Cedar Canyon, Twelvemile, Noelke, Single Tree, and Schneeman Draw to support the upgrade of the STEC 345-kV double circuit line from Bakersfield to Schneeman Draw. Transmission line scope will be performed by STEC. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-05-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 102396 | 102395
6287 | Sherry Sw. - Webb/Kennedale 345 kV DCKT Line | Upgrade the existing 345 kV Line |  | Sherry | Webb/Kennedale | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4252 | 2030-05-15 |  | 345 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 3 |  |  |  |  | 1911, 1918, 1929, 1930, 1932, 1934 | Y |  |  |  | 14016 | 6287
99346 | Rebuild the Temple Pecan Creek Switch - Belfalls/STR 26/4C 345 kV Double Circuit Line | Rebuild the Temple Pecan Creek Switch - Belfalls/STR 26/4C 345 kV Double Circuit Line |  | Temple Pecan Creek | Belfalls | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6434 | 2030-05-15 |  | 345 | 0 | 2.6 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3404, 3412 | Y |  |  |  | 99347 | 99346
91399 | Bitter_Creek_Substation_Upgrade | Oncor will upgrade the existing 345-kV double-circuit transmission lines Bitter Creek - Morgan Creek (Cattleman) and Bitter Creek - Sweetwater East. Part of the Permian Basin Reliability Plan released by ERCOT, under transmission upgrades L24 |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8256 | 2030-05-15 |  | 345 | 0 | 0 | 0 |  | Nolan | Nolan | Tier 4 |  |  |  |  | 11420, 71050 | Y |  |  |  | 91400 | 91399
102795 | Bakersfield_NevillRoad_NorthMcCamey_Transmission_Line_Upgrade | PL and LCRA joint PBRP_L14 project by upgrading of the existing Bakersfield - Nevill Road - North McCamey 345kV transmission lines and adding of new 345kV Bakersfield - Nevill Road - North McCamey second circuits |  | Nevill Road | Bakersfield/North McCamey | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | PBRP_L14_Joint | 2030-05-15 |  | 345 | 16.27 | 16.27 | 0 |  | Upton | Pecos | Tier 1 |  |  |  |  | 844, 76000, 76002 | Y |  |  |  | 102796 | 102795
102795 | Bakersfield_NevillRoad_NorthMcCamey_Transmission_Line_Upgrade | PL and LCRA joint PBRP_L14 project by upgrading of the existing Bakersfield - Nevill Road - North McCamey 345kV transmission lines and adding of new 345kV Bakersfield - Nevill Road - North McCamey second circuits |  | Nevill Road | Bakersfield/North McCamey | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | PBRP_L14_Joint | 2030-05-15 |  | 345 | 16.27 | 16.27 | 0 |  | Upton | Pecos | Tier 1 |  |  |  |  | 844, 76000, 76002 | Y |  |  |  | 102796 | 102795
92282 | Faulkner - Cryo 138kV - Part of Upgrade L4 2024 Permian Basin Study |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2030-06-01 |  | 138 | 22.8 | 0 | 0 |  | Reeves | Reeves | Tier 2 |  |  |  |  | 38124, 60721 | Y |  |  |  | 92283 | 92282
92276 | Bottlebrush 345kV - Part of Upgrade L13 2024 Permian Basin Study |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2030-06-01 |  | 345 | 174.84 | 29.81 | 1500 |  | Pecos | Pecos | Tier 1 |  |  |  |  | 38430, 38431, 38432, 38435, 38439, 38441, 38442, 38443, 38455, 60404 | Y |  |  |  | 92277 | 92276
92274 | Whitebaker 345kV - Part of Upgrade L13 2024 Permian Basin Study |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2030-06-01 |  | 345 | 22 | 0 | 1500 |  |  |  | Tier 1 |  |  |  |  | 38430, 38435, 38436, 38437, 76002 | Y |  |  |  | 92275 | 92274
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures. Kramer Lane (KA) substation will be cut-into this line in 2023 |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2030-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238, 9276 | Y | N |  | Will add the ptoject to the base case. | 8207 | 1031
91586 |  |  |  | TENASKA | NEW SUBSTATION PLANK | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-07-05 |  | 138 | 0 | 0 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 370, 371, 415 | Y |  |  |  | 91587 | 91586
89920 | GVEC Nixon substation | Rebuild existing substation, 138 kV bus, new PWT, new Control House, new HV and LV structures, containment foundations, bus, panels, etc |  | Gonzales |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2030-10-25 | 2958101 | 138 | 0 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 | [5 empty] | Y |  |  |  | 89921 | 89920
99784 | Lytle: Expand 345 kV Station | Interconnect the Cinco III load to the expanded Lytle 345 kV station | Owner and Transmission Owner Project Number Update | Lytle |  | Planned |  | AEP TCC/ETT TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025325 | 2030-11-30 |  | 345 | 0 | 0 | 1200 |  | Medina |  | Tier 2 |  |  |  |  | 8962, 88962 | Y |  |  |  | 99785 | 99784
98599 | Bluff Creek to Mulberry Creek: Rebuild 345 kV Line as a Double Circuit | Rebuild existing 345 kV line from Bluff Creek to Mulberry Creek as a double circuit line |  | Bluff Creek | Mulberry Creek | Planned | TP2024147 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2030-11-30 |  | 345 | 26.9 | 0 | 0 |  | Taylor | Jones | Tier 4 |  |  |  |  | 6235, 60040 | Y | N |  |  | 98600 | 98599
100466 | Big Hill 765-kV Substation Addition | LCRA TSC will construct a new Big Hill 765-kV yard adjacent to the existing Big Hill 345-kV Substation and install two new 765/345-kV autotransformers. |  | Big Hill |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8263 | 2030-12-01 |  | 765 | 0 | 0 | 4806 | -900,0 | Schleicher |  | Tier 1 |  |  |  |  | 76003, 76500 | Y |  |  |  | 100467 | 100466 | 2024-EHV-CORE-PB2b
92340 |  |  |  | New 138 KV station "Warg" | New 138 KV station "Warg" | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-12-01 |  | 138 | 4 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 173, 176, 177 | Y |  |  |  | 92341 | 92340
99385 | Establish Bell County East 765/345 kV Switch | Establish Bell County East 765/345 kV Switch |  | Bell County East | Bell County East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6430 | 2030-12-02 |  | 765 | 0 | 0 | 2250 |  | Bell | Bell | Tier 1 |  |  |  |  | 3687, 3807, 3808, 3809 | Y |  |  |  | 99386 | 99385
81277 | Midland East – Midland County NW 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Midland East | Midland County Northwest | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8729 | 2030-12-15 |  | 345 | 0 | 42.6 | 0 |  | Midland | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1021, 1185 | Y |  |  |  | 81278 | 81277
98595 | Solstice to Howard: Construct New 765 kV Single Circuit Line | Construct a new 765 kV single circuit line from Solstice to Howard | Company Contact Update | Solstice | Howard | Planned |  | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 |  | 2030-12-30 |  | 765 | 185 | 0 | 4500 | -600,0 | Pecos | Bexar | Tier 1 |  |  |  |  | 6129, 6130, 6137, 6144, 6145, 6164, 60404 | Y |  |  |  | 98596 | 98595
98991B | Kinnebrew POI - Chalk 69 kV to 138 kV Line Conversion | Oncor's portion of the Permian Basin Reliability Plan Upgrade ID L27B. Convert the existing Sterling County - Kinnebrew POI 69-kV line to 138-kV. |  | Kinnebrew | Sterling County | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L27_B | 2030-12-30 |  | 138 | 10.6 | 0 | 0 |  | Sterling | Sterling | Tier 3 |  |  |  |  | 10189, 60167 | Y |  |  |  | 100075 | 98991
98574 | Cedar Hill to Oak Creek: Rebuild 138 kV Line | Rebuild the Cedar Hill to Oak Creek 138 kV line | Company Contact, Transmission Owner Project Number, and RPG Date Update | Cedar Hill | Oak Creek | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2025197 | 2030-12-30 |  | 138 | 2 | 26 | 0 |  | Coke | Coke | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 6319, 6325, 6335, 6351, 6425, 60724 | Y |  |  |  | 98575 | 98574
91578 | buffalo_clover_substation_addition | Adding buffalo Clover PEC bus to Brazos Anduin Bus. | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2030-12-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 124, 70000 | Y |  |  |  | 91582 | 91578
100597 | Sand Lake - Big Hill (LCRA) 765 kV Line | Add Permian Basin Reliability Plan Upgrade ID 765_Import_2E. Add a new Big Hill – Sand Lake 765-kV single-circuit line |  | Sand Lake | Big Hill | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import2_E | 2030-12-31 |  | 765 | 211.2 | 0 | 0 |  | Ward | Schleicher | Tier 1 |  |  |  |  | 18736, 76500 | Y |  |  |  | 100598 | 100597
99241 | Sand Lake 765/345 kV Autotransformer #1 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_2C. Establish the Sand Lake 765/345 kV Switch with one 765/345 kV autotransformer |  | Sand Lake | Sand Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import2_C | 2030-12-31 |  | 765 | 0 | 0 | 2250 | -675,0 | Ward | Ward | Tier 1 |  |  |  |  | 11084, 11098, 18736, 18737, 18739, 18740 | Y |  |  |  | 99343 | 99241
91939 | Solstice to Bottlebrush: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Solstice to Bottlebrush |  | Solstice | Bottlebrush | Planned |  | AEP TNC/TNMP | Tong Wang twang1@aep.com 918-599-2635 | TP2024076 | 2030-12-31 |  | 345 | 31 | 0 | 0 |  | Pecos | Reeves | Tier 1 | [5 empty] | Y | N |  |  | 91940 | 91939
91906 | Carver to Friend Ranch: Rebuild 138 kV Line | Rebuild the Carver to Friend Ranch 138 kV line |  | Carver | Friend Ranch | Planned |  | AEP TNC | Nathan Cowan myturner@aep.com 918-599-2437 | TP2025168 | 2030-12-31 |  | 138 | 0 | 33 | 0 |  | Sutton | Crockett | Tier 3 |  |  |  |  | 6562, 60412 | Y | N |  |  | 91907 | 91906
99263 | Sand Lake 765/345 kV Autotransformer #2 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_2C. Add a second 765/345 kV autotransformer at Sand Lake |  | Sand Lake | Sand Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import2_C | 2030-12-31 |  | 765 | 0 | 0 | 2250 | -225,0 | Ward | Ward | Tier 1 |  |  |  |  | 18736, 18738, 18739 | Y |  |  |  | 99264 | 99263
98955 | Duende: Construct New 765 kV Station | Install two 765 kV shunt reactors at the new Duende 765 kV station on the new Solstice to Howard 765 kV line |  | Duende |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2030-12-31 |  | 765 | 0 | 0 | 0 | -600,0 | Edwards |  | Tier 4 |  |  |  |  | 6144, 60212, 60213, 60214 | Y |  |  |  | 98956 | 98955
100153 | Construct the Big Hill (LCRA TSC) - Bell County East 765 kV Line | Add Permian Basin Reliability Plan Upgrade ID 765_Import_2D. Add a new Bell East (ONCOR) – Big Hill (LCRA) 765-kV single-circuit line |  | Big Hill (LCRA TSC) | Bell County East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import2_D | 2030-12-31 |  | 765 | 233.4 | 0 | 0 |  | Schleicher | Bell | Tier 1 |  |  |  |  | 3807, 76500 | Y |  |  |  | 100154 | 100153
45015 | Barnhart to Cassava: Rebuild 69 kV line | Rebuild the Barnhart to Cassava 69 kV line |  | Barnhart | Cassava | Planned | 942 - 1120 | AEP TNC | LaRissa Lundry twang1@aep.com 918-599-2635 | 2756 | 2030-12-31 01:00 |  | 69 | 0 | 6.021 | 0 |  | Irion | Irion | Tier 4 |  |  |  |  | 6530, 6532, 6537, 60359 | Y | N |  |  | 65525 | 45015
102068 | Construct a new 765kV Howard Rd Switching Station with two 765/345kV autotransformers connnection into the two new positions at Howard Rd 345kV station. Also construct the station with 4 line terminals to accommodate the full 765kV build out. The station w |  |  |  |  | Planned |  | CPS/AEP | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2031-01-01 |  | 765 | 185 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5228, 5229, 5231, 5232, 60214 | Y |  |  |  | 102069 | 102068
71877 | CPSE_Cagnon to Shepherd Rebuild (Phase B) |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0281 | 2031-01-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5054, 5230, 5378, 5465 | Y |  |  |  | 71878 | 71877
45068 | Merida to Harlandale Rebuild | CPSE_Merida to Harlandale Rebuild |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0233 | 2031-05-15 |  | 138 | 0 | 10 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5310, 5385, 5395 | Y |  |  |  | 45069 | 45068
5479 | Trinidad - Tri Corner 345 kV Double-Circuit Line | Upgrade existing DCKT line |  | Trinidad Sw. Sta | TriCorner/Watermill | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4045 | 2031-05-15 |  | 345 | 0 | 92.1 | 0 |  | Henderson | Dallas | Tier 3 |  |  |  |  | 2432, 3123, 3124 | Y | N |  |  | 13184 | 5479
64065 | Alice to Kingsville 138 kV Line Rebuild | Rehab the Alice to Kingsville 138 kV line |  | Alice | Kingsville | Conceptual |  | AEP TCC | Charity Kreher deevans@aep.com 918-599-2938 | TA2021079 | 2031-05-31 |  | 138 | 0 | 22.48 | 0 |  | Jim Wells | Kleberg | Tier 4 |  |  |  |  | 8503, 8518 | Y |  |  |  | 66649 | 64065
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits, as recommended in 2013 RTP. |  | Bevo | Carrizo Springs | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 1 |  | 2012-04-12 | 2012-08-12 | 2012-09-12 | 5871, 8244 | N | N |  | This new line was part of Karnes and Medina Electric Cooperatives Project that was approved in 2012. This also helped voltage on AEP transmission under contingencies. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 10984 | 3595 | 2013-R104
73053B | Wimberley Loop to New Substation | Adds new 138 kV branch (219 MVA) from Wimberley to a new three terminal ring bus substation between Dripping Springs and Rutherford. |  | Wimberley | Cebolla Creek | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2031-06-01 |  | 138 | 13.44 | 0 | 0 |  | Hays | Hays | Tier 2 | 22RPG026 | 2022-08-29 | 2023-02-03 |  | 70496, 70511 | Y | N |  |  | 99289 | 73053
90330 |  |  |  | Red River | JSR1 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2031-09-02 |  | 69 | 1.2 | 0 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 715, 719, 735 | Y |  |  |  | 90331 | 90330
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2031-10-26 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7622 | Y | N |  |  | 78325 | 3321
67915 | Asherton to West Batesville: Rebuild 138 kV Line | Rehab Asherton to West Batesville 138 kV line |  | Asherton | West Batesville | Planned |  | AEP TCC/ETT | John Solis jlsolis@aep.com 361-881-5574 |  | 2031-11-30 |  | 138 | 0 | 36.09 | 0 |  | Dimmit | Zavala | Tier 3 |  |  |  |  | 8236, 8283, 8285 | Y |  |  |  | 67916 | 67915
57910 | Uvalde to West Batesville: Rebuild 138 kV Line | Rebuild the Uvalde to West Batesville 138 kV line |  | Uvalde | West Batesville | Planned | 1117 - 1295 | AEP TCC | Lance Price jlsolis@aep.com 361-881-5574 | 3836 | 2031-11-30 |  | 138 | 0 | 20.6 | 0 |  | Uvalde | Zavala | Tier 4 |  |  |  |  | 8234, 8236 | Y | N |  |  | 65580 | 57910
73001 | Truscott Humble Tap: Rebuild 69 kV Line | Rehab Truscott Humble Tap 69 kV line |  | Moorhouse | Truscott Humble | Planned |  | AEP TNC | Craig Tabor twang1@aep.com 918-599-2635 |  | 2031-11-30 |  | 69 | 0 | 13.92 | 0 |  | Knox | Knox | Tier 4 |  |  |  |  | 6080, 6082, 6084, 6085, 60023 | Y | N |  |  | 73002 | 73001
50898 | Alamito Creek to Paisano to Alpine: Rebuild 69 kV line | Rehab Alamito Creek to Paisano to Alpine 69 kV line |  | Alamito Creek | Alpine | Planned | 1045 - 1218 | AEP TNC | Brooks Dow twang1@aep.com 918-599-2635 | 2793 | 2031-12-31 |  | 69 | 0 | 22.26 | 0 |  | Presidio | Brewster | Tier 4 | 20RPG017 |  |  |  | 6666, 6667, 6672 | Y | N |  |  | 50899 | 50898
50647 | CPSE_Merida to Westside MLSE | Upgrade terminal at Merida to ensure a 2000 A rating. |  | Merida | Westside | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0773 | 2032-01-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5490 | Y |  |  |  | 50648 | 50647
102869 | Upgrade Calallen to Driscoll |  |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2032-05-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | N | N |  |  | 102870 | 102869
76790 | Upgrade Pearsall Auto | Upgrade Pearsall Auto |  | Pearsall | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2032-05-01 |  | 138 | 0 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5893, 5895 | Y |  |  |  | 76791 | 76790
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing Elkton 345/138 kV autotransformer |  | Elkton | Elkton | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6032 | 2032-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 10501 | 3155
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and-or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle-Weiderstein | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0645b | 2032-06-01 12:00 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5360, 5435 | Y | N |  | There are no transformers associated with this project | 9557 | 2306
4425 | New TR-AW Ckt 1032 AW-MR Ckt 1039 MR-JV Ckt 961 | Old Description in Planbook Add 2nd Ckt from TR to HL to tie-in to HL-JV Ckt 1032 (part of old CKT 961), bypassing HL and creating TR-AW-MR-JV Ckt. New description Ckt 1032 from TR-AW, Ckt 1039 from MR-AW and CKT 961 from MR - JV |  | Techridge 9190 AshtonWoods 9224 | AshtonWoods 9226 Jollyville 9223 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2032-08-01 |  | 138 | 1.7 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9190, 9223, 9224, 9226, 9230, 9231 | Y | N |  |  | 11984 | 4425
4084 | Barton-Vega: Upgrade Ckt 928 | Reconductor to 2000 amps |  | Barton | Vega | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2032-08-10 |  | 138 | 0 | 4.05 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9158, 9285 | Y |  |  |  | 11609 | 4084
3334 | Fort Sam to Kirby and Fort Sam to Tenth Street MLSE Upgrade | Upgrade entire bus and terminals at Fort Sam and ensure a rating of 2000 A. |  | Fort Sam | Kirby/Tenth Street | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0744 | 2032-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5160, 5250, 5420 | Y | N |  | There are no transformers associated with this project | 10692 | 3334
70889 | SA College Hills: Rebuild 69 kV Station | Rehab the SA College Hills 69 kV station |  | SA College Hills |  | Planned |  | AEP TNC | Chase Isaac twang1@aep.com 918-599-2635 |  | 2033-07-31 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6468, 6470 | Y |  |  |  | 70890 | 70889

## PlannedTPIT020126NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2026
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
81354 | GSEC_9452_Add_Snodgrass_Sub | Adding new Snodgrass sub to connect to AEP's Juncus Station. | Add New Load and Sub |  |  | Planned |  | GSEC | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2025-04-01 |  | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 9452, 60002 | Y | Y |  |  | 81355 | 81354
99746 | 16th Street auto transformer replacement/addition. |  |  |  |  | In-Service |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-04-23 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38310, 38320 | Y |  |  |  | 99747 | 99746
99776 | Replacement of Lake Whitney auto transformer. |  |  |  |  | In-Service |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37410, 37420 | Y |  |  |  | 99777 | 99776
90446 | Avila BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 88914 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-01 |  | 138 | 0.22 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38340, 136502 | Y |  |  |  | 90447 | 90446
81544 | GSEC_9466_Add_CampSprings_Sub | Add Big Country's Camp Springs Sub 9MW | ISD exceeds NMMS model load date |  |  | Planned |  | GSEC | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2025-05-01 |  | 138 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 9466, 68012 | Y |  |  |  | 81545 | 81544
90393 | Evelyn BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 86784 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-06 |  | 138 | 0.23 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 114262 | Y |  |  |  | 90443 | 90393
72037A | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | New 345kV Seabreeze (SEB) substation for generator interconnection to Tanglewood Solar (23INR0054). Loop Ckt.27B into Seabreeze substation to create new Ckt.27 DOW to Seabreeze to Oasis. |  | Seabreeze | DOW/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-21 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 42500, 43020, 43035, 43150, 43300 | Y | N |  |  | 100208 | 72037
72037B | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | Install generator lead from Seabreeze (SEB) substation to TANGLE (TNG) customer substation (23INR0054). |  | Seabreeze | TANGLE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-21 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43020, 113341, 113345 | Y | N |  | Cost included in main phase | 100209 | 72037
93348 | Adds Cochise Customer Sub |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38160, 38190 | Y |  |  |  | 93349 | 93348
82321 | PMCR for 2nd TX in Coachwhip | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38170 | Y |  |  |  | 82322 | 82321
87889 | Install 2x 40 MVAR Cap bank at League City. |  |  | League City (38920) |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 | 0,80 | Galveston | Galveston | Tier 4 |  |  |  |  | 38920 | Y |  |  |  | 87890 | 87889
90450 | Headcamp BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 85045 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-06-16 |  | 138 | 0.1 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38465, 136432 | Y |  |  |  | 90451 | 90450
76918 | Primavera 138 kV: Construct new station | New station to serve Tesla load | In-Service Date Update | Primavera |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023059 | 2025-06-25 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8003, 8518, 8749, 8921, 88747 | Y |  |  |  | 76919 | 76918
69467 | Dupont to Resnik: Rebuild 138 kV Line | Rebuild the Dupont to Resnik 138 kV line | IN-SERVICE | Dupont | Resnik | In-Service |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2025-06-25 |  | 138 |  | 0.83 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8422, 8580 | Y |  |  |  | 69468 | 69467
50900 | Mason to North Brady: Rebuild 69 kV line | Rehab Mason to North Brady 69 kV line | IN-SERVICE | Mason | North Brady | In-Service | 1046 - 1219 | AEP TNC | Chris Carroll twang1@aep.com 918-599-2635 | 2794 | 2025-06-25 |  | 69 | 0 | 30.24 | 0 |  | Mason | McCulloch | Tier 3 | 19RPG019 | 2019-10-01 | 2019-11-01 |  | 6006, 6381, 6393, 6406, 60386 | Y | N |  |  | 65550 | 50900
93003 | Adds TNMP Turkeyfoot 69kV Substation |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-07-01 |  | 69 | 0 | 0 | 0 |  | Bosque | Coryell | Tier 4 |  |  |  |  | 37470, 37515, 37520 | Y |  |  |  | 93183 | 93003
99926 | Addition of Wolfcamp substation | The addition of Wolfcamp substation, load, and transmission line. |  |  |  | In-Service |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-07-02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38113, 38115 | Y |  |  |  | 99927 | 99926
90448 | Bocanova BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 89822 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-07-19 |  | 138 | 0.1 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39030, 114342 | Y |  |  |  | 90449 | 90448
82829 | New Furhman Substation | Adds New Furhman switching station on Rayburn - Vanderbilt line for generator interconnect |  | Rayburn | Vanderbilt | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-07-24 |  | 138 | 0.84 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5502, 5506, 5584 | Y | N |  |  | 82830 | 82829
93681 | New Transformer will be added Loma Alta. |  |  | Loma Alta | Loma Alta | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2025-07-24 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5943, 5962 | Y |  |  |  | 93682 | 93681
87479I | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Hyde Park to Downtown Ckt.32A to increase thermal limits as part of FRM upgrades |  | Kirby | Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47321, 47660 | Y | N |  |  | 87821 | 87479
87479E | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Jeanetta to WA Parish Ckt.64A to increase thermal limits as part of FRM upgrades |  | Jeanetta | WAP | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47300 | Y | N |  |  | 87825 | 87479
87479H | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Stadium to Fannin Ckt.08B to increase thermal limits as part of FRM upgrades |  | Stadium | Fannin | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 87824 | 87479
87479G | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Hyde Park to Downtown Ckt.32A to increase thermal limits as part of FRM upgrades |  | Hyde Park | Downtown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47510, 47690 | Y | N |  |  | 87823 | 87479
87479F | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Bellaire to Jeanetta Ckt.64B to increase thermal limits as part of FRM upgrades |  | Bellaire | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47000, 47300 | Y | N |  |  | 87822 | 87479
90232I | Facility Ratings Methodology (FRM) Upgrades | Upgrade Hyde Park to Downtown Ckt.32A to increase thermal limits as part of FRM upgrades |  | Hyde Park | Downtown | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 102820 | 90232
87479D | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits as part of FRM upgrades |  | Bellaire | WAP | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47000 | Y | N |  |  | 87820 | 87479
87479C | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Ckt.06D NASA to Webster to increase thermal limits as part of FRM upgrades |  | NASA | Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42970, 43500 | Y | N |  |  | 87819 | 87479
87479B | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Ckt.99A PH Robinson to Meadow to increase thermal limits as part of FRM upgrades |  | PH Robinson | Meadow | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Galveston | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 87818 | 87479
87479A | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits as part of FRM upgrades |  | PSARCO | BIGVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40190, 41305 | Y | N |  |  | 87817 | 87479
90730 | TNMP Willow 345kV Switching Station |  |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-08-15 |  | 345 | 0 | 0 | 0 |  | Robertson | Robertson | Tier 4 |  |  |  |  | 1624, 3400, 6310, 39950, 39960, 121035 | Y |  |  |  | 98761 | 90730
99859 | Addition of the Mainland to Vertus 138KV line. |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-09-04 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38830, 114512 | Y |  |  |  | 99860 | 99859
99956 | Addition of Harrell Ranch substation | Model of Harrell Ranch substation, load, and lines. |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-09-04 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38420, 38433, 38440 | Y |  |  |  | 99957 | 99956
71935 | Upgrade Hondo Creek to Castroville to 138kV | Upgrade Castroville sub to 138kV and line from Hondo creek to Castroville |  |  |  | Planned | 71917 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-09-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | 22RPG022 |  |  |  | 5804, 5807, 5808, 5810, 5819, 5821 | Y |  |  |  | 73097 | 71935
91494 |  |  |  | Perry | Perry | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-10-01 |  | 69 | 0 | 0 | 100 |  | Falls | Falls | Tier 4 |  |  |  |  | 91, 92 | Y |  |  |  | 91495 | 91494
76721 | Winding Oaks 138 kV Switch (Rayburn POI) | Establish Winding Oaks POD 138 kV Switch |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3095 | 2025-10-30 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 1751, 2626, 12704 | Y |  |  |  | 76722 | 76721
99546 | Establish Richland Chambers Generator Tie Line |  |  | Richland Chambers 345 kV Switch | Generator | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2025-10-30 |  | 345 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3134, 121123 | Y |  |  |  | 99547 | 99546
72566 | Cedar Valley to Friendship Storm Hardening | Rebuild single circuit section of Cedar Valley to Friendship and reconductor with bundled 795 ACSR Conductor, 440 MVA. Replaces Project ID 61268 |  | Cedar Valley | Friendship | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-11-30 |  | 138 | 0 | 4.3 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70506, 70507 | Y | N |  |  | 72567 | 72566
87475 | RCEC_Add_CavenderBus | Adding Cavender Bus, Load and Branch from Cavender to Cavender_P8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2145, 6861 | Y |  |  |  | 87476 | 87475
72588C | Trading Post to Cedar Valley Storm Hardening | Upgrading switch to bring line to full rating | [5 empty] | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70505, 70506 | Y |  |  |  | 91746 | 72588
55873 | Upgrade Moore to Hondo Creek 138 kV line | Replace the 336 ACSR with 1020 ACCC conductor while keeping the existing structures that still meet our standards. |  | Moore | Hondo Creek | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 138 | 0 | 13.5 | 0 |  | Medina | Frio | Tier 2 | 19RPG021 | 2019-11-20 | 2020-05-21 |  | 5819, 5827 | Y | N | Field engineering is still occurring due to short timeline for this upgrade. Details may change. | Current plan is to upgrade the line using mostly existing structures. Detailed field engineering is underway and could change the plan. | 55874 | 55873
93657 | Adds Monarch Gen Tie Switching Station |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37513, 37515, 37520, 155222 | Y |  |  |  | 98573 | 93657
82250 | Adds an additional line and energize load. | Adds a bundled double circuit line and energize both loads at Pilot Point bus #37365. |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2236, 37365 | Y |  |  |  | 99695 | 82250
70900D | Roanoke Area Upgrades | Establish Dunham 345 kV Switch |  | Dunham Switch | Dunham Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2025-12-14 |  | 345 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 646, 1421, 1730, 1849, 2081, 21851, 31875, 33646 | Y | N |  |  | 102861 | 70900
78363 | Gunter 345/138 kV Switch | Establish Gunter 345/138 kV Switch |  | Gunter |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3301 | 2025-12-15 |  | 345 | 0 | 0 | 600 | 75,0 | Collin |  | Tier 3 |  |  |  |  | 1730, 2235, 2236, 2373, 11735, 11757, 12235, 12468 | Y |  |  |  | 78364 | 78363
77174 | Rebuild Old Lake Sw - Ringgold Magnolia 69 kV line | Rebuild Old Lake Sw - Ringgold Magnolia 69 kV line |  | Old Lake Switch | Ringgold Magnolia | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3508 | 2025-12-15 |  | 69 | 0 | 13 | 0 |  | Clay | Montague | Tier 4 |  |  |  |  | 1524, 11541, 11545 | Y |  |  |  | 77175 | 77174
70900C | Roanoke Area Upgrades | Establish Exchange - Kingsridge 138 kV Double-Circuit Line |  | Exchange Switch | Kingsridge Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2025-12-15 |  | 138 | 3.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 12036, 12080, 12081, 112033 | Y | N |  |  | 102862 | 70900
66492A | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Jacksboro Amoco - Jacksboro Sinclair 69 kV Line |  | Jacksboro Sinclair | Jacksboro Amoco | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3006 | 2025-12-15 |  | 69 | 0 | 14 | 0 |  | Jack | Jack | Tier 4 |  |  |  |  | 1542, 1556, 1557, 1558 | Y |  |  |  | 72962 | 66492
72596C | PEC_MarshallFord_Paleface_StormHardening | Upgrade to terminal equipment and update to final circuit rating. Terminal end equipment update to be completed Fall 2024 based on original project schedule. (Replaces ERCOT Project # 61274C) | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC/LCRATSC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-15 |  | 138 | 0 | 11.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  |  | 73445 | 72596
72579A | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Mountain Top to Blanco 69 kV circuit to 138 kV with bundled 795 kcmil conductor (440 MVA). (Replaces ERCOT Project # 70367A) |  | Mountain Top | Blanco | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-19 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 7148, 70480, 70482, 70484 | Y | Y |  |  | 72580 | 72579
72574 | topo_update | Upgrade Junction from tap station to a three terminal ring bus. Replaces Project ID 63916. |  | NEW JUNCTION 70600 |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-25 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70600 | Y |  |  |  | 80916 | 72574
70665C | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits. Transmission portion of upgrade. |  | PSARCO | BIGVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40190, 40390, 40890, 41301, 48141, 113219 | Y | N |  |  | 98432 | 70665
75792 | New substation for generation interconnection project for 21INR0359 | New substation for generation interconnection project for 21INR0359 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 68035, 68040, 68091 | Y |  |  |  | 75793 | 75792
75788 | This project will intercept the second circuit of a common tower at Reata station. | This project will intercept the second circuit of a common tower at Reata station. |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | Eastland | Eastland | Tier 4 |  |  |  |  | 68008, 68011, 68051, 153635 | Y |  |  |  | 75789 | 75788
72651 | Add_Josephine_Load | Tapping the Nevada and Shelby transmission line, and adding Josephine Load. | [5 empty] | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 991, 6991 | Y |  |  |  | 76031 | 72651
91774 | Janka: Construct New 345 kV Station | Interconnect the Evergrid load to the new Janka 345 kV station on the Edith Clarke to Tesla 345 kV line |  | Edith Clarke | Tesla | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TP2025126 | 2026-01-08 |  | 345 | 0.2 | 0 | 0 |  | Hardeman | Hardeman | Tier 4 |  |  |  |  | 60139, 60501, 60505, 61616 | Y | N |  |  | 91775 | 91774
73408 | Odysseus: Build new 345 kV station | Interconnect Ulysses Solar to the Odysseus 345 kV Station on the Bluff Creek to SA Red Creek 345 kV line |  | Odysseus |  | Planned |  | AEP TNC | Zach Lachiusa twang1@aep.com 918-599-2635 |  | 2026-01-08 |  | 345 | 0 | 0 | 0 |  | Coke |  | Tier 4 |  |  |  |  | 6444, 60040, 60072 | Y | N |  |  | 73409 | 73408
72935 | Saragosa: Install 2nd Bay | Install 2nd Bay at Saragosa Substation |  | Saragosa |  | Planned |  | AEP TNC | Damian Raab twang1@aep.com 918-599-2635 |  | 2026-01-08 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60716 | Y | N |  |  | 72936 | 72935
50845 | Kinnison: Expand 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | In-Service Date Update | Kinnison |  | Under Construction | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2797 | 2026-01-08 |  | 138 | 0 | 0 | 130 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 6604, 6607, 6611, 60431, 60432 | Y | N |  |  | 65545 | 50845
63635 | Tribute: Build 138 kV Station | Build new 138 kV Station on the San Angelo Power to Red Creek 138 kV line |  | Tribute |  | Planned | 1132 - 1310 | AEP TNC | Larry Brown twang1@aep.com 918-599-2635 | 1877 | 2026-01-08 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6442, 6473, 60008 | Y | N |  |  | 63636 | 63635
45174 | Ollin to LCRA Crane: Partial Build, Partial Rebuild, and Conversion | Build new Ollin 138 kV station; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage |  | Ollin | LCRA Crane | Planned | 939 - 1117 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 2767 | 2026-01-08 01:00 |  | 138 | 0.52 | 0 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6600, 6605, 6606, 6610, 6613, 6668, 6669, 60428, 60429, 60431, 60432, 60441, 76615 | Y | N |  |  | 65527 | 45174
51012 | Kinnison to Sage: Rebuild 69 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | In-Service Date Update | Kinnison | Sage | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2823 | 2026-01-08 01:00 |  | 69 | 0 | 0.25 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-17 |  | 6604, 60431 | Y | N |  |  | 65555 | 51012
76214 | North Edinburg: 345 kV Reconfigure | Reconfigure North Edinburg 345 kV station: 2nd reactor |  | North Edinburg |  | Planned |  | AEP TCC | Curtis Brown jlsolis@aep.com 361-881-5574 | TP2019168 | 2026-01-09 |  | 345 | 0 | 0 | 0 | -50,0 | Hidalgo |  | Tier 4 |  |  |  |  | 5660, 8341, 8383, 8452, 8455, 8901, 8905 | Y |  |  |  | 76215 | 76214
76151 | Gas Pad Tap: Replace CTVT | Replace CTVT combination unit at Gas Pad station along the Lote Bush to Yucca Drive 138 kV line | In-Service Date Update | Gas Pad Tap |  | In-Service |  | AEP TNC | Bill Edwards twang1@aep.com 918-599-2635 |  | 2026-01-09 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 11245, 60397 | Y | N |  |  | 76152 | 76151
70779 | Tortuga: Install Cap Bank | Install a 23.0 MVAR capacitor bank at the Tortuga 138 kV station |  | Tortuga |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2022188 | 2026-01-09 |  | 138 | 0 | 0 | 0 | 0,23 | Nueces |  | Tier 4 |  |  |  |  | 8697 | Y |  |  |  | 70780 | 70779
68252 | Lobo: Line settings | Interconnect Guajillo to the Lobo 345 kV station | Owner and Contact Update | Lobo |  | Under Construction |  | ETT | Glen Reed gareed@aep.com 918-599-2664 |  | 2026-01-09 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219, 163223 | Y |  |  |  | 68253 | 68252
50868 | Rosata - Structure 31/8: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild | IN-SERVICE | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown mlforcum@aep.com 918-599-2674 | 3780 | 2026-01-09 |  | 138 | 0 | 15.5 | 0 |  | Goliad | Karnes | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8153, 8186 | Y | N |  |  | 50869 | 50868
57906 | Laredo to University: Rebuild 138 kV Line | Reconductor the Del Mar to University 138 kV line |  | Laredo | University | Under Construction | 1119 - 1297 | AEP TCC | Bradley Case jlsolis@aep.com 361-881-5574 | 3838 | 2026-01-10 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645, 8647 | Y | N |  |  | 65579 | 57906
90004 | Juncus: Construct New 69 kV Temporary Tap | Interconnect the TEC Snodgrass load to the new Juncus 69 kV temporary tap on the Abilene South to Steamboat 69 kV line |  | Juncus |  | Planned |  | AEP TNC | Bill Edwards twang1@aep.com 918-599-2635 | TP2023074 | 2026-01-10 |  | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6326, 6328, 60002 | Y | Y |  |  | 91319 | 90004
71879 | Update Ratings |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0939b | 2026-01-22 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5133, 5371 | Y |  |  |  | 71880 | 71879
91565 |  |  |  | Navarro Mills Tap | Navarro Mills | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-01-23 |  | 69 | 0 | 1.1 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 186, 3511 | Y |  |  |  | 91566 | 91565
70536 | New 138 kV Verde Circle Substation | New 138 kV Verde Circle Substation looping into existing 138 kV Westover Hills and VLSI line. |  |  |  | Planned | T-0316 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0971 | 2026-01-28 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5466, 5467, 5488 | Y |  |  |  | 70537 | 70536
81274 | Ranger Camp – Cattleman 345 kV Double-Circuit Line | Construct a new 345 kV double-circuit line from Ranger Camp to Cattleman |  | Ranger Camp | Cattleman | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8648 | 2026-01-30 |  | 345 | 6.8 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 10053 | Y |  |  |  | 81275 | 81274
87344 | Addicks 345kV to White oak Ckt.71B Upgrades | Upgrade Ckt.71B Addicks to White Oak to increase thermal limits |  | Addicks | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-30 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45600, 46600 | Y | N |  |  | 87345 | 87344
76350 | Install new TARGA 138kV customer substation as Ckt.86 Jordan to TARGA to CITIES. | Install new TARGA 138kV customer substation as Ckt.86 Jordan to TARGA to CITIES. |  | TARGA | Jordan/CITIES | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40340, 40855, 40950 | Y | N |  |  | 100086 | 76350
69463 | Gulch: Construct new 345 kV Station | Interconnect Arroyo Solar to the new Gulch 345 kV station on the La Palma to Rio Hondo 345 kV line |  | Gulch |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2026-01-30 |  | 345 | 0.1 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8317, 8318, 8704, 8705 | Y |  |  |  | 70802 | 69463
72040B | Blueridge to WA Parish Ckt.02A Upgrades (22RPG041) | Upgrade portions of Ckt.02A Blueridge tap to DEWALT (P1048-3) as a Hardening upgrade. |  | Blueridge | DEWALT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 2.94 | 0 |  | Harris | Fort Bend | Tier 4 | 22RPG041 | 2022-11-21 | 2022-12-15 | 2022-12-15 | 44180, 48163 | Y | N |  | Cost included in main entry | 91116 | 72040
72063 | Moody to Stewart Ckt.63 Upgrades P1041 | Reconductor portions of Ckt.63 Stewart to West Galveston as a Hardening project |  | Stewart | West Galveston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 3.97 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42950, 42951 | Y | N |  |  | 72064 | 72063
99399 | TH Wharton CB2 Cap Bank | Remove 120 MVAR CB1 cap bank from Velasco substation. Install removed CB1 cap bank at TH Wharton substation as replacement for THW CB2. |  | Velasco | TH Wharton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 43360, 45515 | Y | N |  |  | 99400 | 99399
78476 | Waterhole 345kV Substation - Gulf Star Storage - Generator Interconnection (23INR0460) | Install Gulf Star Storage at Waterhole 345kV substation. Connect at the same generator lead as Gulf Star Solar (Gulf Star Storage - 23INR0460) |  | Waterhole |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44880, 112878 | Y | N |  |  | 98397 | 78476
86011 | Snug 138kV Substation expansion for Cottonwood Bayou Storage (21INR0443) | Install Cottonwood Bayou Storage (21INR0443) at Snug 138kV substation. Connect at the same generator lead as Cottonwood Bayou Solar. |  | Snug |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 44890, 113435 | Y | N |  |  | 86012 | 86011
90232C | Facility Ratings Methodology (FRM) Upgrades | Upgrade Ckt.06D NASA to Webster to increase thermal limits as part of FRM upgrades |  | NASA | Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42970, 43500 | Y | N |  |  | 102823 | 90232
90232F | Facility Ratings Methodology (FRM) Upgrades | Upgrade Bellaire to Jeanetta Ckt.64B to increase thermal limits as part of FRM upgrades |  | Bellaire | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47000, 47300 | Y | N |  |  | 102824 | 90232
76194 | Angstrom: Construct New 345 kV Terminal | Interconnect Pintail Pass BESS to the Angstrom 345 kV station | Company Contact and In-Service Date Update | Angstrom |  | Planned |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2023132 | 2026-01-31 |  | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8249, 8956 | Y |  |  |  | 76195 | 76194
80630 | Angstrom to STP: Increase 345 kV Line MOT | Increase the MOT on the Angstrom to STP 345 kV line | Status and In-Service Date Update | Angstrom | STP | Under Construction | TA2024200 | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 |  | 2026-01-31 |  | 345 | 0 | 0 | 0 |  | San Patricio | Matagorda | Tier 4 |  |  |  |  | 5915, 8249, 8676 | Y |  |  |  | 80631 | 80630
80508 | Kilby: Construct New 345 kV Station | Interconnect Quantum Solar to the new Kilby 345 kV station on the Clear Crossing to Pendulo 345 kV line | Company Contact, In-Service Date, and Dollars Update | Kilby |  | Planned | TP2023844 | ETT | Dave Goetz myturner@aep.com 918-599-2437 |  | 2026-01-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60089, 60507, 60514, 145568 | Y | N |  |  | 80509 | 80508
80572 | Miel: Construct New 138 kV Station | Interconnect Nightfall Solar to the new Miel 138 kV station on the Razorback to Uvalde 138 kV line |  | Miel |  | Planned | TP2023841 | ETT | Zachary Lachiusa jlsolis@aep.com 361-881-5574 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 4 |  |  |  |  | 8234, 8707, 8747 | Y | N |  |  | 80573 | 80572
99187 | This involves moving Harmony to a different bus/bay at Hill Country to alleviate the loading on HC auto 3 & 4. | Move Harmony - Hill Country from Auto 3&4 to Hill Country Auto 1&2. This involves moving Harmony to a different bus/bay at Hill Country to alleviate the loading on HC auto 3 & 4. |  | 5195 | 5210 | Planned | S-1053a, T-0411 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5195, 5208, 5210 | Y |  |  |  | 99188 | 99187
90232E | Facility Ratings Methodology (FRM) Upgrades | Upgrade Jeanetta to WA Parish Ckt.64A to increase thermal limits as part of FRM upgrades |  | Jeanetta | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47300 | Y | N |  |  | 102821 | 90232
90232D | Facility Ratings Methodology (FRM) Upgrades | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits as part of FRM upgrades |  | Bellaire | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44005, 47000 | Y | N |  |  | 102822 | 90232
66200D | Upgrade Taylor - Holland 69 kV Line | Rebuild the Granger - Taylor 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6173 | 2026-01-31 |  | 69 | 0 | 5.9 | 0 |  | Williamson | Williamson | Tier 4 | 22RPG036 |  |  |  | 118, 3648, 3649, 13647 | Y |  |  |  | 71897 | 66200
86013 | Fairmont Distribution Reconfigurations with 4th Transformer | Install fourth Fairmont distribution transformer on Ckt.95F to create new Ckt.95F SOUTH to Fairmont TR4 tap to Clear Lake tap to Polaris tap to Kemah tap to PH Robinson 138kV North. Remove Fairmont TR3 from Ckt.95F and onto the Ckt.35A Fairmont line position. |  | Fairmont |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42610, 42613, 42614, 48108, 742613 | Y | N |  |  | 87387 | 86013
86015 | King Substation - Add 3rd Distribution Transformer | Install the third King distribution transformer. Tap on Ckt.86E to create new Ckt.86E Newport to King tap to Jonte. |  | King | Newport/Jonte | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40912, 41150, 45660, 48182 | Y | N |  |  | 100273 | 86015
78425 | Danbury to LONG / Longbow BESS (25INR0328) | Expand facilities at customer-owned LONG substation for Longbow BESS (25INR0328). Utilize existing generator lead LONG to Longbow Solar. |  | DANBUR | LONG | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42875, 112662 | Y | N |  |  | 98396 | 78425
90157 | NRG THW GT at TH Wharton 345kV (24INR0482) | Install NRG THW GT at TH Wharton 345kV substation. Connect at the same generator lead as 05THWGEN |  | TH Wharton |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 90159 | 90157
81006 | DIABOX Customer Load Addition with related line upgrades | Upgrade Ckt.21E MOMENT to SOLMER to SR Bertron to increase thermal limits |  | SOLMER | SR Bertron/ MOMENT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 2.12 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40480, 41090, 41400, 41480 | Y | N |  |  | 81007 | 81006
73371B | BP24 Sub Upgrades | Upgrade Bellaire Auto A5 CTs to increase thermal limits |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47000, 47015, 49003 | Y | N |  |  | 89979 | 73371
73352C | PH Robinson Area 138kV Upgrades | Increase thermal limits through the application of 110% Emergency ratings for Ckt.79C BIGBAY to BAYOU. Request customers to approve the 110% Emergency rating of relevant equipment at Bigbay substation on the Ckt.79C line position. Bayou substation equipment has been upgraded and meets the Minimum ratings as of April 2025. |  | BIGBAY | BAYOU | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42160, 42180 | Y | N |  |  | 73355 | 73352
86009 | Expand ADLONG substation for XE Murat Storage (24INR0329) | Expand facilities at customer-owned ADLONG substation for XE Murat Storage (24INR0329). Utilize existing generator lead Eastgate to XE Murat Solar. |  | Eastgate | ADLONG | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40690, 113542 | Y | N |  |  | 98398 | 86009
50866 | Structure 31/8 - Kenedy SS: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown mlforcum@aep.com 918-599-2674 | 3779 | 2026-01-31 01:00 |  | 138 | 0 | 14.3 | 0 |  | Karnes | Karnes | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8153, 8186 | Y | N |  |  | 50867 | 50866
44946 | CPSE_New_Scenic_Loop_138kV_Load_Serving_Station | The new Scenic Loop 138 kV load serving station will be looped into existing Ranchtown to LCRA (Menger Creek) 138 kV transmission line. The substation should be located south west of the existing Fair Oaks Ranch and north east of the existing Ranchtown substation. |  |  |  | Planned | S-0885 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0275 | 2026-01-31 20:00 |  | 138 | 9 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5358, 5363, 7665 | Y |  |  |  | 44947 | 44946
87508 | RCEC_BranchChanges_Kaufman_Update2 | Modifying branch impedance between ROSHILRC and TALTY_RC |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-02-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6894, 6902 | Y |  |  |  | 87509 | 87508
88046 | Rebuild Omicron to Rafter |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-02-03 |  | 138 | 0 | 1.7 | 0 |  | Bexar | Medina | Tier 2 |  |  |  |  | 5326, 5355 | Y |  |  |  | 88047 | 88046
73364 | CPSE_New_Omicron_Substation |  |  |  |  | Planned | T-350, S-0975 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-02-03 |  | 138 | 0 | 0 | 0 |  | Bexar |  | Tier 4 |  |  |  |  | 5055, 5326, 5355 | Y |  |  |  | 73365 | 73364
91285 | TNMP Lago Mar Substation |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-02-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38815, 38820, 38850 | Y |  |  |  | 91286 | 91285
73661 | New transformer (T2) at BPUB Palo Alto Substation | Adding load (T2) on bus 5965 Palo Alto. |  | BPUB Palo Alto 5965 |  | Planned |  | BPUB/BROWNSVILLE PUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2026-02-27 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 5965 | Y | N |  |  | 80506 | 73661
90232B | Facility Ratings Methodology (FRM) Upgrades | Upgrade Ckt.99A PH Robinson to Meadow to increase thermal limits as part of FRM upgrades |  | PH Robinson | Meadow | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-02-28 |  | 345 | 0 | 0 | 0 |  | Galveston | Brazoria | Tier 4 |  |  |  |  | 42000, 43030 | Y | N |  |  | 102825 | 90232
68150 | Abilene South to Estes: Rebuild 138 kV Line | Rehab Abilene South to structure 33/7 |  | Abilene South | Estes | Under Construction |  | AEP TNC | Forrest Farson myturner@aep.com 918-599-2437 |  | 2026-02-28 | 2958101 | 138 | 0 | 18.3 | 0 |  | Taylor | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6260, 6313, 60063, 60336, 60355, 60365, 60773, 61015 | Y | N |  |  | 68151 | 68150
71926 | Upgrade BURNS to Heidelberg line | Upgrade BURNS to Heidelberg line to be 478MVA capable |  | Burns | Heidelberg | Planned | 7192871930 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-03-01 |  | 138 | 0 | 10 | 0 |  | Cameron | Hidalgo | Tier 4 |  |  |  |  | 5763, 5765 | Y |  |  |  | 71927 | 71926
87497 | RCEC_BranchChanges_Kaufman__Update1 | Modifying branch impedance between Boze and Scury_RC |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6903, 6908 | Y |  |  |  | 87498 | 87497
80384 |  | Reconductor Gibbons Creek to Greens Prairie Line |  | Gibbons Creek | Greens Pairie | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-03-01 |  | 138 | 0 | 12.9 | 0 |  | Grimes | Brazos | Tier 4 |  |  |  |  | 964, 32878 | Y |  |  |  | 80385 | 80384
78357 | Wilmer 345/138 kV Switch | Establish Wilmer 345/138 kV Switch |  | Wilmer |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4369 M4371 M4372 | 2026-03-02 |  | 345 | 0 | 0 | 1200 | 0,220.8 | Dallas |  | Tier 1 | 24RPG022 | 2024-07-02 | 2024-07-29 |  | 2261, 2342, 2344, 2427, 2429, 2432, 2967, 3083, 3084, 3085, 13082, 23082 | Y |  |  |  | 78373 | 78357
70900E | Roanoke Area Upgrades | Establish Ramhorn Hill 345 kV Switch and Ramhorn Hill – Dunham 345 kV Double-Circuit Line |  | Dunham Switch | Ramhorn Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2026-03-15 |  | 345 | 36.8 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 12067, 12068 | Y | N |  |  | 102863 | 70900
66473 | Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line | Upgrade the Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line |  | Mesquite East | Oates | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4137 | 2026-03-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 831, 2742, 2747, 2756, 2764, 2765, 2766, 2767 | Y |  |  |  | 66475 | 66473
66188 | Cedar Crest - Dealey - West Levee 138 kV Line | Upgrade the existing 138 kV Line |  | Ceadr Crest | West Levee | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4212 | 2026-03-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2400, 2493, 2842 | Y |  |  |  | 66189 | 66188
71985 | Cypress Water 138 kV Switch | Rebuild the existing Northlake(Cypress Waters) 138 kV Switch |  | Northlake |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4353 | 2026-03-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 2362, 2363, 2367, 2385, 2386, 2390, 2395, 2587 | Y |  |  |  | 73110 | 71985
62643 | Rebuild Waco East 138 kV Switch | Rebuild Waco East 138 kV Switch |  | Waco East | Waco East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6146 | 2026-03-15 | 2958101 | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3434, 3438, 3439, 3443, 3452, 3481, 3482, 3551, 3559, 3708, 13438 | Y |  |  |  | 62664 | 62643
87395 | Caldwell Substation Addition | LCRA TSC will build a new substation, Caldwell Substation, to manage 12 MW of load in the summer of 2024. This substation will be on the Cooks Point - Lyle Wolz 138-kV transmission line. The new substation will be approximately 5 miles south of Cooks Point substation. LCRA will install circuit breakers in a ring bus formation |  | Caldwell | Caldwell | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2026-03-16 01:00 |  | 138 | 0 | 0 | 0 |  | Burleson | Burleson | Tier 4 |  |  |  |  | 7566, 7567, 7569 | Y | N |  |  | 87396 | 87395
70660 | Plaza to Grant Ckt.08I Upgrade | Install parallel underground portion of Ckt.08I Plaza to Grant to increase thermal limits. |  | Plaza | Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-03-29 00:10 |  | 138 | 0 | 0.44 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47110, 47350 | Y | N |  |  | 98382 | 70660
76139 | Juncus: Construct New 69 kV Station | Interconnect the TEC Snodgrass load to the new Juncus 69 kV station on the Abilene South to Steamboat 69 kV line |  | Juncus |  | Planned |  | AEP TNC | Bill Edwards myturner@aep.com 918-599-2437 | TP2023074 | 2026-03-31 |  | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6326, 6328, 60002 | Y | Y |  |  | 76140 | 76139
72942 | Bluff Creek: 138 kV Station Work | Replace fourteen (14) 138 kV Breakers and one (1) Circuit Switcher | Company Contact and In-Service Date Update | Bluff Creek |  | Planned |  | AEP TNC | Remington Hajdik myturner@aep.com 918-599-2437 |  | 2026-03-31 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6216, 6260, 6351, 60040, 60043, 66216, 66217, 180455, 180463 | Y | N |  |  | 72943 | 72942
65683 | To add Open Sky Station | To interconnect GINR 20INR0241 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-03-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68001, 68004, 68014, 183452, 184183 | Y | N |  |  | 65684 | 65683
90964 | Tier 3 project to add second autotransformer at Long Draw |  |  | Long Draw 345 kV | Long Draw 138 kV | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2026-03-31 |  | 345 | 0.5 | 0 | 706 |  | Borden | Borden | Tier 3 | 24RPG027 | 2024-08-28 | 2024-09-20 |  | 59900, 59906, 59991 | Y |  |  |  | 90965 | 90964
80319 | Devine: Install Cap Bank | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch |  | Devine |  | Planned |  | ETT | Will Simmons jlsolis@aep.com 361-881-5574 |  | 2026-03-31 |  | 138 | 0 | 0 | 0 | 0,23 | Medina |  | Tier 4 | 23RPG024 | 2024-08-23 | 2024-09-23 |  | 8732 | Y |  |  |  | 80322 | 80319
73025 | CPSE_New_Shaula_POI | [6 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-03-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5133, 5380, 5915 | Y |  |  |  | 73026 | 73025
92646 | Oncor_MNE_92646_Saddlewood 138 kV Switch |  |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-03-31 |  | 138 | 0 | 0 | 0 |  | Hunt | Hunt | Tier 4 |  |  |  |  | 1815, 1819, 2843 | Y |  |  |  | 92647 | 92646
69888A | Deepwater to Clinton Ckts.33B-33C Line Upgrades | Fully reconductor Ckt.33B Deepwater to Texpet Switchrack to Harrisburg ahead of future 138kV conversions. |  | Deepwater | Harrisburg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-03-31 |  | 69 | 0 | 3.82 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40470, 40800, 41560, 41561 | Y | N |  |  | 91910 | 69888
70880 | Rebuild Carancahua -TinTop | Rebuild Carancahua to TinTop with 795ACSR |  | Carancahua | Tin Top | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-04-01 |  | 69 | 0 | 12.93 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5569, 5570, 5571, 5573 | Y |  |  |  | 70881 | 70880
91911 | Establish Gristmill 345 kV Switch | Establish Gristmill 345 kV Switch for Yaupon Solar and Storage |  | Gristmill | Gristmill | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6232 | 2026-04-16 |  | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3706, 3765, 39950 | Y |  |  |  | 91912 | 91911
92625 | Oncor_ME_TILLMAN 138 kV Switch |  |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-04-30 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2534, 2856, 12585 | Y |  |  |  | 92626 | 92625
88867 | Rosita Creek Substation 138-kV T2 Power Transformer Addition. Replacing Committed project 57343 | Add second 138/13.09-kV power transformer bay with new 138-kV transmission switch and circuit switcher interconnected at LCRA Switch# 12669. New power transformer capacity will be 15/20/25 MVA. Replaces committed project 57343. | Recent projected load increases beyond ALDR. Justification is to provide on-site backup power source for new and existing critical medical center, governmental and educational facility loads. Power transformer lead-time increases. | Rosita Creek | Rosita Creek | Planned |  | RGEC | Ruben Quiroga rquiroga@rgec.coop 830-291-4203 |  | 2026-04-30 | 2025-09-01 | 138 | 0 | 0 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 78015 | Y |  |  |  | 88868 | 88867
99744 | Laredo VFT North: 138 kV Breaker Addition | Install additional 138 kV breaker on the Lobo circuit #1 138 kV terminal at the Laredo VFT North 138 kV station | In-Service Date Update | Laredo VFT North |  | Planned | TP2023630 | ETT | Remington Hajdik jlsolis@aep.com 361-881-5574 |  | 2026-04-30 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 | [5 empty] | Y |  |  |  | 99745 | 99744
1275 | Hawkins to Gainesville | Hawkins to Gainesville |  | Hawkins | Gainesville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-04-30 | 2026-11-01 | 69 | 0 | 6.72 | 80 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 705, 706, 707, 726, 33705, 33726 | Y |  |  |  | 67891 | 1275
69489 | Shepley: Construct New Distribution Station | Construct new distribution station on the Victoria to Dupont Switch 138 kV line | In-Service Date Update | Shepley |  | Under Construction |  | AEP TCC | Will Simmons deevans@aep.com 918-599-2938 |  | 2026-04-30 |  | 138 | 0 | 0 | 50 |  | Victoria |  | Tier 4 |  |  |  |  | 8143, 8172, 8719 | Y |  |  |  | 69490 | 69489
64581D | New 138kV Waterfowl substation | Install new CEHE-owned 138kV Waterfowl (WTR) substation. Remove existing Seaway Switchrack. Reconfigure existing Ckt.02F to create new Ckt.02L Waterfowl to Franklins Camp. |  | Waterfowl | Franklins Camp | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-04-30 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 5568, 43470 | Y | N |  | Cost included in main entry | 102647 | 64581
99904 | Install a new 138kV transmission line approximately .1 miles long to connect the generator’s interconnection facilities to Leon Creek Switchyard. |  |  | 5260 | 171073 | Planned | S-0977, T-0335 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-05-01 |  | 138 | 0.13 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5260, 171073 | Y |  |  |  | 99905 | 99904
75255F | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5260, 5385 | Y |  |  |  | 75960 | 75255
72582C | Nameless to Leander Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. (Replaces ERCOT Project # 61279C) | 1/10/2023: Added information to clarify circuit rating. | Hero Way | Nameless | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-05-01 | 2026-05-01 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70526, 70536 | Y | N |  |  | 72585 | 72582
70884 | Rebuild Rio Colorado - Bay City | Rebuild Rio Colorado - Bay City 795 ACSR |  | Rio Colorado | Bay City | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 9.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5560, 5563 | Y |  |  |  | 70885 | 70884
78483 | Rebuild Nada to El Campo 69 kV line | Rebuild Nada to El Campo 69 kV line from 4/0 to 795. 2023 RTP |  | Nada | El Campo | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 15.44 | 0 |  | Colorado | Wharton | Tier 4 |  |  |  |  | 5536, 5538 | Y | N |  |  | 78484 | 78483
102871 | Add Fort Bobcat load serving station and Tline to STEC Orange Grove |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 138 | 1 | 0 | 0 |  | Nueces | Nueces | Tier 4 | [5 empty] | Y | N |  |  | 102872 | 102871
82851 | Adds TNMP White Oak Substation |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39580 | Y |  |  |  | 82852 | 82851
70882 | Rebuild Olivia - Carancahua | rebuild Olivia sw to Carancahua 795 ACSR |  | Olivia SW | Carancahua | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 8.71 | 0 |  | Jackson | Matagorda | Tier 4 |  |  |  |  | 5573, 5574 | Y |  |  |  | 70883 | 70882
89957 | RCEC_Commerce_South_Load | Adding Commerce South Bus, Load and Branch from Saddle to Comm_S1_8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 2843, 6856 | Y |  |  |  | 89958 | 89957
91847A | Hornsby Load Power Transformer Addition |  |  | Honrsby |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8186 | 2026-05-08 |  | 345 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7047 | Y |  |  |  | 91956 | 91847
1205 | Planned reconductor from Hasse to Gustine | Planned reconductor from Hasse to Gustine |  | HASSE | GUSTINE | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-05-14 |  | 69 | 0 | 7.34 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 273, 277 | Y |  |  |  | 54001 | 1205
89986 | Mule Deer 345 kV Switch | Establish Mule Deer 345 kV Switch |  | Windmill | Wallaby | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3031 | 2026-05-14 |  | 345 | 0 | 0 | 0 |  | Deaf Smith | Deaf Smith | Tier 4 |  |  |  |  | 23909, 23910, 23921 | Y |  |  |  | 89987 | 89986
87799 | Old Country 345 kV Switch | Old Country 345 kV Switch |  | Old Country |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4172 | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 1906, 2255, 3376 | Y |  |  |  | 87800 | 87799
76652 | Line Termination at Cypress Waters | Vineyard Switch – Hackberry Switch 138 kV Line Termination at Cypress Waters 138 kV Switch |  | Cypress Waters |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5344 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2017, 2386, 2392 | Y |  |  |  | 76653 | 76652
92867 | Oncor_ME_Renner Switch – Plano West Switch 138 kV Double-Circuit Line | Upgrade Renner Switch – Plano West Switch 138 kV Double-Circuit Line |  | Renner | Plano West | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4246 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2352, 2353, 2669, 2670, 2671, 2673 | Y |  |  |  | 92869 | 92867
92854 | Oncor_ME_Carrollton East Switch-Carrollton Tarpley Rd 138 kV Double-Circuit Line Section | Carrollton East Switch-Carrollton Tarpley Rd 138 kV Double-Circuit Line Section |  | Carrollton East | Carrollton Tarpley Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4246 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2558, 2559, 2577, 2578 | Y |  |  |  | 92855 | 92854
92680 | Oncor_ME_Stainback 345 kV Switch | Establish Stainback 345 kV Switch |  | Stainback 345 kV Switch |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2217, 2427, 2466, 3159 | Y |  |  |  | 92681 | 92680
88035 | Pastores 138 kV Switch | Construct a new 138 kV Switch |  | McDonald Road | Catclaw/Mudstone | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8817 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 1225, 1333, 10121, 11222 | Y |  |  |  | 88040 | 88035
71178 | Seagoville-Watermill 138 kV Line | Rebuild Seagoville-Watermill 138 kV Line |  | Seagoville | Watermill | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4081 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 2429, 2434, 3076, 3077, 3079, 3083 | Y |  |  |  | 71179 | 71178
7126 | Renner TPL 138 kV Capacitors | Upgrade existing capacitor banks |  | RENNER SWITCH | RENNER SWITCH | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3048 | 2026-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas | Dallas | Tier 4 |  |  |  |  | 2352, 2353 | Y | N |  |  | 14964 | 7126
92849 | Oncor_ME_92849_Renner Switch 138kV Capacitor Bank | Install Capacitor Banks at Renner switch |  | Renner Switch | Renner Switch | Planned | M4021 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 | 0,220 | Collin | Collin | Tier 4 |  |  |  |  | 2352, 2353 | Y |  |  |  | 92864 | 92849
62666C | Upgrade and convert McGregor - Waco West Line | Rebuild the Bewley - McGregor Phillips Tap Line |  | Bewley Sub | McGregor Phillips Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6172 | 2026-05-15 |  | 69 | 0 | 4 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3372, 3594 | Y |  |  |  | 93107 | 62666
82810C | Olympus 138 kV Switch | Establish POI for Gaia Solar |  | Olympus | Gaia | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6330 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3723, 153963 | Y |  |  |  | 100066 | 82810
78361A | Lake Creek - Rattlesnake Road 345 kV Line | Establish Lake Creek Switch - St Johns 345 kV Line, rebuild the Lake Creek Switch - Rattlesnake Road 345 kV Line, and install second circuit from Lake Creek Switch - Rattlesnake Road Switch |  | Lake Creek | Rattlesnake Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6276 | 2026-05-15 |  | 345 | 0 | 5.1 | 0 |  | McLennan | McLennan | Tier 3 |  |  |  |  | 3384, 3399, 3409 | Y |  |  |  | 81575 | 78361
87804 | Establish Notus 345 kV Switch | Establish Notus 345 kV Switch |  | Notus Switch | Notus Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6371 | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 1906, 3376, 68091 | Y |  |  |  | 87805 | 87804
91534 | Establish Glaze Lake 138 kV Switch | Establish Glaze Lake 138 kV Switch for Leon Solar |  | Glaze Lake 138 kV Switch | Glaze Lake 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6345 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Leon | Leon | Tier 4 |  |  |  |  | 3355, 3357, 3790 | Y |  |  |  | 91535 | 91534
72576B | Lago Vista to Nameless Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. (Replaces ERCOT Project #61277B) | 1/10/2023: Added information to clarify circuit rating. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70352, 70526 | Y | N |  |  | 72578 | 72576
80921 | Downtown Kyle Substation Addition | Models the addition of a planned substation in Kyle area. |  | DOWNTOWN KYLE 70503 |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 70198, 70502, 70503 | Y |  |  |  | 80922 | 80921
99185 | This involves moving Potranco to a different bus/bay at Cagnon to alleviate the loading on Cagnon auto 3 & 4. | Move Potranco - Cagnon from Auto 3 & 4 to Cagnon Auto 1 & 2. This involves moving Potranco to a different bus/bay at Cagnon to alleviate the loading on Cagnon auto 3 & 4. |  | 5346 | 5055 | Planned | S-1053b, T-0412 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5053, 5055, 5346 | Y |  |  |  | 99186 | 99185
71950 | Twin Buttes Load 138-KV Circuit Breaker Addition | Provide a 138-kV point of interconnection at the Twin Buttes Substation to connect to a new Golden Spread Electric Cooperative Transmission line. Update contingencies |  | Twin Buttes |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 | [5 empty] | Y | N |  |  | 78299 | 71950
70534 | Hueco Springs Substation Addition | NBU is constructing a new 138-kV substation to serve a new residential development. LCRA TSC will provide transmission service to the new load serving substation on the T235 Henne to Comal. |  | Henne | Comal | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7174, 7176, 7179 | Y | N |  |  | 70535 | 70534
70196 | Kingsland 1 - Sandy Creek Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 7.3-mile Kingsland 1 ¿ Sandy Creek (T400) 69-kV transmission line. |  | Kingsland 1 | Sandy Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 |  | 69 | 0 | 7.3 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7121, 7400, 7404 | Y | Y |  |  | 70197 | 70196
78408 | Henne Substation Bus Upgrade | LCRA TSC intends to build a new 138 kV line from Henne to Kohlenberg and accommodate this line at Henne. Henne substation will be converted to a breaker and half configuration to improve reliability and support the project. |  | Henne | Henne | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 | 2026-05-06 | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7172, 7173, 7174, 7176, 7182 | Y | N |  |  | 78411 | 78408
92629 | Gabriel - Rivery MLSE Upgrade | Remove an MLSE on T457 Gabriel - Rivery 138-kV transmission line to achieve the full conductor rating. |  | Gabriel Substation |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-762-3658 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7346, 7347 | Y |  |  |  | 92630 | 92629 | 2023-SC17
92575 | LCRATSC_Canyon_San_Marcos_Transmission_Line_Upgrade |  |  | 7192 | 7200 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org | PLC-7656 | 2026-05-15 | 2026-04-17 | 138 | 0 | 2.8 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7192, 7200, 70502 | Y |  |  |  | 92576 | 92575 | 2024-SC1
92598 | Bluebonnet - Wyldwood Transmission Line Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee. |  | 7210 | 7556 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org | PLC-6949 | 2026-05-15 |  | 138 | 0 | 2.43 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7210, 7556 | Y |  |  |  | 92599 | 92598 | 2024-SC20
73106 | Lockhart - San Marcos Transmission Line Conversion | The five LCRA TSC-owned transmission line sections from Lockhart to San Marcos will be converted to 138-kV (T220 San Marcos to Camp Gary to Robert Brown Jr., T519 Robert Brown Jr. to Clear Fork, and T601 Clear Fork to Lockhart). |  | Lockhart | San Marcos | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Hays | Tier 4 |  |  |  |  | 7188, 7191, 7192, 7194, 7195, 7196, 7215, 7216 | Y | N |  |  | 78513 | 73106 | 2023-SC11
85963 | FPP Yard 2 - Lytton Springs Transmission Line Overhaul | LCRA TSC will overhaul FPP Yard #2 - Lytton Springs 345-kV transmission line T255 to ensure structural integrity of the circuit. Engineering will review this transmission circuit for scope including hardware/insulator integrity, structural load issues, need for containment (dead-ends) structures, and clearances at highway and railroad crossings. |  | FPP Yard 2 | Lytton Springs | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 | 2026-05-15 | 345 | 0 | 0 | 0 |  | Fayette | Caldwell | Tier 4 | 24RPG013 | 2024-04-11 | 2024-05-03 |  |  | Y |  |  |  | 85964 | 85963
71130 | Centerville Switch - Lake Hubbard Switch 138 kV Double-Circuit Line | Upgrade the existing 138 kV Double-Circuit Line |  | Lake Hubbard | Centerville | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4126 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2401, 2402, 2439, 2450 | Y |  |  |  | 71131 | 71130
80546B | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild and double-circuit the Round Rock Westinghouse - Georgetown East 138 kV Line Section |  | Round Rock Westinghouse Tap | Georgetown East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2026-05-15 |  | 138 | 9.1 | 9.1 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 3669, 3677, 7528, 7532 | Y |  |  |  | 87619 | 80546 | 2023-SC17
81223 | Range Rider 138 kV Switch | Construct a new 138 kV switch replacing existing Morgan Creek 138 kV Switch. |  | Range Rider 138 kV Switch | Range Rider 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8721 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 1032, 1033, 10050, 10183, 11032, 11033, 11034, 11035, 180031, 180032, 180033, 180034, 180035, 180036 | Y |  |  |  | 100162 | 81223
87861 | Range Rider - Ranger Camp 138 kV Double-Circuit Line | Construct a new 138 kV Double-Circuit Line from Range Rider to Ranger Camp Switch. |  | Ranger Camp 345/138 kV Switch | Range Rider 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8722 | 2026-05-15 |  | 138 | 1.2 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1032, 10050 | Y |  |  |  | 87862 | 87861
63948 | Establish Fallstown 138 kV Switch | Establish Fallstown 138 kV Switch |  | Fallstown | Fallstown | Planned |  | ONCOR | Harsh Naik | M3018 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 | [5 empty] | Y |  |  |  | 87782 | 63948
70900F | Roanoke Area Upgrades | Establish Roanoke_Exchange 138 kV Line |  | Roanoke Switch | Exchange Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2026-05-15 |  | 345 | 11.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 1845, 1851, 1871, 12077, 15115, 15118, 15855 | Y | N |  |  | 102864 | 70900
100008 | Oncor_MW_NoTPIT_CedarElm_Tie_For_Trojan | Add tie line for Trojan Sola at Cedar Elm 345 kV Switch (Project INR and Name 23INR0296 - Trojan Solar) | [5 empty] | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-05-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 11735, 144513 | Y |  |  |  | 100009 | 100008
92872 | North Main 138kV Capacitor Bank | North Main 138kV Capacitor Bank |  | North Main | North Main | Planned | M5187 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 | 0,110 | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1961 | Y |  |  |  | 92873 | 92872
92845 | Oncor_ME_92845_Watermill_Reindeer_Line_Upgrade | Upgrade Watermill to Reindeer 138 kV Line |  | Watermill Switch | Reindeer | Planned | M4430 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-05-15 |  | 138 | 0 | 2.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2429, 3065 | Y |  |  |  | 92846 | 92845
92870 | Oncor_ME_92870_Bradberry Switch 138kV Capacitor Bank |  |  | Bradberry Switch | Bradberry Switch | Planned | M4431 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Dallas |  | Tier 4 |  |  |  |  | 3064 | Y |  |  |  | 92871 | 92870
78367 | Montfort Switch-Shankle Switch 138 kV Line | Rebuild Montfort Switch - Shankle Switch 138 kV Line |  | Montfort | Shankle | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4002 | 2026-05-15 |  | 138 | 0 | 18 | 0 |  | Navarro | Ellis | Tier 3 |  |  |  |  | 192, 2330, 2331, 3454, 12329 | Y |  |  |  | 78368 | 78367
78361B | Lake Creek - Rattlesnake Road 345 kV Line | Establish Possum Trot 345 kV Switch |  | Possum Trot | Possum Trot | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6276 | 2026-05-16 |  | 345 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 3 |  |  |  |  | 3384, 3399, 3402, 3403, 3405, 3409, 3410, 3412, 3741, 3791, 13402, 13405, 13410 | Y |  |  |  | 91985 | 78361
71903 | Establish Launch Pad 138 kV Switch | Establish Launch Pad 138 kV Switch |  | Launch Pad | Launch Pad | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6156 | 2026-05-16 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3372, 3593, 3594, 3601, 3709 | Y |  |  |  | 71904 | 71903
80466 | Oleander: Construct New 138 kV Terminal | Interconnect Citrus Flatts BESS to the Oleander 138 kV station |  | Oleander |  | Under Construction |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 |  | 2026-05-16 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 80022, 164522 | Y |  |  |  | 80467 | 80466
80422 | Add_Triangle_Park_Load |  |  | Triangle Park |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-05-19 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32854 | Y |  |  |  | 89954 | 80422
91584 |  |  |  | HOLDER | RISING STAR | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-05-22 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 292, 33285, 33289 | Y |  |  |  | 91585 | 91584
99453W | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade STP equipment on Ckt.44 STP to Hillje to increase thermal limits as part of FRM2 upgrades. |  | STP | Hillje | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-29 |  | 345 | 0 | 0 | 0 |  | Matagorda | Wharton | Tier 4 |  |  |  |  | 5915, 9063, 44200 | Y | N |  |  | 102603 | 99453
90180B | Clodine Reconfiguration for Houston IV BESS (24INR0584) | Reposition Ckt.25B Clodine to Roark to the existing W670/W710 breaker position. |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 90182 | 90180
64581A | New 138kV Waterfowl substation | Reconfigure existing Ckt.02F (move Seadoc/Seaway onto other circuit) resulting in Ckt.36 COPPER to Booster tap to Jones Creek. |  | COPPER | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 5568, 42195, 42199, 42215, 42540, 43211, 43212, 43221, 48006, 48007, 48039, 48333, 48334 | Y | N |  |  | 102644 | 64581
90180A | Clodine Reconfiguration for Houston IV BESS (24INR0584) | Install one new generator lead at the existing Clodine W670/W680 breaker position for Houston IV BESS. |  | Clodine | Generator | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 90181 | 90180
64581B | New 138kV Waterfowl substation | Install new CEHE-owned 138kV Waterfowl (WTR) substation. Reconfigure existing Ckt.02F and install new conductor to create new Ckt.54A Jones Creek to Waterfowl |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 42540, 43470 | Y | N |  | Cost included in main entry | 102645 | 64581
64581C | New 138kV Waterfowl substation | Install new CEHE-owned 138kV Waterfowl (WTR) substation. Convert customer-owned Seadoc substation to loop service. Reconfigure existing Ckt.02F and reconnect Seadoc/Seaway to create new Ckt.02F Jones creek to Seadoc loop to Seaway tap to Waterfowl. |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 42540, 43211, 43222, 43470, 48007 | Y | N |  | Cost included in main entry | 102646 | 64581
59959 | CPSE_New_Old_Hickory_Switchyard | Build a new Old Hickory 345 switchyard to connect Old Hickory Solar plant. |  | 5133 | 5915 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0303; S-0940 | 2026-05-30 20:00 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5133, 5323, 5915 | Y |  |  |  | 59960 | 59959
64042 | Barrilla Junction: 69 kV Loop Rebuild | Rebuild Barrilla Junction to Saragosa to Cherry Creek to Verhalen to Hoefs Road stations, convert to 138 kV |  | Barrilla Junction | Hoefs Road Station | Planned | 1141 - 1319 | AEP TNC | Brent Harris twang1@aep.com 918-599-2635 | 1886 | 2026-05-31 |  | 69 | 0 |  | 0 |  | Pecos | Reeves | Tier 3 | 21RPG023 | 2021-12-17 | 2022-01-14 |  | 6649, 6650, 6651, 6652, 6653, 6654, 60206, 60207, 60208, 60716, 60802, 60808, 69023, 69047 | Y | N |  |  | 64043 | 64042
73359 | Vertrees: Construct New Distribution Station | Construct new distribution station on the Stewart Road to Weslaco Unit 138 kV line | Company Contact and In-Service Date Update | Vertrees |  | Planned |  | AEP TCC | Jacob Pyle jlsolis@aep.com 361-881-5574 |  | 2026-05-31 | 2958101 | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8348, 8662, 8737, 8951 | Y |  |  |  | 73360 | 73359
63922 | Tiki Island Distribution Upgrades | Install double-tap distribution service to Tiki Island. Existing tap will remain on Ckt.63E La Marque to Stewart. Tap Ckt.93C La Marque to West Galveston for the new tap section to Tiki Island. |  | Tiki Island | LaMarque/West Galveston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 42860, 43290, 43351, 43352, 43355, 43400, 48551, 48552, 48855 | Y | N |  |  | 91179 | 63922
75835D | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Upgrade equipment to increase thermal limits. Phase Two of overall approved upgrades |  | Stone Lake | Tomball | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2025-12-10 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 23RPG012 | 2023-05-04 | 2023-05-26 | 2023-05-26 | 46510, 48348 | Y | N |  |  | 98431 | 75835
71004A | Julia CEHE-Owned Sub for Melaza Solar (21INR0220) | Install new Julia (JUL) CEHE substation for generator interconnection to Maleza Solar. Loop Ckt.72 into Julia substation to create new Ckt.72 Hillje to Julia to Blue |  | Julia | Hillje/Blue | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44060, 44200, 44220 | Y | N |  |  | 87171 | 71004
78427A | Bohemian (BOH) 138kV CEHE Substation for Destiny Storage (24INR0397) | Install new CEHE 138kV Bohemian (BOH) substation for generator interconnection to Destiny Storage. Loop Ckt.66K into substation to create new Ckt.66 Crosby to Bohemian to Eastgate. |  | Rhapsody | Crosby/ Eastgate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40390, 40690, 40970 | Y | N |  |  | 100262 | 78427
78485F | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Hayes to Britmoore to increase thermal limits. |  | Bellaire | Hillcroft | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 6.41 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 44120, 48159 | Y | N |  | Cost included in | 98951 | 78485
90130 | Install (2) new 100 MVA distribution transformers at Orchard substation. | Install two(2) new 100 MVA distribution transformers at Orchard substation. |  | Orchard | Beasly/ MARICK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y | N |  |  | 90133 | 90130
6749 | Rosata: Build 138kV Substation | Build new Rosata 138 kV POD Switch on the Coleto Creek to Kenedy 138 kV line | Status and In-Service Date Update | Rosata |  | Planned | 898 - 1076 | AEP TCC | Chase Stevens deevans@aep.com 918-599-2938 | 3682 | 2026-05-31 | 2018-01-10 | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7241, 8153, 8162, 8186, 88153 | Y | Y |  |  | 14542 | 6749
99798 | Citrus City: Install 138 kV circuit breakers | Install breakers at the Citrus City 138 kV station |  | Citrus City |  | Planned |  | AEP TCC | Charles Burks jlsolis@aep.com 361-881-5574 | TP2023324 | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 80123 | Y |  |  |  | 99799 | 99798
69473 | Jaguar: Construct New Distribution Station | Construct new distribution station on the McGruder to Thomaston 138 kV line | In-Service Date Update | Jaguar |  | Under Construction |  | AEP TCC | Will Simmons deevans@aep.com 918-599-2938 |  | 2026-05-31 |  | 138 | 0 | 0 | 40 |  | Victoria |  | Tier 4 |  |  |  |  | 8183, 8194, 8724 | Y |  |  |  | 69474 | 69473
92998 | LeMay: Expand 138 kV Station | Interconnect the new White Water Midstream load to the existing LeMay 138 kV station |  | LeMay |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  |  | 8627 | Y | N |  |  | 92999 | 92998
80482 | North McAllen: Construct New 138 kV Terminal | Interconnect Carambola BESS to the North McAllen 138 kV station |  | North McAllen |  | Planned | TP2023631 | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8632 | Y |  |  |  | 80483 | 80482
50890 | Port Lavaca: Station Rebuild (Cangrejo) | Rebuild the Port Lavaca (Cangrejo) station |  | Port Lavaca |  | Planned | 1057 - 1230 | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 | 3787 TA2019045 | 2026-05-31 |  | 69 | 0 | 37.81 | 0 |  | Calhoun |  | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8135 | Y | N |  |  | 50891 | 50890
76293 | Upgraded Cedvale-MiDiva138KV |  |  | Cerdarvale | Midiva | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 0.15 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38145, 38152 | Y |  |  |  | 76294 | 76293
76291 | Upgraded Cedarvale–BoneSpringsTap–Fishhook |  |  | Cedarvale to Bone Springs Tap | Bone Springs Tap to Fishhook | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 12.59 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38145, 38165, 38180 | Y |  |  |  | 76292 | 76291
76232 | Reconductor Mivida-Coachwhip-Fishhook 2045 ACCC |  |  | Mivida PSSE Bus# 38152 | Fishhook PSSE Bus# 38180 | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 14.39 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38152, 38170, 38180 | Y |  |  |  | 76233 | 76232
66077 | Reconductor both Pecos-Cedarvale 138 kV ckts |  |  | Pecos (bus # 38091) | Cedarvale (bus # 38145) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 15.34 | 0 |  | Reeves | Ward | Tier 4 |  |  |  |  | 38091, 38145 | Y |  |  |  | 66078 | 66077
66208 | Rebuild League City-Hidden Lakes with bundled 795 ACSS |  |  | Hidden Lakes (bus # 38900) | League City (bus # 38920) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 3.21 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  |  | 66209 | 66208
92687 | Oncor_ME_92687_Burkett 138 kV Switch |  |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2471, 2710, 2893 | Y |  |  |  | 92688 | 92687
70628 | Japhet 138kV Distribution Sub and Upgrades | Upgrade portions of 69kV Ckt.12 Garden Villas to Bringhurst to Clinton. Install new 138kV Japhet distribution substation. Move 69kV Bringhurst substation load to new Japhet substation and retire Bringhurst substation. Retire portions of Ckt.12 and convert the remaining portions of Ckt.12 to 138kV service. Loop new Japhet substation to create new 138kV Ckt.13 University to Japhet to Clinton. |  | Japhet | University/Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40350, 40352, 42690, 45070, 47540, 47700, 47760, 48764 | Y | N |  |  | 91551 | 70628
99004 | Install 30MVAR cap bank at Fulshear distribution substation. |  |  | Fulshear |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 | 0,30 | Fort Bend |  | Tier 4 |  |  |  |  | 44750 | Y | N |  |  | 99005 | 99004
99453S | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.39B Addicks to Obrien to increase thermal limits as part of FRM2 upgrades. |  | Addicks | Obrien | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44500, 45600 | Y | N |  |  | 102624 | 99453
99453X | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Hillje equipment on Ckt.44 STP to Hillje to increase thermal limits as part of FRM2 upgrades. |  | STP | Hillje | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Matagorda | Wharton | Tier 4 |  |  |  |  | 5915, 9063, 44200 | Y | N |  |  | 102623 | 99453
90232A | Facility Ratings Methodology (FRM) Upgrades | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits as part of FRM upgrades |  | PSARCO | BIGVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40190, 41301 | Y | N |  |  | 102826 | 90232
85970A | Athena (ATH) 138kV CEHE Station for RAVEN (RVN) / Raven Solar & Storage (24INR0209 & 24INR0210) | Loop new Athena CEHE 138kV substation into Ckt.65C East Bernard to Wallis to create new Ckt.65 East Bernard to Athena to Wallis. |  | Athena | East Bernard/Wallis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Wharton | Austin | Tier 4 |  |  |  |  | 44190, 44740, 46650 | Y | N |  |  | 87177 | 85970
87640 | New load customer interconnection RAOULT connecting on ckt 86 between DALTON and BRINE. | New load customer interconnection RAOULT connecting on ckt 86 between DALTON and BRINE. Expect transmission breakers in ring bus configuration for new RAOULT substation. |  | RAOULT | DALTON/ BRINE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40220, 40740, 41740 | Y | N |  |  | 87641 | 87640
99453A | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.18 STP to Shaula (Elm Creek) to increase thermal limits as part of FRM2 upgrades. |  | STP | Shaula | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Matagorda | Tier 4 |  |  |  |  | 5380, 5915 | Y | N |  |  | 102604 | 99453
99453B | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.69B Greens Bayou to Deepwater to increase thermal limits as part of FRM2 upgrades |  | Greens Bayou | Deepwater | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40450, 40700 | Y | N |  |  | 102605 | 99453
99453D | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.97A North Belt to TH Wharton to increase thermal limits as part of FRM2 upgrades. |  | North Belt | TH Wharton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45500, 46100 | Y | N |  |  | 102606 | 99453
99453C | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.27 STP to Old Hickory (Elm Creek) to increase thermal limits as part of FRM2 upgrades. |  | STP | Old Hickory | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Matagorda | Tier 4 |  |  |  |  | 5133, 5915 | Y | N |  |  | 102607 | 99453
99453H | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.97C Jordan to King to increase thermal limits as part of FRM2 upgrades. |  | Jordan | King | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Chambers | Harris | Tier 4 |  |  |  |  | 40850, 40900 | Y | N |  |  | 102608 | 99453
99453I | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.02B WA Parish to Nash to increase thermal limits as part of FRM2 upgrades. |  | WA Parish | Nash | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Brazoria | Tier 4 |  |  |  |  | 42980, 44010 | Y | N |  |  | 102609 | 99453
99453K | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.72A Jeanetta to WA Parish to increase thermal limits as part of FRM2 upgrades. |  | Jeanetta | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44000, 47300 | Y | N |  |  | 102611 | 99453
99453M | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.75H King to Rothwood to increase thermal limits as part of FRM2 upgrades. |  | King | Rothwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40900, 46290 | Y | N |  |  | 102612 | 99453
99453V | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.99 Limestone to Navarro to increase thermal limits as part of FRM2 upgrades. |  | Limestone | Navarro | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Navarro | Limestone | Tier 4 |  |  |  |  | 46020, 68091 | Y | N |  |  | 102614 | 99453
99453L | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.97G Chambers to Jordan to increase thermal limits as part of FRM2 upgrades. |  | Chambers | Jordan | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Chambers | Tier 4 |  |  |  |  | 40255, 40850 | Y | N |  |  | 102617 | 99453
99453E | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.97B King to North Belt to increase thermal limits as part of FRM2 upgrades. |  | King | North Belt | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40900, 46100 | Y | N |  |  | 102618 | 99453
85970B | Athena (ATH) 138kV CEHE Station for RAVEN (RVN) / Raven Solar & Storage (24INR0209 & 24INR0210) | Install one generator lead from Athena CEHE 138kV substation to RAVEN / Raven Solar & Storage (24INR0209 & 24INR0210). |  | Athena | RAVEN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 87178 | 85970
90336 | DURZNO (DUR) 138kV Customer Substation | Install new customer-owned 138kV DURZNO (DUR) substation. Loop into Ckt.54 to create new Ckt.54 Jones Creek to DURZNO to Waterfowl. |  | DURAZNO | Jones Creek/ Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 |  | 138 | 0.2 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42540, 43470, 43481 | Y | N |  |  | 90760 | 90336
71004B | Julia CEHE-Owned Sub for Melaza Solar (21INR0220) | Install generator lead from Julia (JUL) CEHE substation to MALEZA/Maleza Solar |  | Julia | MALEZA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44220, 113251 | Y | N |  |  | 87172 | 71004
78427B | Bohemian (BOH) 138kV CEHE Substation for Destiny Storage (24INR0397) | Install generator lead from Bohemian (BOH) substation to Rhapsody / RHAPSO (RHA) / Destiny Storage |  | Rhapsody | BOHEMI | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40970, 113862 | Y | N |  |  | 100263 | 78427
65906 | To add Jordan Station for GINR 21INR0031 |  |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68001, 68014, 68016 | Y |  |  |  | 65907 | 65906
45029 | Grandview Highland Hills Rebuild | CPSE_Rebuild of 138 kV double circuit line Line between Grandview to Highland Hills. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0273 | 2026-06-01 |  | 138 | 0 | 11.6 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-11 |  |  | 5030, 5095, 5175, 5205 | Y |  |  |  | 45030 | 45029
61090 | Timbercreek 138kV substation | Change name to Establish 138kV Timbercreek substation with (2) 40MVA transformers and will cut into existing Ckt 948 (Onion Creek to Pilot Knob) |  | Onion Creek | Pilot Knob |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9240, 9251, 9259 | Y |  |  |  | 61091 | 61090
102401 | LST_SamSwitch_Resiliency_(GTC)_Project | This project loops Helix to Navarro Circuit into LST Sam Switch station |  | Helix | Navarro | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-06-01 |  | 345 | 0 | 0 | 0 |  | Hill | Hill | Tier 3 | 25RPG031 |  |  |  | 68035, 68090, 68096 | Y |  |  |  | 102402 | 102401
77320 | Add CapBANK in COYANOSA |  |  | COYANOSA |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38380 | Y |  |  |  | 77321 | 77320
65663 | Double Ckt Line M138-K | Project Delayed Indefinitely. |  | Pecos (bus # 38091) | Faulkner (bus # 38124) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-06-01 |  | 138 | 0 | 26.2 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38091, 38124 | N |  |  |  | 65664 | 65663
89959 | RCEC_RockWallHwy276Load | Adding Rockwall Highway Bus, Load and Branch from RockWallHwy to RCKWL_E1_8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2710, 6972 | Y |  |  |  | 89960 | 89959
89952 | RCEC_AllenNorthLoad | Adding Allen North Load Bus, Load and Branch from Allen NLoad to RIDGVIEW_8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2585, 6857 | Y |  |  |  | 89953 | 89952
86323 | AEN_MagnesiumPlant_Northland_Ckt_979_RECONDUCTOR |  |  | 9128 | 9238 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  |  | 86324 | 86323
87146 | GSEC_Tier4_9468_Add_Bull_Sub | New Substation Load out of 68001 Claytonville | Adding new 1400MW load with deposit and agreement. | Claytonville |  | Planned |  | GSEC | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2026-06-01 |  | 345 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 9468, 68001 | Y |  |  |  | 87147 | 87146
67093 | New 138 kV station cut-in between Garfield and Hi-Cross | New 138 kV Easton Park Substation cut-in on CKT963 from Garfield to Hi-Cross substation to serve BBEC Load |  | 9143 |  | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-20 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9071, 9143, 9147 | Y |  |  |  | 67094 | 67093
61228 | AEN_McNeil__JustinLane__ckt_811_reconductor | Reconductor 3.98 miles of circuit to 3000 Amps. |  | McNeil [9080] | Justin Lane [9225] | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-21 |  | 138 | 0 | 3.98 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9080, 9225 | Y |  |  |  | 61229 | 61228
70186 | Buchanan CTEC - Kingsland 1 Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 6.2-mile Buchanan to Kingsland 2 to Kingsland 1 (T291) 69-kV transmission line. |  | Buchanan CTEC | Kingsland 1 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 69 | 0 | 6.2 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7402, 7404 | Y | Y |  |  | 78419 | 70186
81305 | Expanse - Vealmoor 138 kV Line Rebuild | Rebuild the existing Expanse – Vealmoor 138 kV Line with both circuits in place and establish the new Tredway 138 kV Switch. |  | Expanse | Tredway | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8681 | 2026-06-30 |  | 138 | 0 | 27.7 | 0 |  | Martin | Martin | Tier 3 |  | 2023-09-29 |  |  | 1355, 10090, 10097, 10098, 10110, 10113, 11006, 11303, 11338, 11348, 11349, 11368, 11383, 23829, 23835, 23838, 23849, 23880 | Y |  |  |  | 93169 | 81305
71917 | Upgrade STEC castroville to Pearson to 138kV | Upgrade STEC Bader station to 138kV. Upgrade STEC Castroville to bader and bader to pearson to 138kV |  | 5808 | 5813 | Planned | 71935 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-06-30 |  | 138 | 0 | 10.51 | 0 |  | Medina | Medina | Tier 2 | 22RPG022 | 2022-08-08 | 2022-12-06 |  | 5802, 5804, 5810, 5811, 5813 | Y |  |  |  | 71918 | 71917
63956 | Clear Crossing: Build 345 kV terminal | Interconnect HODL Ranch II at Clear Crossing 345 kV station |  | Clear Crossing | HODL Ranch II | Under Construction | 1139 - 1317 | ETT | Raza Ansari myturner@aep.com 918-599-2437 | 1884 | 2026-06-30 |  | 345 | 0 | 0 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  |  | 60017, 60515 | Y | N |  |  | 63957 | 63956
80484 | Closner: Construct New 138 kV Terminal | Interconnect Gunnar BESS to the Closner 138 kV station. |  | Closner |  | Planned |  | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 |  | 2026-06-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8029 | Y |  |  |  | 80485 | 80484
87031 | Primavera: Construct New 138 kV Terminal | Interconnect Project Lynx Storage to the Primavera 138 kV station |  | Primavera |  | Planned |  | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2024100 | 2026-06-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8003 | Y |  |  |  | 87032 | 87031
102815 | SandLake - North McCamey Transmission Line Addition | LCRA TSC and ONCOR joint project to add the Sand Lake-North McCamey 345-kV double-circuit transmission line. 22RPG010. Also see PMCR 69709, LCRATSC_Bearkat_NorthMcCamey_TransmissionLineAddition. |  | North McCamey | Sand Lake | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 345 | 186 | 0 | 0 |  | Glasscock | Ward | Tier 1 | 22RPG010 | 2022-04-12 | 2022-07-13 |  | 11098, 76000 | Y | Y |  |  | 102816 | 102815 | 2021-FW15
61404 | Boerne Split-Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T228 Boerne to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 7.3-mile double-circuit transmission line by replacing the aging conductor. |  | Boerne, Bergheim | Welfare, Kendall | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 345 | 0 | 7.3 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7153, 7168, 7770 | Y | N |  |  | 78327 | 61404
91402 | Buchanan_Burnet_TL_Overhaul | Perform an overhaul on the 11.4 mile T108 Buchanan - Burnet 69-kV (de-energized) transmission line |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6943 | 2026-06-30 |  | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  |  | 7087, 7092, 7093, 7097, 7100 | Y |  |  |  | 91403 | 91402
73401 | Fredonia - Mason Transmission Line Overhaul | Perform an overhaul on the 11 mile T289 Fredonia (CTEC) - Mason (CTEC) 69-kV transmission line. Per LCRA TSC Transmission System Planning procedure, replacement structures will be capable of operating at 138-kV. |  | Fredonia | Mason | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-06-30 |  | 69 | 0 | 11 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 7395, 76391 | Y | N |  |  | 73402 | 73401
91630 | Jim Treece: Interconnect New 345 kV Generator | Interconnect Blue Summit II Energy Storage to the existing Jim Treece 345 kV station |  | Jim Treece |  | Planned |  | ETT | Tong Wang twang1@aep.com 918-599-2635 | TP2025111 | 2026-06-30 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 | [5 empty] | Y | N |  |  | 91631 | 91630
69709 | Bearkat - North McCamey Transmission Line Addition | LCRA TSC and WETT joint project to add the Bearkat-North McCamey 345-kV double-circuit transmission line. 22RPG010 |  | Bearkat | Sand Lake | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 345 | 140 | 0 | 0 |  | Glasscock | Ward | Tier 1 | 22RPG010 | 2022-04-12 | 2022-07-13 |  | 59903, 76000 | Y | Y |  |  | 78333 | 69709 | 2021-FW15
71952 | LCRA TSC Bluffton to Buchanan Transmission Line Overhaul | Overhaul circuit and replace conductor with single-Drake conductor (117 MVA) from Bluffton to Buchanan. Replacement structures should be 138-kV double-circuit capable of supporting a single-Suwannee conductor. Install OPGW. |  | Bluffton | Buchanan | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 69 | 0 | 7 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7406 | Y | N |  |  | 72467 | 71952
102534 | Pamela Heights I battery storage at Callisto substation… Connect with HO Clarke 138kV substation at the same generator lead as 01HOCCLO |  |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-06-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47150, 113105 | Y | N |  |  | 102535 | 102534
76914 | Ocelot: Construct New 138 kV Station | Interconnect the Ocelot load to the new Ocelot 138 kV station on the Military Highway to Palo Alto 138 kV line | Status, Customer Contact, and In-Service Date Update | Ocelot |  | Under Construction | TP2023032 | AEP TCC | Kymberly Cude jlsolis@aep.com 361-881-5574 |  | 2026-06-30 |  | 138 | 0.189 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8047, 8275, 8950 | Y |  |  |  | 76915 | 76914
64858 | La Palma Expansion | Construct 3 Breaker Ring Bus. Construct 345 kV Line from La Palma 345 kV station to Kingfisher 345 kV (Sharyland) station. | In-Service Date Update | La Palma | Kingfisher | Planned |  | AEP TCC/SLU | Lorraine Timmerman jlsolis@aep.com 361-881-5574 | TP2021588 | 2026-06-30 |  | 345 | 6.5 | 0 | 0 |  | Cameron | Cameron | Tier 2 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8317, 8383, 79500, 79501, 80137 | Y |  |  |  | 65264 | 64858
99641 | Static: Expand 345 kV Station | Install two 345 kV breakers at the existing Static 345 kV station |  |  |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2025246 | 2026-06-30 |  | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 | [5 empty] | Y |  |  |  | 99642 | 99641
99540 | Anastase: Construct New 138 kV Station | Interconnect Rutile BESS to the new Anastase 138 kV station on the Ballinger to Red Creek 138 kV line between Ballinger and Weiss |  |  |  | Conceptual |  | AEP TNC | Maria Turner myturner@aep.com 918-599-2437 | TP2025343 | 2026-06-30 |  | 138 | 0 | 0 | 0 |  | Runnels |  | Tier 4 |  |  |  |  | 6340, 60216, 60399, 69216 | Y |  |  |  | 99541 | 99540
70192 | Doss - Headwaters Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 14.2-mile Doss - Headwaters (T508) 69-kV transmission line. |  | Doss | Headwaters | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-06-30 | 2024-04-19 | 69 | 0 | 14.2 | 0 |  | Gillespie | Gillespie | Tier 4 |  |  |  |  | 7408, 7410 | Y | Y |  |  | 70193 | 70192
81594 | Dunlay substation | Adds STEC Dunlay Load serving station |  | Dunlay |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-07-01 |  | 138 |  | 0 | 0 |  | Medina |  | Tier 2 |  |  |  |  | 5802, 5807, 5813 | Y | N |  |  | 81595 | 81594
90010 | Magill: Construct New 138 kV Terminal | Interconnect City Breeze BESS to the Magill 138 kV station |  | Magill |  | Planned |  | AEP TCC | Brooks Dow deevans@aep.com 918-599-2938 | TP2024104 | 2026-07-15 00:02 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8111, 114071 | Y |  |  |  | 90011 | 90010
70898 | Flomot Tap: Rebuild 69 kV Line | Rehab Flomot Tap 69 kV Line | Company Contact and In-Service Date Update | Flomot Tap | Flomot | Planned |  | AEP TNC | Chris Carroll myturner@aep.com 918-599-2437 |  | 2026-07-31 |  | 69 | 0 | 7.06 | 0 |  | Motley | Motley | Tier 4 |  |  |  |  | 6041, 6042 | Y | N |  |  | 70899 | 70898
79462 | Expand HO Clarke substation for Callisto II (22INR0558) | Expand HO Clarke substation for Callisto II (22INR0558) |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-07-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 79463 | 79462
90232G | Facility Ratings Methodology (FRM) Upgrades | Upgrade Stadium to Fannin Ckt.08B to increase thermal limits as part of FRM upgrades |  | Stadium | Fannin | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47090, 47420 | Y | N |  |  | 102827 | 90232
99917 | Fayetteville AT2 Autotransformer Restoration | LCRA will install, test, and commission a replacement 672 MVA Auto Transformer (AT2) to replace the existing failed unit. SMIT will manufacture and design the replacement 672MVA AT2 which is covered under warranty. The new unit will be identical in ratings but shall include additional improvements to mitigate sound level. The sound mitigation options will cost [redacted] and consist of upgraded core steel grade M075-23 (instead of M105-30), sound panels between tank wall stiffeners, and new low noise fans. The improvements in sound design shall reduce sound levels by ~8dBA. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-07-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 99918 | 99917
61552 | Matador to Turkey: Rebuild 69 kV Line | Rebuild 69 kV line from Matador to Turkey |  | Matador | Turkey | Under Construction | 1128 - 1306 | AEP TNC | Chris Carroll twang1@aep.com 918-599-2635 | 1873 | 2026-07-31 |  | 69 | 0 | 26.9 | 0 |  | Motley | Hall | Tier 4 |  |  |  |  | 6020, 6024, 6039, 6041, 6044, 6140, 60351 | Y | N |  |  | 65596 | 61552
76286 | Hecker to Resnik: Rebuild 138 kV Line | Rebuild the Hecker to Resnik 138 kV line | Company Contact and In-Service Date Update | Hecker | Resnik | Planned |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2023506 | 2026-07-31 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 8580 | Y |  |  |  | 76287 | 76286
48774 | Fincas: Build new 138 kV distribution station | Construct new distribution station on the University to Wormser 138 kV line | In-Service Date Update | Fincas |  | Under Construction | 1026 - 1204 | AEP TCC | Travis Coody jlsolis@aep.com 361-881-5574 | 3765 | 2026-07-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8039, 8295, 8649, 8650, 8653 | Y | N |  |  | 81145 | 48774
90008 | Tango to Pawnee: Rebuild 345 kV Line | Rebuild the Tango to Pawnee 345 kV line |  | Tango | Pawnee | Planned |  | AEP TCC/CPS,STEC | Craig Tabor jlsolis@aep.com 361-881-5574 | TP2024118 | 2026-07-31 |  | 345 | 1.2 | 1.2 | 0 |  | Bee | Karnes | Tier 1 | 22RPG048 | 2022-12-29 | 2024-04-10 | 2024-04-23 | 5725, 8689 | Y |  |  |  | 90009 | 90008
90232H | Facility Ratings Methodology (FRM) Upgrades | Upgrade Kirby to Garrott Ckt.37A to increase thermal limits as part of FRM upgrades |  | Kirby | Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47320, 47660 | Y | N |  |  | 102828 | 90232
91558 | 138kV transmission upgrade to serve Kirkland large load. | Modifying branch info between BLDSW_RC and BLACKLND_8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-08-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 6886, 12713 | Y |  |  |  | 91559 | 91558
91555 | Switchyard to accommodate for Telios Large Load. | Added Kirkland and Telios bus, along with load and branches |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-08-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 6879, 6882, 6915, 6950, 6980 | Y |  |  |  | 91556 | 91555
87512 | RCEC_BranchChanges_Kaufman_Update4 | Updating branch info between I20_RC and COMBINRC1 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-08-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6904 | Y |  |  |  | 87513 | 87512
90851 | add 19.2 MVAR Capacitor at Rio Colorado |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-08-01 12:00 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5563 | Y |  |  |  | 90852 | 90851
75790 | Placeholder Station for Erath Solar POI | Placeholder Station for Erath Solar POI |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-08-27 |  | 345 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 68020, 68025, 68030 | Y |  |  |  | 75791 | 75790
80632 | Install Kilgore 35kV Distribution Substation. Loop on Ckt.86B to create new Ckt.86 CHEVRON to Kilgore to LANGSTON | Install Kilgore 35kV Distribution Substation. Loop on Ckt.86B to create new Ckt.86 CHEVRON to Kilgore to LANGSTON |  | Kilgore | CHEVRON/LANGSTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 |  | 138 | 5.12 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40300, 40775, 44830 | Y | N |  |  | 87179 | 80632
71106 | Dunlavy to HO Clarke Ckt.40A Partial Reconductor | Reconductor portions of Ckt.40A Dunlavy to HO Clarke ahead of future 138kV conversions |  | Dunlavy | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 |  | 69 | 0 | 4.41 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47160, 47320, 47580 | Y | N |  |  | 71107 | 71106
73063 | Big Foot to Lytle: Convert to 138 kV | Convert the Big Foot to Lytle 69 kV line to 138 kV and interconnect Rowan Digital to the Lytle 138 kV station |  | Big Foot | Lytle | Planned |  | AEP TCC | Will Simmons jlsolis@aep.com 361-881-5574 | TP2022155 | 2026-08-31 |  | 138 | 0 | 12 | 0 | 0,23 | Medina | Frio | Tier 4 |  |  |  |  | 8208, 8216, 8218, 8221, 8223, 8622, 8732, 8962, 58280 | Y |  |  |  | 73064 | 73063
100018 | Rebuild Spruce to Pawnee into a double circuit | This project is Phase 1 of the Spruce to Pawnee Double Circuit Rebuild. This Phase captures the completion of the new second circuit from Spruce to Pawnee with the final rating of circuit 2. |  | 5400 | 5725 | Planned |  | CPS/STEC | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-08-31 |  | 345 | 45.83 | 45.83 | 0 |  |  |  | Tier 1 |  |  |  |  | 5400, 5725 | Y |  |  |  | 100019 | 100018
92655 | Oncor_MNE_92655_Farm Road 138 kV Switch |  |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-08-31 |  | 138 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1822, 1823, 2844 | Y |  |  |  | 92656 | 92655
82298 | PMCR for Adding TNMP Woodhouse New Station | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-08-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  | 2024-02-27 | 38295, 38308, 38355, 60717 | Y |  |  |  | 82299 | 82298
76242 | Lytle: Construct New 138 kV Terminal | Convert the Big Foot to Lytle 69 kV line to 138 kV and interconnect Rowan Digital to the Lytle 138 kV station |  | Lytle |  | Planned |  | ETT | Will Simmons jlsolis@aep.com 361-881-5574 | TP2022155 | 2026-08-31 |  | 138 | 0.1 | 0 | 0 | 0,23 | Medina |  | Tier 4 |  |  |  |  | 8962 | Y |  |  |  | 76243 | 76242
67326 | Ajo to Reforzar: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Ajo to Reforzar |  | Ajo | Reforzar | Under Construction |  | AEP TCC/ETT | Curtis Brown jlsolis@aep.com 361-881-5574 | TP2022030 | 2026-08-31 |  | 345 | 11 | 0 | 0 |  | Kenedy | Brooks | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80076, 80078 | Y |  |  |  | 67327 | 67326
90452 | Red Egret BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 76067 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-08-31 |  | 138 | 1.15 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38820, 113533 | Y |  |  |  | 90453 | 90452
91174 | Upgrade Eustace-Walton line to Cumberland conductor | Upgrade Eustace-Walton line to Cumberland conductor |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-09-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6899, 6951 | Y |  |  |  | 98999 | 91174
78169 | Lewisville Switch to Highland | Lewisville Switch to Highland |  | Lewisville Switch | Highland | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-09-04 |  | 138 | 0 | 2.8 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 645, 664 | Y |  |  |  | 78170 | 78169
61444 | GVEC Kicaster Substation Addition (formerly Wilson South) | Add a new load-serving substation 4.35 miles south of La Vernia along FM 775 with a 40 MVA PWT. |  | Wilson South |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-09-11 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 5418, 7615, 7629 | Y | N |  |  | 78418 | 61444
66206A | Upgrade Temple - Minerva 69 kV Line | Upgrade Temple - Marak 69 kV Line |  | Temple | Marak | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6186 | 2026-09-15 |  | 69 | 20.5 | 0 | 0 |  | Bell | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3496, 3689, 3726 | Y |  |  |  | 68923 | 66206
72579B | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Blanco to Devil's Hill 69 kV circuits to 138 kV with bundled 795 kcmil conductor (440 MVA). (Replaces ERCOT Project # 70367B) |  | Blanco | Devil's Hill | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-09-15 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 70482, 70484, 70493 | Y | Y |  |  | 72581 | 72579
66289C | Tyler to Athens 138 kV line Conversion | Tyler to Athens 138 kV Operation |  | Tyler | Athens | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6094 | 2026-09-15 |  | 138 | 0 | 0 | 0 |  | Henderson | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3108, 3142, 3197, 3236, 3238, 13235 | Y |  |  |  | 87816 | 66289
66202B | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Elkhart - Grapeland 69 kV Line |  | Elkhart | Grapeland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6182 | 2026-09-15 |  | 69 | 0 | 11 | 0 |  | Anderson | Houston | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3285, 3286, 3290 | Y |  |  |  | 71894 | 66202
66492B | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Grindstone - Jacksboro Sinclair 69 kV Line |  | Jacksboro Sinclair | Grindstone | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3006 | 2026-09-15 |  | 69 | 0 | 15 | 0 |  | Jack | Palo Pinto | Tier 4 |  |  |  |  | 1557, 1572 | Y |  |  |  | 72964 | 66492
71002 | Tidehaven: Construct New Distribution Station | Construct new distribution station on the Blessing to Palacios 69 kV line | In-Service Date Update | Tidehaven |  | Planned | 1028 - 1206 | AEP TCC | Marc Wilson deevans@aep.com 918-599-2938 | 3767 DP21X0007 | 2026-09-30 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8044, 8119, 8121, 8131, 8132, 8133, 8555, 8666 | Y | N |  |  | 71003 | 71002
67320 | Cruce to Reforzar: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cruce to Reforzar |  | Cruce | Reforzar | Under Construction |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022033 | 2026-09-30 |  | 345 | 48 | 0 | 0 |  | Jim Hogg | Brooks | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80078, 80079 | Y |  |  |  | 67339 | 67320
66101 | Del Sol to Frontera: Build New 345 kV Double Circuit Line | Build new 345 kV double circuit line from Del Sol to Frontera. Expand Frontera Station and install two (2) autotransformers. |  | Del Sol | Frontera | Planned |  | AEP TCC/ETT | Brent Harris jlsolis@aep.com 361-881-5574 | TP2020838 | 2026-09-30 |  | 138 | 36 | 0 | 1350 |  | Starr | Hidalgo | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8355, 8980, 8992, 80004, 80005, 80119, 80355 | Y |  |  |  | 66102 | 66101
73448 | Roma: Build new 138 kV terminal | Bordertown BESS interconnection to Roma Station on Roma Switch to Rio Grande City | In-Service Date Update | Roma |  | Planned |  | AEP TCC | William Lovelace jlsolis@aep.com 361-881-5574 |  | 2026-09-30 |  | 138 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 8795, 8796, 87960 | Y |  |  |  | 73449 | 73448
72268 | CPSE_New Ingram Rd Substation |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-10-01 |  | 138 | 0 | 0 | 0 |  | Bexar |  | Tier 4 |  |  |  |  | 5102, 5241, 5346 | Y |  |  |  | 72269 | 72268
78478 | Rebuild Oaks to Poteet to Pearsall 69 kV line | Rebuild Oaks to Poteet to Pearsall 69 kV line from 4/0 to 795. 2023 RTP |  | Oaks | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-10-01 |  | 69 | 0 | 38.95 | 0 |  |  |  | Tier 2 |  |  | 2020-05-21 |  | 5710, 5712, 5893 | Y | N |  |  | 78479 | 78478
78177 |  |  |  | Pleasant Grove | Pleasant Grove | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 69 | 0 | 0 | 0 | 0,7.2 | Falls | Falls | Tier 4 |  |  |  |  | 81 | Y |  |  |  | 78178 | 78177
78181 |  |  |  | Midway | Midway | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 69 | 0 | 0 | 0 | 0,7.2 | Falls | Falls | Tier 4 |  |  |  |  | 185 | Y |  |  |  | 78182 | 78181
99608 | Establish Foggle Switch - North Athens Switch 138 kV Line | Establish Foggle Switch - North Athens Switch 138 kV Line |  | Foggle Switch | North Athens Switch (Rayburn) | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6348 | 2026-10-15 |  | 138 | 0 | 1.4 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  |  | 3233, 6867 | Y |  |  |  | 99609 | 99608
102563 | BEPC_TPIT102563_BrushieCap |  |  | 199 |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-22 |  | 69 | 0 | 0 | 0 | 0,7.2 | Navarro |  | Tier 4 |  |  |  |  | 199 | Y |  |  |  | 102564 | 102563
75776A | Samaritan 138kV Switching Station | Reconfigure Ckt.26C Angleton to STRATT and loop into new CEHE-owned 138kV Samaritan switching station to create new Ckt.26 Angleton to Samaritan to STRATT. No line upgrades Ckt.26 Angleton to Samaritan to STRATT. |  | Samaritan | Angleton/STRATT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42030, 42110, 43300 | Y | N |  |  | 100295 | 75776
75776B | Samaritan 138kV Switching Station | Connect Samaritan CEHE substation with two leads to TNMP_White Oak distribution substation. |  | Samaritan | Angleton/Clute | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-30 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39580, 42030 | Y | N |  |  | 100296 | 75776
73578A | Heights 138kV Loop Conversion | Rebuild/Reconductor Dead Ckt.40Z to prepare for 138kV Conversion. De-energize Ckt.31C Dunlavy to Heights and repurpose as Ckt.09D tap to Dunlavy TR1 load. |  | Dunlavy | Heights | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46615, 47580, 47581, 47591, 47682, 48572 | Y | N |  |  | 90931 | 73578
65719 | Rebuild/reconductor portions of Ckt.05A Missouri City to Sienna as a Hardening upgrade(24RPG030). | Rebuild and reconductor portion of Missouri City to Sienna Ckt.05A as a Hardening upgrade |  | Missouri City | Sienna | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 3.8 | 0 |  | Fort Bend | Fort Bend | Tier 4 | 24RPG030 | 2024-09-18 | 2024-10-10 | 2024-10-10 | 48237, 48336 | Y | N |  |  | 90165 | 65719
45511 | Laredo to Del Mar: 138 kV Line Rebuild | Rebuild Laredo to Del Mar 138 kV Line | Company Contact and In-Service Date Update | Laredo | Del Mar | Planned | 992 - 1170 | AEP TCC | Bradley Case jlsolis@aep.com 361-881-5574 | 3746 | 2026-10-31 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645 | Y | N |  |  | 65531 | 45511 | 2018-S4
75780A | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy BESS (26INR0250) | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. |  | Elmaton | STP/WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 5915, 43990, 44000 | Y | N |  |  | 102654 | 75780
73362 | Uribe: Construct New Distribution Station | Construct new distribution station on the Molina to Zapata 138 kV line |  | Uribe |  | Planned |  | AEP TCC | Alex Perkins jlsolis@aep.com 361-881-5574 |  | 2026-10-31 | 2958101 | 138 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 8299, 8646, 8985, 8993, 80230 | Y |  |  |  | 73363 | 73362
73098 | Castroville Cut-in 138 kV | Cut the AEP line from Quihi to CPS Castroville into the newly converted to 138 kV STEC Castroville station. |  | Quihi | Castroville (CPS) | Planned | TP2022982 | ETT | Jeremy Brazeal jlsolis@aep.com 361-881-5574 |  | 2026-10-31 | 2023-05-25 | 138 | 0.4 | 0 | 0 |  | Medina |  | Tier 2 | 22RPG022 | 2023-08-22 | 2023-11-22 |  | 5083, 5804, 8248 | Y |  |  |  | 73099 | 73098
99453P | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.62B Waterhole to Jones Creek to increase thermal limits as part of FRM2 upgrades. |  | Waterhole | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Brazoria | Tier 4 |  |  |  |  | 42530, 44880 | Y | N |  |  | 102616 | 99453
99453R | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.62A Bailey to Waterhole to increase thermal limits as part of FRM2 upgrades. |  | Bailey | Waterhole | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44040, 44880 | Y | N |  |  | 102615 | 99453
79451A | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. |  | Ancla | Angleton/West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 43380, 46630 | Y | N |  |  | 87173 | 79451
90038 | McKenzie Road to Winthorp: Construct New 138 kV Line | Interconnect the new Winthorp load station to the existing McKenzie Road 138 kV station |  | McKenzie Road | Winthorp | Planned |  | AEP TCC/ETT | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2024150 | 2026-10-31 |  | 138 | 0.15 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8545, 8858 | Y | N |  |  | 90039 | 90038
78490C | Jeanetta Auto Upgrades | Upgrade Ckt.25B Roark equipment and reconductor near Roark substation to increase thermal limits |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 0.04 | 0 |  | Harris | Harris | Tier 3 | 23RPG031 | 2023-10-04 | 2023-10-26 |  | 44590, 48315, 48316 | Y | N |  |  | 79427 | 78490
78490D | Jeanetta Auto Upgrades | Reconductor Ckt.25B Clodine to Roark TR8 tap to increase thermal limits. |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 3.67 | 0 |  | Harris | Harris | Tier 3 | 23RPG031 | 2023-10-04 | 2023-10-26 |  | 44140, 48315 | Y | N |  |  | 79428 | 78490
86022 | Jordan 138kV Substation Expansion for Coneflower Storage (23INR0425) | Expand 138kV Jordan substation for Coneflower Storage generator interconnection (23INR0425) |  | Jordan |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  |  | 40855, 113981 | Y | N |  |  | 86023 | 86022
73578B | Heights 138kV Loop Conversion | Repurpose/retire existing 69kV Ckts 34A/34B. Unbundle parallel-bundled portions of Ckt.40A HOC to Dunlavy. Reconfigure Ckt.40A to reach a Minimum 1-2000AAC limiting conductor @ 90/120Deg. Upgrade HOC line relaying on 69kV Ckt.40A HOC to Dunlavy. |  | Dunlavy | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 90932 | 73578
75780B | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy BESS (26INR0250) | Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy BESS (26INR0250) |  | Elmaton | DUFFY | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43990, 114361 | Y | N |  |  | 102655 | 75780
79451B | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. | Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. |  | Ancla | ROYAL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  |  | 87174 | 79451
73578D | Heights 138kV Loop Conversion | Convert Heights substation to 138kV service. Retire/repurpose portions of 69kV Ckts. 34A/34B for the new Heights 138kV loop. Reconfigure Ckt.09D to create new Ckt.09D Eureka TR2/TR3 tap to HE-DN_TR1 tap to Heights 138kV to White Oak. Reconductor any existing 1-795AAC limiting conductor to 2-959ACSS. Remove existing Heights 7.2 MVAR cap bank from Heights TR1. |  | Heights | San Felipe/White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:03 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45752, 46615, 46620, 47160, 47581, 47591, 47680, 47682, 47685, 747680 | Y | N |  |  | 90933 | 73578
73578E | Heights 138kV Loop Conversion | Remove White Oak auto A2/A4 and remaining 69kV facilities |  | White Oak |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:04 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46615, 46620, 47680, 49021, 49042 | Y | N |  |  | 90934 | 73578
89955 | RCEC_Peerless_Load | Adding Pearless Bus, Load and Branch from Pearless to PRLS_RC |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-11-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1823, 6792 | Y |  |  |  | 89956 | 89955
91176 | Add Combine Switch station next to the existing Combine station. The new Combine switch will connect to Combine NTMWD | Add Combine Switch station next to the existing Combine station. The new Combine switch will connect to Combine NTMWD |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-11-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6858, 6903, 6904, 6905 | Y |  |  |  | 91177 | 91176
70714 | La Cima Substation Addition | Add new substation to 138 kV line between Ranch Road 12 and Hill Top and install 46.7 MVA distribution transformer. The new substation will be located approximately 0.30 miles from Ranch Road 12 substation. |  | Ranch Road 12 | La Cima | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-11-10 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7185, 7186, 7190 | Y | N |  |  | 70715 | 70714
78175 |  |  |  | Franklin | Franklin | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-11-12 |  | 138 | 0 | 0 | 0 | 0,9 | Robertson | Robertson | Tier 4 |  |  |  |  | 57 | Y |  |  |  | 78176 | 78175
99544 | Establish Baines Creek 138 kV Switch | Establish Baines Creek 138 kV Switch XE Bonham Solar |  | Baines Creek 138 kV Switch | Baines Creek 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6375 | 2026-11-15 |  | 138 | 0 | 0 | 0 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 3632, 3634, 3802 | Y |  |  |  | 99545 | 99544
93242 | Saxet Substation Upgrade | This Saxet Substation Upgrade project (Phase 2) will be a continuation of the Saxet Substation Addition project (Phase 1) where LCRA TSC installed two new transmission hard taps with associated structures to LCRA TSC owned 138-kV transmission lines T522 Lon Hill – Weil Tract and T437 Lon Hill (AEP) – Nueces Bay (AEP). In this project, LCRA TSC will upgrade from the hard tap installations to a breakered facility and connect the LCRA TSC 138-kV transmission lines T522 Lon Hill – Weil Tract and T437 Lon Hill (AEP) – Nueces Bay (AEP) to the new Saxet substation. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7500 | 2026-11-20 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8441, 8452, 8858, 78568, 78569, 78570 | Y |  |  |  | 93247 | 93242
81215 | Oklaunion: Reconfigure 138 kV Station | Reconfigure the Oklaunion 138 kV station from a straight bus to a ring bus | Company Contact and In-Service Date Update | Oklaunion |  | Planned | TP2023876 | AEP TNC/ETT | James Weaver myturner@aep.com 918-599-2437 |  | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6066, 6097, 6098, 6100 | Y | N |  |  | 81216 | 81215
73621A | Hawkinsville (HAW) CNP-Owned 345kV Substation for Lavaca Bay Solar (23INR0084) | New 345kV Hawkinsville (HAW) substation for generator interconnection to Lavaca Bay Solar. Loop Ckt.27D into substation to create new Ckt.27 Jones Creek to Hawkinsville to Refuge. |  | Waterhole | BAILEY/Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 345 | 1.4 | 0 | 0 |  | Matagorda | Brazoria | Tier 4 |  |  |  |  | 42400, 42440, 42530 | Y | N |  |  | 87138 | 73621
85947 | Euclid_Substation_Addition_Updated | LCRA TSC provide a new transmission point of interconnection by constructing a new 345-kV substation and cut-in T510 Hutto - Zorn. T510 will also be looped into the new Limmer 345-kV substation |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-11-30 | 2026-11-20 | 345 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 3 |  |  |  |  | 7041, 7045, 7341 | Y |  |  |  | 100110 | 85947
81576 | Tesla: Construct New 345 kV Terminal | Interconnect the Lancium load to the existing Tesla 345 kV station | In-Service Date Update | Tesla |  | Planned | TP2024048 | AEP TNC/ETT | Zachary Lachiusa myturner@aep.com 918-599-2437 |  | 2026-11-30 |  | 345 | 0.5 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501 | Y |  |  |  | 81577 | 81576
90065 | Abilene Northwest to Mulberry Creek: Rebuild 138 kV Line | Rebuild the Abilene Northwest to Mulberry Creek 138 kV line | Company Contact and In-Service Date Update | Abilene Northwest | Mulberry Creek | Planned |  | AEP TNC | Charles Burks myturner@aep.com 918-599-2437 | TP2023881 | 2026-11-30 |  | 138 | 0 | 2.58 | 0 |  | Taylor | Jones | Tier 4 |  |  |  |  | 6228, 6288 | Y | N |  |  | 90066 | 90065
73059 | Barrera: Construct New Distribution Station | Construct new distribution station on the North Laredo Switch to Reveille 138 kV line | In-Service Date Update | Barrera |  | Planned |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 |  | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8108, 8612, 8619, 8627, 8717, 88000 | Y |  |  |  | 73060 | 73059
68183 | Estes to Putnam: Rebuild 138 kV line | Rehab the Abilene South to Putnam 138 kV line |  | Estes | Putnam | Under Construction | 68150 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 |  | 2026-11-30 | 2024-11-30 | 138 | 0 | 15 | 0 |  | Callahan | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6309, 60365, 61015 | Y | N |  |  | 68184 | 68183
93127 | Lueders: Construct New Distribution Station | Construct new distribution station on the Fort Phantom to Paint Creek 138 kV line between California Creek and Fort Phantom |  | Lueders |  | Planned |  | AEP TNC | Nelson Carroll myturner@aep.com 918-599-2437 | DR23N0002 | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Shackelford |  | Tier 4 |  |  |  |  | 6165, 6200, 60070 | Y | N |  |  | 93128 | 93127
67318 | Cruce: Construct New 345A kV Station | Construct a new 345 kV station on the Cenizo to Reforzar 345 kV line and the Del Sol to San Miguel 345 kV line |  | Cruce |  | Under Construction |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2022034 | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Jim Hogg |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 5901, 80079, 80280, 80281 | Y |  |  |  | 98843 | 67318
80464 | McKenzie Road: Rebuild 138 kV Station | Interconnect the Bootstrap loads to the rebuilt McKenzie Road 138 kV station | In-Service Date Update | Nueces | Nueces | Planned |  | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2023884 | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8520, 8545, 8858, 78568, 78569 | Y |  |  |  | 80465 | 80464
86882 | McKenzie to Westside: Reconductor 138 kV Line | Reconductor the McKenzie to Westside 138 kV line |  | McKenzie Road | Westside | Planned |  | AEP TCC/ETT | Douglas Evans deevans@aep.com 918-599-2938 | TP2024025 | 2026-11-30 |  | 138 | 0 | 0.32 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8485, 8858 | Y | Y |  |  | 86883 | 86882
68254 | Friend Ranch: Build new 138 kV Terminal | Interconnect Blue Sky Solar to the Friend Ranch 138 kV Station |  | Friend Ranch |  | Planned |  | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 |  | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 | [5 empty] | Y | N |  |  | 68255 | 68254
79988 | Lucero: Construct New 345 kV Station | Interconnect SanPat Solar I and SanPat Solar II to the new Lucero 345 kV station on the Angstrom to Naismith 345 kV line |  | Lucero |  | Planned | TP2023838 | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 |  | 2026-11-30 |  | 345 | 0.2 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8249, 8659, 80039 | Y | N |  |  | 79989 | 79988
61396 | Hamilton Road to Maxwell: Rebuild 138 kV Line | Rebuild the Hamilton Road to Maxwell 138 kV line |  | Hamilton Road | Maxwell | Planned |  | AEP TCC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | TA2019800 | 2026-11-30 |  | 138 | 0 | 29 | 0 |  | Val Verde | Val Verde | Tier 3 | 20RPG022 | 2020-11-02 | 2021-01-19 |  | 8257, 8998 | Y |  |  |  | 65593 | 61396
67322 | Cenizo to Cruce: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cenizo to Cruce |  | Cenizo | Cruce | Under Construction |  | AEP TCC/ETT | Marc Wilson jlsolis@aep.com 361-881-5574 | TP2022031 | 2026-11-30 |  | 345 | 69 | 0 | 0 |  | Webb | Jim Hogg | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079, 80220 | Y |  |  |  | 67323 | 67322
67324 | Cruce to Del Sol: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cruce to Del Sol |  | Cruce | Del Sol | Under Construction |  | AEP TCC/ETT | Marc Wilson jlsolis@aep.com 361-881-5574 | TP2022032 | 2026-11-30 |  | 345 | 54.2 | 0 | 0 |  | Jim Hogg | Starr | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079, 80355 | Y |  |  |  | 67325 | 67324
69253 | Cangrejo to Dacosta: Rebuild 138 kV Line | Rehab 138 kV line from Cangrejo to Dacosta |  | Cangrejo | Dacosta | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2026-11-30 |  | 138 | 0 | 17.97 | 0 |  |  |  | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8133, 8135, 8136, 8140, 8141, 8143, 8169, 8536, 8721, 8722, 8723, 8756, 80064, 88133 | Y |  |  |  | 87986 | 69253
73621B | Hawkinsville (HAW) CNP-Owned 345kV Substation for Lavaca Bay Solar (23INR0084) | Install generator lead from Hawkinsville (HAW) substation to LAVACA / Lavaca Bay Solar. |  | Waterhole | PHOTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 00:01 |  | 345 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 | [5 empty] | Y | N |  |  | 87139 | 73621
73371E | BP24 Sub Upgrades | Upgrade Whaley to WA Parish Ckt.72F to increase thermal limits |  | Whaley | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 00:04 | 2958101 | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44005, 44070 | Y | N |  |  | 89980 | 73371
70800 | Triada: Build New 345 kV Station | Interconnect Siete Wind to the new Triada 345 kV station on the Avanzada to Lobo 345 kV line | In-Service Date Update | Triada |  | Planned |  | ETT | Zachary Lachiusa jlsolis@aep.com 361-881-5574 | TP2022749 | 2026-11-30 12:00 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 5709, 8718, 80219, 80235 | Y |  |  |  | 70801 | 70800
93061 | Embar Switch 138 kV Capacitor Bank | Adds Embar Switch 138 kV Capacitor Bank |  | Fullerton Switch | Fullerton Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8874 | 2026-12-01 |  | 138 | 0 | 0 | 0 | 0,110.4 | Andrews | Andrews | Tier 4 |  |  |  |  | 18690 | Y |  |  |  | 93062 | 93061
70282 | New 138kV Brushy Creek Substation |  |  | Thompsons Creek | Snook | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-12-01 |  | 138 | 2.81 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32857, 32863, 32867 | Y |  |  |  | 91640 | 70282
91988 | Savanna - Canal Road 138 kV Line Rebuild | Rebuild the existing Savanna - Canal Road 138 kV Line |  | Driver | Canal Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8685 | 2026-12-01 |  | 138 | 0 | 0 | 0 |  | Reagan | Upton | Tier 4 |  |  |  |  | 10025, 10037, 23870 | Y |  |  |  | 92188 | 91988
99391A | Stanton East - Midland Basin - Spraberry 69 kV Line Conversion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L18. Convert the existing Stanton East - Midland Basin - Spraberry 69-kV line to 138-kV and cut into Consavvy 138 kV Switch to establish the Spraberry - Consavvy 138 kV Line. |  | Spraberry | Consavvy | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L18_A | 2026-12-01 |  | 138 | 0 | 5.5 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 1227, 1228, 1231, 1329, 1330, 11134, 11388 | Y |  |  |  | 99392 | 99391
91851 | Pinery 138 kV Switch | Establish Pinery 138 kV Switch |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8831 | 2026-12-01 |  | 138 | 0 | 0 | 0 | 0,110.4 | Culberson | Culberson | Tier 4 |  |  |  |  | 1079, 1090, 1095, 11079, 11132, 11224, 18695, 18719, 18727 | Y |  |  |  | 98733 | 91851
70371 | D'Hanis Capacitor addition | Add 9.6 MVAR capacitor step at D'Hanis |  | D'Hanis |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5814 | Y | N |  |  | 70372 | 70371
71319 | Upgrade Pearsall Station | Upgrade Pearsall Station to breaker and a half |  | Pearsall | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5893, 5895 | Y |  |  |  | 71320 | 71319
70373 | Driscoll Capacitor addition | adds 3 9.6 MVAR capacitor steps at Driscoll |  | Driscoll |  |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 69 | 0 | 0 | 0 | 0,28.8 |  |  | Tier 4 |  |  |  |  | 5640 | Y |  |  |  | 70374 | 70373
67329 | San Miguel to Cruce 345 kV lines | New San Miguel to Cruce 345 kV double circuit lines |  | San Miguel | Cruce | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 345 | 231.12 | 0 | 0 |  | Atascosa | Duval | Tier 1 | 21RPG017 | 2021-09-23 | 2021-12-23 |  |  | Y |  |  |  | 67330 | 67329
71928 | Upgrade Heidelberg to AEP Weslaco line | Upgrade Heidelberg to STEC WESLACO and STEC WESLACO to AEP Weslaco lines to be 478MVA capable |  | Heidelberg | Weslaco | Planned | 7193071926 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 138 | 0 | 8.6 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5765, 5768, 8354 | Y |  |  |  | 71929 | 71928
76109 | West Sinton Capacitor addition | Add a 3.6 MVAR step to existing West Sinton Capacitor |  | West Sinton |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 69 | 0 | 0 | 0 | 0,3.6 |  |  | Tier 4 |  |  |  |  | 5622 | N | N |  |  | 76110 | 76109
86782 | Add Dansk load serving substation | Cuts in new Dansk load serving station on existing Red Bluff to Danevang transmission line |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  | 2024-02-01 |  | 5546, 5549, 5588 | Y | N |  |  | 86783 | 86782
76788 | Upgrade Victoria-Rayburn | Upgrade Victoria- Loop 463- Rayburn to 403 MVA |  | Rayburn | Victoria | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 138 | 0 | 11.57 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5502, 5680, 8172 | Y |  |  |  | 76789 | 76788
81315 | add 19.2 MVAR Capacitor at Rossville | add 19.2 MVAR Capacitor at Rossville. 2023 RTP |  | Rossville |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5718 | Y |  |  |  | 87403 | 81315
76786 | Upgrade Driscoll- Loyola | Upgrade Driscol-Ricardo-Riviera-Loyola to 959.6 ACSS |  | Driscoll | Loyola | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 69 | 0 | 23.89 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 5640, 5645, 5646, 5650 | Y |  |  |  | 76787 | 76786
87069 | LST_Phantomhill_Hub Conversion | Loop another circuit of the LST Crez line into Phantom Hill station as part of Gen Interconnection Project 23INR0244, 22INR0457 and 20INR0242 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68000, 68001, 68004 | Y |  |  |  | 87070 | 87069
71182 | Reiter 345/138 kV Switch | Construct a new 345/138 kV switch |  | Odessa EHV | Wolf/Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8629 | 2026-12-01 |  | 345 | 0 | 0 | 1200 |  | Ector | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1018, 11010, 11028, 18544, 18545, 18546, 18547 | Y |  |  |  | 81601 | 71182
93683 | New Transformer will be added at Titan Substation. |  |  | Titan | Titan | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5963 | Y |  |  |  | 93684 | 93683
91419 | Max Zuehlke_Gay Hill_TL_Upgrade | Replace 336 (Linnet) conductor with 959 (Suwannee) and replace a limited number of structures to accommodate the new conductor. |  |  |  | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2026-12-01 |  | 138 | 0 | 0 | 0 |  | Washington | Washington | Tier 4 |  |  |  |  | 7565, 7572 | Y |  |  |  | 91420 | 91419
70299 | New Holleman Substation | [6 empty] | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 32005, 32892, 32893 | Y |  |  |  | 88269 | 70299
99411 | Daybreak_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor's Good Morning substation addition. Requires coordination with Oncor. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-12-02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 10168, 71212, 71214, 71216 | Y |  |  |  | 99412 | 99411
99138 | Establish Herndon 345 kV Switch | Establish Herndon 345 kV Switch |  | Herndon | Herndon | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6407 | 2026-12-02 |  | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3377, 3704, 3804 | Y |  |  |  | 99139 | 99138
89988 | McGee 345 kV Switch | Construct new 345 kV switch to connect generator |  | Wolf | Meteor | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8830 | 2026-12-03 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 10009, 10012, 11010 | Y |  |  |  | 91898 | 89988
61601 | Coody Crossing 345 kV Switch | Add Coody Crossing 345 kV Switch |  | Clear Crossing | Tecumseh Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8560 | 2026-12-03 |  | 345 | 0 | 0 | 0 |  | Throckmorton | Throckmorton | Tier 4 |  |  |  |  | 11418, 11419, 60514 | Y |  |  |  | 64014 | 61601
99150 | Establish Wags 345 kV Switch | Establish Wags 345 kV Switch |  | Wags | Wags | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6408 | 2026-12-03 |  | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3704, 3804, 3805 | Y |  |  |  | 99151 | 99150
102630 | BEPC_TPIT102630_Merryman |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-12-04 |  | 138 | 0 | 0 | 0 |  | Robertson |  | Tier 4 |  |  |  |  | 31, 32, 35, 36, 39, 53, 61, 79, 80, 1571, 1572, 11571 | Y |  |  |  | 102631 | 102630
80376 |  |  |  | WEST WEATHERFORD | SHADY GROVE | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-12-11 |  | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 477, 512, 513, 515, 1589 | Y |  |  |  | 80377 | 80376
102767 | BEPC_TPIT102767_OldGarner |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-12-11 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 510, 513, 1589 | Y |  |  |  | 102768 | 102767
75524 | This converts Bell County to Gabriel to 138 KV |  |  | Bell County | Gabriel | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-12-12 |  | 138 | 0 | 0 | 0 |  | Bell | Williamson | Tier 4 |  |  |  |  | 114, 118, 122, 132, 133, 7345, 7346 | Y |  |  |  | 75525 | 75524
93191 | Bent Tree 138 kV Substation | Establish Bent Tree 138 kV Substation with 55.2 MVAR capacitor bank using 3-18.4 MVAR stages |  | Bent Tree Substation | Bent Tree Substation | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6388 | 2026-12-14 |  | 138 | 0 | 0 | 0 | 0,55.2 | Williamson | Williamson | Tier 4 |  |  |  |  | 3664, 3667, 3764 | Y |  |  |  | 93192 | 93191
72011A | Tonkawa - Ranger Camp 345 kV Line Rebuild | Tonkawa - Ranger Camp 345 kV Second Circuit Addition |  | Tonkawa | Ranger Camp | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2026-12-15 |  | 345 | 0 | 21.3 | 0 |  | Mitchell | Scurry | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 10049, 11048 | Y |  |  |  | 99961 | 72011
81034 | Lamesa - Willow Valley 138 kV Line | Rebuild Lamesa to Willow Valley 138 kV line. |  | Lamesa Switch | Willow Valley Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8654 | 2026-12-15 |  | 138 | 0 | 32.1 | 0 |  | Borden | Dawson | Tier 3 |  |  |  |  | 1163, 1301, 1307, 1308 | Y |  |  |  | 81035 | 81034
99413 | Establish Pivot 138/69 kV Switch | Construct Pivot 138/69 kV Switch approved as part of 24RPG015 |  | Lamesa | Pivot | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8800 | 2026-12-15 |  | 69 | 0 | 2.1 | 0 |  | Dawson | Dawson | Tier 1 | 24RPG015 | 2024-05-02 |  |  | 1163, 1164, 1362, 1363, 1364, 1389, 1390, 1391, 9400, 11362, 18881, 18882, 18920 | Y |  |  |  | 99414 | 99413
102849 | Union 138 kV Switch | Establish Union 138 kV Switch |  | Union | Union | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8608 | 2026-12-15 |  | 138 | 0 | 13.6 | 0 |  | Scurry | Scurry | Tier 4 |  |  |  |  | 1064, 1304, 1310, 1311, 1312, 1313, 1314, 10050, 18555, 180256 | Y |  |  |  | 102850 | 102849
99479A | Snyder - China Grove 69 kV Loop Converstion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L23. Convert the existing Snyder - Scurry - China Grove and Snyder - Amoco Tap - China Grove 69-kV lines to 138-kV. This phase converts the existing Snyder - Lake Thomas 69 kV Line into 138 kV and reterminates into the new Bluff Creek 138 kV Switch. |  | China Grove | Bluff Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L23 | 2026-12-15 |  | 138 | 0 | 8 | 0 |  | Scurry | Scurry | Tier 1 |  |  |  |  | 1300, 1309, 1310, 1318, 1367, 1368, 1369, 1372, 10191, 10192, 10193, 10199, 10200, 10202 | Y |  |  |  | 99480 | 99479
62445 | Base Camp (FKA Eagle Mountain) 138kV Switch Rebuild | Rebuild existing 138 kV Switch |  | Base Camp | Base Camp | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5261 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 568, 1859, 1860, 1864, 1865, 11859, 11860, 11861, 11864, 11865, 11866, 12065 | Y |  |  |  | 70920 | 62445
64239 | Vineyard Switch-Cypress Waters Switch 138 kV Line | Construct a new 138 kV circuit from Vineyard to Cypress Waters |  | Cypress Waters Switch | Vineyard Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5320 | 2026-12-15 |  | 138 | 7.4 | 0 | 0 |  | Dallas | Tarrant | Tier 3 |  |  |  |  | 2017, 2022, 2386, 12012, 12013, 15030, 15031, 15035, 15040, 15041 | Y |  |  |  | 86787 | 64239
91074 | POI for Fort Watt Storage (Emerald Hills Switch) | POI for Fort Watt Storage (Emerald Hills Switch) |  | Everman Switch | Burleson Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3512 | 2026-12-15 | 2024-05-15 | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1588, 1933, 2208 | Y |  |  |  | 91075 | 91074
62434 | Sargent Road - Industrial Blvd 138 kV DCKT Line | Upgrade existing 138 kV Line |  | Sargent Road Switch | Industrial Blvd Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4128 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2940, 2947, 2972, 2973, 2974, 2975, 2976, 2977, 2982 | Y |  |  |  | 99935 | 62434
66190 | East Levee - Industrial Blvd 138 kV DCKT Line | Rebuild East Levee - Industrial Blvd 138 kV DCKT Line |  | East Levee | Industrial | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4213 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2481, 2482, 2874, 2875, 2876, 2974, 2976 | Y |  |  |  | 66191 | 66190
92847 | Oncor_ME_Norwood 345 kV Terminal Equipment | Upgrade Norwood Switch 345 kV Terminal Equipment |  | Norwood |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4425 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 1928, 2406 | Y |  |  |  | 92851 | 92847
81418 | Reiter to Yarbrough 138 kV Line Rebuild | Rebuild the existing138 kV line from Reiter to Yarbrough |  | Reiter | Yarbrough | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8527 | 2026-12-15 |  | 138 | 0 | 27.2 | 0 |  | Ector | Crane | Tier 3 |  |  |  |  | 11111, 18545 | Y |  |  |  | 81419 | 81418
102846 | Longshore 345 kV Switch Rebuild | Longshore 345 kV Switch Rebuild: Cattleman 345 kV Line Re-terminations |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Mitchell | Howard | Tier 1 | 23RPG034 |  |  |  | 1058, 10053, 18548 | Y |  |  |  | 102847 | 102846
87017 | Riverton - Sandlake 138 kV Line Conversion 345 kV and Riverton - Sandlake 138 kV Line | Convert Riverton – Sandlake 138 kV Line to 345 kV and Establish Riverton – Sandlake 138 kV Line |  | Riverton | Sandlake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8793 | 2026-12-15 |  | 345 | 39.9 | 0 | 0 |  | Ward | Reeves | Tier 1 | 24RPG010 | 2024-03-18 |  |  | 1011, 11083, 11084, 11097, 11098 | Y |  |  |  | 87679 | 87017
99269 | Grady - Coronado Midstream Tap - Sale Ranch 138 kV line | Add Permian Basin Reliability Plan Upgrade ID L19. Upgrade the existing Grady - Coronado Midstream Tap - Sale Ranch 138-kV line |  | Grady | Sale Ranch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8834 | 2026-12-15 |  | 138 | 0 | 7.2 | 0 |  | Martin | Martin | Tier 3 |  |  |  |  | 23841, 23842, 23844 | Y |  |  |  | 99270 | 99269
99287 | Clearfork 345 kV Switch | Construct Clearfork 345 kV Switch approved as part of 24RPG015 |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8801 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 1 | 24RPG015 | 2024-05-02 |  |  |  | Y |  |  |  | 99288 | 99287
91881 | Medallion138 kV Switch | Add Medallion138 kV Switch |  | Midland | Midland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8821 | 2026-12-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Midland | Midland | Tier 4 |  |  |  |  | 1172, 1195, 1200, 10124, 11145 | Y |  |  |  | 91882 | 91881
66218B | Hillsboro - Italy 69 kV Line | Rebuild the Milford-Italy 69 kV Line |  | Milford | Italy | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4326 | 2026-12-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  | 2021-04-23 | 2021-05-18 |  | 2337, 2338 | Y |  |  |  | 73690 | 66218
99941 | Kirkland 138 kV Capacitor Bank | Kirkland 138 kV Capacitor Bank |  | Kirkland |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4022 | 2026-12-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas |  | Tier 4 |  |  |  |  | 2456 | Y | N |  |  | 99942 | 99941
71910A | Rebuild the Hillsboro - Elm Mott 69 kV Line | Rebuild the Elm Mott Switch - West 69 kV Line Section |  | Elm Mott 69 kV Switch | West 69 kV Substation | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6221 | 2026-12-15 |  | 69 | 0 | 9 | 0 |  | McLennan | McLennan | Tier 3 |  |  |  |  | 3408, 3526, 3527, 3528, 3529, 13525 | Y |  |  |  | 91605 | 71910
87792 | Establish the Bynum 345 kV Switch | Establish the Bynum 345 kV Switch |  | Bynum Switch | Bynum Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6369 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 1907, 3383, 68090 | Y |  |  |  | 87793 | 87792
91461 | Establish Tarantula 345 kV Switch | Establish Tarantula 345 kV Switch for Three Canes Solar |  | Tarantula 345 kV Switch | Tarantula 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6412 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3344, 3380, 3381, 68091 | Y |  |  |  | 99548 | 91461
91457 | Establish Drane 345 kV Switch | Establish Drane 345 kV Switch |  | Drane 345 kV Switch | Drane 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6410 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3295, 3376, 68091 | Y |  |  |  | 91458 | 91457
73567 | Berry Creek Substation Addition | Substation addition to provide Point of Interconnection for Oncor Andice substation addition. |  | Berry Creek |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7361, 7521, 70522 | Y | N |  |  | 78401 | 73567
89912 | Olmos to Wilson T297 Transmission Line Rebuild | Rebuild 7.18 miles of 138 kV from 477 conductor wood pole line to 795 drake conductor concrete/steel transmission line |  | Olmos | Wilson | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Wilson | Tier 4 |  |  |  |  | 7613, 7615 | Y |  |  |  | 89913 | 89912
22TPIT0000 | Parkway Substation T2 Replacement | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2026-12-15 | 2025-08-08 | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10680 | 3324
80546C | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild and double-circuit the Georgetown East - Sonterra 138 kV Line Section |  | Georgetown East | Sonterra | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2026-12-15 |  | 138 | 12.9 | 12.9 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 121, 3688, 7346, 7528 | Y |  |  |  | 87631 | 80546 | 2023-SC17
87768 | Pintail 138 kV Capacitor Bank | Install a 110.4 MVAR Capacitor Bank at Pintail 138 kV Switch |  | Pintail | Pintail | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6346 | 2026-12-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Williamson | Williamson | Tier 4 |  |  |  |  | 3692 | Y |  |  |  | 87769 | 87768
76660 | Rebuild Temple Switch and install auto #2 | Rebuild Temple Switch and install auto #2 |  | Temple | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6197 | 2026-12-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3414, 3415, 3718 | Y |  |  |  | 76661 | 76660 | 2023-NC60
76572 | Temple - Temple Pecan 138 kV 2nd Circuit | Temple - Temple Pecan 138 kV 2nd Circuit |  | Temple | Temple Pecan Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6235 | 2026-12-15 |  | 138 | 0 | 4.4 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3415, 3420 | Y |  |  |  | 76573 | 76572
76650 | Establish Walleye Creek 345/138 kV Switch | Establish Walleye Creek 345/138 kV Switch |  | Walleye Creek | Walleye Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6243 | 2026-12-15 |  | 345 |  | 4.5 | 600 | 0,110.4 | Milam | Milam | Tier 3 |  |  |  |  | 116, 3541, 3712, 3713, 3714, 3715, 3716, 3717, 3742, 7040, 13429, 13430 | Y |  |  |  | 76651 | 76650
66214 | Upgrade and convert Brownwood - Lake Brownwood 69 kV Line to 138 kV | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV, decommission the Brownwood 69 kV Switch and Autotransformer |  | Brownwood | Lake Brownwood | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6164 | 2026-12-15 |  | 138 | 0 | 10.8 | 0 |  | Brown | Brown | Tier 4 |  |  |  |  | 1637, 1661, 1662, 1670, 3800, 6408 | Y |  |  |  | 92939 | 66214
71187 | Reiter - Tesoro 345 kV Double-Circuit Line | Construct new 2.5-mile 345 kV double-circuit line from Tesoro to Reiter |  | Tesoro | Reiter | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8629 | 2026-12-15 |  | 345 | 5 | 0 | 0 |  | Midland | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 18540, 18544 | Y |  |  |  | 71189 | 71187
87510 | RCEC_BranchChanges_Kaufman_Update3 | Modifying branch impedance between I20_RC and TALTY_RC |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-12-16 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6902 | Y |  |  |  | 87511 | 87510
87653 | Stoplight (fka Bluff Creek) - Union 138 kV Line Rebuild | Rebuild the existing Stoplight (fka Bluff Creek) - Union 138 kV Line Rebuild |  | Stoplight (fka Bluff Creek) | Union | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9002 | 2026-12-16 |  | 138 | 0 | 16 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  |  | 1310, 10200, 18555 | Y |  |  |  | 87654 | 87653
82714 | Rebuild of Airport of Substation | Atlas Substation will be replacing Airport Substation. |  | Filter Plant (BPUB), South Plant (BPUB), and Southmost (STEC) | Atlas (BPUB) | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2026-12-22 | 2026-03-02 | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5789, 59420, 59440, 59500 | Y | N |  |  | 82715 | 82714
68205 | GENRAL to Garden Villas Rebuild | Rebuild and Reconductor portion of Ckt.12B Bringhurst (GENRAL) to Garden Villas to prepare for future 138kV Conversion |  | GENRAL | Garden Villas | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-30 | 2025-09-11 | 69 | 0 | 9.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42690, 47540 | Y | N |  |  | 68206 | 68205
85965 | RGEC_Altuda 69-kV In-line_Breaker_Installation | Install 69-kV breaker between Alpine Switch and Persimmon Gap substation at Altuda substation. |  | Alpr2A (6665) | PrsmnGap2A (6669) | Planned | 61232 | RGEC | Ruben Quiroga rquiroga@rgec.coop 830-291-4203 |  | 2026-12-30 |  | 69 | 0 | 0 | 0 |  | Brewster | Brewster | Tier 4 | [5 empty] | Y |  |  |  | 85966 | 85965
45136 | CPSE_New Midtown Substation | New Mid Town substation looped into Comal St to Olmos transmission line. |  |  |  | Planned | S-0910 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0283 | 2026-12-30 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5096, 5311, 5325 | Y |  |  |  | 45137 | 45136
87431 | Rebuild Wickett to Winkler 69kV line. |  |  | TNMP Winkler (37960) | TNMP Wickett (37980) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 6.8 | 0 |  | Winkler | Ward | Tier 4 |  |  |  |  | 37960, 37980 | Y |  |  |  | 87432 | 87431
86796 | Buccaneer: Construct New 69 kV Station | Interconnect the Oncor Regency station to the new Buccaneer 69 kV station on the Eden to North Brady 69 kV line between Melvin and North Brady |  | Buccaneer |  | Planned | TP2024028 | AEP TNC | Sally Matthews myturner@aep.com 918-599-2437 |  | 2026-12-31 |  | 69 | 0 | 0 | 0 |  | McCulloch |  | Tier 4 |  |  |  |  | 6006, 6380, 60005 | Y | N |  |  | 86797 | 86796
86771 | Scissortail: Construct New 138 kV Station | Interconnect the TNMP Flycatcher station to the new Scissortail 138 kV station on the Saragosa to Solstice 138 kV line between Hoef's Road and Verhalen |  | Scissortail |  | Planned | TP2024044 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 6077, 60207, 60808 | Y | N |  |  | 86772 | 86771
75786 | This project will create a POI Bus (station) named Skydancer to interconnect 23INR0295 | This project will create a POI Bus (station) named Skydancer to interconnect 23INR0295 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 68055, 68080, 68090 | Y |  |  |  | 75787 | 75786
98593 | Quanah: Rebuild 69 kV Station | Rehab Quanah 69 kV station | Terminal, Company Contact and In-Service Date Update | Quanah |  | Planned |  | AEP TNC | William Lovelace myturner@aep.com 918-599-2437 | TA2018027 | 2026-12-31 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6048, 6051, 6057, 69194 | Y |  |  |  | 98594 | 98593
98612 | Plover: Rebuild 69 kV Station | Rebuild Eldorado Cities Service Co. Tap and rename to Plover | Associated Projects, Company Contact, Transmission Owner Project Number, and In-Service Date Update | Plover |  | Planned | TA2024810 | AEP TNC | Lance Ordner myturner@aep.com 918-599-2437 |  | 2026-12-31 |  | 69 | 0 | 0 | 0 |  | Schleicher |  | Tier 4 |  |  |  |  | 6505, 6506, 6507, 6508, 6693, 60161 | Y | N |  |  | 98613 | 98612
98616 | Dotterel: Rebuild 69 kV Station | Rebuild Middle Valley REA Tap and rename to Dotterel | Company Contact, Transmission Owner Project Number, and In-Service Date Update | Dotterel |  | Planned | TA2024810 | AEP TNC | Lance Ordner myturner@aep.com 918-599-2437 |  | 2026-12-31 |  | 69 | 0 | 0 | 0 |  | Schleicher |  | Tier 4 | [5 empty] | Y | N |  |  | 98617 | 98616
100030 | Beeville: Replace 69 kV Cap Banks | Replace the failed 69 kV capacitor banks at the existing Beeville 69 kV station |  | Beeville |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-12-31 |  | 69 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8198, 8199 | Y |  |  |  | 100031 | 100030
59197 | Mason to Mason Switch: Rebuild 69 kV Line | Rehab the Mason to Mason Switch 69 kV Line | Company Contact and In-Service Date Update | Mason | Mason Switch | Planned | 1126 - 1304 | AEP TNC | Forrest Farson myturner@aep.com 918-599-2437 | 1871 | 2026-12-31 |  | 69 | 0 | 10.3 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6393, 6394, 6396, 6407, 60458 | Y | N |  |  | 59198 | 59197
64499 | Hyde Park to Downtown Ckt.32A Upgrades | Upgrade Hyde Park to Downtown Ckt.32A |  | Downtown | Hyde Park | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 69 | 0 | 1.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47500, 47510, 47570, 47690 | Y | N |  |  | 64500 | 64499
72029A | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ Solar (23INR0040) and Dori BQ BESS (24INR0196) | Loop new CEHE 138kV substation Ashville (ASH) into Ckt.06F Garden Villas to Holmes to create new Ckt.06 Garden Villas to Ashville to Holmes |  | Ashville | Garden Villas/ Holmes | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42680, 42770, 47210 | Y | N |  |  | 90115 | 72029
87429 | Reconductor Wickett to Staghorn 138kV line. |  |  | TNMP Wickett (37981) | TNMP Staghorn (37990) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 12.05 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37981, 37990 | Y |  |  |  | 87430 | 87429
77803 | Cowpen 345kV station from TNMP submitted Cowpen/Silverleaf RPG |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 345 | 14.26 | 0 | 1500 |  | Reeves | Reeves | Tier 1 |  | 2023-05-11 | 2023-11-27 | 2024-01-09 | 18669, 38023, 38027, 38042, 38043, 38044, 38045, 38048, 38055 | Y |  |  |  | 77804 | 77803
77807 | Silverleaf 345kV station from TNMP submitted Cowpen/Silverleaf RPG |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 345 | 4.05 | 0 | 2250 |  | Ward | Ward | Tier 1 |  | 2023-05-11 | 2023-11-27 | 2024-01-09 | 18668, 38091, 38143, 38145, 38147, 38148, 38149, 38150, 38165 | Y |  |  |  | 77808 | 77807
77805 | TNMP Pecos County RPG |  |  | Leon Creek (bus # 38355) | Coyanosa (bus # 38380) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 31.2 | 0.6 | 0 |  | Pecos | Reeves | Tier 1 |  | 2023-08-02 | 2024-02-08 | 2024-03-06 | 6601, 38355, 38380, 38445 | Y |  |  |  | 77806 | 77805
66366 | Rebuild Brazoria - Retrieve 138kV with bundled 795 ACSS | Planned ISD is Q4 2024, but project design currently under internal review. |  | TNMP Brazoria (bus # 39600) | CenterPoint Retrieve (bus # 43170) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 6.17 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39600, 43170 | Y |  |  |  | 66367 | 66366
76669 | Eiland - Elbow 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L20H. Upgrade the existing Eiland - Elbow 138-kV line |  | Elbow | Eiland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8665 | 2026-12-31 |  | 138 | 0 | 18.5 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 23834, 23853 | Y |  |  |  | 77043 | 76669
99427 | Luther - Bulldog 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L20I. Upgrade the existing Luther - Bulldog 138-kV line |  | Luther | Bulldog | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8553 | 2026-12-31 |  | 138 | 0 | 18.6 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 23831, 23832, 23833 | Y |  |  |  | 99428 | 99427
61406 | Kendall - Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T584 Kendall to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 10.2-mile double-circuit transmission line by replacing the aging conductor. |  | Kendall | Welfare | Planned | 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-12-31 |  | 138 | 0 | 10.2 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7152, 7153, 7770 | Y | N |  |  | 78330 | 61406
91847B | Hornsby Load Power Transformer Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8186 | 2026-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7045, 7047, 7341 | Y |  |  |  | 102392 | 91847
85973 | Georgetown - Rivery Transmission Line Upgrade | LCRA TSC will upgrade T597 Georgetown - Rivery 138-kV transmission line to achieve a higher operational rating. |  | Georgetown Substation |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-762-3658 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7343, 7347 | Y |  |  |  | 85974 | 85973 | 2023-SC17
85950 | Alford Substation Addition | This project will construct the new 138-kV Alford Substation. Alford will be near the existing Oncor Midkiff Substation and the planned Oncor Catclaw Switch. Alford will connect T594 Midkiff to Skywest and T611 Benedum to Midkiff and will provide two (2) 138-kV POIs for Oncor Catclaw Switch. | [5 empty] | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 | 23RPG019 | 2023-08-03 | 2023-08-25 |  | 1210, 10058, 71210, 71211, 71213 | Y |  |  |  | 85951 | 85950 | 2023-FW8
100020 | Rebuild Spruce to Pawnee into a double circuit | This project is phase 2 of the Spruce to Pawnee Double circuit rebuild. Phase 2 captures the CPS owned portion of the existing Spruce to Pawnee circuit 1 being upgraded. The remaining STEC owned portion will be upgraded/completed at a later date. |  | 5400 | 5725 | Planned |  | CPS/STEC | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-12-31 |  | 345 | 45.83 | 45.83 | 0 |  |  |  | Tier 1 |  |  |  |  | 5400, 5725 | Y |  |  |  | 100021 | 100020
99453J | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.98A Bellaire to Smithers to increase thermal limits as part of FRM2 upgrades. |  | Bellaire | Smithers | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44650, 47000 | Y | N |  |  | 102610 | 99453
102536 | Rebuild/reconductor portions of Ckt.94B King to CHAMON as a Hardening upgrade |  |  | King | CHAMON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 48186, 111263 | Y | N |  |  | 102537 | 102536
87637 | Install (2) new 100 MVA distribution transformers at Liberty substation to serve customer load. | Install (2) new 100 MVA distribution transformers at Liberty substation to serve customer load. |  | Baytown | KENNY/ Baytown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40961, 40962 | Y | N |  |  | 90200 | 87637
87346 | Upgrade Ckt 25 Jeanetta to Westwood to increase thermal limits | Upgrade Ckt 25 Jeanetta to Westwood to increase thermal limits |  | Westwood | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 2.16 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47310, 48417 | Y | N |  |  | 87347 | 87346
75856A | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. Loop into Ckt.96G to create new Ckt.96G PHILIP to ETHYL 138kV to BEARLE. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. |  | ETHYL | South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 69 | 1.33 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41240, 41370 | Y | N |  |  | 90334 | 75856
75856B | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. Loop into Ckt.96G to create new Ckt.96G PHILIP to ETHYL 138kV to BEARLE. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. | Convert ETHYL customer 69kV substation to 138kV. Loop into Ckt.96G to create new Ckt.96G PHILIP to ETHYL 138kV to BEARLE. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. |  | ETHYL | Jefferson/South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40550, 41230, 41250, 41270, 41381, 41382 | Y | N |  |  | 90335 | 75856
72044A | Clute 138kV Switching Station | Reconfigure existing Ckt.82F RIWOOD to CAVERN to BIPORT and loop into new CEHE-owned 138kV Clute switching station to create new Ckt.82 RIWOOD to Clute to CAVERN to BIPORT. |  | Clute | RIWOOD/CAVERN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 | 42050, 43150, 43330 | Y | N |  |  | 87454 | 72044
78485C | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade portions of Ckt.05E Bellaire to Sharpstown to Hillcroft to increase thermal limits. |  | Bellaire | Hillcroft | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 3.09 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 47015, 48145, 48343 | Y | N |  |  | 98949 | 78485
78485D | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Bellaire to Ulrich to Hillcroft to increase thermal limits. |  | Bellaire | Hillcroft | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 6.41 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 48146, 48378, 48512 | Y | N |  |  | 98950 | 78485
90161A | Install new Mill Creek (MLC) distribution substation with (2) 100 MVA transformers. | Install new Mill Creek (MLC) distribution substation with (2) 100 MVA transformers. Loop substation on Ckt.81G to create new Ckt.81G Pinehurst to Mill Creek to Tomball. |  | Mill Creek | Pinehurst/ Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 9 | 0 | 0 |  | Montgomery | Harris | Tier 4 |  |  |  |  | 44850, 46240, 46510 | Y | N |  |  | 91233 | 90161
90161C | Install new Mill Creek (MLC) distribution substation with (2) 100 MVA transformers. | Convert Pinehurst to unity power factor substation. |  | Pinehurst |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Montgomery |  | Tier 4 | [5 empty] | Y | N |  | No Transmission upgrades expected. | 91234 | 90161
90161B | Install new Mill Creek (MLC) distribution substation with (2) 100 MVA transformers. | Relocate existing Kluge 80 MVAR cap bank CB1 from Ckt.81F line position to Ckt.81G line position. |  | Kluge |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 91235 | 90161
72044B | Clute 138kV Switching Station | [6 empty] | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  |  | 87455 | 72044
72029B | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ Solar (23INR0040) and Dori BQ BESS (24INR0196) | Install one generator lead from CEHE 138kV substation Ashville (ASH) to SUNLIT/Dori BQ Solar. Utilize same generator lead as Dori BQ BESS. |  | Ashville | SUNLIT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 90116 | 72029
78455 | Oasis 345kV Substation / SOHO BESS II (25INR0162) | Install SOHO BESS II at Oasis 345kV substation… Connect at the same generator lead as SOHO BESS (SOHO BESS II - 25INR0162) |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 43035, 113321, 113322 | Y | N |  |  | 78456 | 78455
72029C | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ Solar (23INR0040) and Dori BQ BESS (24INR0196) | Install one generator lead from CEHE 138kV substation Ashville (ASH) to SUNLIT/Dori BQ BESS. Utilize same generator lead as Dori BQ Solar. |  | Ashville | SUNLIT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 90117 | 72029
78461B | West Columbia to Damon and Needville to Big Creek Ckt.89A Upgrades | Rebuild/reconductor Needville to Big Creek Ckt.89 as a Hardening upgrade. |  | Needville | Big Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 5.46 | 0 |  | Brazoria | Brazoria | Tier 4 | 23RPG021 | 2023-08-10 | 2023-08-31 | 2023-08-31 | 42380, 42390 | Y | N |  |  | 78463 | 78461
78468A | Pradera (PRD) CEHE-Owned 345kV Substation for Austin Bayou Solar (25INR0102) | New 345kV Pradera (PRD) substation for generator interconnection to Austin Bayou Solar (25INR0102). Loop Ckt.27 into Pradera substation to create new Ckt.27 Seabreeze to Pradera to Savannah. |  | Pradera | Savannah/ Seabreeze | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:02 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42590, 43020, 43035 | Y | N |  |  | 102676 | 78468
72044C | Clute 138kV Switching Station | Reconfigure existing Ckt.26D STRATT to SINTEK and loop into new CEHE-owned 138kV Clute switching station to create new Ckt.26 STRATT to Clute to SINTEK. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 | 42030, 42050, 42110, 42111, 43240, 43300 | Y | N |  |  | 87456 | 72044
72044D | Clute 138kV Switching Station | [6 empty] | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  |  | 87457 | 72044
78468B | Pradera (PRD) CEHE-Owned 345kV Substation for Austin Bayou Solar (25INR0102) | Install generator lead from Pradera (PRD) substation to AUSTIN (ABY) customer substation (25INR0102). |  | Pradera | AUSTIN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:03 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 102677 | 78468
80468 | Conoco: Construct New 138 kV Terminal | Interconnect Isaac Solar to the Conoco 138 kV station | Company Contact and In-Service Date Update | Conoco |  | Planned |  | AEP TCC | William Edwards deevans@aep.com 918-599-2938 |  | 2026-12-31 12:00 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8114, 113651 | Y |  |  |  | 80469 | 80468

## CompletedTPIT020126NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2026
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
82210 | PMCR for LEAGUE CITY STATION REBUILD | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-05-31 | 2025-01-24 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38920 | Y |  |  |  | 82211 | 82210
73368 | Grey Well Draw - Buffalo 138 kV Second Circuit | Add Grey Well Draw - Buffalo 138 kV Second Circuit |  | Grey Well Draw | Buffalo | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8692 | 2024-12-15 | 2025-01-01 | 138 | 6 | 26.2 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 10061, 11390, 11396, 23837, 23858 | Y |  |  |  | 87790 | 73368
77074 | Buda to Turnersville Storm Hardening | Rebuild single circuit section of Buda to Turnersville and reconductor with bundled 795 ACSR Conductor, 439 MVA. |  | Buda | Turnersville | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-12-31 | 2025-01-09 | 138 | 0 | 3.8 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7500, 70498 | Y | N |  |  | 77075 | 77074
73352B | PH Robinson Area 138kV Upgrades | Upgrade Ckt.79F PH Robinson to Seabrook to HANNAH to HUNTER to increase thermal limits |  | PH Robinson | Seabrook | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:01 | 2025-01-09 | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42780, 42830, 42852, 48282 | Y | N |  |  | 73354 | 73352
90790 | Palafox: Construct New 138 kV Temporary Tap | Construct new temporary tap on the North Laredo Switch to Reveille 138 kV line between Barrera and North Laredo Switch | IN-SERVICE |  |  | In-Service |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 | TP2024132 | 2025-01-18 | 2025-01-18 | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8108, 8909, 88000 | Y |  |  |  | 90791 | 90790
78167 | Add 2nd autotransformer at Trumbull | Add 2nd autotransformer at Trumbull |  | Trumbull | Trumbull | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-01-23 | 2025-02-20 | 69 | 0 | 0 | 40 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 221, 222 | Y |  |  |  | 78168 | 78167
76682 | Add Capacitor Bank at Savanna 138 kV Substation | Add Capacitor Bank at Savanna 138 kV Substation |  | Savanna |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8694 | 2025-01-31 | 2025-01-31 | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 10025, 23867, 23870 | Y |  |  |  | 81462 | 76682
73371F | BP24 Sub Upgrades | Upgrade Jeanetta to WA Parish Ckt.64A to increase thermal limits |  | Jeanetta | WA Parish | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-01-31 00:05 | 2025-06-05 | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47300 | Y | N |  |  | 89975 | 73371
73371H | BP24 Sub Upgrades | Upgrade White Oak to Jeanetta Ckt.72B to increase thermal limits |  | White Oak | Jeanetta | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-01-31 00:07 | 2025-02-11 | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46600, 47300 | Y | N |  |  | 89977 | 73371
67919 | Avanzada: Construct New 345 kV Station | Interconnect Outpost Solar to the Lobo to Fowlerton 345 kV line | IN-SERVICE | Avanzada |  | In-Service |  | ETT | Zachary Lachiusa jlsolis@aep.com 361-881-5574 |  | 2025-02-14 | 2025-02-14 | 345 | 0.1 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 5709, 80219, 80235 | Y |  |  |  | 67920 | 67919
6216 | Bartlett Switch to Bartlett | Bartlett Switch to Bartlett |  | Bartlett Switch | Bartlett | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-02-14 12:00 | 2025-05-12 | 69 | 0 | 2.7 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 114, 118 | Y |  |  |  | 13941 | 6216
81605 | Kolb Lake 138 kV POD | Establish Kolb Lake 138 kV POD |  | Kolb Lake POD | Kolb Lake POD | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6229 | 2025-02-15 | 2958101 | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3307, 3340, 3346, 3347, 3747 | Y |  |  |  | 81606 | 81605
72876A | Provide 138 kV POD for Skybox at Teal Switch |  |  | Teal | Skybox | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6259 | 2025-02-15 | 2958101 | 138 | 0.2 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3362, 3371 | Y |  |  |  | 72877 | 72876
50725 | Lean Clay 138 kV Switch | Construct a new 138 kV switch |  | Culberson | Sand Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8658 | 2025-02-15 | 2025-02-01 | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 1097, 11078, 11086 | Y |  |  |  | 82894 | 50725
70223 | Mont - Pilot Grove Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 8-mile Mont ¿ Pilot Grove (T140) 138-kV transmission line. |  | Mont | Pilot Grove | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-02-17 | 2025-02-21 | 138 | 0 | 8 | 0 |  | Lavaca | Lavaca | Tier 4 |  |  |  |  | 7234, 7235, 7249 | Y | Y |  |  | 70224 | 70223
79683 | Add Branch between Padua and Sommers |  |  | 5395 | 170722 | Planned | S-0969, T-0327 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-02-18 | 2025-02-18 | 138 | 2.06 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5395, 170722 | Y |  |  |  | 79684 | 79683
54220 | Brazos' member will build McFarland substation, Brazos will install POI Picard | Brazos' member will build McFarland substation, Brazos will install POI Picard |  | Picard | Picard | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-02-23 | 2025-05-18 | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 483, 485, 486, 527 | Y |  |  |  | 54221 | 54220
76622 | Expand Peters 138kV substation for Walstrom BESS (22INR0540). | Expand Peters 138kV substation for Walstrom BESS (22INR0540). |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 | 2025-02-28 | 138 | 0 | 0 | 0 |  | Austin | Austin | Tier 4 |  |  |  |  | 46220, 171382 | Y | N |  |  | 76623 | 76622
78374 | Rockhound 345/138 kV Switch | Construct a new 345/138 kV Switch |  | Falcon Seaboard | Midland East | Under Construction |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8705 | 2025-03-01 | 2025-02-14 | 345 | 0 | 0 | 1200 |  | Midland | Martin | Tier 3 | 24RPG002 | 2024-01-11 |  |  | 1021, 1025, 10062, 10063, 10064, 10065, 11390, 23837, 23843, 23858 | Y |  |  |  | 78375 | 78374
61392 | Bergheim - Fair Oaks Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T238 Bergheim to Fair Oaks 138-kV and T656 Bergheim to Kendall 345-kV 4.1-mile double-circuit transmission line by replacing the aging conductor. |  | Bergheim | Fair Oaks Ranch/Kendall | Planned | 61406, 61358, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-03-12 | 2025-03-12 | 345 | 0 | 4.1 | 0 |  | Comal | Kendall | Tier 4 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7169, 7170, 7770 | Y | N |  |  | 61393 | 61392
45501 | Eldorado Live Oak to Sonora: Rebuild 69 kV line | Rehab Eldorado Live Oak to Sonora 69 kV line | IN-SERVICE | Eldorado Live Oak | Sonora | In-Service | 982 - 1160 | AEP TNC | David Baker twang1@aep.com 918-599-2635 | 2769 | 2025-03-12 01:00 | 2025-03-12 | 69 | 0 | 23.92 | 0 |  | Schleicher | Sutton | Tier 3 | 18RPG012 | 2018-12-18 | 2019-01-17 |  | 6054, 6498, 6503, 6505, 6509, 6510, 6513 | Y | N |  |  | 65530 | 45501
72500 | Rio Lago - New 138kV Substation | Loop new 138kV substation into the existing 138kV Bandera to Verde Creek line and install 40MVA distribution transformer. The new substation will be located approximately 1.64 miles from Bandera substation (23INR0078) |  | Bandera | Verde Creek | Planned |  | BEC | Jhonatan Guerrero Rivera j.rivera@banderaelectric. 830-612-0048 |  | 2025-03-17 | 2025-03-21 | 138 | 0.1 | 0 | 0 |  | Bandera | Bandera | Tier 4 |  |  |  |  | 7146, 7436, 7438 | Y | N |  |  | 72501 | 72500
47541 | Crane Circuit Breaker Addition | Provide transmission service to American Electric Power at Crane Substation. Adding one (1) breaker and associated equipment needed to connect the AEP-owned Crane to Kinnison 138-kV transmission line. |  | Crane Substation | Crane Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2025-03-17 02:00 | 2025-02-26 | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 76615 | Y | N |  |  | 78402 | 47541
73895 | Sunglow Substation Addition | This project provides a point of interconnection for a new battery energy storage resource at a new 138-kV Sunglow Substation between LCRA TSC T627 and LCRA Rosita Creek Substation. |  | Sunglow |  | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-03-28 | 2025-03-12 | 138 | 0 | 0 | 0 |  | Maverick |  | Tier 4 |  |  |  |  | 8260, 78015, 78016 | Y | N |  |  | 73896 | 73895
69890 | Bailey 345kV Substation Expansion for Ray Gulf Wind (22INR0517) | Expand 345kV Bailey substation for Ray Gulf Wind generator interconnection (22INR0517) |  | Bailey |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-03-31 | 2025-07-08 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44040, 114215 | Y | N |  |  | 69891 | 69890
71954 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 |  | Orange Grove | Talitha | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-04-01 | 2025-04-01 | 138 | 0.73 | 0 | 0 |  | Jim Wells | Jim Wells | Tier 4 |  |  |  |  | 5660, 5661 | Y |  |  |  | 71955 | 71954
61234 | Antler - Bergheim Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the T493 Antler to Bergheim 138-kV and T389 Bergheim to Hays Energy 345-kV 7.2-mile double-circuit transmission line by replacing the aging conductors from Antler to Bergheim substations. |  | Antler | Bergheim | Planned | 61406, 61358, 61392, 61350, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-04-01 | 2025-02-24 | 345 | 0 | 7.2 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7043, 7170, 7171, 7770 | Y | N |  |  | 78331 | 61234
71982 | Upgrade Orange Grove station | Upgrade Orange Grove stationto ring bus |  | Orange Grove | Orange Grove | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-04-01 | 2025-04-01 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 71983 | 71982
79990 | Add new Yellow Wolf station for 21INR0428 |  |  | Limestone | Gibbons Creek | Under Construction |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2025-04-08 | 2025-04-23 | 345 | 0 | 0 | 0 |  | Leon |  | Tier 4 |  |  |  |  | 967, 46020, 79007 | Y | N |  |  | 79991 | 79990
4323 | CPSE_Brooks_MLSE | Upgrade terminal at Brooks and ensure a rating of 2000 A (minimum) at both Braunig and Brooks terminals |  | Braunig | Brooks | In-Service |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0669 | 2025-04-10 | 2025-04-10 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5394 | Y | Y |  |  | 11875 | 4323
72576A | Lago Vista to Nameless Transmission Line Upgrade | Rebuild and upgrade Nameless to Lago Vista with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA). Final span of conductor and terminal equipment at Nameless will be upgraded to 440 MVA with ERCOT project #72576B. (Replaces ERCOT Project # 61277A) | 1/10/2023: Added information to clarify timing for final circuit rating upgrade. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2025-04-15 | 2025-04-01 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70352, 70526 | Y | N |  |  | 72577 | 72576
70922 | Chief Brady - Georgetown Transmission Line Upgrade | LCRA TSC will upgrade T355 Chief Brady - Georgetown 138-kV transmission line to achieve a higher operational rating. |  | Chief Brady | Georgetown | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-04-18 | 2025-04-18 | 138 | 0 | 3 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7343, 7366 | Y | N |  |  | 70923 | 70922 | 2023-SC17
71956 | Elgin Switch Substation Upgrade | LCRATSC will install a new three-breaker ring bus substation at Elgin Switch. Oncor will relocate its facilities from Elgin Switch to Brushy Creek. Install a temporary shoo-fly between T668 and T260 to maintain through-path during construction. |  | Elgin Switch |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-04-24 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 3541, 3650, 7321, 7324, 7338 | Y | N |  |  | 73564 | 71956
89905 | Addition of facilities installed at OCI ALAMO 1 substation to install a Gen-Tie to Power Soportar Battery Energy Storage System (BESS). |  |  | 5007 | 171082 | Planned | S-1023, T-0363 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-01 | 2025-05-07 | 138 | 0.06 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5007, 171082 | Y |  |  |  | 89906 | 89905
69345 | Limmer Substation Addition | Construct a new LCRA TSC-owned Limmer Substation in the Hutto to Zorn 345 kV line approximately 3 miles east of Hutto. Limmer Substation will be installed initially as a five-breaker 345 kV breaker-and-a-half arrangement. |  | Zorn, Hutto | Limmer | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-01 | 2025-05-01 | 345 | 0 | 0 | 0 |  | Williamson | Travis | Tier 3 | 22RPG027 | 2022-08-29 | 2022-09-27 |  | 3696, 7042, 7340, 7341 | Y | Y |  |  | 78338 | 69345
80753 | LST_Claytonville to Camp Springs 138 kV line additions | LST_Claytonville to Camp Springs 138 kV line additions |  | Claytonville 138 |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-05-01 | 2025-03-31 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68009, 68012 | Y |  |  |  | 80754 | 80753
71930 | Upgrade RIOHONDO to BURNS line | Upgrade RIOHONDO to BURNS line to be 478MVA capable |  | Rio Hondo | Burns | Under Construction | 7192671928 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-05-01 | 2025-07-01 | 138 | 0 | 12.2 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5763, 8319 | Y |  |  |  | 71931 | 71930
72588A | Trading Post to Cedar Valley Storm Hardening |  |  | Trading Post | Cedar Valley | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2025-05-05 | 2025-05-01 | 138 | 0 | 6.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70505, 70506 | Y | N |  |  | 72589 | 72588
67992D | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade | Upgrade Hamilton to Medical Center 138KV Line to 469MVA |  | 5187 | 5300 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-09 | 2025-04-16 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5187, 5300 | Y |  |  |  | 67994 | 67992
75889 | Add_Wellborn_Load |  |  | Wellborn |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-05-14 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32895 | Y |  |  |  | 89951 | 75889
89984 | Kangaroo 345 kV Switch | Establish Kangaroo 345 kV Switch |  | Blackwater Draw Switch | Ogallala | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3030 | 2025-05-14 | 2025-06-12 | 345 | 0 | 0 | 0 |  | Castro | Castro | Tier 4 |  |  |  |  | 23912, 23915, 23920, 144842 | Y |  |  |  | 89985 | 89984
69552B | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 345 kV Switch, Autotransformers, and 345 kV Tie Lines to Limmer (LCRA) |  | Teal | Teal | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6165 | 2025-05-15 | 2025-05-30 | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 3696, 7341, 13363, 13364, 25090 | Y |  |  |  | 88554 | 69552
78371 | Richardson East Switch – Richardson Spring Creek 138 kV Line Section | Upgrade Richardson East Switch – Richardson Spring Creek 138 kV Line Section |  | Richardson East | Richardson Spring Creek | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4402 | 2025-05-15 | 2025-05-21 | 138 | 0 | 2.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2689, 2690 | Y |  |  |  | 78372 | 78371
82808 | Stranger 345 kV Switch | Establish Stranger 345 kV Switch |  | Stranger Switch | Stranger Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6320 | 2025-05-15 | 2025-05-15 | 345 | 0 | 0 | 0 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 3390, 3711, 3721, 154063 | Y |  |  |  | 82809 | 82808
81358A | Grindstone 138 kV Switch |  |  | Grindstone Switch | Grindstone Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1754 | 2025-05-15 | 2025-05-15 | 138 | 0 | 0 | 0 |  | Palo Pinto | Palo Pinto | Tier 4 |  |  |  |  | 1569, 1571, 1575, 1592, 1599, 154402 | Y |  |  |  | 81359 | 81358
87760 | Full House 138 kV Switch | Establish Full House 138 kV Switch for Lucky Bluff BESS |  | Full House | Full House | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6327 | 2025-05-15 | 2025-05-08 | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 1636, 1641, 1652, 153852 | Y |  |  |  | 87761 | 87760
78365 | Fryers Creek 138/69 kV Switch | Construct the new Fryers Creek 138/69 kV Switch |  | Boggy Creek | Boggy Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6295 | 2025-05-15 | 2958101 | 138 | 5 | 0 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 132, 3415, 3493, 3496, 3607, 3643, 3644, 3645, 3689, 3726 | Y |  |  |  | 81558 | 78365
71199 | Yucca Drive - Moss 138 kV Line | Rebuild existing 138 kV line |  | Yucca Drive | Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9047 | 2025-05-15 | 2025-05-30 | 138 | 0 | 35.2 | 0 |  | Ector | Winkler | Tier 4 |  |  |  |  | 1009, 1019, 11015, 11128, 18663 | Y |  |  |  | 76384 | 71199
66569 | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch |  | Mulberry Creek | Mulberry Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9022 | 2025-05-15 | 2025-05-15 | 345 | 0 | 0 | 0 |  | Jones | Jones | Tier 3 | 21RPG021 | 2021-12-17 | 2022-01-12 |  | 1435, 1459, 6235, 11420 | Y |  |  |  | 81422 | 66569
72007 | Ranger Camp 345/138/69 kV Switch | Construct a new 345/138/69 kV Switch to replace existing Morgan Creek Switch |  | Ranger Camp 345/138 kV Switch | Ranger Camp 345/138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3024 | 2025-05-15 | 2025-04-16 | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1025, 1030, 1032, 1033, 1064, 1189, 1190, 1348, 1378, 10049, 10050, 10051, 10052, 10134, 11004, 11035, 11332, 11342, 11393 | Y |  |  |  | 81363 | 72007
89982 | Wrangler 345 kV Switch | Establish 345 Switch |  | Cottonwood | White River | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3032 | 2025-05-15 | 2025-05-16 | 345 | 0 | 0 | 0 |  | Motley | Motley | Tier 4 |  |  |  |  | 23919, 23922, 59904 | Y |  |  |  | 89983 | 89982
52247 | Marrs - Handley 69 kV Line Conversion to 138 kV | Convert the existing Marrs-Handley 69 kV line to 138 kV operation |  | Marrs SW | Handley | Under Construction |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5222 | 2025-05-15 | 2025-05-30 | 138 | 2.2 | 13 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1951, 1952, 1967, 1968, 1969, 2158, 2159, 2160, 2162, 11950, 11951, 11952, 11967 | Y |  |  |  | 86795 | 52247
82806 | Establish Long Hollow 345 kV Switch (POI for Pinnington Solar) | Establish Long Hollow 345 kV Switch (POI for Pinnington Solar) |  | Graham Plant Switch | Parker Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3509 | 2025-05-15 | 2025-06-30 | 345 | 0 | 0 | 0 |  | Young | Parker | Tier 4 |  |  |  |  | 1430, 1436, 1506 | Y |  |  |  | 82807 | 82806
71980 | Watermill 345 kV Switch | Rebuild the existing Watermill 345 kV Switch |  | Watermill |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4012 | 2025-05-15 | 2958101 | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 |  |  |  |  | 2398, 2427, 2428, 2429, 2432, 2435, 2466, 2847, 2997, 3159, 12429 | Y |  |  |  | 76731 | 71980
72004 | Cat Claw 138 kV Dynamic Reactive Device (formerly Midkiff) | Install a new Dynamic Reactive Device at Cat Claw (formerly Midkiff) |  | Cat Claw | Cat Claw | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8675 R8680 R8695 | 2025-05-15 | 2025-05-12 | 138 | 0 | 0 | 0 | -250250 | Upton | Upton | Tier 3 |  |  |  |  | 1210, 1217, 10058, 10059, 10060, 11218, 11345, 23870, 23871 | Y |  |  |  | 73345 | 72004
78382 | Adds Capacitor Bank at White Dune | Adds Capacitor Bank at White Dune |  | White Dune |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8669 | 2025-05-15 | 2025-06-30 | 138 | 0 | 0 | 0 | 0,110.4 | Winkler | Winkler | Tier 4 |  |  |  |  | 18692 | Y |  |  |  | 80906 | 78382
81383 | Edwards Tap - Sandhills Tap 138 kV Line Rebuild | Edwards Tap - Sandhills Tap 138 kV Line Rebuild |  | Odessa EHV | Wolf | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8528 | 2025-05-15 | 2025-07-24 | 138 | 0 | 11.71 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 1102, 1103, 1110 | Y |  |  |  | 81384 | 81383
87285 | Establish Stouts Creek 345 kV Switch | Establish Stouts Creek 345 kV Switch |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R984 | 2025-05-15 | 2025-06-13 | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1696, 2514, 12464, 120976 | Y |  |  |  | 87286 | 87285
76578 | Upgrade the Temple Pecan - Temple Elm 138 kV Double-Circuit Line | Upgrade the 5-mile Temple Pecan - Temple Elm 138 kV Double-Circuit Line |  | Temple Pecan Creek | Temple Elm Creek | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6234 | 2025-05-15 | 2025-06-05 | 138 | 0 | 10 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3420, 13662 | Y |  |  |  | 76579 | 76578 | 2023-NC61
70704B | Florence Substation Addition | Fixes Florence bus disconnection issue by removing temporary equipment associated with FLORENCE substation cut-in |  |  |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6320 | 2025-05-15 | 2025-05-15 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7521, 7523, 70522 | Y |  |  |  | 90388 | 70704
70704A | Florence Substation Addition |  |  | Andice | Glasscock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6320 | 2025-05-15 | 2025-05-15 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7521, 7523, 70522 | Y | N |  |  | 70705 | 70704
77041 | Leon Switch - Putnam Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 8.9-mile Leon Switch – Putnam (T727) 138-kV transmission line between Leon Switch existing structure #1/1 and Putnam existing structure #9/10. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Leon Switch | Putnam | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-05-21 | 138 | 0 | 8.95 | 0 |  | Eastland | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | Y |  |  | 77042 | 77041
85959 | San Marcos - Strahan Transmission Line Upgrade | LCRA TSC will upgrade T230 San Marcos - Strahan 138-kV transmission line to achieve a higher operational rating. |  | San Marcos (7192) | Strahan (7193) | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-04-30 | 138 | 0 | 1.25 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7192, 7193 | Y |  |  |  | 85960 | 85959
73793 | McCarty Lane - Zorn Transmission Line Storm Hardening | Perform storm hardening on the 4.2 mile McCarty Lane - Zorn (T202) 138-kV transmission line. T202 is double-circuited with McCarty Lane - Beback - Zorn (T201) 138-kV transmission line. |  | McCarty Lane East | Zorn | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-05-01 | 138 | 0 | 8.58 | 0 |  | Hays | Guadalupe | Tier 4 |  |  |  |  | 7180, 7182, 7187 | Y | N |  |  | 73794 | 73793
73838 | Redwood - San Marcos Transmission Line Upgrade | LCRA TSC will upgrade T200 Redwood - San Marcos 138-kV transmission line to obtain a higher operational rating. |  | Redwood | San Marcos | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-05-13 | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7188, 7192 | Y | N |  |  | 73839 | 73838
72870 | Soda Lake Generator Circuit Breaker Addition | This project provides a point of interconnection for a new 202.99 MW Solar Energy at the 138-kV Soda Lake Substation by reconfiguring the Soda Lake Substation to breaker-and-a-half to add new 138-kV line terminal and one POI structure to accommodate the new interconnection. Update contingencies |  | Soda Lake |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-06-09 | 138 | 0 | 0 | 0 |  | Crane |  | Tier 4 | [5 empty] | Y | N |  |  | 78298 | 72870
70538 | Pilot Grove - Yoakum Gartner Road Transmission Line Overhaul | Perform an overhaul on the 7.8 mile T614 Pilot Grove (structure #8/2) - Yoakum Gartner Road 138-kV transmission line. Structure #8/2 and the remaining portion of T614 will be overhauled as part of the FY23 Mont - Pilot Grove Transmission Line Overhaul project. |  | Pilot Grove | Yoakum Gartner | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-05-15 | 138 | 0 | 0 | 0 |  | Lavaca | DeWitt | Tier 4 |  |  |  |  | 7234, 7242 | Y | N |  |  | 70539 | 70538
91455 | Establish Dorsett 345 kV Switch |  |  | Dorsett 345 kV Switch | Dorsett 345 kV Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6323 | 2025-05-15 | 2025-05-08 | 345 | 0 | 0 | 0 |  | Rusk | Rusk | Tier 4 |  |  |  |  | 3100, 3105, 3339, 121043 | Y |  |  |  | 91529 | 91455
82810A | Olympus 138 kV Switch | Establish Olympus 138 kV Switch |  | Olympus Switch | Olympus Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6330 | 2025-05-15 | 2025-05-08 | 138 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3125, 3127, 3454, 3466, 3723 | Y |  |  |  | 82811 | 82810
62666A | Upgrade and convert McGregor - Waco West Line | Rebuild and Upgrade McGregor Phillips - Waco West Switch 69 kV Line |  | Waco West | McGregor Phillips | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6172 | 2025-05-15 | 2025-12-15 | 69 | 0 | 17.5 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3370, 3437, 3584 | Y |  |  |  | 93105 | 62666
91060 | Establish Flying Tiger 138 kV Switch | Establish Flying Tiger 138 kV Switch |  | Flying Tiger 138 kV Switch |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3302 | 2025-05-15 | 2025-04-17 | 138 | 0 | 0 | 0 |  | Lamar | Lamar | Tier 4 |  |  |  |  | 1693, 1700, 2163 | Y |  |  |  | 91061 | 91060
62068 | Lakeway - Marble Falls Transmission Line Storm Hardening | Increase the reliability of transmission facilities on the T497 Lakeway - Marble Falls 23-mile 138-kV transmission line. |  | Lakeway | Marble Falls | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-16 | 2025-05-16 | 138 | 0 | 0 | 0 |  | Travis | Burnet | Tier 4 | 22RPG031 | 2022-10-12 | 2022-11-03 |  | 7348, 7349, 7351, 7356, 7474, 7476, 7538, 7540 | Y | N | 22RPG031 reclassified as Tier 4 neutral by RPG review on 11/03/2022 |  | 62069 | 62068
66447 | Reforzar: Construct New 345 kV Station | Construct a new 345 kV station on the Lon Hill to North Edinburg 345 kV line | IN-SERVICE | Reforzar |  | Under Construction |  | AEP TCC | Chase Isaac jlsolis@aep.com 361-881-5574 | TP2022035 | 2025-05-16 | 2025-05-16 | 345 | 0 | 0 | 0 |  | Brooks |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8455, 8905, 80078 | Y |  |  |  | 67317 | 66447
75887 | Add_SteepHollow_Load |  |  | Steep Hollow |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-05-19 | 2025-05-19 | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 | [5 empty] | Y |  |  |  | 91905 | 75887
88063 | Valley South 345 kV Switch New POI (Platinum Storage) | Install new POI |  | Valley South |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3069 | 2025-05-22 | 2025-05-22 | 345 | 0 | 0 | 0 |  | Fannin |  | Tier 4 | [5 empty] | Y |  |  |  | 88064 | 88063
67992A | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade | Shepherd Rd to Valley Rd 138kV line Reconfiguration. |  | 5378, 5465 | 5320 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-29 | 2025-04-07 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5230, 5378, 5465 | Y |  |  |  | 72403 | 67992
67992C | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade | Looping of 345KV Howard Rd switching station into existing Cagnon to AVR and Cagnon to Spruce 34KV lies. The switching station will have 2 600MVA 345KV/138KV autotransformers. |  | 5056 | 5400 and 5475 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-29 | 2025-04-07 | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5056, 5230, 5231, 5400, 5475 | Y |  |  |  | 67993 | 67992
78485A | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Westchase to Hayes to Britmoore to increase thermal limits. Upgrade Ckt.24 Bellaire equipment and relay limits. |  | Westchase | Britmoore | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-30 | 2025-02-07 | 138 | 0 | 6.21 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 48159, 48420 | Y | N |  |  | 90166 | 78485
6719A | Twelvemile Substation Addition | Cuts into first circuit |  | Bakersfield | Schneeman Draw | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018769 | 2025-05-30 | 2025-06-17 | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  |  | 7053, 76008, 76015 | Y | N |  |  | 58408 | 6719
6719B | Twelvemile Substation Addition | Cuts into the second circuit |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018769 | 2025-05-30 | 2025-06-17 | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  |  | 7053, 76008, 76015 | Y |  |  |  | 90722 | 6719
66221L | Galena Park Area Conversion Project | De-energize Ckt.20 Greens Bayou to GYPSUM. |  | Greens Bayou | GYPSUM | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 | 2025-04-11 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40619, 40725, 40751, 48131 | Y | N |  |  | 98425 | 66221
78485E | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Westchase to Hayes to Britmoore to increase thermal limits. Upgrade Ckt.24 Bellaire equipment and relay limits. |  | Westchase | Britmoore | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 | 2025-06-03 | 138 | 1.2 | 6.21 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 44120, 48159 | Y | N |  |  | 90170 | 78485
69902A | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. Loop Ckt.18E into Mission substation to create new Ckt.18 Gibbons Creek to Mission to Zenith. (Ckt.18 Gibbons Creek to Mission tie-line). |  | MISSION | Zenith | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 | 2025-05-07 | 345 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  |  | 967, 44900, 44920 | Y | N |  |  | 98392 | 69902
69902C | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | Install generator lead from Mission (MSS) substation to Parliament/Parliament Solar |  | MISSION | Parliament | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:01 | 2025-05-07 | 345 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  |  | 44920, 113925 | Y | N |  |  | 98393 | 69902
73578C | Heights 138kV Loop Conversion | Convert Eureka to double-tap service. Tap Ckt.81J to create new Ckt.81J White Oak to Eureka TR1 tap to Wirt. |  | Wirt | White Oak | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:02 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44656, 45750, 45751, 46615 | Y | N |  |  | 90928 | 73578
73578K | Heights 138kV Loop Conversion | Convert Eureka to double-tap service. Tap Ckt.09D to create new Ckt.09D San Felipe to Eureka TR2/TR3 tap to White Oak. Reconductor Ckt.09D Eureka TR2/TR3 tap to White Oak to increase thermal limits. Upgrade San Felipe line relaying Ckt.09D San Felipe to White Oak. |  | San Felipe | White Oak | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:02 | 2025-05-14 | 138 | 0 | 1.57 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45750, 45752, 46615, 47382, 47685 | Y | N |  |  | 90929 | 73578
73578J | Heights 138kV Loop Conversion | Reconfigure Ckt.40A Dunlavy to HO Clarke with a temporary (BP25 to BP26) configuration. Remove the Dunlavy TR3 tap section from Ckt.40A and install tap section to Ckt.90A. |  | Dunlavy | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:04 | 2025-05-08 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47160, 47850 | Y | N |  |  | 90927 | 73578
73578G | Heights 138kV Loop Conversion | Tap existing Ckt.90A Kirby to Garrott near Tower 34720 to serve Dunlavy transformer TR3 load. Create Ckt.90A Kirby tap to DN-TR3 tap to Garrott. |  | Kirby | Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:05 | 2025-05-08 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47580, 47593, 47660, 48363 | Y | N |  |  | 90930 | 73578
11TPIT0011 | East_Village138kV Substation | East_Village 138kV Substation |  | Techridge | East_Village SUB | In-Service |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-06-01 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9045, 9190, 9195 | Y |  |  |  | 13043 | 5357
70349 | Belknap to Fort Griffin: Rebuild 69 kV Line | Rehab Belknap to Fort Griffin 69 kV line | IN-SERVICE | Belknap | Fort Griffin | In-Service |  | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 |  | 2025-06-11 | 2025-06-11 | 69 | 0 | 23.6 | 0 |  | Jones | Shackelford | Tier 4 | 22RPG020 | 2022-06-27 | 2022-07-22 |  | 6178, 6210, 6214, 60398, 60409, 60445, 60466, 60471 | Y | N |  |  | 70350 | 70349
90353 | Establish Sandy Ranch 345 kV Switch | Establish Sandy Ranch 345 kV Switch |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3125 | 2025-06-20 | 2025-06-06 | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1697, 2464, 2621, 121022 | Y |  |  |  | 90354 | 90353
72880 | Sisseton: Build 69 kV station | Build 69 kV switch station on the Aspermont to Hamlin 69 kV line | IN-SERVICE | Sisseton |  | In-Service |  | AEP TNC | Charles Burks twang1@aep.com 918-599-2635 | TP2022059 | 2025-06-25 | 2025-05-14 | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6073, 6156, 6184, 6185, 6186, 6187, 60068 | Y |  |  |  | 72881 | 72880
49574 | Tesla: Build 345 kV terminal | Interconnect Misae II solar farm at Tesla | IN-SERVICE | Tesla |  | In-Service | 1023 - 1201 | ETT | Raza Ansari twang1@aep.com 918-599-2635 | 2785 | 2025-06-25 | 2025-06-17 | 345 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501, 143964 | Y | N |  |  | 49575 | 49574
76574 | TexasAg Wind Interconnection | Interconnect TexasAg to the Brisita 345 kV station | IN-SERVICE | Brisita |  | In-Service |  | ETT | John Solis jlsolis@aep.com 361-881-5574 | TP2023129 | 2025-06-25 | 2025-05-14 | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8383, 8574, 8693, 88693 | Y |  |  |  | 76575 | 76574
67921 | Sisseton: Build 69 kV tap | Build new 69 kV tap on the Aspermont to Hamlin 69 kV line | IN-SERVICE | Sisseton |  | In-Service |  | AEP TNC | Charles Burks twang1@aep.com 918-599-2635 |  | 2025-06-25 | 2025-05-14 | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6073, 6156, 6184, 6185, 6186, 6187, 60068 | Y |  |  |  | 67922 | 67921
63924 | Quasar: Build New 345 kV Station | Interconnect Brass Fork Solar to the Clear Crossing to Coulomb 345 kV Line | In-Service | Quasar |  | Planned | 1138 - 1316 | ETT | Zach Lachiusa twang1@aep.com 918-599-2635 | 1883 | 2025-06-25 | 2025-06-27 | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60514, 60703, 60712 | Y | N |  |  | 63925 | 63924
48816 | Mulberry Creek: Rebuild 345 kV station | Rebuild Mulberry Creek 345 kV station and replace both autotransformers | IN-SERVICE | Mulberry Creek |  | Under Construction | 1015 - 1193 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 | 2776 | 2025-06-25 01:00 | 2025-06-30 | 345 | 0 | 0 | 900 |  | Jones |  | Tier 4 | 21RPG021 | 2021-12-15 | 2022-01-13 |  | 1435, 1459, 6230, 6231, 6232, 6235, 11420, 60040, 60104, 60105, 60788, 60789 | Y | N |  |  | 65536 | 48816
45155 | Ollin: Build 138 kV station | Construct new Ollin 138 kV station | IN-SERVICE | Ollin |  | In-Service | 939 - 1117 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 2752 | 2025-06-26 01:00 | 2025-06-26 | 138 | 0.1 | 0 | 0 |  | Crane |  | Tier 4 | 19RPG013 |  |  |  | 6600, 6604, 6605, 6606, 6607, 6610, 6611, 6613, 6668, 6669, 60428, 60429, 60431, 60432, 60441, 76615 | Y | N |  |  | 45156 | 45155
70019 | Add 138kV Locust-Hickory line 700MVA |  |  | Locust | Hickory | Planned |  | DME | Mark Zimmerer 940-349-7169 |  | 2025-06-30 | 2025-06-30 | 138 | 0 | 1.85 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 922, 924 | Y | N |  |  | 70020 | 70019 | N/A
86043 | Saxet Substation Addition Phase 2 | This PMCR models the phase 2 cut-in of T437 Nueces Bay – Lon Hill with the second Saxet Hard Tap. LCRA TSC will add a temporary Tap on T437 |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-06-30 | 2025-06-06 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8441, 8452, 78568 | Y |  |  |  | 86044 | 86043
5430K | Conversion to 138kV | Construct new 138kV Hickory substation and terminate the existing Bonnie Brae - Hickory (which is already insulated for 138kV) at the new 138kV Hickory substation. |  | Bonnie Brae | Hickory | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2025-07-01 | 2025-07-01 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 931 | Y | N | N/A |  | 55205 | 5430 | N/A
64776 | Upgrade 138kV DentonWest-RDWells line to 700MVA (SUM2024) |  |  | RD Wells | Denton West | Planned |  | DME | Mark Zimmerer 940-349-7169 |  | 2025-07-01 | 2025-07-01 | 138 | 0 | 4.47 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 930, 986 | Y | N |  |  | 64777 | 64776 | N/A
5430O | Conversion to 138kV | Reconnect the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2025-07-01 | 2025-07-01 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 930 | Y | N | N/A |  | 55209 | 5430 | N/A
77648B | Establish Tiger Creek 345 kV Switch for Jaguar Solar/BESS | Tiger Creek Switch - Jaguar Solar/BESS 345 kV Line |  | Tiger Creek Switch | Jaguar Solar/BESS | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6223 | 2025-07-14 | 2025-10-16 | 345 | 0.5 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 3379, 153783 | Y |  |  |  | 87809 | 77648
13TPIT0070 | Nash Creek Substation | Rebuild existing substation, and replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2025-07-30 | 2025-07-30 | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7596 | Y | N |  |  | 78324 | 3322
72882 | Lockhart - Luling 69-kV Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 15.8-mile Lockhart – Luling (T157) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Lockhart | Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-07-30 | 2025-06-27 | 69 | 0 | 15.83 | 0 |  | Caldwell | Caldwell | Tier 4 | 23RPG004 | 2023-02-24 | 2023-03-20 |  | 7215, 7218, 7220, 7223 | Y | N |  |  | 72883 | 72882
87389 | Friendswood Energy GENCO GT (24INR0456) | Friendswood Energy GENCO GT at HO Clarke substation. Utilize existing HO Clarke to Friendswood Energy generator lead. |  | HO Clarke |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 | 2025-07-25 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47170, 111183 | Y | N |  |  | 87390 | 87389
64069 | Charger Solar Interconnection | Connect the Charger Interconnection to the Angstrom to STP 345 kV line | IN-SERVICE | Angstrom | STP | In-Service |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2021165 | 2025-07-31 | 2025-07-08 | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 5915, 8249, 8676, 8678 | Y |  |  |  | 64070 | 64069
77827 | Reconductor TNMP Cottonwood to Oncor Lean Clay |  |  | Oncor Lean Clay (11078) | TNMP Cottonwood (38099) | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-08-15 | 2025-02-21 | 138 | 0 | 0.33 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 11078, 38099, 38100 | Y |  |  |  | 87863 | 77827
76076 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild Las Cruces to Milo 138 kV line | IN-SERVICE | Las Cruces | Milo | In-Service | 1116 - 1294 | AEP TCC/ETT | William Lovelace jlsolis@aep.com 361-881-5574 | TP2020072 3835 | 2025-08-15 | 2025-08-15 | 138 | 0 | 2.4 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8112, 8918 | Y |  |  |  | 76077 | 76076
72876B | Provide 138 kV POD for Skybox at Teal Switch |  |  | Teal | Skybox | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6259 | 2025-08-19 | 2958101 | 138 | 0.2 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3362, 3371 | Y |  |  |  | 99290 | 72876
69552C | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 345 kV Switch, Autotransformers, and 345 kV Tie Lines to Limmer (LCRA) |  | Teal | Teal | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6165 | 2025-08-20 | 2025-05-30 | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 3696, 7341, 13363, 13364, 25090 | Y |  |  |  | 99403 | 69552
87846 | Bradberry 138 kV Switch | Bradberry 138 kV Switch |  | Bradberry |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4015 | 2025-08-30 | 2958101 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 3064, 3065, 3066 | Y |  |  |  | 87847 | 87846
78485B | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.09A Britmoore to Hayes to Alief to increase thermal limits. |  | Britmoore | Alief | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-08-30 | 2025-06-03 | 138 | 0 | 2 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 44020, 44120, 44310 | Y | N |  |  | 98948 | 78485
75835A | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Partial reconductor Ckt.66B Stone Lake to Tomball. Phase One of overall approved upgrades |  | Stone Lake | Tomball | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-08-30 | 2025-07-29 | 138 | 0 | 5.71 | 0 |  | Harris | Harris | Tier 3 | 23RPG012 | 2023-05-04 | 2023-05-26 | 2023-05-26 | 44840, 46510, 48348 | Y | N |  |  | 98429 | 75835
6253 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | In-Service |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-09-04 | 2025-09-04 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238, 9276 | Y |  |  |  | 13981 | 6253
66202A | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Palestine - Elkhart 69 kV Line |  | Palestine | Elkhart | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6182 | 2025-09-15 | 2025-08-06 | 69 | 0 | 9.8 | 0 |  | Anderson | Anderson | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3273, 3285 | Y |  |  |  | 66203 | 66202
66210 | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV. Relocate the Lake Creek 138/69 kV Auto to Marlin. |  | Lake Creek | Marlin | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1743 | 2025-09-15 | 2025-12-01 | 138 | 0 | 13.7 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3410, 3411, 3416, 3418, 3694, 13401, 13639 | Y |  |  |  | 66211 | 66210
90786 | Establish Yarrelton 345 kV Switch | Establish Yarrelton 345 kV Switch for Hermes Solar and Storage |  | Yarrelton | Yarrelton | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6261 | 2025-09-29 | 2025-12-17 | 345 | 0 | 0 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3687, 3762, 3766, 154643 | Y |  |  |  | 90787 | 90786
76234 | Wormser Road: Construct New 138 kV Terminal | Interconnect Seven Flags BESS to the Wormser Road 138 kV station | IN-SERVICE | Wormser Road |  | Under Construction |  | AEP TCC | William Lovelace jlsolis@aep.com 361-881-5574 | TP2023311 | 2025-09-30 | 2025-09-15 | 138 |  |  |  |  | Webb |  | Tier 4 |  |  |  |  | 8295 | Y |  |  |  | 76235 | 76234
50878 | North Edinburg: 345 kV Reconfigure | Reconfigure the North Edinburg 345 kV station | In-Service | North Edinburg |  | In-Service | 1056 - 1229 | AEP TCC | Curtis Brown jlsolis@aep.com 361-881-5574 | 3786 | 2025-09-30 | 2025-11-24 | 345 | 0 | 0 | 0 | -100,0 | Hidalgo |  | Tier 4 |  |  |  |  | 8341, 8383 | Y | N |  |  | 50879 | 50878
76686 | Hog Mountain 138 kV POD | Add Hog Mountain 138 kV POD |  | Quartz Sand | Hog Mountain POD | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8673 R8791 | 2025-09-30 | 2025-12-30 | 138 | 5.4 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 1229, 18552 | Y |  |  |  | 76687 | 76686
76705 | Prairieland 345/138 kV Switch and 138 kV Line | Establish Prairieland 345/138 kV Switch and Prairieland – Quartz Sand 138 kV Line |  | Prairieland | Quartz Sand | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8632 | 2025-09-30 | 2025-12-16 | 345 | 6 | 0 | 0 |  | Glasscock | Glasscock | Tier 2 |  |  |  |  | 1030, 1058, 1229, 11387, 18548, 18549, 18550, 18551, 18552 | Y |  |  |  | 91943 | 76705
50847 | Sage: Expand 69 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | IN-SERVICE | Sage |  | In-Service | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2799 | 2025-10-06 | 2025-10-06 | 69 | 0 | 0 | 0 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-06-21 |  | 6604 | Y | N |  |  | 50848 | 50847
81358B | Grindstone 138 kV Switch |  |  | Grindstone | Black Springs BESS | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1754 | 2025-10-15 | 2025-10-10 | 138 | 0 | 0 | 0 |  | Palo Pinto | Palo Pinto | Tier 4 |  |  |  |  | 1569, 154402 | Y |  |  |  | 98712 | 81358
78414 | SW3379 Replacement | Replacing existing 1200 Amp switch and 1800 Amp bypass jumper with new 3000 Amp switch. |  |  |  | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2025-10-26 | 2025-09-15 | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 | [5 empty] | Y |  |  |  | 78417 | 78414
78490A | Jeanetta Auto Upgrades | Replace existing 600 MVA Jeanetta Auto A1 with 800 MVA autotransformer |  | Jeanetta |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 | 2025-05-19 | 345 | 0 | 0 | 200 |  | Harris |  | Tier 3 | 23RPG031 | 2023-10-04 | 2023-10-26 |  | 47300, 47310, 49024 | Y | N |  |  | 79425 | 78490
78490B | Jeanetta Auto Upgrades | Replace existing 600 MVA Jeanetta Auto A3 with 800 MVA autotransformer |  | Jeanetta |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 | 2025-03-23 | 345 | 0 | 0 | 200 |  | Harris |  | Tier 3 | 23RPG031 | 2023-10-04 | 2023-10-26 |  | 47300, 47310, 49082 | Y | N |  |  | 79426 | 78490
75938 | Expand Zenith substation with addition of 35kV Distribution Facilities. Tap TR1 on Ckt.09J to create new Ckt.09J Zenith to Zenith TR1 tap to Fry Road tap. Tap TR2 on Ckt.76A to create new Ckt.76A Zenith to Zenith TR2 tap to Fry Road tap. | Expand Zenith substation with addition of 35kV Distribution Facilities. Tap TR1 on Ckt.09J to create new Ckt.09J Zenith to Zenith TR1 tap to Fry Road tap. Tap TR2 on Ckt.76A to create new Ckt.76A Zenith to Zenith TR2 tap to Fry Road tap. |  | Zenith | Fry Road | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 | 2025-03-05 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44910 | Y | N |  |  | 75939 | 75938
76274 | Hamilton Road: Construct New 138 kV Terminal | Interconnect Tierra Seca BESS to the Hamilton Road 138 kV station | In-Service | Hamilton Road |  | In-Service |  | AEP TCC/ETT | Robert Dougherty jlsolis@aep.com 361-881-5574 | TP2023133 | 2025-10-31 | 2025-10-29 | 138 | 0.1 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  |  | 8255, 8684, 8687, 8688, 8690 | Y |  |  |  | 76275 | 76274
80486 | Loxley: Construct New 138 kV Station | Interconnect the Loxley load to the new Loxley 138 kV station on the Pleasanton to Trumbo 138 kV line | IN-SERVICE | Loxley |  | Planned |  | AEP TCC | Bill Edwards jlsolis@aep.com 361-881-5574 |  | 2025-10-31 | 2025-12-18 | 138 | 0.1 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  |  | 5429, 8203, 80491 | Y |  |  |  | 80487 | 80486
72065 | Lake Jackson Distribution Substation Conversion to Low-Profile | Rebuild Lake Jackson 138/12kV distribution substation to low-profile |  | Lake Jackson |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 | 2025-09-24 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42880, 43172 | Y | N |  |  | 72066 | 72065
76624 | WA Parish 345kV Substation Expansion for Crowned Heron Storage (24INR0405) | Expand 345kV WA Parish substation for Crowned Heron Storage (24INR0405) |  | WA Parish | HERON | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:01 | 2025-12-16 | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 44000, 114042 | Y | N |  |  | 93236 | 76624
77122 | Mulberry Creek: Construct New 345 kV Terminal | Interconnect the Lancium load to the Mulberry Creek 345 kV station | IN-SERVICE | Mulberry Creek |  | Planned | TP2023636 | AEP TNC | Forrest Farson myturner@aep.com 918-599-2437 |  | 2025-11-30 | 2025-12-31 | 345 | 2.25 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6235 | Y | N |  |  | 77123 | 77122
66221K | Galena Park Area Conversion Project | Rebuild GYPSUM customer substation for 138kV loop-tap service. Tap new GYPSUM substation (Spear Stone) from Ckt.94 between TANKER and new Galena Park tap to create new Ckt.94M CITFIL to Normandy tap to Galena Park tap to Spear Stone to TANKER |  | CITFIL | Tanker | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 | 2025-11-07 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40590, 40612, 40630, 40731, 40739, 41172, 48130, 48261, 48402, 48613 | Y | N |  |  | 98664 | 66221
78480A | Weinbrenner (WEI) 138kV CEHE Station for LONGPO (LNP) / Long Point Solar 19INR0042 | Loop new CEHE 138kV substation Weinbrenner (WEI) into Ckt.02J Burke to Eagle Nest to create new Ckt.02 Burke to Weinbrenner to Eagle Nest. |  | Weinbrenner | Burke/ Eagle Nest | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 | 2025-12-10 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42410, 42430, 42990 | Y | N |  |  | 100090 | 78480
78480B | Weinbrenner (WEI) 138kV CEHE Station for LONGPO (LNP) / Long Point Solar 19INR0042 | Install one generator lead from CEHE 138kV substation Weinbrenner (WEI) to LONGPO (LNP) / Long Point Solar (19INR0042) |  | Weinbrenner | LONGPO | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 00:01 | 2025-12-10 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42990, 114583 | Y | N |  |  | 100091 | 78480
78471 | WA Parish 345kV Substation Expansion for Bypass Storage (23INR0336) | Expand 345kV WA Parish substation for Bypass Storage (23INR0336) |  | WA Parish | BYPASS | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 00:01 | 2025-10-30 | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 44000, 113803 | Y | N |  |  | 93237 | 78471
66221M | Galena Park Area Conversion Project | Reconfigure Galena Park by removing the temporary Ckt.94M Galena Park loop. Tap Galena Park transformer on Ckt.21K between Fidelity and Witter. |  | Fidelity | Witter | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 00:06 | 2025-11-07 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40590, 40611, 40612, 40619, 40630, 40751, 48402, 48610 | Y | N |  | Cost included in main entry | 98665 | 66221
70886 | Rebuild TinTop - Rio Colorado | Rebuild TinTop- Rio Colorado 795ACSR |  | Tin Top | Rio Colorado | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 | 2025-07-03 | 69 | 0 | 15.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5563, 5569 | Y |  |  |  | 70887 | 70886
92600B | John_Dumas_Circuit_Breaker_Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7999 | 2025-12-01 | 2025-12-22 | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7041, 7042, 7341 | Y |  |  |  | 100070 | 92600
92600A | John_Dumas_Circuit_Breaker_Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7999 | 2025-12-01 | 2025-12-22 | 345 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7041, 7042 | Y |  |  |  | 92601 | 92600
71937 | Caterpillar Substation | Add T6, 40 MVA. 138-26.08 kV PWT to Caterpillar Substation |  | Caterpillar |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-01 | 2026-01-12 | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 | [5 empty] | Y | N |  |  | 71938 | 71937
86633 | Dusty Road 345 kV Switch | Establish Dusty Road 345 kV Switch |  | Tonkawa | Graham | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8809 | 2025-12-04 | 2025-12-04 | 345 | 0 | 0 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  |  | 1048, 1430, 11050, 144787 | Y |  |  |  | 86634 | 86633
80913 | Sloan 138 kV Switch. | Establish Sloan 138 kV Switch |  | Midessa South Switch | Odessa/Midland East Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8659 | 2025-12-04 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 1059, 1124, 1138, 11137, 11138, 11143, 11165 | Y |  |  |  | 90314 | 80913
81389 | Sandhills Tap - Wolf 138 kV Line Rebuild | Sandhills Tap - Wolf 138 kV Line Rebuild |  | Odessa EHV | Wolf | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8528 | 2025-12-15 | 2025-12-15 | 138 | 0 | 14.2 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 1013, 1103, 11018 | Y |  |  |  | 87113 | 81389
87830 | Blue Mountain 138 kV Capactior Bank | Add 138 kV Capacitor Bank at Blue Mountain Switch |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8799 | 2025-12-15 | 2025-11-15 | 138 | 0 | 0 | 0 | 0,110.4 | Loving | Loving | Tier 4 |  |  |  |  | 18680 | Y |  |  |  | 87831 | 87830
81060 | Riverton-Border-Quarry Field 138 kV Second Circuit | Add Permian Basin Reliability Plan Upgrade ID L1A and L1D Riverton-Border-Quarry Field 138 kV Second Circuit |  | Riverton | Quarry Field | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8733 | 2025-12-15 | 2025-12-01 | 138 | 29.7 | 0 | 0 |  | Reeves | Loving | Tier 4 |  |  |  |  | 11083, 11089 | Y |  |  |  | 98685 | 81060
100459 | Establish Token 138 kV POD |  |  | Token 138 kV |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3040 | 2025-12-15 | 2025-12-15 | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 968, 2181, 2477 | Y |  |  |  | 100460 | 100459
5475 | Lufkin Switch - Redland Switch 345 kV Line | Construct a new 345 kV Line from Lufkin Switch to Redland Switch |  | Lufkin Switch | Redland Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6077 | 2025-12-15 | 2025-12-15 | 345 | 8.1 | 0 | 0 |  | Angelina | Angelina | Tier 2 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3117, 3321 | Y | N |  |  | 13180 | 5475
62666B | Upgrade and convert McGregor - Waco West Line | McGregor Phillips - Waco West 138 kV Operation |  | McGregor Phillips | Waco West | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6172 | 2025-12-15 | 2025-12-31 | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3370, 3372, 3436, 3437, 3440, 3441, 3446, 3562, 3584, 3585, 3594, 3596, 3793, 13436, 13438 | Y |  |  |  | 93100 | 62666
66289B | Tyler to Athens 138 kV line Conversion | Establish Foggle Switch, Establish Poynor POI, Echols to Athens 69 kV Line Upgrade |  | Athens | Echols | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6094 | 2025-12-15 | 2025-12-15 | 69 | 0 | 0 | 0 |  | Henderson | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3108, 3126, 3233, 3238, 3239, 3248, 3256, 3269, 3270, 3288, 3801, 6805 | Y |  |  |  | 92110 | 66289
82810B | Olympus 138 kV Switch | Topology Correction: Add missing Olympus Switch - Kerens 138 kV Line Section |  | Olympus Switch | Kerens | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6330 | 2025-12-15 | 2025-05-08 | 138 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3125, 3466, 3723 | Y |  |  |  | 100595 | 82810
81175 | Salt Flat Road 138 kV Switch and Salt Flat Road - Barr Ranch - Reiter 138 kV Second Circuit | Add Salt Flat Road 138 kV Switch and Salt Flat Road - Barr Ranch - Reiter 138 kV Second Circuit & De-energize auto at Odessa EHV |  | Reiter | Salt Flat Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8704 | 2025-12-15 | 2025-12-15 | 138 | 44 | 4.4 | 0 |  | Ector | Midland | Tier 3 |  |  |  |  | 1027, 1028, 1111, 1123, 1193, 1234, 1276, 1277, 11111, 11217, 11235, 11344, 18528, 18545, 18701, 23859 | Y |  |  |  | 93103 | 81175
72958 | Graham to Graham Switch 69 kV Line Rebuild | Graham to Graham Switch 69 kV Line Rebuild |  | Graham | Graham | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3001 | 2025-12-15 | 2025-12-31 | 69 | 0 | 0 | 0 |  | Young | Young | Tier 4 |  |  |  |  | 1597, 1602 | Y |  |  |  | 72959 | 72958
72009 | Cattleman 345/138 kV Switch | Construct a new 345/138 kV Switch to replace existing Morgan Creek Switch |  | Cattleman | Cattleman | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8647 | 2025-12-15 | 2025-11-15 | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 1032, 1058, 10053, 10054, 10055, 10056, 11395, 18548 | Y |  |  |  | 81376 | 72009
90899 | Establish Woodbury 138 kV Switch | Establish Woodbury 138 kV Switch for Three W Solar |  | Woodbury | Woodbury | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6251 | 2025-12-15 | 2025-12-05 | 138 | 0 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 237, 3522, 3781, 155482 | Y |  |  |  | 90900 | 90899
62448 | Rebuild Marlin 69 kV Switch | Rebuild Marlin 69 kV Switch |  | Marlin | Marlin | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1752 | 2025-12-15 | 2025-12-01 | 69 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3418, 3638, 13639 | Y |  |  |  | 62658 | 62448
80546A | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Increase the maximum operating temperature of the Hutto - Round Rock 138 kV Line and rebuild the Round Rock Westinghouse Tap - Round Rock Westinghouse 138 kV Line Section |  | Hutto Switch | Round Rock Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2025-12-15 | 2026-01-06 | 138 | 0 | 8.8 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 3664, 3666, 3667, 3668, 3669, 3670 | Y |  |  |  | 81498 | 80546 | 2023-SC17
87758 | Badger 345 kV Switch | Establish Badger 345 kV Switch for Sypert Branch Solar |  | Badger | Badger | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6317 | 2025-12-15 | 2025-12-05 | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3687, 3761, 13429, 171165 | Y |  |  |  | 87759 | 87758
76135 | Hackberry Switch – DFW D-East 2 138 kV DCKT Line Section | Rebuild Hackberry Switch – DFW D-East 2 138 kV DCKT Line Section |  | Dallas | Dallas | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4347 M4357 | 2025-12-15 | 2025-12-31 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 | 23RPG020 |  |  |  | 1996, 1997, 2001, 2010, 2388, 15020, 15021, 15025, 15026, 15045, 15046 | Y |  |  |  | 76136 | 76135 | 2022-NC6
76690 | Add Atchison POD | Add Atchison POD |  | Border Switch | Atchison | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8698 R8726 | 2025-12-16 | 2025-12-16 | 138 | 7 | 0 | 0 |  | Loving | Loving | Tier 4 |  |  |  |  | 11189, 11356, 18670, 18672, 18710 | Y |  |  |  | 98678 | 76690
87477 | [5 empty] | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-12-16 | 2025-04-01 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 3275, 3278, 6935, 6939 | Y |  |  |  | 87478 | 87477
81270 | Construct the new Prong Moss 345 kV switch | Construct a new 345 kV switch |  | Prong Moss | Prong Moss | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2025-12-30 | 2025-12-31 | 345 | 0 | 0 | 0 |  | Howard | Howard | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1025, 10049, 10057, 10062 | Y |  |  |  | 81271 | 81270
90784 | Reconductor portions of Ckt.63C Moody to West Galveston as a Hardening project. |  |  | Moody | West Galveston | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 | 2025-10-31 | 138 | 0 | 2.78 | 0 |  | Galveston | Galveston | Tier 4 | 24RPG037 | 2024-12-06 | 2025-01-02 |  | 42950, 43400 | Y | N |  | Related to MOD Project 72063 | 90785 | 90784
99397 | Buffalo Creek BESS (26INR0405) at Cedar Creek 345kV CEHE Substation | Interconnect new generation facility for Buffalo Creek BESS (26INR0405) at Cedar Creek 345kV CEHE Substation. Utilize existing generator lead. Remove existing generator lead conductor and install new bundled 959ACSS conductor. |  | Cedar Creek | Buffalo Creek | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 | 2025-12-20 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 99398 | 99397
100667 | Oncor_MNE_100667_Cloud 138 kV POD | Establish Cloud 138 kV POD |  | Cloud 138 kV POD |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3309 | 2025-12-31 | 2025-12-31 | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2687, 2691, 12691 | Y |  |  |  | 100668 | 100667
73123 | Sim Gideon - Swiftex Transmission Line Upgrade | LCRA TSC will upgrade T608 Sim Gideon - Swiftex 138-kV transmission line to achieve a higher operational rating. |  | Sim Gideon | Swiftex | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-12-31 | 2025-12-31 | 138 | 0 | 10 | 0 |  | Bastrop | Bastrop | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 7310, 7319, 7326 | Y | N |  |  | 73124 | 73123 | 2023-SC15
72040A | Blueridge to WA Parish Ckt.02A Upgrades (22RPG041) | Upgrade portions of Ckt.02A Quail Valley tap to WA Parish and Ckt.02A DEWALT to Sienna tap as a Hardening upgrade. |  | DEWALT | Sienna | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 | 2958101 | 138 | 0 | 6.14 | 0 |  | Harris | Fort Bend | Tier 4 | 22RPG041 | 2022-11-21 | 2022-12-15 | 2022-12-15 | 44180, 48302, 48335 | Y | N |  |  | 91115 | 72040
72647 | Add_Blue_Ridge_Load | Tapping the Blueridge substation and Climax Switching Station, and adding Blue Ridge load. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-01-01 | 2025-08-01 | 69 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 6803, 37240, 37245, 37280 | Y |  |  |  | 78600 | 72647
64063 | BRP Antlia BESS Interconnection | Connect BRP Antlia BESS to the Maxwell 138 kV station | Status and In-Service Date Update | Maxwell | Antlia | In-Service |  | AEP TCC | Joseph Isaac mlforcum@aep.com 918-599-2674 |  | 2026-01-08 | 2025-01-31 | 138 | 0 | 0 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8998, 88999 | Y |  | TP2021260 |  | 64064 | 64063
4645 | Rebuild of Myra to Spring | Rebuild of Myra to Spring |  | Myra | Spring | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-01-12 | 2025-08-01 | 138 | 0 | 13.9 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 684, 690, 691 | Y |  |  |  | 12221 | 4645
87905 | Hartring – Upland 138 kV Double Circuit Line | Construct new Hartring – Upland 138 kV Double Circuit Line |  | Ringo | LCRA Benedum | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8713 | 2026-01-31 12:00 | 2025-12-10 | 138 | 18 | 0 | 0 |  | Upton | Reagan | Tier 2 | 24RPG024 | 2024-08-09 |  |  | 18671, 18674, 18675, 18676 | Y |  |  |  | 93273 | 87905

## CancelledTPIT020126NoCost
FEBRUARY BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 2/1/2026
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
55603 | Big Foot to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley | Cancelled, incorrectly submitted prior to RPG submission. | Big Foot | Pearsall | Planned | 1104 - 1282 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3821 | 2022-11-30 | 2025-05-12 | 69 | 0 | 14.79 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8216, 8218 | N |  |  |  | 65571 | 55603
3901 | Lobo to Freer: Rebuild 69 kV line | Rebuild Lobo to Freer 69 kV line with 795 ACSS | CANCELLED | Lobo | Freer | Planned | 677 - 0846 | AEP | Brandon Cogan bcogan@aep.com 918-599-2857 | 2596 | 2025-01-07 |  | 69 | 0 | 49.8 | 0 |  | Webb | Duval | Tier 3 |  |  |  |  | 8505, 80222 | N | N |  |  | 11371 | 3901 | 2013-R90
81573 | Oklaunion: Construct New 345 kV Terminal | Interconnect the Alpha load to the existing Oklaunion 345 kV station | CANCELLED | Oklaunion |  | Conceptual |  | AEP TNC/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-03-11 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6100 | N |  |  |  | 81574 | 81573
61467 | Merrilltown Substation Addition | New 138 kV station - Oncor load | [5 empty] | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-03-14 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson | Williamson | Tier 4 |  |  |  |  | 9223, 9224, 9230, 9231 | N |  |  |  | 61468 | 61467
07TPIT0069 | Sterrett - Sardis 138 kV line | Upgrade existing 138 kV line |  | Sterrett | Sardis | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M361-E | 2025-05-15 |  | 138 | 0 | 2 | 0 |  | Ellis | Ellis | Tier 4 | [5 empty] | N | N |  |  | 10446 | 3102
61451 | La Vernia Substation | Replace T2, 20 MVA with a 40MVA dual high-dual low |  | La Vernia | La Vernia | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.or |  | 2025-05-16 |  | 138 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7614 | N | N |  |  | 61452 | 61451
70943 | Double circuit 138kV tie between Pyote and Coyanosa | Project resubmitted as PMCR ID # 77805 |  | Pyote (bus # 38001) | Coyanosa (bus # 38380) | Conceptual |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-06-01 |  | 138 | 15 | 0 | 0 |  | Ward | Reeves | Tier 2 |  |  |  |  | 38001, 38380 | N |  |  |  | 70944 | 70943
48854 | Adds Annova and Port South Bus and lines | Adds Annova and Port South buses, lines to connect Annova to Port South, line from HWY 511 to Port South, and reconnects line from S Carbide to HWY 511 into Port South |  | Annova LNG | Port South | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-06-01 |  | 138 | 22.1 | 0 | 0 | 0,120 | Cameron | Cameron | Tier 4 |  |  |  |  | 5767, 5775, 5776, 8337 | N | N |  |  | 48855 | 48854
64021 | Texana Solar Interconnection | Connect the Texana Solar to the El Campo to Victoria 138 kV line | CANCELLED | El Campo | Victoria | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2020888 | 2025-06-24 |  | 138 | 0 | 0 | 0 |  | Wharton | Victoria | Tier 4 |  |  |  |  | 8099, 8102, 8117, 8192, 8675 | N |  |  |  | 64022 | 64021
65723 | Riedel: Build New Distribution Station | Construct new distribution station on the Magnolia Tap to Nixon 138 kV line | CANCELLED | Riedel |  |  | 1032 - 1210 | AEP TCC/LCRA | Michael Forcum mlforcum@aep.com 918-599-2674 | 3771 | 2025-06-24 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  |  | 8583 | N | Y |  |  | 65724 | 65723
69469 | Equinox Solar Project | Equinox Solar Project | CANCELLED | Cenizo | Del Sol |  |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2025-06-25 |  | 345 | 0 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  |  | 80355, 88355 | N |  |  |  | 69470 | 69469
76174 | Origin 138 kV Interconnection | Interconnect Callon Petroleum on the Saragosa to Solstice 138 kV line | CANCELLED | Origin |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-06-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60206, 60207, 60208, 60209, 60211, 60716 | N | N |  |  | 76175 | 76174
71136 | Waxahachie-Waxahachie OCF 69 kV Line Rebuild | Rebuild the existing Waxahachie-Waxahachie OCF 69 kV Line |  | Wilmer | Waxahachie | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4339 | 2025-07-01 |  | 69 | 0 | 0 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  |  | 2335, 2343 | N |  |  |  | 71137 | 71136
92695 | Switchgrass station and Customer sub | Project cancelled by customer. |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-10-01 |  | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38069, 38070, 38071, 38294 | N |  |  |  | 94008 | 92695
78627 | RCEC_SherwoodShores_AddCap |  |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6806 | N |  |  |  | 78628 | 78627
76288 | Hecker to McCampbell: Rebuild 138 kV Line | Rebuild the Hecker to McCampbell 138 kV Line | CANCELLED | Hecker | McCampbell | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2023507 | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 80470 | N | N |  |  | 76289 | 76288
76280 | Reforzar: Build new 345 kV station - stage 2 | Build new 345 kV station on the Lon Hill to North Edinburg 345 kV line | CANCELLED | Reforzar |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022035 | 2026-01-30 |  | 345 | 0 | 0 | 0 |  | Brooks |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80078 | N |  |  |  | 76281 | 76280
16TPIT0068 | Venus - Chaparral Steel Tap 138 kV Line | Upgrade existing line |  | Venus | Chaparral Steel Tap | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4113-E | 2026-05-15 |  | 138 | 0 | 5.5 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 1908, 2300 | N | N |  |  | 10426 | 3082 | 2013-R50
16TPIT0064 | Simpson Stuart - Lancaster Witt 138 kV Line | Upgrade existing line |  | Simpson Stuart | Lancaster Witt | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4112-E | 2026-05-15 |  | 138 | 0 | 3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2988, 3068 | N | N |  |  | 10416 | 3072 | 2013-R25
81146 | Southmayd 138 kV Switch | Establish Southmayd 138 kV Switch |  | Southmayd |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4338 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  |  | 1744, 2790, 11704 | N |  |  |  | 81147 | 81146
5496 | Forney Switch 345 kV Terminal Equipment | Upgrade the terminal equipment at Forney 345 kV Switch |  | Royse |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3022 | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 4 |  |  |  |  | 2437, 2478 | N |  |  |  | 62442 | 5496
92865 | Oncor_ME_92865_Kirkland Park 138kV Capacitor Bank | Install capacitor banks at Kirkland Park |  | Kirkland Park | Kirkland Park | Planned | M4022 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 | 0,110 | Dallas |  | Tier 4 |  |  |  |  | 2457 | N |  |  |  | 92866 | 92865
3276 | JT Deely to Martinez MLSE Upgrade | Upgrade terminal at JT Deely to ensure a rating of 2386 A (minimum). |  | JT Deely | Martinez | Planned | S-0759 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5110, 5294 | N | N |  | There are no transformers associated with this project | 10627 | 3276
81581 | Riley: Construct New 345 kV Terminal | Interconnect the Gamma load to the existing Riley 345 kV station | CANCEL | Riley |  | Conceptual |  | AEP TNC/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-06-30 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6111 | N |  |  |  | 81582 | 81581
81647 | Dupont Switch to Sardinia: Construct New 138 kV Line | Interconnect the Epsilon load to the new Sardinia 138 kV station out of the existing Dupont Switch 138 kV station | CANCEL | Dupont Switch | Sardinia | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-06-30 |  | 138 | 2 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 8143, 81433 | N |  |  |  | 81648 | 81647
66122 | Tiempo: Build new 345 kV terminal | Interconnect Redonda Solar to the Tiempo 345 kV station |  | Tiempo |  | Under Construction |  | ETT | Aaron Fahey jlsolis@aep.com 361-881-5574 | TP2022009 | 2026-07-15 |  | 345 | 0.1 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 80224, 80232 | N |  |  |  | 66511 | 66122
70662 | Cobra: Build new 345 kV station | Interconnect Garcitas Solar to the new Cobra 345 kV station on the Radiant to Static 345 kV line | CANCEL | Cobra |  | Planned |  | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2022750 | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5915, 8676, 8715, 8728 | N |  |  |  | 70663 | 70662
81825 | Houdini: Construct New 345 kV Station | Interconnect the Xi load to the new Houdini 345 kV station on the STP to WAP 345 kV line | CANCEL | Houdini |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 43990, 44000, 88800 | N |  |  |  | 81826 | 81825
81799 | Four Corners: Construct New 345 kV Station | Interconnect the Nu load to the new Four Corners 345 kV station on the Edith Clarke to Tesla 345 kV line | CANCEL | Four Corners |  | Conceptual |  | AEP TNC/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Hardeman |  | Tier 4 |  |  |  |  | 60501, 60505, 61616 | N | N |  |  | 81800 | 81799
81657 | Verhalen: Construct New 138 kV Terminal | Interconnect the Eta load to the existing Verhalen 138 kV station | CANCEL | Verhalen |  | Conceptual |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60207 | N |  |  |  | 81658 | 81657
81697 | Amber: Construct New 345 kV Station | Interconnect the Kappa load to the new Amber 345 kV station on the Blue Lacy to Reforzar and Blue Lacy to Nelson Sharpe 345 kV lines and add capacitors | CANCEL | Amber |  | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 | 0,523.6 | Nueces |  | Tier 3 |  |  |  |  | 80078, 84550, 84555, 85000 | N |  |  |  | 81698 | 81697
90045 | Vanhagar to Collier: Construct New 138 kV Line | Interconnect the new Collier load station to the new Vanhagar 138 kV station on the Saragosa to Solstice 138 kV line between Hoef's Road and Verhalen | CANCEL | Vanhagar | Collier | Planned |  | AEP TNC | William Simmons twang1@aep.com 918-599-2635 | TP2024119 | 2027-02-28 |  | 138 | 1.5 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 6077, 60127, 60128, 60808 | N | N |  |  | 90914 | 90045
78473A | Odin (ODI) 138kV CEHE Substation | (In terms of completed Waterfowl substation) Loop new CEHE 138kV substation Odin (ODI) into Ckt.36 to create new Ckt.36 COPPER to Odin to Booster tap to Jones Creek. |  | Odin | Brazosport/ Booster | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 |  |  |  |  | 42199, 42215, 42280 | N | N |  |  | 87133 | 78473
78473B | Odin (ODI) 138kV CEHE Substation | Install one generator lead from CEHE 138kV substation Odin (ODI) to VALHAL (VAL) / Valhalla Solar (26INR0042) |  | Odin | VALHAL | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-04-30 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 |  |  |  |  | 42280, 113811 | N | N |  |  | 87134 | 78473
76121 | Beeville Capacitor Addition | Add second 4.8 MVAR step at Beeville |  | Beeville |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-05-01 |  | 69 | 0 | 0 | 0 | 0,4.8 |  |  | Tier 4 |  |  |  |  | 5674 | N | N |  |  | 76122 | 76121
5522 | Lake Hubbard 345/138 kV Switching Station | Construct new 345/138 kV switching station |  | Lake Hubbard |  | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4139 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 |  |  |  |  | 2401, 2402, 2455, 12455, 12456 | N | N |  |  | 13249 | 5522
5525 | Forney - Lake Hubbard 345 kV Line | Construct new 345 kV line |  | Forney | Lake Hubbard | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4233 | 2027-05-15 |  | 345 | 0 | 7.5 | 0 |  | Kaufman | Dallas | Tier 2 |  |  |  |  | 2455, 2467 | N | N |  |  | 13252 | 5525
73540 | LCRATSC_Carlson_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor Lund substation addition. |  | Carlson |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 3650, 7337, 7338 | N | N |  |  | 73541 | 73540
81556 | Haber: Construct New 345 kV Terminal | Interconnect the Crunch load to the new Haber 345 kV station | CANCEL | Haber |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-05-30 |  | 345 | 1 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 81003, 81004 | N |  |  |  | 81557 | 81556
87029 | Parana: Construct New 138 kV Station | Interconnect Portside Energy Center Solar & Storage to the new Parana 138 kV station on the Big Three to Dupont SW 138 kV line | CANCEL | Parana |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | TP2024062 | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 80064 | N |  |  |  | 87030 | 87029
81548 | Haber: Construct New 345 kV Station | Interconnect the Theta load to the new Haber 345 kV station on the Cobra to Static 345 kV line | CANCEL | Haber |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-05-31 |  | 345 | 7 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 8676, 8728, 81003, 81006 | N |  |  |  | 81549 | 81548
81553 | Haber: Construct New 345 kV Terminal | Interconnect the Theta load to the new Haber 345 kV station | CANCEL | Haber |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-05-31 |  | 345 | 1 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 81003, 81005 | N |  |  |  | 81554 | 81553
69479 | Radiant: Build new 345 kV Station | Interconnect Lunis Creek Solar to the new Radiant 345 kV station on the Cobra to STP 345 kV line | CANCEL | Radiant |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2027-05-31 |  | 345 | 0.2 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5915, 8676, 8715 | N |  |  |  | 69480 | 69479
50282 | Adds new Jaguar sub near Twin Pines Switch | Adds new Jaguar sub between Twin Pines Switch and Highlands Sub. For AEP load. | AEP is looking at another location to serve the load. | Highlands Sub | Twin Pines Switch | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5602, 5604, 5609 | N | N |  |  | 50283 | 50282
81655 | Candela: Construct New 345 kV Station | Interconnect the Zeta load to the new Candela 345 kV station | CANCEL | Candela |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2027-06-01 |  | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8317, 8704, 8755 | N |  |  |  | 81656 | 81655
81746 | Calabaza: Construct New 138 kV Terminal | Interconnect the Lambda load to the new Calabaza 138 kV station | CANCEL | Calabaza |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-06-02 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 80380 | N | N |  |  | 81747 | 81746
76916 | Snapdragon: Construct New 138 kV Station | Interconnect Desert Vine Solar to the new Snapdragon 138 kV station on the Revilla to Zapata 138 kV line | CANCELLED | Snapdragon |  | Planned |  | AEP TCC/ETT | Zachary Lachiusa jlsolis@aep.com 361-881-5574 | TP2023012 | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 8299, 8736, 8957 | N | Y |  |  | 76917 | 76916
89993 | STP to Zoisite: Construct New 345 kV Line | Interconnect the HIF load to the new Zoisite 345 kV station on the STP to Zoisite 345 kV line | CANCEL | STP | Zoisite | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2027-06-30 |  | 345 | 1.6 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 | [5 empty] | N | N |  |  | 89994 | 89993
90018 | Sand Crab: Construct New 138 kV Terminal | Interconnect Canvasback BESS to the Sand Crab 138 kV station | CANCEL | Sand Crab |  | Planned |  | AEP TCC | Brooks Dow deevans@aep.com 918-599-2938 |  | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 | [5 empty] | N | N |  |  | 90019 | 90018
44870 | Charlotte 69 kV Station | Charlotte 69 kV Station: Add Cap Bank |  | Charlotte | - | Planned | 976 - 1154 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3734 | 2027-07-01 |  | 69 | 0 | 0 | 0 | 0,7.2 | Atascosa |  | Tier 3 | [5 empty] | N | N |  |  | 44871 | 44870
87899 | Vaso: Construct New 138 kV Station | Interconnect the Alpha load to the new Vaso 138 kV station on the Cantwell to Citgo North Oak 138 kV line | CANCEL | Vaso |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-08-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8466 | N |  |  |  | 87900 | 87899
4490 | LaPalma: Add 2nd 345/138 kV autotransformer | Add 345/138 kV autotransformer capacity at LaPalma | CANCELLED | LaPalma |  |  | 710 - 0880 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 2904 | 2027-09-30 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 4 |  |  |  |  | 8314, 8317, 8356 | N | N |  |  | 12067 | 4490 | 2014-S15, S16
79456A | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072) | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072). Loop Ckt.18 into Huizache substation to create new Ckt.18 Speedway to Huizache to DOW. |  | Huizache | Speedway/DOW | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 43060, 46640 | N | N |  |  | 87175 | 79456
79456B | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072) | Install generator lead from Huizache (HUI) substation to customer substation HIGHCH (HIC) for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072). |  | Huizache | HIGHCH (High Chap) | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | N | N |  |  | 87176 | 79456
72457 | AddKiowaToQuinlanLine | Add 138kV line from Kiowa to Quinlan |  | Kiowa | Quinlan | Planned |  | RCEC | Scott Donhamsdonham@rayburnelectric.com 469-402-2024 |  | 2028-01-01 | 2025-06-01 | 138 | 8 | 0 | 0 |  | Hunt | Hunt | Tier 2 |  |  |  |  | 6796, 6884 | N |  |  |  | 72458 | 72457
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line | Project Deferral | Cresson | Rocky Creek | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5228 | 2028-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  |  | 1881, 2202 | N | N |  |  | 12436 | 4834
81588 | Chalybe: Expand 345 kV Station | Interconnect the Delta load to the Chalybe 345 kV station on the Chalybe to Kingfisher and Chalybe to Palmito 345 kV lines | CANCEL | Chalybe |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-06-01 |  | 345 | 46 | 0 | 1350 |  | Cameron |  | Tier 4 |  |  |  |  | 8735, 79500, 79501, 88337 | N | N |  |  | 81589 | 81588
90012 | Lumos: Construct New 345 kV Station | Interconnect Ross Solar & Storage to the new Lumos 345 kV station on the Angstrom to Static 345 kV line | CANCEL | Lumos |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | TP2024105 | 2028-06-30 |  | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 8249, 8676, 80082 | N | N |  |  | 90013 | 90012
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-12-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5626, 5634 | N | N |  |  | 11275 | 3818 | 2014-S2
86275 | AEN_REPLACE_DUNLAP_345kV_DLAT1_and_DLAT2_AUTOS_WITH__New_672_MVAs | Replace Autos with new 672 MVA |  | 9044 | 9045 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 345 | 0 | 0 | 672 |  | Travis | Travis | Tier 4 |  |  |  |  | 9044, 9045, 90001, 90007 | N |  |  |  | 86276 | 86275
6930 | New Paloma Substation | Adds new station and short line from Midstream |  | Midstream | Paloma | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-06-01 |  | 138 | 0.9 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5643, 5644 | N | N |  |  | 14749 | 6930
6743 | Magellan Tank Farm: LCRA Interconnect | Add 138kV Tie Line between Navigation 138kV substation and Magellan's 138kV substation. Add Metering at Magellan's Substation. | Cancelled | Navigation | Magellan |  | 905 - 1083 | AEP TCC/LCRA | Michael Glueck bcogan@aep.com 918-599-2857 | 3689 | 2029-07-01 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 78460 | N | Y |  |  | 14536 | 6743
65648 | Interconnects Faulkner Data Center | Project has been cancelled. |  | TNMP Faulkner (bus # 38124) | Customer substation (bus # 38125) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-10-01 |  | 138 | 0.15 | 0 | 0 | 0,160 | Reeves | Reeves | Tier 4 |  |  |  |  | 38124, 38125 | N |  |  |  | 65649 | 65648
5524 | Royse South 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | Royse | Forney | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4234 | 2030-05-15 12:00 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 3 |  |  |  |  | 2437, 2467, 2469, 2470, 2471, 2472, 2474, 2478, 2485, 2702, 2710, 12471 | N | N |  |  | 49918 | 5524 | 2017-NC34
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2030-12-17 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7239 | N | N |  |  | 10694 | 3336
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 5600, 5601, 5602 | N | N |  |  | 8729 | 1538
3822 | San Miguel to Sigmor 138 kV line upgrade | Upgrade San Miguel to Sigmor 138 kV line as recommended in 2013 RTP. Will investigate re-conductoring on existing structures with ACCC and other high temperature conductors. |  | San Miguel | Sigmor | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 138 | 0 | 26.3 | 0 |  | Atascosa | Live Oak | Tier 3 |  |  |  |  | 5689, 5902, 8404 | N | N |  | Studies after the 2013 RTP have shown that AEP's approved project to rebuild the 69 kV Beeville to Three Rivers to 138 kV, TPIT 5166, reduces the loading on this line. STEC believes that rebuilding San Miguel to Sigmor is likely to be justified in the future by load growth and or generation additions. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 11279 | 3822 | 2013-R102
5220 | Move Orange Grove load to 138 kV bus | Move load from the 69 KV to the 138 KV instead of replacing auto. 2015 RTP |  | Orange Grove |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 138 | 0 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 5660 | N | N |  |  | 12887 | 5220
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into future 138kV Martinez to Skyline transmission line |  | Converse | Martinez-Skyline | Planned | T-0177 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0601 | 2032-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5098, 5294, 5368 | N | N |  | There are no transformers associated with this project | 8143 | 967
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Howard line. |  | Masterson Rd. | Cagnon-Howard | Planned | T-0910 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0538 | 2032-06-05 |  | 138 | 8 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5054, 5230, 5296 | N | N |  | There are no transformers associated with this project | 9466 | 2218
44963 | USAA Rebuild 138 kV Station | CPSE_USAA 138 kV Substation Rebuild and Line Reconfiguration. |  |  |  | Planned | S-0896 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0285 | 2032-07-01 |  | 138 | 0.6 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-10 |  |  | 5125, 5170, 5208, 5300, 5450, 5451, 5452, 5453 | N |  |  |  | 44964 | 44963

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2022-C1 | Cap bank Addition at AIRPRO Station | CNP | 2025 min
2016-N1 | Kiamichi Energy Facility (140077) 345-kV Reactor Addition | KIOWA POWER PARTNERS LLC (RE) | 2025 min
2021-N2 | City View (1483) – Ceramic (1485) 138-kV Line Terminal Equipment Upgrade | Oncor | 2024
2020-NC19 | Cedar Crest (2493) to Dealey (2842) to West Levee (2400) 138-kV Line Upgrades | Oncor | 2024
2021-NC9 | Sargant – Saint Augustine 138-kV Line Upgrade | Oncor | 2024
2022-NC1 | Waco Northeast Tap (3551) to Waco North (3552) 138-kV Line Upgrade | Oncor | 2024
2022-NC2 | Brand (827) to Ben Davis (968) 138-kV Line Upgrade | GPL | 2024 |  |  | 67170
2022-NC3 | Argyle - Corinth 138-kV Line Upgrade | ONCOR | 2024
2022-NC4 | Wilmer - Southside Filtration Tap East - Kleberg - Seagoville - Seagoville Switch 138-kV Line Upgrade | Oncor | 2024 |  |  | 71178
2022-NC5 | New International Airport Switch 345/138-kV Station | Oncor | 2024
2022-NC6 | Hackberry - DFW D-East 138-kV Line Upgrades | Oncor | 2024
2022-NC7 | Liggett Switch- DFW Area 138-kV Line Upgrades | Oncor | 2024
2022-NC8 | Lake Creek - Elm Mott 138-kV Line Upgrades | Oncor | 2024
2022-NC9 | Tin Roof 345-kV Expansion | Oncor | 2024
2022-NC10 | Randol Mill Tap East - Randol Mill 138-kV Line Upgrade | Oncor | 2024
2021-FW2 | Yucca Drive Switch - Wolfcamp - Courtney Creek 69-kV to 138-kV Line Conversion | Oncor | 2024
2021-FW4 | Rio Pecos - Rankin - Texon Tap - Atlantic Best Tap - Kemper Tap - Big Lake 69-kV to 138-kV Line Conversion | AEP | 2024
2021-FW5 | Caymus TNP - Gas Pad and Caymus TNP - Caymus Compressor TNP 138-kV Line Terminal Equipment Upgrade | TNMP, AEP | 2024
2021-FW6 | Monument Draw TNP to Monument Draw Gray Oak TNP 138-kV Line Terminal Equipment Upgrade | TNMP | 2027
2021-FW7 | TNMP Flat Top 138/25-kV Transformer Upgrade | TNMP | 2024
2021-FW8 | Wink TNP - California TNP 69-kV to 138-kV Line Conversion | TNMP | 2027
2021-FW12 | Moss Switch - Ector Harper - Red Lakes Switch - Penwell POD - Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2021-FW16 | 16th Street TNP - Fort Stockton TNP 69-kV Line Upgrade | TNMP | 2024
2021-FW19 | Morgan Creek SES - Longshore Switch 345-kV Line Upgrade | ONCOR | 2027
2021-FW20 | Lamesa - Key Sub - Gail Sub - Willow Valley Switch 138-kV Line Upgrade | Oncor | 2024
2021-FW23 | Big Spring West - Stanton East 138-kV Line Upgrade | Oncor | 2024
2021-FW24 | Adobe Meadow - Midland East 138-kV Line Upgrade | Oncor | 2025 min
2022-FW1 | Lynx - Tombstone - Fort Stockton Plant - Leon Creek TNP 138-kV Line Upgrade | AEP, TNMP | 2024
2022-FW2 | Cedarvale 345-kV Subtation Expansion | TNMP, Oncor | 2024
2022-FW3 | New Reiter 345/138-kV Substation and Quail East 345-kV Substation | Oncor | 2024
2022-FW4 | New Opyote to Pyote 138-kV Line Addition | TNMP, Oncor | 2024
2022-FW5 | New Load Bus 900012 - New Load Bus 900021 138-kV Line Addition | Oncor | 2024
2022-FW6 | Far West Reactive Power Support Device Additions | TNMP, Oncor, AEP | 2024 |  |  | 65648, 63661, 65642
2022-FW7 | Leon Creek TNP - Airport TNP 138-kV Line Limiting Element Upgrade | TNMP | 2024
2022-FW8 | New Load Bus 900080 - New Load Bus 900032 138-kV Line Addition | Oncor | 2024
2022-FW9 | Cholla 345/138-kV Station Addition | TNMP, Oncor | 2024
2022-FW10 | Dollarhide - Dollarhide Unocal 138-kV Line Upgrade | Oncor | 2024
2022-FW11 | Pecos TNP - Faulkner Toyah TNP 138-kV Line Addition | TNMP | 2024
2022-FW12 | Tarbush TNP - Pig Creek 138-kV Line Upgrade | TNMP, AEP | 2024
2022-FW13 | Yarbrough Sub - Pecos Trails POD - Monahans Tap 2 - Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2022-FW14 | Odessa EHV Switch - Rexall - General Tire Switch - Southwestern Portland Tap - Edwards Tap - Judkins - Sandhills Tap - Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2022-FW15 | Holt Switch - Turnbaugh Corner Switch - Scharbauer POI - Oncor 900053 Tap - Notrees Southeast POI - Blockline POD - Amburguey - Yucca Drive Switch 138-kV Line Upgrade | Oncor | 2024
2022-FW16 | Moss Switch - Shin Oak POD - Yucca Drive Switch 138-kV Line Upgrade | Oncor | 2024
2022-FW17 | Moss Switch - Trigas Odessa Southwest - Big Three Odessa Tap 138-kV Line Upgrade | Oncor | 2024
2022-FW18 | Odessa EHV Switch - Trigas Odessa Tap 138-kV Line Upgrade | Oncor | 2024
2022-FW19 | Lamesa - Jim Payne POI - Paul D Tap 138-kV Line Upgrade | Oncor | 2024
2022-FW20 | Spraberry Switch - CRMWD 7 Tap - Meyers Draw - Dewey Lake Tap - Polecat Creek Switch 138-kV Line Upgrade | Oncor | 2025 min |  |  | 45640
2022-FW21 | Midland East – Midland County NW 345-kV Line Rebuild and Second Circuit Addition | Oncor | 2025 min
2022-FW22 | Midessa South 345/138-kV Transformer Upgrade and Second 345/138-kV Transformer Addition | Oncor | 2025 min
2022-FW23 | Consavvy South 345/138-kV Station Addition | Oncor | 2024
2022-FW24 | Faraday - Lamesa - Clearfork - Riverton 345-kV Double Circuit Line Addition | Oncor, WETT | 2024
2022-FW25 | Cedarvale Third 345/138-kV Transformer Addition | TNMP | 2024
2022-FW26 | Tarbush TNP - Leon Creek TNP and Woodward - Airport TNP - Leon Creek TNP 138-kV Line Additions | TNMP | 2024
2021-W1 | Cassava - San Angelo Concho 69-kV to 138-kV Line Conversion | AEP | 2025 min
2021-W2 | Morgan Creek - McDonald 138-kV Line Upgrade | Oncor | 2024
2021-W7 | San Angelo Highland Street - San Angelo South Tap - San Angelo Power Station 138-kV Line Upgrade | AEP | 2025
2021-W9 | San Angelo Paulann - San Angelo North 138-kV Line Upgrade | AEP | 2027
2021-W10 | San Angelo Red Creek - San Angelo Coke Street - Rusthill 138-kV Line Upgrade | AEP | 2025
2021-W12 | Cap Bank Addition at 138-kV Hargrove Substation | AEP | 2027
2022-W1 | China Grove - Getty Tap 138-kV Line Upgrade | ONCOR | 2028
2022-W2 | Morgan Creek SES - Tonkawa 345-kV Line Rebuild and Second Circuit Addition | ONCOR | 2025
2022-W3 | Colorado City - Plowboy 69-kV to 138-kV Line Conversion | ONCOR | 2025
2022-W4 | Abilene Northwest - Abilene Mulberry Creek - Abilene Industrial Park - Abilene Elmcreek 138-kV Line Upgrade | AEP | 2024
2022-W5 | Scurry Chevron - Kndrsacrc - New Load Bus 900041 Tap - Knapp 138-kV Line Upgrade | Oncor | 2027
2022-W6 | Morgan Creek - Westbrook - Latan Howard Tap 69-kV Line Upgrade | Oncor | 2024
2022-W7 | Knapp - Bluff Creek Switch - Exxon Sharon Ridge 138-kV Line Upgrade | Oncor | 2027
2021-WFW1 | Big Lake - Barnhart - Cassava 69-kV to 138-kV Line Conversion | AEP | 2027
2022-WFW1 | Twin Buttes - Hargrove - Pumpjack - Jerry - Russek Street - Big Lake 138-kV line Upgrade | AEP, LCRA TSC | 2024
2022-WFW2 | Midessa South SW - Consavvy - Longshore Switch - Morgan Creek SES 345-kV Line Upgrades | Oncor | 2025 min
2022-WFW3 | Morgan Creek SES - Falcon Seaboard - Midland East 345-kV Line Rebuild and Second Circuit Addition | Oncor | 2025 min
2022-SC1 | Sim Gideon - Bastrop City - Swiftex 138-KV Line Upgrade | LCRA TSC | 2027
2022-SC2 | San Marcos - Camp Gray - Robert Brown Jr - Clear Fork - Lockhart 69-kV to 138-kV Line Conversion | LCRA TSC | 2028
2022-SC3 | Pintail and Mallard 138-kV Substation and Line Additions | Oncor | 2025
2022-SC4 | Samsung 345-kV Substation and Line Addition | Oncor | 2028
2022-SC5 | Sandow Switch 345/138-kV Substation Expansion | Oncor | 2024
2022-SC6 | Howard - San Miguel 345-kV Double Circuit Line Addition and Beck Road 345/138-kV Substation Expansion | CPS, STEC | 2027
2022-SC7 | Decker 138-kV Bus Tie Breaker Upgrade | AEN | 2027
2022-SC8 | Lytton Substation 345/138-kV Transformer Addition | AEN | 2027
2022-S1 | Corpus Christi Sub 138/69-kV Transformer Addition and New 138-kV (8462) Substation and Line Additions | AEP, STEC | 2024
2022-S2 | Fannisub - Goliad 69-kV Line Upgrade | AEP, STEC | 2024
2022-S3 | Pearsall 138/69-kV Transformer Upgrade | STEC | 2027
2022-S4 | Cap Bank Addition at 138-kV Wormser Road Substation | AEP | 2025
2022-S5 | Reactor Addition at 345-kV NSub Substation | AEP | 2027
2022-S6 | San Diego - Freer 69-kV Line Upgrade | AEP | 2024
2022-S7 | Rincon - Gregory 69-kV Line Upgrade | AEP | 2024
2022-S8 | Rio Hondo - Burns - Heidelburg 138-kV Line Upgrade | STEC | 2024
2022-S9 | LA Palma – Haine Dr 138-kV Line Upgrade | AEP | 2025
2022-S10 | Wesmer - Pantera 138-kV Line Upgrade | AEP | 2024
2022-S11 | North Laredo- Unitec - Gateway West Tap 138-kV Line Upgrade | AEP | 2025

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Cindy Miller | Camiller2@aep.com | Cindy Miller: 918 599 2891 | Glen Reed; Brandon Cogan; Mike Forcum; Jeff Ellis; Mina Turner; Lisa Kelso; | gareed@aep.com; bcogan@aep.com; mlforcum@aep.com; dnlyons@aep.com; jlellis@aep.com; myturner@aep.com; lokelso@aep.com; | Michael Forcum: 918 599 2674 Glen Reed: 918 599 2664 Brandon Cogan: 918 599 2857 Jeff Ellis: 918 599 3458
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Hunt, Dandy; Brion Ryan | dandy.hunt@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | Reza:512 322 6740 Dandy:512 322 6748 Brion: 512-322-6879
BPUB | Primary | Luis Martinez | lugmartinez@brownsville-pub.com; | Luis: 956 983 6212 | Javier Martinez Jr. | jamartinez@brownsville-pub.com; | Javier: 956 983 6530
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Brian Hithersay | bhithersay@brazoselectric.com | Brian: 254-750-6795 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | Edward Lopez | elopez@btutilities.com | Edward: 979 821 5697 | David Hering | dhering@btutilities.com | David: 979 821 5652
CNP | Primary & Secondary | Wesley Woitt | wesley.woitt@centerpointenergy.com | Wesley Woitt: 713-207-2760 | Samuel Whisler; Raja Sekhar Kakarla; Cody Mann | samuel.whisler@centerpointenergy.com; rajasekhar.kakarla@centerpointenergy.com; cody.mann@centerpointenergy.com | Samuel Whisler: 713-207-2767 Raja Sekhar Kakarla: 713-207-3614 Cody Mann: 713-207-3149
COCS | Primary | Glenn Gavit | ggavit@cstx.gov | Glenn: 979 764 3682 | Timothy Crabb, Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | William Robertson | wrobertson@cpsenergy.com | William: 210 353 4147 | Kenneth Bowen Marcos Terrazas Zuber Vohra Eduardo Olivarez | kbowen@cpsenergy.com; mterrazas1@cpsenergy.com; ZMVohra@cpsenergy.com; EJOlivarez@cpsenergy.com | Kenneth: 210 353 4142 Marcos: 210 353 2451 Zuber: 210 353 4262 Eduardo: 210 353 2357
CTT (Cross Texas Transmission) | Primary & Secondary | Christina Minchew | cminchew@lspower.com | Christina: 636:698:8443 | Ramya Nagarajan | RNagarajan@lspower.com | Ramya: 737-881-5008
DENTON | Primary & Secondary | Mark Zimmerer | Mark.Zimmerer@cityofdenton.com | Mark: 940 349 7169 | Cody Tenorio | Cody.Tenorio@cityofdenton.com | Cody: 940 349 7532
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | David Grubbs Kevin Sills | Dgrubbs@gpltexas.org; ksills@gpltexas.org | David: 972-205-2664 Kevin: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; BEC (Bandera); BBEC; CTEC; GVEC; NBU; SBEC; RGEC | Primary & Secondary | Dylan Preas | dylan.preas@lcra.org | Dylan: 512-578-4514 | Naved Khan | naved.khan@lcra.org | Naved: 512-578-4176
Lone Star | Primary & Secondary | Chenyan Guo | chenyan.guo@fpl.com | Chenyan: 561-304-5692 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Jared Gurley | Jared.Gurley@oncor.com | Jared: 817-215-6079 | Zahra Jianpanah | Zahra.Jianpanah@oncor.com
PEC | Primary & Secondary | Charles DeWitt | charles.dewitt@peci.com | Charles: 830-225-0673 | Joshua Rivers | joshua.rivers@peci.com | Joshua: 830-330-4192
Rayburn | Primary | Stephen Geiger | sgeiger@rayburnelectric.com | Stephen: 469-402-2112 | Scott Donham | Sdonham@rayburnelectric.com | Scott: 469-402-2024
Sharyland Utilities | Primary & Secondary | Brad Schwarz | bschwarz@huntpower.com | Brad: 512-289-7425 | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243
STEC | Primary & Secondary | Teddi Flessner Long Tran | tflessner@stec.org long.tran@stec.org | Teddi: 361 485 6119 Long: 361 485 6318 | Paul Person Loretta Gonzalez | pperson@stec.org; lgonzalez@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Kevin Sills | Ksills@gpltexas.org | Kevin: 972-205-2603
TNMP | Primary & Secondary | Ross Cloninger | ross.cloninger@tnmp.com | Ross: 281-581-4733 | Xia, Tao Roberts, Vincent Gerety, Chris | Tao.Xia@tnmp.com; Vincent.Roberts@tnmp.com; Christopher.Gerety@tnmp.com; | Tao: 281-581-4764 Vincent:409-949-5608 Chris:409-949-5605
Wind Energy Texas Transmission (WETT) | Primary | Chris Ramirez | cramirez@wettllc.com | Chris: 737-218-4525 | Yang Zhang | yzhang@wettllc.com | Yang: 737-218-4542

## TSPResponsibility
Field Name | Required/ Optional
ERCOT Project Number | Required
RTP Project Number | Required if in RTP
RPG Project Number | Required for submitted Tier 1, 2, and 3 projects
Project Title | Required
Project Description | Optional
Comments/Reasons for Delays/Cancellations/Speedup | Optional
Terminal "from" Location | Optional
Terminal "to" Location | Optional
Transmission Status | Optional
Associated Projects (project number) | Optional
Transmission Owner | Required
TSP/Company Contact | Required
Transmission Owner Project Number | Optional
Projected In-Service Date (Month/Yr) | Required
Actual In-Service Date (Month/Yr) | Required once energized in the field
CONFIDENTIAL Total Project Estimated Cost | Required
Service Level kV | Required
Trans Circuit Miles New | Optional
Trans Circuit Miles Rebuilt or Upgraded | Optional
Autotransformer Capacity (MVA) | Optional
Reactive Capability Added | Optional
County Location for Substation or for a Line | Optional
County Location for Ending Point for a Line | Optional
Planning Charter Tier | Required
Date Submitted TO ERCOT for RPG Review | Required for submitted Tier 1, 2, and 3 projects
Date RPG Review Completed (Month/Yr) | Required for submitted Tier 1, 2, and 3 projects, if RPG review has been completed.
Date ERCOT BOD Review Completed | -Required for submitted Tier 1 projects, if ERCOT BOD review completed.
SSWG Base Case Related Bus Numbers | Required
Is the project reflected in SSWG Base Cases? | Required
Part of Interface (Y/N) | Required
Requested Additional Information | Optional

## Cost Summary Info
Net Effective Date | Actual In-Service Date | Tab | Cost Summary
past < effective < TPIT | past < actual < TPIT | Complete | Year Completed
past < effective < TPIT | TPIT < actual < future | Planned | Current Year Planned
past < effective < TPIT | actual == NULL | Planned | Current Year Planned
TPIT < effecitve < Current Year end | past < actual < future | Planned | Current Year Planned
TPIT < effecitve < Current Year end | actual == NULL | Planned | Current Year Planned
Current Year end < effective < future | past < actual < future | Future | Year
Current Year end < effective < future | actual == NULL | Future | Year