## ImprovementCostSummary10152024
| Project Cost | [5 empty] | XFMR MVA
| 345 | 138 | 115 | 69 | Total |  | 345 | 138 | 115 | 69 | Total
2023 | 804773000 | 1338626414 | 0 | 243978000 | 2387377414 | 2023 | 4560 | 330 | 0 | 0 | 4890 | For ROS and BOD Reports
2024 | 1122477000 | 2293140052 | 0 | 613003577.09 | 4028620629.09 | 2024 | 7550 | 988.8 | 0 | -300 | 8238.8 | ·All Projects (in engineering, routing, licensing and construction): | [5 empty] | 16504724742
2025 | 1598407000 | 1967372674 | 0 | 394956000 | 3960735674 | 2025 | 7300 | 170 | 0 | 320 | 7790 | ·Transmission Projects Energized in 2024: | [5 empty] | 2435179629.09
2026 | 3410149068 | 2218645000 | 15000000 | 749113000 | 6392907068 | 2026 | 10500 | 1140 | 0 | 0 | 11640
2027 | 1512214570 | 746901000 | 0 | 376521000 | 2635636570 | 2027 | 600 | 135 | 0 | 0 | 735
2028 | 698120000 | 366478430 | 0 | 261025000 | 1325623430 | 2028 | 2112 | 0 | 0 | 0 | 2112
2029 | 79200000 | 291045000 | 0 | 55753000 | 425998000 | 2029 | 672 | 0 | 0 | 0 | 672
2030 | 29600000 | 125200000 | 0 | 1950000 | 156750000 | 2030 | 1200 | 0 | 0 | 0 | 1200
2031 | 0 | 0 | 0 | 13633000 | 13633000 | 2031 | 0 | 0 | 0 | 0 | 0
2024COM | 525237000 | 1483179052 | 0 | 426763577.09 | 2435179629.09 | 2024COM | 2300 | 590.8 | 0 | -400 | 2490.8
2024PLAN | 597240000 | 809961000 | 0 | 186240000 | 1593441000 | 2024PLAN | 5250 | 398 | 0 | 100 | 5748
2023-2031 | 9254940638 | 9347408570 | 15000000 | 2709932577.09 | 21327281785.09 | 2023-2031 | 34494 | 2763.8 | 0 | 20 | 37277.8
2023-2024 | 1927250000 | 3631766466 | 0 | 856981577.09 | 6415998043.09 | 2023-2024 | 12110 | 1318.8 | 0 | -300 | 13128.8
2025-2031 | 7327690638 | 5715642104 | 15000000 | 1852951000 | 14911283742 | 2025-2031 | 22384 | 1445 | 0 | 320 | 24149
| Circuit Miles New |  |  |  |  | Circuit Miles Rebuilt, Reconductored or Upgraded | [5 empty] | Total Circuit Miles New, Rebuilt, Reconductored or Upgraded
| 345 | 138 | 115 | 69 | Total |  | 345 | 138 | 115 | 69 | Total |  | 345 | 138 | 115 | 69 | Total
2023 | 228.641 | 60.22 | 0 | 19.5 | 308.361 | 2023 | 32.92 | 311.031 | 0 | 74.36 | 418.311 | 2023 | 261.561 | 362.791 | 0 | 88.16 | 712.512
2024 | 187.44 | 136.584 | 0 | 9.8 | 333.824 | 2024 | 22.9 | 805.15 | 0 | 268.69 | 1096.74 | 2024 | 210.34 | 941.734 | 0 | 278.49 | 1430.564
2025 | 53.7 | 123.25 | 0 | 1.33 | 178.28 | 2025 | 27.17 | 366.8 | 0 | 224.93 | 618.9 | 2025 | 76.37 | 489.22 | 0 | 226.26 | 791.85
2026 | 680.68 | 107.62 | 3 | 21.6 | 812.9 | 2026 | 275.27 | 668.83 | 0 | 364.57 | 1308.67 | 2026 | 955.95 | 776.45 | 3 | 386.17 | 2121.57
2027 | 64.77 | 31.67 | 0 | 13.1 | 109.54 | 2027 | 86.5 | 208.27 | 0 | 245.8 | 540.57 | 2027 | 151.27 | 239.94 | 0 | 258.9 | 650.11
2028 | 46 | 9 | 0 | 0 | 55 | 2028 | 247 | 311.668 | 0 | 195.071 | 753.739 | 2028 | 293 | 320.668 | 0 | 195.071 | 808.739
2029 | 0 | 13.54 | 0 | 2 | 15.54 | 2029 | 0 | 100.99 | 0 | 37.96 | 138.95 | 2029 | 0 | 114.53 | 0 | 39.96 | 154.49
2030 | 10 | 10 | 0 | 0 | 20 | 2030 | 21.2 | 120.21 | 0 | 0 | 141.41 | 2030 | 31.2 | 130.21 | 0 | 0 | 161.41
2031 | 0 | 0 | 0 | 0 | 0 | 2031 | 0 | 0 | 0 | 2 | 2 | 2031 | 0 | 0 | 0 | 2 | 2
2024COM | 137.44 | 85.61 | 0 | 9.8 | 232.85 | 2024COM | 14.3 | 494.63 | 0 | 149.21 | 658.14 | 2024COM | 151.74 | 580.24 | 0 | 159.01 | 890.99
2024PLAN | 50 | 50.974 | 0 | 0 | 100.974 | 2024PLAN | 8.6 | 310.52 | 0 | 119.48 | 438.6 | 2024PLAN | 58.6 | 361.494 | 0 | 119.48 | 539.574
2023-2031 | 1271.231 | 491.884 | 3 | 67.33 | 1833.445 | 2023-2031 | 712.96 | 2892.949 | 0 | 1413.381 | 5019.29 | 2023-2031 | 1984.191 | 3384.833 | 3 | 1480.711 | 6852.735
2023-2024 | 416.081 | 196.804 | 0 | 29.3 | 642.185 | 2023-2024 | 55.82 | 1116.181 | 0 | 343.05 | 1515.051 | 2023-2024 | 471.901 | 1312.985 | 0 | 372.35 | 2157.236
2025-2031 | 855.15 | 295.08 | 3 | 38.03 | 1191.26 | 2025-2031 | 657.14 | 1776.768 | 0 | 1070.331 | 3504.239 | 2025-2031 | 1512.29 | 2071.848 | 3 | 1108.361 | 4695.499

## FutureTPIT100124NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2024
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
82304 | Blackjack 138kV-69kV Substation |  |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-10-02 |  | 138 | 0.674 | 0 | 178 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 1646, 1647, 37650, 37680, 37681, 37682 | Y |  |  |  | 87722 | 82304
75518 | Rising Star Area Conversions |  |  | Carlton Switch | Carlton (298) | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-10-10 |  | 69 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 297, 298, 299 | Y |  |  |  | 75519 | 75518
67919 | Avanzada: Construct New 345 kV Station | Interconnect Outpost Solar to the Lobo to Fowlerton 345 kV line | Contact Update | Avanzada |  | Under Construction |  | ETT | Adam Wells jlsolis@aep.com 361-881-5574 |  | 2024-10-15 |  | 345 | 0.1 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 5709, 80219, 80235 | Y |  |  |  | 67920 | 67919
88063 | Install new POI | Install new POI |  | Valley South |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3069 | 2024-10-15 |  | 345 | 0 | 0 | 0 |  | Fannin |  | Tier 4 | [5 empty] | Y |  |  |  | 88064 | 88063
72586 | Seward Junction capacitor bank addition | Install 31.3 Mvar capacitor bank at Seward Junction. Replaces ERCOT Project # 70361. |  | Seward Junction |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-10-15 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson |  | Tier 4 |  |  |  |  | 70524 | Y | Y |  |  | 72587 | 72586
66194B | Holliday - Navy Kickapoo 69 kV Line | Idle Holliday-Navy Kickapoo 69 kV line and Demolish Blackwell 69 kV Substation |  | Holliday | Navy Kickapoo | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4022 | 2024-10-15 |  | 69 | 0 | 0 | 0 |  | Archer | Archer | Tier 4 |  |  |  |  | 1473, 1525, 1526, 1527, 1528 | Y |  |  |  | 78353 | 66194
48327 | Reconductor 138kV ckt 972 Howard Lane to McNeil to 3000A. |  |  | 9079 | 9217 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinene 512-322-6740 |  | 2024-10-18 |  | 138 | 0 | 2.81 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9079, 9217 | Y |  |  |  | 48328 | 48327
61358 | Highway 46-River Oaks Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T518 Highway 46 to River Oaks 138-kV and T389 Bergheim to Hays Energy 345-kV 8.6-mile double-circuit transmission line by replacing the aging conductor. Project ID 61356 captures the T389 Bergheim - Hays Energy 345-kV conductor upgrade for modeling purposes. |  | Highway 46 | River Oaks | Planned | 61406, 61392, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-10-25 |  | 345 | 0 | 8.6 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7043, 7173, 7177, 7770 | Y | N |  |  | 78326 | 61358
72213 | Cedar Hill: Upgrade Relays | Upgrade relays for the Sterling City terminal and Miles terminal at the Cedar Hill 138 kV station | Schedule Update | Cedar Hill |  | Planned |  | AEP TNC | Douglas Jansen twang1@aep.com 918-599-2635 | TP2022739 | 2024-10-30 |  | 69 | 0 | 0 | 0 |  | Lee |  | Tier 4 |  |  |  |  | 6422, 6423, 6431 | Y | N |  |  | 72214 | 72213
49574 | Tesla: Build 345 kV terminal | Interconnect Misae II solar farm at Tesla | Contact Update | Tesla |  | Planned | 1023 - 1201 | ETT | Raza Ansari twang1@aep.com 918-599-2635 | 2785 | 2024-10-30 |  | 345 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501 | Y | N |  |  | 49575 | 49574
69283 | Naismith to Resnik: Build New 138 kV Line | Build New 138 kV line from Naismith to Resnik | Schedule, Cost Update | Naismith | Resnik | Planned | 1063 - 1236 | AEP TCC | Thomas Reynolds mlforcum@aep.com 918-599-2674 | TP2017032 | 2024-10-30 12:00 |  | 138 | 3 | 0 | 0 |  | San Patricio | San Patricio | Tier 1 | 19RPG0016 | 2019-10-07 | 2020-05-19 | 2020-06-15 | 8580, 8660, 8674 | Y | N |  |  | 69284 | 69283
6373 | Hamilton Road to Picacho Ckt #2: Rebuild 138 kV Line | Rebuild Hamilton Road to Picacho 138 kV line ckt #2 | Contact Update | Hamilton Road | Picacho | Planned | 870-1051 | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 | 3660 | 2024-10-31 |  | 138 | 0 | 8.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8186, 8255, 8684, 8688, 8690 | Y | N |  |  | 65505 | 6373 | 2017-W1, W2, NWNH2
73057 | Basil: Construct New 138 kV Station | Interconnect Tulsita Solar to the new Basil 138 kV station on the Euler to Tuleta 138 kV line | Contact and In-Service Date Update | Basil |  | Planned |  | AEP TCC | Raza Ansari jlsolis@aep.com 361-881-5574 |  | 2024-10-31 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8162, 8590, 8595, 8731 | Y |  |  |  | 73058 | 73057
3297 | Tezel Road - New 138kV Substation | Loop new 138 kV substation into the existing 138 kV Helotes to Bandera line. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2024-10-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5020, 5200, 5421 | Y |  |  | There are no transformers associated with this project | 10840 | 3297
57750 | Seabrook 138kV Distribution Substation | Build new 138kV Seabrook distribution substation. Double tap from Ckt.79F PH Robinson to Hanna and Ckt.96A PH Robinson to Bayou. |  | Seabrook |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42160, 42780, 42851, 42852, 42853, 48282, 48283, 48851, 48852 | Y | N |  |  | 86005 | 57750
75628 | Poetry 345 kV Switch | Establish Poetry 345 kV Switch |  | Poetry | Poetry | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3228 | 2024-10-31 |  | 345 | 0 | 0 | 0 |  | Kaufman |  | Tier 4 | [5 empty] | Y |  |  |  | 87875 | 75628
73371A | BP24 Sub Upgrades | Upgrade Bellaire Auto A2 spans and CTs to increase thermal limits |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47000, 47010, 49084 | Y | N |  |  | 73372 | 73371
66130 | North Shore Reactive Project | Install 69.2 MVAR capacitor banks at Hecker and Resnik 138 kV stations | Contact Update | Hecker | Resnik | Planned |  | AEP TCC | Chase Isaac deevans@aep.com 918-599-2938 | TP2021207 | 2024-10-31 |  | 138 | 0 | 0 | 0 | 0,69.2 | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 8580 | Y |  |  |  | 66131 | 66130
78464 | Refuge 345kV Substation Expansion for Peyton Creek Wind II (20INR0155) | Expand 345kV Refuge substation for Peyton Creek Wind II (20INR0155) |  | Refuge |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  |  | 78465 | 78464
69281 | Angstrom to Naismith: Build New 345 kV Line | Build New 345 kV Line from Angstrom to Naismith | Contact Update | Angstrom | Naismith | Under Construction | TP2020205 | AEP TCC | William Lovelace deevans@aep.com 918-599-2938 |  | 2024-10-31 |  | 345 | 19 | 0 | 0 |  | San Patricio | San Patricio | Tier 1 | 19RPG0016 | 2019-10-07 | 2020-05-19 | 2020-06-15 | 8249, 8659 | Y | N |  |  | 69282 | 69281
72870 | LCRATSC Soda Lake CB Addition | This project provides a point of interconnection for a new 202.99 MW Solar Energy at the 138-kV Soda Lake Substation by reconfiguring the Soda Lake Substation to breaker-and-a-half to add new 138-kV line terminal and one POI structure to accommodate the new interconnection. Update contingencies |  | Soda Lake |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-10-31 |  | 138 | 0 | 0 | 0 |  | Crane |  | Tier 4 | [5 empty] | Y | N |  |  | 78298 | 72870
57549A | Garden Villas 138kV Load Conversion | Reposition existing Garden Villas dual-voltage transformers TR1/TR2. Reposition one of the transformers with Ckt.06G Garden Villas to Drouet and rename transformer as TR4. |  | Garden Villas | Drouet | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42680, 42690 | Y | N |  |  | 79860 | 57549
57549B | Garden Villas 138kV Load Conversion | Reposition existing Garden Villas dual-voltage transformers TR1/TR2. Reposition one of the transformers with Ckt.07A Garden Villas to Chocolate Bayou tap and rename transformer as TR3. |  | Garden Villas | Chocolate Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42042, 42680, 42681, 42683, 42690 | Y | N |  | Cost included in main project | 79859 | 57549
73371B | BP24 Sub Upgrades | Upgrade Bellaire Auto A5 CTs to increase thermal limits |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-10-31 00:01 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47000, 47015, 49003 | Y | N |  |  | 73373 | 73371
68254 | Friend Ranch: Build new 138 kV Terminal | Interconnect Blue Sky Solar to the Friend Ranch 138 kV Station | Schedule Update | Friend Ranch |  | Planned |  | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 |  | 2024-11-01 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 | [5 empty] | Y | N |  |  | 68255 | 68254
6934B | Elm Creek - New 345 kV Reactor | Install new 345 kV 60 Mvar Reactor at Elm Creek Substation. | [5 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0873, S-0893 | 2024-11-01 |  | 345 | 0 | 0 | 0 | 60,0 | Guadalupe |  | Tier 4 |  |  |  |  | 5133 | Y |  |  |  | 14754 | 6934
79683 | Add Branch between Padua and Sommers |  |  | 5395 | 170722 | Planned | S-0969, T-0327 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2024-11-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5395, 170722 | Y |  |  |  | 79684 | 79683
77648A | Establish Tiger Creek 345 kV Switch for Jaguar Solar/BESS | Establish Tiger Creek 345 kV Switch for Jaguar Solar/BESS |  | Tiger Creek Switch | Tiger Creek Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6223 | 2024-11-14 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 13401, 13405, 68090 | Y |  |  |  | 77649 | 77648
52728 | Add Foundry 138 kV Switch | Oncor's portion of AEP's Crane Area Transmission Project |  | LCRA Arco Crane | Navajo Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8502 | 2024-11-15 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  | 2019-06-01 | 2019-07-22 |  | 10002, 11202, 60448, 71199 | Y |  |  |  | 52730 | 52728 | 2019-FW2
51010 | Heron to Ollin: Rebuild and convert to 138 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/ Company Contact Update | Heron | Ollin | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2798 | 2024-11-15 |  | 138 | 0 | 2 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 60441, 60448 | Y | N |  |  | 51011 | 51010
73025 | CPSE_New_Shaula_POI | [6 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2024-11-21 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5133, 5380, 5915 | Y |  |  |  | 73026 | 73025
50843 | Heron: Build 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/Company Contact Update | Heron |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2796 | 2024-11-22 |  | 138 | 0 | 0 | 90 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 6610, 6611, 6614, 60447, 60448 | Y | N |  |  | 50844 | 50843
73050 | LCRATSC_JohnDumas_Substation_Addition | Substation addition to provide point interconnection for a new power plant. |  | John Dumas |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-11-25 |  | 345 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7041, 7047, 7050 | Y | N |  |  | 73051 | 73050
6216 | Bartlett Switch to Bartlett | Bartlett Switch to Bartlett |  | Bartlett Switch | Bartlett | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-11-28 12:00 |  | 69 | 0 | 2.7 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 114, 118 | Y |  |  |  | 13941 | 6216
87594 | Rebuild League City-Dickinson 138kV with 2-795 ACSS. |  |  | Dickinson (38850) | League City (38920) | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-11-30 |  | 138 | 0 | 5.6 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38850, 38920 | Y |  |  |  | 87595 | 87594
76145 | Matador: Station Build | Build a new Matador station five breaker ring bus | Contact and Cost Update | Matador |  | Planned |  | AEP TNC | Chris Carrol twang1@aep.com 918-599-2635 | TA2020140 | 2024-11-30 |  | 69 | 0 | 0 | 0 |  | Motley |  | Tier 4 |  |  |  |  | 6039, 6074, 6140, 6141 | Y | N |  |  | 76146 | 76145
63635 | Tribute: Build 138 kV Station | Build new 138 kV Station on the San Angelo Power to Red Creek 138 kV line | In-Service Date Update | Tribute |  | Planned | 1132 - 1310 | AEP TNC | Larry Brown twang1@aep.com 918-599-2635 | 1877 | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6442, 6473, 60008 | Y | N |  |  | 63636 | 63635
87477 | [5 empty] | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2024-11-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 3275, 3278, 6935, 6939 | Y |  |  |  | 87478 | 87477
78455 | Oasis 345kV Substation / SOHO BESS II (25INR0162) | Install SOHO BESS II at Oasis 345kV substation… Connect at the same generator lead as SOHO BESS (SOHO BESS II - 25INR0162) |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-11-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 78456 | 78455
73166 | Whitepoint: Rebuild Station | Rehab Whitepoint 138/69 kV Station | Status and In-Service Date Update | Whitepoint |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TA2018035 | 2024-11-30 |  | 138 | 0 | 0 | 130 |  | San Patricio |  | Tier 4 |  |  |  |  | 8960, 8961 | Y | N |  |  | 73167 | 73166
57797 | Athey: Build 138 kV Station | Build new 138 kV Station on the Ft Stockton to Rio Pecos 138 kV line |  | Athey |  | Under Construction | 1109 - 1287 | AEP TNC | Shawn Ketcher twang1@aep.com 918-599-2635 | 1866 | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60718, 60792, 60798 | Y | N |  |  | 65578 | 57797
72042 | Oasis 345kV Substation Expansion for SMT Ironman BESS (24INR0265) | Expand 345kV Oasis substation for SMT Ironman BESS (24INR0265) |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-11-30 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 43030, 43035, 113613 | Y | N |  |  | 72043 | 72042
50966 | Naismith: Build 345/138 kV Station | Build new 345/138 kV station with two autotransformers | In-Service Date and Estimated Cost Update | Naismith |  | Planned | 1063 - 1236 | AEP TCC | Thomas Reynolds mlforcum@aep.com 918-599-2674 | TP2017032 | 2024-11-30 |  | 345 | 0 | 0 | 1350 |  | San Patricio |  | Tier 1 | 19RPG0016 | 2019-10-07 | 2020-05-19 | 2020-06-15 | 8659, 8660, 8674 | Y | N |  |  | 69279 | 50966
69463 | Gulch: Construct new 345 kV Station | Interconnect Arroyo Solar to the new Gulch 345 kV station on the La Palma to Rio Hondo 345 kV line | Description and Contact Update | Gulch |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-11-30 |  | 345 | 0.1 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8317, 8318, 8704, 8705 | Y |  |  |  | 70802 | 69463
70665C | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits |  | PSARCO | BIGVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-11-30 |  | 138 | 0.83 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40190, 41305 | Y | N |  |  | 75838 | 70665
70704 | LCRATSC_Florence_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Andice and Glasscock and install 46.7 MVA distribution transformer. The new substation will be located approximately 4.87 miles from Glasscock substation. |  | Andice | Glasscock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7521, 7523, 70522 | Y | N |  |  | 70705 | 70704
76080 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild Mines Road to North Laredo SW 138 kV line | Contact Update | Mines Road | North Laredo | Planned | 1116 - 1294 | AEP TCC/ETT | William Lovelace jlsolis@aep.com 361-881-5574 | 3835 | 2024-11-30 |  | 138 | 0 | 5.85 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8643, 8909 | Y |  |  |  | 76081 | 76080
70798 | Stewart Road: Station work | Kiskadee Storage | Contact and In-Service Date Update | Stewart Road |  | Planned |  | AEP TCC | Curtis Brown jlsolis@aep.com 361-881-5574 | TP2022166 | 2024-11-30 |  | 138 | 1 | 0 | 0 |  | Hidalgo |  | Tier 4 | [5 empty] | Y |  |  |  | 70799 | 70798
71011 | Solstice: CT Removal | Remove CTs from Solstice station located along the Solstice to Sand Lake ONCOR and the Solstice to Bakersfield LCRA 345 kV double circuit lines | Estimated Cost Update | Solstice |  | Planned |  | AEP TNC | Chris Caroll twang1@aep.com 918-599-2635 |  | 2024-11-30 |  | 345 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 11098, 60404, 76002 | Y | N |  |  | 71012 | 71011
77035 | New Mathis Substation | Remove Mathis substation, construct new Mathis substation | Status, Contact, and In-Service Date Update | Mathis |  | Under Construction |  | AEP TCC | Chase Isaac deevans@aep.com 918-599-2938 | DP20X0003 | 2024-11-30 |  | 69 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 5666, 5668, 8107, 8407, 8424, 8671 | Y |  |  |  | 77036 | 77035
50948 | Angstrom - Grissom: Build New Line | Angstrom - Grissom: Build New Line | In-Service Date Update | Angstrom | Grissom | Planned | 1063 - 1236 | AEP TCC | Teresa Trotman mlforcum@aep.com 918-599-2674 | 3797 | 2024-11-30 |  | 345 | 17 | 0 | 0 |  | San Patricio | Bee | Tier 1 | 19RPG0016 | 2019-10-07 | 2020-05-19 | 2020-06-09 | 8249, 8624 | Y | N |  |  | 50949 | 50948
6749 | Rosata: Build 138kV Substation | Build new Rosata 138 kV POD Switch on the Coleto Creek to Kenedy 138 kV line | Contact Update | Rosata |  | Planned | 898 - 1076 | AEP TCC | Chase Stevens deevans@aep.com 918-599-2938 | 3682 | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7241, 8153, 8162, 8186, 88153 | Y | Y |  |  | 14542 | 6749
78425 | Danbury to LONG / Longbow BESS (25INR0328) | Expand facilities at customer-owned LONG substation for Longbow BESS (25INR0328). Utilize existing generator lead LONG to Longbow Solar. |  | Danbury | LONG | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-11-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42875, 112662 | Y | N |  |  | 78426 | 78425
73371H | BP24 Sub Upgrades | Upgrade White Oak to Jeanetta Ckt.72B to increase thermal limits |  | White Oak | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-11-30 00:07 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46600, 47300 | Y | N |  |  | 73379 | 73371
70371 | D'Hanis Capacitor addition | Add 9.6 MVAR capacitor step at D'Hanis |  | D'Hanis |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-12-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5814 | Y | N |  |  | 70372 | 70371
71954 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 |  | Orange Grove | Talitha | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-12-01 |  | 138 | 0.73 | 0 | 0 |  | Jim Wells | Jim Wells | Tier 4 |  |  |  |  | 5660, 5661 | Y |  |  |  | 71955 | 71954
1205 | Planned reconductor from Hasse to Gustine | Planned reconductor from Hasse to Gustine |  | HASSE | GUSTINE | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-12-01 |  | 69 | 0 | 7.34 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 273, 277 | Y |  |  |  | 54001 | 1205
71982 | Upgrade Orange Grove station | Upgrade Orange Grove stationto ring bus |  | Orange Grove | Orange Grove |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 71983 | 71982
4645 | Rebuild of Myra to Spring | Rebuild of Myra to Spring |  | Myra | Spring | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-12-01 |  | 138 | 0 | 13.9 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 684, 690, 691 | Y |  |  |  | 12221 | 4645
70884 | Rebuild Rio Colorado - Bay City | Rebuild Rio Colorado - Bay City 795 ACSR |  | Rio Colorado | Bay City | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-12-01 |  | 69 | 0 | 9.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5560, 5563 | Y |  |  |  | 70885 | 70884
45155 | Ollin: Build 138 kV station | Construct new Ollin 138 kV station | TSP/ Companny Contact Update | Ollin |  | Planned | 939 - 1117 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 2752 | 2024-12-01 01:00 |  | 138 | 0.1 | 0 | 0 |  | Crane |  | Tier 4 | 19RPG013 |  |  |  | 6600, 6604, 6605, 6606, 6607, 6610, 6611, 6613, 6668, 6669, 60428, 60429, 60431, 60432, 60441, 76615 | Y | N |  |  | 45156 | 45155
70354 | LCRATSC_WolfLane_Substation_Upgrade | Upgrade Wolf Lane Substation to a 3000 A, 138-kV ring bus arrangement. Contingency Update |  | Wolf Lane |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-12-10 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 | [5 empty] | Y | Y |  |  | 70355 | 70354
88058 | Upgrade the existing 55.2 MVAR capacitor bank to a 110.4 MVAR capacitor bank | Upgrade the existing 55.2 MVAR capacitor bank to a 110.4 MVAR capacitor bank |  | Tex Harvey |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8812 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 1221 | Y |  |  |  | 88061 | 88058
5436 | Morgan Creek - McDonald 138 kV Line | Upgrade existing line | Project Deferral | Morgan Creek | McDonald Rd | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8360 | 2024-12-15 |  | 138 | 0 | 31.8 | 0 |  | Howard | Mitchell | Tier 3 | 23RPG011 | 2023-05-03 | 2023-05-26 |  | 1032, 1333, 11395 | Y |  |  |  | 73625 | 5436
71989 | Big Spring West - Stanton East 138 kV Line | Rebuild the existing 138 kV line |  | Big Spring West | Stanton East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8303 | 2024-12-15 |  | 138 | 0 | 17.6 | 0 |  | Martin | Howard | Tier 4 |  |  |  |  | 1322, 1324, 1325, 1326, 10044, 11316, 11324, 11331 | Y |  |  |  | 73334 | 71989
71993 | Tributary - Vincent 138 kV Line Section | Rebuild the existing 138 kV line |  | Tributary | Vincent | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8667 | 2024-12-15 |  | 138 | 0 | 11.2 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 1394, 1397, 10047 | Y |  |  |  | 73300 | 71993
61932B | Holliday - Seymour 69 kV Line | Re-terminate line into new bay at Seymour Switch |  | Holliday | Seymour | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4028 | 2024-12-15 |  | 69 | 0 | 0 | 0 |  | Archer | Baylor | Tier 3 | 21RPG007 | 2021-04-26 | 2021-05-18 |  | 1527, 1530 | Y |  |  |  | 73028 | 61932
77650 | Establish Steakley Dam 345 kV Switch for Blevins Solar | Establish Steakley Dam 345 kV Switch for Blevins Solar |  | Steakley Dam | Steakley Dam | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6282 | 2024-12-15 |  | 345 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3404, 3409, 3741 | Y |  |  |  | 77651 | 77650
76682 | Add Capacitor Bank at Savanna 138 kV Substation | Add Capacitor Bank at Savanna 138 kV Substation |  | Savanna |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8694 | 2024-12-15 |  | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 10025, 23867, 23870 | Y |  |  |  | 81462 | 76682
76719 | Establish Blue Mountain 138 kV Switch | Establish 138 kV Switch |  | Blue Mountain | Blue Mountain |  |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8702 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1092, 11070, 11113, 11382, 18680 | Y |  |  |  | 81370 | 76719
81063 | Progress Park 138 kV Switch | Establish Progress Park 138 kV Switch |  | Progress Park |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3076 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  |  | 1699, 12677, 12678 | Y |  |  |  | 81065 | 81063
81148 | Lago Vista T3 addition | T3 addition with bus tie breakers |  | LAGO VISTA 70352 |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 70352 | Y |  |  |  | 81149 | 81148
72649B | Add_Celina_Load |  |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2350, 6793, 12351 | Y |  |  |  | 78609 | 72649
81605 | Kolb Lake 138 kV POD | Establish Kolb Lake 138 kV POD |  | Kolb Lake POD | Kolb Lake POD | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6229 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3307, 3340, 3346, 3347, 3747 | Y |  |  |  | 81606 | 81605
52247 | Marrs - Handley 69 kV Line Conversion to 138 kV | Convert the existing Marrs-Handley 69 kV line to 138 kV operation |  | Marrs SW | Handley | Under Construction |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5222 | 2024-12-15 |  | 138 | 2.2 | 13 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1951, 1952, 1967, 1968, 1969, 2158, 2159, 2160, 2161, 2162, 11950, 11951, 11952, 11967 | Y |  |  |  | 86795 | 52247
62693 | Courtney Creek - Yucca Drive 69 kV Line Conversion to 138 kV | Add Courtney Creek - Yucca Drive 69 kV Line Conversion to 138 kV |  | Courtney Creek | Yucca Drive | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8591 | 2024-12-15 |  | 69 | 0 | 44 | 0 |  | Pecos | Ward | Tier 3 | 22RPG025 | 2022-08-24 | 2022-09-16 |  | 1009, 1015, 1202, 1203, 1204, 1238, 1239, 1240, 1242, 11204, 11238, 11242, 11258, 11262, 60792 | Y |  |  |  | 87202 | 62693
87756 | Rowan Creek 138 kV Switch | Establish Rowan Creek 138 kV Switch for Azalea Springs Solar |  | Rowan Creek | Rowan Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6257 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3349, 3351, 3760 | Y |  |  |  | 87757 | 87756
70900B | Roanoke Area Upgrades | Establish Exchange 345 kV Switch |  | Exchange Switch | Kingsridge Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2024-12-15 |  | 345 | 0.4 | 0 | 1500 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 1845, 1851, 1855, 2081, 12077, 12078, 12079, 12080, 12081 | Y | N |  |  | 87467 | 70900
52332 | Lamesa - Paul Davis Tap 138 kV Line Section | Upgrade the existing 138 kV line |  | Lamesa | Paul Davis Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8499, R8475 | 2024-12-15 |  | 138 | 0 | 17 | 0 |  | Dawson | Dawson | Tier 3 |  |  |  |  | 1163, 1169, 18880 | Y |  |  |  | 87135 | 52332
80550 | Central Park 138 kV Switch | Establish Central Park 138 kV Switch for Graphic Packaging International, LLC |  | Central Park | Central Park | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6273 | 2024-12-15 |  | 138 | 1.2 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3446, 3474, 3544, 3547 | Y |  |  |  | 87808 | 80550
62666A | Upgrade and convert McGregor - Waco West Line | Rebuild the Waco West - McGregor Phillips 69 kV Line |  | Waco West | McGregor Phillips | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6172 | 2024-12-15 |  | 69 | 0 | 19 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3370, 3437, 3441, 3584, 3586 | Y |  |  |  | 87909 | 62666
73043 | Peck - Driver 138 kV Line | Construct a new 138 kV line | [5 empty] | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8603 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | 22RPG047 | 2022-12-27 | 2023-01-20 |  | 1217, 1222, 1223, 1226, 1329, 1330, 10114, 10126, 11222, 11226, 11227, 18664, 23863 | Y |  |  |  | 87662 | 73043
73368 | Grey Well Draw - Buffalo 138 kV Second Circuit | Add Grey Well Draw - Buffalo 138 kV Second Circuit |  | Grey Well Draw | Buffalo | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8692 | 2024-12-15 |  | 138 | 6 | 26.2 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 10061, 11390, 11396, 23837, 23858 | Y |  |  |  | 87790 | 73368
66289A | Tyler to Athens 138 kV line Conversion | Chandler West to Echols 69 Kv Line Upgrade |  | Chandler | Echols | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6094 | 2024-12-15 |  | 69 | 0 | 0 | 0 |  | Henderson | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3108, 3236, 13235 | Y |  |  |  | 87814 | 66289
81378 | Odessa EHV - Edwards Tap 138 kV Line Rebuild | Odessa EHV - Edwards Tap 138 kV Line Rebuild |  | Odessa EHV | Wolf | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8528 | 2024-12-15 |  | 138 | 0 | 16.6 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 1027, 1052, 1053, 1054, 1099, 1110, 10134, 11003, 11281 | Y |  |  |  | 87865 | 81378
66567 | Add Wolf - Moss 138 kV Line Rebuild | Add Wolf - Moss 138 kV Line Rebuild |  | Wolf | Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8530 | 2024-12-15 |  | 138 | 0 | 34.5 | 0 |  | Ward | Ector | Tier 3 | 22RPG013 | 2022-05-11 | 2022-06-03 |  | 1013, 1019, 1292, 11292, 11293 | Y |  |  |  | 87221 | 66567
5466 | Redland Switch 345/138 kV Autotransformer | Install new 345/138 kV Autotransformer at Redland Switch previously known as Herty North |  | Redland | Redland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6076 | 2024-12-15 |  | 345 | 0 | 0 | 600 |  | Angelina | Angelina | Tier 3 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3306, 3321, 3322 | Y | N |  |  | 13170 | 5466
5467 | Nacogdoches Southeast_Redland 345kV Line | Establish a new 345kV Line between Nacogdoches Southeast Switch and Redland Switch |  | Nacogdoches Southeast | Redland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6075 | 2024-12-15 |  | 345 | 13.4 | 0 | 0 |  | Nacogdoches | Angelina | Tier 2 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3119, 3321 | Y | N |  |  | 13171 | 5467
68955 | Meteor 345 kV Switch | Establish Meteor 345 kV Switch |  | Wolf | Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8619 | 2024-12-15 |  | 345 | 0 | 0 | 0 |  | Ward | Ector | Tier 4 |  |  |  |  | 1018, 10012, 11010 | Y |  |  |  | 68957 | 68955
71908 | Install second 345/138 kV Auto at Temple Pecan Creek | Install second 345/138 kV Auto at Temple Pecan Creek and cut in the Temple - Lake Creek 345 kV Line |  | Temple Pecan Creek | Temple Pecan Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6239 | 2024-12-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3404, 3412, 3414, 3420, 13412 | Y |  |  |  | 71909 | 71908 | 2023-NC60
71960 | Upgrade Grady - Expanse 138 kV Line | Rebuild the existing 138 kV line |  | Grady | Expanse | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8639 | 2024-12-15 |  | 138 | 0 | 6.4 | 0 |  | Martin | Martin | Tier 4 |  |  |  |  | 11368, 23842 | Y |  |  |  | 71962 | 71960
71976 | Watermill 138 kV Switch | Rebuild the existing Watermill 138 kV Switch |  | Watermill |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3031 | 2024-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 2126, 2238, 2427, 2429, 2430, 12430, 12433 | Y |  |  |  | 71977 | 71976
66200C | Upgrade Taylor - Holland 69 kV Line | Rebuild the Bartlett - Granger 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6173 | 2024-12-15 |  | 69 | 0 | 6.9 | 0 |  | Williamson | Williamson | Tier 4 | 22RPG036 |  |  |  | 3647, 3648 | Y |  |  |  | 71896 | 66200
72876 | Provide 138 kV POD for Skybox at Teal Switch | Provide 138 kV POD for Skybox at Teal Switch |  | Teal | Skybox | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6259 | 2024-12-15 |  | 138 | 0.2 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3362, 3371 | Y |  |  |  | 72877 | 72876
45640 | Spraberry - Polecat Creek 138 kV Line | Upgrade the existing 138 kV line |  | Spraberry | Polecat Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8645 | 2024-12-15 |  | 138 | 0 | 32.4 | 0 |  | Midland | Glasscock | Tier 3 |  |  |  |  | 1328, 1329, 1337, 10029, 11337, 11350, 11372, 11394 | Y |  |  |  | 73413 | 45640
78374 | Rockhound 345/138 kV Switch | Construct a new 345/138 kV Switch |  | Falcon Seaboard | Midland East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8705 | 2024-12-16 |  | 345 | 0 | 0 | 1200 |  | Midland | Martin | Tier 3 | 24RPG002 | 2024-01-11 |  |  | 1021, 1025, 10062, 10063, 10064, 10065, 11390, 23837, 23843, 23858 | Y |  |  |  | 78375 | 78374
56350D | Burnett - Bowie 69 kV Line | Rebuild Old lake Switch - Smith Creek Line (FKA Ringgold Magnolia tap - Bellevue) |  | Burnett | Ringgold Magnolia Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4015 | 2024-12-16 |  | 69 | 0 | 9.8 | 100 |  | Wichita | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 11541, 17010, 33770 | Y | N |  |  | 73041 | 56350
13TPIT0070 | Nash Creek Substation | Rebuild existing substation, and replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2024-12-20 |  | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7596 | Y | N |  |  | 78324 | 3322
78553 | [5 empty] | In-Service |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2024-12-25 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2626, 6791, 6807 | Y |  |  |  | 80747 | 78553
54521 | Hilltop_Weatherford_Rebuild |  |  | Weatherford (1589) | Hilltop (501) | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-12-26 |  | 138 | 0 | 13 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 501, 505, 512, 1589 | Y |  |  |  | 54522 | 54521
77041 | LCRATSC_LeonSwitch_Putnam_TL_Overhaul | LCRA TSC will perform an overhaul on the 8.9-mile Leon Switch – Putnam (T727) 138-kV transmission line between Leon Switch existing structure #1/1 and Putnam existing structure #9/10. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Leon Switch | Putnam | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-12-26 |  | 138 | 0 | 8.95 | 0 |  | Eastland | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | Y |  |  | 77042 | 77041
69902A | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. Loop Ckt.18E into Mission substation to create new Ckt.18 Gibbons Creek to Mission to Zenith. (Ckt.18 Gibbons Creek to Mission tie-line). Install generator lead from Mission (MSS) substation to Parliament/Parliament Solar |  | MISSION | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-30 |  | 345 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  |  | 967, 44900, 44920, 113925 | Y | N |  |  | 78230 | 69902
5167 | Poesta to Tuleta: Build new double circuit 138/69 kV line | Construct a new 138/69 kV Poesta station and install a 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. |  | Poesta | Tuleta | Under Construction | 742 - 0925 | AEP TCC | Dave Goetz mlforcum@aep.com 918-599-2674 | 2916 | 2024-12-30 |  | 138 | 23.5 | 23.5 | 0 |  | Bee | Bee | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8195, 8196, 8197, 8198, 8584, 8585, 8586, 8590, 8592, 8593, 8629, 85851, 88198 | Y | N |  |  | 61033 | 5167 | 2015-S10
73338A | Pythias (PYT) 138kV CNP Station for Second Division Solar (20INR0248) | Loop new CNP 138kV substation Pythias (PYT) into Ckt.60H to create new Ckt.60 San Bernard to Pythias to West Columbia. |  | Pythias | San Bernard/ West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43090, 43110, 43380 | Y | N |  |  | 88037 | 73338
67422E | Greens Bayou to Clinton 138kV Conversion | Rebuild-Reconductor Ckt.10A Wallisville tap to TEXWAL |  | Wallisville | TEXWAL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 69 | 0 | 1.44 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41570, 41682 | Y | N |  |  | 87578 | 67422
86011 | Snug 138kV Substation expansion for Cottonwood Bayou Storage (21INR0443) | Install Cottonwood Bayou Storage (21INR0443) at Snug 138kV substation. Connect at the same generator lead as Cottonwood Bayou Solar. |  | Snug |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 44890, 113435 | Y | N |  |  | 86012 | 86011
78420 | Baytown Distribution Transformer | Install third Baytown distribution transformer on Ckt.03B to create new Ckt.03B Kenny tap to Baytown tap to Baytown 138kV. |  | Baytown | KENNY | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40170, 40171, 40172, 40173, 44630 | Y | N |  |  | 87362 | 78420
73476 | Rebuild Kermit #2 as Windblown 69kV Substation. | Rebuild Kermit #2 Substation as Windblown 69kV Substation, and rebuild Wink-Windblown 69kV Line. |  | TNMP Wink (37920) | TNMP Windblown (38270) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-12-31 |  | 69 | 0 | 10.8 | 0 |  | Winkler | Winkler | Tier 4 |  |  |  |  | 37920, 38250, 38260, 38270, 38290 | Y |  |  |  | 87443 | 73476
48774 | Fincas: Build new 138 kV distribution station | Construct new distribution station on the University to Wormser 138 kV line | In-Service Date Update | Fincas |  | Planned | 1026 - 1204 | AEP TCC | Travis Coody mlforcum@aep.com 918-599-2674 | 3765 | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8039, 8649, 8653 | Y | N |  |  | 81145 | 48774
78423 | Bellaire to WAP Ckt.50A Upgrade - WAP Switch 0505 | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits |  | Bellaire | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47000 | Y | N |  |  | 78424 | 78423
77074 | Buda to Turnersville Storm Hardening | Rebuild single circuit section of Buda to Turnersville and reconductor with bundled 795 ACSR Conductor, 439 MVA. |  | Buda | Turnersville | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-12-31 |  | 138 | 0 | 3.8 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7500, 70498 | Y | N |  |  | 77075 | 77074
76176 | Transmission POI for Dogfish BESS |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38331, 38455, 38465 | Y |  |  |  | 76177 | 76176
75930 | Expand Highlands substation with addition of 3rd distribution transformer. Transformer expected at Ckt.66F Garth to Highlands tap to Haney. |  |  | Highlands | Garth/Haney | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40812 | Y | N |  |  | 75931 | 75930
70633A | Burke to Eagles Nest Ckt.02J Upgrades | Upgrade Ckt.02J Burke to Eagles Nest as a Hardening upgrade |  | Burke | Eagles Nest | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 4.59 | 0 |  | Brazoria | Brazoria | Tier 4 | 22RPG037 | 2022-10-31 | 2022-11-22 | 2022-11-22 | 42410, 42430, 42980 | Y | N |  |  | 72452 | 70633
72053 | Oasis 345kV Substation Expansion for SOHO BESS (23INR0419) | Expand 345kV Oasis substation for SOHO BESS (23INR0419). Reposition existing Ckts. 18B and 27B Oasis to Dow and Ckt.99E Meadow to Oasis. |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  |  | 72054 | 72053
69892 | Deer Park Tap to NOBEL Ckt.21C Upgrades | Upgrade portions of Deer Park Tap to Underwood tap to NOBEL Ckt.21C as a Hardening upgrade |  | Underwood | NOBEL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 |  | 138 | 0 | 1.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 48084, 48389 | Y | N |  |  | 69893 | 69892
71319 | Upgrade Pearsall Station | Upgrade Pearsall Station to breaker and a half |  | Pearsall | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5893, 5895 | Y |  |  |  | 71320 | 71319
59099 | Blessing to Celanese: Rebuild 138 kV line | Rebuild the Blessing to Celanese 138 kV line | In-Service Date Update | Blessing | Celanese Bay City | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2020227 | 2024-12-31 |  | 138 | 11.54 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 8116, 8121, 8191, 8558 | Y |  |  |  | 65587 | 59099 | 2020-C1
64063 | BRP Antlia BESS Interconnection | Connect BRP Antlia BESS to the Maxwell 138 kV station | In-Service Date Update | Maxwell | Antlia | Planned |  | AEP TCC | Joseph Isaac mlforcum@aep.com 918-599-2674 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8998, 88999 | Y |  | TP2021260 |  | 64064 | 64063
64069 | Charger Solar Interconnection | Connect the Charger Interconnection to the Angstrom to STP 345 kV line | Contact Update | Angstrom | STP | Planned |  | AEP TCC | Teresa Trotman deevans@aep.com 918-599-2938 | TP2021165 | 2024-12-31 |  | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 5915, 8249, 8676, 8678 | Y |  |  |  | 64070 | 64069
63579 | Roby to Rotan: Rebuild 69 kV Line | Rebuild the Roby to Rotan 69 kV Line |  | Roby | Rotan | Planned | 1130 - 1308 | AEP TNC | Christopher Carroll twang1@aep.com 918-599-2635 | 1875 | 2024-12-31 |  | 69 | 0 | 8 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 6194, 6195, 6196 | Y | N |  |  | 63580 | 63579
52068 | Coy City Tap to Pleasanton: Convert to 138 kV | Convert Pleasanton to Three Rivers 69 kV line and Coy City Tap to Fashing 69 kV line to 138 kV, reterminate Pleasanton to Three Rivers into 138 kV yards at Pleasanton and Three Rivers, install new terminal for the Trumbo line at Pleasanton, and convert Fashing, Coy City Tap, and Schottky stations to 138 kV | Project Title, TSP/Company Contact, Estimated Cost, Trans Circuit Miles Rebuilt Update | Pleasanton | Three Rivers | Planned | 1077 - 1250 | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 | 3802 TP2020193 | 2024-12-31 |  | 138 | 0 | 8.46 | 0 |  | Atascosa | Live Oak | Tier 4 |  |  |  |  | 8142, 8199, 8200, 8203, 8400, 8403, 8406, 8507, 8599, 8600, 84061, 85071, 85991, 86001, 88507 | Y | N |  |  | 65610 | 52068 | 2019-S2
63956 | Clear Crossing: Build 345 kV terminal | Interconnect HODL Ranch II at Clear Crossing 345 kV station | In-Service Date Update | Clear Crossing | HODL Ranch II | Planned | 1139 - 1317 | ETT | Adam Wells twang1@aep.com 918-599-2635 | 1884 | 2024-12-31 |  | 345 | 0 | 0 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  |  | 60017, 60515 | Y | N |  |  | 63957 | 63956
70717 | LCRATSC_Yarrington_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Rohr and Goforth and install 46.7 MVA distribution transformer. The new substation will be located approximately 0.17 miles from Rohr substation. |  | Rohr | Goforth | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-12-31 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7501, 7514, 7515 | Y | N |  |  | 70718 | 70717
70633B | Burke to Eagles Nest Ckt.02J Upgrades | Upgrade Ckt.02K Eagles Nest to West Columbia as a Hardening upgrade |  | Eagles Nest | West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:01 |  | 138 | 0 | 1.86 | 0 |  | Brazoria | Brazoria | Tier 4 | 22RPG037 | 2022-10-31 | 2022-11-22 | 2022-11-22 | 42430, 43380 | Y | N |  |  | 72451 | 70633
73352B | PH Robinson Area 138kV Upgrades | Upgrade Ckt.79F PH Robinson to Seabrook to HANNAH to HUNTER to increase thermal limits |  | PH Robinson | Seabrook | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42780, 42830, 42852, 48282 | Y | N |  |  | 73354 | 73352
73338B | Pythias (PYT) 138kV CNP Station for Second Division Solar (20INR0248) | Install one generator lead for new interconnection to DAMAZO / Second Division Solar |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43090, 113702 | Y | N |  |  | 88038 | 73338
73371C | BP24 Sub Upgrades | Upgrade Crosby to Danek Ckt.08G to increase thermal limits |  | Crosby | Danek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40390, 40396 | Y | N |  |  | 73374 | 73371
86009 | Expand ADLONG substation for XE Murat Storage (24INR0329) | Expand facilities at customer-owned ADLONG substation for XE Murat Storage (24INR0329). Utilize existing generator lead Eastgate to XE Murat Solar. |  | Eastgate | ADLONG | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40690, 113542 | Y | N |  |  | 86010 | 86009
49564 | Mantle: Construct New 345 kV Station | Mantle: Construct New 345 kV Station | TSP/Company Contact and In-Service Date Update | Mantle |  | Planned | 1035 - 1213 | AEP TCC | Tom Reynolds mlforcum@aep.com 918-599-2674 | 3774 TP2018166 | 2024-12-31 20:00 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8059, 8383, 8573, 80598 | Y | N |  |  | 49565 | 49564
75889 | Add_Wellborn_Load |  |  | Wellborn |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-01-01 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32895 | Y |  |  |  | 80379 | 75889
75887 | Add_SteepHollow_Load |  |  | Steep Hollow |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-01-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32879 | Y |  |  |  | 80378 | 75887
86782 | Add Dansk load serving substation | Cuts in new Dansk load serving station on existing Red Bluff to Danevang transmission line |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-01-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  | 2024-02-01 |  | 5546, 5549, 5588 | Y | N |  |  | 86783 | 86782
72037A | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | New 345kV Seabreeze (SEB) substation for generator interconnection to Tanglewood Solar (23INR0054). Loop Ckt.27B into Seabreeze substation to create new Ckt.27 DOW to Seabreeze to Oasis. |  | Seabreeze | DOW/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-01-15 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 43020, 43035 | Y | N |  |  | 87458 | 72037
72037B | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | Install generator lead from Seabreeze (SEB) substation to TANGLE (TNG) customer substation (23INR0054). |  | Seabreeze | TANGLE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-01-15 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43020, 113341 | Y | N |  | Cost included in main phase | 87459 | 72037
68179 | North Edinburg Red Gate | North Edinburg: Install 3 - 138 kV breakers. Re-terminate Falfurrias 138 kV Line. Terminate Redgate (STEC) 138 kV Line. | Contact Update | North Edinburg | Redgate (STEC) | Planned |  | AEP TCC | Curtis Brown jlsolis@aep.com 361-881-5574 |  | 2025-01-17 |  | 138 | 0.08 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8380, 88380 | Y |  |  |  | 68180 | 68179
70223 | LCRATSC_Mont_PilotGrove_TL_Overhaul | LCRA TSC will perform an overhaul on the 8-mile Mont ¿ Pilot Grove (T140) 138-kV transmission line. |  | Mont | Pilot Grove | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-01-24 |  | 138 | 0 | 8 | 0 |  | Lavaca | Lavaca | Tier 4 |  |  |  |  | 7234, 7235, 7249 | Y | Y |  |  | 70224 | 70223
68252 | Lobo: Line settings | Interconnect Guajillo to the Lobo 345 kV station | Contact Update | Lobo |  | Under Construction |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2025-01-30 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219, 163223 | Y |  |  |  | 68253 | 68252
85975 | Carrizo Springs Substation 69-kV Breaker Installation and Power Transformer Upgrade | Carrizo Springs Substation 69-kV Breaker Installation and Power Transformer Upgrade | [5 empty] | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2025-01-30 |  | 69 | 0 | 0 | 0 |  | Dimmit | Dimmit | Tier 4 | [5 empty] | Y |  | Install 69-kV breaker at R3021T fuse and replace existing power transformer with 25/33 MVA transformer. |  | 85976 | 85975
61224 | AEN_Decker_SH_ckt_1008__reconductor | Upgrade the 7.04 mile Decker to Sand Hill 138 kV transmission line (Ckt 1008) with bundled 795 ACSS Drake conductor rated for 3000 amps |  | Decker [9187] | Sandhill [9216] | Planned |  | AEN | Shirley Mathew shirley.mathew@austinener 512-322-6103 |  | 2025-01-31 |  | 138 | 0 | 7.04 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9187, 9216 | Y |  |  |  | 61225 | 61224
73895 | LCRATSC_Sunglow_Substation_addition | This project provides a point of interconnection for a new battery energy storage resource at a new 138-kV Sunglow Substation between LCRA TSC T627 and LCRA Rosita Creek Substation. |  | Sunglow |  | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-01-31 |  | 138 | 0 | 0 | 0 |  | Maverick |  | Tier 4 |  |  |  |  | 8260, 78015, 78016 | Y | N |  |  | 73896 | 73895
81345 | Adding McFarland |  |  |  |  | Planned |  | TCEC | Andrew Kutsar akutsar@tcectexas.com 817-444-3201 |  | 2025-01-31 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 79700 | Y |  |  |  | 81346 | 81345
69902B | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | Upgrade Ckt.71C TH Wharton to Zenith in order to increase thermal limits |  | TH Wharton | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-01-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44900, 45500 | Y | N |  |  | 78231 | 69902
47541 | Crane Circuit Breaker Addition | Provide transmission service to American Electric Power at Crane Substation. Adding one (1) breaker and associated equipment needed to connect the AEP-owned Crane to Kinnison 138-kV transmission line. |  | Crane Substation | Crane Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2025-01-31 02:00 |  | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 76615 | Y | N |  |  | 78402 | 47541
82829 | New Furhman Substation | Adds New Furhman switching station on Rayburn - Vanderbilt line for generator interconnect |  | Rayburn | Vanderbilt | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-02-01 |  | 138 | 0.84 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5502, 5506, 5584 | Y | N |  |  | 82830 | 82829
71935 | Upgrade Hondo Creek to Castroville to 138kV | Upgrade Castroville sub to 138kV and line from Hondo creek to Castroville |  |  |  |  | 71917 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-02-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | 22RPG022 |  |  |  | 5804, 5807, 5808, 5810, 5819, 5821 | Y |  |  |  | 73097 | 71935
50725 | Lean Clay 138 kV Switch | Construct a new 138 kV switch |  | Culberson | Sand Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8658 | 2025-02-15 |  | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 1097, 11078, 11086 | Y |  |  |  | 82894 | 50725
77827 | Reconductor TNMP Cottonwood to Oncor Lean Clay |  |  | Oncor Lean Clay (11078) | TNMP Cottonwood (38099) | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-02-15 |  | 138 | 0 | 0.33 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 11078, 38099, 38100 | Y |  |  |  | 87863 | 77827
76622 | Expand Peters 138kV substation for Walstrom BESS (22INR0540). | Expand Peters 138kV substation for Walstrom BESS (22INR0540). |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 |  | 138 | 0 | 0 | 0 |  | Austin | Austin | Tier 4 |  |  |  |  | 46220, 171382 | Y | N |  |  | 76623 | 76622
72029A | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ BESS (23INR0040) | Loop new CEHE 138kV substation Ashville (ASH) into Ckt.06F Garden Villas to Holmes to create new Ckt.06 Garden Villas to Ashville to Holmes |  | Ashville | Garden Villas | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42680, 42770, 47210 | Y | N |  |  | 87144 | 72029
50845 | Kinnison: Expand 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/Company Contact, In-Service Date Update | Kinnison |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2797 | 2025-02-28 |  | 138 | 0 | 0 | 130 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 6604, 6607, 6611, 60431, 60432 | Y | N |  |  | 65545 | 50845
50847 | Sage: Expand 69 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/Company Contact, In-Service Date Update | Sage |  | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2799 | 2025-02-28 |  | 69 | 0 | 0 | 0 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-06-21 |  | 6604 | Y | N |  |  | 50848 | 50847
76076 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild Las Cruces to Milo 138 kV line | Contact Update | Las Cruces | Milo | Planned | 1116 - 1294 | AEP TCC/ETT | William Lovelace jlsolis@aep.com 361-881-5574 | 3835 | 2025-02-28 |  | 138 | 0 | 2.4 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8112, 8918 | Y |  |  |  | 76077 | 76076
78459 | Peters 138kV Substation Expansion for Walstrom BESS (22INR0540) | Expand Peters 138kV substation for generator lead to WALSTR (WAL) / Walstrom BESS (22INR0540). |  | Peters |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 |  | 138 | 0 | 0 | 0 |  | Austin | Austin | Tier 4 | [5 empty] | Y | N |  |  | 78460 | 78459
70282 | New 138kV Brushy Creek Substation |  |  | Thompsons Creek | Snook | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-02-28 |  | 138 | 2.81 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32857, 32863, 32867 | Y |  |  |  | 70301 | 70282
72500 | Rio Lago - New 138kV Substation | Loop new 138kV substation into the existing 138kV Bandera to Verde Creek line and install 40MVA distribution transformer. The new substation will be located approximately 1.64 miles from Bandera substation (23INR0078) |  | Bandera | Verde Creek | Planned |  | BEC | Jhonatan Guerrero Rivera j.rivera@banderaelectric. 830-612-0048 |  | 2025-02-28 |  | 138 | 0.1 | 0 | 0 |  | Bandera | Bandera | Tier 4 |  |  |  |  | 7146, 7436, 7438 | Y | N |  |  | 72501 | 72500
72029B | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ BESS (23INR0040) | Install one generator lead from CEHE 138kV substation Ashville (ASH) to SUNLIT/Dori BQ BESS |  | Ashville | SUNLIT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 87145 | 72029
70660 | Plaza to Grant Ckt.08I Upgrade | Install parallel underground portion of Ckt.08I Plaza to Grant to increase thermal limits. |  | Plaza | Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 00:10 |  | 138 | 0 | 0.44 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47110, 47350 | Y | N |  |  | 70661 | 70660
51012 | Kinnison to Sage: Rebuild 69 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | TSP/ Company Contact, In-Service Date Update | Kinnison | Sage | Planned | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2823 | 2025-02-28 01:00 |  | 69 | 0 | 0.25 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-17 |  | 6604, 60431 | Y | N |  |  | 65555 | 51012
45501 | Eldorado Live Oak to Sonora: Rebuild 69 kV line | Rehab Eldorado Live Oak to Sonora 69 kV line |  | Eldorado Live Oak | Sonora | Planned | 982 - 1160 | AEP TNC | David Baker twang1@aep.com 918-599-2635 | 2769 | 2025-02-28 01:00 |  | 69 | 0 | 23.92 | 0 |  | Schleicher | Sutton | Tier 3 | 18RPG012 | 2018-12-18 | 2019-01-17 |  | 6054, 6498, 6503, 6505, 6509, 6510, 6513 | Y | N |  |  | 65530 | 45501
76918 | Primavera 138 kV: Construct new station | New station to serve Tesla load |  | Primavera |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023059 | 2025-03-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8003, 8518, 8749, 8921, 88747 | Y |  |  |  | 76919 | 76918
55873 | Upgrade Moore to Hondo Creek 138 kV line | Replace the 336 ACSR with 1020 ACCC conductor while keeping the existing structures that still meet our standards. |  | Moore | Hondo Creek | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-03-01 |  | 138 | 0 | 13.5 | 0 |  | Medina | Frio | Tier 2 | 19RPG021 | 2019-11-20 | 2020-05-21 |  | 5819, 5827 | Y | N | Field engineering is still occurring due to short timeline for this upgrade. Details may change. | Current plan is to upgrade the line using mostly existing structures. Detailed field engineering is underway and could change the plan. | 55874 | 55873
85965 | RGEC_Altuda 69-kV In-line_Breaker_Installation | Install 69-kV breaker between Alpine Switch and Persimmon Gap substation at Altuda substation. |  | Alpr2A (6665) | PrsmnGap2A (6669) | Planned |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2025-03-01 |  | 69 | 0 | 0 | 0 |  | Brewster | Brewster | Tier 4 | [5 empty] | Y |  |  |  | 85966 | 85965
76078 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild Mines Road to Milo 138 kV line | In-Service Date and Estimated Cost Update | Mines Road | Milo | Planned | 1116 - 1294 | AEP TCC/ETT | William Lovelace mlforcum@aep.com 918-599-2674 | 3835 | 2025-03-31 |  | 138 | 0 | 2.95 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8643, 8918 | Y |  |  |  | 76079 | 76078
80956 | Holly: 138 kV Breaker Replacement | Upgrade 138 kV bus tie breaker at the Holly 138 kV station | Contact Update | Holly |  | Planned | TP2023629 | AEP TCC | Brooks Dow deevans@aep.com 918-599-2938 |  | 2025-03-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8486 | Y | N |  |  | 80957 | 80956
70886 | Rebuild TinTop - Rio Colorado | Rebuild TinTop- Rio Colorado 795ACSR |  | Tin Top | Rio Colorado | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-04-01 |  | 69 | 0 | 15.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5563, 5569 | Y |  |  |  | 70887 | 70886
81354 | GSEC_9452_Add_Snodgrass_Sub | Adding new Snodgrass sub to connect to AEP's Juncus Station. | Add New Load and Sub |  |  | Planned |  | GSEC | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2025-04-01 |  | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 9452, 60002 | Y | Y |  |  | 81355 | 81354
70550 | Create_GP_Solar_POI_Bus | Created GP Solar POI bus. |  | Glen Pine | Explorer | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-04-01 |  | 138 | 0 | 0 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 6802, 6829, 6833 | Y |  |  |  | 72028 | 70550
73661 | New transformer (T2) at BPUB Palo Alto Substation | Adding load (T2) on bus 5965 Palo Alto. |  | BPUB Palo Alto 5965 |  | Planned |  | BPUB/BROWNSVILLE PUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2025-04-02 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 5965 | Y | N |  |  | 80506 | 73661
73663 | New transformer (T1) at BPUB Waterport Substation | BPUB new load T1 at bus 59450 |  | Waterport Substation (59450) |  | Planned |  | BPUB/BROWNSVILLE PUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2025-04-02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 59450 | Y | N |  |  | 80507 | 73663
76690 | Add Atchison POD | Add Atchison POD |  | Border Switch | Atchison | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8698 R8726 | 2025-04-15 |  | 138 | 7 | 0 | 0 |  | Loving | Loving | Tier 4 |  |  |  |  | 11089, 11189, 18670, 18672 | Y |  |  |  | 76691 | 76690
78183 |  |  |  | Henry | Henry | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-04-15 |  | 69 | 0 | 0 | 0 | 0,12 | Childress | Childress | Tier 4 |  |  |  |  | 740 | Y |  |  |  | 78184 | 78183
72576A | Lago Vista to Nameless Transmission Line Upgrade | Rebuild and upgrade Nameless to Lago Vista with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA). Final span of conductor and terminal equipment at Nameless will be upgraded to 440 MVA with ERCOT project #72576B. (Replaces ERCOT Project # 61277A) | 1/10/2023: Added information to clarify timing for final circuit rating upgrade. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2025-04-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70352, 70526 | Y | N |  |  | 72577 | 72576
61234 | Antler-Bergheim Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the T493 Antler to Bergheim 138-kV and T389 Bergheim to Hays Energy 345-kV 7.2-mile double-circuit transmission line by replacing the aging conductors from Antler to Bergheim substations. |  | Antler | Bergheim | Planned | 61406, 61358, 61392, 61350, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-04-16 |  | 345 | 0 | 7.2 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7043, 7170, 7171, 7770 | Y | N |  |  | 78331 | 61234
72882 | LCRATSC_Lockhart_Luling_69kV_TL_Overhaul | LCRA TSC will perform an overhaul on the 15.8-mile Lockhart – Luling (T157) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Lockhart | Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-04-25 |  | 69 | 0 | 15.83 | 0 |  | Caldwell | Caldwell | Tier 4 | 23RPG004 | 2023-02-24 | 2023-03-20 |  | 7215, 7218, 7220, 7223 | Y | N |  |  | 72883 | 72882
1275 | Hawkins to Gainesville | Hawkins to Gainesville |  | Hawkins | Gainesville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-04-28 |  | 69 | 0 | 6.72 | 80 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 705, 706, 707, 726, 33705, 33726 | Y |  |  |  | 67891 | 1275
45136 | CPSE_New Midtown Substation | New Mid Town substation looped into Comal St to Olmos transmission line. |  |  |  |  | S-0910 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0283 | 2025-04-29 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5096, 5311, 5325 | Y |  |  |  | 45137 | 45136
50900 | Mason to North Brady: Rebuild 69 kV line | Rehab Mason to North Brady 69 kV line | Contact Update | Mason | North Brady | Planned | 1046 - 1219 | AEP TNC | Chris Carroll twang1@aep.com 918-599-2635 | 2794 | 2025-04-30 |  | 69 | 0 | 30.24 | 0 |  | Mason | McCulloch | Tier 3 | 19RPG019 | 2019-10-01 | 2019-11-01 |  | 6006, 6381, 6393, 6406, 60386 | Y | N |  |  | 65550 | 50900
63924 | Quasar: Build New 345 kV Station | Interconnect Brass Fork Solar to the Clear Crossing to Coulomb 345 kV Line | In-Service Date and Estimated Cost Update | Quasar |  | Planned | 1138 - 1316 | ETT | Zach Lachiusa twang1@aep.com 918-599-2635 | 1883 | 2025-04-30 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60514, 60703, 60712 | Y | N |  |  | 63925 | 63924
45511 | Laredo to Del Mar: 138 kV Line Rebuild | Rebuild Laredo to Del Mar 138 kV Line | Estimated Cost Update | Laredo | Del Mar | Planned | 992 - 1170 | AEP TCC | William Lovelace mlforcum@aep.com 918-599-2674 | 3746 | 2025-04-30 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645 | Y | N |  |  | 65531 | 45511 | 2018-S4
81347 | Adding Crucis Substation | [6 empty] | TCEC | Andrew Kutsar akutsar@tcectexas.com 817-444-3201 |  | 2025-04-30 |  | 138 | 0 | 0 | 0 |  | Hood |  | Tier 4 |  |  |  |  | 79701 | Y |  |  |  | 81348 | 81347
80858 | Sterling City: Upgrade 69 kV Relays | Upgrade relays at the Sterling City 69 kV station on the Angora 69 kV terminal | Contact Update | Sterling City |  | Planned | TP2023887 | AEP TNC | Wade Weller twang1@aep.com 918-599-2635 |  | 2025-04-30 |  | 69 | 0 | 0 | 0 |  | Sterling |  | Tier 4 |  |  |  |  | 6435, 6484 | Y | N |  |  | 80859 | 80858
45174 | Ollin to LCRA Crane: Partial Build, Partial Rebuild, and Conversion | Build new Ollin 138 kV station; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage | Project Description, TSP Company Contact, and In-Service Date Update | Ollin | LCRA Crane | Planned | 939 - 1117 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 2767 | 2025-04-30 01:00 |  | 138 | 0.52 | 0 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6600, 6605, 6606, 6610, 6613, 6668, 6669, 60428, 60429, 60431, 60432, 60441, 76615 | Y | N |  |  | 65527 | 45174
45421 | McElroy to Sage: Rebuild 69 kV line | Build new Ollin 138 kV station with a 138/69 kV auto; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage |  | McElroy | Sage | Planned | 939 - 1117 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 2768 | 2025-04-30 01:00 |  | 69 | 0 | 1.99 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6604, 6607 | Y | N |  |  | 65529 | 45421
72651 | Add_Josephine_Load | [6 empty] | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 991, 6991 | Y |  |  |  | 76031 | 72651
80753 | LST_Claytonville to Camp Springs 138 kV line additions | LST_Claytonville to Camp Springs 138 kV line additions |  | Claytonville 138 |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68009, 68012 | Y |  |  |  | 80754 | 80753
76194 | Angstrom: Construct New 345 kV Terminal | Interconnect Pintail Pass BESS to the Angstrom 345 kV station | Contact Update | Angstrom |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2023132 | 2025-05-01 |  | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8249, 8956 | Y |  |  |  | 76195 | 76194
71879 | Update Ratings |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0939b | 2025-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5133, 5371 | Y |  |  |  | 71880 | 71879
70536 | New 138 kV Verde Circle Substation | New 138 kV Verde Circle Substation looping into existing 138 kV Westover Hills and VLSI line. |  |  |  | Planned | T-0316 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0971 | 2025-05-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5466, 5467, 5488 | Y |  |  |  | 70537 | 70536
65661 | Rebuild Wickett-Pyote 138 kV line |  |  | Wickett (but # 37981) | Pyote (bus # 38001) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-01 |  | 138 | 0 | 12.88 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37981, 38001 | Y |  |  |  | 65662 | 65661
71930 | Upgrade RIOHONDO to BURNS line | Upgrade RIOHONDO to BURNS line to be 478MVA capable |  | Rio Hondo | Burns | Planned | 7192671928 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-05-01 |  | 138 | 0 | 12.2 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5763, 8319 | Y |  |  |  | 71931 | 71930
81544 | GSEC_9466_Add_CampSprings_Sub | Add Big Country's Camp Springs Sub 9MW | ISD exceeds NMMS model load date |  |  | Planned |  | GSEC | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2025-05-01 |  | 138 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 9466, 68012 | Y |  |  |  | 81545 | 81544
73364 | CPSE_New_Omicron_Substation | [6 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5055, 5326, 5355 | Y |  |  |  | 73365 | 73364
71917 | Upgrade STEC castroville to Pearson to 138kV | Upgrade STEC Bader station to 138kV. Upgrade STEC Castroville to bader and bader to pearson to 138kV |  | 5808 | 5813 | Planned | 71935 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-05-01 |  | 138 | 0 | 10.51 | 0 |  | Medina | Medina | Tier 2 | 22RPG022 | 2022-08-08 | 2022-12-06 |  | 5802, 5804, 5810, 5811, 5813 | Y |  |  |  | 71918 | 71917
61392 | Bergheim-Fair Oaks Ranch Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T238 Bergheim to Fair Oaks 138-kV and T656 Bergheim to Kendall 345-kV 4.1-mile double-circuit transmission line by replacing the aging conductor. |  | Bergheim | Fair Oaks Ranch/Kendall | Planned | 61406, 61358, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-03 |  | 345 | 0 | 4.1 | 0 |  | Comal | Kendall | Tier 4 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7169, 7170, 7770 | Y | N |  |  | 61393 | 61392
70922 | LCRATSC_ChiefBrady_Georgetown_TL_Upgrade | LCRA TSC will upgrade T355 Chief Brady - Georgetown 138-kV transmission line to achieve a higher operational rating. |  | Chief Brady | Georgetown | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-05 |  | 138 | 0 | 3 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7343, 7366 | Y | N |  |  | 70923 | 70922 | 2023-SC17
72588A | Trading Post to Cedar Valley Storm Hardening |  |  | Trading Post | Cedar Valley | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2025-05-05 |  | 138 | 0 | 6.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70505, 70506 | Y | N |  |  | 72589 | 72588
45125 | Quintana Rd to South San Rebuild | Rebuild 1.3 miles of 138 kV transmission line form Quintana Rd substation to South San substation. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0271 | 2025-05-14 |  | 138 | 0 | 1.29 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-15 |  |  | 5350, 5385 | Y |  |  |  | 45126 | 45125
69552B | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 345 kV Switch, Autotransformers, and 345 kV Tie Lines to Limmer (LCRA) |  | Teal | Teal | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6165 | 2025-05-15 |  | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 3696, 7341, 13363, 13364, 25090 | Y |  |  |  | 88554 | 69552
81358 | Grindstone 138 kV Switch | Establish Grindstone 138 kV Switch |  | Grindstone Switch | Grindstone Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1754 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Palo Pinto | Palo Pinto | Tier 4 |  |  |  |  | 1569, 1571, 1575, 1592, 1599 | Y |  |  |  | 81359 | 81358
72007 | Ranger Camp 345/138/69 kV Switch | Construct a new 345/138/69 kV Switch to replace existing Morgan Creek Switch |  | Ranger Camp 345/138 kV Switch | Ranger Camp 345/138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3024 | 2025-05-15 |  | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1025, 1030, 1032, 1033, 1064, 1189, 1190, 1348, 1378, 10049, 10050, 10051, 10052, 10134, 11004, 11032, 11033, 11034, 11035, 11048, 11332, 11342, 11393 | Y |  |  |  | 81363 | 72007
78382 | Adds Capacitor Bank at White Dune | Adds Capacitor Bank at White Dune |  | White Dune |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8669 | 2025-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Winkler | Winkler | Tier 4 |  |  |  |  | 18692 | Y |  |  |  | 80906 | 78382
85959 | ¿¿SAN MARCOS – STRAHAN¿ ¿¿Transmission Line Upgrade¿ | LCRA TSC will upgrade T230 San Marcos - Strahan 138-kV transmission line to achieve a higher operational rating. |  | San Marcos (7192) | Strahan (7193) | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 1.25 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7192, 7193 | Y |  |  |  | 85960 | 85959
86043 | LCRA TSC will add a temporary Tap on T437 | This PMCR models the phase 2 cut-in of T437 Nueces Bay – Lon Hill with the second Saxet Hard Tap. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8441, 8452, 78568 | Y |  |  |  | 86044 | 86043
87758 | Badger 345 kV Switch | Establish Badger 345 kV Switch for Sypert Branch Solar |  | Badger | Badger | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6317 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3687, 3761, 13429 | Y |  |  |  | 87759 | 87758
76578 | Upgrade the Temple Pecan - Temple Elm 138 kV Double-Circuit Line | Upgrade the 5-mile Temple Pecan - Temple Elm 138 kV Double-Circuit Line |  | Temple Pecan Creek | Temple Elm Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6234 | 2025-05-15 |  | 138 | 0 | 10 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3420, 13662 | Y |  |  |  | 76579 | 76578 | 2023-NC61
71980 | Watermill 345 kV Switch | Rebuild the existing Watermill 345 kV Switch |  | Watermill |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4012 | 2025-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 |  |  |  |  | 2398, 2427, 2428, 2429, 2432, 2435, 2466, 2847, 2997, 3159, 12429 | Y |  |  |  | 76731 | 71980
73793 | LCRATSC_McCartyLaneEast_Zorn_TL_Storm_Hardening | Perform storm hardening on the 4.2 mile McCarty Lane - Zorn (T202) 138-kV transmission line. T202 is double-circuited with McCarty Lane - Beback - Zorn (T201) 138-kV transmission line. |  | McCarty Lane East | Zorn | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 8.58 | 0 |  | Hays | Guadalupe | Tier 4 |  |  |  |  | 7180, 7182, 7187 | Y | N |  |  | 73794 | 73793
76705 | Prairieland 345/138 kV Switch and 138 kV Line | Establish Prairieland 345/138 kV Switch and Prairieland – Quartz Sand 138 kV Line |  | Prairieland | Quartz Sand | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8632 | 2025-05-15 |  | 138 | 6 | 0 | 0 |  | Glasscock | Glasscock | Tier 2 |  |  |  |  | 1030, 1058, 1328, 11387, 18548, 18549, 18550, 18551, 18552 | Y |  |  |  | 81372 | 76705
66569 | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch |  | Mulberry Creek | Mulberry Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9022 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Jones | Jones | Tier 3 | 21RPG021 | 2021-12-17 | 2022-01-12 |  | 1435, 1459, 6235, 11420 | Y |  |  |  | 81422 | 66569
69345 | LCRATSC_Limmer_Substation_Addition | Construct a new LCRA TSC-owned Limmer Substation in the Hutto to Zorn 345 kV line approximately 3 miles east of Hutto. Limmer Substation will be installed initially as a five-breaker 345 kV breaker-and-a-half arrangement. |  | Zorn, Hutto | Limmer | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Williamson | Travis | Tier 3 | 22RPG027 | 2022-08-29 | 2022-09-27 |  | 3696, 7042, 7340, 7341 | Y | Y |  |  | 78338 | 69345
81383 | Edwards Tap - Sandhills Tap 138 kV Line Rebuild | Edwards Tap - Sandhills Tap 138 kV Line Rebuild |  | Odessa EHV | Wolf | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8528 | 2025-05-15 |  | 138 | 0 | 11.71 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 1102, 1103, 1110 | Y |  |  |  | 81384 | 81383
80546A | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Increase the maximum operating temperature the Hutto - Round Rock 138 kV Line |  | Hutto Switch | Round Rock Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2025-05-15 |  | 138 | 0 | 8.8 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 3664, 3666, 3667, 3668, 3670 | Y |  |  |  | 81498 | 80546 | 2023-SC17
78365 | Boggy Creek 138/69 kV Switch | Construct the new Boggy Creek 138/69 kV Switch |  | Boggy Creek | Boggy Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6295 | 2025-05-15 |  | 138 | 5 | 0 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 132, 3415, 3493, 3496, 3607, 3643, 3644, 3645, 3689 | Y |  |  |  | 81558 | 78365
78395 | LCRATSC Thompsonville switching structure replacement | Replace switching structure and load-serving power transformer at Thompsonville station. |  | Thompsonville |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | 1026926 | 2025-05-15 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 | [5 empty] | Y |  |  |  | 78396 | 78395
78371 | Richardson East Switch – Richardson Spring Creek 138 kV Line Section | Upgrade Richardson East Switch – Richardson Spring Creek 138 kV Line Section |  | Richardson East | Richardson Spring Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4402 | 2025-05-15 |  | 138 | 0 | 2.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2689, 2690 | Y |  |  |  | 78372 | 78371
82808 | Stranger 345 kV Switch | Establish Stranger 345 kV Switch |  | Stranger Switch | Stranger Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6320 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 3390, 3711, 3721 | Y |  |  |  | 82809 | 82808
82806 | Establish Long Hollow 345 kV Switch (POI for Pinnington Solar) | Establish Long Hollow 345 kV Switch (POI for Pinnington Solar) |  | Graham Plant Switch | Parker Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3509 | 2025-05-15 |  | 345 | 0 | 0 | 0 |  | Young | Parker | Tier 4 |  |  |  |  | 1430, 1436, 1506 | Y |  |  |  | 82807 | 82806
82810 | Olympus 138 kV Switch | Establish Olympus 138 kV Switch |  | Olympus Switch | Olympus Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6330 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3125, 3127, 3454, 3466, 3723 | Y |  |  |  | 82811 | 82810
82826 | Sunflower 138 kV Switch | Establish Sunflower 138 kV Switch |  | Sunflower Switch | Sunflower Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6322 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 170, 3592, 3722 | Y |  |  |  | 82827 | 82826
80913 | Sloan 138 kV Switch | Establish Sloan 138 kV Switch. |  | Midland Airport, Midland East | Midessa South | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8659 | 2025-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Midland | Midland | Tier 4 |  |  |  |  | 1059, 1124, 1138, 11137, 11138, 11143, 11165 | Y |  |  |  | 80955 | 80913
62666B | Upgrade and convert McGregor - Waco West Line | Rebuild McGregor Phillips - McGregor Phillips Tap 138 kV Line |  | McGregor Phillips | McGregor Phillips Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6172 | 2025-05-15 |  | 138 | 0 | 4 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3372, 3594 | Y |  |  |  | 87910 | 62666
87846 | Bradberry 138 kV Switch | Bradberry 138 kV Switch |  | Bradberry |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4015 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 3064, 3065, 3066 | Y |  |  |  | 87847 | 87846
87760 | Full House 138 kV Switch | Establish Full House 138 kV Switch for Lucky Bluff BESS |  | Full House | Full House | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6327 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 1636, 1641, 1652 | Y |  |  |  | 87761 | 87760
77648B | Establish Tiger Creek 345 kV Switch for Jaguar Solar/BESS | Tiger Creek Switch - Jaguar Solar/BESS 345 kV Line |  | Tiger Creek Switch | Jaguar Solar/BESS | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6223 | 2025-05-15 |  | 345 | 0.5 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 13401, 153783 | Y |  |  |  | 87809 | 77648
70538 | LCRATSC_PilotGrove_YoakumGartner_TL_Overhaul | Perform an overhaul on the 7.8 mile T614 Pilot Grove (structure #8/2) - Yoakum Gartner Road 138-kV transmission line. Structure #8/2 and the remaining portion of T614 will be overhauled as part of the FY23 Mont - Pilot Grove Transmission Line Overhaul project. |  | Pilot Grove | Yoakum Gartner | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Lavaca | DeWitt | Tier 4 |  |  |  |  | 7234, 7242 | Y | N |  |  | 70539 | 70538
70534 | LCRATSC_Hueco_Springs_Sub_Add | NBU is constructing a new 138-kV substation to serve a new residential development. LCRA TSC will provide transmission service to the new load serving substation on the T235 Henne to Comal. |  | Henne | Comal | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7174, 7176, 7179 | Y | N |  |  | 70535 | 70534
66188 | Cedar Crest - Dealey - West Levee 138 kV Line | Upgrade the existing 138 kV Line |  | Ceadr Crest | West Levee | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4212 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2400, 2493, 2842 | Y |  |  |  | 66189 | 66188
62643 | Rebuild Waco East 138 kV Switch | Rebuild Waco East 138 kV Switch |  | Waco East | Waco East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6146 | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3434, 3438, 3439, 3443, 3452, 3481, 3482, 3551, 3559, 3708, 13438 | Y |  |  |  | 62664 | 62643
62068 | Lakeway-Marble Falls Transmission Line Storm Hardening | Increase the reliability of transmission facilities on the T497 Lakeway ¿ Marble Falls 23-mile 138-kV transmission line. |  | Lakeway | Marble Falls | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Burnet | Tier 4 | 22RPG031 | 2022-10-12 | 2022-11-03 |  | 7348, 7349, 7351, 7356, 7474, 7476, 7538, 7540 | Y | N | 22RPG031 reclassified as Tier 4 neutral by RPG review on 11/03/2022 |  | 62069 | 62068
62448 | Rebuild Marlin 69 kV Switch | Rebuild Marlin 69 kV Switch |  | Marlin | Marlin | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1752 | 2025-05-15 |  | 69 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3418, 3638, 13639 | Y |  |  |  | 62658 | 62448
71199 | Yucca Drive - Moss 138 kV Line | Rebuild existing 138 kV line |  | Yucca Drive | Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9047 | 2025-05-15 |  | 138 | 0 | 35.2 | 0 |  | Ector | Winkler | Tier 4 |  |  |  |  | 1009, 1019, 11015, 11128, 18663 | Y |  |  |  | 76384 | 71199
71956 | LCRATSC_ElginSwitch_Substation_Addition | LCRATSC will install a new three-breaker ring bus substation at Elgin Switch. Oncor will relocate its facilities from Elgin Switch to Brushy Creek. Install a temporary shoo-fly between T668 and T260 to maintain through-path during construction. |  | Elgin Switch |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 3541, 3650, 7321, 7324, 7338 | Y | N |  |  | 73564 | 71956
72004 | Cat Claw 138 kV Dynamic Reactive Device (formerly Midkiff) | Install a new Dynamic Reactive Device at Cat Claw (formerly Midkiff) |  | Cat Claw | Cat Claw | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8675 R8680 R8695 | 2025-05-15 |  | 138 | 0 | 0 | 0 | -250250 | Upton | Upton | Tier 3 |  |  |  |  | 1210, 1217, 10058, 10059, 10060, 11218, 11345, 23870, 23871 | Y |  |  |  | 73345 | 72004
66200D | Upgrade Taylor - Holland 69 kV Line | Rebuild the Granger - Taylor 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6173 | 2025-05-15 |  | 69 | 0 | 5.9 | 0 |  | Williamson | Williamson | Tier 4 | 22RPG036 |  |  |  | 3644, 3645, 3646, 3648, 3649, 13646 | Y |  |  |  | 71897 | 66200
73838 | LCRATSC_Redwood_SanMarcos_TL_Upgrade | LCRA TSC will upgrade T200 Redwood - San Marcos 138-kV transmission line to obtain a higher operational rating. |  | Redwood | San Marcos | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7188, 7192 | Y | N |  |  | 73839 | 73838
87395 | LCRATSC_Caldwell_Substation_Addition | LCRA TSC will build a new substation, Caldwell Substation, to manage 12 MW of load in the summer of 2024. This substation will be on the Cooks Point - Lyle Wolz 138-kV transmission line. The new substation will be approximately 5 miles south of Cooks Point substation. LCRA will install circuit breakers in a ring bus formation |  | Caldwell | Caldwell | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2025-05-15 01:00 |  | 138 | 0 | 0 | 0 |  | Burleson | Burleson | Tier 4 |  |  |  |  | 7566, 7567, 7569 | Y | N |  |  | 87396 | 87395
80464 | McKenzie Road: Rebuild 138 kV Station | Interconnect the Bootstrap loads to the rebuilt McKenzie Road 138 kV station | Contact Update | Nueces | Nueces | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2023883 | 2025-05-16 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8520, 8545, 8858, 78568, 78569 | Y |  |  |  | 80465 | 80464
87861 | Range Rider - Ranger Camp 138 kV Double-Circuit Line | Construct a new 138 kV Double-Circuit Line from Range Rider to Ranger Camp Switch. |  | Ranger Camp 345/138 kV Switch | Range Rider 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8722 | 2025-05-16 |  | 138 | 1.2 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1032, 10050 | Y |  |  |  | 87862 | 87861
76274 | Hamilton Road: Construct New 138 kV Terminal | Interconnect Tierra Seca BESS to the Hamilton Road 138 kV station | Contact Update | Hamilton Road |  | Planned |  | ETT/AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023133 | 2025-05-18 |  | 138 | 0.1 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  |  | 8255, 8684, 8688, 8690 | Y |  |  |  | 76275 | 76274
48816 | Mulberry Creek: Rebuild 345 kV station | Rebuild Mulberry Creek 345 kV station and replace both autotransformers | Transmission Status Update | Mulberry Creek |  | Under Construction | 1015 - 1193 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 | 2776 | 2025-05-28 01:00 |  | 345 | 0 | 0 | 900 |  | Jones |  | Tier 4 | 21RPG021 | 2021-12-15 | 2022-01-13 |  | 1435, 1459, 6230, 6231, 6232, 6235, 11420, 60040, 60788, 60789 | Y | N |  |  | 65536 | 48816
67992C | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Looping of 345KV Howard Rd switching station into existing Cagnon to AVR and Cagnon to Spruce 34KV lies. The switching station will have 2 600MVA 345KV/138KV autotransformers. |  | 5056 | 5400 and 5475 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-29 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5056, 5230, 5231, 5400, 5475 | Y |  |  |  | 67993 | 67992
67992A | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Shepherd Rd to Valley Rd 138kV line Reconfiguration. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-29 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5230, 5378, 5465 | Y |  |  |  | 72403 | 67992
6719 | Twelvemile Substation Addition | Construct a new substation named Twelvemile off the Bakersfield to Schneeman Draw transmission line to support a generation interconnection request (16INR0104) |  | Bakersfield | Schneeman Draw | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018769 | 2025-05-30 |  | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 |  |  |  |  | 7053, 76008, 76015 | Y | N |  |  | 58408 | 6719
73408 | Odysseus: Build new 345 kV station | Interconnect Ulysses Solar to the Odysseus 345 kV Station on the Bluff Creek to SA Red Creek 345 kV line | In-Service Date Update | Odysseus |  | Planned |  | AEP TNC | Zach Lachiusa twang1@aep.com 918-599-2635 |  | 2025-05-30 |  | 345 | 0 | 0 | 0 |  | Coke |  | Tier 4 |  |  |  |  | 6444, 60040, 60072 | Y | N |  |  | 73409 | 73408
76574 | TexasAg Wind Interconnection | Interconnect TexasAg to the Brisita 345 kV station | Owner and Contact Update | Brisita |  | Planned |  | ETT | John Solis jlsolis@aep.com 361-881-5574 | TP2023129 | 2025-05-30 |  | 345 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8383, 8574, 8693, 88693 | Y |  |  |  | 76575 | 76574
69467 | Dupont to Resnik: Rebuild 138 kV Line | Rebuild the Dupont to Resnik 138 kV line | Contact Update | Dupont | Resnik | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-05-30 |  | 138 |  | 0.83 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8422, 8580 | Y |  |  |  | 69468 | 69467
70779 | Tortuga: Install Cap Bank | Install a 23.0 MVAR capacitor bank at the Tortuga 138 kV station | Description and Contact Update | Tortuga |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2022188 | 2025-05-30 |  | 138 | 0 | 0 | 0 | 0,23 | Nueces |  | Tier 4 |  |  |  |  | 8697 | Y |  |  |  | 70780 | 70779
50868 | Rosata - Structure 31/8: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown mlforcum@aep.com 918-599-2674 | 3780 | 2025-05-31 |  | 138 | 0 | 15.5 | 0 |  | Goliad | Karnes | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8153, 8186 | Y | N |  |  | 50869 | 50868
55572 | Burma to Sterling City: Rebuild 69 kV Line | Rehab the Burma to Sterling City 69 kV Line | In-Service Date Update | Burma | Sterling City | Under Construction | 1096 - 1274 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 | 1864 | 2025-05-31 |  | 69 | 0 | 32 | 0 |  | Tom Green | Sterling | Tier 3 | 20RPG021 | 2020-10-01 | 2020-11-01 |  | 6435, 6439, 6445, 6446, 6460, 6461, 60411, 61016, 61017 | Y | N |  |  | 55573 | 55572
67921 | Sisseton: Build 69 kV tap | Build new 69 kV tap on the Aspermont to Hamlin 69 kV line | Project Description and In-Service Date Update | Sisseton |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-05-31 |  | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6073, 6156, 6184, 6185, 6186, 6187, 60068 | Y |  |  |  | 67922 | 67921
67992D | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade,CPSE_Medina_to_36th_Street_Upgrade | Upgrade Hamilton to Medical Center 138KV Line to 469MVA |  | 5187 | 5300 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5187, 5300 | Y |  |  |  | 67994 | 67992
75856B | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. Loop into Ckt.06E to create new Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. | Convert ETHYL customer 69kV substation to 138kV. Loop into Ckt.06E to create new Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. |  | ETHYL | South Channel/Jefferson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40550, 41240, 41270, 41370, 41381, 41382 | Y | N |  |  | 87551 | 75856
75856A | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. Loop into Ckt.06E to create new Ckt.06 Jefferson to ETHYL 138kV to South Channel. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. |  | ETHYL | South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 69 | 1.33 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41240, 41370 | Y | N |  |  | 87552 | 75856
87889 | Install 2x 40 MVAR Cap bank at League City. |  |  | League City (38920) |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 | 0,80 | Galveston | Galveston | Tier 4 |  |  |  |  | 38920 | Y |  |  |  | 87890 | 87889
63922 | Tiki Island Distribution Upgrades | Install double-tap distribution service to Tiki Island. Existing tap will remain on Ckt.63E La Marque to Stewart. Tap Ckt.93C La Marque to West Galveston for the new tap section to Tiki Island. |  | Tiki Island | LaMarque/West Galveston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 42860, 43290, 43351, 43352, 43355, 43400, 48551, 48552, 48855 | Y | N |  |  | 87343 | 63922
78485D | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade portions of Ckt.05E Bellaire to Sharpstown to Hillcroft to increase thermal limits. |  | Bellaire | Hillcroft | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 6.41 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 48146, 48378, 48512 | Y | N |  |  | 78487 | 78485
73621A | Hawkinsville (HAW) CNP-Owned 345kV Substation for Lavaca Bay Solar (23INR0084) | New 345kV Hawkinsville (HAW) substation for generator interconnection to Lavaca Bay Solar. Loop Ckt.27D into substation to create new Ckt.27 Jones Creek to Hawkinsville to Refuge. |  | Refuge | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 1.4 | 0 | 0 |  | Matagorda | Brazoria | Tier 4 |  |  |  |  | 42400, 42440, 42530 | Y | N |  |  | 87138 | 73621
75938 | Expand Zenith substation with addition of 35kV Distribution Facilities. Tap TR1 on Ckt.09J to create new Ckt.09J Zenith to Zenith TR1 tap to Fry Road tap. Tap TR2 on Ckt.76A to create new Ckt.76A Zenith to Zenith TR2 tap to Fry Road tap. | Expand Zenith substation with addition of 35kV Distribution Facilities. Tap TR1 on Ckt.09J to create new Ckt.09J Zenith to Zenith TR1 tap to Fry Road tap. Tap TR2 on Ckt.76A to create new Ckt.76A Zenith to Zenith TR2 tap to Fry Road tap. |  | Zenith | Fry Road | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44910 | Y | N |  |  | 75939 | 75938
76234 | Wormser Road: Construct New 138 kV Terminal | Interconnect Seven Flags BESS to the Wormser Road 138 kV station | Contact Update | Wormser Road |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023311 | 2025-05-31 |  | 138 |  |  |  |  | Webb |  | Tier 4 |  |  |  |  | 8295 | Y |  |  |  | 76235 | 76234
73448 | Roma: Build new 138 kV terminal | Bordertown BESS interconnection to Roma Station on Roma Switch to Rio Grande City | In-Service Date Update | Roma |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 8795, 8796, 87960 | Y |  |  |  | 73449 | 73448
72065 | Lake Jackson Distribution Substation Conversion to Low-Profile | Rebuild Lake Jackson 138/12kV distribution substation to low-profile |  | Lake Jackson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42880, 43172 | Y | N |  |  | 72066 | 72065
72935 | Saragosa: Install 2nd Bay | Install 2nd Bay at Saragosa Substation | Contact Update | Saragosa |  | Planned |  | AEP TNC | Damian Raab twang1@aep.com 918-599-2635 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60716 | Y | N |  |  | 72936 | 72935
72880 | Sisseton: Build 69 kV station | Build 69 kV switch station on the Aspermont to Hamlin 69 kV line | Transmission Owner Project Number and In-Service Date Update | Sisseton |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TP2022059 | 2025-05-31 |  | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6073, 6156, 6184, 6185, 6186, 6187, 60068 | Y |  |  |  | 72881 | 72880
78495 | Hillje 345kV Substation Expansion for Space City Solar - Generator Interconnection (21INR0341) | Expand Hillje 345kV substation and install one generator lead for new interconnection to MIDANE customer substation for Space City Solar |  | Hillje | MIDANE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44200, 112261 | Y | N |  |  | 78496 | 78495
82321 | PMCR for 2nd TX in Coachwhip | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38170 | Y |  |  |  | 82322 | 82321
78490A | Jeanetta Auto Upgrades | Replace existing 600 MVA Jeanetta Auto A1 with 800 MVA autotransformer |  | Jeanetta |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 0 | 0 | 200 |  | Harris | Harris | Tier 3 |  |  |  |  | 47300, 47310, 49024 | Y | N |  |  | 79425 | 78490
80850 | Lon Hill to Sinton: Bypass Waterworks 69 kV station | Relocate portion of 69 kV line between Odem and Stevens Tap to bypass Waterworks 69 kV station | Contact Update | Odem | Stevens Tap | Planned | TA2022133 | AEP TCC | Travis Coody deevans@aep.com 918-599-2938 |  | 2025-05-31 |  | 69 | 0 | 0.45 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8810, 8865, 8867 | Y | N |  |  | 80851 | 80850
66221K | Galena Park Area Conversion Project | Rebuild GYPSUM customer substation for 138kV loop-tap service. Tap new GYPSUM substation (Spear Stone) from Ckt.94 between TANKER and new Galena Park tap to create new Ckt.94M CITFIL to Normandy tap to Galena Park tap to Spear Stone to TANKER |  | CITFIL | Tanker | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40590, 40612, 40630, 40731, 40739, 41172, 48130, 48402, 48613 | Y | N |  |  | 86753 | 66221
66221L | Galena Park Area Conversion Project | De-energize Ckt.20 Greens Bayou to GYPSUM. |  | Greens Bayou | GYPSUM | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40619, 40725, 40751, 48131 | Y | N |  |  | 86752 | 66221
71004A | Julia CNP-Owned Sub for Melaza Solar (21INR0220) | Install new Julia (JUL) CNP substation for generator interconnection to Maleza Solar. Loop Ckt.72 into Julia substation to create new Ckt.72 Hillje to Julia to Blue |  | Julia | Hillje/Blue | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44060, 44200, 44220 | Y | N |  |  | 87171 | 71004
78490B | Jeanetta Auto Upgrades | Replace existing 600 MVA Jeanetta Auto A3 with 800 MVA autotransformer |  | Jeanetta |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 0 | 0 | 200 |  | Harris | Harris | Tier 3 |  |  |  |  | 47300, 47310, 49082 | Y | N |  |  | 79426 | 78490
78485B | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.09A Britmoore to Hayes to Alief to increase thermal limits. |  | Britmoore | Alief | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 138 | 0 | 2 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 44020, 44120, 44310 | Y | N |  |  | 78488 | 78485
78490C | Jeanetta Auto Upgrades | Upgrade Ckt.25B Roark equipment and reconductor near Roark substation to increase thermal limits |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 |  | 345 | 0 | 0.04 | 0 |  | Harris | Harris | Tier 3 | [5 empty] | Y | N |  |  | 79427 | 78490
71004B | Julia CNP-Owned Sub for Melaza Solar (21INR0220) | Install generator lead from Julia (JUL) CNP substation to MALEZA/Maleza Solar |  | Julia | MALEZA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:01 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44220, 113251 | Y | N |  |  | 87172 | 71004
73621B | Hawkinsville (HAW) CNP-Owned 345kV Substation for Lavaca Bay Solar (23INR0084) | Install generator lead from Hawkinsville (HAW) substation to LAVACA / Lavaca Bay Solar. |  | Hawkinsville |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:01 |  | 345 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 | [5 empty] | Y | N |  |  | 87139 | 73621
73578C | Heights 138kV Loop Conversion | Convert Eureka to double-tap service. Tap Ckt.81J to create new Ckt.81J White Oak to Eureka TR1 tap to Wirt.Convert Eureka to double-tap service. Tap Ckt.09D to create new Ckt.09D San Felipe to Eureka TR2/TR3 tap to White Oak. Reconductor Ckt.09D Eureka TR2/TR3 tap to White Oak to increase thermal limits. Upgrade San Felipe line relaying Ckt.09D San Felipe to White Oak. |  | Wirt | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44656, 45750, 45751, 45752, 46615, 47382, 47685 | Y | N |  |  | 87298 | 73578
73578H | Heights 138kV Loop Conversion | Install 7.2MVAR cap bank at Dunlavy TR2. |  | Dunlavy |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:05 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47580 | Y | N |  |  | 87299 | 73578
73578I | Heights 138kV Loop Conversion | Install 7.2MVAR cap bank at Hyde Park TR2. |  | Hyde Park |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:05 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47690 | Y | N |  |  | 87301 | 73578
73578G | Heights 138kV Loop Conversion | Tap existing Ckt.90A Kirby to Garrott near Tower 34720 to serve Dunlavy transformer TR3 load. Create Ckt.90A Kirby tap to DN-TR3 tap to Garrott. |  | Kirby | Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:05 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47580, 47583, 47660, 48363 | Y | N |  |  | 87300 | 73578
66221G | Galena Park Area Conversion Project | Rebuild Galena Park substation for double tap service. Tap Galena Park TR2 on Ckt.21K between Fidelity and Witter. |  | Fidelity | Witter | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:06 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40590, 40610, 40611, 40612, 40630, 40710, 48402, 48610, 48613 | Y | N |  | Cost included in main entry | 86754 | 66221
79990 | Add new Yellow Wolf station for 21INR0428 |  |  | Limestone | Gibbons Creek | Under Construction |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2025-06-01 |  | 345 | 0 | 0 | 0 |  | Leon |  | Tier 4 |  |  |  |  | 967, 46020, 79007 | Y | N |  |  | 79991 | 79990
86319 | AEN_Garfield_HiCross_CKT_963_Reconductor | 138kV.Garfield_HiCross_CKT_963_Reconductor, replaces the existing ACSR with 795 ACSS conductor. |  | 9071 | 9147 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9071, 9147 | Y |  |  |  | 86320 | 86319
86325 | AEN_McNeil_Magnesium_Plant_Ckt_977_RECONDUCTOR |  |  | 9077 | 9238 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238 | Y |  |  |  | 86326 | 86325
81315 | add 19.2 MVAR Capacitor at Rossville | add 19.2 MVAR Capacitor at Rossville. 2023 RTP |  | Rossville |  |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-06-01 |  | 69 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5718 | Y |  |  |  | 87403 | 81315
80422 | Add_Triangle_Park_Load |  |  | Triangle Park |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32854 | Y |  |  |  | 80423 | 80422
11TPIT0011 | East_Village138kV Substation | East_Village 138kV Substation |  | Techridge | East_Village SUB |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9045, 9190, 9195 | Y |  |  |  | 13043 | 5357
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures. Kramer Lane (KA) substation will be cut-into this line in 2023 |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2025-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238, 9276 | Y | N |  | Will add the ptoject to the base case. | 8207 | 1031
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 3000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2025-06-10 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 9723 | 2443
44946 | CPSE_New_Scenic_Loop_138kV_Load_Serving_Station | The new Scenic Loop 138 kV load serving station will be looped into existing Ranchtown to LCRA (Menger Creek) 138 kV transmission line. The substation should be located south west of the existing Fair Oaks Ranch and north east of the existing Ranchtown substation. |  |  |  | Planned | S-0885 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0275 | 2025-06-13 20:00 |  | 138 | 9 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5358, 5363, 7665 | Y |  |  |  | 44947 | 44946
6253 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-06-26 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238, 9276 | Y |  |  |  | 13981 | 6253
72878 | LCRATSC_Leesville_Substation_Addition | This project provides a point of interconnection for a new 95 MW Solar Farm and 33 MW Battery Energy Storage System via a new 138-kV Leesville Substation on T605 between Deer Creek and LCRA Nixon substations. |  | Leesville | Leesville | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-06-30 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7595, 7599, 7621 | Y | N |  |  | 72879 | 72878
70192 | LCRATSC_Doss_Headwaters_TL_Overhaul | LCRA TSC will perform an overhaul on the 14.2-mile Doss ¿ Headwaters (T508) 69-kV transmission line. |  | Doss | Headwaters | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-06-30 |  | 69 | 0 | 14.2 | 0 |  | Gillespie | Gillespie | Tier 4 |  |  |  |  | 7408, 7410 | Y | Y |  |  | 70193 | 70192
70196 | LCRATSC_Kingsland1_SandyCreek_TL_Overhaul | LCRA TSC will perform an overhaul on the 7.3-mile Kingsland 1 ¿ Sandy Creek (T400) 69-kV transmission line. |  | Kingsland 1 | Sandy Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-06-30 |  | 69 | 0 | 7.3 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7121, 7400, 7404 | Y | Y |  |  | 70197 | 70196
70019 | Add 138kV Locust-Hickory line 700MVA |  |  | Locust | Hickory | Planned |  | DME | Mark Zimmerer 940-349-7169 |  | 2025-06-30 |  | 138 | 0 | 1.85 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 922, 924 | Y | N |  |  | 70020 | 70019 | N/A
64776 | Upgrade 138kV DentonWest-RDWells line to 700MVA (SUM2024) |  |  | RD Wells | Denton West | Planned |  | DME | Mark Zimmerer 940-349-7169 |  | 2025-07-01 |  | 138 | 0 | 4.47 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 930, 986 | Y | N |  |  | 64777 | 64776 | N/A
5430O | Conversion to 138kV | Reconnect the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2025-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 930 | Y | N | N/A |  | 55209 | 5430 | N/A
5430K | Conversion to 138kV | Construct new 138kV Hickory substation and terminate the existing Bonnie Brae - Hickory (which is already insulated for 138kV) at the new 138kV Hickory substation. |  | Bonnie Brae | Hickory | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2025-07-01 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 931 | Y | N | N/A |  | 55205 | 5430 | N/A
86736 | Royse Switch Sw (Guevara Storage) |  |  | Royse |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4008 | 2025-07-16 |  | 345 | 0 | 0 | 0 |  | Rockwall | Rockwall | Tier 4 |  |  |  |  | 2478, 153842 | Y | N |  |  | 86737 | 86736
87479I | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Hyde Park to Downtown Ckt.32A to increase thermal limits as part of FRM upgrades |  | Kirby | Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47321, 47660 | Y | N |  |  | 87821 | 87479
87479F | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Bellaire to Jeanetta Ckt.64B to increase thermal limits as part of FRM upgrades |  | Bellaire | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47000, 47300 | Y | N |  |  | 87822 | 87479
87479G | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Hyde Park to Downtown Ckt.32A to increase thermal limits as part of FRM upgrades |  | Hyde Park | Downtown | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47510, 47690 | Y | N |  |  | 87823 | 87479
87479H | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Stadium to Fannin Ckt.08B to increase thermal limits as part of FRM upgrades |  | Stadium | Fannin | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 87824 | 87479
87479E | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Jeanetta to WA Parish Ckt.64A to increase thermal limits as part of FRM upgrades |  | Jeanetta | WAP | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47300 | Y | N |  |  | 87825 | 87479
72942 | Bluff Creek: 138 kV Station Work | Replace fourteen (14) 138 kV Breakers and one (1) Circuit Switcher | In-Service Date Update | Bluff Creek |  | Planned |  | AEP TNC | Alex Perkins twang1@aep.com 918-599-2635 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6216, 6260, 6351, 60040, 60043, 66216, 66217, 180455, 180463 | Y | N |  |  | 72943 | 72942
87479D | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits as part of FRM upgrades |  | Bellaire | WAP | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47000 | Y | N |  |  | 87820 | 87479
87479C | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Ckt.06D NASA to Webster to increase thermal limits as part of FRM upgrades |  | NASA | Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42970, 43500 | Y | N |  |  | 87819 | 87479
69473 | Jaguar: Construct New Distribution Station | Construct new distribution station on the McGruder to Thomaston 138 kV line | Description and Contact Update | Jaguar |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2025-07-31 |  | 138 | 0 | 0 | 40 |  | Victoria |  | Tier 4 |  |  |  |  | 8183, 8194, 8724 | Y |  |  |  | 69474 | 69473
87479A | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits as part of FRM upgrades |  | PSARCO | BIGVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40190, 41305 | Y | N |  |  | 87817 | 87479
87479B | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Ckt.99A PH Robinson to Meadow to increase thermal limits as part of FRM upgrades |  | PH Robinson | Meadow | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Galveston | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 87818 | 87479
49550 | Port Isabel: Rebuild As GIS Station | Rebuild Port Isabel as a GIS | Contact Update | Port Isabel |  | Planned | 958 - 1136 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3716 | 2025-08-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  |  | 49551 | 49550
76624 | WA Parish 345kV Substation Expansion for Crowned Heron Storage (24INR0405) | Expand 345kV WA Parish substation for Crowned Heron Storage (24INR0405) |  | WA Parish | HERON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-08-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 44000, 114042 | Y | N |  |  | 76625 | 76624
88867 | Rosita Creek Substation 138-kV T2 Power Transformer Addition. Replacing Committed project 57343 | Add second 138/13.09-kV power transformer bay with new 138-kV transmission switch and circuit switcher interconnected at LCRA Switch# 12669. New power transformer capacity will be 15/20/25 MVA. Replaces committed project 57343. | Recent projected load increases beyond ALDR. Justification is to provide on-site backup power source for new and existing critical medical center, governmental and educational facility loads. Power transformer lead-time increases. |  |  | Planned |  | RGEC | Larry Powell lpowell@rgec.coop 830-563-6178 |  | 2025-09-01 |  | 138 | 0 | 0 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 78015 | Y |  |  |  | 88868 | 88867
75958 | add 19.2 MVAR Capacitor at Rio Colorado | Adds 2 9.6 MVAR step caps at Rio Colorado |  | Rio Colorado |  |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-09-01 |  | 69 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5563 | Y |  |  |  | 75959 | 75958
66210 | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV. Relocate the Lake Creek 138/69 kV Auto to Marlin. |  | Lake Creek | Marlin | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1743 | 2025-09-15 |  | 138 | 0 | 13.7 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3410, 3411, 3416, 3418, 3694, 3695, 13639 | Y |  |  |  | 66211 | 66210
66202A | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Palestine - Elkhart 69 kV Line |  | Palestine | Elkhart | Under Construction |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6182 | 2025-09-15 |  | 69 | 0 | 9.8 | 0 |  | Anderson | Anderson | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3273, 3285 | Y |  |  |  | 66203 | 66202
71950 | Twin Buttes Load 138kV Circuit Breaker Addition | Provide a 138-kV point of interconnection at the Twin Buttes Substation to connect to a new Golden Spread Electric Cooperative Transmission line. Update contingencies |  | Twin Buttes |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-09-16 |  | 138 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 | [5 empty] | Y | N |  |  | 78299 | 71950
59197 | Mason to Mason Switch: Rebuild 69 kV Line | Rehab the Mason to Mason Switch 69 kV Line | Contact Update | Mason | Mason Swicth | Planned | 1126 - 1304 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 | 1871 | 2025-09-30 |  | 69 | 0 | 10.3 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6393, 6394, 6396, 6407, 60458 | Y | N |  |  | 59198 | 59197
50878 | North Edinburg: 345 kV Reconfigure | Reconfigure the North Edinburg 345 kV station | Contact Update | North Edinburg |  | Planned | 1056 - 1229 | AEP TCC | Randy Weaver jlsolis@aep.com 361-881-5574 | 3786 | 2025-09-30 |  | 345 | 0 | 0 | 0 | -100,0 | Hidalgo |  | Tier 4 |  |  |  |  | 8341, 8383 | Y | N |  |  | 50879 | 50878
76139 | Juncus: Construct New 69 kV Station | Interconnect the Snodgrass load to the new Juncus 69 kV station on the Abilene South to Steamboat 69 kV line | Title, Description, and Contact Update | Juncus |  | Planned |  | AEP TNC | Bill Edwards twang1@aep.com 918-599-2635 | TA2023074 | 2025-09-30 |  | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6326, 6328, 60002 | Y | Y |  |  | 76140 | 76139
69890 | Bailey 345kV Substation Expansion for Ray Gulf Wind (22INR0517) | Expand 345kV Bailey substation for Ray Gulf Wind generator interconnection (22INR0517) |  | Bailey |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-09-30 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 | [5 empty] | Y | N |  |  | 69891 | 69890
80466 | Oleander: Construct New 138 kV Terminal | Interconnect Citrus Flatts BESS to the Oleander 138 kV station | Contact Update | Oleander |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2025-09-30 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 | [5 empty] | Y |  |  |  | 80467 | 80466
73067 | Marina: Construct New Station | Construct new network station on the Highway 9 to Morris St and Nueces Bay 138 kV lines | Contact and Circuit Miles Update | Marina |  | Planned |  | AEP TCC | Marc Wilson deevans@aep.com 918-599-2938 |  | 2025-09-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8064, 8441, 8470, 8474, 8620, 8623, 8733 | Y |  |  |  | 73068 | 73067
76214 | North Edinburg: 345 kV Reconfigure | Reconfigure North Edinburg 345 kV station: 2nd reactor | Contact Update | North Edinburg |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2019168 | 2025-09-30 |  | 345 | 0 | 0 | 0 | -50,0 | Hidalgo |  | Tier 4 |  |  |  |  | 5660, 8341, 8383, 8452, 8455, 8901, 8905 | Y |  |  |  | 76215 | 76214
70714 | LCRATSC_La_Cima_Substation_Addition | Add new substation to 138 kV line between Ranch Road 12 and Hill Top and install 46.7 MVA distribution transformer. The new substation will be located approximately 0.30 miles from Ranch Road 12 substation. |  | Ranch Road 12 | La Cima | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-10-01 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7185, 7186, 7190 | Y | N |  |  | 70715 | 70714
78627 | RCEC_SherwoodShores_AddCap |  |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6806 | Y |  |  |  | 78628 | 78627
70012 | West Weatherford to Oran Voltage Conversion | West Weatherford to Oran Voltage Conversion |  | West Weatherford | Oran | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-10-03 |  | 138 | 0 | 0.1 | 0 |  | Palo Pinto | Parker | Tier 4 |  |  |  |  | 515, 518, 519, 785, 1569, 1585, 1589 | Y |  |  |  | 70013 | 70012
80484 | Closner: Construct New 138 kV Terminal | Interconnect Gunnar BESS to the Closner 138 kV station. | Contact Update | Closner |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2025-10-18 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8029 | Y |  |  |  | 80485 | 80484
72344 | PALMETTO_CUTIN |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-10-23 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 39510, 110505 | N |  |  |  | 72345 | 72344
59959 | CPSE_New_Old_Hickory_Switchyard | Build a new Old Hickory 345 switchyard to connect Old Hickory Solar plant. |  | 5133 | 5915 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0303; S-0940 | 2025-10-24 20:00 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5133, 5323, 5915 | Y |  |  |  | 59960 | 59959
80852 | Lolita: Construct New 138 kV Terminal | Interconnect Third Coast BESS to the Lolita 138 kV station | Contact Update | Lolita |  | Planned | TP2023138 | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2025-10-30 |  | 138 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 8125 | Y | N |  |  | 80853 | 80852
87285 | Establish Stouts Creek 345 kV Switch | Establish Stouts Creek 345 kV Switch |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R984 | 2025-10-30 |  | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1696, 2514, 12464, 120972 | Y |  |  |  | 87286 | 87285
66122 | Tiempo: Build new 345 kV terminal | Interconnect Redonda Solar to the Tiempo 345 kV station | Contact Update | Tiempo |  | Planned |  | ETT | Adam Wells jlsolis@aep.com 361-881-5574 | TP2022009 | 2025-10-31 |  | 345 | 0.1 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 80224, 80232 | Y |  |  |  | 66511 | 66122
80486 | Loxley: Construct New 138 kV Station | Interconnect the Loxley load to the new Loxley 138 kV station on the Pleasanton to Trumbo 138 kV line | Contact Update | Loxley |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2025-10-31 |  | 138 | 0.1 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  |  | 5429, 8203, 80491 | Y |  |  |  | 80487 | 80486
70349 | Belknap to Fort Griffin: Rebuild 69 kV Line | Rehab Belknap to Fort Griffin 69 kV line | In-Service Date Update | Belknap | Fort Griffin | Planned |  | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 |  | 2025-10-31 |  | 69 | 0 | 23.6 | 0 |  | Jones | Shackelford | Tier 4 | 22RPG020 | 2022-06-27 | 2022-07-22 |  | 6178, 6210, 6214, 60398, 60409, 60445, 60466, 60471 | Y | N |  |  | 70350 | 70349
75776A | Samaritan 138kV Switching Station | In terms of completed Clute substation: Reconfigure Ckt.26 Angleton to Clute and loop into new CNP-owned 138kV Samaritan switching station to create new Ckt.26 Angleton to Samaritan to Clute. |  | Samaritan | Angleton/STRATT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42030, 42110, 43300 | Y | N |  |  | 87131 | 75776
64581A | New 138kV Waterfowl substation | Reconfigure existing Ckt.02F (move Seadoc/Seaway onto other circuit) resulting in Ckt.36 COPPER to Booster tap to Jones Creek. |  | COPPER | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 5568, 42195, 42199, 42215, 42540, 43211, 43212, 43221, 48006, 48007, 48039, 48333, 48334 | Y | N |  |  | 87023 | 64581
75810A | Install new 345kV Speedway substation for interconnection to Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. Install generator lead from Speedway to CRADLE solar | Install new 345kV Speedway (SPD) substation for generator interconnection to CRADLE/ Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. |  | Speedway | DOW/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 43035, 43060 | Y | N |  |  | 87165 | 75810
86013 | Fairmont Distribution Reconfigurations with 4th Transformer | Install fourth Fairmont distribution transformer on Ckt.95F to create new Ckt.95F SOUTH to Fairmont TR4 tap to Clear Lake tap to Polaris tap to Kemah tap to PH Robinson 138kV North. Remove Fairmont TR3 from Ckt.95F and onto the Ckt.35A Fairmont line position. |  | Fairmont |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42610, 42613, 42614, 48108, 742613 | Y | N |  |  | 87387 | 86013
78427A | Bohemian (BOH) 138kV CEHE Substation for Destiny Storage (24INR0397) | Install new CEHE 138kV Bohemian (BOH) substation for generator interconnection to Destiny Storage. Loop Ckt.66K into substation to create new Ckt.66 Crosby to Bohemian to Eastgate. |  | Bohemian | Crosby/ Eastgate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40390, 40690, 40970 | Y | N |  |  | 87352 | 78427
78480A | Weinbrenner (WEI) 138kV CEHE Station for LONGPO (LNP) / Long Point Solar 19INR0042 | Loop new CEHE 138kV substation Weinbrenner (WEI) into Ckt.02J Burke to Eagle Nest to create new Ckt.02 Burke to Weinbrenner to Eagle Nest. |  | Weinbrenner | Burke/ Eagle Nest | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42410, 42430, 42990 | Y | N |  |  | 87161 | 78480
72059 | Hillje 345kV Substation Expansion for Ramsey Storage - Generator Interconnection to FLATLA (FLA) (21INR0505) | Expand Hillje 345kV substation and install one generator lead for new interconnection to FLATLA (FLA) customer substation for Ramsey Storage |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44200, 113595 | Y | N |  |  | 72060 | 72059
76151 | Gas Pad Tap: Replace CTVT | Replace CTVT combination unit at Gas Pad station along the Lote Bush to Yucca Drive 138 kV line | Contact, In-Service Date, and Cost Update | Gas Pad Tap |  | Planned |  | AEP TNC | Bill Edwards twang1@aep.com 918-599-2635 |  | 2025-10-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 11245, 60397 | Y | N |  |  | 76152 | 76151
75810B | Install new 345kV Speedway substation for interconnection to Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. Install generator lead from Speedway to CRADLE solar | Install generator lead from Speedway (SPD) substation to CRADLE (CDL) customer substation (23INR0150). |  | Speedway | CRADLE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 87164 | 75810
64581B | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Reconfigure existing Ckt.02F and install new conductor to create new Ckt.02 Jones Creek to Waterfowl |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 42540, 43470 | Y | N |  | Cost included in main entry | 87024 | 64581
78427B | Bohemian (BOH) 138kV CEHE Substation for Destiny Storage (24INR0397) | Install generator lead from Bohemian (BOH) substation to Rhapsody / RHAPSO (RHA) / Destiny Storage |  | Rhapsody | Bohemian | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40970, 113861 | Y | N |  |  | 87353 | 78427
75776B | Samaritan 138kV Switching Station | Connect Samaritan CNP substation with two leads to TNMP_White Oak distribution substation. |  | Samaritan | Angleton/Clute | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39580, 42030 | Y | N |  |  | 87132 | 75776
78480B | Weinbrenner (WEI) 138kV CEHE Station for LONGPO (LNP) / Long Point Solar 19INR0042 | Install one generator lead from CEHE 138kV substation Weinbrenner (WEI) to LONGPO (LNP) / Long Point Solar (19INR0042) |  | Weinbrenner | LONGPO | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 87162 | 78480
64581C | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Convert customer-owned Seadoc and Seaway substations to loop service. Reconfigure existing Ckt.02F and reconnect Seadoc/Seaway to create new Ckt.02x Jones creek to Seadoc to Seaway to Waterfowl. |  | Jones Creek | Waterfowl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 42540, 43211, 43222, 43470, 48007 | Y | N |  | Cost included in main entry | 87025 | 64581
64581D | New 138kV Waterfowl substation | Install new CNP-owned 138kV Waterfowl (WTR) substation. Remove existing Seaway Switchrack. Reconfigure existing Ckt.02F to create new Ckt.02y Waterfowl to Franklins Camp. |  | Waterfowl | Franklins Camp | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 5568, 43470 | Y | N |  | Cost included in main entry | 87026 | 64581
80508 | Kilby: Construct New 345 kV Station | Interconnect Quantum Solar to the new Kilby 345 kV station on the Clear Crossing to Pendulo 345 kV line | Contact Update | Kilby |  | Planned | TP2023844 | ETT | Dave Goetz twang1@aep.com 918-599-2635 |  | 2025-11-01 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60089, 60507, 60514 | Y | N |  |  | 80509 | 80508
61406 | Kendall-Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T584 Kendall to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 10.2-mile double-circuit transmission line by replacing the aging conductor. |  | Kendall | Welfare | Planned | 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-11-07 |  | 138 | 0 | 10.2 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7152, 7153, 7770 | Y | N |  |  | 78330 | 61406
61404 | Boerne Split-Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T228 Boerne to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 7.3-mile double-circuit transmission line by replacing the aging conductor. |  | Boerne, Bergheim | Welfare, Kendall | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-11-14 |  | 345 | 0 | 7.3 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7153, 7168, 7770 | Y | N |  |  | 78327 | 61404
78167 | Add 2nd autotransformer at Trumbull | Add 2nd autotransformer at Trumbull |  | Trumbull | Trumbull | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-11-15 |  | 69 | 0 | 0 | 40 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 221, 222 | Y |  |  |  | 78168 | 78167
73359 | Vertrees: Construct New Distribution Station | Construct new distribution station on the Stewart Road to Weslaco Unit 138 kV line | Contact Update | Vertrees |  | Planned |  | AEP TCC | Travis Coody jlsolis@aep.com 361-881-5574 |  | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8348, 8662, 8737, 8951 | Y |  |  |  | 73360 | 73359
72566 | Cedar Valley to Friendship Storm Hardening | Rebuild single circuit section of Cedar Valley to Friendship and reconductor with bundled 795 ACSR Conductor, 440 MVA. Replaces Project ID 61268 |  | Cedar Valley | Friendship | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-11-30 |  | 138 | 0 | 4.3 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70506, 70507 | Y | N |  |  | 72567 | 72566
61394 | Portilla: Construct New Distribution Station | Construct new distribution station on the Lon Hill to Warburton 138 kV line | In-Service Date Update | Portilla |  | Planned |  | AEP TCC | Damian Raab mlforcum@aep.com 918-599-2674 | DP21X0008 | 2025-11-30 |  | 138 | 1.5 | 0 | 0 | 0,14.4 | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8020, 8027, 8046, 8920, 8924 | Y |  |  |  | 61395 | 61394
78471 | WA Parish 345kV Substation Expansion for Bypass Storage (23INR0336) | Expand 345kV WA Parish substation for Bypass Storage (23INR0336) |  | WA Parish | BYPASS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 44000, 113801 | Y | N |  |  | 78472 | 78471
80482 | North McAllen: Construct New 138 kV Terminal | Interconnect Carambola BESS to the North McAllen 138 kV station | Contact Update | North McAllen |  | Planned | TP2023631 | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8632 | Y |  |  |  | 80483 | 80482
82851 | Adds TNMP White Oak Substation |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39580 | Y |  |  |  | 82852 | 82851
87475 | [5 empty] | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2145, 6861 | Y |  |  |  | 87476 | 87475
70880 | Rebuild Carancahua -TinTop | Rebuild Carancahua to TinTop with 795ACSR |  | Carancahua | Tin Top | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 69 | 0 | 12.93 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5569, 5570, 5571, 5573 | Y |  |  |  | 70881 | 70880
76788 | Upgrade Victoria-Rayburn | Upgrade Victoria- Loop 463- Rayburn to 403 MVA |  | Rayburn | Victoria | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 138 | 0 | 11.57 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5502, 5680, 8172 | Y |  |  |  | 76789 | 76788
70299 | New Holleman Substation | [6 empty] | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 32005, 32892, 32893 | Y |  |  |  | 88269 | 70299
71926 | Upgrade BURNS to Heidelberg line | Upgrade BURNS to Heidelberg line to be 478MVA capable |  | Burns | Heidelberg | Planned | 7192871930 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 |  | 138 | 0 | 10 | 0 |  | Cameron | Hidalgo | Tier 4 |  |  |  |  | 5763, 5765 | Y |  |  |  | 71927 | 71926
62666C | Upgrade and convert McGregor - Waco West Line | Waco West - McGregor Phillips 138 kV Operation |  | Waco West | McGregor Phillips | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6172 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3370, 3372, 3436, 3437, 3440, 3441, 3446, 3562, 3584, 3585, 3586, 3596, 13436, 13438 | Y |  |  |  | 87911 | 62666
88035 | Construct a new 138 kV Switch | Construct a new 138 kV Switch |  | McDonald Road | Catclaw/Mudstone | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8817 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 1225, 1333, 10121, 11222 | Y |  |  |  | 88040 | 88035
87830 | Oncor_FW__Blue Mountain 138 kV Capactior Bank | [6 empty] | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2025-12-15 |  | 138 | 0 | 0 | 0 | 0,110.4 |  |  | Tier 4 |  |  |  |  | 18680 | Y |  |  |  | 87831 | 87830
66289B | Tyler to Athens 138 kV line Conversion | Establish Foggle Switch, Establish Poynor POI, Echols to Athens 69 kV Line Upgrade |  | Athens | Echols | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6094 | 2025-12-15 |  | 69 | 0 | 0 | 0 |  | Henderson | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3108, 3126, 3232, 3233, 3238, 3239, 3248, 3256, 3269, 3288, 3801 | Y |  |  |  | 87815 | 66289
72009 | Cattleman 345/138 kV Switch | Construct a new 345/138 kV Switch to replace existing Morgan Creek Switch |  | Cattleman | Cattleman | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8647 | 2025-12-15 |  | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 1058, 10053, 10054, 10055, 10056, 11395, 18548 | Y |  |  |  | 81376 | 72009
81223 | Range Rider 138 kV Switch | Construct a new 138 kV switch replacing existing Range Rider 138 kV Switch. |  | Range Rider 138 kV Switch | Range Rider 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8721 | 2025-12-15 |  | 345 | 0 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1032 | Y |  |  |  | 81367 | 81223
78367 | Montfort Switch-Shankle Switch 138 kV Line | Rebuild Montfort Switch - Shankle Switch 138 kV Line |  | Montfort | Shankle | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4002 | 2025-12-15 |  | 138 | 0 | 18 | 0 |  | Navarro | Ellis | Tier 3 |  |  |  |  | 192, 2330, 2331, 3454, 12329 | Y |  |  |  | 78368 | 78367
81175 | Salt Flat Road 138 kV Switch and Salt Flat Road - Barr Ranch - Reiter 138 kV Second Circuit | Add Salt Flat Road 138 kV Switch and Salt Flat Road - Barr Ranch - Reiter 138 kV Second Circuit |  | Reiter | Salt Flat Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8704 | 2025-12-15 |  | 138 | 44 | 4.4 | 0 |  | Ector | Midland | Tier 3 |  |  |  |  | 1027, 1111, 1193, 1234, 1276, 11111, 11217, 11235, 11344, 18545, 18701, 23859 | Y |  |  |  | 87224 | 81175
86633 | Dusty Road 345 kV Switch | Establish Dusty Road 345 kV Switch |  | Tonkawa | Graham | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8809 | 2025-12-15 |  | 345 | 0 | 0 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  |  | 1048, 1430, 11050 | Y |  |  |  | 86634 | 86633
66214 | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV |  | Brownwood | Firerock | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6164 | 2025-12-15 |  | 138 | 0 | 15.5 | 0 |  | Brown | Brown | Tier 4 |  |  |  |  | 1662, 1670, 1671, 6408 | Y |  |  |  | 66215 | 66214
70900C | Roanoke Area Upgrades | Establish Exchange - Kingsridge 138 kV Double-Circuit Line |  | Exchange Switch | Kingsridge Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2025-12-15 |  | 138 | 3.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 12033, 12036, 12080, 12081 | Y | N |  |  | 87468 | 70900
76650 | Establish Walleye Creek 345/138 kV Switch | Establish Walleye Creek 345/138 kV Switch |  | Walleye Creek | Walleye Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6243 | 2025-12-15 |  | 345 |  | 4.5 | 600 | 0,110.4 | Milam | Milam | Tier 3 |  |  |  |  | 116, 3541, 3712, 3713, 3714, 3715, 3716, 3717, 3742, 7040, 13429, 13430 | Y |  |  |  | 76651 | 76650
78363 | Gunter 345/138 kV Switch | Establish Gunter 345/138 kV Switch |  | Gunter |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3301 | 2025-12-15 |  | 345 | 0 | 0 | 600 | 75,0 | Collin |  | Tier 3 |  |  |  |  | 1730, 2235, 2236, 2373, 11735, 11757, 12235, 12468 | Y |  |  |  | 78364 | 78363
78357 | Wilmer 345/138 kV Switch | Establish Wilmer 345/138 kV Switch |  | Wilmer |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4369 M4371 M4372 | 2025-12-15 |  | 345 | 0 | 0 | 1200 | 0,220.8 | Dallas |  | Tier 1 |  |  |  |  | 2261, 2342, 2344, 2427, 2429, 2432, 2967, 3083, 3084, 3085, 13082, 23082, 60017 | Y |  |  |  | 78373 | 78357
81060 | Riverton-Border-Quarry Field 138 kV Second Circuit | Riverton-Border-Quarry Field 138 kV Second Circuit |  | Riverton | Quarry Field | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8733 | 2025-12-15 |  | 138 | 29.7 | 0 | 0 |  | Reeves | Loving | Tier 4 |  |  |  |  | 11083, 11089, 11189, 18672, 18677 | Y |  |  |  | 87856 | 81060
87799 | Old Country 345 kV Switch | Old Country 345 kV Switch |  | Old Country |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4172 | 2025-12-15 |  | 345 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 1907, 2255, 68091 | Y |  |  |  | 87800 | 87799
80546B | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild and double-circuit the Round Rock Westinghouse Tap - Georgetown East 138 kV Line Section |  | Round Rock Westinghouse Tap | Georgetown East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2025-12-15 |  | 138 | 9.1 | 9.1 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 3664, 3669, 3677, 7528, 7532 | Y |  |  |  | 87619 | 80546 | 2023-SC17
70900E | Roanoke Area Upgrades | Establish Ramhorn Hill 345 kV Switch and Ramhorn Hill – Dunham 345 kV Double-Circuit Line |  | Dunham Switch | Ramhorn Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2025-12-15 |  | 345 | 36.8 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 1421, 2081, 21851, 31875 | Y | N |  |  | 87470 | 70900
70900D | Roanoke Area Upgrades | Establish Dunham 345 kV Switch |  | Dunham Switch | Dunham Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2025-12-15 |  | 345 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 646, 1730, 1849, 21851, 33646 | Y | N |  |  | 87469 | 70900
62445 | Base Camp (FKA Eagle Mountain) 138kV Switch Rebuild | Rebuild existing 138 kV Switch |  | Base Camp | Base Camp | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5261 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 568, 1859, 1860, 1864, 1865, 11859, 11860, 11861, 11864, 11865, 11866, 12065 | Y |  |  |  | 70920 | 62445
81389 | Sandhills Tap - Wolf 138 kV Line Rebuild | Sandhills Tap - Wolf 138 kV Line Rebuild |  | Odessa EHV | Wolf | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8528 | 2025-12-15 |  | 138 | 0 | 14.2 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 1013, 1103, 11018 | Y |  |  |  | 87113 | 81389
66190 | East Levee - Industrial Blvd 138 kV DCKT Line | Rebuild East Levee - Industrial Blvd 138 kV DCKT Line |  | East Levee | Industrial | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4213 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2481, 2482, 2874, 2875, 2876, 2974, 2976 | Y |  |  |  | 66191 | 66190
62434 | Sargent Road - Industrial Blvd 138 kV DCKT Line | Upgrade existing 138 kV Line |  | Sargent Road Switch | Industrial Blvd Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4128 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2940, 2947, 2972, 2973, 2974, 2975 | Y |  |  |  | 62435 | 62434
5475 | Lufkin Switch - Redland Switch 345 kV Line | Construct a new 345 kV Line from Lufkin Switch to Redland Switch |  | Lufkin Switch | Redland Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6077 | 2025-12-15 |  | 345 | 8.1 | 0 | 0 |  | Angelina | Angelina | Tier 2 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3117, 3321 | Y | N |  |  | 13180 | 5475
66473 | Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line | Upgrade the Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line |  | Mesquite East | Oates | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4137 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 831, 2742, 2747, 2756, 2764, 2765, 2766, 2767 | Y |  |  |  | 66475 | 66473
71178 | Seagoville-Watermill 138 kV Line | Rebuild Seagoville-Watermill 138 kV Line |  | Seagoville | Watermill | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4081 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 |  |  |  |  | 2429, 2434, 3076, 3077, 3079, 3083 | Y |  |  |  | 71179 | 71178
76135 | Hackberry Switch – DFW D-East 2 138 kV DCKT Line Section | Rebuild Hackberry Switch – DFW D-East 2 138 kV DCKT Line Section |  | Dallas | Dallas | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4347 M4357 | 2025-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 | 23RPG020 |  |  |  | 1996, 1997, 2001, 2010, 2388, 15020, 15021, 15025, 15026, 15045, 15046 | Y |  |  |  | 76136 | 76135 | 2022-NC6
77624 | Wallaby Switch 345 kV Switch | Establish Wallaby Switch 345 kV Switch |  | AJ Swope | Windmill | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3021 | 2025-12-15 |  | 345 | 0 | 0 | 0 |  | Deaf Smith | Deaf Smith | Tier 4 |  |  |  |  | 23906, 23909, 23910 | Y |  |  |  | 77627 | 77624
66492A | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Jacksboro Amoco - Jacksboro Sinclair 69 kV Line |  | Jacksboro Sinclair | Jacksboro Amoco | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3006 | 2025-12-15 |  | 69 | 0 | 14 | 0 |  | Jack | Jack | Tier 4 |  |  |  |  | 1542, 1555, 1556, 1557, 1558, 11556 | Y |  |  |  | 72962 | 66492
72596C | PEC_MarshallFord_Paleface_StormHardening | Upgrade to terminal equipment and update to final circuit rating. Terminal end equipment update to be completed Fall 2024 based on original project schedule. (Replaces ERCOT Project # 61274C) | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC/LCRATSC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-15 |  | 138 | 0 | 11.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  |  | 73445 | 72596
75255F | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5260, 5385 | Y |  |  |  | 75960 | 75255
81274 | Ranger Camp – Cattleman 345 kV Double-Circuit Line | Construct a new 345 kV double-circuit line from Ranger Camp to Cattleman |  | Ranger Camp | Cattleman | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8648 | 2025-12-16 |  | 345 | 6.8 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 10053 | Y |  |  |  | 81275 | 81274
72579A | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Mountain Top to Blanco 69 kV circuit to 138 kV with bundled 795 kcmil conductor (440 MVA). (Replaces ERCOT Project # 70367A) |  | Mountain Top | Blanco | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-19 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 7148, 70480, 70482, 70484 | Y | Y |  |  | 72580 | 72579
72574 | topo_update | Upgrade Junction from tap station to a three terminal ring bus. Replaces Project ID 63916. |  | NEW JUNCTION 70600 |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-25 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70600 | Y |  |  |  | 80916 | 72574
70305 | Camp Elizabeth: Build new 69 kV station | Construct new 69 kV box bay station with capacitor bank on the College Hills West to Sterling City 69 kV line | Schedule Update | Camp Elizabeth |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-12-30 |  | 69 | 0 | 0 | 0 | 0,7.7 | Sterling |  | Tier 4 |  |  |  |  | 6417, 6435, 6436, 6641, 11352 | Y | N |  |  | 70306 | 70305
81270 | Construct the new Prong Moss 345 kV switch | Construct a new 345 kV switch |  | Prong Moss | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2025-12-30 |  | 345 | 0 | 0 | 0 |  | Howard | Howard | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1025, 10049, 10057, 10062 | Y |  |  |  | 81271 | 81270
73332 | Install Hermann (HER) Distribution Substation | Install Hermann (HER) Distribution Substation. Loop on Ckt.08I to create new Ckt.08 Plaza to Hermann to Grant. |  | Hermann | Plaza/Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45120, 47110, 47350 | Y | N |  |  | 87181 | 73332
75830A | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). | Loop Ckt.27 into Savannah substation to create new Ckt.27 Seabreeze to Savannah to Oasis. |  | Savannah | Seabreeze/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 43020, 43035, 43180 | Y | N |  |  | 87166 | 75830
82250 | PMCR for PILOT POINT NEW STATION | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2236, 37365 | Y |  |  |  | 82251 | 82250
76350 | Install new TARGA 138kV customer substation as Ckt.86 Jordan to TARGA to CITIES. | Install new TARGA 138kV customer substation as Ckt.86 Jordan to TARGA to CITIES. |  | TARGA | Jordan/CITIES | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40340, 40855, 40950 | Y | N |  |  | 87180 | 76350
86015 | King Substation - Add 3rd Distribution Transformer | Install the third King distribution transformer. Tap on Ckt.86E to create new Ckt.86E Newport to King tap to Jonte. |  | King | Newport/Jonte | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40912, 41150, 45660, 48182 | Y | N |  |  | 86016 | 86015
75788 | This project will intercept the second circuit of a common tower at Reata station. | This project will intercept the second circuit of a common tower at Reata station. |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | Eastland | Eastland | Tier 4 |  |  |  |  | 68008, 68011, 68051 | Y |  |  |  | 75789 | 75788
73123 | LCRATSC_SimGideon_Swiftex_TL_Upgrade | LCRA TSC will upgrade T608 Sim Gideon - Swiftex 138-kV transmission line to achieve a higher operational rating. |  | Sim Gideon | Swiftex | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-12-31 |  | 138 | 0 | 10 | 0 |  | Bastrop | Bastrop | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 7310, 7319, 7326 | Y | N |  |  | 73124 | 73123 | 2023-SC15
70307 | BRYN_Standard_PMCR_Dansby_Rebuild_fix | Reference Project 4577 Dansby Rebuild. Project 4577 was added to convert Dansby 69kV bus to Breaker and a Half configuration. |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-12-31 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  |  | 32875, 32897 | Y |  |  |  | 75508 | 70307
73059 | Barrera: Construct New Distribution Station | Construct new distribution station on the North Laredo Switch to Reveille 138 kV line | Contact and In-Service Date Update | Barrera |  | Planned |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8108, 8612, 8619, 8627, 8717, 8909 | Y |  |  |  | 73060 | 73059
73065 | Magana Hein: Build new 138 kV distribution station | Construct new distribution station on the Molina to Wormser Road 138 kV line | Contact Update | Magana Hein |  | Planned |  | AEP TCC | Travis Coody jlsolis@aep.com 361-881-5574 |  | 2025-12-31 |  | 138 | 2.6 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8295, 8641, 8646, 8801, 80230 | Y |  |  |  | 73066 | 73065
72868 | LCRATSC_Benedum_CB_Addition | This project provides a point of interconnection for a new 307.46 MW Battery Energy Storage at the 138-kV Benedum Substation by adding a connection to the ring bus to accommodate the new interconnection. Update contingencies |  | Benedum |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-12-31 |  | 138 | 0.1 | 0 | 0 |  | Upton |  | Tier 4 | [5 empty] | Y | N |  |  | 78297 | 72868
80630 | Angstrom to STP: Increase 345 kV Line MOT | Increase the MOT on the Angstrom to STP 345 kV line | Contact and In-Service Date Update | Angstrom | STP | Planned | TA2024200 | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | San Patricio | Matagorda | Tier 4 |  |  |  |  | 5915, 8249, 8676 | Y |  |  |  | 80631 | 80630
68150 | Abilene South to Estes: Rebuild 138 kV Line | Rehab Abilene South to structure 33/7 | Project Title, Project Description, Terminal To Location, and Estimated Cost Update | Abilene South | Estes | Under Construction |  | AEP TNC | Michael Glueck twang1@aep.com 918-599-2635 |  | 2025-12-31 |  | 138 | 0 | 18.3 | 0 |  | Taylor | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6260, 6313, 60063, 60336, 60355, 60365, 60773, 61015 | Y | N |  |  | 68151 | 68150
72268 | CPSE_New Ingram Rd Substation | [6 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar |  | Tier 4 |  |  |  |  | 5102, 5241, 5346 | Y |  |  |  | 72269 | 72268
72063 | Moody to Stewart Ckt.63 Upgrades P1041 | Reconductor portions of Ckt.63 Stewart to West Galveston as a Hardening project |  | Stewart | West Galveston | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 345 | 0 | 4.03 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42950, 42951, 43400 | Y | N |  |  | 72064 | 72063
72040 | Blueridge to WA Parish Ckt.02A Upgrades (22RPG041) | Upgrade portions of Ckt.02A Blueridge tap to WA Parish as a Hardening upgrade |  | HO Clarke | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 138 | 0 | 9.08 | 0 |  | Harris | Harris | Tier 4 | 22RPG041 | 2022-11-21 | 2022-12-15 | 2022-12-15 | 44180, 48163, 48302, 48335 | Y | N |  |  | 72473 | 72040
73352A | PH Robinson Area 138kV Upgrades | Reposition existing PH Robinson to BACLIF generator lead from the PHR_South bus to the PHR_North bus. |  | PH Robinson | BACLIF | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42010, 42015, 111131 | Y | N |  |  | 73353 | 73352
76914 | Ocelot: Build new 138 kV station | BPUB interconnection at Ocelot on Military Highway to Palo Alto | In-Service Date Update | Military Highway | Palo Alto | Conceptual | TP2023032 | AEP TCC | Michael Forcum mlforcum@aep.com 918-282-8376 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8047, 8275, 8950 | Y |  |  |  | 76915 | 76914
75792 | New substation for generation interconnection project for 21INR0359 | New substation for generation interconnection project for 21INR0359 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 68035, 68040, 68091 | Y |  |  |  | 75793 | 75792
76196 | Lobo: 138 kV Breaker Replacement | Replace 138 kV breakers at the Lobo 138 kV station | Contact Update | Lobo |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023015 | 2025-12-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80221 | Y |  |  |  | 76197 | 76196
65683 | To add Open Sky Station | To interconnect GINR 20INR0241 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68001, 68004, 68014 | Y | N |  |  | 65684 | 65683
57906 | Laredo to University: Rebuild 138 kV Line | Reconductor the Del Mar to University 138 kV line | Description, Contact, and In-Service Date Update | Laredo | University | Planned | 1119 - 1297 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3838 | 2025-12-31 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645, 8647 | Y | N |  |  | 65579 | 57906
75830B | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). | Install generator lead from Savannah (SAV) substation to CASCAD (CSC) customer substation (23INR0091). |  | Savannah | CASCAD | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43180, 113751 | Y | N |  |  | 87167 | 75830
73352C | PH Robinson Area 138kV Upgrades | Upgrade Ckt.79C BIGBAY to BAYOU to increase thermal limits. Request customers to approve 110% Emergency rating of in-series equipment at BBP/BYU. |  | BIGBAY | BAYOU | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42160, 42180 | Y | N |  |  | 73355 | 73352
73352D | PH Robinson Area 138kV Upgrades | Upgrade PH Robinson 'North' Bus fault duty to 80KA |  | PH Robinson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 00:03 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 73356 | 73352
87901 | Kallisto: Construct New Station to interconnect Beta | Construct 138 kV station to interconnect Beta | NEW | King Ranch Gas Plant |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2026-01-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 80228 | Y |  |  |  | 87902 | 87901
81895 | BPUB Branch Changes | Removing branch Price to Loma, adding Price to Stillman, adding another branch Loma Alta to Stillman. |  | 59410, 5962 | 79601, 79601 | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2026-01-01 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 59410, 79601 | Y |  |  |  | 81896 | 81895
87640 | New load customer interconnection RAOULT connecting on ckt 86 between DALTON and BRINE. | New load customer interconnection RAOULT connecting on ckt 86 between DALTON and BRINE. |  | RAOULT | DALTON/BRINE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-20 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40220, 40740, 41740 | Y | N |  |  | 87641 | 87640
77144 | Pompano: New 138 kV Station | New station for Next Decade/ Rio Grande LNG | Contact, In-Service Date, and Reactive Capability Update | Pompano |  | Planned |  | AEP TCC | Robert Younger jlsolis@aep.com 361-881-5574 | TP2015151 | 2026-01-31 |  | 138 | 0 | 0 | 0 | 0,276.4 | Cameron |  | Tier 4 |  |  |  |  | 8337, 8535, 79601 | Y |  |  |  | 77145 | 77144
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 36th Street | Merida | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0196 | 2026-01-31 |  | 138 | 0 | 4 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 9559 | 2308
6572 | Ballinger to Eden 69 kV line: Rebuild taps | Rebuild Taps on the Ballinger to Eden 69 kV line | Contact, Schedule Update | Ballinger | Eden | Planned | 890 - 1068 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2814 | 2026-01-31 |  | 69 | 0 | 2.8 | 0 |  | Runnels | Concho | Tier 4 |  |  |  |  | 6338, 6369, 6370, 6372, 6376 | Y | N |  |  | 65513 | 6572
78473A | Odin (ODI) 138kV CEHE Substation | (In terms of completed Waterfowl substation) Loop new CEHE 138kV substation Odin (ODI) into Ckt.36 to create new Ckt.36 COPPER to Odin to Booster tap to Jones Creek. |  | Odin | Brazosport/ Booster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 |  |  |  |  | 42199, 42215, 42280 | Y | N |  |  | 87133 | 78473
78473B | Odin (ODI) 138kV CEHE Substation | Install one generator lead from CEHE 138kV substation Odin (ODI) to VALHAL (VAL) / Valhalla Solar (26INR0042) |  | Odin | VALHAL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 |  |  |  |  | 42280, 113811 | Y | N |  |  | 87134 | 78473
48818 | Ballinger: Rebuild 138 kV Station | Rehab the 138/69 kV autotransformer at Ballinger | In-Service Date Update | Ballinger |  | Planned | 1016 - 1194 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2777 | 2026-01-31 01:00 |  | 138 | 0 | 0 | 130 |  | Runnels |  | Tier 4 |  |  |  |  | 6338, 6340 | Y | N |  |  | 65537 | 48818
50866 | Structure 31/8 - Kenedy SS: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild |  | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown mlforcum@aep.com 918-599-2674 | 3779 | 2026-01-31 01:00 |  | 138 | 0 | 14.3 | 0 |  | Karnes | Karnes | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8153, 8186 | Y | N |  |  | 50867 | 50866
61232 | RGEC Persimmon Gap Substation 69-kV Transmission Line Extension and Substation Expansion | Extend Alpine-Persimmon Gap 69-kV Transmission Line at Switch# 6669 and Install Circuit Switcher to accommodate new substation power transformer and distribution bays. New power transformer capacity will be 12/16/20 MVA. | Scheduled RUS Construction Work Plan Project | Persimmon Gap | Persimmon Gap | Planned |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2026-02-01 |  | 69 | 0 | 0 | 0 |  | Brewster | Brewster | Tier 4 | [5 empty] | Y | N |  |  | 61233 | 61232
69479 | Radiant: Build new 345 kV Station | Interconnect Lunis Creek Solar to the new Radiant 345 kV station on the Cobra to STP 345 kV line | Description and Contact Update | Radiant |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-02-28 |  | 345 | 0.2 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5915, 8676, 8715 | Y |  |  |  | 69480 | 69479
80824 | Zenaida: Construct New 138 kV Station | Interconnect Dove Run Solar to the new Zenaida 138 kV station on the Crestonio to Falfurrias 138 kV line | Contact Update | Zenaida |  | Planned | TP2023843 | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2026-02-28 |  | 138 | 0 | 0 | 0 |  | Duval |  | Tier 4 |  |  |  |  | 8510, 8695, 80043 | Y | N |  |  | 80825 | 80824
69489 | Shepley: Construct New Distribution Station | Construct new distribution station on the Victoria to Dupont Switch 138 kV line | Description and Contact Update | Shepley |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-02-28 |  | 138 | 0 | 0 | 50 |  | Victoria |  | Tier 4 |  |  |  |  | 8143, 8172, 8719 | Y |  |  |  | 69490 | 69489
76242 | Lytle: Construct New 138 kV Terminal | Convert the Big Foot to Lytle 69 kV line to 138 kV and interconnect Rowan Digital to the Lytle 138 kV station | Owner, Contact, and In-Service Date Update | Lytle |  | Planned |  | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022155 | 2026-02-28 |  | 138 | 0.1 | 0 | 0 | 0,23 | Medina |  | Tier 4 |  |  |  |  | 8962 | Y |  |  |  | 76243 | 76242
73063 | Big Foot to Lytle: Convert to 138 kV | Convert the Big Foot to Lytle 69 kV line to 138 kV and interconnect Rowan Digital to the Lytle 138 kV station | Project Title, Project Description, Company Contact, Cost, Trans Circuit Miles New, Reactive Capability Added Update | Big Foot | Lytle | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2022155 | 2026-02-28 |  | 138 | 0 | 12 | 0 | 23,0 | Medina | Frio | Tier 4 |  |  |  |  | 8208, 8216, 8218, 8221, 8223, 8622, 8732, 8962, 58280 | Y |  |  |  | 73064 | 73063
70882 | Rebuild Olivia - Carancahua | rebuild Olivia sw to Carancahua 795 ACSR |  | Olivia SW | Carancahua | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-03-01 |  | 69 | 0 | 8.71 | 0 |  | Jackson | Matagorda | Tier 4 |  |  |  |  | 5573, 5574 | Y |  |  |  | 70883 | 70882
82714 | Rebuild of Airport of Substation | Atlas Substation will be replacing Airport Substation. |  | Filter Plant (BPUB), South Plant (BPUB), and Southmost (STEC) | Atlas (BPUB) | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2026-03-02 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5789, 59420, 59440, 59500 | Y | N |  |  | 82715 | 82714
78414 | Replacing existing 1200 Amp switch and 1800 Amp bypass jumper with new 3000 Amp switch. |  |  |  |  | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2026-03-04 |  | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 | [5 empty] | Y |  |  |  | 78417 | 78414
78169 | Lewisville Switch to Highland | Lewisville Switch to Highland |  | Lewisville Switch | Highland | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-03-15 |  | 138 | 0 | 2.8 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 645, 664 | Y |  |  |  | 78170 | 78169
80376 |  |  |  | WEST WEATHERFORD | SHADY GROVE | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-03-15 |  | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 477, 512, 513, 515, 1589 | Y |  |  |  | 80377 | 80376
70186 | LCRATSC_BuchananCTEC_Kingsland1_TL_Overhaul | LCRA TSC will perform an overhaul on the 6.2-mile Buchanan to Kingsland 2 to Kingsland 1 (T291) 69-kV transmission line. |  | Buchanan CTEC | Kingsland 1 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-03-25 |  | 69 | 0 | 6.2 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7402, 7404 | Y | Y |  |  | 78419 | 70186
71937 | Caterpillar Substation | Add T6, 40 MVA. 138-26.08 kV PWT to Caterpillar Substation |  | Caterpillar |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-03-26 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 | [5 empty] | Y | N |  |  | 71938 | 71937
75780A | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy Solar (23INR0057) | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. |  | Elmaton | STP/WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-03-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 5915, 43990, 44000 | Y | N |  |  | 87168 | 75780
75780B | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy Solar (23INR0057) | Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy Solar (23INR0057) |  | Elmaton | DUFFY | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-03-30 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 87169 | 75780
80572 | Miel: Construct New 138 kV Station | Interconnect Nightfall Solar to the new Miel 138 kV station on the Razorback to Uvalde 138 kV line | Owner and Contact Update | Miel |  | Planned | TP2023841 | ETT | John Solis jlsolis@aep.com 361-881-5574 |  | 2026-03-31 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 4 |  |  |  |  | 8234, 8707, 8747 | Y | N |  |  | 80573 | 80572
80830 | Zenaida: Construct New 138 kV Station | Interconnect Sun Cactus Solar to the new Zenaida 138 kV station on the Crestonio to Falfurrias 138 kV line | NEW | Zenaida |  | Planned | TP2023851 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-03-31 |  | 138 | 0 | 0 | 0 |  | Duval |  | Tier 4 |  |  |  |  | 80043 | Y | N |  |  | 80831 | 80830
80468 | Conoco: Construct New 138 kV Terminal | Interconnect Isaac Solar to the Conoco 138 kV station | Contact Update | Conoco |  | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2026-03-31 12:00 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8114, 113651 | Y |  |  |  | 80469 | 80468
77122 | Mulberry Creek: Construct New 345 kV Terminal | Interconnect the Lancium load to the Mulberry Creek 345 kV station | Contact Update | Mulberry Creek |  | Planned | TP2023636 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 |  | 2026-04-30 |  | 345 | 2.25 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6235 | Y | N |  |  | 77123 | 77122
87031 | Primavera: Construct New 138 kV Terminal | Interconnect Project Lynx Storage to the Primavera 138 kV station | NEW | Primavera |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | TP2024100 | 2026-04-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8003 | Y |  |  |  | 87032 | 87031
64858 | La Palma Expansion | Construct 3 Breaker Ring Bus. Construct 345 kV Line from La Palma 345 kV station to Kingfisher 345 kV (Sharyland) station. | Contact Update | La Palma | Kingfisher | Planned |  | AEP TCC/SLU | Randy Weaver jlsolis@aep.com 361-881-5574 | TP2021588 | 2026-04-30 |  | 345 | 6.5 | 0 | 0 |  | Cameron | Cameron | Tier 2 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8317, 8383, 79500, 79501, 80137 | Y |  |  |  | 65264 | 64858
73098 | Castroville Cut-in 138 kV | Cut the AEP line from Quihi to CPS Castroville into the newly converted to 138 kV STEC Castroville station. |  | Quihi | Castroville (CPS) | Planned | TP2022982 | ETT | Lance Price jlsolis@aep.com 361-881-5574 |  | 2026-04-30 |  | 138 | 0.4 | 0 | 0 |  | Medina |  | Tier 2 | 22RPG022 | 2023-08-22 | 2023-11-22 |  | 5083, 5804, 8248 | Y |  |  |  | 73099 | 73098
71002 | Tidehaven: Construct New Distribution Station | Construct new distribution station on the Blessing to Palacios 69 kV line | Description and Contact Update | Tidehaven |  | Planned | 1028 - 1206 | AEP TCC | Marc Wilson deevans@aep.com 918-599-2938 | 3767 DP21X0007 | 2026-04-30 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8044, 8119, 8121, 8131, 8132, 8133, 8555, 8666 | Y | N |  |  | 71003 | 71002
70373 | Driscoll Capacitor addition | adds 3 9.6 MVAR capacitor steps at Driscoll |  | Driscoll |  |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 0 | 0 | 0,28.8 |  |  | Tier 4 |  |  |  |  | 5640 | Y |  |  |  | 70374 | 70373
81229 | Upgrade Oaks Auto | Upgrade Oaks Auto to 150MVA |  | Oaks | Oaks | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 138 | 0 | 0 | 150 |  |  |  | Tier 4 |  |  |  |  | 5712, 5713 | Y |  |  |  | 81230 | 81229
78483 | Rebuild Nada to El Campo 69 kV line | Rebuild Nada to El Campo 69 kV line from 4/0 to 795. 2023 RTP |  | Nada | El Campo | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 15.44 | 0 |  | Colorado | Wharton | Tier 4 |  |  |  |  | 5536, 5538 | Y | N |  |  | 78484 | 78483
78478 | Rebuild Oaks to Poteet to Pearsall 69 kV line | Rebuild Oaks to Poteet to Pearsall 69 kV line from 4/0 to 795. 2023 RTP |  | Oaks | Pleasanton | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 18.5 | 0 |  |  |  | Tier 2 |  |  | 2020-05-21 |  | 5710, 5712, 5893 | Y | N |  |  | 78479 | 78478
76768 | Upgrade Pearson -Pearsall | Upgrade the Pearson-Natalia-Devine-Moore-Pearsall to 795 ACSR |  | Pearson | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 22.24 | 0 |  | Frio | Medina | Tier 4 |  |  |  |  | 5811, 5828, 5830, 5857, 5858, 5893, 58570 | Y |  |  |  | 76769 | 76768
76109 | West Sinton Capacitor addition | Add a 3.6 MVAR step to existing West Sinton Capacitor |  | West Sinton |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 0 | 0 | 0,3.6 |  |  | Tier 4 |  |  |  |  | 5622 | Y | N |  |  | 76110 | 76109
76816 | Upgrade Loyola Auto | Upgrade Loyola Auto |  | Loyola | Loyola | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5648, 5650 | Y |  |  |  | 76817 | 76816
75989 | Rebuild Vanderbilt -Pt Lavaca | Rebuild Vanderbilt - Placedo - Kamey -Pt Lavaca 69kV to 795 ACSR |  | Vanderbilt | Port Lavaca | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 26.47 | 0 |  | Victoria | Calhoun | Tier 4 |  |  |  |  | 5582, 5586, 5590, 5591, 5592 | Y |  |  |  | 75990 | 75989
76786 | Upgrade Calallen- Loyola | Upgrade Calallen- Robstown - CC Sw- Driscol-Ricardo-Riviera-Loyola to 959.6 ACSS |  | Calallen | Loyola | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 69 | 0 | 46.57 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 5626, 5634, 5636, 5640, 5645, 5646, 5650 | Y |  |  |  | 76787 | 76786
71928 | Upgrade Heidelberg to AEP Weslaco line | Upgrade Heidelberg to STEC WESLACO and STEC WESLACO to AEP Weslaco lines to be 478MVA capable |  | Heidelberg | Weslaco | Planned | 7193071926 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-05-01 |  | 138 | 0 | 8.6 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5765, 5768, 8354 | Y |  |  |  | 71929 | 71928
72582C | Nameless to Leander Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. (Replaces ERCOT Project # 61279C) | 1/10/2023: Added information to clarify circuit rating. | Hero Way | Nameless | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-05-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70526, 70536 | Y | N |  |  | 72585 | 72582
82840 |  |  |  | HYDRA | Hydroponic | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-05-02 |  | 115 | 3 | 0 | 0 |  | Lubbock | Lubbock | Tier 4 |  |  |  |  | 700, 59122 | Y |  |  |  | 82841 | 82840
5479 | Trinidad - Tri Corner 345 kV Double-Circuit Line | Upgrade existing DCKT line |  | Trinidad Sw. Sta | TriCorner/Watermill | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4045 | 2026-05-15 |  | 345 | 0 | 92.1 | 0 |  | Henderson | Dallas | Tier 3 |  |  |  |  | 2432, 3123, 3124 | Y | N |  |  | 13184 | 5479
61601 | Add Coody Crossing 345 kV Switch | Add Coody Crossing 345 kV Switch |  | Clear Crossing | Tecumseh Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8560 | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Throckmorton | Throckmorton | Tier 4 |  |  |  |  | 11418, 11419, 60514 | Y |  |  |  | 64014 | 61601
71130 | Centerville Switch - Lake Hubbard Switch 138 kV Double-Circuit Line | Upgrade the existing 138 kV Double-Circuit Line |  | Lake Hubbard | Centerville | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4126 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2401, 2402, 2439, 2450 | Y |  |  |  | 71131 | 71130
68681 | Lamar Blossom Switch - Clarksville 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Lamar | River Crest | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5325 | 2026-05-15 |  | 69 | 0 | 0 | 0 |  | Lamar | Red River | Tier 4 |  |  |  |  | 1772, 1785, 11784 | Y |  |  |  | 68682 | 68681
71912A | Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Fort Hood - Killeen Park Street Tap 138 kV Line |  | Killeen Fort Hood | Killeen Park Street Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6245 | 2026-05-15 |  | 138 | 0 | 3.95 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3626, 3627, 3635, 13626 | Y |  |  |  | 71913 | 71912
71903 | Establish Launch Pad 138 kV Switch | Establish Launch Pad 138 kV Switch |  | Launch Pad | Launch Pad | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6156 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3372, 3593, 3594, 3601, 3709 | Y |  |  |  | 71904 | 71903
72576B | Lago Vista to Nameless Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. (Replaces ERCOT Project #61277B) | 1/10/2023: Added information to clarify circuit rating. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70352, 70526 | Y | N |  |  | 72578 | 72576
71985 | Cypress Water 138 kV Switch | Rebuild the existing Northlake(Cypress Waters) 138 kV Switch |  | Northlake |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4353 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 2362, 2363, 2367, 2385, 2386, 2390, 2395, 2587 | Y |  |  |  | 73110 | 71985
66218B | Hillsboro - Italy 69 kV Line | Rebuild the Milford-Italy 69 kV Line |  | Milford | Italy | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4326 | 2026-05-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  | 2021-04-23 | 2021-05-18 |  | 2337, 2338 | Y |  |  |  | 73690 | 66218
77174 | Rebuild Old Lake Sw - Ringgold Magnolia 69 kV line | Rebuild Old Lake Sw - Ringgold Magnolia 69 kV line |  | Old Lake Switch | Ringgold Magnolia | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3508 | 2026-05-15 |  | 69 | 0 | 13 | 0 |  | Clay | Montague | Tier 4 |  |  |  |  | 1524, 11541, 11545 | Y |  |  |  | 77175 | 77174
76652 | Line Termination at Cypress Waters | Vineyard Switch – Hackberry Switch 138 kV Line Termination at Cypress Waters 138 kV Switch |  | Cypress Waters |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5344 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2017, 2386, 2392 | Y |  |  |  | 76653 | 76652
81551 | Dos Rios 138 kV Switch | Establish Dos Rios 138 kV Switch |  | Dos Rios Switch | Dos Rios Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6231 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 32, 3707, 3725 | Y |  |  |  | 81552 | 81551
78408 | LCRA TSC Henne Substation Bus Upgrade | LCRA TSC intends to build a new 138 kV line from Henne to Kohlenberg. LCRA TSC will have to accommodate this line at Henne. Henne substation can be converted to a breaker and half to improve reliability and support the project. |  | Henne | Henne | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7172, 7173, 7174, 7176, 7182 | Y | N |  |  | 78411 | 78408
81146 | Southmayd 138 kV Switch | Establish Southmayd 138 kV Switch |  | Southmayd |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4338 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  |  | 1744, 2790, 11704 | Y |  |  |  | 81147 | 81146
80921 | Downtown Kyle Substation Addition | Models the addition of a planned substation in Kyle area. |  | DOWNTOWN KYLE 70503 |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 70198, 70502, 70503 | Y |  |  |  | 80922 | 80921
73106 | LCRATSC_Lockhart_SanMarcos_TL_Conversion_Updated | The five LCRA TSC-owned transmission line sections from Lockhart to San Marcos will be converted to 138-kV (T220 San Marcos to Camp Gary to Robert Brown Jr., T519 Robert Brown Jr. to Clear Fork, and T601 Clear Fork to Lockhart). |  | Lockhart | San Marcos | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Hays | Tier 4 |  |  |  |  | 7188, 7191, 7192, 7194, 7195, 7196, 7215, 7216 | Y | N |  |  | 78513 | 73106 | 2023-SC11
81067 | Balch Springs Tap – Balch Springs 138 kV Line Section | Rebuild Balch Springs Tap – Balch Springs 138 kV Line Section |  | Balch Springs Tap | Balch Springs | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4194 | 2026-05-15 |  | 138 | 0 | 3.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2775, 2776, 2777, 2778 | Y |  |  |  | 81068 | 81067
5526 | Forney 345/138 kV Switch | Rebuild existing 345/138 kV switching |  | Forney |  | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4114 | 2026-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 3 |  |  |  |  | 2437, 2438, 22438 | Y | N |  |  | 78356 | 5526
78369 | Rebuild Sam Switch - Venus Switch 345 kV DCKT | Rebuild Sam Switch - Venus Switch 345 kV DCKT |  | Venus | Sam | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6293 | 2026-05-15 |  | 345 | 0 | 76 | 0 |  | Ellis | Hill | Tier 1 |  |  |  |  | 1906, 1907, 3374, 3389, 68090 | Y |  |  |  | 78370 | 78369
76312 | Establish Ramhorn 138kV Switch | Establish Ramhorn 138kV Switch |  | Dunham | Dunham | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5007 | 2026-05-15 |  | 138 | 0 | 0 | 600 |  | Denton | Denton | Tier 3 |  |  |  |  | 568, 1570, 1840, 1842 | Y |  |  |  | 82052 | 76312
85963 | LCRATSC_FPP Yard 2_Lytton Springs Transmission Line Overhaul_355T255 | LCRA TSC will overhaul FPP Yard #2 - Lytton Springs 345-kV transmission line T255 to ensure structural integrity of the circuit. Engineering will review this transmission circuit for scope including hardware/insulator integrity, structural load issues, need for containment (dead-ends) structures, and clearances at highway and railroad crossings. |  | FPP Yard 2 | Lytton Springs | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Fayette | Caldwell | Tier 4 | 24RPG013 | 2024-04-11 | 2024-05-03 |  |  | Y |  |  |  | 85964 | 85963
80546C | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild and double-circuit the Georgetown East - Sonterra 138 kV Line Section |  | Georgetown East | Sonterra | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2026-05-15 |  | 138 | 12.9 | 12.9 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 121, 3688, 7346, 7528 | Y |  |  |  | 87631 | 80546 | 2023-SC17
70900F | Roanoke Area Upgrades | Establish Roanoke_Exchange 138 kV Line |  | Roanoke Switch | Exchange Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2026-05-15 |  | 138 | 11.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 1854, 12077 | Y | N |  |  | 87471 | 70900
87804 | Establish Notus 345 kV Switch | Establish Notus 345 kV Switch |  | Notus Switch | Notus Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6371 | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 2255, 3376, 68091 | Y |  |  |  | 87805 | 87804
81305 | Oncor_FW_Expanse - Tredway 138 kV Line | Rebuild the existing Expanse – Vealmoor 138 kV Line with both circuits in place. |  | Expanse | Tredway | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8681 | 2026-05-15 |  | 345 | 0 | 27.7 | 0 |  | Martin | Martin | Tier 3 |  | 2023-09-29 |  |  | 1355, 10032, 10090, 10097, 10098, 10110, 10112, 10113, 11006, 11338, 11348, 11349, 11368, 11383, 23829, 23835, 23838, 23849, 23880 | Y |  |  |  | 87873 | 81305
63948 | Establish Fallstown 138 kV Switch | Establish Fallstown 138 kV Switch |  | Fallstown | Fallstown | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3018 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 | [5 empty] | Y |  |  |  | 87782 | 63948
85950 | LCRATSC_ALFORD_SUB_ADD | This project will construct the new 138-kV Alford Substation. Alford will be near the existing Oncor Midkiff Substation and the planned Oncor Catclaw Switch. Alford will connect T594 Midkiff to Skywest and T611 Benedum to Midkiff and will provide two (2) 138-kV POIs for Oncor Catclaw Switch. | [5 empty] | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 | 23RPG019 | 2023-08-03 | 2023-08-25 |  | 1210, 10058, 71210, 71211, 71213 | Y |  |  |  | 85951 | 85950 | 2023-FW8
85973 | LCRATSC_GEORGETOWN_RIVERY_T597_Ratings_Impedance | LCRA TSC will upgrade T597 Georgetown - Rivery 138-kV transmission line to achieve a higher operational rating. |  | Georgetown Substation |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-762-3658 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7343, 7347 | Y |  |  |  | 85974 | 85973 | 2023-SC17
6777 | Establish Division Sub Cedar Hill - Liggett 138 kV Line | Establish Division Sub and Loop Cedar Hill - Liggett 138 kV line in to Great Southwest / General Motors | Project Deferral | Grand Prairie West | Mayfield Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5280 | 2026-05-15 02:01 |  | 138 | 6 | 0 | 0 |  | Dallas | Tarrant | Tier 2 |  |  |  |  | 1919, 2137, 2138, 2140, 2143, 2265, 2274, 12265 | Y | N |  |  | 72912 | 6777
87792 | Establish the Bynum 345 kV Switch | Establish the Bynum 345 kV Switch |  | Bynum Switch | Bynum Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6369 | 2026-05-16 |  | 345 | 0 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 1907, 3383, 68090 | Y |  |  |  | 87793 | 87792
81006 | Add load at Diabox and thermally uprate Ckt 21 MOMENT-SOLMER-SRB |  |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 40480, 41090, 41400, 41480 | Y | N |  |  | 81007 | 81006
73423 | Buddy Owens: Build new 138 kV Substation | Build new 138 kV substation on Key Switch to North McAllen 138 kV line | Contact Update | Buddy Owens |  | Conceptual |  | AEP TCC | Travis Coody mlforcum@aep.com 918-599-2674 |  | 2026-05-30 |  | 138 | 0 | 0 | 80 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8632, 8773, 8973 | Y |  |  |  | 73424 | 73423
76580 | Poblano: Build new 138 kV station | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | Contact Update | Poblano |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2026-05-30 02:00 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 8008, 8009, 8234, 8236 | Y |  |  |  | 76581 | 76580
73578A | Heights 138kV Loop Conversion | Rebuild/Reconductor Dead Ckt.40Z Str #14606-26374 to prepare for 138kV Conversion. De-energize Ckt.31C Dunlavy to Heights and repurpose as Ckt.09D tap to Dunlavy TR1 load. |  | Dunlavy | Heights | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45752, 46615, 47580, 47581, 47582, 47682, 47685 | Y | N |  |  | 87302 | 73578
86791 | Crane to Rio Pecos: Rebuild 138 kV Line | Rebuild the Crane to Rio Pecos 138 kV line | NEW | Crane | Rio Pecos | Planned | TP2024050 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-05-31 |  | 138 | 0 | 23.65 | 0 |  | Crane | Crockett | Tier 1 | 23RPG023 | 2023-08-11 | 2024-01-18 | 2024-01-24 | 6601, 76615 | Y | N |  |  | 86792 | 86791
72044A | Clute 138kV Switching Station | Reconfigure existing Ckt.82F RIWOOD to CAVERN to BIPORT and loop into new CEHE-owned 138kV Clute switching station to create new Ckt.82 RIWOOD to Clute to CAVERN to BIPORT. |  | Clute | RIWOOD/CAVERN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 | 42050, 43150, 43330 | Y | N |  |  | 87454 | 72044
80632 | Install Kilgore 35kV Distribution Substation. Loop on Ckt.86B to create new Ckt.86 CHEVRON to Kilgore to LANGSTON | Install Kilgore 35kV Distribution Substation. Loop on Ckt.86B to create new Ckt.86 CHEVRON to Kilgore to LANGSTON |  | CHEVRON/LANGSTON | Kilgore | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 5.12 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40300, 40775, 44830 | Y | N |  |  | 87179 | 80632
87346 | Upgrade Ckt 25 Jeanetta to Westwood to increase thermal limits | Upgrade Ckt 25 Jeanetta to Westwood to increase thermal limits |  | Jeanetta | Westwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47310, 48417 | Y | N |  |  | 87347 | 87346
76293 | Upgraded Cedvale-MiDiva138KV |  |  | Cerdarvale | Midiva | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 0.15 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38145, 38152 | Y |  |  |  | 76294 | 76293
76291 | Upgraded Cedarvale–BoneSpringsTap–Fishhook |  |  | Cedarvale to Bone Springs Tap | Bone Springs Tap to Fishhook | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 12.59 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38145, 38165, 38180 | Y |  |  |  | 76292 | 76291
76232 | Reconductor Mivida-Coachwhip-Fishhook 2045 ACCC |  |  | Mivida PSSE Bus# 38152 | Fishhook PSSE Bus# 38180 | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 14.39 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38152, 38170, 38180 | Y |  |  |  | 76233 | 76232
71106 | Dunlavy to HO Clarke Ckt.40A Partial Reconductor | Reconductor portions of Ckt.40A Dunlavy to HO Clarke ahead of future 138kV conversions |  | Dunlavy | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 69 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47160, 47320, 47580, 48150, 48363 | Y | N |  |  | 71107 | 71106
70898 | Flomot Tap: Rebuild 69 kV Line | Rehab Flomot Tap 69 kV Line | In-Service Date, Estimated Cost Update | Flomot Tap | Flomot | Planned |  | AEP TNC | Chris Carroll twang1@aep.com 918-599-2635 |  | 2026-05-31 |  | 69 | 0 | 7.06 | 0 |  | Motley | Motley | Tier 4 |  |  |  |  | 6041, 6042 | Y | N |  |  | 70899 | 70898
66101 | Del Sol to Frontera: Build New 345 kV Double Circuit Line | Build new 345 kV double circuit line from Del Sol to Frontera. Expand Frontera Station and install two (2) autotransformers | Contact Update | Del Sol | Frontera | Planned |  | ETT/AEP TCC | Brent Harris jlsolis@aep.com 361-881-5574 | TP2020838 | 2026-05-31 |  | 345 | 36 | 0 | 1350 |  | Starr | Hidalgo | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8355, 8980, 8992, 80119, 80355 | Y |  |  |  | 66102 | 66101
64042 | Barrilla Junction: 69 kV Loop Rebuild | Rebuild Barrilla Junction to Saragosa to Cherry Creek to Verhalen to Hoefs Road stations, convert to 138 kV | Contact Update | Barrilla Junction | Hoefs Road Station | Planned | 1141 - 1319 | AEP TNC | Brent Harris twang1@aep.com 918-599-2635 | 1886 | 2026-05-31 |  | 69 | 0 |  | 0 |  | Pecos | Reeves | Tier 3 | 21RPG023 | 2021-12-17 | 2022-01-14 |  | 6649, 6650, 6651, 6652, 6653, 6654, 60206, 60207, 60208, 60385, 60716, 60808, 69023, 69047 | Y | N |  |  | 64043 | 64042
66208 | Rebuild League City-Hidden Lakes with bundled 795 ACSS |  |  | Hidden Lakes (bus # 38900) | League City (bus # 38920) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 3.21 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  |  | 66209 | 66208
66077 | Reconductor both Pecos-Cedarvale 138 kV ckts |  |  | Pecos (bus # 38091) | Cedarvale (bus # 38145) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 15.34 | 0 |  | Reeves | Ward | Tier 4 |  |  |  |  | 38091, 38145 | Y |  |  |  | 66078 | 66077
85987A | Upgrade Ckt.26 Clute to SINTEK to increase thermal limits. Upgrade Ckt.26F Velasco to CAMDEN to increase thermal limits. | Upgrade Ckt.26 Clute to SINTEK to increase thermal limits. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 5.26 | 0 |  | Brazoria | Brazoria | Tier 3 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 42050, 43240 | Y | N |  |  | 85988 | 85987
69253 | Cangrejo to Dacosta: Rebuild 138 kV Line | Rehab 138 kV line from Cangrejo to Dacosta | In-Service Date and RPG Dates Update | Cangrejo | Dacosta | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2026-05-31 |  | 138 | 0 | 17.97 | 0 |  |  |  | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8133, 8135, 8136, 8140, 8141, 8143, 8169, 8536, 8721, 8722, 8723, 8756, 80064, 88133 | Y |  |  |  | 87986 | 69253
78490D | Jeanetta Auto Upgrades | Reconductor Ckt.25B Clodine to Roark TR8 tap to increase thermal limits. |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 345 | 0 | 3.67 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 44140, 44592 | Y | N |  |  | 79428 | 78490
76576 | Asherton to Uvalde: Convert to 138 kV | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | Estimated Cost and RPG Number Update | Asherton | Uvalde | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-05-31 |  | 138 | 0 | 59.74 | 0 |  | Dimmit | Uvalde | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 7867, 8005, 8006, 8007, 8008, 8231, 8242, 8243, 8244, 8280, 8283, 8284, 8672 | Y | N |  |  | 78243 | 76576
81215 | Oklaunion: Reconfigure 138 kV Station | Reconfigure the Oklaunion 138 kV station from a straight bus to a ring bus | NEW | Oklaunion |  | Planned | TP2023876 | ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6066, 6097, 6098, 6100 | Y | N |  |  | 81216 | 81215
78485A | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Westchase to Hayes to Britmoore to increase thermal limits. Upgrade Ckt.24 Bellaire equipment and relay limits. |  | Westchase | Britmoore | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 6.21 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 44120, 48159, 48420 | Y | N |  |  | 78486 | 78485
85970A | Athena (ATH) 138kV CEHE Station for RAVEN (RVN) / Raven Solar & Storage (24INR0209 & 24INR0210) | Loop new Athena CEHE 138kV substation into Ckt.65C East Bernard to Wallis to create new Ckt.65 East Bernard to Athena to Wallis. |  | Athena | East Bernard/Wallis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Wharton | Austin | Tier 4 |  |  |  |  | 44190, 44740, 46650 | Y | N |  |  | 87177 | 85970
44399 | South Padre Island: Rebuild as GIS station | Rebuild South Padre Island as a GIS | Contact Update | South Padre Island | - | Planned | 948 - 1126 | AEP TCC | Ali Abukar deevans@aep.com 918-599-2938 | 3712 | 2026-05-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8335, 8917 | Y | N |  |  | 44400 | 44399
50890 | Port Lavaca: Station Rebuild (Cangrejo) | Rebuild the Port Lavaca (Cangrejo) station | Contact and RPG Date Update | Port Lavaca |  | Planned | 1057 - 1230 | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 | 3787 TA2019045 | 2026-05-31 |  | 69 | 0 | 37.81 | 0 |  | Calhoun |  | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8135 | Y | N |  |  | 50891 | 50890
61552 | Matador to Turkey: Rebuild 69 kV Line | Rebuild 69 kV line from Matador to Turkey | Status, Contact, and In-Service Date Update | Matador | Turkey | Under Construction | 1128 - 1306 | AEP TNC | Chris Carroll twang1@aep.com 918-599-2635 | 1873 | 2026-05-31 |  | 69 | 0 | 26.9 | 0 |  | Motley | Hall | Tier 4 |  |  |  |  | 6020, 6024, 6039, 6041, 6044, 6140, 60351 | Y | N |  |  | 65596 | 61552
78485C | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade portions of Ckt.05E Bellaire to Sharpstown to Hillcroft to increase thermal limits. |  | Bellaire | Hillcroft | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 3.09 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 47015, 48145, 48343 | Y | N |  |  | 78489 | 78485
72044B | Clute 138kV Switching Station | [6 empty] | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  |  | 87455 | 72044
85970B | Athena (ATH) 138kV CEHE Station for RAVEN (RVN) / Raven Solar & Storage (24INR0209 & 24INR0210) | Install one generator lead from Athena CEHE 138kV substation to RAVEN / Raven Solar & Storage (24INR0209 & 24INR0210). |  | Athena | RAVEN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 87178 | 85970
85987B | Upgrade Ckt.26 Clute to SINTEK to increase thermal limits. Upgrade Ckt.26F Velasco to CAMDEN to increase thermal limits. | Upgrade Ckt.26F Velasco to CAMDEN to increase thermal limits. |  | CAMDEN | Velasco | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 |  | 138 | 0 | 0.28 | 0 |  | Brazoria | Brazoria | Tier 3 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 43360, 43365 | Y | N |  |  | 85989 | 85987
73578B | Heights 138kV Loop Conversion | Repurpose/retire existing 69kV Ckts 34A/34B. Unbundle parallel-bundled portions of Ckt.40A HOC to Dunlavy. Reconfigure Ckt.40A to reach a Minimum 1-2000AAC limiting conductor @ 90/120Deg. Upgrade HOC ine relaying on 69kV Ckt.40A HOC to Dunlavy. |  | Dunlavy | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47160, 47580 | Y | N |  |  | 87303 | 73578
72044C | Clute 138kV Switching Station | Reconfigure existing Ckt.26D STRATT to SINTEK and loop into new CEHE-owned 138kV Clute switching station to create new Ckt.26 STRATT to Clute to SINTEK. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 | 42030, 42050, 42110, 42111, 43240, 43300 | Y | N |  |  | 87456 | 72044
73578D | Heights 138kV Loop Conversion | Convert Heights substation to 138kV service. Retire/repurpose portions of 69kV Ckts. 34A/34B for the new Heights 138kV loop. Reconfigure Ckt.09D to create new Ckt.09D Eureka TR2/TR3 tap to HE-DN_TR1 tap to Heights 138kV to White Oak. Reconductor any existing 1-795AAC limiting conductor to 2-959ACSS. Remove existing Heights 7.2 MVAR cap bank from Heights TR1. |  | Heights | San Felipe/White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:03 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46615, 46620, 47160, 47581, 47680, 47682, 47685, 747680 | Y | N |  |  | 87304 | 73578
72044D | Clute 138kV Switching Station | [6 empty] | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  |  | 87457 | 72044
73578E | Heights 138kV Loop Conversion | Remove White Oak auto A2/A4 and remaining 69kV facilities |  | White Oak |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:04 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46615, 46620, 47680, 49021, 49042 | Y | N |  |  | 87305 | 73578
76569 | Asherton: Rebuild 138 kV station | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | Contact Update | Asherton |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2026-05-31 02:00 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 8005, 8242, 8244, 8280, 8283 | Y |  |  |  | 76570 | 76569
87146 | GSEC_Tier4_9468_Add_Bull_Sub | New Substation Load out of 68001 Claytonville | Adding new 1400MW load with deposit and agreement. | Claytonville |  | Planned |  | GSEC | Chris Koenig ckoenig@gsec.coop 806-349-5201 |  | 2026-06-01 |  | 345 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 9468, 68001 | Y |  |  |  | 87147 | 87146
77320 | Add CapBANK in COYANOSA |  |  | COYANOSA |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38380 | Y |  |  |  | 77321 | 77320
76082 | Union Carbide: Rebuild 138 kV Station | Rebuild Union Carbide as new AIS station Chalybe | Contact Update | Union Carbide |  | Planned |  | AEP TCC | Charity Kreher jlsolis@aep.com 361-881-5574 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 5767, 5963, 5965, 8337, 8338, 8535, 8735, 79601 | Y |  |  |  | 76083 | 76082
80404 |  | Reroute East to Rodgers 69kV line to create East to Rayburn 69kV line to accommodate the TXDOT SH6 project. |  | BRYN EAST | RAYBURN | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-06-01 |  | 69 | 1 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32849, 32861, 32874 | Y |  |  |  | 88297 | 80404
76286 | Hecker to Resnik: Rebuild 138 kV Line | Rebuild the Hecker to Resnik 138 kV line | Contact Update | Hecker | Resnik | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2023506 | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 8580 | Y |  |  |  | 76287 | 76286
71408 | Upgrade CKT943 to 3000 amperes | Replace existing 2-795ACSR conductors with 2-795 ACSS conductors and the upgrade the terminal equipment to 3000 amperes. |  | Lytton Springs | Pilot Knob | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-01 |  | 138 | 0 | 11.13 | 0 |  | Caldwell | Travis | Tier 4 |  |  |  |  | 9075, 9259 | Y |  |  |  | 71409 | 71408
65906 | To add Jordan Station for GINR 21INR0031 |  |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68001, 68014, 68016 | Y |  |  |  | 65907 | 65906
65663 | Double Ckt Line M138-K | Project Delayed Indefinitely. |  | Pecos (bus # 38091) | Faulkner (bus # 38124) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-06-01 |  | 138 | 0 | 26.2 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38091, 38124 | N |  |  |  | 65664 | 65663
61090 | Timbercreek 138kV substation | Change name to Establish 138kV Timbercreek substation with (2) 40MVA transformers and will cut into existing Ckt 948 (Onion Creek to Pilot Knob) |  | Onion Creek | Pilot Knob |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9240, 9251, 9259 | Y |  |  |  | 61091 | 61090
45029 | Grandview Highland Hills Rebuild | CPSE_Rebuild of 138 kV double circuit line Line between Grandview to Highland Hills. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0273 | 2026-06-01 |  | 138 | 0 | 11.6 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-11 |  |  | 5030, 5095, 5175, 5205 | Y |  |  |  | 45030 | 45029
86323 | AEN_MagnesiumPlant_Northland_Ckt_979_RECONDUCTOR |  |  | 9128 | 9238 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  |  | 86324 | 86323
81647 | Dupont Switch to Sardinia: Construct New 138 kV Line | Interconnect the Epsilon load to the new Sardinia 138 kV station out of the existing Dupont Switch 138 kV station | NEW | Dupont Switch | Sardinia | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-06-01 |  | 138 | 2 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 8143, 81433 | Y |  |  |  | 81648 | 81647
81581 | Riley: Construct New 345 kV Terminal | Interconnect the Gamma load to the existing Riley 345 kV station | NEW | Riley |  | Conceptual |  | ETT/AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-06-01 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6111 | Y |  |  |  | 81582 | 81581
80424 |  | Rebuild / Reconductor Dansby to Business Park 69kV for Rail Spur |  | Dansby | Bryn Business Park | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-06-01 |  | 69 | 0 | 3.3 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32871, 32875 | Y |  |  |  | 80425 | 80424
80384 |  | Reconductor Gibbons Creek to Greens Prairie Line |  | Gibbons Creek | Greens Pairie | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-06-01 |  | 138 | 0 | 12.9 | 0 |  | Grimes | Brazos | Tier 4 |  |  |  |  | 964, 32878 | Y |  |  |  | 80385 | 80384
76660 | Rebuild Temple Switch and install auto #2 | Rebuild Temple Switch and install auto #2 |  | Temple | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6197 | 2026-06-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3414, 3415, 3718 | Y |  |  |  | 76661 | 76660 | 2023-NC60
76572 | Temple - Temple Pecan 138 kV 2nd Circuit | Temple - Temple Pecan 138 kV 2nd Circuit |  | Temple | Temple Pecan Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6235 | 2026-06-15 |  | 138 | 0 | 4.4 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3415, 3420 | Y |  |  |  | 76573 | 76572
73762 | LCRATSC_Peppergrass_Substation_addition | American Electric Power (AEP) is building a new load serving substation and needs transmission service from the LCRA TSC owned 138-kV T470 Abilene South to McElmurray transmission line. LCRA TSC will install a new 138-kV bus and provide transmission service to the new AEP substation. |  | Peppergrass |  | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org |  | 2026-06-16 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6260, 76316, 76317 | Y | N |  |  | 73763 | 73762
67093 | New 138 kV station cut-in between Garfield and Hi-Cross | New 138 kV Easton Park Substation cut-in on CKT963 from Garfield to Hi-Cross substation to serve BBEC Load |  | 9143 |  | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-20 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9071, 9143, 9147 | Y |  |  |  | 67094 | 67093
61228 | AEN_McNeil__JustinLane__ckt_811_reconductor | Reconductor 3.98 miles of circuit to 3000 Amps. |  | McNeil [9080] | Justin Lane [9225] | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-06-21 |  | 138 | 0 | 3.98 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9080, 9225 | Y |  |  |  | 61229 | 61228
69709 | LCRATSC_Bearkat_NorthMcCamey_SandLake_TransmsissionLineAddition | LCRA TSC, Oncor , and WETT joint project to add the Bearkat-North McCamey 345-kV double-circuit transmission line and North McCamey-Sand Lake 345-kV double-circuit transmission line. 22RPG010 |  | Bearkat | Sand Lake | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-26 |  | 345 | 165 | 0 | 0 |  | Glasscock | Ward | Tier 1 | 22RPG010 | 2022-04-12 | 2022-07-13 |  | 11098, 59903, 76000 | Y | Y |  |  | 78333 | 69709 | 2021-FW15
73401 | LCRATSC_Fredonia_Mason_TL_Upgrade | Perform an overhaul on the 11 mile T289 Fredonia (CTEC) - Mason (CTEC) 69-kV transmission line. Per LCRA TSC Transmission System Planning procedure, replacement structures will be capable of operating at 138-kV. |  | Fredonia | Mason | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-06-30 |  | 69 | 0 | 11 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 7395, 76391 | Y | N |  |  | 73402 | 73401
73496 | Nelson Sharpe: Construct New 345 kV Terminal | Interconnect Noria Hondo Solar and BESS to the Nelson Sharpe 345 kV station | Contact Update | Nelson Sharpe |  | Conceptual |  | AEP TCC | Robert Dougherty deevans@aep.com 918-599-2938 |  | 2026-06-30 |  | 345 | 1 | 0 | 0 |  | Nueces |  | Tier 4 | [5 empty] | Y |  |  |  | 73497 | 73496
71952 | LCRA TSC Bluffton to Buchanan Transmission Line Overhaul | Overhaul circuit and replace conductor with single-Drake conductor (117 MVA) from Bluffton to Buchanan. Replacement structures should be 138-kV double-circuit capable of supporting a single-Suwannee conductor. Install OPGW. |  | Bluffton | Buchanan | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 69 | 0 | 7 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7406 | Y | N |  |  | 72467 | 71952
72479 | Cobia: Build new 138 kV Station | Build new 138 kV station along the Carbide to Joslin 138 kV line | Contact Update | Cobia |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-06-30 |  | 138 | 0.1 | 0 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | 8132, 8133, 8140, 8155, 8685, 8720, 8741, 8742, 88742, 708133 | Y |  |  |  | 72482 | 72479
70675 | Aransas Pass to Rincon: Rebuild 69 kV Line | Rebuild the Aransas Pass to Gregory to Rincon 69 kV line | Contact Update | Aransas Pass | Rincon | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2022132 | 2026-06-30 |  | 69 | 0 | 16 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8416, 8421, 8427 | Y |  |  |  | 70676 | 70675
81573 | Oklaunion: Construct New 345 kV Terminal | Interconnect the Alpha load to the existing Oklaunion 345 kV station | NEW | Oklaunion |  | Conceptual |  | ETT/AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-06-30 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6100 | Y |  |  |  | 81574 | 81573
86796 | Buccaneer: Construct New 69 kV Station | Interconnect the Oncor Regency station to the new Buccaneer 69 kV station on the Eden to North Brady 69 kV line between Melvin and North Brady | NEW | Buccaneer |  | Planned | TP2024028 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-07-31 |  | 69 | 0 | 0 | 0 |  | McCulloch |  | Tier 4 |  |  |  |  | 6006, 6380, 60005 | Y | N |  |  | 86797 | 86796
55217 | Putnam to Leon: Rebuild 138 kV line | Rehab the Putnam to Leon (Oncor) 138 kV line | Project Description and In-Service Date Update | Putnam | Leon | Planned | 1042 - 1269 | AEP TNC | LaRissa Lundry twang1@aep.com 918-599-2635 | 1859 | 2026-07-31 |  | 138 | 0 | 20.81 | 0 |  | Callahan | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | N |  |  | 55218 | 55217
79462 | Expand HO Clarke substation for Callisto II (22INR0558) | Expand HO Clarke substation for Callisto II (22INR0558) |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 79463 | 79462
75790 | Placeholder Station for Erath Solar POI | Placeholder Station for Erath Solar POI |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-08-27 |  | 345 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 68020, 68025, 68030 | Y |  |  |  | 75791 | 75790
82298 | PMCR for Adding TNMP Woodhouse New Station | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-08-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  | 2024-02-27 | 38295, 38308, 38355, 60717 | Y |  |  |  | 82299 | 82298
70673 | Clairmont Sun Oil Tap: Rebuild 69 kV Line | Rehab Clairmont Sun Oil Tap 69 kV Line | In-Service Date Update | Clairmont | Sun Clairmont | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2021233 | 2026-08-31 |  | 69 | 0 | 0 | 0 |  | Kent | Kent | Tier 4 |  |  |  |  | 6197, 6198 | Y |  |  |  | 70674 | 70673
43434 | This is the POI for High Noon Solar and Storage |  |  | Boot Hill | Boot Hill | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-09-01 |  | 138 | 0 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 444, 445, 446 | Y |  |  |  | 43435 | 43434
72579B | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Blanco to Devil's Hill 69 kV circuits to 138 kV with bundled 795 kcmil conductor (440 MVA). (Replaces ERCOT Project # 70367B) |  | Blanco | Devil's Hill | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-09-15 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 70482, 70484, 70493 | Y | Y |  |  | 72581 | 72579
66289C | Tyler to Athens 138 kV line Conversion | Tyler to Athens 138 kV Operation |  | Tyler | Athens | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6094 | 2026-09-15 |  | 138 | 0 | 0 | 0 |  | Henderson | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3108, 3142, 3197, 3236, 3238, 13235 | Y |  |  |  | 87816 | 66289
66492B | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Grindstone - Jacksboro Sinclair 69 kV Line |  | Jacksboro Sinclair | Grindstone | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3006 | 2026-09-15 |  | 69 | 0 | 15 | 0 |  | Jack | Palo Pinto | Tier 4 |  |  |  |  | 1557, 1572 | Y |  |  |  | 72964 | 66492
66206A | Upgrade Temple - Minerva 69 kV Line | Upgrade Temple - Marak 69 kV Line |  | Temple | Marak | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6186 | 2026-09-15 |  | 69 | 20.5 | 0 | 0 |  | Bell | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3643, 3689 | Y |  |  |  | 68923 | 66206
86829 | Fort Stockton Plant to Lynx: Rebuild 138 kV Line | Rehab the Fort Stockton Plant to Lynx 138 kV line | NEW | Fort Stockton Plant | Lynx | Planned | TA2020218 | AEP TNC | Charity L Kreher twang1@aep.com 918-599-2635 |  | 2026-09-30 |  | 138 | 0 | 37 | 0 |  | Pecos | Pecos | Tier 4 | 23RPG008 | 2023-04-14 | 2023-05-05 |  | 6630, 6671, 60400 | Y | N |  |  | 86830 | 86829
76818 | Upgrade Rayburn Auto Station | Upgrade Rayburn Auto |  | Rayburn | Rayburn | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-10-01 |  | 138 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5500, 5502 | N |  |  |  | 76819 | 76818
78177 |  |  |  | Pleasant Grove | Pleasant Grove | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 69 | 0 | 0 | 0 | 0,7.2 | Falls | Falls | Tier 4 |  |  |  |  | 81 | Y |  |  |  | 78178 | 78177
78181 |  |  |  | Midway | Midway | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 69 | 0 | 0 | 0 | 0,7.2 | Falls | Falls | Tier 4 |  |  |  |  | 185 | Y |  |  |  | 78182 | 78181
78175 |  |  |  | Franklin | Franklin | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 138 | 0 | 0 | 0 | 0,9 | Robertson | Robertson | Tier 4 |  |  |  |  | 57 | Y |  |  |  | 78176 | 78175
61444 | Add a new load serving substation about 4.35 miles south of La Vernia along FM 775 | Add a new load serving substation about 4.35 miles south of La Vernia along FM 775, w/40 MVA PWT |  | Wilson South |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-10-22 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 5418, 7615, 7629 | Y | N |  |  | 78418 | 61444
79451A | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. |  | Ancla | Angleton/West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 43380, 46630 | Y | N |  |  | 87173 | 79451
6072 | Eldorado to Ft. McKavitt: Rebuild 69 kV Line | Rehab Eldorado to Ft. McKavitt 69 kV line | Project Title, TSP/Company Contact, In-Service Date Update | Eldorado Tap | Ft. McKavitt | Planned | 786 - 0971 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2677 | 2026-10-31 |  | 69 | 0 | 19.41 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  |  | 6505, 6506, 6507, 6508 | Y | N |  |  | 13794 | 6072
75835A | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits |  | Stone Lake | Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 8.29 | 0 |  | Harris | Harris | Tier 3 |  |  |  |  | 44840, 46510, 48348 | Y | N |  |  | 75836 | 75835
73362 | Uribe: Construct New Distribution Station | Construct new distribution station on the Molina to Zapata 138 kV line | Contact Update | Uribe |  | Planned |  | AEP TCC | Coby Hendrick jlsolis@aep.com 361-881-5574 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 8299, 8646, 8985, 8993, 80230 | Y | N |  |  | 73363 | 73362
86022 | Jordan 138kV Substation Expansion for Coneflower Storage (23INR0425) | Expand 138kV Jordan substation for Coneflower Storage generator interconnection (23INR0425) |  | Jordan |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Chambers |  | Tier 4 |  |  |  |  | 40855, 113981 | Y | N |  |  | 86023 | 86022
87637 | Install new distribution transformer to serve 32 MW customer load. | Install new distribution transformer to serve 32 MW customer load. |  | Liberty |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40961, 40962 | Y | N |  |  | 87638 | 87637
87344 | Upgrade 345kV Ckt 71 Addicks-White Oak to increase thermal limits | Upgrade 345kV Ckt 71 Addicks-White Oak to increase thermal limits |  | Addicks | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45600, 46600 | Y | N |  |  | 87345 | 87344
79451B | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. | Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. |  | Ancla | ROYAL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 87174 | 79451
85947 | LCRA TSC will provide a transmission point of interconnection via a new 345-kV Euclid substation | LCRA TSC provide a new transmission point of interconnection by constructing a new 345-kV substation and cut-in T510 Hutto - Zorn. T510 will also be looped into the new Limmer 345-kV substation |  | Euclid (7041) | Euclid (7041) | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7042, 7045, 7341 | Y |  |  |  | 85949 | 85947
86882 | McKenzie to Westside: Reconductor 138 kV Line | Reconductor the McKenzie to Westside 138 kV line | NEW | McKenzie | Westside | Planned |  | ETT/AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2024025 | 2026-11-30 |  | 138 | 0 | 0.32 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8485, 8858 | Y | Y |  |  | 86883 | 86882
80907 | Fort Stockton Plant: Rebuild 138/69 kV Station | Rebuild the Fort Stockton Plant 138/69 kV station | NEW | Fort Stockton Plant |  | Planned | TP2023319 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-11-30 |  | 138 | 0 | 0 | 90 |  | Pecos |  | Tier 4 |  |  |  |  | 6630, 38355 | Y | N |  |  | 80908 | 80907
79988 | Lucero: Construct New 345 kV Station | Interconnect SanPat Solar I and SanPat Solar II to the new Lucero 345 kV station on the Angstrom to Naismith 345 kV line | NEW | Lucero |  | Planned | TP2023838 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-11-30 |  | 345 | 0.2 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8249, 8659, 80039 | Y | N |  |  | 79989 | 79988
45397 | Lion: 138 kV Station & Transmission Line | Lion: 138 kV Station with new line to Stewart Road |  | Lion | Stewart Road | Planned | 885 - 1063 | AEP TCC | Michael Glueck mlforcum@aep.com 918-599-2674 | 3672 TP2018218 | 2026-11-30 |  | 138 | 2.71 | 0 | 40 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8758, 8951, 8969 | Y | N |  |  | 65528 | 45397
66447 | Reforzar: Construct New 345 kV Station | Construct a new 345 kV station on the Lon Hill to North Edinburg 345 kV line | Project Title, Project Description, Estimated Cost, RPG Number, and RPG Dates Update | Reforzar |  | Planned |  | AEP TCC | Joseph C Isaac mlforcum@aep.com 918-599-2674 | TP2022035 | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Brooks |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8455, 8905, 80078 | Y |  |  |  | 67317 | 66447
67318 | Cruce: Construct New 345 kV Station | Construct a new 345 kV station on the Cenizo to Reforzar 345 kV line and the Del Sol to San Miguel 345 kV line | Contact and County Update | Cruce |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022034 | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Jim Hogg |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079 | Y |  |  |  | 67319 | 67318
67322 | Cenizo to Cruce: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cenizo to Cruce | Contact Update | Cenizo | Cruce | Planned |  | AEP TCC/ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022031 | 2026-11-30 |  | 345 | 69 | 0 | 0 |  | Webb | Jim Hogg | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079, 80220 | Y |  |  |  | 67323 | 67322
67324 | Cruce to Del Sol: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cruce to Del Sol | Contact and County Update | Cruce | Del Sol | Planned |  | AEP TCC/ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2022032 | 2026-11-30 |  | 345 | 54.2 | 0 | 0 |  | Jim Hogg | Starr | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079, 80355 | Y |  |  |  | 67325 | 67324
67326 | Ajo to Reforzar: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Ajo to Reforzar | Contact Update | Ajo | Reforzar | Planned |  | AEP TCC/ETT | Curtis Brown jlsolis@aep.com 361-881-5574 | TP2022030 | 2026-11-30 |  | 345 | 11 | 0 | 0 |  | Kenedy | Brooks | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80076, 80078 | Y |  |  |  | 67327 | 67326
61396 | Hamilton Road to Maxwell: Rebuild 138 kV Line | Rebuild the Hamilton Road to Maxwell 138 kV line | In-Service Date Update | Hamilton Road | Maxwell | Planned |  | AEP TCC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | TA2019800 | 2026-11-30 |  | 138 | 0 | 29 | 0 |  | Val Verde | Val Verde | Tier 3 | 20RPG022 | 2020-11-02 | 2021-01-19 |  | 8257, 8998 | Y |  |  |  | 65593 | 61396
70630 | Ballinger to Santa Anna: Rebuild 69 kV line | Rebuild 69 kV line and rebuild taps on the Ballinger to Santa Anna 69 kV line. | Contact and In-Service Date Update | Ballinger | Santa Anna | Planned |  | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | TA2021193 | 2026-11-30 |  | 69 | 0 | 0 | 0 |  | Runnels | Coleman | Tier 3 | 22RPG028 | 2022-08-01 | 2022-09-01 |  | 6329, 6338, 6341, 6342, 6343, 6344, 6345, 6346, 6349, 6353, 60019, 60024, 60029 | Y |  |  |  | 70664 | 70630
68183 | Estes to Putnam: Rebuild 138 kV line | Rehab the Abilene South to Putnam 138 kV line | Contact and In-Service Date Update | Estes | Putnam | Under Construction | 68150 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 |  | 2026-11-30 |  | 138 | 0 | 15 | 0 |  | Callahan | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6309, 60365, 61015 | Y | N |  |  | 68184 | 68183
73061 | Falfurrias to King Ranch: 138 kV Line Rebuild | Rehab the Falfurrias to King Ranch 138 kV line | Contact Update | Falfurrias | King Ranch | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2026-11-30 |  | 138 | 0 | 20.5 | 0 |  | Brooks | Kleberg | Tier 4 |  | 2023-01-24 | 2023-02-24 |  | 8510, 80228 | Y | N |  |  | 73062 | 73061
87069 | LST_Phantomhill_Hub Conversion | Loop another circuit of the LST Crez line into Phantom Hill station as part of Gen Interconnection Project 23INR0244, 22INR0457 and 20INR0242 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68000, 68001, 68004 | Y |  |  |  | 87070 | 87069
67329 | San Miguel to Cruce 345 kV lines | New San Miguel to Cruce 345 kV double circuit lines |  | San Miguel | Cruce | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 345 | 231.12 | 0 | 0 |  | Atascosa | Duval | Tier 1 | 21RPG017 | 2021-09-23 | 2021-12-23 |  | 5901, 80079 | Y |  |  |  | 67330 | 67329
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  |  | 5705 | Y | N |  |  | 9835 | 2554
75524 | This converts Bell County to Gabriel to 138 KV |  |  | Bell County | Gabriel | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-12-12 |  | 138 | 0 | 0 | 0 |  | Bell | Williamson | Tier 4 |  |  |  |  | 114, 118, 122, 132, 133, 7345, 7346 | Y |  |  |  | 75525 | 75524
87653 | Bluff Creek to Scurry Chevron Line Rebuild | Rebuild Bluff Creek to Scurry Chevron |  | Bluff Creek | Scurry Chevron | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9002 | 2026-12-15 |  | 138 | 0 | 16 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  |  | 1309, 1310, 1312 | Y |  |  |  | 87654 | 87653
87010 | Establish Drill Hole 345/138 kV Switch | Establish Drill Hole 345/138 kV Switch |  | Drill Hole Switch | Drill Hole Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8725 | 2026-12-15 |  | 345 | 0 | 0 | 1200 |  | Culberson | Culberson | Tier 1 | 24RPG010 | 2024-03-18 |  |  | 10073, 10074, 10075, 10076, 11090, 11271, 11272, 18709 | Y |  |  |  | 87735 | 87010
76696 | Construct a new Border Ã¢â‚¬â€œ Shifting Sands 138 kV Line | Construct a new Border – Shifting Sands 138 kV Line |  | Atchison | Shifting Sands | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8628 | 2026-12-15 |  | 138 | 22.3 | 0 | 0 |  | Loving | Winkler | Tier 2 |  |  |  |  | 11089, 11189, 11392, 18672, 18705 | Y |  |  |  | 87872 | 76696
76712 | Bluff Creek to China Grove Line Rebuild | Rebuild existing 138 kV Line |  | Bluff Creek 138 kV Switch | China Grove Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8655 | 2026-12-15 |  | 138 | 0 | 12.8 | 0 |  | Scurry | Mitchell | Tier 3 |  |  |  |  | 1309, 1318 | Y |  |  |  | 87645 | 76712
80546D | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild and double-circuit the Sonterra - Salado 138 kV Line Section. Establish Salado 138 kV Switch and the Salado Switch - Round Rock Switch 138 kV Line |  | Sonterra | Salado Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 121, 3640, 3664, 3667, 3668, 3677, 3730, 3764, 3777, 13640, 13641, 61413640 | Y |  |  |  | 87642 | 80546 | 2023-SC17
87017 | Riverton - Sandlake 138 kV Line Conversion 345 kV and Riverton - Sandlake 138 kV Line | Convert Riverton – Sandlake 138 kV Line to 345 kV and Establish Riverton – Sandlake 138 kV Line |  | Riverton | Sandlake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8793 | 2026-12-15 |  | 345 | 39.9 | 0 | 0 |  | Ward | Reeves | Tier 1 | 24RPG010 | 2024-03-18 |  |  | 1011, 11083, 11084, 11097, 11098 | Y |  |  |  | 87679 | 87017
78361 | Lake Creek - Rattlesnake Road 345 kV Line | Rebuild the Lake Creek - Rattlesnake Road 345 kV Line (McLennan Area Project) |  | Lake Creek | Rattlesnake Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6276 | 2026-12-15 |  | 345 | 0 | 5.1 | 0 |  | McLennan | McLennan | Tier 3 |  |  |  |  | 3384, 3399, 3409 | Y |  |  |  | 81575 | 78361
73567 | LCRATSC_BerryCreek_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor Andice substation addition. |  | Berry Creek |  | Conceptual |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7361, 7521, 70522 | Y | N |  |  | 78401 | 73567
81227 | Cattleman – Gascondades 345 kV Reroute | Terminate Morgan Creek – Gascondades 345 kV Line into Cattleman 345 kV Switch |  | Cattleman | Gascondades | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8647 | 2026-12-15 |  | 345 | 0 | 2.5 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 10053, 76030 | Y |  |  |  | 81664 | 81227
72958 | Graham to Cottonwood 69 kV Line Rebuild | Graham to Cottonwood 69 kV Line Rebuild |  | Graham | Graham | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3001 | 2026-12-15 |  | 69 | 0 | 0 | 0 |  | Young | Young | Tier 4 |  |  |  |  | 1597, 1602, 1603 | Y |  |  |  | 72959 | 72958
76654 | Establish Voss Lake 345/138 kV Switch | Establish Voss Lake 345/138 kV Switch |  | Voss Lake | Voss Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6278 | 2026-12-15 |  | 345 | 0 | 5.6 | 600 | 0,110.4 | Milam | Milam | Tier 3 |  |  |  |  | 3675, 3678, 3687, 3717, 3740, 3750, 3751, 3752, 3761, 13429, 13430 | Y |  |  |  | 76655 | 76654 | 2023-SC9
81299 | Ranger Camp – Prong Moss 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Ranger Camp | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2026-12-15 |  | 345 | 0 | 61.4 | 0 |  | Mitchell | Howard | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 10057 | Y |  |  |  | 81300 | 81299
87413 | Establish Fallstown Switch – Pleasant Valley/Fisher Road 138 kV Double-Circuit Line and Fallstown Switch – Ceramic/Wichita Falls PPG 138 kV Double-Circuit Line | Establish Fallstown Switch – Pleasant Valley/Fisher Road 138 kV Double-Circuit Line and Fallstown Switch – Ceramic/Wichita Falls PPG 138 kV Double-Circuit Line |  | Fallstown Switch | Pleasant Valley/Fisher Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4024 | 2026-12-15 |  | 138 | 0 | 10.7 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1450, 1483, 1484, 1485, 1488, 17005 | Y |  |  |  | 87414 | 87413
81152 | China Grove to Tributary Line Rebuild | Rebuild China_Grove - Tributary 138 kV Line |  | China Grove | Tributary Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8656 | 2026-12-15 |  | 138 | 0 | 23.7 | 0 |  | Mitchell | Howard | Tier 3 |  |  |  |  | 1318, 1394 | Y |  |  |  | 87650 | 81152
68706 | Edgewood Switch – Royse Switch 138 kV Line | Rebuild and convert the Edgewood-Iron Bridge 69 kV to 138 kV operation |  | Edgewood | Able Springs | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3227 | 2026-12-15 |  | 69 | 0 | 0 | 0 |  | Van Zandt | Kaufman | Tier 4 |  |  |  |  | 2471, 2721, 3163, 3165, 3167, 3168, 3169, 3181, 3182, 3185, 3188, 3189, 3191, 3192, 3193, 6920, 6922, 12467, 12469, 12470, 12472, 13188, 13191 | Y |  |  |  | 68707 | 68706
22TPIT0000 | Parkway Substation | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10680 | 3324
64239 | Vineyard Switch-Cypress Waters Switch 138 kV Line | Construct a new 138 kV circuit from Vineyard to Cypress Waters |  | Cypress Waters Switch | Vineyard Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5320 | 2026-12-15 |  | 138 | 7.4 | 0 | 0 |  | Dallas | Tarrant | Tier 3 |  |  |  |  | 2017, 2022, 2386, 12012, 12013, 15030, 15031, 15035, 15040, 15041 | Y |  |  |  | 86787 | 64239
71156 | Ennis West Switch-Waxahachie Switch 138 kV Line Rebuild | Rebuild the Ennis West-Waxahachie 138 kV Line |  | Ennis West | Waxahachie | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4200 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2241, 2321, 12320 | Y |  |  |  | 71160 | 71156
76669 | Rebuild Elbow to Redberry to Bulldog 138 kV Line | Rebuild Elbow to Redberry to Bulldog 138 kV Line |  | Elbow | Bulldog | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8666 | 2026-12-15 |  | 138 | 0 | 18.5 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 10080, 23833, 23834 | Y |  |  |  | 77043 | 76669
78046 | TOYAH CREEK 345 kV Switch | Adding Oncor's portion of TNMP Silverleaf and Cowpen 345/138-kV Stations Project (23RPG013) |  | Sand Lake | Solstice | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8715 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Ward | Pecos | Tier 1 | 23RPG013 | 2023-05-18 | 2023-06-09 |  | 11098, 18669, 60404 | Y |  |  |  | 78049 | 78046
71182 | Reiter 345/138 kV Switch | Construct a new 345/138 kV switch |  | Odessa EHV | Wolf/Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8629 | 2026-12-15 |  | 345 | 0 | 0 | 1200 |  | Ector | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1018, 11010, 11028, 18544, 18545, 18546, 18547 | Y |  |  |  | 81601 | 71182
78044 | ROCK DRAW 345 kV Switch | Adding Oncor's portion of TNMP Silverleaf and Cowpen 345/138-kV Stations Project (23RPG013) |  | Sand Lake | North McCamey | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8716 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Ward | Upton | Tier 1 | 23RPG013 | 2023-05-18 | 2023-06-09 |  | 11098, 18668, 76000 | Y |  |  |  | 78048 | 78044
87021 | Construct Drill Hole – Riverton 345 kV Double-Circuit | Construct Drill Hole – Riverton 345 kV Double-Circuit |  | Drill Hole Switch | Riverton Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8748 | 2026-12-16 |  | 345 | 36 | 0 | 0 |  | Culberson | Reeves | Tier 1 | 24RPG010 | 2024-03-18 |  |  | 10073, 11084 | Y |  |  |  | 87022 | 87021
81418 | Reiter to Yarbrough 138 kV Line Rebuild | 138 kV existing line rebuild. |  | Reiter | Yarbrough | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8527 | 2026-12-16 |  | 138 | 0 | 27.2 | 0 |  | Ector | Crane | Tier 3 |  |  |  |  | 11111, 18545 | Y |  |  |  | 81419 | 81418
73436 | Rockhound - Connell 345 kV Double-Circuit Line | Construct a new 345 kV Double-Circuit Line and establish a 345/138 kV Switch |  | Rockhound | Connell | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8718, R8807 | 2026-12-16 |  | 345 | 10 | 0 | 1200 |  | Martin | Midland | Tier 2 |  |  |  |  | 10033, 10036, 10062, 10085, 10086, 10087, 10088, 10089, 11371, 23840, 23841, 23855 | Y |  |  |  | 81403 | 73436
72502 | Tarpley Substation Upgrades | Provide transmission point of interconnection to Battery energy storage system near the Tarpley Substation. Add a 138kV bay and associated circuit breaker to existing substation (25INR0188) |  | Tarpley |  | Planned |  | BEC | Jhonatan Guerrero Rivera j.rivera@banderaelectric. 830-612-0048 |  | 2026-12-30 |  | 69 | 0.1 | 0 | 0 |  | Bandera |  | Tier 4 | [5 empty] | Y | N |  |  | 72503 | 72502
81415 | Tonkawa Switch Syncrhonous Condenser | Add Tonkawa Switch Syncrhonous Condenser |  | Tonkawa | Tonkawa | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | D20232 | 2026-12-30 |  | 345 | 0 | 0 | 0 | 0,350 | Scurry | Scurry | Tier 1 |  |  |  |  | 1048, 18556, 18557 | Y |  |  |  | 81416 | 81415
81410 | Reiter Switch Syncrhonous Condenser | Add Reiter Switch Syncrhonous Condenser |  | Reiter | Reiter | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | D20231 | 2026-12-30 |  | 345 | 0 | 0 | 0 | 0,350 | Ector | Ector | Tier 1 |  |  |  |  | 18544, 18553, 18554 | Y |  |  |  | 81411 | 81410
81034 | Lamesa - Willow Valley 138 kV Line | Rebuild Lamesa to Willow Valley 138 kV line. |  | Lamesa Switch | Willow Valley Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8654 | 2026-12-30 |  | 138 | 0 | 32.1 | 0 |  | Borden | Dawson | Tier 3 |  |  |  |  | 1163, 1301, 1307, 1308 | Y |  |  |  | 81035 | 81034
81686 | Blu Lacy: Construct New 345 kV Station | Interconnect the Pi load to the new Blu Lacy 345 kV station on the Lon Hill to Reforzar and Lon Hill to Nelson Sharpe 345 kV lines and add capacitors |  | Blu Lacy |  | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-12-30 |  | 345 | 0 | 0 | 0 | 0,523.6 | Nueces |  | Tier 3 |  |  |  |  | 8455, 80078, 84550, 85000 | Y | N |  |  | 81687 | 81686
75786 | This project will create a POI Bus (station) named Skydancer to interconnect 23INR0295 | This project will create a POI Bus (station) named Skydancer to interconnect 23INR0295 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 68055, 68080, 68090 | Y |  |  |  | 75787 | 75786
87429 | Reconductor Wickett to Staghorn 138kV line. |  |  | TNMP Wickett (37981) | TNMP Staghorn (37990) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 12.05 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37981, 37990 | Y |  |  |  | 87430 | 87429
87431 | Rebuild Wickett to Winkler 69kV line. |  |  | TNMP Winkler (37960) | TNMP Wickett (37980) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 6.8 | 0 |  | Winkler | Ward | Tier 4 |  |  |  |  | 37960, 37980 | Y |  |  |  | 87432 | 87431
86771 | Scissortail: Construct New 138 kV Station | Interconnect the TNMP Flycatcher station to the new Scissortail 138 kV station on the Saragosa to Solstice 138 kV line between Hoef's Road and Verhalen | NEW | Scissortail |  | Planned | TP2024044 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 6077, 60207, 60808 | Y | N |  |  | 86772 | 86771
87423 | Reconfigure TNMP Pyote 138kV Substation. |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0.92 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37990, 38001, 38005 | Y |  |  |  | 87424 | 87423
67422F | Greens Bayou to Clinton 138kV Conversion | Remove CASTEN and Wallisville substations from Ckt.10A service. Resulting in Ckt.10A Clinton to Greens Bayou |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40250, 40352, 40720, 41682 | Y | N |  |  | 87579 | 67422
78468 | Pradera (PRD) CEHE-Owned 345kV Substation for Austin Bayou Solar (25INR0102) | New 345kV Pradera (PRD) substation for generator interconnection to Austin Bayou Solar (25INR0102). Loop Ckt.27 into Pradera substation to create new Ckt.27 Seabreeze to Pradera to Savannah. Install generator lead from Pradera (PRD) substation to AUSTIN (ABY) customer substation (25INR0102). |  | Pradera | Savannah/ Seabreeze | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42590, 43020, 43180 | Y | N |  |  | 87142 | 78468
73441 | Dupont Switch to Joslin: Rebuild 138 kV Line | Rehab the Dupont Switch to Joslin 138 kV Line | TSP/Company Contact, In-Service Date, and Tier Update | Dupont | Joslin | Planned |  | AEP TCC | Travis Coody mlforcum@aep.com 918-599-2674 |  | 2026-12-31 |  | 138 | 0 | 32.6 | 0 |  | Victoria | Calhoun | Tier 4 | 22RPG040 | 2022-11-01 | 2022-12-01 |  | 8140, 8141, 8143, 80064 | Y |  |  |  | 73442 | 73441
76916 | Snapdragon: Construct New 138 kV Station | Interconnect Desert Vine Solar to the new Snapdragon 138 kV station on the Revilla to Zapata 138 kV line | Title, Description, Location, Status, Contact, In-Service Date, Cost, and County Update | Snapdragon |  | Planned |  | AEP TCC/ETT | Adam Wells jlsolis@aep.com 361-881-5574 | TP2023012 | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 8299, 8736, 8957 | Y | Y |  |  | 76917 | 76916
77803 | Cowpen 345kV station from TNMP submitted Cowpen/Silverleaf RPG |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 345 | 14.26 | 0 | 1500 |  | Reeves | Reeves | Tier 1 |  | 2023-05-11 | 2023-11-27 | 2024-01-09 | 18669, 38023, 38027, 38042, 38043, 38044, 38045, 38048, 38055 | Y |  |  |  | 77804 | 77803
81657 | Verhalen: Construct New 138 kV Terminal | Interconnect the Eta load to the existing Verhalen 138 kV station | NEW | Verhalen |  | Conceptual |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60207 | Y |  |  |  | 81658 | 81657
81783 | Ingleside to Seabird: Construct New 138 kV Line | Interconnect the Mu load to the new Seabird 138 kV station on the Homeport to Ingleside 138 kV line, construct a new 138 kV line from Ingleside to Seabird, and add capacitors | NEW | Ingleside | Seabird | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-12-31 |  | 138 | 2.9 | 0 | 0 | 0,69.1 | San Patricio | Nueces | Tier 4 |  |  |  |  | 8425, 8808, 84250 | Y | N |  |  | 81784 | 81783
81825 | Houdini: Construct New 345 kV Station | Interconnect the Xi load to the new Houdini 345 kV station on the STP to WAP 345 kV line |  | Houdini |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 43990, 44000, 88800 | Y |  |  |  | 81826 | 81825
70628 | Japhet 138kV Distribution Sub and Upgrades | Upgrade portions of 69kV Ckt.12 Garden Villas to Bringhurst to Clinton. Install new 138kV Japhet distribution substation. Move 69kV Bringhurst substation load to new Japhet substation and retire Bringhurst substation. Retire portions of Ckt.12 and convert the remaining portions of Ckt.12 to 138kV service. Loop new Japhet substation to create new 138kV Ckt.13 University to Japhet to Clinton. |  | Japhet | University/Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40350, 40352, 42690, 45070, 47540, 47700, 47760, 47764 | Y | N |  |  | 78244 | 70628
81368 | Rio Pecos: Upgrade 138 kV Terminals | Upgrade the Soaptree and Whitebaker 138 kV terminals at the Rio Pecos 138 kV station | Contact Update | Rio Pecos |  | Planned | TP2023625 | AEP TNC | Russell Burnett twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6601, 38445 | Y | N |  |  | 81369 | 81368
80315 | Big Foot to Pearsall: Convert to 138 kV | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch | NEW | Big Foot | Pearsall | Planned | 1104 - 1282 | AEP TCC | Will Simmons mlforcum@aep.com 918-599-2674 | 3821 | 2026-12-31 |  | 138 | 0 | 14.79 | 0 |  | Frio | Frio | Tier 4 | 23RPG024 | 2023-08-29 | 2023-09-28 |  | 8216, 8218, 8221, 8752 | Y |  |  |  | 80316 | 80315
80317 | Dilley Switch to Pearsall: Convert to 138 kV, Reroute from Dilley to Dilley Switch, Rebuild Dilley to Dilley Switch 69 kV, and Double Circuit Dilley Switch to Pearsall with Dilley to Dilley Switch | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch | Contact, In-Service Date, and RPG Date Update | Dilley Switch | Pearsall | Planned | 1104 - 1282 | AEP TCC | Will Simmons jlsolis@aep.com 361-881-5574 | 3822 | 2026-12-31 |  | 138 | 0 | 19.8 | 0 |  | Frio | Frio | Tier 4 | 23RPG024 | 2023-08-29 | 2023-09-28 |  | 8208, 8210, 8212, 8216, 8752 | Y |  |  |  | 80318 | 80317
80319 | Devine: Install Cap Bank | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch | Contact and In-Service Date Update | Devine |  | Planned |  | ETT | Will Simmons jlsolis@aep.com 361-881-5574 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 | 0,23 | Medina |  | Tier 4 | 23RPG024 | 2024-08-23 | 2024-09-23 |  | 8732 | Y |  |  |  | 80322 | 80319
81659 | Lytle: Construct New 138 kV Terminal | Interconnect the Cinco II load to the existing Lytle 138 kV station and add capacitors | NEW | Lytle |  | Conceptual |  | AEP TCC/ETT | John Solis jlsolis@aep.com 361-881-5574 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 | 0,34.5 | Medina |  | Tier 4 |  |  |  |  | 8962 | Y |  |  |  | 81660 | 81659
81697 | Amber: Construct New 345 kV Station | Interconnect the Kappa load to the new Amber 345 kV station on the Blue Lacy to Reforzar and Blue Lacy to Nelson Sharpe 345 kV lines and add capacitors |  | Amber |  | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 | 0,523.6 | Nueces |  | Tier 3 |  |  |  |  | 80078, 84550, 84555, 85000 | Y |  |  |  | 81698 | 81697
81799 | Four Corners: Construct New 345 kV Station | Interconnect the Nu load to the new Four Corners 345 kV station on the Edith Clarke to Tesla 345 kV line |  | Four Corners |  | Conceptual |  | AEP TNC/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Hardeman |  | Tier 4 |  |  |  |  | 60501, 60505, 61616 | Y | N |  |  | 81800 | 81799
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0733 | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y | Y |  |  | 11872 | 4320
51005 | Rocksprings to Friess Ranch: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line | Contact Update | Rocksprings | Friess Ranch | Planned | 1044 - 1217 | AEP TCC/AEP TNC, ETT | Greg Crane deevans@aep.com 918-599-2938 | 2792 | 2026-12-31 |  | 69 | 0 | 22.6 | 0 |  | Edwards | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 8238, 60210 | Y | N |  |  | 51006 | 51005
55421 | Ballinger to Concho: Rebuild 69 kV line | Rebuild Ballinger to Concho 69 kV line, install POP switch for Rowena, install CB at Miles, install POP switch for Harriett REA | Terminal To Location, TSP/ Company Contact, and In-Service Date Update | Ballinger | San Angelo Concho | Planned | 1088 - 1271 | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 | 1861 | 2026-12-31 |  | 69 | 0 | 20.45 | 0 |  | Runnels | Tom Green | Tier 3 | 20RPG004 | 2020-04-08 | 2020-04-30 | 2020-05-08 | 6338, 6409, 6410, 6411, 6412, 6413, 6450 | Y | N |  |  | 55422 | 55421
64499 | Hyde Park to Downtown Ckt.32A Upgrades | Upgrade Hyde Park to Downtown Ckt.32A |  | Downtown | Hyde Park | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 345 | 0 | 1.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47500, 47510, 47570, 47690 | Y | N |  |  | 64500 | 64499
66366 | Rebuild Brazoria - Retrieve 138kV with bundled 795 ACSS | Planned ISD is Q4 2024, but project design currently under internal review. |  | TNMP Brazoria (bus # 39600) | CenterPoint Retrieve (bus # 43170) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 6.17 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39600, 43170 | Y |  |  |  | 66367 | 66366
68205 | GENRAL to Garden Villas Rebuild | Rebuild and Reconductor portion of Ckt.12B GENRAL to Garden Villas to prepare for future 138kV Conversion |  | GENRAL | Garden Villas | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 69 | 0 | 9.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42690, 47670 | Y | N |  |  | 68206 | 68205
69888A | Deepwater to Clinton Ckts.33B-33C Line Upgrades | Fully reconductor Ckt.33B Deepwater to Texpet Switchrack to Harrisburg ahead of future 138kV conversions. |  | Deepwater | Harrisburg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 69 | 0 | 3.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40470, 40800, 41560, 41561 | Y | N |  |  | 70971 | 69888
77805 | TNMP Pecos County RPG |  |  | Leon Creek (bus # 38355) | Coyanosa (bus # 38380) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 31.2 | 0.6 | 0 |  | Pecos | Reeves | Tier 1 |  | 2023-08-02 | 2024-02-08 | 2024-03-06 | 6601, 38355, 38380, 38445 | Y |  |  |  | 77806 | 77805
77807 | Silverleaf 345kV station from TNMP submitted Cowpen/Silverleaf RPG |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 345 | 4.05 | 0 | 2250 |  | Ward | Ward | Tier 1 |  | 2023-05-11 | 2023-11-27 | 2024-01-09 | 18668, 38091, 38143, 38145, 38147, 38148, 38149, 38150, 38165 | Y |  |  |  | 77808 | 77807
78461B | West Columbia to Damon and Needville to Big Creek Ckt.89A Upgrades | Rebuild/reconductor Needville to Big Creek Ckt.89 as a Hardening upgrade. |  | Needville | Big Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 5.46 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42380, 42390 | Y | N |  |  | 78463 | 78461
67422G | Greens Bayou to Clinton 138kV Conversion | Convert Wallisville substation from Ckt.10A service to 138kV loop service on unnamed 138kV Greens Bayou to Clinton Ckt.xx to create new Ckt.xx TEXWAL to Wallisville to Clinton. Serve CASTEN customer substation from Wallisville with dedicated transformer service. |  | Greens Bayou | Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 2.17 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40250, 40350, 41575, 41660, 41680 | Y | N |  |  | 87580 | 67422
87497 | [5 empty] | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-01-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6903, 6908 | Y |  |  |  | 87498 | 87497
81590 | Rio Medina substation | Adds Rio Medina Load serving station |  | Rio Medina |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-01-01 |  | 138 | 4.5 | 0 | 0 |  | Medina |  | Tier 2 |  |  | 2024-02-01 |  | 5804, 5805 | Y | N |  |  | 81591 | 81590
67320 | Cruce to Reforzar: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cruce to Reforzar | Contact and County Update | Cruce | Reforzar | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022033 | 2027-01-01 |  | 345 | 48 | 0 | 0 |  | Jim Hogg | Brooks | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80078, 80079 | Y |  |  |  | 67339 | 67320
87508 | [5 empty] | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-01-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6894, 6902 | Y |  |  |  | 87509 | 87508
87510 | [5 empty] | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-01-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6902 | Y |  |  |  | 87511 | 87510
87512 | [5 empty] | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-01-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6904 | Y |  |  |  | 87513 | 87512
87514 | [5 empty] | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-01-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6903, 6904 | Y |  |  |  | 87515 | 87514
81594 | Dunlay substation | Adds STEC Dunlay Load serving station |  | Dunlay |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-01-01 |  | 138 |  | 0 | 0 |  | Medina |  | Tier 2 |  |  |  |  | 5802, 5807, 5813 | Y | N |  |  | 81595 | 81594
65837 | New Cachena Substation |  |  | 5133 | 5323 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 5068, 5133, 5323 | Y |  |  |  | 65838 | 65837
65154 | Mason Switch to Yellowjacket: Rebuild 69 kV Line | Rehab the Mason Switch to Yellowjacket 69 kV Line | Contact Update | Mason Switch | Yellowjacket | Planned | 1142 - 1320 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 | 2836 | 2027-01-31 |  | 69 | 0 | 26.45 | 0 |  | Menard | Mason | Tier 4 | 21RPG014 | 2021-08-01 | 2021-09-01 |  | 6363, 6396, 23824 | Y | N |  |  | 65155 | 65154
86800 | Pendulo: Construct New 345 kV Terminal | Interconnect Rubicon Alpha Wind to the Pendulo 345 kV station | NEW | Pendulo |  | Planned | TP2024057 | ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60507 | Y | N |  |  | 86801 | 86800
86884 | Saragosa: Construct New 138 kV Terminal | Interconnect Bracero Pecan Storage to the Saragosa 138 kV station | NEW | Saragosa |  | Planned | TP2024091 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-02-28 |  | 138 | 0.5 | 0 | 0 |  | Reeves |  | Tier 4 |  | 2024-03-21 | 2024-04-12 |  | 60716 | Y | N |  |  | 86885 | 86884
55550 | Brushline: Construct New Distribution Station | Construct new 138/13 kV station Brushline | Contact and In-Service Date Update | Brushline |  | Planned | 1106 - 1284 | AEP TCC | Richard Locke twang1@aep.com 918-599-2635 | 3826 | 2027-02-28 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 5754, 8963, 8972 | Y |  |  |  | 55551 | 55550
79456A | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072) | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072). Loop Ckt.18 into Huizache substation to create new Ckt.18 Speedway to Huizache to DOW. |  | Huizache | Speedway/DOW | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-02-28 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 43060, 46640 | Y | N |  |  | 87175 | 79456
79456B | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072) | Install generator lead from Huizache (HUI) substation to customer substation HIGHCH (HIC) for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072). |  | Huizache | HIGHCH (High Chap) | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-02-28 00:01 |  | 345 | 0.07 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 87176 | 79456
86912 |  |  |  | Gabriel | Schwertner | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-02 |  | 138 | 0 | 12.6 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 122, 7346 | Y |  |  |  | 86913 | 86912
80342 |  |  |  | HILLTOP LAKES | HILLTOP LAKES | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 0 | 60 |  | Leon | Leon | Tier 4 |  |  |  |  | 47, 48 | Y |  |  |  | 80343 | 80342
80336 |  |  |  | WESTLOOP | BROCK | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 2.23 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 480, 487 | Y |  |  |  | 80337 | 80336 | 2023-NC26
80340 |  |  |  | Keith Switch | Iola | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 6.1 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 2, 4 | Y |  |  |  | 80341 | 80340
78173 |  |  |  | Trimmier | Trimmier | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 0 | 0 | 0,12 | Bell | Bell | Tier 4 |  |  |  |  | 136 | Y |  |  |  | 78174 | 78173
78179 |  |  |  | Ding Dong | Ding Dong | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 0 | 0 | 0,12 | Bell | Bell | Tier 4 |  |  |  |  | 115 | Y |  |  |  | 78180 | 78179
72568 | Friendship to Rutherford Storm Hardening | Rebuild single circuit section of Friendship to Rutherford and reconductor with bundled 795 ACSR Conductor, 440 MVA. Replaces Project ID 61270. |  | Friendship | Rutherford | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-03-15 |  | 138 | 0 | 4.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70507, 70509 | Y | N |  |  | 72569 | 72568
61449 | Clark Church (Ottine New) Substation | Build New 69/138 Substation by Birdhouse to Replace existing Ottine station, add 20MVA; demo existing Ottine substation |  | Ottine | Ottine | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2027-03-25 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7594 | Y | N |  |  | 61450 | 61449
77172 | Add new carbon capture load at Alazan | Project will be modified after station engineering is completed. | Contact and In-Service Date Update | Alazan |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Kleberg |  | Tier 4 |  |  |  |  | 8515 | Y |  |  |  | 77173 | 77172
69471 | Villa Cavazos: Construct New 138 kV Terminal | Interconnect Eval BESS to the Villa Cavazos 138 kV station | Description, Contact, and In-Service Date Update | Villa Cavazos |  | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2027-03-31 |  | 138 | 0.35 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 80229 | Y |  |  |  | 69472 | 69471
80295 | Add 2nd transformer at Ponder | Add 2nd transformer at Ponder |  | Ponder | Ponder | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-04-15 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 642 | Y |  |  |  | 80296 | 80295
87027 | Black Bayou: Construct New 138 kV Terminal | Interconnect Two Brothers BESS to the Black Bayou 138 kV station | NEW | Black Bayou |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | TP2024060 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 8911 | Y |  |  |  | 87028 | 87027
86802 | Saragosa: Construct New 138 kV Terminal | Interconnect Cantaloupe Solar & Storage to the Saragosa 138 kV station | NEW | Saragosa |  | Planned | TP2024067 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60716 | Y | N |  |  | 86803 | 86802
81576 | Tesla: Build new 345 kV Terminal to interconnect Beta | Interconnect the Lancium load to the existing Tesla 345 kV station | Description, Status, In-Service Date, Dollars, and Circuit Miles Update | Tesla |  | Planned | TP2024048 | ETT/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-04-30 |  | 345 | 0.5 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501 | Y |  |  |  | 81577 | 81576
54892 | Eden to North Brady: Rebuild 69 kV line | Rehab Eden to North Brady 69 kV line |  | Eden | North Brady | Planned | 1039 - 1266 | AEP TNC | Larry Brown twang1@aep.com 918-599-2635 | 1856 | 2027-04-30 |  | 69 | 0 | 32.7 | 0 |  | Concho | McCulloch | Tier 3 | 22RPG009 | 2022-03-23 | 2022-04-14 |  | 6006, 6372, 6380, 6384, 6385, 60005, 60797 | Y | N |  |  | 65568 | 54892
70662 | Cobra: Build new 345 kV station | Interconnect Garcitas Solar to the new Cobra 345 kV station on the Radiant to Static 345 kV line | Contact Update | Cobra |  | Planned |  | AEP TCC | Adam Wells deevans@aep.com 918-599-2938 | TP2022750 | 2027-04-30 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5915, 8676, 8715, 8728 | Y |  |  |  | 70663 | 70662
73032 | Mulberry Creek: Rebuild 138 kV Station | Rebuild Mulberry Creek 138 kV station | Projected In-Service Date Update | Mulberry Creek |  | Planned |  | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 |  | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6231, 6232, 6235, 6288 | Y | N |  |  | 73033 | 73032
87019 | Rincon: Upgrade 138 kV Bus | Upgrade the Rincon 138 kV bus | NEW | Rincon |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2024029 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8418, 8437, 8961 | Y |  |  |  | 87020 | 87019
58010 | North McAllen: Rebuild 138 kV Station | Rehab the North McAllen 138 kV station | Contact and In-Service Date Update | McAllen |  | Planned | 1118 - 1296 | AEP TCC | Thomas Neils jlsolis@aep.com 361-881-5574 | 3837 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8368, 8631, 8632 | Y |  |  |  | 65583 | 58010
76121 | Beeville Capacitor Addition | Add second 4.8 MVAR step at Beeville |  | Beeville |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-05-01 |  | 69 | 0 | 0 | 0 | 0,4.8 |  |  | Tier 4 |  |  |  |  | 5674 | Y | N |  |  | 76122 | 76121
73366 | CPSE_New_Wiseman_Substation | Loop new 138 kV substation into existing 138kV Cagnon to Helotes Transmission Line. | [5 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5055, 5200, 5487 | Y |  |  |  | 73367 | 73366
76790 | Upgrade Pearsall Auto | Upgrade Pearsall Auto |  | Pearsall | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5893, 5895 | Y |  |  |  | 76791 | 76790
88041 | Rebuild Leon Creek to Pearsal |  |  |  |  | Planned | T-0396 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5260, 5335 | Y |  |  |  | 88042 | 88041
76123 | D'Hanis Capacitor 2nd step addition | D'Hanis Capacitor 2nd step addition 9.6 MVAR |  | D'Hanis |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-05-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5814 | Y | N |  |  | 76124 | 76123
76777 | Rebuild Nursery-El Toro | Rebuild Nursery- Fordtran Sw- Inez - El Toro Sw Station to 795 ACSR |  | Nursery | El Toro | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-05-01 |  | 69 | 0 | 24.8 | 0 |  | Victoria | Jackson | Tier 4 |  |  |  |  | 5504, 5510, 5514, 5516 | Y |  |  |  | 76778 | 76777
84892 | New transmission line between Tally and Ranchtown |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5358, 5422 | Y |  |  |  | 84893 | 84892
84894 | Upgrade transmission line between Tally and Texas Research |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5422, 5430 | Y |  |  |  | 84895 | 84894
20TPIT0000 | Parkway Substation T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2027-05-14 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10679 | 3323
87770 | Establish a 110.4 MVAR Capacitor Bank at Midnight 138 kV Substation | Establish a 110.4 MVAR Capacitor Bank at Midnight 138 kV Substation |  | Midnight Substation | Midnight Substation | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6346 | 2027-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Williamson | Williamson | Tier 4 |  |  |  |  | 3677 | Y |  |  |  | 87771 | 87770
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line | Project Deferral | Handley | Hemphill | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5214 | 2027-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 11818 | 4270
87768 | Establish a 110.4 MVAR Capacitor Bank at Pintail 138 kV Switch | Establish a 110.4 MVAR Capacitor Bank at Pintail 138 kV Switch |  | Midnight Substation | Midnight Substation | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6167 | 2027-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Williamson | Williamson | Tier 4 |  |  |  |  | 3692 | Y |  |  |  | 87769 | 87768
87677 | Rebuild the Fryers Creek - Temple 138 kV Line | Rebuild the Fryers Creek - Temple 138 kV Line on new structures |  | Fryers Creek | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6335 | 2027-05-15 |  | 138 | 4.5 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3415, 3493 | Y |  |  |  | 87678 | 87677
87675 | Rebuild the Bell County - Fryers Creek 138 kV Line | Rebuild the Bell County - Fryers Creek 138 kV Line on new structures |  | Bell County | Fryers Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6336 | 2027-05-15 |  | 138 | 3.2 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 132, 3493 | Y |  |  |  | 87676 | 87675
87673 | Rebuild the Salado - Bell County 138 kV Line | Rebuild the Salado - Bell County 138 kV Line on new structures |  | Salado | Bell County | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6280 | 2027-05-15 |  | 138 | 7.8 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 132, 3640 | Y |  |  |  | 87674 | 87673
80546E | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild the Gabriel to Structure 25/8 Line Section and upgrade terminal equipment to meet or exceed 3200 A. |  | Gabriel | Structure 25/8 | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2027-05-15 |  | 138 | 0 | 2.4 | 0 |  | Williamson | Williamson | Tier 3 |  |  |  |  | 3664, 3669, 3677, 3688, 7346, 7528, 7532 | Y |  |  |  | 87647 | 80546 | 2023-SC17
85977 | Upgrade the existing T367 Cedar Hill - Swiftex 138-kV transmission line from Cedar Hill to Str 181 | Upgrade the existing T367 Cedar Hill - Swiftex 138-kV transmission line from Cedar Hill to Str 181 (Elgin Tap) |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 3674, 7326, 7331 | Y |  |  |  | 85978 | 85977 | 2023-SC15
85979 | Perform an overhaul on the 2.2 mile T728 Elgin (structure #17/7) - Elgin Tap 138-kV transmission line. | Perform an overhaul on the 2.2 mile T728 Elgin (structure #17/7) - Elgin Tap 138-kV transmission line. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 3674, 7326, 7331, 13674 | Y |  |  |  | 85980 | 85979 | 2023-SC15
80870 | Add synchronous condenser at Bakersfield substation. |  |  | Bakersfield (BAKESW) | Bakersfield (BAKESW) | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | 1030378 | 2027-05-15 |  | 345 | 0 | 0 | 0 | -350350 | Pecos | Pecos | Tier 1 | 23RPG027 | 2023-09-07 | 2023-09-28 |  | 76002, 76101, 76102 | Y |  |  |  | 80926 | 80870 | 2023-FW10
81232 | Cattleman – Bitter Creek/Champion Creek 345 kV Reroute | Terminate Morgan Creek – Bitter Creek/Champion Creek Double-Circuit 345 kV Line into Cattleman 345 kV Switch |  | Cattleman | Bitter Creek and Champion Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8647 | 2027-05-15 |  | 345 | 0 | 5 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 1414, 10053, 11032, 11033, 11034, 71050 | Y |  |  |  | 81665 | 81232
78404 | BBEC Bastrop Village Addition |  |  | Bastrop Village |  | Planned |  | BBEC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7555, 7556, 7561 | Y | N |  |  | 78406 | 78404
81373 |  |  |  | Longstreet | Buckholts | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-05-15 |  | 138 | 0 | 1.5 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 65, 108, 110, 3749 | Y |  |  |  | 81374 | 81373
76728 | Skyview 345/138 kV Switch | Establish Skyview 345/138 kV Switch |  | Skyview |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4350 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 1922, 1924, 1927, 2119, 2120, 2123, 2124, 2125, 2127, 2128, 2129, 2130, 2131, 2132, 2134, 2231, 2243, 2244, 11938 | Y |  |  |  | 76831 | 76728
73570 | LCRATSC_Steger_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor New Sweden substation addition. |  | Steger |  | Conceptual |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7336, 7337, 7339 | Y | N |  |  | 73571 | 73570
71187 | Reiter - Tesoro 345 kV Double-Circuit Line | Construct new 2.5-mile 345 kV double-circuit line from Tesoro to Reiter |  | Tesoro | Reiter | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8629 | 2027-05-16 |  | 345 | 5 | 0 | 0 |  | Midland | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 18540, 18544 | Y |  |  |  | 71189 | 71187
81548 | Haber: Construct New 345 kV Station | Interconnect the Iota load to the new Haber 345 kV station on the Cobra to Static 345 kV line |  | Haber |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-05-28 |  | 345 | 7 | 0 | 0 |  | Victoria |  | Tier 3 |  |  |  |  | 8676, 8728, 81003, 81006 | Y |  |  |  | 81549 | 81548
81553 | Haber: Construct New 345 kV Terminal | Interconnect the Theta load to the new Haber 345 kV station |  | Haber |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-05-29 |  | 345 | 1 | 0 | 0 |  | Victoria |  | Tier 3 |  |  |  |  | 81003, 81005 | Y |  |  |  | 81554 | 81553
70706 | Tungsten (Carbide): Rebuild 138/69 kV Station | Rehab the Tungsten (Carbide) 138/69 kV station | Contact Update | Tungsten |  | Planned |  | AEP TCC | Teresa Trotman deevans@aep.com 918-599-2938 |  | 2027-05-30 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 | 21RPG024 | 2021-12-16 | 2022-01-18 |  | 5598, 8144, 8149, 8152, 8154, 8159, 8161, 8189, 8190, 8536, 8723, 80135, 110331, 110332, 110334, 110335, 110336 | Y |  |  |  | 78605 | 70706
81556 | Haber: Construct New 345 kV Terminal | Interconnect the Crunch load to the new Haber 345 kV station |  | Haber |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-05-30 |  | 345 | 1 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 81003, 81004 | Y |  |  |  | 81557 | 81556
59086 | Corichi to Victoria: Rebuild 138 kV Line | Rebuild the Corichi to Victoria 138 kV line | Title, Description, Location, and Contact Update | Corichi | Victoria | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2020888 | 2027-05-30 |  | 138 | 0 | 42.76 | 0 |  | Jackson | Victoria | Tier 3 |  | 2022-02-22 | 2022-03-01 |  | 8118, 8172 | Y | N |  |  | 65585 | 59086
67427 | Greens Bayou to Clinton 138kV Conversion | Upgrade Ckt.16C MINING Switchrack to MINING/BENTON ahead of future 138kV Conversions |  | Mining Switchrack | BENTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 69 | 0 | 1.9 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40470, 41062, 41063, 41380, 48171, 48177 | N | N |  |  | 67428 | 67427
70712 | SAPS to Red Creek: Rebuild 138 kV Line | Rehab the SAPS to Red Creek 138 kV line | In-Service Date Update | SAPS | Red Creek | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2020210 | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 |  |  |  |  | 6442, 6473, 6480, 60008 | Y |  |  |  | 70713 | 70712
80576 | Chalmers: Construct New Distribution Station | Construct new distribution station on the Lane City to Magill 138 kV line | Contact Update | Chalmers |  | Planned | DP23X0014 | AEP TCC | Lance Price deevans@aep.com 918-599-2938 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8111, 8127, 8668, 8750, 89500 | Y |  |  |  | 80577 | 80576
76131 | Pendulo: Build New 345 kV terminal | Interconnect Inertia Solar and BESS 2 to the Pendulo 345 kV Station on the Clear Crossing to Smoky Hill line | TSP/Company Contact and In-Service Date Update | Pendulo |  | Planned |  | ETT | Craig Tabor twang1@aep.com 918-599-2635 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60507 | Y | N |  |  | 76132 | 76131
70891 | Eola Tap: Rebuild 69 kV Line | Rehab Eola Tap 69 kV Line | In-Service Date, Estimated Cost Update | Eola Tap | Eola | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-05-31 |  | 69 | 0 | 11.69 | 0 |  | Concho | Concho | Tier 4 |  |  |  |  | 6370, 6371 | Y | N |  |  | 70892 | 70891
77031 | Las Lomas: Construct New Distribution Station | Construct new distribution station on the La Grulla to Rio Grande City 138 kV line |  | Las Lomas |  | Planned |  | AEP TCC | Eric Locke mlforcum@aep.com 918-599-2674 | DP24X0003 | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 8793, 8798, 8806 | Y |  |  |  | 77032 | 77031
72884 | Gonzales: Build 69 kV STATCOM | Build new 69 kV STATCOM at the Gonzales 69 kV station | Transmission Owner Project Number and In-Service Date Update | Gonzales |  | Planned |  | ETT | Tong Wang twang1@aep.com 918-599-2635 | TP2022130 | 2027-05-31 |  | 69 | 0 | 0 | 0 | -25,25 | Presidio |  | Tier 4 |  |  |  |  | 6675, 60203 | Y | N |  |  | 72885 | 72884
73055 | Hamlin to Roby: Rebuild 69 kV line | Rehab Hamlin to Roby 69 kV line | TSP/Company Contact, In-Service Date, Planning Tier, RPG Number, and RPG Dates Update | Hamlin | Roby | Planned |  | AEP TNC | Damian Rabb mlforcum@aep.com 918-599-2674 |  | 2027-05-31 |  | 69 | 0 | 25.23 | 0 |  | Fisher | Jones | Tier 4 | 23RPG002 | 2023-02-01 | 2023-02-28 |  | 6185, 6192, 6193, 6194, 6195, 6638 | Y | N |  |  | 73056 | 73055
81655 | Candela: Construct New 345 kV Station | Interconnect the Zeta load to the new Candela 345 kV station |  | Candela |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2027-06-01 |  | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8317, 8704, 8755 | Y |  |  |  | 81656 | 81655
81724 | Calabaza: Construct New 138 kV Station | Interconnect the Omicron load to the new Calabaza 138 kV station on the Gila to Tortuga and Nueces Bay to Saxet 138 kV lines |  | Calabaza |  | Conceptual |  | AEP TCC/LCRA | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8168, 8441, 78568, 80260, 80380 | Y |  |  |  | 81725 | 81724
86321 | AEN_Lakeshore_Northland_Ckt_916_Reconductor |  |  | 9128 | 9228 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9228 | Y |  |  |  | 86322 | 86321
86331 | AEN_Wheless_Mueller_Ckt_1016_Reconductor |  |  | 9291 | 9342 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9291, 9342 | Y |  |  |  | 86332 | 86331
86313 | AEN_345kV_CRASCO_SWYD_Addition | Crasco Switchyard will serve Bottom Grass BESS..The new the switchyard will be cut-in to345Kv CKT 3123 Holman - Hillje. |  |  |  | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 345 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 9067, 9073, 44200 | Y |  |  |  | 86314 | 86313
15TPIT0031 | Chavaneaux_Chavaneaux Tap Rebuild (Brooks to Chavaneaux ckt) | Rebuild 138 kV transmission from Chavaneaux to Chavaneaux Tap. This rebuild is for Brooks to Chavaneaux ckt. |  | Brooks | Chavaneaux | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0260 | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y |  |  | There are no transformers associated with this project | 9555 | 2304
67091 | Second 138 kV transmission Line from DL-DP CKT1034 | Second 138 kV transmission Line from Dunlap to Decker CKT1034 |  | 9045 | 9188 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 138 | 5.22 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9045, 9188 | Y |  |  |  | 67092 | 67091
81746 | Calabaza: Construct New 138 kV Terminal | Interconnect the Lambda load to the new Calabaza 138 kV station |  | Calabaza |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-06-02 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 80380 | Y | N |  |  | 81747 | 81746
45068 | Merida to Harlandale Rebuild | CPSE_Merida to Harlandale Rebuild |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0233 | 2027-06-05 |  | 138 | 0 | 10 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5310, 5385, 5395 | Y |  |  |  | 45069 | 45068
75255C | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5230, 5260 | Y |  |  |  | 75849 | 75255
75255B | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5230, 5231 | Y |  |  |  | 75848 | 75255
75255D | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5056, 5231 | Y |  |  |  | 75850 | 75255
75255E | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5056, 5231 | Y |  |  |  | 75851 | 75255
75255A | CPSE_Howard to San Miguel Double Circuit Line Addition |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5231, 5901 | Y |  |  |  | 75256 | 75255
49556 | Ozona: Rebuild 69 kV station | Replace existing Ozona 69 kV station with a new 69 kV ring bus | TSP/Company Contact, In-Service Date, and Estimated Cost Update | Ozona |  | Planned | 1018 - 1196 | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 | 2780 | 2027-06-30 |  | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6550, 6560 | Y | N |  |  | 65538 | 49556
87328 | Sunstone: Construct New 138 kV Station | Interconnect the Inner Harbor Desalination Plant load to the new Sunstone 138 kV station on the Morris Street to Nueces Bay 138 kV line | NEW | Sunstone |  | Planned |  | AEP TCC/ETT | Doug Evans deevans@aep.com 918-599-2938 | TP2022754 | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8022, 8441, 8733 | Y | Y |  |  | 87329 | 87328
81238 | Zoisite: Construct New 345 kV Station | Interconnect the HIF load to the new Zoisite 345 kV station on the STP to Zoisite 345 kV line | Contact Update | Zoisite |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2023803 | 2027-06-30 |  | 345 | 1.6 | 0 | 0 | 0,261.8 | Matagorda |  | Tier 4 |  |  |  |  | 5915, 8754 | Y |  |  |  | 81239 | 81238
86857 | Blessing: Install New 345 kV Cap Bank | Install new capacitor bank at the Blessing 345 kV station | NEW | Blessing |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023803 | 2027-06-30 |  | 345 | 0 | 0 | 0 | 0,130.9 | Matagorda |  | Tier 4 |  |  |  |  | 8123 | Y |  |  |  | 86858 | 86857
71881 | Install 31.3 Mvar capacitor bank at Andice. | Install 31.3 Mvar capacitor bank at Andice. Formerly TPIT project number 70365. |  | Andice |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-07-01 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson |  | Tier 4 |  |  |  |  | 70522 | Y | Y |  |  | 71882 | 71881
87899 | Vaso: Construct New Station to interconnect Alpha | Construct 138 kV station to interconnect Alpha |  | Cantwell |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-07-01 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8466 | Y |  |  |  | 87900 | 87899
84896 | New Legend Falls Substation looped into the existing Tally to Texas Research transmission line. This station supports the RPG approved Rio Medina project |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-07-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5259, 5422, 5430 | Y |  |  |  | 84897 | 84896
85008 | Add Rio Medina - Legend Falls Tline | Add Rio Medina - Legend Falls Tline as part of the Rio Medina RPG Project |  | Rio Medina |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-07-01 12:01 |  | 138 | 5.6 | 0 | 0 |  | Medina | Medina | Tier 2 |  |  | 2024-02-01 |  | 5259, 5805 | Y | N |  |  | 85009 | 85008
52464 | Alamito Creek to Ft. Davis: Rebuild 69 kV Line | Alamito Creek to Ft. Davis: Rebuild 69 kV line | Project Title, Project Description, and In-Service Date Update | Alamito Creek | Ft Davis | Planned | 1070 - 1243 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2831 | 2027-08-31 |  | 69 | 0 | 20.5 | 0 |  | Presidio |  | Tier 4 |  |  |  |  | 6676, 6677, 6678, 6691, 6692 | Y | N |  |  | 65564 | 52464
86317 | AEN_DP_OnionCreek_Ckt_924_Reconductor |  |  | 9187 | 9251 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-09-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9187, 9251 | Y |  |  |  | 86318 | 86317
86327 | AEN_New_138kV_Southshore_Substation_Addition |  |  | 9179 | 9132 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-09-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9132, 9134, 9179 | Y |  |  |  | 86328 | 86327
86333 | AEN_OnionCreek_StoneyRidge_Ckt_1026_Reconductor |  |  | 9237 | 9251 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-09-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9237, 9251 | Y |  |  |  | 86334 | 86333
66492C | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Jacksboro Amoco - Chico City Services 69 kV Line |  | Jacksboro Amoco | Chico City Services | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3006 | 2027-09-15 |  | 69 | 0 | 7.3 | 0 |  | Jack | Wise | Tier 4 |  |  |  |  | 1554, 1555 | Y |  |  |  | 72963 | 66492
66206B | Upgrade Temple - Minerva 69 kV Line | Upgrade Marak - Minerva 69 kV Line |  | Marak | Minerva | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6186 | 2027-09-15 |  | 69 | 13.1 | 0 | 0 |  | Milam | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3643, 3684, 3685, 3689 | Y |  |  |  | 68924 | 66206
66202B | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Elkhart - Crockett 69 kV Line |  | Elkhart | Crockett | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6182 | 2027-09-15 |  | 69 | 0 | 19.5 | 0 |  | Anderson | Houston | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3285, 3286, 3289, 3290 | Y |  |  |  | 71894 | 66202
87635 | WETT Pitchfork Synchronous Condenser |  |  | Cottonwood | Pitchfork | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2027-10-01 |  | 345 | 0 | 0 | 0 |  | Borden | Borden | Tier 1 | 23RPG026 | 2023-09-01 | 2023-09-28 |  | 59904, 59908, 59913, 59914, 59915 | Y |  |  |  | 87636 | 87635
87629 | WETT Binturong Synchronous Condenser |  |  | Bearkat | Binturong | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2027-10-01 |  | 345 | 0.25 | 0 | 0 |  | Glasscock | Glasscock | Tier 1 | 23RPG026 | 2023-09-01 | 2023-09-28 |  | 59903, 59919, 59920, 59921 | Y |  |  |  | 87630 | 87629
87367 |  |  |  | Temple Switch | Poage | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-10-01 |  | 138 | 0 | 2 | 75 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 126, 130, 133, 3415, 33126 | Y |  |  |  | 87368 | 87367
87633 | WETT Buck Canyon Synchronous Condenser |  |  | Long Draw | Buck Canyon | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2027-10-01 |  | 345 | 0.25 | 0 | 0 |  | Borden | Borden | Tier 1 | 23RPG026 | 2023-09-01 | 2023-09-28 |  | 59900, 59916, 59917, 59918 | Y |  |  |  | 87634 | 87633
70800 | Triada: Build New 345 kV Station | Interconnect Siete Wind to the new Triada 345 kV station on the Avanzada to Lobo 345 kV line | In-Service Date Update | Triada |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2022749 | 2027-10-31 12:00 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8718, 80219, 80235 | Y |  |  |  | 70801 | 70800
80502 | Lon Hill: Construct New 345 kV Terminal | Interconnect the Tom Cruise load to the Lon Hill 345 kV station | Contact Update | Lon Hill |  | Planned | TP2023885 | AEP TCC | Michael Glueck deevans@aep.com 918-599-2938 |  | 2027-11-30 |  | 345 | 0.1 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8455, 80037 | Y |  |  |  | 80503 | 80502
72999 | Haskell to Munday: Rebuild 69 kV Line | Rehab Haskell to Munday 69 kV Line | Contact Update | Haskell | Munday | Planned |  | AEP TNC | Bill Edwards twang1@aep.com 918-599-2635 |  | 2027-11-30 |  | 69 | 0 | 21.71 | 0 |  | Haskell | Knox | Tier 4 | 22RPG043 | 2022-12-15 | 2023-01-11 |  | 6107, 6122, 6123, 6124, 6125, 6126, 60021 | Y | N |  |  | 73000 | 72999
73001 | Truscott Humble Tap: Rebuild 69 kV Line | Rehab Truscott Humble Tap 69 kV line | Contact Update | Moorhouse | Truscott Humble | Planned |  | AEP TNC | Craig Tabor twang1@aep.com 918-599-2635 |  | 2027-11-30 |  | 69 | 0 | 13.92 | 0 |  | Knox | Knox | Tier 4 |  |  |  |  | 6080, 6082, 6084, 6085, 60023 | Y | N |  |  | 73002 | 73001
70710 | Eden to Yellowjacket: Rebuild 69 kV Line | Rehab the Eden to Yellowjacket 69 kV line | Contact and Tier Update | Eden | Yellowjacket | Planned |  | AEP TNC | Damian Raab twang1@aep.com 918-599-2635 | TA2021119 | 2027-11-30 |  | 69 | 0 | 0 | 0 |  | Concho | Menard | Tier 3 |  |  |  |  | 6363, 6372 | Y |  |  |  | 70711 | 70710
71912B | Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Park Street Tap - Killeen Taft 138 kV Line |  | Killeen Park Street Tap | Killeen Taft | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6245 | 2027-12-15 |  | 138 | 0 | 3.95 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3367, 3619, 3621, 3622, 3623, 3635 | Y |  |  |  | 71914 | 71912
68700 | Bonham - Toco Switch 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Bonham | Toco | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3016 | 2027-12-15 |  | 69 | 0 | 35 | 0 |  | Fannin | Lamar | Tier 4 |  |  |  |  | 1703, 1761, 1788, 1789, 1790, 11789 | Y |  |  |  | 68701 | 68700
1549 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-15 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 | [5 empty] | Y | N |  |  | 8754 | 1549
87699 | Belton - Killeen 138 kV Line via Belton Southwest | Upgrade Belton - Killeen 138 kV Line via Belton Southwest |  | Belton | Killeen | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R902 | 2027-12-15 |  | 138 | 0 | 17.2 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3423, 3610, 3633, 13610 | Y |  |  |  | 87700 | 87699 | 2023-NC36
87707 | Salado 345/138 kV Autotransformer #1 and #2 | Install Salado 345/138 kV Autotransformer #1 and #2 |  | Salado | Salado | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6354 | 2027-12-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3640, 3699, 3745, 3746 | Y |  |  |  | 87708 | 87707
85955 | GVEC will perform a voltage conversion on 5.1 miles of 69 Kv line (Olmos to Lavernia TL) to 138 KV transmission line | GVEC will perform a voltage conversion on 5.1 miles of 69 KV line (Olmos to Lavernia TL) to 138 KV transmission line |  | Olmos | LaVernia | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2027-12-15 |  | 69 | 0 | 5.1 | 0 |  | Wilson | Wilson | Tier 4 | [5 empty] | Y |  |  |  | 85956 | 85955
72011 | Tonkawa - Ranger Camp 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Tonkawa | Ranger Camp | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2027-12-15 |  | 345 | 0 | 21.3 | 0 |  | Mitchell | Scurry | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 11048 | Y |  |  |  | 81371 | 72011
66023 | T340 T-Line Upgrade | Upgrading the Marion to Sheriff's Posse Transmission Line T340 from 795 ACSR to 959 ACSS conductor. Upgrades to conductor and structures are included. Structures designed for ultimate build-out of double-circuit bundled 959 ACSS in preparation for additional future capacity. |  | Marion | Sheriff's Posse | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2027-12-15 |  | 138 | 0 | 3.4 | 0 |  | Guadalupe | Comal | Tier 4 |  |  |  |  | 7178, 7460 | Y | N |  |  | 78403 | 66023
81296 | Prong Moss – Rockhound 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Prong Moss | Rockhound | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2027-12-15 |  | 345 | 0 | 60.2 | 0 |  | Midland | Howard | Tier 1 | 23RPG029 |  |  |  | 10057, 10062 | Y |  |  |  | 81297 | 81296
81440 | Wolf to Monahan to Pecos / Odessa EHV to Reiter138 kV Line Rebuild | 138 kV existing line rebuild. |  | Wolf/Odessa EHV | Pecos/Reiter | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8527, R8629 | 2027-12-16 |  | 138 | 0 | 11.6 | 0 |  | Ward | Ector | Tier 3 |  |  |  |  | 1013, 1027, 1107, 11117, 18545 | Y |  |  |  | 81441 | 81440
72032 | Stewart to West Bay Ckts 48A & 59A Upgrades | Reconductor Ckts. 48A & 59A Stewart to West Bay as a Hardening upgrade. |  | Stewart | West Bay | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 40 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 43290, 43520, 43521 | N |  |  |  | 72033 | 72032
57910 | Uvalde to West Batesville: Rebuild 138 kV Line | Rebuild the Uvalde to West Batesville 138 kV line | Contact Update | Uvalde | West Batesville | Planned | 1117 - 1295 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3836 | 2027-12-31 |  | 138 | 0 | 20.6 | 0 |  | Uvalde | Zavala | Tier 4 |  |  |  |  | 8234, 8236 | Y | N |  |  | 65580 | 57910
73100 | Asherton to Piloncillo: Rebuild 138 kV Line | Rehab Asherton to Piloncillo 138 kV line | Contact Update | Asherton | Piloncillo | Planned | TA2021030 | AEP TCC | William Simmons jlsolis@aep.com 361-881-5574 |  | 2027-12-31 |  | 138 | 0 | 13.43 | 0 |  | Dimmit | Dimmit | Tier 4 |  |  |  |  | 8283, 8970, 80481 | Y |  |  |  | 73101 | 73100
78461A | West Columbia to Damon and Needville to Big Creek Ckt.89A Upgrades | Rebuild/reconductor portions of West Columbia to Damon Ckt.89A as a Hardening upgrade. |  | West Columbia | Damon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 6.6 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42370, 43380 | Y | N |  |  | 78462 | 78461
76237 | Lobo: Construct New 345 kV Terminal | Interconnect Cuchillas Solar to the Lobo 345 kV station | Owner and Contact Update | Lobo |  | Planned |  | ETT | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023320 | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219 | Y |  |  |  | 76238 | 76237
72457 | AddKiowaToQuinlanLine | Add 138kV line from Kiowa to Quinlan |  | Kiowa | Quinlan | Planned |  | RCEC | Scott Donhamsdonham@rayburnelectric.com 469-402-2024 |  | 2028-01-01 |  | 138 | 8 | 0 | 0 |  | Hunt | Hunt | Tier 2 |  |  |  |  | 6796, 6884 | Y |  |  |  | 72458 | 72457
45566 | Holly to Southside: Upgrade 138 kV Line | Upgrade the Holly to Southside 138 kV line | Contact and Cost Update | Holly | Southside | Planned | 994 - 1172 | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | 3747 TP-2019-065 | 2028-01-30 |  | 138 | 0 | 1.8 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486 | Y | N |  |  | 65532 | 45566
87092 | Arcadia to Southside: Upgrade 138 kV Line | Upgrade the Arcadia to Southside 138 kV line | NEW | Arcadia | Southside | Planned | 994 - 1172 | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | 3747 TP-2019-065 | 2028-01-30 |  | 138 | 0 | 2.59 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486, 8496, 8609, 8617, 8618 | Y | N |  |  | 87093 | 87092
64067 | Bessel to King Ranch: 138 kV Line Rebuild | Rehab the Bessel to King Ranch 138 kV line | Contact and In-Service Date Update | Bessel | Stratton | Planned |  | AEP TCC | Chase Isaac deevans@aep.com 918-599-2938 | TA2020081 | 2028-01-31 |  | 138 | 0 | 26.59 | 0 |  | Nueces | Kleberg | Tier 4 | 23RPG001 | 2023-01-25 | 2023-02-24 |  | 8060, 8498, 8512, 8514, 8665, 80228 | Y |  |  |  | 64068 | 64067
55624 | Escondido to Ganso: Rebuild 138 kV line | Rebuild 138 kV line from Escondido to Ganso | Contact Update | Escondido | Ganso | Planned | 1105 - 1283 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3825 | 2028-02-28 |  | 138 | 0 | 10.198 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 8260, 8267 | Y |  |  |  | 65575 | 55624
55626 | Ganso to Hamilton Road: Rebuild 138 kV line | Rebuild 138 kV line from Ganso to Hamilton Road | Contact Update | Maverick | Hamilton Road | Planned | 1105 - 1283 | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 | 3824 | 2028-02-28 |  | 138 | 0 | 41.1 | 0 |  | Maverick | Val Verde | Tier 3 | 22RPG044 | 2022-12-15 | 2023-01-17 |  | 8255, 8267, 8692 | Y |  |  |  | 65576 | 55626
80970 | Joule: Construct New 345 kV Station | Interconnect Zeissel Solar and Storage to the new Joule 345 kV station on the Clear Crossing to Coulomb 345 kV line | NEW | Joule |  | Planned | TP2024020 | ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2028-02-28 |  | 345 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 60094, 60702, 60722 | Y | Y |  |  | 80971 | 80970
86933 | Paladio: Construct New 345 kV Station | Interconnect Argenta Solar and Storage to the new Paladio 345 kV station on the Goddard to Tango 345 kV line | NEW | Paladio |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2024012 | 2028-02-28 |  | 345 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8012, 8606, 8689 | Y |  |  |  | 86934 | 86933
80330 |  |  |  | DWU Southside | McCree | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-15 |  | 69 | 0 | 7.45 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 230, 832 | Y |  |  |  | 80331 | 80330 | 2023-NC24
80327 | RTP projects included the addition of 18.4 MVAR capacitor at Whitesboro SW | RTP projects included the addition of 18.4 MVAR capacitor at Whitesboro SW |  | Whitesboro SW | Whitesboro SW | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-15 |  | 138 | 0 | 0 | 0 | 0,18.4 | Grayson | Grayson | Tier 4 |  |  |  |  | 718 | Y |  |  |  | 80328 | 80327 | 2023-N14
80334 |  |  |  | CONCORD | WILDCAT TAP | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-15 |  | 138 | 0 | 4.9 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 388, 394 | Y |  |  |  | 80335 | 80334 | 2023-NC25
51001 | Friess Ranch to Sonora: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line | Contact Update | Friess Ranch | Sonora | Planned | 1044 - 1217 | AEP TNC/AEP TCC | Greg Crane twang1@aep.com 918-599-2635 | 2791 | 2028-03-31 12:00 |  | 69 | 0 | 24.3 | 0 |  | Sutton | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 6513, 6570, 8238, 8239, 60210, 60438 | Y | N |  |  | 65554 | 51001
88049 | Loop in Cagnon to Howard into Omicron |  |  |  |  | Planned | T-0394 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5054, 5230, 5326 | Y |  |  |  | 88050 | 88049
88046 | Rebuild Omicron to Rafter |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5326, 5355 | Y |  |  |  | 88047 | 88046
76107 | City of Robstown Capacitor | Add a new cap bank at City of Robstown sub with 2 9.6 MVAR steps |  | City of Robstown |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5630 | N | N |  |  | 76108 | 76107
87701 | Establish the Watercrest 138 kV Switch | Establish the Watercrest 138 kV Switch |  | Watercrest | Watercrest | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6353 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3626, 3627, 3744, 13628 | Y |  |  |  | 87702 | 87701 | 2023-NC57
81225 | Cattleman - Range Rider 138 kV Double-Circuit Line | Construct a new 138 kV double-circuit line from Cattleman to Range Rider Switch |  | Cattleman | Range Rider | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8722 | 2028-05-15 |  | 345 | 0 | 6.6 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1032, 10054 | Y |  |  |  | 81226 | 81225
71877 | CPSE_Cagnon to Shepherd Rebuild (Phase B) |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0281 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5054, 5230, 5378, 5465 | Y |  |  |  | 71878 | 71877
86838 | AEN_JustinLane_KoenigLane_Ckt__conversion_to_138kV | Justin Lane Koenig Lane convert to 138kV |  | 9225 | 9227 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9225, 9227 | Y |  |  |  | 86839 | 86838
80420 |  | Rebuild / Reconductor Greens Prairie to South Switch 138kV Line |  | Bryn South Switch | Greens Pairie | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 138 | 0 | 4.5 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32007, 32878, 32880, 32893 | Y |  |  |  | 80421 | 80420
86240 | AEN_REPLACE_LYTTON__345kV_LYAT1_and_LYAT2_AUTOS_WITH__New_672_MVAs | Replace the two existing 345kV Lytton Autos with two new 672 MVA/345kV autos |  | Lytton 9074 | Lytton 9075 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-06-01 |  | 345 | 0 | 0 | 762 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 9074, 9075, 9078, 9081 | Y |  |  |  | 86241 | 86240
81588 | Chalybe: Construct New 345 kV Station | Interconnect the Delta load to the new Chalybe 345 kV station on the Chalybe to Kingfisher and Chalybe to Palmito 345 kV lines |  | Chalybe |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-06-01 |  | 345 | 46 | 0 | 1350 |  | Cameron |  | Tier 4 |  |  |  |  | 8735, 79500, 79501, 88337 | Y | N |  |  | 81589 | 81588
86315 | AEN_Barton_Vega_Ckt_928_Reconductor |  |  | 9158 | 9285 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9158, 9285 | Y |  |  |  | 86316 | 86315
81302 | Rockhound - Midland East 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Rockhound | Midland East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2028-06-15 |  | 345 | 0 | 24.2 | 0 |  | Midland | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1021, 10062 | Y |  |  |  | 81303 | 81302
66492D | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Chico West - Chico City Services 69 kV Line |  | Chico City Services | Chico West | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3006 | 2028-09-15 |  | 69 | 0 | 6 | 0 |  | Jack | Jack | Tier 4 |  |  |  |  | 1553, 1554 | Y |  |  |  | 76368 | 66492
5889 | MIRAGE - 138kV Substation Removal | Remove 138kV MIRAGE customer-owned substation from CEHE service. |  | MIRAGE | MCCABE/BIMONT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40200, 40209, 42351, 42360 | N | N |  |  | 13606 | 5889
78545 | Brookhollow to Cangrejo: Rebuild 69 kV Line | Rebuild 69 kV line from Brookhollow to Cangrejo | Project Title, Project Description, In-Service Date, Dollars, and Service Level kV Update | Brookhollow | Cangrejo | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2028-11-30 |  | 69 | 0 | 2.15 | 0 |  | Calhoun | Calhoun | Tier 1 |  |  |  |  | 8133, 8135, 8720, 8723, 8756, 88133 | Y |  |  |  | 78546 | 78545
69277 | Cangrejo to Carbide: Rebuild 138 kV Line | Rebuild 138 kV Line from Cangrejo to Carbide | In-Service Date and RPG Dates Update | Cangrejo | Carbide | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2028-11-30 |  | 138 | 0 | 11 | 0 |  | Calhoun | Calhoun | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8140, 8155, 8190, 8723 | Y |  |  |  | 69278 | 69277
55617 | Campwood to Rocksprings: Rebuild 69 kV Line | Rebuild the Campwood to Rocksprings 69 kV line | Title, Description, Location, Contact, In-Service Date, Cost, Miles, and RPG Dates Update | Campwood | Rocksprings | Planned | 1102 - 1280 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3820 | 2028-11-30 |  | 69 | 0 | 27.2 | 0 |  | Edwards | Edwards | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 8365, 8633 | Y |  |  |  | 65573 | 55617
55605 | Rebuild 69 kV line from Campwood to Rocksprings | New Barksdale to Rocksprings: Rebuild 69 kV line | Contact and In-Service Date Update | New Barksdale | Rocksprings | Planned | 1102 - 1280 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | 3819 | 2028-11-30 |  | 69 | 0 | 19.51 | 0 |  | Edwards | Edwards | Tier 3 |  |  |  |  | 8238, 8365 | Y |  |  |  | 65572 | 55605
55470 | Bison to Ozona: Rebuild 69 kV Line | Rehab 69 kV line from Bison to Ozona | Project Title and In-Service Date Update | Bison | Ozona | Planned | 1095 - 1273 | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 | 1863 | 2028-11-30 |  | 69 | 0 | 27 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  |  | 6549, 6560, 60395 | Y | N |  |  | 65570 | 55470
50876 | Victoria to Port Lavaca: Retire 69 kV Line | Retire 69 kV Line on Victoria to Port Lavaca | In-Service Date and Estimated Cost Update | Port Lavaca | Victoria | Planned | 1054 - 1227 | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 | 3782 | 2028-11-30 |  | 69 | 0 | 29 | 0 |  | Calhoun | Victoria | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8135, 8136, 8169 | Y | N |  |  | 50877 | 50876
84902 | Rebuild Spruce to Pawnee into a double circuit |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5400, 5725 | Y |  |  |  | 84903 | 84902
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-12-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5626, 5634 | Y | N |  |  | 11275 | 3818 | 2014-S2
81236 | Cattleman – Longshore 345 kV Double-Circuit Line Rebuild | Rebuild the existing 345 kV Double Circuit Line |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 | 2028-12-15 |  | 345 | 0 | 66.8 | 0 |  | Howard | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1058, 10053, 18548 | Y |  |  |  | 81385 | 81236
81240 | Consavvy – Odessa EHV 345 kV Double Circuit Line Rebuild | Rebuild the existing 345 kV Double-Circuit Line |  | Consavvy | Odessa EHV | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 | 2028-12-15 |  | 345 | 0 | 40 | 0 |  | Midland | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1125, 11016, 11028, 11387, 18540, 18548 | Y |  |  |  | 81241 | 81240
71910 | Rebuild the Hillsboro - Elm Mott 69 kV Line | Rebuild the Hillsboro - Elm Mott 69 kV Line |  | Hillsboro | Elm Mott | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6221 | 2028-12-15 |  | 69 | 0 | 25.4 | 0 |  | Hill | McLennan | Tier 3 |  |  |  |  | 3408, 3523, 3524, 3525, 3526, 3527, 3528, 3529, 13525 | Y |  |  |  | 71911 | 71910
81277 | Midland East – Midland County NW 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Midland East | Midland County Northwest | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8729 | 2028-12-15 |  | 345 | 0 | 42.6 | 0 |  | Midland | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1021, 1185 | Y |  |  |  | 81278 | 81277
87705 | Pepper Creek - Temple Elm Creek 138 kV Double-Circuit Line | Reconductor the Pepper Creek - Temple Elm Creek 138 kV Double-Circuit Line |  | Pepper Creek | Temple Elm Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6198 | 2028-12-15 |  | 138 | 0 | 6.2 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3484, 3608, 13608, 13662 | Y |  |  |  | 87706 | 87705 | 2023-NC51
87703 | Belton - Killeen 138 kV Line via Nolanville | Reconductor the Belton - Killeen 138 kV Line via Nolanville |  | Belton | Killeen | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6347 | 2028-12-15 |  | 138 | 0 | 24.8 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3366, 3423, 3429, 3444, 3610, 3616, 3617, 3618, 3619, 13426, 13427 | Y |  |  |  | 87704 | 87703 | 2023-NC22, 2023-NC36, 2023-NC50
87711 | Watercrest - Killeen 138 kV Line | Upgrade the Watercrest - Killeen 138 kV Line |  | Watercrest | Killeen | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6355 | 2028-12-15 |  | 138 | 0 | 7 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3423, 3428, 13628 | Y |  |  |  | 87712 | 87711
87709 | Belton - Temple 138 kV Line | Rebuild the Belton - Temple 138 kV Line |  | Belton | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6199 | 2028-12-15 |  | 138 | 0 | 9.6 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3415, 3602, 3610, 3611, 3612 | Y |  |  |  | 87710 | 87709 | 2023-NC5, 2023-NC17
87695 | Establish a new Oncor-owned Bell County 138 kV Switch | Establish a new Oncor-owned Bell County 138 kV Switch |  | Bell County | Bell County | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6363 | 2028-12-15 |  | 138 | 0 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 132, 3493, 3598, 3640 | Y |  |  |  | 87696 | 87695
87697 | Bell County - Poage - Seaton 69 kV Line Conversion to 138 kV | Bell County - Poage - Seaton 69 kV Line Conversion to 138 kV |  | Bell County | Seaton | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6367 | 2028-12-16 |  | 138 | 0 | 17.8 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 126, 130, 131, 133, 3598, 3636, 3735, 33126 | Y |  |  |  | 87698 | 87697
81268 | Longshore – Consavvy 345 kV Double-Circuit Line Rebuild | Rebuild existing 345 kV Double-Circuit Line |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 | 2028-12-16 |  | 345 | 0 | 66.8 | 0 |  | Howard | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1058, 11387, 18548 | Y |  |  |  | 81388 | 81268
87648 | Carver to Poblano: Convert 69 kV Line to 138 kV | Convert the Sonora to Uvalde 69 kV line to 138 kV and reterminate at Carver and Poblano | NEW | Carver | Poblano | Planned |  | AEP TCC/AEP TNC, ETT | Doug Evans deevans@aep.com 918-599-2938 | TP2024058 | 2028-12-29 |  | 138 | 1 | 107.5 | 0 |  | Sutton | Uvalde | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 6513, 6570, 8009, 8230, 8231, 8238, 8365, 8633, 60039, 60119, 60120, 60121, 60210, 60412, 80073, 80074, 80075, 80081 | Y | Y |  |  | 87649 | 87648
67915 | Asherton to West Batesville: Rebuild 138 kV Line | Rehab Asherton to West Batesville 138 kV line | Contact Update | Asherton | West Batesville | Planned |  | AEP TCC/ETT | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-12-30 |  | 138 | 0 | 36.09 | 0 |  | Dimmit | Zavala | Tier 3 |  |  |  |  | 8236, 8283, 8285 | Y |  |  |  | 67916 | 67915
85953 | LCRATSC will convert (T269) Camp Wood – Leakey 69-kV to a 138 KV TL. | LCRATSC will perform a voltage conversion on Camp Wood – Leakey (T269) 69-kV transmission line. This project will increase the reliability of transmission facilities by converting the substation equipment at Camp Wood and Leakey substation to operate at 138-kV. |  | Bandera 7438 | Leakey 7426 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-12-30 |  | 138 | 0 | 0 | 0 |  | Bandera | Real | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 7426, 7428, 7438, 7439, 7440, 8633, 80074 | Y |  |  |  | 87789 | 85953 | 2023-W14
59394 | Pointer to Rule: Rebuild 69 kV Line | Rehab the Pointer to Rule 69 kV Line | In-Service Date and Service Level kV Update | Pointer | Rule | Planned | 1122 - 1300 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 1867 | 2028-12-31 |  | 69 | 0 | 14.78 | 0 |  | Haskell | Knox | Tier 4 |  |  |  |  | 763, 6014, 6115, 6120, 60346 | Y | N |  |  | 59395 | 59394
45015 | Barnhart to Cassava: Rebuild 69 kV line | Rebuild the Barnhart to Cassava 69 kV line | In-Service Date Update | Barnhart | Cassava | Planned | 942 - 1120 | AEP TNC | LaRissa Lundry twang1@aep.com 918-599-2635 | 2756 | 2028-12-31 01:00 |  | 69 | 0 | 6.021 | 0 |  | Irion | Irion | Tier 4 |  |  |  |  | 6530, 6532, 6537, 60359 | Y | N |  |  | 65525 | 45015
50645 | CPSE_Rafter 138kV Cap Bank | [6 empty] | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-01-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5355 | Y |  |  |  | 50646 | 50645
76133 | West Childress: Station Rehab | Rehab the West Childress station | In-Service Date Update | West Childress |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2020223 | 2029-01-31 |  | 138 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 6030, 6135 | Y | N |  |  | 76134 | 76133
73116 | Install new Cedar Port Mobile (CDM) 138kV Distribution Substation | Install new Cedar Port Mobile (CDM) 138kV Distribution Substation. Loop from existing Ckt.03B to create new Ckt.03B Trinity Bay to Cedar Port Mobile to KENNY tap. |  | Cedar Port Mobile | Trinity | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-01-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40921, 41610, 48360 | N | N |  |  | 73120 | 73116
80323 | Add 2nd transformer at Retta Substation | Add 2nd transformer at Retta Substation |  | Retta | Retta | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-15 |  | 138 | 0 | 0 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 429 | Y |  |  |  | 80324 | 80323
80346 |  |  |  | SANDY SWITCH | CRUTCHFIELD | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-15 |  | 138 | 0 | 3.2 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 5, 8 | Y |  |  |  | 80347 | 80346
80373 |  |  |  | IOLA | CRUTCHFIELD | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-15 |  | 138 | 0 | 5.5 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 4, 8 | Y |  |  |  | 80374 | 80373
80579 | La Palma to Stewart Road: Convert to 138 kV | Convert the La Palma to Stewart Road 69 kV line to 138 kV | NEW | La Palma | Stewart Road | Planned | TA2020071 | AEP TCC | William Lovelace mlforcum@aep.com 918-599-2674 |  | 2029-03-30 |  | 138 | 0 | 37.5 | 0 |  | Cameron | Hidalgo | Tier 3 | 23RPG005 | 2023-03-01 | 2023-03-23 |  | 5778, 8040, 8310, 8314, 8701, 8703, 8748, 8751, 8949, 8951, 80104, 80229 | Y | N |  |  | 80580 | 80579
50898 | Alamito Creek to Paisano to Alpine: Rebuild 69 kV line | Rehab Alamito Creek to Paisano to Alpine 69 kV line | Contact Update | Alamito Creek | Alpine | Planned | 1045 - 1218 | AEP TNC | Brooks Dow twang1@aep.com 918-599-2635 | 2793 | 2029-03-31 |  | 69 | 0 | 22.26 | 0 |  | Presidio | Brewster | Tier 4 | 20RPG017 |  |  |  | 6666, 6667, 6672 | Y | N |  |  | 50899 | 50898
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0385 | 2029-05-15 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5250, 5395, 5416 | Y | N |  | There are no transformers associated with this project | 10365 | 3021
72051 | Twinwood Mobile (TWM) 138kV Distribution Substation | Install new Twinwood Mobile (TWM) 138kV Distribution Substation. Loop from existing Ckt.25E to create new Ckt.25E Foster to Twinwood Mobile to Peters |  | Twinwood | Foster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44256, 44861, 46220 | N | N |  |  | 72052 | 72051
76348 | Reconductor Foxtail-PIGCreek-1926ACSS-138KV |  |  | Foxtail | PIG Creek | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0.68 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38294, 60393 | Y |  |  |  | 76349 | 76348
70796 | El Campo to Corichi: Rebuild 138 kV Line | Rehab the El Campo to Corichi 138 kV line | Title, Description, Location, Contact, and In-Service Date Update | El Campo | Corichi | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TA2018020 | 2029-05-31 |  | 138 | 0 | 13.26 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8099, 8102 | Y |  |  |  | 70797 | 70796
64065 | Alice to Kingsville 138 kV Line Rebuild | Rehab the Alice to Kingsville 138 kV line | Contact and Cost Update | Alice | Kingsville | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TA2021079 | 2029-05-31 |  | 138 | 0 | 22.48 | 0 |  | Jim Wells | Kleberg | Tier 4 |  |  |  |  | 8503, 8518 | Y |  |  |  | 66649 | 64065
66204 | Rebuild Hidden Lakes-PH Robinson with bundled 795 ACSS |  |  | TNMP Hidden Lakes (bus # 38900) | CenterPoint PH Robinson (bus # 42015) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 3.15 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 42015 | Y |  |  |  | 66205 | 66204
60526 | Rebuild West Columbia Local-Angleton with 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39530, 39560 | Y |  |  |  | 60527 | 60526
60504 | Rebuild Caddo-Apache with bundled 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38710, 38720 | Y |  |  |  | 60505 | 60504
60502 | Rebuild Apache-Amoco with bundled 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38620, 38720 | Y |  |  |  | 60503 | 60502
60522 | Rebuild Hidden Lakes-League City with 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  |  | 60523 | 60522
54120 | Rebuild Tejas-Commanche (Bundled 795 ACSS) | Rebuild Tejas - Commanche 138 kV line with Bundled 795 ACSS conductor. |  | Tejas 138 kV Substation (Bus # 38530) | Commanche 138 kV Substation (Bus # 38560) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | STE07318 | 2029-05-31 |  | 138 | 0 | 0.95 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38530, 38560 | Y |  |  |  | 54121 | 54120
87427 | Rebuild Magnolia to Seminole 138kV line. | Replacement for recently committed PMCR # 4010. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38950, 38990 | Y |  |  |  | 87428 | 87427
6687 | Rebuild Rio Hondo to East Rio Hondo | Rebuild the 138 kV line from Rio Hondo to East Rio Hondo. |  | Rio Hondo | East Rio Hondo | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-06-01 |  | 138 | 0 | 8.19 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5764, 8319 | Y | N |  |  | 14458 | 6687
87693 | Rebuild Spruce to Eastside Double Circuit |  |  |  |  | Planned | T-0398 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 3 |  |  |  |  | 5295, 5400 | Y |  |  |  | 87694 | 87693
84898 | New Eastside Switching Station |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5035, 5110, 5250, 5294, 5295, 5371, 5400, 5416, 5485 | Y |  |  |  | 84899 | 84898
86329 | AEN_PilotKnob_CarsonCreek_Ckt_944_RECONDUCTOR |  |  | 9175 | 9259 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9175, 9259 | Y |  |  |  | 86330 | 86329
86836 | AEN_Northland_KoenigLane_Ckt__conversion_to_138kV | Northland to Koenig Lane convert_to_138kV |  | 9129 | 9227 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9129, 9227 | Y |  |  |  | 86837 | 86836
86275 | AEN_REPLACE_DUNLAP_345kV_DLAT1_and_DLAT2_AUTOS_WITH__New_672_MVAs | Replace Autos with new 672 MVA |  | 9044 | 9045 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 345 | 0 | 0 | 672 |  | Travis | Travis | Tier 4 |  |  |  |  | 9044, 9045, 90001, 90007 | Y |  |  |  | 86276 | 86275
86273 | AEN_REPLACE_AUSTROP_345kV_AUAT1_and_AUAT2_AUTOS_WITH__New_672_MVAs_PMCR | Autos to be upgraded to 672 MVAs |  | 7040 | 9328 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 345 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7040, 9328, 9329, 9330 | Y |  |  |  | 86274 | 86273
87269 | AEN_Fiesta_Mueller_new2_138kV_CKT |  |  | 9243 | 9342 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-07-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9004, 9077, 9080, 9128, 9129, 9130, 9213, 9225, 9227, 9243, 9244, 9269, 9342, 90004 | Y |  |  |  | 87270 | 87269
80297 | Add 2nd load at Muenster | Add 2nd load at Muenster |  | Muenster | Muenster | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-07-15 |  | 138 | 0 | 0 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 695 | Y |  |  |  | 80298 | 80297
73053 | Wimberley Loop to New Substation | Adds new 138 kV branch (219 MVA) from Wimberley to a new three terminal ring bus substation between Dripping Springs and Rutherford. |  | Wimberley | Cebolla Creek | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2029-08-01 |  | 138 | 13.44 | 0 | 0 |  | Hays | Hays | Tier 2 | 22RPG026 | 2022-08-29 | 2023-02-03 |  | 70496, 70509, 70511, 70512 | Y | N |  |  | 73054 | 73053
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2029-10-26 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7622 | Y | N |  |  | 78325 | 3321
6685 | Van Vleck substation loop | Replaces single circuit radial line connected to a pole mounted switch with a double circuit transmission loop to the Van Vleck substation and upgrades the 4/0 ACSR to 795 ACSR on 138 kV capable poles. |  | Van Vleck Substation | Van Vleck Switch | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-12-01 |  | 69 | 2 | 2 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5556, 5557, 5558, 5560 | Y | N |  |  | 14456 | 6685
84900 | Rebuild Pawnee to Tango into a double circuit |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5725, 8689 | Y |  |  |  | 84901 | 84900
59260 | Mason Phillips Tap to Mason Phillips: Rebuild 69 kV Line | Rehab the Mason Phillips Tap to Mason Phillips 69 kV Line | Contact, Schedule Update | Seaquist | Mason Phillips | Planned | 1127 - 1305 | AEP TNC | Christopher Carroll twang1@aep.com 918-599-2635 | 1872 | 2029-12-01 |  | 69 | 0 | 13.7 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6395, 6407, 60458 | Y | N |  |  | 65588 | 59260
66118 | Reconductor TI-Lakepointe with 959 ACSS/TW | Project ISD anticipated in 2025. |  | Lakepoint (bus # 37010) | TI (bus # 37080) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-12-31 |  | 138 | 0 | 2.78 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 37010, 37080 | Y |  |  |  | 66119 | 66118
61550 | East Munday to Lake Pauline: Rebuild 138 kV Line | Rehab East Munday to Lake Pauline 138 kV line | In-Service Date Update | East Munday | Lake Pauline | Planned | 1129 - 1307 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 1874 | 2030-04-30 |  | 138 | 0 | 59.97 | 0 |  | Knox | Hardeman | Tier 4 | 20RPG018 |  |  |  | 6037, 6050, 6110 | Y | N |  |  | 65594 | 61550
5981 | Shamburger North 345/138 kV Sw. Sta. | Establish Shamburger North 345/138 kV Sw. Sta. | Project Deferral | Shamburger North | Shamburger North | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6083 | 2030-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 2485, 3103, 3201, 3206, 3217, 3223, 3226 | Y | N |  |  | 13696 | 5981
5982 | Shamburger North - Shamburger 138 kV Line | Upgrade Shamburger North - Shamburger 138 kV Line | Project Deferral | Shamburger North | Shamburger | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6084 | 2030-05-15 |  | 138 | 10 | 0 | 0 |  | Smith | Smith | Tier 4 |  |  |  |  | 3104, 3206, 3226 | Y | N |  |  | 13697 | 5982
17TPIT0031 | Elkton 345/138 kV autotransformer | Replace existing autotransformer |  | Elkton | Elkton | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6032-E | 2030-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 3 |  |  |  |  | 3105, 3106, 29150 | Y | N |  |  | 10501 | 3155
6287 | Sherry Sw. - Webb/Kennedale 345 kV DCKT Line | Upgrade the existing 345 kV Line |  | Sherry | Webb/Kennedale | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4252 | 2030-05-15 |  | 345 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 3 |  |  |  |  | 1911, 1918, 1929, 1930, 1932, 1934 | Y |  |  |  | 14016 | 6287
6304 | Shamburger North - Shamburger 345 kV Line | Upgrade existing 345 kV Line | Project Deferral | Shamburger North | Shamburger | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6085 | 2030-05-15 |  | 345 | 10 | 10 | 0 |  | Smith | Smith | Tier 3 |  |  |  |  | 3103, 3223 | Y | N |  |  | 14033 | 6304
52070 | Carver to Maxwell: Rebuild 138 kV line | Rehab Carver to Maxwell 138 kV Line | Contact Update | Carver | Maxwell | Planned | 1079 - 1252 | AEP TCC/AEP TNC | Damian Raab twang1@aep.com 918-599-2635 | 3804 | 2030-05-31 |  | 138 | 0 | 60.24 | 0 |  | Sutton | Val Verde | Tier 3 | 22RPG042 | 2022-12-02 | 2022-12-28 |  | 8259, 8261, 8991, 8998, 60412, 60440 | Y | N |  |  | 65562 | 52070
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2030-12-17 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7239 | Y | N |  |  | 10694 | 3336
70889 | SA College Hills: Rebuild 69 kV Station | Rehab the SA College Hills 69 kV station | In-Service Date Update | SA College Hills |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2031-04-30 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6468, 6470 | Y |  |  |  | 70890 | 70889
72956 | Bellville South - Prairie View Transmission Line Upgrade | the proposed project converts the existing 69kV transmission line T283 from Bellville South- Quanex Sw - Sunnyside - Prarie View substation to 138kV. The proposed project improves the reliabiltiy of transmission facilities on the 26.1 mile transmission line and increases the line capacity for long term system growth. |  | Bellville South | Prairie View | Conceptual | Project transitioned to STEC from LCRA . Previous Mod Project #47428 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-05-15 |  | 69 | 0 | 0 | 0 |  | Austin | Waller | Tier 3 |  |  |  |  | 7269, 57660, 57664, 57666 | N | N |  |  | 72957 | 72956
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits, as recommended in 2013 RTP. |  | Bevo | Carrizo Springs | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 1 |  | 2012-04-12 | 2012-08-12 | 2012-09-12 | 5871, 8244 | N | N |  | This new line was part of Karnes and Medina Electric Cooperatives Project that was approved in 2012. This also helped voltage on AEP transmission under contingencies. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 10984 | 3595 | 2013-R104

## CompletedTPIT100124NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2024
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
5430Q | Conversion to 138kV | Retire the existing 69kV RD Wells substation together with the autotransformers |  | RD Wells |  | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2023-01-01 | 2019-07-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 930, 932 | Y | N | N/A |  | 55211 | 5430 | N/A
5430P | Conversion to 138kV | Transfer the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2023-01-01 | 2019-07-01 | 69 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 910, 932 | Y | N | N/A |  | 55210 | 5430 | N/A
5430H | Conversion to 138kV | Reconstruct the 69kV Bonnie Brae - North Lakes to 138kV and terminate it at the new 138kV North lakes substation after the 69kV Bonnie Brae substation is converted to 138kV. Reconstruction will be completed by 12/19/2016. Cost already accounted for in the Reconstruct 69kV BonnieBrae-NLakes sub-phase. |  | Bonnie Brae | North Lakes | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2023-01-01 | 2018-12-11 | 138 | 0 | 1.521 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 928, 931 | Y | N | N/A |  | 55202 | 5430 | N/A
67900 | NBU ECMornhinweg Substation Upgrade | NBU is adding a second power transformer at EC Mornhinweg and reconfiguring the substation to a ring bus arrangement. |  | EC Mornhinweg | GPI Switch | Under Construction | 61593 | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2023-01-01 01:00 | 2022-12-20 | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 | [5 empty] | Y | N |  |  | 67901 | 67900
68754 | Buchanan Ranch 138 kV Expansion | Expand existing substation with additional transformers and capacitor bank |  | Buchanan Ranch | Buchanan Ranch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8616 | 2023-01-05 | 2023-10-15 | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 11335, 23857, 23858 | Y |  |  |  | 68756 | 68754
69904 | Interconnects Leon Creek Bitcoin |  |  | TNMP Leon Creek (bus # 38355) | Customer substation (bus # 38356) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-01-15 |  | 138 | 0 | 0 | 0 | 0,160 | Pecos | Pecos | Tier 4 |  |  |  |  | 38355, 38356 | Y |  |  |  | 69905 | 69904
62450 | Pin Oak 138 kV Switch (Formerly Big Brown Tap) | Pin Oak 138 kV Switch (Formerly Big Brown Tap) |  | Pin Oak | Pin Oak | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R2014 | 2023-01-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 196, 212, 3505, 3506, 3507, 3510 | Y |  |  |  | 62451 | 62450
66020 | New substation to connect Mustang Creek INR | New substation to connect Mustang Creek INR |  | Galow |  | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-01-27 | 2022-11-15 | 138 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5521, 5523, 78104 | Y | N |  |  | 66021 | 66020
63433 | Rebuilds AEP Creosote-TNMP Coyanosa138 kV line as Dbl Ckt |  |  | AEP Creosote (bus # 60377) and TNMP TransPecos Tap (bus # 38376) | TNMP Coyanosa (bus # 38380) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-01-28 |  | 138 | 0 | 0.87 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38376, 38380, 60377 | Y |  |  |  | 63434 | 63433
58006 | Magnolia Cap Bank | Install Cap bank at Magnolia | IN-SERVICE | Magnolia |  | In-Service |  | AEP TCC | James Douglas bcogan@aep.com 918-599-2674 | TP2020066 | 2023-01-30 | 2022-12-19 | 138 | 0 | 0 | 0 | 0,14.4 | Karnes |  | Tier 4 |  |  |  |  | 8583 | Y |  |  |  | 58007 | 58006
66530 | Add Consavvy 345/138 kV Switch | Add Consavvy 345/138 kV Switch |  | Consavvy | Consavvy | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8498 | 2023-01-30 | 2023-02-14 | 345 | 0 | 0 | 1200 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 1030, 1058, 1125, 1133, 1329, 11016, 11123, 11386, 11387, 11388, 11389, 19000, 23856, 23860 | Y |  |  |  | 66531 | 66530
57167 | Faysville substation conversion from 69 to 138 kV | Converts Faysville to 138 and connects to Redgate |  | Faysville | Red Gate | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-01-31 | 2023-06-15 | 138 | 8.46 |  | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5780, 5782, 5784, 5786, 5788, 8377 | Y | N |  |  | 63732 | 57167
61875 | Hungerford to East Bernard Ckt.60 Upgrades | Upgrade Hungerford to East Berrnard Ckt.60 to increase thermal limits |  | Hungerford | Caney | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-01-31 | 2023-01-23 | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44150, 44190 | Y | N |  |  | 61876 | 61875
59763 | Construct three terminal 138 kV capable switching station | Change Markham hard wire tap point to 3 way switching station |  | Cayce Switch |  | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-02-15 | 2023-05-15 | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5554, 5555, 5556, 5557, 8984 | Y | N |  |  | 65899 | 59763
51996 | Rebuild Markham Tap to AEP Markham Tap | Rebuild Markham Tap to AEP Markham Tap with 138 kV capable structures |  | Markham Tap | AEP MarkhamTap | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-02-15 | 2023-06-15 | 69 | 0 | 1.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5557, 8984 | Y | N |  |  | 51997 | 51996 | 2019-C1
59518 | upgrade the Desoto-Sterrett 138 kV Line | upgrade the existing Desoto-Sterrett 138 kV Line |  | Desoto | Sterrett | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4122 | 2023-02-15 | 2023-01-15 | 138 | 0 | 8.3 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  |  | 217, 2317, 2424 | Y |  |  |  | 59519 | 59518
65652 | Interconnects Tarbush Data Canter |  |  | TNMP Tarbush (bus # 38295) | Customer substation (bus # 38296) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-02-28 |  | 138 | 0 | 0 | 0 | 0,160 | Pecos | Pecos | Tier 4 |  |  |  |  | 38295, 38296 | Y |  |  |  | 65653 | 65652
72593B | Marshall Ford to Trading Post Storm Hardening | Phase 1: Reconductor segment of T323 Marshall Ford to Paleface and T315 Marshall Ford to Trading Post that is double circuit using Galveston ACCC conductor. (Replaces ERCOT Project # 61264B) |  | Marshall Ford | Trading Post | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-02-28 | 2023-02-01 | 138 | 0 | 3.6 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  |  | 72594 | 72593
58542B | CATTAIL_SUBSTATION | 1) Cat Tail to Cherokee 138kv line |  | Cherokee (39075) | Cat Tail ( 38580 ) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-03-01 | 2023-03-03 | 138 | 1.5 | 0 | 0 |  | Galveston | Galveston | Tier 2 |  | 2020-04-16 | 2020-09-16 |  | 38580, 39075 | Y |  |  |  | 71934 | 58542
54084 | King Mountain Sub Upgrade | Provide transmission service to a generator. Add a 138-kV bay and associated circuit breaker to the existing substation. ERCOT (ERCOT Generation Interconnection or Change Request No. 20INR0226) |  | King Mountain Sub | King Mountain Sub | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-03-01 | 2023-03-01 | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 76635 | Y | N |  |  | 54085 | 54084
57343 | Rosita Creek Substation 138-kV T2 Power Transformer Addition | Add second 138/13.09-kV power transformer bay with new 138-kV transmission switch and circuit switcher interconnected at LCRA Switch# 12669. New power transformer capacity will be 15/20/25 MVA. | Recent projected load increases beyond ALDR. Justification is to provide on-site backup power source for new and existing critical medical center, governmental and educational facility loads. Power transformer lead-time increases. | Pueblo | Escondido | Planned |  | RGEC | Larry T. Powell lpowell@rgec.coop 830-563-6178 |  | 2023-03-01 | 2023-03-01 | 138 | 0 | 0 | 0 |  | Maverick | Maverick | Tier 4 | [5 empty] | Y | N |  |  | 57344 | 57343
69483 | Wolf Tank Storage Interconnect | Wolf Tank Storage Interconnect | IN-SERVICE | Lobo Station | Wolf Tank Storage WSL | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2021136 | 2023-03-03 | 2023-03-03 | 138 | 0.2 | 0 | 0 |  | Jackson | Jackson | Tier 4 |  |  |  |  | 80221 | Y |  |  |  | 69484 | 69483
61356 | Hays Energy-Henne Split Transmission Line Upgrade | This project will increase the reliability and capacity of the transmission facilities on the T389 Bergheim to Hays Energy 5.4-mile 345-kV section of transmission line by replacing the aging conductor from Hays Energy Substation to Henne Split. |  | Hays Energy | Henne Split | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-03-03 | 2023-03-03 | 345 | 0 | 5.4 | 0 |  | Hays | Comal | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7043, 7770 | Y | N |  |  | 78301 | 61356
59265 | Hurst - International Airport 138 kV Double-Circuit Line Section | Upgrade existing 138 kV Line |  | Hurst | International Airport | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5216 | 2023-03-15 | 2022-12-15 | 138 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 2115, 2116, 2117, 2121, 2125, 2243, 2244 | Y |  |  |  | 59266 | 59265 | 2020-NC8
7124 | Flat Iron - Barr Ranch - Pegasus South 138 kV Line | Construct new Flat Iron - Barr Ranch - Pegasus South 138 kV Line and Barr Ranch 138 kV Switch |  | Flat Iron | Pegasus South | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8574 | 2023-03-15 | 2023-05-15 | 138 | 18 | 0 | 0 | 0,55.2 | Midland | Midland | Tier 2 | 21RPG010 | 2021-06-02 | 2021-06-23 | 2021-12-13 | 1237, 11217, 11235 | Y |  |  |  | 62668 | 7124
14TPIT0010 | Handley - Sherry 138 kV line | Upgrade existing line |  | Handley | Sherry | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5155-E | 2023-03-15 12:00 | 2022-12-15 | 138 | 0 | 8.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1919, 1920, 1950, 1951, 2245, 2247, 2251, 2252 | Y | N |  |  | 59262 | 2582
72593A | Marshall Ford to Trading Post Storm Hardening | Phase 2: Rebuild single circuit section of Marshall Ford to Trading Post (T315) and reconductor with bundled 795 ACSR Conductor, 440 MVA; Reconductor segment of T323 Marshall Ford to Paleface that is double circuited with T315 using Cardinal ACCC conductor. (Replaces ERCOT Project # 61264A) |  | Marshall Ford | Trading Post | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-03-22 | 2023-03-01 | 138 | 0 | 4.1 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7356, 70505 | Y | N |  |  | 72595 | 72593
57645 | Hillje 345kV Danish Fields Solar (21INR0069) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Danish Fields Solar |  | Hillje |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-03-31 | 2023-03-17 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 57646 | 57645
4895 | CPSE_Capitol Cement Transmission Reconfiguration | Re-configurate Capitol Cement by loop into the existing Dresden to Skyline 138 kV transmission line and removing the existing Captiol Cement to Tuttle 138 kV transmission line. |  | Capitol Cement | Dresden/Skyline | Planned | S-0767, S-0961 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0246 | 2023-03-31 | 2023-03-26 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5075, 5130, 5370, 5435 | Y | N |  |  | 12507 | 4895
50440 | Delhi Substation Addition | Add a new load serving substation 10 miles north of IH-10 along 304, w/30 MVA PWT. |  | Delhi | Delhi | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-03-31 | 2023-03-31 | 69 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7896 | Y | N |  |  | 50441 | 50440
51734 | Blue Stem to Delhi Transmission Line | Build new 9.5 mile 138/69 kV transmission. |  | BlueStem | Delhi | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-03-31 02:00 | 2023-03-31 | 69 | 9.5 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7230, 7231, 7895, 7896 | Y | N |  |  | 51843 | 51734
72392 | TNMP_72392_OLD_OCEAN_SLCP_IMPEDANCE_RECONDUCTOR | REBUILD OLD-OCEAN TO PHILLIPS 5 |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-04-01 | 2023-05-03 | 69 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39750, 39870 | Y |  |  |  | 72393 | 72392
78339 | [7 empty] | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2023-04-13 | 2024-10-01 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2625, 6795, 6999 | Y |  |  |  | 78340 | 78339
61436 | Bastrop West - Split Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 2.4-mile portion of Bastrop West ¿ Sim Gideon (T410) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Bastrop West | Sim Gideon | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-04-15 | 2023-04-15 | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 | 22RPG005 | 2022-03-04 |  |  | 7310, 7555 | Y | N |  |  | 78305 | 61436
72599 | Hunter to McCarty Lane Storm Hardening | Phase 2: Rebuild single-circuit section of Hunter to McCarty Lane 138 kV with single, circuit bundled 795 ACSR Conductor, 440 MVA. (Replaces ERCOT Project # 61262) |  | McCarty Lane | Hunter | Planned |  | PEC/LCRATSC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-04-22 | 2023-05-01 | 138 | 0 | 1.57 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 70491 | Y | N |  |  | 72601 | 72599
63900 | Nebula: Build New 345 kV Station | Interconnect Andromeda Solar on the Dermott to Figaro 345 kV Line | IN-SERVICE | Nebula |  | In-Service | 1135 - 1313 | ETT | Adam Wells twang1@aep.com 918-599-2635 | 1880 | 2023-04-29 | 2023-04-29 | 345 | 0 | 0 | 0 |  | Scurry |  | Tier 4 |  |  |  |  | 11305, 60011, 60715 | Y | N |  |  | 63901 | 63900
61865 | Muldoon Substation Addition | Provide transmission service to a generator. LCRA TSC will construct a new substation, Muldoon Substation, on T133 between LCRA TSC Flatonia and Plum Substations and more specifically between str #192 and str #197. The substation will be a three breaker ring bus configuration and will provide a 138-kV line termination for a 240 MW solar generation facility. |  | Muldoon Substation | Muldoon Substation | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-04-30 | 2023-04-30 | 138 | 0 | 0 | 0 |  | Fayette | Fayette | Tier 4 |  |  |  |  | 7248, 7274, 7279 | Y | N |  |  | 61866 | 61865
70188 | LCRATSC_ClearSprings_CB_Addition | Provide a transmission point of interconnection for a new Battery Energy Storage System at the Clear Springs Substation by adding an additional 138-kV double bus, double breaker bay to accommodate the new interconnection. Contingency Update |  | Clear Springs | Clear Springs | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-04-30 | 2023-04-30 | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 | [5 empty] | Y | Y |  |  | 70189 | 70188
70998 | Hillje 345kV Substation - Danish Fields Battery Storage - Generator Interconnection (21INR0450) | Install Danish Fields Battery Storage¿ Connect at the same generator lead as Danish Fields Solar I-II-III at Hillje CNP station. |  | Hillje |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-04-30 | 2023-03-17 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 70999 | 70998
56003G | Mont Belvieu Reliability Project | Upgrade Ckt.84D Cedar Bayou Plant to Cedar Bayou Tap to HOPSON with minimum 682MVA Emergency Rating |  | Cedar Bayou Plant | Cedar Bayou/HOPSON | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-04-30 | 2023-05-04 | 138 | 0 | 8.61 | 0 |  | Chambers | Chambers | Tier 3 | 20RPG015 | 2020-09-01 | 2020-09-24 |  | 40012, 40015, 41690 | Y | N |  |  | 56081 | 56003
66011C | CNP ARCHER POI for BROTMAN Power | Upgrade Ckt 26 Angleton to WINMIL to increase thermal limits |  | Angleton | WINMIL | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-04-30 12:01 | 2023-04-21 | 138 | 0 | 1.15 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 44531 | Y | N |  |  | 72742 | 66011
59095 | Athey: Build 138 kV Temporary Hard Tap | Build new 138 kV temporary tap on the Ft Stockton to Rio Pecos 138 kV line | IN-SERVICE | Athey |  | In-Service | 1123 - 1301 | AEP TNC | Shawn Ketcher twang1@aep.com 918-599-2635 | 1868 | 2023-05-01 | 2023-05-01 | 138 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 60718, 60792, 60798 | Y | N |  |  | 59096 | 59095
73494 | Frontera Interconnection | Interconnect Frontera IPP at Frontera SW | IN-SERVICE | Frontera SW |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-05-02 | 2023-05-02 | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 | [5 empty] | Y | N |  |  | 73495 | 73494
52064 | Bay City - Lane City: 138 kV Line Rebuild | Rebuild the Bay City - Magill - Lane City 138 kV Line | IN-SERVICE | Bay City | Lane City | In-Service | 1078 - 1251 | AEP TCC | Marc E. Wilson mlforcum@aep.com 918-599-2674 | 3803 | 2023-05-03 | 2023-05-03 | 138 | 0 | 16 | 0 |  | Matagorda | Wharton | Tier 3 |  |  |  |  | 8111, 8113, 8127 | Y | N |  |  | 65558 | 52064
58008 | Laredo VFT North to Las Cruces: Rebuild 138 kV Line | Rebuild Laredo VFT North to Las Cruces 138 kV line | IN-SERVICE | Laredo | Laredo | In-Service | 1116 - 1294 | AEP TCC | William Lovelace mlforcum@aep.com 918-599-2674 | 3835 | 2023-05-04 | 2023-05-04 | 138 | 0 | 0.48 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8112, 80013 | Y |  |  |  | 76075 | 58008
45101 | Chavaneaux_Chavaneaux Tap (Chavaneaux to Palo Alto)- 138 kV | CPSE_Chavaneaux_Chavaneaux 138 kV Tap Rebuild (Chavaneaux to Palo Alto). |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0256 | 2023-05-04 | 2023-04-21 | 138 | 0 | 0.9 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5085, 5330 | Y |  |  |  | 45102 | 45101
70902 | LCRATSC_Settlers_Substation_Addition | Provide two transmission Points of Interconnection (POIs) on LCRA TSC-owned transmission lines T231 Bastrop City to Webberville and T171 Austrop to Sim Gideon to serve new BBEC customer load. |  | Austrop, Webberville | Sim Gideon, Bastrop City | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-11 | 2023-05-11 | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7310, 7322, 7327, 7328, 7329, 9328 | Y | N |  |  | 70903 | 70902
7161 | Naval Base to North Padre Island: Rebuild 69 kV Line | Rehab Naval Base to North Padre Island 69 kV line | IN-SERVICE | Naval Base | North Padre Tap | In-Service | 909 - 1087 | AEP TCC | Bill Roberts mlforcum@aep.com 918-599-2674 | 3690 | 2023-05-11 | 2023-05-11 | 69 | 0 | 12.7 | 0 |  | Nueces | Nueces | Tier 3 | 19RPG001 | 2019-02-06 | 2019-03-06 |  | 8495, 8847, 8856 | Y | N |  |  | 65519 | 7161 | 2018-S1
61591 | Sandy Creek Autotransformer Upgrade | Increase the reliability of substation equipment at Sandy Creek Substation through the replacement of the Sandy Creek 138/69-kV AT1 autotransformer with a new 70 MVA unit. Increase the capacity of T400 Sandy Creek - Sunrise Beach 69-kV transmission circuit by upgrading limiting element jumper at Sunrise Beach Substation. |  | Sandy Creek | Sunrise Beach | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7121, 7127, 7400 | Y | N |  |  | 61592 | 61591
53968 | Fayetteville_Salem_TransmissionLine_Rehabilitation | Increase the reliability of transmission facilities on the T177 Fayetteville to Salem 138-kV and T211 FPP Yard #1 to Salem 345-kV 19.3-mile double-circuit transmission line by replacing the existing Condor conductor from Fayetteville Substation to Salem Substation. |  | Fayetteville | Salem | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 345 | 0 | 19.3 | 0 |  | Fayette | Washington | Tier 3 | 22RPG011 | 2022-04-19 | 2022-05-11 |  | 7056, 7058, 7286, 7289 | Y | N |  |  | 78300 | 53968
61599 | Pinto Creek Circuit Breaker Addition | This project provides a point of interconnection for a new generator by converting Pinto Creek Substation into a ring bus (GINR # 21INR0019). |  | Pinto Creek | Pinto Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Kinney |  | Tier 4 |  |  |  |  | 78255 | Y | N |  |  | 61600 | 61599
61453 | Ingram - Jack Furman Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 3.3-mile Ingram ¿ Jack Furman (T521) transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Ingram | Jack Furman | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7141, 7142 | Y | N |  |  | 61454 | 61453
61455 | Hunt - Ingram Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 6.4-mile Hunt ¿ Ingram (T487) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Hunt | Ingram | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7142, 7144 | Y | N |  |  | 61456 | 61455
61440 | Harper Road - Jack Furman Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 4.6-mile Harper Road ¿ Jack Furman (T368) transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Harper Road | Jack Furman | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7140, 7141 | Y | N |  |  | 61441 | 61440
59263 | Weatherford Switch - Azle 138 kV Line | Upgrade existing 138 kV Line |  | Weatherford | Azle | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5172 | 2023-05-15 | 2023-05-01 | 138 | 0 | 11.5 | 0 |  | Parker | Tarrant | Tier 4 |  |  |  |  | 1592, 2062, 15015 | Y |  |  |  | 59524 | 59263
66196 | WichitaFalls PPG Terminal Equipment | Upgrade the existing terminal equipment at PPG |  | Wichita Falls PPG |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4025 | 2023-05-15 | 2023-05-11 | 138 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1484, 1485, 17005 | Y |  |  |  | 66197 | 66196
63929 | Buntin Drive 69 kV Substation Conversion To 138 kV | Convert Buntin Drive 69 kV Substation To 138 kV |  | Buntin |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4064 | 2023-05-15 | 2023-05-26 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2486, 2494, 2951, 2984 | Y |  |  |  | 63930 | 63929
62636 | Rebuild Waco West (Peppervine) 138 kV Switch | Rebuild Waco West (Peppervine) 138 kV Switch |  | Waco West | Waco West | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6141 | 2023-05-15 | 2023-11-28 | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3433, 3436, 3437, 3446, 3560, 3563, 3590, 3591, 13436 | Y |  |  |  | 62637 | 62636
62349 | Rebuild Fairfield West as Ranchland 138 kV Switch | Rebuild Fairfield West as Ranchland 138 kV Switch |  | Ranchland | Ranchland | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6136 | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 196, 3495, 3503, 3504, 3558, 3625, 13501, 13681 | Y |  |  |  | 71865 | 62349
72564 | Buttercup Bus Upgrade | Upgrade the Buttercup bus from operate/transfer to double-bus double-breaker. Replaces Project ID 51740. |  | Buttercup |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-05-15 | 2024-04-01 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 70531 | Y | N |  |  | 72565 | 72564
61853 | LCRATSC Lampasas Substation Upgrade | This project will improve the reliability of Lampasas Substation by replacing obsolete and aged equipment and by converting the substation from single-bus-single-breaker design to double-bus-double-breaker design. Lampasas Substation is an important hub for the transmission system in Burnet, Lampasas, San Saba, and Mills counties, and this project will improve transmission system reliability in those areas. |  | Lampasas | Lampasas | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Lampasas | Lampasas | Tier 4 | [5 empty] | Y | N |  |  | 61854 | 61853
71871 | Update Line Characteristics and Rating. |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0280 | 2023-05-15 | 2023-04-13 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5053, 5054, 5230, 5378 | Y |  |  |  | 71872 | 71871
53958 | Fairland - Lago Vista Transmission Line Rehabilitation | Increase the reliability of transmission facilities on the T414 Fairland - Lago Vista 21-mile 138-kV transmission line by replacing the existing Condor conductor with Drake conductor. |  | Fairland | Lago Vista | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Burnet | Travis | Tier 3 | 22RPG029 | 2022-09-14 |  |  | 7518, 70352 | Y | N |  |  | 53959 | 53958
53999 | ElCampo - Ricebird Transmission Line Strom Hardening | Increase the reliability of transmission facilities on the T589 El Campo ¿ Ricebird 4.6-mile 138-kV transmission line. |  | El Campo | Ricebird | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8102, 78104 | Y | N |  |  | 54000 | 53999
62669 | Pegasus South - Pleasant Farms Tap 138 kV Line Rebuild | Rebuild existing Pegasus South - Pleasant Farms Tap 138 kV Line |  | Pegasus South | Pleasant Farms Tap | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8574 | 2023-05-15 | 2023-05-30 | 138 | 0 | 9.6 | 0 |  | Midland | Ector | Tier 4 | 21RPG010 | 2021-06-02 | 2021-06-23 | 2021-12-13 | 1236, 1237, 71230 | Y |  |  |  | 62672 | 62669
54103 | Hilltop - Strahan Transmission Line Upgrade | Increase the reliability of transmission facilities on the T445: Hilltop ¿ Strahan 1.25-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. |  | Hilltop | Strahan | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7190, 7193 | Y | N |  |  | 54104 | 54103
66175 | Liggett 138 kV Terminal Equipment | Upgrade the terminal equipment at Liggett 138 kV Switch |  | Liggett |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4094 | 2023-05-15 | 2023-05-30 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 1922, 1924, 2053, 2055 | Y |  |  |  | 66176 | 66175
54080 | Lockhart - Lulig Transmission Line Overhaul | LCRA TSC will perform an overhaul of T184 (from Lockhart structure #301 to Luling) with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T184 will be 795 ACSR Drake. Note: Condor conductor replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7216, 7224 | Y | N |  |  | 54081 | 54080
67766 | Southlake Capacitors | Install new 138 kV capacitor bank |  | Southlake |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3011 | 2023-05-15 | 2023-05-26 | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 2020 | Y |  |  |  | 67767 | 67766
54082 | Lockhart - Red Rock Transmission Line Overhaul | LCRA TSC will perform an overhaul of T578 (from Lockhart structure #301 to Red Rock) with replacement structures that are capable of operating at 138-kV and supporting a single 959 ACSR Suwannee conductor. The replacement conductor on T578 will be 959 ACSR Suwannee. This overhaul will include the installation of a 72-count optical ground wire (OPGW). Note: Condor conductor, new OPGW and any structure replacement (from Lockhart to structure #301) will be taken into account on Lockhart - Split Transmission Line Upgrade project with ISD of May 15, 2023. |  | Lockhart (structure #301) | Red Rock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-05-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Caldwell | Bastrop | Tier 4 |  |  |  |  | 7216, 7560 | Y | N |  |  | 54083 | 54082
67610 | LCRATSC_ChiefBrady_Substation_Upgrade | Chief Brady Substation will be upgraded to increase the bus rating and replace equipment identified as obsolete. The substation upgrade will also install Tier 3 Physical Security Measures. -Contingency Update |  | Chief Brady | Chief Brady | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 01:00 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y | N |  |  | 67611 | 67610
52318 | Royse Switch - Greenbriar Switch 138 kV Line | Upgrade the Royse Switch - Greenbriar Switch 138 kV Line |  | Royse | Greenbriar | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4292 | 2023-05-15 01:00 | 2023-09-22 | 138 | 0 | 0 | 0 |  | Collin | Rockwall | Tier 3 | 20RPG002 |  | 2020-04-13 |  | 2472, 2706, 2708, 12527 | Y |  |  |  | 52319 | 52318 | 2020-NC3
67906 | LCRATSC_WeltnerRoad_CB_Addition | LCRA TSC will install circuit breakers at Weltner Road Substation in order to increase the reliability to the load served by NBU. This project will also configure the bus at Weltner Road to a ring bus. Update contingencies |  | Weltner Road | Weltner Road | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-05-15 01:00 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 | [5 empty] | Y | N |  |  | 67907 | 67906
56350A | Burnett - Bowie 69 kV Line | Rebuild Smith Creek - Tower one 69 kV Line (FKA Bellevue - Bowie) and establish Hopewell Switch |  | Bowie | Ringgold Magnolia Tap | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4015 | 2023-05-17 | 2023-05-26 | 69 | 0 | 10 | 0 |  | Montague | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 632, 768, 1540, 1547, 1548, 1549, 1550, 11548, 11550, 11582, 17010, 33770 | Y | N |  |  | 73038 | 56350
4487 | Nueces Area 69kV Reinforcement | Expand and add new 138/69kV Auto at Valero East 69kV substation. Add 5th breaker to Champlin 138kV substation. Construct Champlin to Valero East 138kV Line. | IN-SERVICE | Champlin | Valero East | In-Service | 709 - 0879 | AEP TCC | John Pulay mlforcum@aep.com 918-599-2857 | 2903 TP2016067 | 2023-05-22 01:00 | 2023-05-22 | 138 | 1.6 | 0 | 200 |  | Nueces |  | Tier 4 | 19RPG011 |  |  |  | 8476, 8528 | Y | N |  |  | 13570 | 4487 | 2014-S14, 2015-S8
59452 | Air Liquide Pass Through 138 kV Station | Air Liquide to construct 138 kV Ring Bus | IN-SERVICE | Dupont SW Ingleside |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2020197 | 2023-05-26 | 2023-05-26 | 138 | 0.01 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8422, 8818, 8978, 8979 | Y | Y |  |  | 59453 | 59452
59804C | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86N Jonte to Lockwood tap to Scenic Woods radial |  | Lockwood | Jonte/Scenic Woods | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-30 | 2023-05-16 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 46032, 46331, 46336 | Y | N |  | Cost included in main project | 72789 | 59804
71299 | McKenzie to Westside: Rebuild 138 kV Line | Rebuild McKenzie to Westside 138 kV Line | IN-SERVICE | McKenzie Road | Westside | In-Service | 968 - 1146 | ETT | James Weaver mlforcum@aep.com 918-599-2674 | TP2018126 | 2023-05-30 | 2023-05-30 | 138 | 0 | 11.48 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8485, 8858 | Y | N |  |  | 71300 | 71299
62133 | West Columbia to Damon Ckt.89A Thermal Uprate | Upgrade West Columbia to Damon to Ckt.89A to Minimum 210 MVA Continuous rating |  | West Columbia | Damon | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-05-10 | 138 | 0 | 10.3 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42370, 43380, 43384 | Y | N |  |  | 62134 | 62133
68242A | Garrott to Midtown to Polk Ckt.90 Upgrades Phase Two | Replace Midtown reactor R2 at 0.343 Ohm. Adjust underground circuit ratings to reflect the updated reactor R2 values. |  | Garrott | Midtown | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-04-05 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47661, 47706, 47707, 47708, 47709, 47730, 47731 | Y | N |  |  | 72026 | 68242
72057 | Greens Bayou to LYCHEM Ckt.08 Upgrade (2023) | Rebuild and reconductor a de-energized section of Ckt.38Z. Loop the rebuilt section into 138kV Ckt.08F between Moore Road and Uvalde tap. The reconfiguration creates additional conductor impedance on the line to increase the fault duty margin for future generation. |  | Moore Road | Uvalde | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-03-29 | 138 | 0 | 3.25 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40281, 40555, 40559, 41023, 41651 | Y | N |  |  | 72784 | 72057
66043B | Ckt29 THW-WhiteOak Reconductor and 138kV Conversion | Reconductor remaining portions of 69kV Ckt.29A TH Wharton to Little York to White Oak for 138kV conversion. Reconnect as 138kV Ckt.11A TH Wharton to Little York to White Oak. Swap positions for Ckt.95A and Ckt. 81K at the approach spans into TH Wharton. |  | TH Wharton | White Oak | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-04-26 | 138 | 0 | 12.33 | 0 |  | Harris | Harris | Tier 4 | 21RPG016 | 2021-09-08 | 2021-09-30 | 2021-09-30 | 45101, 45500, 45510, 45511, 45512, 45515, 45530, 45760, 45781, 45782, 45862, 45921, 45922, 45990, 45995, 46100, 46301, 46615, 46620, 46660 | Y | N |  |  | 72853 | 66043
67270C | BP23 Reliability Upgrades | Upgrade Ckt.08L HO Clarke to BUNKER to increase thermal limits |  | HO Clarke | BUNKER | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-04-08 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47150, 47340 | Y | N |  |  | 67273 | 67270
63971 | Mykawa Distribution Facilities | Install distribution facilities at MYKAWA substation |  | Mykawa |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-05-23 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 42741, 42742, 42750, 42751, 42752, 42753, 43051 | Y | N |  |  | 63972 | 63971
70606 | ARCHER to Karsten Ckt.26 Upgrades | Upgrade Ckt.26 Archer to Karsten to increase thermal limits. |  | ARCHER | Karsten | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-04-12 | 138 | 0 | 8.51 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44410 | Y | N |  |  | 70607 | 70606
59804B | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86M Jonte to Greens Road tap |  | Jonte | Greens Road | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-05-16 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 45821, 46331 | Y | N |  | Cost included in main project | 72791 | 59804
59804A | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.86E to create new Ckt.86E Crosby to Newport to Jonte |  | Jonte | Crosby/Newport | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 | 2023-05-16 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41150, 45660, 46032 | Y | N |  |  | 72790 | 59804
64505A | Flewellen to Peters Ckt.25E Upgrades | Upgrade Ckt.25E Flewellen to Foster to increase thermal limits |  | Flewellen | Foster | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:01 | 2023-06-23 | 138 | 0 | 1.9 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 21RPG011 | 2021-06-04 | 2021-07-02 |  | 44230, 44256, 44861, 46220 | Y | N |  |  | 64506 | 64505
65716A | Jonte Related Upgrades | Upgrade Ckt.86N Jonte to Lockwood tap to increase thermal limits |  | Jonte | Lockwood | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 | 2023-05-16 | 138 | 0 | 0.1 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 46032 | Y | N |  |  | 65717 | 65716
65716B | Jonte Related Upgrades | Install 20 MVAR cap bank at Jonte substation |  | Jonte |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 | 2023-05-16 | 138 | 0 | 0 | 0 | 0,20 | Harris |  | Tier 4 |  |  |  |  | 45660 | Y | N |  |  | 65718 | 65716
66013 | CNP WATERHOLE POI for G Star Solar | New 345kV Waterhole (WAT) substation for generator interconnection to G-Star Solar. Loop Ckt.62 into substation to create new Ckt.62 Bailey to Waterhole to Jones Creek. |  | Waterhole | BAILEY/Jones Creek | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 12:00 | 2023-05-15 | 345 | 0.08 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 42530, 44040, 44880 | Y | N |  |  | 66014 | 66013
66194A | Holliday - Navy Kickapoo 69 kV Line | Establish Pecan Tree and Shortgrass 138 kV substations |  | Holliday | Bowman | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4022 | 2023-06-15 | 2023-04-01 | 138 | 0 | 0 | 0 |  | Archer | Archer | Tier 4 |  |  |  |  | 1424, 1431, 1527, 11525, 11527, 11528 | Y |  |  |  | 78352 | 66194
61932A | Holliday - Seymour 69 kV Line | Rebuild the Holliday - Seymour 69 kV Line. |  | Holliday | Seymour | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4028 | 2023-06-15 | 2023-03-01 | 69 | 0 | 0 | 0 |  | Archer | Baylor | Tier 3 | 21RPG007 | 2021-04-26 | 2021-05-18 |  | 1527, 1530, 1532, 1534 | Y |  |  |  | 73027 | 61932
61362 | Henne-River Oaks Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the 2.4-mile T237 River Oaks to Henne 138-kV and T389 Bergheim to Hays Energy 345-kV double-circuit transmission line between River Oaks Substation and Henne Split and the 1.4-mile T237 River Oaks to Henne 138-kV single-circuit transmission line between Henne Split and Henne Substation by replacing the aging conductors. |  | Henne | River Oaks | Planned | 61406, 61358, 61392, 61350, 61234, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-15 | 2023-06-15 | 345 | 0 | 3.8 | 0 |  | Comal | Comal | Tier 4 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7043, 7172, 7173, 7770 | Y | N |  |  | 78302 | 61362
57925 | Midland County Northwest to Texaco Mabee Tap 138 kV Double-Circuit Line Section | Add Midland County NW - Texaco Mabee Tap 138 kV Double-Circuit Line Section Rebuild |  | Midland County Northwest | Texaco Mabee Tap | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8558 | 2023-06-15 01:00 | 2022-12-21 | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 | 21RPG003 | 2021-02-16 | 2021-03-12 |  | 1174, 1178, 1179, 1182, 1183, 11299, 11300, 11301 | Y |  |  |  | 60059 | 57925 | 2020-FW6, 2020-FW9
66621 | Sandhills - Sandhills Tap 138 kV Line Rebuild | Add Sandhills - Sandhills Tap 138 kV Line Rebuild |  | Sandhills | Sandhills Tap | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8612 | 2023-06-16 | 2023-05-30 | 138 | 0 | 23 | 0 | 0,55.2 | Ector | Crane | Tier 4 |  |  |  |  | 1103, 1104, 10006, 10007, 11111, 11117 | Y |  |  |  | 66681 | 66621
3505 | Cibolo Substation, T3 transformer addition | Add T3, 40 MVA 138-26.18 kV power transformer, CSW and low side |  | Cibolo |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-06-21 | 2023-06-21 | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7608 | Y | N |  |  | 10887 | 3505
54204 | Gonzales - Hochheim Transmission Line Overhaul | Increase the reliability and capacity of transmission facilities on the T542 Luling ¿ Cuero 19.6-mile 69-kV transmission line from Gonzales (structure #33) to Hochheim Tap. LCRA TSC will perform an overhaul of T542 with replacement structures that are capable of operating at 138-kV and supporting a single 795 ACSR Drake conductor. The replacement conductor on T542 will be 795 ACSR Drake. This overhaul will include the installation of a 72-count optical ground wire (OPGW). |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-06-30 | 2023-06-30 | 69 | 0 | 0 | 0 |  | Gonzales | DeWitt | Tier 4 |  |  |  |  | 7223, 78577 | Y | N |  |  | 54205 | 54204
61461 | Buchanan CTEC - Pitsburg Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 14.5-mile Buchanan CTEC ¿ Pitsburg (T267) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Buchanan CTEC | Pitsburg | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 | 2023-06-30 | 69 | 0 | 0 | 0 |  | Llano | Llano | Tier 3 | 22RPG030 | 2022-09-14 |  |  | 7101, 7116, 7119 | Y | N |  |  | 61462 | 61461
61459 | Buchanan CTEC-Buchanan Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 2.8-mile Buchanan ¿ Buchanan CTEC (T106) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Buchanan CTEC | Buchanan | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 | 2023-06-30 | 69 | 0 | 0 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7092, 7101 | Y | N |  |  | 61460 | 61459
72874 | LCRATSC Twin Buttes 345-kV CB Addition | This project provides a point of interconnection for a new solar and battery energy storage system at the 345-kV Twin Buttes Substation by adding a position to an existing breaker-and-a-half bay to accommodate the interconnection. Update contingencies |  | Twin Buttes |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-06-30 | 2023-06-30 | 138 | 1 | 0 | 0 |  | Tom Green |  | Tier 4 | [5 empty] | Y | N |  |  | 72875 | 72874
71942 | LCRATSC_Birdhouse_Substation_Addition | LCRATSC will provide a point of interconnection for a new solar and battery energy storage system at a new 138-kV Birdhouse Substation |  | Birdhouse | Birdhouse | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-06-30 | 2023-06-30 | 138 | 0 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  |  | 7224, 7245, 7255 | Y | N |  |  | 72418 | 71942
59317 | Deer Park Tap to Cardiff Ckt.96E Upgrades | Upgrade Deer Park Tap to Cardiff Ckt.96E to Minimum 300 MVA Emergency rating |  | Deer Park | Cardiff | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-06-30 | 2023-06-15 | 138 | 0 | 5.8 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42240, 42610, 43250, 48085, 48108, 48388, 48401 | Y | N |  |  | 78245 | 59317
45084B | Braunig to Highland Rebuild | Rebuild approximately sixteen circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Schillers Tap to Braunig'. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0194, T-0238 | 2023-07-15 | 2023-04-19 | 138 | 0 | 16 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  |  | 45086 | 45084
51736 | Cibolo to McQueeney Transmission Line | Install 10.62 miles of 1192 Bunting to existing transmission structures, circuit to help with load flows per the TPA and will be source for Santa Clara Substation. |  | Cibolo | McQueency | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2023-07-28 | 2023-07-28 | 138 | 10.62 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7606, 7608 | Y | N |  |  | 51737 | 51736
51841 | Cibolo-McQueeney Tap to Santa Clara Transmission Line Addtition | Build 5 onmiles of new double circuit 138kV t-line loop, 1192 ACSR Bunting, from H-pole structure to Santa Clara Substation |  | H-pole ( Structure/Tap) | Santa Clara | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-07-28 | 2023-07-28 | 69 | 10 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7606, 7608, 7891 | Y | N |  |  | 57331 | 51841
50446 | Santa Clara Substation Addition | Add a new load serving substation 10 miles west of City of Seguin, of IH-10, w/ twin 40 MVA PWTs. |  | Santa Clara Substation | Santa Clara Substation | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-07-28 | 2023-07-28 | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7891 | Y | N |  |  | 50447 | 50446
52183 | EXTER 69kV Substation Removal | Remove EXTER 69kV Substation from Ckt.53B |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-07-31 | 2023-06-19 | 138 | 0 | 0 | 0 |  | Galveston | Harris | Tier 4 |  |  |  |  | 42080, 42600, 43500, 43510, 44440, 49087 | Y | N |  | Cost included in MOD 52181 - ENCO new customer sub | 73718 | 52183
63493 | Noelke to Schneeman Draw 2nd circuit | Add the 2nd circuit to the CREZ Noelke to Schneeman Draw 345 kV line |  | Noelke | Schneeman Draw | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-07-31 | 2023-12-05 | 345 | 15.8 | 0 | 0 |  | Crockett | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 7053, 76005 | Y | N |  |  | 63494 | 63493
63491 | Schneeman Draw to Big Hill 2nd circuit | Add the 2nd circuit to CREZ Schneeman Draw to Big Hill 345 kV line |  | Schneeman Draw | Big Hill | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-07-31 | 2023-12-06 | 345 | 59.1 | 0 | 0 |  | Crockett | Schleicher | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76003, 76005 | Y | N |  |  | 63492 | 63491
59398B | San Bernard (SAN) Sub for Brazoria County Solar (20INR0098) | Upgrade San Bernard to West Columbia Ckt.60 to increase thermal limits. Increase fault duty at West Columbia to 63KA |  | San Bernard | West Columbia | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-07-31 | 2023-08-10 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43010, 43110, 43120, 43190, 43341, 43380 | Y | N |  |  | 59768 | 59398
64572A | HO Clarke Bus Upgrade | Upgrade bus work at HO Clarke 138kV facilities |  | HO Clarke |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-07-31 00:01 | 2023-08-09 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47150, 47170, 47175 | Y | N |  |  | 64573 | 64572
64572B | HO Clarke Bus Upgrade | Upgrade Ckt.90A HO Clarke to HOC TR1 to increase thermal limits |  | HO Clarke | HO Clarke | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-07-31 00:02 | 2023-08-09 | 138 | 0 | 0.44 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47151, 47175 | Y | N |  | Cost included in main entry | 64574 | 64572
73381 | TNMP_JACKRABBIT_CUTIN_AC_4-5-2023 |  |  | BUS 38091 TNPECOS___1 | BUS 38114 TNREEVSCOT1 | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-08-02 | 2023-09-01 | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38091, 38095, 38114 | Y |  |  |  | 73382 | 73381
58917 | Horizon 138 bus and line to Pearsall | Adds new Horizon Switch station to connect Horizon solar generation and a line to Pearsall |  | Horizon Swttch | Pearsall | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2023-08-11 | 2023-07-15 | 138 | 0.4 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5895, 5897 | Y | N |  |  | 58918 | 58917
61851 | Marion AT2 Autotransformer Upgrade | Increase the reliability of substation equipment at Marion Substation through the replacement of the Marion AT2 345/138-kV autotransformer and installation of three 345-kV shunt reactors. |  | Marion 345 | Marion 138 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-08-25 | 2023-08-25 | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7044, 7178, 7822 | Y | N |  |  | 61852 | 61851
5166 | Poesta to Three Rivers: Rebuild 69 kV line | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. | IN-SERVICE | Borglum | Three Rivers | In-Service | 742 - 0925 | AEP TCC | Dave Gotez bcogan@aep.com 918-599-2857 | 2915 | 2023-08-29 | 2023-08-29 | 138 | 6 | 22 | 0 |  | Bee | Live Oak | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8142, 8156, 8196, 8199, 8400, 8403, 84006 | Y | N |  |  | 57889 | 5166 | 2015-S10
57890 | Brightside Permanent Connection | Construct Charter Station | IN SERVICE | Beeville | Three Rivers | In-Service | 1114 - 1292 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3833 | 2023-08-30 | 2023-08-30 | 138 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8142, 8156, 8403 | Y |  |  |  | 57891 | 57890
60530 | Rebuild TI-South with 959 ACSS | update the impedance |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-09-01 |  | 138 | 0 | 2.76 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 37080, 37100 | Y |  |  |  | 60531 | 60530
71946 | LCRATSC_Hornsby_CircuitBreaker_Addition | Provide transmission service to a generator by adding an additional breaker-and-a-half bay to Hornsby Substation to accommodate a new circuit termination. |  | Hornsby |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-09-29 | 2023-09-29 | 345 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 | [5 empty] | Y | N |  |  | 71947 | 71946
57731B | Hornsby Substation Addition | Construct a new 345-kV substation between Clear Springs to Gilliland Creek 345-kV transmission line to provide transmission service to a load-serving substation. Restore 138-kV transmission line from Decker to Sand Hill by removing temporary substation/arrangements made in first phase to serve load. |  | Clear Springs | Gilleland Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2023-09-29 | 2023-09-29 | 345 | 0 | 0 | 960 |  | Travis | Travis | Tier 4 |  |  |  |  | 7047, 7050, 7340, 7916, 9187, 9216 | Y | N |  |  | 57740 | 57731
73129 | Cenizo: Build 345 kV terminal | Build new terminals at Cenizo, Del Sol, Lobo, and Pomelo | IN-SERVICE | Cenizo |  | In-Service |  | ETT | James Weaver mlforcum@aep.com 918-599-2674 | TP2021704 | 2023-10-13 | 2023-10-13 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80220 | Y | Y |  |  | 73130 | 73129
71161 | Haggerty-Anna and Haggerty-Stone Creek 138 kV Lines | Establish Haggerty-Anna and Haggerty-Stone Creek 138 kV Lines |  | Haggerty | Anna and stone creek | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4333 | 2023-10-15 | 2023-10-03 | 138 | 0 | 0 | 0 |  | Grayson | Grayson | Tier 4 |  |  |  |  | 1699, 1713, 1715, 1717, 1753, 1754, 1839, 12677 | Y |  |  |  | 71162 | 71161
70824 | Lavender 138 kV Switch | Establish Lavender 138 kV Switch |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5326 | 2023-10-15 | 2023-06-15 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2261, 2429, 2967 | Y |  |  |  | 70825 | 70824
67904 | Haggerty 138 kV Switch | Establish Haggerty 138 kV Switch |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4330 | 2023-10-15 | 2021-11-04 | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  |  | 1714, 1715, 1717, 1740, 1749, 1750, 1753, 2644, 12677 | Y |  |  |  | 67905 | 67904
66218A | Hillsboro - Italy 69 kV Line | Rebuild the Hillsboro-Milford 69 kV Line |  | Hillsboro | Milford | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4326 | 2023-10-15 | 2023-12-15 | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  | 2021-04-23 | 2021-05-18 |  | 2338, 3523 | Y |  |  |  | 73689 | 66218
72346 | FM524_CUT_IN_LINE_S | CUTING FM524 INTO LINE S |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-10-23 | 2023-10-15 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 39703, 110505 | Y |  |  |  | 72347 | 72346
76137 | Molina: Install cap bank | Install cap banks at Santo Nino, Molina, and Wormser Road | IN-SERVICE | Molina |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-10-30 | 2023-10-30 | 138 | 0 | 0 | 0 | 0,15.4 | Webb |  | Tier 4 |  |  |  |  | 80230 | Y |  |  |  | 76138 | 76137
71944 | LCRATSC_SingleTree_Substation_Addition | LCRATSC will provide a transmission point of interconnection for a new wind resource on the Noelke – Schneeman Draw 345-kV double circuit transmission line by adding a new 345-kV breaker-and-a-half substation, Single Tree Substation. |  | Single Tree | Single Tree | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-10-30 | 2023-10-30 | 345 | 0 | 0 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  |  | 7053, 76004, 76005 | Y | N |  |  | 72350 | 71944
69475 | Wormser Road: Install cap bank | Install cap bank at Wormser Road | IN-SERVICE | Wormser |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-10-30 | 2023-10-30 | 138 | 0 | 0 | 0 | 0,23 | Webb |  | Tier 4 |  |  |  |  | 8295 | Y | N |  |  | 69476 | 69475
69007 | Tiempo: Build new 345 kV station | Construct new Tiempo 345 kV station for the ETT 2nd circuits project | N-SERVICE | Tiempo |  | In-Service |  | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | TP2021706 | 2023-10-30 | 2023-10-30 | 345 | 0 | 0 | 0 |  | Zapata |  | Tier 1 |  |  |  |  | 80220, 80224, 80226, 162499 | Y | Y |  |  | 69008 | 69007
66200A | Upgrade Taylor - Holland 69 kV Line | Rebuild the Holland - Bartlett Tap 69 kV Line |  | Taylor | Holland | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6173 | 2023-10-30 | 2023-11-15 | 69 |  | 5.7 | 0 |  | Bell | Bell | Tier 4 | 22RPG036 |  |  |  | 3646, 13647 | Y |  |  |  | 66201 | 66200
43460 | Moody to Stewart Ckt.63 Upgrades P1016 | Upgrade Ckt.63 Moody to Stewart as a Hardening project |  | Moody | Stewart | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 | 2023-10-31 | 138 | 0 | 3.81 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42950, 42951, 42952, 42953, 43290, 43355, 43405, 43520, 43521 | Y |  |  |  | 43461 | 43460
64999C | PH Robinson to LaMarque Ckt.93B Upgrades | Rebuild and reconductor portions of Ckt.93B Hitchcock to LarMarque as a Hardening upgrade. Upgrade substation equipment at Hitchcock to increase thermal limits. |  | Hitchcock | LarMarque | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 | 2023-09-29 | 138 | 0 | 4.95 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-13 | 2021-05-14 | 42800, 42860 | Y | N |  |  | 65002 | 64999
57350 | Lyons to Gay Hill T-line pole change out and reconductor | Replace existing structure with upgraded structures and replace existing 336.4 ACSR Linnet with 795 ACSR Drake on Lyons to Gay Hill transmission line. |  | Lyons | Gay Hill | Planned |  | BBEC | Curtis Fischercurtis.fischer@bluebonnet.coop curtis.fischer@bluebonnet 979-716-0253 |  | 2023-10-31 | 2023-10-31 | 138 | 0 | 11.51 | 0 |  | Burleson | Washington | Tier 4 |  |  |  |  | 7572, 7573 | Y |  |  |  | 57351 | 57350
68242B | Garrott to Midtown to Polk Ckt.90 Upgrades Phase Two | Adjust underground circuit ratings to reflect the updated reactor R2 values. |  | Midtown | Polk | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 | 2023-10-24 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47707, 47709, 47730, 47731 | Y | N |  |  | 72027 | 68242
59804D | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90C North Belt to Greens Road tap to Jonte |  | Greens Road | North Belt/Jonte | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 | 2023-10-19 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 45822, 46031, 46112 | Y | N |  | Cost included in main project | 72792 | 59804
64999A | PH Robinson to LaMarque Ckt.93B Upgrades | Rebuild and reconductor portions of Ckt.93B AlgoaCorner to Alta Loma as a Hardening upgrade. |  | PH Robinson | Alta Loma | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 | 2023-09-29 | 138 | 0 | 22.31 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-13 | 2021-05-14 | 42015, 42061 | Y | N |  |  | 65000 | 64999
72236 | Hawk Hollow Sw (Eiffel Solar) | Establish Hawk Hollow Sw |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4346 | 2023-10-31 | 2022-12-31 | 138 | 0 | 0 | 0 |  | Lamar | Lamar | Tier 4 |  |  |  |  | 1693, 1768, 11768, 11770, 144263 | Y |  |  |  | 72237 | 72236
59804E | Jonte 138kV Switching Substation | Install new 138kV Jonte switching station. Reconfigure existing Ckt.90C to create new Ckt.90E Jonte to Lockwood tap to Lauder tap to Scenic Woods radial |  | Jonte | Lockwood/Lauder/Scenic Woods | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 | 2023-10-19 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45660, 46031 | Y | N |  | Cost included in main project | 72793 | 59804
64999B | PH Robinson to LaMarque Ckt.93B Upgrades | Rebuild and reconductor portions of Ckt.93B Alta Loma to Hitchcock as a Hardening upgrade. Upgrade substation equipment at Hitchcock to increase thermal limits. |  | Alta Loma | Hitchcock | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-10-31 00:01 | 2023-09-29 | 138 | 0 | 6.38 | 0 |  | Galveston | Galveston | Tier 4 | 21RPG006 | 2021-04-22 | 2021-05-13 | 2021-05-14 | 42061, 42800 | Y | N |  |  | 65001 | 64999
68673 | Reconductor TNMP Wink-Oncor Wink Ckt 2 |  |  | TNMP WInk (37900) | Oncor Wink (1074) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-11-01 | 2023-09-30 | 138 | 0 | 1.18 | 0 |  | Winkler | Winkler | Tier 4 |  |  |  |  | 1074, 37900 | Y |  |  |  | 68674 | 68673
5165 | Poesta: Construct a new 138/69 kV station | Construct a new 138/69 kV Poesta station and install an 138/69 kV autotransformer with 130 MVA capacity at Poesta station. Rebuild and convert Beeville - Three Rivers 69 kV line to 138 kV and reterminate into Poesta. Construct the new 138/69 kV double circuit transmission line from Tuleta - Beeville. | IN-SERVICE | Borglum |  | In-Service | 742 - 0925 | AEP TCC | Dave Goetz bcogan@aep.com 918-599-2857 | 2914 TP2014129 | 2023-11-02 | 2023-11-02 | 138 | 0 | 0 | 130 |  | Bee |  | Tier 1 | 15RPG004 | 2015-03-01 | 2015-09-01 | 2015-10-01 | 8107, 8196, 8197, 8198, 8199, 8205, 8904 | Y | N |  |  | 13315 | 5165 | 2015-S10
67917 | Brackettville and Hamilton Road Relay Upgrades for Pinto Creek | Upgrade relays at Brackettville 138 kV station and upgrade relays at Hamilton Road 138 kV station | IN-SERVICE | Brackettville | Hamilton Road | In-Service |  | AEP TCC | Michael Pitts mlforcum@aep.com 918-599-2674 |  | 2023-11-15 | 2023-11-15 | 138 | 0 | 0 | 0 |  | Kinney | Val Verde | Tier 4 |  |  |  |  | 8252, 8255, 78255 | Y |  |  |  | 67918 | 67917
45399 | Bearkat Loop - Bearkat to Longshore | Adds 345 KV line from Bearkat to Longshore. |  | Bearkat | Longshore | Planned |  | WETT/ONCOR | Yang Zhang yzhang@wettllc.com 737-218-4520 |  | 2023-11-16 | 2023-11-07 | 345 | 27 | 0 | 0 |  | Glasscock | Howard | Tier 1 |  | 2017-08-15 | 2018-09-19 | 2018-10-09 | 1058, 59903 | Y | N |  |  | 45473 | 45399
76245 | Pomelo to Pronto: Build new 345 kV line | Install conductor between North Edinburg and Tiempo | IN-SERVICE | Pomelo | Pronto | In-Service |  | ETT | Teresa Trotman mlforcum@aep.com 918-599-2674 | TP2021702 | 2023-11-16 | 2023-11-16 | 345 | 11.5 | 0 | 0 |  | Hidalgo | Starr | Tier 3 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8574, 80231, 80355 | Y | N |  |  | 76246 | 76245
73125 | Del Sol: Line settings | Build new terminals at Cenizo, Del Sol, Lobo, and Pomelo | N-SERVICE | Del Sol |  | In-Service |  | ETT | James Weaver mlforcum@aep.com 918-599-2674 | TP2021704 | 2023-11-16 | 2023-11-16 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80335 | Y | Y |  |  | 73126 | 73125
69005 | Rapido: Build new 345 kV station | Construct new Rapido 345 kV station for the ETT 2nd circuits project | IN-SERVICE | Rapido |  | In-Service |  | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | TP2021707 | 2023-11-17 | 2023-11-17 | 345 | 0 | 0 | 0 |  | Starr |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80227, 80355, 80381, 161855 | Y | Y |  |  | 69006 | 69005
75682 | Add Branch between Libra and Elm Creek |  |  | 5133 | 170882 | Planned | T-0323 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2023-11-27 | 2023-11-21 | 345 | 0.16 | 0 | 0 |  | Wilson | Guadalupe | Tier 4 |  |  |  |  | 5133, 170882 | Y |  |  |  | 75683 | 75682
7013 | NASA Substation Upgrades | Upgrade substation equipment at NASA on Ckt.06 NASA to Webster to increase thermal limits |  | NASA | NASA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 | 2024-10-31 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42610, 42970, 43500 | Y | N |  |  | 14835 | 7013
64491 | Bellaire to Smithers Ckt.98A Upgrade | Upgrade Bellaire to Smithers Ckt.98A to increase thermal limits |  | Bellaire | Smithers | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 | 2023-11-13 | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44650, 47000 | Y | N |  |  | 64492 | 64491
61400 | Esperanza-Fair Oaks Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the 4.3-mile T503 Esperanza to Fair Oaks Ranch 138-kV and T656 Bergheim to Kendall 345-kV double-circuit transmission line between Esperanza Substation and existing structure #173 and the 0.12-mile T506 Fair Oaks to Fair Oaks Ranch 138-kV and T656 double-circuit transmission line between Fair Oaks Substation and structure #173B by replacing the aging conductors. |  | Esperanza | Fair Oaks | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2023-11-30 | 2024-02-29 | 345 | 0 | 4.42 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 5470, 7046, 7169, 7710, 7770 | Y | N |  |  | 78303 | 61400
4567 | BRYN_4567_Smetana_to_Leonard | Build Smetana to Leonard Rd 138 line in existing 69KV ROW of old Annex to Atkins line |  | 32897 | 32863 | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2023-11-30 | 2023-08-28 | 138 | 0.75 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32850, 32851, 32853, 32868 | Y |  |  |  | 76693 | 4567
75901 | Upgrade Ckt.90D Garrott to Midtown to increase thermal limits | Upgrade Ckt.90D Garrott to Midtown to increase thermal limits |  | Garrott | Midtown | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 | 2024-04-23 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47660, 47661, 47707, 47709 | Y | N |  |  | 75902 | 75901
67987 | BIGVUE to Channelview Relay Upgrades | Upgrade BIGVUE and Channelview relays to increase thermal limits on Ckt.03G BIGVUE to Lyondell |  | BIGVUE | Lyondell | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-11-30 | 2023-11-20 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40190, 40280, 40281, 48232 | Y | N |  |  | 67988 | 67987
5792A | Leonard Road Substation 138 | Convert Leonard RD Sub to 138kV. Substation will be on a radial fed out of Smetana Sub until Line from Atkins to Leonard Rd is complete. Leonard Rd has dual voltage Transformer. |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2023-11-30 | 2023-08-28 | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32051, 32851, 32864 | Y | N |  |  | 72135 | 5792
66368 | Rebuild West Columbia Main - Brazoria 138kV with 795 ACSS |  |  | West Columbia Main (bus # 39500) | Brazoria (bus # 39600) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-12-01 | 2023-12-18 | 138 | 0 | 10.2 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 39600 | Y |  |  |  | 66369 | 66368
66198 | Rebuild West Columbia Main-CNP West Columbia with bundled 795 ACSS |  |  | TNMP West Columbia Main (bus # 39500) | CenterPoint West Columbia (bus # 43380) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-12-01 | 2023-09-25 | 138 | 0 | 0.32 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 43380 | Y |  |  |  | 66199 | 66198
72570 | PEC_HeroWay_Substation_Addition | Add new three terminal ring bus substation to 138 kV line between Nameless and Leander and install 46.7 MVA distribution transformer. The new substation will be located approximately 3.1 miles (45% of existing line length) from Leander substation. Replaces Project ID 63906. |  | Nameless | Leander | Planned | 61279 | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-12-01 | 2024-03-01 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 70525, 70526, 70536 | Y | N |  |  | 72571 | 72570
64754 |  | Loop new 138kV Crossroads substation into existing 138kV Potranco to AMD transmission line |  |  |  | Planned | T-0310 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0962 | 2023-12-01 | 2023-12-07 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5002, 5102, 5346 | Y |  |  |  | 64755 | 64754
78281 | [5 empty] | In-Service |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2023-12-01 | 2023-12-20 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2626, 6791, 6807 | Y |  |  |  | 78282 | 78281
73127 | Pomelo: Construct (2) 345 kV terminals | Build new terminals at Cenizo, Del Sol, Lobo, and Pomelo | IN-SERVICE | Pomelo |  | In-Service |  | ETT | James Weaver mlforcum@aep.com 918-599-2674 | TP2021704 | 2023-12-07 | 2023-12-07 | 345 | 0 | 0 | 0 |  | Starr |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8574 | Y | Y |  |  | 73128 | 73127
69002 | Pronto: Build new 345 kV station | Construct new Pronto 345 kV station for the ETT 2nd circuits project | IN-SERVICE | Pronto |  | In-Service |  | ETT | Adam Wells mlforcum@aep.com 918-599-2674 | TP2021709 | 2023-12-08 | 2023-12-08 | 345 | 0 | 0 | 0 |  | Starr |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80231, 80355, 80381, 160885, 161855 | Y | Y |  |  | 69003 | 69002
76247 | Rapido to Tiempo: Build new 345 kV line | Install conductor between North Edinburg and Tiempo | IN-SERVICE | Rapido | Tiempo | In-Service |  | ETT | Teresa Trotman mlforcum@aep.com 918-599-2674 | TP2021702 | 2023-12-13 | 2023-12-13 | 345 | 26.5 | 0 | 0 |  | Starr | Zapata | Tier 3 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80224, 80227, 80355 | Y | Y |  |  | 76248 | 76247
55299 | Munday to Throckmorton: Rebuild 69 kV line | Rehab 69 kV line from Munday to Throckmorton | IN-SERVICE | Munday | Throckmorton | In-Service | 1094 - 1272 | AEP TNC | Raza Ansari twang1@aep.com 918-599-2635 | 1862 | 2023-12-14 | 2023-12-14 | 69 | 0 | 34.55 | 0 |  | Knox | Throckmorton | Tier 4 | 21RPG015 | 2021-08-24 | 2021-09-28 |  | 6107, 6204, 6205 | Y | N |  |  | 65569 | 55299
76385 | Gibson 345 kV Switch | Establish the Gibson 345 kV Switch |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6218 | 2023-12-15 | 2023-12-15 | 345 | 0 | 0 | 0 |  | Milam |  | Tier 4 |  |  |  |  | 3705, 3706, 39950 | Y |  |  |  | 76386 | 76385
66571 | Texaco Mabee Tap - Midland East 138 kV Line Rebuild | Add Texaco Mabee Tap - Midland East 138 kV Line Rebuild |  | Texaco Mabee Tap | Midland East | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8304 | 2023-12-15 | 2023-12-15 | 138 | 0 | 15.4 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 1023, 1171, 1178, 1184, 11278, 11279, 11280, 11301 | Y |  |  |  | 76426 | 66571
76564 | Little Pond 345 kV Switch | Establish the Little Pond 345 kV Switch |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6188 | 2023-12-15 | 2023-12-15 | 345 | 0 | 0 | 0 |  | Milam |  | Tier 4 |  |  |  |  | 3377, 3687, 3704 | Y |  |  |  | 76565 | 76564
68793 | Expanse 345/138 kV Switch | Construct a new 345/138 kV switch |  | Brown | Grady | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8593 | 2023-12-15 | 2023-12-15 | 345 | 0 | 0 | 1200 |  | Martin | Martin | Tier 3 | 22RPG007 | 2022-03-06 | 2022-04-04 |  | 11338, 11366, 11367, 11368, 11369, 11370, 23842 | Y |  |  |  | 74017 | 68793
59835 | Royse Switch-Terrell Switch 69 kV Line Conversion to 138 kV | Convert the existing 69 kV Line to 138 kV |  | Royse | Terrell | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3223 | 2023-12-15 | 2023-12-11 | 69 | 0 | 0 | 0 |  | Rockwall | Rockwall | Tier 4 |  |  |  |  | 2463, 2471, 2472, 2721, 2722, 2729, 2773, 3188, 12470, 12722, 12729, 12730 | Y |  |  |  | 59836 | 59835
66186 | Carrollton Northwest - Carrollton East 138 kV Line | Terminate the existing Northlake - Carrollton East 138 kV Line at Carrollton Northwest |  | Carrollton East |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4205 | 2023-12-15 | 2023-12-21 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2362, 2363, 2385, 2578 | Y |  |  |  | 66187 | 66186
68968 | North Edinburg to Pomelo: Build new 345 kV line | Install conductor between North Edinburg and Tiempo | IN-SERVICE | North Edinburg | Pomelo | In-Service |  | ETT | Teresa Troman mlforcum@aep.com 918-599-2674 | TP2021702 | 2023-12-15 | 2023-12-15 | 345 | 40.501 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 3 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8383, 8574 | Y | Y |  |  | 76241 | 68968
72582B | Nameless to Leander Transmission Line Upgrade | Rebuild and upgrade Leander to Hero Way with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA).(Replaces ERCOT Project # 61279B) |  | Leander | Hero Way | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2023-12-15 | 2024-03-01 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70525, 70536 | Y | N |  |  | 72584 | 72582
72000 | DeCordova Switch_Carmichael Bend Switch 138 kV Line | Upgrade existing DeCordova Switch Carmichael Bend Switch 138 kV Line |  | DeCordova Switch | Carmichael Bend Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3019 | 2023-12-15 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Hood | Hood | Tier 4 |  |  |  |  | 1891, 2888 | Y |  |  |  | 72001 | 72000
64484 | Cumby_Kiowa Conversion | Converting voltages for several Rayburn buses from 69 kV to 138 kV. |  | Cumby | Kiowa | Planned |  | RCEC | Scott Donhamsdonham@rayburnelectric.com 469-402-2024 |  | 2023-12-15 | 2023-05-03 | 138 | 0 | 0 | 0 |  | Hunt | Hunt | Tier 4 |  |  |  |  | 6823, 6861, 6869, 6871, 37361 | Y |  |  |  | 72129 | 64484
71997 | Collin Autotransformer #2 tertiary reactors | Install new reactors on Collin Autotransformer #2 |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4014 | 2023-12-15 | 2023-12-26 | 345 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  |  | 29578 | Y |  |  |  | 71998 | 71997
71991 | Valley South 345 kV Reactors | Install new 345 kV reactors |  | Valley South |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3013 | 2023-12-15 | 2023-12-29 | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1729 | Y |  |  |  | 71992 | 71991
72002 | Anna Autotransformer #2 tertiary reactors | Install new reactors on Anna Autotransformer #2 |  | Anna |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4013 | 2023-12-15 | 2023-12-08 | 345 | 0 | 0 | 0 |  | Collin |  | Tier 4 |  |  |  |  | 12374 | Y |  |  |  | 72003 | 72002
63933 | Cedar Crest 69 kV Substation Conversion To 138 kV | Convert Cedar Crest 69 kV Substation To 138 kV |  | Cedar Crest |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4193 | 2023-12-15 | 2023-05-15 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2486, 2493, 2494, 2495, 2982, 2985, 12486 | Y |  |  |  | 68789 | 63933
45670 | East Stiles - Rocky Road 138 kV Line | Upgrade the existing 138 kV line |  | East Stiles | Rocky Road | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8597 | 2023-12-15 | 2023-09-15 | 138 | 0 | 7.1 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 23864, 23869 | Y |  |  |  | 71129 | 45670
64382 | Bowman Auto 1 Upgrade | Upgrade existing Bowman Auto #1 300 MVA to 600 MVA. |  | Bowman | Bowman | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4021 | 2023-12-15 | 2023-12-15 | 345 | 0 | 0 | 600 |  | Archer | Archer | Tier 3 | 22RPG008 | 2022-03-15 | 2022-04-15 |  | 1422, 1423, 29048 | Y | N |  |  | 64383 | 64382
59745 | Royse Switch - Oates (GP&L) 138 kV Line | Upgrade existing 138 kV Line |  | Royse | Oates | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4236 | 2023-12-15 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Rockwall | Dallas | Tier 4 | [5 empty] | Y |  |  |  | 59746 | 59745 | 2020-NC25
62436 | Cedar Hill - Desoto Hampton Road 138 kV Line | Rebuild the existing 138 kV Line |  | Cedar Hill Switch | Desoto Hampton Road | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4175 | 2023-12-15 | 2023-12-19 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 3058, 3059, 3060, 3065, 3066 | Y |  |  |  | 62437 | 62436
50896 | Garnet: Build new 138 kV station | Interconnect Norton solar farm on the Ballinger to Oak Creek 138 kV line | IN-SERVICE | Garnet |  | In-Service | 1049 - 1222 | AEP TNC | Bryan Oyster mlforcum@aep.com 918-599-2674 | 2824 | 2023-12-15 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Runnels |  | Tier 4 |  |  |  |  | 6325, 6340, 60451 | Y | N |  |  | 50897 | 50896
69417 | Crater Rock 138 kV Switch | Establish Crater Rock 138 kV Switch |  | Horseshoe Springs | Three Mile Draw | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8604 | 2023-12-15 | 2023-12-14 | 138 | 0 | 0 | 0 |  | Culberson | Culberson | Tier 4 |  |  |  |  | 1095, 11103, 11224 | Y |  |  |  | 69419 | 69417
64856 | North Edinburg to Palmito: Build second circuit 345 kV line | Hang conductor to complete a double circuit between North Edinburg and Palmito for the ETT 2nd circuits project | IN-SERVICE | North Edinburg | Palmito | In-Service |  | ETT/SHARYLAND | Teresa Trotman mlforcum@aep.com 918-599-2674 | TP2021701 | 2023-12-15 | 2023-12-15 | 345 | 48 | 0 | 0 |  | Hidalgo | Cameron | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8383, 79500 | Y | Y |  |  | 68950 | 64856
65366 | Converts TNMP Lone Oak to 138 kV. | TNMP Lone Oak conversion projected to be ready by 5/15/2023. |  | Rayburn Loan Oak (Bus # 6871) | TNMP Loan Oak (Bus # 37360) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2023-12-15 | 2023-06-19 | 138 | 0 | 0 | 0 |  | Rains | Rains | Tier 4 |  |  |  |  | 37360, 37361 | Y |  |  |  | 65367 | 65366
66006 | Sherry 138 KV Switch Terminal Equipment | Upgrade terminal equipment a Sherry 138 kV Switch |  | Sherry |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5101 | 2023-12-15 | 2023-10-15 | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 1919, 2257 | Y |  |  |  | 66007 | 66006
71180 | Hutto - Brushy Creek 138 kV Line | Hutto - Hutto East (Teal) - Brushy Creek 138 kV Line |  | Hutto | Brushy Creek | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6211 | 2023-12-15 | 2023-12-15 | 138 | 11.6 | 10.4 | 0 |  | Williamson | Williamson | Tier 3 | 22RPG016 | 2022-05-01 | 2022-06-01 |  | 3362, 3541, 3673, 3692, 3693 | Y |  |  |  | 71181 | 71180
69552A | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 138 kV Switch (Oncor) | Hard Tap POI to be complete in May 2024 | Teal | Teal | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6165 | 2023-12-15 | 2024-05-15 | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 3666, 3673, 13364 | Y |  |  |  | 69553 | 69552
68761 | Blue Acres - South Midland 138 kV Line | Upgrade the existing 138 kV Line |  | Blue Acres | South Midland | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8617 | 2023-12-15 | 2023-08-31 | 138 | 0 | 5.5 | 0 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 23857, 23860 | Y |  |  |  | 68764 | 68761
68768 | Buffalo - Triangle 138 kV Line | Upgrade the existing 138 kV Line |  | Buffalo | Triangle | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8618 | 2023-12-15 | 2023-09-30 | 138 | 0 | 3.5 | 0 |  | Midland | Midland | Tier 3 | 22RPG006 | 2022-03-06 | 2022-04-04 |  | 23837, 23839 | Y |  |  |  | 68770 | 68768
71164 | Haggerty-Bells 138 kV Line Section | Rebuild portion of Haggerty-Bells 138 kV Line Section |  | Haggerty | Bells | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4336 | 2023-12-16 | 2023-12-12 | 138 | 0 | 0 | 0 |  | Grayson | Grayson | Tier 4 |  |  |  |  | 1699, 1753, 12677 | Y |  |  |  | 71165 | 71164
62041 | Twinwood 138kV Distribution Substation | Remove Twinwood Mobile (TWM) substation and install new Twinwood (TWN) 138kV Distribution Substation. Loop from existing Ckt.25E to create new Ckt.25E Foster to Twinwood to Peters |  | Twinwood | Foster/ Peters | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-30 | 2023-11-14 | 138 | 0.08 | 0 | 0 |  | Fort Bend | Austin | Tier 4 |  |  |  |  | 44230, 44256, 44860, 44861, 46220 | Y | N |  |  | 62042 | 62041
57412 | GENRAL Substation Removal | Remove 69kV GENRAL substation from CNP service |  | GENRAL | Garden Villas | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 | 2024-01-22 | 69 | 0 | 9.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42690, 47540, 47670 | Y | N |  |  | 61869 | 57412
70596 | LCRATSC_CraneEast_CB_Sub_Upgrade | Install circuit breakers in a ring bus configuration at Crane East Substation. Install two (2) 31.2 MVAR 138-kV capacitor banks at Crane East Substation. All substation equipment at Crane East Substation connected in series with the existing 138-kV transmission lines shall support a minimum rating of 3000 A at 105 degree F ambient temperature. |  | Crane EAst |  | Planned |  | LCRATSC | Dylan Preas dylan.preas.@lcra.org 512-578-4514 |  | 2023-12-31 | 2023-12-31 | 138 | 0 | 0 | 0 | 0,62.4 | Upton | Upton | Tier 4 |  |  |  |  | 71214 | Y | N |  |  | 70597 | 70596
66050 | 138 kV Fulshear Distribution Substation | Install Fulshear Distribution Substation to create Ckt.25 FOSTER to Fulshear to Twinwood. |  | Fulshear | FOSTER/Twinwood | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-12-31 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44230, 44256, 44750, 44860, 46220 | Y | N |  |  | 81349 | 66050
70194 | LCRATSC_Hallettsville_Mont_TL_Overhaul | LCRA TSC will perform an overhaul on the 2.3-mile Hallettsville ¿ Mont (T593) 138-kV transmission line. |  | Hallettsville | Mont | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2023-12-31 | 2023-12-31 | 138 | 0 | 2.3 | 0 |  | Lavaca | Lavaca | Tier 4 |  |  |  |  | 7246, 7249 | Y | Y |  |  | 78306 | 70194
76620 | This is a duplicate project. Correct project is MOD78457 | This is a duplicate project. Correct project is MOD78457 |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-01 | 2024-04-26 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 76621 | 76620
75564 | Brightright Switch (Hopkins Solar) |  |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R990 | 2024-01-01 | 2023-05-15 | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 11684, 11688, 11689, 120825 | Y |  |  |  | 75565 | 75564
52260 | India to DWU Rebuild | India to DWU Rebuild |  | India | Dallas Water Utilities | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-01-01 | 2023-08-31 | 69 | 0 | 0 | 0 |  | Ellis | Dallas | Tier 4 |  |  |  |  | 230, 2351 | Y |  |  |  | 52261 | 52260 | 2019-NC2
52688 | Angleton Substation Expansion | Expand Angleton substation for the Myrtle Solar generator interconnection (19INR0041). |  | Angleton |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 | 2022-12-08 | 138 | 0.07 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110 | Y | N |  |  | 55842 | 52688
52322 | Establish Courtney Creek Switch | Establish Courtney Creek 138/69 kV Switch |  | Courtney Creek Switch | Athey (AEP) | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8479 | 2024-01-05 | 2023-05-23 | 138 | 0 | 0 | 82 |  | Pecos | Pecos | Tier 4 | [5 empty] | Y |  |  |  | 80768 | 52322
57521B | Stone Lake New Sub Ckt66 | Upgrade Ckt.66 Hockley to Stone Lake BP2023 as a transmission project. |  | Stone Lake | Hockley/Tomball | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 | 2022-11-07 | 138 | 0 | 15.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45880, 45886 | Y | N |  | Cost included in main entry | 80168 | 57521
62728 | Wink - Shifting Sands 69 kV Line Conversion to 138 kV | Convert the existing Wink - Shifting Sands 69 kV Line to 138 kV |  | Wink | Shifting Sands | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8581 | 2024-01-05 | 2023-12-15 | 69 | 0 | 13 | 0 |  | Winkler | Winkler | Tier 4 | [5 empty] | Y |  |  |  | 80770 | 62728
59552 | Rebuild Eskota - Sweetwater No.2 69 kV Line | Rebuild Eskota - Sweetwater No.2 69 kV Line |  | Eskota | Sweetwater No. 2 | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8570 | 2024-01-05 | 2023-05-30 | 69 | 0 | 16.3 | 0 |  | Nolan | Nolan | Tier 4 |  |  |  |  | 1340, 1381, 1382, 1383, 1384, 1385, 1386, 1387, 11384 | Y |  |  |  | 76429 | 59552
64589 | Jeanetta Auto A3 Upgrade | Upgrade Jeanetta Auto A3 to increase thermal limits |  | Jeanetta |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 | 2023-01-12 | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47300, 47310, 49082 | Y | N |  |  | 64590 | 64589
61519 | Salt Flat Road - Skywest 138 kV Line Rebuild | Salt Flat Road - Skywest 138 kV Line Rebuild |  | Salt Flat Road | Skywest | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8569 | 2024-01-05 | 2023-12-21 | 138 | 0 | 1 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23859, 71210 | Y |  |  |  | 61521 | 61519
61516 | Blissard - East Stiles 138 kV Line Section | Rebuild the Blissard - East Stiles 138 kV Line Section |  | Blissard | East Stiles | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8565 | 2024-01-05 | 2023-06-29 | 138 | 0 | 13.1 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 11353, 23869 | Y |  |  |  | 61518 | 61516
57521C | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 00:01 | 2022-11-07 | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 80169 | 57521
57521D | Stone Lake New Sub Ckt66 | Add Cap Bank #1 at Stone Lake Substation |  | Stone Lake |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-05 00:02 | 2022-11-07 | 138 | 0 | 0 | 0 | 0,14.4 | Harris |  | Tier 4 |  |  |  |  | 44840 | Y | N |  | Cost included in main entry | 80170 | 57521
62327 | Upgrade Fairfield West - Big Brown Tap 138 kV Line | Upgrade Fairfield West - Big Brown Tap 138 kV Line |  | Fairfield West | Big Brown Tap Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6138 | 2024-01-15 | 2023-12-15 | 138 | 0 | 8 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 196, 3508, 3510 | Y |  |  |  | 62328 | 62327
66178 | Centerville Switch - Centerville Road - Lake Hubbard Switch 138 kV Double-Circuit Line | Upgrade the existing 138 kV DCKT Line |  | Lake Hubbard | Centerville | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4127 | 2024-01-15 | 2023-12-05 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2401, 2402, 2439, 2450, 2917, 2918 | Y |  |  |  | 66179 | 66178
71193 | Blue Acres - Yosemite 138 kV Line | Upgrade the existing 138 kV line |  | Blue Acres | Yosemite | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8638 | 2024-01-15 | 2024-02-09 | 138 | 0 | 5.9 | 0 |  | Midland | Midland | Tier 4 | [5 empty] | Y |  |  |  | 80828 | 71193
71995 | Weatherford West 138 kV Switch Terminal Equipment | Upgrade terminal equipment at Weatherford West 138 kV Switch |  | Weatherford |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5519 | 2024-01-15 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 512, 1589 | Y |  |  |  | 71996 | 71995
61438 | Sim Gideon - Tahitian Village Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 5.1-mile Sim Gideon ¿ Tahitian Village (T648) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Sim Gideon | Tahitian Village | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-01-21 | 2024-05-09 | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7310, 7575 | Y | N |  |  | 61439 | 61438
64774 |  | Loop new 138kV Donop substation into existing 138kV Southton to Braunig transmission line. |  |  |  | Planned | T-0311 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0963 | 2024-01-25 | 2024-02-01 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5128, 5394 | Y |  |  |  | 64775 | 64774
48587 | Tesoro 345/138 kV Switch | Construct a new 345/138 kV switch (formerly known as Quail East) |  | Consavvy | Quail/Midessa South | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8634 | 2024-01-30 | 2024-02-05 | 345 | 0 | 0 | 1200 |  | Midland | Midland | Tier 3 | 22RPG032 | 2022-10-11 | 2022-11-07 |  |  | Y |  |  |  | 80829 | 48587
64941A | PETSON to MONSAN Ckt.04D Upgrade | Upgrade Ckt 04D PETSON to MONSAN to increase thermal limits. Upgrade MONSAN equipment to 4000A. |  | PETSON | MONSAN | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-30 12:00 | 2023-05-24 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42940, 43070 | Y | N |  |  | 75897 | 64941
72034 | Blodgett to TECO Ckt.37C Upgrades | Rebuild/Reconductor Ckt.37C Blodgett to TECO as a Hardening upgrade |  | Blodgett | TECO | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-11-08 | 138 | 0 | 3.02 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47430, 47520 | Y | N |  |  | 72035 | 72034
73452 | TNMP_WINK_FISHHOOK_RECONDUCTOR_AC_4-5-2023 |  |  | bus 37900 wink to bus 38180 fishhook |  |  |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-01-31 | 2023-11-17 | 138 | 13.5 | 0 |  |  | Pecos | Pecos | Tier 4 |  |  |  |  | 37900, 38180 | Y |  |  |  | 73453 | 73452
70665B | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | Upgrade Ckt.03G BIGVUE to Lyondell tap to increase thermal limits |  | BIGVUE | Lyondell | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-11-20 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40190, 41023 | Y | N |  |  | 75839 | 70665
67422A | Greens Bayou to Clinton 138kV Conversion | Rebuild-Reconductor Ckt.61A Greens Bayou to Wallisville (TEXWAL LOCATION) to Prepare for 138kV Conversion |  | Greens Bayou | Wallisville | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-08-09 | 69 | 0 | 6.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40720, 41681 | Y | N |  |  | 87573 | 67422
77146 | Reconducter WNK-AAT-MDT-FSH |  |  | Wink (37900) | Fishhook (38180) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-01-31 | 2024-01-19 | 138 | 0 | 13.18 | 0 |  | Winkler | Ward | Tier 4 |  |  |  |  | 37900, 38135, 38140, 38180 | Y |  |  |  | 77147 | 77146
66532 | Grey Well Draw - Pronghorn 138 kV Line Rebuild | Add Grey Well Draw - Pronghorn 138 kV Line Rebuild |  | Grey Well Draw | Pronghorn | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8606 | 2024-01-31 | 2024-02-05 | 138 | 9.9 | 0 | 0 |  | Midland | Midland | Tier 4 | [5 empty] | Y |  |  |  | 80769 | 66532
67933 | Springwood & Rayford Substation Upgrades | Install 3rd distribution transformer at Rayford substation. Install in-series breakers at Springwood to increase reliability on the Ckt.22B Rothwood to Rothwood loop. |  | Rothwood | Springwood | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-12-12 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46260, 46270, 46273, 46295, 48273 | Y | N |  |  | 80833 | 67933
64493 | Bellaire to WAP Ckt.50A Upgrade | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits |  | Bellaire | WA Parish | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-10-16 | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47000 | Y | N |  |  | 64494 | 64493
72049 | Crabb River Road to Imperial Ckt.80B Upgrades | Reconductor portions of Ckt.80B Crabb River Road to Imperial as a Hardening upgrade |  | Crabb River | Imperial | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-12-13 | 138 | 0 | 5.04 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44341, 48167 | Y | N |  |  | 81350 | 72049
69888B | Deepwater to Clinton Ckts.33B-33C Line Upgrades | Rebuild-Reconductor portions of Ckt.33C Clinton to Harrisburg ahead of future 138kV conversions. |  | Clinton | Harrisburg | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2024-01-11 | 69 | 0 | 4.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40352, 40800 | Y | N |  | Cost included in other phase. | 70972 | 69888
71196 | Grey Well Draw - Pecan Grove 138 kV Line | Rebuild existing 138 kV line |  | Grey Well Draw | Pecan Grove | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8640 | 2024-01-31 | 2024-02-05 | 138 | 0 | 7.8 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23860, 23861 | Y |  |  |  | 71198 | 71196
69908 | Install 138kV Capacitor Bank at FM524 |  |  | TNMP FM524 Substation (bus # 39703) |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-01-31 | 2023-12-20 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39703 | Y |  |  |  | 69909 | 69908
66074 | Double ckt Soaptree-Holiday-AlamoSt |  |  | Soaptree (bus # 38450) | Alamo Street (bus # 38330) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-01-31 |  | 138 | 0 | 31.9 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38331, 38450, 38455 | Y |  |  |  | 66075 | 66074
67270E | BP23 Reliability Upgrades | Upgrade Ckt.27A DOW to Jones Creek to increase thermal limits |  | DOW | Jones Creek | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-10-31 | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 42530 | Y | N |  |  | 67275 | 67270
67270D | BP23 Reliability Upgrades | Upgrade Ckt.08B Knight tap to Stadium to Fannin to increase thermal limits |  | Knight | Fannin | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-12-14 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47090, 47420, 48198 | Y | N |  |  | 67274 | 67270
67270B | BP23 Reliability Upgrades | Upgrade Ckt.37A Bellaire to Kirby to increase thermal limits |  | Bellaire | Kirby | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-10-16 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47015, 47320 | Y | N |  |  | 67272 | 67270
67270A | BP23 Reliability Upgrades | Upgrade Ckt.21J Airline to White Oak to increase thermal limits |  | Airline | White Oak | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2023-11-30 | 138 | 0 | 3 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45630, 46610 | Y | N |  |  | 67271 | 67270
63495 | Cedar Canyon to Noelke 2nd circuit | Add the 2nd circuit to CREZ Cedar Canyon to Noelke 345 kV line |  | Cedar Canyon | Noelke | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-01-31 | 2024-02-13 | 345 | 16 | 0 | 0 |  | Crockett | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 7053, 76015 | Y | N |  |  | 63496 | 63495
67217A | Addicks to Campbell Ckts 09 & 21 Upgrades | Upgrade Ckt.09I Addicks to Campbell tap to increase thermal limits |  | Addicks | Campbell | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2024-01-04 | 138 | 0 | 3.53 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45610, 48056 | Y | N |  |  | 67218 | 67217
67217B | Addicks to Campbell Ckts 09 & 21 Upgrades | Upgrade Ckt.21H Addicks to Campbell tap to increase thermal limits |  | Addicks | Campbell | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 | 2024-01-04 | 138 | 0 | 3.53 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45610, 46610, 48057, 48349 | Y | N |  | Cost included in Phase A | 67219 | 67217
70623C | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04 Danbury to Liverpool to Snug to increase thermal limits |  | Liverpool | Danbury/Snug | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 00:02 | 2024-05-24 | 138 | 0 |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42870, 42875, 44890 | Y | N |  |  | 70626 | 70623
66221E | Galena Park Area Conversion Project | De-energize Ckt.20C Galena Park to Greens Bayou |  | Galena Park | Greens Bayou | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 00:04 | 2023-02-08 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40725 | Y | N |  | Cost included in main entry | 86744 | 66221
66221J | Galena Park Area Conversion Project | Expand Clinton 138kV Facilities and Install 200MVA Autotransformer. Loop existing 138kV Clinton circuits into expanded 138kV Clinton substation. Install as Clinton Auto A1. |  | Clinton |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 00:08 | 2023-12-16 | 138 | 0 | 0 | 200 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40235, 40350, 40352, 49004 | Y | N |  | Cost included in main entry | 86745 | 66221
64941B | PETSON to MONSAN Ckt.04D Upgrade | Upgrade Ckt 04D PETSON to MONSAN to increase thermal limits. Upgrade PETSON equipment to 4000A. |  | PETSON | MONSAN | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-01-31 12:00 | 2024-01-07 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42940, 43070 | Y | N |  |  | 75898 | 64941
6931 | New Tres Lagos Substation | Adds new station and short line from W Edinburg-Alton line |  | West Edinburg | Alton | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-02-01 | 2024-05-15 | 138 | 1.8 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5770, 5771, 5772 | Y | N |  |  | 14750 | 6931
61457 | Nada - Ricebird Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 13.1-mile Nada ¿ Ricebird (T588) 138-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Nada | Ricebird | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-02-02 | 2024-02-02 | 138 | 0 | 0 | 0 |  | Colorado | Wharton | Tier 4 |  |  |  |  | 78103, 78104 | Y | N |  |  | 61458 | 61457
68974 | Second circuit from San Miguel to Fowlerton 345 kV | String the second circuit on existing towers from San Miguel to Fowlerton |  | San Miguel | Fowlerton | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-02-08 | 2024-05-01 | 345 | 36.4 | 0 | 0 |  | Atascosa | McMullen | Tier 1 |  |  |  |  | 5709, 5901 | Y | N |  |  | 68975 | 68974
75514 | Rising Star Area Conversions | This project converts the voltage from Holder (292) to Nimrod (289) to 138 KV |  | Holder (292) | Nimrod (289) | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-02-12 | 2024-02-29 | 138 | 0 | 28.5 | 0 |  | Brown | Comanche | Tier 4 |  |  |  |  | 285, 289, 292 | Y |  |  |  | 75515 | 75514
66124 | Prarie Swiitch Wind Interconnect | Connect Crawfish to El Campo to Lane City 138 kV Line | IN-SERVICE | EL CAMPO | LANE CITY PUMP | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2021286 | 2024-02-14 | 2024-02-14 | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8102, 8104, 8679 | Y |  |  |  | 66125 | 66124
64310 | Cumby-Cumby Tap Line Conversion | Cumby - Cumby Tap Radial Line 69 to 138 kV Conversion. Project requires coordination with RCEC and TNMP. |  | Cumby Tap | Cumby Substation | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R944 | 2024-02-16 | 2024-03-11 | 138 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1812, 1813, 1815, 6861 | Y | N |  |  | 66059 | 64310
52147 | Rising Star Area Conversions | Converts voltage to 138 KV from Holder to Nimrod to Rising Star. |  | Holder |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-02-22 | 2024-02-29 | 138 | 0 | 0 | 0 |  | Brown | Comanche | Tier 4 |  |  |  |  | 289, 292, 293 | Y |  |  |  | 52148 | 52147
72055 | Fort Bend 138kV Substation Expansion for Brazos Bend BESS (23INR0363) | Expand Fort Bend 138kV substation for Brazos Bend BESS generator interconnection (23INR0363) |  | Fort Bend |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 | 2023-11-17 | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44280, 113302 | Y | N |  |  | 72056 | 72055
65003 | WA Parish to Nash Ckt.02B Upgrades | Upgrade Ckt.02B WA Parish to Nash to replace aging infrastructure and to address line clearance concerns |  | WA Parish | Nash | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 | 2024-02-06 | 138 | 0 | 18.02 | 0 |  | Fort Bend | Brazoria | Tier 4 | 21RPG013 | 2021-08-08 | 2021-09-10 |  | 42410, 42980, 44010, 48364, 48365 | Y | N |  |  | 65004 | 65003
70665D | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | Install generator lead from Danek (DNK) substation to JADE/Remy Jade. |  | Danek | JADE | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 | 2024-03-14 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 75841 | 70665
66221A | Galena Park Area Conversion Project | Remove Galena Park Auto A1. Remove Galena Park 69kV facilities. Remove Galena Park 138kV ring bus. Rebuild Galena Park substation for double-tap 138kV service. |  | Galena Park |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 | 2024-02-15 | 69 | 0 | 0 | -200 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40610, 40611, 40752, 49015 | Y | N |  |  | 86746 | 66221
66221B | Galena Park Area Conversion Project | De-energize Ckt.38A Galena Park to GYPSUM |  | Galena Park | GYPSUM | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:01 | 2024-02-08 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40611, 40619, 40720, 40751 | Y | N |  | Cost included in main entry | 86747 | 66221
66221C | Galena Park Area Conversion Project | De-energize Ckt.17A Galena Park to Greens Bayou |  | Galena Park | Greens Bayou | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:02 | 2024-02-08 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 |  | Y | N |  | Cost included in main entry | 86748 | 66221
66221D | Galena Park Area Conversion Project | De-energize Ckt.38B Clinton to Greens Bayou |  | Clinton | Greens Bayou | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:03 | 2024-02-08 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40352, 40720 | Y | N |  | Cost included in main entry | 86749 | 66221
66221F | Galena Park Area Conversion Project | Rebuild Galena Park substation for double tap service. Bypass Galena Park breakers with Ckt.94 and tap Galena Park to create new Ckt.94M CITFIL to Normandy tap to Galena Park tap to TANKER |  | CITFIL | TANKER | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:05 | 2024-02-18 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40610, 40611, 40612, 40613, 40614, 40615, 40630, 48130, 48261, 48613 | Y | N |  | Cost included in main entry | 86750 | 66221
66221H | Galena Park Area Conversion Project | Join 69kV Greens Bayou buses 40720 & 40725 at a Minimum 40KAIC |  | Greens Bayou |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-02-28 00:07 | 2024-02-08 | 69 | 0 | 0 | 0 |  | Harris |  | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40720, 40725, 41570, 41681 | Y | N |  | Cost included in main entry | 86751 | 66221
4010 | Rebuild Magnolia - Seminole 138 kV line. | *Project pushed back to 2023. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | STE07216 | 2024-03-01 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38950, 38990 | Y |  |  |  | 11530 | 4010
68804 | Loop Nine 345/138 kV Switch | Establish Loop Nine 345/138 kV Switch |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4327 | 2024-03-05 | 2023-06-05 | 345 | 0 | 0 | 0 |  | Ellis | Dallas | Tier 3 | 22RPG014 | 2022-05-15 | 2022-06-15 |  |  | Y |  |  |  | 81620 | 68804 | 2021-NC2
62712 | Driver - Skywest 138 kV Line Rebuild | Rebuild the existing Driver - Skywest 138 kV Line |  | Driver | Skywest | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8564 | 2024-03-15 | 2024-06-01 | 138 | 0 | 11.9 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 23863, 71210 | Y |  |  |  | 62716 | 62712
75516 | Rising Star Area Conversions | This converts from NImrod (289) to Rising Star (285) to 138 KV service |  | Nimrod (289) | Rising Star (285) | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-03-20 | 2024-03-11 | 138 | 0 | 0 | 0 |  | Eastland | Comanche | Tier 4 |  |  |  |  | 281, 285, 289 | Y |  |  |  | 75517 | 75516
70964 | WETT 345 kV Volta witch | Construct new 345 kV Volta Switch and two approximately 0.15-mile 345 kV lines between WETT-owned Volta 345 kV Switch and Oncor-owned Expanse |  | Howard | Martin | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2024-03-25 | 2024-06-04 | 345 | 0.3 | 0 | 0 |  | Howard | Martin | Tier 3 | 22RPG007 | 2022-03-06 | 2022-04-04 |  | 11366, 11369, 59900, 59901, 59910 | Y |  |  |  | 80004 | 70964
81396 |  |  |  | RUCKER | RUCKER | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-03-26 | 2024-05-09 | 69 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 287, 1663 | Y |  |  |  | 81397 | 81396
71190 | Einstein - St Lawrence 138 kV Line | Upgrade the existing 138 kV line |  | Einstein | St. Lawrence | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8646 | 2024-03-28 | 2024-03-18 | 138 | 0 | 4.6 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 23852, 23854 | Y |  |  |  | 71192 | 71190
66011A | CNP ARCHER POI for BROTMAN Power | CNP ARCHER POI for BROTMAN Power |  | ARCHER | Rosharon/MANVEL | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-29 12:00 | 2023-03-04 | 138 | 0.66 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44390, 44410, 44430, 44600, 48173, 112969 | Y | N |  |  | 72740 | 66011
66635 | Lamesa 69 kV Substation Conversion to 138 kV | Add Lamesa 69 kV Substation Conversion to 138 kV |  | Lamesa 69 kV | Lamesa 138 kV | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8595 | 2024-03-30 | 2024-03-09 | 69 | 0 | 0 | 0 |  | Dawson | Dawson | Tier 4 | [5 empty] | Y |  |  |  | 80849 | 66635
66011B | CNP ARCHER POI for BROTMAN Power | Upgrade Ckt.26 Rosharon to ARCHER to increase thermal limits. |  | ARCHER | Rosharon/MANVEL | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-30 12:00 | 2023-03-04 | 138 | 0 | 1.28 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44600 | Y | N |  |  | 72741 | 66011
55464 | Adds new Morrow sub near Pearsall | Adds new Morrow substation and short line from Morrow to the Pearsall substation |  | Pearsall | Morrow | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-03-31 | 2024-06-18 | 138 | 0.91 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5895, 5896 | Y | N |  |  | 55465 | 55464
70623A | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04B Hudson to MONSAN to increase thermal limits. Reconductor to 2-959ACSS. |  | Hudson | MONSAN | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 | 2023-06-15 | 138 | 0 | 2 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42100, 42940 | Y | N |  |  | 70624 | 70623
5792B | Leonard Road Substation 138 | Rebuild 138kV Line From Atkins to Leonard in existing 69kV Right of Way. |  | Leonard | Atkins | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2024-03-31 | 2023-09-18 | 138 | 0 | 2 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32851, 32862 | Y | N |  |  | 72136 | 5792
70623E | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04B Hudson to MONSAN to increase thermal limits. Upgrade MONSAN equipment. |  | Hudson | MONSAN | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 | 2023-08-07 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42100, 42940 | Y | N |  |  | 75627 | 70623
70665A | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | New 138kV Danek (DNK) substation for generator interconnection to Remy Jade. Loop Ckt.08G into substation to create new Ckt.08 Crosby to Danek to Highlands tap. |  | Danek | Crosby/Highlands | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 | 2024-03-14 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40390, 40396, 40890, 48141, 113219 | Y | N |  |  | 75840 | 70665
56012 | PSARCO Fault Duty Upgrade with Bus Reactors | Install (3) 10-Ohm Reactors at PSARCO by splitting PSARCO bus as a fault duty upgrade |  | PSARCO |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 | 2023-07-12 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 89391 | 56012
67422H | Greens Bayou to Clinton 138kV Conversion | Rebuild-Reconductor Ckt.61A Greens Bayou (TEXWAL LOCATION) to Wallisville to Prepare for 138kV Conversion |  | Greens Bayou | Wallisville | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 00:01 | 2024-03-31 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40720, 41682 | Y | N |  |  | 87574 | 67422
70623B | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04A Mustang Bayou to Hudson to increase thermal limits |  | Hudson | Mustang | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 00:01 | 2023-06-15 | 138 | 0 |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42100, 42960, 48112 | Y | N |  |  | 70625 | 70623
70623D | Cottonwood Bayou - Related Upgrades | Upgrade Ckt.04 Snug to PETSON to increase thermal limits |  | Snug | PETSON | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 00:03 | 2023-12-20 | 138 | 0 |  | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43070, 44890 | Y | N |  |  | 70627 | 70623
66017A | Westpark Area Upgrades | Upgrade Ckt.05E Bellaire to Sharpstown tap and Dunvale tap to Jeanetta to increase thermal limits |  | Bellaire | Jeanetta | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 12:00 | 2023-06-30 | 138 | 0 | 3.6 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44760, 44762, 47015, 47072, 47310, 48088, 48343 | Y | N |  |  | 78248 | 66017
65704 | Crosby 35kV Distribution Substation | Expand Crosby substation with 35kV Distribution Facilities |  | Crosby | Highlands/Atascosita | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 12:00 | 2023-06-24 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40390 | Y | N |  |  | 65705 | 65704
66017B | Westpark Area Upgrades | Upgrade Ckt.24B Dunvale tap to Westchase tap to increase thermal limits. |  | Dunvale | Westchase | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-03-31 12:01 | 2023-09-18 | 138 | 0 | 2.7 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44762, 47014, 47072, 47442 | Y | N |  |  | 78249 | 66017
52169 | Rising Star Area Conversions | This converts the voltage to 138 following Rising Star Substation Voltage Conversion |  | Rising Star | Downing | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-04-10 | 2024-05-16 | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 281, 285, 294 | Y |  |  |  | 52170 | 52169
81726 | Mobile substation | Project is to add a mobile substation next to Airport Substation tapping into the Transmission line that is Filter Plant to Airport Substation. Then connecting lines South Plant to Southmost by passing Airport Substation. This is due to Airport Substation being decommissioned in April. |  | 59420 Filter Plant, 59500 South Plant | Mobile substation, 5789 Southmost | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2024-04-15 | 2024-04-15 | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5789, 5946, 59420, 59430, 59460, 59500 | Y |  |  |  | 81727 | 81726
76686 | Add Hog Mountain 138 kV POD | Add Hog Mountain 138 kV POD |  | Quartz Sand | Hog Mountain POD | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8673 R8791 | 2024-04-15 |  | 138 | 5.4 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 1328, 18552 | Y |  |  |  | 76687 | 76686
57169 | Rebuild Redgate to N Edinburg 138 kV | Rebuild Redgate to N Edinburg 138kV and opens Redgate tap |  | Redgate | Faysville Switch | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-04-27 | 2024-05-22 | 138 | 0 | 3.45 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5779, 5784, 8380, 88380 | Y | N |  |  | 63733 | 57169
72649A | Add_Celina_Load |  |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2024-04-30 | 2024-04-30 | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2350, 6790, 6793, 6825 | Y |  |  |  | 78608 | 72649
67604 | Stafford Reconfigurations Ckt.05D | Reconfigure Stafford loads served from Ckt.05D. Create Ckt.05D Westchase tap to Stafford loop to Stafford TR4 tap to Missouri City tap |  | Stafford | Missouri City | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-04-30 | 2024-02-06 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44015, 44020, 44670, 44673, 44674, 44676, 44760, 44761, 48162, 48351, 48352, 48358, 49911 | Y | N |  |  | 86917 | 67604
69894 | HO Clarke Substation Expansion for Callisto Energy Center (22INR0490 & 22INR0491) | Expand HO Clarke substation for Callisto Energy Center generator interconnection (22INR0490 & 22INR0491) |  | HO Clarke |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-04-30 | 2024-05-01 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47150, 113105 | Y | N |  |  | 69895 | 69894
70961A | Crosby Sub Exp for HOLY/Citadel BESS and Upgrades | Expand Crosby substation for HOLY/Citadel BESS generator interconnection (24INR0147). Reposition Ckt.08H to a new breaker position. |  | Crosby |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-04-30 | 2024-02-05 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40390, 113333 | Y | N |  |  | 70962 | 70961
72596A | PEC_MarshallFord_Paleface_StormHardening | Rebuild single circuit section of Paleface to Marshal Ford and reconductor with Single 959 ACSS Conductor, 380 MVA; (Replaces ERCOT Project # 61274A) | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-04-30 | 2024-05-01 | 138 | 0 | 3.65 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  |  | 72598 | 72596
72582A | Nameless to Leander Transmission Line Upgrade | Rebuild and upgrade Nameless to Hero Way with double-circuit capable structures and cut in Hero Way substation (ERCOT Project #72570). Install 1 ckt with bundled 795 kcmil conductor (440 MVA). Final span of conductor and terminal equipment at Nameless will be upgraded to 440 MVA with ERCOT project #72576B. (Replaces ERCOT Project # 61279A) | 1/10/2023: Identified related substation project and added information to clarify timing for final circuit rating upgrade. | Hero Way | Nameless | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-05-01 | 2023-12-01 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70526, 70536 | Y | N |  |  | 72583 | 72582
68055 | Rio Colorado substation | Adds new Rio Colorado load serving station between Bay City and Tin Top |  | Rio Colorado |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-05-01 | 2024-02-01 | 69 | 3.8 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5560, 5563, 5569 | Y | N |  |  | 68056 | 68055
72596B | PEC_MarshallFord_Paleface_StormHardening | Reconductor triple circuit section in conjunction with LCRA TSC Storm Hardening project (ERCOT Project #62068) with Single Suwanee Conductor. (Replaces ERCOT Project # 61274B) | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC/LCRATSC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-05-01 | 2024-05-01 | 138 | 0 | 11.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  |  | 72597 | 72596
56350B | Burnett - Bowie 69 kV Line | Rebuild Burnett-Ringgold Magnolia Tap Line |  | Burnett | Ringgold Magnolia Tap | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4015 | 2024-05-14 | 2024-06-15 | 69 | 0 | 20.1 | 100 |  | Wichita | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 1452, 1491, 1543, 1544, 1545 | Y | N |  |  | 73039 | 56350
56350C | Burnett - Bowie 69 kV Line | Establish Old lake switch and convert Fisher Road - Old Lake Switch (FKA Burnett-Ringgold Magnolia Tap) Line from 69 kV to 138 kV |  | Burnett | Ringgold Magnolia Tap | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4015 | 2024-05-14 | 2024-06-15 | 138 | 0 |  | 100 |  | Wichita | Clay | Tier 3 | 21RPG008 | 2021-04-23 | 2021-05-18 |  | 775, 1426, 1452, 1491, 1524, 1543, 1544, 1545, 11540, 11541, 33770 | Y | N |  |  | 73040 | 56350
67377 | Upgrade Bowman Autotransfomer 2 | Upgrade existing Bowman Auto #2 300 MVA to 600 MVA. |  | Bowman | Bowman | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4026 | 2024-05-15 | 2024-05-15 | 345 | 0 | 0 | 600 |  | Archer | Archer | Tier 3 | 22RPG008 | 2022-03-29 | 2022-04-15 |  | 1422, 1424, 29050 | Y | N |  |  | 67378 | 67377
71973 | Morgan Creek - Barber Lake Rebuild West Ckt | Rebuild the existing 138 kV line |  | Morgan Creek | Barber Lake | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8623 | 2024-05-15 | 2024-05-22 | 138 | 0 | 4.75 | 0 |  | Mitchell | Mitchell | Tier 4 |  |  |  |  | 1032, 1190 | Y |  |  |  | 81360 | 71973
70977 | Ozark Trail 345 kV Switch | Establish Ozark Trail 345 kV Switch to provide a POI for Hornet Solar |  | Ogallala | Tule Canyon | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8027 | 2024-05-15 | 2024-05-17 | 345 | 0 | 0 | 0 |  | Castro | Swisher | Tier 4 |  |  |  |  | 23901, 23912, 23914 | Y |  |  |  | 70980 | 70977
45689 | Pronghorn - Salt Flat Road 138 kV Line | Upgrade the existing 138 kV line |  | Pronghorn | Salt Flat Road | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8642 | 2024-05-15 | 2023-12-08 | 138 | 0 | 7.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 23856, 23859 | Y |  |  |  | 71135 | 45689
69352 | Pebble Creek - Desoto 138 kV Line | Rebuild the Pebble Creek - Desoto 138 kV Line |  | Desoto | Pebble Creek | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4328 | 2024-05-15 | 2023-06-05 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 | 22RPG014 | 2022-05-15 | 2022-06-15 |  | 2229, 2328, 2424 | Y |  |  |  | 69353 | 69352 | 2021-NC2
71175 | Tall City - Pecan Grove 138 kV Line | Upgrade the existing 138 kV line |  | Tall City | Pecan Grove | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8635 | 2024-05-15 | 2024-06-01 | 138 | 0 | 11.6 | 0 |  | Midland | Martin | Tier 4 |  |  |  |  | 23840, 23855, 23861 | Y |  |  |  | 71177 | 71175
71172 | Luther - Vealmoor 138 kV Line | Upgrade the existing 138 kV line |  | Luther | Vealmoor | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8636 | 2024-05-15 | 2024-06-12 | 138 | 0 | 10 | 0 |  | Borden | Howard | Tier 4 |  |  |  |  | 23831, 23835 | Y |  |  |  | 71174 | 71172
61402 | Boerne-Esperanza Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the 1.7-mile T657 Boerne to Esperanza 138-kV and T656 Bergheim to Kendall 345-kV double-circuit transmission line between Boerne Split and Esperanza Substation and the 2.2-mile T657 Boerne to Esperanza 138-kV and T228 Boerne to Welfare double-circuit transmission line between Boerne Substation and Boerne Split by replacing the aging conductors. |  | Boerne | Esperanza | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 | 2024-05-10 | 345 | 0 | 3.9 | 0 |  | Kendall | Kendall | Tier 4 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7153, 7168, 7710, 7770 | Y | N |  |  | 61403 | 61402
61465 | Starcke - Wirtz Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 6.7-mile Starcke - Wirtz (T654) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Starcke | Wirtz | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 | 2024-05-15 | 138 | 0 | 0 | 0 |  | Burnet | Burnet | Tier 4 |  |  |  |  | 7104, 7351 | Y | N |  |  | 61466 | 61465
76431 | Establish 345 kV Bale Switch | Establish 345 kV Bale Switch |  | 345 kV St John Switch | 345 kV Jewett Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6256 | 2024-05-15 | 2024-05-15 | 345 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3384, 3390, 3711, 153733 | Y |  |  |  | 76432 | 76431
76684 | Add Centralia 138 kV Capacitors | Add Centralia 138 kV Capacitors |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8700 | 2024-05-15 | 2024-06-05 | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 1209 | Y |  |  |  | 76685 | 76684
73434 | Shaw 138 kV POD | Add Shaw 138 kV POD |  | Midkiff | Shaw POD | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8697 | 2024-05-15 | 2024-06-30 | 138 | 0 | 0 | 0 | 0,55.2 | Reagan | Glasscock | Tier 4 |  |  |  |  | 11222, 18664 | Y |  |  |  | 73435 | 73434
61463 | Marshall Ford - McNeil Transmission Line Storm Hardening | LCRA TSC will perform a Storm Hardening on the 14.2-mile Marshall Ford ¿ McNeil (T197) 138-kV transmission line. This project will increase both the reliability and safety of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards and will be in compliance with PUCT storm hardening requirements for this circuit. |  | Marshall Ford | McNeil | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 | 2024-05-15 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 | 22RPG018 | 2022-06-15 | 2022-07-08 |  | 7334, 7356, 7542 | Y | N | 22RPG018 reclassified as Teir 4 neutral by REPG review on 1/08/2022 |  | 61464 | 61463
73417 | LCRATSC_Schumansville_SheriffsPosse_StormHardening | Perform storm hardening on the 5.6 mile Schumansville - Sheriff's Posse (T307) transmission line. T307 shares ROW with de-energized T409 Comal - Sheriff's Posse between structure #5 and Sheriff's Posse. Design of T307 should allow for the future addition of circuit T409 on double-circuit structures between Sheriff's Posse and structure #5. |  | Schumansville | Sheriff's Posse | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2024-05-15 | 2024-05-15 | 138 | 0 | 6 | 0 |  | Guadalupe | Comal | Tier 4 |  |  |  |  | 7460, 7609 | Y | N |  |  | 73418 | 73417
73443 | Utilize Melton POI via Navarro 345 kV Switch for Project Lefty | Utilize Melton POI via Navarro 345 kV Switch for Project Lefty |  | Navarro | Navarro | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6338 | 2024-05-15 | 2024-04-15 | 345 | 0.2 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3373, 68091 | Y |  |  |  | 73444 | 73443
68797 | Morgan Creek - Barber Lake East 138 kV Line | Upgrade the existing 138 kV Line |  | Morgan Creek | Barber Lake | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8624 | 2024-05-15 | 2024-05-22 | 138 | 0 | 4.83 | 0 |  | Mitchell | Mitchell | Tier 4 |  |  |  |  | 1032, 11393 | Y |  |  |  | 81361 | 68797
45084A | Braunig to Highland Rebuild | Rebuild approximately six circuit miles of 138kV transmission from Braunig to Highland Hills/Brooks. This rebuild is between 'Highland Hills to Schillers Tap'. |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0194, T-0238 | 2024-05-15 | 2024-05-03 | 138 | 0 | 6 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5030, 5095, 5205 | Y |  |  |  | 45085 | 45084
71940 | LCRATSC_Saxet_Substation_Addition | LCRA TSC will provide two transmission points of interconnection by installing taps on the LCRA TSC owned 138-kV transmission lines T522 Weil – Lon Hill and T437 Lon Hill – Nueces Bay to serve AEP customer load. |  | Saxet |  | Planned |  | LCRATSC/AEP TCC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 | 2024-05-15 | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8441, 8452, 8482, 78568, 78569 | Y | Y |  |  | 72407 | 71940
71948 | LCRATSC_Copperas_Copperas_TL_Overhaul | LCRA TSC will perform an overhaul on the 2.4-mile portion of Copperas Cove Oncor – Copperas Cove PEC (T393) 138-kV transmission line between Copperas Cove PEC Substation and Oncor Tie existing structure #35/8. |  | Copperas (ONCOR) | Copperas (PEC) | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-05-15 | 2024-05-15 | 138 | 0 | 3 | 0 |  | Coryell | Coryell | Tier 4 |  |  |  |  | 3630, 7061 | Y | N |  |  | 71949 | 71948
71898 | Install two additional 9.2 Mvar stages at Carroll Springs 69 kV Cap Bank | Install two additional 9.2 Mvar stages at Carroll Springs 69 kV Cap Bank |  | Carroll Springs | Carroll Springs | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6241 | 2024-05-15 | 2024-06-15 | 69 | 0 | 0 | 0 | 0,18.4 | Anderson | Anderson | Tier 4 |  |  |  |  | 3270 | Y |  |  |  | 71899 | 71898
70900A | Roanoke Area Upgrades | Establish Kingsridge 138 kV Switch |  | Kingsridge | Kingsridge | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5281 M5144 M5146 M5148 | 2024-05-15 | 2024-05-15 | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 21RPG008 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 566, 1856, 2027, 2033, 2034, 2036, 2037, 2038, 12033, 12034, 12036, 12043, 12044, 12045, 12046 | Y | N |  |  | 72013 | 70900
72572 | Highway 32 capacitor bank addition | Install 31.3 Mvar capacitor bank at Highway 32. Replaces Project ID 70363. |  | Highway 32 |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 | 0,31.2 | Hays |  | Tier 4 |  |  |  |  | 70546 | Y | Y |  |  | 72573 | 72572
72863 | Delaware River 138 kV Switch | Establish Delaware River 138 kV Switch for merchant plant |  | Horseshoe Springs | Riverton | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8621 | 2024-05-15 | 2024-05-07 | 138 | 0 | 0 | 0 |  | Culberson | Reeves | Tier 4 |  |  |  |  | 11112, 11190, 11272 | Y |  |  |  | 72865 | 72863
76680 | Add Capacitor Bank at East Stiles | Add Capacitor Bank at East Stiles |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8693 | 2024-05-15 | 2024-07-08 | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 23869 | Y |  |  |  | 76681 | 76680
78683A | POI for Connolly Storage (Denton Creek Switch) | Establish Connolly Storage POI |  | Bennett Road Switch | Krum Tap Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3500 | 2024-05-15 | 2024-05-15 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 1510, 1566, 1568 | Y |  |  |  | 79645 | 78683
5940B | Mountain Home Substation and Transmission Line Addition | Cut-in the existing Gillespie to Fredericksburg 138-kV transmission line (T379) at Peach substation (converted to 138-kV, located adjacent to Live Oak substation), re-terminate and convert the existing 69-kV Harper to Live Oak transmission line to form 138-kV Headwaters to Peach transmission line, and connect the existing 69-kV Gillespie to Live Oak (T131) and existing Live Oak to Goehman Tap (T287) transmission lines to create a continuous 69-kV circuit from Gillespie to Goehman Tap. |  | Headwater | Goehman Tap. | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1017394 | 2024-05-15 | 2024-05-15 | 138 | 0 | 22.5 | 0 |  | Kerr | Gillespie | Tier 1 | 16RPG015 | 2016-11-18 |  |  | 7130, 7410, 7412, 7413 | Y | N |  |  | 78336 | 5940
57726 | Commerce - Royse 69 kV Line Conversion to 138 kV | Convert existing 69 kV Line to 138 kV |  | Commerce Switch | Royse | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R985 | 2024-05-15 01:00 | 2024-05-23 | 138 | 0 | 38.3 | 0 |  | Hunt | Rockwall | Tier 3 | 20RPG023 | 2020-12-23 | 2021-01-19 |  |  | Y | N |  |  | 81830 | 57726 | 2020-NC5
59525 | Cedar Crest Switch - Wall Street 69 kV Line Section Conversion To 138 kV | Convert existing 69 kV Line to 138 kV operation |  | Cedar Crest | Wall Street | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4071 | 2024-05-16 | 2023-12-15 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 | [5 empty] | Y |  |  |  | 68717 | 59525
70204 | LCRATSC_McCarty_Rattler_TL_Upgrade | LCRA plans to upgrade T725 McCarty Lane - Rattler 138-kV transmission line to obtain a higher operational rating. |  | McCarty Lane | Rattler | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-05-17 | 2024-02-26 | 138 | 0 | 1.27 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7182, 7184 | Y | N |  |  | 78307 | 70204
70351 | LCRATSC_Rattler_Redwood_TL_Upgrade | Upgrade T262 Rattler - Redwood 138-kV transmission line to obtain a higher operational rating. |  | Rattler | Redwood | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-05-17 | 2024-05-15 | 138 | 0 | 1.07 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7184, 7188 | Y | N |  |  | 70352 | 70351
64505B | Flewellen to Peters Ckt.25E Upgrades | Upgrade Ckt.25E Foster to Twinwood Mobile to Peters to increase thermal limits |  | Foster | Peters | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-30 00:02 | 2023-06-23 | 138 | 0 | 27.4 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 21RPG011 | 2021-06-04 | 2021-07-02 |  | 44256, 44860, 46220 | Y | N |  | Cost included in main entry | 64507 | 64505
77148 | Coryell Rebuild |  |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-05-31 | 2024-05-15 | 69 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 4 |  |  |  |  | 37520, 37530, 37570, 37580 | Y |  |  |  | 77149 | 77148
76212 | Model Coachwhip Sub |  |  | From Mivida PSSE bus# 38152 | To Fishhook PSSE Bus# 38180 | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-05-31 | 2024-07-19 | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38152, 38170, 38180 | Y |  |  |  | 76213 | 76212
75835B | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. |  | Hockley |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 | 2024-05-09 | 138 | 0 | 0 | 0 | 0,40 | Harris | Harris | Tier 3 |  |  |  |  | 45880 | Y | N |  |  | 75837 | 75835
75936 | Galena Park Distribution Transformer Addition | Expand Galena Park substation with addition of 3rd distribution transformer. Transformer expected at Ckt.94M Normandy tap to Galena Park tap to TANKER. |  | Galena Park |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 | 2024-04-08 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 75937 | 75936
69896 | Singleton Expansion for Limousin Oak Storage (22INR0338) | Expand Singleton 345kV substation and install one generator lead for new interconnection to Limousin Oak Storage |  | Singleton |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 | 2024-05-03 | 345 | 0 | 0 | 0 |  | Grimes |  | Tier 4 |  |  |  |  | 40090, 40942, 44645, 48214, 120742 | Y | N |  |  | 69897 | 69896
48415B | TransPecos Capbank in TNMP West Texas System | Expands TransPecos Capacitor bank by 1 block of 20 Mvar. |  | TransPecos (Bus #38377) | TransPecos (Bus #38377) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | NTE07919 | 2024-05-31 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38377 | Y |  |  |  | 48417 | 48415
43212B | Caymus Capbanks in TNMP West Texas System | Expands Caymus Capacitor bank by 1 block of 20 Mvar. |  | Caymus (Bus #38410) | Caymus (Bus #38410) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | NTE07819 | 2024-05-31 |  | 138 | 0 | 0 | 0 | 0,20 | Reeves | Reeves | Tier 4 |  |  |  |  | 38410 | Y |  |  |  | 48414 | 43212
67422B | Greens Bayou to Clinton 138kV Conversion | Reduce existing Greens Bayou cap bank CB1 from 120 MVAR to 100 MVAR |  | Greens Bayou | 0 | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 | 2024-03-01 | 138 | 0 | 0 | 0 | -20,0 | Harris | Harris | Tier 4 |  |  |  |  | 40717 | Y | N |  |  | 87575 | 67422
69900A | Eastgate (EAS) 138kV CNP Substation for XE Murat Solar (22INR0354) | New 138kV Eastgate (EAS) substation for generator interconnection to XE Murat Solar. Loop Ckt.66E into substation to create new Ckt.66 Crosby to Eastgate to Atascocita. |  | Eastgate | Atascocita/Crosby | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 | 2023-05-13 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40130, 40390, 40690 | Y | N |  | Loop Ckt.66E into new substation to create new Ckt.66 Crosby to Eastgate to Atascocita. | 86051 | 69900
69900B | Eastgate (EAS) 138kV CNP Substation for XE Murat Solar (22INR0354) | Install generator lead from Eastgate (EAS) substation to ADLONG/XE Murat Solar |  | Eastgate | ADLONG | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 | 2023-05-13 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 86050 | 69900
66046 | Ckt09 Zenith-VillageCreek Reconfigurations | Expand Zenith 138kV substation and install radial section Ckt.45 Zenith to Village Creek. Reconfigure Ckt.09K at Village Creek to create Ckt.09K Zenith to Village Creek tap to Franz. |  | Zenith | Village Creek | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 | 2023-02-28 | 138 | 3.6 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44260, 44270, 44271, 44272, 44910, 48272 | Y | N |  |  | 80706 | 66046
75932 | Village Creek Distribution Transformer Addition | Expand Village Creek substation with addition of 3rd distribution transformer. Transformer expected at Ckt.09K Zenith to Village Creek to Franz. |  | Village Creek | Zenith/ Franz | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 | 2024-05-10 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44272 | Y | N |  |  | 80705 | 75932
82210 | PMCR for LEAGUE CITY STATION REBUILD | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38920 | Y |  |  |  | 82211 | 82210
66009B | SNUG (SNU) 138kV CEHE Station for Cottonwood Bayou Solar (21INR0228 | Install one generator lead for new interconnection to COTTON/Cottonwood Bayou Solar |  | SNUG | COTTON | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 | 2024-03-21 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 44890, 113435 | Y | N |  |  | 75723 | 66009
63834A | Alvin Area 138kV Conversions | Reconfigure existing Ckt.26H Archer to Karsten to create new Ckt.26H Archer to Manvel. |  | Karsten | Manvel | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 | 2023-04-26 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42570, 44390, 44410, 44430, 44440 | Y | N |  |  | 79862 | 63834
67422C | Greens Bayou to Clinton 138kV Conversion | Convert Wallisville substation from double-tap service to loop service on Ckt.10A. Remove TEXWAL substation from Ckt.10 service. Resulting in Ckt.10A Clinton to CASTEN tap to Wallisville loop to Greens Bayou |  | Clinton | Greens Bayou | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:01 | 2024-02-07 | 69 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 40720, 41570, 41680, 41681, 41682, 48299, 48372, 48412, 48413 | Y | N |  |  | 87576 | 67422
67422D | Greens Bayou to Clinton 138kV Conversion | Rebuild TEXWAL substation as 138kV breakered station. Rebuild Wallisville substation as 138kV loop-tap station. Expand Greens Bayou 138kV 'West' bus and Clinton 138kV station with new line positions. Reconfigure and connect new 138kV stations to create new 138kV Ckt.xx Greens Bayou to TEXWAL to Wallisville to Clinton. |  | Greens Bayou | Clinton | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:02 | 2024-02-07 | 138 | 2.17 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40350, 40715, 41575 | Y | N |  | Cost included in Phase C | 87577 | 67422
63834B | Alvin Area 138kV Conversions | Reconfigure existing Ckt.26B Rosharon to Karsten to create new Ckt.26B Manvel to Alvin tap to Karsten. |  | Manvel | Rosharon | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:02 | 2023-04-26 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42073, 44390, 44410, 44430, 48173 | Y | N |  | Cost in main project | 79863 | 63834
73371D | BP24 Sub Upgrades | Wharton Loop Upgrade Ckt.60B (BP24 Sub Upgrades) |  | Wharton | Caney | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:03 | 2023-08-23 | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 43570, 44131, 44132 | Y | N |  |  | 73375 | 73371
63834C | Alvin Area 138kV Conversions | Reconfigure existing Ckt.05B LIMBERG to Friendswood tap to Webster to create new Ckt.05B LIMBERG to Alvin tap to Friendswood tap. Rebuild Alvin substation for double-tap service. |  | LIMBERG | Webster | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:03 | 2023-04-26 | 138 | 0 | 0 | 0 |  | Brazoria | Harris | Tier 4 |  |  |  |  | 42072, 42651, 43280, 48111, 48172 | Y | N |  | Cost in main project | 79864 | 63834
63834D | Alvin Area 138kV Conversions | Rebuild portions of Ckt.53 Webster to Karsten to HO Clarke for 138kV Line Conversion. Retire the remaining portions of Ckt.53. Retire KR-A1 and WEB-A1 |  | Karsten | Webster/HO Clarke | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:04 | 2023-04-26 | 69 | 0 | 0 | -300 |  | Brazoria | Harris | Tier 4 |  |  |  |  | 44390, 44400, 44440, 47160, 49022 | Y | N |  | Cost in main project | 79861 | 63834
73371E | BP24 Sub Upgrades | Upgrade Whaley to WA Parish Ckt.72F to increase thermal limits |  | Whaley | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:04 | 2026-05-31 | 345 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44005, 44070 | Y | N |  |  | 73376 | 73371
73371I | BP24 Sub Upgrades | Upgrade Jefferson to South Channel Ckt.06E to increase thermal limits |  | Jefferson | South Channel | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 00:08 | 2024-02-06 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41240, 41370 | Y | N |  |  | 73380 | 73371
66009A | SNUG (SNU) 138kV CEHE Station for Cottonwood Bayou Solar (21INR0228 | Loop new CEHE 138kV substation SNUG (SNU) into Ckt.04 Liverpool to PETSON to create new Ckt.04 Liverpool to SNUG to PETSON. |  | SNUG | Liverpool/PETSON | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 12:00 | 2024-03-21 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42870, 43070, 44890 | Y | N |  |  | 66010 | 66009
65719 | Rebuild and reconductor portion of Missouri City to Sienna Ckt.05A as a Hardening upgrade | Rebuild and reconductor portion of Missouri City to Sienna Ckt.05A as a Hardening upgrade |  | Missouri City | Sienna | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-05-31 12:00 |  | 138 | 0 | 3.7 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44482, 44652 | Y | N |  |  | 65720 | 65719
66113 | Add WalnutSpr Auto & 138kV Switchyard |  |  | Oncor Walnut Springs (Bus # 1646, 1647) | TNMP Walnut Springs (Bus # 37680, 37681) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-06-01 |  | 138 | 0 | 0 | 208.8 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 1646, 1647, 37680, 37681 | Y |  |  |  | 66115 | 66113
5621 | South McAllen-Bentsen and North Edinburg-West Edinburg 138 kV Station Upgrades | 138 kV Upgrades at North Edinburg and South McAllen | IN-SERVICE | North Edinburg | North McAllen | In-Service | 795 - 0980 | AEP TCC | Todd Siegert bcogan@aep.com 918-599-2857 | 3585 | 2024-06-12 | 2023-01-25 | 138 | 0 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8367, 8371, 8631, 79603 | Y | N |  |  | 13351 | 5621 | 2017-S9
5206 | Brackettville to Escondido: Construct 138 kV line | Build a single circuit capable 138 kV circuit from Brackettville to Escondido station |  | Brackettville | Escondido | In-Service | 762-0947 | AEP TCC | James Weaver bcogan@aep.com 918-599-2857 | 3570 TP2017041 | 2024-06-12 | 2023-12-21 | 138 | 45 | 0 | 0 |  | Kinney | Maverick | Tier 2 | 16RPG001 | 2016-01-05 | 2017-01-20 | 2017-02-08 | 8252, 8260 | Y | N |  |  | 12865 | 5206 | 2015-S6
77046 | AEP_TCC_OdemSandPit | Add Odem Sand station |  | Edroy | Smith | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | DP22X0029 | 2024-06-12 | 2024-12-31 | 69 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8408, 8734, 8866 | Y |  |  |  | 77047 | 77046
44854 | Lipton: Build 138 kV Box Bay | New Lipton 138 kV Station, replaces Lipton Hard Tap |  | Lipton |  | In-Service |  | AEP TCC | Jeremy Brazeal mlforcum@aep.com 918-599-2674 | TP2018214 | 2024-06-12 | 2024-05-14 | 138 | 0 | 0 | 0 |  | Zavala |  | Tier 4 |  |  |  |  | 8236, 8283, 8285, 88285 | Y | N |  |  | 44855 | 44854
87029 | Chocolate Bayou to Portside Energy Center: Construct New 138 kV Line | Interconnect Portside Energy Center Solar & Storage to the Chocolate Bayou 138 kV station | NEW | Chocolate Bayou | Portside Energy Center | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | TP2024062 | 2024-06-12 |  | 138 | 1.5 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 80064 | Y |  |  |  | 87030 | 87029
69221 | Rebuild 69 kV Line from Blessings to Palacios | Rebuild 69 kV Line from Blessings to Palacios |  | Blessing | Palacios | In-Service |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2024-06-12 | 2023-11-16 | 69 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5571, 8119, 8131, 8148 | Y |  |  |  | 87836 | 69221
4495 | Champlin: Station Reconfigure | Expand existing breaker configuration to a four (4) breaker ring bus expandable to a six (6) breaker ring bus configuration. | Schedule Update | Champlin |  | In-Service | 694 - 0864 | AEP TCC | John Pulay mlforcum@aep.com 918-599-2674 | 3541 TP2014064 | 2024-06-12 | 2023-03-19 | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8476, 8479, 8528, 8711 | Y | N |  |  | 78259 | 4495
80462 | Lon Hill to Weil Tract 138 kV(LCRA): Construct Temp Tap | Construct Temp Tap on the Lon Hill to Weil Tract 138 kV line |  | Nueces | Nueces | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-06-12 | 2024-07-17 | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 78569 | Y |  |  |  | 80463 | 80462
76920 | Kingsville to Bunsen: Construct Primavera Tap | Add Tesla Load |  | Bunsen | Kingsville | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023059 | 2024-06-12 | 2024-01-31 | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8518, 8749, 8921, 88747 | Y |  |  |  | 76921 | 76920
50954 | Whitepoint: Add Second Auto | Whitepoint: Add Second Auto | Schedule Update | Whitepoint |  | In-Service | 1085 - 1258 | AEP TCC | Dave Goetz mlforcum@aep.com 918-599-2674 | 3805 | 2024-06-12 | 2024-05-15 | 345 | 0 | 0 | 500 |  | San Patricio |  | Tier 4 |  |  |  |  | 8956, 8961 | Y | N |  |  | 50955 | 50954
54811 | Winecup: Build 69 kV station | Construct new 69 kV box bay on the North San Angelo to San Angelo Grape Creek Tap 69 kV line | IN-SERVICE | Winecup |  | Planned | 1041 - 1268 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | 1858 | 2024-06-12 | 2024-07-01 | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6459, 6465, 60796 | Y | N |  |  | 54812 | 54811
57908 | North Edinburg:138 kV Station Work | Install two 138 kV series reactors | Status Update | North Edinburg |  | In-Service | 1112 - 1290 | AEP TCC | Curtis Brown mlforcum@aep.com 918-599-2674 | 3831 | 2024-06-12 | 2023-12-20 | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8341, 8380, 8383, 88381, 88382 | Y | N |  |  | 57909 | 57908
61398 | Whitepoint 138 kV Station: Upgrade Pelican Terminal | Whitepoint 138 kV Station: Upgrade Pelican Terminal | Schedule Update | Whitepoint |  | Planned |  | AEP TCC | Brandon Cogan mlforcum@aep.com 918-599-2674 | TP2020040 | 2024-06-12 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 | 19RPG0016 |  |  |  | 8961, 80259 | Y |  |  |  | 61399 | 61398
50882 | Lon Hill to Structure 25/4: Rebuild 138 kV Line | Rehab Lon Hill to Structure 25/4 138 kV Line | Schedule Update | Lon Hill | Haisley | In-Service | 1055 - 1228 | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | 3785 | 2024-06-12 | 2023-12-23 | 138 | 0 | 10.2 | 0 |  | San Patricio | San Patricio | Tier 3 | 19RPG014 | 2019-08-13 | 2019-10-07 |  | 8027, 8452, 8920, 8924 | Y | N |  |  | 65548 | 50882
63902 | Bakersfield: Build New 345 kV Terminal | Interconnect Hydra BESS to the Bakersfield 345 kV Station | IN-SERVICE | Bakersfield |  | In-Service | 1136 - 1314 | ETT | Rasa Ansari twang1@aep.com 918-599-2635 | 1881 | 2024-06-12 | 2024-05-01 | 345 | 0 | 0 | 0 |  | Pecos |  | Tier 4 |  |  |  |  | 76002, 135602 | Y | N |  |  | 63903 | 63902
50160 | Beeville to Goliad: Rebuild 69 kV Line | Rehab 69 kV Line from Beeville to Goliad | Schedule Update | Beeville | Goliad | In-Service | 961 - 1139 | AEP TCC | Eric Scott bcogan@aep.com 918-599-2857 | 3719 TA2018010 | 2024-06-12 | 2022-10-31 | 69 | 0 | 22.21 | 0 |  | Bee | Goliad | Tier 3 | 19RPG008 | 2019-04-30 | 2019-05-30 |  | 8584, 8586, 8587 | Y | N |  |  | 65542 | 50160
59088 | Alice - Falfurrias: Line Rebuild | Alice - Falfurrias: Line Rebuild |  | Alice | Falfurrias | In-Service |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2020088 | 2024-06-12 | 2023-05-16 | 69 | 0 | 3.67 | 0 |  | Jim Wells | Brooks | Tier 2 |  |  |  |  | 8500, 8508, 8878, 8894 | Y |  |  |  | 65586 | 59088
66128 | Clarkwood: Build new 138 kV terminal | Interconnect BRP Carina BESS to the Clarkwood 138 kV station | Schedule Update | BRP Carina | Clarkwood | In-Service |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021308 | 2024-06-12 | 2023-10-25 | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8479, 88479 | Y |  |  |  | 66129 | 66128
66192 | Abilene NW: Build 138 kV terminal | Interconnect Lancium to the Abilene NW 138 kV station | Schedule Update | Abilene Northwest | Lancium | In-Service |  | AEP TNC | Brian Oyster twang1@aep.com 918-599-2635 |  | 2024-06-12 | 2023-06-30 | 138 | 0.2 | 0 | 0 |  | Taylor | Taylor | Tier 4 |  |  |  |  | 6228, 6476 | Y | N |  |  | 66193 | 66192
50872 | Structure 25/7 - Medio Creek: Rebuild 138 kV Line | Rehab Structure 25/7 to Medio Creek 138 kV Line |  | Haisley | Medio Creek | In-Service |  | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 | TA2018060 | 2024-06-12 | 2023-12-23 | 138 | 0 | 14.9 | 0 |  | San Patricio | Refugio | Tier 3 | 19RPG014 | 2019-08-13 | 2019-10-07 |  | 8912, 8920 | Y | N |  |  | 65546 | 50872
57912 | Champlin to Weil Tract: Rebuild 138 kV Line | Rebuild Champlin to Weil Tract 138 kV Line | Schedule Update | Champlin | Weil Tract | In-Service | 1111 - 1289 | ETT | Thomas Naves mlforcum@aep.com 918-599-2674 | 3830 | 2024-06-12 | 2024-04-08 | 138 | 0 | 1.37 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8476, 8482 | Y | N |  |  | 65581 | 57912
65987 | Gibbs: Build new 138 kV terminal | Interconnect Jackalope Solar to the Gibbs 138 kV station | In-Service Date Update | Gibbs |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2021288 | 2024-06-12 | 2024-08-30 | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8173, 88173 | Y |  |  |  | 65988 | 65987
63964 | Bronco: Build new 69 kV Terminal | Interconnect House Mountain BESS to the Bronco 69 kV Station | IN-SERVICE | Bronco |  | In-Service | 1140 - 1318 | AEP TNC | Robert Younger twang1@aep.com 918-599-2635 | 1885 | 2024-06-12 | 2023-09-13 | 69 | 0 | 0 | 0 |  | Brewster |  | Tier 4 | [5 empty] | Y | N |  |  | 63965 | 63964
64089 | Peregrine Solar Interconnection | Connect the Peregrine Solar to the Coleto Creek to Grissom 345 kV line | Schedule Update | Coleto Creek | Grissom | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2024-06-12 |  | 345 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8164, 8624, 8673, 88673 | Y |  |  |  | 64090 | 64089
67913 | Pomelo: Build new 345 kV terminal | Interconnect Anemoi Storage to the Pomelo 345 kV station | Schedule Update | Hidalgo | Hidalgo | In-Service |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2024-06-12 | 2023-12-20 | 345 | 0.05 | 0 | 0 |  | Hidalgo | Hidalgo | Tier 4 | [5 empty] | Y |  |  |  | 67914 | 67913
66292 | Salvare: Build 345 kV station | Interconnect Iris Energy on the Jim Treece to Tesla 345 kV line | IN-SERVICE | Salvare |  | In-Service |  | ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2024-06-12 | 2023-04-06 | 345 | 0.01 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60504, 60510, 60511, 61001 | Y | N |  |  | 66293 | 66292
66386 | Albany to Throckmorton: Rebuild 69 kV line | Rehab 69 kV line from Albany to Throckmorton | IN-SERVICE | Albany | Throckmorton | In-Service |  | AEP TNC | Raza Ansari twang1@aep.com 918-599-2635 |  | 2024-06-12 | 2024-05-15 | 69 | 0 | 32.36 | 0 |  | Shackelford | Throckmorton | Tier 4 | 21RPG015 | 2022-08-21 | 2022-09-21 |  | 6205, 6206, 6207 | Y | N |  |  | 66387 | 66386
65725 | James Rowe: Construct New Distribution Station | Construct New Distribution Station on the North McAllen to West McAllen 138 kV Line | Schedule Update | James Rowe |  | Planned | 1030 - 1208 | AEP TCC | Alison Scribailo mlforcum@aep.com 918-599-2674 | 3769 | 2024-06-12 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8041, 8367, 8631 | Y | N |  |  | 65726 | 65725
50874 | Smith - Mathis: Line Rebuild | Smith - Mathis: Line Rebuild |  | Smith | Mathis | In-Service | 1053 - 1226 | AEP TCC | Joseph Page bcogan@aep.com 918-599-2857 | 3781 | 2024-06-12 | 2024-02-28 | 69 | 0 | 22.47 | 0 |  | San Patricio | San Patricio | Tier 3 | 20RPG001 | 2020-02-15 | 2020-03-24 |  | 8407, 8408, 8424, 8866 | Y | N |  |  | 65547 | 50874
68229 | Penumbra: Build new 345 kV Station | Interconnect Montgomery Ranch Wind to the Avogadro to Edith Clarke 345 kV line | Contact, Cost Update | Penumbra |  | Planned |  | AEP TNC | Zach Lachiusa twang1@aep.com 918-599-2635 |  | 2024-06-12 | 2023-11-15 | 345 | 0 | 0 | 0 |  | Foard |  | Tier 4 |  |  |  |  | 60059, 60500, 60506, 60722 | Y | N |  |  | 68230 | 68229
69226 | Rebuild 69 kV Line from Point Comfort to Carancahua | Rebuild 69 kV Line from Point Comfort to Carancahua |  | Point Comfort | Carancahua | In-Service |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2024-06-12 | 2024-05-14 | 69 | 0 | 0 | 0 |  | Calhoun | Jackson | Tier 4 |  |  |  |  | 8131, 8132, 8555 | Y |  |  |  | 69227 | 69226
69224 | Brookhollow to Port Lavaca: Rebuild 138 kV Line | Rebuild 138 kV Line from Brookhollow to Port Lavaca |  | Brookhollow | Port Lavaca | Planned |  | AEP TCC | Lorraine Timmerman mlforcum@aep.com 918-599-2674 |  | 2024-06-12 |  | 138 | 0 | 2.7 | 0 |  | Calhoun | Calhoun | Tier 1 | 21RPG002 | 2021-02-01 | 2021-10-27 |  | 8133, 8135, 8140, 8155, 8741 | Y |  |  |  | 71834 | 69224
69481 | Resaca: Install Cap Bank | Resaca Capacitor | Schedule Update | Resaca |  | In-Service |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2024-06-12 | 2023-12-15 | 69 | 0 | 0 | 0 | 0,11.5 | Cameron |  | Tier 4 |  |  |  |  | 8626 | Y |  |  |  | 69482 | 69481
68970 | Lobo: Build (2) 345 kV terminals | Construct new terminals at Cenizo, Del Sol, Lobo, and Pomelo for the ETT 2nd circuits project | Transmission Status, In-Service Date, Planning Tier, RPG Number, and RPG Dates Update | Lobo |  | In-Service |  | ETT | James Weaver mlforcum@aep.com 918-599-2674 | TP2021704 | 2024-06-12 | 2024-05-01 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80219 | Y | Y |  |  | 68971 | 68970
68972 | Tiempo to Fowlerton: Add Second 345 kV Circuit | Hang conductor to complete a double circuit between Tiempo and Fowlerton for the ETT 2nd circuits project | Project Title, Transmission Status, Owner, In-Service Date, RPG Number, and RPG Dates Update | Tiempo | Fowlerton | In-Service |  | ETT/STEC | Teresa Trotman mlforcum@aep.com 918-599-2674 | TP2021703 | 2024-06-12 | 2024-05-01 | 345 | 63.38 | 0 | 0 |  | Webb | Zapata | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 5709, 80219, 80220, 80221, 80224, 80230 | Y | Y |  |  | 68973 | 68972
68266 | Dry Frio: Build new 138 kV station | Interconnect Sunray Solar to the Dry Frio 138 kV station | Contact Update | Dry Frio |  | In-Service |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-06-12 | 2023-05-02 | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 4 |  |  |  |  | 8234, 8241, 8707 | Y |  |  |  | 68267 | 68266
68960 | North Edinburg: Expand 345 kV station | Construct new terminals at North Edinburg for the ETT 2nd circuits project | Transmission Status, Planning Tier, RPG Number, and RPG Dates Update | North Edinburg |  | In-Service |  | AEP TCC | James Weaver mlforcum@aep.com 918-599-2674 | TP2021705 | 2024-06-12 | 2024-05-15 | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8383, 8455, 8901, 8905 | Y |  |  |  | 71132 | 68960
71000 | TCC& TNC Cap Bank Rehab | TCC& TNC Cap Bank Rehab | IN-SERVICE |  |  | In-Service |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TA2022031 | 2024-06-12 | 2024-06-12 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6216, 6338, 6468, 6615, 8169, 8348, 8427 | Y | N |  |  | 71001 | 71000
70225 | Junction: Install capacitor bank | Install Capacitor Bank at Junction Station | IN-SERVICE | Junction |  | In-Service |  | AEP TNC | Damian Raab twang1@aep.com 918-599-2635 |  | 2024-06-12 | 2024-08-20 | 69 | 0 | 0 | 0 | 0,7.7 | Kimble |  | Tier 4 |  |  |  |  | 6400 | Y | N |  |  | 70226 | 70225
72085 |  |  | IN-SERVICE |  |  | In-Service |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2024-06-12 | 2024-06-01 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8111, 8127, 8668, 89500 | Y |  |  |  | 72086 | 72085
72309 | AEP_TCC_LonHillHaisley | Lon Hill to Structure 25/4: Rebuild 138 kV Line |  | Lon Hill | Haisley | In-Service |  | AEP TCC | Nathan Cowan bcogan@aep.com 918-599-2857 |  | 2024-06-12 | 2024-12-23 | 138 | 0 | 10.2 | 0 |  | San Patricio | San Patricio | Tier 3 |  |  |  |  | 8027, 8046, 8912, 8920 | Y |  |  |  | 72310 | 72309
76141 | Santo Nino: Install cap bank | Install cap banks at Santo Nino, Molina, and Wormser Road |  | Santo Nino |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2024-06-12 | 2024-02-12 | 138 | 0 | 0 | 0 | 0,23.1 | Webb |  | Tier 4 |  |  |  |  | 8653 | Y |  |  |  | 76142 | 76141
50870 | Coleto Creek - Rosata: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild | IN-SERVICE | Coleto Creek | Rosata | In-Service | 1052 - 1225 | AEP TCC | Curtis Brown bcogan@aep.com 918-599-2857 | 3778 | 2024-06-12 01:00 | 2024-05-14 | 138 | 0 | 15.3 | 0 |  | Goliad | Goliad | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8153, 8162 | Y | N |  |  | 50871 | 50870
68780 | Triangle - Yosemite 138 kV Line | Upgrade the existing 138 kV Line |  | Triangle | Yosemite | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8626 | 2024-06-13 | 2024-09-15 | 138 | 0 | 11.2 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 11390, 23858 | Y |  |  |  | 85995 | 68780
71968 | Midkiff - Pemkiff 138 kV Line | Rebuild the existing 138 kV line |  | Midkiff | Pemkiff | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8641 | 2024-06-13 | 2024-06-21 | 138 | 0 | 0.31 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 1210, 23871 | Y |  |  |  | 71970 | 71968
50710 | Quartz Sand 138 kV Switch | Construct a new 138 kV switch |  | Spraberry | Polecat Creek | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8670 | 2024-06-13 | 2024-06-22 | 138 | 0 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 1328 | Y |  |  |  | 73335 | 50710
66216 | Upgrade and convert Waco West - Temple 69 kV Line to 138 kV | Upgrade and convert Waco West - Temple 69 kV Line to 138 kV |  | Waco West | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6191 | 2024-06-15 |  | 138 | 0.7 | 6.7 | 0 |  | McLennan | Bell | Tier 4 | 22RPG046 | 2022-12-01 | 2023-01-01 |  | 147, 3361, 3417, 3437, 3446, 3544, 3578, 3580, 3581, 3644, 13662 | Y |  |  |  | 67582 | 66216
71901 | Install 110.4 Mvar 138 kV capacitor bank at Thorndale North | Install 110.4 Mvar 138 kV capacitor bank at Thorndale North |  | Thorndale North | Thorndale North | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6236 | 2024-06-15 | 2024-06-15 | 138 | 0 | 0 | 0 | 0,110.4 | Milam | Milam | Tier 4 | [5 empty] | Y |  |  |  | 71902 | 71901
66522 | Andrews North - Paul Davis Tap 138 kV Line Rebuild | Add Andrews North - Paul Davis Tap 138 kV Line Rebuild |  | Andrews North | Paul Davis Tap | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8596 | 2024-06-15 | 2024-06-01 | 138 | 0 | 25 | 0 |  | Andrews | Dawson | Tier 4 | 21RPG012 | 2021-08-03 | 2021-08-26 |  | 1159, 1167, 11206 | Y |  |  |  | 87117 | 66522
71873 | CPSE_Hill Country Auto# 2 Impedance Upgrade |  |  |  |  | Planned | S-0769 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2024-06-20 | 2024-08-22 | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2022-07-09 |  | 5210, 5211, 5213 | Y |  |  |  | 71874 | 71873
61350 | Antler-Highway 46 Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the T610 Antler to Highway 46 138-kV and T389 Bergheim to Hays Energy 345-kV 10.4-mile double-circuit transmission line by replacing the aging conductors from Antler to Highway 46 substations. |  | Antler | Highway 46 | Planned | 61406, 61358, 61392, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-06-21 | 2024-06-21 | 345 | 0 | 10.4 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7043, 7171, 7177, 7770 | Y | N |  |  | 78332 | 61350
60625 | AEN_22TPIT60625_DECKER_BUS_TIE_CLOSE | Close the Decker 138 kV bus tie |  | 9187 | 9188 |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-06-21 | 2023-02-08 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 | [5 empty] | Y | N |  |  | 60626 | 60625
52670 | Rising Star Area voltage conversion | This portion of the project connects Green Creek Switch |  | Stephenville | Carlton Switch | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-06-24 |  | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 286, 294, 33286 | Y |  |  |  | 52671 | 52670
18TPIT0001 | Wiederstein Substation Transformer Replacement | Replace T1, 20 MVA with a 40 MVA 138-26.18 kV transformer |  | Wiederstein |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2024-06-28 | 2024-07-10 | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7461 | Y | N |  |  | 10675 | 3319
70200 | LCRATSC_ChiefBrady_RoundRock_TL_Upgrade | LCRA TSC will upgrade T378 Chief Brady - Round Rock 138-kV transmission line to achieve a higher operational rating. |  | Chief Brady | Round Rock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-06-28 | 2024-07-01 | 138 | 0 | 5.1 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3668, 7366 | Y | N |  |  | 70201 | 70200 | 2023-SC17
61230 | Altair - Garwood Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 9.4-mile Altair ¿ Garwood (T542) (including all the tap lines) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Altair | Garwood | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2024-06-28 | 2024-06-24 | 69 | 0 | 0 | 0 |  | Colorado | Colorado | Tier 4 |  |  |  |  | 78106, 78530 | Y | N |  |  | 61231 | 61230
70190 | LCRATSC_Cuero_Substation_Upgrade | Increase the reliability of substation equipment at the Cuero Substation by converting the station bus layout from single bus single breaker to a breaker and a half configuration, replacing obsolete and/or aged equipment, upgrade facility structures as required, and installing a new control enclosure to adhere to high wind requirements. Contingency Update |  | Cuero | Cuero | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2024-06-28 | 2024-06-24 | 138 | 0 | 0 | 0 |  | DeWitt | DeWitt | Tier 4 | 23RPG015 | 2023-06-02 | 2023-06-26 |  |  | Y | Y |  |  | 70191 | 70190
76676 | Roadrunner 138 kV Capacitors | Add Capacitor at Roadrunner. |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8677 | 2024-06-30 | 2024-06-27 | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 11199 | Y |  |  |  | 76679 | 76676
61513 | New RELLIS Substation |  |  | Steele Store | Smetana | Under Construction |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2024-06-30 | 2024-10-30 | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32780, 32852, 32853 | Y |  |  |  | 80552 | 61513
70961B | Crosby Sub Exp for HOLY/Citadel BESS and Upgrades | Upgrade Ckt.66F Baytown to Baytown TR1 tap to increase thermal limits |  | Baytown | Baytown | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-06-30 | 2024-09-27 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40170, 44630 | Y | N |  |  | 70963 | 70961
51225 | Driver - Hadacol Corner 138 kV Line | Upgrade the existing 138 kV line |  | Driver Tap | Hadacol Corner | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8637 | 2024-06-30 | 2024-06-27 | 138 | 0 | 3.2 | 0 |  | Midland | Reagan | Tier 4 |  |  |  |  | 23863, 23867 | Y |  |  |  | 71134 | 51225
72061 | HO Clarke to Kirby Ckt.90A Upgrade to Limiting Section | Upgrade Ckt.90A HO Clarke to Kirby to increase thermal limits. |  | HO Clarke | Kirby | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-06-30 | 2024-10-31 | 138 | 0 | 6.78 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 48157, 48363 | Y | N |  |  | 72062 | 72061
78476 | Waterhole 345kV Substation - Gulf Star Storage - Generator Interconnection (23INR0460) | Install Gulf Star Storage at Waterhole 345kV substation… Connect at the same generator lead as Gulf Star Solar (Gulf Star Storage - 23INR0460) |  | Waterhole |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-06-30 | 2025-01-31 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44880, 112878 | Y | N |  |  | 78477 | 78476
73371F | BP24 Sub Upgrades | Upgrade Jeanetta to WA Parish Ckt.64A to increase thermal limits |  | Jeanetta | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-06-30 00:05 | 2024-10-31 | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47300 | Y | N |  |  | 73377 | 73371
73371G | BP24 Sub Upgrades | Upgrade Ckt.27A DOW to Jones Creek to increase thermal limits for Continuous ratings |  | DOW | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-06-30 00:06 | 2024-10-31 | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 42530 | Y | N |  |  | 73378 | 73371
11TPIT0008 | RAINEY_ST 138kV substation | Establish a new 138kV Rainey St. Substation with (2) 50MVA transformers and cut into existing Ckt 1015 (Pedernales to Seaholm). |  | Rainey St Substation | Rainey St Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | PLAN_117_P158 PLAN_117_P166 PLAN_117_P167 | 2024-07-01 |  | 138 | 0.1 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9118, 9132, 9261 | Y | N |  |  | 8208 | 1032
5430N | Conversion to 138kV | Construct a new 138kV Eagle substation along the 138kV Hickory - Locust line |  | Eagle |  | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2024-07-01 | 2019-07-01 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 926 | Y | N | N/A |  | 55208 | 5430 | N/A
66120 | Rebuild Freeway Park-Dickinson with bundled 795 ACSS |  |  | Freeway Park (bus # 38820) | Dickinson (bus # 38820) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-07-01 | 2024-04-01 | 138 | 0 | 6.25 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38820, 38850 | Y |  |  |  | 66121 | 66120
75520 | Rising Star Area Conversions |  |  | Green Creek | Carlton | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-07-10 | 2024-08-23 | 69 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 298, 299, 33286 | Y |  |  |  | 75521 | 75520
60094 | Convert Waco East - Elm Mott 69 kV Line to 138 kV | Convert Waco East - Elm Mott 69 kV Line to 138 kV and relocate the Waco East Substation to the double circuit line going towards Lake Creek/Waco West |  | Waco East | Elm Mott | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6147 | 2024-07-15 | 2024-05-15 | 138 | 0 | 10 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3407, 3408, 3438, 3439, 3443, 3571, 3573, 3708, 13438 | Y |  |  |  | 62645 | 60094
70742B | Pleak 35kV Distribution Substation | Convert Needville to a breakered substation. |  | Needville |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-07-31 | 2024-04-17 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42370, 42380, 42390, 43380 | Y | N |  |  | 86079 | 70742
78457 | Pledger Distibution Substation | Rebuild Pledger distribution substation from tap to loop-tap service. |  | Pledger |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-07-31 | 2024-04-26 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43110, 43120, 43121, 43340, 48281 | Y | N |  |  | 80967 | 78457
52179 | Rising Star Area Conversions | This converts Hasse to Downing to 138 KV |  | Downing | Hasse | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-08-10 | 2024-05-17 | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 277, 278, 281, 1649, 33281 | Y |  |  |  | 52180 | 52179
75522 | Rising Star Area Conversions |  |  | Stephenville | Stephenville | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-08-10 |  | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 286, 295, 299 | Y |  |  |  | 75523 | 75522
87389 | Friendswood Energy GENCO GT (24INR0456) | Friendswood Energy GENCO GT at HO Clarke substation. Utilize existing HO Clarke to Friendswood Energy generator lead. |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-08-14 | 2024-12-31 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 87390 | 87389
72596D | PEC_MarshallFord_Paleface_StormHardening | Align Impedances and ratings on line to current delays and project status. Future phases were also adjusted. |  |  |  | In-Service |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-08-15 | 2024-05-01 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70477, 77356 | Y |  |  |  | 87546 | 72596
78683B | POI for Connolly Storage (Denton Creek Switch) | Establish Denton Creek Switch tie line to Connolly storage |  | Bennett Road Switch | Krum Tap Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3500 | 2024-08-16 | 2024-05-15 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 1510, 154272 | Y |  |  |  | 79646 | 78683
73578F | Heights 138kV Loop Conversion | Install 7.2MVAR cap bank at Hyde Park TR3. |  | Hyde Park |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-08-30 00:05 | 2024-12-31 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47690 | Y | N |  |  | 87297 | 73578
76618 | Expand 345kV Refuge substation for Peyton Creek Wind II (20INR0155) | Expand 345kV Refuge substation for Peyton Creek Wind II (20INR0155) |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-08-31 | 2024-05-13 | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42400, 111383 | Y | N |  |  | 76619 | 76618
54220 | Brazos' member will build McFarland substation, Brazos will install POI Picard | Brazos' member will build McFarland substation, Brazos will install POI Picard |  | Picard | Picard | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-09-01 |  | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 485, 486, 527 | Y |  |  |  | 54221 | 54220
63497 | Bakersfield to Cedar Canyon 2nd circuit | Add the 2nd circuit to CREZ Bakersfield to Cedar Canyon 345 kV line |  | Bakersfield | Cedar Canyon | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2024-09-01 | 2024-09-12 | 345 | 21.1 | 0 | 0 |  | Pecos | Crockett | Tier 2 |  | 2021-02-04 | 2021-06-11 |  | 76002, 76015 | Y | N |  |  | 63498 | 63497
52175 | Rising Star Area Conversions | This continues the Rising Star Area Conversions with Downing to Mountary | Carlton to Downing 138 kV Conversion | Carlton | Downing | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2024-09-10 | 2024-06-06 | 138 | 0 | 0 | 0 |  | Erath | Comanche | Tier 4 |  |  |  |  | 281, 294, 297 | Y |  |  |  | 52176 | 52175
61138 | Bergstrom Sub Cap Addition | Add a 31.2 MVAR Cap Bank at the Bergstrom Substation |  | Bergstrom | Bergstrom | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2024-09-13 | 2023-12-07 | 138 | 0 | 0 | 0 | 0,31.2 | Travis | Travis | Tier 4 |  |  |  |  | 9165 | Y |  |  |  | 61139 | 61138
66200B | Upgrade Taylor - Holland 69 kV Line | Rebuild the Bartlett Tap - Bartlett 69 kV Line |  | Taylor | Holland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6173 | 2024-09-15 |  | 69 | 0 | 5.3 | 0 |  | Bell | Williamson | Tier 4 | 22RPG036 |  |  |  | 3647, 13647 | Y |  |  |  | 71895 | 66200
45693 | Rocky Road - Stiles 138 kV Line | Upgrade the existing 138 kV line |  | Rocky Road | Stiles | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8599 | 2024-09-15 | 2024-09-20 | 138 | 0 | 6.6 | 0 |  | Reagan | Reagan | Tier 4 |  |  |  |  | 23864, 23868 | Y |  |  |  | 71171 | 45693
72588B | Trading Post to Cedar Valley Storm Hardening | Terminal Equipment upgrade on this facility before project completion that increases rating on the line. |  | Trading Post | Cedar Valley | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2024-09-16 | 2024-09-01 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70505, 70506 | Y | N |  |  | 87525 | 72588
86962 | Planck: Install New WSL Metering | Interconnect Torrecillas BESS to the existing Planck 345 kV station | NEW | Planck |  | Planned |  | ETT | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2024040 | 2024-09-30 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219 | Y |  |  |  | 86963 | 86962
70742A | Pleak 35kV Distribution Substation | Install new Pleak (PLK) 138/35kV Distribution Substation. Loop from existing Ckt.89A to create new Ckt.89 Big Creek to Pleak to Fort Bend. |  | Pleak | Big Creek/Fort Bend | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-09-30 | 2024-05-14 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42370, 42380, 42390, 44280, 44680 | Y | N |  |  | 86078 | 70742
76369 | BRINE Substation Upgrades | Upgrade substation equipment at BRINE on Ckt.86H DALTON to BRINE to Mont Belvieu. |  | BRINE | DALTON/Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-09-30 | 2024-10-31 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40220, 40740 | Y | N |  |  | 76370 | 76369
59093 | Starr Solar Connection | Starr Solar Connection | In-Service Date Update | Roma Tap |  | Under Construction |  | AEP TCC | William Lovelace mlforcum@aep.com 918-599-2674 | TP2020209 | 2024-09-30 |  | 138 | 0.1 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 8795, 88795 | Y |  |  |  | 59094 | 59093
49572 | Goodlett to Quanah: Build a new portion of 69 kV line | Build new section of 69 kV line between Goodlett and Quanah | In-Service Date Update | Goodlett | Quanah | Planned | 1022 - 1200 | AEP TNC | Dewey Peters twang1@aep.com 918-599-2635 | 2784 | 2024-09-30 | 2022-10-31 | 69 | 6 | 0 | 0 |  | Hardeman |  | Tier 2 | 19RPG020 | 2019-11-01 | 2020-01-01 |  | 6051, 6052, 60446 | Y | N |  |  | 49573 | 49572
70777 | Bunsen: Install Cap Bank | Install a 15.4 MVAR capacitor bank at the Bunsen 138 kV station | In-Service Date Update | Bunsen |  | Planned |  | AEP TCC | Brooks Dow deevans@aep.com 918-599-2938 | TP2022722 | 2024-09-30 |  | 138 | 0 | 0 | 0 | 0,15.4 | Nueces |  | Tier 4 |  |  |  |  | 8459 | Y |  |  |  | 70778 | 70777
76694 | Calmont 69 kV line rebuild | Calmont 69 kV line rebuild |  | Calmont | Calmont | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5137 | 2024-10-01 |  | 69 | 0 | 2.9 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 11956, 12089 | Y |  |  |  | 76695 | 76694
75567 | Create_Magness_Bus |  |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2024-10-01 | 2024-09-19 | 138 | 0 | 0 | 0 |  | Hunt | Hunt | Tier 4 |  |  |  |  | 6817, 6879, 6883 | Y |  |  |  | 75568 | 75567

## CancelledTPIT100124NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2024
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
4146 | Hillje 345kV Substation Expansion for Juanita Hill Solar - (21INR0480) | Expand Hillje 345kV substation and install one generator lead for new interconnection to Juanita Hill Solar |  | Hillje |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-02-28 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | N | N |  |  | 11666 | 4146
55622 | Dilley to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley | Cancelled, incorrectly submitted prior to RPG submission. | Dilley | Pearsal | Planned | 1104 - 1282 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3822 | 2023-05-01 |  | 69 | 0 | 17.7 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8208, 8216 | N |  |  |  | 66650 | 55622
4804 | Wichita Falls South 345/138 kV autotransformer | Install autotransformer |  | Wichita Falls South |  | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R4010 | 2023-05-15 |  | 345 | 0 | 0 | 600 |  | Archer |  | Tier 3 |  |  |  |  | 1422, 1425, 1464, 11464, 11465 | N | N |  |  | 12410 | 4804
72731 | Hummingbird Storage (at Krum West Sw) | Point of interconnection to connect Hummingbird storage to existing Krum West Switch 345kV station |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3015 | 2023-05-15 |  | 345 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 1730, 153341 | N |  |  |  | 72732 | 72731
51243 | Keller Wall Price 138 kV Switch | Upgrade Roanoke - Keller Wall Price Switch 138 kV Double-Circuit Line |  | Keller Wall Price |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5251 | 2023-05-15 |  | 138 | 0 | 0 | 0 |  | Denton | Tarrant | Tier 4 |  |  |  |  | 566, 1852, 1854, 1856, 1857, 2027, 2033, 2034, 2036, 2037, 2038, 2058, 11857, 12038, 12307, 15100, 15101 | N |  |  |  | 52845 | 51243
6282 | Everman - Benbrook 345 kv line | Upgrade the existing 345 kV Line |  | Everman | Benbrook | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5273 | 2023-05-15 |  | 345 |  | 29 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1870, 1886, 1935 | N |  |  |  | 14014 | 6282
6291 | Royse Sw. Sta. - Farmersville Sw. Sta. 345 kV DCKT Line | Rebuild existing 345 kV Line |  | Royse | Farmersville | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4255 | 2023-05-15 |  | 345 | 0 | 30.4 | 0 |  | Rockwall | Collin | Tier 3 |  |  |  |  | 1685, 2461, 2478 | N |  |  |  | 14020 | 6291
70657 | Add dedicated transformer at Galena for Lehigh | Add dedicated transformer at Galena for Lehigh |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2023-05-31 00:10 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | N | N |  |  | 70658 | 70657
5647 | Del Rio to Buena Vista, rebuild 138 kV line | Rebuild Del Rio to Buena Vista 138 kV line |  | Del Rio | Buena Vista | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-06-13 |  | 138 | 0 | 2.4 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8690 | N | N |  |  | 13381 | 5647
45513 | Santo Nino - Wormser: 138 kV Line Rebuild | Rebuild Santo Nino - Wormser 138 kV line with 795 ACSS | CANCELLED | Santo Nino | Wormser | Conceptual | 991 - 1169 | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | 3745 | 2023-07-01 |  | 138 | 0 | 0 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8295, 8649, 8653 | N | N |  |  | 45514 | 45513 | 2018-S2
5646 | Buena Vista to Picacho, rebuild 138 kV line | Rebuild Buena Vista to Picacho 138 kV line |  | Buena Vista | Picacho | Conceptual |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2023-08-01 |  | 138 | 0 | 3 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8186 | N | N |  |  | 13380 | 5646
73168 | Dupont Switch: Rebuild 138 kV Station | Rebuild Dupont Switch 138 kV Station | Cancel, pending RPG approval. | Dupont SS |  |  |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2021712 | 2023-08-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8422 | N | N |  |  | 73169 | 73168
66632 | Coyote - Bulldog 138 kV Line Rebuild | Add Coyote - Bulldog 138 kV Line Rebuild |  | Coyote | Bulldog | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8553 | 2023-12-15 |  | 138 | 0 | 11.9 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 23832, 23833 | N |  |  |  | 66634 | 66632
6755 | Stratton: Add Cap Bank | Add 14.4Mvar Cap Bank at Stratton 138kV Substation | CANCELLED | Stratton |  | Planned | 903 - 1081 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3687 | 2023-12-31 |  | 138 | 0 | 0 | 0 | 0,14.4 | Nueces |  | Tier 4 |  |  |  |  | 8514 | N | N |  |  | 14548 | 6755
69487 | Wahpekute: Build new 69 kV tap | Build new 69 kV tap along the Jayton to Rotan 69 kV line | CANCELLED | Wahpekute |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2024-01-31 |  | 69 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 6162, 6196, 60057 | N |  |  |  | 69488 | 69487
63633 | Tribute: Build 138 kV Temorary Tap | Build new 138 kV temporary tap on the San Angelo Power to Red Creek 138 kV line | CANCELLED | Tribute |  | Planned | 1131 - 1309 | AEP TNC | Larry Brown twang1@aep.com 918-599-2635 | 1876 | 2024-03-01 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6442, 6473, 60008 | N | N |  |  | 63634 | 63633
62652 | Removing 69kV BES elements from BPUB Airport Substation. | BPUB plans to remove the 138/69kV transformer and 69kV bus at Airport Substation. BPUB will be upgrading to a 138/12.5kV transformer. |  | 59460 | 59460 | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2024-04-18 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5946, 59460 | N |  |  |  | 62653 | 62652
06TPIT0143 | Temple Switch - Temple SE 138 kV line | Upgrade existing 138 kV line |  | Temple Switch | Temple SE | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R448-E | 2024-05-15 |  | 138 | 0 | 4.4 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3415, 3612 | N | N |  |  | 8521 | 1342
73613 | LCRATSC_DraftHorse_Substation_Addition | Substation addition to accommodate new BBEC load. |  | Draft Horse |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2024-05-15 |  | 138 | 0 | 0 | 0 |  | Washington |  | Tier 4 |  |  |  |  | 7286, 7289, 7295 | N | N |  |  | 73614 | 73613
08TPIT0007 | Austin Ranch - Hebron 138 kV line | Upgrade existing 138 kV line |  | Austin Ranch | Hebron | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3002-E | 2024-05-15 |  | 138 | 0 | 0.7 | 0 |  | Denton | Denton | Tier 4 | [5 empty] | N | N |  |  | 10541 | 3195
5645 | Hamilton Road to Picacho, rebuild 138 kV line | Rebuild Hamilton Road to Picacho 138 kV line | CANCELLED | Hamilton Road | Picacho | Conceptual |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-06-01 |  | 138 | 0 | 8.8 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8255, 8684 | N | N |  |  | 13379 | 5645
3901 | Lobo to Freer: Rebuild 69 kV line | Rebuild Lobo to Freer 69 kV line with 795 ACSS | Description Update | Lobo | Freer | Planned | 677 - 0846 | AEP | Brandon Cogan bcogan@aep.com 918-599-2857 | 2596 | 2024-06-30 |  | 69 | 0 | 49.8 | 0 |  | Webb | Duval | Tier 3 |  |  |  |  | 8505, 80222 | N | N |  |  | 11371 | 3901 | 2013-R90
49926 | Brinker-DentonSteam Ckt1 Upgrade |  |  | Brinker | Denton Steam | Planned |  | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2024-07-01 | 2024-07-01 | 138 | 0 | 0.63 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 982 | N | N |  |  | 49929 | 49926
44419 | Load serving |  |  | Mayhill | Denton Steam/Brinker | Planned |  | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2024-07-01 | 2024-07-01 | 138 | 5.1 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 929, 982 | N | N |  |  | 44420 | 44419
44416 | Add a 2nd circuit at Brinker - Denton Steam |  |  | Brinker | Denton Steam | Planned |  | DME | Chuck Sears |  | 2024-07-01 | 2022-07-01 | 138 | 0.631 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 927, 982 | N | N |  |  | 44417 | 44416
15TPIT0049 | Permian Basin 345 kV Switching Station | Construct 345 kV switching station and install 345/138 kV autotransformer |  | Permian Basin |  | Conceptual | R8100C-E & R8100B-E | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8100B-E | 2024-07-15 |  | 345 | 0 | 0 | 600 |  | Ward |  | Tier 1 |  | 2013-02-15 |  | 2013-09-15 | 1010, 11010 | N | N |  | Estimated cost is included in total estimated cost for 15TPIT0047. | 10184 | 2836
65723 | Riedel: Build New Distribution Station | Construct new distribution station on the Magnolia Tap to Nixon 138 kV line | CANCELLED | Riedel |  |  | 1032 - 1210 | AEP TCC/LCRA | Michael Forcum mlforcum@aep.com 918-599-2674 | 3771 | 2024-08-02 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  |  | 8583 | N | Y |  |  | 65724 | 65723
69469 | Equinox Solar Project | Equinox Solar Project | CANCELLED | Cenizo | Del Sol |  |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 |  | 2024-08-02 |  | 345 | 0 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  |  | 80355, 88355 | N |  |  |  | 69470 | 69469
64021 | Texana Solar Interconnection | Connect the Texana Solar to the El Campo to Victoria 138 kV line | CANCELLED | El Campo | Victoria | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2020888 | 2024-09-30 |  | 138 | 0 | 0 | 0 |  | Wharton | Victoria | Tier 4 |  |  |  |  | 8099, 8102, 8117, 8192, 8675 | N |  |  |  | 64022 | 64021
69485 | Wahpekute: Build new 69 kV station | Build new 69 kV station with a capacitor bank along the Jayton to Rotan 69 kV line | CANCELLED | Wahpekute |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2024-10-31 |  | 69 | 0 | 0 | 0 | 0,3.8 | Fisher |  | Tier 4 |  |  |  |  | 6162, 6196, 60057, 60066 | N |  |  |  | 69486 | 69485
61467 | Merrilltown Substation Addition | New 138 kV station - Oncor load | [5 empty] | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-03-14 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson | Williamson | Tier 4 |  |  |  |  | 9223, 9224, 9230, 9231 | N |  |  |  | 61468 | 61467
07TPIT0069 | Sterrett - Sardis 138 kV line | Upgrade existing 138 kV line |  | Sterrett | Sardis | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M361-E | 2025-05-15 |  | 138 | 0 | 2 | 0 |  | Ellis | Ellis | Tier 4 | [5 empty] | N | N |  |  | 10446 | 3102
61451 | La Vernia Substation | Replace T2, 20 MVA with a 40MVA dual high-dual low |  | La Vernia | La Vernia | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.or |  | 2025-05-16 |  | 138 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7614 | N | N |  |  | 61452 | 61451
70943 | Double circuit 138kV tie between Pyote and Coyanosa | Project resubmitted as PMCR ID # 77805 |  | Pyote (bus # 38001) | Coyanosa (bus # 38380) | Conceptual |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-06-01 |  | 138 | 15 | 0 | 0 |  | Ward | Reeves | Tier 2 |  |  |  |  | 38001, 38380 | N |  |  |  | 70944 | 70943
48854 | Adds Annova and Port South Bus and lines | Adds Annova and Port South buses, lines to connect Annova to Port South, line from HWY 511 to Port South, and reconnects line from S Carbide to HWY 511 into Port South |  | Annova LNG | Port South | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-06-01 |  | 138 | 22.1 | 0 | 0 | 0,120 | Cameron | Cameron | Tier 4 |  |  |  |  | 5767, 5775, 5776, 8337 | N | N |  |  | 48855 | 48854
76174 | Origin 138 kV Interconnection | Interconnect Callon Petroleum on the Saragosa to Solstice 138 kV line | CANCELLED | Origin |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-06-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60206, 60207, 60208, 60209, 60211, 60716 | N | N |  |  | 76175 | 76174
5461 | Load serving |  |  | Puckrus | Mayhill | Planned |  | DME | Chuck Sears cxsears@cityofdenton.com 940-349-7111 |  | 2025-07-01 | 2023-07-01 | 138 | 1.9 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 917, 929 | N | N |  |  | 13164 | 5461
76288 | Hecker to McCampbell: Rebuild 138 kV Line | Rebuild the Hecker to McCampbell 138 kV Line | CANCELLED | Hecker | McCampbell | Planned |  | AEP TCC | Brandon Cogan bcogan@aep.com 918-599-2857 | TP2023507 | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 80470 | N | N |  |  | 76289 | 76288
61446 | Wilson-SS Felps Tap to Wilson South | Build 0.99 miles of new double circuit 138kV t-line loop, 795 ACSR Drake, along FM 775 to Wilson South Substation, about 4.35 miles south of La Vernia |  | Wilson South | Wilson | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-20 |  | 138 | 0.99 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 5418, 7615, 7627, 7628, 7629 | N | N |  |  | 61448 | 61446
76280 | Reforzar: Build new 345 kV station - stage 2 | Build new 345 kV station on the Lon Hill to North Edinburg 345 kV line | CANCELLED | Reforzar |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022035 | 2026-01-30 |  | 345 | 0 | 0 | 0 |  | Brooks |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80078 | N |  |  |  | 76281 | 76280
16TPIT0068 | Venus - Chaparral Steel Tap 138 kV Line | Upgrade existing line |  | Venus | Chaparral Steel Tap | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4113-E | 2026-05-15 |  | 138 | 0 | 5.5 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 1908, 2300 | N | N |  |  | 10426 | 3082 | 2013-R50
5496 | Forney Switch 345 kV Terminal Equipment | Upgrade the terminal equipment at Forney 345 kV Switch |  | Royse |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3022 | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 4 |  |  |  |  | 2437, 2478 | N |  |  |  | 62442 | 5496
16TPIT0064 | Simpson Stuart - Lancaster Witt 138 kV Line | Upgrade existing line |  | Simpson Stuart | Lancaster Witt | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4112-E | 2026-05-15 |  | 138 | 0 | 3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2988, 3068 | N | N |  |  | 10416 | 3072 | 2013-R25
3276 | JT Deely to Martinez MLSE Upgrade | Upgrade terminal at JT Deely to ensure a rating of 2386 A (minimum). |  | JT Deely | Martinez | Planned | S-0759 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5110, 5294 | N | N |  | There are no transformers associated with this project | 10627 | 3276
5525 | Forney - Lake Hubbard 345 kV Line | Construct new 345 kV line |  | Forney | Lake Hubbard | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4233 | 2027-05-15 |  | 345 | 0 | 7.5 | 0 |  | Kaufman | Dallas | Tier 2 |  |  |  |  | 2455, 2467 | N | N |  |  | 13252 | 5525
5522 | Lake Hubbard 345/138 kV Switching Station | Construct new 345/138 kV switching station |  | Lake Hubbard |  | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4139 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 |  |  |  |  | 2401, 2402, 2455, 12455, 12456 | N | N |  |  | 13249 | 5522
73540 | LCRATSC_Carlson_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor Lund substation addition. |  | Carlson |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 3650, 7337, 7338 | N | N |  |  | 73541 | 73540
50282 | Adds new Jaguar sub near Twin Pines Switch | Adds new Jaguar sub between Twin Pines Switch and Highlands Sub. For AEP load. | AEP is looking at another location to serve the load. | Highlands Sub | Twin Pines Switch | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5602, 5604, 5609 | N | N |  |  | 50283 | 50282
44870 | Charlotte 69 kV Station | Charlotte 69 kV Station: Add Cap Bank |  | Charlotte | - | Planned | 976 - 1154 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3734 | 2027-07-01 |  | 69 | 0 | 0 | 0 | 0,7.2 | Atascosa |  | Tier 3 | [5 empty] | N | N |  |  | 44871 | 44870
4490 | LaPalma: Add 2nd 345/138 kV autotransformer | Add 345/138 kV autotransformer capacity at LaPalma | CANCELLED | LaPalma |  |  | 710 - 0880 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 2904 | 2027-09-30 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 4 |  |  |  |  | 8314, 8317, 8356 | N | N |  |  | 12067 | 4490 | 2014-S15, S16
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line | Project Deferral | Cresson | Rocky Creek | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5228 | 2028-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  |  | 1881, 2202 | N | N |  |  | 12436 | 4834
6930 | New Paloma Substation | Adds new station and short line from Midstream |  | Midstream | Paloma | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-06-01 |  | 138 | 0.9 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5643, 5644 | N | N |  |  | 14749 | 6930
6743 | Magellan Tank Farm: LCRA Interconnect | Add 138kV Tie Line between Navigation 138kV substation and Magellan's 138kV substation. Add Metering at Magellan's Substation. | Cancelled | Navigation | Magellan |  | 905 - 1083 | AEP TCC/LCRA | Michael Glueck bcogan@aep.com 918-599-2857 | 3689 | 2029-07-01 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 78460 | N | Y |  |  | 14536 | 6743
65648 | Interconnects Faulkner Data Center | Project has been cancelled. |  | TNMP Faulkner (bus # 38124) | Customer substation (bus # 38125) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-10-01 |  | 138 | 0.15 | 0 | 0 | 0,160 | Reeves | Reeves | Tier 4 |  |  |  |  | 38124, 38125 | N |  |  |  | 65649 | 65648
5524 | Royse South 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | Royse | Forney | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4234 | 2030-05-15 12:00 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 3 |  |  |  |  | 2437, 2467, 2469, 2470, 2471, 2472, 2474, 2478, 2485, 2702, 2710, 12471 | N | N |  |  | 49918 | 5524 | 2017-NC34
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 5600, 5601, 5602 | N | N |  |  | 8729 | 1538
5220 | Move Orange Grove load to 138 kV bus | Move load from the 69 KV to the 138 KV instead of replacing auto. 2015 RTP |  | Orange Grove |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 138 | 0 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 5660 | N | N |  |  | 12887 | 5220
3822 | San Miguel to Sigmor 138 kV line upgrade | Upgrade San Miguel to Sigmor 138 kV line as recommended in 2013 RTP. Will investigate re-conductoring on existing structures with ACCC and other high temperature conductors. |  | San Miguel | Sigmor | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 138 | 0 | 26.3 | 0 |  | Atascosa | Live Oak | Tier 3 |  |  |  |  | 5689, 5902, 8404 | N | N |  | Studies after the 2013 RTP have shown that AEP's approved project to rebuild the 69 kV Beeville to Three Rivers to 138 kV, TPIT 5166, reduces the loading on this line. STEC believes that rebuilding San Miguel to Sigmor is likely to be justified in the future by load growth and or generation additions. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 11279 | 3822 | 2013-R102

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2023-C1 | North Rosenberg (944070) 345-kV Substation Addition and 345-kV Double-Circuit Line Additions from Whaley (44070) to North Rosenberg (944070) to Obrien (44500) | CNP | 2025
2023-C2 | Formosa (8126) to Lolita (8125) to Blessing (8121) 138-kV Line Upgrade | AEP | 2025
2023-C3 | Cangrejo (8720) to Pcomfort (8132) 69-kV Line Upgrade | AEP | 2025
2023-C4 | South Texas Project (5915) to WA Parish (44000) 345-kV Line Upgrade | AEP, CNP | 2025
2023-E1 | Big Brown Ses (3381) to Jewett (3391) 345-kV Double-Circuit Line Upgrade | ONCOR | 2025
2023-E2 | Canton Switch (3174) to Edgewood (3181) 138-kV Line Upgrade | ONCOR | 2025
2016-N1 | Kiamichi Energy Facility (140077) 345-kV Reactor Addition | KIOWA POWER PARTNERS LLC (RE) | 2026MIN
2023-N1 | Gainesville 138/69-kV Transformer Upgrade | BEPC | 2026
2023-N2 | Beaver (1524) to Old Lake Switch (11541) 69-kV Line Upgrade | ONCOR | 2026
2023-N3 | LPL Line Upgrades | LPL | 2025
2023-N4 | Sand Road (6063) to Southwest Vernon (6064) 69-kV Line Upgrade | AEP | 2026
2023-N5 | Parkway (1499) to Bowman (1423) to Lake Wichita (1446) 138-kV Line Upgrades | ONCOR | 2025
2023-N6 | Fisher Road (1427) to Wichita Falls (1448) 138-kV Line Upgrade | ONCOR | 2025
2023-N7 | Hawk Hollow Switch (11768) to Deport (1768) to Rivercrest SES (1780) 138-kV Line Upgrades | ONCOR | 2025
2023-N8 | Yellow House Canyon Substation 345/115-kV Transformer Upgrade | LPL | 2028
2023-N9 | Spur 138/69-kV Transformer Upgrade | AEP | 2029
2023-N10 | Pleasant Valley Switch (1450) to Ceramic (1485) to Wichita Falls PPG (1484) to Wichita Falls PPG Oxygen (17005) to City View (1483) 138-kV Line Upgrades | ONCOR | 2025
2023-N11 | Wichita Falls South Switch (1464) to Arrowhead (1478) to Rathgeber (1480) 138-kV Line Upgrades | ONCOR | 2026
2023-N12 | Bonham Switch (1760) - Bonham (1808) - Copperhead Switch (11809) 138-kV Line Upgrade | ONCOR | 2025
2023-N13 | Whitesboro Southwest (718) 138-kV Capacitor Bank Addition | BEPC | 2028
2022-NC2 | Brand (827) to Ben Davis (968) 138-kV Line Upgrade | GPL | 2025 | 2024 | Planned | 67170
2022-NC5 | New International Airport Switch 345/138-kV Station | ONCOR | 2025
2022-NC7 | Liggett Switch- DFW Area 138-kV Line Upgrades | ONCOR | 2025
2023-NC1 | Miller to Palopnto 138-kV Line Upgrades | BEPC, ONCOR | 2025
2023-NC2 | Carmichael Bend Switch to Benbrook Switch 345-kV Line Upgrade | ONCOR | 2025
2023-NC3 | Randol Mill Tap East (2104) to Randol Mill (2106) 138-kV Line Upgrade | ONCOR | 2025
2023-NC4 | Watermill Switch (2428) to Loop Nine Switch (22427) 345-kV Line Addition | ONCOR | 2025
2023-NC5 | Temple Switch (3415) to Temple Southeast (3612) 138-kV Line Upgrade | ONCOR | 2025
2023-NC6 | Telico Area Upgrades | ONCOR | 2025
2023-NC7 | Four Brothers Switch -Tradinghouse - Outlaw - Lake Hall Switch - Sam Switch Area Improvements | ONCOR | 2026
2023-NC8 | Gunter 345/138-kV Substation Addition | ONCOR | 2025
2023-NC9 | Seagoville to Watermill 138-kV Line Upgrade | ONCOR | 2025 | 2025 | Planned | 71178
2023-NC10 | Prairie Creek to Mesquite North 138-kV Line Upgrade | ONCOR | 2025
2023-NC11 | Centerville Area Line Upgrades | GPL | 2025 | 2025 | Planned | 73348
2023-NC12 | Mexia Transformer Upgrade | ONCOR | 2025
2023-NC13 | Hillboro 138-kV Area Upgrades | BEPC | 2025
2023-NC14 | Killeen to Salado 345-kV Line Upgrade | ONCOR | 2029
2023-NC15 | Renner Switch 345/138-kV Transformer Upgrade | ONCOR | 2025
2023-NC16 | Sardis Area 138-kV Line Upgrades | ONCOR | 2025
2023-NC17 | Temple Southeast (3612) to Scott and White (3602) to Temple South (3611) 138-kV Line Upgrades | ONCOR | 2025
2023-NC18 | Tri Corner (2432) to Seagoville Switch (2433) to Forney Switch (2437) 345-kV Line Upgrade | ONCOR | 2025
2023-NC19 | Venus - Fort Smith - Sam Switch Double Circuit 345-kV Line Upgrades and Venus Kemp Ranch 345/138-kV Transformer Addition | ONCOR | 2025
2023-NC20 | Kemp South (2726) to Seven Points (3264) to Will White POI (3287) 138-kV Line Upgrade | ONCOR | 2026
2023-NC21 | Cedar Creek Pump (3263) to Mankin SW (3265) 138-kV Line Upgrade | ONCOR | 2025
2023-NC22 | Nolanville (3617) to Harker Heights (3618) 138-kV Line Upgrade | ONCOR | 2025
2023-NC23 | Venus - Navarro - Jewett Area 345-kV Line Upgrades | ONCOR | 2026
2023-NC24 | Southside POI (230) to MCCree (832) 69-kV Line Upgrade | BEPC | 2028
2023-NC25 | Concord (394) to Wildcat Switching Station (388) 138-kV Line Upgrade | BEPC | 2028
2023-NC26 | West Loop (480) - Brock (487) 138-kV Line Upgrade | BEPC | 2026
2023-NC27 | Olney 138/69-kV Transformer Upgrade | BEPC | 2028
2023-NC28 | Commerce Switch (1816) - Crossroads Switch (1844) 138-kV Line Upgrade | ONCOR | 2026
2023-NC29 | Mitchell Bend Switch (1895) - Carmichel (2285) 345-kV Circuit Addition | ONCOR | 2026
2023-NC30 | PNTHRISL (1966) - Randoll Mill (2106) 138-kV Line Upgrade | ONCOR | 2026
2023-NC31 | Parkdale Switch (2445) - Pleasant Grove Tap 1 (2960) 138-kV Line Upgrade | ONCOR | 2026
2023-NC32 | Cedar Crest Switch (2486) - Buntin Drive (2985) 138-kV Line Upgrade | ONCOR | 2026
2023-NC33 | Sargent Road (2941) - Saint Augustine Tap 2 (2951) 138-kV Line Upgrade | ONCOR | 2025
2023-NC34 | Temple Pecan Creek (3412) - Temple Switch (3414) 345-kV Line Upgrade | ONCOR | 2026
2023-NC35 | Navarro (3478) - Haney (213) - Hubbard (3515) 138-kV Line Upgrade | ONCOR | 2026
2023-NC36 | Temple Belton 138-kV Line Upgrades | ONCOR | 2025
2023-NC37 | Hillboro 138/69-kV Transformer Upgrade | ONCOR | 2025
2023-NC38 | Watermill 345/138-kV Transformer Upgrade | ONCOR | 2025
2023-NC39 | Navarro (3479) to Richland (3486) 69-kV Line Upgrade | ONCOR | 2028
2023-NC40 | Mclennan County East (3442) to Tradinghouse Tap (3555) to Hallsburg (95) to Lake Creek (3410) 138-kV Line Upgrades | BEPC | 2028
2023-NC41 | Watermill 138-kV Area Upgrades | ONCOR | 2026
2023-NC42 | Waxahachie Area 69-kV and 138-kV Line Upgrades | ONCOR | 2026MIN
2023-NC43 | Wilmer 138/69-kV Transformer Upgrade | ONCOR | 2026
2023-NC44 | Corinth (1985) to Argyle (1984) to Highlands TNP (1974) 138-kV Line Upgrades | ONCOR | 2025
2023-NC45 | Cleburne Switch (2279) to Keene (2294) to Alvarado (2297) to Griffith (1905) to Railport (442) to Venus (1908) 138-kV Line Upgrades | BEPC, ONCOR | 2025
2023-NC46 | Desoto Switch (2424) to Parkerville Road (12425, 2425) 138-kV Line Upgrade | ONCOR | 2025
2023-NC47 | Carrollton Tarpley Road (2559) to Carrollton East (2578) 138-kV Line Upgrade | ONCOR | 2028
2023-NC48 | Plano Arco (2671) to Plano West (2673) 138-kV Line Upgrade | ONCOR | 2029
2023-NC49 | Greenville Avenue Switch (2882) to Greenville Avenue (12882) 138-kV Line Upgrade | ONCOR | 2028
2023-NC50 | Harker Heights (3618) to Killeen Taft Street (3616) to Killeen Elm (13427) 138-kV Line Upgrades | ONCOR | 2025
2023-NC51 | Temple Area 138-kV Upgrades | ONCOR | 2025
2023-NC52 | Cedar Hill Switch (2422) to Fish Creek Switch (2491) 138-kV Line Upgrade | ONCOR | 2026
2023-NC53 | Centerville Road Switch Area 138-kV Line Upgrades | ONCOR | 2026
2023-NC54 | Corsicana (3468) to Barry (Oncor) (3471) 69-kV Line Upgrades | ONCOR | 2028
2023-NC55 | Everman 345/138-kV Transformer Addition | ONCOR | 2028
2023-NC56 | Everman (1883,1884) to Marrs (1969) 138-kV Upgrade | ONCOR | 2028
2023-NC57 | Killeen Area 138-kV Capacitor Bank Additions | ONCOR | 2025
2023-NC58 | Lake Creek 345/138-kV Transformer Upgrade | ONCOR | 2028
2023-NC59 | Plano Highway 190 Area 138-kV Line Upgrades | ONCOR | 2029
2023-NC60 | Temple Switch and Temple Pecan 345/138-kV Transformer Additions | ONCOR | 2025
2023-NC61 | Temple Pecan Area 138-kV Upgrades | ONCOR | 2025
2023-NC62 | Whitney 345/138-kV Transformer Upgrade | BEPC | 2025
2023-NC63 | DFW and Euless Area 138-kV Upgrades | ONCOR | 2025
2021-W5 | Sacroc - Deep Creek Sub 138-kV Line Upgrade | ONCOR | 2026
2023-W1 | Hamlin to Roby 69-kV Line Rebuild | AEP | 2026 | 2027 | Planned | 73055
2023-W2 | San Angelo Mathis Field - Tankersley - Mertzon - Cassava 69-kV Line Upgrade | AEP | 2025
2023-W3 | Colorado City to Plowboy 69-kV Line Upgrade | ONCOR | 2026
2023-W4 | Bluff Creek Switch - China Grove Switch - Oncor 900067 Tap - Getty Vealmoor Tap 138-kV Line Upgrade | ONCOR | 2025
2023-W5 | Sterling City to Camp Elizabeth 69-kV Line Upgrade | AEP | 2025
2023-W6 | Cedar Hills to Silver Tap 69-kV Line Upgrade | AEP | 2025
2023-W7 | Carlsbad Tap to Burma 69-kV Line Upgrade | AEP | 2026
2023-W8 | San Angelo North 138/69-kV Transformer Upgrade | AEP | 2028
2023-W9 | New Load Bus 900110 138-kV Cap Bank Addition | AEP | 2028
2023-W10 | Dermott - Scurry Chevron - Kndrsacrc - Oncor900041 Tap - Knapp - Bluff Creek 138-kV Line Upgrade | ONCOR | 2025
2023-W11 | Red Creek Area 138-kV Lines Upgrade | AEP | 2026
2023-W12 | Morgan Creek SES - Tonkawa 345-kV Line Rebuild | ONCOR | 2025
2023-W13 | Bondroad to Friess Ranch 69-kV Line Upgrade | AEP | 2028
2023-W14 | Campwood - Barcksdale - Rocksprings 69-kV Line Upgrade | AEP | 2025 | 2028 | Planned | 55617, 55605
2023-W15 | San Angelo Redcreek Third 345/138-kV Transformer Addition | AEP | 2026
2023-W16 | Abilene Northwest-Abi Mulberry Creek-Abi Industrial Park-Abi Elmcreek 138-kV Upgrade | AEP | 2025
2023-W17 | Dermott to Ennis Creek Switch 138-kV Line Upgrade | ONCOR | 2028
2023-W18 | Golden Switch to Sun Switch 138-kV Line Upgrade | ONCOR | 2029
2023-W19 | Bluff Creek Switch - Exxon Sharon Ridge 138-kV Line Upgrade | ONCOR | 2026MIN
2021-FW4 | Rio Pecos - Rankin - Texon Tap - Atlantic Best Tap - Kemper Tap - Big Lake 69-kV to 138-kV Line Conversion | AEP | 2025
2021-FW5 | Caymus TNP - Gas Pad 138-kV Line and Caymus TNP - Caymus Compressor TNP Line Terminal Equipment Upgrade | AEP | 2025
2021-FW6 | TNMP Monument Draw to Monument Draw Gray Oak 138-kV Line Terminal Equipment Upgrade | TNMP | 2028
2021-FW7 | TNMP Flat Top 138/25-kV Transformer Upgrade | TNMP | 2025
2021-FW8 | TNMP Wink - TNMP California 69-kV to 138-kV Line Conversion | TNMP | 2028
2021-FW16 | 16th Street TNP - Fort Stockton TNP 69-kV Line Upgrade | TNMP | 2025
2021-FW19 | Morgan Creek SES - Longshore Switch 345-kV Line Upgrade | ONCOR | 2026
2021-FW20 | Lamesa - Key Sub - Gail Sub - Willow Valley Switch 138-kV Line Upgrade | ONCOR | 2026MIN
2022-FW2 | Cedarvale 345-kV Subtation Expansion | ONCOR, TNMP | 2025
2022-FW10 | Dollarhide - Dollarhide Unocal 138-kV Line Upgrade | ONCOR | 2025
2022-FW15 | Holt Switch - Turnbaugh Corner Switch - Scharbauer POI - Oncor 900053 Tap - Notrees Southeast POI - Blockline POD - Amburguey - Yucca Drive Switch 138-kV Line Upgrade | ONCOR | 2025
2022-FW23 | Consavy South 345/138 S-kV Susbstation Addition and 345-kV Line Addition | ONCOR | 2025
2022-FW24 | Faraday - Lamesa - Clearfork - Riverton 345-kV Double Circuit Line Addition | ONCOR, WETT | 2026MIN
2022-FW25 | Cedarvale Third 345/138-kV Transformer Addition | TNMP | 2026
2023-FW1 | Glasscock County North - Forsan Tap - Mcdonald - Polecat Creek Switch 138-kV Line Upgrade | ONCOR | 2028
2023-FW2 | Illinois - Pandale - Ozona Rea - Ozona - Friend Ranch - Atlantic Sonora 69-kV Upgrade | AEP | 2025
2023-FW3 | Collie Field Tap TNP - IH 20 TNP 138-kV Line Upgrade | TNMP | 2028
2023-FW4 | Buzzard Draw Switch - Koch Tap - Vealmoor 138-kV Line Upgrade | ONCOR | 2025
2023-FW5 | Gemsbok TNP 138-kV Cap Bank Addition | TNMP | 2028
2023-FW6 | Foxtail TNP to Pig Creek 138-kV Line Upgrade | TNMP | 2026
2023-FW7 | Wolfcamp - Courtney Creek 69-kV to 138-kV Line Conversion | ONCOR | 2025
2023-FW8 | Midkiff Switch 138-kV Cap Bank Addition | ONCOR | 2028
2023-FW9 | East Stiles 138-kV Cap Banks Addition | ONCOR | 2025
2023-FW10 | Far West Reactive Power Support Device Addition | AEP, ONCOR, TNMP | 2028
2023-FW11 | New Load Bus 900062 138-kV Cap Bank Addition | AEP | 2025
2023-FW12 | Foxtail TNP to Flat Top TNP 138-kV Line Upgrade | AEP, TNMP | 2025
2023-FW13 | Bulldog - Elbow - Eiland - Einstein - Carterville 138-kV Line Upgrade | ONCOR | 2025
2023-FW14 | Spraberry Switch to Skywest 138-kV Line Upgrade | LCRA, ONCOR | 2025
2023-FW15 | Odessa to Onc900016 138-kV Line Upgrade | ONCOR | 2025
2023-FW16 | Fort Stockton Plant - Leon Creek TNP 138-kV Line Upgrade | AEP, TNMP | 2026
2021-WFW1 | Big Lake - Barnhart - Cassava 69-kV to 138-kV Line Conversion | AEP | 2028
2022-WFW1 | Twin Buttes - Hargrove - Pumpjack - Jerry - Russek Street - Big Lake 138-kV line Upgrade | AEP, LCRA | 2025
2022-WFW2 | Midessa South SW - Consavvy - Longshore Switch - Morgan Creek SES 345-kV Line Upgrades | ONCOR | 2026MIN
2023-WFW1 | Exxon Sharon Ridge to Willow Valley Switch 138-kV Line Upgrade | ONCOR | 2026MIN
2023-WFW2 | Morgan Creek SES - Falcon Seaboard - Midland East 345-kV Line Upgrade | ONCOR | 2026MIN
2022-SC7 | Decker 138-kV Bus Tie Breaker Upgrade | AEN | 2025
2022-SC8 | Lytton Substation 345/138-kV Transformer Addition | AEN | 2025
2023-SC1 | Austrop Substation 345/138-kV Transformer Addition | LCRA | 2025
2023-SC2 | Austrop (9328) to Dunlap (9045) Second 138-kV Line Addition | AEN | 2025
2023-SC3 | Dessau (9193) to McNeil AEN (9076) 138-kV Circuit 2 Upgrade | AEN | 2025
2023-SC4 | Hutto Switch (3666) 138-kV Cap Bank Addition | ONCOR | 2025
2023-SC5 | Beck Road 345/138-kV Substation Expansion | CPS | 2028
2023-SC6 | Lytton Springs (9074) to Garfield (7048) to Austrop (7040) 345-kV Line Upgrades | AEN, LCRA | 2025
2023-SC7 | Cachena (5068) 345-kV Reactor Addition | CPS | 2025
2023-SC8 | Dunlap 345/138-kV Transformer Addition | AEN | 2025
2023-SC9 | Scooter 345/138-kV Substation Addition | ONCOR | 2025 | 2026 | Planned | 76654
2023-SC10 | Wiseman 138-kV Substation Addition and CPS Multiple Cap Bank Additions | CPS | 2025 | 2028 | Planned | 73366, 75493
2023-SC11 | Lockhart to San Marcos 69-kV to 138-kV Line Conversion | LCRA | 2025 | 2026 | Planned | 73106
2023-SC12 | Lytton Springs to Pilot Knob 138-kV Line Upgrade | AEN | 2025 | 2026 | Planned | 71408
2023-SC13 | AEN Dunlap to Decker Power Plant 138-KV Second Circuit Addition | AEN | 2025 | 2027 | Planned | 67091
2023-SC14 | Trading Post and Cedar Valley Substation 138-kV Cap Bank Additions | LCRA | 2025
2023-SC15 | Sim Gideon Area 138-kV Line Upgrades | LCRA, ONCOR | 2025
2023-SC16 | Hondo to Hondo Creek Switching Station 138-kV Line Upgrade | CPS, STEC | 2025
2023-SC17 | Round Rock, Hutto, and Georgetown Area 138-kV Line Upgrades | LCRA, ONCOR | 2025
2023-SC18 | El Campo Sub to Nada 69-kV Line Upgrade | STEC | 2025
2023-SC19 | South to Central Texas 345-kV Double-Circuit Line Additions | AEN, AEP, LCRA, ONCOR | 2029
2023-SC20 | Pearson - Natalia - Devine - Moore - Pearsall 69-kV Line Rebuild | STEC | 2026 | 2026 | Planned | 76768
2023-SC21 | Big Foot to Lytle 69-kV to 138-kV Line Conversion | AEP | 2025 | 2026 | Planned | 73063
2022-S2 | Fannisub - Goliad 69-kV Line Upgrade | AEP, STEC | 2025
2022-S3 | Pearsall 138/69-kV Transformer Upgrade | STEC | 2026 | 2027 | Planned | 76790
2023-S1 | LGE to Dupont Switch - Ingleside 138-kV Line Upgrade | AEP | 2025
2023-S2 | Lon Hill to Calallen Sub 69-kV Line Limiting Element Upgrade | AEP, STEC | 2025
2023-S3 | Oaks Sub 138/69-kV Transformer Upgrade | STEC | 2025
2023-S4 | Poteet Sub to Oaks Sub 69-kV Line Upgrade | STEC | 2025
2023-S5 | Poteet Sub to Pearsall Switching Station 69-kV Line Upgrade | STEC | 2025
2023-S6 | Rossville Substation Cap Bank Addition | STEC | 2025
2023-S7 | Static (8676) 345-kV Reactor Addition | AEP | 2026MIN

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Cindy Miller | Camiller2@aep.com | Cindy Miller: 918 599 2891 | Glen Reed; Brandon Cogan; Mike Forcum; Jeff Ellis; Mina Turner; Lisa Kelso; | gareed@aep.com; bcogan@aep.com; mlforcum@aep.com; dnlyons@aep.com; jlellis@aep.com; myturner@aep.com; lokelso@aep.com; | Michael Forcum: 918 599 2674 Glen Reed: 918 599 2664 Brandon Cogan: 918 599 2857 Jeff Ellis: 918 599 3458
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Hunt, Dandy; Brion Ryan | dandy.hunt@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | Reza:512 322 6740 Dandy:512 322 6748 Brion: 512-322-6879
BPUB | Primary | Luis Martinez | lugmartinez@brownsville-pub.com; | Luis: 956 983 6212 | Javier Martinez Jr. | jamartinez@brownsville-pub.com; | Javier: 956 983 6530
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Brian Hithersay | bhithersay@brazoselectric.com | Brian: 254-750-6795 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | Edward Lopez | elopez@btutilities.com | Edward: 979 821 5697 | David Hering | dhering@btutilities.com | David: 979 821 5652
CNP | Primary & Secondary | Wesley Woitt | wesley.woitt@centerpointenergy.com | Wesley Woitt: 713-207-2760 | Samuel Whisler; Raja Sekhar Kakarla; Cody Mann | samuel.whisler@centerpointenergy.com; rajasekhar.kakarla@centerpointenergy.com; cody.mann@centerpointenergy.com | Samuel Whisler: 713-207-2767 Raja Sekhar Kakarla: 713-207-3614 Cody Mann: 713-207-3149
COCS | Primary | Glenn Gavit | ggavit@cstx.gov | Glenn: 979 764 3682 | Timothy Crabb, Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | William Robertson | wrobertson@cpsenergy.com | William: 210 353 4147 | Kenneth Bowen Marcos Terrazas Zuber Vohra Eduardo Olivarez | kbowen@cpsenergy.com; mterrazas1@cpsenergy.com; ZMVohra@cpsenergy.com; EJOlivarez@cpsenergy.com | Kenneth: 210 353 4142 Marcos: 210 353 2451 Zuber: 210 353 4262 Eduardo: 210 353 2357
CTT (Cross Texas Transmission) | Primary & Secondary | Christina Minchew | cminchew@lspower.com | Christina: 636:698:8443 | Ramya Nagarajan | RNagarajan@lspower.com | Ramya: 737-881-5008
DENTON | Primary & Secondary | Mark Zimmerer | Mark.Zimmerer@cityofdenton.com | Mark: 940 349 7169 | Cody Tenorio | Cody.Tenorio@cityofdenton.com | Cody: 940 349 7532
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | David Grubbs Kevin Sills | Dgrubbs@gpltexas.org; ksills@gpltexas.org | David: 972-205-2664 Kevin: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; BEC (Bandera); BBEC; CTEC; GVEC; NBU; SBEC; RGEC | Primary & Secondary | Dylan Preas | dylan.preas@lcra.org | Dylan: 512-578-4514 | Naved Khan | naved.khan@lcra.org | Naved: 512-578-4176
Lone Star | Primary & Secondary | Chenyan Guo | chenyan.guo@fpl.com | Chenyan: 561-304-5692 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Jared Gurley | Jared.Gurley@oncor.com | Jared: 817-215-6079 | Zahra Jianpanah | Zahra.Jianpanah@oncor.com
PEC | Primary & Secondary | Charles DeWitt | charles.dewitt@peci.com | Charles: 830-225-0673 | Joshua Rivers | joshua.rivers@peci.com | Joshua: 830-330-4192
Rayburn | Primary | Stephen Geiger | sgeiger@rayburnelectric.com | Stephen: 469-402-2112 | Scott Donham | Sdonham@rayburnelectric.com | Scott: 469-402-2024
Sharyland Utilities | Primary & Secondary | Brad Schwarz | bschwarz@huntpower.com | Brad: 512-289-7425 | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243
STEC | Primary & Secondary | Teddi Flessner Long Tran | tflessner@stec.org long.tran@stec.org | Teddi: 361 485 6119 Long: 361 485 6318 | Paul Person Loretta Gonzalez | pperson@stec.org; lgonzalez@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Kevin Sills | Ksills@gpltexas.org | Kevin: 972-205-2603
TNMP | Primary & Secondary | Ross Cloninger | ross.cloninger@tnmp.com | Ross: 281-581-4733 | Xia, Tao Roberts, Vincent Gerety, Chris | Tao.Xia@tnmp.com; Vincent.Roberts@tnmp.com; Christopher.Gerety@tnmp.com; | Tao: 281-581-4764 Vincent:409-949-5608 Chris:409-949-5605
Wind Energy Texas Transmission (WETT) | Primary | Chris Ramirez | cramirez@wettllc.com | Chris: 737-218-4525 | Yang Zhang | yzhang@wettllc.com | Yang: 737-218-4542

## TSPResponsibility
Field Name | Required/ Optional
ERCOT Project Number | Required
RTP Project Number | Required if in RTP
RPG Project Number | Required for submitted Tier 1, 2, and 3 projects
Project Title | Required
Project Description | Optional
Comments/Reasons for Delays/Cancellations/Speedup | Optional
Terminal "from" Location | Optional
Terminal "to" Location | Optional
Transmission Status | Optional
Associated Projects (project number) | Optional
Transmission Owner | Required
TSP/Company Contact | Required
Transmission Owner Project Number | Optional
Projected In-Service Date (Month/Yr) | Required
Actual In-Service Date (Month/Yr) | Required once energized in the field
CONFIDENTIAL Total Project Estimated Cost | Required
Service Level kV | Required
Trans Circuit Miles New | Optional
Trans Circuit Miles Rebuilt or Upgraded | Optional
Autotransformer Capacity (MVA) | Optional
Reactive Capability Added | Optional
County Location for Substation or for a Line | Optional
County Location for Ending Point for a Line | Optional
Planning Charter Tier | Required
Date Submitted TO ERCOT for RPG Review | Required for submitted Tier 1, 2, and 3 projects
Date RPG Review Completed (Month/Yr) | Required for submitted Tier 1, 2, and 3 projects, if RPG review has been completed.
Date ERCOT BOD Review Completed | -Required for submitted Tier 1 projects, if ERCOT BOD review completed.
SSWG Base Case Related Bus Numbers | Required
Is the project reflected in SSWG Base Cases? | Required
Part of Interface (Y/N) | Required
Requested Additional Information | Optional