## ImprovementCostSummary10232026
| Project Cost | [6 empty] | XFMR MVA
| 765 | 345 | 138 | 115 | 69 | Total |  | 765 | 345 | 138 | 115 | 69 | Total
2025 Completed | 0 | 1338595000 | 1713556500 | 0 | 322517000 | 3374668500 | 2025 Completed | 0 | 10300 | 130 | 0 | 40 | 10470 |  | For ROS and BOD Reports
2026 Completed | 0 | 763293000 | 486329000 | 0 | 133966000 | 1383588000 | 2026 Completed | 0 | 2400 | 40 | 0 | 80 | 2520 |  | ·All Projects (in engineering, routing, licensing and construction): |  |  |  | 63598157748
2026 Planned | 0 | 3005025000 | 1745012778 | 0 | 580261000 | 5330298778 | 2026 Planned | 0 | 3856 | 50 | 0 | 100 | 4006 |  | ·Transmission Projects Energized in 2026: |  |  |  | 1383588000
2027 | 0 | 5202494202 | 3667097686 | 15000000 | 403294000 | 9287885888 | 2027 | 0 | 14250 | 1100 | 0 | 125 | 15475 |  | ·Transmission Projects Planned to Energize in 2026: |  |  |  | 5330298778
2028 | 1632100000 | 5003012539 | 5374677101 | 0 | 641707000 | 12651496640 | 2028 | 4500 | 9342 | 365 | 0 | -852 | 13355
2029 | 2040500000 | 4443705002 | 2799260003 | 0 | 337907000 | 9671372005 | 2029 | 9000 | 10506 | 290 | 0 | 200 | 19996
2030 | 9159690000 | 1569308003 | 1454582432 | 0 | 171663000 | 12355243435 | 2030 | 22806 | 5350 | 90 | 0 | 0 | 28246
2031 | 2800268000 | 2273175002 | 664980000 | 0 | 104953000 | 5843376002 | 2031 | 13650 | 4144 | 0 | 0 | 0 | 17794
2032 | 4604330000 | 1856810000 | 234075000 | 0 | 21900000 | 6717115000 | 2032 | 15066 | 0 | 0 | 0 | 0 | 15066
2033 | 0 | 1533190000 | 203180000 | 0 | 5000000 | 1741370000 | 2033 | 0 | 0 | 0 | 0 | 0 | 0
2026 Completed | 0 | 763293000 | 486329000 | 0 | 133966000 | 1383588000 | 2026 Completed | 0 | 2400 | 40 | 0 | 80 | 2520
2026 Planned | 0 | 2354311000 | 1411288778 | 0 | 292418000 | 4058017778 | 2026 Planned | 0 | 3856 | 50 | 0 | 0 | 3906
2025-2033 | 20236888000 | 26988607748 | 18342750500 | 15000000 | 2723168000 | 68356414248 | 2025-2033 | 65022 | 60148 | 2065 | 0 | -307 | 126928
2025-2026 | 0 | 5106913000 | 3944898278 | 0 | 1036744000 | 10088555278 | 2025-2026 | 0 | 16556 | 220 | 0 | 220 | 16996
2027-2033 | 20236888000 | 21881694748 | 14397852222 | 15000000 | 1686424000 | 58267858970 | 2027-2033 | 65022 | 43592 | 1845 | 0 | -527 | 109932
| Circuit Miles New | [6 empty] | Circuit Miles Rebuilt, Reconductored or Upgraded | [6 empty] | Total Circuit Miles New, Rebuilt, Reconductored or Upgraded
| 765 | 345 | 138 | 115 | 69 | Total |  | 765 | 345 | 138 | 115 | 69 | Total |  | 765 | 345 | 138 | 115 | 69 | Total
2025 Completed | 0 | 17.93 | 139.05 | 0 | 0 | 156.98 | 2025 Completed | 0 | 11.3 | 380.72 | 0 | 161.44 | 553.46 | 2025 Completed | 0 | 29.23 | 518.94 | 0 | 161.44 | 709.61
2026 Completed | 0 | 49.6 | 21.47 | 0 | 0 | 71.07 | 2026 Completed | 0 | 11.8 | 96.41 | 0 | 86.13 | 194.34 | 2026 Completed | 0 | 56.9 | 117.88 | 0 | 86.13 | 260.91
2026 Planned | 0 | 699.76 | 91.58 | 0 | 20.5 | 811.84 | 2026 Planned | 0 | 118.06 | 387.68 | 0 | 227.16 | 732.9 | 2026 Planned | 0 | 817.82 | 475.86 | 0 | 247.66 | 1541.34
2027 | 0 | 533.68 | 162.039 | 3 | 36.43 | 735.149 | 2027 | 0 | 396.28 | 600.0926 | 0 | 117.94 | 1114.3126 | 2027 | 0 | 929.96 | 762.1316 | 3 | 154.37 | 1849.4616
2028 | 184.8 | 889.81 | 346.33 | 0 | 1.6 | 1422.54 | 2028 | 0 | 626.35 | 1115.708 | 0 | 457.22 | 2199.278 | 2028 | 184.8 | 1516.16 | 1456.538 | 0 | 458.82 | 3616.318
2029 | 257.45 | 767.35 | 90.96 | 0 | 2 | 1117.76 | 2029 | 0 | 213.7 | 803.2543 | 0 | 92.4 | 1118.0543 | 2029 | 257.45 | 981.05 | 888.9143 | 0 | 86.9 | 2223.0143
2030 | 982.9 | 237.76 | 227.08 | 0 | 34.4 | 1482.14 | 2030 | 0 | 420.24 | 415.19 | 0 | 72.051 | 907.481 | 2030 | 982.9 | 658 | 494.59 | 0 | 106.451 | 2241.941
2031 | 578 | 270.45 | 59.04 | 0 | 15.7 | 923.19 | 2031 | 0 | 437.33 | 373.61 | 0 | 59.62 | 870.56 | 2031 | 578 | 707.78 | 432.65 | 0 | 75.32 | 1793.75
2032 | 417 | 176.28 | 0 | 0 | 0 | 593.28 | 2032 | 292.8 | 271.9 | 110.84 | 0 | 0 | 675.54 | 2032 | 709.8 | 448.18 | 110.84 | 0 | 0 | 1268.82
2033 | 0 | 112.5 | 0.3 | 0 | 0 | 112.8 | 2033 | 0 | 240.1 | 66.75 | 0 | 0 | 306.85 | 2033 | 0 | 352.6 | 67.05 | 0 | 0 | 419.65
2026 Completed | 0 | 49.6 | 21.47 | 0 | 0 | 71.07 | 2026 Completed | 0 | 11.8 | 96.41 | 0 | 86.13 | 194.34 | 2026 Completed | 0 | 56.9 | 117.88 | 0 | 86.13 | 260.91
2026 Planned | 0 | 362.66 | 78.58 | 0 | 0 | 441.24 | 2026 Planned | 0 | 118.06 | 294.04 | 0 | 108.97 | 521.07 | 2026 Planned | 0 | 480.72 | 369.22 | 0 | 108.97 | 958.91
2025-2033 | 2420.15 | 3755.12 | 1137.849 | 3 | 110.63 | 7426.749 | 2025-2033 | 292.8 | 2747.06 | 4350.2549 | 0 | 1273.961 | 8672.7759 | 2025-2033 | 2712.95 | 6497.68 | 5325.3939 | 3 | 1377.091 | 15924.8149
2025-2026 | 0 | 767.29 | 252.1 | 0 | 20.5 | 1039.89 | 2025-2026 | 0 | 141.16 | 864.81 | 0 | 474.73 | 1480.7 | 2025-2026 | 0 | 903.95 | 1112.68 | 0 | 495.23 | 2511.86
2027-2033 | 2420.15 | 2987.83 | 885.749 | 3 | 90.13 | 6386.859 | 2027-2033 | 292.8 | 2605.9 | 3485.4449 | 0 | 799.231 | 7192.0759 | 2027-2033 | 2712.95 | 5593.73 | 4212.7139 | 3 | 881.861 | 13412.9549

## FutureTPIT100126NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2026
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
70550 | Create_GP_Solar_POI_Bus | Created GP Solar POI bus. |  | Glen Pine | Explorer | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-01-01 |  | 138 | 0 | 0 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 6802, 6829, 6833 | Y |  |  |  | 72028 | 70550
105622A | Adds type A load records at King |  |  | King |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-01 00:01 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40913 | Y |  |  |  | 109935 | 105622
61406 | Kendall - Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T584 Kendall to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 10.2-mile double-circuit transmission line by replacing the aging conductor. |  | Kendall | Welfare | Planned | 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2027-01-29 |  | 138 | 0 | 10.2 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7152, 7153, 7770 | Y | N |  |  | 78330 | 61406
73025 | New Shaula 345kV Substation | New Shaula 345kV Substation will be looped into the existing Elm Creek to STP circuit 1 transmission line. |  | 5380 | 5133, 5915 | Planned | T-0328 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0970 | 2027-01-29 |  | 345 | 0 | 0 | 0 |  | DeWitt | DeWitt | Tier 4 |  |  |  |  | 5133, 5380, 5915 | Y |  |  |  | 73026 | 73025
99000D | Install (2) 14.4 MVAR distribution cap banks at Twinwood substation. Install (2) 14.4 MVAR distribution cap banks at Fulshear substation. Install (2) 40 MVAR transmission cap bank at Peters substation. | Install (2) 14.4 MVAR distribution cap banks at Twinwood substation. |  | Twinwood |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 |  | 138 | 0 | 0 | 0 | 0,28.8 | Fort Bend |  | Tier 4 |  |  |  |  | 44860 | Y | N |  |  | 109557 | 99000
100305 | Cross Expansion: Modify existing 345 kV Station | Expand Cross station to connect a large load |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Hall |  | Tier 4 |  |  |  |  | 60501, 79002, 79004, 79010 | Y |  |  |  | 100306 | 100305
69902B | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | Upgrade Ckt.71C TH Wharton to Zenith in order to increase thermal limits |  | TH Wharton | Zenith | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44900, 45500 | Y | N |  |  | 98394 | 69902
98593 | Quanah: Rebuild 69 kV Station | Rehab Quanah 69 kV station | Dollars Update | Quanah |  | Planned |  | AEP TNC | William Lovelace myturner@aep.com 918-599-2437 | TA2018027 | 2027-01-31 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6048, 6051, 6057, 69194 | Y |  |  |  | 98594 | 98593
75255F | San Antonio South Reliability RPG Project | Rebuild approximately 3 circuit miles of 138KV Transmission from Leon Creek to South San to meet current CPS Energy and industry standards. The new line will require a rating of 478MVA. |  | 5260 | 5385 | Under Construction |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-01-31 |  | 138 | 0 | 2.89 | 0 |  | Bexar | Bexar | Tier 1 | 22RPG048 | 2022-12-29 |  | 2023-08-31 | 5260, 5385 | Y |  |  |  | 75960 | 75255
90065 | Abilene Northwest to Mulberry Creek: Rebuild 138 kV Line | Rebuild the Abilene Northwest to Mulberry Creek 138 kV line | Company Contact and In-Service Date Update | Abilene Northwest | Mulberry Creek | Planned |  | AEP TNC | Charles Burks myturner@aep.com 918-599-2437 | TP2023881 | 2027-01-31 |  | 138 | 0 | 2.58 | 0 |  | Taylor | Jones | Tier 4 |  |  |  |  | 6228, 6288 | Y | N |  |  | 90066 | 90065
86796 | Buccaneer: Construct New 69 kV Station | Interconnect the Oncor Regency station to the new Buccaneer 69 kV station on the Eden to North Brady 69 kV line between Melvin and North Brady |  | Buccaneer |  | Planned | TP2024028 | AEP TNC | Sally Matthews myturner@aep.com 918-599-2437 |  | 2027-01-31 |  | 69 | 0 | 0 | 0 |  | McCulloch |  | Tier 4 |  |  |  |  | 6006, 6380, 60005 | Y | N |  |  | 86797 | 86796
86800 | Pendulo: Construct New 345 kV Terminal | Interconnect Rubicon Alpha Wind to the Pendulo 345 kV station |  | Pendulo |  | Planned | TP2024057 | ETT/AEP TNC/ETT | Bill Edwards myturner@aep.com 918-599-2437 |  | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60507 | Y | N |  |  | 86801 | 86800
67422F | Greens Bayou to Clinton 138kV Conversion | Remove Wallisville substation from Ckt.10A service… Resulting in Ckt.10A Clinton to Greens Bayou |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40250, 40251, 40352, 40720, 41680, 41681, 41682, 48413 | Y | N |  |  | 87579 | 67422
65837 | New Cachena 345kV Switchyard | The New 345kV Cachena switchyard will be looped into the future 345 kV Elm Creek to New Hickory ckt 1 transmission line . This loop should be rated to match or exceed the existing line rating. |  | 5068 | 5133, 5323 | Under Construction | T-0313 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0966 | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 5068, 5133, 5323 | Y |  |  |  | 65838 | 65837
99000A | Install (2) 14.4 MVAR distribution cap banks at Twinwood substation. Install (2) 14.4 MVAR distribution cap banks at Fulshear substation. Install (2) 40 MVAR transmission cap bank at Peters substation. | Install (2) 14.4 MVAR distribution cap banks at Fulshear substation. |  | Fulshear |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 |  | 138 | 0 | 0 | 0 | 0,28.8 | Fort Bend |  | Tier 4 |  |  |  |  | 44750 | Y | N |  |  | 109554 | 99000
67329 | San Miguel to Cruce 345 kV lines | New San Miguel to Cruce 345 kV double circuit lines |  | San Miguel | Cruce | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-01-31 |  | 345 | 231.12 | 0 | 0 |  | Atascosa | Duval | Tier 1 | 21RPG017 | 2021-09-23 | 2021-12-23 |  |  | Y |  |  |  | 67330 | 67329
73496 | Nelson Sharpe: Construct New 345 kV Terminal | Interconnect Noria Hondo Solar and BESS to the Nelson Sharpe 345 kV station |  | Nelson Sharpe |  | Planned |  | AEP TCC | Curtis Brown deevans@aep.com 918-599-2938 |  | 2027-01-31 |  | 345 | 1 | 0 | 0 |  | Nueces |  | Tier 4 | [5 empty] | Y |  |  |  | 73497 | 73496
109924 | Install a new 138kV switchyard to connect new El Patrimonio Solar PV Generation. The switchyard will be looped into the existing 138 kV Leon Creek to Trumbo transmission line. |  |  | 5333 | 5260, 5429 | Under Construction | S-0973 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0374 | 2027-01-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5260, 5333, 5429 | Y |  |  |  | 109925 | 109924
90059 | Cascabel: Construct New 345 kV Station | Interconnect Moccasin Solar to the new Cascabel 345 kV station on the Clear Crossing to Figaro 345 kV line between Clear Crossing and Kirchoff | In-Service Date Update | Cascabel |  | Planned |  | ETT | George K Githiomi myturner@aep.com 918-599-2437 | TP2024121 | 2027-01-31 |  | 345 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 60124, 60515, 60705 | Y | N |  |  | 90060 | 90059
75255C | San Antonio South Reliability RPG Project | The Leon Creek to Howard Rd circuit should be upgraded to 698 MVA, minimum. |  | 5230 | 5260 | Under Construction |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-01-31 |  | 138 | 0 | 4.87 | 0 |  | Bexar | Bexar | Tier 1 | 22RPG048 | 2022-12-29 |  | 2023-08-31 | 5230, 5260 | Y |  |  |  | 75849 | 75255
67422G | Greens Bayou to Clinton 138kV Conversion | Convert Wallisville substation from Ckt.10A service to 138kV loop service on 138kV TEXWAL to Clinton Ckt.13 to create new Ckt.13 Greens Bayou to TEXWAL to Wallisville to Clinton. |  | Greens Bayou | Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 00:01 |  | 138 | 2.17 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40250, 40350, 41575, 41660, 41680 | Y | N |  |  | 87580 | 67422
78461B | West Columbia to Damon and Needville to Big Creek Ckt.89A Upgrades | Rebuild/reconductor Needville to Big Creek Ckt.89 as a Hardening upgrade. |  | Needville | Big Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-01-31 00:01 |  | 138 | 0 | 5.46 | 0 |  | Brazoria | Brazoria | Tier 4 | 23RPG021 | 2023-08-10 | 2023-08-31 | 2023-08-31 | 42380, 42390 | Y | N |  |  | 78463 | 78461
20TPIT0000 | Parkway Substation T1 Replacement | Replace T1, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2027-02-04 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10679 | 3323
99138 | Establish Herndon 345 kV Switch | Establish Herndon 345 kV Switch |  | Herndon | Herndon | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6407 | 2027-02-15 |  | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3377, 3804, 3805 | Y |  |  |  | 99139 | 99138
65719 | Rebuild/reconductor portions of Ckt.05A Missouri City to Sienna as a Hardening upgrade(24RPG030). | Rebuild and reconductor portion of Missouri City to Sienna Ckt.05A as a Hardening upgrade |  | Missouri City | Sienna | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-02-28 |  | 138 | 0 | 3.8 | 0 |  | Fort Bend | Fort Bend | Tier 4 | 24RPG030 | 2024-09-18 | 2024-10-10 | 2024-10-10 | 48237, 48336 | Y | N |  |  | 90165 | 65719
76242 | Lytle: Construct New 138 kV Terminal | Convert the Big Foot to Lytle 69 kV line to 138 kV and interconnect Rowan Digital to the Lytle 138 kV station | Transmission Status, Transmission Owner and In-Service Date Update | Lytle |  | Under Construction |  | ETT/AEP TCC/ETT | Will Simmons jlsolis@aep.com 361-881-5574 | TP2022155 | 2027-02-28 |  | 138 | 0.1 | 0 | 0 | 0,23 | Medina |  | Tier 4 |  |  |  |  | 8962 | Y |  |  |  | 76243 | 76242
64499 | Hyde Park to Downtown Ckt.32A Upgrades | Upgrade Hyde Park to Downtown Ckt.32A |  | Downtown | Hyde Park | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-02-28 |  | 69 | 0 | 1.2 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47500, 47510, 47570, 47690 | Y | N |  |  | 64500 | 64499
73063 | Big Foot to Lytle: Convert to 138 kV | Convert the Big Foot to Lytle 69 kV line to 138 kV and interconnect Rowan Digital to the Lytle 138 kV station | Transmission Status, In-Service Date and Reactive Capability Added Update | Big Foot | Lytle | Under Construction |  | AEP TCC | Will Simmons jlsolis@aep.com 361-881-5574 | TP2022155 | 2027-02-28 |  | 138 | 0 | 12 | 0 |  | Medina | Frio | Tier 4 |  |  |  |  | 8208, 8216, 8218, 8221, 8223, 8622, 8732, 8962, 58280 | Y |  |  |  | 73064 | 73063
90232B | Facility Ratings Methodology (FRM) Upgrades | Upgrade Ckt.99A PH Robinson to Meadow to increase thermal limits as part of FRM upgrades |  | PH Robinson | Meadow | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-02-28 |  | 345 | 0 | 0 | 0 |  | Galveston | Brazoria | Tier 4 |  |  |  |  | 42000, 43030 | Y | N |  |  | 102825 | 90232
81229 | Upgrade Oaks Auto | Upgrade Oaks Auto to 150MVA |  | Oaks | Oaks | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-03-01 |  | 138 | 0 | 0 | 150 |  |  |  | Tier 4 |  |  |  |  | 5712, 5713 | Y |  |  |  | 81230 | 81229
76816 | Upgrade Loyola Auto | Upgrade Loyola Auto |  | Loyola | Loyola | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5648, 5650 | Y |  |  |  | 76817 | 76816
90476 |  |  |  | Sivells Bend Tap | Sivells Bend | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-01 |  | 69 | 1.5 | 0 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 716, 725, 727 | Y |  |  |  | 90477 | 90476
89961 | RCEC_Horton_Load | Added Horton bus, along with load and branches |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1820, 6869 | Y |  |  |  | 89962 | 89961
99391B | Stanton East - Midland Basin - Spraberry 69 kV Line Conversion to 138 kV | Add part of Permian Basin Reliability Plan Upgrade ID L18. Decommissions Midland Basin, Midland Gulf, Spraberry, Martin, and Stanton East 69 kV Stations. |  | Spraberry | Stanton East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L18_A | 2027-03-01 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 1230, 1231, 1329, 1330, 24968 | Y |  |  |  | 99393 | 99391
104551 | Models ALUVIUM |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-03-01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 39515, 110505, 114841 | Y |  |  |  | 104552 | 104551
112691 | WETT Buck Canyon 345 kV Station for Synchronous Condensers |  |  | Long Draw | Buck Canyon | Under Construction |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2027-03-10 |  | 345 | 0.64 | 0 | 0 |  | Borden | Borden | Tier 3 | 24RPG041 | 2025-01-03 | 2025-01-28 |  | 59900, 59916 | Y |  |  |  | 112692 | 112691
107120 | Pastor Substation Addition | LCRA TSC will install the transmission interconnection facilities including constructing a new 345-kV substation ("Pastor"). |  | Pastor |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-03-11 |  | 345 | 0 | 0 | 0 |  | Concho |  | Tier 3 |  |  |  |  | 6444, 7077, 76009, 76010 | Y |  |  |  | 107121 | 107120
72568 | Friendship to Rutherford Storm Hardening | Rebuild single circuit section of Friendship to Rutherford and reconductor with bundled 795 ACSR Conductor, 440 MVA. Replaces Project ID 61270. |  | Friendship | Rutherford | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-03-15 |  | 138 | 0 | 4.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70507, 70509 | Y | N |  |  | 72569 | 72568
87697 | Bell County - Poage - Seaton 69 kV Line Conversion to 138 kV | Bell County - Poage - Seaton 69 kV Line Conversion to 138 kV |  | Bell County | Seaton | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6367 | 2027-03-15 |  | 138 | 0 | 17.8 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 126, 130, 131, 133, 3598, 3636, 33126 | Y |  |  |  | 87698 | 87697
89952 | RCEC_AllenNorthLoad | Adding Allen North Load Bus, Load and Branch from Allen NLoad to RIDGVIEW_8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-03-15 |  | 138 | 1 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2585, 6857 | Y |  |  |  | 89953 | 89952
80336 |  |  |  | WESTLOOP | BROCK | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 2.23 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 480, 487 | Y |  |  |  | 80337 | 80336 | 2023-NC26
78179 |  |  |  | Ding Dong | Ding Dong | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-15 |  | 138 | 0 | 0 | 0 | 0,12 | Bell | Bell | Tier 4 |  |  |  |  | 115 | Y |  |  |  | 78180 | 78179
91570 |  |  |  | Gustine | Pottsville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-03-19 |  | 69 | 0 | 0 | 0 |  | Hamilton | Hamilton | Tier 4 |  |  |  |  | 178, 272, 273 | Y |  |  |  | 91571 | 91570
89922 | Whaley 345kV Substation Expansion for ROSE/Rock Rose Energy BESS (26INR0201) | Expand Whaley 345kV Substation for ROSE / Rock Rose Energy BESS (26INR0201). Connect generator through one new generator lead. |  | Waterhole |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-03-19 00:01 |  | 345 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 44070, 115083 | Y | N |  |  | 111564 | 89922
102536 | Rebuild/reconductor portions of Ckt.94B King to CHAMON as a Hardening upgrade |  |  | King | CHAMON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-03-30 |  | 138 | 0 | 3.45 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 48186, 111263 | Y | N |  |  | 102537 | 102536
44399 | South Padre Island: Rebuild as GIS station | Rebuild South Padre Island as a GIS | In-Service Date Update | South Padre Island | - | Planned | 948 - 1126 | AEP TCC | Carlo Matheny deevans@aep.com 918-599-2938 | 3712 | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 | 24RPG036 | 2024-11-25 | 2024-12-27 |  | 8335, 8917 | Y | N |  |  | 44400 | 44399
86771 | Scissortail: Construct New 138 kV Station | Interconnect the TNMP Flycatcher station to the new Scissortail 138 kV station on the Saragosa to Solstice 138 kV line between Hoef's Road and Verhalen | Dollars Update | Scissortail |  | Planned | TP2024044 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 6077, 60207, 60808 | Y | N |  |  | 86772 | 86771
80852 | Lolita: Construct New 138 kV Terminal | Interconnect Third Coast BESS to the Lolita 138 kV station | In-Service Date Update | Lolita |  | Planned | TP2023138 | AEP TCC | Sally Matthews deevans@aep.com 918-599-2938 |  | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 8125 | Y | N |  |  | 80853 | 80852
80502 | Lon Hill: Construct New 345 kV Terminal | Interconnect the Tom Cruise load to the Lon Hill 345 kV station | TSP/Company Contact Update | Lon Hill |  | Planned | TP2023885 | AEP TCC | David Baker deevans@aep.com 918-599-2938 |  | 2027-03-31 |  | 345 | 0.1 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8455, 80037 | Y |  |  |  | 80503 | 80502
76914 | Ocelot: Construct New 138 kV Station | Interconnect the Ocelot load to the new Ocelot 138 kV station on the Military Highway to Palo Alto 138 kV line | TSP/Company Contact, In-Service Date and Dollars Update | Ocelot |  | Under Construction | TP2023032 | AEP TCC | Jennifer K Goodin jlsolis@aep.com 361-881-5574 |  | 2027-03-31 |  | 138 | 0.189 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8046, 8047, 8275, 8950 | Y |  |  |  | 76915 | 76914
99917 | Fayetteville AT2 Autotransformer Restoration | LCRA will install, test, and commission a replacement 672 MVA Auto Transformer (AT2) to replace the existing failed unit. SMIT will manufacture and design the replacement 672MVA AT2 which is covered under warranty. The new unit will be identical in ratings but shall include additional improvements to mitigate sound level. The sound mitigation options will cost $550,120 and consist of upgraded core steel grade M075-23 (instead of M105-30), sound panels between tank wall stiffeners, and new low noise fans. The improvements in sound design shall reduce sound levels by ~8dBA. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2027-03-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 99918 | 99917
105602 | MODELS FLYCATCHER |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 6077, 38182 | Y |  |  |  | 105603 | 105602
100478 | Establish Woodfin 138 kV Switch | Establish Woodfin 138 kV Switch |  | Woodfin 345 kV Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3341 | 2027-03-31 | 2025-05-15 | 345 | 0 | 0 | 0 |  | Lamar | Lamar | Tier 4 |  |  |  |  | 1465, 1690, 11683 | Y |  |  |  | 100479 | 100478
109599 | Expand Katy Substation Ckt.09H for 4th Distribution Transformer. |  |  | Katy |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-03-31 |  | 138 | 0 | 0 | 0 |  | Waller |  | Tier 4 |  |  |  |  | 44420 | Y |  |  |  | 109600 | 109599
110102 | This models upgrades required for a proposed load addition | Co-located with battery storage Project. Interconnect into existing Elmaton substation located between South Texas Project and W.A. Parish |  | Elmaton | Elmaton | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-04-01 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 110103 | 110102
76293 | Upgraded Cedvale-MiDiva138KV |  |  | Cerdarvale | Midiva | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-04-01 |  | 138 | 0 | 0.15 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38145, 38152 | Y |  |  |  | 76294 | 76293
86782 | Add Dansk load serving substation | Cuts in new Dansk load serving station on existing Red Bluff to Danevang transmission line |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-04-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  | 2024-02-01 |  | 5546, 5549, 5588 | Y | N |  |  | 86783 | 86782
80404 |  | Reroute East to Rodgers 69kV line to create East to Rayburn 69kV line to accommodate the TXDOT SH6 project. |  | BRYN EAST | RAYBURN | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-04-01 |  | 69 | 1 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32849, 32861, 32874 | Y |  |  |  | 112134 | 80404
92890 | Add Fresa load serving substation |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-04-01 |  | 69 | 0 | 0 | 0 |  | Atascosa | Atascosa | Tier 4 |  |  | 2024-02-01 |  | 5710, 5714, 5733 | Y | N |  |  | 92891 | 92890
91457B | Establish Drane 345 kV Switch | Drane 345 kV Switch Gen Tie |  | Drane 345 kV Switch | Tormes Solar | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6410 | 2027-04-01 |  | 345 | 0.1 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3295, 155125 | Y |  |  |  | 112225 | 91457
73663 | New transformer (T1) at BPUB Waterport Substation | BPUB new load T1 at bus 59450 |  | Waterport Substation (59450) |  | Planned |  | BPUB/BROWNSVILLE PUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2027-04-02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 59450 | Y | N |  |  | 80507 | 73663
112656 | Hagansport 138 kV Switch | Hagansport 138 kV Switch |  | Hagansport Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3333 | 2027-04-04 |  | 138 | 0 | 0 | 0 |  | Franklin | Franklin | Tier 4 |  |  |  |  | 1794, 121485 | Y |  |  |  | 112657 | 112656
104567 | BBEC Sandy Hill T2 | Add Second Transformer at Sandy Hill |  | Sandy Hill |  | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2027-04-11 |  | 138 | 0 | 0 | 0 |  | Washington |  | Tier 4 |  |  |  |  | 7570 | Y |  |  |  | 104568 | 104567
80295 | Add 2nd transformer at Ponder | Add 2nd transformer at Ponder |  | Ponder | Ponder | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-04-15 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 642 | Y |  |  |  | 80296 | 80295
82840 |  |  |  | HYDRA | Hydroponic | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-04-16 |  | 115 | 3 | 0 | 0 |  | Lubbock | Lubbock | Tier 4 |  |  |  |  | 700, 59122 | Y |  |  |  | 82841 | 82840
105135 | Missouri City Low Profile Conversion | Convert Missouri City distribution substation to low-profile. Install Missouri City TR4 at Ckt.02A Blueridge to Missouri City to DEWALT. |  | Missouri City | Blueridge / DEWALT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 44481, 44484, 48163 | Y | N |  |  | 109609 | 105135
103299 | Bluff Creek: Upgrade Relaying and Communication | Upgrade the relaying and communication at the Bluff Creek 138 kV station to support the Buffalo Gap Wind Repower |  | Bluff Creek |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2025822 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  | 2026-02-11 | 2026-02-11 | 2026-02-11 |  | Y | N |  |  | 103300 | 103299
99798 | Citrus City: Install 138 kV circuit breakers | Install breakers at the Citrus City 138 kV station | Transmission Status and In-Service Date Update | Citrus City |  | Under Construction |  | AEP TCC | George Githiomi jlsolis@aep.com 361-881-5574 | TP2023324 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 80123 | Y |  |  |  | 99799 | 99798
90051 | Riley: Construct New 345 kV Terminal | Interconnect the Sabey Data Center load to the existing Riley 345 kV station | In-Service Date Update | Riley |  | Planned |  | AEP TNC/ETT | Jim Nivens myturner@aep.com 918-599-2437 | TP2024133 | 2027-04-30 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6101, 60150, 60151 | Y |  |  |  | 90052 | 90051
98601 | Riley: Expand 345 kV Station | Interconnect Dundee Wind and Felix Solar to the existing Riley 345 kV station | Company Contact Update | Riley |  | Planned |  | ETT/AEP TNC | Jim Nivens myturner@aep.com 918-599-2437 | TP2025169 | 2027-04-30 |  | 345 | 0.25 | 0 | 0 |  | Wilbarger |  | Tier 4 | [5 empty] | Y | N |  |  | 98602 | 98601
84900 | 23RPG032: San Antonio South Reliability II: Rebuild Pawnee to Tango into a double circuit | Rebuild approximately 12 miles of existing horizontal single circuit 345kV transmission infrastructure into new vertical double circuit 345kV transmission infrastructure. |  | 5725 | 8689 | Under Construction |  | CPS/CPS, STEC, AEP | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0401 | 2027-04-30 |  | 345 | 12.2 | 12.2 | 0 |  | Karnes | Bee | Tier 1 | 23RPG032 |  |  | 2024-04-23 | 5725, 8689 | Y |  |  |  | 84901 | 84900
84902 | 23RPG032: San Antonio South Reliability II: Rebuild Spruce to Pawnee into a double circuit | The final upgrades on the STEC side will be completed and the ultimate ratings of the double circuit will be realized. |  | 5400 | 5725 | Under Construction | S-1067 | CPS/CPS, STEC | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0400 | 2027-04-30 |  | 345 | 45.83 | 45.83 | 0 |  | Bexar | Karnes | Tier 1 | 23RPG032 |  |  | 2024-04-23 | 5400, 5725 | Y |  |  |  | 84903 | 84902
90049 | Yellowjacket: Construct New 138 kV Terminal | Interconnect Black and Gold Energy Storage to the Yellowjacket 138 kV station | Dollars Update | Yellowjacket |  | Planned |  | ETT | Christopher Carroll myturner@aep.com 918-599-2437 | TP2024115 | 2027-04-30 |  | 138 | 0.2 | 0 | 0 |  | Menard |  | Tier 4 | [5 empty] | Y |  |  |  | 90050 | 90049
86802 | Saragosa: Construct New 138 kV Terminal | Interconnect Cantaloupe Solar to the Saragosa 138 kV station |  | Saragosa |  | Planned | TP2024067 | AEP TNC | Michael Pitts twang1@aep.com 918-599-2635 |  | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60716 | Y | N |  |  | 86803 | 86802
87019 | Rincon: Upgrade 138 kV Bus | Upgrade the Rincon 138 kV bus | Company Contact Update | Rincon |  | Planned |  | AEP TCC | Jennifer Kates deevans@aep.com 918-599-2938 | TP2024029 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8418, 8437, 8961 | Y |  |  |  | 87020 | 87019
87027 | Black Bayou: Construct New 138 kV Terminal | Interconnect Two Brothers BESS to the Black Bayou 138 kV station | TSP/Company Contact Update | Black Bayou |  | Planned |  | AEP TCC | George Githiomi deevans@aep.com 918-599-2938 | TP2024060 | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 8911 | Y |  |  |  | 87028 | 87027
51005 | Rocksprings to Friess Ranch: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line | In-Service Date Update | Rocksprings | Friess Ranch | Planned | 1044 - 1217 | AEP TCC/AEP TNC, ETT | Greg Crane deevans@aep.com 918-599-2938 | 2792 | 2027-04-30 |  | 69 | 0 | 22.6 | 0 |  | Edwards | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 8238, 60210 | Y | N |  |  | 51006 | 51005
86022 | Jordan 138kV Substation Expansion for Coneflower Storage (23INR0425) | Expand 138kV Jordan substation for Coneflower Storage generator interconnection (23INR0425) |  | Jordan | Coneflower | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-04-30 00:01 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40855, 113981 | Y | N |  |  | 86023 | 86022
76580 | Poblano: Build new 138 kV station | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | In-Service Date Update | Poblano |  | Under Construction |  | AEP TCC | Chris Carroll jlsolis@aep.com 361-881-5574 |  | 2027-04-30 02:00 |  | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 8008, 8009, 8234, 8236 | Y |  |  |  | 76581 | 76580
75255D | San Antonio South Reliability RPG Project | Rebuild/Upgrade 14.9 mile Cagnon to Howard 345kV double circuit transmission line with a minimum rating of 1746 MVA. |  | 5231 | 5056 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 345 | 0 | 14.36 | 0 |  | Bexar | Bexar | Tier 1 | 22RPG048 | 2022-12-29 |  | 2023-08-31 | 5056, 5231 | Y |  |  |  | 75850 | 75255
87508 | RCEC_BranchChanges_Kaufman_Update2 | Modifying branch impedance between ROSHILRC and TALTY_RC |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-05-01 |  | 138 | 0 | 4.51 | 0 |  | Kaufman | Kaufman | Tier 4 |  |  |  |  | 6894, 6902 | Y |  |  |  | 87509 | 87508
87497 | RCEC_BranchChanges_Kaufman__Update1 | Modifying branch impedance between Boze and Scury_RC |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-05-01 |  | 138 | 0 | 3.65 | 0 |  | Kaufman | Kaufman | Tier 4 |  |  |  |  | 6903, 6908 | Y |  |  |  | 87498 | 87497
91463 | New Station tapping Oak Grove to Rand 138kV line. | New Station tapping Oak Grove to Rand 138kV line. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6896, 6906, 6913 | Y |  |  |  | 91464 | 91463
88041 | 24RPG004: Omicron Reliability Project: Rebuild Leon Creek to Pearsal | Rebuild ~1.6 miles of double-ckt from Leon Creek to Pearsall transmission line with normal and emergency ratings of at least 478MVA |  | 5260 | 5335 | Under Construction |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0396 | 2027-05-01 |  | 138 | 0 | 1.67 | 0 |  | Bexar | Bexar | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5260, 5335 | Y |  |  |  | 88042 | 88041
75255E | San Antonio South Reliability RPG Project | Rebuild/Upgrade 14.9 mile Cagnon to Howard 345kV double circuit transmission line with a minimum rating of 1746 MVA. |  | 5231 | 5056 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-01 |  | 345 | 0 | 14.36 | 0 |  | Bexar | Bexar | Tier 1 | 22RPG048 | 2022-12-29 |  | 2023-08-31 | 5056, 5231 | Y |  |  |  | 75851 | 75255
99266 | Big Spring - Steer 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L21B. Upgrade the existing Big Spring - Steer 138-kV line. |  | Big Spring | Steer | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L21_B | 2027-05-01 |  | 138 | 0 | 5.8 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 1322, 10044 | Y |  |  |  | 99267 | 99266
99341 | Horntoad 345 kV Switch | Add Horntoad 345 kV Switch to connect a generator |  | Horntoad | Horntaod | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8911 | 2027-05-06 |  | 345 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 11084, 11098, 18740 | Y |  |  |  | 99342 | 99341
82826 | Sunflower 138 kV Switch | Establish Sunflower 138 kV Switch |  | Sunflower Switch | Sunflower Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6322 | 2027-05-06 |  | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 170, 3592, 3722 | Y |  |  |  | 82827 | 82826
103506 | Add Spadefoot 345 kV Switch | Add Spadefoot 345 kV Switch |  | Spadefoot | Spadefoot | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8925 | 2027-05-13 |  | 345 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 10216, 11010, 11188 | Y |  |  |  | 103507 | 103506
89912 | Olmos to Wilson T297 Transmission Line Rebuild | Rebuild 7.18 miles of 138 kV from 477 conductor wood pole line to 795 drake conductor concrete/steel transmission line |  | Olmos | Wilson | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2027-05-14 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Wilson | Tier 4 |  |  |  |  | 7613, 7615 | Y |  |  |  | 89913 | 89912
100257 | Hill Country Auto #4 will be replaced Summer 2027 to a 10% impedance auto. |  |  | 5211 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0959 | 2027-05-14 |  | 345 | 0 | 0 | 600 |  | Bexar |  | Tier 4 |  |  |  |  | 5208, 5211, 5215 | Y |  |  |  | 100258 | 100257
109898 | Construct New Alamo City 138kV Substation |  |  | 5008 | 5110, 5294 | Planned | S-1074 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0416 | 2027-05-14 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5008, 5110, 5294 | Y |  |  |  | 109899 | 109898
107130 | LCRATSC Highline Substation Addition | LCRA TSC will install the transmission interconnection facilities including constructing a new 345-kV substation ("Highline"). |  | Highline Substation |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-05-14 |  | 345 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  |  | 7034, 7040, 7042 | Y |  |  |  | 107131 | 107130
107128 | Concho River Substation Addition | LCRA TSC will install the transmission interconnection facilities including constructing a new 345-kV substation (Concho River Substation). |  | Concho River |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-05-14 |  | 345 | 0 | 0 | 0 |  | Concho |  | Tier 4 |  |  |  |  | 7077, 76010, 76012 | Y |  |  |  | 107129 | 107128
92625 | Chelsea 138 kV Switch | Chelsea 138 kV Switch |  | Chelsea Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5019 | 2027-05-14 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2534, 2856, 12585 | Y |  |  |  | 92626 | 92625
111798 | Establish Wingate 345 kV Switch | Establish Wingate 345 kV Switch |  | Wingate 345 kV Switch | Wingate 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6464 | 2027-05-15 |  | 345 | 2 | 0 | 0 |  | Nacogdoches | Nacogdoches | Tier 4 |  |  |  |  | 3109, 3117, 3819 | Y |  |  |  | 111799 | 111798
112695 | WETT Pitchfork 345 kV Station for Synchronous Condensers |  |  | Cottonwood | Pitchfork | Under Construction |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2027-05-15 |  | 345 | 0 | 0.21 | 0 |  | Dickens | Dickens | Tier 3 | 25RPG005 | 2025-02-14 | 2025-03-10 |  | 59904, 59908, 59913 | Y |  |  |  | 112696 | 112695
110174 | Lytton Springs - Mendoza Transmission Line Upgrade | Upgrade the 0.6-mile Lytton Springs - Mendoza 138-kV circuit to achieve a minimum 724 MVA emergency rating. This is an LCP Upgrade project to support Batch Zero Base Load. |  | Lytton Springs | Mendoza | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0.6 | 0 |  | Caldwell | Caldwell | Tier 4 | [5 empty] | Y |  |  |  | 110175 | 110174
104623 | Establish Triple Seven 345 kV Switch | Establish Triple Seven 345 kV Switch for Thomas Cameron BESS |  | Triple Seven | Triple Seven | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6405 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Lampasas | Lampasas | Tier 4 |  |  |  |  | 3422, 3424, 3816 | Y |  |  |  | 104624 | 104623
104625 | Establish Rumor 345 kV Switch | Establish Rumor 345 kV Switch for Chisme Solar and Storage |  | Rumor | Rumor | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6406 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Mills | Mills | Tier 4 |  |  |  |  | 1444, 3424, 3821, 155683 | Y |  |  |  | 104626 | 104625
104652 | Establish Bell Springs 138 kV Switch | Establish Bell Springs 138 kV Switch for Vial BESS |  | Bell Springs 138 kV Switch | Bell Springs 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6472 | 2027-05-15 |  | 138 | 1 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 234, 3522, 3817 | Y |  |  |  | 104653 | 104652
104655 | Establish Gamblin 138 kV Switch | Establish Gamblin 138 kV Switch for Willis Storage |  | Gamblin 138 kV Switch | Gamblin 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6456 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Rains | Rains | Tier 4 |  |  |  |  | 1723, 3171, 3818 | Y |  |  |  | 104656 | 104655
104660 | Establish Peach Tree 138 kV Switch | Establish Peach Tree 138 kV Switch for Fairway Storage |  | Peach Tree 138 kV Switch | Peach Tree 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6470 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 196, 3508, 3863 | Y |  |  |  | 104661 | 104660
105008 | Wingjet_Switch_138kV | Establish Wingjet 138 kV Switch |  | Base Camp Switch | Hicks Switch | Planned | M5009 | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1858, 2082, 12065, 12069 | Y |  |  |  | 105009 | 105008
105060 | Union - Deep Creek 138 kV Line Rebuild | Rebuild existing 138 kV line |  | Union | Deep Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8744 | 2027-05-15 |  | 138 | 0 | 9.8 | 0 |  | Scurry | Scurry | Tier 3 | 26RPG014 |  | 2026-04-10 | 2026-05-04 | 1304, 1311 | Y |  |  |  | 105061 | 105060
105063 | Union - Dermott 138 kV Line Rebuild | Rebuild existing 138 kV Line |  | Union | Dermott | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8839 | 2027-05-15 |  | 138 | 0 | 6.4 | 0 |  | Scurry | Scurry | Tier 3 | 26RPG014 | 2026-04-10 | 2026-05-04 |  | 1312, 11306, 18555 | Y |  |  |  | 105064 | 105063
105316 | Ennis West Switch – Sterrett Switch 138kV Line Upgrade | Upgrade Ennis West Switch – Sterrett Switch 138kV Line |  | Ennis West Switch | Sterrett Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4200 | 2027-05-15 |  | 138 | 0 | 21 | 0 |  | Ellis | Ellis | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2241, 2315, 2316, 2319, 2320, 2321, 12320 | Y |  |  |  | 105317 | 105316
105472 | Silverleaf 345kV BUS from TNMP submitted Cowpen/Silverleaf RPG |  |  |  |  | Planned |  | TNMP | Francisco Hernandez francisco.hernandez@tnmp. 281-581-4714 |  | 2027-05-15 |  | 345 | 0 | 0 | 2250 |  | Ward | Ward | Tier 1 | 23RPG013 |  |  |  | 18668, 38143, 38147, 38148, 38149, 38150, 38151, 38153 | Y |  |  |  | 105473 | 105472
91881B | Medallion 138 kV Switch | Reterminates South Curtis 138 kV POD into a new terminal at Medallion 138 kV Switch |  | Midland | Midland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8821 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 10124, 11145, 11179, 11279 | Y |  |  |  | 105664 | 91881
91847C | Hornsby Load Power Transformer Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8186 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7047 | Y |  |  |  | 106814 | 91847
72011B | Tonkawa - Ranger Camp 345 kV Line Rebuild | Tonkawa - Ranger Camp 345 kV Line Rebuild |  | Tonkawa | Ranger Camp | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2027-05-15 |  | 345 | 0 | 21.3 | 0 |  | Mitchell | Scurry | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 11048 | Y |  |  |  | 99962 | 72011
100184 | LyttonSprings_Mendoza_Transmission_Line_Upgrade | LCRA TSC will upgrade T534 Lytton Springs - Mendoza 138-kV transmission line to obtain a higher operational rating. |  | Lytton Springs | Mendoza | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7325, 9075 | Y |  |  |  | 100185 | 100184
100698 | Install a 35.72MVAr Capacitor Bank at Potranco Substation |  |  | 5346 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 | 0,35.72 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5346 | Y |  |  |  | 100699 | 100698
102788 | Overland_Substation_Addition | Construct a new 345-kV Overland substation and cut-in the double circuit Bakersfield Substation to Solstice Substation 345-kV transmission line (T718 and T683) to provide two (2) Points of Interconnection |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 60404, 76002, 76007 | Y |  |  |  | 102789 | 102788
102846 | Longshore 345 kV Switch Rebuild | Longshore 345 kV Switch Rebuild: Cattleman 345 kV Line Re-terminations |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8719 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Mitchell | Howard | Tier 1 | 23RPG034 |  |  |  | 1058, 10053, 18548 | Y |  |  |  | 102847 | 102846
99353 | Oak Spring (fka Roscoe, Plowboy) 345/138 kV Switch | Add Permian Basin Reliability Plan Upgrade ID L25A and L25B. Establish a new Roscoe 345/138-kV substation near the Sweetwater Tap (1341) and install two new 345/138-kV transformers. Loop the existing Sweetwater East - Champion Creek/Bitter Creek - Cattleman 345-kV double-circuit line into Roscoe. |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8613 | 2027-05-15 |  | 345 | 0.1 | 0 | 1200 |  | Nolan | Nolan | Tier 3 |  |  |  |  | 1030, 1341, 1414, 10100, 10101, 10104, 10105, 10163, 11420, 71050 | Y |  |  |  | 103781 | 99353
91626 | Upgrading Buda to Manchaca | Upgrading Buda to Manchaca branch to minimum of 379 MVA. | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70498, 70504 | Y |  |  |  | 91627 | 91626
92347 |  |  |  | New station Walston | Butler | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 104, 105, 3283 | Y |  |  |  | 92348 | 92347
92622 | Elroy_Wolf_Lane_Transmission_Line_Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee |  |  |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6950 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Travis | Tier 4 |  |  |  |  | 7209, 7212 | Y |  |  |  | 92623 | 92622 | 2024-SC20
92627 | Colton_Mendoza_Transmission_Line_Upgrade | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7994 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Travis | Tier 4 |  |  |  |  | 7208, 7325 | Y |  |  |  | 92628 | 92627 | 2024-SC20
92778 | Dunham 345-138 kV Switch and Dunham - Burger Lake 138 kV Line Section | Establish Dunham 345/138 kV Switch and Dunham - Burger Lake 138 kV Line Section |  | Dunham | Dunham | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5007 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Denton | Denton | Tier 3 | 25RPG023 |  |  |  | 1840, 11840, 12068, 15114 | Y |  |  |  | 92779 | 92778
93191 | Bent Tree 138 kV Substation | Establish Bent Tree 138 kV Substation with 55.2 MVAR capacitor bank using 3-18.4 MVAR stages |  | Bent Tree Substation | Bent Tree Substation | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6388 | 2027-05-15 |  | 138 | 0 | 0 | 0 | 0,55.2 | Williamson | Williamson | Tier 4 |  |  |  |  | 3664, 3667, 3764 | Y |  |  |  | 93192 | 93191
98873 | Prong Moss 345-138 kV auto-transformers and 138 kV Switch | Add Permian Basin Reliability Plan Upgrade ID L20A, L20B and L20D Establish a new Prong Moss 345/138-kV substation and install two new 345/138-kV transformers. Loop the existing Elbow - Bulldog 138-kV line into Prong Moss. Loop the existing Hill Crest - McDonald Road 138-kV line into Prong Moss |  | Prong Moss | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8661 | 2027-05-15 |  | 138 | 0 | 0 | 600 |  | Howard | Howard | Tier 3 |  |  |  |  | 1333, 10057, 10066, 10067, 10068, 10080, 11351, 23833 | Y |  |  |  | 98874 | 98873
98875 | Redberry (fka Elbow) - Prong Moss 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L20C Upgrade the existing Redberry (fka Elbow) - Prong Moss 138-kV line |  | Elbow | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L20_C | 2027-05-15 |  | 138 | 0 | 5.782 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 10066, 10080 | Y |  |  |  | 98952 | 98875
99064 | Clarksville 69 kV Capacitor Bank | Clarksville 69 kV Capacitor Bank |  | Clarksville |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5350 | 2027-05-15 |  | 69 | 0 | 0 | 0 | 0,13.8 | Red River |  | Tier 4 |  |  |  |  | 1784 | Y | N |  |  | 99065 | 99064
99321 | Austin Ranch 138kV Capacitor Bank | Austin Ranch 138kV Capacitor Bank |  | Austin Ranch | Austin Ranch | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M3222 | 2027-05-15 |  | 138 | 0 | 0 | 0 | 0,110 | Denton | Denton | Tier 4 |  |  |  |  | 2378 | Y |  |  |  | 99322 | 99321
99367 | China Grove - 900126 (towards Barber Lake) 138 kV Line Section Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22F. Upgrade the existing China Grove - 900126 138-kV line |  | China Grove | Barber Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_F | 2027-05-15 |  | 138 | 0 | 0.1 | 0 |  | Mitchell | Mitchell | Tier 4 |  |  |  |  | 1190, 19521 | Y |  |  |  | 99368 | 99367
99542 | Establish Axtell 345 kV Switch | Establish Axtell 345 kV Switch for Pepper Solar |  | Axtell 345 kV Switch | Axtell 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6469 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3405, 3406, 3806 | Y |  |  |  | 99543 | 99542
99610 | Upgrade Jacksonville Switch 138/69 kV Auto | Upgrade Jacksonville Switch 138/69 kV Auto |  | Jacksonville 69 kV Switch | Jacksonville 69 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6399 | 2027-05-15 |  | 69 | 0 | 0 | 125 |  | Cherokee | Cherokee | Tier 4 |  |  |  |  | 3253, 3254 | Y |  |  |  | 99611 | 99610
99624 | Upgrade Redland Switch - Herty Tap 138 kV Line Section | Upgrade Redland Switch - Herty Tap 138 kV Line Section |  | Redland 138 kV Switch | Herty Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6291 | 2027-05-15 |  | 138 | 0 | 6.9 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3306, 3318 | Y |  |  |  | 99625 | 99624
99685 | Nimbus 345 kV Switch | Establish Nimbus 345 kV Switch |  | Nimbus Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4475 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2217, 2249, 2466 | Y |  |  |  | 99686 | 99685
99687 | Paradise Lake 345 kV Switch | Establish Paradise Lake 345 kV Switch |  | Franklin | Franklin | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3340 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1695, 2449, 11699 | Y |  |  |  | 99696 | 99687
99833 | LCRATSC_Kempner-Lampasas_Transmission_Line_Overhaul | Perform an overhaul on the 7.7 mile T154 Kempner - Lampasas 138-kV transmission line. |  | 7061 Copperas Cove | 7260 Kempner | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-05-15 |  | 138 | 0 | 5.62 | 0 |  | Lampasas | Lampasas | Tier 4 |  |  |  |  | 7064, 7260 | Y |  |  |  | 99834 | 99833
99941 | Kirkland 138 kV Capacitor Bank | Kirkland 138 kV Capacitor Bank |  | Kirkland |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4022 | 2027-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas |  | Tier 4 |  |  |  |  | 2457 | Y | N |  |  | 99942 | 99941
80546C | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild and double-circuit the Georgetown East - Sonterra 138 kV Line Section |  | Georgetown East | Sonterra | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2027-05-15 |  | 138 | 12.9 | 12.9 | 0 |  | Williamson | Williamson | Tier 3 | 24RPG018, 25RPG006 | 2025-02-21 | 2025-03-17 |  | 121, 3688, 7346, 7528 | Y |  |  |  | 87631 | 80546 | 2023-SC17
80546D | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild and double-circuit the Sonterra - Salado 138 kV Line Section. Establish Salado 138 kV Switch and the Salado Switch - Round Rock Switch 138 kV Line |  | Sonterra | Salado Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 3 | 24RPG018, 25RPG006 | 2025-02-21 | 2025-03-17 |  | 121, 3640, 3664, 3668, 3677, 3730, 3764, 3777, 13640, 13641 | Y |  |  |  | 87642 | 80546 | 2023-SC17
87673 | Rebuild the Salado - Bell County 138 kV Line | Rebuild the Salado - Bell County 138 kV Line on new structures |  | Salado | Bell County | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6280 | 2027-05-15 |  | 138 | 7.8 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 132, 3640 | Y |  |  |  | 87674 | 87673
87675 | Rebuild the Bell County - Fryers Creek 138 kV Line | Rebuild the Bell County - Fryers Creek 138 kV Line on new structures |  | Bell County | Fryers Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6336 | 2027-05-15 |  | 138 | 3.2 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 132, 3493 | Y |  |  |  | 87676 | 87675
87707 | Salado 345/138 kV Autotransformer #1 and #2 | Install Salado 345/138 kV Autotransformer #1 and #2 |  | Salado | Salado | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6354, R6202 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3640, 3699, 3745, 3746 | Y |  |  |  | 87708 | 87707
87792 | Establish the Bynum 345 kV Switch | Establish the Bynum 345 kV Switch |  | Bynum Switch | Bynum Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6369 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 1907, 3383, 68090 | Y |  |  |  | 87793 | 87792
85977B | Cedar Hill - Swiftex Transmission Line Upgrade | Corrects topology for Elgin Tap and its associated branches |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 7310, 7319, 7326, 7331, 7674, 13674 | Y |  |  |  | 90939 | 85977 | 2023-SC15
91312 | LCRATSC Austrop - Garfield Transmission Line Upgrade | LCRA TSC will upgrade the Austrop - Zorn 345-kV double-circuit transmission line to achieve a higher operational rating. Coordinating PMCRs include 91312, 104635, and 104639. |  | 7040 | 7048 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8063, PLC-8139, PLC-8140 | 2027-05-15 |  | 345 | 0 | 16.8 | 0 |  | Travis | Bastrop | Tier 1 |  |  |  |  | 7034, 7040, 7042, 7048 | Y |  |  |  | 91313 | 91312 | 2024-SC19
91382 | Henne_Kohlenberg_Transmission_Line_Addition | New Braunfels Utilities will be building a new substation to serve new customer load near Kohlenberg Rd. LCRA TSC will build a new transmission line from Henne Substation to the new Kohlenberg substation and provide transmission service via a new transmission level bus. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.prease@lcra.org 512-578-4514 | PLC-6682 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7174, 7464 | Y |  |  |  | 91383 | 91382
91397 | Wolf_Lane_Wyldwood_Transmission_Line_Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee |  | Wyldwood | Wolf Lane | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6945 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7210, 7212 | Y |  |  |  | 91398 | 91397 | 2024-SC20
91404 | Howard Lane_Wells Branch_TL_Upgrade | LCRA TSC will upgrade T387 Howard Lane - Wells Branch 138-kV transmission line to achieve a higher operational rating. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7655 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7288, 7335 | Y |  |  |  | 91405 | 91404
76728 | Skyview 345/138 kV Switch | Establish Skyview 345/138 kV Switch |  | Skyview |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4350 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 |  |  |  |  | 1922, 1924, 1927, 2119, 2120, 2123, 2124, 2125, 2127, 2128, 2129, 2130, 2131, 2132, 2134, 2231, 2243, 2244, 11938 | Y |  |  |  | 76831 | 76728
78046 | Blue Goose (fka Toyah Creek) 345 kV Switch | Adding Oncor's portion of TNMP Silverleaf and Cowpen 345/138-kV Stations Project (23RPG013) |  | Sand Lake | Solstice | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8715 | 2027-05-15 |  | 345 | 0 | 0 | 0 |  | Ward | Pecos | Tier 1 | 23RPG013 | 2023-05-18 | 2023-06-09 |  | 11098, 18669, 60404 | Y |  |  |  | 78049 | 78046
5526 | Three Creek 345/138 kV Switch (fka Forney) | Rebuild existing 345/138 kV switching |  | Forney |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4114 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Kaufman |  | Tier 1 | 24RPG021 | 2024-07-02 | 2024-07-29 |  | 2432, 2437, 2438, 12438, 22438 | Y | N |  |  | 78356 | 5526
78369 | Rebuild Sam Switch - Venus Switch 345 kV DCKT | Rebuild Sam Switch - Venus Switch 345 kV DCKT |  | Venus | Sam | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | R6293 | 2027-05-15 |  | 345 | 0 | 76 | 0 |  | Ellis | Hill | Tier 1 | 24RPG017 | 2024-06-07 | 2024-07-02 |  | 1906, 1907, 3374, 3389, 68090 | Y |  |  |  | 78370 | 78369
80870 | Bakersfield Dynamic Reactive Substation Upgrade | Add a 350 MVAR synchronous condenser at Bakersfield substation based on ERCOT recommendation. |  | Bakersfield (BAKESW) | Bakersfield (BAKESW) | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | 1030378 | 2027-05-15 |  | 345 | 0 | 0 | 0 | -350350 | Pecos | Pecos | Tier 1 | 23RPG027 | 2023-09-07 | 2023-09-28 |  | 76002, 76101, 76102 | Y |  |  |  | 80926 | 80870 | 2023-FW10
85977A | Cedar Hill - Swiftex Transmission Line Upgrade | Upgrade the existing T367 Cedar Hill - Swiftex 138-kV transmission line from Cedar Hill to Str 181 (Elgin Tap) |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 3674, 7326, 7331 | Y |  |  |  | 85978 | 85977 | 2023-SC15
85979 | Elgin - Elgin Tap Transmission Line Overhaul | Perform an overhaul on the 2.2 mile T728 Elgin (structure #17/7) - Elgin Tap 138-kV transmission line. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-05-15 | 2958101 | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 3674, 7326, 7331, 13674 | Y |  |  |  | 85980 | 85979 | 2023-SC15
71156 | Ennis West Switch-Waxahachie Switch 138 kV Line Rebuild | Rebuild the Ennis West-Waxahachie 138 kV Line |  | Ennis West | Waxahachie | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4200 | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2241, 2321, 12320 | Y |  |  |  | 71160 | 71156
71912A | Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Fort Hood - Killeen Park Street Tap 138 kV Line |  | Killeen Fort Hood | Killeen Park Street Tap | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6245 | 2027-05-15 |  | 138 | 0 | 3.95 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3626, 3627, 3635, 13626 | Y |  |  |  | 71913 | 71912
71912B | Killeen Fort Hood - Killeen Taft 138 kV Line | Rebuild the Killeen Park Street Tap - Killeen Taft 138 kV Line |  | Killeen Park Street Tap | Killeen Taft | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6245 | 2027-05-15 |  | 138 | 0 | 3.95 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3367, 3619, 3621, 3622, 3623, 3635 | Y |  |  |  | 71914 | 71912
99136 | Wilke 138 kV Capacitors | Install 110.4 MVAR capacitor bank at Wilke 138 kV Substation |  | Wilke | Wilke | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6457 | 2027-05-16 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3734 | Y |  |  |  | 99137 | 99136
89889 | Three Creek 138 kV Capacitor Bank | Three Creek 138 kV Capacitor Bank |  | Three Creek |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4114 | 2027-05-16 |  | 138 | 0 | 0 | 0 | 0,110.4 | Kaufman |  | Tier 4 |  |  |  |  | 2438 | Y | N |  |  | 89891 | 89889
87701 | Establish the Roberts 138 kV Switch | Establish the Roberts 138 kV Switch |  | Watercrest | Watercrest | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6353 | 2027-05-16 |  | 138 | 0 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3626, 3627, 3744, 13628 | Y |  |  |  | 87702 | 87701 | 2023-NC57
87695 | Hartrick 138 kV Switch | Establish Hartrick 138 kV Switch |  | Bell County | Bell County | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6363 | 2027-05-16 |  | 138 | 0 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 132, 3493, 3598, 3640 | Y |  |  |  | 87696 | 87695
91461B | Establish Tarantula 345 kV Switch | Establish Tarantula 345 kV Switch Gen Tie |  | Tarantula 345 kV Switch | Tehuacana Creek Solar | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6412 | 2027-05-19 |  | 345 | 0.1 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3344, 155173 | Y |  |  |  | 111951 | 91461
86912 |  |  |  | Gabriel | Schwertner | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-05-21 |  | 138 | 0 | 12.6 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 122, 7346 | Y |  |  |  | 86913 | 86912
70800 | Triada: Build New 345 kV Station | Interconnect Siete Wind to the new Triada 345 kV station on the Avanzada to Lobo 345 kV line | In-Service Date Update | Triada |  | Planned |  | ETT/AEP TCC/ETT | Zachary Lachiusa jlsolis@aep.com 361-881-5574 | TP2022749 | 2027-05-25 12:00 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8718, 80219, 80235 | Y |  |  |  | 70801 | 70800
75835C | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Phase Three of overall approved upgrades. |  | Stone Lake | Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-27 |  | 138 | 0 | 2.45 | 0 |  | Harris | Harris | Tier 3 | 23RPG012 | 2023-05-04 | 2023-05-26 | 2023-05-26 | 44840, 48348 | Y | N |  | Cost included in main entry | 98430 | 75835
78173 |  |  |  | Trimmier | Trimmier | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-05-28 |  | 138 | 0 | 0 | 0 | 0,12 | Bell | Bell | Tier 4 |  |  |  |  | 136 | Y |  |  |  | 78174 | 78173
102777 | Prairieland 138/35kV Distribution Substation | Install Prairieland (PRL) 138/35kV Distribution Substation. Loop on Ckt.66B Hockley to Stone Lake to create new Ckt.66B Hockley to Prairieland to Stone Lake. |  | Prairieland | Hockley/Stone Lake | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45140, 45880 | Y | N |  |  | 102963 | 102777
104643B | Ckt.66B Stone Lake to Hockley Hardening and Waller Cap Bank | Install 20 MVAr transmission cap bank at Waller tapped on Ckt.77B to Hockley. Install 14.4 MVAr cap bank at Waller substation connected to TR3. |  | Waller |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-29 |  | 138 | 0 | 0 | 0 | 0,34.4 | Harris |  | Tier 4 |  |  |  |  | 46560 | Y | N |  |  | 109699 | 104643
104643A | Ckt.66B Stone Lake to Hockley Hardening and Waller Cap Bank | Upgrade Ckt.66B Hockley to (Prairieland) to Stone Lake to increase thermal limits (Hockley equipment upgrade) |  | Stone Lake | Hockley | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-29 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45140, 45880 | Y | N |  |  | 109698 | 104643
72213 | Cedar Hill: Upgrade Relays | Upgrade relays for the Sterling City terminal and Miles terminal at the Cedar Hill 138 kV station | In-Service Date Update | Cedar Hill |  | Planned |  | AEP TNC | Chase Stevens myturner@aep.com 918-599-2437 | TP2022739 | 2027-05-30 |  | 69 | 0 | 0 | 0 |  | Lee |  | Tier 4 |  |  |  |  | 6422, 6423, 6431 | Y | N |  |  | 72214 | 72213
73061 | Falfurrias to King Ranch: 138 kV Line Rebuild | Rehab the Falfurrias to King Ranch 138 kV line | In-Service Date and Dollars Update | Falfurrias | King Ranch | Conceptual |  | AEP TCC | Sally Matthews deevans@aep.com 918-599-2938 |  | 2027-05-30 |  | 138 | 0 | 20.5 | 0 |  | Brooks | Kleberg | Tier 4 |  | 2023-01-24 | 2023-02-24 |  | 8510, 80228 | Y | N |  |  | 73062 | 73061
68254 | Friend Ranch: Build new 138 kV Terminal | Interconnect Blue Sky Solar to the Friend Ranch 138 kV Station | In-Service Date Update | Friend Ranch |  | Planned |  | AEP TNC | Robert Younger myturner@aep.com 918-599-2437 |  | 2027-05-30 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 | [5 empty] | Y | N |  |  | 68255 | 68254
90255B | Jordan / Mont Belvieu Area Improvement Project | Upgrade Ckt.84D Cedar Bayou to CD/HOPSON to increase thermal limits. |  | Cedar Bayou | Cedar Bayou Distribution | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40015, 48065 | Y | N |  |  | 111226 | 90255
90255E | Jordan / Mont Belvieu Area Improvement Project | Apply 110% Emergency rating for the EAGLE customer substation 2000A equipment to increase thermal limits on Ckts 52B / 52C. Upgrade existing 515 / 515 MVA Mont Belvieu relay system limits on Ckt.52C line position. |  | EAGLE | WINFRE/Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40500, 41111 | Y | N |  |  | 111227 | 90255
90255C | Jordan / Mont Belvieu Area Improvement Project | Upgrade Ckt.86A Cedar Bayou to CHEVRON to increase thermal limits. |  | Cedar Bayou | CHEVRON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Harris | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40015, 40300 | Y | N |  |  | 111228 | 90255
99728 | Kilby: Expand 345 kV Station | Interconnect Briggs Solar and BESS to the existing Kilby 345 kV station | Transmission Owner Update | Kilby |  | Planned | TP2025196 | ETT/AEP TNC | Dave Goetz myturner@aep.com 918-599-2437 |  | 2027-05-30 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 | [5 empty] | Y |  |  |  | 99729 | 99728
104643C | Ckt.66B Stone Lake to Hockley Hardening and Waller Cap Bank | Rebuild and reconductor Ckt.66B Hockley to (Prairieland) to Stone Lake as a Hardening upgrade. |  | Stone Lake | Hockley | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-30 |  | 138 | 0 | 5.75 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45140, 45880 | Y | N |  |  | 109700 | 104643
90008 | Tango to Pawnee: Rebuild 345 kV Line | Rebuild the Tango to Pawnee 345 kV line | In-Service Date Update | Tango | Pawnee | Planned |  | AEP TCC/CPS,STEC | Craig Tabor jlsolis@aep.com 361-881-5574 | TP2024118 | 2027-05-30 |  | 345 | 1.2 | 1.2 | 0 |  | Bee | Karnes | Tier 1 | 22RPG048 | 2022-12-29 | 2024-04-10 | 2024-04-23 | 5725, 8689 | Y |  |  |  | 90009 | 90008
76569 | Asherton: Rebuild 138 kV station | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | In-Service Date Update | Asherton |  | Under Construction |  | AEP TCC | Chris Carroll jlsolis@aep.com 361-881-5574 |  | 2027-05-30 02:00 |  | 138 | 0 | 0 | 0 |  | Dimmit |  | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 8005, 8242, 8244, 8280, 8283 | Y |  |  |  | 76570 | 76569
90047 | Big Hill to Rockefeller Storage: Construct New 345 kV Line | Interconnect Rockefeller Storage to the existing Big Hill 345 kV station | Company Contact Update | Big Hill | Rockefeller Storage | Planned |  | AEP TNC | Lance Price twang1@aep.com 918-599-2635 | TP2024144 | 2027-05-31 |  | 345 | 0.2 | 0 | 0 |  | Schleicher | Schleicher | Tier 4 | [5 empty] | Y |  |  |  | 90048 | 90047
99134 | Install generator lead at existing GBY Substation for new interconnection to NRG customer substation. Previously known as GBY-6 |  |  | Greens Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 99135 | 99134
90255A | Jordan / Mont Belvieu Area Improvement Project | Install 120 MVAr cap bank at Mont Belvieu Ckt.84E to WARVUE. |  | Mont Belvieu | WARVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 41111 | Y | N |  |  | 111229 | 90255
110068A | This models the new CEHE Raider Substation and upgrades required for a proposed load addition | Install new 345kV CEHE Raider substation. Loop 345 kV Ckt. 72 Bailey-Cedar Creek line into the new 345 kV Raider substation. Upgrade line relaying on Ckt 72 Cedar Creek-Raider-Bailey. Remove temporary 138 kV service. |  | Raider | Cedar Creek/Bailey | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 43010, 44040, 44090, 44990, 44999, 49924 | Y | N |  |  | 112118 | 110068
112585A | Removal of 140MVAr SVC and facilities from Bellaire and Crosby 138kV substations. | Remove the 140MVAr SVC and facilities from Bellaire 138kV substation |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 | -140,0 | Harris |  | Tier 4 |  |  |  |  | 47016 | Y | N |  |  | 112607 | 112585
112585B | Removal of 140MVAr SVC and facilities from Bellaire and Crosby 138kV substations. | Remove the 140MVAr SVC and facilities from Crosby 138kV substation |  | Crosby |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 | -140,0 | Harris |  | Tier 4 |  |  |  |  | 40390 | Y | N |  |  | 112608 | 112585
82851B | Adds TNMP White Oak Substation | In-service Whiteoak bus and loads, and match CNP ISD date to interconnect together. |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-05-31 | 2027-05-31 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39580 | Y |  |  |  | 113225 | 82851
85987A | Upgrade Ckt.26 STRATT to SINTEK to increase thermal limits. Upgrade Ckt.26F Velasco to CAMDEN to increase thermal limits. | Upgrade Ckt.26D Clute to SINTEK to increase thermal limits. (Expect a full 2-959ACSS reconductor Ckt.26 Clute to SINTEK and a 1-795AAC conductor limitation Ckt.26 STRATT to Clute) |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 5.26 | 0 |  | Brazoria | Brazoria | Tier 3 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 43240, 43300 | Y | N |  |  | 104726 | 85987
73098 | Castroville Cut-in 138 kV | Cut the AEP line from Quihi to CPS Castroville into the newly converted to 138 kV STEC Castroville station. | In-Service Date Update | Quihi | Castroville (CPS) | Planned | TP2022982 | ETT/AEP TCC/ETT | Jeremy Brazeal jlsolis@aep.com 361-881-5574 |  | 2027-05-31 | 2023-05-25 | 138 | 0.4 | 0 | 0 |  | Medina |  | Tier 2 | 22RPG022 | 2023-08-22 | 2023-11-22 |  | 5083, 5804, 8248 | Y |  |  |  | 73099 | 73098
99453E | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.97B King to North Belt to increase thermal limits as part of FRM2 upgrades. |  | King | North Belt | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40900, 46100 | Y | N |  |  | 102618 | 99453
63635 | Tribute: Build 138 kV Station | Build new 138 kV Station on the San Angelo Power to Red Creek 138 kV line | TSP/Company Contact Update | Tribute |  | Planned | 1132 - 1310 | AEP TNC | Robert Younger myturner@aep.com 918-599-2437 | 1877 | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6442, 6473, 60008 | Y | N |  |  | 63636 | 63635
102786 | Fairbanks Substation 4th Transformer | Add 4th Transformer at Fairbanks Substation |  | Fairbanks |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 | 2026-05-04 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 45760 | Y | N |  |  | 105996 | 102786
102542 | Expand Peters 138kV Substation from ring bus to Breaker-and-Half configuration. Connect two circuits from Peters to TRENCH (TRE) customer owned substation |  |  | Peters | TRENCK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 46210, 46220 | Y | N |  |  | 109558 | 102542
104643D | Ckt.66B Stone Lake to Hockley Hardening and Waller Cap Bank | Rebuild and reconductor Ckt.66B Hockley to (Prairieland) to Stone Lake as a Hardening upgrade. |  | Stone Lake | Hockley | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 1.83 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44840, 45140, 45880 | Y | N |  |  | 109701 | 104643
109652A | Flewellen 4th Distribution Transformer Addition and associated upgrades | Install fourth Flewellen distribution transformer TR4. Tap transformer at the Flewellen breaker position on Ckt.09H Flewellen to Katy. |  | Flewellen |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 44230 | Y |  |  |  | 109714 | 109652
109652B | Flewellen 4th Distribution Transformer Addition and associated upgrades | Upgrade Flewellen equipment at the Ckt.73D breaker position to Obrien to increase thermal limits Ckt.73D Obrien to Flewellen. |  | Flewellen |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 44230, 44510 | Y |  |  |  | 109715 | 109652
109652C | Flewellen 4th Distribution Transformer Addition and associated upgrades | Upgrade Ckt.09G Brazos Valley to Fort Bend to increase thermal limits. |  | Flewellen |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 44100, 44280 | Y |  |  |  | 109716 | 109652
109652D | Flewellen 4th Distribution Transformer Addition and associated upgrades | Upgrade Crabb River Road substation equipment to increase thermal limits on Ckt.09F Reading to Crabb River Road. |  | Crabb River Road | Reading | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 44170, 44570 | Y |  |  |  | 109717 | 109652
91713 | Install (1) 40 MVAr switchable cap bank at Hockley substation. |  |  | Hockley |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 | 0,40 | Harris |  | Tier 4 |  |  |  |  | 45880 | Y | N |  |  | 109838 | 91713
99950 | Expansion of Stillman to accomodate interconnection of Resaca Oasis Storage BESS | Interconnection of GINR #27INR0399 Resaca Oasis Storage to Sharyland's Stillman Station. Planned COD is 09/20/2027 | NEW - IA Signed |  |  | Planned |  | SLU | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2027-05-31 |  | 138 | 0.02 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 1571, 1572, 11571 | Y | Y |  |  | 99951 | 99950
75776A | Samaritan 138kV Switching Station | Reconfigure Ckt.26C Angleton to STRATT and loop into new CEHE-owned 138kV Samaritan switching station to create new Ckt.26 Angleton to Samaritan to STRATT. No line upgrades Ckt.26 Angleton to Samaritan to STRATT. |  | Samaritan | Angleton/STRATT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42030, 42110, 43300 | Y | N |  |  | 100295 | 75776
99453U | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.98I Zenith to TH Wharton to increase thermal limits as part of FRM2 upgrades. |  | Zenith | TH Wharton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44900, 45500 | Y | N |  |  | 102613 | 99453
69892 | Deer Park Tap to NOBEL Ckt.21C Upgrades | Upgrade portions of Deer Park Tap to Underwood tap to NOBEL Ckt.21C as a Hardening upgrade |  | Deer Park | NOBEL | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 1.06 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 48084, 48389 | Y | N |  |  | 69893 | 69892
99453Z | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.99 Singleton to Gibbons Creek to increase thermal limits as part of FRM2 upgrades. |  | Singleton | Gibbons Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 967, 44645 | Y | N |  |  | 102620 | 99453
99453S | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.39B Addicks to Obrien to increase thermal limits as part of FRM2 upgrades. |  | Addicks | Obrien | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44500, 45600 | Y | N |  |  | 102624 | 99453
99453N | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.18D DOW to Jones Creek to increase thermal limits as part of FRM2 upgrades. |  | DOW | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 42530 | Y | N |  |  | 102626 | 99453
99453Y | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.75 Singleton to Gibbons Creek to increase thermal limits as part of FRM2 upgrades. |  | Singleton | Gibbons Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 967, 44645 | Y | N |  |  | 102627 | 99453
90242A | Clute to Velasco Ckt.82 Upgrades RPG | Upgrade Ckt.26E SINTEK to CAMDEN to increase thermal limits. |  | SINTEK | CAMDEN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0.62 | 0 |  | Brazoria | Brazoria | Tier 4 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 43240, 43365 | Y | N |  |  | 102648 | 90242
90242B | Clute to Velasco Ckt.82 Upgrades RPG | Upgrade Ckt.82F RIWOOD to CAVERN to BIPORT to increase thermal limits. (Expect partial reconductor to Ckt.86F RIWOOD to CAVERN with 1-795ACSR limiting conductor and full 2-959ACSS reconductor to Ckt.86F CAVERN to BIPORT) |  | CAVERN | Clute/BIPORT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0.31 | 0 |  | Brazoria | Brazoria | Tier 4 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 42190, 43330 | Y | N |  |  | 102649 | 90242
90242C | Clute to Velasco Ckt.82 Upgrades RPG | Upgrade Ckt.82G BIPORT to OYSTER CREEK to increase thermal limits. |  | BIPORT | OYSTER CREEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0.21 | 0 |  | Brazoria | Brazoria | Tier 4 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 42190, 43335 | Y | N |  |  | 102650 | 90242
90242D | Clute to Velasco Ckt.82 Upgrades RPG | Upgrade Ckt.82D GLOBAL to Velasco to increase thermal limits. |  | GLOBAL | Velasco | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 1.06 | 0 |  | Brazoria | Brazoria | Tier 4 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 43345, 43360 | Y | N |  |  | 102651 | 90242
103423 | Bellaire to Ulrich Hardening | Rebuild/reconductor portions of Ckt.35 Bellaire to Ulrich as a Hardening upgrade. |  | Bellaire | Ulrich | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 1.14 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47441, 48511 | Y | N |  |  | 103424 | 103423
100503A | Webster Distribution Upgrades | Remove existing Webster TR3 tap from Ckt.35A Polaris to PH Robinson. Reconfigure tap section and reconnect to another circuit. |  | Polaris | PH Robinson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 42010, 43503, 48288, 48394 | Y | N |  |  | 103956 | 100503
100503D | Webster Distribution Upgrades | Expand Webster with new TR4 distribution transformer and connect to Ckt.95F Polaris to Webster TR4 to Kemah. |  | Webster | Polaris /Kemah | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 43504, 48194, 48289, 48395 | Y | N |  |  | 103957 | 100503
100503C | Webster Distribution Upgrades | Disconnect Webster TR2 from Ckt.92A service and reconnect as Ckt.93A PH Robinson to Webster TR1/TR2 to Webster main bus. |  | Webster | PH Robinson /Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 43501, 43502 | Y | N |  | Cost included in main entry | 103958 | 100503
100503B | Webster Distribution Upgrades | Disconnect Webster TR2 from Ckt.92A service and reconnect at other circuit location (see other entry for TR2). Reconnect Webster TR3 as Ckt.92A El Dorado to WEB-TR3 to Kemah. |  | Webster | El Dorado /Kemah | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 43503, 48393, 48394 | Y | N |  | Cost included in main entry | 103959 | 100503
76369 | BRINE Substation Upgrades | Upgrade substation equipment at BRINE on Ckt.86H DALTON to BRINE to Mont Belvieu. |  | BRINE | DALTON/Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40220, 41111, 41740 | Y | N |  |  | 98395 | 76369
89924 | Weinbrenner 138kV Substation Expansion for SWITCH (SWG)/Elio BESS (25INR0103) | Expand 138kV Weinbrenner substation for SWITCH (SWG)/Elio BESS (25INR0103). Install one new generator lead from Weinbrenner to SWITCH/Elio BESS |  | Weinbrenner |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42990, 114681 | Y | N |  |  | 89925 | 89924
90063 | Elm Creek to Mulberry Creek: Rebuild 138 kV Line | Rebuild the Elm Creek to Mulberry Creek 138 kV line | Dollars Update | Elm Creek | Mulberry Creek | Planned |  | AEP TNC | Charles Burks twang1@aep.com 918-599-2635 | TP2023600 | 2027-05-31 |  | 138 | 0 | 5.7 | 0 |  | Taylor | Jones | Tier 4 |  |  |  |  | 6231, 6255, 60772 | Y | N |  |  | 90064 | 90063
81215 | Oklaunion: Reconfigure 138 kV Station | Reconfigure the Oklaunion 138 kV station from a straight bus to a ring bus | Company Contact and In-Service Date Update | Oklaunion |  | Planned | TP2023876 | AEP TNC/ETT | James Weaver myturner@aep.com 918-599-2437 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6066, 6097, 6098, 6100 | Y | N |  |  | 81216 | 81215
82851A | Adds TNMP White Oak Substation | New TNMP White Oak substation. |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39580 | Y |  |  |  | 82852 | 82851
84892 | 23RPG028: STEC Rio Medina Project: New transmission line between Tally and Ranchtown | Install new 138kV single circuit transmission line from Ranchtown to Talley Road (~12 miles) with normal and emergency ratings of at least 469 MVA. This new transmission line requires a single route CCN. |  | 5422 | 5358 | Planned | S-1061 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0393 | 2027-05-31 |  | 138 | 12 | 0 | 0 |  | Medina | Bexar | Tier 2 | 23RPG028 |  | 2024-02-16 |  | 5358, 5422 | Y |  |  |  | 84893 | 84892
87423 | Reconfigure TNMP Pyote 138kV Substation. |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-05-31 |  | 138 | 0.92 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37990, 38001, 38005 | Y |  |  |  | 87424 | 87423
6072 | Eldorado to Ft. McKavitt: Rebuild 69 kV Line | Rehab Eldorado to Ft. McKavitt 69 kV line | TSP/Company Contact Update | Eldorado Tap | Ft. McKavitt | Planned | 786 - 0971 | AEP TNC | Dave Baker myturner@aep.com 918-599-2437 | 2677 | 2027-05-31 |  | 69 | 0 | 19.41 | 0 |  | Schleicher | Schleicher | Tier 4 |  |  |  |  | 6505, 6506, 6507, 6508 | Y | N |  |  | 13794 | 6072
75776B | Samaritan 138kV Switching Station | Connect Samaritan CEHE substation with two leads to TNMP_White Oak distribution substation. |  | Samaritan | Angleton/Clute | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39580, 42030 | Y | N |  |  | 100296 | 75776
85987B | Upgrade Ckt.26 STRATT to SINTEK to increase thermal limits. Upgrade Ckt.26F Velasco to CAMDEN to increase thermal limits. | Upgrade Ckt.26F CAMDEN to Velasco to increase thermal limits. |  | CAMDEN | Velasco | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-05-31 00:01 |  | 138 | 0 | 0.28 | 0 |  | Brazoria | Brazoria | Tier 3 | 24RPG012 | 2024-04-10 | 2024-05-02 | 2024-05-02 | 43360, 43365 | Y | N |  |  | 104727 | 85987
65906 | To add Jordan Station for GINR 21INR0031 |  |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2027-06-01 |  | 345 | 0 | 0 | 0 |  | Fisher | Fisher | Tier 4 |  |  |  |  | 68001, 68014, 68016 | Y |  |  |  | 65907 | 65906
71319 | Upgrade Pearsall Station | Upgrade Pearsall Station equipment for full auto xfmr ratings. (Upgrade station to breaker and a half is complete) |  | Pearsall | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5893, 5895 | Y |  |  |  | 71320 | 71319
80422 | Add_Triangle_Park_Load | Adding second distribution transformer at Triangle Park |  | Triangle Park |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32854 | Y |  |  |  | 89954 | 80422
61090 | Timbercreek 138kV substation | Change name to Establish 138kV Timbercreek substation with (2) 40MVA transformers and will cut into existing Ckt 948 (Onion Creek to Pilot Knob) |  | Onion Creek | Pilot Knob |  |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9240, 9251, 9259 | Y |  |  |  | 61091 | 61090
93685 | New Transformer will be added at Titan Substation. |  |  | Titan | Titan | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5963 | Y |  |  |  | 93686 | 93685
99369 | Union (fka Sun) - Golden Switch - Dermott 138 kV line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22C. Upgrade the existing Union (fka Sun) - Golden Switch - Dermott 138-kV line |  | Union | Dermott | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_C | 2027-06-01 |  | 138 | 0 | 13.6 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  |  | 1064, 1067, 1311, 1313, 1314, 1315, 11306, 18555 | Y |  |  |  | 105031 | 99369
103793 | BRYN_GreensPrairie_Rebuild | Rebuild Greens Prairie 138-kV Substation to add a second distribution transformer |  | BTU Greens Prairie |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32878 | Y |  |  |  | 103794 | 103793
111357 | LST_OpenSky_Second_Ckt_Loopin | Loop 2nd 345 kV circuit into Open Sky Station to support 25INR0473 project |  | Phantom Hill | Claytonville | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2027-06-01 |  | 345 | 0 | 0 | 0 |  | Jones | Jones | Tier 4 |  |  |  |  | 68001, 68004, 68014 | Y |  |  |  | 111358 | 111357
81299 | Ranger Camp – Prong Moss 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Ranger Camp | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2027-06-01 |  | 345 | 0 | 61.4 | 0 |  | Mitchell | Howard | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 10049, 10057 | Y |  |  |  | 81300 | 81299
110451 | STEC Hammer Load Project Phase 1 | -Construct new transmission line from STEC George West to load site |  | George West |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-06-01 12:15 |  | 138 | 0.2 | 0 | 0 |  | Live Oak | Live Oak | Tier 3 | [5 empty] | Y | N |  |  | 110452 | 110451
102484 |  |  |  | Silver City | Branchville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-06-04 |  | 69 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 61, 63, 65 | Y |  |  |  | 102485 | 102484
112234 | Model Cowpen 138kV Substation |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-06-11 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 | [5 empty] | Y |  |  |  | 112235 | 112234
91062 | Add Boles Station which taps the Quinlan North to Magness line | Adding Boles Bus and updating the line information |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-06-11 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6817, 6823, 6883 | Y |  |  |  | 91063 | 91062
75255B | San Antonio South Reliability RPG Project | Install a 3rd 600MVA 345/138kV autotransformer at Howard. |  | 5231 | 5230 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-06-15 |  | 345 | 0 | 0 | 600 |  | Bexar | Bexar | Tier 1 | 22RPG048 | 2022-12-29 |  | 2023-08-31 | 5230, 5231 | Y |  |  |  | 75848 | 75255
6572 | Ballinger to Eden 69 kV line: Rebuild taps | Rebuild Taps on the Ballinger to Eden 69 kV line | In-Service Date Update | Ballinger | Eden | Planned | 890 - 1068 | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 | 2814 | 2027-06-30 |  | 69 | 0 | 2.8 | 0 |  | Runnels | Concho | Tier 4 |  |  |  |  | 6338, 6369, 6370, 6372, 6376 | Y | N |  |  | 65513 | 6572
81227 | Cattleman – Gascondades 345 kV Reroute | Terminate Morgan Creek – Gascondades 345 kV Line into Cattleman 345 kV Switch |  | Cattleman | Gascondades | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8647 | 2027-06-30 |  | 345 | 0 | 2.5 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 10053, 11032, 11033, 11034, 76030 | Y |  |  |  | 81664 | 81227
80970 | Joule: Construct New 345 kV Station | Interconnect Zeissel Solar and Storage to the new Joule 345 kV station on the Clear Crossing to Coulomb 345 kV line |  | Joule |  | Planned | TP2024020 | ETT/AEP TNC/ETT | Sara Watson twang1@aep.com 918-599-2635 |  | 2027-06-30 |  | 345 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 60094, 60702, 60722 | Y | Y |  |  | 80971 | 80970
73661 | New transformer (T2) at BPUB Palo Alto Substation | Adding load (T2) on bus 5965 Palo Alto. |  | BPUB Palo Alto 5965 |  | Planned |  | BPUB/BROWNSVILLE PUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 5965 | Y | N |  |  | 80506 | 73661
76576 | Asherton to Uvalde: Convert to 138 kV | Convert Asherton to Uvalde 69 kV to 138 kV, rebuild Asherton 138 kV station, build new Poblano 138 kV station | In-Service Date Update | Asherton | Uvalde | Under Construction |  | AEP TCC | Chris Carroll jlsolis@aep.com 361-881-5574 |  | 2027-06-30 |  | 138 | 0 | 59.74 | 0 |  | Dimmit | Uvalde | Tier 3 | 23RPG007 | 2023-04-12 | 2023-05-19 |  | 7867, 8005, 8006, 8007, 8008, 8231, 8242, 8243, 8244, 8280, 8283, 8284, 8672 | Y | N |  |  | 78243 | 76576
90173C | Cedar Bayou 5 Generator Interconnection (23INR0029) | Upgrade Ckt.84K HOPSON to WARVUE to increase thermal limits. |  | HOPSON | WARVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 41690, 41700 | Y | N |  |  | 90209 | 90173
90173B | Cedar Bayou 5 Generator Interconnection (23INR0029) | Upgrade Ckt.97E Cedar Bayou to Chambers to increase thermal limits. |  | Cedar Bayou | Chambers | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-06-30 |  | 345 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40000, 40255 | Y | N |  |  | 90208 | 90173
90055 | Ursidae: Construct New 138 kV Station | Interconnect Northington Solar to the new Ursidae 138 kV station on the El Campo to Victoria 138 kV line between Corichi and El Campo | TSP/Company Contact Update | Ursidae |  | Planned |  | AEP TCC | Curtis Brown deevans@aep.com 918-599-2938 | TP2024151 | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 8099, 8102, 80101 | Y | N |  |  | 90056 | 90055
90033 | Reveille to Navitas: Construct New 138 kV Line | Interconnect the new Navitas load station to the existing Reveille 138 kV station | Dollars Update | Reveille | Navitas | Planned |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 | TP2024157 | 2027-06-30 |  | 138 | 0.15 | 0 | 0 | 0,37.4 | La Salle | La Salle | Tier 4 |  |  |  |  | 8612, 80095 | Y | N |  |  | 90034 | 90033
98612 | Plover: Rebuild 69 kV Station | Rebuild Eldorado Cities Service Co. Tap and rename to Plover | Company Contact Update | Plover |  | Planned | TA2024810 | AEP TNC | David Baker myturner@aep.com 918-599-2437 |  | 2027-06-30 |  | 69 | 0 | 0 | 0 |  | Schleicher |  | Tier 4 |  |  |  |  | 6505, 6506, 6507, 6508, 6693, 60161 | Y | N |  |  | 98613 | 98612
93117 | Gibson: Construct New Distribution Station | Construct new distribution station on the Abilene South to Putnam 138 kV line between Abilene South and Vinson | In-Service Date Update | Gibson |  | Planned |  | AEP TNC | Nelson Carroll myturner@aep.com 918-599-2437 | DR24N0009 | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6260, 60080, 60355 | Y | N |  |  | 93118 | 93117
98616 | Dotterel: Rebuild 69 kV Station | Rebuild Middle Valley REA Tap and rename to Dotterel | Company Contact Update | Dotterel |  | Planned | TA2024810 | AEP TNC | David Baker myturner@aep.com 918-599-2437 |  | 2027-06-30 |  | 69 | 0 | 0 | 0 |  | Schleicher |  | Tier 4 | [5 empty] | Y | N |  |  | 98617 | 98616
90173A | Cedar Bayou 5 Generator Interconnection (23INR0029) | Connect new generation facility to Cedar Bayou 345kV substation with 721 MW combined cycle natural gas-fired units. |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-06-30 |  | 345 | 0 | 0 | 0 |  | Chambers |  | Tier 4 | [5 empty] | Y | N |  |  | 90207 | 90173
109847A | DRILCO Area improvements in support of proposed load addition. | Upgrade Substation equipment at DRILCO and North Belt to increase rating of ckt 67 |  | DRILCO | North Belt | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 109937 | 109847
72884 | Gonzales: Build 69 kV STATCOM | Build new 69 kV STATCOM at the Gonzales 69 kV station |  | Gonzales |  | Planned |  | ETT/AEP TNC/ETT | Bradley Case myturner@aep.com 918-599-2437 | TP2022130 | 2027-06-30 |  | 69 | 0 | 0 | 0 | -25,25 | Presidio |  | Tier 4 |  |  |  |  | 6675, 60203 | Y | N |  |  | 72885 | 72884
48818 | Ballinger: Rebuild 138 kV Station | Rehab the 138/69 kV autotransformer at Ballinger | In-Service Date Update | Ballinger |  | Planned | 1016 - 1194 | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 | 2777 | 2027-06-30 01:00 |  | 138 | 0 | 0 | 130 |  | Runnels |  | Tier 4 |  |  |  |  | 6338, 6340 | Y | N |  |  | 65537 | 48818
5458 | Load serving |  |  | Underwood |  | Planned |  | DME | Zimmerer, Mark J 940-349-7169 |  | 2027-07-01 | 2027-07-01 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 930, 933, 986 | Y | N |  |  | 100508 | 5458
90903 | ALUVIUM gen tie station |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-07-01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39500, 39515, 110505 | Y |  |  |  | 90905 | 90903
76291 | Upgraded Cedarvale–BoneSpringsTap–Fishhook |  |  | Cedarvale to Bone Springs Tap | Bone Springs Tap to Fishhook | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-07-01 |  | 138 | 0 | 12.59 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38145, 38165, 38180 | Y |  |  |  | 76292 | 76291
104871 | Oncor_ME_104871_Healey_345kV_Switch | Establish Healey 345 kV Switch interconnection to Erika Solar |  | Tricorner | Elkton | Planned | M4378 | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 |  | 2027-07-01 |  | 345 | 0 | 0 | 0 |  | Kaufman | Kaufman | Tier 4 |  |  |  |  | 2855, 155832 | Y |  |  |  | 104872 | 104871
105622B | Adds type A load records at King |  |  | King |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-07-01 00:01 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40912, 40913 | Y |  |  |  | 109936 | 105622
85008 | Add Rio Medina - Legend Falls Tline | Add Rio Medina - Legend Falls Tline as part of the Rio Medina RPG Project |  | Rio Medina |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-07-01 12:01 |  | 138 | 5.6 | 0 | 0 |  | Medina | Medina | Tier 2 |  |  | 2024-02-01 |  | 5259, 5805 | Y | N |  |  | 85009 | 85008
91708 | New San Geronimo Substation | adds new San Geronimo station on STEC Rio Medina - CPS Legend Falls line |  | Rio Medina | Legend Falls | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-07-01 12:15 |  | 138 | 0 | 0 | 0 |  | Medina | Medina | Tier 4 |  |  |  |  | 5259, 5805, 5808 | Y | N |  |  | 91709 | 91708
100684 | Install a 50MVAr Capacitor Bank at Grissom Substation |  |  | 5185 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1044 | 2027-07-15 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5185 | Y |  |  |  | 100685 | 100684
112684 | WETT Binturong 345 kV Station for Synchronous Condensers |  |  | Bearkat | Binturong | Under Construction |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2027-07-15 |  | 345 | 0.52 | 0 | 0 |  | Glasscock | Glasscock | Tier 3 | 24RPG041 | 2025-01-03 | 2025-01-28 |  | 59903, 59919 | Y |  |  |  | 112685 | 112684
73436B | Rockhound - Connell 345 kV Double-Circuit Line | Rockhound - Connell 345 kV Double-Circuit Line |  | Rockhound | Connell | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8718, R8807 | 2027-07-24 |  | 345 | 10 | 0 | 1200 |  | Martin | Midland | Tier 1 | 24RPG020 | 2024-05-15 | 2025-11-19 |  | 10062, 10085, 10086, 10087, 10088, 10089, 10221 | Y |  |  |  | 112693 | 73436
87633 | WETT Buck Canyon Synchronous Condenser |  |  | Buck Canyon | Buck Canyon | Under Construction |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2027-07-30 |  | 345 | 0 | 0 | 200 |  | Borden | Borden | Tier 1 | 23RPG026 | 2023-09-01 | 2023-09-28 |  | 59916, 59917, 59918 | Y |  |  |  | 112694 | 87633
72032 | Stewart to West Bay Ckts 48A & 59A Upgrades | Reconductor Ckts. 48A & 59A Stewart to West Bay as a Hardening upgrade. |  | Stewart | West Bay | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-07-31 |  | 138 | 0 | 21.7 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 43290, 43520, 43521 | Y |  |  |  | 72033 | 72032
90057 | Volar: Construct New 138 kV Station | Interconnect XE Flying Kite Solar to the new Volar 138 kV station on the Crystal City to Poblano 138 kV line between La Pryor and Poblano | Company Contact Update | Volar | XE Flying Kite Solar | Planned |  | AEP TCC | Ali Barkat jlsolis@aep.com 361-881-5574 | TP2024145 | 2027-07-31 |  | 138 | 2 | 0 | 0 |  | Zavala | Zavala | Tier 4 |  |  |  |  | 8008, 8009, 8062 | Y |  |  |  | 90058 | 90057
100030 | Beeville: Replace 69 kV Cap Banks | Replace the failed 69 kV capacitor banks at the existing Beeville 69 kV station | Company Contact, In-Service Date and Reactive Capability Update | Beeville |  | Planned |  | AEP TCC | Leigh Kuder deevans@aep.com 918-599-2938 |  | 2027-07-31 |  | 69 | 0 | 0 | 0 | 0,23 | Bee |  | Tier 4 |  |  |  |  | 8198, 8199 | Y |  |  |  | 100031 | 100030
110481 | Ad Hoc TPIT: 150 MVAR Reactive Compensation at Load Site (Nova Prime 138 kV) |  |  | Nova Prime 138 kV | Nova Prime 138 kV | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2027-08-01 |  | 138 | 0 | 0 | 0 | 0,150 | Kent | Kent | Tier 4 | [5 empty] | N |  |  |  | 110482 | 110481
102879 | Add Zella Station for GINR on San Miguel to Fowlerton |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-08-01 |  | 345 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 | [5 empty] | Y | N |  |  | 102880 | 102879
81373 |  |  |  | Longstreet | Buckholts | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-08-13 |  | 138 | 0 | 1.5 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 65, 108, 110, 3749 | Y |  |  |  | 81374 | 81373
91108 | Fisk 345 kV Switch | Construct a new 345 kV Switch. |  | Brown Switch | Central Bluff | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6328 | 2027-08-17 |  | 345 | 0 | 0 | 0 |  | Coleman | Coleman | Tier 4 |  |  |  |  | 1444, 11263, 11406, 184063 | Y |  |  |  | 91109 | 91108
81415 | Hermleigh Synchronous Condenser | Add Hermleigh Syncrhonous Condenser |  | Tonkawa | Tonkawa | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | D20232 | 2027-08-18 |  | 345 | 0 | 0 | 0 | 0,350 | Scurry | Scurry | Tier 1 |  |  |  |  | 1048, 18556, 18557 | Y |  |  |  | 100033 | 81415
75856A | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. Loop into Ckt.96G to create new Ckt.96G PHILIP to ETHYL 138kV to BEARLE. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. |  | ETHYL | South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-08-30 |  | 69 | 0 | 1.33 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41240, 41370 | Y | N |  |  | 90334 | 75856
75856B | Rebuild and reconductor portions of Ckt.28A to prepare for ETHYL 138kV conversion. Loop into Ckt.96G to create new Ckt.96G PHILIP to ETHYL 138kV to BEARLE. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. | Convert ETHYL customer 69kV substation to 138kV. Loop into Ckt.96G to create new Ckt.96G PHILIP to ETHYL 138kV to BEARLE. Retire ETHYL 69kV substation and remaining portions of 69kV Ckt.16D and Ckt.28A. |  | ETHYL | PHILIP / BEARLE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-08-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40550, 41230, 41250, 41270, 41381, 41382 | Y | N |  |  | 90335 | 75856
69471 | Villa Cavazos: Construct New 138 kV Terminal | Interconnect Eval BESS to the Villa Cavazos 138 kV station |  | Villa Cavazos |  | Planned |  | AEP TCC | Bradley Case jlsolis@aep.com 361-881-5574 |  | 2027-08-31 |  | 138 | 0.35 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 80229 | Y |  |  |  | 69472 | 69471
110465 | Add 200 MVar cap bank at Ghost Town |  |  | Ghost Town |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2027-08-31 |  | 345 | 0 | 0 | 0 | 0,200 | Gray |  | Tier 4 | [5 empty] | N | N |  |  | 110466 | 110465
80858 | Sterling City: Upgrade 69 kV Relays | Upgrade relays at the Sterling City 69 kV station on the Angora 69 kV terminal | In-Service Date Update | Sterling City |  | Planned | TP2023887 | AEP TNC | Chase Stevens myturner@aep.com 918-599-2437 |  | 2027-08-31 |  | 69 | 0 | 0 | 0 |  | Sterling |  | Tier 4 |  |  |  |  | 6435, 6484 | Y | N |  |  | 80859 | 80858
110463 | Add 80 MVar of cap banks at Miami Wind |  |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2027-08-31 |  | 345 | 0 | 0 | 0 | 0,80 | Gray |  | Tier 4 | [5 empty] | N | N |  |  | 110464 | 110463
73059 | Barrera: Construct New Distribution Station | Construct new distribution station on the North Laredo Switch to Reveille 138 kV line | In-Service Date Update | Barrera |  | Planned |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 |  | 2027-08-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8108, 8612, 8619, 8627, 8717, 88000 | Y |  |  |  | 73060 | 73059
111270 | Fort Stockton Switch: Construct New 138 kV Terminal | Construct a new 138 kV terminal at Fort Stockton Switch for the new TNMP line to Woodhouse |  | Fort Stockton Switch |  | Planned |  | AEP TNC | Damian P Raab myturner@aep.com 918-599-2437 |  | 2027-08-31 |  | 138 | 0.1 | 0 | 0 |  | Pecos |  | Tier 1 | 23RPG023 | 2023-08-11 | 2024-01-18 | 2024-01-24 |  | Y | N |  |  | 111271 | 111270
110517 | Ad Hoc TPIT: 350 MVAR Reactive Compensation at Mhos 345 kV |  |  | Mhos 345 kV | Mhos 345 kV | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2027-09-01 |  | 345 | 0 | 0 | 0 | 0,350 | Scurry | Scurry | Tier 4 | [5 empty] | N |  |  |  | 110518 | 110517
90111 |  |  |  | Gainesville | Red River | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-01 |  | 69 | 1.2 | 0 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 719, 726, 735 | Y |  |  |  | 90112 | 90111
91611 |  |  |  | Spring | Rector | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-01 |  | 138 | 0 | 11.4 | 0 |  | Cooke | Denton | Tier 4 |  |  |  |  | 672, 680, 684 | Y |  |  |  | 91612 | 91611
102665 | BEPC_TPIT102665_Greyfox |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-03 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 468, 469, 477, 478, 479, 482, 484, 33478 | Y |  |  |  | 102666 | 102665
102765 | BEPC_TPIT102765_Mahogany |  |  | Nolan | Tenaska | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-06 |  | 138 | 0 | 0 | 0 |  | Johnson |  | Tier 4 |  |  |  |  | 370, 401, 410 | Y |  |  |  | 102766 | 102765
113288 | Oncor_MW_113288_Halsell_Switch | Establish Halsell 345 kV Switch (POI for Possum Kingdom Solar and Storage) |  |  |  | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 |  | 2027-09-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1421, 11523, 17029 | Y |  |  |  | 113289 | 113288
66202C | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Grapeland - Crockett 69 kV Line |  | Grapeland | Crockett | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6182 | 2027-09-15 |  | 69 | 0 | 8.5 | 0 |  | Houston | Houston | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3286, 3289 | Y |  |  |  | 99515 | 66202
81440 | Yarbrough - Pecos Trail 138 kV Line Section Rebuild | Rebuild the existing 138 kV line section from Yarbrough - Pecos Trail POD 138 kV. |  | Wolf | Yarbrough | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8527 | 2027-09-15 |  | 138 | 0 | 9.4 | 0 |  | Ward | Ector | Tier 3 | 25RPG008 |  |  |  | 10006, 11117 | Y |  |  |  | 81441 | 81440
66492C | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Jacksboro Amoco - Chico City Services 69 kV Line |  | Jacksboro Amoco | Chico City Services | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M3006 | 2027-09-15 |  | 69 | 0 | 7.3 | 0 |  | Jack | Wise | Tier 4 |  |  |  |  | 1554, 1555, 11557 | Y |  |  |  | 72963 | 66492
66206B | Upgrade Temple - Minerva 69 kV Line | Upgrade Marak - Minerva 69 kV Line |  | Marak | Minerva | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6186 | 2027-09-15 |  | 69 | 13.1 | 0 | 0 |  | Milam | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3684, 3689, 3803 | Y |  |  |  | 68924 | 66206
91496 |  |  |  | Perry | Ben Hur | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-16 |  | 138 | 0 | 0 | 100 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 85, 91, 92, 97, 98, 99, 103, 154691 | Y |  |  |  | 102790 | 91496
73448 | Roma: Build new 138 kV terminal | Bordertown BESS interconnection to Roma Station on Roma Switch to Rio Grande City | In-Service Date Update | Roma |  | Planned |  | AEP TCC | William Lovelace jlsolis@aep.com 361-881-5574 |  | 2027-09-28 |  | 138 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 8795, 8796, 87960 | Y |  |  |  | 73449 | 73448
87635 | WETT Pitchfork Synchronous Condenser |  |  | Pitchfork | Pitchfork | Under Construction |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2027-09-30 |  | 345 | 0 | 0 | 200 |  | Dickens | Dickens | Tier 1 | 23RPG026 | 2023-09-01 | 2023-09-28 |  | 59913, 59914, 59915 | Y |  |  |  | 112697 | 87635
79988 | Lucero: Construct New 345 kV Station | Interconnect SanPat Solar I and SanPat Solar II to the new Lucero 345 kV station on the Angstrom to Naismith 345 kV line | In-Service Date and Dollars should be Update | Lucero |  | Planned | TP2023838 | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 |  | 2027-09-30 |  | 345 | 0.2 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8249, 8659, 80039 | Y | N |  |  | 79989 | 79988
80327 | RTP projects included the addition of 18.4 MVAR capacitor at Whitesboro SW | RTP projects included the addition of 18.4 MVAR capacitor at Whitesboro SW |  | Whitesboro SW | Whitesboro SW | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-09-30 |  | 138 | 0 | 0 | 0 | 0,18.4 | Grayson | Grayson | Tier 4 |  |  |  |  | 718 | Y |  |  |  | 80328 | 80327 | 2023-N14
90040 | Del Sol: Construct New 345 kV Terminal | Interconnect Diamondback Solar to the Del Sol 345 kV station | In-Service Date Update | Del Sol |  | Planned |  | ETT | Jarrod Evans 361-881-5574 | TP2024116 | 2027-09-30 |  | 345 | 0 | 0 | 0 |  | Starr |  | Tier 4 | [5 empty] | Y |  |  |  | 90041 | 90040
104617 | Refugio 138/69 kV:Install Capacitor Bank | Install 17.2 Mvar cap bank at the Refugio 69 kV station | NEW | Refugio |  | Planned | TP2025250 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2027-09-30 |  | 69 | 0 | 0 | 0 | 0,17.2 | Refugio |  | Tier 4 |  |  |  |  | 8833 | Y |  |  |  | 104618 | 104617
76232 | Reconductor Mivida-Coachwhip-Fishhook 2045 ACCC |  |  | Mivida PSSE Bus# 38152 | Fishhook PSSE Bus# 38180 | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-10-01 |  | 138 | 0 | 14.39 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38152, 38170, 38180 | Y |  |  |  | 76233 | 76232
110084A | This models upgrades required for a proposed load addition | Install new 345kV substation. Loop WAP-Whaley Ckt 72. |  | CEHE_Newsub | WAParish/Whaley | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-01 |  | 345 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 1 | [5 empty] | N | N |  | Cost unavailble at this time. | 110503 | 110084
77805 | TNMP Pecos County RPG: Leon Creek to Coyanosa 138kV Double Ckt |  |  | Leon Creek (bus # 38355) | Coyanosa (bus # 38380) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-10-01 |  | 138 | 31.2 | 0.6 | 0 |  | Pecos | Reeves | Tier 1 | 23RPG023 | 2023-08-02 | 2024-02-08 | 2024-03-06 | 6601, 38355, 38380, 38445 | Y |  |  |  | 77806 | 77805
91481 | RCEC_Kemp_RC_station | New TVEC substation by tapping Oncor's line Kemp to Seven Points 138kV. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2726, 3264, 6901 | Y |  |  |  | 91482 | 91481
110090A | This models upgrades required for a proposed load addition | Install 345 kV substation. Loop 345 kV Circuit 97 Jordan – King into the new 345 kV substation. |  | NEWSUB | Jordan/King | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-01 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 110256 | 110090
105600 | MODELS HALITE |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2027-10-01 |  | 138 | 0 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38308, 38332, 38355, 38380 | Y |  |  |  | 105601 | 105600
103867 | BRYN_ShadyLane_Rebuild | Rebuild Shady Lane into a ring bus configuration. MAY NEED TO DELETE THIS LATER IF IT CONFLICTS WITH A FUTURE NOMCR OR NMMS TOPOLOGY. |  | BTU Shady Lane |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2027-10-01 |  | 69 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 | [5 empty] | Y |  |  |  | 103868 | 103867
110079A | This models upgrades required for a proposed load addition near King Substation | Install 345 kV CEHE_NewSub on ckt 75 King to Greens Bayou to create ckt.75 King to CEHE_NewSub to Greens Bayou. Upgrade substation equipment at King and Greens Bayou substations. |  | CEHE_NewSub | King/Greens Bayou | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-01 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 110549 | 110079
87677 | Rebuild the Fryers Creek - Temple 138 kV Line | Rebuild the Fryers Creek - Temple 138 kV Line on new structures |  | Fryers Creek | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6335 | 2027-10-15 |  | 138 | 4.5 | 0 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3415, 3493 | Y |  |  |  | 87678 | 87677
43434 | This is the POI for High Noon Solar and Storage |  |  | Boot Hill | Boot Hill | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-10-21 |  | 138 | 0 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 444, 445, 446 | Y |  |  |  | 43435 | 43434
102632 | BEPC_TPIT102632_BLACKTHORN |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-10-22 |  | 69 | 0 | 0 | 0 |  | Ellis |  | Tier 4 |  |  |  |  | 193, 202, 204, 210, 214, 215, 1571, 1572, 11571 | Y |  |  |  | 102656 | 102632
100537 | Add new Iron Horse station for 25INR0230 |  |  | Limestone | Gibbons Creek | Planned |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2027-10-23 |  | 345 | 0 | 0 | 0 |  | Leon |  | Tier 4 |  |  |  |  | 967, 46020, 79011 | Y | N |  |  | 100538 | 100537
99910 | County Line Substation Addition | Provide transformation service to a BBEC-member load in close proximity of existing Wolf Lane Substation. The 138-kV County Line Substation will be cut-in on T582 Elroy-Wolf Lane transmission line. |  | Elroy | Wolf Lane | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2027-10-24 |  | 138 | 0 | 0 | 0 | 0,62.4 | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7209, 7211, 7212 | Y |  |  |  | 99911 | 99910
87328 | Sunstone: Construct New 138 kV Station | Interconnect the Inner Harbor Desalination Plant load to the new Sunstone 138 kV station on the Morris Street to Nueces Bay 138 kV line | In-Service Date Update | Sunstone |  | Planned |  | AEP TCC/ETT | LaRissa Lundry deevans@aep.com 918-599-2938 | TP2022754 | 2027-10-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8022, 8441, 8733 | Y | Y |  |  | 87329 | 87328
90053 | Dokmai: Construct New 138 kV Station | Interconnect Hyfuels Western Farmland Wind to the new Dokmai 138 kV station on the Cangrejo to Dacosta 138 kV line between Beecher and Cangrejo | TSP/Company Contact and In-Service Date Update | Dokmai |  | Planned |  | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 | TP2024120 | 2027-10-30 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | 8721, 8723, 80090 | Y | N |  |  | 90054 | 90053
91259A | Phelps (PHE) CEHE Station for SKIPJA (SKP) / Skipjack Energy Storage (26INR0189) | Install new Phelps (PHE) 138kV Substation for generator interconnection to SKIPJA (SKP) - Skipjack Energy Storage (26INR0189). Loop into existing Ckt.02B WA Parish to Nash to create new Ckt.02 WA Parish to Phelps to Nash. |  | Phelps | WA Parish /Nash | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42460, 42980, 44010 | Y |  |  |  | 100299 | 91259
81152 | Buford (fka China Grove) to Tributary 138 kV Line Rebuild | Rebuild Buford (fka China Grove) to Tributary 138 kV Line Rebuild |  | Rebuild Buford (fka China Grove) | Tributary Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8656 | 2027-10-31 |  | 138 | 0 | 23.7 | 0 |  | Mitchell | Howard | Tier 3 | 26RPG010 | 2026-03-03 | 2026-03-30 |  | 1318, 10119 | Y |  |  |  | 87650 | 81152
90031 | LLaves: Construct New 345 kV Station | Interconnect Keys Hollow Solar & Storage to the new Llaves 345 kV station on the Coleto Creek to Raptor 345 kV line | TSP/Company Contact Update | Llaves |  | Planned |  | AEP TCC | Michael Pitts deevans@aep.com 918-599-2938 | TP2024167 | 2027-10-31 |  | 345 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 8164, 8673, 80134 | Y | N |  |  | 90032 | 90031
90014 | Palafox: Construct New 138 kV Station | Construct new STEC distribution station on the North Laredo Switch to Reveille 138 kV line between Barrera and North Laredo Switch | TSP/Company Contact Update | Palafox |  | Planned |  | AEP TCC | Jarrod Evans jlsolis@aep.com 361-881-5574 | TP2024132 | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8053, 8717, 8909, 88000 | Y |  |  |  | 90037 | 90014
90134A | Elvis (EVS) 138kV CEHE Substation for ROCK N ROLL Storage (24INR0234) | Install new Elvis (EVS) 138kV CEHE Substation for generator interconnection to Rock N Roll Storage. Connect to Ckt.26B WINMIL to Rosharon to create new Ckt.26 WINMIL to Elvis to Rosharon. |  | Elvis | WINMIL/Rosharon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 44531, 44560, 44600 | Y | N |  |  | 90847 | 90134
89939A | Install new Skains (SKA) 345kV Substation for generator interconnection to Hollow Branch Creek Solar (24INR0422) | Install new Skains (SKA) 345kV Substation for generator interconnection to Hollow Branch Creek Solar (24INR0422). Loop into existing Ckt.74 Singleton to Jewett (ONCOR) to create new Ckt.74 Singleton to Skains to Jewett. |  | Skains | Singleton/Jewett | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Leon | Tier 4 |  |  |  |  | 3391, 44645, 44660 | Y | N |  |  | 90853 | 89939
110166 | County Line Dynamic Reactive Substation Upgrade | Install reactive support at the County Line 138-kV Substation. This is an LCP Upgrade project to support Batch Zero Base Load |  | County Line |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 | 0,62.4 | Bastrop |  | Tier 4 | [5 empty] | Y |  |  |  | 110167 | 110166
100333 | Ghost Town: Add new 345 kV Station | Add new substation to serve 25INR0080 & 26INR0113 |  | Gray | Ghost Town | Planned |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2027-10-31 |  | 345 | 14.3 | 0 | 0 |  | Gray |  | Tier 4 |  |  |  |  | 79000, 79008 | Y |  |  |  | 100334 | 100333
98610 | Riley: Expand 345 kV Station | Interconnect the OPS load to the existing Riley 345 kV station | Company Contact Update | Riley |  | Planned | TP2025219 | ETT/AEP TNC | Jim Nivens myturner@aep.com 918-599-2437 |  | 2027-10-31 |  | 345 | 6 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6111, 60188, 60189 | Y |  |  |  | 98611 | 98610
98802 | Claror: Construct New 345 kV Station | Interconnect Bigway Solar I and II to the new Claror 345 kV station on the Edith Clarke to Cottonwood 345 kV line | In-Service Date Update | Claror |  | Planned |  | ETT | Ali Barkat 918-599-2437 | TP2025175 | 2027-10-31 |  | 345 | 0 | 0 | 0 |  | King |  | Tier 4 |  |  |  |  | 59904, 60154, 60500 | Y |  |  |  | 98803 | 98802
55421 | Ballinger to Concho: Rebuild 69 kV line | Rebuild Ballinger to Concho 69 kV line, install POP switch for Rowena, install CB at Miles, install POP switch for Harriett REA | Transmission Status Update | Ballinger | San Angelo Concho | Under Construction | 1088 - 1271 | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 | 1861 | 2027-10-31 |  | 69 | 0 | 20.45 | 0 |  | Runnels | Tom Green | Tier 3 | 20RPG004 | 2020-04-08 | 2020-04-30 | 2020-05-08 | 6338, 6409, 6410, 6411, 6412, 6413, 6450 | Y | N |  |  | 55422 | 55421
80576 | Chalmers: Construct New Distribution Station | Construct new distribution station on the Lane City to Magill 138 kV line | In-Service Date Update | Chalmers |  | Planned | DP23X0014 | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8111, 8127, 8668, 8750, 89500 | Y |  |  |  | 80577 | 80576
79451A | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. |  | Ancla | Angleton /West Columbia | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 43380, 46630 | Y | N |  |  | 87173 | 79451
73332 | Install Hermann (HER) Distribution Substation | Install Hermann (HER) Distribution Substation. Loop on Ckt.08I to create new Ckt.08 Plaza to Hermann to Grant. |  | Hermann | Plaza/Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45120, 47110, 47350 | Y | N |  |  | 87181 | 73332
90134B | Elvis (EVS) 138kV CEHE Substation for ROCK N ROLL Storage (24INR0234) | Install one generator lead from Elvis (EVS) 138kV CEHE Substation to customer-owned ROCK_N (RNR) for ROCK N ROLL Storage (24INR0234) customer substation. |  | ROCK_N |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | Costs included in main entry | 90848 | 90134
91259B | Phelps (PHE) CEHE Station for SKIPJA (SKP) / Skipjack Energy Storage (26INR0189) | Install one generator lead from Phelps (PHE) 138kV Substation to SKIPJA (SKP) / Skipjack Energy Storage (26INR0189) |  | Phelps | SKIPJA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y |  |  | Costs included in main entry. | 100300 | 91259
89939B | Install new Skains (SKA) 345kV Substation for generator interconnection to Hollow Branch Creek Solar (24INR0422) | Install one generator lead from Skains (SKA) 345kV CEHE Substation to HOLLOW (HLW) / Hollow Branch Solar (24INR0422) |  | Skains | HOLLOW | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-10-31 00:01 |  | 345 | 0 | 0 | 0 |  | Grimes |  | Tier 4 | [5 empty] | Y | N |  | Costs included in main entry | 90854 | 89939
89955 | RCEC_Peerless_Load | Adding Pearless Bus, Load and Branch from Pearless to PRLS_RC |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-11-01 |  | 138 | 1 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1823, 6792 | Y |  |  |  | 89956 | 89955
91135 | Add the Frankston station which taps the Coffee to Blackburn line | Adding the Frankston station, tapping Rayburn's Coffee and Oncor's Blackburn stations. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-11-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 3325, 6855, 6871 | Y |  |  |  | 91136 | 91135
102559 | BEPC_TPIT_KosseSW_Kosse |  |  | 85 | 89 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-11-05 |  | 69 | 0 | 5.5 | 0 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 85, 89 | Y |  |  |  | 102560 | 102559
91986 | Establish the Wofford/Berryville POI | Establish the Wofford/Berryville POI |  | Frankston | Berryville | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6332 | 2027-11-06 |  | 138 | 2 | 0 | 0 |  | Anderson | Anderson | Tier 4 |  |  |  |  | 3782, 3783, 6871 | Y |  |  |  | 91987 | 91986
110156 | CTT Red Rock station/Cross Expansion | Will replace CTT Cross Expansion PMCR. Adds total of 225 MVar cap banks, removes series capacitors. |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2027-11-15 |  | 345 | 0 | 0 | 0 | 0,225 | Hall |  | Tier 4 |  |  |  |  | 23914, 79001, 79002, 79003, 79004, 79010 | N | N |  |  | 110157 | 110156
109706 | Angstrom: Expand 345 kV Station | Interconnect Alila Solar to the Angstrom 345 kV station |  | Ansgtrom | N/A | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2023019 | 2027-11-15 |  | 345 | 1 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 | [5 empty] | Y | N |  |  | 109707 | 109706
75524 | This converts Bell County to Gabriel to 138 KV |  |  | Bell County | Gabriel | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-11-18 |  | 138 | 0 | 0 | 0 |  | Bell | Williamson | Tier 4 |  |  |  |  | 114, 118, 122, 132, 133, 7345, 7346, 13647 | Y |  |  |  | 75525 | 75524
111353 | Oncor_FW_Ward - Barnsley 69 kV Line Conversion to 138 kV | Convert Ward - Barnsley 69 kV Line to 138 kV |  | Ward | Barnsley Sub | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8923 | 2027-11-20 |  | 138 | 0 | 7.5 | 0 |  | Ward | Crane | Tier 4 |  |  |  |  | 1203, 1204, 10250, 11205, 12390 | Y |  |  |  | 111354 | 111353
80340 |  |  |  | Keith Switch | Iola | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-11-26 |  | 138 | 0 | 6.1 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 2, 4 | Y |  |  |  | 80341 | 80340
73067 | Marina: Construct New Station | Construct new network station on the Highway 9 to Morris St and Nueces Bay 138 kV lines | In-Service Date Update | Marina |  | Planned |  | AEP TCC | Marc Wilson deevans@aep.com 918-599-2938 |  | 2027-11-30 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8064, 8441, 8470, 8474, 8620, 8623, 8733 | Y |  |  |  | 73068 | 73067
73423 | Buddy Owens: Build new 138 kV Substation | Build new 138 kV substation on Key Switch to North McAllen 138 kV line | Company Contact and In-Service Date Update | Buddy Owens |  | Conceptual |  | AEP TCC | Victoria Diaz jlsolis@aep.com 361-881-5574 |  | 2027-11-30 |  | 138 | 0 | 0 | 80 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8632, 8773, 8973 | Y |  |  |  | 73424 | 73423
75255A | San Antonio South Reliability RPG Project | Construct a new, 50-mile Howard Rd to San Miguel 345kV double circuit transmission line with a normal and emergency rating of at least 1982 MVA per circuit; this transmission line will require approximately 50 mile of new Right of Way (ROW). |  | 5231 | 5901 | Planned |  | CPS/CPS, STEC | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2027-11-30 |  | 345 | 50 | 0 | 0 |  | Bexar | Atascosa | Tier 1 | 22RPG048 | 2022-12-29 |  | 2023-08-31 | 5231, 5901 | Y |  |  |  | 75256 | 75255
73032 | Mulberry Creek: Rebuild 138 kV Station | Rebuild Mulberry Creek 138 kV station | In-Service Date and Tier Update | Mulberry Creek |  | Planned |  | AEP TNC | Forrest Farson myturner@aep.com 918-599-2437 |  | 2027-11-30 |  | 138 | 0 | 0 | 0 |  | Jones |  | Tier 4 | 25RPG034 | 2025-09-22 | 2025-10-16 |  | 6228, 6231, 6232, 6235, 6287, 6288, 60104, 60772 | Y | N |  |  | 73033 | 73032
71002 | Tidehaven: Construct New Distribution Station | Construct new distribution station on the Blessing to Palacios 69 kV line | In-Service Date Update | Tidehaven |  | Planned | 1028 - 1206 | AEP TCC | Marc Wilson deevans@aep.com 918-599-2938 | 3767 DP21X0007 | 2027-11-30 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8044, 8119, 8121, 8131, 8132, 8133, 8555, 8666 | Y | N |  |  | 71003 | 71002
70710 | Eden to Yellowjacket: Rebuild 69 kV Line | Rehab the Eden to Yellowjacket 69 kV line |  | Eden | Yellowjacket | Planned |  | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 | TA2021119 | 2027-11-30 |  | 69 | 19.5 | 0 | 0 |  | Concho | Menard | Tier 3 |  |  |  |  | 6363, 6372 | Y |  |  |  | 70711 | 70710
45397 | Lion: 138 kV Station & Transmission Line | Lion: 138 kV Station with new line to Stewart Road | In-Service Date Update | Lion | Stewart Road | Planned | 885 - 1063 | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 | 3672 TP2018218 | 2027-11-30 |  | 138 | 2.71 | 0 | 40 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8758, 8951, 8969 | Y | N |  |  | 65528 | 45397
104463 | Wren: Construct New 345 kV Station | Interconnect the Eolic load to the new Wren 345 kV station via (2) new single circuits from Rio Hondo 345 kV station. | TSP/Company Contact Update | Wren |  | Planned | TP2025127 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2027-11-30 |  | 345 | 0 | 0 | 0 | 0,260 | Cameron |  | Tier 4 |  |  |  |  | 8013, 8318, 8704, 8759, 80416 | Y |  |  | This project aligns with Project Set #2 in the approved LLIS# 2215 LCP | 104464 | 104463
103952 | LCRATSC_Shoreline_Substation_Addition | LCRA TSC will construct the new 138-kV Shoreline Substation. Shoreline Substation will provide 138-kV POI to serve Oncor's Rattan Substation load. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-11-30 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 3672, 7288, 7332 | Y |  |  |  | 103953 | 103952
90340B | South Lane City substation expansion for BRP Diran BESS (23INR0137) | Relocate existing Ckt.60D South Lane City to Dyann with expansion of South Lane City to BAAH configuration. |  | South Lane City | Dyann | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-11-30 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 | [5 empty] | Y | N |  | Costs included in main entry | 90342 | 90340
90340A | South Lane City substation expansion for BRP Diran BESS (23INR0137) | Expand South Lane City substation for generator interconnection to BRP Diran BESS. Convert South Lane City to BAAH configuration. |  | South Lane City | BRP Diran BESS | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-11-30 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 90341 | 90340
87629 | WETT Binturong Synchronous Condenser |  |  | Binturong | Binturong | Under Construction |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2027-11-30 |  | 345 | 0 | 0 | 200 |  | Glasscock | Glasscock | Tier 1 | 23RPG026 | 2023-09-01 | 2023-09-28 |  | 59919, 59920, 59921 | Y |  |  |  | 112690 | 87629
99808 | Cesium: Construct New 345 kV Station | Interconnect the Castle load to the new Cesium 345 kV station on the Clear Crossing to Figaro 345 kV line between Figaro and Kirchoff | Transmission Owner Update | Cesium |  | Planned | TP2025188 | ETT/AEP TNC/ETT | Sara Watson myturner@aep.com 918-599-2437 |  | 2027-11-30 |  | 345 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 60198, 60704, 60715 | Y |  |  |  | 99809 | 99808
93048 | Add Liendo load serving substation |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 138 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  | 2024-02-01 |  | 7272, 57668, 57674 | Y | N |  |  | 93049 | 93048
102867 | Upgrade Sargent to Franklins Camp 2025 RTP |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5564, 5566 | Y | N |  |  | 102868 | 102867
99280 | Natural Dam - Beals Creek 138 kV Line | Add Permian Basin Reliability Plan Upgrade ID L21A. Upgrade the existing Natural Dam - Beals Creek 138-kV line |  | Natural Dam | Bealscreek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L21_A | 2027-12-01 |  | 138 | 0 | 7.4 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 11325, 11331, 23836 | Y |  |  |  | 99281 | 99280
99391C | Stanton East - Midland Basin - Spraberry 69 kV Line Conversion to 138 kV | Add part of Permian Basin Reliability Plan Upgrade ID L18. Convert the existing Stanton East - Midland Basin - Spraberry 69-kV line to 138-kV and cut into Rockhound and Stanton East 138 kV Switches to establish the Consavvy - Rockhound - Stanton East 138 kV Line. |  | Consavvy | Stanton East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L18_A | 2027-12-01 |  | 138 | 0 | 26.8 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 1326, 10063, 11134, 11388 | Y |  |  |  | 99394 | 99391
89991 | Upgrade Sargent - Bay City | Upgrade Sargent - Bay City line to 795ACSR. 2024 RTP; 2025 RTP |  | Sargent | Bay City | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 69 | 0 | 18.5 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 5560, 5564 | Y |  |  |  | 89992 | 89991
91553 | RCEC_Union_Valley | 180MW load connecting to a new load serving station from RCEC's Union Valley Station to Blackland RC. This includes an installation of 100 MVAR Capacitor Bank at Union Valley Load Station (6981) |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2027-12-01 |  | 138 | 5.14 | 0 | 0 | 0,100 | Hunt | Hunt | Tier 4 |  |  |  |  | 6860, 6886, 6981 | Y |  |  |  | 91554 | 91553
78044 | Hays Hill (fka Rock Draw) 345 kV Switch | Adding Oncor's portion of TNMP Silverleaf and Cowpen 345/138-kV Stations Project (23RPG013) |  | Sand Lake | North McCamey | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8716 | 2027-12-01 |  | 345 | 0 | 0 | 0 |  | Ward | Upton | Tier 1 | 23RPG013 | 2023-05-18 | 2023-06-09 |  | 11098, 18668, 76000 | Y |  |  |  | 78048 | 78044
80824 | Zenaida: Construct New 138 kV Station | Interconnect Dove Run Solar to the new Zenaida 138 kV station on the Crestonio to Falfurrias 138 kV line | In-Service Date Update | Zenaida |  | Planned | TP2023843 | AEP TCC | Andrew Garlick jlsolis@aep.com 361-881-5574 |  | 2027-12-01 |  | 138 | 0 | 0 | 0 |  | Duval |  | Tier 4 |  |  |  |  | 8510, 8695, 80043 | Y | N |  |  | 80825 | 80824
80830 | Zenaida: Construct New 138 kV Station | Interconnect Sun Cactus Solar to the new Zenaida 138 kV station on the Crestonio to Falfurrias 138 kV line | In-Service Date Update | Zenaida |  | Planned | TP2023851 | AEP TCC | Andrew Garlick jlsolis@aep.com 361-881-5574 |  | 2027-12-01 |  | 138 | 0 | 0 | 0 |  | Duval |  | Tier 4 |  |  |  |  | 80043 | Y | N |  |  | 80831 | 80830
15TPIT0044 | Fowlerton Capacitor | Add 19.2 MVAR capacitor |  | Fowlerton |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 138 | 0 | 0 | 0 | 0,19.2 | La Salle |  | Tier 4 |  |  |  |  | 5705 | Y | N |  |  | 9835 | 2554
110733 | Related_WylieSW_LCP_Upgrades_Walnut_Newman_Line | Related_WylieSW_LCP_Upgrades_Walnut_Newman_Line |  | Walnut | Newman | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | 0 | 2027-12-01 |  | 138 | 0 | 0.56 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 823, 849 | Y |  |  |  | 110734 | 110733
110733 | Related_WylieSW_LCP_Upgrades_Walnut_Newman_Line | Related_WylieSW_LCP_Upgrades_Walnut_Newman_Line |  | Walnut | Newman | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | 0 | 2027-12-01 |  | 138 | 0 | 0.56 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 823, 849 | Y |  |  |  | 110734 | 110733
110749 | Related_WylieSW_LCP_Upgrades_Walnut_Naaman_Line | Related_WylieSW_LCP_Upgrades_Walnut_Naaman_Line |  | Walnut | Naaman | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | 0 | 2027-12-01 |  | 138 | 0 | 2.82 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 823, 825 | Y |  |  |  | 110750 | 110749
110749 | Related_WylieSW_LCP_Upgrades_Walnut_Naaman_Line | Related_WylieSW_LCP_Upgrades_Walnut_Naaman_Line |  | Walnut | Naaman | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | 0 | 2027-12-01 |  | 138 | 0 | 2.82 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 823, 825 | Y |  |  |  | 110750 | 110749
99006 | Establish El Capitan 345/138 kV Switch | Add Permian Basin Reliability Plan Upgrade ID L5A Establish a new Culberson 345/138-kV substation at the existing Culberson Switch and install two new 345/138-kV transformers |  | El Capitan | El Capitan | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L5_A | 2027-12-01 |  | 345 | 0 | 0 | 1200 | -75,0 | Culberson | Culberson | Tier 3 |  |  |  |  | 1096, 1097, 1303, 10179, 10180, 10181, 10182, 10271, 10272, 11082, 11191, 18726 | Y |  |  |  | 111461 | 99006
93088A | Cattleman - Champion Creek/Bitter Creek - Sweetwater East 345-kV Double-Circuit Line Rebuild 345 kV Double-Circuit Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L24A. LCRA and Oncor joint project to add L24A Upgrade the existing Cattleman - Champion Creek/Bitter Creek - Sweetwater East 345-kV double-circuit line |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L24_A | 2027-12-01 |  | 345 | 0 | 83.22 | 0 |  | Nolan | Mitchell | Tier 1 |  | 2023-09-29 |  |  | 10105, 11420, 71050 | Y |  |  |  | 111639 | 93088
110063 | This models upgrades required for a proposed load addition. | Connect customer load at Seabreeze or TANGLEWOOD substations |  | Seabreeze | Seabreeze | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | N | N |  |  | 110064 | 110063
108819 | Upgrades conductor rating |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | PBRP Upgrade L13 | 2027-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1907, 2303, 11908, 38430, 38445 | Y |  |  |  | 108820 | 108819
100680 | Install a 50MVAr Capacitor Bank at Grandview Substation |  |  | 5175 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1047 | 2027-12-01 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5175 | Y |  |  |  | 100681 | 100680
102865 | Add Moursund load serving station |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-01 |  | 138 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5502, 5506, 5508 | Y | N |  |  | 102866 | 102865
99016 | Drill Hole - El Capitan (fka Culberson) 345 kV double-circuit line | Add Permian Basin Reliability Plan Upgrade ID L5D Add a new Drill Hole - El Capitan (fka Culberson) 345-kV double-circuit line |  | Drill Hole | El Capitan | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L5_D | 2027-12-01 |  | 345 | 36.2 | 0 | 0 |  | Culberson | Culberson | Tier 2 |  |  |  |  | 10073, 10180 | Y |  |  |  | 99017 | 99016
104619 | Addition of Blue Moon substation | Addition of Blue Moon substation on 138 kV line connecting Bertram to Burnet. |  |  |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2027-12-06 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7100, 70009, 70520, 70522 | Y |  |  |  | 104620 | 104619
110819 | Add Quantum 345 kV Switch | Connect Quantum 345 kV Switch to the existing Longshore - Cattleman Switch 345 kV line, approximately 13 miles Southwest of Colorado City, TX off of CR 365. | [5 empty] | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2027-12-09 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1058, 10053, 10252, 184451 | Y |  |  |  | 110820 | 110819
100076 | Establish Maxdale 138 kV Switch | Establish Maxdale 138 kV Switch for Cosper Solar |  | Maxdale | Maxdale | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6468 | 2027-12-09 |  | 138 | 0 | 0 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 115, 3785, 3812 | Y |  |  |  | 100077 | 100076
111417 | Littlestar 138 kV Switch | Establish new 138 kV Switch |  | Little Star | Little Star | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8978 | 2027-12-09 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 1102, 1110, 18523 | Y |  |  |  | 111418 | 111417
103919 | Potterson Lake 138 kV Switch | Establish new 138 kV Switch |  | Catclaw | Mudstone | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8908 | 2027-12-09 12:00 |  | 138 | 0 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 10238, 11283, 18664 | Y |  |  |  | 103924 | 103919
70012A | BEPC_NOTPIT_ClarkLakeVoltConv1 |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-12-11 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 510, 513, 515, 1585 | Y |  |  |  | 106697 | 70012
6777 | Establish Division Sub Cedar Hill - Liggett 138 kV Line | Establish Division Sub and Loop Cedar Hill - Liggett 138 kV line in to Great Southwest / General Motors | Project Deferral | Grand Prairie West | Mayfield Tap | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5280 | 2027-12-14 02:01 |  | 138 | 6 | 0 | 0 |  | Dallas | Tarrant | Tier 2 | 23RPG018 |  |  |  | 1919, 2137, 2138, 2140, 2143, 2265, 2274, 12265 | Y | N |  |  | 72912 | 6777
103265 | Hunt Area System Restoration | LCRA TSC will restore and replace flood damaged transmission facilities at the Hunt substation and damaged structures on 138-kV Hunt to Turtle Creek transmission line (T240). |  | Hunt |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Kerr |  | Tier 4 |  |  |  |  | 7142, 7144, 7442, 7750 | Y |  |  |  | 103266 | 103265
100695 | Install a 50MVAr Capacitor Bank at Omicron Substation |  |  | 5326 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1048 | 2027-12-15 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5326 | Y |  |  |  | 100696 | 100695
91945 | Establish Alder 138 kV Switch | Establish Alder 138 kV Switch |  | Alder | Alder | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6329 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Van Zandt | Van Zandt | Tier 2 | 24RPG007 |  |  |  | 3173, 3175, 3184 | Y |  |  |  | 91946 | 91945
92274 | Whitebaker 345kV - Part of Upgrade L13 2024 Permian Basin Study |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | PBRP Upgrade L13 | 2027-12-15 |  | 345 | 22 | 0 | 1500 |  |  |  | Tier 1 |  |  |  |  | 38430, 38435, 38436, 38437, 76002 | Y |  |  |  | 92275 | 92274
92852A | Monticello_Paris_Line_Upgrade | Upgrade Monticello - Woodard 345 kV Line |  | Monticello | Woodard | Planned | R986 | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | R986 | 2027-12-15 |  | 345 | 0 | 33.3 | 0 |  | Titus | Lamar | Tier 1 | 25RPG026 | 2025-07-23 |  |  | 1695, 11699 | Y |  |  |  | 93063 | 92852
93466 | Rebuild Odessa EHV - Reiter 138 kV Double Circuit Line | Add Permian Basin Reliability Plan Upgrade ID L17 Upgrade Odessa - Reiter 138kV double-circuit line |  | Odessa EHV | Reiter | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB L17 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Ector | Ector | Tier 3 |  |  |  |  | 1027, 18545 | Y |  |  |  | 93467 | 93466
98878 | Chalk 69 kV Substation Conversion to 138 kV | Add Permian Basin Reliability Plan Upgrade ID L20G. Construct a new Chalk 138-kV substation at the existing Chalk 69-kV substation and loop the existing McDonald Road – Navigation 138-kV line into Chalk |  | Prong Moss | McDonald Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L20_G | 2027-12-15 |  | 138 | 1 | 0 | 0 |  | Howard | Glasscock | Tier 3 |  |  |  |  | 1333, 1352, 10066, 10112, 10186, 10187, 10188 | Y |  |  |  | 98883 | 98878
99271 | Upgrade Hutto 138 kV terminal equipment | Upgrade Hutto 138 kV terminal equipment for the Hutto - Teal 138 kV Line |  | Hutto | Hutto | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6205 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3362, 3666 | Y |  |  |  | 99272 | 99271
99284 | Ranger Camp Switch - Barber Lake Switch 138 kV Line (East Circuit, 2nd Circuit) | Add Permian Basin Reliability Plan Upgrade ID L22A. Install a new 3.68-mile, 138 kV second conductor on existing double-circuit structures from Ranger Camp to Barber Lake (via Frontier) |  | Ranger Camp | Barber Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_A | 2027-12-15 |  | 138 | 3.68 | 0 | 0 |  | Mitchell | Mitchell | Tier 3 |  |  |  |  | 1189, 10050 | Y |  |  |  | 99285 | 99284
99407 | Sun - Sacroc - Union 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22D. Upgrade the existing Sun - Sacroc - Union 138 kV Line Rebuild. |  | Sun | Union | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_D | 2027-12-15 |  | 138 | 0 | 1.3 | 0 |  | Scurry | Scurry | Tier 4 |  |  |  |  | 1064, 1311 | Y |  |  |  | 99408 | 99407
99479B | Snyder - China Grove 69 kV Loop Converstion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L23. Convert the existing Snyder - Scurry - China Grove and Snyder - Amoco Tap - China Grove 69-kV lines to 138-kV. This converts the Snyder - Ira - China Grove 69 kV Line into 138 kV and reterminates into the new Bluff Creek 138 kV Switch. |  | China Grove | Bluff Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L23 | 2027-12-15 |  | 138 | 0 | 12.8 | 0 |  | Scurry | Scurry | Tier 1 |  |  |  |  | 1318, 1319, 1367, 10191, 10201 | Y |  |  |  | 99481 | 99479
99622 | Establish Pin Oak 345 kV Switch | Establish Pin Oak 345 kV Switch |  | Pin Oak 345 kV Switch | Pin Oak 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6331 | 2027-12-15 |  | 345 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 1 | 25RPG004 |  |  |  | 3133, 3134, 3308, 3344, 3380, 3381, 3390, 3391, 68091 | Y |  |  |  | 99623 | 99622
87705 | Pepper Creek - Temple Elm Creek 138 kV Double-Circuit Line | Reconductor the Pepper Creek - Temple Elm Creek 138 kV Double-Circuit Line |  | Pepper Creek | Temple Elm Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6198 | 2027-12-15 |  | 138 | 0 | 6.2 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3484, 3608, 13608, 13662 | Y |  |  |  | 87706 | 87705 | 2023-NC51
87709 | Belton - Temple 138 kV Line | Rebuild the Belton - Temple 138 kV Line |  | Belton | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6199 | 2027-12-15 |  | 138 | 0 | 9.6 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3415, 3602, 3610, 3611, 3612, 3759 | Y |  |  |  | 87710 | 87709 | 2023-NC5, 2023-NC17
91459 | Establish Mosher 345 kV Switch | Establish Mosher 345 kV Switch for Glasgow Solar |  | Mosher 345 kV Switch | Mosher 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6321 | 2027-12-15 |  | 345 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 2466, 3763, 68091 | Y |  |  |  | 91460 | 91459
71910B | Rebuild the Hillsboro - Elm Mott 69 kV Line | Rebuild the West - Abbott 69 kV Line Section |  | West 69 kV Substation | Abbott 69 kV Substation | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6221 | 2027-12-15 |  | 69 | 0 | 6.3 | 0 |  | McLennan | Hill | Tier 3 |  |  |  |  | 3524, 3525 | Y |  |  |  | 91606 | 71910
81067 | Balch Springs Tap – Balch Springs 138 kV Line Section | Rebuild Balch Springs Tap – Balch Springs 138 kV Line Section |  | Balch Springs Tap | Balch Springs | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4194 | 2027-12-15 |  | 138 | 0 | 3.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2775, 2776, 2777, 2778 | Y |  |  |  | 81068 | 81067
81225 | Cattleman - Range Rider 138 kV Double-Circuit Line | Construct a new 138 kV double-circuit line from Cattleman to Range Rider Switch |  | Cattleman | Range Rider | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8722 | 2027-12-15 |  | 138 | 0 | 6.6 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10054, 10183 | Y |  |  |  | 81226 | 81225
81232 | Cattleman – Bitter Creek/Champion Creek 345 kV Reroute | Terminate Morgan Creek – Bitter Creek/Champion Creek Double-Circuit 345 kV Line into Cattleman 345 kV Switch |  | Cattleman | Bitter Creek and Champion Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8647 | 2027-12-15 |  | 345 | 0 | 5 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 1414, 10053, 10105, 71050 | Y |  |  |  | 81665 | 81232
66190 | East Levee - Industrial Blvd 138 kV DCKT Line | Rebuild East Levee - Industrial Blvd 138 kV DCKT Line |  | East Levee | Industrial | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4213 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2481, 2482, 2874, 2875, 2876, 2974, 2976 | Y |  |  |  | 66191 | 66190
68681 | Lamar Blossom Switch - Clarksville 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Lamar | River Crest | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5325 | 2027-12-15 |  | 69 | 0 | 0 | 0 |  | Lamar | Red River | Tier 4 |  |  |  |  | 1772, 1785, 11784 | Y |  |  |  | 68682 | 68681
68706 | Edgewood Switch – Royse Switch 138 kV Line | Rebuild and convert the Edgewood-Iron Bridge 69 kV to 138 kV operation |  | Edgewood | Able Springs | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3227 | 2027-12-15 |  | 69 | 0 | 0 | 0 |  | Van Zandt | Kaufman | Tier 4 |  |  |  |  | 2471, 2721, 3163, 3165, 3167, 3168, 3169, 3181, 3182, 3185, 3188, 3189, 3191, 3192, 3193, 6920, 6922, 12467, 12469, 12470, 12472, 13188, 13191 | Y |  |  |  | 68707 | 68706
72940 | FireHall_138kV_Switch | Establish Fire Hall 138 kV Switch |  | Roanoke Switch | Kingsridge Switch | Planned | M5352 | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 |  | 2027-12-15 |  | 138 | 3.4 | 0 | 0 |  | Tarrant | Denton | Tier 4 |  |  |  |  | 1846, 2118, 15101 | Y |  |  |  | 72941 | 72940
76654 | Establish Voss Lake 345/138 kV Switch | Establish Voss Lake 345/138 kV Switch |  | Voss Lake | Voss Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6278 | 2027-12-15 |  | 345 | 0 | 5.6 | 600 | 0,110.4 | Milam | Milam | Tier 1 | 25RPG009 | 2025-03-11 |  |  | 3687, 3717, 3740, 3749, 3750, 3751, 3752, 3761, 13429, 13430 | Y |  |  |  | 76655 | 76654 | 2023-SC9
111207 | Stainback 345 kV Capacitor Bank |  |  | Stainback 345 kV Switch |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5017 | 2027-12-15 |  | 345 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2217 | Y |  |  |  | 111208 | 111207
87010 | Establish Drill Hole 345/138 kV Switch | Establish Drill Hole 345/138 kV Switch |  | Drill Hole Switch | Drill Hole Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8725 | 2027-12-15 |  | 345 | 2.32 | 0 | 1200 |  | Culberson | Culberson | Tier 1 | 24RPG010 | 2024-03-18 |  |  | 10073, 10074, 10075, 10076, 10228, 10269, 10270, 11090, 11271, 11272, 18709 | Y |  |  |  | 111488 | 87010
111794 | Establish Iron Crest 138 kV Switch | Establish Iron Crest 138 kV Switch |  | Iron Crest 138 kV Switch | Iron Crest 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6440 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Anderson | Anderson | Tier 4 |  |  |  |  | 3275, 3278, 3279, 3823, 3896, 6935, 6939 | Y |  |  |  | 111795 | 111794
111870 | Establish Caroline Creek 138 kV Switch | Establish Caroline Creek 138 kV Switch |  | Caroline Creek 138 kV Switch | Caroline Creek 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6543 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3394, 3501, 3893 | Y |  |  |  | 111871 | 111870
111952 | Binkley 138 kV Switch | Binkley 138 kV Switch |  | Binkley Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3367 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Grayson | Grayson | Tier 4 |  |  |  |  | 11750, 12677, 12678, 17028 | Y |  |  |  | 111953 | 111952
110583 | Fire Hall 138 kV Capacitor Bank | Establish Fire Hall 138 kV Capacitor Bank |  | Fire Hall |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5352 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 2118 | Y |  |  |  | 112556 | 110583
104821 | Wycliff 138 kV POD | Wycliff 138 kV POD |  | Dallas | Dallas | Planned | M4389 | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 |  | 2027-12-15 | 2025-12-31 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2749, 2815, 3036 | Y |  |  |  | 104822 | 104821
104824 | Wilson 138 kV Switch | Establish Wilson 138 kV Switch |  | Dallas | Dallas | Planned | M4380 | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 |  | 2027-12-15 | 2025-12-31 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 | 25RPG004 |  |  |  | 2126, 2238, 2429, 2942, 2943, 3068, 3074 | Y |  |  |  | 104825 | 104824
104898 | Deaf Smith - Theory 345 kV Double-Circuit and Wallaby - AJ Swope 345 kV Line Cut-In | Construct Deaf Smith - Theory 345 kV Double-Circuit Line and Cut-In Wallaby - AJ Swope 345 kV Line into Deaf Smith 345 kV Switch |  | Deaf Smith | Theory | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8899 | 2027-12-15 |  | 345 | 60 | 0 | 0 |  | Deaf Smith | Deaf Smith | Tier 3 | 26RPG013 | 2026-03-26 | 2026-04-16 |  | 23906, 23908, 23909, 23911 | Y |  |  |  | 104899 | 104898
102849B | Union 138 kV Switch | Cut-in the Deep Creek - Sacroc 138 kV Line Section into Union 138 kV Switch |  | Union | Union | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8608 | 2027-12-15 |  | 138 | 0 | 13.6 | 0 |  | Scurry | Scurry | Tier 4 |  |  |  |  | 1304, 1311, 18555 | Y |  |  |  | 105053 | 102849
105330 | Sterrett Switch – MidlothianTXI 138kV_Line_Upgrade | Upgrade Sterrett Switch – MidlothianTXI 138kV Line Upgrade |  | Sterrett Switch | Midlothian TXI | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4349 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 1 |  | 2025-02-06 | 2026-03-19 |  | 203, 2305, 2307, 2308, 2309, 2317, 12307, 12317 | Y |  |  |  | 105331 | 105330 | 25RPT004
105332 | Watermill Switch – Stainback Switch 345kV Double-Circuit Line Upgrade | Upgrade Watermill Switch – Stainback Switch 345kV Double-Circuit Line Upgrade |  | Watermill Switch | Stainback Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4432 | 2027-12-15 |  | 345 | 0 | 3 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2217, 2427 | Y |  |  |  | 105333 | 105332
105320 | Pebble Creek 138 kV Capacitor | Establish Pebble Creek 138 kV Capacitor |  | Pebble Creek 138 kV Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4434 | 2027-12-15 |  | 138 | 0 | 0 | 0 | 0,220.8 | Ellis |  | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2229 | Y |  |  |  | 105831 | 105320
104506 | Establish Kilough 138 kV POD | Establish Kilough 138 kV POD |  | Kilough 138 kV POD | Kilough 138 kV POD | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6511 | 2027-12-15 |  | 138 | 0 | 0 | 0 |  | Cherokee | Cherokee | Tier 4 |  |  |  |  | 3114, 3325, 3824 | Y |  |  |  | 104507 | 104506
87021 | Construct Drill Hole – Riverton 345 kV Double-Circuit | Construct Drill Hole – Riverton 345 kV Double-Circuit |  | Drill Hole Switch | Riverton Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8748 | 2027-12-16 |  | 345 | 36 | 0 | 0 |  | Culberson | Reeves | Tier 1 | 24RPG010 | 2024-03-18 |  |  | 10073, 11084 | Y |  |  |  | 87022 | 87021
105334 | Watermill Switch – Wilson Switch 138 kV Double-Circuit Line | Upgrade Watermill Switch – Wilson Switch 138 kV Double-Circuit Line |  | Watermill Switch | Wilson Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4363 | 2027-12-16 |  | 138 | 0 | 1.25 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2429, 3074 | Y |  |  |  | 105608 | 105334
105324 | Mesquite Switch – Seagoville Switch 138kV Line | Upgrade Mesquite Switch – Seagoville Switch 138kV Line |  | Mesquite Switch | Seagoville Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4435 | 2027-12-16 |  | 138 | 0 | 8.3 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2434, 2756, 2771, 2775, 2777, 2778, 2779, 3075, 13075 | Y |  |  |  | 105325 | 105324
105314 | Cedar Crest Switch – Wilson Switch 138kV Line | Upgrade Cedar Crest Switch – Wilson Switch 138kV Line |  | Cedar Crest Switch | Wilson Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4406 | 2027-12-16 |  | 138 | 0 | 5.3 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2126, 2238, 2486, 2495, 2985, 2986, 3067, 3072, 3074 | Y |  |  |  | 105315 | 105314
90061 | Poisson: Construct New 345 kV Station | Interconnect Short Creek Solar to the new Poisson 345 kV station on the Riley to Fisher Road 345 kV line |  | Poisson |  | Planned |  | AEP TNC | Melissa Skillman twang1@aep.com 918-599-2635 | TP2024154 | 2027-12-17 |  | 345 | 0 | 0 | 0 |  | Wichita |  | Tier 4 |  |  |  |  | 1425, 6101, 60136 | Y | N |  |  | 91151 | 90061
102661 | BEPC_TPIT102661_Pursley |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2027-12-17 |  | 69 | 0.13 | 0 | 0 |  | Navarro |  | Tier 4 |  |  |  |  | 190, 191, 194, 199 | Y |  |  |  | 102662 | 102661
61449 | Clark Church/Birdhouse (Ottine New) Substation | Build New 138 Substation adjacent to LCRA Birdhouse station; replaces existing Ottine station, add 20MVA |  | Ottine | Ottine | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2027-12-17 |  | 138 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7594 | Y | N |  |  | 61450 | 61449
80850 | Lon Hill to Sinton: Bypass Waterworks 69 kV station | Relocate portion of 69 kV line between Odem and Stevens Tap to bypass Waterworks 69 kV station | In-Service Date Update | Odem | Stevens Tap | Planned | TA2022133 | AEP TCC | Travis Coody deevans@aep.com 918-599-2938 |  | 2027-12-21 |  | 69 | 0 | 0.45 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8810, 8865, 8867 | Y | N |  |  | 80851 | 80850
104595 | BBEC Max Zuehlke substation high side upgrade | Replace 336 (Linnet) conductor, jumpers, and connectors with 959 (Suwannee) conductor, jumpers, and connectors.(MLSE) |  | Max Zuehlke |  | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2027-12-26 |  | 138 | 0 | 0 | 0 |  | Washington |  | Tier 4 |  |  |  |  | 7564, 7565 | Y |  |  |  | 104596 | 104595
104605 | BBEC Lexington to Lyle Wolz Transmission Line Upgrade | Replace 336 (Linnet) conductor with 959 (Suwannee) and replace a limited number of structures to accommodate the new conductor. |  | Lexington | Lyle Wolz | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2027-12-26 |  | 138 | 0 | 12.4 | 0 |  | Lee | Burleson | Tier 4 |  |  |  |  | 7567, 7571 | Y |  |  |  | 104606 | 104605
104601 | BBEC Lyle Wolz to Lyons Transmission Line Upgrade | Replace 336 (Linnet) conductor with 959 (Suwannee) and replace a limited number of structures to accommodate the new conductor. |  | Lyle Wolz | Lyons | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2027-12-26 |  | 138 | 0 | 14 | 0 |  | Burleson | Burleson | Tier 4 |  |  |  |  | 7567, 7573 | Y |  |  |  | 104602 | 104601
105470 | Cowpen 345kV Bus from TNMP submitted Cowpen/Silverleaf RPG |  |  |  |  | Planned |  | TNMP | Francisco Hernandez francisco.hernandez@tnmp. 281-581-4714 |  | 2027-12-27 |  | 345 | 0 | 0 | 1500 |  | Reeves | Reeves | Tier 1 | 23RPG013 |  |  |  | 18669, 38041, 38042, 38043, 38044, 38048 | Y |  |  |  | 105471 | 105470
104599 | BBEC Gay Hill substation high side upgrade | Replace 336 (Linnet) conductor, jumpers, and connectors with 959 (Suwannee) conductor, jumpers, and connectors. (MLSE) |  | Gay Hill |  | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2027-12-28 |  | 138 | 0 | 0 | 0 |  | Washington |  | Tier 4 |  |  |  |  | 7565, 7570, 7572, 7573 | Y |  |  |  | 104600 | 104599
99821 | LCRATSC_Copperas_Cove-Kempner_Transmission_Line_Overhaul | Perform an overhaul on the 5.6 mile T721 Kempner - Copperas Cove 138-kV transmission line. |  | 7323 | 7330 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-12-29 |  | 138 | 0 | 5.62 | 0 |  | Lampasas | Lampasas | Tier 4 |  |  |  |  | 7061, 7260 | Y |  |  |  | 99822 | 99821
85965 | RGEC_Altuda 69-kV In-line_Breaker_Installation | Install 69-kV breaker between Alpine Switch and Persimmon Gap substation at Altuda substation. | Working on engineering design with consultant. | Alpr2A (6665) | PrsmnGap2A (6669) | Planned | 61232 | RGEC | Ruben Quiroga rquiroga@rgec.coop 830-291-4203 |  | 2027-12-30 |  | 69 | 0 | 0 | 0 |  | Brewster | Brewster | Tier 4 | [5 empty] | Y |  |  |  | 85966 | 85965
61232 | RGEC Persimmon Gap Substation 69-kV Transmission Line Extension and Substation Expansion | Extend Alpine-Persimmon Gap 69-kV Transmission Line at Switch# 6669 and Install Circuit Switcher to accommodate new substation power transformer and distribution bays. New power transformer capacity will be 12/16/20 MVA. | Scheduled RUS Construction Work Plan Project | Persimmon Gap | Persimmon Gap | Planned | 85965 | RGEC | Ruben Quiroga rquiroga@rgec.coop 830-291-4203 |  | 2027-12-30 |  | 69 | 0 | 0 | 0 |  | Brewster | Brewster | Tier 4 | [5 empty] | Y | N |  |  | 61233 | 61232
100674 | Install a 50MVAr Capacitor Bank at Crossroads Substation |  |  | 5102 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1050 | 2027-12-30 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5102 | Y |  |  |  | 100675 | 100674
109610B | Missouri City to HO Clarke - Hardening Upgrades | Rebuild/reconductor portions of Ckt.05A HO Clarke to Blue Ridge as a Hardening upgrade. |  | HO Clarke | Missouri City | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-30 |  | 138 | 0 | 1.06 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47170, 48037 | Y | N |  | Cost included in main entry | 109612 | 109610
100672 | Install a 50MVAr Capacitor Bank at Castroville Substation |  |  | 5083 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1045 | 2027-12-30 |  | 138 | 0 | 0 | 0 | 0,50 | Medina |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5083 | Y |  |  |  | 100673 | 100672
107134 | LCRATSC Laurel Substation Addition | LCRA TSC will install the transmission interconnection facilities (TIF) including constructing a new 138-kV substation ("Laurel Substation Addition"). |  | Laurel Substation |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-12-30 |  | 138 | 0 | 0 | 0 |  | Lampasas |  | Tier 4 |  |  |  |  | 7061, 7062, 7260 | Y |  |  |  | 107135 | 107134
102996 | Install new 138kV AERIE (AER) customer substation. Loop on Ckt.02B to create new Ckt.02 Nash to AERIE to Burke. | Install new 138kV AERIE (AER) customer substation. Loop on Ckt.02B to create new Ckt.02 Nash to AERIE to Burke. |  | AERIE | Nash / Burke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42410, 42470, 42980 | Y | N |  |  | 102997 | 102996
103878 | Fairbanks Substation 4th Transformer |  |  | Deihl | White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 4.15 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45730, 46610 | Y | N |  |  | 103879 | 103878
104559B | Hockley Distribution Transformer Addition with Upgrades | Upgrade Ckt.66A Flewellen to Katy tap to increase thermal limits |  | Flewellen | Katy | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Waller | Tier 4 |  |  |  |  | 44230, 48203 | Y | N |  |  | 104561 | 104559
90035 | Edith Clarke: Expand 345 kV Station | Interconnect Seine BESS to the existing Edith Clarke 345 kV station | Project Title, Terminal "to" Location, TSP/Company Contact, In-Service Date and County Location for ending point Update | Edith Clarke |  | Planned |  | AEP TNC | Jarrod Evans myturner@aep.com 918-599-2437 | TP2024193 | 2027-12-31 |  | 345 | 0.3 | 0 | 0 |  | Foard |  | Tier 4 |  |  |  |  | 60500 | Y | N |  |  | 91677 | 90035
92280 | Alamo St - Bottlebrush 138kV - Upgrade L12 2024 Permian Basin Study | Alamo St - Bottlebrush 138kV - Upgrade L12 2024 Permian Basin Study |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | PBRP Upgrade L12 | 2027-12-31 |  | 138 | 31.75 | 28.7 | 0 |  | Pecos | Pecos | Tier 2 |  |  |  |  | 38310, 38320, 38331, 38360, 38365, 38381, 38383, 38439 | Y |  |  |  | 92281 | 92280
78404 | LCRATSC Bastrop Colony Substation Addition (formerly Bastrop Village) |  |  | Bastrop Colony |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8067 | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7555, 7556, 7561 | Y | N |  |  | 92458 | 78404
98994B | Replace Harrisburg with new Manchester Subsation | Upgrade existing Ckt.70B GOODYEAR to Magnolia Park to increase thermal limits. Loop new Manchester distribution substation on existing Ckt.70B to create new Ckt.70B GOODYEAR to Manchester to Magnolia Park. No Transmission Breakers expected |  | Manchester | GOODYEAR/Magnolia Park | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40650, 44930, 47700, 740800 | Y | N |  | Cost included in main entry | 98996 | 98994
99796 | Ganado: Expand 138 kV Station | Interconnect Dios BESS to the existing Ganado 138 kV station | Company Contact Update | Ganado |  | Planned |  | AEP TCC | Remington Hajdik deevans@aep.com 918-599-2938 | TP2025221 | 2027-12-31 |  | 138 | 0.1 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 8117 | Y |  |  |  | 99797 | 99796
99919 | Georgetown Power Transformer Upgrade | Upgrade the Georgetown 138-kV transmission bus to a four circuit breaker improved bus with Gas Insulated Switchgear (GIS). The new switchgear and all 138-kV series equipment should be rated at 4000 continuous amps. Upgrade Georgetown T1 and Georgetown T2. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7343, 7366 | Y |  |  |  | 99920 | 99919
99924 | Pine Path Substation Addition | Construct a new 138-kV substation to cut-in on T670 to serve new customer load in the BBEC service territory. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  |  | 7310, 7311, 7324 | Y |  |  |  | 99937 | 99924
67427B | MINING 138kV Conversion and BENTON customer substation removal(24RPG033). | Install new customer-owned MINING 138kV substation. Loop substation on existing Ckt.06G to create new Ckt.06 Pasadena to College tap to MINING to Jefferson. |  | MINING-138 | College /Jefferson | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | 24RPG033 | 2024-11-07 | 2024-12-02 | 2024-12-02 | 40470, 41030, 41061, 41071, 41240, 41380, 48171, 48177, 48274, 111102 | Y | N |  | Costs included in main entry | 91249 | 67427
67427A | MINING 138kV Conversion and BENTON customer substation removal(24RPG033). | Rebuild/Repurpose existing 69kV Ckt.16C MINING Switchrack to MINING tap section. Retire MINING Switchrack from Ckt.16C to create new Ckt.16C Deepwater to South Channel. Remove customer-owned BENTON substation from CEHE service. Retire MINING 69kV substation. |  | Deepwater | South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | 24RPG033 | 2024-11-07 | 2024-12-02 | 2024-12-02 | 40470, 41380 | Y | N |  |  | 91250 | 67427
91394 | Mendoza_Substation_Upgrade | Increase the transformation capacity at Mendoza Substation by installing an additional power transformer and upgrade the existing bus configuration to an improved bus arrangement. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8202 | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7325 | Y |  |  |  | 91395 | 91394
91545 | Birdhouse Substation Upgrade | Upgrade Birdhouse substation to provide a new POI for GVEC PWT. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | PLC-6656 | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 |  |  |  |  | 7255 | Y |  |  |  | 91546 | 91545
78495 | Hillje 345kV Substation Expansion for Space City Solar - Generator Interconnection (21INR0341) | Expand Hillje 345kV substation and install one generator lead for new interconnection to MIDANE customer substation for Space City Solar |  | Hillje | MIDANE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44200, 112261 | Y | N |  |  | 78496 | 78495
73065 | Magana Hein: Build new 138 kV distribution station | Construct new distribution station on the Molina to Wormser Road 138 kV line |  | Magana Hein |  | Planned |  | AEP TCC | Thomas Neils jlsolis@aep.com 361-881-5574 |  | 2027-12-31 |  | 138 | 2.6 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8295, 8641, 8646, 8801, 80230 | Y |  |  |  | 73066 | 73065
73352A | PH Robinson Area 138kV Upgrades | Reposition existing PH Robinson to BACLIF generator lead from the PHR_South bus to the PHR_North bus. |  | PH Robinson | BACLIF | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42010, 42015, 111131 | Y | N |  |  | 73353 | 73352
76237 | Lobo: Construct New 345 kV Terminal | Interconnect Cuchillas Solar to the Lobo 345 kV station |  | Lobo |  | Planned |  | ETT/AEP TCC/ETT | John Solis jlsolis@aep.com 361-881-5574 | TP2023320 | 2027-12-31 | 2025-06-01 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219 | Y |  |  |  | 76238 | 76237
90161C | Install new Mill Creek (MLC) distribution substation with (2) 100 MVA transformers. | Convert Pinehurst to unity power factor substation. |  | Pinehurst |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Montgomery |  | Tier 4 | [5 empty] | Y | N |  | No Transmission upgrades expected. | 102977 | 90161
103501 | LCRATSC Beecham Gap Area Substation Addition | LCRA TSC provide a new transmission point of interconnection (POI) for Brazos Electric Cooperative-owned transmission line to their Beecham Gap Substation at Kempner substation. |  | Kempner |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Lampasas |  | Tier 4 | [5 empty] | Y |  |  |  | 103502 | 103501
102779 | Fairbanks (FB) Substation Expansion | Expand existing 138kV Fairbanks substation with in-series breakers. |  | Fairbanks | TH Wharton/Deihl | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 102781 | 102779
109638 | Install new Bypass BESS II generator storage and connect to WA Parish 345kV North. Utilize same generator lead as Bypass BESS. |  |  | WA Parish |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y |  |  |  | 109639 | 109638
110055 | Clear Crossing: Install New 345 kV Capacitor Bank | Install a new capacitor bank at the Clear Crossing 345 kV station | Reactive Capability Update | Clear Crossing |  | Planned |  | AEP TNC/ETT | Mina Turner myturner@aep.com 918-599-2437 | TP2026076 | 2027-12-31 |  | 345 | 0 | 0 | 0 | 0,261.9 | Haskell |  | Tier 4 |  |  |  |  | 60515 | Y | N |  |  | 110056 | 110055
111604 | LCRATSC Gillespie Nimitz Storm Hardening | LCRA will replace the conductor between Gillespie and Nimitz (T266) as part of an effort to rebuild and harden the circuit resulting in greater durability and reliability of assets in the area. |  | Gillespie | Nimitz | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8473 | 2027-12-31 |  | 138 | 0 | 2.9006 | 0 |  | Gillespie | Gillespie | Tier 4 |  |  |  |  | 7128, 7132, 7133 | Y |  |  |  | 111605 | 111604
102538 | Install distribution transformers at Intercontinental distribution substation. |  |  | Intercontinental |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 45910 | Y | N |  |  | 112470 | 102538
109858 | Gillespie - Goehmann Lane Transmission Line Upgrade | Upgrade the 69-kV 3.6 mile Gillespie - Goehmann Lane transmission line to achieve a 67 MVA minimum emergency rating. This is an LCP Upgrade project to support Batch Zero Base Load |  | Gillespie | Goehmann Lane | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2027-12-31 |  | 69 | 0 | 3.6 | 0 |  | Gillespie | Gillespie | Tier 4 | [5 empty] | Y |  |  |  | 109859 | 109858
90189 | Meadow 345kV Substation Expansion for Aldrin 345 BESS(25INR0425). | Expand 345kV Meadow (MDO) substation for ALDRIN (ALD) / Aldrin 345 BESS (25INR0425). |  | Meadow |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  |  | 90190 | 90189
105424 | Cascabel: Expand 345 kV Station | Interconnect the Crusoe load at the Cascabel 345 kV station | NEW | Cascabel |  | Planned |  | ETT/AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2026076 | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Stonwall |  | Tier 4 |  |  |  |  | 60515 | Y |  |  |  | 105425 | 105424
104744A | High Voltage Mitigation - WA Parish Area | Install (2) 40 MVAr shunt reactors on the tertiary of Bellaire Auto A1 |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 | -80,0 | Harris |  | Tier 4 |  |  |  |  | 49001 | Y | N |  |  | 109528 | 104744
104744D | High Voltage Mitigation - WA Parish Area | Install (2) 40 MVAr shunt reactors on the tertiary of Jeanetta Auto A2 |  | Jeanetta |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 | -80,0 | Harris |  | Tier 4 |  |  |  |  | 49082 | Y | N |  |  | 109529 | 104744
104744C | High Voltage Mitigation - WA Parish Area | Install (2) 40 MVAr shunt reactors on the tertiary of Jeanetta Auto A1 |  | Jeanetta |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 | -80,0 | Harris |  | Tier 4 |  |  |  |  | 49024 | Y | N |  |  | 109530 | 104744
104744B | High Voltage Mitigation - WA Parish Area | Install (2) 40 MVAr shunt reactors on the tertiary of Bellaire Auto A2 |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 | -80,0 | Harris |  | Tier 4 |  |  |  |  | 49084 | Y | N |  |  | 109531 | 104744
109610A | Missouri City to HO Clarke - Hardening Upgrades | Rebuild/reconductor Ckt.02A HO Clarke to Blue Ridge to Missouri City as a Hardening upgrade. Rebuild/reconductor Ckt.02A Blue Ridge tap section as a Hardening upgrade. |  | HO Clarke | Missouri City | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 6.26 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44082, 47150, 48036, 48163 | Y | N |  |  | 109611 | 109610
102540 | Upgrade Ckt.67B North Belt to DRILCO to increase thermal limits. |  |  | North Belt | DRILCO | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45740, 46110 | Y | N |  |  | 102541 | 102540
90161A | Install new Mill Creek (MLC) distribution substation with (2) 100 MVA transformers. | Install new Mill Creek (MLC) distribution substation with (2) 100 MVA transformers. Loop substation on Ckt.81G to create new Ckt.81G Pinehurst to Mill Creek to Tomball. |  | Mill Creek | Pinehurst /Tomball | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 138 | 9 | 0 | 0 |  | Montgomery | Harris | Tier 4 |  |  |  |  | 44850, 46240, 46510 | Y | N |  |  | 102975 | 90161
98994A | Replace Harrisburg with new Manchester Subsation | Remove Harrisburg from Ckts. 33B & 33C service to create new Ckt.33 TEXPET to Clinton. |  | Deepwater | TEXPET | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40352, 40800, 41560, 740800 | Y | N |  |  | 98995 | 98994
72059 | Hillje 345kV Substation Expansion for Ramsey Storage - Generator Interconnection to FLATLA (FLA) (21INR0505) | Expand Hillje 345kV substation and install one generator lead for new interconnection to FLATLA (FLA) customer substation for Ramsey Storage |  | Hillje |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44200, 113595 | Y | N |  |  | 90911 | 72059
73352D | PH Robinson Area 138kV Upgrades | Upgrade PH Robinson 'North' Bus fault duty to 80KA |  | PH Robinson |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 00:03 |  | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 | [5 empty] | Y | N |  |  | 73356 | 73352
110447 | STEC Ammonia Plant Load Phase 2 | -Rebuild the existing Victoria Plant to Shepley to Dupont 138-kV transmission line with normal and emergency ratings of at least 485 MVA, approximately 7.66-mile; -Rebuild the existing Victoria Plant to Dupont 138-kV transmission line ckt2 with normal and emergency ratings of at least 485 MVA, approximately 7.66-mile; -Remove the double-circuit section of the Victoria Plant to Shepley and Victoria Plant to Dupont circuits (by rebuilding the two circuits on separate structures) |  | Victoria | Dupont | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-12-31 12:15 |  | 138 | 7.66 | 15.32 | 0 |  | Victoria | Victoria | Tier 1 | 25RPG012 |  | 2026-01-13 |  |  | Y | N |  |  | 110448 | 110447
80342 |  |  |  | HILLTOP LAKES | HILLTOP LAKES | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-01-06 |  | 138 | 0 | 0 | 60 |  | Leon | Leon | Tier 4 |  |  |  |  | 47, 48 | Y |  |  |  | 80343 | 80342
102659 | BEPC_TPIT102659_KellerUpgrade |  |  | 565 | 1856 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-01-07 |  | 138 | 0 | 0.27 | 0 |  | Tarrant |  | Tier 4 |  |  |  |  | 565, 1856 | Y |  |  |  | 102660 | 102659
73100 | Asherton to Piloncillo: Rebuild 138 kV Line | Rehab the Asherton to Piloncillo 138 kV line |  | Asherton | Piloncillo | Planned | TA2021030 | AEP TCC | William Simmons jlsolis@aep.com 361-881-5574 |  | 2028-01-13 | 2958101 | 138 | 0 | 13.43 | 0 |  | Dimmit | Dimmit | Tier 4 |  |  |  |  | 8283, 8970, 80481 | Y |  |  |  | 73101 | 73100
70675 | Aransas Pass to Rincon: Rebuild 69 kV Line | Rebuild the Aransas Pass to Gregory to Rincon 69 kV line | In-Service Date Update | Aransas Pass | Rincon | Planned |  | AEP TCC | Michael Blackwell deevans@aep.com 918-599-2938 | TP2022132 | 2028-01-14 |  | 69 | 0 | 8.5 | 0 |  | San Patricio | San Patricio | Tier 2 | 24RPG035 | 2024-11-11 |  |  | 8416, 8421, 8427 | Y |  |  |  | 70676 | 70675
105624 | AEN_McNeil_JustinLn_Ckt_811_Reconductor | Reconductor 3.98 miles of circuit to 3000 Amps. |  | 9291 | 9342 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-01-19 |  | 69 | 0 | 3.98 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9080, 9225 | Y |  |  |  | 105625 | 105624
87367 |  |  |  | Temple Switch | Poage | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-01-28 |  | 138 | 0 | 2 | 75 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 126, 130, 133, 3415, 33126 | Y |  |  |  | 87368 | 87367
78468A | Pradera (PRD) CEHE-Owned 345kV Substation for Austin Bayou Solar (25INR0102) | New 345kV Pradera (PRD) substation for generator interconnection to Austin Bayou Solar (25INR0102). Loop Ckt.27 into Pradera substation to create new Ckt.27 Seabreeze to Pradera to Savannah. |  | Pradera | Savannah/Seabreeze | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-01-30 00:02 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42590, 43020, 43035 | Y | N |  |  | 102676 | 78468
73055 | Hamlin to Roby: Rebuild 69 kV line | Rehab Hamlin to Roby 69 kV line | Company Contact and In-Service Date Update | Hamlin | Roby | Planned |  | AEP TNC | Bill Edwards myturner@aep.com 918-599-2437 |  | 2028-01-31 |  | 69 | 0 | 25.23 | 0 |  | Fisher | Jones | Tier 4 | 23RPG002 | 2023-02-01 | 2023-02-28 |  | 6185, 6192, 6193, 6194, 6195, 6638 | Y | N |  |  | 73056 | 73055
72479 | Cobia: Build new 138 kV Station | Build new 138 kV station along the Carbide to Joslin 138 kV line | In-Service Date Update | Cobia |  | Planned |  | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 |  | 2028-01-31 |  | 138 | 0.1 | 0 | 0 |  | Calhoun |  | Tier 4 |  |  |  |  | 8132, 8133, 8140, 8155, 8685, 8720, 8741, 8742, 88742, 708133 | Y |  |  |  | 72482 | 72479
70673 | Clairmont Sun Oil Tap: Rebuild 69 kV Line | Rehab Clairmont Sun Oil Tap 69 kV Line |  | Clairmont | Sun Clairmont | Planned |  | AEP TNC | Travis Coody myturner@aep.com 918-599-2437 | TA2021233 | 2028-01-31 |  | 69 | 0 | 0 | 0 |  | Kent | Kent | Tier 4 |  |  |  |  | 6197, 6198 | Y |  |  |  | 70674 | 70673
92743 | Rebuild ~3 miles of double-ckt from VLSI to Grissom transmission line with normal and emergency ratings of at least 478MVA | Rebuild ~3 miles of double-ckt from VLSI to Grissom transmission line with normal and emergency ratings of at least 478MVA. Note: Only the conductor needs to be upgraded. All other substation equipment is rated at least 2000A or 478MVA. |  | 5467 | 5185 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0377 | 2028-01-31 |  | 138 | 0 | 3.03 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5185, 5467 | Y |  |  |  | 92744 | 92743
103454 | Viper: Construct New 138 kV Station | Interconnect Sugaree Solar and Althea Storage to the new Viper 138 kV station on the Brackettville to Escondido 138 kV line | TSP/Company Contact and Transmision Circuit Miles New Update | VIPER |  | Planned |  | AEP TCC | Melissa L Skillman jlsolis@aep.com 361-881-5574 | TP2025819 | 2028-01-31 |  | 138 | 0.1 | 0 | 0 |  | Maverick |  | Tier 4 |  |  |  |  | 8073, 8252, 8260 | Y | N |  |  | 103455 | 103454
100700 | Install a 28.57MVAr Capacitor Bank at Ranchtown Substation |  |  | 5358 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1042 | 2028-01-31 |  | 138 | 0 | 0 | 0 | 0,28.57 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5358 | Y |  |  |  | 100701 | 100700
77144A | Pompano: New 138 kV Station | Skid Station |  |  |  | Planned |  | AEP TCC | Robert Younger jlsolis@aep.com 361-881-5574 | TP2015151 | 2028-01-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 | [5 empty] | Y |  |  |  | 103038 | 77144
98582 | Rapido: Expand 345 kV Station | Interconnect Barrosos Creek to the existing Rapido 345 kV station | Transmission Owner, Company Contact and In-Service Date Update | Rapido |  | Planned |  | ETT | Michael Blackwell jlsolis@aep.com 361-881-5574 | TP2025226 | 2028-01-31 |  | 345 | 0 | 0 | 0 |  | Starr |  | Tier 4 | [5 empty] | Y |  |  |  | 98583 | 98582
86933 | Paladio: Construct New 345 kV Station | Interconnect Argenta Solar and Storage to the new Paladio 345 kV station on the Goddard to Tango 345 kV line | Company Contact and In-Service Date Update | Paladio |  | Planned |  | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2024012 | 2028-01-31 |  | 345 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8012, 8606, 8689 | Y |  |  |  | 86934 | 86933
78468B | Pradera (PRD) CEHE-Owned 345kV Substation for Austin Bayou Solar (25INR0102) | Install generator lead from Pradera (PRD) substation to AUSTIN (ABY) customer substation (25INR0102). |  | Pradera | AUSTIN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-01-31 00:03 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 102677 | 78468
110657 | Ad Hoc TPIT: Rebuild approximately 3.33-mile 345 kV double circuit from WETT's Mhos to Oncor's Dermott Switch station |  |  | Mhos 345 kV | Oncor's Dermott Switch 345 kV station | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2028-02-01 |  | 345 | 0 | 3.33 | 0 |  | Scurry | Scurry | Tier 3 | [5 empty] | N |  |  |  | 110658 | 110657
110729 | Ad Hoc TPIT: Rebuild approximately 33-mile 345 kV double circuit from Nova Prime to Mhos |  |  | Nova Prime 345 kV | Mhos 345 kV | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2028-02-01 |  | 345 | 0 | 33 | 0 |  | Kent | Scurry | Tier 3 | [5 empty] | N |  |  |  | 110730 | 110729
110639 | Ad Hoc TPIT: Rebuild approximately 8.1-mile 345 kV double circuit from WETT's Galvani to Oncor's Scurry County South station |  |  | Galvani 345 kV | Oncor's Scurry County South | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2028-02-01 |  | 345 | 0 | 8.1 | 0 |  | Scurry | Scurry | Tier 3 | [5 empty] | N |  |  |  | 110640 | 110639
103998 | BRYN_Tabor_Load_Addition | Adding transmission load to Tabor 138-kV |  | BTU Tabor |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-02-04 |  | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32882 | Y |  |  |  | 103999 | 103998
80317 | Dilley Switch to Pearsall: Convert to 138 kV, Reroute from Dilley to Dilley Switch, Rebuild Dilley to Dilley Switch 69 kV, and Double Circuit Dilley Switch to Pearsall with Dilley to Dilley Switch | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch |  | Dilley Switch | Pearsall | Planned | 1104 - 1282 | AEP TCC | Will Simmons jlsolis@aep.com 361-881-5574 | 3822 | 2028-02-15 |  | 138 | 0 | 19.8 | 0 |  | Frio | Frio | Tier 4 | 23RPG024 | 2023-08-29 | 2023-09-28 |  | 8208, 8210, 8212, 8216, 8752 | Y |  |  |  | 80318 | 80317
80315 | Big Foot to Pearsall: Convert to 138 kV | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch |  | Big Foot | Pearsall | Planned | 1104 - 1282 | AEP TCC | Will Simmons mlforcum@aep.com 918-599-2674 | 3821 | 2028-02-17 |  | 138 | 0 | 14.79 | 0 |  | Frio | Frio | Tier 4 | 23RPG024 | 2023-08-29 | 2023-09-28 |  | 8216, 8218, 8221, 8752 | Y |  |  |  | 80316 | 80315
100054 | Luna to Mesquite: Rebuild 138 kV Line | Rebuild the Luna to Mesquite 138 kV line | TSP/Company Contact Update | Luna | Mesquite | Planned |  | AEP TCC | Matthew McLauchlin jlsolis@aep.com 361-881-5574 | TP2025785 | 2028-02-28 |  | 138 | 0 | 1.25 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 8554, 8656 | Y |  |  |  | 100055 | 100054
100291 | Most_Limiting_Series_Element_FY2025_Substation_Upgrade | Increase the capacity of transmission circuits by upgrading the limiting elements at various substations. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-02-28 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7560, 7575, 7576, 78103, 78104 | Y |  |  |  | 100292 | 100291
91744A | New 138kV CEHE Station Grassland for OCI SunRoper (24INR0257) | Loop new Grassland (GRS) CEHE 138kV substation into Ckt.60D Dyann to South Lane City to create new Ckt.60 Dyann to Grassland to South Lane City. |  | Grassland | Dyann/South Lane City | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 42730, 42985, 43190 | Y | N |  |  | 92897 | 91744
93163 | Diablo: Construct New Distribution Station | Construct new distribution station on the North McCamey to Palouse 138 kV line between Crossover and Palouse |  | Diablo |  | Planned |  | AEP TNC | Jacob Pyle myturner@aep.com 918-599-2437 | DR24N0002 | 2028-02-28 |  | 138 | 8.4 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | 60115, 60723, 60728 | Y | N |  |  | 93164 | 93163
98798 | Beecher: Expand 138 kV Station | Interconnect Leopard BESS to the existing Beecher 138 kV station | TSP/Company Contact Update | Beecher |  | Planned |  | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 | TP2025255 | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 8088, 8721 | Y |  |  |  | 98799 | 98798
65154 | Mason Switch to Yellowjacket: Rebuild 69 kV Line | Rehab the Mason Switch to Yellowjacket 69 kV Line | In-Service Date Update | Mason Switch | Yellowjacket | Planned | 1142 - 1320 | AEP TNC | Carol Matheny myturner@aep.com 918-599-2437 | 2836 | 2028-02-28 |  | 69 | 0 | 26.45 | 0 |  | Menard | Mason | Tier 4 | 21RPG014 | 2021-08-01 | 2021-09-01 |  | 6363, 6396, 23824 | Y | N |  |  | 65155 | 65154
73441 | Dupont Switch to Joslin: Rebuild 138 kV Line | Rehab the Dupont Switch to Joslin 138 kV Line | Company Contact and In-Service Date Update | Dupont | Joslin | Planned |  | AEP TCC | Travis Coody myturner@aep.com 918-599-2437 |  | 2028-02-28 |  | 138 | 0 | 32.6 | 0 |  | Victoria | Calhoun | Tier 4 | 22RPG040 | 2022-11-01 | 2022-12-01 |  | 8140, 8141, 8143, 8722, 80064 | Y |  |  |  | 73442 | 73441
76286 | Hecker to Resnik: Rebuild 138 kV Line | Rebuild the Hecker to Resnik 138 kV line | Company Contact and In-Service Date Update | Hecker | Resnik | Planned |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2023506 | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8422, 8565, 8580, 80470 | Y |  |  |  | 76287 | 76286
104448 | Salvare: Install New 345 kV Feed | Install 2nd POI for IRIS Data center | TSP/Company Contact and In-Service Date Update | Salvare |  | Planned |  | ETT | Ali Barkat myturner@aep.com 918-599-2437 | TP2026040 | 2028-02-28 |  | 345 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60284, 60511 | Y | N |  |  | 104449 | 104448
110866 | Stewart Road to Progresso: Convert to 138 kV | Convert Stewart Road to Progresso 69 kV line to 138 kV | Dollars Should be Update | Stewart Road | Progresso | Planned |  | AEP TCC | Robert Younger deevans@aep.com 918-599-2938 |  | 2028-02-28 |  | 138 | 0 | 19.4 | 0 |  | Cameron | Hidalgo | Tier 3 | 23RPG005 | 2023-03-01 | 2023-03-23 |  | 5778, 8040, 8703, 8751, 8949, 8951 | Y | N |  | This project aligns with Project Set #5 and #6 in the approved LLIS# 2215 LCP | 110867 | 110866
110441 | Rio Bravo: Add Capacitor | Install additional reactive support at Rio Bravo 138 kV station | County Location, SSWG Base Case Bus Number, and Other (optional) updates | Rio Bravo |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 |  | 2028-02-28 |  | 138 | 0 | 0 | 0 | 0,34.5 | Webb |  | Tier 4 |  |  |  |  | 8646 | Y | N |  | This project in conjunction with MOD Project Number 110439, replace Project Set #1 (Zapata capacitors at bus 8299) in the approved LLIS# 2215 LCP | 110442 | 110441
110439 | Molina: Add Capacitor | Install additional reactive support at Molina 138 kV station | County Location, SSWG Base Case Bus Number Updates, and Other (optional) updates | Molina |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 |  | 2028-02-28 |  | 138 | 0 | 0 | 0 | 0,34.5 | Webb |  | Tier 4 |  |  |  |  | 80230 | Y | N |  | This project in conjunction with MOD Project Number 110441, replace Project Set #1 (Zapata capacitors at bus 8299) in the approved LLIS# 2215 LCP | 110440 | 110439
107136 | LCRATSC Duff Ranch Substation Addition | LCRA TSC will install the transmission interconnection facilities including constructing a new 345-kV substation ("Duff Ranch Substation Addition"). |  | Duff Ranch |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-02-28 |  | 345 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 76003, 76009, 76018 | Y |  |  |  | 107137 | 107136
80319 | Devine: Install Cap Bank | Convert the Big Foot to Dilley 69 kV line to 138 kV, rebuild the Dilley to Dilley Switch 69 kV line, and reroute the Big Foot to Dilley line from Dilley to Dilley Switch | In-Service Date, RPG submitted date and review date Update | Devine |  | Planned |  | AEP TCC/ETT | Will Simmons jlsolis@aep.com 361-881-5574 | TA2018040 | 2028-02-28 |  | 138 | 0 | 0 | 0 | 0,23 | Medina |  | Tier 4 | 23RPG024 | 2023-08-29 | 2023-09-28 |  | 8732 | Y |  |  |  | 80322 | 80319
91744B | New 138kV CEHE Station Grassland for OCI SunRoper (24INR0257) | Install one generator lead from Grassland (GRS) CEHE 138kV substation to SUNROP (SUN) / OCI SunRoper |  | Grassland |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y |  |  |  | 92898 | 91744
103456 | Frontera to Key Switch: Rebuild/Re-conductor 138 kV Line | Rebuild/Re-conductor the Frontera to Key Switch 138 kV line | TSP/Company Contact Update | Frontera | Key Switch | Planned |  | AEP TCC | Curtis E Brown jlsolis@aep.com 361-881-5574 | TP2025872 | 2028-02-29 |  | 138 | 0 | 9.3 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 8773, 8980, 80108 | Y | N |  | This project aligns with Project Set #3 and #4 in the approved LLIS# 2215 LCP | 103457 | 103456
91774 | Janka: Construct New 345 kV Station | Interconnect the Evergrid load to the new Janka 345 kV station on the Edith Clarke to Tesla 345 kV line | Transmission Owner Update | Janka |  | Planned |  | ETT/AEP TNC | Carol A Matheny myturner@aep.com 918-599-2437 | TP2025126 | 2028-02-29 12:00 |  | 345 | 0.2 | 0 | 0 |  | Hardeman |  | Tier 4 |  |  |  |  | 60139, 60501, 60505, 61616 | Y |  |  |  | 91775 | 91774
70012B | BEPC_NOTPIT_ClarkLakeVoltConv1 |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 513, 515, 518, 519 | Y |  |  |  | 106698 | 70012
70012C | BEPC_NOTPIT_ClarkLakeVoltConv1 |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-14 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 518, 519, 785 | Y |  |  |  | 106699 | 70012
77144B | Pompano: New 138 kV Station | Final Station | In-Service Date Update | Pompano |  | Planned |  | AEP TCC | Robert Younger jlsolis@aep.com 361-881-5574 | TP2015151 | 2028-03-20 |  | 138 | 0 | 20.4 | 0 | 0,276.4 | Cameron |  | Tier 4 |  |  |  |  | 8058, 8337, 8535, 79601, 85351, 85352 | Y |  |  |  | 77145 | 77144
70012D | BEPC_NOTPIT_ClarkLakeVoltConv1 |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-21 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 519, 1569 | Y |  |  |  | 106700 | 70012
99453B | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.69B Greens Bayou to Deepwater to increase thermal limits as part of FRM2 upgrades |  | Greens Bayou | Deepwater | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-03-30 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40450, 40700 | Y | N |  |  | 102605 | 99453
72044A | Clute 138kV Switching Station | Reconfigure existing Ckt.82F RIWOOD to CAVERN to BIPORT and loop into new CEHE-owned 138kV Clute switching station to create new Ckt.82 RIWOOD to Clute to CAVERN to BIPORT. |  | Clute | RIWOOD/CAVERN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-03-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 | 42050, 43150, 43330 | Y | N |  |  | 104728 | 72044
72044C | Clute 138kV Switching Station | Reconfigure existing Ckt.26D STRATT to SINTEK and loop into new CEHE-owned 138kV Clute switching station to create new Ckt.26 STRATT to Clute to SINTEK. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-03-30 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 | 42050, 43240, 43300 | Y | N |  |  | 104730 | 72044
52464 | Alamito Creek to Ft. Davis: Rebuild 69 kV Line | Alamito Creek to Ft. Davis: Rebuild 69 kV line | TSP/Company Contact and In-Service Date Update | Alamito Creek | Ft Davis | Planned | 1070 - 1243 | AEP TNC | David Baker myturner@aep.com 918-599-2437 | 2831 | 2028-03-31 |  | 69 | 0 | 20.5 | 0 |  | Presidio |  | Tier 4 |  |  |  |  | 6676, 6677, 6678, 6691, 6692 | Y | N |  |  | 65564 | 52464
100073 | Rio Pecos: Expand 138 kV Station | Interconnect Midnight Sun BESS to the existing Rio Pecos 138 kV station | TSP/Company Contact Update | Rio Pecos |  | Planned |  | AEP TNC | Brooks Dow myturner@aep.com 918-599-2437 | TP2025332 | 2028-03-31 |  | 138 | 0.1 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6601, 136821 | Y |  |  |  | 100074 | 100073
99540 | Anastase: Construct New 138 kV Station | Interconnect Rutile BESS to the new Anastase 138 kV station on the Ballinger to Red Creek 138 kV line between Ballinger and Weiss | TSP/Company Contact Update | Anastase |  | Conceptual |  | AEP TNC | Jonathan Reith myturner@aep.com 918-599-2437 | TP2025343 | 2028-03-31 |  | 138 | 0 | 0 | 0 |  | Runnels |  | Tier 4 |  |  |  |  | 6340, 60216, 60399 | Y |  |  |  | 99541 | 99540
81686 | Chalcedony: Construct New 345 kV Station | Interconnect the Monarch load to the new Chalcedony 345 kV station on the Lon Hill to Nelson Sharpe 345 kV line |  | Chalcedony |  | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2028-03-31 |  | 345 | 1.5 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8455, 80078, 84555, 85000 | Y | N |  |  | 81687 | 81686
102755 | BEPC_TPIT102755_Dennis |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-03-31 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 489, 494, 507 | Y |  |  |  | 102756 | 102755
111374 | Gliese: Construct New 138 kV Station | Interconnect the Valverde load to the new Gliese 138 kV Station on the Hamilton Road to Picacho 138 kV line | NEW | Gliese |  | Planned |  | ETT | John Solis jlsolis@aep.com 361-881-5575 | TP2026120 | 2028-03-31 |  | 138 | 1 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 8052, 8255, 8684, 80530 | Y | N |  |  | 111375 | 111374
104028 | Steppe: Construct New 345 kV Station | Interconnect West Munday Wind to the new Steppe 345 kV station on the Joule to Quasar 345 kV line between Gauss and Quasar |  | Steppe |  | Planned |  | ETT | Nathan L Cowan myturner@aep.com 918-599-2437 | TP2025777 | 2028-03-31 |  | 345 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 60283, 60703, 60712 | Y | N |  |  | 104029 | 104028
110092 | This models upgrades required for a proposed load addition | Install new 138kV CEHEsub Customer substation. Loop on Ckt. 48 to create new Ckt. 48 Jordan to CEHEsub to DUNCAN. |  | CEHEsub | Jordan/DUNCAN | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-01 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 | [5 empty] | N | N |  |  | 110093 | 110092
110575 | Ad Hoc TPIT: 345 kV Second Circuit from Long Draw to Venturi to Volta to Grelton to Oncor's ODESEHV2_5 station |  |  | Long Draw 345 kV | Oncor's ODESEHV2_5 345 kV station | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2028-04-01 |  | 345 | 108.38 | 0 | 0 |  | Borden | Ector | Tier 3 | [5 empty] | N |  |  |  | 110576 | 110575
111822 | Saltdome Capacitor 2nd step addition |  |  | Saltdome |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-04-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5551 | Y | N |  |  | 111823 | 111822
110828 | STEC Mesquite Large Load Project Phase 1 | Construct Mesquite large load 345-kV POI |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-04-01 12:15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110829 | 110828
102670 | BEPC_TPIT102670_Rockett |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-04-03 |  | 69 | 0 | 6.5 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 214, 218 | Y |  |  |  | 102671 | 102670
102634 | BEPC_TPIT10264_Egan_HappyHill_Improvement |  |  | 438 | 412 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-04-03 |  | 138 | 0 | 2 | 36 |  | Johnson |  | Tier 4 |  |  |  |  | 405, 412, 419, 432, 438, 439, 33405 | Y |  |  |  | 102635 | 102634
107132 | Water Valley Substation Addition | LCRA TSC will install the transmission interconnection facilities including constructing a new 345-kV substation ("Water Valley"). |  | Water Valley Substation |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-04-04 |  | 345 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 76009, 76070, 76090 | Y |  |  |  | 107133 | 107132
110282 | New CTT Celtic Green 345 kV station |  |  | CTT Gray | AEP Tesla | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-04-17 |  | 345 | 0 | 0 | 0 |  | Wheeler |  | Tier 4 |  |  |  |  | 60504, 79009, 79491, 79492 | Y | N |  |  | 110283 | 110282
110304 | Add double circuit line from CTT Red Rock to Oncor Ogallala |  |  | CTT Red Rock | Oncor Ogallala | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-04-17 |  | 345 | 0 | 0 | 0 |  | Hall | Castro | Tier 3 | [5 empty] | N | Y |  |  | 110305 | 110304
103474 | Pomelo: Expand 345 kV Station | Interconnect Monte Cristo 2 to the existing Pomelo 345 kV station | NEW | Pomelo |  | Planned |  | ETT | Glen Reed gareed@aep.com 918-599-2664 | TP2025925 | 2028-04-30 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 | [5 empty] | Y | N |  |  | 103475 | 103474
80907 | Fort Stockton Plant: Rebuild 138/69 kV Station | Rebuild the Fort Stockton Plant 138/69 kV station | Dollars, Tier, RPG Number and RPG Date Update | Fort Stockton Plant |  | Planned | TP2023319 | AEP TNC | Damian P Raab myturner@aep.com 918-599-2437 |  | 2028-04-30 |  | 138 | 0 | 0 | 90 |  | Pecos |  | Tier 3 | 25RPG032 | 2025-10-15 | 2025-10-15 |  | 6630, 38355 | Y | N |  |  | 80908 | 80907
91747 | Install (1) 60 MVAr switchable cap bank at Willow substation. Connect CB1 at the Willow breaker position with Willow TR3 distribution transformer | Install (1) 60 MVAr switchable cap bank at Willow substation. Connect CB1 at the Willow breaker position with Willow TR3 distribution transformer |  | Willow |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-30 |  | 138 | 0 | 0 | 0 | 0,60 | Harris |  | Tier 4 |  |  |  |  | 46660 | Y | N |  |  | 111097 | 91747
93461A | Willow Substation Load Addition Upgrades | Install (1) 60 MVAr switchable cap bank at Willow substation. |  | Willow |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-30 |  | 138 | 0 | 0 | 0 | 0,60 | Harris |  | Tier 4 |  |  |  |  | 46660 | Y | N |  |  | 111098 | 93461
98584 | Tiempo: Expand 345 kV Station | Interconnect Corralitos Wind 1 and 2 to the existing Tiempo 345 kV station | Transmission Owner, Company Contact and In-Service Date Update | Tiempo |  | Planned |  | ETT | Michael Blackwell jlsolis@aep.com 361-881-5574 | TP2025252 | 2028-04-30 |  | 345 | 0 | 0 | 0 |  | Zapata |  | Tier 4 | [5 empty] | Y |  |  |  | 98585 | 98584
103392 | Cuernos: Construct New 345 kV Station | Interconnect La Salle Solar to the new Cuernos 345 kV station on the Lobo to Fowlerton 345 kV line | NEW | Cuernos |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025856 | 2028-04-30 |  | 345 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 5709, 8826, 80219 | Y | N |  |  | 103393 | 103392
104030 | Sunflower: Construct New 138 kV Station | Interconnect August Draw Solar to the new Sunflower 138 kV station on the Scissortail to Solstice 138 kV line between Hoefs Road and Scissortail |  | Sunflower |  | Planned |  | AEP TNC | Charity Kreher myturner@aep.com 918-599-2437 | TP2025812 | 2028-04-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 6077, 60242, 60808 | Y | N |  |  | 104031 | 104030
99551 | Chalice: Construct New 345 kV Station | Interconnect Corvus Solar to the new Chalice 345 kV station on the Cenizo to Lobo 345 kV line | TSP/Company Contact Update | Chalice |  | Planned |  | ETT | Sara Watson jlsolis@aep.com 361-881-5574 | TP2025348 | 2028-04-30 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80217, 80219, 80220 | Y |  |  |  | 99552 | 99551
99825 | Boiken: Construct New 345 kV Station | Interconnect Lancium data center load to the new Boiken 345 kV station on the Tesla to Tule Canyon 345 kV line | Project Title, Description, Terminal from and Reactive Capability Update | Boiken |  | Planned |  | AEP TNC | Zach Lachiusa myturner@aep.com 918-599-2437 | TP2025947 | 2028-04-30 |  | 345 | 0.2 | 0 | 0 |  | Hall |  | Tier 4 |  |  |  |  | 60501, 60518, 79002, 79004, 79010 | Y |  |  |  | 99826 | 99825
86884 | Saragosa: Construct New 138 kV Terminal | Interconnect Bracero Pecan Storage to the Saragosa 138 kV station | In-Service Date Update | Saragosa | Bracero Pecan | Planned | TP2024091 | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 |  | 2028-04-30 |  | 138 | 0.5 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  | 2024-03-21 | 2024-04-12 |  | 60716 | Y | N |  |  | 86885 | 86884
90043 | Candela: Construct New 345 kV Station | Interconnect the new Eneus load station to the new Candela 345 kV station on the Gulch to La Palma 345 kV line | TSP/Company Contact and In-Service Date Update | Kelvin | Eneus | Planned |  | AEP TCC | Carol Matheny jlsolis@aep.com 361-881-5574 | TP2024073 | 2028-04-30 |  | 345 | 1 | 0 | 0 | 0,260 | Cameron | Cameron | Tier 4 |  |  |  |  | 8013, 8317, 8704, 80113 | Y |  |  |  | 90044 | 90043
98737 | Agrios: Construct New 345 kV Station | Interconnect Grapefruit Solar to the new Agrios 345 kV station on the North Edinburg to Reforzar 345 kV line | TSP/Company Contact Update | Agrios |  | Planned |  | AEP TCC | Sally Matthews jsolis@aep.com 361-881-5574 | TP2025218 | 2028-04-30 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8098, 8905, 80078, 80233 | Y |  |  |  | 98738 | 98737
93461B | Willow Substation Load Addition Upgrades | Install (1) 60 MVAr cap bank at Klein substation. Tap the cap bank on Ckt.81F Klein to Kluge. |  | Klein |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-30 |  | 138 | 0 | 0 | 0 | 0,60 | Harris |  | Tier 4 |  |  |  |  | 45940 | Y | N |  |  | 111100 | 93461
90255D | Jordan / Mont Belvieu Area Improvement Project | Upgrade Ckt.86H BRINE to Mont Belvieu to increase thermal limits. |  | BRINE | Mont Belvieu | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-30 |  | 138 | 0 | 2.8 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40220, 41111, 41740 | Y | N |  |  | 111230 | 90255
93461C | Willow Substation Load Addition Upgrades | Install (3) 14.4 MVAr switchable cap banks at Klein substation. Connect cap banks at the 35kV distribution level. |  | Klein |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-04-30 |  | 138 | 0 | 0 | 0 | 0,43.2 | Harris |  | Tier 4 |  |  |  |  | 45940 | Y | N |  |  | 111099 | 93461
76777 | Rebuild Nursery-El Toro | Rebuild Nursery- Fordtran Sw- Inez - El Toro Sw Station to 795 ACSR |  | Nursery | El Toro | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 24.8 | 0 |  | Victoria | Jackson | Tier 4 |  |  |  |  | 5504, 5510, 5514, 5516 | Y |  |  |  | 76778 | 76777
110437 | Rio Hondo to Bonilla: Rebuild/Reconductor 345 kV Line | Rebuild/Reconductor Rio Hondo to Bonilla 345 kV line | SSWG Base Case Number and Other (Optional) Updates | Rio Hondo | Bonilla | Planned | TP2026176 | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 |  | 2028-05-01 |  | 345 | 0 | 11.6 | 0 |  | Cameron | Cameron | Tier 3 | [5 empty] | Y | N |  | This project aligns with Project Set #7 in the approved LLIS# 2215 LCP | 110438 | 110437
110751 | Related_WylieSW_LCP_Upgrades_Jupiter_College_Line | Related_WylieSW_LCP_Upgrades_Jupiter_College_Line |  | Jupiter | College | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | 0 | 2028-05-01 |  | 138 | 0 | 2.82 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 806, 829 | Y |  |  |  | 110752 | 110751
88049 | 24RPG004: Omicron Reliability Project : Loop in Cagnon to Howard into Omicron | Install new 138kV double-ckt line (~5 miles) from new Omicron substation to loop into existing Cagnon-Howard line |  | 5326 | 5054, 5230 | Planned | S-1082 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0394 | 2028-05-01 |  | 138 | 10 | 0 | 0 |  | Bexar | Bexar | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5054, 5230, 5326 | Y |  |  |  | 88050 | 88049
45125 | Quintana Rd to South San Rebuild | Rebuild 1.3 miles of 138 kV transmission line form Quintana Rd substation to South San substation. |  | 5350 | 5385 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0271 | 2028-05-01 |  | 138 | 0 | 1.29 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-15 |  |  | 5350, 5385 | Y |  |  |  | 45126 | 45125
72956 | Bellville South - Prairie View Transmission Line Upgrade | the proposed project converts the existing 69kV transmission line T283 from Bellville South- Quanex Sw - Sunnyside - Prarie View substation to 138kV. The proposed project improves the reliabiltiy of transmission facilities on the 26.1 mile transmission line and increases the line capacity for long term system growth. |  | Bellville South | Prairie View | Conceptual | Project transitioned to STEC from LCRA . Previous Mod Project #47428 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 0 | 0 |  | Austin | Waller | Tier 3 |  |  |  |  | 7269, 57660, 57664, 57666 | N | N |  |  | 72957 | 72956
76107 | Riverside Capacitor | Add a new cap bank at Riverside sub with 2 9.6 MVAR steps |  | Riverside |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5632 | Y | N |  |  | 76108 | 76107
110751 | Related_WylieSW_LCP_Upgrades_Jupiter_College_Line | Related_WylieSW_LCP_Upgrades_Jupiter_College_Line |  | Jupiter | College | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | 0 | 2028-05-01 |  | 138 | 0 | 2.82 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 806, 829 | Y |  |  |  | 110752 | 110751
1549 | Devine Switch breaker addition | Adds breakers to Devine Switch to allow closing of normally open Devine Switch to Devine. Creates 3- terminal switching station |  | Devine Switch |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 69 | 0 | 0 | 0 |  | Medina |  | Tier 4 | [5 empty] | Y | N |  |  | 8754 | 1549
102875 | Upgrade Franklins Camp Auto |  |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-05-01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | N | N |  |  | 102876 | 102875
110084B | This models upgrades required for a proposed load addition | Upgrade substation equipment at 345kV Ckt 64 WAP-Wolf. |  | CEHE_Newsub | WAParish/Wolf | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-01 |  | 345 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 1 | [5 empty] | N | N |  |  | 110504 | 110084
85955 | Olmos to LaVernia TL, T533 | Olmos to LaVernia TL, Rebuild 5.1 miles of 69 kV line to 138 kV transmission line |  | Olmos | LaVernia | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2028-05-10 | 2958101 | 69 | 0 | 5.1 | 0 |  | Wilson | Wilson | Tier 4 | [5 empty] | Y |  |  |  | 85956 | 85955
99532 | Establish Guthrie 138 kV Switch | Establish 138 kV Switch |  | Big Spring Switch | Tributary | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8916 | 2028-05-11 |  | 138 | 0 | 0 | 0 |  | Howard | Mitchell | Tier 4 |  |  |  |  | 1322, 10119, 10206 | Y |  |  |  | 99533 | 99532
81236 | Cattleman – Longshore 345 kV Double-Circuit Line Rebuild | Rebuild the existing 345 kV Double Circuit Line |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 R8719 | 2028-05-15 |  | 345 | 0 | 66.8 | 0 |  | Howard | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1058, 10053 | Y |  |  |  | 81385 | 81236
81268 | Longshore – Consavvy 345 kV Double-Circuit Line Rebuild | Rebuild existing 345 kV Double-Circuit Line |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 | 2028-05-15 |  | 345 | 0 | 66.8 | 0 |  | Howard | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1058, 11387, 18548 | Y |  |  |  | 81388 | 81268
103305 | LCRATSC Beback circuit breaker addition | Increase the reliability of Beback by installing circuit breakers and increase the transmission line capacity by upgrading the transmission bus. |  | Beback |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7180, 7182, 7187 | Y |  |  |  | 103306 | 103305
103310 | LCRATSC Airline - Naval Base Transmission Line Overhaul | Perform an overhaul on the 9.4 mile T475 Airline - Naval Base 138-kV transmission line. |  | Airline | Naval Base | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 9.3 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8490, 8548, 8997 | Y |  |  |  | 103311 | 103310
93250A | Utley_Substation_and_Transmission_Line_Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8065 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7310, 7316, 7317, 7322, 7327 | Y |  |  |  | 103936 | 93250
104557 | Dale to Lockhart Transmission line overhaul | Perform an overhaul and voltage conversion on T125 Dale - Lockhart transmission line from Dale Substation to Lockhart Substation. |  | Lockhart | Dale | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-05-15 |  | 138 | 0 | 7.26 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7206, 7215, 7216 | Y |  |  |  | 104558 | 104557
99344 | Rebuild the MInerva - Cannon 138 kV Line | Rebuild the MInerva - Cannon 138 kV Line |  | Minerva | Cannon | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6414 | 2028-05-15 |  | 138 | 0 | 10.2 | 0 |  | Milam | Milam | Tier 1 |  |  |  |  | 64, 3683, 3707 | Y |  |  |  | 99345 | 99344
99346 | Rebuild the Temple Pecan Creek Switch - Belfalls/STR 26/4C 345 kV Double Circuit Line | Rebuild the Temple Pecan Creek Switch - Belfalls/STR 26/4C 345 kV Double Circuit Line |  | Temple Pecan Creek | Belfalls | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6434 | 2028-05-15 |  | 345 | 0 | 2.6 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3404, 3412 | Y |  |  |  | 99347 | 99346
99479C | Snyder - China Grove 69 kV Loop Converstion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L23. Convert the existing Snyder - Scurry - China Grove and Snyder - Amoco Tap - China Grove 69-kV lines to 138-kV. This converts the China Grove - Snyder 69 kV Line into 138 kV and reterminates into the new Snyder 138 kV Switch. |  | China Grove | Snyder | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L23 | 2028-05-15 |  | 138 | 0 | 10.2 | 0 |  | Scurry | Scurry | Tier 1 |  |  |  |  | 1304, 1305, 1306, 1318, 1319, 1376, 10203, 11375 | Y |  |  |  | 99482 | 99479
99522 | Upgrading line | Upgrading conductor to 1xSuwannee | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70488, 70489 | Y |  |  |  | 99523 | 99522
99774 | Butler_Elgin_Transmission_Line_Overhaul | Perform an overhaul on the 2.8-mile T260 Butler - Elgin 138-kV transmission line. |  | Butler | Elgin | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Williamson | Tier 4 |  |  |  |  | 7321, 7324 | Y |  |  |  | 99775 | 99774
99818 | LCRATSC_Manor_Shadow_Glen_Transmission_Line_Upgrade | Upgrade the existing T649 Manor - Shadow Glen 138-kV transmission line to a minimum 105 deg. F ambient temperature rating of 700 MVA |  | 7323 | 7330 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-05-15 |  | 138 | 0 | 1.74 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7323, 7330 | Y |  |  |  | 99819 | 99818
99827A | LCRATSC_Canyon-Gofort_Transmission_Line_Overhaul |  |  | 7200 Canyon | 7515 Rohr | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-05-15 |  | 138 | 0 | 4.5 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7200, 7515 | Y |  |  |  | 99828 | 99827
99827B | LCRATSC_Canyon-Gofort_Transmission_Line_Overhaul |  |  | 7515 Rohr | 7514 Yarrington | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-05-15 |  | 138 | 0 | 0.51 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7514, 7515 | Y |  |  |  | 99829 | 99827
99827C | LCRATSC_Canyon-Gofort_Transmission_Line_Overhaul |  |  | 7514 Yarrington | 7501 Goforth | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-05-15 |  | 138 | 0 | 4.16 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7501, 7514 | Y |  |  |  | 99830 | 99827
100078 | Provide 345 kV POD to customer via POI from LCRA's Bow Wood 345 kV Switch | Provide 345 kV POD to customer via POI from LCRA's Bow Wood 345 kV Switch |  | Mikeska | Bow Wood | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6476 | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | McCulloch | McCulloch | Tier 4 |  |  |  |  | 3811, 76006 | Y |  |  |  | 100079 | 100078
100155 | Establish Mormino 345 kV Switch for customer POD | Establish Mormino 345 kV Switch for customer POD |  | Mormino | Mormino | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6370 | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3403, 3779, 3791 | Y |  |  |  | 100156 | 100155
100178 | HarrisBranch_McNeil_Transmission_Line_Upgrade | LCRA TSC will upgrade T146 Harris Branch - McNeil 138-kV transmission line to achieve a higher operational rating. |  | Harris Branch | Mcneil | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7333, 7334 | Y |  |  |  | 100179 | 100178
100180 | HarrisBranch_ShadowGlen_Transmission_Line_Upgrade | LCRA TSC will upgrade T574 Harris Branch - Shadow Glen 138-kV transmission line to achieve a higher operational rating. |  | Harris Branch | Shadow Glen | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7323, 7333 | Y |  |  |  | 100181 | 100180
100182 | Henne_Zorn_Transmission_Line_Upgrade | LCRA TSC will upgrade T204 Henne - Zorn 138-kV transmission line to achieve a higher operational rating. |  | Henne | Zorn | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Hays | Tier 4 |  |  |  |  | 7174, 7180 | Y |  |  |  | 100183 | 100182
100279 | Alford_Benedum_Transmission_Line_Upgrade | LCRA TSC will upgrade T611 Alford (Midkiff) - Benedum 138-kV transmission line to obtain a higher operational rating. |  | Alford | Benedum | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 |  |  |  |  | 71211, 71213 | Y |  |  |  | 100280 | 100279
100283 | Comfort_Cypress_Creek_Transmission_Line_Upgrade | LCRA TSC will upgrade T121 Comfort - Cypress Creek 138-kV transmission line to achieve a higher operational rating. |  | Comfort | Cypress Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Kendall | Kendall | Tier 4 |  |  |  |  | 7155, 7156 | Y |  |  |  | 100284 | 100283
100285A | Comfort_Kendall_Transmission_Line_Upgrade |  |  | Comfort | Kendall | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Kendall | Kendall | Tier 4 |  |  |  |  | 7138, 7150, 7155 | Y |  |  |  | 100286 | 100285
100287 | Comfort_Raymond_Barker_Transmission_Line_Upgrade | LCRA TSC will upgrade T122 Comfort - Raymond F. Barker 138-kV transmission line to achieve a higher operational rating. |  | Comfort | Raymond Barker | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Kendall | Kerr | Tier 4 |  |  |  |  | 7155, 7158 | Y |  |  |  | 100288 | 100287
100289 | CypressCreek_Raymond_Barker_Transmission_Line_Upgrade | LCRA TSC will upgrade T662 Cypress Creek - Raymond F. Barker 138-kV transmission line to achieve a higher operational rating. |  | Cypress Creek | Raymond Barker | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Kerr | Kendall | Tier 4 |  |  |  |  | 7156, 7158 | Y |  |  |  | 100290 | 100289
100293 | Zorn_Load_Circuit_Breaker_Addition | Install a new 345-kV transmission point of interconnection to serve GVEC member load |  | Zorn |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7042 | Y |  |  |  | 100294 | 100293
91392 | Bergheim_Autotransformer_Upgrade | To improve efficiency and reliability of the transmission system, LCRA TSC will replace the existing Bergheim AT1 autotransformer with a higher capacity unit and install a second autotransformer at Bergheim Substation. |  | Bergheim |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7662 | 2028-05-15 |  | 345 | 0 | 12.7 | 672 |  | Comal | Comal | Tier 3 | 24RPG038 | 2024-12-17 | 2025-01-13 |  | 7170, 7770, 7771, 7772, 70170, 70493 | Y |  |  |  | 91408 | 91392
91628 | Upgrading Buda to Rutherford | Upgrading Buda to Rutherford branch to minimum 379 MVA. | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70498, 70509 | Y |  |  |  | 91629 | 91628
91293 | LCRATSC_Gabriel-Schwertner TL conversion | This project is needed to meet a request from BEPC to voltage convert (69-138-kV) and increase the capacity of the BEPC-owned Gabriel - Schwertner circuit on the TSC-owned 138-kV T359 transmission line. As part of this upgrade, LCRA TSC will upgrade conductor on T359 from Gabriel to Str. 21R. |  |  |  | Planned |  | LCRATSC | dylan.preas@lcra.org 512-578-4514 | PLC-8197 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7345, 7346, 7523 | Y |  |  |  | 91970 | 91293
92565 | Sim_Gideon_Winchester_Transmission_Line_Upgrade | LCRA TSC will upgrade Sim Gideon - Winchester 138-kV transmission line to achieve a higher operational rating |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7654 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7306, 7310 | Y |  |  |  | 92566 | 92565 | 2023-SC15
92572 | Lockhart Mendoza Transmission Line Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8191 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7206, 7215, 7216, 7325 | Y |  |  |  | 92573 | 92572 | 2024-SC20
92602 | Bastrop West - Bluebonnet Transmission Line Upgrade | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee. |  | 7555 | 7556 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org | PLC-8101 | 2028-05-15 |  | 138 | 0 | 6.1 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7555, 7556, 7561 | Y |  |  |  | 92603 | 92602 | 2024-SC20
17TPIT0001 | 36th St to Merida - 138 kV Transmission Line Rebuild | Rebuild approximately four circuit miles of 138 kV transmission from 36th Street to Merida |  | 5427 | 5310 | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0196 | 2028-05-15 |  | 138 | 0 | 2.95 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5427 | Y | N |  | There are no transformers associated with this project | 9559 | 2308
45136 | New Midtown 138kV Substation | New Mid Town substation looped into Comal St to Olmos transmission line. |  | 5311 | 5096, 5325 | Planned | S-0910 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0283 | 2028-05-15 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5096, 5311, 5325 | Y |  |  |  | 45137 | 45136
50645 | CPSE_Rafter 138kV Cap Bank |  |  | 5355 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0922 | 2028-05-15 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 4 | 24RPG004 |  | 2024-07-26 |  | 5355 | Y |  |  |  | 50646 | 50645
73762 | Peppergrass Substation Addition | American Electric Power (AEP) is building a new load serving substation and needs transmission service from the LCRA TSC owned 138-kV T470 Abilene South to McElmurray transmission line. LCRA TSC will install a new 138-kV bus and provide transmission service to the new AEP substation. |  | Peppergrass |  | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org | PLC-4477 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6260, 76316, 76317 | Y | N |  |  | 73763 | 73762
110180 | Harris Branch - Shadow Glen Transmission Line Upgrade | Upgrade the 2.97-mile Harris Branch - Shadow Glen 138-kV circuit to achieve a minimum 706 MVA emergency rating. This is an LCP Upgrade project to support Batch Zero Base Load |  | Harris Branch | Shadow Glen | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 2.97 | 0 |  | Travis | Travis | Tier 4 | [5 empty] | Y |  |  |  | 110181 | 110180
100285B | Comfort_Kendall_Transmission_Line_Upgrade |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 102393 | 100285
103308 | LCRATSC Lago Vista Substation Upgrade | LCRA TSC will improve reliability at the Lago Vista substation by replacing obsolete oil circuit breakers and its adjacent switches and making other improvements. |  | Lago Vista |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 | [5 empty] | Y |  |  |  | 103309 | 103308
111724 | Gossip 345 kV Switch | Establish Gossip 345 kV Switch |  | Gossip Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M43505 | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  | 2025-02-06 | 2026-03-19 |  | 1902, 1907, 15106 | Y |  |  |  | 111725 | 111724
110320 | Lomond 345 kV Switch Capacitor Banks | Establish Lomond 345 kV Switch Capacitor Banks |  | Lomond Switch | Lomond Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3521 | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1479 | Y |  |  |  | 112554 | 110320
113229 | Oncor_MNW_113229_Cashion_Switch | Establish Cashion 345 kV Switch POI for Nymphaea |  |  |  | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 |  | 2028-05-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 1730, 17030, 60224 | Y |  |  |  | 113230 | 113229
104832 | Oncor_MW_104832_CarolinaStorage_Switch | Establish Switch for Carolina Storage |  | Bowman Switch | Cobb Switch | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 |  | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1422, 1458, 15119 | Y |  |  |  | 104833 | 104832
105012 | Lomond_Switch_345kV | Establish Lomond 345 kV Switch |  | Bowman Switch | Fisher Road Switch | Planned | M3521 | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 |  | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 3 |  |  |  |  | 1422, 1425, 1479 | Y |  |  |  | 105013 | 105012
105312 | Alba Road 345 kV Switch | Establish Alba Road 345 kV Switch |  | Alba Road Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4385 | 2028-05-15 |  | 345 | 0 | 0 | 0 |  | Dallas |  | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2398, 2427, 2946, 3062 | Y |  |  |  | 105313 | 105312
105343 | Big Spring - Tributary Switch 138 kV Line | Rebuild the existing 14.0-mile Big Spring - Tributary Switch 138 kV line |  | Big Spring | Tributary | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8890 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 | 26RPG010 | 2026-03-03 | 2026-03-30 |  | 1322, 10119, 10206 | Y |  |  |  | 105344 | 105343
105418 | Establish Lufkin Chipper Mill Capacitor Bank | Establish Lufkin Chipper Mill Capacitor Bank |  | Lufkin Chipper Mill | Lufkin Chipper Mill | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6458 | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3349 | Y |  |  |  | 105419 | 105418
109788 | Upgrade LYLEWOLZ Cap Bank from 15.6 MVAR to 31.2 MVAR | LCRA will improve reliability at various substations by replacing capacitor banks |  | Lyle Wolz |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 | PLC-8446 | 2028-05-15 |  | 138 | 0 | 0 | 0 | 0,15.6 | Burleson |  | Tier 4 |  |  |  |  | 7567 | Y |  |  |  | 109789 | 109788
110014 | Install 138 kV Capacitor Bank at Hutto 138 kV Switch | Install 138 kV Capacitor Bank at Hutto 138 kV Switch |  | Hutto | Hutto | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6534 | 2028-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Williamson | Williamson | Tier 4 |  |  |  |  | 3666 | Y |  |  |  | 110015 | 110014
110026 | Upgrade Temple Switch - Voss Lake Switch - Sandow Switch 138 kV Line | Upgrade Temple Switch - Voss Lake Switch - Sandow Switch 138 kV Line |  | Temple | Sandow | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6531 | 2028-05-15 |  | 138 | 0 | 38.9 | 0 |  | Bell | Milam | Tier 1 | 25RPG009 |  |  |  | 3415, 3485, 3675, 3732, 3749, 3750, 13430 | Y |  |  |  | 110027 | 110026
110263 | A new Helotes 345kV substation will be constructed |  |  | 5201 | 5056, 5211, 5200 | Under Construction | S-0941 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0410 | 2028-05-15 |  | 345 | 0 | 0 | 1200 |  | Bexar | Bexar | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5056, 5200, 5201, 5211 | Y |  |  |  | 110264 | 110263
103271 | LCRATSC Aviation Substation Addition | The new Aviation Substation will be constructed along LCRA TSC transmission line T359 Gabriel to Glasscock. Aviation will serve GUS customer load. |  | Gabriel | Glasscock | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2028-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7346, 7523, 7531 | Y |  |  |  | 103272 | 103271
104635 | LCRATSC Garfield - Lytton Springs Transmission Line Upgrade | LCRA TSC will upgrade the Austrop - Zorn 345-kV double-circuit transmission line to achieve a higher operational rating. Coordinating PMCRs include 91312, 104635, and 104639. |  | 7048 | 9074 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8063, PLC-8139, PLC-8140 | 2028-05-16 |  | 345 | 0 | 24.7 | 0 |  | Bastrop | Caldwell | Tier 1 |  |  |  |  | 7034, 7042, 7048, 9074 | Y |  |  |  | 104637 | 104635 | 2024-SC19
93274B | Bastrop_Mesquite_Substation_Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-4500 | 2028-05-16 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7310, 7319, 7326 | Y |  |  |  | 110906 | 93274
93250B | Utley_Substation_and_Transmission_Line_Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8065 | 2028-05-16 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7316 | Y |  |  |  | 112220 | 93250
93274A | Bastrop_Mesquite_Substation_Addition |  |  | 7320 | 7320 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-4500 | 2028-05-16 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7310, 7316, 7320, 7322 | Y |  |  |  | 93305 | 93274
93679 | New BPUB substation |  |  | Loma Alta/CRONUS | NIMZO | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2028-05-25 |  | 138 | 24 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 5962, 59551 | Y |  |  |  | 93680 | 93679
77172 | Caravel: Construct New 138 kV Station | Interconnect the 1PointFive USA load to the new Caravel 138 kV station on the Barney Davis to Nelson Sharpe 138 kV line between Alazan and Barney Davis | Reactive Capability Update | Caravel |  | Planned |  | AEP TCC/ETT | LaRissa Lundry jlsolis@aep.com 361-881-5574 | TP2024088 | 2028-05-30 |  | 138 | 0 | 0 | 0 | 0,57.6 | Kleberg |  | Tier 4 |  |  |  |  | 8458, 8515, 80099 | Y |  |  |  | 77173 | 77172
78461A | West Columbia to Damon and Needville to Big Creek Ckt.89A Upgrades | Rebuild/reconductor portions of West Columbia to Damon Ckt.89A as a Hardening upgrade. |  | West Columbia | Damon | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-30 |  | 138 | 0 | 6.6 | 0 |  | Brazoria | Brazoria | Tier 4 | 23RPG021 | 2023-08-10 | 2023-08-31 | 2023-08-31 | 42370, 43380, 49914 | Y | N |  |  | 78462 | 78461
103450 | Bodkin: Construct New 138 kV Station | Interconnect Bowstring BESS to the new Bodkin 138 kV station on the Rincon to Whitepoint 138 kV line | Terminal "from" Update | Bodkin |  | Planned |  | AEP TCC | Lance Price jlsolis@aep.com 361-881-5574 | TP2025808 | 2028-05-30 |  | 138 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8418, 8961, 80329 | Y | N |  |  | 103451 | 103450
99644 | Victoria to Warburton: Rebuild 138 kV Line | Rebuild the Victoria to Warburton 138 kV line | Terminal from, Terminal to, and In-Service Date Update | Victoria | Warburton | Planned |  | AEP TCC | Charity Kreher deevans@aep.com 918-599-2938 | TA2022330 | 2028-05-30 |  | 138 | 0 | 14.64 | 0 |  | Victoria | Victoria | Tier 3 | 25RPG021 | 2025-06-27 | 2025-07-22 |  | 5607, 8172 | Y |  |  |  | 99645 | 99644
84894 | 23RPG028: STEC Rio Medina Project: Upgrade transmission line between Tally and Texas Research | Upgrade existing Talley to TX Research line (~8 miles) to at least 469 MVA with a two-hour emergency rating, based on preliminary review should not require pole replacement. This transmission rebuild is in support of the Rio Medina RPG Project. This rebuild would prevent overloading the transmission system under adverse conditions. |  | 5422 | 5430 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0392 | 2028-05-30 |  | 138 | 0 | 8 | 0 |  | Medina | Bexar | Tier 2 | 23RPG028 |  | 2024-02-16 |  | 5422, 5430 | Y |  |  |  | 84895 | 84894
91843 | East Munday: Rebuild 138 kV Station | Rebuild the East Munday 138 kV station | In-Service Date Update | East Munday |  | Planned |  | AEP TNC | Bill Edwards myturner@aep.com 918-599-2437 | TP2023800 | 2028-05-30 |  | 138 | 0 | 0 | 0 |  | Knox |  | Tier 4 | 25RPG002 | 2025-01-20 | 2025-02-12 |  | 6110, 6117, 6161, 6320 | Y | N |  |  | 91844 | 91843
109607 | Upgrade Ckt.25B Clodine to Roark to increase thermal limits. |  |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 44140, 48315 | Y |  |  |  | 109608 | 109607
73366 | New Wiseman 138kV Substation | Loop new 138 kV substation into existing 138kV Cagnon to Helotes Transmission Line. |  | 5487 | 5055, 5200 | Planned | T-0317 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0934 | 2028-05-30 |  | 138 | 0 | 0 | 0 |  | Bexar |  | Tier 4 |  |  |  |  | 5055, 5200, 5487 | Y |  |  |  | 73367 | 73366
90255F | Jordan / Mont Belvieu Area Improvement Project | Install new CEHE-owned Sjolander substation. Reconfigure existing Ckt.84D Cedar Bayou to CD/HOPSON and loop into Sjolander substation to create new Ckt.84 Cedar Bayou to Cedar Bayou tap to Sjolander to HOPSON. |  | Sjolander | Cedar Bayou /HOPSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-30 |  | 138 | 2 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40015, 40050, 41690, 48065 | Y | N |  |  | 111231 | 90255
99009A | 138kV Flewellen to Fort Bend Ckt 09G-60E Upgrades | Upgrade Ckt.09G Flewellen to Brazos Valley to increase thermal limits. Expect 2-959ACSS reconductor as first phase of Ckt.09G upgrade. |  | Flewellen | Brazos Valley | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-30 |  | 138 | 0 | 5.03 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 25RPG010 | 2025-03-26 | 2025-04-18 | 2025-04-18 | 44100, 44230 | Y | N |  |  | 99010 | 99009
111323E | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.06L Plaza to Knight to Gulfgate to increase thermal limits. |  | Plaza | Gulfgate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-30 |  | 138 | 0 | 9.03 | 0 |  | Chambers | Chambers | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 47350, 48126, 48199 | Y | N |  |  | 111335 | 111323 | 26RPG006
90255H | Jordan / Mont Belvieu Area Improvement Project | Install new CEHE-owned Sjolander substation. Reconfigure existing Ckt.86 CHEVRON to Kilgore to LANGSTON and loop into Sjolander substation to create new Ckt.86 Sjolander to Kilgore to LANGSTON. |  | Kilgore | Sjolander/LANGSTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-30 00:01 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40050, 44830 | Y | N |  |  | 111233 | 90255
90255G | Jordan / Mont Belvieu Area Improvement Project | Install new CEHE-owned Sjolander substation. Reconfigure existing Ckt.86A Cedar Bayou to CHEVRON and loop into Sjolander substation to create new Ckt.86 Cedar Bayou to Sjolander to Kilgore to Langston. |  | Cedar Bayou | Sjolander | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-30 00:01 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40015, 40050, 40300 | Y | N |  |  | 111232 | 90255
90255I | Jordan / Mont Belvieu Area Improvement Project | Install new CEHE-owned Sjolander substation. Disconnect existing circuits 86A and 86B from CHEVRON customer substation. Reconnect CHEVRON substation to Sjolander substation as Ckt.13 Sjolander to CHEVRON and Ckt.23 Sjolander to CHEVRON. |  | Sjolander | CHEVRON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-30 00:02 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 3 | 24RPG026 | 2024-08-21 | 2024-09-12 | 2024-09-12 | 40050, 40300, 44830 | Y | N |  |  | 111234 | 90255
76196 | Lobo: 138 kV Breaker Replacement | Replace 138 kV breakers at the Lobo 138 kV station | Company Contact Update | Lobo |  | Planned |  | AEP TCC | Bradley Case jlsolis@aep.com 361-881-5574 | TP2023015 | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80221 | Y |  |  |  | 76197 | 76196
104559A | Hockley Distribution Transformer Addition with Upgrades | Install 3rd Transformer and 8th 35 kV feeder at Hockley distribution substation |  | Hockley |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 45880 | Y | N |  |  | 104560 | 104559
75830A | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). Loop Ckt.27 into Savannah substation to create new Ckt.27 Seabreeze to Savannah to Oasis. |  | Savannah | Seabreeze/Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 42590, 43020, 43035, 43180 | Y | N |  |  | 102674 | 75830
100534 | Misty Substation Addition | LCRA TSC will construct a new load-serving Misty Substation cut-in to T185 Austrop - Zorn & T246 Lytton Springs - Zorn 345-kV double-circuit transmission line. |  | Misty |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8282 | 2028-05-31 |  | 345 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7034, 7042, 7051, 9074 | Y |  |  |  | 100535 | 100534
110075A | Install Morton 138/35kV Distribution Substation with double-tap service. | Install Morton 138/35kV Distribution Substation with double-tap service. Tap Ckt.09H to create new Ckt.09H Katy to Morton to Franz |  | Morton | Katy /Franz | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Waller | Tier 4 |  |  |  |  | 44260, 44420, 45031, 48431 | Y | N |  |  | 110904 | 110075
109920 | Rebuild Bandera to Hamilton Wolfe 138kV Transmission Line |  |  | 5020 | 5187 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0417 | 2028-05-31 |  | 138 | 0 | 1.87 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5020, 5187 | Y |  |  |  | 109921 | 109920
104607 | Pronto: Expand 345 kV Station | Interconnect Half Moon Solar to the existing Pronto 345 kV station | NEW | Pronto |  | Planned | TP2025797 | AEP/ETT | Glen Reed gareed@aep.com 918-599-2664 |  | 2028-05-31 |  | 345 | 0.25 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 80231 | Y |  |  |  | 104608 | 104607
104611 | Asherton: Expand 138 kV Station | Interconnect Wilks data center load to the existing Asherton138 kV station | Terminal "from" Update | Asherton |  | Planned | TP2026003 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | Asherton | 2028-05-31 |  | 138 | 0.4 | 0 | 0 |  | Dimmit |  | Tier 4 |  |  |  |  | 8283, 80418 | Y |  |  |  | 104612 | 104611
99274A | Cedar Bayou RPG - Substation Upgrades (25RPG014) | Replace existing 600 MVA 345/138kV Cedar Bayou Auto A1 with new 800 MVA autotransformer. Install 2.5-Ohm reactor in-series with new CBY-A1 on the 138kV side of the autotransformer. |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 345 | 0 | 0 | 200 |  | Chambers |  | Tier 3 | 25RPG014 | 2025-05-22 | 2025-06-13 | 2025-06-16 | 40000, 40010, 40040, 49005 | Y | N |  |  | 99275 | 99274
99274B | Cedar Bayou RPG - Substation Upgrades (25RPG014) | Replace existing Cedar Bayou parallel 345/138kV autotransformers 2A/2B with new 800 MVA autotransformer as CBY-A2. Remove existing 10-Ohm reactor from the 138kV side of the 2A/2B parallel autotransformers. Replace with 2.5-Ohm reactor in-series with new CBY-A2 on the 138kV side of the autotransformer. |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 345 | 0 | 0 | 0 |  | Chambers |  | Tier 3 | 25RPG014 | 2025-05-22 | 2025-06-13 | 2025-06-16 | 40000, 40005, 40015, 40030, 49006, 49007 | Y | N |  | Cost included in main entry | 99276 | 99274
99274C | Cedar Bayou RPG - Substation Upgrades (25RPG014) | Install 2.5-Ohm reactor in-series with existing Cedar Bayou A3 on the 138kV side of the autotransformer. |  | Cedar Bayou |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Chambers |  | Tier 3 | 25RPG014 | 2025-05-22 | 2025-06-13 | 2025-06-16 | 40000, 40015, 40020, 49008 | Y | N |  | Cost included in main entry | 99277 | 99274
99802 | Aetos: Construct New 138 kV Station | Interconnect Paradiso BESS to the new Aetos 138 kV station on the Big Foot to Pleasanton 138 kV line | Company Contact and In-Service Date Update | Aetos |  | Planned |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 | TP2025254 | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  |  | 8203, 8221, 80297 | Y |  |  |  | 99803 | 99802
99863 | Doffing: Construct New Distribution Station | Construct new distribution station on the Stewart Road to Hi-Line 138 kV line |  | Doffing |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 5778, 8951, 80294, 80298 | Y |  |  |  | 99864 | 99863
99933 | La Plaza: Construct New Distribution Station | Construct new distribution station on the Polk Avenue to South McAllen 138 kV line between Hall Acres and South McAllen |  | La Plaza |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | DP25X0035 | 2028-05-31 |  | 138 | 0.6 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8371, 8760, 80300 | Y |  |  |  | 99934 | 99933
84896 | 23RPG028: STEC Rio Medina Project: New 138kV Legend Falls Substation | New 138kV Legend Falls Substation looped into the existing Tally to Texas Research transmission line. This station supports the RPG approved Rio Medina project |  | 5259 | 5422, 5430 | Planned | T-0413 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1055 | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Medina |  | Tier 2 | 23RPG028 |  | 2024-02-16 |  | 5259, 5422, 5430 | Y |  |  |  | 84897 | 84896
86829 | Fort Stockton Plant to Lynx: Rebuild 138 kV Line | Rehab the Fort Stockton Plant to Lynx 138 kV line | Company Contact and In-Service Date Update | Fort Stockton Plant | Lynx | Planned | TA2020218 | AEP TNC | Damian Raab myturner@aep.com 918-599-2437 |  | 2028-05-31 |  | 138 | 0 | 37 | 0 |  | Pecos | Pecos | Tier 4 | 23RPG008 | 2023-04-14 | 2023-05-05 |  | 6630, 6671, 60400 | Y | N |  |  | 86830 | 86829
86857 | Blessing: Install New 345 kV Cap Bank | Install new capacitor bank at the Blessing 345 kV station | In-Service Date Update | Blessing |  | Planned |  | AEP TCC | LaRissa Lundry deevans@aep.com 918-599-2938 | TP2023803 | 2028-05-31 |  | 345 | 0 | 0 | 0 | 0,130.9 | Matagorda |  | Tier 4 |  |  |  |  | 8123 | Y |  |  |  | 86858 | 86857
91537 | Starlite_Substation_Addition | LCRA TSC will construct the 138-kV Starlite Substation to facilitate the Generation Interconnection Request (GINR) submitted for by the Interconnecting Entity, "Blanquilla BESS LLC" (Generator). |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-05-31 | 2027-03-31 | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8452, 78569, 78570 | Y |  |  |  | 91538 | 91537
93224 | Eastpoint: Construct New Distribution Station | Construct new distribution station on the North Laredo Switch to Wormser Road 138 kV line between Gateway West Tap and Unitec |  | Eastpoint |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-05-31 |  | 138 | 7.2 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8080, 8134, 8650 | Y |  |  |  | 93225 | 93224
98997 | Rebuild/reconductor Ckt.89A West Columbia to Damon and Ckt.89A Damon to Needville to increase thermal limits. Upgrade Ckt.89A West Columbia equipment to increase thermal limits. | Rebuild/reconductor Ckt.89A West Columbia to Damon (3.74 miles) and Ckt.89A Damon to Needville (10.1 miles) to increase thermal limits. Upgrade Ckt.89A West Columbia equipment to increase thermal limits. |  | West Columbia | Needville | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 13.84 | 0 |  | Brazoria | Brazoria | Tier 3 | 25RPG011 | 2025-05-05 | 2025-05-28 | 2025-05-28 | 42370, 42380, 43380, 49914 | Y | N |  | Cost included in main entry | 98998 | 98997
99009C | 138kV Flewellen to Fort Bend Ckt 09G-60E Upgrades | Upgrade Ckt.60E Flewellen to Fort Bend to increase thermal limits. Expect 2-959ACSS reconductor as first phase of Ckt.60E upgrade |  | Flewellen | Fort Bend | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 8.63 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 25RPG010 | 2025-03-26 | 2025-04-18 | 2025-04-18 | 44230, 44280 | Y | N |  | Cost included in main entry | 99012 | 99009
102544 | Expand Sjolander 9-breaker BAAH substation to 12-breaker BAAH for a total of four line positions to Chevron. Relocate existing Sjolander Ckt.84 to Cedar Bayou to new line position. |  |  | Sjolander | Cedar Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 102545 | 102544
111323G | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.79F PH Robinson to Seabrook to HANNA to HUNTER in order to increase thermal limits. |  | PH Robinson | HUNTER | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 9.97 | 0 |  |  |  | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 42010, 42780, 42830, 48282, 48852 | Y | N |  |  | 111336 | 111323 | 26RPG006
111323H | Upgrades related to the Baytown Area Load Addition | Install (3) 7.2 MVAR distribution cap banks at Bayway substation. |  | Bayway |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,21.6 |  |  | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 42170 | Y | N |  |  | 111337 | 111323 | 26RPG006
111323I | Upgrades related to the Baytown Area Load Addition | Install (1) 60 MVAR cap bank at Mykawa substation. |  | Mykawa |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,60 |  |  | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 42750 | Y | N |  |  | 111338 | 111323 | 26RPG006
111323J | Upgrades related to the Baytown Area Load Addition | Install (1) 60 MVAR switchable cap bank at Humble substation. |  | Humble |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,60 |  |  | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 40830 | Y | N |  |  | 111339 | 111323 | 26RPG006
111323B | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.86 DALTON (to RAOULT) to BRINE to increase thermal limits. |  | DALTON | BRINE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 3.39 | 0 |  | Chambers | Chambers | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 40220, 40740, 41740 | Y | N |  |  | 111340 | 111323 | 26RPG006
111323D | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.08 Hermann to Grant to increase thermal limits. |  | Hermann | Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0.97 | 0 |  | Harris | Harris | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 45120, 47110 | Y | N |  |  | 111341 | 111323 | 26RPG006
111323A | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.84K HOPSON to WARVUE to increase thermal limits. |  | HOPSON | WARVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 1.27 | 0 |  | Chambers | Chambers | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 41690, 41700 | Y | N |  |  | 111342 | 111323 | 26RPG006
111323C | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.03G Lyondell to Channelview (distribution) to Channelview (ring bus) in order to increase thermal limits. |  | Lyondell | Channelview | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 40280, 40281 | Y | N |  |  | 111343 | 111323 | 26RPG006
111323F | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.73B Britmoore to Woodcreek to Memorial to Westheimer in order to increase thermal limits. |  | Britmoore | Westheimer | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 7.19 | 0 |  |  |  | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 44120, 44780, 48246, 48398 | Y | N |  |  | 111344 | 111323 | 26RPG006
111323K | Upgrades related to the Baytown Area Load Addition | Install (2) 14.4 MVAR distribution cap banks at Treaschwig substation. |  | Treaschwig |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,28.8 |  |  | Tier 3 |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | 46550 | Y | N |  |  | 111345 | 111323 | 26RPG006
109585B | TEXPET Customer and Area 138kV Conversions. | Expand Mag Park 138kV substation and upgrade to 63KA fault duty. Reposition Ckt.08C Mag Park to NINTH to expanded substation position and remove existing MP-TR5 service from this circuit. |  | Mag Park | NINTH | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y |  |  |  | 109669 | 109585
110649 | Loop in 345 kV double circuit lines from Singleton to Jewett into Iron Horse substation |  |  | Limestone | Twin Oak | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-05-31 |  | 345 | 10 | 0 | 0 |  | Limestone | Robertson | Tier 3 | [5 empty] | N | N |  |  | 110650 | 110649
110655 | Loop in 345 kV double circuit lines from Limestone to Twin Oak into Iron Horse substation |  |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-05-31 |  | 345 | 10 | 0 | 0 |  |  |  | Tier 3 | [5 empty] | N | N |  |  | 110656 | 110655
110182 | Add 230 MVAr of cap bank |  |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-05-31 |  | 345 | 0 | 0 | 0 | 0,230 | Leon | Leon | Tier 4 | [5 empty] | N | N |  |  | 110183 | 110182
99000B | Install (2) 14.4 MVAR distribution cap banks at Twinwood substation. Install (2) 14.4 MVAR distribution cap banks at Fulshear substation. Install (2) 40 MVAR transmission cap bank at Peters substation. | Install (1) 40 MVAR transmission cap bank at Peters substation. (first of two) |  | Peters |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,40 | Fort Bend |  | Tier 4 |  |  |  |  | 46220 | Y | N |  |  | 109555 | 99000
109571 | Upgrade Ckt.86E Newport to King to Jonte to increase thermal limits. |  |  | Newport | Jonte | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 11.21 | 0 |  | Harris | Harris | Tier 3 | 26RPG019 | 2026-05-07 | 2026-05-29 | 2026-06-01 | 41150, 45660, 48182 | Y |  |  |  | 109572 | 109571
109573 | Upgrade Ckt.60A Fort Bend to Rosenberg to increase thermal limits. |  |  | Fort Bend | Rosenberg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44280, 44615 | Y |  |  |  | 109574 | 109573
109603A | HO Clarke to University 69kV to 138kV Conversion. | Upgrade portions of retired 69kV Ckt.12 Clinton to Garden Villas (4.7 miles) in preparation for 138kV conversion. Upgrade portions of existing 69kV Ckt.19A Garden Villas to HO Clarke (7.6 miles) in preparation for 138kV conversion. Retire Ckt.19A and reconnect rebuilt circuits to create new 138kV Ckt.xx HO Clarke to University. Retire/remove Garden Villas 69kV facilities including auto A1. |  | HO Clarke | University | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 12.3 | 0 |  | Harris | Harris | Tier 3 | 26RPG011 | 2026-03-06 | 2026-03-27 | 2026-03-30 | 42680, 42690, 47160, 47170, 47760, 49016 | Y |  |  |  | 109604 | 109603
109603B | HO Clarke to University 69kV to 138kV Conversion. | Reconductor portions (2.27 miles) of Ckt.08L HOC to Bunker as part of Ckt.19A Garden Villas to HO Clarke pre-conversion rebuild. |  | HO Clarke | University | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 2.27 | 0 |  | Harris | Harris | Tier 3 | 26RPG011 | 2026-03-06 | 2026-03-27 | 2026-03-30 | 47150, 47340 | Y |  |  | Cost included in main entry | 109605 | 109603
109603C | HO Clarke to University 69kV to 138kV Conversion. | Reconductor portions (2.48 miles) of Ckt.06L Knight to Gulfgate as part of Ckt.19A Garden Villas to HO Clarke pre-conversion rebuild. |  | Plaza | Gulfgate | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 2.48 | 0 |  | Harris | Harris | Tier 3 | 26RPG011 | 2026-03-06 | 2026-03-27 | 2026-03-30 | 48126, 48199 | Y |  |  | Cost included in main entry | 109606 | 109603
109640 | Convert existing Needville 138/12kV distribution substation to 138/35kV. Remove existing Big Creek 138/12kV distribution substation to create new Ckt.89B Needville to Pleak. |  |  | Needville | Pleak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42370, 42380, 42389, 42390, 44680 | Y |  |  |  | 109642 | 109640
109646 | Install Pine Island (PNI) 35kV Distribution Substation. Loop on Ckt.65B to create new Ckt.65B Waller (tap) to Pine Island to Peters. |  |  | Pine Island | Waller / Peters | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  |  | 44940, 46220, 48564 | Y |  |  |  | 109647 | 109646
99409 | Hockley Cap Bank Addition | Hockley Cap Bank Addition, originally added to cases as part of Project 91713 |  | Hockley |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,40 | Harris |  | Tier 4 |  |  |  |  | 45880 | Y | N |  |  | 109836 | 99409
110075B | Install Morton 138/35kV Distribution Substation with double-tap service. | Install Morton 138/35kV Distribution Substation with double-tap service. Tap Ckt.09K to create new Ckt.09K Village Creek to Morton to Franz. |  | Morton | Village Creek /Franz | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44260, 45033, 48272, 48432 | Y |  |  | Cost included in main entry. | 110905 | 110075
109585A | TEXPET Customer and Area 138kV Conversions. | Remove 69kV TEXPET customer substation facilities. Install new 138kV TEXPET customer substation. Expand Clinton 138kV and Mag Park 138kV substations. Deenergize the non-upgraded portions of Ckt.33x. Energize the rebuilt portions of Ckt.33x as 138kV Ckt.xx Mag Park to TEXPET 138kV to Deepwater. Expect this circuit position at Mag Park to take over the existing MP-TR5 transformer service. |  | TEXPET | Clinton/Deepwater | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y |  |  |  | 109670 | 109585
75830B | New 345kV Savannah (SAV) substation for generator interconnection to Cascade Solar (23INR0091). | Install generator lead from Savannah (SAV) substation to CASCAD (CSC) customer substation (23INR0091). |  | Savannah | CASCAD | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43180, 113752 | Y | N |  |  | 102675 | 75830
109585C | TEXPET Customer and Area 138kV Conversions. | De-energize 69kV Ckt.16C Deepwater to South Channel. De-energize 69kV Ckt.23A Deepwater to South Channel. De-energize 138/69kV South Channel auto A1 and all remaining South Channel 69kV facilities. Retire all remaining Deepwater 69kV facilities. |  | Deepwater | South Channel | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 00:02 |  | 69 | 0 | 0 | -316 |  | Harris | Harris | Tier 4 | [5 empty] | Y |  |  |  | 109672 | 109585
109585D | TEXPET Customer and Area 138kV Conversions. | De-energize 69kV Ckt.10A Clinton to Greens Bayou. De-energize 138/69kV Clinton auto A1 and all remaining Clinton 69kV facilities. De-energize 138/69kV Greens Bayou auto A5 and all remaining Greens Bayou 69kV facilities. |  | Clinton | Greens Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 00:02 |  | 69 | 0 | 0 | -536 |  | Harris | Harris | Tier 4 | [5 empty] | Y |  |  |  | 109671 | 109585
91399 | Bitter_Creek_Substation_Upgrade | Oncor will upgrade the existing 345-kV double-circuit transmission lines Bitter Creek - Morgan Creek (Cattleman) and Bitter Creek - Sweetwater East. Part of the Permian Basin Reliability Plan released by ERCOT, under transmission upgrades L24 |  | Bitter Creek | Bitter Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8256 | 2028-06-01 |  | 345 | 0 | 0 | 0 |  | Nolan | Nolan | Tier 4 | [5 empty] | Y |  |  |  | 91400 | 91399
70282 | New 138kV Brushy Creek Substation |  |  | Thompson Creek | Snook | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 138 | 2.81 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32857, 32863, 32867 | Y |  |  |  | 104056 | 70282
80420 |  | Rebuild / Reconductor Greens Prairie to South Switch 138kV Line |  | Bryn South Switch | Greens Pairie | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 138 | 0 | 4.5 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32007, 32878, 32880, 32893 | Y |  |  |  | 80421 | 80420
92734 | Construct Mascho - Border - Drill Hole 345 kV DCKT Line | Construct Mascho - Border - Drill Hole 345 kV DCKT Line. Also adds Permian Basin Reliability Plan Upgrade ID L2B. Loop the Stage 5 upgrade of new Clearfork - Drill Hole 345-kV double-circuit line into the new Border 345-kV substation |  | Mascho | Drill Hole | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8792 R8802 R8803 | 2028-06-01 |  | 345 | 196.8 | 0 | 0 |  | Andrews | Culberson | Tier 1 | 24RPG015 | 2024-05-17 | 2025-06-26 |  | 10073, 18718, 18879 | Y |  |  |  | 105929 | 92734
110909 | Rebuild Tri County to Parkway and Fratt to Parkway 138kV circuits |  |  | 5156, 5445 | 7611 | Conceptual |  | CPS/LCRA | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5165, 5445, 7611 | N |  |  |  | 110910 | 110909
110911 | Helotes to Hill Country 2nd Ckt Addition and Rebuild |  |  |  |  | Conceptual | S-XXXX | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2028-06-01 |  | 345 | 9 | 9 | 0 |  |  |  | Tier 1 |  |  |  |  | 5201, 5211 | N |  |  |  | 110912 | 110911
110921 | Add Reactive Support at Spruce |  |  |  |  | Conceptual |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5110 | N |  |  |  | 110922 | 110921
100678 | Install a 50MVAr Capacitor Bank at Fratt Substation |  |  | 5165 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 4 |  |  |  |  | 5165 | Y |  |  |  | 100679 | 100678
100693 | Install a 35.72MVAr Capacitor Bank at Legend Falls Substation |  |  | 5259 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 | 0,35.72 | Medina |  | Tier 4 |  |  |  |  | 5259 | Y |  |  |  | 100694 | 100693
103257 | Models TNMP Galveston RPG study |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2028-06-01 |  | 138 | 3.1 | 21.4 | 0 |  | Galveston | Brazoria | Tier 2 |  |  |  |  | 38820, 38830, 38900, 38920, 38930, 38950, 38980, 38990, 39010, 39015, 39030, 42015 | Y |  |  |  | 103258 | 103257
103787 | BRYN_ColeLane | Construct Cole Lane 138-kV Substation by cutting into the existing Keith Switch to Steep Hollow 138-kV transmission line. |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 2, 32850, 32879 | Y |  |  |  | 103796 | 103787
103820 | BRYN_Snook_Rebuild | Rebuild Snook Substation to remove the 69-kV bus and transfer distribution load to the 138-kV bus. |  | BTU Snook |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  | Burleson | Burleson | Tier 4 |  |  |  |  | 32857, 32865 | Y |  |  |  | 103830 | 103820
80424 |  | Rebuild / Reconductor Dansby to Business Park 69kV for Rail Spur |  | Dansby | Bryn Business Park | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 69 | 0 | 3.3 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32871, 32875 | Y |  |  |  | 80425 | 80424
99022 | Border - Quarry Field 345 kV double-circuit line | Add Permian Basin Reliability Plan Upgrade ID L2C Add a new Border - Quarry Field 345-kV double-circuit line |  | Border | Quarry Field | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L2_C | 2028-06-01 |  | 345 | 23.6 | 0 | 0 |  | Loving | Loving | Tier 2 |  |  |  |  | 11188, 18718 | Y |  |  |  | 99023 | 99022
99100A | BRYN_99100_RELLIS_CAPS | Install first 54 MVAr (in three 18 MVAr stages) 138-kV capacitor bank at RELLIS |  | RELLIS |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 | 0,54 | Brazos |  | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32780 | Y |  |  |  | 99152 | 99100
99100B | BRYN_99100_RELLIS_CAPS | Install second 54 MVAr (in three 18 MVAr stages) 138-kV capacitor bank at RELLIS |  | RELLIS |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 | 0,54 | Brazos |  | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32780 | Y |  |  |  | 99153 | 99100
99516 | Upgrading line to bundled drake | [6 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70524, 70525 | Y |  |  |  | 99517 | 99516
99520 | Union (fka Sun) - Ranger Camp 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22B. Upgrade the existing Union (fka Sun) - Ranger Camp 138-kV line. |  | Union | Dermott | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_B | 2028-06-01 |  | 138 | 0 | 32.88 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  |  | 10050, 18555 | Y |  |  |  | 99521 | 99520
70299 | New Holleman Substation | [6 empty] | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 32005, 32892, 32893 | Y |  |  |  | 88269 | 70299
91621 | Adding Highway 71 between Wirtz and Johnson city | Adding highway 71 into the model Summer 2028 | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2028-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7104, 70003, 70516 | Y |  |  |  | 91622 | 91621
14TPIT0038 | Northland to Mag Plant Circuit 979 Upgrade | Reconductor the existing Northland to Mag Plant circuit from single 795SCAR to bundle 795 ACSR Drake and increase rating to 3000 Amp |  | Northland Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | NEW | 2028-06-01 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  | Will add the project to the base case | 9723 | 2443
110453 | STEC Hammer Load Project Phase 2 | -Tap STEC San Miguel to Cruce 345kV ckt 1 to create a new 345kV station -Install 2 345/138kV autos and expand the new station to a 345/138 station - Construct and approximately 18.25 mile 138kV transmission line from the new 138kV station to STEC George West |  | George West, San Miguel | Cruce | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-06-01 12:15 |  | 138 | 0 | 18.25 | 0 |  | Live Oak | Live Oak | Tier 3 | [5 empty] | Y | N |  |  | 110454 | 110453
64067 | Bessel to King Ranch: 138 kV Line Rebuild | Rehab the Bessel to King Ranch 138 kV line | In-Service Date Update | Bessel | Stratton | Planned |  | AEP TCC | Sally Matthews deevans@aep.com 918-599-2938 | TA2020081 | 2028-06-15 |  | 138 | 0 | 26.59 | 0 |  | Nueces | Kleberg | Tier 4 | 23RPG001 | 2023-01-25 | 2023-02-24 |  | 8060, 8498, 8512, 8513, 8514, 8665, 80228 | Y |  |  |  | 64068 | 64067
81895 | BPUB Branch Changes | Removing branch Price to Loma, adding Price to Stillman, adding another branch Loma Alta to Stillman. |  | 59410, 5962 | 79601, 79601 | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2028-06-23 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5962, 59410, 79601 | Y |  |  |  | 81896 | 81895
79451B | Loop new Ancla CEHE 138kV substation into Ckt.04E Angleton to West Columbia to create new Ckt.04 Angleton to Ancla to West Columbia. Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. | Install one generator lead from Ancla CEHE 138kV substation to ROYAL / Royal River BESS. |  | Ancla | ROYAL | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-06-28 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 46630, 115323 | Y | N |  |  | 87174 | 79451
109847B | DRILCO Area improvements in support of proposed load addition. | Upgrade Substation equipment at Humble and Treaschwig to increase rating of ckt 66 |  | Humble | Treaschwig | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-06-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  | Cost included in Main Entry | 109938 | 109847
110162 | County Line - Garfield Transmission Line Addition | LCRA TSC will construct a new 138-kV transmission line between County Line and Garfield substations. Project marked as conceptual for the moment as this project is also identified as an LCP Upgrade project to support Batch Zero Base Load. |  | County Line | Garfield | Conceptual |  | LCRATSC | Dylan Preas dylan.preas.@lcra.org 512-578-4514 |  | 2028-06-30 |  | 138 | 1.4 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 | [5 empty] | Y |  |  |  | 110163 | 110162
109769A | This models upgrades related to the Willow Phase 3 Load addition | Build a new 138 kV circuit between Tomball and T.H. Wharton using the open circuit position on the existing double circuit towers. Loop the new circuit into Willow substation creating TH Wharton to Willow to Tomball. |  | Willow | Tomball/TH Wharton | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-06-30 |  | 138 | 13.46 | 0 | 0 |  | Harris | Harris | Tier 3 | 26RPG023 | 2026-05-28 | 2026-06-23 |  | 45940, 46510, 46660 | N | N |  |  | 109942 | 109769
91567 |  |  |  | New station Rhew | New station Rhew | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-06-30 |  | 345 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 3, 5133, 5901 | Y |  |  |  | 91568 | 91567
91386 | Smithville_Substation_Upgrade | Increase the reliability of the Smithville substation by replacing assets identified as a high failure risk, removing the 138x69-kV auto transformer, and converting T344 New Rosanky - Smithville to 138-kV |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7727 | 2028-06-30 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7314, 7315, 7558 | Y |  |  |  | 91387 | 91386
111459 | Upgrade Driscoll - San Diego | Upgrade Driscoll - Central - Ben Bolt - San Diego |  | Driscoll | San Diego | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-06-30 |  | 69 | 0 | 32.66 | 0 |  | Nueces | Duval | Tier 4 |  |  |  |  | 5640, 5652, 5653, 5654 | Y |  |  |  | 111460 | 111459
93088B | Cattleman - Champion Creek/Bitter Creek - Sweetwater East 345-kV Double-Circuit Line Rebuild 345 kV Double-Circuit Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L24A. LCRA and Oncor joint project to add L24A Upgrade the existing Cattleman - Champion Creek/Bitter Creek - Sweetwater East 345-kV double-circuit line |  | Cattleman | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L24_A | 2028-06-30 |  | 345 | 0 | 0 | 0 |  | Nolan | Mitchell | Tier 1 |  | 2023-09-29 |  |  | 1414, 10053, 10105, 11420, 71050 | Y |  |  |  | 111640 | 93088
109751 | Big Sandy Circuit Breaker Addition | Provide transformation by installing circuit breakers for 138-kV bus terminations on the transmission bus at Big Sandy Substation |  | Big Sandy |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-06-30 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  |  | 7316 | Y |  |  |  | 109752 | 109751
109759 | Hardening Project for circuit 05 WAP to Missouri City(26RPG021). | Hardening Project for circuit 05 WAP to Missouri City(26RPG021). |  | HO Clarke | Missouri City | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-06-30 |  | 138 | 0 | 9.62 | 0 |  | Harris | Harris | Tier 4 | 26RPG021 | 2026-05-21 | 2026-06-12 | 2026-06-15 | 44010, 48237, 48336 | Y | N |  |  | 109760 | 109759
109761 | Rebuild/reconductor portions of Ckt.05D Missouri City to Westchase as a Hardening Upgrade(26RPG024). | Rebuild/reconductor portions of Ckt.05D Missouri City to Westchase as a Hardening Upgrade(26RPG024). |  | Westchase | Missouri City | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-06-30 |  | 138 | 0 | 8.5 | 0 |  | Harris | Fort Bend | Tier 3 | 26RPG024 | 2026-06-03 | 2026-06-24 | 2026-06-25 | 44670, 44760, 48162, 48358, 49911 | Y | N |  |  | 109762 | 109761
70712 | SAPS to Red Creek: Rebuild 138 kV Line | Rehab the SAPS to Red Creek 138 kV line | In-Service Date, Dollars and Miles Rebuild Update | SAPS | Red Creek | Planned |  | AEP TNC | Sally Matthews myturner@aep.com 918-599-2437 | TA2020210 | 2028-06-30 |  | 138 | 0 | 18.62 | 0 |  | Tom Green | Tom Green | Tier 3 | 26RPG003 | 2026-02-28 | 2026-03-31 |  | 6442, 6473, 6480, 60008 | Y |  |  |  | 70713 | 70712
109769B | This models upgrades related to the Willow Phase 3 Load addition | Disconnect Willow substation from existing ckt.81 leaving a T.H. Wharton to Klein ckt.81. |  | TH Wharton | Klein | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-06-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 26RPG023 | 2026-05-28 | 2026-06-23 |  | 45510, 45940 | N | N |  |  | 109943 | 109769
109769C | This models upgrades related to the Willow Phase 3 Load addition | Reconfigure 138 kV ckt.81 Tomball to Mill Creek to Pinehurst to Kluge by looping the Pinehurst to Kluge ckt.81 segment into Tomball creating the following circuit Tomball to Mill Creek to Pinehurst to Tomball. |  | Tomball | Pinehurst | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-06-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 26RPG023 | 2026-05-28 | 2026-06-23 |  | 45952, 46240, 46510 | N | N |  | Cost included in main entry. | 109944 | 109769
109769D | This models upgrades related to the Willow Phase 3 Load addition | Reconfigure 138 kV ckt.81 Tomball to Mill Creek to Pinehurst to Kluge to create a new cicuit from Kluge to Tomball |  | Kluge | Tomball | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-06-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 26RPG023 | 2026-05-28 | 2026-06-23 |  | 45952, 46510 | N | N |  | Cost included in main entry. | 109945 | 109769
103259 | Llano: Build new 69 kV Station | Interconnect PEC's New Junction Station to the Junction to Mason Switch 69 kV Line | NEW | Llano |  | Planned |  | AEP TNC | Jonathon Reith myturner@aep.com 918-599-2437 |  | 2028-06-30 |  | 69 | 0 | 0 | 0 |  | Kimble |  | Tier 4 |  | 2026-02-10 |  | 2026-02-10 | 6399, 6400, 60267, 60774, 70600 | Y | N |  |  | 103260 | 103259
103459 | Clear Crossing: Expand 345 kV Station | Interconnect the Google Ranger load to the existing Clear Crossing 345 kV station | Project Description and Transmission Owner Update | Clear Crossing |  | Planned |  | ETT/AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2025843 | 2028-06-30 |  | 345 | 3.4 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60262, 60263, 60515 | Y | N |  |  | 103460 | 103459
86791 | Crane to Rio Pecos: Rebuild 138 kV Line | Rebuild the Crane to Rio Pecos 138 kV line | In-Service Date Update | Crane | Rio Pecos | Planned | TP2024050 | AEP TNC | Damian P Raab twang1@aep.com 918-599-2635 |  | 2028-06-30 |  | 138 | 0 | 23.65 | 0 |  | Crane | Crockett | Tier 1 | 23RPG023 | 2023-08-11 | 2024-01-18 | 2024-01-24 | 6601, 76615 | Y | N |  |  | 86792 | 86791
90000 | Upgrade San Diego - Orange Grove SW | Upgrade San Diego - Orange Grove SW to 795 ACSR. 2024 RTP |  | San Diego | Orange Grove SW | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-06-30 |  | 69 | 0 | 21.56 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5654, 5658 | Y |  |  |  | 90001 | 90000
110240 | Southeast Brownsville Large load transmission system improvements project | -Construct a new Portsouth 138-kV substation with six terminals: Hairpin the new Portsouth 138kV substaiton onto the existing HWY 511 to S Carbide (Chalybe) 138kV tline using single ckt structures which creates the new HWY511- Portsouth and Portsouth-Chalybe 138kV tlines Hairpin Portsouth onto the existing Waterport to Southmost 138kV tline using single ckt structures which creats the new Waterport - Portsouth and Portsouth-Southmost 138kV tlines -Construct a new Boca Chica 138-kV substation with six terminals as a Gas-Insulated substation -Construct a new Portsouth to Boca Chica 138-kV double-circuit transmission line using double-circuit structures -Rebuild the existing South Carbide (Chalybe) to Portsouth to Hwy511 138-kV transmission line segments using single-circuit structures |  | Portsouth | Boca Chica | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-06-30 12:15 |  | 138 | 19.1 | 4.5 | 0 |  | Cameron | Cameron | Tier 2 | 25RPG039 |  | 2026-05-14 |  |  | Y | N |  |  | 110241 | 110240
111376 | Add Boca Chica and double ckt to portsouth |  |  | Boca Chica | PORTSOUTH | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-06-30 12:15 |  | 138 | 38.2 | 0 | 0 |  | Cameron | Cameron | Tier 2 | 25RPG039 | 2025-11-14 | 2026-05-15 |  | 5773, 5787 | Y | N |  |  | 111377 | 111376
111361 | Add Portsouth loop in Southmost - Waterport |  |  | PORTSOUTH | PORTSOUTH | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-06-30 12:15 |  | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 2 | 25RPG039 | 2025-11-14 | 2026-05-15 |  | 5773, 5789, 59450 | Y | N |  |  | 111362 | 111361
110077C | This models upgrades required for a proposed load addition. | Install 300 MVAR capacitor bank at the NewSub. |  | NewSub |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 345 | 0 | 0 | 0 | 0,300 | Waller |  | Tier 4 | [5 empty] | N | N |  | No cost estimate available at this time. | 110497 | 110077
104562 | Glint: Construct New 138 kV Station | Interconnect Falcon BESS to the new Glint 138 kV station on the Lopeno to Zapata 138 kV line | NEW | Glint |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2026040 | 2028-07-01 |  | 138 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 8299, 8831, 8957 | Y | Y |  |  | 104563 | 104562
110077A | This models upgrades required for a proposed load addition. | Install new 345 kV substation (NewSub). Loop into the existing Zenith to Mission ckt. 18. |  | NewSub | Zenith/Mission | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 345 | 0 | 0 | 0 |  | Harris | Waller | Tier 4 | [5 empty] | N | N |  | No cost estimate available at this time. | 110078 | 110077
110086B | This models upgrades required for a proposed load addition | Install new customer 345 kV sub. Loop into new 345 kV CEHE sub with two leads each 3.6 miles. |  | NEWSUB | Zenith/Gibbons Creek | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 345 | 7.2 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  | Cost included in main entry. | 110571 | 110086
110086A | This models upgrades required for a proposed load addition | Install new 345 kV CEHE-owned sub. Loop on 345 kV Zenith to Gibbons Creek Ckt.18 & 50 |  | Becker | Zenith/Gibbons Creek | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 110087 | 110086
110219B | This models upgrades required for a proposed load addition | Rebuild/Reconductor 138kV ckt.66 from Haney to Crosby. Upgrade substation equipment at Haney substation. |  | Haney | Crosby | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 138 | 0 | 3.95 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  | Cost included in main entry. | 110602 | 110219
110057A | This models upgrades required for a proposed load addition | Install new 345 kV substation (NewSub). Loop into the existing Zenith to Mission ckt.18 and Zenith to Gibbons Creek ckt.50. |  | NewSub | Zenith/Gibbons Creek; | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 345 | 0 | 0 | 0 |  | Harris | Grimes | Tier 4 | [5 empty] | N | N |  |  | 110065 | 110057
110077B | This models upgrades required for a proposed load addition. | Loop NewSub into the existing Zenith to Gibbons Creek ckt. 50. |  | NewSub | Zenith/Gibbon's Creek | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 345 | 0 | 0 | 0 |  | Harris | Grimes | Tier 4 | [5 empty] | N | N |  | No cost estimate available at this time. | 110496 | 110077
110086C | This models upgrades required for a proposed load addition | Install one 300 MVAR capacitor bank at new 345 kV CEHE sub. |  | Becker |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 345 | 0 | 0 | 0 | 0,300 | Harris | Harris | Tier 4 | [5 empty] | N | N |  | Cost included in main entry. | 110572 | 110086
110077D | This models upgrades required for a proposed load addition. | Install 300 MVAR capacitor bank at the 345 kV Zenith substation. |  | Zenith |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 345 | 0 | 0 | 0 | 0,300 | Harris |  | Tier 4 | [5 empty] | N | N |  | No cost estimate available at this time. | 110498 | 110077
110219A | This models upgrades required for a proposed load addition | Loop Newsub into ckt.08 between Crosby and Danek. Upgrade substation equipment at Crosby and Danek. |  | Newsub | Crosby/Danek | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-07-01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 110601 | 110219
90025 | Festin: Construct New 345 kV Station | Interconnect Sunscape Renewable Solar and Storage to the new Festin 345 kV station on the Lon Hill to Reforzar 345 kV line | In-Service Date Update | Festin |  | Planned |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2024111 | 2028-07-31 |  | 345 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8455, 80078, 80085 | Y |  |  |  | 90026 | 90025
110577 | Add CTT Comanchero station on Tule Canyon - Red Rock (Cross) dbl ckt |  |  | Tule Canyon | Red Rock | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-07-31 |  | 345 | 0 | 0 | 0 |  | Briscoe | Hall | Tier 4 |  |  |  |  | 23914, 79010, 79012 | N | N |  |  | 110578 | 110577
110286 | New double circuit line from CTT Railhead to Celtic Green |  |  | Railhead | Celtic Green | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-07-31 |  | 345 | 63.24 | 0 | 0 |  | Carson | Wheeler | Tier 3 | [5 empty] | N | N |  |  | 110287 | 110286
55550 | Brushline: Construct New Distribution Station | Construct new 138/13 kV station Brushline | Company Contact and In-Service Date Update | Brushline |  | Planned | 1106 - 1284 | AEP TCC | Julkarnain Chowdhury myturner@aep.com 918-599-2437 | 3826 | 2028-07-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 5754, 8963, 8972 | Y |  |  |  | 55551 | 55550
110589 | Add two lines between CTT Comanchero and White River |  |  | Comanchero | White River | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-07-31 |  | 345 | 0 | 0 | 0 |  | Briscoe |  | Tier 3 | [5 empty] | N | N |  |  | 110590 | 110589
110595 | Add dbl ckt between CTT Red Rock and Edith Clark |  |  | Red Rock | Edith Clark | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-07-31 |  | 345 | 60 | 0 | 0 |  | Hall | Foard | Tier 3 | [5 empty] | N | N |  |  | 110596 | 110595
110316 | Taps 2nd Alibates to Gray ckt into CTT Railhead |  |  | Alibates | Gray | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-07-31 |  | 345 | 0 | 0 | 0 |  | Carson | Gray | Tier 4 | [5 empty] | N | N |  |  | 110317 | 110316
103816 | Montura: Construct New 345 kV Station | Interconnect Bullring Wind 1, 2, and 3 to the new Montura 345 kV station on the Cruce to Del Sol 345 kV line | NEW | Montura |  | Planned |  | ETT | Marc E Wilson jlsolis@aep.com 361-881-5574 | TP2025870 | 2028-08-30 |  | 345 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 80079, 80346, 80355 | Y | N |  |  | 103817 | 103816
110467 | Adds 2nd circuit from Allen Creek to Gray |  |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-08-31 |  | 345 | 23.4 | 0 | 0 |  | Gray | Hall | Tier 3 | [5 empty] | N | N |  |  | 110468 | 110467
110471 | Add double ckt line from Allen Creek to Cross (Red Rock) |  |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-08-31 |  | 345 | 63 | 0 | 0 |  | Gray | Hall | Tier 3 | [5 empty] | N | N |  |  | 110472 | 110471
110681 | Add double ckt line from Ghost Town to Alibates |  |  | Ghost Town | Alibates | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-08-31 |  | 345 | 41 | 0 | 0 |  | Gray | Carson | Tier 3 | [5 empty] | N | N |  |  | 110682 | 110681
76082 | Union Carbide: Rebuild 138 kV Station | Rebuild Union Carbide as new AIS station Chalybe | Dollars Update | Union Carbide |  | Planned |  | AEP TCC | Nathan Cowan jlsolis@aep.com 361-881-5574 |  | 2028-08-31 | 2958101 | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 5767, 5963, 5965, 8337, 8338, 8535, 8735, 79601 | Y |  |  |  | 76083 | 76082
107551 | Robertson Prison: Convert to 138 kV | Interconnect Hamby Solar to the Robertson Prison 138 kV station on the Fort Phantom Plant to Abilene South 138 kV line | TSP/Company Contact Update | Robertson Prison |  | Planned |  | AEP TNC | Lance L Price myturner@aep.com 918-599-2437 | TP2026066 | 2028-08-31 |  | 138 | 0 | 2.2 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6200, 6220, 6221, 6245, 6568, 60292, 60366 | Y |  |  |  | 107552 | 107551
103822 | Red Creek: Expand 345 kV Station | Interconnect the Juvo load to the existing Red Creek 345 kV station | Project Description Update | Red Creek |  | Planned |  | AEP TNC | Nathan Cowan myturner@aep.com 918-599-2437 | TP2025786 | 2028-08-31 |  | 345 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6444, 60274 | Y |  |  |  | 103823 | 103822
110645 | Tap 2nd Limestone - Gibbons Creek ckt into CTT Iron Horse |  |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-08-31 |  | 345 | 0 | 0 | 0 |  | Leon |  | Tier 3 | [5 empty] | N | N |  |  | 110646 | 110645
70706 | Tungsten (Carbide): Rebuild 138/69 kV Station | Rehab the Tungsten (Carbide) 138/69 kV station | In-Service Date Update | Tungsten |  | Planned |  | AEP TCC | Jarrod Evans deevans@aep.com 918-599-2938 |  | 2028-08-31 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 | 21RPG024 | 2021-12-16 | 2022-01-18 |  | 5598, 8144, 8149, 8152, 8154, 8159, 8161, 8189, 8190, 8536, 8723, 80135, 110331, 110332, 110334, 110335, 110336 | Y |  |  |  | 78605 | 70706
111370 | Hairpin Portsouth HWY511 to Chalybe |  |  | PORTSOUTH | PORTSOUTH | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-08-31 12:15 |  | 138 | 0 | 4.5 | 0 |  | Cameron | Cameron | Tier 2 | 25RPG039 | 2025-11-14 | 2026-05-15 |  | 5767, 5773, 8735 | Y | N |  |  | 111371 | 111370
99357 | Add Permian Basin Reliability Plan Upgrade ID L25D and L25E. | Add Permian Basin Reliability Plan Upgrade ID L25D and L25E. Build Oak Spring - Plowboy 138-kV line. Move the Eskota 138/69-kV transformer 1 to Plowboy. |  | Oak Spring | Plowboy | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8805 | 2028-09-01 |  | 138 | 2.4 | 0 | 0 |  | Nolan | Nolan | Tier 2 |  |  |  |  | 1339, 1340, 1378, 1380, 1381, 10103, 10104, 11380, 701380 | Y |  |  |  | 99676 | 99357
91615 |  |  |  | Concord | Crowley | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-09-01 |  | 138 | 0 | 9.3 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 394, 398, 399 | Y |  |  |  | 91616 | 91615
102685 | BEPC_TPIT102685_Add_Delia |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-09-01 |  | 69 | 1.5 | 0 | 0 | 0,10 | Limestone |  | Tier 4 |  |  |  |  | 107, 112, 186 | Y |  |  |  | 102686 | 102685
55626 | Ganso to Hamilton Road: Rebuild 138 kV line | Rebuild 138 kV line from Ganso to Hamilton Road |  | Maverick | Hamilton Road | Planned | 1105 - 1283 | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 | 3824 | 2028-09-14 |  | 138 | 0 | 41.1 | 0 |  | Maverick | Val Verde | Tier 3 | 22RPG044 | 2022-12-15 | 2023-01-17 |  | 8255, 8267, 8692 | Y |  |  |  | 65576 | 55626
66492D | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Chico West - Chico City Services 69 kV Line |  | Chico City Services | Chico West | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M3006 | 2028-09-15 |  | 69 | 0 | 6 | 0 |  | Jack | Jack | Tier 4 |  |  |  |  | 1553, 1554, 15117 | Y |  |  |  | 76368 | 66492
55624 | Escondido to Ganso: Rebuild 138 kV line | Rebuild 138 kV line from Escondido to Ganso |  | Escondido | Ganso | Planned | 1105 - 1283 | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 | 3825 | 2028-09-21 |  | 138 | 0 | 10.198 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 8260, 8267 | Y |  |  |  | 65575 | 55624
58010 | North McAllen: Rebuild 138 kV Station | Rehab the North McAllen 138 kV station |  | McAllen |  | Planned | 1118 - 1296 | AEP TCC | Thomas Neils jlsolis@aep.com 361-881-5574 | 3837 | 2028-09-21 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8368, 8631, 8632 | Y |  |  |  | 65583 | 58010
110832 | Ad Hoc TPIT: Arrow Load Serving Station | Construct a new 345 kV load serving station by tapping the existing Kingfisher to North Edinburg/Stewart Road Circuits | NEW | Kingfisher | Stewart Road | Conceptual |  | SLU | Charles Aleman caleman@huntutility.com 682-406-9656 |  | 2028-09-29 |  | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8383, 79501, 79503, 80137 | N |  |  |  | 110840 | 110832
109847C | DRILCO Area improvements in support of proposed load addition. | Install 80 MVAR capacitor bank at the 138 kV Intercontinental substation by tapping into Ckt 67 Intercontinental to INTEQ |  | Intercontinental |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-09-30 |  | 138 | 0 | 0 | 0 | 0,80 | Harris | Harris | Tier 4 | [5 empty] | N | N |  | Cost included in Main Entry | 109939 | 109847
54892 | Eden to North Brady: Rebuild 69 kV line | Rehab Eden to North Brady 69 kV line | In-Service Date Update | Eden | North Brady | Planned | 1039 - 1266 | AEP TNC | Bradley Case myturner@aep.com 918-599-2437 | 1856 | 2028-09-30 |  | 69 | 0 | 32.7 | 0 |  | Concho | McCulloch | Tier 4 | 22RPG009 | 2022-03-23 | 2022-04-14 |  | 6006, 6372, 6380, 6384, 6385, 60005, 60797 | Y | N |  |  | 65568 | 54892
111305 | Goddard: Expand 345 kV Station | Interconnect Bayou Creek Solar to the existing Goddard 345 kV Statiom |  | Goddard |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2026163 | 2028-09-30 |  | 345 | 1.3 | 0 | 0 |  | San Patricio |  | Tier 4 | [5 empty] | Y | N |  |  | 111306 | 111305
99111A | Loop new CEHE 138kV substation Persimmon (PER) into Ckt.04A Mustang Bayou to HUDSON to create new Ckt.04 Mustang Bayou to Persimmon to HUDSON. Install one generator lead from CEHE 138kV substation Persimmon (PER) to KINETIC (KIN) / Willow Beach Wind. | Loop new CEHE 138kV substation Persimmon (PER) into Ckt.04A Mustang Bayou to HUDSON to create new Ckt.04 Mustang Bayou to Persimmon to HUDSON. |  | Persimmon | Mustang Bayou/HUDSON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-09-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42960, 43550, 111321 | Y | N |  | Cost included in main entry | 99112 | 99111
52070 | Carver to Maxwell: Rebuild 138 kV line | Rehab Carver to Maxwell 138 kV Line | Company Contact and In-Service Date Update | Carver | Maxwell | Planned | 1079 - 1252 | AEP TCC/AEP TNC | Jeremy Brazeal myturner@aep.com 918-599-2437 | 3804 | 2028-09-30 | 2958101 | 138 | 0 | 60.24 | 0 |  | Sutton | Val Verde | Tier 3 | 22RPG042 | 2022-12-02 | 2022-12-28 |  | 8259, 8261, 8991, 8998, 60412, 60440 | Y | N |  |  | 65562 | 52070
99111B | Loop new CEHE 138kV substation Persimmon (PER) into Ckt.04A Mustang Bayou to HUDSON to create new Ckt.04 Mustang Bayou to Persimmon to HUDSON. Install one generator lead from CEHE 138kV substation Persimmon (PER) to KINETIC (KIN) / Willow Beach Wind. | Install one generator lead from CEHE 138kV substation Persimmon (PER) to KINETIC (KIN) / Willow Beach Wind. |  | Persimmon | KINETIC | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-09-30 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | Cost included in main entry | 99113 | 99111
91453 | Canton area RPG update | Canton Rebuild as a 3 breaker ring bus and tapping Oncor Canton to Explorer Pipeline 138kV line. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2028-10-01 |  | 138 | 0 | 4.2 | 0 |  | Van Zandt | Van Zandt | Tier 2 |  |  |  |  | 3184, 6837 | Y |  |  |  | 103387 | 91453
110084D | This models upgrades required for a proposed load addition | Add Capacitor to nearby Raider substation. |  | Raider |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-01 |  | 345 | 0 | 0 | 0 | 0,500 | Fort Bend | Fort Bend | Tier 1 | [5 empty] | N | N |  |  | 110506 | 110084
109810 | PSH Large Load | Upgrade 138 kV line from Nquin_RC (6883) to Quinl_RC (6884) to Cumberland conductor. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2028-10-01 |  | 138 | 0 | 3.46 | 0 |  | Hunt | Hunt | Tier 4 |  |  |  |  | 6883, 6884 | Y |  |  |  | 109811 | 109810
109704 | Carnelian: Construct New 345 kV Station | Interconnect the Somerset Rebel load to the new Carnelian 345 kV station on the Whitepoint to Angstrom 345 kV line |  | Angstrom | White point | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2026075 | 2028-10-01 |  | 345 | 2.5 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8249, 8829, 8830, 8956, 80484 | Y | N |  |  | 109705 | 109704
103468 | Misty Power Transformer Addition | Add two power transformers at Misty substations |  | Misty |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8282 | 2028-10-01 |  | 345 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7051 | Y |  |  |  | 103469 | 103468
110084C | This models upgrades required for a proposed load addition | Add Capacitor to nearby Raider substation. |  | Raider |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-01 |  | 345 | 0 | 0 | 0 | 0,250 | Fort Bend | Fort Bend | Tier 1 | [5 empty] | N | N |  |  | 110505 | 110084
110084E | This models upgrades required for a proposed load addition | Add additional capacitor to nearby Raider substation. |  | Raider |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-01 |  | 345 | 0 | 0 | 0 | 0,100 | Fort Bend | Fort Bend | Tier 1 | [5 empty] | N | N |  |  | 110507 | 110084
99530 | Deep Creek - Snyder - China Grove 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L22E. Upgrade the existing Deep Creek - China Grove 138-kV line |  | Deep Creek | China Grove | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L22_E | 2028-10-01 |  | 138 | 0 | 14.56 | 0 |  | Scurry | Scurry | Tier 3 |  |  |  |  | 1304, 1318, 10203 | Y |  |  |  | 99531 | 99530
93831 | New substation to replace Loma Alta |  |  | Stillman, Waterport, and also future Nimzo Substations | Cipher (Loma Alta) | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2028-10-02 |  | 138 | 0 | 0 | 0 | 0,50 |  |  | Tier 3 |  |  |  |  | 5943, 5944, 5962, 59450, 59510, 59551, 79601 | Y |  |  |  | 93832 | 93831
99648 | Pecan Bayou: 138 kV Circuit Breaker Addition | Install two 138 kV circuit breakers at the Pecan Bayou 138 kV station | In-Service Date and County Update | Pecan Bayou |  | Planned |  | AEP TNC | Jennifer Kates myturner@aep.com 918-599-2437 | TP2023323 | 2028-10-15 |  | 138 | 0 | 0 | 0 |  | Callahan |  | Tier 4 | [5 empty] | Y | N |  |  | 99649 | 99648
98622 | Chalybe to Palmito: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Chalybe to Palmito | Company Contact, In-Service Date and Dollars Update | Chalybe | Palmito | Planned |  | AEP TCC/AEP TCC/SLU | Nathan Cowan jlsolis@aep.com 361-881-5574 | TP2025010 | 2028-10-31 |  | 345 | 2 | 0 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 79500, 88337 | Y |  |  |  | 98839 | 98622
98632 | Chalybe: Install two STATCOMs at the 138 kV Station | Install two 150 MVAR STATCOMs at the Chalybe 138 kV station | Company Contact, In-Service Date, Dollars and Reactive Capability Update | Chalybe |  | Planned |  | AEP TCC | Nathan Cowan jlsolis@aep.com 361-881-5574 | TP2025010 | 2028-10-31 |  | 138 | 0 | 0 | 0 | -300300 | Cameron |  | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 8735, 80282, 80283 | Y |  |  |  | 98842 | 98632
98637 | Chalybe to Stillman: Construct New 138 kV Line | Construct a new 138 kV single circuit line from Chalybe to Stillman | Company Contact, In-Service Date and Dollars Update | Chalybe | Stillman | Planned |  | AEP TCC/SLU | Nathan Cowan jlsolis@aep.com 361-881-5574 | TP2025010 | 2028-10-31 |  | 138 | 1 | 0 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 8735, 79601 | Y |  |  |  | 98844 | 98637
5889 | MIRAGE - 138kV Substation Removal | Remove 138kV MIRAGE customer-owned substation from CEHE service. |  | MIRAGE | MCCABE/BIMONT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40200, 40209, 42351, 42360 | N | N |  |  | 13606 | 5889
98620 | Chalybe to Kingfisher: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Chalybe to Kingfisher | Company Contact, In-Service Date and Dollars Update | Chalybe | Kingfisher | Planned |  | AEP TCC/AEP TCC/SLU | Nathan Cowan jlsolis@aep.com 361-881-5574 | TP2025010 | 2028-10-31 |  | 345 | 22 | 0 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 79501, 88337 | Y |  |  |  | 98838 | 98620
98618 | Chalybe: Expand 345 kV Station | Install two 345/138 kV autotransformers at the Chalybe 345/138 kV station | Company Contact, In-Service Date and Dollars Update | Chalybe |  | Planned | TP2025010 | AEP TCC | Nathan Cowan jlsolis@aep.com 361-881-5574 |  | 2028-10-31 |  | 345 | 0 | 0 | 1350 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2025-03-24 | 2025-09-24 | 2025-12-24 | 8735, 88337 | Y |  |  |  | 98837 | 98618
90191 | Bromine 138/35kV Distribution Substation | Install Bromine 138/35kV Distribution Substation. Loop on Ckt.66A to create new Ckt.66A Katy tap to Bromine to Freeman. |  | Bromine | Katy/Freeman | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 45040, 45770, 48203 | Y | N |  |  | 104531 | 90191
76131 | Pendulo: Build New 345 kV terminal | Interconnect Inertia Solar and BESS 2 to the Pendulo 345 kV Station on the Clear Crossing to Smoky Hill line |  | Pendulo |  | Planned |  | ETT/AEP TNC/ETT | Lance Price myturner@aep.com 918-599-2437 |  | 2028-10-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60507 | Y | N |  |  | 76132 | 76131
102968B | Circle Lake (CIR) CEHE Substation for Two Barbaras BESS (27INR0109) | Install one generator lead from Circle Lake (CIR) 138kV CEHE Substation to customer-owned TWO_BA (TBB) substation for Two Barbaras BESS (27INR0109). |  | Circle Lake | TWO_BA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  | Cost Included in Main Entry | 102970 | 102968
111348 | Dry Hollow: Construct New Switch Station | Interconnect CVEC's Hog Creek substation to the new Dry Hollow 69 kV switch station on the Redbo to Eola Tap 69 kV line |  | Dry Hollow |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2026180 | 2028-10-31 |  | 69 | 0.1 | 0 | 0 |  | Concho |  | Tier 4 |  |  |  |  | 6370, 6371, 60478, 60479 | Y | N |  |  | 111349 | 111348
111258B | Newby (NBY) CEHE-Owned 345 kV Substation for DEWEY (DWY) / Jewett Energy Center (29INR0150) | Loop new Newby (NBY) 345kV CEHE Substation into Ckt.98 to create new Ckt.98 Limestone to Newby to Jewett. Install (1) 6-Ohm reactor at Newby substation in-series with Ckt.98 Newby to Limestone. |  | Newby | Limestone / Jewett | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 345 | 0 | 0 | 0 |  | Freestone | Leon | Tier 4 |  |  |  |  | 3391, 46020, 46820, 46829 | Y |  |  | Cost included in main entry. | 111260 | 111258
111258A | Newby (NBY) CEHE-Owned 345 kV Substation for DEWEY (DWY) / Jewett Energy Center (29INR0150) | Loop new Newby (NBY) 345kV CEHE Substation into Ckt.74 to create new Ckt.74 Jewett to Newby to Limestone. Install (1) 6-Ohm reactor at Newby substation in-series with Ckt.74 Newby to Limestone. |  | Newby | Jewett / Limestone | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 345 | 0 | 0 | 0 |  | Freestone | Leon | Tier 4 |  |  |  |  | 3390, 46020, 46820, 46828 | Y |  |  |  | 111259 | 111258
103414 | Rio Hondo: 138 kV Breaker Replacement | Replace 138 kV breakers at the Rio Hondo 138 kV station | NEW | Rio Hondo |  | Planned |  | AEP TCC | Curtis Brown jlsolis@aep.com 361-881-5574 | TP2025950 | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 | [5 empty] | Y | N |  |  | 103415 | 103414
111258C | Newby (NBY) CEHE-Owned 345 kV Substation for DEWEY (DWY) / Jewett Energy Center (29INR0150) | Install dual generator leads from Newby (NBY) 345kV CEHE Substation to customer-owned Dewey Prairie - DEWEY_ (DWP) |  | Newby | DEWEY | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 345 | 0 | 0 | 0 |  | Freestone | Leon | Tier 4 | [5 empty] | Y |  |  | Cost included in main entry. | 111261 | 111258
102968A | Circle Lake (CIR) CEHE Substation for Two Barbaras BESS (27INR0109) | Install new Circle Lake (CIR) 138kV CEHE Substation for generator interconnection to Two Barbaras BESS. Connect to Ckt.81G Pinehurst to Mill Creek to create new Ckt.81 Pinehurst to Circle Lake to Mill Creek. |  | Circle Lake | Pinehurst /Mill Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-10-31 |  | 138 | 0 | 0 | 0 |  | Montgomery |  | Tier 4 |  |  |  |  | 44820, 44850, 46240 | Y | N |  |  | 102969 | 102968
111985 | This is a new planned substation project | BPUB has a planned new substation project that will be between our existing Waterport Substation and STEC's Southmost Substation. |  |  |  | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2028-11-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5789, 59450, 59470 | Y |  |  |  | 111986 | 111985
107126 | Crabapple Substation Addition | LCRA TSC will provide one (1) 138-kV POI(s) at Crabapple for a generation interconnection. |  | Crabapple |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-11-20 |  | 138 | 0 | 0 | 0 |  | Gillespie |  | Tier 4 |  |  |  |  | 7126, 7128, 7132, 7135 | Y |  |  |  | 107127 | 107126
90029 | Dupont Switch to Dupont PP1 Circuit 2: Rebuild 138 kV Line | Rebuild the Dupont Switch to Dupont PP1 Circuit 2 138 kV line | Company Contact and In-Service Date Update | Dupont Switch | Dupont PP1 | Planned |  | AEP TCC | Remington Hajdik deevans@aep.com 918-599-2938 | TP2024138 | 2028-11-30 |  | 138 | 0 | 1.52 | 0 |  | San Patricio | San Patricio | Tier 4 | [5 empty] | Y |  |  |  | 90030 | 90029
102774B | Twinwood (TWN) 138kV CEHE Substation RHEMAN (RHE) / Twinwood Solar (26INR0425) and Maderagemela BESS (26INR0426) | Install one generator lead from Twinwood (TWN) 138kV Substation to RHEMAN (RHE) / Twinwood Solar (26INR0425) and Maderagemela BESS (26INR0426). |  | Twinwood (new) | RHEMAN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-11-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y | N |  |  | 102967 | 102774
110417 | Cascabel: Install New 345 kV Capacitor Bank | Install a new capacitor bank at the Cascabel 345 kV station | Transmission Owner and Reactive Capability Update | Cascabel |  | Conceptual |  | AEP TNC/ETT | Mina Turner myturner@aep.com 918-599-2437 |  | 2028-11-30 |  | 345 | 0 | 0 | 0 | 0,183 | Jones |  | Tier 4 |  |  |  |  | 60124 | Y | N |  |  | 110418 | 110417
102774A | Twinwood (TWN) 138kV CEHE Substation RHEMAN (RHE) / Twinwood Solar (26INR0425) and Maderagemela BESS (26INR0426) | Install new Twinwood (TWN) 138kV Substation for generator interconnection to RHEMAN (RHE) / Twinwood Solar (26INR0425) and Maderagemela BESS (26INR0426). Loop into existing Ckt.25E to create new Ckt.25 Fulshear to Twinwood (new) to Twinwood (distribution loop) to Peters. |  | Twinwood (new) | Fulshear/Twinwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-11-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44750, 44860, 44865 | Y | N |  |  | 102966 | 102774
103518 | Faisan: Construct New 345 kV Station | Interconnect the Helios II load to the new Faisan 345 kV station | TSP/Company Contact Update | Faisan |  | Planned |  | AEP TNC | Ali Barkat myturner@aep.com 918-599-2437 | TP2025943 | 2028-11-30 |  | 345 | 0 | 0 | 0 |  | Dickens |  | Tier 4 |  |  |  |  | 59913, 60270, 60271 | Y | N |  |  | 103519 | 103518
104026 | Morado (Abilene Northwest): Rebuild 138 kV Station | Rebuild the Morado (Abilene Northwest) 138 kV station | In-Service Date and RPG Dates Update | Morado |  | Planned |  | AEP TNC | Carol A Matheny myturner@aep.com 918-599-2437 | TP2023700 | 2028-11-30 |  | 138 | 0 | 0.1 | 0 | 0,34.6 | Jones |  | Tier 3 | 25RPG036 | 2025-10-08 | 2025-10-31 |  | 6201, 6223, 6224, 6225, 6228, 6229, 6255, 6288, 60282, 60387 | Y | N |  |  | 104027 | 104026
99794 | Frontera: 138 kV Breaker Replacement | Replace 138 kV breakers at the Frontera 138 kV station | TSP/Company Contact and In-Service Date Update | Frontera |  | Planned |  | AEP TCC | Curtis Brown jlsolis@aep.com 361-881-5574 | TP2025213 | 2028-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8980, 80004, 80005, 80119, 80295, 80296 | Y |  |  |  | 99795 | 99794
90016 | Dupont Switch to Dupont PP1 Circuit 1: Rebuild 138 kV Line | Rebuild the Dupont Switch to Dupont PP1 Circuit 1 138 kV line | Company Contact and In-Service Date Update | Dupont Switch | Dupont PP1 | Planned |  | AEP TCC | Remington Hajdik deevans@aep.com 918-599-2938 | TP2024138 | 2028-11-30 |  | 138 | 0 | 1.46 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8422, 8817, 8819 | Y |  |  |  | 90017 | 90016
90002 | Salvare: Install New 345 kV Capacitor Bank | Install a new capacitor bank at the Salvare 345 kV station | ISD Update | Salvare |  | Planned |  | ETT | Matthew McLauchlin myturner@aep.com 918-599-2437 | TP2024109 | 2028-11-30 |  | 345 | 0 | 0 | 0 | 0,46.1 | Childress |  | Tier 4 |  |  |  |  | 60511 | Y | N |  |  | 91298 | 90002
91853 | Fort Stockton Plant to Solstice: Rebuild 138 kV Line | Rebuild the Fort Stockton Plant to Solstice 138 kV line and retire the PST at Solstice | In-Service Date Update | Fort Stockton Plant | Solstice | Planned |  | AEP TNC | Damian Raab myturner@aep.com 918-599-2437 | TP2025145 | 2028-11-30 |  | 138 | 0 | 25 | 0 |  | Pecos | Pecos | Tier 3 | H.B. 5066 |  |  | 2024-10-31 | 6630, 60384, 60385 | Y | N |  |  | 91854 | 91853
91906 | Carver to Friend Ranch: Rebuild 138 kV Line | Rebuild the Carver to Friend Ranch 138 kV line | TSP/Company Contact and In-Service Date Update | Carver | Friend Ranch | Planned |  | AEP TNC | Travis Coody myturner@aep.com 918-599-2437 | TP2025168 | 2028-11-30 |  | 138 | 0 | 33 | 0 |  | Sutton | Crockett | Tier 3 | H.B. 5066 |  |  | 2024-10-31 | 6562, 60412 | Y | N |  |  | 91907 | 91906
98561 | Solstice to Hayter Tap: Rebuild 138 kV Line Double Circuit | Rebuild the Solstice to Hayter Tap 138 kV line as a double circuit | In-Service Date Update | Solstice | Hayter Tap | Planned |  | AEP TNC | Damian Raab myturner@aep.com 918-599-2437 |  | 2028-11-30 |  | 138 | 1.7 | 1.7 | 0 |  | Pecos | Pecos | Tier 2 | H.B. 5066 |  |  | 2024-10-31 | 6680, 60444, 60802, 78925 | Y |  |  |  | 98562 | 98561
50876 | Victoria to Port Lavaca: Retire 69 kV Line | Retire 69 kV Line on Victoria to Port Lavaca | TSP/Company Contact Update | Port Lavaca | Victoria | Planned | 1054 - 1227 | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 | 3782 | 2028-11-30 |  | 69 | 0 | 29 | 0 |  | Calhoun | Victoria | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8135, 8136, 8169 | Y | N |  |  | 50877 | 50876
55470 | Bison to Lightyear: Rebuild 69 kV Line | Rehab the Bison to Lightyear 69 kV line | Project Title, Project Description, Terminal To Location, and TSP/Company Contact Update | Bison | Lightyear | Planned | 1095 - 1273 | AEP TNC | Travis Coody myturner@aep.com 918-599-2437 | 1863 | 2028-11-30 |  | 69 | 0 | 27 | 0 |  | Reagan | Crockett | Tier 4 |  |  |  |  | 6549, 6560, 60395 | Y | N |  |  | 65570 | 55470
69277 | Cangrejo to Carbide: Rebuild 138 kV Line | Rebuild 138 kV Line from Cangrejo to Carbide |  | Cangrejo | Carbide | Planned |  | AEP TCC | Lorraine Timmerman jlsolis@aep.com 361-881-5574 |  | 2028-11-30 |  | 138 | 0 | 11 | 0 |  | Calhoun | Calhoun | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8140, 8155, 8190, 8723 | Y |  |  |  | 69278 | 69277
78545 | Brookhollow to Cangrejo: Rebuild 69 kV Line | Rebuild 69 kV line from Brookhollow to Cangrejo |  | Brookhollow | Cangrejo | Planned |  | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 |  | 2028-11-30 |  | 69 | 0 | 2.15 | 0 |  | Calhoun | Calhoun | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8133, 8135, 8720, 8723, 8756, 88133 | Y |  |  |  | 78546 | 78545 | 2019-C2
102980 | Expand 138kV Weinbrenner substation for LIATRI (LIA)/Liatris Flexible Gas - 26INR0408. Install one new generator lead from Weinbrenner to LIATRI/Liatris Flexible Gas | Expand 138kV Weinbrenner substation for LIATRI (LIA)/Liatris Flexible Gas - 26INR0408. Install one new generator lead from Weinbrenner to LIATRI/Liatris Flexible Gas |  | Weinbrenner |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-11-30 |  | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  |  | 102981 | 102980
103421 | Weslaco Unit: 138 kV Breaker Replacement | Replace 138 kV breakers at the Weslaco Unit 138 kV station | NEW | Weslaco Unit |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025944 | 2028-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 | [5 empty] | Y | N |  |  | 103422 | 103421
99513 | Dry Lake (fka 900005Tap) - Faulkner (TNMP) 345 kV double-circuit line | Joint Oncor and TNMP project to Add Permian Basin Reliability Plan Upgrade ID L5F Add a new 900005Tap - Faulkner 345-kV double-circuit line |  | Dry Lake (ONCOR) | Faulkner (TNMP) | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L5_F | 2028-12-01 |  | 345 | 63.36 | 0 | 0 |  | Reeves | Reeves | Tier 2 |  |  |  |  | 18723, 38125 | Y |  |  |  | 99514 | 99513
99020 | Border 345/138 kV Switch and two new 345/138 kV Autotransformers | Add Permian Basin Reliability Plan Upgrade ID L2A Establish a new Border 345/138-kV substation and install two new 345/138-kV transformers |  | Border | Border | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L2_A_B | 2028-12-01 |  | 345 | 0 | 0 | 1200 | 75,0 | Loving | Loving | Tier 3 |  |  |  |  | 18672, 18718, 18720, 18721 | Y |  |  |  | 99021 | 99020
92278 | Faulkner 345kV - Part of Upgrade L5 2024 Permian Basin Study |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | PBRP Upgrade L5 | 2028-12-01 |  | 345 | 79.28 | 0 | 1500 |  | Pecos | Reeves | Tier 1 |  |  |  |  | 38124, 38125, 38126, 38127, 60404 | Y |  |  |  | 92279 | 92278
99518 | Dry Lake (ONC900005_TAP 11610) - Faulkner (TNMP) 138 kV double-circuit line | Joint Oncor and TNMP project to Add Permian Basin Reliability Plan Upgrade ID L3 Connect new load buses to ONC900005_TAP (11610) and Faulkner and form a 138-kV double-circuit loop: 11610 - 900005 - 900111 - 900023 - 900012 - 900021 - 900038 - 38124 |  | Dry Lake (ONCOR) | FAULKNER (TNMP) | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L3_A | 2028-12-01 |  | 138 | 120 | 0 | 0 |  | Reeves | Reeves | Tier 2 |  |  |  |  | 18732, 38124 | Y |  |  |  | 99519 | 99518
99018 | Dry Lake 345/138 kV Switch (fka ONC900005_TAP 11610) and two new 345/138 kV autotransformers | Add Permian Basin Reliability Plan Upgrade ID L5B and L5E Establish a new ONC900005_TAP 345/138-kV substation and install two new 345/138-kV transformers and Add a new El Capitan - Dry Lake (fka 900005Tap) 345-kV double-circuit line |  | El Capitan | Dry Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L5_B_E | 2028-12-01 |  | 345 | 50 | 0 | 1200 | 75,0 | Culberson | Reeves | Tier 1 |  |  |  |  | 10179, 10180, 11082, 18723, 18724, 18725, 18726, 18732 | Y |  |  |  | 99019 | 99018
98953 | McDonald Road - Polecat Creek 138 kV Rebuild | Rebuild the 13.75 mile McDonald Road Switch - Polecat Creek Switch 138 kV Line |  | McDonald Road | Polecat Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8207 | 2028-12-01 |  | 138 | 0 | 13.75 | 0 |  | Glasscock | Glasscock | Tier 3 | 25RPG035 |  |  |  | 1333, 1334, 1335, 11337 | Y |  |  |  | 98954 | 98953
98991A | Kinnebrew POI - Chalk 69 kV to 138 kV Line Conversion | Oncor's portion of the Permian Basin Reliability Plan Upgrade ID L27B. Convert the existing Chalk - Kinnebrew POI 69-kV line to 138-kV. |  | Kinnebrew | Chalk | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L27_B | 2028-12-01 |  | 138 | 13.6 | 0 | 0 |  | Sterling | Sterling | Tier 3 |  |  |  |  | 1333, 6641, 9429, 10189, 11352 | Y |  |  |  | 98993 | 98991
76768 | Upgrade Pearson -Pearsall | Upgrade the Pearson-Natalia-Devine-Moore-Pearsall to 795 ACSR |  | Pearson | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-12-01 |  | 69 | 0 | 34.62 | 0 |  | Frio | Medina | Tier 4 |  |  |  |  | 5811, 5828, 5830, 5857, 5858, 5893, 58570 | Y |  |  |  | 76769 | 76768
109808 | Rivercrest Switch - Hawk Hallow Switch 138 kV Line | Upgrade Rivercrest Switch - Hawk Hallow Switch 138 kV Line |  | Rivercrest Switch | Hawk Hallow Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3234 | 2028-12-01 |  | 138 | 0 | 25.5 | 0 |  | Red River | Lamar | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 1768, 1780, 11768 | Y |  |  |  | 111637 | 109808 | 2024-N14
109845 | Oncor_ME_109845_Cleburne Switch - Venus 138 kV Line Section and Rebuild Cleburne 138 kV Switch | Upgrade Cleburne Switch - Venus 138 kV Line Section and Rebuild Cleburne 138 kV Switch |  | Venus Substation | Cleburne Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5371, M5196 | 2028-12-01 |  | 138 | 0 | 19.5 | 0 |  | Ellis | Johnson | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 442, 1905, 1908, 2279, 2294, 2297 | Y |  |  |  | 112114 | 109845 | 2024-NC04
110377 | Greene Switch - Wilmer Switch 345 kV Double-Circuit Line | Establish Greene Switch - Wilmer Switch 345 kV Double-Circuit Line |  | Greene Switch | Wilmer Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4364 | 2028-12-01 |  | 345 | 3 | 0 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 3063, 3085 | Y |  |  |  | 112115 | 110377 | 2024-NC86
110268 | Lavon 345/138 kV Switch | Lavon 345/138 kV Switch |  | Lavon 345/138 kV Switch | Lavon 345/138 kV Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3313 | 2028-12-01 |  | 345 | 0 | 0 | 0 |  | Collin | Collin | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 2256, 2461, 2475, 2513, 2514, 12256, 12464 | Y |  |  |  | 112133 | 110268 | 2024-NC59
105345 | Black Hawk 138 kV Switch | Establish new 138 kV Switch |  |  |  | Planned | R8796 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2028-12-01 |  | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 10119, 10127, 10206, 23833 | Y |  |  |  | 105412 | 105345
92911 | Adds Capacitor Bank at Wildhorse POD | Adds Capacitor Bank at Wildhorse POD |  | Wildhorse POD | Wildhorse POD | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8664 | 2028-12-06 | 2027-05-15 | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 1397 | Y |  |  |  | 92912 | 92911
102561 | BEPC_TPIT_FortGatesSW_FortGates |  |  | 250 | 254 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-12-08 |  | 69 | 0 | 2 | 0 |  | Coryell | Coryell | Tier 4 |  |  |  |  | 250, 254 | Y |  |  |  | 102562 | 102561
99620 | Rebuild Pin Oak Switch - Jewett Switch 345 kV Double Circuit Line | Rebuild Pin Oak Switch - Jewett Switch 345 kV Double Circuit Line |  | Pin Oak Switch | Jewett Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1704 | 2028-12-15 |  | 345 | 0 | 65 | 0 |  | Freestone | Leon | Tier 1 | 25RPG004 |  |  |  | 3308, 3390, 3391 | Y |  |  |  | 99621 | 99620
99626 | Upgrade Richland Chambers Switch - Trinidad Switch 345 kV Double Circuit Line | Upgrade Richland Chambers Switch - Trinidad Switch 345 kV Double Circuit Line |  | Richland Chambers Switch | Trinidad Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6027 | 2028-12-15 |  | 345 | 0 | 33 | 0 |  | Freestone | Henderson | Tier 1 | 25RPG004 |  |  |  | 3123, 3124, 3133, 3134 | Y |  |  |  | 99627 | 99626
87699 | Belton - Killeen 138 kV Line via Belton Southwest | Upgrade Belton - Killeen 138 kV Line via Belton Southwest |  | Belton | Killeen | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R902 | 2028-12-15 |  | 138 | 0 | 17.2 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3423, 3610, 3633, 3776, 13610 | Y |  |  |  | 87700 | 87699 | 2023-NC36
87703 | Belton - Killeen 138 kV Line via Nolanville | Reconductor the Belton - Killeen 138 kV Line via Nolanville |  | Belton | Killeen | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6347 | 2028-12-15 |  | 138 | 0 | 24.8 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3366, 3423, 3429, 3444, 3610, 3616, 3617, 3618, 3619, 13426, 13427 | Y |  |  |  | 87704 | 87703 | 2023-NC22, 2023-NC36, 2023-NC50
87711 | Watercrest - Killeen 138 kV Line | Upgrade the Watercrest - Killeen 138 kV Line |  | Watercrest | Killeen | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6355 | 2028-12-15 |  | 138 | 0 | 7 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3423, 3428, 13628 | Y |  |  |  | 87712 | 87711
71910C | Rebuild the Hillsboro - Elm Mott 69 kV Line | Rebuild the Abbott - Hillsboro Switch 69 kV Line |  | Abbott 69 kV Substation | Hillsboro 69 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6221 | 2028-12-15 |  | 69 | 0 | 10.1 | 0 |  | Hill | Hill | Tier 3 |  |  |  |  | 3523, 3524 | Y |  |  |  | 91607 | 71910
92852B | Monticello_Paris_Line_Upgrade | Upgrade Woodard - Paris 345 kV Line |  | Woodard | Paris | Planned | R986 | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | R986 | 2028-12-15 |  | 345 | 0 | 16.8 | 0 |  | Lamar | Lamar | Tier 1 | 25RPG026 | 2025-07-23 |  |  | 1692, 11699 | Y |  |  |  | 93064 | 92852
68700 | Bonham - Toco Switch 69 kV Line Rebuild | Rebuild the existing 69 kV Line |  | Bonham | Toco | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3016 | 2028-12-15 |  | 69 | 0 | 35 | 0 |  | Fannin | Lamar | Tier 4 |  |  |  |  | 1703, 1761, 1788, 1789, 1790, 11789 | Y |  |  |  | 68701 | 68700
81296A | Prong Moss – Rockhound 345 kV Line Rebuild | Prong Moss – Rockhound 345 kV Line Rebuild |  | Prong Moss | Rockhound | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2028-12-15 |  | 345 | 0 | 60.2 | 0 |  | Midland | Howard | Tier 1 | 23RPG029 |  |  |  | 10057, 10062 | Y |  |  |  | 81297 | 81296
105322 | Ironwood 345/138 kV Switch | Establish Ironwood 345/138 kV Switch |  | Ironwood Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4398 | 2028-12-15 |  | 345 | 2 | 0.5 | 120 | 0,210.8 | Ellis |  | Tier 1 | 25RPG004, 26RPG028 | 2025-02-06 | 2026-03-19 |  | 1906, 1907, 1910, 1939, 1940, 2255, 2287, 2289, 2303, 2305, 2632, 3383, 3389, 11885, 11886, 11901, 11904, 11909, 12632, 22632 | Y |  |  |  | 111540 | 105322
105318 | Greene 345/138 kV Switch | Establish Greene 345/138 kV Switch |  | Greene Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4255 | 2028-12-15 |  | 345 | 0 | 0 | 1200 | 0,350.4 | Dallas |  | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2126, 2238, 2398, 2427, 2946, 3062, 3063, 3067, 3068, 3069, 13063, 23063 | Y |  |  |  | 112550 | 105318
109876 | Establish Windy Ridge 138 kV Switch | Establish Windy Ridge 138 kV Switch |  | Windy Ridge | Windy Ridge | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6483 | 2028-12-15 |  | 138 | 5 | 0 | 0 |  | Williamson | Williamson | Tier 2 | [5 empty] | Y |  |  |  | 109877 | 109876
105326 | Parker Switch – Hicks Switch 345kV Line | Upgrade Parker Switch – Hicks Switch 345kV Line |  | Parker Switch | Hick Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5105 | 2028-12-15 |  | 345 | 0 | 23 | 0 |  | Parker | Tarrant | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 1436, 2081 | Y |  |  |  | 105327 | 105326
105328 | Pebble Creek Switch – Shankle Switch 138kV Line Upgrade | Upgrade Pebble Creek Switch – Shankle Switch 138kV Line |  | Pebble Creek Switch | Shankle Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4397 | 2028-12-15 |  | 138 | 0 | 16.6 | 0 |  | Ellis | Ellis | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 221, 2229, 12329, 12344 | Y |  |  |  | 105329 | 105328
110036 | Construct the Voss Lake - Walleye Creek 138 kV Line | Construct the Voss Lake - Walleye Creek 138 kV Line |  | Voss Lake | Walleye Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6552 | 2028-12-15 |  | 138 | 2 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3712, 3750 | Y |  |  |  | 110037 | 110036
110246 | Roanoke - Kingsridge 138 kV Line | Upgrade Roanoke - Kingsridge 138 kV Line |  | Roanoke | Kingsridge | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5351 | 2028-12-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  | 2025-11-18 | 2026-05-18 |  | 1846, 1856, 1857, 1872, 2038, 2118, 11857, 15101, 15116 | Y |  |  |  | 110477 | 110246
100599 | Establish Hillsboro Switch 138/69 kV Auto #2 | Establish Hillsboro Switch 138/69 kV Auto #2 |  | Hillsboro 138 kV Switch | Hillsboro 69 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6488 | 2028-12-15 |  | 138 | 0 | 0 | 104 |  | Hill | Hill | Tier 4 |  |  |  |  | 3522, 3523, 3814 | Y |  |  |  | 100600 | 100599
104158 | Pecos Trail to Wolf 138 kV Line Section Rebuild | Rebuild the existing 138 kV line section from Pecos Trail to Wolf 138 kV. |  | Pecos Trail | Wolf | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8527 | 2028-12-15 |  | 138 | 0 | 9.7 | 0 |  | Ward | Ward | Tier 3 | 25RPG008 |  |  |  | 1013, 1107, 11117 | Y |  |  |  | 104159 | 104158
104328 | New 138 KV BOLM Substation Cut-in on CKT1021 BE to KB | New 138 KV BOLM Substation Cut-in on CKT1021 BE to KB |  | 9180 | 9163, 9123 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2028-12-15 |  | 138 | 0 | 0.2 | 0 |  |  |  | Tier 4 |  |  |  |  | 9123, 9163, 9180 | Y |  |  |  | 104329 | 104328
99066 | Royse Switch – Farmersville Switch 345 kV Double-Circuit Line | Upgrade Royse Switch – Farmersville Switch 345 kV Double-Circuit Line |  | Farmersville Switch | Royse Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4255 | 2028-12-15 |  | 345 | 0 | 0 | 0 |  | Collin | Rockwall | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 1685, 2461, 2478 | Y |  |  |  | 99067 | 99066
99350 | Rebuild the Bell County East - Voss Lake 345 kV DCKT Line | Rebuild the Bell County East - Voss Lake 345 kV DCKT Line |  | Bell County East | Voss Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6401 | 2028-12-15 |  | 345 | 0 | 29.6 | 0 |  | Bell | Milam | Tier 1 |  |  |  |  | 3687, 3751, 3761 | Y |  |  |  | 99351 | 99350
99359 | Sweetwater Creek POI - Eskota 69 kV line and convert to 138 kV | Rebuild the Sweetwater Creek POI - Eskota 69 kV line and convert to 138 kV approved as part of the 24RPG040 Oncor Roscoe Area Upgrades Project. |  | Eskota | Oak Spring | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9000 | 2028-12-15 |  | 138 | 0 | 24.6 | 0 |  | Nolan | Nolan | Tier 2 | 24RPG040 | 2024-12-23 | 2025-05-30 |  | 1339, 1340, 1406, 1407, 1408, 1409, 1413, 9451 | Y |  |  |  | 99360 | 99359
99383 | Establish Paramount 345 kV Switch | Establish Paramount 345 kV Switch |  | Tower | Tower | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6454 | 2028-12-15 |  | 345 | 1.2 | 0 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3413, 3414, 3699, 3780 | Y |  |  |  | 99384 | 99383
99361 | Permian Basin Reliability Plan Upgrade ID L25C | Add Permian Basin Reliability Plan Upgrade ID L25C. Convert the existing Plowboy - Eskota 69-kV line to 138 kV. Rebuild the Eskota 138/69 kV Switch approved as part of the part of Permian Basin Reliability Plan Upgrade ID L25C. Required to convert the existing Plowboy - Eskota 69-kV line to 138-Kv |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8805 R8806 R8823 | 2028-12-15 |  | 138 | 0 | 10.88 | 0 |  |  |  | Tier 3 |  |  |  |  | 1339, 1340, 1380, 1381, 1382, 1384, 1386, 1387, 1406, 1409, 10091, 10103, 10198, 11341, 11384, 76319, 180052, 180054 | Y |  |  |  | 99404 | 99361
99479D | Snyder - China Grove 69 kV Loop Converstion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L23. Convert the existing Snyder - Scurry - China Grove and Snyder - Amoco Tap - China Grove 69-kV lines to 138-kV. This converts the Snyder - Scurry 69 kV Line into 138 kV and reterminates into the new Bluff Creek and Snyder 138 kV Switches. |  | Snyder | Bluff Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L23 | 2028-12-15 |  | 138 | 0 | 13.2 | 0 |  | Scurry | Scurry | Tier 1 |  |  |  |  | 1306, 1370, 1372, 10199, 10203, 10204, 10205 | Y |  |  |  | 99484 | 99479
99239A | Establish Muscovy 345/138 kV Switch | Establish the Muscovy 345/138 kV Switch |  | Muscovy | Muscovy | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6212, R6342, R6362 | 2028-12-15 |  | 345 | 0 | 0 | 700 |  | Williamson | Williamson | Tier 1 | 25RPG009 | 2025-03-11 |  |  | 3673, 3692, 3700, 3787, 13673, 13692, 13695 | Y |  |  |  | 99240 | 99239
99239C | Establish Muscovy 345/138 kV Switch | Construct the Muscovy - Limmer (LCRA TSC) 345 kV Double-Circuit Line |  | Muscovy | Limmer (LCRA TSC) | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6212, R6342, R6362 | 2028-12-16 |  | 345 | 4 | 0 | 0 |  | Williamson | Williamson | Tier 1 | 25RPG009 | 2025-03-11 |  |  | 3700, 7341 | Y |  |  |  | 99268 | 99239
99387 | Rebuild the Paramount - Salado 345 kV DCKT Line | Rebuild the Paramount - Salado 345 kV DCKT Line |  | Tower | Salado | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6358 | 2028-12-16 |  | 345 | 0 | 12.4 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3699, 3780 | Y |  |  |  | 99388 | 99387
99389 | Rebuild the Paramount - Temple 345 kV DCKT Line | Rebuild the Paramount - Temple 345 kV DCKT Line |  | Tower | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6402 | 2028-12-16 |  | 345 | 0 | 2.9 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3414, 3780 | Y |  |  |  | 99390 | 99389
104460 | Kingsbury Substation Addition | Add new load serving substation 1.5 miles northwest of Kingsbury w/40 MVA PWT, station to be cut into LCRA T158 ckt. |  |  |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2028-12-22 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7180, 7183, 7222 | Y |  |  |  | 104461 | 104460
80373 |  |  |  | IOLA | CRUTCHFIELD | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-12-29 |  | 138 | 0 | 5.5 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 4, 8 | Y |  |  |  | 80374 | 80373
91623 |  |  |  | Lillian | Highpoint | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2028-12-29 |  | 138 |  | 5.5 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 419, 439 | Y |  |  |  | 91624 | 91623
85953 | Camp Wood - Leakey Transmission Line Conversion | LCRATSC will perform a voltage conversion on Camp Wood – Leakey (T269) 69-kV transmission line. This project will increase the reliability of transmission facilities by converting the substation equipment at Camp Wood and Leakey substation to operate at 138-kV. |  | Bandera 7438 | Leakey 7426 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-12-30 | 2958101 | 138 | 0 | 0 | 0 |  | Bandera | Real | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 7426, 7428, 7438, 7439, 7440, 8633, 80074 | Y |  |  |  | 87789 | 85953 | 2023-W14
112127 | Upgrade Batesville - Crystal City SW as part of Crystal City SW to Downie upgrade |  |  | Batesville | Crystal City SW | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-12-30 |  | 69 | 0 | 17.3 | 0 |  | Zavala | Zavala | Tier 4 |  |  |  |  | 5849, 5855 | Y |  |  |  | 112128 | 112127
104632 | Canopy: Construct New 345 kV Station | Interconnect Palo Verde Wind to the New Canopy 345 kV Station on the Grissom to Lon Hill 345 kV line | NEW | Canopy |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2026011 | 2028-12-30 |  | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8455, 8624, 80419 | Y |  |  |  | 104633 | 104632
103344G | PH Robinson to WA Parish Hardening 25RPG028 | Rebuild and reconductor Ckt.99B Oasis to WA Parish as a Hardening upgrade. |  | Oasis | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-30 |  | 345 | 0 | 19.58 | 0 |  |  |  | Tier 4 | 25RPG028 |  | 2026-02-06 |  | 43035, 44000 | Y | N |  |  | 103440 | 103344
103344E | PH Robinson to WA Parish Hardening 25RPG028 | Rebuild and reconductor Ckt.18C Oasis to WA Parish as a Hardening upgrade |  | Oasis | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-30 |  | 345 | 0 | 19.56 | 0 |  |  |  | Tier 4 | 25RPG028 |  | 2026-02-06 |  | 43035, 44000 | Y | N |  |  | 103438 | 103344
103344C | PH Robinson to WA Parish Hardening 25RPG028 | Rebuild and reconductor Ckt.99E Meadow to Oasis as a Hardening upgrade |  | Meadow | Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-30 |  | 345 | 0 | 3.18 | 0 |  |  |  | Tier 4 | 25RPG028 |  | 2026-02-06 |  | 43030, 43035, 49932, 49933 | Y | N |  |  | 103436 | 103344
103344A | PH Robinson to WA Parish Hardening 25RPG028 | Rebuild and reconductor Ckt.99A PH Robinson to Meadow as a Hardening upgrade |  | PH Robinson | Meadow | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-30 |  | 345 | 0 | 17.4 | 0 |  | Galveston | Brazoria | Tier 4 | 25RPG028 |  | 2026-02-06 |  | 42000, 43030 | Y | N |  |  | 103434 | 103344
100647 | Install a 50MVAr Capacitor Bank at Anderson Substation |  |  | 5003 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1043 | 2028-12-30 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5003 | Y |  |  |  | 100648 | 100647
112131 | Upgrade N.Batesville - Leona - Uvalde Sw - Uvalde Sub - Downie | Upgrade N.Batesville - Leona - Uvalde Sw - Uvalde Sub - Downie as part of Crystal City SW to Downie rebuild |  | N. Batesville | Downie | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-12-30 |  | 69 | 0 | 24.5 | 0 |  | Zavala | Uvalde | Tier 4 |  |  |  |  | 5820, 5822, 5823, 5836, 5883 | Y |  |  |  | 112132 | 112131
112129 | Upgrade N.Batesville - S. Batesville - Batesville Sw | Upgrade N.Batesville - S. Batesville - Batesville Sw as part of Crystal City SW to Downie rebuild |  | N. Batesville | Batesville | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-12-30 |  | 69 | 0 | 7.5 | 0 |  | Zavala | Zavala | Tier 4 |  |  |  |  | 5836, 5848, 5849 | Y |  |  |  | 112130 | 112129
81238 | Zoisite: Construct New 345 kV Station and 345 kV Lines to STP | Interconnect the HIF load to the new Zoisite 345 kV station and construct two new STP to Zoisite 345 kV lines. Install two (2) capacitor banks. | Project Description and In-Service Date Update | STP | Zoisite | Planned |  | AEP TCC | LaRissa Lundry deevans@aep.com 918-599-2938 | TP2023803 | 2028-12-30 |  | 345 | 1.6 | 0 | 0 | 0,261.8 | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5915, 8123, 8754, 8789, 80056 | Y |  |  |  | 81239 | 81238
110383 | Add 210 MVAr cap bank to Sycamore station |  |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 | 0,210 | Leon |  | Tier 4 | [5 empty] | N |  |  |  | 110384 | 110383
110375 | Lane City Pump to Lane City: Rebuild 138 kV Line | Rebuild the Lane City Pump to Lane City 138 kV Line for CNP base load | Project Title and Description Update | Lane City Pump | Lane City | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2028-12-31 |  | 138 | 0 | 4.5 | 0 |  | Wharton | Wharton | Tier 4 | [5 empty] | Y | N |  |  | 110376 | 110375
55217 | Putnam to Leon: Rebuild 138 kV line | Rehab the Putnam to Leon (Oncor) 138 kV line | TSP/Company Contact Update | Putnam | Leon | Planned | 1042 - 1269 | AEP TNC | LaRissa Lundry myturner@aep.com 918-599-2437 | 1859 | 2028-12-31 |  | 138 | 0 | 20.81 | 0 |  | Callahan | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | N |  |  | 55218 | 55217
59394 | Pointer to Rule: Rebuild 69 kV Line | Rehab the Pointer to Rule 69 kV Line |  | Pointer | Rule | Planned | 1122 - 1300 | AEP TNC | Sally Matthews myturner@aep.com 918-599-2437 | 1867 | 2028-12-31 |  | 69 | 0 | 14.78 | 0 |  | Haskell | Knox | Tier 4 |  |  |  |  | 763, 6014, 6115, 6120, 60346 | Y | N |  |  | 59395 | 59394
45566 | Holly to Southside: Upgrade 138 kV Line | Upgrade the Holly to Southside 138 kV line | Company Contact and In-Service Date Update | Holly | Southside | Planned | 994 - 1172 | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | 3747 TP-2019-065 | 2028-12-31 |  | 138 | 0 | 1.8 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486 | Y | N |  |  | 65532 | 45566
70891 | Eola Tap: Rebuild 69 kV Line | Rehab Eola Tap 69 kV Line | In-Service Date Update | Eola Tap | Eola | Planned |  | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 |  | 2028-12-31 |  | 69 | 0 | 11.69 | 0 |  | Concho | Concho | Tier 4 |  |  |  |  | 6370, 6371 | Y | N |  |  | 70892 | 70891
110350 | Tap 2nd Limestone - Gibbons Creek into Yellow Wolf |  |  | Limestone | Gibbons Creek | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  | Leon |  | Tier 4 | [5 empty] | N | N |  |  | 110351 | 110350
111307 | Resnik: Epand 138 kV Station | Interconnect Gregory Power Partners (GPP) to the Existing Resnik 138 kV Station |  | Resnik |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5576 | TP2026170 | 2028-12-31 |  | 138 | 0.1 | 0 | 0 |  | San Patricio |  | Tier 4 | [5 empty] | Y | N |  |  | 111308 | 111307
103419 | Weslaco Switch: 138 kV Breaker Replacement | Replace 138 kV breakers at the Weslaco Switch 138 kV station | NEW | Weslaco Switch |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2026026 | 2028-12-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 | [5 empty] | Y | N |  |  | 103420 | 103419
103472 | LCRATSC Limmer Muscovy Transmission Line Addition | LCRATSC shall build 50% of two new transmission lines from Limmer to ONCOR Muscovy. |  | Limmer (LCRA) | Muscovy (ONCOR) | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2028-12-31 |  | 345 | 4 | 0 | 0 |  | Williamson | Williamson | Tier 1 | 25RPG009 | 2025-03-11 | 2026-05-08 |  |  | Y |  |  |  | 103473 | 103472
111116 | Cruce: Expand 345 kV Station | Interconnect the Duval Data Center load to the Cruce 345 kV station | NEW | Cruce |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 |  | 2028-12-31 |  | 345 | 2 | 0 | 0 |  | Duval |  | Tier 4 |  |  |  |  | 80078, 80079, 80528 | Y |  |  |  | 111117 | 111116
76696 | Border - Shifting Sands 138 kV Line and add Wink - Shifting Sands 138 kV second circuit | Add Permian Basin Reliability Plan Upgrade ID L1B and L1C Construct a new Border – Shifting Sands 138 kV Line and Add Wink - Shifting Sands 138-kV second circuit |  | Atchison | Wink | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8628 | 2028-12-31 |  | 138 | 64.6 | 0 | 0 |  | Loving | Winkler | Tier 2 |  |  |  |  | 1074, 1075, 1296, 10257, 11089, 11391, 18672, 18705 | Y |  |  |  | 111419 | 76696
91487 | Austrop - Sim Gideon Transmission Line Upgrade | LCRA TSC will upgrade the Austrop - Sim Gideon 138-kV double-circuit transmission line to achieve a higher operational rating. This line consists of the following transmission circuits. T171 Austrop - Sim Gideon T172 Bastrop City - Sim Gideon (via Settlers) T231 Bastrop City - Webberville (via Settlers) T673 Austrop - Webberville |  | Austrop | Sim Gideon | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8100 | 2028-12-31 |  | 138 | 0 | 34.65 | 0 |  | Travis | Bastrop | Tier 3 |  |  |  |  | 7310, 7316, 7320, 7327, 7329, 9328 | Y |  |  |  | 91488 | 91487
104628 | LCRATSC Joliet Substation Addition | Construct a new substation to serve load for BBEC. This substation will be located in the south of the city of Lockhart area close to LCRA TSC owned T157 Lockhart - Magnolia Mercer. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2028-12-31 |  | 69 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7215, 7218, 7219 | Y |  |  |  | 104629 | 104628
99549 | Long Creek - Sweetwater East 345 kV Double Circuit Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L24B. Upgrade the existing Long Creek - Mulberry Creek (Oncor) - Sweetwater East 345-kV double-circuit line |  | Sweetwater East | Long Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L24_B | 2028-12-31 |  | 345 | 0 | 84.6 | 0 |  | Nolan | Shackelford | Tier 1 |  |  |  |  | 1435, 1459, 11420 | Y |  |  |  | 99550 | 99549
103006A | CEHE Upgrades as part of TNMP's Galveston Region Project | Install new 138kV PH Robinson to TNMP-Hidden Lakes tie-line. |  | PH Robinson | TNMP-Hidden Lakes | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 |  | 138 | 0.46 | 0 | 0 |  | Galveston | Galveston | Tier 3 | 24RPG039 |  |  |  |  | Y | N |  |  | 103007 | 103006
110185 | Austrop - Sim Gideon Transmission Line Upgrade | Upgrade the Austrop - Sim Gideon 138-kV double-circuit transmission line, including lines connecting to Bastrop City and Webberville, to achieve a minimum 560 MVA emergency rating for all lines in series at the Austrop, Webberville, Sim Gideon, Settlers, and Bastrop City substations. Ideally, lines will be rated to 4000A. This is an LCP Upgrade project to support Batch Zero Base Load |  | Austrop | Sim Gideon | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-12-31 |  | 138 | 0 | 17.3 | 0 |  | Travis | Bastrop | Tier 4 | [5 empty] | Y |  |  |  | 110186 | 110185
103344I | PH Robinson to WA Parish Hardening 25RPG028 | Upgrade Oasis 345kV fault duty to 63KA. |  | Oasis | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 | 25RPG028 |  | 2026-02-06 |  |  | Y | N |  |  | 103442 | 103344
109648A | PH Robinson to Algoa Corner P1056 Hardening (26RPG020) | Rebuild/reconductor portions of Ckt.93B PH Robinson to Alta Loma as a Hardening upgrade. Increase PH Robinson Ckt.93B equipment to increase thermal limits. |  | PH Robinson | Alta Loma | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 |  | 138 | 0 | 9.46 | 0 |  | Galveston | Galveston | Tier 3 | 26RPG020 | 2026-05-18 | 2026-06-09 | 2026-06-10 | 42015, 42061 | Y |  |  |  | 109695 | 109648
109648B | PH Robinson to Algoa Corner P1056 Hardening (26RPG020) | Rebuild/reconductor portions of Ckt.06K PH Robinson to Pilgrim as a Hardening upgrade |  | PH Robinson | Pilgrim | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 |  | 138 | 0 | 0.35 | 0 |  | Harris | Galveston | Tier 3 | 26RPG020 | 2026-05-18 | 2026-06-09 | 2026-06-10 | 42015, 48284 | Y |  |  | Cost included in main entry. | 109696 | 109648
109648C | PH Robinson to Algoa Corner P1056 Hardening (26RPG020) | Rebuild/reconductor portions of Ckt.04A Friendswood to Mustang Bayou as a Hardening upgrade |  | Friendswood | Mustang Bayou | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 |  | 138 | 0 | 7.05 | 0 |  | Harris | Brazoria | Tier 3 | 26RPG020 | 2026-05-18 | 2026-06-09 | 2026-06-10 | 42960, 48112 | Y |  |  | Cost included in main entry. | 109697 | 109648
109743 | Mulberry Creek: Expand 345 kV Station | Interconnect the Lancium load to the Mulberry Creek 345 kV station | NEW | Mulberry Creek |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2026091 | 2028-12-31 |  | 345 | 2.5 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6235, 60519 | Y |  |  |  | 109744 | 109743
110324 | Add new CTT Sycamore 345 kV station |  |  |  |  | Conceptual |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  | Leon |  | Tier 4 |  |  |  |  | 46020, 79007, 79011, 79014 | N | N |  |  | 110325 | 110324
99122 | Drill Hole 765/345 kV Autotransformer #1 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1C. Establish the Drill Hole 765/345 kV Switch with one 765/345 kV autotransformer |  | Drill Hole | Drill Hole | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_C | 2028-12-31 |  | 765 | 0 | 0 | 2250 | -675,0 | Culberson | Culberson | Tier 1 |  |  |  |  | 10073, 18733, 18734 | Y |  |  |  | 99123 | 99122
99124 | Longshore 765/345 kV Autotransformer #1 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1B. Establish the Longshore 765/345 kV Switch with one 765/345 kV autotransformer |  | Longshore | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_B | 2028-12-31 |  | 765 | 0 | 0 | 2250 | -675,0 | Howard | Howard | Tier 1 |  |  |  |  | 1058, 18112, 18113 | Y |  |  |  | 99125 | 99124
103344B | PH Robinson to WA Parish Hardening 25RPG028 | Upgrade Ckt.99A PH Robinson to Meadow to increase thermal limits. |  | PH Robinson | Meadow | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  | Galveston | Brazoria | Tier 4 | 25RPG028 |  | 2026-02-06 |  | 42000, 43030 | Y | N |  |  | 103435 | 103344
99126 | Drill Hole - Longshore 765 kV Line | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1E. Add a new Longshore – Drill Hole 765-kV single-circuit line |  | Drill Hole | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_E | 2028-12-31 |  | 765 | 184.8 | 0 | 0 |  | Culberson | Howard | Tier 1 |  |  |  |  | 18112, 18733 | Y |  |  |  | 99127 | 99126
103344D | PH Robinson to WA Parish Hardening 25RPG028 | Upgrade Ckt.99E Meadow to Oasis to increase thermal limits. |  | Meadow | Oasis | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 | 25RPG028 |  | 2026-02-06 |  | 43030, 43035, 49932 | Y | N |  |  | 103437 | 103344
87092 | Arcadia to Southside: Upgrade 138 kV Line | Upgrade the Arcadia to Southside 138 kV line | Company Contact and In-Service Date Update | Arcadia | Southside | Planned | 994 - 1172 | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | 3747 TP-2019-065 | 2028-12-31 |  | 138 | 0 | 2.59 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8483, 8486, 8496, 8609, 8617, 8618 | Y | N |  |  | 87093 | 87092
103344F | PH Robinson to WA Parish Hardening 25RPG028 | Upgrade Ckt.18C Oasis to WA Parish to increase thermal limits. |  | Oasis | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 | 25RPG028 |  | 2026-02-06 |  | 43035, 44000 | Y | N |  |  | 103439 | 103344
100281 | Benedum_Autotransformer_Addition | Benedum Substation will be cut-in to the PUCT-approved Bearkat to North McCamey 345-kV transmission line and two 345/138-kV autotransformers will be installed at Benedum Substation |  | Benedum |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  | Upton | Upton | Tier 3 | 24RPG024 | 2024-08-09 | 2025-01-01 |  | 59903, 71213, 76000, 76200, 76201, 76202 | Y |  |  |  | 100282 | 100281
103344H | PH Robinson to WA Parish Hardening 25RPG028 | Upgrade Ckt.99B Oasis to WA Parish to increase thermal limits. |  | Oasis | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 | 25RPG028 |  | 2026-02-06 |  | 43035, 44000 | Y | N |  |  | 103441 | 103344
81783 | Ingleside to Seabird: Construct New 138 kV Line | Interconnect the Mu load to the new Seabird 138 kV station on the Homeport to Ingleside 138 kV line, construct a new 138 kV line from Ingleside to Seabird, and add capacitors |  | Ingleside | Seabird | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2028-12-31 |  | 138 | 2.9 | 0 | 0 | 0,69.1 | San Patricio | Nueces | Tier 4 |  |  |  |  | 8425, 8808, 84250 | Y | N |  |  | 81784 | 81783
81659 | Lytle: Construct New 138 kV Terminal | Interconnect the Cinco II load to the existing Lytle 138 kV station and add capacitors |  | Lytle |  | Conceptual |  | AEP TCC/ETT | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-12-31 |  | 138 | 0 | 0 | 0 | 0,34.5 | Medina |  | Tier 4 |  |  |  |  | 8962 | Y |  |  |  | 81660 | 81659
98599 | Bluff Creek to Mulberry Creek: Rebuild 345 kV Line as a Double Circuit | Rebuild existing 345 kV line from Bluff Creek to Mulberry Creek as a double circuit line | Tier, RPG number and Review Date Update | Bluff Creek | Mulberry Creek | Planned | TP2024147 | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2028-12-31 |  | 345 | 26.9 | 0 | 0 |  | Taylor | Jones | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 6235, 60040 | Y | N |  |  | 98600 | 98599
71004B | Julia CEHE-Owned Sub for Melaza Solar (21INR0220) | Install generator lead from Julia (JUL) CEHE substation to MALEZA/Maleza Solar |  | Julia | MALEZA | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 00:01 | 2026-05-15 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44220, 113251 | Y | N |  |  | 87172 | 71004
103006B | CEHE Upgrades as part of TNMP's Galveston Region Project | Upgrade Meadow Auto A1 to increase thermal limits. |  | Meadow |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 3 | 24RPG039 |  |  |  |  | Y | N |  |  | 103008 | 103006
51001 | Friess Ranch to Sonora: Rebuild 69 kV line | Rehab Rocksprings to Sonora 69 kV line | TSP/Company Contact Update | Friess Ranch | Sonora | Planned | 1044 - 1217 | AEP TNC/AEP TCC | Greg Crane myturner@aep.com 918-599-2437 | 2791 | 2028-12-31 12:00 |  | 69 | 0 | 24.3 | 0 |  | Sutton | Sutton | Tier 3 | 19RPG018 | 2019-10-24 | 2019-11-18 |  | 6513, 6570, 8238, 8239, 60210, 60438 | Y | N |  |  | 65554 | 51001
110449 | STEC Ammonia Plant Load Project Phase 3 | -Rebuild the existing Formosa to Joslin 138-kV transmission line with normal and emergency ratings of at least 485 MVA, approximately 2.41-mile -Rebuild the existing Tungsten to Vistron to Black Bayou to Big Three to Dupont 138-kV transmission line with normal and emergency ratings of at least 485 MVA, approximately 21.11-mile. |  | Formosa,Tungsten | Joslin,Dupont | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-12-31 12:15 |  | 138 | 0 | 23.5 | 0 |  | Victoria | Victoria | Tier 1 | 25RPG012 |  | 2026-01-13 |  |  | Y | N |  |  | 110450 | 110449
49564 | Mantle: Construct New 345 kV Station | Mantle: Construct New 345 kV Station | In-Service Date Update | Mantle |  | Planned | 1035 - 1213 | AEP TCC | Tom Reynolds jlsolis@aep.com 361-881-5574 | 3774 TP2018166 | 2028-12-31 20:00 |  | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8059, 8383, 8573 | Y | N |  |  | 49565 | 49564
111193 | LCRATSC Webberville Power Transformer Addition | LCRA TSC will improve reliability at the Webberville Substation by installing a second power transformer. New circuit breakers and switches shall meet LCRA TSC minimum 138-kV design standards. |  | Webberville |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2029-01-01 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7327, 7329, 9328 | Y |  |  |  | 111194 | 111193
80330 |  |  |  | DWU Southside | McCree | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-01-05 |  | 69 | 0 | 7.45 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 230, 832 | Y |  |  |  | 80331 | 80330 | 2023-NC24
80334 |  |  |  | CONCORD | WILDCAT TAP | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-01-05 |  | 138 | 0 | 4.9 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 388, 394 | Y |  |  |  | 80335 | 80334 | 2023-NC25
100702 | Install a 28.57MVAr Capacitor Bank at Tallly Rd Substation |  |  | 5422 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-01-31 |  | 138 | 0 | 0 | 0 | 0,28.57 | Medina |  | Tier 4 |  |  |  |  | 5422 | Y |  |  |  | 100703 | 100702
99726 | Dulce: Construct New 345 kV Station | Interconnect Iguala Solar to the new Dulce 345 kV station on the Static to STP 345 kV line | Company Contact Update | Dulce |  | Planned |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2025344 | 2029-01-31 |  | 345 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 5915, 8676, 80286 | Y |  |  |  | 99727 | 99726
49556 | Ozona: Rebuild 69 kV station | Replace existing Ozona 69 kV station with a new 69 kV ring bus | TSP/Company Contact and In-Service Date Update | Ozona |  | Planned | 1018 - 1196 | AEP TNC | Travis Coody myturner@aep.com 918-599-2437 | 2780 | 2029-01-31 |  | 69 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6550, 6551, 6560, 60194 | Y | N |  |  | 65538 | 49556
109933 | Install new 345kV transmission loop in conjunction with S-0996 Nockenut switchyard and 1st structure outside new switchyard for Point of Interconnect (POI) |  |  | 5326 | 51335380 | Planned | S-0996 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0337 | 2029-01-31 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Wilson | Tier 4 |  |  |  |  | 5133, 5320, 5380 | Y |  |  |  | 109934 | 109933
109739 | Donatello: Construct New 345 kV Station | Interconnect the Mirando Valley Wind and the Viento Bravo Wind to the new Donatello 345 kV station on the Cenizo to Cruze 345 kV line | NEW | Donatello |  | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2026135 | 2029-01-31 |  | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80079, 80220, 80515 | Y | N |  |  | 109740 | 109739
72999 | Haskell to Munday: Rebuild 69 kV Line | Rehab Haskell to Munday 69 kV Line | In-Service Date Update | Haskell | Munday | Planned |  | AEP TNC | Bill Edwards myturner@aep.com 918-599-2437 |  | 2029-01-31 |  | 69 | 0 | 21.71 | 0 |  | Haskell | Knox | Tier 4 | 22RPG043 | 2022-12-15 | 2023-01-11 |  | 6107, 6122, 6123, 6124, 6125, 6126, 60021 | Y | N |  |  | 73000 | 72999
73116 | Install new Cedar Port Mobile (CDM) 138kV Distribution Substation | Install new Cedar Port Mobile (CDM) 138kV Distribution Substation. Loop from existing Ckt.03B to create new Ckt.03B Trinity Bay to Cedar Port Mobile to KENNY tap. |  | Cedar Port Mobile | Trinity | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-01-31 |  | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40921, 41610, 48360 | N | N |  |  | 73120 | 73116
103412 | Brownsville SW: 69 kV Breaker Replacement | Replace 69 kV breakers at the Brownsville 69 kV station | NEW | Brownsville SW |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2025939 | 2029-01-31 |  | 69 | 0 | 0 | 0 |  | Cameron |  | Tier 4 | [5 empty] | Y | N |  |  | 103413 | 103412
99207 | 25RPG020 CPS Energy Large Load Additions Project: Rebuild Cagnon to VLSI transmission line | Rebuild (8.7 miles) Cagnon to VLSI transmission line to at least 478MVA |  | 5055 | 5467 | Planned | S-1060 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0397 | 2029-01-31 |  | 138 | 0 | 8.74 | 0 |  | Bexar | Bexar | Tier 1 | 25RPG020 |  |  |  | 5055, 5467 | Y |  |  |  | 99208 | 99207
103962 | Wesmer: 138 kV Breaker and Circuit Switcher Replacement | Replace 138 kV breakers and circuit switches at the Wesmer 138 kV station | NEW | Wesmer |  | Planned |  | AEP TCC | Tyler Harble jlsolis@aep.com 361-881-5574 | TP2025940 | 2029-01-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 | [5 empty] | Y | N |  |  | 103963 | 103962
110943B | Cooke County Resiliency Project | Rebuild the Sivells Bend Tap to Sivell’s bend transmission line |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-02-01 |  | 69 |  | 7.5 | 0 |  | Cooke | Cooke | Tier 2 | 26RPG007 | 2026-05-06 |  |  | 716, 725, 727 | Y |  |  |  | 111218 | 110943
111302 | Harligen SW: Expand 138 kV Station | Interconnect the Power Proof Properties load to the existing Harligen SW 138 kV station | NEW |  |  | Planned |  | AEP TCC | Remington Hajdik jlsolis@aep.com 361-881-5575 | TP2026149 | 2029-02-28 |  | 138 | 0.5 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8327, 89146 | Y |  |  |  | 111303 | 111302
111350 | Specter: Construct New Switch Station | Interconnect TEC's Rainey substation to the new Specter 138 kV switch station on the Abilene Plant to Putnam 138 kV line |  | Specter |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2026164 | 2029-02-28 |  | 138 | 0 | 0 | 0 |  | Callahan |  | Tier 4 |  |  |  |  | 6078, 6275, 6670, 60476 | Y | N |  |  | 111351 | 111350
110419 | Cesium: Install New 345 kV Capacitor Bank | Install a new capacitor bank at the Cesium 345 kV station | Transmission Owner and Reactive Capability Update | Cascabel |  | Conceptual |  | AEP TNC/ETT | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-02-28 |  | 345 | 0 | 0 | 0 | 0,183 | Fisher |  | Tier 4 |  |  |  |  | 60198 | Y | N |  |  | 110420 | 110419
111248 | Elmdale: Install capacitor bank | Install a new capacitor bank at the Elmdale 69 kV station |  | Elmdale |  | Planned |  | ETT | Mina Turner myturner@aep.com 918-599-2437 | TP2026164 | 2029-02-28 |  | 69 | 0 | 0 | 0 | 15.4,0 | Callahan |  | Tier 4 |  |  |  |  | 6301 | Y | N |  |  | 111249 | 111248
72502 | Tarpley Substation Upgrade | Provide transmission point of interconnection to Battery energy storage system near the Tarpley Substation. Add a 138kV bay and associated circuit breaker to existing substation (25INR0196) |  | Tarpley |  | Planned |  | BEC | Dylan Garzad.garza@banderaelectric.com.866.226.3372 ext. 6803 d.garza@banderaelectric.c 8662263-372-6803 Ext 6803 |  | 2029-02-28 |  | 138 | 0.1 | 0 | 0 |  | Bandera |  | Tier 4 | [5 empty] | Y | N |  |  | 72503 | 72502
91903 | Iowa: Construct New Distribution Station | Construct new distribution station on the Bates to Liston 138 kV line | TSP/Company Contact and In-Service Date Update | Iowa |  | Planned |  | AEP TCC | Michael Dawson jlsolis@aep.com 361-881-5574 |  | 2029-02-28 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8392, 8394, 80180 | Y | N |  |  | 91904 | 91903
99629 | BEPC_TPIT_HAMILTONGTC_GUSTINETOINDIANGAP |  |  | Gustine | Indian Gap | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-01 |  | 69 | 0 | 12.8 | 0 |  | Comanche | Hamilton | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 262, 265, 268, 269, 273 | Y |  |  |  | 99630 | 99629
91483 | RCEC_Watkins_Station | New REC station cutting into Ray Raymond to Explorer line and new 12.35 mile from new REC station to Watkins |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2029-03-01 |  | 138 | 0 | 19 | 0 |  | Van Zandt | Van Zandt | Tier 2 |  |  |  |  | 6802, 6833, 6906, 6907 | Y |  |  |  | 91484 | 91483
109724 | Wadsworth: Retire Station | Retire the Wadsworth station |  | Plotner |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | DP26X0012 | 2029-03-01 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8114, 8115, 8139 | Y | N |  |  | 109725 | 109724
109958 | Install a new 138kV transmission loop and switchyard to connect new Moonstone Solar PV Generation |  |  | 5313 | 5132, 5155 | Planned | S-1069 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0414 | 2029-03-01 |  | 138 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 5132, 5155, 5313 | Y |  |  |  | 109959 | 109958
99639 | BEPC_TPIT_HAMILTONGTC_PancakeSyrup |  |  | Pancake | Pancake | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-15 |  | 138 | 0 | 0 | 200 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 158, 159 | Y |  |  |  | 99640 | 99639
99652 | BEPC_TPIT_HAMILTONGTC_Energize_Odell |  |  | Hasse | Odell | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-22 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 273, 277, 278, 33273 | Y |  |  |  | 99653 | 99652
99674 | BEPC_TPIT_HAMILTONGTC_Energize_IndianGap |  |  | Odell | Indian Gap | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-03-29 |  | 138 | 0 | 0 | 0 |  | Comanche | Hamilton | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 262, 268, 273, 33262, 33273 | Y |  |  |  | 99675 | 99674
77031 | Las Lomas: Construct New Distribution Station | Construct new distribution station on the La Grulla to Rio Grande City 138 kV line | In-Service Date Update | Las Lomas |  | Planned |  | AEP TCC | Morris Everroad jlsolis@aep.com 361-881-5574 | DP24X0003 | 2029-03-31 |  | 138 | 0 | 0 | 0 |  | Starr |  | Tier 4 |  |  |  |  | 8793, 8798, 8806 | Y |  |  |  | 77032 | 77031
70630 | Ballinger to Santa Anna: Rebuild 69 kV line | Rebuild 69 kV line and rebuild taps on the Ballinger to Santa Anna 69 kV line. | In-Service Date Update | Ballinger | Santa Anna | Planned |  | AEP TNC | Michael Pitts myturner@aep.com 918-599-2437 | TA2021193 | 2029-03-31 |  | 69 | 0 | 0 | 0 |  | Runnels | Coleman | Tier 3 | 22RPG028 | 2022-08-01 | 2022-09-01 |  | 6329, 6338, 6341, 6342, 6343, 6344, 6345, 6346, 6349, 6353, 60019, 60024, 60029 | Y |  |  |  | 70664 | 70630
49550 | Port Isabel: Rebuild As GIS Station | Rebuild Port Isabel as a GIS | Company Contact and In-Service Date Update | Port Isabel |  | Planned | 958 - 1136 | AEP TCC | Forrest Farson deevans@aep.com 918-599-2938 | 3716 | 2029-03-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8338, 8744 | Y | N |  |  | 49551 | 49550
104630 | Colmena: Construct new 345 kV Station | Interconnect Abeja Solar to the new Colmena 345 kV Station on the Tango to Goddard 345 kV line | NEW | Colmena |  | Planned |  | AEP TCC | Michael Blackwell jlsolis@aep.com 361-881-5574 | TP2026011 | 2029-03-31 |  | 345 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8012, 8689, 80392, 80393 | Y |  |  |  | 104631 | 104630
109767 | North Laredo: Expand 345 kV Station | Interconnect the Regis Sumlin load to the existing North Laredo 345 kV station | NEW | North Laredo |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2026106 | 2029-03-31 |  | 345 | 4.5 | 0 | 0 | 0,47 | Webb |  | Tier 4 |  |  |  |  | 8909, 80526 | Y |  |  |  | 109768 | 109767
109765 | Goddard: Expand 345 kV Station | Interconnect the FrontierGen Load to the existing Goddard 345 kV station | NEW | Goddard |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2026107 | 2029-03-31 |  | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8606, 80525 | Y |  |  |  | 109766 | 109765
109763 | Smoky Hill: Expand 345 kV Station | Interconnect the Crusoe Haskell II load to the Smoky Hill 345 kV station | TSP/Company Contact Update | Smoky Hill |  | Planned |  | ETT | Ali Barkat myturner@aep.com 918-599-2437 | TP2026103 | 2029-03-31 |  | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 6104, 60330 | Y |  |  |  | 109764 | 109763
109733 | Plotner: Construct New Distribution Station | Construct new distribution station on the Wadsworth to Celanese 138 kV line | NEW | Plotner |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | DP26X0012 | 2029-03-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8138, 8852, 80124 | Y | N |  |  | 109734 | 109733
102667 | BEPC_TPIT102667_Bream |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-02 |  | 138 | 0 | 0 | 0 |  | Robertson |  | Tier 4 |  |  |  |  | 26, 30, 32, 37, 79, 3707 | Y |  |  |  | 102669 | 102667
99679 | BEPC_TPIT_HAMILTONGTC_Energize_Waring |  |  | Indian Gap | Waring | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-05 |  | 138 | 0 | 0 | 0 |  | Hamilton | Comanche | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 268, 269, 273, 33262, 33268, 33273 | Y |  |  |  | 99680 | 99679
99683 | BEPC_TPIT_HAMILTONGTC_Energize_Gustine |  |  | Odell | Gustine | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-12 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 272, 273, 33263 | Y |  |  |  | 99684 | 99683
99689 | BEPC_TPIT_HAMILTONGTC_Energize_Resley |  |  | Gustine | Resley | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-19 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 178, 272, 33263, 155321 | Y |  |  |  | 99690 | 99689
99691 | BEPC_TPIT_HAMILTONGTC_Energize_Potsville |  |  | Resley | Potsville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-04-26 |  | 138 | 0 | 0 | 0 |  | Comanche | Hamilton | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 178, 258, 272, 151971, 151973 | Y |  |  |  | 99692 | 99691
104082 | Alice to Falfurrias: Convert to 138 kV | Convert Alice to Falfurrias to 138 Kv opertions and Build Alice, North Ella, and Premont to 138 kV standard | NEW | Alice | Falfurrias | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2026020 | 2029-04-30 |  | 138 | 0 | 0 | 0 |  | Jim Wells | Brooks | Tier 3 | 25RPG045 | 2025-12-10 | 2026-01-07 |  | 8500, 8503, 8508, 8510, 8878, 8894, 80394, 80395 | Y | N |  |  | 104083 | 104082
104388 | Government Wells: Capacitor Bank Installation | Install Capacitor Bank at the Government Wells 69 kV station (Alice Area Upgrades) |  | Government Wells |  | Planned | NEW | AEP TCC | John Solis jlsolis@aep.com 361-881-5576 | TP2026024 | 2029-04-30 |  | 69 | 0 | 0 | 0 | 0,7.2 | Duval |  | Tier 3 |  | 2025-12-10 | 2026-01-09 | 2026-01-12 | 8505, 80222, 80414 | Y | N |  |  | 104389 | 104388
109601 | Expand Mykawa 138kV substation and install one generator lead for new interconnection to Megamouth Energy Storage (26INR0341). |  |  | Mykawa |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-04-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y |  |  |  | 109602 | 109601
105912 | Ciruela: Construct New 345 kV Station | Interconnect the Panther load to the new Ciruela 345 kV station on the Bonilla to Rio Hondo 345 kV line |  | Ciruela |  | Planned |  | AEP TCC | Robert Younger jlsolis@aep.com 361-881-5575 | TP2026093 | 2029-04-30 |  | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8318, 8573, 8834, 80458, 80462, 80463 | Y |  |  |  | 105913 | 105912
93226 | Fort Stockton Switch: Expand 345 kV Station | Install three 345/138 kV autotransformers at the Fort Stockton Switch 345/138 kV station | Company Contact, RPG Number and BOD Review date Update | Fort Stockton Switch |  | Planned |  | AEP TNC | Damian Raab myturner@aep.com 918-599-2437 | TP2025141 | 2029-04-30 |  | 345 | 0 | 0 | 2250 |  | Pecos |  | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 60146, 60147, 60148, 60149, 60152, 60153, 60404, 60717, 76007, 78926 | Y |  |  |  | 93227 | 93226
109735 | Jacaranda: Construct New 345 kV Station | Interconnect the Lancium load to the new Jacaranda 345 kV station and install two autotransformers |  | Jacaranda |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2026088 | 2029-04-30 |  | 345 | 3 | 0 | 900 |  | Taylor |  | Tier 4 |  |  |  |  | 60282, 60311, 60312, 60313, 60315, 60316 | Y | N |  |  | 109736 | 109735
109737 | Jacaranda to Mulberry Creek: Construct two new 345 kV lines | Construct two new 345 kV lines between Jacaranda and Mulberry Creek |  | Jacaranda | Mulberry Creek | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2026088 | 2029-04-30 |  | 345 | 6 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6235, 60311 | Y | N |  |  | 109738 | 109737
104390 | Stadium: Capacitor Bank Installation | Install Capacitor Bank at the Stadium 69 kV station (Alice Area Upgrades) |  | Stadium |  | Planned | NEW | AEP TCC | John Solis jlsolis@aep.com 361-881-5576 | TP2026024 | 2029-04-30 |  | 69 | 0 | 0 | 0 | 0,14.4 | Jim Wells |  | Tier 3 |  | 2025-12-10 | 2026-01-09 | 2026-01-12 | 8889 | Y | N |  |  | 104391 | 104390
111346 | Jacaranda to Paulownia (Oncor): Construct two new 345 kV lines | Construct two new 345 kV lines between Jacaranda and Paulownia (Oncor) |  | Jacaranda | Paulownia | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2026088 | 2029-04-30 |  | 345 | 0.2 | 0 | 0 |  | Taylor |  | Tier 4 | [5 empty] | Y | N |  |  | 111347 | 111346
110425 | San Angelo Red Creek to San Angelo Paulann: Rebuild 138 kV Line | Rebuild the SA Red Creek to SA Paulann 138 kV line | NEW | SA Red Creek | SA Paulann | Conceptual |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-04-30 |  | 138 | 0 | 6.4 | 0 |  | Tom Green | Tom Green | Tier 4 | [5 empty] | Y | N |  |  | 110426 | 110425
110084F | This models upgrades required for a proposed load addition | Add additional Capacitor to nearby Raider substation. |  | Raider |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-01 |  | 345 | 0 | 0 | 0 | 0,350 | Fort Bend | Fort Bend | Tier 1 | [5 empty] | N | N |  |  | 110508 | 110084
110753 | Related_WylieSW_LCP_Upgrades_Nevada_WylieSW_Line | Related_WylieSW_LCP_Upgrades_Nevada_WylieSW_Line |  | Nevada | WylieSW | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | 0 | 2029-05-01 |  | 138 | 0 | 3.71 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 811, 833 | Y |  |  |  | 110754 | 110753
110753 | Related_WylieSW_LCP_Upgrades_Nevada_WylieSW_Line | Related_WylieSW_LCP_Upgrades_Nevada_WylieSW_Line |  | Nevada | WylieSW | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | 0 | 2029-05-01 |  | 138 | 0 | 3.71 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 811, 833 | Y |  |  |  | 110754 | 110753
110870 | STEC_110870_MesquiteLargeLoadProjectPhase2 | Install up to 250 MVAR of dynamic reactive support at 91302 RODG_EDW POI 138-kV Substation Install up to 250 MVAR of dynamic reactive support at 5727 PAWNEESUB8 138-kV Substation |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-05-01 12:15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110871 | 110870
110581 | STEC Palangana Large Load Addition Phase 1 | Install up to 250 MVAR of dynamic reactive support at 91302 RODG_EDW POI 138-kV Substation Install up to 250 MVAR of dynamic reactive support at 5727 PAWNEESUB8 138-kV Substation |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-05-01 12:15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110582 | 110581
99693 | BEPC_TPIT_HAMILTONGTC_Energize_HamiltonSyrup |  |  | Potsville | Syrup | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-03 |  | 138 | 0 | 0 | 0 |  | Hamilton | Cooke | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 158, 159, 178, 258, 33258 | Y |  |  |  | 99694 | 99693
99718 | BEPC_TPIT_HAMILTONGTC_Energize_Gatesville |  |  | Syrup | Gatesville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-10 |  | 138 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 157, 158, 159, 250, 33157 | Y |  |  |  | 99719 | 99718
111644 | GVEC FM725 Substation Addition | GVEC is adding a new 138 kV substation 2.5 Miles Northwest of the McQueeney Substation, cutting into T498, to serve a 40 MVA load added to the area. |  | McQueeney | Schumansville | Planned |  | GVEC | Rene Hernandez rhernandez@gvec.org 830-263-2034 |  | 2029-05-11 |  | 138 | 0 | 0 | 0 |  | Guadalupe | Guadalupe | Tier 4 |  |  |  |  | 7606, 7607, 7609 | Y |  |  |  | 111645 | 111644
4270 | Handley - Hemphill 138 kV Line | Upgrade existing line | Project Deferral | Handley | Hemphill | Conceptual |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5214 | 2029-05-15 |  | 138 | 0 | 7.4 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1950, 2164, 2167 | Y | N |  |  | 11818 | 4270
73570 | Steger Substation Addition | Substation addition to provide Point of Interconnection for Oncor New Sweden substation addition. |  | Steger |  | Conceptual |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7336, 7337, 7339 | Y | N |  |  | 73571 | 73570
73567 | Berry Creek Substation Addition | Substation addition to provide Point of Interconnection for Oncor Andice substation addition. |  | Berry Creek |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7361, 7521, 70522 | Y | N |  |  | 78401 | 73567
66023 | T340 T-Line Upgrade | Upgrading the Marion to Sheriff's Posse Transmission Line T340 from 795 ACSR to 959 ACSS conductor. Upgrades to conductor and structures are included. Structures designed for ultimate build-out of double-circuit bundled 959 ACSS in preparation for additional future capacity. The adjacent line, T339 is built in a double circuit configuration with T340 between Marion and Sheriff's Posse. It will be taken out of service and rebuilt as part of this project. T339 is single conductor 959 Suwanee today, and is planned to be rebuilt with the same conductor during this project. | Contracting has taken longer than originally expected. | Marion | Sheriff's Posse | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2029-05-15 |  | 138 | 0 | 6.8 | 0 |  | Guadalupe | Comal | Tier 4 |  |  |  |  | 7178, 7460 | Y | N |  |  | 78403 | 66023
81551 | Dos Rios 138 kV Switch | Establish Dos Rios 138 kV Switch |  | Dos Rios Switch | Dos Rios Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6231 | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 30, 3707, 3725 | Y |  |  |  | 81552 | 81551
92854 | Carrollton East Switch-Carrollton Tarpley Rd 138 kV Double-Circuit Line Section | Carrollton East Switch-Carrollton Tarpley Rd 138 kV Double-Circuit Line Section |  | Carrollton East | Carrollton Tarpley Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4246 | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2558, 2559, 2577, 2578 | Y |  |  |  | 92855 | 92854
93306 | Bastrop_Mesquite_Utley_Transmission_Line_Addition | Provide looped transmission service for BBEC-member load at 138-kV Utley Substation |  | 7320 | 7317 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7317, 7320 | Y |  |  |  | 93307 | 93306
99243 | Big Spring - Signal Mountain 69 kV Conversion to 138 kV | Add Permian Basin Reliability Plan Upgrade ID L20E and L20F. Convert the existing Big Spring - Signal Mountain 69-kV line to 138-kV. Connect Signal Mountain to Prong Moss. |  | Big Spring | Prong Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L20_E_F | 2029-05-15 |  |  | 0 | 8.7 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 1322, 1323, 1351, 1353, 10066, 10190 | Y |  |  |  | 99244 | 99243
99417 | Establish Lamesa 345/138 kV Switch | Construct Lamesa 345/138 kV Switch approved as part of 24RPG015 |  | Lamesa | Lamesa | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8800 | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Dawson | Dawson | Tier 1 | 24RPG015 | 2024-05-02 |  |  | 1163, 10082, 10083, 10084 | Y |  |  |  | 99418 | 99417
99419 | Lamesa - Faraday 345 kV Double Circuit Line | Oncor and WETT joint project to construct the Lamesa (Oncor) - Faraday (WETT) 345 kV DCKT Line approved as part of 24RPG015 |  | Lamesa | Faraday | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8792 | 2029-05-15 |  | 345 | 154 | 0 | 0 |  | Dawson | Borden | Tier 1 | 24RPG015 | 2024-05-02 |  |  | 10082, 59905 | Y |  |  |  | 99420 | 99419
99524 | Upgrading line | Upgrade conductor to 1xSuwannee | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70489, 70491 | Y |  |  |  | 99525 | 99524
99823 | LCRATSC_Flatonia-Luling_Transmission_Line_Conversion | LCRA TSC will upgrade terminal facilities at Luling, Harwood, Bluestem, Thompsonville, Waelder, and Flatonia substations along the Flatonia - Luling 69-kV transmission line to operate at 138-kV. |  | 7248 Flatonia | 7224 Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Fayette | Caldwell | Tier 4 |  |  |  |  | 7223, 7224, 7230, 7231, 7232, 7247, 7248, 7895, 7896 | Y |  |  |  | 99824 | 99823
99831 | LCRATSC_Cedar_Hill_Manor_Transmission_Line_Upgrade | LCRA TSC will upgrade T495 Cedar Hill - Manor 138-kV transmission line to achieve a higher operational rating. |  | 7330 Manor | 7331 Cedar Hill | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2029-05-15 |  | 138 | 0 | 8.2 | 0 |  | Travis | Bastrop | Tier 4 |  |  |  |  | 7330, 7331 | Y |  |  |  | 99832 | 99831
99913 | Eagle Lake - El Campo Transmission Line Overhaul | Perform an overhaul on the 38.2 mile T548 Eagle Lake - El Campo (including all tap lines) 69-kV transmission line. Per LCRA TSC Transmission System Planning procedure, replacement structures will be capable of operating at 138-kV. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2029-05-15 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 3 |  |  |  |  | 8100, 8541, 78105, 78538, 78539, 78542, 78543 | Y |  |  |  | 99914 | 99913
99922 | Green Valley Substation Addition | Provide a transmission point of interconnection at the new Green Valley Substation. A new GVEC customer has requested 500 MW of load on LCRA TSC-owned 345-kV double-circuit line, T248 Marion -Zorn and T419 Clear Springs - Marion. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-762-3658 |  | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7042, 7044, 7050, 7054 | Y |  |  |  | 99923 | 99922
99928 | Three Lakes Substation Addition | Provide a transmission point of interconnection at the new Three Lakes Substation. A new PEC customer has requested 800 MW of load on LCRA TSC-owned 345-kV T775 John Dumas - Hornsby |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7041, 7047, 7059 | Y |  |  |  | 99929 | 99928
81296B | Prong Moss – Rockhound 345 kV Line Rebuild | Prong Moss – Rockhound 345 kV Second Circuit Addition |  | Prong Moss | Rockhound | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2029-05-15 |  | 345 | 0 | 60.2 | 0 |  | Midland | Howard | Tier 1 | 23RPG029 |  |  |  | 10057, 10062 | Y |  |  |  | 102848 | 81296
103301 | LCRATSC Paige - Sim Gideon Transmission Line Upgrade | LCRA TSC will perform an overhaul on the 9.8-mile T151 Paige - Sim Gideon 138-kV transmission line and upgrade the line to achieve a higher operational rating. |  | Gideon | Paige | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 9.8 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7308, 7310 | Y |  |  |  | 103302 | 103301
103835 | LCRATSC Brenham North - Highway 36 Transmission Line Overhaul | Perform an overhaul on the 9.1 mile T215 Brenham North - Highway 36 138-kV transmission line. |  | Brenham North | Highway 36 | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 9.1 | 0 |  | Washington | Washington | Tier 4 |  |  |  |  | 7291, 7294 | Y |  |  |  | 103836 | 103835
104639 | LCRA TSC Lytton Springs - Zorn Transmission Line Upgrade | LCRA TSC will upgrade the Austrop - Zorn 345-kV double-circuit transmission line to achieve a higher operational rating. Coordinating PMCRs include 91312, 104635, and 104639. |  | 9074 | 7042 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8063, PLC-8139, PLC-8140 | 2029-05-15 |  | 345 | 0 | 46.2 | 0 |  | Caldwell | Guadalupe | Tier 1 |  |  |  |  | 7034, 7042, 7051, 9074 | Y |  |  |  | 104642 | 104639 | 2024-SC19
105749 | Goatpad 138kV Switch | Establish Goatpad 138kV Switch |  | Goatpad | Goatpad | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4525 | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 1 | 25RPG004 |  |  |  | 226, 2286, 2310, 16309 | Y |  |  |  | 105750 | 105749
105833 | Alba Road 345kV Statcom | Upgrade Alba Road 345kV Statcom |  | Alba Switch |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4386 | 2029-05-15 |  | 345 | 0 | 0 | 0 | 250250 | Dallas |  | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 3062, 3091 | Y |  |  |  | 105834 | 105833
105836 | Greene 345kV STATCOM | Establish Greene 345kV STATCOM |  | Greene |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4387 | 2029-05-15 |  | 345 | 0 | 0 | 0 | 0,250 | Dallas |  | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 3063, 3090 | Y |  |  |  | 105837 | 105836
99318 | Mascho - Lamesa 345 kV Double Circuit Line | Construct Mascho - Lamesa 345 kV DCKT Line approved as part of 24RPG015 |  | Mascho 345 kV Switch | Lamesa 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8792 | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Andrews | Dawson | Tier 1 | 24RPG015 | 2024-05-02 |  |  | 10082, 18879 | Y |  |  |  | 105945 | 99318
109749 | Settlers Autotransformer Addition | Construct a new 345-kV yard adjacent to the existing 138-kV Settlers Substation and cut-in to the Austrop - Lost Pines 345-kV double-circuit transmission line (owned by Austin Energy). LCRA TSC will install two 345/138-kV autotransformers at Settlers Substation. |  | Settlers |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-05-15 |  | 345 | 0 | 0 | 1344 |  | Bastrop |  | Tier 3 |  |  |  |  | 7040, 7327, 7377, 9041, 73771, 73772 | Y |  |  |  | 109750 | 109749
109786 | LCRATSC Sim Gideon Substation Upgrade | The upgrade of the Sim Gideon Substation to increase its current-carrying capability and improve overall system reliability. |  | Sim Gideon |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org | PLC-8317 | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  |  | 7306, 7308, 7310, 7316, 7319, 7320, 7555, 7575 | Y |  |  |  | 109787 | 109786
109790 | LCRATSC Gabriel Rivery Transmission Line Upgrade | LCRA TSC will upgrade T457 Gabriel - Rivery 138-kV transmission line to achieve a higher operational rating. The need for this project with identified by ERCOT in the EIR for RPG 25RPG009. |  | Gabriel | Rivery | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8540 | 2029-05-15 |  | 138 | 0 | 2.44 | 0 |  | Williamson | Williamson | Tier 4 | 25RPG009 | 2025-03-17 | 2026-08-19 |  | 7343, 7346, 7347 | Y |  |  |  | 109791 | 109790
110010 | Rebuild the Revolution Switch - Ash Creek Switch 138 kV Line | Rebuild the Revolution Switch - Ash Creek Switch 138 kV Line |  | Revolution Switch | Ash Creek Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6415 | 2029-05-15 |  | 138 | 0 | 32.4 | 0 |  | Hill | Navarro | Tier 1 | 25RPG041, 25RPG043 | 2025-11-12 | 2026-08-19 |  | 213, 3387, 3473, 3515 | Y |  |  |  | 110011 | 110010
110018A | Rebuild the Temple - Temple Pecan Creek Switch 345 kV Double Circuit Line | Rebuild the Temple - Temple Pecan Creek 345 kV Lines |  | Temple | Temple Pecan Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6532 | 2029-05-15 |  | 345 | 0 | 8.8 | 0 |  | Bell | Bell | Tier 1 | 25RPG009 |  |  |  | 3412, 3414 | Y |  |  |  | 110019 | 110018
110030 | Establish Lorraine 345 kV Switch | Establish Lorraine 345 kV Switch |  | Lorraine | Lorraine | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6541 | 2029-05-15 |  | 345 | 0.6 | 0 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3414, 3780, 3885 | Y |  |  |  | 110031 | 110030
110018B | Rebuild the Temple - Temple Pecan Creek Switch 345 kV Double Circuit Line | Rebuild the Temple - Temple Pecan Creek 138 kV Lines |  | Temple | Temple Pecan Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6532 | 2029-05-15 |  | 138 | 0 | 8.8 | 0 |  |  |  | Tier 1 | 25RPG009 |  |  |  | 3415, 3420 | Y |  |  |  | 110046 | 110018
111240 | LCRATSC Crosswinds Goforth Transmission Line Overhaul | Perform an overhaul on the 3 mile T661 Crosswinds - Goforth 138kV transmission line. |  | Crosswinds | Goforth | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2029-05-15 |  | 138 | 0 | 3.14 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7501, 7503 | Y |  |  |  | 111241 | 111240
111242 | LCRATSC Crosswinds Turnersville Transmission Line Overhaul | Perform an overhaul on the 3.8 mile T272 Crosswinds - Turnersville transmission line. |  | Crosswinds | Turnersville | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2029-05-15 |  | 138 | 0 | 3.69 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7500, 7503 | Y |  |  |  | 111243 | 111242
111245A | Gillespie - Fredericksburg - Goehmann Lane - Kendall Transmission Line Overhaul |  |  | Gillespie | Goehmann Lane | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 14.6 | 0 |  | Gillespie | Gillespie | Tier 3 |  |  |  |  | 7130, 7132, 7145, 7149, 7150, 7413, 7414, 7415, 7416, 7417, 7752 | Y |  |  |  | 111246 | 111245
111280 | Chappell Hill - Waller Transmission Line Overhaul | Perform an overhaul on the 16 mile T232 Chappell Hill - Waller transmission line replacing conductor with single-Suwannee. |  | Chappell Hill | Waller | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.org 512-578-4514 | PLC-8346 | 2029-05-15 |  | 138 | 0 | 15.93 | 0 |  | Washington | Waller | Tier 4 |  |  |  |  | 7272, 7574 | Y |  |  |  | 111281 | 111280
111282 | Hunt - Turtle Creek Transmission Line Storm Hardening | LCRA will replace the conductor between Hunt and Turtle Creek as part of an effort to rebuild and storm harden the circuit resulting in greater durability and reliability of assets in the area. |  | Hunt | Turtle Creek | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.org 512-578-4514 | PLC-8473 | 2029-05-15 |  | 138 | 0 | 12.8643 | 0 |  | Kerr | Kerr | Tier 4 |  |  |  |  | 7144, 7442 | Y |  |  |  | 111283 | 111282
111372 | LCRATSC Cedar Hill Power Transformer Addition | This project will add a second power transformer (T2) to Cedar Hill substation. |  | Cedar Hill |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  |  | 7331 | Y |  |  |  | 111373 | 111372
111378 | LCRATSC Giddings Winchester Transmission Line Overhaul | This project performs an overhaul on the T222 Giddings - Winchester 138-kV transmission line. |  | Giddings | Winchester | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Lee | Fayette | Tier 4 |  |  |  |  | 7302, 7306 | Y |  |  |  | 111379 | 111378
111702 | Sunrise 138 kV Switch | Establish Sunrise 138 kV Switch |  | Sunrise Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5018 | 2029-05-15 |  | 138 | 1.4 | 0 | 0 |  | Dallas |  | Tier 4 |  | 2025-02-06 | 2026-03-19 |  | 3083, 16900 | Y |  |  |  | 111703 | 111702
100136 | WETT project to loop Faraday station in the existing Long Draw to Scurry 345 kV double circuit transmission line approved as part of 24RPG015. |  |  | Faraday | Faraday | Planned |  | WETT | Christopher Ramirez cramirez@wettllc.com |  | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Borden | Borden | Tier 1 | 24RPG015 | 2024-05-03 | 2024-05-28 | 2025-05-16 | 59905, 59912, 59922 | Y |  |  |  | 111877 | 100136
111533 | NBU Comal Substation Breaker and a Half Upgrade | In conjunction with LCRA's Breaker and a Half upgrade at Comal Substation, NBU will upgrade the T335 line terminal and three transformer terminals. |  | Comal | Loop 337 | Planned |  | NBU | Jeff Morrissjmorriss@nbutexas.com.830.608.8881 jmorriss@nbutexas.com 8662263-372-6803 Ext 6803 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 | [5 empty] | Y | N |  |  | 111534 | 111533
110172 | Sim Gideon Substation Upgrade | LCRA TSC will upgrade terminal equipment in series L_WINCHE8_1Y (Bus #7306) - L_SIMGID8_1Y (Bus #7310) 138.0-kV line transmission line to achieve a higher operational rating, minimum 4000A, as an LCP upgrade for Batch Zero Base Load. |  | Sim Gideon |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 | [5 empty] | Y |  |  |  | 110173 | 110172
109874 | Rebuild Sandow 345 kV Switch | Rebuild Sandow 345 kV Switch |  | Sandow Switch | Sandow Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6281 | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 3 | [5 empty] | Y |  |  |  | 109875 | 109874
109890 | Rebuild Lufkin Switch - Nacogdoches Southeast Switch 138 kV Line | Rebuild Lufkin Switch - Nacogdoches Southeast Switch 138 kV Line |  | Lufkin Switch | Nacogdoches Southeast Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6062 | 2029-05-15 |  | 138 | 0 | 22.4 | 0 |  | Angelina | Nacogdoches | Tier 1 | [5 empty] | Y |  |  |  | 109891 | 109890
109851 | Establish Redland Switch 345/138 kV Auto #2 | Establish Redland Switch 345/138 kV Auto #2 |  | Redland 345 kV Switch | Redland 138 kV Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6508 | 2029-05-15 |  | 345 | 0 | 0 | 600 |  | Angelina | Angelina | Tier 1 | [5 empty] | Y |  |  |  | 109852 | 109851
109886A | Establish Kolb Lake 138 kV Switch And Capacitor Bank | Establish Kolb Lake 138 kV Switch |  | Kolb Lake Switch | Kolb Lake Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6505 | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 1 | [5 empty] | Y |  |  |  | 109887 | 109886
110038 | Establish Rosebud 345 kV Switch | Establish Rosebud 345 kV Switch |  | Rosebud | Rosebud | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6559 | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 3 | [5 empty] | Y |  |  |  | 110039 | 110038
110132 | River Oaks Bus Substation Upgrade | LCRA will upgrade terminal equipment at River Oaks Substation to increase the operational rating of the terminating 138 kV lines as an LCP project for Batch Zero Base Load |  | River Oaks |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2029-05-15 |  | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 | [5 empty] | Y |  |  |  | 110133 | 110132
110024 | Rebuild the Hutto - Gilleland Creek 138 kV DCKT Line | Rebuild the Hutto - Gilleland Creek 138 kV DCKT Line |  | Hutto | Gilleland Creek (LCRA TSC) | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6521 | 2029-05-15 |  | 138 | 0 | 34.5 | 0 |  | Williamson | Travis | Tier 3 | [5 empty] | Y |  |  |  | 110025 | 110024
103303 | LCRATSC Paige - Winchester Transmission Line Upgrade | LCRA TSC will perform an overhaul on the 15-mile T615 Paige - Winchester 138-kV transmission line and upgrade the line to achieve a higher operational rating. |  | Paige | Winchester | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2029-05-16 |  | 138 | 0 | 14.85 | 0 |  | Bastrop | Fayette | Tier 4 |  |  |  |  | 7306, 7308, 7310 | Y |  |  |  | 103304 | 103303
111245B | Gillespie - Fredericksburg - Goehmann Lane - Kendall Transmission Line Overhaul |  |  | Goehmann Lane | Kendall | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-05-16 |  | 138 | 0 | 20.5 | 0 |  | Gillespie | Kendall | Tier 3 |  |  |  |  | 7150, 7416 | Y |  |  |  | 111247 | 111245
109886B | Establish Kolb Lake 138 kV Switch And Capacitor Bank | Establish Kolb Lake 138 kV Switch Capacitor Bank |  | Kolb Lake Switch | Kolb Lake Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6505 | 2029-05-16 |  | 138 | 0 | 0 | 0 | 0,110.4 | Angelina | Angelina | Tier 1 | [5 empty] | Y |  |  |  | 109928 | 109886
103784 | BEPC_TPIT_Beecham_Gap |  |  | Kempner | Beecham Gap | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-16 |  | 138 | 0 | 15 | 0 |  | Coryell |  | Tier 4 |  |  |  |  | 256, 260, 7260 | Y |  |  |  | 103785 | 103784
99720 | BEPC_TPIT_HAMILTONGTC_Energize_FortGates |  |  | Gatesville | Fort Gates | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-17 |  | 138 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 149, 250, 254, 33157, 33254 | Y |  |  |  | 99721 | 99720
99722 | BEPC_TPIT_HAMILTONGTC_Energize_Snelling |  |  | Fort Gates | Snelling | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-24 |  | 138 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 149, 33254, 33266, 33267 | Y |  |  |  | 99723 | 99722
110397 | Lon Hill to Bunsen: Rebuild 138 kV | Rebuild Bunsen to Lon Hill 138 kV line | NEW | Lon Hill | Bunsen | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2029-05-29 |  | 138 | 2.6 | 0 | 0 |  |  |  | Tier 1 | 25RPG016 |  |  |  |  | Y | N |  |  | 110398 | 110397
93661 | New BPUB substation needed to service new load. Will require 6 miles of 138kV transmission line. |  |  | Nimzo | DEMETER | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2029-05-29 |  | 138 | 12 | 0 | 0 |  |  |  | Tier 2 |  |  |  |  | 59551, 59555 | Y |  |  |  | 93662 | 93661
72051 | Twinwood Mobile (TWM) 138kV Distribution Substation | Install new Twinwood Mobile (TWM) 138kV Distribution Substation. Loop from existing Ckt.25E to create new Ckt.25E Foster to Twinwood Mobile to Peters |  | Twinwood | Foster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44256, 44861, 46220 | N | N |  |  | 72052 | 72051
59260 | Mason Phillips Tap to Mason Phillips: Rebuild 69 kV Line | Rehab the Mason Phillips Tap to Mason Phillips 69 kV Line | In-Service Date Update | Seaquist | Mason Phillips | Planned | 1127 - 1305 | AEP TNC | Christopher Carroll twang1@aep.com 918-599-2635 | 1872 | 2029-05-30 |  | 69 | 0 | 13.7 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6395, 6407, 60458 | Y | N |  |  | 65588 | 59260
109575I | Upgrade ckt26 from Angleton to CAMDEN and ckt82 from Angleton to Oyster Creek to increase thermal limits. | Upgrade Ckt.26E SINTEK to CAMDEN to increase thermal limits. |  | SINTEK | CAMDEN | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 26RPG012 | 2026-03-16 | 2026-04-06 | 2026-04-07 | 43240, 43365 | Y |  |  |  | 109583 | 109575
109575H | Upgrade ckt26 from Angleton to CAMDEN and ckt82 from Angleton to Oyster Creek to increase thermal limits. | Upgrade Ckt.82G BIPORT to Oyster Creek to increase thermal limits. |  | BIPORT | Oyster Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 26RPG012 | 2026-03-16 | 2026-04-06 | 2026-04-07 | 42190, 43335 | Y |  |  |  | 109584 | 109575
109950 | Install a new 138kV transmission loop in conjunction with the S-1086 Taormina BESS switchyard project |  |  | 5425 | 5465, 5025 | Planned | S-1086 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0373 | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5025, 5425, 5465 | Y |  |  |  | 109951 | 109950
109966 | The New Generation Facility will be looped into the 345 kV Elm Creek to South Texas Project (STP) circuit 1 |  |  | 5236 | 5320, 5380 | Planned | S-1090 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0420 | 2029-05-31 |  | 345 | 0 | 0 | 0 |  | Guadalupe | Wilson | Tier 4 |  |  |  |  | 5236, 5320, 5380 | Y |  |  |  | 109967 | 109966
109980 | Loop In Foster Rd Substation into Beck Road to Kirby 138kV transmission line |  |  | 5162 | 5035, 5250 | Planned | S-1089 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5035, 5162, 5250 | Y |  |  |  | 109981 | 109980
110569 | Janka: Add Reactive Support | Add Reactive Support at the Janka 345 kV Station | NEW | Janka |  | Conceptual |  | ETT | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-05-31 |  | 345 | 0 | 0 | 0 | 0,350 | Hardeman |  | Tier 4 |  |  |  |  | 61616 | Y | N |  |  | 110570 | 110569
111043A | Install new 138/35 kV Lee Road Distribution Substation. | Install Lee Road 138/35kV Distribution Substation. Loop on existing circuit as Ckt.66D Humble to Lee Road to Treaschwig. |  | Lee Road | Humble / Treaschwig | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40830, 45020, 46550 | Y |  |  |  | 111044 | 111043
100071 | Taurus: Construct New 345 kV Station | Interconnect TNMP data center load to the new Taurus 345 kV station on the Solstice to Sand Lake 345 kV line | Project Description and In-Service Date Update | Taurus |  | Conceptual |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-05-31 |  | 345 | 0.2 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 18669, 60404, 60462 | Y |  |  |  | 100072 | 100071
111364 | Install new 138kV transmission loop and substation |  |  | 5230 | 5326 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5230, 5326, 5472 | Y |  |  |  | 111365 | 111364
110068B | This models the new CEHE Raider Substation and upgrades required for a proposed load addition | Loop 345 kV Ckt. 64 Wolf-Hillje line into the new 345 kV CEHE Raider substation. Upgrade line relaying on Ckt 64 WOLF-Raider-Hillje. |  | Raider | Wolf/Hillje | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44160, 44200, 44990 | Y | N |  |  | 112119 | 110068
109575G | Upgrade ckt26 from Angleton to CAMDEN and ckt82 from Angleton to Oyster Creek to increase thermal limits. | Upgrade Ckt.82 Clute to CAVERN to BIPORT to increase thermal limits. |  | CAVERN | Clute/BIPORT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 26RPG012 | 2026-03-16 | 2026-04-06 | 2026-04-07 | 42190, 43330 | Y |  |  |  | 109582 | 109575
109575F | Upgrade ckt26 from Angleton to CAMDEN and ckt82 from Angleton to Oyster Creek to increase thermal limits. | Upgrade Ckt.82 RIWOOD to Clute to increase thermal limits. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 26RPG012 | 2026-03-16 | 2026-04-06 | 2026-04-07 | 42050, 43150 | Y |  |  |  | 109581 | 109575
109575E | Upgrade ckt26 from Angleton to CAMDEN and ckt82 from Angleton to Oyster Creek to increase thermal limits. | Upgrade Ckt.82C Angleton to RIWOOD to increase thermal limits. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 26RPG012 | 2026-03-16 | 2026-04-06 | 2026-04-07 | 42110, 43150 | Y |  |  |  | 109580 | 109575
109575D | Upgrade ckt26 from Angleton to CAMDEN and ckt82 from Angleton to Oyster Creek to increase thermal limits. | Upgrade Ckt.26 Clute to SINTEK to increase thermal limits. |  | Clute | SINTEK | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 26RPG012 | 2026-03-16 | 2026-04-06 | 2026-04-07 | 42050, 43240 | Y |  |  |  | 109579 | 109575
109575C | Upgrade ckt26 from Angleton to CAMDEN and ckt82 from Angleton to Oyster Creek to increase thermal limits. | Upgrade Ckt.26 STRATT to Clute to increase thermal limits. |  | STRATT | Clute | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 26RPG012 | 2026-03-16 | 2026-04-06 | 2026-04-07 | 42050, 43300 | Y |  |  |  | 109578 | 109575
109575B | Upgrade ckt26 from Angleton to CAMDEN and ckt82 from Angleton to Oyster Creek to increase thermal limits. | Upgrade Ckt.26I Samaritan to STRATT to increase thermal limits. |  | Samaritan | STRATT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 26RPG012 | 2026-03-16 | 2026-04-06 | 2026-04-07 | 42030, 43300 | Y |  |  |  | 109577 | 109575
109575A | Upgrade ckt26 from Angleton to CAMDEN and ckt82 from Angleton to Oyster Creek to increase thermal limits. | Upgrade Ckt.26C Angleton to Samaritan to increase thermal limits. |  | Angleton | Samaritan | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 3.23 | 0 |  | Brazoria | Brazoria | Tier 3 | 26RPG012 | 2026-03-16 | 2026-04-06 | 2026-04-07 | 42030, 42110 | Y |  |  |  | 109576 | 109575
99000C | Install (2) 14.4 MVAR distribution cap banks at Twinwood substation. Install (2) 14.4 MVAR distribution cap banks at Fulshear substation. Install (2) 40 MVAR transmission cap bank at Peters substation. | Install (1) additional 40 MVAR switchable transmission cap bank at Peters substation. (second of two) |  | Peters |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 | 0,40 | Fort Bend |  | Tier 4 |  |  |  |  | 46220 | Y | N |  |  | 109556 | 99000
109615A | WA Parish 138kV Fault Upgrade with Bus Reactors | Install (2) 5-Ohm Reactors at WA Parish as a fault duty upgrade. Split the existing WA Parish 138kV West bus. Install equipment to maintain 80KA fault duty. |  | WA Parish | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y |  |  |  | 109673 | 109615
110423 | San Angelo Red Creek to San Angelo Coke Street: Rebuild 138 kV Line | Rebuild the SA Red Creek to Coke Street 138 kV line | NEW | SA Red Creek | SA Coke Street | Conceptual |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-05-31 |  | 138 | 0 | 8.1 | 0 |  | Tom Green | Tom Green | Tier 4 | [5 empty] | Y | N |  |  | 110424 | 110423
111043B | Install new 138/35 kV Lee Road Distribution Substation. | Upgrade Ckt.66D Treaschwig to Westfield to increase thermal limits. |  | Treaschwig | Westfield | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 46550, 46570 | Y |  |  |  | 111045 | 111043
99724 | BEPC_TPIT_HAMILTONGTC_Energize_LeonCrusader |  |  | Snelling | Crusader | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Coryell | Coryell | Tier 2 | 25RPG003 | 2025-01-30 | 2025-08-26 |  | 126, 142, 145, 149, 33126, 33145, 33266 | Y |  |  |  | 99725 | 99724
99009D | 138kV Flewellen to Fort Bend Ckt 09G-60E Upgrades | Upgrade Ckt.60E Flewellen to Fort Bend to increase thermal limits. Expect Flewellen equipment upgrades and Fort Bend equipment/Relay upgrades to reach the Minimum ratings as second phase of upgrade |  | Flewellen | Fort Bend | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 25RPG010 | 2025-03-26 | 2025-04-18 | 2025-04-18 | 44230, 44280 | Y | N |  |  | 99013 | 99009
99009B | 138kV Flewellen to Fort Bend Ckt 09G-60E Upgrades | Upgrade Ckt.09G Flewellen to Brazos Valley to increase thermal limits. Expect FL/BV equipment upgrade as second phase of Ckt.09G upgrade. |  | Flewellen | Brazos Valley | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 3 | 25RPG010 | 2025-03-26 | 2025-04-18 | 2025-04-18 | 44100, 44230 | Y | N |  |  | 99011 | 99009
93217 | Update Topology in Brownsville Area per Approved RPG Project | Adding in 345 kV topology for LRGV Brownsville area (new 345 kV Chalybe station with two (2) 675 MVA autos being fed from Sharyland's Kingfisher and Palmito stations) per the BOD approved RPG project. Also added additional 138 kV feed from Stillman to AEP's Chalybe 138 kV | Added two (2) 675 MVA Autotransformers to serve load on 138 kV system | Chalybe |  | Planned | 77144 | SLU | Charles Aleman caleman@huntutility.com 682-406-9656 |  | 2029-05-31 |  | 345 | 47 | 0 | 1350 |  | Cameron |  | Tier 1 | 24RPG008 | 2024-06-11 | 2024-09-25 | 2024-12-03 | 8735, 79500, 79501, 79502, 79596, 79597, 79601 | Y | N |  |  | 94231 | 93217
93134 | Minnesota: Construct New Distribution Station | Construct new distribution station on the North Edinburg to Pharr 138 kV line between McColl Road and Pharr |  | Minnesota |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8085, 8372, 8908 | Y |  |  |  | 93135 | 93134
87427 | Rebuild Magnolia to Seminole 138kV line. | Replacement for recently committed PMCR # 4010. |  | Magnolia Sub | Seminole Sub | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 3.3 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38950, 38990 | Y |  |  |  | 87428 | 87427
54120 | Rebuild Tejas-Commanche (Bundled 795 ACSS) | Rebuild Tejas - Commanche 138 kV line with Bundled 795 ACSS conductor. |  | Tejas 138 kV Substation (Bus # 38530) | Commanche 138 kV Substation (Bus # 38560) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | STE07318 | 2029-05-31 |  | 138 | 0 | 0.95 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38530, 38560 | Y |  |  |  | 54121 | 54120
60502 | Rebuild Apache-Amoco with bundled 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38620, 38720 | Y |  |  |  | 60503 | 60502
60504 | Rebuild Caddo-Apache with bundled 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38710, 38720 | Y |  |  |  | 60505 | 60504
60522 | Rebuild Hidden Lakes-League City with 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  |  | 60523 | 60522
60526 | Rebuild West Columbia Local-Angleton with 795 ACSS | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 39530, 39560 | Y |  |  |  | 60527 | 60526
61550 | East Munday to Lake Pauline: Rebuild 138 kV Line | Rehab East Munday to Lake Pauline 138 kV line | TSP/Company Contact and In-Service Date Update | East Munday | Lake Pauline | Planned | 1129 - 1307 | AEP TNC | Greg Crane myturner@aep.com 918-599-2437 | 1874 | 2029-05-31 |  | 138 | 0 | 59.97 | 0 |  | Knox | Hardeman | Tier 4 | 20RPG018 |  |  |  | 6037, 6050, 6110 | Y | N |  |  | 65594 | 61550
66204 | Rebuild Hidden Lakes-PH Robinson with bundled 795 ACSS |  |  | TNMP Hidden Lakes (bus # 38900) | CenterPoint PH Robinson (bus # 42015) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 3.15 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 42015 | Y |  |  |  | 66205 | 66204
70796 | El Campo to Corichi: Rebuild 138 kV Line | Rehab the El Campo to Corichi 138 kV line | TSP/Company Contact Update | El Campo | Corichi | Planned |  | AEP TCC | Craig Tabor deevans@aep.com 918-599-2938 | TA2018020 | 2029-05-31 |  | 138 | 0 | 13.26 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 8099, 8102 | Y |  |  |  | 70797 | 70796
76348 | Reconductor Foxtail-PIGCreek-1926ACSS-138KV |  |  | Foxtail | PIG Creek | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-05-31 |  | 138 | 0 | 0.68 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38294, 60393 | Y |  |  |  | 76349 | 76348
109615D | WA Parish 138kV Fault Upgrade with Bus Reactors | Reposition existing Ckt.02B WA Parish to Nash (Phelps) as part of WAP 138kV West reactor additions |  | WA Parish | Phelps | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y |  |  | Cost included in main entry | 109680 | 109615
109615G | WA Parish 138kV Fault Upgrade with Bus Reactors | Reposition existing Ckt.82A WA Parish to Thompsons as part of WAP 138kV West reactor additions |  | Thompsons | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y |  |  | Cost included in main entry | 109678 | 109615
109615B | WA Parish 138kV Fault Upgrade with Bus Reactors | Modeling change only for this line position (No reposition |  | WA Parish |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y |  |  | Cost included in main entry | 109679 | 109615
109615E | WA Parish 138kV Fault Upgrade with Bus Reactors | Reposition existing WAP GT-1 generator lead as part of WAP 138kV West reactor additions |  | WA Parish |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y |  |  | Cost included in main entry | 109676 | 109615
109615F | WA Parish 138kV Fault Upgrade with Bus Reactors | Reposition existing Ckt.80A WA Parish to Thompsons as part of WAP 138kV West reactor additions |  | Thompsons | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y |  |  | Cost included in main entry | 109677 | 109615
109615H | WA Parish 138kV Fault Upgrade with Bus Reactors | Reposition existing Standby transformers ST5A / ST5B as part of WAP 138kV West reactor additions |  | WA Parish |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y |  |  | Cost included in main entry | 109675 | 109615
109615C | WA Parish 138kV Fault Upgrade with Bus Reactors | Reposition existing WAP GT-2 generator lead as part of WAP 138kV West reactor additions |  | WA Parish |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-05-31 00:01 |  | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 | [5 empty] | Y |  |  | Cost included in main entry | 109674 | 109615
109878 | Seagoville Switch Auto #2 | Install Seagoville Switch Auto #2 + Rebuild Seagoville 345 kV Switch |  | Seagoville Switch | Seagoville Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4535 | 2029-06-01 |  | 345 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 1 | TBD |  |  |  |  | Y |  |  |  | 109879 | 109878 | TBD
100687 | Install a 50MVAr Capacitor Bank at Helotes Substation |  |  | 5200 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1075 | 2029-06-01 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 4 |  |  |  |  | 5200 | Y |  |  |  | 100688 | 100687
110511 | Carmichael Bend Switch - DeCordova Dam 138 kV Line | Upgrade Carmichael Bend Switch - DeCordova Dam 138 kV Line |  | Carmichael Bend Switch | DeCordova Dam | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5117 | 2029-06-01 |  | 138 | 0 | 0 | 0 |  | Hood | Hood | Tier 3 | [5 empty] | Y |  |  |  | 110512 | 110511
110603 | Scurry County South - China Grove 138 kV Double-Circuit Line | Loop the existing Snyder - Buford 138 kV Line into the existing Scurry County South 345/138 kV switch to establish the new Scurry County South Switch - Buford Switch138 kV Line. Install a new 5.6-mile, 138 kV second conductor on existing double-circuit structures from Scurry County South 138 kV Switch to Bufford 138 kV Switch. |  | Scurry County South | Buford (China Grove) | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com | R8887 | 2029-06-01 |  | 138 | 5.3 |  | 0 |  | Scurry | Scurry | Tier 4 | [5 empty] | Y |  |  |  | 110604 | 110603
100665 | Install a 21.42MVAr Capacitor Bank at Bulverde Substation |  |  | 5051 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1046 | 2029-06-01 |  | 138 | 0 | 0 | 0 | 0,21.42 | Comal |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5051 | Y |  |  |  | 100666 | 100665
86240 | AEN_REPLACE_LYTTON__345kV_LYAT1_and_LYAT2_AUTOS_WITH__New_672_MVAs | Replace the two existing 345kV Lytton Autos with two new 672 MVA/345kV autos |  | Lytton 9074 | Lytton 9075 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 345 | 0 | 0 | 762 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 9074, 9075, 9078, 9081 | Y |  |  |  | 86241 | 86240
67091 | Second 138 kV transmission Line from DL-DP CKT1034 | Second 138 kV transmission Line from Dunlap to Decker CKT1034 |  | 9045 | 9188 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 138 | 5.22 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9045, 9188 | Y |  |  |  | 67092 | 67091
45029 | Grandview Highland Hills Rebuild | CPSE_Rebuild of 138 kV double circuit line Line between Grandview to Highland Hills. |  | 5175 | 5205 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0273 | 2029-06-01 |  | 138 | 0 | 5.7 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-11 |  |  | 5030, 5095, 5175, 5205 | Y |  |  |  | 45030 | 45029
6687 | Rebuild Rio Hondo to East Rio Hondo | Rebuild the 138 kV line from Rio Hondo to East Rio Hondo. |  | Rio Hondo | East Rio Hondo | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-06-01 |  | 138 | 0 | 8.19 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5764, 8319 | N | N |  |  | 14458 | 6687
70307A | BRYN_Standard_PMCR_Dansby_Rebuild_fix | Reference Project 4577 which was added to convert Dansby 69kV bus to Breaker and a Half configuration |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-06-01 |  | 69 | 0 | 0 | 200 |  | Brazos |  | Tier 4 |  |  |  |  | 32875, 32897 | Y |  |  |  | 112558 | 70307
70307B | BRYN_Standard_PMCR_Dansby_Rebuild_fix |  |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-06-01 |  | 69 | 0 | 0 | 0 |  | Brazos |  | Tier 4 | [5 empty] | Y |  |  |  | 112557 | 70307
109931 | Cedar Hill Switch - Webb 345 kV Line | Upgrade Cedar Hill Switch - Webb 345 kV Line |  | Cedar Hill Switch | Webb | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4522, M4230 | 2029-06-01 |  | 345 | 0 | 7.5 | 0 |  | Dallas | Dallas | Tier 1 |  | 2025-11-18 | 2026-05-18 |  |  | Y |  |  |  | 109932 | 109931
110587 | Longshore - Rockhound 345 kV Double Circuit Line | Construct new 25.5-mile Rockhound - Longshore 345 kV Double-Circuit Line |  | Rockhound | Longshore | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com | R8728 | 2029-06-01 |  | 345 | 51 | 0 | 0 |  | Howard | Midland | Tier 2 | 26RPG015 | 2026-04-09 |  |  |  | Y |  |  |  | 110588 | 110587
104001 | BRYN_KoppeBridge_Load_Addition | Adding second distribution transformer at Koppe Bridge |  | BTU Koppe Bridge |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32860 | Y |  |  |  | 104002 | 104001
109952 | Commerce Switch - Paris Switch 138 kV Double-Circuit Line | Upgrade Commerce Switch - Paris Switch 138 kV Double-Circuit Line |  | Commerce Switch | Paris Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3327 | 2029-06-01 |  | 138 | 0 | 36.1 | 0 |  | Hunt | Lamar | Tier 1 | 25RPG040, 25RPG042 | 2025-11-18 | 2026-05-18 |  | 1693, 1801, 1802, 1816, 1820, 1838, 1844, 2932, 11806, 17011 | Y |  |  |  | 112111 | 109952 | 2024-NC36
110389 | Loop Nine Switch - Watermill Switch 345 kV Line | Upgrade Loop Nine Switch - Watermill Switch 345 kV Line |  | Loop Nine Switch | Watermill Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4443 | 2029-06-01 |  | 345 | 0 | 4 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 2427, 2847 | Y |  |  |  | 112117 | 110389 | 2024-NC16
110667 | Grand Prairie 138 kV Capacitor | Install Grand Prairie 138 kV Capacitor |  | Grand Prairie | Grand Prairie | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4019 | 2029-06-01 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  | 2025-11-18 | 2026-05-18 |  | 2260, 12492, 16262 | Y |  |  |  | 112409 | 110667
110669 | Park Row 138 kV Capacitor | Install Park Row 138 kV Capacitor |  | Park Row | Park Row | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4523 | 2029-06-01 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  | 2025-11-18 | 2026-05-18 |  | 2257 | Y |  |  |  | 112421 | 110669
112454 | BRYN_Rayburn_Load_Addition | Adding second distribution transformer at Rayburn |  | BTU Rayburn |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-06-01 |  | 69 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32861 | Y |  |  |  | 112455 | 112454
104084 | Rincon to Tungsten: Rebuild 138 kV Line | Rebuild the Rincon to Tungsten 138 kV line | NEW | Rincon | Tungsten | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 | TP2026007 | 2029-06-30 |  | 138 | 0 | 54.1 | 0 |  | Calhoun | Refugio | Tier 3 |  |  |  |  | 8144, 8189, 8437, 80065 | Y | N |  |  | 104085 | 104084
99908 | Altair - Eagle Lake Transmission Line Overhaul | Perform an overhaul on the 11.4 mile T547 Altair - Eagle Lake (including all tap lines) 69-kV transmission line. Per LCRA TSC Transmission System Planning procedure, replacement structures will be capable of operating at 138-kV. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-762-3658 |  | 2029-06-30 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8523, 8527, 8529, 78105, 78106, 78524, 78526, 78528 | Y |  |  |  | 99909 | 99908
103831 | Songbird: Construct New 345 kV Station | Interconnect Oriole Solar to the new Songbird 345 kV station on the Foxtail - Perigee 345 kV line | TSP/Company Contact Update | Songbird |  | Planned |  | AEP TNC | Bill Edwards myturner@aep.com 918-599-2437 | TP2025938 | 2029-06-30 |  | 345 | 0 | 0 | 0 |  | Knox |  | Tier 4 |  |  |  |  | 6076, 60275, 60791 | Y | N |  |  | 103832 | 103831
98569 | Oso Creek to Westside: Construct New 138 kV Line | Construct a new 138 kV single circuit line from Oso Creek to Westside | In-Service Date Update | Oso Creek | Westside | Planned |  | AEP TCC | Brooks Dow deevans@aep.com 918-599-2938 | TP2025225 | 2029-06-30 |  | 138 | 6 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8089, 8485 | Y |  |  |  | 98570 | 98569
109722 | Facet: Construct New 345 kV Station | Interconnect Titus Solar and Diamond Cowboy Storage to the new Facet 345 kV station on the Angstrom to Grissom 345 kV line | NEW | Facet |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2026145 | 2029-06-30 |  | 345 | 0.25 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8249, 8624, 8853 | Y | N |  |  | 109723 | 109722
110523 | STEC Rogers Large Load addition Phase 1 | -Install a new 385 MVAR capacitor bank on the 138kV side of the new STEC-owned Alsatian 345/138kV station -Add the second 138kV ckt along the existing Legend Falls to STEC Castroville corridor: Legend Falls - San Geronimo, San Geronimo - Rio Medina, Rio Medina - Castroville, with a 426/474 MVA rating -Add the 2nd ckt to existing Pearson to Castroville corridor: Pearson - Dunlay, Dunlay-new STEC Alsatian, Alsatian -Bader, Bader - Castroville, with a rating of 426/474 MVA |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-06-30 12:15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 | 25RPG046 |  |  |  |  | Y | N |  |  | 110524 | 110523
110461 | STEC Edwards Large Load Addition Phase 1 | -(CPS South San Antonio Reliability Project 1 & 2) - Install 162 MVAr of reactive support at the Edward POI - Add a second 138kV ckt from Pearson to Edward to Castroville with 474 MVA rating - Install 19./2 MVAR of reactive power compensation at Natalia sub 69kV |  | Pearson | Castroville | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-06-30 12:15 |  | 138 | 0 |  | 0 |  | Medina | Medina | Tier 1 | 25RPG046 |  |  |  |  | Y | N |  |  | 110462 | 110461
71881 | Install 31.3 Mvar capacitor bank at Andice. | Install 31.3 Mvar capacitor bank at Andice. Formerly TPIT project number 70365. |  | Andice |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2029-07-01 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson |  | Tier 4 |  |  |  |  | 70522 | Y | Y |  |  | 71882 | 71881
110057B | This models upgrades required for a proposed load addition | Install one 300 MVAR capacitor bank at 345 kV NewSub. Install one 300 MVAR capacitor bank at 345 kV Singleton. |  | NewSub | Singleton | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-07-01 |  | 345 | 0 | 0 | 0 | 0,600 | Harris | Grimes | Tier 4 | [5 empty] | N | N |  | Cost is included in phase A | 110066 | 110057
110090B | This models upgrades required for a proposed load addition | Install 345 kV substation. Loop 345 kV Circuit 97 Jordan to King into the new 345 kV substation. Install 200MVAR Cap Bank at new sub. |  | NEWSUB | Jordan/North Belt | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-07-01 |  | 345 | 0 | 0 | 0 | 0,200 | Harris | Harris | Tier 4 | [5 empty] | N | N |  | Cost included in main entry | 110257 | 110090
76818 | Upgrade Rayburn Auto Station | Upgrade Rayburn Auto |  | Rayburn | Rayburn | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-07-01 |  | 138 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5500, 5502 | N |  |  |  | 76819 | 76818
110872 | STEC Mesquite Large Load Project Phase 3 | Upgrade 8162 COLETO4A - 8172 VICTORIA4A 138-kV Line CKT 1 Upgrade 8162 COLETO4A - 8172 VICTORIA4A 138-kV Line CKT 2 Upgrade 8535 POMPANO4A - 8735 CHALYBE4A 138-kV Line CKT 1 Upgrade 5705 FOWLERTNSUB8 - 5723 LOSANGLESUB8 138-kV Line CKT 1 Add a minimum 15MVAR shunt on 8412 REFUGIO4A or 8813 QUINTANA4A Upgrade 5689 AEPCHKCNSUB8 - 8404 SIGMOR4A 138-kV Line CKT 1 Upgrade 5723 LOSANGLESUB8 - 8612 REVEILLE4A 138-kV Line CKT 1 Upgrade 5728 CHOATESUB8 - 5730 FORCORNERSB8 138-kV Line CKT 1 Upgrade 5689 AEPCHKCNSUB8 - 5902 MIGUEL8 138-kV Line CKT 1 Upgrade 5688 GEORGEWSTSW8 - 8404 SIGMOR4A 138-kV Line CKT 1 Upgrade 8112 LSCRUCES4A - 80013 LARDVNTH4A 138-kV Line CKT 1 Upgrade 80013 LARDVNTH4A - 80165 LARDVFT4A 138-kV Line CKT 1 Upgrade 8060 BESSEL4A - 8452 LON_HILL4A 138-kV Line CKT 1 |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-07-01 12:15 |  | 138 | 0 |  | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110873 | 110872
110845 | STEC Palangana Large Load Project Phase 2 | Install reactive support at 80013 LARDVNTH4A 138-kV Substation |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-07-01 12:15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110846 | 110845
109972 | Construct a new CPS Owned switchyard to connect new Lavender BESS Generation Project |  |  | 5280 | 5110, 5255 | Planned | S-1087 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0419 | 2029-07-03 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5110, 5255, 5280 | Y |  |  |  | 109973 | 109972
111221 | Angstrom: Expand 345 kV Station | Interconnect the Ripper Industrial load to the existing Angstrom 345 kV station | NEW | Angstrom |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2026123 | 2029-07-31 |  | 345 | 1.6 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8249, 80514 | Y | N |  |  | 111222 | 111221
73053A | Wimberley Loop to New Substation | Adds new 138 kV branch (219 MVA) from Wimberley to a new three terminal ring bus substation between Dripping Springs and Rutherford. |  | Wimberley | Cebolla Creek | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2029-08-01 |  | 138 | 13.44 | 0 | 0 |  | Hays | Hays | Tier 2 | 22RPG026 | 2022-08-29 | 2023-02-03 |  | 70509, 70511, 70512 | Y | N |  |  | 73054 | 73053
91937 | Cryo to Faulkner: Construct New 138 kV Line | Construct a new 138 kV single circuit line from Cryo to Faulkner | TSP/Company Contact and In-Service Date Update | Cryo | Faulkner | Planned |  | AEP TNC/TNMP | David Baker myturner@aep.com 918-599-2437 | TP2025146 | 2029-08-31 |  | 138 | 11.5 | 0 | 0 |  | Reeves | Reeves | Tier 2 | H.B. 5066 |  |  | 2024-10-31 |  | Y | N |  |  | 91938 | 91937
110591 | Ad Hoc TPIT: 432 MVAR Reactive Compensation at Pitchfork 345 kV |  |  | Pitchfork 34k kV | Pitchfork 345 kV | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2029-09-01 |  | 345 | 0 | 0 | 0 | 0,432 | Dickens | Dickens | Tier 4 | [5 empty] | N |  |  |  | 110592 | 110591
110847 | STEC Palangana Large Load Project Phase3 | Establish CCNG Palangana 345-kV POI Install reactive support at Palanaga POI to achieve unity power factor AEP Laredo Area Upgrades RPG Option 3 |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-09-01 12:15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110848 | 110847
110874 | STEC Mesquite Large Load Project Phase 4 | Install 200MVAR reactive support at Palangana POI to achieve unity power factor |  | 0 | 0 | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-09-01 12:15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110875 | 110874
102672A | BEPC_TIER3_MillerRPG |  |  | RW Miller | Bunker | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-09-03 |  | 138 | 0 | 41.34 | 0 |  | Palo Pinto |  | Tier 3 | 26RPG002 | 2026-02-02 | 2026-03-17 |  | 306, 312, 331, 1576 | Y |  |  |  | 105026 | 102672
110373 | Rebuild Black Fork Switch - Hideaway Lake Tap 138 kV Line Section | Rebuild Black Fork Switch - Hideaway Lake Tap 138 kV Line Section |  | Black Fork Switch | Hideaway Lake Tap | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6368 | 2029-09-15 |  | 138 | 0 | 9.1 | 0 |  | Smith | Smith | Tier 4 | [5 empty] | Y |  |  |  | 110374 | 110373
6666 | BRYN_6666_Steele_Store_to_Cooks_Point | Construct 138kV line from BTU Steele Store to LCRA Cooks Point (Bundled 1033 ACSR - Curlew & 959 ACSS Suwannee) |  | 32852 | 7569 | Planned |  | BRYN/BTU AND LCRA TSC | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-10-01 |  | 138 | 7.2 | 0 | 0 |  | Brazos | Burleson | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 7569, 32852 | Y |  |  |  | 91617 | 6666
99105B | BRYN_99105_RIVERSIDE | Construct RELLIS to Riverside 138-kV transmission line on double-circuit capable structures. |  | RELLIS | Riverside | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-10-01 |  | 138 | 6.1 | 0 | 0 |  | Brazos | Brazos | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32780, 32858 | Y |  |  |  | 99184 | 99105
99103 | BRYN_99103_RELLIS_TNPONE_DC345KV | Expand the existing RELLIS 138 kV Substation to establish the BTU RELLIS 345/138 kV Switchyard. Install at RELLIS Switchyard two 345/138 kV autotransformers with a nameplate rating of 600 MVA. Expand the TNP One Substation to accommodate two additional 345 kV line terminals. Construct a 40-mile, 345 kV double-circuit line from BTU RELLIS to TNMP TNP One. |  | RELLIS | TNP One | Planned |  | BRYN/BTU AND TNMP | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-10-01 |  | 345 | 43 | 0 | 1200 |  | Brazos | Robertson | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32780, 32781, 32782, 32783, 39950 | Y |  |  |  | 99539 | 99103
99105A | BRYN_99105_RIVERSIDE | Construct Riverside 138-kV switching station by cutting into the existing Dansby to Thompson Creek 138-kV transmission line. |  |  |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2029-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32858, 32863, 32897 | Y |  |  |  | 99183 | 99105
110230 | Nikola: Construct New 345 kV Station | Interconnect the Lancium load to the new Nikola 345 kV station |  | Nikola |  | Planned |  | ETT | Zachary Lachiusa myturner@aep.com 918-599-2437 | TP2024089 | 2029-10-30 |  | 345 | 18 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60300, 60472, 60473, 60504 | Y | N |  |  | 110231 | 110230
91941 | Solstice to Faulkner: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Solstice to Faulkner | RPG Number and BOD Review date Update | Solstice | Faulkner | Planned |  | AEP TNC/TNMP | Brent Harris myturner@aep.com 918-599-2437 | TP2024165 | 2029-10-30 |  | 345 | 40 | 0 | 0 |  | Pecos | Reeves | Tier 1 | H.B. 5066 |  |  | 2024-10-31 |  | Y | N |  |  | 91942 | 91941
99453G | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.75B Kuykendahl to Roans Prairie to increase thermal limits as part of FRM2 upgrades. |  | Kuykendahl | Roans Prairie | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Harris | Grimes | Tier 4 |  |  |  |  | 40600, 48205 | Y | N |  |  | 102621 | 99453
99453Q | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.98G Smithers to WA Parish to increase thermal limits as part of FRM2 upgrades. |  | Smithers | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44005, 44650 | Y | N |  |  | 102622 | 99453
99453T | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.74C Tomball to Singleton to increase thermal limits as part of FRM2 upgrades. |  | Tomball | Singleton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Harris | Grimes | Tier 4 |  |  |  |  | 44645, 46500 | Y | N |  |  | 102625 | 99453
102771A | Aquila (AQU) CEHE-Owned 345kV Substation for TALON (TAL) / Eagle Claw Energy Storage (27INR0085) | Install new 345kV Aquila (AQU) substation for generator interconnection to TALON (TAL) / Eagle Claw Energy Storage (27INR0085). Loop Ckt.99D Singleton to Zenith to create new Ckt.99 Singleton to Aquila to Zenith. |  | Aquila | Zenith / Singleton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Harris | Tier 4 |  |  |  |  | 44645, 44900, 44980 | Y | N |  |  | 102964 | 102771
109753 | Vitex: Construct New 345 kV Station | Interconnect the Lancium load to the new Vitex 345 kV station on the Bluff Creek to Mulberry Creek 345 kV line | NEW | Vitex |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2026090 | 2029-10-31 |  | 345 | 15 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6235, 60040, 60803, 60804, 60805 | Y | N |  |  | 109754 | 109753
55605 | New Barksdale to Rocksprings: Rebuild 69 kV Line | Rebuild the Campwood to Rocksprings 69 kV line | Transmission Owner and In-Service Date Update | New Barksdale | Rocksprings | Planned | 1102 - 1280 | AEP TCC | Greg Crane jlsolis@aep.com 361-881-5574 | 3819 | 2029-10-31 |  | 69 | 0 | 19.51 | 0 |  | Edwards | Edwards | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 8238, 8365 | Y |  |  |  | 65572 | 55605
55617 | Campwood to New Barksdale: Rebuild 69 kV Line | Rebuild the Campwood to Rocksprings 69 kV line | In-Service Date Update | Campwood | New Barksdale | Planned | 1102 - 1280 | AEP TCC/ETT | Greg Crane jlsolis@aep.com 361-881-5574 | 3820 | 2029-10-31 |  | 69 | 0 | 7.73 | 0 |  | Edwards | Edwards | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 8365, 8633 | Y |  |  |  | 65573 | 55617
99453F | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.75D Roans Prairie to Singleton increase thermal limits as part of FRM2 upgrades. |  | Roans Prairie | Singleton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 |  | 345 | 0 | 0 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 40600, 44645 | Y | N |  |  | 102619 | 99453
102771B | Aquila (AQU) CEHE-Owned 345kV Substation for TALON (TAL) / Eagle Claw Energy Storage (27INR0085) | Install generator lead from Aquila (AQU) substation to TALON (TAL) customer substation (27INR0085). |  | Aquila | TALON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2029-10-31 00:01 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  | Cost included in main entry | 102965 | 102771
92432 |  |  |  | Reno | New Station Nofoul | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-11-15 |  | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 534, 541, 542 | Y |  |  |  | 92433 | 92432
59086 | Corichi to Victoria: Rebuild 138 kV Line | Rebuild the Corichi to Victoria 138 kV line | In-Service Date Update | Corichi | Victoria | Planned |  | AEP TCC | Travis Coody deevans@aep.com 918-599-2938 | TP2020888 | 2029-11-15 |  | 138 | 0 | 42.76 | 0 |  | Jackson | Victoria | Tier 3 |  | 2022-02-22 | 2022-03-01 |  | 8099, 8117, 8118, 8172 | Y | N |  |  | 65585 | 59086
109839 | Lightyear: Construct New 138 kV Station | Construct new 138 kV station on the Illinois # 4 to Ozona 138 kV line |  | Lightyear |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2026095 | 2029-11-29 |  | 138 | 2 | 0 | 0 |  | Crockett | Crockett | Tier 4 |  |  |  |  | 6549, 60192, 60194 | Y | N |  |  | 110227 | 109839
98991B | Kinnebrew POI - Chalk 69 kV to 138 kV Line Conversion | Oncor's portion of the Permian Basin Reliability Plan Upgrade ID L27B. Convert the existing Sterling County - Kinnebrew POI 69-kV line to 138-kV. |  | Kinnebrew | Sterling County | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L27_B | 2029-11-29 |  | 138 | 10.6 | 0 | 0 |  | Sterling | Sterling | Tier 3 |  |  |  |  | 10189, 60167 | Y |  |  |  | 100075 | 98991
93428 | Creosote to Toyah Creek: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Creosote to Toyah Creek | Transmission Owner, TSP/Company Contact, Dollars should be and Miles New Update | Creosote | Toyah Creek | Planned |  | AEP TNC/ONCOR | David Baker myturner@aep.com 918-599-2437 | TP2024162 | 2029-11-30 |  | 345 | 11.5 | 0 | 0 |  | Reeves | Reeves | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 38376, 38380, 60140, 60141, 60142, 60143, 60144, 60145, 60377 | Y |  |  |  | 93429 | 93428
93624 | L7C Add a new Creosote - Blue Goose (fka Toyah Creek) 345-kV double-circuit line | AEP and Oncor joint project to add the 23-mile L7C Creosote - Blue Goose (fka Toyah Creek) 345-kV double-circuit transmission line part of the local common projects approved as part of the Permian Basin Reliability Plan |  | Creosote | Blue Goose | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L7C | 2029-11-30 |  | 345 | 46 | 0 | 0 |  | Ward | Pecos | Tier 1 |  | 2023-05-18 | 2023-06-09 |  | 18669, 60141, 60145 | Y |  |  |  | 93625 | 93624
98556 | Cedar Hill to Sterling City: Convert to 138 kV | Convert the Cedar Hill to Sterling City 69 kV line to 138 kV | Company Contact Update | Cedar Hill | Sterling City | Planned | TP2025199 | AEP TNC | Bradley Case myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0 | 36.5 | 90 |  | Coke | Sterling | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 6423, 6425, 6427, 6428, 6429, 6430, 6431, 6432, 6433, 6434, 6435, 6484, 6488, 60162, 60166, 60169, 60170, 60171, 60172, 60173, 60174, 60175, 60185, 60187 | Y |  |  |  | 98558 | 98556
98559 | Sterling City to Chalk: Convert to 138 kV | Convert the Sterling City to Chalk 69 kV line to 138 kV | Company Contact, Transmission Owner Project Number, In-Service Date, and RPG Dates Update | Sterling City | Chalk | Planned | TP2025199 | AEP TNC | Bradley Case myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0 | 1.6 | 0 |  | Sterling | Sterling | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 6417, 6435, 6436, 11352, 60167, 60168, 60171 | Y |  |  |  | 98560 | 98559
98574 | Cedar Hill to Oak Creek: Rebuild 138 kV Line | Rebuild the Cedar Hill to Oak Creek 138 kV line | In-Service Date Update | Cedar Hill | Oak Creek | Planned |  | AEP TNC/AEP TNC/ETT | Bradley Case myturner@aep.com 918-599-2437 | TP2025197 | 2029-11-30 |  | 138 | 2 | 26 | 0 |  | Coke | Coke | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 6319, 6325, 6335, 6351, 6425, 60724 | Y |  |  |  | 98575 | 98574
99749 | Friend Ranch to Illinois #4: Convert to 138 kV | Convert the Friend Ranch to Illinois #4 69 kV line to 138 kV | Transmission Owner and Company Contact Update | Friend Ranch | Illinois #4 | Planned | TP2025183 | AEP TNC | Travis Coody myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0 | 23.8 | 0 |  | Crockett | Crockett | Tier 2 | H.B. 5066 |  |  | 2024-10-31 | 6549, 6550, 6551, 6560, 6562, 6564, 6565, 6567, 60190, 60191, 60192, 60194 | Y |  |  |  | 99750 | 99749
98626 | Abilene Northwest to Oak Creek: Reterminate 138 kV Line Into Nicole | Reterminate the Abilene Northwest to Oak Creek 138 kV line from Oak Creek into the existing Nicole 138 kV station | Company Contact, Transmission Owner Project Number, In-Service Date, and RPG Date Update | Abilene Northwest | Nicole | Planned | TP2025197 | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0.75 | 0 | 0 |  | Taylor | Coke | Tier 1 | H.B. 5066 |  |  | 2024-10-31 |  | Y | N |  |  | 98627 | 98626
98628 | Ballinger to Oak Creek: Reterminate 138 kV Line Into Nicole | Reterminate the Ballinger to Oak Creek 138 kV line from Oak Creek into the existing Nicole 138 kV station | Company Contact, Transmission Owner Project Number, In-Service Date, and RPG Date Update | Ballinger | Nicole | Planned | TP2025197 | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2029-11-30 |  | 138 | 0.25 | 0 | 0 |  | Runnels | Coke | Tier 1 | H.B. 5066 |  |  | 2024-10-31 |  | Y | N |  |  | 98629 | 98628
91939 | Solstice to Bottlebrush: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Solstice to Bottlebrush | In-Service Date Update | Solstice | Bottlebrush | Planned |  | AEP TNC/TNMP | Brent Harris myturner@aep.com 918-599-2437 | TP2024076 | 2029-11-30 |  | 345 | 31 | 0 | 0 |  | Pecos | Reeves | Tier 1 | H.B. 5066 |  |  | 2024-10-31 |  | Y | N |  |  | 91940 | 91939
103416 | South McAllen: 138 kV Breaker Replacement | Replace 138 kV breakers at the South McAllen 138 kV station | NEW | South McAllen |  | Planned |  | AEP TCC | Raza S Ansari jlsolis@aep.com 361-881-5574 | TP2026008 | 2029-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 | [5 empty] | Y | N |  |  | 103417 | 103416
93453 | Creosote: Expand 345 kV Station | Install two 345/138 kV autotransformers at the Creosote 345/138 kV station | TSP/Company Contact, Dollars should be and Autotransformer Capability Update | Creosote |  | Planned |  | AEP TNC | Michael Forcum mlforcum@aep.com 918-599-2674 |  | 2029-11-30 |  | 345 | 0 | 0 | 1500 |  | Reeves |  | Tier 1 | H.B. 5066 |  |  | 2024-10-31 |  | Y |  |  |  | 93454 | 93453
110622 | Ad Hoc TPIT: Build approximately 60-mile 345 kV double circuit from WETT's Buck Canyon to Nova Prime |  |  | Buck Canyon 345 kV | Nova Prime 345 kV | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2029-12-01 |  | 345 | 60 | 0 | 0 |  | Borden | Kent | Tier 1 | [5 empty] | N |  |  |  | 110623 | 110622
99411 | Daybreak_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor's Good Morning substation addition. Requires coordination with Oncor. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 10168, 71212, 71214, 71216 | Y |  |  |  | 99412 | 99411
6685 | Van Vleck substation loop | Replaces single circuit radial line connected to a pole mounted switch with a double circuit transmission loop to the Van Vleck substation and upgrades the 4/0 ACSR to 795 ACSR on 138 kV capable poles. |  | Van Vleck Substation | Van Vleck Switch | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-12-01 |  | 69 | 2 | 2 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5556, 5557, 5558, 5560 | N | N |  |  | 14456 | 6685
110853 | Build approximately 43.36-mile 345 kV double circuit line from Muleshoe to Mhos substation |  |  | Muleshoe 345kv bus | Mhos 345kv bus | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2029-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 | [5 empty] | N |  |  |  | 110854 | 110853
110851 | Build approximately 94.5-mile 345 kV double circuit line from Buck Canyon to Pitchfork substation |  |  | Buck Canyon 345 kV | Pitchfork 345 kV | Conceptual |  | WETT | Lei Liu lliu@wettllc.com |  | 2029-12-01 |  | 345 | 94.5 | 0 | 0 |  | Borden | Dickens | Tier 1 | [5 empty] | N |  |  |  | 110852 | 110851
110573 | Buford (fka China Grove) Switch - Barber Lake Switch 138 kV Line (West Circuit) | Rebuild the 9.03-mile west circuit of Buford (fka China Grove) Switch - Barber Lake Switch 138 kV Line |  | Buford (fka China Grove) Switch | Barber Lake Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com | R8846 | 2029-12-01 |  | 138 | 0 | 9.03 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 110574 | 110573
110362 | Desoto 345/138 kV Autotransformer #2 | Install Desoto 345/138 kV Autotransformer #2 |  | Desoto Switch | Desoto Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4027 | 2029-12-01 |  | 345 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 2424, 2431, 12432 | Y |  |  |  | 111647 | 110362 | 2024-NC80
110342 | Desoto Switch - Loop Nine Switch 138 kV Line | Establish Desoto Switch - Loop Nine Switch 138 kV Line |  | Desoto Switch | Loop Nine Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4011 | 2029-12-01 |  | 138 | 0 | 3.82 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 2424, 2848 | Y |  |  |  | 111643 | 110342 | 2024-NC80
109812 | Rivercrest Switch - Sulphur Springs East Tap 138 kV Line | Upgrade Rivercrest Switch - Sulphur Springs East Tap 138 kV Line |  | Rivercrest Switch | Sulphur Springs East Tap | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3326 | 2029-12-01 |  | 138 | 0 | 30.1 | 0 |  | Red River | Hopkins | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 1780, 1793, 1794, 1796, 1797, 11796, 11797 | Y |  |  |  | 111641 | 109812 | 2024-E8
110521 | Farmland 345 kV Switch Rebuild and Farmland - Long Draw 345 kV Line | Rebuild the existing 22.8-mile Farmland - Long Draw 345 kV Line and terminate the circuit into the newly rebuilt Farmland 345 kV Switch and WETT's existing Long Draw 345 kV Switch |  | Farmland | Long Draw | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8786 | 2029-12-01 |  | 345 | 0 | 22.8 | 0 |  | Lynn | Borden | Tier 3 |  |  |  |  | 23924, 59900 | Y |  |  |  | 110522 | 110521
104609 | BBEC Brenham North to Sandy Hill Transmission Line Upgrade | Replace 336 (Linnet) conductor with 959 (Suwannee) and replace a limited number of structures to accommodate the new conductor. |  | Brenham North | Sandy Hill | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2029-12-01 |  | 138 | 0 | 8.6 | 0 |  | Washington | Washington | Tier 4 |  |  |  |  | 7294, 7570 | Y |  |  |  | 104610 | 104609
112560 | Desoto 345/138 kV Switch Rebuild | Desoto 345/138 kV Switch Rebuild |  | Desoto Switch | Desoto Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4448 | 2029-12-01 |  | 345 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  |  | Y |  |  |  | 112561 | 112560 | 2024-NC80
110579 | Buford (fka China Grove) Switch - Barber Lake Switch 138 kV Line (East Circuit) | Rebuild the 9.03-mile east circuit of Buford (fka China Grove) Switch - Barber Lake Switch 138 kV Line |  | Buford (fka China Grove) Switch | Barber Lake Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com | R8845 | 2029-12-01 |  | 138 | 0 | 9.03 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 110580 | 110579
110683 | Ad Hoc TPIT: Build 345 kV double circuit from WETT's Buck Canyon to Oncor's White River station |  |  | Buck canyon 345 kV | Oncor's White River 345 kV station | Conceptual |  | WETT | Chris Ramirez cramirez@wettllc.com 737-218-4525 |  | 2029-12-01 |  | 345 | 110 | 0 | 0 |  | Borden | Floyd | Tier 1 | [5 empty] | N |  |  |  | 110684 | 110683
110553 | Sulphur Springs East Tap - Sulphur Springs East Switch 138 kV Line | Upgrade Sulphur Springs East Tap - Sulphur Springs East Switch 138 kV Line |  | Sulphur Springs East Switch | Sulphur Springs East Tap | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3326 | 2029-12-01 |  | 138 | 0 | 5.5 | 0 |  | Hopkins | Hopkins | Tier 3 |  | 2025-11-18 | 2026-05-18 |  |  | Y |  |  |  | 110554 | 110553
105626 | BEPC_TIER1_Goatherd |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-12-03 |  | 138 | 0 | 0 | 0 |  | Ellis |  | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 220, 223, 226 | Y |  |  |  | 105627 | 105626
110004 | Rebuild the Hillsboro Switch - Ash Creek Switch 138 kV Line | Rebuild the Hillsboro Switch - Ash Creek Switch 138 kV Line |  | Hillsboro Switch | Ash Creek Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6426 | 2029-12-15 |  | 138 | 0 | 19.3 | 0 |  | Hill | Hill | Tier 1 | 25RPG041, 25RPG043 | 2025-11-12 | 2026-08-19 |  | 234, 3473, 3522, 3817 | Y |  |  |  | 110005 | 110004
89918 | GVEC Gonzales substation | Rebuild existing substation, 138 kV bus, new PWT, new Control House, new HV and LV structures, containment foundations, bus, panels, etc |  | Gonzales |  |  |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2029-12-15 | 2958101 | 138 | 0 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 | [5 empty] | Y |  |  |  | 89919 | 89918
99314 | Establish Dinosaur 765/345 kV Switch | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1A. Establish the Dinosaur 765/345 kV Switch with two 765/345 kV autotransformers |  | Dinosaur | Dinosaur | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | PB_765_Import1_A | 2029-12-15 |  | 765 | 0 | 0 | 4500 | -900,0 | Somervell | Somervell | Tier 1 |  |  |  |  | 1899, 1900, 1902, 1981, 11886, 15207, 15208, 15209, 15210 | Y |  |  |  | 99315 | 99314
110178 | Bowman 345 kV Switch Capacitor Bank | Bowman 345 kV Switch Capacitor Bank |  | Bowman Switch | Bowman Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3568 | 2029-12-15 |  | 345 | 0 | 0 | 0 |  | Wichita |  | Tier 4 |  |  |  |  | 1422 | Y |  |  |  | 112555 | 110178
99239B | Establish Muscovy 345/138 kV Switch | Construct the Muscovy - Voss Lake 345 kV Double-Circuit Line |  | Muscovy | Voss Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6212, R6342, R6362 | 2029-12-15 |  | 345 | 30 | 0 | 0 |  | Williamson | Milam | Tier 1 | 25RPG009 | 2025-03-11 |  |  | 3700, 3751 | Y |  |  |  | 99265 | 99239
110608 | Venus 345 kV Switch Terminal Equipment | Upgrade Venus 345 kV Switch Terminal Equipment |  | Venus Switch |  | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5374 | 2029-12-15 |  | 345 | 0 | 0 | 0 |  | Ellis |  | Tier 3 | [5 empty] | Y |  |  |  | 110609 | 110608
92867 | Renner Switch – Plano West Switch 138 kV Double-Circuit Line | Upgrade Renner Switch – Plano West Switch 138 kV Double-Circuit Line |  | Renner | Plano West | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4246 | 2029-12-15 |  | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2352, 2353, 2669, 2670, 2671, 2673 | Y |  |  |  | 92869 | 92867
105838 | Wilmer 345kV Statcom | Establish Wilmer 345kV Statcom |  | Wilmer |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5016 | 2029-12-15 |  | 345 | 0 | 0 | 0 | 0,250 | Dallas |  | Tier 1 | 25RPG004 |  | 2026-03-19 |  | 3085, 3092 | Y |  |  |  | 105839 | 105838
110016 | Install Voss Lake 345/138 kV Auto #2 | Install Voss Lake 345/138 kV Auto #2 |  | Voss Lake | Voss Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6551 | 2029-12-15 |  | 345 | 0 | 0 | 600 |  | Milam | Milam | Tier 3 | [5 empty] | Y |  |  |  | 110017 | 110016
110044 | Rebuild Hutto - Round Rock Northeast 138 kV DCKT Line Section | Rebuild Hutto - Round Rock Northeast 138 kV DCKT Line Section |  | Hutto | Round Rock Northeast | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6553 | 2029-12-15 |  | 138 | 0 | 5.3 | 0 |  | Williamson | Williamson | Tier 1 |  |  |  |  | 3666, 3667, 3670 | Y |  |  |  | 110045 | 110044
81240 | Consavvy – Odessa EHV 345 kV Double Circuit Line Rebuild | Rebuild the existing 345 kV Double-Circuit Line |  | Consavvy | Odessa EHV | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3027 | 2029-12-15 |  | 345 | 0 | 40 | 0 |  | Midland | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1125, 11016, 11028, 11387, 18540, 18548 | Y |  |  |  | 81241 | 81240
110034 | Establish Bob White 345 kV Switch | Establish Bob White 345 kV Switch |  | Bob White | Bob White | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6542 | 2029-12-15 |  | 345 | 0 | 0 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3414, 3687, 3792 | Y |  |  |  | 110035 | 110034
81302 | Rockhound - Midland East 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Rockhound | Midland East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2029-12-15 |  | 345 | 0 | 24.2 | 0 |  | Midland | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1021, 10062 | Y |  |  |  | 81303 | 81302
110022 | Rebuild the Cannon - Dos Rios - Robertson 138 kV Line | Rebuild the Cannon - Dos Rios - Robertson 138 kV Line |  | Cannon | Robertson | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6460 | 2029-12-15 |  | 138 | 0 | 19.2 | 0 |  | Milam | Robertson | Tier 1 | 25RPG009 |  |  |  | 32, 3707, 3725 | Y |  |  |  | 110023 | 110022
110012 | Rebuild the Trinidad Switch - Mankin Switch 138 kV Line | Rebuild the Trinidad Switch - Mankin Switch 138 kV Line |  | Trinidad Switch | Mankin Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6048 | 2029-12-15 |  | 138 | 0 | 4.1 | 0 |  | Henderson | Henderson | Tier 1 | 25RPG041, 25RPG043 | 2025-11-12 | 2026-08-19 |  | 3127, 3260, 3265, 3276 | Y |  |  |  | 110013 | 110012
80346 |  |  |  | SANDY SWITCH | CRUTCHFIELD | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2029-12-21 |  | 138 | 0 | 3.2 | 0 |  | Grimes | Grimes | Tier 4 |  |  |  |  | 5, 8 | Y |  |  |  | 80347 | 80346
100163 | BowWood_Load_Circuit_Breaker_Addition | Install a new transmission point of interconnection for a large load at Bow Wood Substation. |  | Bow Wood | Bow Wood | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-12-31 |  | 345 | 0 | 0 | 0 |  | McCulloch | McCulloch | Tier 4 |  |  |  |  | 76006 | Y |  |  |  | 100164 | 100163
109860 | Red Rock Bus Substation Upgrade | Upgrade terminal equipment of L_LOCKHA8_1Y (Bus #7216) - L_REDROC8_1Y (Bus #7560) 138.0-kV line as an LCP project for Batch Zero Base Load |  | Red Rock |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2029-12-31 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 | [5 empty] | Y |  |  |  | 109861 | 109860
109798 | Antler Bus Substation Upgrade | Upgrade terminal equipment at Antler (Bus #7171) to increase operational rating of terminating 138.0-kV lines, minimum 943 MVA, as an LCP Upgrade project for Batch Zero Base Load. |  | Antler |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-12-31 |  | 138 | 0 |  | 0 |  | Comal |  | Tier 4 | [5 empty] | Y |  |  |  | 109799 | 109798
66118 | Reconductor TI-Lakepointe with 959 ACSS/TW | Project ISD anticipated in 2025. |  | Lakepoint (bus # 37010) | TI (bus # 37080) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-12-31 |  | 138 | 0 | 2.78 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 37010, 37080 | Y |  |  |  | 66119 | 66118
110164 | Austrop Bus Substation Upgrade | Upgrade terminal equipment of Austrop (Bus #9328) to increase operational rating of terminating 138-kV lines to 643 MVA. Upgrade project for Batch Zero Base Load |  | Austrop |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2029-12-31 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 | [5 empty] | Y |  |  |  | 110165 | 110164
109882 | Winchester Dynamic Reactive Substation Upgrade | Add 350MVAr cap bank at the Winchester 345kV substation as an LCP project for Batch Zero Base Load |  | Winchester |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2029-12-31 |  | 345 | 0 | 0 | 0 | 0,350 | Fayette |  | Tier 4 | [5 empty] | Y |  |  |  | 109883 | 109882
109916 | Highway 46 Bus Substation Upgrade | Upgrade terminal equipment at Highway46 (Bus #7177) to increase operational rating of terminating 138.0-kV lines as an LCP Upgrade project for Batch Zero Base Load. |  | Highway46 |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2029-12-31 |  | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 | [5 empty] | Y |  |  |  | 109917 | 109916
109856 | Robert Brown Jr Bus Substation Upgrade | Upgrade terminal equipment of L_ROBRJR8_1Y (Bus #7194) - L_CAMPGA8_1Y (Bus #7196) 138.0-kV line as an LCP project for Batch Zero Base Load |  | Robert Brown Jr |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2029-12-31 |  | 138 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 | [5 empty] | Y |  |  |  | 109857 | 109856
109862 | Clear Fork Bus Substation Upgrade | Upgrade terminal equipment of L_ROBRJR8_1Y (Bus #7194) - L_CLEAFO8_1Y (Bus #7195) 138.0-kV line as an LCP project for Batch Zero Base Load |  | Clear Fork |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2029-12-31 |  | 138 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 | [5 empty] | Y |  |  |  | 109863 | 109862
99857 | LCRATSC_Gooseneck_Substation_Addition | Add Gooseneck substation cut into LCRA TSC-owned 345-kV double-circuit line, T248 Marion -Zorn and T250 Clear Springs - Zorn. |  | 7052 Gooseneck |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2029-12-31 |  | 345 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7042, 7050, 7052, 7054 | Y |  |  |  | 99858 | 99857
100025 | Naismith: Expand 138 kV Station | Interconnect Arcadia eFuels load to the existing Naismith 138 kV station | Project Description Update | Naismith |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2029-12-31 |  | 138 | 4 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8660, 80333 | Y |  |  |  | 100026 | 100025
110136 | Lyle Wolz Substation Upgrade | LCRA will upgrade terminal equipment at LYLEWO (7567) to achieve a minimum 345 MVA rating. Upgrade project for Batch Zero Base Load |  | Lyle Wolz |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2029-12-31 |  | 138 | 0 | 0 | 0 |  | Burleson |  | Tier 4 | [5 empty] | Y |  |  |  | 110137 | 110136
99323 | Longshore - Dinosaur 765 kV Line | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1D. Add a new New Substation 2 – Longshore 765-kV single-circuit line |  | Longshore | Dinosaur | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_D | 2029-12-31 |  | 765 | 257.45 | 0 | 0 | -450,0 | Howard | Somervell | Tier 1 |  |  |  |  | 15207, 18112 | Y |  |  |  | 99324 | 99323
99141 | Rebuild Flower Grove - Vincent 138 kV Line Rebuild | Upgrade the existing Flower Grove - Vincent 138 kV Line Section |  | Flower Grove | Vincent | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8736 | 2029-12-31 |  | 138 | 0 | 20.3 | 0 |  | Howard | Howard | Tier 4 |  |  |  |  | 1355, 1360, 1396, 10047, 11149, 11362 | Y |  |  |  | 99238 | 99141
99130 | Drill Hole 765/345 kV Autotransformer #2 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1C. Add a second 765/345 kV autotransformer at Drill Hole |  | Drill Hole | Drill Hole | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_C | 2029-12-31 |  | 765 | 0 | 0 | 2250 | -225,0 | Culberson | Culberson | Tier 1 |  |  |  |  | 10073, 18733, 18735 | Y |  |  |  | 99131 | 99130
99128 | Longshore 765/345 kV Autotransformer #2 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_1B. Add a second 765/345 kV autotransformer at Longshore |  | Longshore | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import1_B | 2029-12-31 |  | 765 | 0 | 0 | 2250 | -225,0 | Howard | Howard | Tier 1 |  |  |  |  | 1058, 18112, 18114 | Y |  |  |  | 99129 | 99128
105247 | Dinolong 765 kV Switch | Establish a 765 kV midpoint station to support reactive compensation needs for the Dinosaur - Longshore 765 kV Line |  | Dinosaur | Longshore | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8970 | 2029-12-31 |  | 765 | 0 | 0 | 0 |  | Scurry | Scurry | Tier 4 |  |  |  |  | 10224, 15207, 18112 | Y |  |  |  | 105248 | 105247
110455 | STEC Amphion Load Project Phase 1 | -Hairpin San Miguel to Fowlerton ckt 2 into STEC Amphion load serving station -Loop in and out San Miguel to Cruce into STEC Amphion load station |  | San Miguel | Fowlerton, Cruce | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-01-01 12:15 |  | 345 | 2 | 0 | 0 |  | Atascosa | McMullen | Tier 2 | [5 empty] | Y | N |  |  | 110456 | 110455
110126 | Install a 3rd 600MVA autotransformer at Eastside. |  |  | 5137 | 5136 | Planned | S-1051 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-01-30 |  | 345 | 0 | 0 | 600 |  | Bexar | Bexar | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5136, 5137 | Y |  |  |  | 110127 | 110126
84898 | New Eastside Switching Station |  |  |  |  | Planned | S-1052 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0399 | 2030-01-31 |  | 345 | 0 | 0 | 1200 |  | Bexar | Bexar | Tier 1 | 23RPG032: San Antonio South Reli |  |  |  | 5008, 5110, 5136, 5137, 5162, 5250, 5294, 5371, 5395, 5400, 5485 | Y |  |  |  | 84899 | 84898
104603 | Chalybe: Expand 138 kV Station | Install two (2) 138 kV breakers at the Chalybe 138 kV station | Terminal "from" and TSP/Company Contact Update | Chalybe |  | Planned | TP2026033 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2030-01-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8735 | Y |  |  |  | 104604 | 104603
87693 | Rebuild Spruce to Eastside Double Circuit |  |  |  |  | Planned | T-0398 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-01-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 3 |  |  |  |  | 5137, 5400 | Y |  |  |  | 87694 | 87693
100676 | Install a 50MVAr Capacitor Bank at the future Eastside Substation |  |  | 5136 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1049 | 2030-01-31 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5136 | Y |  |  |  | 100677 | 100676
104593 | Chalybe to Endpoint: Construct New 138 kV Double Circuit Line | Construct a new 138 kV double circuit line from Chalybe to Endpoint | NEW | Chalybe | Endpoint | Planned | TP2026033 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2030-01-31 |  | 138 | 10.5 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 8735, 8832 | Y |  |  |  | 104594 | 104593
104597 | Endpoint: Construct New 138 kV Station | Interconnect Texas LNG load to the new Endpoint 138 kV station | NEW | Endpoint |  | Planned | TP2026033 | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2030-01-31 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8832, 80417 | Y |  |  |  | 104598 | 104597
109729 | O'Connor: Retire Station | Retire the O'Connor station |  | O'Conner |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | DR26X0018 | 2030-02-01 |  | 138 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 8169, 8409, 8591 | Y | N |  |  | 109730 | 109729
109814 | LCRATSC Gabriel Glasscock Transmission Line Upgrade | LCRA will upgrade T359 Gabriel - Glasscock 138-kV transmission line to achieve a higher operational rating. This project is coordinated with the Gabriel – Schwertner Transmission Line Upgrade project |  | Structure 21 | Glasscock Sub | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8461 | 2030-02-01 |  | 138 | 0 | 3.5 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7523, 7531 | Y | Y |  |  | 109815 | 109814
109792 | Hutto - Limmer Transmission Line Upgrade | This project will install the Hutto - Limmer 345-kV transmission line on separate structures to remove an ERCOT double-circuit contingency event. This project will require coordination with Oncor. The need for this project with identified by ERCOT in the EIR for RPG 25RPG009. |  | Hutto | Limmer | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8544 | 2030-02-01 |  | 345 | 0 | 3.38 | 0 |  | Williamson | Williamson | Tier 4 | 25RPG009 | 2025-03-17 | 2025-08-19 |  | 3696, 7341 | Y |  |  |  | 109793 | 109792
109745 | Tivoli: Construct New Distribution Station | Construct new distribution station on the Rincon to Airco 138 kV line | NEW | TIVOLI |  |  |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | DR26X0018 | 2030-02-28 |  | 138 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 8144, 8827, 80065 | Y | N |  |  | 109746 | 109745
104554 | Addition of the Red Gulch 138 kV substation | Addition of Red Gulch station on existing Bertram - Andice transmission line. |  |  |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2030-03-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70001, 70520, 70522 | Y |  |  |  | 104556 | 104554
110943A | Cooke County Resiliency Project | Construct a new breaker station “Bulcher” near Bulcher, TX Construct a new transmission line from Bulcher to Capps Corner Construct a new transmission line from Bulcher to Sivell’s Bend |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-03-01 |  | 69 | 16 | 0 | 0 |  | Cooke | Cooke | Tier 2 | 26RPG007 | 2026-05-06 |  |  | 711, 727, 754 | Y |  |  |  | 111206 | 110943
110677 | Add 180MAr Cap at Elm Creek |  |  | 5133 |  | Conceptual | S-XXXX | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-03-01 |  | 345 | 0 | 0 | 0 |  | Bexar |  | Tier 4 |  |  |  |  | 5133 | N |  |  |  | 110678 | 110677
110665 | Rebuild Elm Creek to STP dbl Ckt |  |  |  |  | Conceptual |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2030-03-01 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 1 |  |  |  |  | 5068, 5133, 5236, 5320, 5323, 5380, 5915 | N |  |  |  | 110666 | 110665
102762 | BEPC_TPIT102762_Whitney_Itasca |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-03-01 |  | 69 | 0 | 16.1 | 0 |  | Bosque |  | Tier 4 |  |  |  |  | 224, 228, 243 | Y |  |  |  | 102763 | 102762
110931 | Pig Creek: Install new 138 kV Capacitor Bank | Install new capacitor banks at the Pig Creek 138 kV station |  | Pig Creek |  | Conceptual |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2030-03-02 |  | 138 | 0 | 0 | 0 | 0,100 | Reeves |  | Tier 4 |  |  |  |  | 60393 | Y | N |  |  | 110932 | 110931
110939 | Musquiz: Install new 138 kV Capacitor Bank | Install new capacitor banks at the Musquiz 138 kV station | NEW |  |  | Conceptual |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2030-03-02 |  | 138 | 0 | 0 | 0 | 0,50 | Reeves |  | Tier 4 |  |  |  |  | 6673 | Y | N |  |  | 110940 | 110939
109718 | Ferranti: Construct New 345 kV Station | Interconnect the OPS 2.0 load to the Ferranti 345 kV station on the Edith Clarke to Riley double circuit line | TSP/Company Contact Update | Ferranti |  | Planned |  | AEP | Bradley Case myturner@aep.com 918-599-2437 | TP2026092 | 2030-03-30 |  | 345 | 3 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6101, 60327, 60328, 60505 | Y | N |  |  | 109721 | 109718
103470 | Welsh HVDC: Build 345 kV Bypass Line | Construct new 345 kV bypass line at the Welsh HVDC 345 kV station |  | Welsh HVDC | Welsh HVDC | Planned |  | AEP TCC | Craig Tabor myturner@aep.com 918-599-2437 | TP2024163 | 2030-03-31 |  | 345 | 0.25 | 0 | 0 |  | Titus | Titus | Tier 4 |  |  |  |  | 5920, 5925 | Y | N |  |  | 103471 | 103470
109818 | Venus â€“ Old Country Switch 345 kV Double-Circuit Line | Upgrade Venus – Old Country Switch 345 kV Double-Circuit Line |  | Venus Switch | Old Country Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4282 | 2030-04-01 |  | 345 | 0 | 15.9 | 0 |  | Ellis | Ellis | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 1907, 2255, 2632, 68091 | Y |  |  |  | 112559 | 109818 | 2024-NC56
91883 | La Palma to Stillman: Rebuild 138 kV Line | Rebuild the La Palma to Stillman 138 kV line | In-Service Date Update | La Palma | Stillman | Planned |  | AEP TCC | Nathan Cowan jlsolis@aep.com 361-881-5574 | TP2025011 | 2030-05-01 |  | 138 | 0 | 22.3 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 8314, 8333, 79601 | Y |  |  |  | 91884 | 91883
91896 | La Palma to Military Highway: Rebuild 138 kV Line | Rebuild the La Palma to Military Highway 138 kV line | In-Service Date Update | La Palma | Military Highway | Planned |  | AEP TCC | Nathan Cowan jlsolis@aep.com 361-881-5574 | TP2025011 | 2030-05-01 |  | 138 | 0 | 22.2 | 0 |  | Cameron | Cameron | Tier 1 | 24RPG008 | 2024-03-07 | 2024-09-27 | 2024-12-03 | 8314, 8339, 80229 | Y |  |  |  | 91897 | 91896
110084G | This models upgrades required for a proposed load addition | Reconductor of 345 kV W.A. Parish to Wolf to Raider ckt 64. |  | CEHE_Newsub | WAParish/Wolf | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-05-01 |  | 345 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 1 | [5 empty] | N | N |  |  | 110509 | 110084
76123 | D'Hanis Capacitor 2nd step addition | D'Hanis Capacitor 2nd step addition 9.6 MVAR |  | D'Hanis |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5814 | N | N |  |  | 76124 | 76123
102873 | Upgrade Aloe to Warburton |  |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 69 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5605, 5606 | N | N |  |  | 102874 | 102873
102877 | Upgrade Bakersfield to Schneeman Draw | Upgrade Bakersfield - Cedar Canyon - Noelke - Schneeman Draw as part of the Permian Basin Reliability plan (project L15) |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7053, 76002, 76004, 76005, 76008, 76015 | Y | N |  |  | 102878 | 102877
90022 | Upgrade Sam Rayburn to Aloe | Upgrade Sam Rayburn to Aloe to 795 ACSR conductor. 2025 RTP. |  | Sam Rayburn | Aloe | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 138 | 0 | 9.6 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5500, 5606 | Y |  |  |  | 90023 | 90022
75989 | Rebuild Vanderbilt -Pt Lavaca | Rebuild Vanderbilt - Placedo - Kamey -Pt Lavaca 69kV to 795 ACSR |  | Vanderbilt | Port Lavaca | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-05-01 |  | 69 | 0 | 26.47 | 0 |  | Victoria | Calhoun | Tier 4 |  |  |  |  | 5582, 5586, 5590, 5591, 5592 | N |  |  |  | 75990 | 75989
110084H | This models upgrades required for a proposed load addition | Reconductor of 345kV ckt.72 W.A. Parish to CEHE_Newsub. |  | CEHE_Newsub | WAParish | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-05-01 |  | 345 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 1 | [5 empty] | N | N |  |  | 110510 | 110084
110296 | Allen Switch - Lavon Switch 138 kV Line | Establish Allen Switch - Lavon Switch 138 kV Line |  | Allen Switch | Lavon Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3342 | 2030-05-01 |  | 138 | 12.7 | 0 | 0 |  | Collin | Collin | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 2475, 2509 | Y |  |  |  | 112135 | 110296 | 2024-NC59
110637 | Rebuild Elm Creek to Skyline |  |  | 5133 | 5371 | Conceptual |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2030-05-01 |  | 345 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 1 |  |  |  |  | 5133, 5371 | N |  |  |  | 110638 | 110637
102663 | BEPC_TPIT102663_Pursley_Emmett |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-05-10 |  | 69 | 0 | 10.5 | 0 |  | Navarro |  | Tier 4 |  |  |  |  | 191, 198, 199 | Y |  |  |  | 102759 | 102663
110006 | Rebuild the Lake Creek Switch - Riesel Switch 138 kV Line | Rebuild the Lake Creek Switch - Riesel Switch 138 kV Line |  | Lake Creek Switch | Riesel Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6433 | 2030-05-15 |  | 138 | 0 | 6.1 | 0 |  | McLennan | Falls | Tier 4 | [5 empty] | Y |  |  |  | 110007 | 110006
110000 | Install Jewett Switch - Crockett Switch 138 kV Line Ckt #2 | Install Jewett Switch - Crockett Switch 138 kV Line Ckt #2 |  | Jewett Switch | Crockett Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6554 | 2030-05-15 |  | 138 | 39 |  | 0 |  | Leon | Houston | Tier 1 | [5 empty] | Y |  |  |  | 110001 | 110000
110338 | Rebuild Voss Lake Switch - Minerva Switch 138 kV Line | Rebuild Voss Lake Switch - Minerva Switch 138 kV Line |  | Voss Lake | Minerva | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6571 | 2030-05-15 |  | 138 | 0 | 13.5 | 0 |  | Milam | Milam | Tier 4 | [5 empty] | Y |  |  |  | 110339 | 110338
110008 | Rebuild the Mankin Switch - Seven Points 138 kV Line Section | Rebuild the Mankin Switch - Seven Points 138 kV Line Section |  | Mankin Switch | Seven Points | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6466 | 2030-05-15 |  | 138 | 0 | 11.2 | 0 |  | Henderson | Henderson | Tier 1 | 25RPG041, 25RPG043 | 2025-11-12 | 2026-08-19 |  | 3262, 3264, 3265, 3287 | Y |  |  |  | 110009 | 110008
110020 | Rebuild Bell County East - Little Pond/Brangus 345 kV DCKT Line | Rebuild Bell County East - Little Pond/Brangus 345 kV DCKT Line |  | Bell County East | Little Pond/Brangus | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6422 | 2030-05-15 |  | 345 | 0 | 46.8 | 0 |  | Bell | Milam | Tier 1 | 25RPG009 |  |  |  | 3377, 3687, 3705, 3762, 3766 | Y |  |  |  | 110021 | 110020
110154 | Rebuild Possum Trot Switch - Belfalls-STR 26-4C 345 kV DCKT Line | Rebuild Possum Trot Switch - Belfalls-STR 26-4C 345 kV DCKT Line |  | Possum Trot | Belfalls | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6459 | 2030-05-15 |  | 345 | 0 | 52.2 | 0 |  | McLennan | Bell | Tier 1 | 25RPG043 |  |  |  | 3404, 3412, 3741, 3791 | Y |  |  |  | 110155 | 110154
110274 | Gunter Switch - Collin Switch 138 kV Line | Upgrade Gunter Switch - Collin Switch 138 kV Line |  | Gunter Switch | Collin Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3319 | 2030-05-15 |  | 138 | 16.4 | 0 | 0 |  | Grayson | Collin | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 675, 1757, 2236, 2350, 2366, 2370, 2380, 12236, 12351, 12366, 12375, 12468 | Y |  |  |  | 112116 | 110274 | 2024-NC76
109894 | Rebuild the Redland Switch - Nacogdoches Southeast Switch 138 kV Line | Rebuild the Redland Switch - Nacogdoches Southeast Switch 138 kV Line |  | Redland Switch | Nacogdoches Southeast Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6538 | 2030-05-15 |  | 138 | 0 | 13.4 | 0 |  | Angelina | Nacogdoches | Tier 1 | [5 empty] | Y |  |  |  | 109895 | 109894
109872 | Establish new Belton 138 kV Switch | Establish new Belton 138 kV Switch |  | Belton | Belton | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6351 | 2030-05-15 |  | 138 | 0 | 0 | 0 |  | Bell | Bell | Tier 4 | [5 empty] | Y |  |  |  | 109873 | 109872
110138 | Bastrop West - Sim Gideon Transmission Line Upgrade | LCRA will upgrade the transmission line from SIMGID (7130) - BASTWE (7555), to achieve a 533 MVA min rating. Upgrade project to support Batch Zero Base Load |  | Sim Gideon | Bastrop West | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2030-05-15 |  | 138 | 0 | 6.73 | 0 |  | Bastrop | Bastrop | Tier 4 | [5 empty] | Y |  |  |  | 110139 | 110138
6287 | Sherry Sw. - Webb/Kennedale 345 kV DCKT Line | Upgrade the existing 345 kV Line |  | Sherry | Webb/Kennedale | Conceptual |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M4252 | 2030-05-15 |  | 345 | 0 | 11.2 | 0 |  | Tarrant | Tarrant | Tier 3 |  |  |  |  | 1911, 1918, 1929, 1930, 1932, 1934 | Y |  |  |  | 14016 | 6287
80579 | La Palma to Progresso: Convert to 138 kV | Convert the La Palma to Progreso 69 kV line to 138 kV | Dollars Should Be Update | La Palma | Progresso | Planned | TA2020071 | AEP TCC | Robert Younger deevans@aep.com 918-599-2938 |  | 2030-05-15 |  | 138 | 0 | 18.1 | 0 |  | Cameron | Hidalgo | Tier 3 | 23RPG005 | 2023-03-01 | 2023-03-23 |  | 8310, 8314, 8701, 8703, 8748, 8751, 80104, 80229 | Y | N |  |  | 80580 | 80579
87770 | Establish a 110.4 MVAR Capacitor Bank at Midnight 138 kV Substation | Establish a 110.4 MVAR Capacitor Bank at Midnight 138 kV Substation |  | Midnight | Midnight | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6346 | 2030-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Williamson | Williamson | Tier 4 |  |  |  |  | 3677 | Y |  |  |  | 87771 | 87770
99605 | Establish Belltown 138 kV Switch | Establish Belltown 138 kV Switch |  | Belltown 138 kV Switch | Belltown 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6414 | 2030-05-15 |  | 138 | 0 | 0 | 0 |  | Van Zandt | Van Zandt | Tier 4 |  |  |  |  | 3197, 3773, 3786 | Y |  |  |  | 99606 | 99605
102795 | Bakersfield_NevillRoad_NorthMcCamey_Transmission_Line_Upgrade | PL and LCRA joint PBRP_L14 project by upgrading of the existing Bakersfield - Nevill Road - North McCamey 345kV transmission lines and adding of new 345kV Bakersfield - Nevill Road - North McCamey second circuits |  | Nevill Road | Bakersfield/North McCamey | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | PBRP_L14_Joint | 2030-05-15 |  | 345 | 16.27 | 16.27 | 0 |  | Upton | Pecos | Tier 1 |  |  |  |  | 844, 76000, 76002 | Y |  |  |  | 102796 | 102795
102795 | Bakersfield_NevillRoad_NorthMcCamey_Transmission_Line_Upgrade | PL and LCRA joint PBRP_L14 project by upgrading of the existing Bakersfield - Nevill Road - North McCamey 345kV transmission lines and adding of new 345kV Bakersfield - Nevill Road - North McCamey second circuits |  | Nevill Road | Bakersfield/North McCamey | Planned |  | GPL | Danh Huynh dhuynh@gpltexas.org 972-205-3826 | PBRP_L14_Joint | 2030-05-15 |  | 345 | 16.27 | 16.27 | 0 |  | Upton | Pecos | Tier 1 |  |  |  |  | 844, 76000, 76002 | Y |  |  |  | 102796 | 102795
103782 | Drill Hole - Sand Lake 765 kV Line | Add a new Drill Hole - Sand Lake 765 kV Line |  | Drill Hole | Sand Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8892 | 2030-05-15 |  | 765 | 57.6 | 0 | 0 |  | Culberson | Ward | Tier 1 | 25RPG022 |  |  |  | 18733, 18736 | Y |  |  |  | 103783 | 103782
4320 | CPSE_Brooks to Chavaneaux MLSE | Upgrade terminals at Brooks and Chavaneaux to ensure a 1364 A rating (minimum) |  | Brooks | Chavaneaux |  |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0733 | 2030-05-30 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y | Y |  |  | 11872 | 4320
109635A | WA Parish 345kV 80kA Fault Upgrade | Upgrade WA Parish 345kV [44000] fault duty to 80KA |  | WA Parish |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y |  |  |  | 109636 | 109635
90027 | Cross Plains to Rising Star: Rebuild 69 kV Line | Rehab the Cross Plains to Rising Star 69 kV line | Company Contact and In-Service Date Update | Cross Plains | Rising Star | Planned | TA2024101 | AEP TNC | Craig Tabor myturner@aep.com 918-599-2437 |  | 2030-05-31 |  | 69 | 0 | 12.96 | 0 |  | Callahan | Eastland | Tier 4 |  |  |  |  | 6357, 6358 | Y | N |  |  | 92899 | 90027
109635B | WA Parish 345kV 80kA Fault Upgrade | Upgrade WA Parish 345kV [44005] fault duty to 80KA |  | WA Parish |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-05-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y |  |  | Cost included in main entry | 109637 | 109635
15TPIT0031 | Chavaneaux_Chavaneaux Tap Rebuild (Brooks to Chavaneaux ckt) | Rebuild 138 kV transmission from Chavaneaux to Chavaneaux Tap. This rebuild is for Brooks to Chavaneaux ckt. |  | Brooks | Chavaneaux | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0260 | 2030-05-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5085 | Y |  |  | There are no transformers associated with this project | 9555 | 2304
15TPIT0033 | Randolph - 138 kV Substation Equipment Upgrade | Upgrade the Weiderstein and Tuttle terminals and ensure a 2000 A rating (minimum). Reconfigure and-or upgrade the main bus to ensure a 2000 A rating (minimum). |  | Randolph | Tuttle-Weiderstein | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0645b | 2030-05-31 12:00 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5360, 5435 | Y | N |  | There are no transformers associated with this project | 9557 | 2306
110935 | Orchrid_138_Switchyard |  |  |  |  | Conceptual |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 |  |  |  |  | 5054, 5083, 5230, 5326, 5426 | N |  |  |  | 110936 | 110935
104249B | BRYN_SOSW-HLMN-DWLRD_Upgrade | Upgrade Dowling Road to Holleman 138kV Line |  | BTU Dowling Road | BTU Holleman | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2030-06-01 |  | 138 | 0 | 1.1 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32005, 32892 | Y |  |  |  | 104251 | 104249
104249A | BRYN_SOSW-HLMN-DWLRD_Upgrade | Upgrade South Switch to Holleman 138kV Line |  | BTU Holleman | BTU South Switch | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2030-06-01 |  | 138 | 0 | 1.35 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32892, 32893 | Y |  |  |  | 104250 | 104249
92282 | Faulkner - Cryo 138kV - Part of Upgrade L4 2024 Permian Basin Study |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2030-06-01 |  | 138 | 22.8 | 0 | 0 |  | Reeves | Reeves | Tier 2 |  |  |  |  | 38124, 60721 | Y |  |  |  | 92283 | 92282
92276 | Bottlebrush 345kV - Part of Upgrade L13 2024 Permian Basin Study |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 | PBRP Upgrade L13 | 2030-06-01 |  | 345 | 174.84 | 29.81 | 1500 |  | Pecos | Pecos | Tier 1 |  |  |  |  | 38430, 38431, 38432, 38435, 38439, 38441, 38442, 38443, 38455, 60404 | Y |  |  |  | 92277 | 92276
110565 | Carmichael Bend Switch - Cleburne North 138 kV Line Section | Carmichael Bend Switch - Cleburne North 138 kV Line Section |  | Carmichael Bend Switch | Cleburne North | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5226 | 2030-06-01 |  | 138 | 0 | 0 | 0 |  | Johnson | Johnson | Tier 3 | [5 empty] | Y |  |  |  | 110566 | 110565
110907 | Castroville_to_Rafter_DblCkt_&_Rebuild | Rebuild existing Castroville to Rafter ckt 1 (~6 miles) single circuit to have normal and emergency ratings of at least 3000A. Construct new Castroville to Rafter ckt 2 (~6 miles) to match ratings of ckt 1 |  | 5083 | 5355 | Conceptual | S-XXXX | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2030-06-01 |  | 138 | 6 | 6 | 0 |  | Medina | Medina | Tier 3 |  |  |  |  | 5083, 5355 | N |  |  |  | 110908 | 110907
110913 | WOH Area Upgrades |  |  |  |  | Conceptual |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5003, 5020, 5185, 5200, 5466, 5467, 5487, 5488 | N |  |  |  | 110914 | 110913
110915 | Omicron Area Upgrades |  |  |  |  | Conceptual |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5055, 5326, 5355, 5430 | N |  |  |  | 110916 | 110915
110917 | New_Grissom_Ingram_Circuit |  |  |  |  | Conceptual |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 3 |  |  |  |  | 5185, 5241 | N |  |  |  | 110918 | 110917
110919 | CPS Lylte Tline Rebuilds |  |  |  |  | Conceptual |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5290, 5390, 5813, 8962 | N |  |  |  | 110920 | 110919
110923 | Castroville_345KVSwitchingStation_Changes |  |  |  |  | Conceptual |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5056, 5083, 5084, 5231, 5299, 5901, 7046, 55958 | N |  |  |  | 110924 | 110923
110925 | Add Reactive Support |  |  |  |  | Conceptual |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-06-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5083, 5201, 5211 | N |  |  |  | 110926 | 110925
104571 | Addition of the Feldspar 138 kV substation | Adding 138 kV Feldspar station to the line connecting Buda to Rutherford. |  |  |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70007, 70498, 70509 | Y |  |  |  | 104572 | 104571
16TPIT0007 | McNeil to MagPlant Ckt 977 Upgrade | Reconductor existing McNeil to MagPlant circuit from 2000 to 3000 Amp. Relocate McNeil to Summit Circuit 907 and McNeil to MagPlant Circuit 977 to separate structures. Kramer Lane (KA) substation will be cut-into this line in 2023 |  | McNeil Substation | Mag Plant Substation | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 | P396 | 2030-06-01 |  | 138 | 0 | 3.24 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238, 9276 | Y | N |  | Will add the ptoject to the base case. | 8207 | 1031
71408 | Upgrade CKT943 to 3000 amperes | Replace existing 2-795ACSR conductors with 2-795 ACSS conductors and the upgrade the terminal equipment to 3000 amperes. |  | Lytton Springs | Pilot Knob | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2030-06-01 |  | 138 | 0 | 11.13 | 0 |  | Caldwell | Travis | Tier 4 |  |  |  |  | 9075, 9259 | Y |  |  |  | 71409 | 71408
86315 | AEN_Barton_Vega_Ckt_928_Reconductor |  |  | 9158 | 9285 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9158, 9285 | Y |  |  |  | 86316 | 86315
86317 | AEN_DP_OnionCreek_Ckt_924_Reconductor |  |  | 9187 | 9251 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9187, 9251 | Y |  |  |  | 86318 | 86317
86333 | AEN_OnionCreek_StoneyRidge_Ckt_1026_Reconductor |  |  | 9237 | 9251 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9237, 9251 | Y |  |  |  | 86334 | 86333
86838 | AEN_JustinLane_KoenigLane_Ckt__conversion_to_138kV | Justin Lane Koenig Lane convert to 138kV |  | 9225 | 9227 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2030-06-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9225, 9227 | Y |  |  |  | 86839 | 86838
110830 | STEC_110830_OuroborosLargeLoadProject | Upgrade the 345 kV AEP Rio Hondo (8318) to Candela (8013) Ckt #1 to at least NMRL/EMR rating of 2850 MVA Upgrade 345 kV SHRY Kingfisher (79501) to AEP La Palma (8317) to Candela (8013) Ckt #1 to at least NMRL/EMR rating of 2600 MVA Upgrade 138 kV AEP Harlingen Switch (8327) to Oleander (80022) Ckt 1 to at least NMRL/EMGY rating of 250 MVA Upgrade 138 kV AEP Aztec (8708) to Hidalgo Energy Centre (8963) Ckt #1 to at least NMRL/EMGY rating of 440 MVA Upgrade 69 kV AEP La Palma (8289) to Brownsville (8331) Ckt #1 to at least NMRL/EMGY rating 60 MVA Upgrade 69 kV AEP La Palma (8310) to Resaca (8626) Ckt #1 to at least NMRL/EMGY rating 45 MVA |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-06-01 12:15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 | [5 empty] | Y | N |  |  | 110831 | 110830
100466 | Big Hill 765-kV Substation Addition | LCRA TSC will construct a new Big Hill 765-kV yard adjacent to the existing Big Hill 345-kV Substation and install two new 765/345-kV autotransformers. |  | Big Hill |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-8263 | 2030-06-30 |  | 765 | 0 | 0 | 4806 | -900,0 | Schleicher |  | Tier 1 |  | 2025-07-11 | 2026-03-02 |  | 76003, 76500 | Y |  |  |  | 100467 | 100466 | 2024-EHV-CORE-PB2b
103248 | Nevill_Road_North_McCamey_Transmission_Line_Addition | Install a 345-kV circuit on the second position of the North McCamey – Nevill Road 345-kV transmission line from North McCamey Substation to a POI with Garland Power & Light (GP&L). Upgrade North McCamey Substation terminal equipment to interconnect the new transmission line. |  | Nevill Road | North McCamey | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-06-30 |  | 345 | 0 | 0 | 0 |  | Pecos | Upton | Tier 1 | [5 empty] | Y |  |  |  | 103249 | 103248
102395 | Bakersfield_SchneemanDraw_Transmission_Line_Upgrade | Upgrade substation equipment at Bakersfield, Cedar Canyon, Twelvemile, Noelke, Single Tree, and Schneeman Draw to support the upgrade of the STEC 345-kV double circuit line from Bakersfield to Schneeman Draw. Transmission line scope will be performed by STEC. |  | Bakersfield | Schneeman Draw | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-06-30 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 102396 | 102395
110457 | STEC Amphion Load Project Phase 2 | -RTP project 2025-MDS01:Upgrade Coleto to Victoria ckt 1 to 485 MVA -RTP project 2025-MDS01: Upgrade Coleto to Victoria ckt 2 to 485 MVA -Upgrade Coleto 345/138 auto 1 to 780 MVA -Upgrade Coleto 345/138 auto 2 to 770 MVA -RTP project 2025-S04: Upgrade Angstrom - Whitepoint ckt 1 to 2405 MVA -Upgrade Lon Hill - Whitepoint ckt 1 to 1256 MVA -RTP project 2025-SC19:Upgrade Hillje to Crasco to 1965 MVA |  | Coleto,Angstrom, Hillje | Victoria,Whitepoint,Crasco | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-06-30 12:15 |  | 138 | 108.68 |  | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110458 | 110457
110077F | This models upgrades required for a proposed load addition. | Install 300 MVAR capacitor bank at the 345 kV Singleton substation. |  | Singleton |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-07-01 |  | 345 | 0 | 0 | 0 | 0,300 | Grimes |  | Tier 4 | [5 empty] | N | N |  | No cost estimate available at this time. | 110500 | 110077
110079B | This models upgrades required for a proposed load addition near King Substation | Install 300 MVAR capacitor bank at CEHE_NewSub. |  | CEHE_NewSub |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-07-01 |  | 345 | 0 | 0 | 0 | 0,300 | Harris |  | Tier 4 | [5 empty] | N | N |  | Cost included in main entry. | 110550 | 110079
104613 | Addition of Highway 45 substation | Addition of Highway 45 138 kV substation between Buda and Manchaca |  |  |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2030-07-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70008, 70498, 70504 | Y |  |  |  | 104614 | 104613
110077E | This models upgrades required for a proposed load addition. | Install second 300 MVAR capacitor bank at the 345 kV Zenith substation. |  | Zenith |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-07-01 |  | 345 | 0 | 0 | 0 | 0,300 | Harris |  | Tier 4 | [5 empty] | N | N |  | No cost estimate available at this time. | 110499 | 110077
110057C | This models upgrades required for a proposed load addition | Install one 300 MVAR capacitor bank at 345 kV Zenith substation. |  | Zenith |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-07-01 |  | 345 | 0 | 0 | 0 | 0,300 | Harris |  | Tier 4 | [5 empty] | N | N |  | Cost is included in phase A | 110067 | 110057
91586 |  |  |  | TENASKA | NEW SUBSTATION PLANK | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-07-05 |  | 138 | 0 | 0 | 0 |  | Johnson | Johnson | Tier 4 |  |  |  |  | 370, 371, 415 | Y |  |  |  | 91587 | 91586
109822 | Old Country Switch - Notus Switch 345 kV Double-Circuit Line | Upgrade Old Country Switch – Notus Switch 345 kV Double-Circuit Line |  | Old Country Switch | Notus Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4511 | 2030-08-01 |  | 345 | 0 | 14.8 | 0 |  | Ellis | Ellis | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 1907, 2255, 3376, 68091 | Y |  |  |  | 111726 | 109822 | 2024-NC42
110815 | Fisher Road - Wichita Falls 138 kV Line Upgrade | Fisher Road - Wichita Falls 138 kV Line Upgrade |  | Fisher Road Switch | Wichita Falls | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | R191 | 2030-08-15 |  | 138 | 0 | 3.52 | 0 |  | Wichita | Wichita | Tier 4 |  | 2025-11-18 | 2026-05-18 |  | 1427, 1448 | Y |  |  |  | 110816 | 110815
99117 | BRYN_99117_ATK-TAMU_UPGRADE | Re-build the existing Atkins to TAMU 138-kV single-circuit transmission line on double-circuit capable structures with one circuit in place with normal and emergency ratings of at least 495 MVA and 521 MVA, respectively, approximately 3.3-mile. |  | Atkins | TAMU | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2030-10-01 |  | 138 | 0 | 3.3 | 0 |  | Brazos | Brazos | Tier 1 | 25RPG001 | 2025-01-10 | 2025-07-05 |  | 32799, 32862 | Y |  |  |  | 99118 | 99117
102993 | BEPC_TIER3_WhitneyAutoUpgrade |  |  | 240 |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-10-01 |  | 345 | 0 | 0 | 700 |  | Hill |  | Tier 3 | 25RPG044 | 2025-12-11 | 2026-01-27 |  | 240, 241, 36996, 36997 | Y |  |  |  | 104013 | 102993 | 2023-NC62
89920 | GVEC Nixon substation | Rebuild existing substation, 138 kV bus, new PWT, new Control House, new HV and LV structures, containment foundations, bus, panels, etc |  | Gonzales |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2030-10-25 | 2958101 | 138 | 0 | 0 | 0 |  | Gonzales | Gonzales | Tier 4 | [5 empty] | Y |  |  |  | 89921 | 89920
111276 | Solstice: Construct New 765 kV Station | Construct the new Solstice 765 kV station and Install two 765/345 kV autotransformers and two 765 kV shunt reactors |  | Solstice |  | Planned |  | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | TP2024146 | 2030-10-30 |  | 765 | 0 | 0 | 4500 |  | Pecos |  | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 6129, 6130, 6137, 6144, 6145, 6164 | Y | N |  |  | 111304 | 111276
98595 | Solstice to Howard: Construct New 765 kV Single Circuit Line | Construct a new 765 kV single circuit line from Solstice to Howard | In-Service Date, Dollars, Autotransformer and Reactive Capability Update | Solstice | Howard | Planned |  | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 |  | 2030-10-30 |  | 765 | 185 | 0 | 0 |  | Pecos | Bexar | Tier 1 | H.B. 5066 |  |  | 2024-10-31 | 6129, 6130, 6137, 6144, 6145, 6164, 60404 | Y |  |  |  | 98596 | 98595
110379 | San Pedro: Construct 345 kV Station | Construct 345 kV station to interconnect STEC Nueces Ammonia Load | NEW | San Pedro |  | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2030-11-01 |  | 345 | 0 | 0 | 0 |  | Nueces |  | Tier 1 | 25RPG016 |  |  |  |  | Y | N |  |  | 110380 | 110379
110391 | Chalcedony to San Pedro: Construct 345 kV circuit. | Construct new double circuit capable structures from San Pedro to Chalcedony 345 kV. String single circuit initially. | Project Title and Project Description Update | San Pedro | Chalcedony | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2030-11-12 |  | 345 | 4.5 | 0 | 0 |  |  |  | Tier 1 | 25RPG016 |  |  |  |  | Y | N |  |  | 110392 | 110391
104018 | Lake Pauline to Quanah: Convert to 138 kV | Convert the Lake Pauline to Quanah 69 kV line to 138 kV |  | Lake Pauline | Quanah | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2025249 | 2030-11-30 |  | 138 | 0 | 2.75 | 0 |  | Childress | Childress | Tier 2 | 25RPG018 | 2025-05-18 | 2025-11-10 |  | 6032, 6048, 6050, 6051, 6053, 60278, 60279, 60280, 60446, 69194 | Y | N |  |  | 104019 | 104018
104020 | Nippert: Construct New 138/69 kV Station | Construct new Nippert 138/69 kV station on the Childress to Quanah 69 kV line between Childress and Goodlet and on the Paducah to West Childress 138 kV line | Terminal From, In-Service Date, RPG Number, Date submitted to ERCOT and Review Completed Date Update | Nippert |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2025249 | 2030-11-30 |  | 138 | 7 | 3.2 | 90 |  | Childress |  | Tier 2 | 25RPG018 | 2025-05-18 | 2025-11-10 |  | 6030, 6032, 6135, 60276, 60277, 60279 | Y | N |  |  | 104021 | 104020
99784 | Surreal: Construct New 345 kV Station | Interconnect the Cinco III load to the new Surreal 345 kV station and install two autotransformers | Project Title, Description, Terminal from, Transmission Owner, Dollars, and Planning Charter Tier Update | Surreal |  | Planned |  | AEP TCC/ETT | Will Simmons jlsolis@aep.com 361-881-5574 | TP2025325 | 2030-11-30 |  | 345 | 0 | 0 | 1350 |  | Medina |  | Tier 4 |  |  |  |  | 8962, 80287, 80288, 80289 | Y |  |  |  | 99785 | 99784
110543 | Timberview Switch - Benbrook Switch 345 kV Line Upgrade | Timberview Switch - Benbrook Switch 345 kV Line Upgrade |  | Timberview Switch | Benbrook Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5273 | 2030-12-01 |  | 345 | 0 | 0 | 0 |  | Johnson | Johnson | Tier 3 | [5 empty] | Y |  |  |  | 110544 | 110543
104615 | BBEC Gay Hill to Sandy Hill Transmission Line Upgrade | Replace 336 (Linnet) conductor with 959 (Suwannee) and replace a limited number of structures to accommodate the new conductor. |  | Gay Hill | Sandy Hill | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2030-12-01 |  | 138 | 0 | 8.9 | 0 |  | Washington | Washington | Tier 4 |  |  |  |  | 7570, 7572 | Y |  |  |  | 104616 | 104615
110494 | Oak Spring Switch - Colorado City Switch 69 kV Line | Rebuild the 18.4-mile Oak Spring - Colorado City 69 kV Line |  | Nolan | Mitchell | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8904 | 2030-12-01 |  | 69 | 18.4 | 0 | 0 |  |  |  | Tier 3 |  |  |  |  | 1378, 11380 | Y |  |  |  | 110495 | 110494
110288 | Graham Plant Switch - Garvey Road Switch 345 kV Line | Upgrade Graham Plant Switch - Garvey Road Switch 345 kV Line |  | Garvey Road Switch | Graham Plant Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3545 | 2030-12-01 |  | 345 | 0 | 17.1 | 0 |  | Young | Young | Tier 3 |  |  |  |  | 1430, 17002 | Y |  |  |  | 110289 | 110288
110232 | LST_Liberty_To_Navarro_New_345kV_Line_BZ_LLI | Build new 345 kV single ckt line connecting LST Liberty Station to LST Navarro Station with 5000 Amps minimum ratings. |  | Navarro | Liberty | Conceptual |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2030-12-01 |  | 345 | 31 | 0 | 0 |  | Hill | Navarro | Tier 2 |  |  |  |  | 68091, 68092 | N | N |  |  | 110233 | 110232
110673 | Sherry 345-138 kV Autotransformer B Upgrade | Sherry 345-138 kV Autotransformer B Upgrade |  | Sherry Switch | Sherry Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5269 | 2030-12-01 |  | 345 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 3 |  | 2025-11-18 | 2026-05-18 |  | 1918, 1920, 11920 | Y |  |  |  | 112408 | 110673
110393 | Comanche Peak Switch - Johnson Switch 345 kV Line | Upgrade Comanche Peak Switch - Johnson Switch 345 kV Line |  | Comanche Peak | Johnson | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5369 | 2030-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 3 |  | 2025-11-18 | 2026-05-18 |  |  | Y |  |  |  | 110480 | 110393
110475 | Notus Switch - Navarro Switch 345 kV Line | Upgrade Notus Switch - Navarro Switch 345 kV Line |  | Notus | Navarro | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4479 | 2030-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 3 | [5 empty] | Y |  |  |  | 110476 | 110475
92340 |  |  |  | New 138 KV station "Warg" | New 138 KV station "Warg" | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-12-01 |  | 138 | 4 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 173, 176, 177 | Y |  |  |  | 92341 | 92340
110515 | STEC Edwards Large Load Addition | -Add a new 345kV path from Howard to Edward - Tap the line from Kendall to Cagnon at 5 miles from Cagnon to add the new CPS substation - Add a new 345kV path from New CPS station to Edward - Add 2 138/345kv autos at Edward with 675 MVA rating - Install 134 MVAR reaction power compensation at Lytle 4A - Upgrade the 138kV line from Bandera to Harmwolf to 371 MVA - Upgrade the 345kV Cachena to ELmcreek line to 1250 MVA - Upgrade the 345kV line from Howard to Spruce to 1563 MVA - Upgrade the 345kV line from Howard to Av Rosenburg to 1453 MVA - Upgrade the 138kV line from Lytle to Lytle4A to 354 MVA - Upgrade Hill Country 345/138 autos 3, 4 to 740 MVA |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-12-01 12:15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 | 25RPG046 |  |  |  |  | Y | N |  |  | 110516 | 110515
110525 | STEC Rodgers Large Load Project Phase 2 | -Rebuild LCRA Henne to Zorn 138kV line to 245 MVA -Install cap bank 19.2 MVAR at STEC Natalia 69kV - Rebuild Palo Duro to Dilley 138kV line with a conductor rated at least 312 MVA - Install a new 134MVAR cap bank at AEP Lytle 138kV - Rebuild CPS / AEP Lytle - Lytle with conductors rated 354 MVA -Rebuild AEP Big Foot to Pleasanton 138kV with conductors 147 MVA - install new cap bank 55.01 MVAR at Pearsall 69kV bus - Install a new cap bank 12MVAR at CPS Somerset 138kV - Construct STEC Alsatian 345/138kV on Bader - Pearson 138kV line .8 miles from Bader with 3 parallel autos 345/138kV 675 MVA rated - Construct a new CPS energy 3 terminal 345kV station from Kendall to Cagnon 5 miles from Cagnon - Construct a new 345kV transmission line from Howard to Alsatian 1746 MVA - Rebuild CPS Omicron to Rafter 138kV 642 MVA - Rebuild CPS Cagnon - Texas Research 465 MVA - Rebuild Bander to Hamilton Wolf 138kV for 371 MVA - rebuild STEC Hondo Creek to Devine 69kV line with 109 MVA rating |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-12-01 12:15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 | 25RPG046 |  |  |  |  | Y | N |  |  | 110526 | 110525
110529 | STEC Rodgers Large Load Phase 3 | -Upgrade CPS Martinez 345/138kV autos 1,2 to 683 MVA -Rebuild CPS Howard to Spruce 345kV to 1580MVA - Rebuild CPS Howard to Braunig to 1457 MVA -Upgrade CPS Hill Country 345/138kV autos 3,4 to 740MVA rating - Rebuild CPS Cachena to Elmcreek to 1250MVA |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-12-01 12:15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 | 25RPG046 |  |  |  |  | Y | N |  |  | 110530 | 110529
99385 | Establish Bell County East 765/345 kV Switch | Add Permian Basin Reliability Plan Upgrade ID 765_Import_2A. Establish Bell County East 765/345 kV Switch |  | Bell County East | Bell County East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import2_A | 2030-12-02 |  | 765 | 0 | 0 | 2250 |  | Bell | Bell | Tier 1 |  |  |  |  | 3687, 3807, 3808, 3809 | Y |  |  |  | 99386 | 99385
102672B | BEPC_TIER3_MillerRPG |  |  | RW Miller | Fox | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2030-12-02 |  | 138 | 0 | 29.48 | 0 |  | Palo Pinto |  | Tier 3 | 26RPG002 | 2026-02-02 | 2026-03-17 |  | 331, 468, 482, 1595, 33312 | Y |  |  |  | 105027 | 102672
110270 | AEN_MC_DE_CKT909_Reconductor |  |  | 9076 | 9193 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinene 512-322-6740 |  | 2030-12-15 |  | 138 | 0 | 3.79 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9076, 9193 | Y |  |  |  | 110271 | 110270
110385 | AEN_DL_AU_CKT920_Reconductor |  |  | 9045 | 9328 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinene 512-322-6740 |  | 2030-12-15 |  | 138 | 0 | 3.73 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9045, 9328 | Y |  |  |  | 110386 | 110385
110340 | Add Temple Switch - Fryers Creek Switch 138 kV Line Ckt #2 | Add Temple Switch - Fryers Creek Switch 138 kV Line Ckt #2 |  | Temple | Fryers Creek | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6572 | 2030-12-15 |  | 138 | 0 | 4.5 | 0 |  | Bell | Bell | Tier 4 | [5 empty] | Y |  |  |  | 110341 | 110340
110336 | Upgrade Salado Switch - Puma 138 kV Line Section | Upgrade Salado Switch - Puma 138 kV Line Section |  | Salado | Puma | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6570 | 2030-12-15 |  | 138 | 0 | 10.4 | 0 |  | Bell | Bell | Tier 4 | [5 empty] | Y |  |  |  | 110337 | 110336
109904 | Rebuild the Lufkin Switch - Stryker Creek Switch 138 kV Line | Rebuild the Lufkin Switch - Stryker Creek Switch 138 kV Line |  | Lufkin Switch | Stryker Creek Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6040 | 2030-12-15 |  | 138 | 0 | 44.4 | 0 |  | Angelina | Cherokee | Tier 1 | [5 empty] | Y |  |  |  | 109905 | 109904
110168 | AEN_Holman_Hillje_ckt_3123_reconductor |  |  | 9073 | 44200 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinene 512-322-6740 |  | 2030-12-15 |  | 345 | 0 | 74.48 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9073, 44200 | Y |  |  |  | 110169 | 110168
86329 | AEN_PilotKnob_CarsonCreek_Ckt_944_RECONDUCTOR |  |  | 9175 | 9259 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2030-12-15 |  | 138 | 0 | 2.83 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9175, 9259 | Y |  |  |  | 86330 | 86329
81277 | Midland East – Midland County NW 345 kV Line Rebuild | Rebuild the existing 345 kV line and add a second circuit to the new line |  | Midland East | Midland County Northwest | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8729 | 2030-12-15 |  | 345 | 0 | 42.6 | 0 |  | Midland | Midland | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1021, 1185 | Y |  |  |  | 81278 | 81277
110032 | Rebuild the TNP One - Herndon/Gibson 345 kV DCKT Line | Rebuild the TNP One - Herndon/Gibson 345 kV DCKT Line |  | Herndon/Gibson | TNP One | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6540 | 2030-12-15 |  | 345 | 0 | 34.6 | 0 |  | Milam | Robertson | Tier 3 |  |  |  |  | 3704, 3706, 3765, 3804, 3805, 39950 | Y |  |  |  | 110033 | 110032
61224 | AEN_Decker_SH_ckt_1008__reconductor | Upgrade the 7.04 mile Decker to Sand Hill 138 kV transmission line (Ckt 1008) with bundled 795 ACSS Drake conductor rated for 3000 amps |  | Decker [9187] | Sandhill [9216] | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinene 512-322-6740 |  | 2030-12-15 |  | 138 | 0 | 7.04 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9187, 9216 | Y |  |  |  | 61225 | 61224
109900 | Rebuild Redland Switch - Kolb Lake Switch 138 kV Line | Rebuild Redland Switch - Kolb Lake Switch 138 kV Line |  | Redland Switch | Kolb Lake Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6509 | 2030-12-15 |  | 138 | 0 | 6.7 | 0 |  | Angelina | Angelina | Tier 1 | [5 empty] | Y |  |  |  | 109901 | 109900
105886 | East Watermill 765 kV Switch | Establish East Watermill 765 kV Switch |  | East Watermill 765 kV Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4477 | 2030-12-16 |  | 765 | 0 | 0 | 4500 |  | Dallas | Rusk | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-09 | 2427, 2432, 16101, 16102, 16105, 16106 | Y |  |  |  | 105887 | 105886
105888 | South Watermill 765 kV Switch | Establish South Watermill 765 kV Switch |  | South Watermill 765 kV Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4478, M4460, M4459 | 2030-12-17 |  | 765 | 0 | 0 | 2250 |  | Ellis |  | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-09 | 2217, 2249, 3159, 16100, 16103, 16104, 16120, 16121 | Y |  |  |  | 105889 | 105888
112326 | South Watermill - East Watermill 765 kV Line | Establish South Watermill - East Watermill 765 kV Line |  | South Watermill | East Watermill | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4478 | 2030-12-17 |  | 765 | 9.4 | 0 | 0 |  | Ellis |  | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-09 | 16100, 16105 | Y |  |  |  | 112327 | 112326
112324 | South Watermill - Dinosaur 765 kV Line | Establish South Watermill - Dinosaur 765 kV Line |  | South Watermill | Dinosaur | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4460 | 2030-12-17 |  | 765 | 77.8 | 0 | 0 |  | Ellis | Somervell | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-09 | 15207, 16100 | Y |  |  |  | 112325 | 112324
102068 | Construct a new 765kV Howard Rd Switching Station with two 765/345kV autotransformers connnection into the two new positions at Howard Rd 345kV station. Also construct the station with 4 line terminals to accommodate the full 765kV build out. The station w |  |  |  |  | Planned |  | CPS/AEP | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2030-12-30 |  | 765 | 185 | 0 | 0 |  |  |  | Tier 1 |  |  |  |  | 5228, 5229, 5231, 5232, 60214 | Y |  |  |  | 102069 | 102068
91578 | buffalo_clover_substation_addition | Adding buffalo Clover PEC bus to Brazos Anduin Bus. | [5 empty] | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2030-12-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 124, 70000 | Y |  |  |  | 91582 | 91578
110266 | LCP Hutto - Limmer Transmission Line Upgrade | Upgrade 345 kV DCKT line from Hutto to Limmer for a minimum of 1989 MVA rating. Project part of LCP effort for Batch Zero Base Load |  | Hutto | Limmer | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 345 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | [5 empty] | Y |  |  |  | 110267 | 110266
109918 | Smithville to Winchester Transmission Line Upgrade | Upgrade L_WINCHE8_1Y (Bus #7306) - L_SMITHV8_1Y (Bus #7314) 138.0-kV line as an LCP for Batch Zero Base Load. |  | Winchester | Smithville | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 14.53 | 0 |  | Bastrop | Fayette | Tier 4 | [5 empty] | Y |  |  |  | 109919 | 109918
110134 | Mason Creek - Pipe Creek Transmission Line Upgrade | Upgrade the 8.9-mile 138-kV Mason Creek - Pipe Creek circuit to achieve a 584 MVA minimum emergency rating. This is an LCP Upgrade project to support Batch Zero Base Load |  | Mason Creek | Pipe Creek | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 8.9 | 0 |  | Bandera | Bandera | Tier 4 | [5 empty] | Y |  |  |  | 110135 | 110134
110146 | Medina Lake - Pipe Creek Transmission Line Upgrade | Upgrade the BEC-owned 7.9-mile Medina Lake - Pipe Creek 138-kV circuit to a minimum 723 MVA emergency rating. This is an LCP Upgrade project to support Batch Zero Base Load. |  | Medina Lake | Pipe Creek | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 7.9 | 0 |  | Bandera | Bandera | Tier 4 | [5 empty] | Y |  |  |  | 110147 | 110146
110057D | This models upgrades required for a proposed load addition | Install 650 MVAR of static and dynamic VAR support at 345 kV NewSub. |  | NewSub |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2030-12-31 |  | 345 | 0 | 0 | 0 | 0,650 | Harris |  | Tier 4 | [5 empty] | N | N |  | Cost is included in phase A | 110626 | 110057
110699 | Upgrading two circuits to bundled Suwannee |  |  |  |  | Conceptual |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2030-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70490, 70493 | Y |  |  |  | 110700 | 110699
110661 | Upgrading two circuits to bundled Suwannee |  |  |  |  | Conceptual |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2030-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70488, 70490 | Y |  |  |  | 110662 | 110661
110539 | KC LCP upgrading circuit to bundled Suwanne | Upgrading line T329 as part of AD_HOC TPIT report. Project is purely conceptual as of 7/2/2026. |  |  |  | Conceptual |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2030-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70170, 70493 | Y |  |  |  | 110540 | 110539
109908 | Esperanza Bus Substation Upgrade | Upgrade terminal equipment at the Esperanza Substation to achieve a minimum 602 MVA emergency rating on the 9-mile Esparanza - Fair Oaks Ranch 138-kV circuit. This is an LCP Upgrade project to support Batch Zero Base Load. |  | Fair Oaks Ranch | Esperanza | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 9 | 0 |  | Bexar | Kendall | Tier 4 | [5 empty] | Y |  |  |  | 109909 | 109908
110073 | Alum Creek to Sim Gideon Transmission Line Upgrade | Upgrade L_SIMGID8_1Y (Bus #7310) - L_ALUMCR8_1Y (Bus #7318) 138.0-kV line as an LCP for Batch Zero Base Load. |  | Sim Gideon | Alum Creek | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 7.89 | 0 |  | Bastrop | Bastrop | Tier 4 | [5 empty] | Y |  |  |  | 110074 | 110073
110158 | Boerne Bus Substation Upgrade | Upgrade terminal equipment at the Boerne Substation to achieve a minimum 584 MVA emergency rating on the 3.9-mile Boerne - Esparanza 138-kV circuit. This is an LCP Upgrade project to support Batch Zero Base Load. |  | Boerne |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 | [5 empty] | Y |  |  |  | 110159 | 110158
110144 | Boerne - Welfare Transmission Line Upgrade | Upgrade the 9.5-mile Boerne - Welfare 138-kV circuit to achieve a minimum 539 MVA emergency rating. This is an LCP Upgrade project to support Batch Zero Base Load |  | Boerne | Welfare | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 9.5 | 0 |  | Kendall | Kendall | Tier 4 | [5 empty] | Y |  |  |  | 110145 | 110144
109902 | Bandera - Mason Creek Transmission Line Upgrade | Upgrade the 6.4-mile Bandera - Mason Creek 138-kV circuit to increase its operational capacity. This is an LCP Upgrade project to support Batch Zero Base Load. |  | Bandera | Mason Creek | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 6.4 | 0 |  | Bandera | Bandera | Tier 4 | [5 empty] | Y |  |  |  | 109903 | 109902
109914 | Gilleland Creek - McNeil Transmission line Upgrade | Upgrade L_MCNEIL8_1Y (Bus #7334) - L_GILLCR8_1Y (Bus #7336) 138.0-kV line as an LCP project for Batch Zero Base Load |  | Gilleland Creek | McNeil | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 7.63 | 0 |  | Travis | Travis | Tier 4 | [5 empty] | Y |  |  |  | 109915 | 109914
109866 | Utley Substation and Transmission Line Addition | Upgrade L_BIGSAN8_1Y (Bus #7316) - L_UTLEY_8_1Y (Bus #7317) 138.0-kV line as an LCP project for Batch Zero Base Load |  | Big Sandy | Utley | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 5 | 0 |  | Bastrop | Bastrop | Tier 4 | [5 empty] | Y |  |  |  | 109867 | 109866
109880 | Concho River Dynamic Reactive Substation Upgrade | Install 125 MVar Capacitor Bank and Concho Pearl DC load POI to resolve low voltages as an LCP project for Batch Zero Base Load |  | Concho River |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 0 | 0 | 0,125 | Concho |  | Tier 4 | [5 empty] | Y |  |  |  | 109881 | 109880
110276 | Bastrop Mesquite - Utley Transmission Line Upgrade | LCRA will upgrade the Utley (7317) to Bastrop Mesquite (7320) 138 kV transmission line to a 1148 minimum MVA rated circuit as part of the LCP effort for Batch Zero Base Load. |  | Utley | Bastrop Mesquite | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 5 | 0 |  | Bastrop | Bastrop | Tier 4 | [5 empty] | Y |  |  |  | 110277 | 110276
110128 | FPP Yard 2 - Lytton Springs Transmission Line Upgrade | Upgrade the FPP Yard 2 - Lytton Springs 345-kV circuit to achieve a 1351 MVA minimum emergency rating. This is an LCP Upgrade project to support Batch Zero Base Load. |  | Fayetteville Power Plant Yard 2 | Lytton Springs | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 345 | 0 | 61.1 | 0 |  | Fayette | Caldwell | Tier 4 | [5 empty] | Y |  |  |  | 110129 | 110128
110387 | Lon Hill to Grissom: Loop 345 kV into San Pedro | Loop in Lon Hill to Grissom 345 kV into 345 kV San Pedro Station | NEW | Lon Hill | Grissom | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2030-12-31 |  | 345 | 5.9 | 0 | 0 |  |  |  | Tier 1 | 25RPG016 |  |  |  |  | Y | N |  |  | 110388 | 110387
110142 | Alum Creek - Smithville Transmission Line Upgrade | LCRA will upgrade the Transmission Line between Alum Creek (7314) and Smithville (7318) to a minimum rating of 340 MVA. Upgrade project for Batch Zero Base Load |  | Smithville | Alum Creek | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 5.95 | 0 |  | Bastrop | Bastrop | Tier 4 | [5 empty] | Y |  |  |  | 110143 | 110142
109906 | Big Hill Dynamic Reactive Substation Upgrade | Add 500Mvar Cap bank at 345kV Big Hill substation as an LCP project for Batch Zero Base Load |  | Big Hill |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2030-12-31 |  | 345 | 0 | 0 | 0 | 0,500 | Schleicher |  | Tier 4 | [5 empty] | Y |  |  |  | 109907 | 109906
109796 | Gilleland Creek Statcom Substation Upgrade | Install 300 MVAR reactive support at Gilleland Creek 345-kV Substation as an LCP project for Batch Zero Base Load |  | Gilleland Creek |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 345 | 0 | 0 | 0 | 0,300 | Travis |  | Tier 4 | [5 empty] | Y |  |  |  | 109797 | 109796
110152 | Fair Oaks Bus Substation Upgrade | Upgrade terminal equipment at the Fair Oaks substation to achieve a 667 MVA minimum emergency rating on the 4.1-mile Bergheim - Fair Oaks 138-kV circuit. This is an LCP Upgrade project to support Batch Zero Base Load |  | Fair Oaks |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-12-31 |  | 138 | 0 | 0 | 0 |  | Kendall |  | Tier 4 | [5 empty] | Y |  |  |  | 110153 | 110152
103479 | Taft: Rebuild Distribution Station | Rebuild the Taft distribution station | NEW | Taft |  | Planned |  | AEP TCC | Armando Reyes deevans@aep.com 918-599-2938 | DP25X0014 | 2030-12-31 |  | 69 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8413, 8812, 8960, 80384 | Y | N |  |  | 103480 | 103479
102955 | Solstice to Sand Lake: Construct New 765 kV Single Circuit Line | Construct a new 765 kV single circuit line from Solstice to Sand Lake | Company Contact Update | Solstice | Sand Lake | Planned |  | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | TP2025846 | 2030-12-31 |  | 765 | 23.5 | 0 | 0 |  | Pecos | Reeves | Tier 1 | 25RPG022 | 2025-06-30 | 2025-07-28 | 2025-12-31 | 6137, 18736 | Y | N |  |  | 102956 | 102955 | temp
98955 | Duende: Construct New 765 kV Station | Install four 765 kV shunt reactors at the new Duende 765 kV station on the new Solstice to Howard 765 kV line | Project Number, RPG Number and BOD Review date Update | Duende |  | Planned |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 | TP2025795 | 2030-12-31 |  | 765 | 0 | 0 | 0 | -1200,0 | Edwards |  | Tier 4 | H.B. 5066 |  |  | 2024-10-31 | 6144, 60212, 60213, 60214 | Y |  |  |  | 98956 | 98955
99263 | Sand Lake 765/345 kV Autotransformer #2 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_2C. Add a second 765/345 kV autotransformer at Sand Lake |  | Sand Lake | Sand Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import2_C | 2030-12-31 |  | 765 | 0 | 0 | 2250 | -225,0 | Ward | Ward | Tier 1 |  |  |  |  | 18736, 18738, 18739 | Y |  |  |  | 99264 | 99263
99241 | Sand Lake 765/345 kV Autotransformer #1 | Add Permian Basin Reliability Plan Upgrade ID 765_Import_2C. Establish the Sand Lake 765/345 kV Switch with one 765/345 kV autotransformer |  | Sand Lake | Sand Lake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import2_C | 2030-12-31 |  | 765 | 0 | 0 | 2250 | -675,0 | Ward | Ward | Tier 1 |  |  |  |  | 11084, 11098, 18736, 18737, 18739, 18740 | Y |  |  |  | 99343 | 99241
100153 | Construct the Big Hill (LCRA TSC) - Bell County East 765 kV Line | Add Permian Basin Reliability Plan Upgrade ID 765_Import_2D. Add a new Bell East (ONCOR) – Big Hill (LCRA) 765-kV single-circuit line |  | Big Hill (LCRA TSC) | Bell County East | Planned |  | ONCOR/ONCOR, LCRA TSC | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import2_D | 2030-12-31 |  | 765 | 233.4 | 0 | 0 |  | Schleicher | Bell | Tier 1 |  |  |  |  | 3807, 76500 | Y |  |  |  | 100154 | 100153
100597 | Sand Lake - Big Hill (LCRA) 765 kV Line | Add Permian Basin Reliability Plan Upgrade ID 765_Import_2E. Add a new Big Hill – Sand Lake 765-kV single-circuit line |  | Sand Lake | Big Hill | Planned |  | ONCOR/LCRA TSC | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_765_Import2_E | 2030-12-31 |  | 765 | 211.2 | 0 | 0 |  | Ward | Schleicher | Tier 1 |  |  |  |  | 18736, 76500 | Y |  |  |  | 100598 | 100597
45015 | Barnhart to Cassava: Rebuild 69 kV line | Rebuild the Barnhart to Cassava 69 kV line | TSP/Company Contact Update | Barnhart | Cassava | Planned | 942 - 1120 | AEP TNC | Nathan Cowan myturner@aep.com 918-599-2437 | 2756 | 2030-12-31 01:00 |  | 69 | 0 | 6.021 | 0 |  | Irion | Irion | Tier 4 |  |  |  |  | 6530, 6532, 6537, 60359 | Y | N |  |  | 65525 | 45015
110189 | Upgrade Pawnee - San Miguel 138 | (5727) PAWNEE SWITCHING STATION to (5902) SAN MIGUEL GEN 138 kV Ckt 1 Rebuild [276 MVA Minimum] |  | Pawnee | San Miguel | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-12-31 12:15 |  | 138 | 0 | 27.1 | 0 |  | Karnes | Atascosa | Tier 4 | [5 empty] | N | N |  |  | 110190 | 110189
110228 | Upgrade Fowlerton to Los Angeles | (5705) FOWLERTON to (5723) LOS ANGELES 138 kV Ckt 1 Rebuild [245 MVA Minimum] or double circuit existing |  | Fowlerton | Los Angeles | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2030-12-31 12:15 |  | 138 | 0 | 16.4 | 0 |  | McMullen | La Salle | Tier 4 | [5 empty] | N | N |  |  | 110229 | 110228
104151 | North Edinburg to North McAllen: Rebuild 138 kV line | North Edinburg to North McAllen: Rebuild 138 kV line |  | North Edinburg | North McAllen | Planned |  | AEP TCC | Craig Tabor jlsolis@aep.com 361-881-5574 | TA2021190 | 2031-01-30 |  | 138 | 0 | 9.15 | 0 |  | Hidalgo | Hidalgo | Tier 2 |  |  |  |  | 8380, 8632 | Y |  |  |  | 104152 | 104151
87648 | Carver to Poblano: Convert 69 kV Line to 138 kV | Convert the Sonora to Uvalde 69 kV line to 138 kV and reterminate at Carver and Poblano | TSP/Company Contact and In-Service Date Update | Carver | Poblano | Planned |  | AEP TCC/AEP TNC, ETT | Greg Crane deevans@aep.com 918-599-2938 | TP2024058 | 2031-01-31 |  | 138 | 1 | 107.5 | 0 |  | Sutton | Uvalde | Tier 4 | 24RPG009 | 2024-03-21 | 2024-04-12 |  | 6513, 6570, 8009, 8230, 8231, 8238, 8365, 8633, 60039, 60119, 60120, 60121, 60210, 60412, 80073, 80074, 80075, 80081 | Y | Y |  |  | 87649 | 87648
110633 | New 138kV Kingsbridge Substation |  |  | 5246 | 5055, 5487 | Planned | S-XXXX | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-01-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5055, 5246, 5487 | Y |  |  |  | 110634 | 110633
105914 | Halcon: Construct New 345 kV Station | Interconnect the Falcon load to the new Halcon 345 kV station connected to the Ciruela 345 kV station on the Bonilla to Rio Hondo 345 kV line | All fields update | Halcon | Ciruela | Planned |  | AEP TCC | Robert Younger jlsolis@aep.com 361-881-5575 | TP2026109 | 2031-01-31 |  | 345 | 1 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8834, 80474, 80477, 80482, 80483 | Y |  |  |  | 105915 | 105914
110427 | San Angelo Red Creek: Upgrade Auto #1 | Upgrade SA Red Creek Auto #1 to 800 MVA Emergency Rating | NEW | SA Red Creek |  | Conceptual |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2031-02-28 |  | 345 | 0 | 0 | 800 |  | Tom Green |  | Tier 3 | [5 empty] | Y | N |  |  | 110428 | 110427
110687 | Rebuild Hill Country to Skyline Dbl Ckt |  |  | 5211 | 5371 | Conceptual |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-03-01 |  | 345 | 0 | 10.96 | 0 |  | Bexar | Bexar | Tier 1 |  |  |  |  | 5211, 7044 | N |  |  |  | 110688 | 110687
110689 | Rebuild Howard to AVR |  |  | 5231 | 5475 | Conceptual |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-03-01 |  | 345 | 0 | 12.62 | 0 |  | Bexar | Bexar | Tier 1 |  |  |  |  | 5231, 5475 | N |  |  |  | 110690 | 110689
110691 | Rebuild Hunt Lane to Medina Base |  |  | 5234 | 5305 | Conceptual |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-03-01 |  | 138 | 0 | 3.8 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5234, 5305 | N |  |  |  | 110692 | 110691
110693 | Rebuild Medina to Pearsal |  |  | 5305 | 5335 | Conceptual |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-03-01 |  | 138 | 0 | 3.1 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5305, 5335 | N |  |  |  | 110694 | 110693
110695 | Rebuild Talley to Medina |  |  | 5422 | 7432 | Conceptual |  | CPS/LCRA | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-03-01 |  | 138 | 0 | 12.36 | 0 |  | Medina | Bandera | Tier 4 |  |  |  |  | 5470, 7169 | N |  |  |  | 110696 | 110695
110663 | Rebuild Helotes to Ranchtown |  |  | 5200 | 5358 | Conceptual |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-03-01 |  | 138 | 0 | 6.6 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5200, 5358 | N |  |  |  | 110664 | 110663
110675 | Rebuild Hill Country to Marion Dbl Ckt |  |  | 5211 | 7044 | Conceptual |  | CPS/LCRA | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-03-01 |  | 345 | 0 | 26.6 | 0 |  | Bexar | Guadalupe | Tier 1 |  |  |  |  | 5211, 7044 | N |  |  |  | 110676 | 110675
110653 | Rebuild Fair Oaks to LCRA Fair Oaks |  |  | 5470 | 7169 | Conceptual |  | CPS/LCRA | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-03-01 |  | 138 | 0 | 4.7 | 0 |  | Bexar | Kendall | Tier 4 |  |  |  |  | 5470, 7169 | N |  |  |  | 110654 | 110653
110643 | Rebuild Chav to Palo Alto |  |  | 5085 | 5330 | Conceptual |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2031-03-01 |  | 138 | 0 | 3.53 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5085, 5330 | N |  |  |  | 110644 | 110643
110519 | Argyle Switch - Corinth 138 kV Line Section | Upgrade Argyle Switch - Corinth 138 kV Line Section |  |  |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5183 | 2031-03-01 |  | 138 | 0 | 2.9 | 0 |  | Denton | Denton | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 1984, 1985 | Y |  |  |  | 111642 | 110519 | 2024-NC72
110943C | Cooke County Resiliency Project | Rebuild the St Jo to Capps Corner transmission line Rebuild the Capps Corner to Nocona Transmission Line Rebuild the Nocona to Alcorn Transmission Line Construct a new transmission line from Bulcher to Alcorn |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2031-03-01 |  | 69 | 14.5 | 21.44 | 0 |  | Cooke | Cooke | Tier 2 | 26RPG007 | 2026-05-06 |  |  | 750, 754, 756, 758 | Y |  |  |  | 111225 | 110943
110485 | Benbrook 345/138 kV Autotransformer #1 | Upgrade Benbrook 345/138 kV Autotransformer #1 |  | Benbrook Switch | Benbrook Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5065 | 2031-04-01 |  | 345 | 0 | 0 | 0 |  | Tarrant |  | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 1869, 11876, 18741 | Y |  |  |  | 111610 | 110485 | 2024-NC79
110254 |  |  |  | San Miguel | Marion | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2031-04-07 |  | 345 | 0 | 68 | 0 |  | Atascosa | Comal | Tier 1 | 26RPG026 | 2026-06-26 |  |  | 3, 5133, 5901, 7044 | Y |  |  |  | 110255 | 110254 | 2025-SC20
110834 | Ad-Hoc TPIT: Arrow - System Upgrades | System upgrades to accommodate the full load at Sharyland's Arrow Load Serving station. Includes 345 kV line upgrades for Mantle - Bonilla | NEW | Kingfisher | Frontera | Conceptual |  | SLU | Charles Aleman caleman@huntutility.com 682-406-9656 |  | 2031-05-01 |  | 345 | 65 | 17.9 | 0 |  | Cameron | Hidalgo | Tier 1 |  |  |  |  | 8013, 8059, 8317, 8573, 8704, 79501, 79503, 80119 | N |  |  |  | 110835 | 110834
110836 | Ad-Hoc TPIT: Five Point Load Energization | Energization of a new load seeking interconnection at Sharyland's Kingfisher Station | NEW | Kingfisher |  | Conceptual |  | SLU | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2031-05-01 |  | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 79501 | N |  |  |  | 110837 | 110836
112229 | Adds Farias load serving substation |  |  | FARIAS |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-05-01 |  | 345 | 10.4 | 2.6 | 0 |  |  |  | Tier 1 | 25RPG016 | 2025-06-12 | 2026-05-27 |  | 5651, 8452, 8455, 8459, 80085, 80419, 84555 | Y | N |  |  | 112230 | 112229
110443 | STEC Nueces Green Ammonia Load Interconnection Project | -Construct a new Farias 345-kV substation cutting in on the existing Reforzar to Lon Hill 345-kV transmission line -Loop in the new Farias onto the existing Lon Hill to Grissom 345-kV transmission line using single-circuit structures, with normal and emergency ratings of at least 1059 MVA and 1195 MVA, respectively, which will require a new right of way (ROW), approximately 5.9 miles; -Construct a new Chalcedony to Nueces Load POI 345-kV transmission line on double-circuit capable structures with one circuit in place, with normal and emergency ratings of at least 2000 MVA, which will require a new ROW, approximately 4.5 miles -Rebuild the existing Lon Hill to Bunsen 138-kV transmission line on double-circuit capable structures with one circuit in place where not sharing a common tower, with normal and emergency ratings of at least 400 MVA, approximately 2.6 miles |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-05-01 12:15 |  | 345 | 10.4 | 2.6 | 0 |  |  |  | Tier 1 | 25RPG016 |  | 2026-03-19 |  |  | Y | N |  |  | 110444 | 110443
110876 | STEC Mesquite Large Load Project Phase 5 | Upgrade 5068 CACHENA - 5133 ELMCREEK 345-kV Line CKT 2 Upgrade 5068 CACHENA - 5323 OLD_HCKRY_5 345-kV Line CKT 2 Upgrade 5133 ELMCREEK - 5380 SHAULA 345-kV Line CKT 1 Upgrade 5915 SO_TEX__345A - 8676 STATIC7A 345-kV Line CKT 1 Upgrade 8012 PALADIO7A - 8606 GODDARD7A 345-kV Line CKT 1 Upgrade 8249 ANGSTRM7A - 8676 STATIC7A 345-kV Line CKT 1 Upgrade 8249 ANGSTRM7A - 8956 WHITEPT7A 345-kV Line CKT 1 Upgrade 8455 LONHILL7A - 8579 KATOEN7A 345-kV Line CKT 1 Upgrade 8579 KATOEN7A - 8606 GODDARD7A 345-kV Line CKT 1 Upgrade 8318 RIOHONDO7A - 8573 BONILLA7A 345-kV Line CKT 1 Construct a new 8318 RIOHONDO7A - 8383 NEDIN7A 345-kV Line on a separate structure. Construct a new 8317 LA PALMA – 79501 KINGFISHER 345-kV Line on a separate structure. Install a 3rd 345/138-kV autotransformer at Coleto Creek Substation. STEC Nueces Green Ammonia Load Interconnection RPG Project Upgrade 8012 PALADIO7A - 8689 TANGO7A 345-kV Line CKT 1 Upgrade 8455 LONHILL7A - 8956 WHITEPT7A 345-kV Line CKT 1 Upgrade 8624 GRISSOM7A - 8673 RAPTOR7A 345-kV Line CKT 1 Upgrade 5323 OLD_HCKRY_5 - 5915 SO_TEX__345A 345-kV Line CKT 2 Upgrade 7042 L_ZORN__5_1Y - 7051 L_MISTY_5_1Y 345-kV Line CKT 1 Upgrade 7042 L_ZORN__5_1Y - 7051 L_MISTY_5_1Y 345-kV Line CKT 2 Upgrade 5725 PAWNEESW5 - 8689 TANGO7A 345-kV Line CKT 2 Upgrade 8164 COLETO7A - 8673 RAPTOR7A 345-kV Line CKT 1 Rebuilding the existing Tango-Goddard-Kateon-Lon Hill 345-kV line to a double circuit |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-05-01 12:15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110877 | 110876
110843 | STEC Ouroboros Large Load Project Phase 2 | AEP Rio Grande Valley System Improvement Project (26RPG009) Construct a new 32-mile 345 kV line (NMRL/EMGY rating of 2400 MVA) from AEP’s Panther to STEC’s Tejon station |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-05-01 12:15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 | [5 empty] | Y | N |  |  | 110844 | 110843
110868 | STEC_110868_PalanganaLargeLoadProjectPhase4 | STEC Nueces Green Ammonia Load Interconnection RPG Project: Install reactive support at 8704 GULCH7A 345-kV Substation Rebuild Angstrom - White Point 345-kV Line Rebuild Katoen - Lon Hill 345-kV line Rebuild Goddard - Katoen 345-kV line Rebuild Grissom - Nueces Green Ammonia 345-kV line Rebuild Paladio - Goddard 345-kV line Rebuild Paladio - Tango 345-kV line Rebuild Coleto - Raptor - Grissom 345-kV lines Rebuilding the existing Tango-Goddard-Kateon-Lon Hill 345-kV line to a double circuit |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-05-01 12:15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y | N |  |  | 110869 | 110868
110170 | Rebuild Possum Trot - Lake Hall Switch - Tradinghouse Switch 345 kV Line | Rebuild Possum Trot - Lake Hall Switch - Tradinghouse Switch 345 kV Line |  | Possum Trot | Tradinghouse | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1717 | 2031-05-15 |  | 345 | 0 | 9.6 | 0 |  | McLennan | McLennan | Tier 1 | 25RPG043 |  |  |  | 3403, 3405, 3779, 3791 | Y |  |  |  | 110171 | 110170
110160 | Rebuild Possum Trot - St Johns Switch - Bale Switch - Stranger Switch 345 kV Line | Rebuild Possum Trot - St Johns Switch - Bale Switch - Stranger Switch 345 kV Line |  | Possum Trot | Stranger | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6429 | 2031-05-15 |  | 345 | 0 | 18.4 | 0 |  | McLennan | Limestone | Tier 1 | 25RPG043 |  |  |  | 3384, 3711, 3721, 3791 | Y |  |  |  | 110161 | 110160
109870 | Construct Elkton - Shamburger 345 kV DCKT Line | Construct Elkton - Shamburger 345 kV DCKT Line |  | Elkton | Shamburger | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6473 | 2031-05-15 |  | 345 | 27.5 | 0 | 0 |  | Smith | Smith | Tier 1 | 25RPG043 | 2025-11-12 | 2026-08-19 |  | 3103, 3105 | Y |  |  |  | 109871 | 109870
104710 | Construct the New Bell County East - Howard (CPS) 765 kV Line | Construct the New Bell County East - Howard (CPS) 765 kV Line |  | New Bell County East | Howard | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6448 | 2031-05-15 |  | 765 | 170.4 | 0 | 0 |  | Bell | Bexar | Tier 1 |  |  |  |  | 3807, 5232 | Y |  |  |  | 104711 | 104710
110346 | Rebuild Hartrick Switch - Crusader - Seaton 138 kV Line | Rebuild Hartrick Switch - Crusader - Seaton 138 kV Line |  | Hartrick Switch | Seaton | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6562 | 2031-05-15 |  | 138 | 0 | 17.8 | 0 |  | Bell | Bell | Tier 4 | [5 empty] | Y |  |  |  | 110347 | 110346
110040 | Rebuild Voss Lake Switch - Sandow Switch 345 kV Line | Rebuild Voss Lake Switch - Sandow Switch 345 kV Line |  | Voss Lake Switch | Sandow Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6564 | 2031-05-15 |  | 345 | 0 | 1.9 | 0 |  | Milam | Milam | Tier 3 | [5 empty] | Y |  |  |  | 110041 | 110040
110002 | Install Crockett Switch - Lufkin Switch 138 kV Line Ckt#2 | Install Crockett Switch - Lufkin Switch 138 kV Line Ckt#2 |  | Crockett Switch | Lufkin Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6555 | 2031-05-15 |  | 138 | 43 | 0 | 0 |  | Houston | Angelina | Tier 1 | [5 empty] | Y |  |  |  | 110003 | 110002
109864 | Establish Shamburger 345/138 kV Switch | Establish Shamburger 345/138 kV Switch |  | Shamburger | Shamburger | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6403 | 2031-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 1 | 25RPG043 | 2025-11-12 | 2026-08-19 |  |  | Y |  |  |  | 109865 | 109864
109868 | Establish Elkton 345-138 kV Switch | Establish Elkton 345-138 kV Switch |  | Elkton | Elkton | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6474 | 2031-05-15 |  | 345 | 0 | 0 | 600 |  | Smith | Smith | Tier 1 | 25RPG043 | 2025-11-12 | 2026-08-19 |  | 3105, 3106, 29150 | Y |  |  |  | 112629 | 109868
110429 | San Angelo Red Creek: Upgrade Auto #2 | Upgrade SA Red Creek Auto #2 to 800 MVA Emergency Rating | NEW | SA Red Creek |  | Conceptual |  | AEP TNC | Mina Turner myturner@aep.com 918-599-2437 |  | 2031-05-30 |  | 345 | 0 | 0 | 800 |  | Tom Green |  | Tier 3 | [5 empty] | Y | N |  |  | 110430 | 110429
109888 | Salem - Warda Transmission Line Overhaul | Upgrade 33-mile Salem to Round tap top to Warda 138kV lines to 478MVA as an LCP project for Batch Zero Base Load |  | Salem | Warda | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2031-05-31 |  | 138 | 0 | 33 | 0 |  | Washington | Fayette | Tier 4 | [5 empty] | Y |  |  |  | 109889 | 109888
64065 | Alice to Kingsville 138 kV Line Rebuild | Rehab the Alice to Kingsville 138 kV line | TSP/Company Contact Update | Alice | Kingsville | Conceptual |  | AEP TCC | Nathan Cowan deevans@aep.com 918-599-2938 | TA2021079 | 2031-05-31 |  | 138 | 0 | 22.48 | 0 |  | Jim Wells | Kleberg | Tier 4 |  |  |  |  | 8503, 8518 | Y |  |  |  | 66649 | 64065
71877 | CPSE_Cagnon to Shepherd Rebuild (Phase B) |  |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0281 | 2031-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5054, 5230, 5378, 5465 | Y |  |  |  | 71878 | 71877
110487 | Construct new Central Bluff - Oak Spring 345 kV Line | Construct new Central Bluff - Oak Spring 345 kV Line |  | Nolan County | Nolan County | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8906 | 2031-06-01 |  | 345 | 37.6 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y |  |  |  | 110488 | 110487
110483 | Three Creek Switch - Tri Corner Switch 345 kV Line | Upgrade Three Creek Switch - Tri Corner Switch 345 kV Line |  | Three Creek Switch | Tri Corner Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4520 | 2031-06-01 |  | 345 | 0 | 0 | 0 |  | Dallas | Kaufman | Tier 3 | [5 empty] | Y |  |  |  | 110484 | 110483
3595 | Bevo to AEP Carrizo Springs 69 kV line | Add 2 mile line by double circuiting two existing circuits, as recommended in 2013 RTP. |  | Bevo | Carrizo Springs | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 69 | 0 | 2 | 0 |  | Dimmit | Dimmit | Tier 1 |  | 2012-04-12 | 2012-08-12 | 2012-09-12 | 5871, 8244 | N | N |  | This new line was part of Karnes and Medina Electric Cooperatives Project that was approved in 2012. This also helped voltage on AEP transmission under contingencies. While much of the projected load is now on the system, not all of the projected load materialized. Studies with newer load projections have not shown the need for this line. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 10984 | 3595 | 2013-R104
73053B | Wimberley Loop to New Substation | Adds new 138 kV branch (219 MVA) from Wimberley to a new three terminal ring bus substation between Dripping Springs and Rutherford. |  | Wimberley | Cebolla Creek | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2031-06-01 |  | 138 | 13.44 | 0 | 0 |  | Hays | Hays | Tier 2 | 22RPG026 | 2022-08-29 | 2023-02-03 |  | 70496, 70511 | Y | N |  |  | 99289 | 73053
103826 | BRYN_MillicanSwitch_Rebuild | Rebuild Millican Switch to remove the 69-kV bus and transfer distribution load to the 138-kV bus. Remove Millican 69-kV Substation. |  | BTU Millican Switch | BTU Millican | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2031-06-01 |  | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 |  |  |  |  | 32855, 32856, 32889 | Y |  |  |  | 103827 | 103826
110294 | Bowman Switch - Garvey Road Switch 345 kV Line | Upgrade Bowman Switch - Garvey Road Switch 345 kV Line |  | Bowman Switch | Garvey Road Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3546 | 2031-06-01 |  | 345 | 0 | 29.18 | 0 |  | Archer | Young | Tier 3 |  |  |  |  | 1422, 17002 | Y |  |  |  | 110295 | 110294
109922 | Hackberry 345 kV Terminal Equipment | Upgrade Hackberry 345 kV Terminal Equipment |  | Hackberry Switch | Hackberry Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4476 | 2031-06-01 |  | 345 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 1 |  | 2025-11-18 | 2026-05-18 |  |  | Y |  |  |  | 109923 | 109922
105648 | LCRATSC_Euclid_Misty_Transmission_Line_Addition | This project will construct two (2) new 345-kV transmission lines between Euclid and Misty substations. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2031-06-30 |  | 345 | 4 | 0 | 0 |  | Caldwell | Caldwell | Tier 1 | 26RPG001 | 2026-01-27 | 2026-07-19 |  | 7045, 7051 | Y |  |  |  | 105649 | 105648
104732 | LCRATSC Euclid to Hillje (Morely) 765kV Transmission Line Addition | Construct a new 765-kV single-circuit transmission line from Euclid Substation to a point-of-interconnection (POI) with CenterPoint Energy (CNPE). |  | Euclid | Morely | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG |  | 2031-06-30 |  | 765 | 130.8 | 0 | 0 |  | Caldwell | Wharton | Tier 1 | 26RPG001 | 2026-01-27 | 2026-07-19 |  | 7650, 45200 | Y |  |  |  | 104733 | 104732
104118 | LCRATSC Euclid 765-kV Substation Addition | This project will construct a new Euclid 765-kV yard adjacent to the existing Euclid 345-kV Substation (PLC-7694) and install two new 765/345-kV autotransformers. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2031-06-30 |  | 765 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 1 | 26RPG001 | 2026-01-27 | 2026-07-19 |  | 3807, 5232, 7041, 7045, 7059, 7650 | Y |  |  |  | 105911 | 104118
110459 | STEC Amphion Load Project Phase3 | -RTP project 2024-CS1: Upgrade Cachena to Old Hickory ckt 2 to 1072MVA -RTP Project 2025-SC20: Upgrade Cachena to Elm Creek ckt 2 to 1965 MVA -RTP Project 2024-SC26: Upgrade Elm Creek to Shaula ckt 1 to 1746 MVA -Upgrade Pawnee to San Miguel 345 to 1810 MVA |  | Pawnee | San Miguel | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-30 12:15 |  | 345 | 0 | 175.87 | 0 |  | Karnes | Atascosa | Tier 2 | [5 empty] | Y | N |  |  | 110460 | 110459
110090C | This models upgrades required for a proposed load addition | Increase the size of the first 345 kV capacitor at NEWSUB bank from 200 MVAR to 300 MVAR. Add second 300MVAR capacitor bank. |  | NEWSUB | Jordan/King | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-07-01 |  | 345 | 0 | 0 | 0 | 0,400 | Harris | Harris | Tier 4 | [5 empty] | N | N |  | Cost included in main entry | 110258 | 110090
110943E | Cooke County Resiliency Project |  |  | Gainesville | Sivells Bend | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2031-09-01 |  | 138 | 0 | 7.3 | 0 |  | Cooke | Cooke | Tier 2 | 26RPG007 | 2026-05-06 |  |  | 716, 719, 721, 725, 726, 727, 735, 33726 | Y |  |  |  | 111464 | 110943
110943D | Cooke County Resiliency Project | Convert existing 69 kV line from Gainesville to St Jo to 138 kV operation including: Gainesville, (future) Bud Long, (future) Hinton, Red River, (future) Gateway, (future) Army Camp, Sivells Bend, (future) Bulcher, Capps Corner, Nocona, Alcorn and St Jo |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2031-09-01 |  | 138 | 0 | 0 | 0 |  | Cooke | Cooke | Tier 2 | 26RPG007 | 2026-05-06 |  |  | 711, 716, 725, 727, 746, 750, 754, 756, 758 | Y |  |  |  | 111237 | 110943
90330 |  |  |  | Red River | JSR1 | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2031-09-02 |  | 69 | 1.2 | 0 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 715, 719, 735 | Y |  |  |  | 90331 | 90330
109805 | Valley Switch - Progress Park Switch 138 kV Line | Upgrade Valley Switch - Progress Park Switch 138 kV Line |  | Valley Switch | Progress Park Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3322 | 2031-10-01 |  | 138 | 0 | 15.6 | 0 |  | Fannin | Grayson | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 1691, 1699, 12678 | Y |  |  |  | 111606 | 109805 | 2024-N07
110395 | Kaufman Northwest Switch - Seven Point 138 kV Line Section | Upgrade Kaufman Northwest Switch - Seven Point 138 kV Line Section |  | Seven Points Switch | Kaufman Northwest Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4450 | 2031-10-01 |  | 138 | 0 | 20.8 | 0 |  | Henderson | Kaufman | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 2724, 2726, 2728, 2774, 3264, 6901 | Y |  |  |  | 112121 | 110395 | 2024-NC53
109741 | Bergheim - Hil Country Transmission Line Addition | This project will install a new 345-kV single-circuit transmission line on double-circuit capable structures from Bergheim and CPS Hill Country substations. This project will require a CCN amendment and coordination with CPS Energy. The need for this project was identified by ERCOT in the EIR for RPG 25RPG017. Topology changes for this project will be submitted by CPS Energy. This PMCR submitted for cost-purposes |  | Bergheim | Hill Country | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2031-10-31 |  | 345 | 0 | 0 | 0 |  | Bexar | Comal | Tier 1 | 25RPG017 | 2025-06-06 | 2026-01-14 |  |  | Y |  |  |  | 109742 | 109741
109843 | Red Hill Switch - Rio Vista Tap 138 kV Line | Upgrade Red Hill Switch - Rio Vista Tap 138 kV Line |  | Red Hill Switch | Rio Vista Tap | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5198 | 2031-11-01 |  | 138 | 0 | 6.6 | 0 |  | Hill | Hill | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 3518, 3720, 37810 | Y |  |  |  | 111652 | 109843 | 2024-NC04
104502 | Rudeloff Substation Addition | Add new load serving substation north Seguin, near corner of Hwy 46 & Rudeloff rd, New 40 MVA PWT, station to be cut into GVEC T618 138 circuit. |  |  |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2031-11-21 |  | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7602, 7603, 7604 | Y |  |  |  | 104503 | 104502
67915 | Asherton to West Batesville: Rebuild 138 kV Line | Rehab Asherton to West Batesville 138 kV line |  | Asherton | West Batesville | Planned |  | AEP TCC/ETT | John Solis jlsolis@aep.com 361-881-5574 |  | 2031-11-30 |  | 138 | 0 | 36.09 | 0 |  | Dimmit | Zavala | Tier 4 |  |  |  |  | 8236, 8283, 8285 | Y |  |  |  | 67916 | 67915
57910 | Uvalde to West Batesville: Rebuild 138 kV Line | Rebuild the Uvalde to West Batesville 138 kV line |  | Uvalde | West Batesville | Planned | 1117 - 1295 | AEP TCC | Lance Price jlsolis@aep.com 361-881-5574 | 3836 | 2031-11-30 |  | 138 | 0 | 20.6 | 0 |  | Uvalde | Zavala | Tier 4 |  |  |  |  | 8234, 8236 | Y | N |  |  | 65580 | 57910
110838 | Ad Hoc TPIT: Expansion of Sharyland's Kingfisher 765 kV Station | Expansion of Sharyland's Kingfisher Station to accommodate 765 kV voltage levels and ties. Proposed alternative is in line with ERCOT's 2024 RTP STEP Plan | NEW | Kingfisher | Blu Lacy | Conceptual |  | SLU | Bradley Schwarz bschwarz@huntpower.com 512-289-7425 |  | 2031-12-01 |  | 765 | 134 | 0 | 6750 | -600,0 | Cameron | Nueces | Tier 1 | 26RPG009 | 2026-02-20 |  |  | 8766, 79501, 79511, 87004 | N |  |  |  | 110839 | 110838
110610 | Mitchell Bend Switch - Carmichael Bend Switch 345 kV Line Upgrade | Mitchell Bend Switch - Carmichael Bend Switch 345 kV Line Upgrade |  | Mitchell Bend | Carmichael Bend | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5377 | 2031-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 | [5 empty] | Y |  |  |  | 110611 | 110610
110629 | Venus Switch - Timberview Switch 345 kV Line Upgrade | Venus Switch - Timberview Switch 345 kV Line Upgrade |  | Venus Switch | Timberview Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5375 | 2031-12-01 |  | 345 | 0 | 0 | 0 |  | Ellis | Tarrant | Tier 3 | [5 empty] | Y |  |  |  | 110630 | 110629
110597 | Venus Switch - Britton Road 345 kV Line Section Upgrade | Venus Switch - Britton Road 345 kV Line Section Upgrade |  | Venus Switch | Britton Road | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5373 | 2031-12-01 |  | 345 | 0 | 0 | 0 |  | Ellis | Johnson | Tier 3 | [5 empty] | Y |  |  |  | 110598 | 110597
110118 | LCRATSC Gabriel Autotransformer Addition | This project will construct a 345-kV yard adjacent to the Gabriel 138-kV yard and install two (2) 345/138-kV autotransformers; the new 345-kV yard will cut in to a new Hutto - Gabriel - Salado 345-kV double-circuit transmission line. The need for this project with identified by ERCOT in the EIR for RPG 25RPG009. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2031-12-14 |  | 345 | 0 | 0 | 1344 |  | Williamson |  | Tier 1 |  | 2026-03-17 | 2026-05-08 |  | 7344, 7346, 73441, 73442 | Y |  |  |  | 110119 | 110118 | 25RPG009
110053 | Rebuild TradingHouse - Sam 345 kV DCKT Line | Rebuild TradingHouse - Sam 345 kV DCKT Line |  | Tradinghouse | Sam | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1706 | 2031-12-15 |  | 345 | 0 | 45.4 | 0 |  | McLennan | Hill | Tier 1 | 25RPG043 |  |  |  | 3379, 3388, 3405, 13405, 68090 | Y |  |  |  | 110054 | 110053 | 2024-NC32
109892 | Upgrade Killeen Switch - Salado Switch 345 kV Line Ckt #1 | Upgrade Killeen Switch - Salado Switch 345 kV Line Ckt #1 |  | Killeen | Salado | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6567 | 2031-12-15 |  | 345 | 0 | 15.7 | 0 |  | Bell | Bell | Tier 3 | [5 empty] | Y |  |  |  | 109893 | 109892
110122 | LCRATSC Gabriel Salado Transmission Line Addition | This project will construct a new 345-kV double-circuit transmission line between Gabriel and Oncor Salado substations. The need for this project with identified by ERCOT in the EIR for RPG 25RPG009. |  | Gabriel | Salado Switch | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2031-12-15 |  | 345 | 14.25 | 0 | 0 |  | Williamson | Bell | Tier 1 | 25RPG009 | 2025-03-17 | 2026-05-08 |  | 3699, 7344 | Y |  |  |  | 111202 | 110122
110120 | LCRATSC Gabriel Hutto Transmission Line Addition | This project will construct a new 345-kV double-circuit transmission line between Gabriel and Oncor Hutto substations. The need for this project with identified by ERCOT in the EIR for RPG 25RPG009. |  | Gabriel | Hutto | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2031-12-15 |  | 345 | 6.3 | 0 | 0 |  | Williamson | Williamson | Tier 1 | 25RPG009 | 2025-03-17 | 2026-05-08 |  | 3696, 7344 | Y |  |  |  | 111201 | 110120
110272 | Glidden Substation Upgrade | LCRA will upgrade Glidden Substation to support voltage conversion Upgrade project is part of the LCP effort and recommendation from CNP/CEHE for Batch Zero Base Load |  | Glidden |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2031-12-31 |  | 138 | 0 | 0 | 0 |  | Colorado |  | Tier 4 | [5 empty] | Y |  |  |  | 110273 | 110272
110223 | LST_Liberty_Area_Transmission_Projects_BZ_LLI | New double ckt 345 kV line connecting Oncor Trading House to LST Liberty Station. New single ckt 345 kV line connecting LST Liberty Station to LST Bullock Station. New 345 kV ckt from LST Bullock to LST Navarro Station in the existing structure. The new circuits will be rated 5000 Amps minimum. |  | Liberty | Trading House_Bullock_Navarro | Conceptual |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2031-12-31 |  | 345 | 90 | 0 | 0 |  | Hill | McLennan | Tier 1 |  |  |  |  | 3405, 13405, 68091, 68092, 68096 | N | N |  |  | 110224 | 110223
109910 | Bellville South - Peters Transmission Line Upgrade | Upgrade Bellville South – Peters Transmission Line to 4000A minimum (T217) as an LCP project for Batch Zero Base Load |  | Bellville South | Peters | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2031-12-31 |  | 138 | 0 | 8.7 | 0 |  | Austin | Austin | Tier 4 | [5 empty] | Y |  |  |  | 109911 | 109910
110225 | Bellville South Substation Upgrade Project | Bellville South Substation Upgrade (to support voltage conversion), requires coordination with CNP/CEHE. Upgrade Project for Batch Zero Base Load |  | Belville South |  | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@lcra.org 512-578-4514 |  | 2031-12-31 |  | 138 | 0 | 0 | 0 |  | Austin |  | Tier 4 | [5 empty] | Y |  |  |  | 110226 | 110225
109884 | Piney Creek - Winchester Transmission Line Addition | Add new Winchester to Piney Creek second circuit with 473MVA minimum rating as an LCP project for Batch Zero Base Load |  | Winchester | Piney Creek | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2031-12-31 |  | 138 | 1.6 | 0 | 0 |  | Fayette | Fayette | Tier 4 | [5 empty] | Y |  |  |  | 109885 | 109884
109912 | Bellville South - Glidden Transmission Line Upgrade | Upgrade Bellville South – Glidden Transmission Line to 4000A minimum (T113) as an LCP project for Batch Zero Base Load |  | Bellville South | Glidden | Conceptual |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2031-12-31 |  | 138 | 0 | 31 | 0 |  | Austin | Colorado | Tier 4 | [5 empty] | Y |  |  |  | 109913 | 109912
103797A | This models CEHE's Portion of the 765 kV STEP project | Install new Morley (MLY) 345kV CEHE substation in BAAH configuration. Loop Ckt.72H into Morley substation to create new Ckt.72 Hillje to Morley to Julia. |  | MORLEY | HILLJE/JULIA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-12-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 44200, 44220, 45210 | Y | N |  |  | 116024 | 103797
50898 | Alamito Creek to Paisano to Alpine: Rebuild 69 kV line | Rehab Alamito Creek to Paisano to Alpine 69 kV line | TSP/Company Contact Update | Alamito Creek | Alpine | Planned | 1045 - 1218 | AEP TNC | Brooks Dow myturner@aep.com 918-599-2437 | 2793 | 2031-12-31 |  | 69 | 0 | 22.26 | 0 |  | Presidio | Brewster | Tier 4 | 20RPG017 |  |  |  | 6666, 6667, 6672 | Y | N |  |  | 50899 | 50898
73001 | Truscott Humble Tap: Rebuild 69 kV Line | Rehab Truscott Humble Tap 69 kV line |  | Moorhouse | Truscott Humble | Planned |  | AEP TNC | Craig Tabor myturner@aep.com 918-599-2437 |  | 2031-12-31 |  | 69 | 0 | 13.92 | 0 |  | Knox | Knox | Tier 4 |  |  |  |  | 6080, 6082, 6084, 6085, 60023 | Y | N |  |  | 73002 | 73001
110088 | Bernardo Substation Upgrade | Upgrade terminal equipment at Bernardo (Bus #7654) to increase the operational rating of terminating 69.0-kV lines as an LCP Upgrade, identified by CNP/CEHE, for Batch Zero Base Load. |  | Bernardo |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2031-12-31 |  | 69 | 0 | 0 | 0 |  | Colorado |  | Tier 4 | [5 empty] | Y |  |  |  | 110089 | 110088
103797C | This models CEHE's Portion of the 765 kV STEP project | Install new Morley (MLY) 765kV CEHE substation. Install 765/345kV Autotransformer A1 with connection to Morley 345kV substation. |  | MORLEY |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-12-31 00:01 |  | 765 | 0 | 0 | 2250 |  | Wharton | Wharton | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 45200, 45210, 49401 | Y | N |  |  | 116025 | 103797
103797B | This models CEHE's Portion of the 765 kV STEP project | Install new Morley (MLY) 345kV CEHE substation in BAAH configuration. Loop Ckt.64E into Morley substation to create new Ckt.64 Hillje to Morley to Wolf. |  | MORLEY | HILLJE/WOLF | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-12-31 00:02 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 44200, 44990, 45210 | Y | N |  |  | 116026 | 103797
103797D | This models CEHE's Portion of the 765 kV STEP project | Install new Morley (MLY) 765kV CEHE substation. Install 765/345kV Autotransformer A2 with connection to Morley 345kV substation. |  | MORLEY |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-12-31 00:03 |  | 765 | 0 | 0 | 2250 |  | Wharton | Wharton | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 45200, 45210, 49402 | Y | N |  |  | 116027 | 103797
103797E | This models CEHE's Portion of the 765 kV STEP project | Install new Morley (MLY) 765kV CEHE substation. Install 765/345kV Autotransformer A3 with connection to Morley 345kV substation. |  | MORLEY | HILLJE/WOLF | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-12-31 00:04 |  | 765 | 0 | 0 | 2400 |  | Wharton | Wharton | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 45200, 45210, 49403 | Y | N |  |  | 116028 | 103797
103797F | This models CEHE's Portion of the 765 kV STEP project | Install new Morley (MLY) 345kV CEHE substation in BAAH configuration. Install 345kV Ckt.1 Hillje to Morley. Install 345kV Ckt.2 Hillje to Morley. |  | MORLEY | HILLJE/JULIA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-12-31 00:05 |  | 345 | 4 | 0 | 0 |  | Wharton | Wharton | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 44200, 45210 | Y | N |  |  | 116029 | 103797
103797G | This models CEHE's Portion of the 765 kV STEP project | Install 765kV line from CEHE's Morley substation to AEP Blu Lacy substation. |  | MORLEY | Blu Lacy | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-12-31 00:06 |  | 765 | 142.8 | 0 | 0 |  | Wharton | Nueces | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 8770, 45200 | Y | N |  |  | 116030 | 103797
103797I | This models CEHE's Portion of the 765 kV STEP project | Install new Morley (MLY) 765kV CEHE substation. Install and connect (1) 300 MVAr switchable bus reactors at Morley 765kV. |  | MORLEY |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2031-12-31 00:08 |  | 765 | 0 | 0 | 0 | -300,0 | Wharton |  | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 45200 | Y | N |  |  | 116031 | 103797
50647 | CPSE_Merida to Westside MLSE | Upgrade terminal at Merida to ensure a 2000 A rating. |  | Merida | Westside | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0773 | 2032-01-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5310, 5490 | Y |  |  |  | 50648 | 50647
103809 | Blu Lacy to Hillje: Construct New 765 kV Line | Construct a new 765 kV single circuit line from Blu Lacy to Howard | NEW | Blu Lacy | Hillje | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2025322 | 2032-01-30 |  | 765 | 72 | 0 | 0 |  | Nueces | Wharton | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 |  | Y | N |  |  | 103810 | 103809
102901 | Blu Lacy to Howard: Construct New 765 kV Line | Construct a new 765 kV single circuit line from Blu Lacy to Howard | In-Service Date Update | Blu Lacy | Howard | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2025322 | 2032-01-30 |  | 765 | 70 | 0 | 0 |  | Nueces | Bexar | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 5232, 8771 | Y | N |  |  | 102902 | 102901
102885 | Blu Lacy: Construct New 765/345 kV Station | Construct new 765/345 kV station on the Lon Hill to Reforzar and Lon Hill to Nelson Sharpe 345 kV lines | In-Service Date Update | Blu Lacy |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2025322 | 2032-01-30 |  | 765 | 2 | 0 | 8316 | -1200,0 | Nueces |  | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 8765, 8766, 8767, 8768, 8769, 8770, 8771, 80078, 80085, 84555, 85000 | Y | N |  |  | 102886 | 102885
109994 | Rebuild the existing Five_pts to Wstside 138-kV transmission line |  |  | 5150 | 5490 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2032-01-31 |  | 138 | 0 | 3.78 | 0 |  | Bexar | Bexar | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5150, 5490 | Y |  |  |  | 109995 | 109994
110478 | Construct a new Hill Country to Bergheim 345-kV transmission line | Construct a new Hill Country to Bergheim 345-kV transmission line on double-circuit structures with one circuit in place, with normal and emergency ratings of at least 1980 MVA, which will require a new right of way (ROW), approximately 14.28 miles |  | 5211 | 7770 | Planned |  | CPS/LCRA | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2032-01-31 |  | 345 | 14.28 | 0 | 0 |  | Bexar | Comal | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5211, 7770 | Y |  |  |  | 110479 | 110478
109992 | Rebuild Castle to Dresden 138kV Transmission Line |  |  | 5080 | 5130 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2032-01-31 |  | 138 | 0 | 3.79 | 0 |  | Bexar | Bexar | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5080, 5130 | Y |  |  |  | 109993 | 109992
109986 | Rebuild the existing Leon Creek to Palo Alto 138-kV transmission line |  |  | 5260 | 5330 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2032-01-31 |  | 138 | 0 | 3.64 | 0 |  | Bexar | Bexar | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5260, 5330 | Y |  |  |  | 109987 | 109986
109984 | Construct a new CPS Owned switchyard construction and gen tie to accommodate connection to the HUISACHE BESS & SOLAR generation site |  |  | 5241 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-XXXX | 2032-01-31 |  | 138 | 0 | 0 | 0 | 0,35.72 | Bexar |  | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5241 | Y |  |  |  | 109985 | 109984
109982 | Install a 50MVAr Capacitor Bank at Panther Springs Substation |  |  | 5331 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-XXXX | 2032-01-31 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5331 | Y |  |  |  | 109983 | 109982
109974 | Rebuild Cagnon to Potranco 138kV Transmission Line |  |  | 5055 | 5346 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2032-01-31 |  | 138 | 0 | 5.87 | 0 |  | Bexar | Bexar | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5055, 5346 | Y |  |  |  | 109975 | 109974
109956 | Rebuild Anderson to Helotes 138kV Transmission Line |  |  | 5003 | 5200 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2032-01-31 |  | 138 | 0 | 5.67 | 0 |  | Bexar | Bexar | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5003, 5200 | Y |  |  |  | 109957 | 109956
109940 | Rebuild the existing Medinabs to 36th Street 138-kV transmission line |  |  | 5305 | 5427 | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2032-01-31 |  | 138 | 0 | 8.57 | 0 |  | Bexar | Bexar | Tier 1 | 25RPG013 and 25RPG017 | 2025-05-27 | 2026-05-13 | 2026-06-01 | 5305, 5427 | Y |  |  |  | 109941 | 109940
100691 | Install a 50MVAr Capacitor Bank at Howard Substation |  |  | 5230 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2032-01-31 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 4 |  |  |  |  | 5230 | Y |  |  |  | 100692 | 100691
110306 | Argyle Switch - Krum Tap Switch 138 kV Line | Upgrade Argyle Switch - Krum Tap Switch 138 kV Line |  | Argyle Switch | Krum Tap Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3520 | 2032-04-01 |  | 138 | 0 | 8.54 | 0 |  | Denton | Denton | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 1984, 1986, 11986 | Y |  |  |  | 111607 | 110306 | 2024-NC40
110290 | Paris Switch - Valley South Switch 345 kV Line | Upgrade Paris Switch - Valley South Switch 345 kV Line |  | Paris Switch | Valley South Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3325 | 2032-04-01 |  | 345 | 0 | 46.3 | 0 |  | Fannin | Lamar | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 1692, 1729 | Y |  |  |  | 112123 | 110290 | 2024-NC31
102869 | Upgrade Calallen to Driscoll |  |  |  |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2032-05-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5626, 5634, 5636, 5640 | N | N |  |  | 102870 | 102869
76790 | Upgrade Pearsall Auto | Upgrade Pearsall Auto |  | Pearsall | Pearsall | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2032-05-01 |  | 138 | 0 | 0 | 0 |  | Frio | Frio | Tier 4 |  |  |  |  | 5893, 5895 | Y |  |  |  | 76791 | 76790
110278 | Gunter 345/138 kV Autotransformer #2 | Gunter 345/138 kV Autotransformer #2 |  | Gunter 345/138 kV Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3321 | 2032-05-01 |  | 345 | 0 | 0 | 0 |  | Collin |  | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 2235, 2236, 21730 | Y |  |  |  | 112120 | 110278 | 2024-NC76
105759 | Wilmer Switch – Navarro Switch (Lonestar) 345 kV Double-Circuit Line | Establish Wilmer Switch – Navarro Switch (Lonestar) 345 kV Double-Circuit Line |  | Wilmer Switch | Navarro Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4446 | 2032-05-15 |  | 345 | 106 | 0 | 0 |  | Dallas | Navarro | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 3085, 68091 | Y |  |  |  | 105760 | 105759 | 2024-NC63
105829A | Establish New Martin Lake 765/345 kV Switch | Establish New Martin Lake 765/345 kV Switch |  | New Martin Lake 765/345 kV Switch | New Martin Lake 765/345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6450, R6451 | 2032-05-15 |  | 765 | 0 | 0 | 2250 |  | Rusk | Rusk | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-09 | 3100, 3102, 3103, 3109, 3116, 3339, 3852, 3858, 3859, 3860 | Y |  |  |  | 105830 | 105829
105744 | Desoto Switch – Sam Switch Switch (Lonestar) 345 kV Double-Circuit Line | Establish Desoto Switch – Sam Switch Switch (Lonestar) 345 kV Double-Circuit Line |  | Desoto Switch | Sam Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4448 | 2032-05-15 |  | 345 | 56 | 0 | 0 |  | Hill | Dallas | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2431, 68090 | Y |  |  |  | 105745 | 105744 | 2024-NC63
105747 | Farmersville Switch – Saltillo Switch 345kV Line | Upgrade Farmersville Switch – Saltillo Switch 345kV Line |  | Farmersville Switch | Saltillo Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3314 | 2032-05-15 |  | 345 | 0 | 59.9 | 0 |  | Collin | Hunt | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 1685, 11700 | Y |  |  |  | 105748 | 105747 | 2024-NC31
105751 | Navarro Switch - Pin Oak Switch 345 kV DCKT Line Upgrade | Navarro Switch - Pin Oak Switch 345 kV DCKT Line Upgrade |  | Navarro | Pin Oak | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6428 | 2032-05-15 |  | 345 | 0 | 62.2 | 0 |  | Navarro | Freestone | Tier 1 | 25RPG038 | 2025-02-06 | 2026-03-19 |  | 3308, 3344, 68091 | Y |  |  |  | 105752 | 105751 | 2024-NC42
105753 | Navarro Switch - Outlaw Switch 345kV Line | Navarro Switch - Outlaw Switch 345kV Line |  | Navarro Switch | Outlaw Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | R6427 | 2032-05-15 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 3386, 68091 | Y |  |  |  | 105754 | 105753 | 2024-NC55
105755 | Trinidad Switch – Tri Corner 345 kV Double-Circuit Line | Upgrade Trinidad Switch – Tri Corner 345 kV Double-Circuit Line |  | Trinidad Switch | Tri Corner Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4045 | 2032-05-15 |  | 345 | 0 | 80.8 | 0 |  | Dallas | Henderson | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2432, 3123, 3124 | Y |  |  |  | 105756 | 105755 | 2024-NC11
105757 | Watermill Switch - Tri Corner Switch 345 kV Double-Circuit Line | Upgrade Watermill Switch - Tri Corner Switch 345 kV Double-Circuit Line |  | Watermill Switch | Tri Corner Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4442 | 2032-05-15 |  | 345 | 0 | 16.8 | 0 |  | Dallas | Dallas | Tier 1 | 25RPG004 | 2025-02-06 | 2026-03-19 |  | 2427, 2432, 16106 | Y |  |  |  | 112584 | 105757 | 2024-NC11
116019A | Install new midpoint 765kV CEHE substation into line from Morley to Martin Lake. Install and connect (2) 300 MVAr switchable line reactors and 2-225MVAR bus reactors. | Install new midpoint 765kV CEHE substation into line from Morley to Martin Lake. Install and connect (1) 300 MVAr switchable line reactors and 2-225MVAR bus reactors. |  | CEHE_NewSub | Morley | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2032-05-16 |  | 765 | 0 | 0 | 0 | -750,0 | Grimes | Wharton | Tier 4 |  |  |  |  | 3852, 45200, 45250 | Y | N |  |  | 116022 | 116019
105829B | Establish New Martin Lake 765/345 kV Switch | Install Martin Lake 765 kV Reactor |  | New Martin Lake 765 kV Switch | New Martin Lake 765 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6450, R6451 | 2032-05-16 |  | 765 | 0 | 0 | 0 | -300,0 | Rusk | Rusk | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-09 | 3852 | Y |  |  |  | 105832 | 105829
116019B | Install new midpoint 765kV CEHE substation into line from Morley to Martin Lake. Install and connect (2) 300 MVAr switchable line reactors and 2-225MVAR bus reactors. | Install new midpoint 765kV CEHE substation into line from Morley to Martin Lake. Install and connect (1) 300 MVAr switchable line reactors. |  | CEHE_NewSub | Martin Lake | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2032-05-16 00:01 |  | 765 | 0 | 0 | 0 | -300,0 | Grimes | Rusk | Tier 4 |  |  |  |  | 3852, 45250 | Y | N |  | Cost included in main entry | 116023 | 116019
103797H | This models CEHE's Portion of the 765 kV STEP project | Install 765kV line from CEHE's Morley substation to Oncor's Martin Lake substation. |  | MORLEY | Martin Lake | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2032-05-16 00:01 |  | 765 | 0 | 292.8 | 0 | -300,0 | Wharton | Rusk | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 3852, 45200 | Y | N |  |  | 116032 | 103797
103797J | This models CEHE's Portion of the 765 kV STEP project | Install new Morley (MLY) 765kV CEHE substation. Install and connect (2) 300 MVAr switchable line reactors at Morley 765kV. |  | Morley |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2032-05-16 00:02 |  | 765 | 0 | 0 | 0 | -600,0 | Grimes | Wharton | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-31 | 45200 | Y | N |  | Cost included in Main Entry | 116033 | 103797
110534 | Benbrook - Carmichael Bend 345 kV Line | Benbrook - Carmichael Bend 345 kV Line Upgrade |  | Benbrook Switch | Carmichael Bend Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5034 | 2032-06-01 |  | 345 | 0 |  | 0 |  | Tarrant | Hood | Tier 3 |  | 2025-11-18 | 2026-05-18 |  |  | Y |  |  |  | 110535 | 110534
110593 | Stoplight Switch (fka Bluff Creek) - Willow Valley Switch 138 kV Line | Rebuild the existing 19.9-mile Stoplight Switch (fka Bluff Creek) - Willow Valley Switch 138 kV Line |  | Stoplight Switch (fka Bluff Creek) | Willow Valley Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com | R8840 | 2032-06-01 |  | 138 | 0 | 0 | 0 |  | Scurry | Borden | Tier 4 | [5 empty] | Y |  |  |  | 110605 | 110593
110298 | Graham Plant Switch - Rice Switch 138 kV Line | Upgrade Graham Plant Switch - Rice Switch 138 kV Line |  | Graham Plant Switch | Rice Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3547 | 2032-06-01 |  | 138 | 0 | 9.3 | 0 |  | Young | Young | Tier 3 |  |  |  |  | 1431, 1477 | Y |  |  |  | 110299 | 110298
110679 | Cedar Hill Switch - Sherry Switch 138 kV Double-Circuit Line | Upgrade Cedar Hill Switch - Sherry Switch 138 kV Double-Circuit Line |  | Cedar Hill Switch | Sherry Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5246 | 2032-06-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 1919, 1920, 2257, 2258, 2259, 2260, 2262, 2264, 2421, 2422, 2491, 12491, 12492, 16262 | Y |  |  |  | 112422 | 110679
112322 | South Watermill - Bell East 765 kV Line | Establish South Watermill - Bell East 765 kV Line |  | South Watermill | Bell East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4458 | 2032-06-17 |  | 765 | 127.3 | 0 | 0 |  | Ellis | Bell | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-09 | 3807, 16100 | Y |  |  |  | 112323 | 112322
14TPIT0098 | Cost Substation Addition | Upgrade the existing 69-kV substation |  | Cost |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2032-10-29 |  | 69 | 0 | 0 | 0 |  | Gonzales |  | Tier 4 |  |  |  |  | 7622 | Y | N |  |  | 78325 | 3321
110248 | Argyle Switch - Highlands 138 kV Line and Argyle Switch Rebuild | Argyle Switch - Highlands 138 kV Line and Argyle Switch Rebuild |  | Argyle 138 kV Switch | Highlands | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3201 | 2032-12-01 |  | 138 | 0 | 7.5 | 0 |  | Denton | Denton | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 1974, 1984 | Y |  |  |  | 111638 | 110248 | 2024-NC72
3334 | Fort Sam to Kirby and Fort Sam to Tenth Street MLSE Upgrade | Upgrade entire bus and terminals at Fort Sam and ensure a rating of 2000 A. |  | Fort Sam | Kirby/Tenth Street | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0744 | 2032-12-01 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5160, 5250, 5420 | Y | N |  | There are no transformers associated with this project | 10692 | 3334
110620 | Benbrook Switch - Parker Switch 345 kV Line Upgrade | Benbrook Switch - Parker Switch 345 kV Line Upgrade |  | Benbrook Switch | Parker Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M5376 | 2032-12-01 |  | 345 | 0 | 0 | 0 |  | Tarrant | Johnson | Tier 3 | [5 empty] | Y |  |  |  | 110621 | 110620
110627 | Paint Creek Switch - Murray Switch 138 kV Line | Rebuild Paint Creek Switch - Murray Switch 138 kV Line |  | Paint Creek Switch | Murray Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | R8938 | 2032-12-01 |  | 138 | 0 | 0 | 0 |  | Haskell | Young | Tier 3 | [5 empty] | Y |  |  |  | 110628 | 110627
110238 | Construct new Alibates - Gray 345 kV Line | Construct new Alibates - Gray 345 kV Line |  |  |  | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8989 | 2032-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 2 | [5 empty] | Y |  |  |  | 110538 | 110238
110318 | Wichita Falls South Switch - Windthorst Switch 138 kV Line | Upgrade Wichita Falls South Switch - Windthorst Switch 138 kV Line |  | Wichita Falls South Switch | Windthorst Switch | Conceptual |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3548 | 2032-12-01 |  | 138 | 0 | 17.68 | 0 |  | Archer | Archer | Tier 3 |  |  |  |  | 1464, 1474, 1475 | Y |  |  |  | 110319 | 110318
110042 | Rebuild Comanche Switch - Comanche Peak Switch 345 kV Line | Rebuild Comanche Switch - Comanche Peak Switch 345 kV Line |  | Comanche Switch | Comanche Peak Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6565 | 2032-12-15 |  | 345 | 0 | 0 | 0 |  | Somervell | Comanche | Tier 3 | [5 empty] | Y |  |  |  | 110043 | 110042
110328 | Rebuild Comanche Switch - Hasse POI 138 kV Line | Rebuild Comanche Switch - Hasse POI 138 kV Line |  | Comanche Switch | Hasse POI | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6149 | 2032-12-15 |  | 138 | 0 | 10.3 | 0 |  | Comanche | Comanche | Tier 4 | [5 empty] | Y |  |  |  | 110329 | 110328
110332 | Rebuild Bell County East Switch - Bob White Switch - Temple Switch 345 kV Double Circuit Line | Rebuild Bell County East Switch - Bob White Switch - Temple Switch 345 kV Double Circuit Line |  | Bell County East | Temple | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6568 | 2032-12-15 |  | 345 | 0 | 5.9 | 0 |  | Bell | Bell | Tier 3 | [5 empty] | Y |  |  |  | 110333 | 110332
112226 | East Watermill - Martin Lake 765 kV Line | Establish East Watermill - Martin Lake 765 kV Line |  | East Watermill 765 kV Switch | Martin Lake 765 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4458 | 2032-12-16 |  | 765 | 145.7 | 0 | 4500 |  | Dallas | Rusk | Tier 1 | 25RPG025 | 2025-07-11 | 2025-11-12 | 2025-12-09 | 3852, 16105 | Y |  |  |  | 112227 | 112226
110104 | Kendall - Horse Hollow Gen Tie Transmission Loop Addition | Add a Horse Hollow Gen Tie to Kerr Data Center to Kendall 345-kV transmission loop as an LCP Upgrade to support Batch Zero Base Load. |  | Kendall | Omega | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2032-12-31 |  | 345 | 0 | 0 | 0 |  | Kendall | Kendall | Tier 4 | [5 empty] | Y |  |  |  | 110105 | 110104
65663 | Double Ckt Line M138-K | Project Delayed Indefinitely. |  | Pecos (bus # 38091) | Faulkner (bus # 38124) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2032-12-31 |  | 138 | 0 | 26.2 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38091, 38124 | N |  |  |  | 65664 | 65663
12TPIT0004 | Sulpher Springs - New 138kV Substation | Loop new 138kV substation into the existing 138kV OW Sommers to Kirby line |  | Sulpher Springs | OW Sommers-Kirby | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0385 | 2033-01-31 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5136, 5395, 5416 | Y | N |  | There are no transformers associated with this project | 10365 | 3021
110292 | New 138kV Rogers Rd Substation |  |  | 5361 | 5003, 5488 | Planned | S-XXXX | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-XXXX | 2033-01-31 |  | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5003, 5361, 5488 | Y |  |  |  | 110293 | 110292
110284 | Anna 345 kV Switch Rebuild and Anna Switch - Valley Switch 345 kV Line | Upgrade Anna Switch - Valley Switch 345 kV Line and Anna 345 kV switch Rebuild |  | Anna 345 kV Switch | Valley 345 kV Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3324 | 2033-03-01 |  | 345 | 0 | 26.6 | 0 |  | Collin | Fannin | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 |  | 1690, 2373 | Y |  |  |  | 112122 | 110284 | 2024-NC31
109824 | Monticello Switch - Allen Switch 345 kV Double-Circuit Line | Upgrade Monticello Switch - Allen Switch 345 kV Double-Circuit Line |  | Monticello Switch | Allen Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3317 | 2033-05-15 |  | 345 | 0 | 143.2 | 0 |  | Collin | Titus | Tier 1 | 25RPG040, 25RPG042 | 2025-11-18 | 2026-05-18 |  | 1695, 1696, 1697, 2256, 2461, 2464, 2513, 2514, 2621, 12464 | Y |  |  |  | 112112 | 109824 | 2024-E9
110381 | Jewett Switch - Greene Switch 345 kV Double-Circuit Line | Establish Jewett Switch - Greene Switch 345 kV Double-Circuit Line |  | Greene Switch | Jewett Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4428 | 2033-05-15 |  | 345 | 112.5 | 0 | 0 |  | Dallas | Leon | Tier 1 | 25RPG042 | 2025-11-18 | 2026-05-18 |  | 3063, 3390, 3391 | Y |  |  |  | 111648 | 110381 | 2024-NC63
110647 | Paris Switch - Valley Switch 138 kV Line | Paris Switch - Valley Switch 138 kV Line Upgrade |  | Paris Switch | Valley Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3323 | 2033-05-15 |  | 138 | 0 | 46.1 | 0 |  | Fannin | Grayson | Tier 1 | 25RPG040 | 2025-11-18 | 2026-05-18 | 2026-06-06 | 1513, 1593, 1691, 1776, 1833, 1835 | Y |  |  |  | 112124 | 110647 | 2024-NC31
110344 | Rebuild Hutto Switch - Salado Switch 345 kV DKCT Line | Rebuild Hutto Switch - Salado Switch 345 kV DKCT Line |  | Hutto Switch | Salado Switch | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6529 | 2033-05-15 |  | 345 | 0 | 36.9 | 0 |  | Williamson | Bell | Tier 3 | [5 empty] | Y |  |  |  | 110345 | 110344
45068 | Merida to Harlandale Rebuild | CPSE_Merida to Harlandale Rebuild |  |  |  | Planned |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0233 | 2033-05-31 |  | 138 | 0 | 10 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5190, 5310, 5385, 5395 | Y |  |  |  | 45069 | 45068
86327 | AEN_New_138kV_Southshore_Substation_Addition |  |  | 9179 | 9132 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2033-06-01 |  | 138 | 0.2 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9132, 9134, 9179 | Y |  |  |  | 86328 | 86327
86323 | AEN_MagnesiumPlant_Northland_Ckt_979_RECONDUCTOR |  |  | 9128 | 9238 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2033-06-01 |  | 138 | 0 | 4.11 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9238 | Y | N |  |  | 86324 | 86323
86321 | AEN_Lakeshore_Northland_Ckt_916_Reconductor |  |  | 9128 | 9228 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2033-06-01 |  | 138 | 0 | 4.41 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9128, 9228 | Y |  |  |  | 86322 | 86321
86331 | AEN_Wheless_Mueller_Ckt_1016_Reconductor |  |  | 9291 | 9342 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2033-06-01 |  | 138 | 0 | 2.13 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9291, 9342 | Y |  |  |  | 86332 | 86331
70889 | SA College Hills: Rebuild 69 kV Station | Rehab the SA College Hills 69 kV station |  | SA College Hills |  | Planned |  | AEP TNC | Ali Barkat myturner@aep.com |  | 2033-07-31 |  | 69 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6468, 6470 | Y |  |  |  | 70890 | 70889
110334 | Rebuild Austrop Substation (LCRA TSC) - Walleye Creek Switch 345 kV Double Circuit Line | Rebuild Austrop Substation (LCRA TSC) - Walleye Creek Switch 345 kV Double Circuit Line |  | Walleye Creek | Austrop (LCRA TSC) | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6569 | 2033-12-15 |  | 345 | 0 | 33.4 | 0 |  | Milam | Travis | Tier 3 | [5 empty] | Y |  |  |  | 110335 | 110334

## PlannedTPIT100126NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2026
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
99746 | 16th Street auto transformer replacement/addition. |  |  |  |  | In-Service |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-04-23 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38310, 38320 | Y |  |  |  | 99747 | 99746
90446 | Avila BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 88914 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-01 |  | 138 | 0.22 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38340, 136502 | Y |  |  |  | 90447 | 90446
99776 | Replacement of Lake Whitney auto transformer. |  |  |  |  | In-Service |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37410, 37420 | Y |  |  |  | 99777 | 99776
90393 | Evelyn BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 86784 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-06 |  | 138 | 0.23 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 114262 | Y |  |  |  | 90443 | 90393
93348 | Adds Cochise Customer Sub |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-30 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38160, 38190 | Y |  |  |  | 93349 | 93348
87889 | Install 2x 40 MVAR Cap bank at League City. |  |  | League City (38920) |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 | 0,80 | Galveston | Galveston | Tier 4 |  |  |  |  | 38920 | Y |  |  |  | 87890 | 87889
82321 | PMCR for 2nd TX in Coachwhip | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38170 | Y |  |  |  | 82322 | 82321
90450 | Headcamp BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 85045 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-06-16 |  | 138 | 0.1 | 0 | 0 |  | Pecos | Pecos | Tier 4 |  |  |  |  | 38465, 136432 | Y |  |  |  | 90451 | 90450
93003 | Adds TNMP Turkeyfoot 69kV Substation |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-07-01 |  | 69 | 0 | 0 | 0 |  | Bosque | Coryell | Tier 4 |  |  |  |  | 37470, 37515, 37520 | Y |  |  |  | 93183 | 93003
100408 | Add Cochise customer sub. |  |  |  |  | In-Service |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-07-02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38160, 38190 | Y |  |  |  | 100409 | 100408
99926 | Addition of Wolfcamp substation | The addition of Wolfcamp substation, load, and transmission line. |  |  |  | In-Service |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-07-02 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38113, 38115 | Y |  |  |  | 99927 | 99926
90448 | Bocanova BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 89822 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-07-19 |  | 138 | 0.1 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39030, 114342 | Y |  |  |  | 90449 | 90448
93681 | New Transformer will be added Loma Alta. |  |  | Loma Alta | Loma Alta | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2025-07-24 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5943, 5962 | Y |  |  |  | 93682 | 93681
87479E | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Jeanetta to WA Parish Ckt.64A to increase thermal limits as part of FRM upgrades |  | Jeanetta | WAP | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47300 | Y | N |  |  | 87825 | 87479
87479G | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Hyde Park to Downtown Ckt.32A to increase thermal limits as part of FRM upgrades |  | Hyde Park | Downtown | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47510, 47690 | Y | N |  |  | 87823 | 87479
87479F | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Bellaire to Jeanetta Ckt.64B to increase thermal limits as part of FRM upgrades |  | Bellaire | Jeanetta | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47000, 47300 | Y | N |  |  | 87822 | 87479
87479I | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Hyde Park to Downtown Ckt.32A to increase thermal limits as part of FRM upgrades |  | Kirby | Garrott | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47321, 47660 | Y | N |  |  | 87821 | 87479
87479D | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits as part of FRM upgrades |  | Bellaire | WAP | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47000 | Y | N |  |  | 87820 | 87479
87479C | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Ckt.06D NASA to Webster to increase thermal limits as part of FRM upgrades |  | NASA | Webster | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42970, 43500 | Y | N |  |  | 87819 | 87479
87479A | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits as part of FRM upgrades |  | PSARCO | BIGVUE | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40190, 41305 | Y | N |  |  | 87817 | 87479
87479B | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Ckt.99A PH Robinson to Meadow to increase thermal limits as part of FRM upgrades |  | PH Robinson | Meadow | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 345 | 0 | 0 | 0 |  | Galveston | Brazoria | Tier 4 | [5 empty] | Y | N |  |  | 87818 | 87479
87479H | Upgrade to increase thermal limits as part of FRM upgrades | Upgrade Stadium to Fannin Ckt.08B to increase thermal limits as part of FRM upgrades |  | Stadium | Fannin | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 87824 | 87479
90232I | Facility Ratings Methodology (FRM) Upgrades | Upgrade Hyde Park to Downtown Ckt.32A to increase thermal limits as part of FRM upgrades |  | Hyde Park | Downtown | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 102820 | 90232
90730 | TNMP Willow 345kV Switching Station |  |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-08-15 |  | 345 | 0 | 0 | 0 |  | Robertson | Robertson | Tier 4 |  |  |  |  | 1624, 3400, 6310, 39950, 39960, 121035 | Y |  |  |  | 98761 | 90730
99956 | Addition of Harrell Ranch substation | Model of Harrell Ranch substation, load, and lines. |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-09-04 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38420, 38433, 38440 | Y |  |  |  | 99957 | 99956
99859 | Addition of the Mainland to Vertus 138KV line. |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-09-04 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38830, 114512 | Y |  |  |  | 99860 | 99859
91494 |  |  |  | Perry | Perry | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-10-01 |  | 69 | 0 | 0 | 100 |  | Falls | Falls | Tier 4 |  |  |  |  | 91, 92 | Y |  |  |  | 91495 | 91494
99546 | Establish Richland Chambers Generator Tie Line |  |  | Richland Chambers 345 kV Switch | Generator | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6361 | 2025-10-30 |  | 345 | 0.1 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3134, 121123 | Y |  |  |  | 99547 | 99546
93657 | Adds Monarch Gen Tie Switching Station |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-01 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 37513, 37515, 37520, 155222 | Y |  |  |  | 98573 | 93657
87510 | RCEC_BranchChanges_Kaufman_Update3 | Modifying branch impedance between I20_RC and TALTY_RC |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6902 | Y |  |  |  | 87511 | 87510
87475 | RCEC_Add_CavenderBus | Adding Cavender Bus, Load and Branch from Cavender to Cavender_P8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2145, 6861 | Y |  |  |  | 87476 | 87475
104036 | Models Pilot Point |  |  |  |  | In-Service |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-03 |  | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 12236, 37365 | Y |  |  |  | 104037 | 104036
82250 | Adds an additional line and energize load. | Adds a bundled double circuit line and energize both loads at Pilot Point bus #37365. |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2236, 37365 | Y |  |  |  | 99695 | 82250
113226 | Fixes Islanded Pilot Point and energize load. | Adding two transmission lines from Pilot Point to Gunter Switch. |  |  |  | In-Service |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-12-03 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2236, 37365 | Y |  |  |  | 113227 | 113226
66492A | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Jacksboro Amoco - Jacksboro Sinclair 69 kV Line |  | Jacksboro Sinclair | Jacksboro Amoco | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M3006 | 2025-12-15 |  | 69 | 0 | 14 | 0 |  | Jack | Jack | Tier 4 |  |  |  |  | 1542, 1556, 1557, 1558 | Y |  |  |  | 72962 | 66492
72579A | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Mountain Top to Blanco 69 kV circuit to 138 kV with bundled 795 kcmil conductor (440 MVA). (Replaces ERCOT Project # 70367A) |  | Mountain Top | Blanco | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-19 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 7148, 70480, 70482, 70484 | Y | Y |  |  | 72580 | 72579
72574 | topo_update | Upgrade Junction from tap station to a three terminal ring bus. Replaces Project ID 63916. |  | NEW JUNCTION 70600 |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-25 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70600 | Y |  |  |  | 80916 | 72574
75788 | This project will intercept the second circuit of a common tower at Reata station. | This project will intercept the second circuit of a common tower at Reata station. |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | Eastland | Eastland | Tier 4 |  |  |  |  | 68008, 68011, 68051, 153635 | Y |  |  |  | 75789 | 75788
75792 | New substation for generation interconnection project for 21INR0359 | New substation for generation interconnection project for 21INR0359 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-12-31 |  | 345 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 68035, 68040, 68091 | Y |  |  |  | 75793 | 75792
72651 | Add_Josephine_Load | Tapping the Nevada and Shelby transmission line, and adding Josephine Load. | [5 empty] | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 991, 6991 | Y |  |  |  | 76031 | 72651
91565 |  |  |  | Navarro Mills Tap | Navarro Mills | Under Construction |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-01-23 |  | 69 | 0 | 1.1 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 186, 3511 | Y |  |  |  | 91566 | 91565
91285 | TNMP Lago Mar Substation |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-02-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38815, 38820, 38850 | Y |  |  |  | 91286 | 91285
76788 | Upgrade Victoria-Rayburn | Upgrade Victoria- Loop 463- Rayburn to 403 MVA |  | Rayburn | Victoria | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-03-01 |  | 138 | 0 | 11.57 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5502, 5680, 8172 | Y |  |  |  | 76789 | 76788
71985 | Cypress Water 138 kV Switch | Rebuild the existing Northlake(Cypress Waters) 138 kV Switch |  | Northlake |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4353 | 2026-03-15 |  | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 3 | 23RPG006 |  |  |  | 2362, 2363, 2367, 2385, 2386, 2390, 2395, 2587 | Y |  |  |  | 73110 | 71985
103801 | Models YELLOWJACKET | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-04-01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 8734, 39030, 39035, 114343 | Y |  |  |  | 103802 | 103801
99544B | Establish Baines Creek 138 kV Switch | Baines Creek 138 kV Switch Gen Tie |  | Baines Creek 138 kV Switch | Bonham Solar I | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6375 | 2026-04-07 |  | 138 | 0.1 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 3802, 155372 | Y |  |  |  | 111920 | 99544
89957 | RCEC_Commerce_South_Load | Adding Commerce South Bus, Load and Branch from Saddle to Comm_S1_8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-05-01 |  | 138 | 1 | 0 | 0 |  | Hunt | Hunt | Tier 4 |  |  |  |  | 2843, 6856 | Y |  |  |  | 89958 | 89957
63948 | Establish Fallstown 138 kV Switch | Establish Fallstown 138 kV Switch |  | Fallstown | Fallstown | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M3018 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Wichita | Wichita | Tier 4 | [5 empty] | Y |  |  |  | 87782 | 63948
92849 | Renner Switch 138kV Capacitor Bank | Install Capacitor Banks at Renner switch |  | Renner Switch | Renner Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4021 | 2026-05-15 |  | 138 | 0 | 0 | 0 | 0,220 | Collin | Collin | Tier 4 |  |  |  |  | 2352, 2353 | Y |  |  |  | 92864 | 92849
7126 | Renner TPL 138 kV Capacitors | Upgrade existing capacitor banks |  | RENNER SWITCH | RENNER SWITCH | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3048 | 2026-05-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Dallas | Dallas | Tier 4 |  |  |  |  | 2352, 2353 | Y | N |  |  | 14964 | 7126
80546B | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Rebuild and double-circuit the Round Rock Westinghouse - Georgetown East 138 kV Line Section |  | Round Rock Westinghouse Tap | Georgetown East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2026-05-15 |  | 138 | 9.1 | 9.1 | 0 |  | Williamson | Williamson | Tier 3 | 24RPG018, 25RPG006 | 2025-02-21 | 2025-03-17 |  | 3669, 3677, 7528, 7532 | Y |  |  |  | 87619 | 80546 | 2023-SC17
71178 | Seagoville-Watermill 138 kV Line | Rebuild Seagoville-Watermill 138 kV Line |  | Seagoville | Watermill | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M4081 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 3 | 23RPG033 |  |  |  | 2429, 2434, 3076, 3077, 3079, 3083 | Y |  |  |  | 71179 | 71178
78367 | Montfort Switch-Shankle Switch 138 kV Line | Rebuild Montfort Switch - Shankle Switch 138 kV Line |  | Montfort | Shankle | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4002 | 2026-05-17 |  | 138 | 0 | 18 | 0 |  | Navarro | Ellis | Tier 3 | 23RPG033 |  |  |  | 192, 2330, 2331, 3789, 12329 | Y |  |  |  | 78368 | 78367
66208 | Rebuild League City-Hidden Lakes with bundled 795 ACSS |  |  | Hidden Lakes (bus # 38900) | League City (bus # 38920) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-05-31 |  | 138 | 0 | 3.21 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38900, 38920 | Y |  |  |  | 66209 | 66208
77320 | Add CapBANK in COYANOSA |  |  | COYANOSA |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 38380 | Y |  |  |  | 77321 | 77320
104040 | Models Rice Tap | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-06-01 |  | 138 | 0 | 0 | 0 |  | Collin | Grayson | Tier 4 |  |  |  |  | 12236, 37363, 37365 | Y |  |  |  | 104041 | 104040
92687 | Burkett 138 kV POD | Burkett 138 kV POD |  | Burkett |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4466 | 2026-06-11 |  | 138 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 2471, 2710, 2893 | Y |  |  |  | 92688 | 92687
50866 | Structure 31/8 - Kenedy SS: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild | In-Service Date Update | Rosata | Kenedy SS | Under Construction | 1052 - 1225 | AEP TCC | Curtis Brown deevans@aep.com 918-599-2938 | 3779 | 2026-06-11 01:00 |  | 138 | 0 | 14.3 | 0 |  | Karnes | Karnes | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8153, 8186 | Y | N |  |  | 50867 | 50866
109708 | LCRA North McCamey Switch Station: Cap Bank Retirement | Retire the AEP Cap Banks at the LCRA's North McCamey Switch station | TSP/Company Contact Update | N. McCamey |  | Planned |  | AEP TCC/LCRA | Daniel DeVita myturner@aep.com 918-599-2437 | TP2026117 | 2026-06-27 |  | 138 | 0 | 0 | 0 |  | Upton |  | Tier 4 |  |  |  |  | 76595 | Y | N |  |  | 109709 | 109708
111219 | Tynan: Expand 69 kV Station | Interconnect Honeycomb Solar and Storage to the Tynan 69 kV station | NEW | Tynan |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5575 | TP2023005 | 2026-06-30 |  | 69 | 0 | 0 | 0 |  | Bee |  | Tier 4 |  |  |  |  | 8107 | Y | N |  |  | 111220 | 111219
71952 | LCRA TSC Bluffton to Buchanan Transmission Line Overhaul | Overhaul circuit and replace conductor with single-Drake conductor (117 MVA) from Bluffton to Buchanan. Replacement structures should be 138-kV double-circuit capable of supporting a single-Suwannee conductor. Install OPGW. |  | Bluffton | Buchanan | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 69 | 0 | 7 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7406 | Y | N |  |  | 72467 | 71952
92629 | Gabriel - Rivery MLSE Upgrade | Remove an MLSE on T457 Gabriel - Rivery 138-kV transmission line to achieve the full conductor rating. |  | Gabriel Substation |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-762-3658 |  | 2026-06-30 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7346, 7347 | Y |  |  |  | 92630 | 92629 | 2023-SC17
102815 | SandLake - North McCamey Transmission Line Addition | LCRA TSC and ONCOR joint project to add the Sand Lake-North McCamey 345-kV double-circuit transmission line. 22RPG010. Also see PMCR 69709, LCRATSC_Bearkat_NorthMcCamey_TransmissionLineAddition. |  | North McCamey | Sand Lake | Under Construction |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 345 | 186 | 0 | 0 |  | Glasscock | Ward | Tier 1 | 22RPG010 | 2022-04-12 | 2022-07-13 |  | 11098, 76000 | Y | Y |  |  | 102816 | 102815 | 2021-FW15
73401 | Fredonia - Mason Transmission Line Overhaul | Perform an overhaul on the 11 mile T289 Fredonia (CTEC) - Mason (CTEC) 69-kV transmission line. Per LCRA TSC Transmission System Planning procedure, replacement structures will be capable of operating at 138-kV. |  | Fredonia | Mason | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-06-30 |  | 69 | 0 | 11 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 7395, 76391 | Y | N |  |  | 73402 | 73401
69709 | Bearkat - North McCamey Transmission Line Addition | LCRA TSC and WETT joint project to add the Bearkat-North McCamey 345-kV double-circuit transmission line. 22RPG010 |  | Bearkat | Sand Lake | Under Construction |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-06-30 |  | 345 | 140 | 0 | 0 |  | Glasscock | Ward | Tier 1 | 22RPG010 | 2022-04-12 | 2022-07-13 |  | 59903, 76000 | Y | Y |  |  | 78333 | 69709 | 2021-FW15
109841 | Red Creek: Expand 345 kV Station | Interconnect the Skybox load to the existing Red Creek 345 kV station | TSP/Company Contact Update | Red Creek |  | Planned |  | AEP TNC | Michael Blackwell myturner@aep.com 918-599-2437 | TP2026069 | 2026-06-30 |  | 345 | 0 | 0 | 0 |  | Tom Green |  | Tier 4 |  |  |  |  | 6444, 60309 | Y | N |  |  | 109842 | 109841
72576B | Lago Vista to Nameless Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. (Replaces ERCOT Project #61277B) | 1/10/2023: Added information to clarify circuit rating. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2026-07-01 |  | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70352, 70526 | Y | N |  |  | 72578 | 72576
90010 | Magill: Construct New 138 kV Terminal | Interconnect City Breeze BESS to the Magill 138 kV station | TSP/Company Contact Update | Magill |  | Planned |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2024104 | 2026-07-15 00:02 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8111, 114071 | Y |  |  |  | 90011 | 90010
91555 | Switchyard to accommodate for Telios Large Load. | Added Kirkland and Telios bus, along with load and branches |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-08-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6879, 6882, 6915, 6950, 6980 | Y |  |  |  | 91556 | 91555
91558 | 138kV transmission upgrade to serve Kirkland large load. | Modifying branch info between BLDSW_RC and BLACKLND_8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-08-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6886, 12713 | Y |  |  |  | 91559 | 91558
91584 |  |  |  | HOLDER | RISING STAR | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-08-01 |  | 138 | 0 | 0 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 292, 33285, 33289 | Y |  |  |  | 91585 | 91584
1205 | Planned reconductor from Hasse to Gustine | Planned reconductor from Hasse to Gustine |  | HASSE | GUSTINE | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-08-01 |  | 69 | 0 | 7.34 | 0 |  | Comanche | Comanche | Tier 4 |  |  |  |  | 273, 277 | Y |  |  |  | 54001 | 1205
90851 | add 19.2 MVAR Capacitor at Rio Colorado |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-08-01 12:00 |  | 69 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5563 | Y |  |  |  | 90852 | 90851
81410 | Oncor_FW_81410_Averitt Synchronous Condenser | Add Averitt Switch Synchronous Condenser |  | Averitt | Averitt | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | D20231 | 2026-08-13 |  | 345 | 0 | 0 | 0 | -175350 | Ector | Ector | Tier 1 | 23RPG029 |  |  |  | 18544, 18553, 18554, 23933, 23934 | Y |  |  |  | 111451 | 81410
75790 | Placeholder Station for Erath Solar POI | Placeholder Station for Erath Solar POI |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-08-27 |  | 345 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 68020, 68025, 68030 | Y |  |  |  | 75791 | 75790
90232G | Facility Ratings Methodology (FRM) Upgrades | Upgrade Stadium to Fannin Ckt.08B to increase thermal limits as part of FRM upgrades |  | Stadium | Fannin | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47090, 47420 | Y | N |  |  | 102827 | 90232
90232A | Facility Ratings Methodology (FRM) Upgrades | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits as part of FRM upgrades |  | PSARCO | BIGVUE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40190, 41301 | Y | N |  |  | 102826 | 90232
90232F | Facility Ratings Methodology (FRM) Upgrades | Upgrade Bellaire to Jeanetta Ckt.64B to increase thermal limits as part of FRM upgrades |  | Bellaire | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47000, 47300 | Y | N |  |  | 102824 | 90232
90232C | Facility Ratings Methodology (FRM) Upgrades | Upgrade Ckt.06D NASA to Webster to increase thermal limits as part of FRM upgrades |  | NASA | Webster | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42970, 43500 | Y | N |  |  | 102823 | 90232
90232D | Facility Ratings Methodology (FRM) Upgrades | Upgrade Bellaire to WAP Ckt.50A to increase thermal limits as part of FRM upgrades |  | Bellaire | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44005, 47000 | Y | N |  |  | 102822 | 90232
99453M | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.75H King to Rothwood to increase thermal limits as part of FRM2 upgrades. |  | King | Rothwood | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40900, 46290 | Y | N |  |  | 102612 | 99453
81006 | DIABOX Customer Load Addition with related line upgrades | Upgrade Ckt.21E MOMENT to SOLMER to SR Bertron to increase thermal limits |  | SOLMER | SR Bertron/MOMENT | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 |  | 138 | 0 | 2.12 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40480, 41090, 41400, 41480 | Y | N |  |  | 81007 | 81006
70660 | Plaza to Grant Ckt.08I Upgrade | Install parallel underground portion of Ckt.08I Plaza to Grant to increase thermal limits. |  | Plaza | Grant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 00:10 |  | 138 | 0 | 0.44 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47110, 47350 | Y | N |  |  | 98382 | 70660
90452 | Red Egret BESS 138kV Gen Tie. |  |  |  |  | Under Construction | 76067 | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-08-31 |  | 138 | 1.15 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 38820, 113533 | Y |  |  |  | 90453 | 90452
78483 | Rebuild Nada to El Campo 69 kV line | Rebuild Nada to El Campo 69 kV line from 4/0 to 795. 2023 RTP |  | Nada | El Campo | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-09-01 |  | 69 | 0 | 15.44 | 0 |  | Colorado | Wharton | Tier 4 |  |  |  |  | 5536, 5538 | Y | N |  |  | 78484 | 78483
70884 | Rebuild Rio Colorado - Bay City | Rebuild Rio Colorado - Bay City 795 ACSR |  | Rio Colorado | Bay City | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-09-01 |  | 69 | 0 | 9.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5560, 5563 | Y |  |  |  | 70885 | 70884
102871 | Add Fort Bobcat load serving station and Tline to STEC Orange Grove |  |  |  |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-09-01 |  | 138 | 1 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5660, 5664 | Y | N |  |  | 102872 | 102871
78169 | Lewisville Switch to Highland | Lewisville Switch to Highland |  | Lewisville Switch | Highland | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-09-04 |  | 138 | 0 | 2.8 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 645, 664 | Y |  |  |  | 78170 | 78169
66289C | Tyler to Athens 138 kV line Conversion | Convert Tyler Switch - Athens 69 kV Line to 138 kV Operation |  | Tyler Switch | Athens | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6094 | 2026-09-15 |  | 138 | 0 | 3.8 | 0 |  | Smith | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3108, 3126, 3142, 3197, 3236, 3238, 3239, 3256, 13235 | Y |  |  |  | 103210 | 66289
66492B | Chico West - Grindstone Switch 69 kV Line rebuild | Upgrade Grindstone - Jacksboro Sinclair 69 kV Line |  | Jacksboro Sinclair | Grindstone | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M3006 | 2026-09-15 |  | 69 | 0 | 15 | 0 |  | Jack | Palo Pinto | Tier 4 |  |  |  |  | 1557, 1572 | Y |  |  |  | 72964 | 66492
72579B | PEC_MountainTop_Blanco_DevilsHill_VoltageUpgrade | Rebuild and upgrade Blanco to Devil's Hill 69 kV circuits to 138 kV with bundled 795 kcmil conductor (440 MVA). (Replaces ERCOT Project # 70367B) |  | Blanco | Devil's Hill | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-09-15 |  | 138 | 0 | 0 | 0 |  | Blanco | Blanco | Tier 4 | 22RPG033 |  | 2022-11-14 |  | 70482, 70493 | Y | Y |  |  | 72581 | 72579
66206A | Upgrade Temple - Minerva 69 kV Line | Upgrade Temple - Marak 69 kV Line |  | Temple | Marak | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6186 | 2026-09-15 |  | 69 | 20.5 | 0 | 0 |  | Bell | Milam | Tier 3 | 22RPG034 | 2022-10-01 | 2022-11-01 |  | 3496, 3689, 3726 | Y |  |  |  | 68923 | 66206
104569 | BBEC Delhi T1 | Add Transformer at Delhi |  | Delhi |  | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2026-09-18 |  | 69 | 0 | 0 | 0 |  | Caldwell |  | Tier 4 |  |  |  |  | 7896 | Y |  |  |  | 104570 | 104569
81305A | Expanse - Vealmoor 138 kV Line Rebuild | Rebuilds the existing Vealmoor – Estacado 138 kV Line with both circuits in place and establish the new Tredway 138 kV Switch. |  | Expanse | Tredway | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8681 | 2026-09-30 |  | 138 | 0 | 15.5 | 0 |  | Martin | Martin | Tier 1 | 24RPG029 | 2023-09-29 |  |  | 1355, 10099, 10110, 10113, 11002, 11005, 11303, 11349, 11368, 23829, 23835, 23838 | Y |  |  |  | 106039 | 81305
50890 | Port Lavaca: Station Rebuild (Cangrejo) | Rebuild the Port Lavaca (Cangrejo) station | In-Service Date Update | Port Lavaca |  | Under Construction | 1057 - 1230 | AEP TCC | Lorraine Timmerman deevans@aep.com 918-599-2938 | 3787 TA2019045 | 2026-09-30 |  | 69 | 0 | 37.81 | 0 |  | Calhoun |  | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8135 | Y | N |  |  | 50891 | 50890
67326 | Ajo to Reforzar: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Ajo to Reforzar | Dollars Update | Ajo | Reforzar | Under Construction |  | AEP TCC/ETT | Curtis Brown jlsolis@aep.com 361-881-5574 | TP2022030 | 2026-09-30 |  | 345 | 11 | 0 | 0 |  | Kenedy | Brooks | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80076, 80078 | Y |  |  |  | 67327 | 67326
81305B | Expanse - Vealmoor 138 kV Line Rebuild | Rebuild the existing Expanse – Estacado 138 kV Line section with both circuits in place establish the new Tredway 138 kV Switch. |  | Expanse | Tredway | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8681 | 2026-09-30 |  | 138 | 0 | 12.8 | 0 |  | Martin | Martin | Tier 1 | 24RPG029 | 2023-09-29 |  |  | 1355, 10090, 10097, 10098, 10110, 10113, 11002, 11006, 11303, 11338, 11348, 11349, 11368, 11383, 23829, 23835, 23838, 23849, 23880 | Y |  |  |  | 106038 | 81305
90232E | Facility Ratings Methodology (FRM) Upgrades | Upgrade Jeanetta to WA Parish Ckt.64A to increase thermal limits as part of FRM upgrades |  | Jeanetta | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-09-30 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47300 | Y | N |  |  | 102821 | 90232
89959 | RCEC_RockWallHwy276Load | Adding Rockwall Highway Bus, Load and Branch from RockWallHwy to RCKWL_E1_8 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 2710, 6972 | Y |  |  |  | 89960 | 89959
77807B | Silverleaf 138kV station from TNMP submitted Cowpen/Silverleaf RPG |  |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 | 23RPG013 | 2023-05-11 | 2023-11-27 | 2024-01-09 |  | Y |  |  |  | 111421 | 77807
92872 | North Main 138kV Capacitor Bank | North Main 138kV Capacitor Bank |  | North Main | North Main | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5187 | 2026-10-15 |  | 138 | 0 | 0 | 0 | 0,110 | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1961 | Y |  |  |  | 92873 | 92872
78177 |  |  |  | Pleasant Grove | Pleasant Grove | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 69 | 0 | 0 | 0 | 0,7.2 | Falls | Falls | Tier 4 |  |  |  |  | 81 | Y |  |  |  | 78178 | 78177
78181 |  |  |  | Midway | Midway | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-15 |  | 69 | 0 | 0 | 0 | 0,7.2 | Falls | Falls | Tier 4 |  |  |  |  | 185 | Y |  |  |  | 78182 | 78181
87512 | RCEC_BranchChanges_Kaufman_Update4 | Updating branch info between I20_RC and COMBINRC1 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-10-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6904 | Y |  |  |  | 87513 | 87512
102563 | BEPC_TPIT102563_BrushieCap |  |  | 199 |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-10-22 |  | 69 | 0 | 0 | 0 | 0,7.2 | Navarro |  | Tier 4 |  |  |  |  | 199 | Y |  |  |  | 102564 | 102563
61444 | GVEC Kicaster Substation Addition (formerly Wilson South) | Add a new load-serving substation 4.35 miles south of La Vernia along FM 775 with a 40 MVA PWT. |  | Wilson South |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2026-10-23 |  | 138 | 0 | 0 | 0 |  | Wilson |  | Tier 4 |  |  |  |  | 5418, 7615, 7629 | Y | N |  |  | 78418 | 61444
87799 | Old Country 345 kV Switch | Old Country 345 kV Switch |  | Old Country |  | In-Service |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4172 | 2026-10-29 | 2026-07-31 | 345 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 1906, 68091 | Y |  |  |  | 87800 | 87799
78490C | Jeanetta Auto Upgrades | Upgrade Ckt.25B Roark equipment and reconductor near Roark substation to increase thermal limits |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-30 |  | 138 | 0 | 0.04 | 0 |  | Harris | Harris | Tier 3 | 23RPG031 | 2023-10-04 | 2023-10-26 |  | 44590, 48315, 48316 | Y | N |  |  | 79427 | 78490
71950 | Twin Buttes Load 138-KV Circuit Breaker Addition | Provide a 138-kV point of interconnection at the Twin Buttes Substation to connect to a new Golden Spread Electric Cooperative Transmission line. Update contingencies |  | Twin Buttes |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-10-30 |  | 138 | 0 | 0 | 0 |  | Tom Green | Tom Green | Tier 4 | [5 empty] | Y | N |  |  | 78299 | 71950
87431 | Rebuild Wickett to Winkler 69kV line. |  |  | TNMP Winkler (37960) | TNMP Wickett (37980) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-10-30 |  | 138 | 0 | 6.8 | 0 |  | Winkler | Ward | Tier 4 |  |  |  |  | 37960, 37980 | Y |  |  |  | 87432 | 87431
67320 | Cruce to Reforzar: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cruce to Reforzar | Dollars Update | Cruce | Reforzar | Under Construction |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2022033 | 2026-10-30 |  | 345 | 48 | 0 | 0 |  | Jim Hogg | Brooks | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80078, 80079 | Y |  |  |  | 67339 | 67320
99641 | Static: Expand 345 kV Station | Install two 345 kV breakers at the existing Static 345 kV station | In-Service Date Update | Static |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2025246 | 2026-10-30 |  | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 | [5 empty] | Y |  |  |  | 99642 | 99641
45511 | Laredo to Del Mar: 138 kV Line Rebuild | Rebuild Laredo to Del Mar 138 kV Line | Company Contact and In-Service Date Update | Laredo | Del Mar | Planned | 992 - 1170 | AEP TCC | Bradley Case jlsolis@aep.com 361-881-5574 | 3746 | 2026-10-31 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645 | Y | N |  |  | 65531 | 45511 | 2018-S4
57906 | Laredo to University: Rebuild 138 kV Line | Reconductor the Del Mar to University 138 kV line | In-Service Date Update | Laredo | University | Under Construction | 1119 - 1297 | AEP TCC | Bradley Case jlsolis@aep.com 361-881-5574 | 3838 | 2026-10-31 |  | 138 | 0 | 2.73 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8293, 8645, 8647 | Y | N |  |  | 65579 | 57906
66101 | Del Sol to Frontera: Build New 345 kV Double Circuit Line | Build new 345 kV double circuit line from Del Sol to Frontera. Expand Frontera Station and install two (2) autotransformers. | Service Level Update | Del Sol | Frontera | Planned |  | AEP TCC/ETT | Brent Harris jlsolis@aep.com 361-881-5574 | TP2020838 | 2026-10-31 |  | 345 | 36 | 0 | 1350 |  | Starr | Hidalgo | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8355, 8980, 8992, 80004, 80005, 80119, 80355 | Y |  |  |  | 66102 | 66101
92998 | LeMay: Expand 138 kV Station | Interconnect the new White Water Midstream load to the existing LeMay 138 kV station | TSP/Company Contact Update | LeMay |  | Planned |  | AEP TCC | Matthew McLauchlin jlsolis@aep.com 361-881-5574 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | La Salle |  | Tier 4 |  |  |  |  | 8627 | Y | N |  |  | 92999 | 92998
109613 | Install generation for Pinewood Solar (25INR0170) at Seabreeze 345kV CEHE substation. Connect at the same generator lead as Tanglewood Solar. |  |  | Seabreeze | TANGLE | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  |  | 109614 | 109613
90964 | Tier 3 project to add second autotransformer at Long Draw |  |  | Long Draw 345 kV | Long Draw 138 kV | Planned |  | WETT | Chris Ramirez cramirez@wettllc.com |  | 2026-10-31 |  | 345 | 0.5 | 0 | 706 |  | Borden | Borden | Tier 3 | 24RPG027 | 2024-08-28 | 2024-09-20 |  | 59900, 59906, 59991 | Y |  |  |  | 90965 | 90964
111495 | LCRATSC Warda Generator Circuit Breaker Addition | This project installs a new 138-kV circuit breaker and associated terminal equipment at the Warda Substation, in a ring bus configuration, to provide a new 138-kV Point of Interconnection to Staccato Storage. |  | Warda |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Fayette |  | Tier 4 | [5 empty] | Y |  |  |  | 111496 | 111495
90232H | Facility Ratings Methodology (FRM) Upgrades | Upgrade Kirby to Garrott Ckt.37A to increase thermal limits as part of FRM upgrades |  | Kirby | Garrott | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47320, 47660 | Y | N |  |  | 102828 | 90232
99453R | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.62A Bailey to Waterhole to increase thermal limits as part of FRM2 upgrades. |  | Bailey | Waterhole | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 44040, 44880 | Y | N |  |  | 102615 | 99453
90006 | Oklaunion: Construct New 345 kV Terminal | Interconnect the OPS load to the existing Oklaunion 345 kV station | In-Service Date Update | Oklaunion |  | Planned |  | AEP TNC/AEP TNC/ETT | Randy Weaver myturner@aep.com 918-599-2437 | TP2024106 | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6100 | Y |  |  |  | 90007 | 90006
87861 | Range Rider - Ranger Camp 138 kV Double-Circuit Line | Construct a new 138 kV Double-Circuit Line from Range Rider to Ranger Camp Switch. |  | Ranger Camp 345/138 kV Switch | Range Rider 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8722 | 2026-10-31 |  | 138 | 1.2 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1032, 10050 | Y |  |  |  | 87862 | 87861
73578A | Heights 138kV Loop Conversion | Rebuild/Reconductor Dead Ckt.40Z to prepare for 138kV Conversion. De-energize Ckt.31C Dunlavy to Heights and repurpose as Ckt.09D tap to Dunlavy TR1 load. |  | Dunlavy | Heights | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46615, 47580, 47581, 47591, 47682, 48752 | Y | N |  |  | 90931 | 73578
90038 | McKenzie Road to Winthorp: Construct New 138 kV Line | Interconnect the new Winthorp load station to the existing McKenzie Road 138 kV station |  | McKenzie Road | Winthorp | Planned |  | AEP TCC/ETT | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2024150 | 2026-10-31 |  | 138 | 0.15 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8545, 8858 | Y | N |  |  | 90039 | 90038
81223 | Range Rider 138 kV Switch | Construct a new 138 kV switch replacing existing Morgan Creek 138 kV Switch. |  | Range Rider 138 kV Switch | Range Rider 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8721 | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 1032, 1033, 10050, 10183, 11032, 11033, 11034, 11035, 180031, 180032, 180033, 180034, 180035, 180036 | Y |  |  |  | 100162 | 81223
91289 | LCRATSC_Settlers Substation Upgrade | Settlers Substation Addition project will construct a new substation connecting to LCRA TSC owned 138-kV transmission lines T171 Austrop to Sim Gideon and T231 Bastrop to Webberville via a hard tap installation. In this project, LCRA TSC will upgrade the hard tap installation to a breakered facility. |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-6691 | 2026-10-31 |  | 138 | 0 | 0 | 0 |  | Bastrop |  | Tier 4 |  |  |  |  | 7322, 7327, 7328, 7329 | Y |  |  |  | 91959 | 91289
78490D | Jeanetta Auto Upgrades | Reconductor Ckt.25B Clodine to Roark TR8 tap to increase thermal limits. |  | Clodine | Roark | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 |  | 138 | 0 | 3.67 | 0 |  | Harris | Harris | Tier 3 | 23RPG031 | 2023-10-04 | 2023-10-26 |  | 44140, 48315 | Y | N |  |  | 79428 | 78490
73578B | Heights 138kV Loop Conversion | Repurpose/retire existing 69kV Ckts 34A/34B. Unbundle parallel-bundled portions of Ckt.40A HOC to Dunlavy. Reconfigure Ckt.40A to reach a Minimum 1-2000AAC limiting conductor @ 90/120Deg. Upgrade HOC line relaying on 69kV Ckt.40A HOC to Dunlavy. |  | Dunlavy | HO Clarke | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 90932 | 73578
73578D | Heights 138kV Loop Conversion | Convert Heights substation to 138kV service. Retire/repurpose portions of 69kV Ckts. 34A/34B for the new Heights 138kV loop. Reconfigure Ckt.09D to create new Ckt.09D Eureka TR2/TR3 tap to HE-DN_TR1 tap to Heights 138kV to White Oak. Reconductor any existing 1-795AAC limiting conductor to 2-959ACSS. Remove existing Heights 7.2 MVAR cap bank from Heights TR1. |  | Heights | San Felipe/White Oak | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:03 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46615, 46620, 47160, 47581, 47591, 47680, 47682, 47685, 48752, 747680 | Y | N |  |  | 90933 | 73578
73578E | Heights 138kV Loop Conversion | Remove White Oak auto A2/A4 and remaining 69kV facilities |  | White Oak |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-10-31 00:04 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46615, 46620, 47680, 49021, 49042 | Y | N |  |  | 90934 | 73578
81594 | Dunlay substation | Adds STEC Dunlay Load serving station |  | Dunlay |  | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-11-01 |  | 138 |  | 0 | 0 |  | Medina |  | Tier 2 |  |  |  |  | 5802, 5807, 5813 | Y | N |  |  | 81595 | 81594
81590 | Rio Medina substation | Adds Rio Medina Load serving station |  | Rio Medina |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-11-01 |  | 138 | 4.5 | 0 | 0 |  | Medina |  | Tier 2 |  |  | 2024-02-01 |  | 5804, 5805 | Y | N |  |  | 81591 | 81590
71917 | Upgrade STEC castroville to Pearson to 138kV | Upgrade STEC Bader station to 138kV. Upgrade STEC Castroville to bader and bader to pearson to 138kV |  | 5808 | 5813 | Under Construction | 71935 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-11-01 |  | 138 | 0 | 10.51 | 0 |  | Medina | Medina | Tier 2 | 22RPG022 | 2022-08-08 | 2022-12-06 |  | 5802, 5804, 5810, 5811, 5813 | Y |  |  |  | 71918 | 71917
91174 | Upgrade Eustace-Walton line to Cumberland conductor | Upgrade Eustace-Walton line to Cumberland conductor |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-11-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6899, 6951 | Y |  |  |  | 98999 | 91174
91596 | Addition of PEC CementPlant_Substation | Adding PEC CementPlant_Substation substation. Adding bus, branch, and load. |  |  |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-11-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70002, 70198, 70498 | Y |  |  |  | 91597 | 91596
91176 | Add Combine Switch station next to the existing Combine station. The new Combine switch will connect to Combine NTMWD | Add Combine Switch station next to the existing Combine station. The new Combine switch will connect to Combine NTMWD |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-11-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6821, 6858, 6903, 6904, 6905 | Y |  |  |  | 91177 | 91176
82298B | PMCR for Adding TNMP Woodhouse New Station |  |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-11-04 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 | 23RTP023 |  |  | 2024-02-27 |  | Y |  |  |  | 111494 | 82298
70714 | La Cima Substation Addition | Add new substation to 138 kV line between Ranch Road 12 and Hill Top and install 46.7 MVA distribution transformer. The new substation will be located approximately 0.30 miles from Ranch Road 12 substation. |  | Ranch Road 12 | La Cima | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-11-10 |  | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 7185, 7186, 7190 | Y | N |  |  | 70715 | 70714
78175 |  |  |  | Franklin | Franklin | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-11-12 |  | 138 | 0 | 0 | 0 | 0,9 | Robertson | Robertson | Tier 4 |  |  |  |  | 57 | Y |  |  |  | 78176 | 78175
87514 | RCEC_BranchChanges_Kaufman_Update5 | Updating line info between Boze and CombineRC1 |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-11-15 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6903, 6904, 6905 | Y |  |  |  | 87515 | 87514
99544A | Establish Baines Creek 138 kV Switch | Establish Baines Creek 138 kV Switch |  | Baines Creek 138 kV Switch | Baines Creek 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6375 | 2026-11-15 |  | 138 | 0 | 0 | 0 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 3632, 3634, 3802 | Y |  |  |  | 99545 | 99544
99608 | Establish Foggle Switch - North Athens Switch 138 kV Line | Establish Foggle Switch - North Athens Switch 138 kV Line |  | Foggle Switch | North Athens Switch (Rayburn) | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6348 | 2026-11-15 |  | 138 | 0 | 1.4 | 0 |  | Henderson | Henderson | Tier 4 |  |  |  |  | 3233, 6867 | Y |  |  |  | 99609 | 99608
64858 | La Palma Expansion | Construct 3 Breaker Ring Bus. Construct 345 kV Line from La Palma 345 kV station to Kingfisher 345 kV (Sharyland) station. | In-Service Date Update | La Palma | Kingfisher | Planned |  | AEP TCC/SLU | Lorraine Timmerman jlsolis@aep.com 361-881-5574 | TP2021588 | 2026-11-16 |  | 345 | 6.5 | 0 | 0 |  | Cameron | Cameron | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8317, 8383, 79500, 79501, 80137 | Y |  |  |  | 65264 | 64858
93242 | Saxet Substation Upgrade | This Saxet Substation Upgrade project (Phase 2) will be a continuation of the Saxet Substation Addition project (Phase 1) where LCRA TSC installed two new transmission hard taps with associated structures to LCRA TSC owned 138-kV transmission lines T522 Lon Hill – Weil Tract and T437 Lon Hill (AEP) – Nueces Bay (AEP). In this project, LCRA TSC will upgrade from the hard tap installations to a breakered facility and connect the LCRA TSC 138-kV transmission lines T522 Lon Hill – Weil Tract and T437 Lon Hill (AEP) – Nueces Bay (AEP) to the new Saxet substation. |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7500 | 2026-11-20 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8441, 8452, 8858, 78568, 78569 | Y |  |  |  | 93247 | 93242
93299 | Add Embar 138 kV POD | Add Embar 138 kV POD |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-11-27 | 2026-11-27 | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 1134, 11273, 18690 | Y |  |  |  | 93300 | 93299
64042 | Barrilla Junction: 69 kV Loop Rebuild | Rebuild Barrilla Junction to Saragosa to Cherry Creek to Verhalen to Hoefs Road stations, convert to 138 kV | TSP/Company Contact and In-Service Date Update | Barrilla Junction | Hoefs Road Station | Planned | 1141 - 1319 | AEP TNC | Brent Harris myturner@aep.com 918-599-2437 | 1886 | 2026-11-30 |  | 69 | 0 |  | 0 |  | Pecos | Reeves | Tier 3 | 21RPG023 | 2021-12-17 | 2022-01-14 |  | 6649, 6650, 6651, 6652, 6653, 6654, 60206, 60207, 60208, 60716, 60802, 60808, 69023, 69047 | Y | N |  |  | 64043 | 64042
67324 | Cruce to Del Sol: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cruce to Del Sol | Dollars Update | Cruce | Del Sol | Under Construction |  | AEP TCC/ETT | Marc Wilson jlsolis@aep.com 361-881-5574 | TP2022032 | 2026-11-30 |  | 345 | 54.2 | 0 | 0 |  | Jim Hogg | Starr | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079, 80355 | Y |  |  |  | 67325 | 67324
69489 | Shepley: Construct New Distribution Station | Construct new distribution station on the Victoria to Dupont Switch 138 kV line | In-Service Date Update | Shepley |  | Under Construction |  | AEP TCC | Will Simmons deevans@aep.com 918-599-2938 |  | 2026-11-30 |  | 138 | 0 | 0 | 50 |  | Victoria |  | Tier 4 |  |  |  |  | 8143, 8149, 8159, 8169, 8172, 8572, 8719 | Y |  |  |  | 69490 | 69489
80464 | McKenzie Road: Rebuild 138 kV Station | Interconnect the Bootstrap loads to the rebuilt McKenzie Road 138 kV station | In-Service Date Update | Nueces | Nueces | Planned |  | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2023884 | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8520, 8545, 8567, 8858, 78568, 78569 | Y |  |  |  | 80465 | 80464
80484 | Closner: Construct New 138 kV Terminal | Interconnect Gunnar BESS to the Closner 138 kV station | In-Service Date Update | Closner |  | Planned |  | AEP TCC | Jeremy Brazeal jlsolis@aep.com 361-881-5574 |  | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8029 | Y |  |  |  | 80485 | 80484
80630 | Angstrom to STP: Increase 345 kV Line MOT | Increase the MOT on the Angstrom to STP 345 kV line | In-Service Date Update | Angstrom | STP | Under Construction | TA2024200 | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 |  | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | San Patricio | Matagorda | Tier 4 |  |  |  |  | 5915, 8249, 8676 | Y |  |  |  | 80631 | 80630
81576 | Tesla: Construct New 345 kV Terminal | Interconnect the Lancium load to the existing Tesla 345 kV station | In-Service Date Update | Tesla |  | Planned | TP2024048 | AEP TNC/ETT | Zachary Lachiusa myturner@aep.com 918-599-2437 |  | 2026-11-30 |  | 345 | 0.5 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501 | Y |  |  |  | 81577 | 81576
86882 | McKenzie to Westside: Reconductor 138 kV Line | Reconductor the McKenzie to Westside 138 kV line | TSP/Company Contact Update | McKenzie Road | Westside | Planned |  | AEP TCC/ETT | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2024025 | 2026-11-30 |  | 138 | 0 | 0.32 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 8485, 8858 | Y | Y |  |  | 86883 | 86882
69253 | Cangrejo to Dacosta: Rebuild 138 kV Line | Rehab 138 kV line from Cangrejo to Dacosta |  | Cangrejo | Dacosta | Planned |  | AEP TCC | Lorraine Timmerman jlsolis@aep.com 361-881-5574 |  | 2026-11-30 |  | 138 | 0 | 17.97 | 0 |  | Calhoun | Calhoun | Tier 1 | 21RPG002 | 2021-02-01 | 2021-09-16 | 2021-10-22 | 8133, 8135, 8136, 8140, 8141, 8143, 8169, 8536, 8721, 8722, 8723, 8756, 80064, 88133 | Y |  |  |  | 87986 | 69253
91630 | Jim Treece: Interconnect New 345 kV Generator | Interconnect Blue Summit II Energy Storage to the existing Jim Treece 345 kV station | In-Service Date Update | Jim Treece |  | Planned |  | ETT | Chase Stevens twang1@aep.com 918-599-2635 | TP2025111 | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 | [5 empty] | Y | N |  |  | 91631 | 91630
61396 | Hamilton Road to Maxwell: Rebuild 138 kV Line | Rebuild the Hamilton Road to Maxwell 138 kV line | TSP/Company Contact Update | Hamilton Road | Maxwell | Planned |  | AEP TCC | Jeremy Brazeal jsolis@aep.com 361-881-5574 | TA2019800 | 2026-11-30 |  | 138 | 0 | 29 | 0 |  | Val Verde | Val Verde | Tier 3 | 20RPG022 | 2020-11-02 | 2021-01-19 |  | 8257, 8998 | Y |  |  |  | 65593 | 61396
67322 | Cenizo to Cruce: Construct New 345 kV Double Circuit Line | Construct a new 345 kV double circuit line from Cenizo to Cruce | Dollars Update | Cenizo | Cruce | Under Construction |  | AEP TCC/ETT | Marc Wilson jlsolis@aep.com 361-881-5574 | TP2022031 | 2026-11-30 |  | 345 | 69 | 0 | 0 |  | Webb | Jim Hogg | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80079, 80220 | Y |  |  |  | 67323 | 67322
109643 | Install temporary tap service on Ckt.60C to create new Ckt.60C South Lane City to Raider tap to New Gulf. |  |  | Raider | South Lane City / New Gulf | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Wharton | Wharton | Tier 4 |  |  |  |  | 43010, 44999, 49924 | Y | N |  |  | 109748 | 109643
67318 | Cruce: Construct New 345 kV Station | Construct a new 345 kV station on the Cenizo to Reforzar 345 kV line and the Del Sol to San Miguel 345 kV line | TSP/Company Contact Update | Cruce |  | Under Construction |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2022034 | 2026-11-30 |  | 345 | 0 | 0 | 0 | -250,0 | Jim Hogg |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 5901, 80079, 80280, 80281 | Y |  |  |  | 98843 | 67318
99791A | Additional Facility Ratings Methodology Phase 2 (FRM2) Substation Upgrades. | Upgrade Ckt.50B Zenith to Gibbons Creek to increase thermal limits as part of FRM2 upgrades. |  | Zenith | Gibbons Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Grimes | Harris | Tier 4 |  |  |  |  | 967, 44900 | Y | N |  |  | 99806 | 99791
85947 | Euclid_Substation_Addition_Updated | LCRA TSC provide a new transmission point of interconnection by constructing a new 345-kV substation and cut-in T510 Hutto - Zorn. T510 will also be looped into the new Limmer 345-kV substation |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-11-30 | 2026-11-20 | 345 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7041, 7045, 7341 | Y |  |  |  | 100110 | 85947
102534 | Pamela Heights I battery storage at Callisto substation… Connect with HO Clarke 138kV substation at the same generator lead as 01HOCCLO |  |  | HO Clarke |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47150, 113105 | Y | N |  |  | 102535 | 102534
99453H | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.97C Jordan to King to increase thermal limits as part of FRM2 upgrades. |  | Jordan | King | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Chambers | Harris | Tier 4 |  |  |  |  | 40850, 40900 | Y | N |  |  | 102608 | 99453
99453I | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.02B WA Parish to Nash to increase thermal limits as part of FRM2 upgrades. |  | WA Parish | Nash | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Fort Bend | Brazoria | Tier 4 |  |  |  |  | 42980, 44010 | Y | N |  |  | 102609 | 99453
99453P | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.62B Waterhole to Jones Creek to increase thermal limits as part of FRM2 upgrades. |  | Waterhole | Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 345 | 0 | 0 | 0 |  | Wharton | Brazoria | Tier 4 |  |  |  |  | 42530, 44880 | Y | N |  |  | 102616 | 99453
103003A | Bellaire 35kV Distribution Upgrades with 3rd Transformer | Reconfigure 35kV Bellaire distribution facilities. Install new 35kV Bellaire distribution TR7 with Ckt.24B service. |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47014, 48512 | Y | N |  |  | 103004 | 103003
103431 | Rebuild/reconductor portions of DEWALT to MULA Ckt.02A as a Hardening upgrade. | Rebuild/reconductor portions of DEWALT to MULA Ckt.02A as a Hardening upgrade. |  | DEWALT | MULA | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 138 | 0 | 1.26 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44180, 44490 | Y | N |  |  | 103432 | 103431
103003B | Bellaire 35kV Distribution Upgrades with 3rd Transformer | Reconfigure 35kV Bellaire distribution facilities. Reconfigure Bellaire 35kV distribution transformer TR6 to receive Ckt.35E service. Reconductor portions of Ckt.35E. |  | Bellaire |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 00:01 |  | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47010, 47011, 47441, 48511 | Y | N |  | Cost included in Phase A | 103005 | 103003
73371E | BP24 Sub Upgrades | Upgrade Whaley to WA Parish Ckt.72F to increase thermal limits |  | Whaley | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 00:04 | 2958101 | 138 | 0 | 0 | 0 |  | Fort Bend | Fort Bend | Tier 4 |  |  |  |  | 44005, 44070 | Y | N |  |  | 89980 | 73371
99391A | Stanton East - Midland Basin - Spraberry 69 kV Line Conversion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L18. Convert the existing Stanton East - Midland Basin - Spraberry 69-kV line to 138-kV and cut into Consavvy 138 kV Switch to establish the Spraberry - Consavvy 138 kV Line. |  | Spraberry | Consavvy | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L18_A | 2026-12-01 |  | 138 | 0 | 5.5 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 1227, 1228, 1231, 1329, 1330, 11134, 11388 | Y |  |  |  | 99392 | 99391
70371 | D'Hanis Capacitor addition | Add 9.6 MVAR capacitor step at D'Hanis |  | D'Hanis |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 69 | 0 | 0 | 0 | 0,9.6 |  |  | Tier 4 |  |  |  |  | 5814 | Y | N |  |  | 70372 | 70371
70373 | Driscoll Capacitor addition | adds 3 9.6 MVAR capacitor steps at Driscoll |  | Driscoll |  |  |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 69 | 0 | 0 | 0 | 0,28.8 |  |  | Tier 4 |  |  |  |  | 5640 | Y |  |  |  | 70374 | 70373
71928 | Upgrade Heidelberg to AEP Weslaco line | Upgrade Heidelberg to STEC WESLACO and STEC WESLACO to AEP Weslaco lines to be 478MVA capable |  | Heidelberg | Weslaco | Planned | 7193071926 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 138 | 0 | 8.6 | 0 |  | Hidalgo | Hidalgo | Tier 4 |  |  |  |  | 5765, 5768, 8354 | Y |  |  |  | 71929 | 71928
76109 | West Sinton Capacitor addition | Add a 3.6 MVAR step to existing West Sinton Capacitor |  | West Sinton |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 69 | 0 | 0 | 0 | 0,3.6 |  |  | Tier 4 |  |  |  |  | 5622 | N | N |  |  | 76110 | 76109
76786 | Upgrade Driscoll- Loyola | Upgrade Driscol-Ricardo-Riviera-Loyola to 795 ACSR |  | Driscoll | Loyola | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 69 | 0 | 23.89 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 5640, 5645, 5646, 5650 | Y |  |  |  | 76787 | 76786
78478 | Rebuild Oaks to Poteet to Pearsall 69 kV line | Rebuild Oaks to Poteet to Pearsall 69 kV line from 4/0 to 795. 2023 RTP |  | Oaks | Pearsall | Under Construction |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 69 | 0 | 38.95 | 0 |  |  |  | Tier 4 |  |  | 2020-05-21 |  | 5710, 5712, 5893 | Y | N |  |  | 78479 | 78478
71182 | Reiter 345/138 kV Switch | Construct a new 345/138 kV switch |  | Odessa EHV | Wolf/Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8629 | 2026-12-01 |  | 345 | 0 | 0 | 1200 |  | Ector | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1018, 11010, 11028, 18544, 18545, 18546, 18547 | Y |  |  |  | 81601 | 71182
82298A | PMCR for Adding TNMP Woodhouse New Station |  |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 | 23RTP023 |  |  | 2024-02-27 | 38295, 38308, 38355, 60717 | Y |  |  |  | 82299 | 82298
87069 | LST_Phantomhill_Hub Conversion | Loop another circuit of the LST Crez line into Phantom Hill station as part of Gen Interconnection Project 23INR0244, 22INR0457 and 20INR0242 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-12-01 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68000, 68001, 68004, 183963 | Y |  |  |  | 87070 | 87069
81315 | add 19.2 MVAR Capacitor at Rossville | add 19.2 MVAR Capacitor at Rossville. 2023 RTP |  | Rossville |  | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 | 0,19.2 |  |  | Tier 4 |  |  |  |  | 5718 | Y |  |  |  | 87403 | 81315
91419 | Max Zuehlke_Gay Hill_TL_Upgrade | Replace 336 (Linnet) conductor with 959 (Suwannee) and replace a limited number of structures to accommodate the new conductor. |  | Max Zuehlke | Gay Hill | Planned |  | BBEC | Curtis Fischer curtis.fischer@bluebonnet |  | 2026-12-01 |  | 138 | 0 | 0 | 0 |  | Washington | Washington | Tier 4 |  |  |  |  | 7565, 7572 | Y |  |  |  | 91420 | 91419
91988 | Savanna - Canal Road 138 kV Line Rebuild | Rebuild the existing Savanna - Canal Road 138 kV Line |  | Driver | Canal Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8685 | 2026-12-01 |  | 138 | 0 | 0 | 0 |  | Reagan | Upton | Tier 4 |  |  |  |  | 10025, 10037, 23870 | Y |  |  |  | 92188 | 91988
93061 | Embar Switch 138 kV Capacitor Bank | Adds Embar Switch 138 kV Capacitor Bank |  | Fullerton Switch | Fullerton Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8874 | 2026-12-01 |  | 138 | 0 | 0 | 0 | 0,110.4 | Andrews | Andrews | Tier 4 |  |  |  |  | 18690 | Y |  |  |  | 93062 | 93061
93683 | New Transformer will be added at Titan Substation. |  |  | Titan | Titan | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2026-12-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5963 | Y |  |  |  | 93684 | 93683
91851 | Pinery 138 kV Switch | Establish Pinery 138 kV Switch |  | Pinery | Pinery | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8831 | 2026-12-01 |  | 138 | 0 | 0 | 0 | 0,110.4 | Culberson | Culberson | Tier 4 |  |  |  |  | 1079, 1090, 1095, 11079, 11132, 11224, 18695, 18719, 18727 | Y |  |  |  | 98733 | 91851
89988 | McGee 345 kV Switch | Construct new 345 kV switch to connect generator |  | Wolf | Meteor | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8830 | 2026-12-03 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 10009, 10012, 11010 | Y |  |  |  | 91898 | 89988
99150 | Establish Wags 345 kV Switch | Establish Wags 345 kV Switch |  | Wags | Wags | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6408 | 2026-12-03 |  | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3377, 3704, 3805 | Y |  |  |  | 99151 | 99150
102630 | BEPC_TPIT102630_Merryman |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-12-04 |  | 138 | 0 | 0 | 0 |  | Robertson |  | Tier 4 |  |  |  |  | 31, 32, 35, 36, 39, 53, 61, 79, 80, 1571, 1572, 11571 | Y |  |  |  | 102631 | 102630
104830 | WesternWind_Switch | Establish Western Wind Switch to interconnect Adamstown solar |  | Krum West Switch | Riley | Planned | M3502 | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 |  | 2026-12-06 |  | 345 | 0 | 0 | 0 |  | Wilbarger | Wilbarger | Tier 4 |  |  |  |  | 1730, 15121, 60225 | Y |  |  |  | 104831 | 104830
100018 | 23RPG032: San Antonio South Reliability II: Rebuild Spruce to Pawnee into a double circuit | This project is Phase 1 of the Spruce to Pawnee Double Circuit Rebuild. This Phase captures the completion of the new second circuit from Spruce to Pawnee with the final rating of circuit 2. |  | 5400 | 5725 | Under Construction | S-1067 | CPS/CPS, STEC | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0400 | 2026-12-08 |  | 345 | 45.83 | 45.83 | 0 |  | Bexar | Karnes | Tier 1 | 23RPG032 |  |  | 2024-04-23 | 5400, 5725 | Y |  |  |  | 100019 | 100018
61601 | Coody Crossing 345 kV Switch | Add Coody Crossing 345 kV Switch |  | Clear Crossing | Tecumseh Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8560 | 2026-12-10 |  | 345 | 0 | 0 | 0 |  | Throckmorton | Throckmorton | Tier 4 |  |  |  |  | 11418, 11419, 60241 | Y |  |  |  | 64014 | 61601
80376 |  |  |  | WEST WEATHERFORD | SHADY GROVE | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-12-11 |  | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 477, 512, 513, 515, 1589 | Y |  |  |  | 80377 | 80376
102767 | BEPC_TPIT102767_OldGarner |  |  |  |  | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-12-11 |  | 138 | 0 | 0 | 0 |  | Parker |  | Tier 4 |  |  |  |  | 510, 513, 1589 | Y |  |  |  | 102768 | 102767
99269 | Grady - Coronado Midstream Tap - Sale Ranch 138 kV line | Add Permian Basin Reliability Plan Upgrade ID L19. Upgrade the existing Grady - Coronado Midstream Tap - Sale Ranch 138-kV line |  | Grady | Sale Ranch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8834 | 2026-12-15 |  | 138 | 0 | 7.2 | 0 |  | Martin | Martin | Tier 3 |  |  |  |  | 23841, 23842, 23844 | Y |  |  |  | 99270 | 99269
66214 | Upgrade and convert Brownwood - Lake Brownwood 69 kV Line to 138 kV | Upgrade and convert Brownwood - Firerock 69 kV Line to 138 kV, decommission the Brownwood 69 kV Switch and Autotransformer |  | Brownwood | Lake Brownwood | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6164 | 2026-12-15 |  | 138 | 0 | 10.8 | 0 |  | Brown | Brown | Tier 4 |  |  |  |  | 1637, 1661, 1662, 1670, 3800, 6408 | Y |  |  |  | 92939 | 66214
99479A | Snyder - China Grove 69 kV Loop Converstion to 138 kV | Adds part of Permian Basin Reliability Plan Upgrade ID L23. Convert the existing Snyder - Scurry - China Grove and Snyder - Amoco Tap - China Grove 69-kV lines to 138-kV. This phase converts the existing Snyder - Lake Thomas 69 kV Line into 138 kV and reterminates into the new Bluff Creek 138 kV Switch. |  | China Grove | Bluff Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | PB_L23 | 2026-12-15 |  | 138 | 0 | 8 | 0 |  | Scurry | Scurry | Tier 1 |  |  |  |  | 1300, 1309, 1310, 1318, 1367, 1368, 1369, 1372, 10191, 10192, 10193, 10199, 10200, 10202 | Y |  |  |  | 99480 | 99479
91461A | Establish Tarantula 345 kV Switch | Establish Tarantula 345 kV Switch |  | Tarantula 345 kV Switch | Tarantula 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6412 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3344, 3380, 3381, 68091 | Y |  |  |  | 99548 | 91461
62434 | Sargent Road - Industrial Blvd 138 kV DCKT Line | Upgrade existing 138 kV Line |  | Sargent Road Switch | Industrial Blvd Switch | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4128 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2940, 2947, 2972, 2973, 2974, 2975, 2976, 2977, 2982 | Y |  |  |  | 99935 | 62434
72011A | Tonkawa - Ranger Camp 345 kV Line Rebuild | Tonkawa - Ranger Camp 345 kV Second Circuit Addition |  | Tonkawa | Ranger Camp | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2026-12-15 |  | 345 | 0 | 21.3 | 0 |  | Mitchell | Scurry | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 10049, 11048 | Y |  |  |  | 99961 | 72011
70900F | Roanoke Area Upgrades | Establish Roanoke_Exchange 138 kV Line |  | Roanoke Switch | Exchange Switch | Under Construction |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5281 M5144 M5146 M5148 | 2026-12-15 |  | 345 | 11.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 22RPG003 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 1845, 1851, 1871, 2036, 12077, 15100, 15115, 15118, 15855 | Y | N |  |  | 102864 | 70900
102849A | Union 138 kV Switch | Establish Union 138 kV Switch |  | Union | Union | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8608 | 2026-12-15 |  | 138 | 0 | 13.6 | 0 |  | Scurry | Scurry | Tier 4 |  |  |  |  | 1064, 1310, 1312, 1313, 1314, 10050, 18555, 180256 | Y |  |  |  | 105033 | 102849
105414 | Establish Phifer Creek Switch | Establish Phifer Creek Switch |  | Phifer Creek Switch | Phifer Creek Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6242 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 45, 3588, 3597, 3634, 3702, 3719 | Y |  |  |  | 105415 | 105414
99287 | Mascho (fka Clearfork) 345 kV Switch | Construct Mascho (fka Clearfork) 345 kV Switch approved as part of 24RPG015 |  | Mascho | Mascho | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8801 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Andrews | Andrews | Tier 1 | 24RPG015 | 2024-05-02 |  |  | 1158, 1287, 11157, 11270, 18879, 23876 | Y |  |  |  | 105997 | 99287
111223 | Oncor_MW_62445_BaseCamp(FKA_EglMnt)_138kV_SwitchRebuild | Rebuild existing Eagle Mountain 345/138 kV Switch and rename to Base Camp 345/138 kV Switch |  | Base Camp | Base Camp | Under Construction |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5261 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 3 | 22RPG039 |  |  |  | 1858, 1859, 1860, 11859, 11860, 11861, 11864, 11865, 11866 | Y | N |  |  | 111224 | 111223
91664 | White Mule (fka Elmar) 138 kV Substation Reconfiguration | Construct a new White Mule (fka Elmar) 138 kV Substation on the Quarry Field - Border 138 kV Line |  | White Mule | White Mule | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8804 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Loving | Loving | Tier 4 |  |  |  |  | 1093, 10156, 10157, 10256, 10257, 11073, 11089, 11189, 18672 | Y |  |  |  | 111490 | 91664
111796 | Establish Massey Lake 138 kV Switch | Establish Massey Lake 138 kV Switch |  | Massey Lake 138 kV Switch | Massey Lake 138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6400 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Anderson | Anderson | Tier 4 |  |  |  |  | 3281, 3297, 3499 | Y |  |  |  | 111797 | 111796
73436A | Rockhound - Connell 345 kV Double-Circuit Line | Rockhound - Sale Ranch 138 kV Double-Circuit Line |  | Rockhound | Sale Ranch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8718, R8807 | 2026-12-15 |  | 138 | 18 | 0 | 0 |  | Martin | Midland | Tier 1 | 24RPG020 | 2024-05-15 | 2025-11-19 |  | 10036, 10086, 10175, 10176, 10221, 11371, 23840, 23841 | Y |  |  |  | 112689 | 73436
22TPIT0000 | Parkway Substation T2 Replacement | Replace T2, 20 MVA with a 40 MVA 138-13.09 kV transformer |  | Parkway |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2026-12-15 | 2025-08-08 | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7611 | Y | N |  |  | 10680 | 3324
71187 | Reiter - Tesoro 345 kV Double-Circuit Line | Construct new 2.5-mile 345 kV double-circuit line from Tesoro to Reiter |  | Tesoro | Reiter | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8629 | 2026-12-15 |  | 345 | 5 | 0 | 0 |  | Midland | Ector | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 18540, 18544 | Y |  |  |  | 71189 | 71187
66202B | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Elkhart - Grapeland 69 kV Line |  | Elkhart | Grapeland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6182 | 2026-12-15 |  | 69 | 0 | 11 | 0 |  | Anderson | Houston | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3285, 3286, 3290 | Y |  |  |  | 71894 | 66202
66218B | Hillsboro - Italy 69 kV Line | Rebuild the Milford-Italy 69 kV Line |  | Milford | Italy | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4326 | 2026-12-15 |  | 69 | 0 | 0 | 0 |  | Ellis | Ellis | Tier 4 |  | 2021-04-23 | 2021-05-18 |  | 2337, 2338 | Y |  |  |  | 73690 | 66218
76572 | Temple - Temple Pecan 138 kV 2nd Circuit | Temple - Temple Pecan 138 kV 2nd Circuit |  | Temple | Temple Pecan Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6235 | 2026-12-15 |  | 138 | 0 | 4.4 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 3415, 3420 | Y |  |  |  | 76573 | 76572
76660 | Rebuild Temple Switch and install auto #2 | Rebuild Temple Switch and install auto #2 |  | Temple | Temple | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6197 | 2026-12-15 |  | 345 | 0 | 0 | 600 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3414, 3415, 3718 | Y |  |  |  | 76661 | 76660 | 2023-NC60
77803 | Cowpen 138kV station from TNMP submitted Cowpen/Silverleaf RPG |  |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-15 |  | 138 | 14.26 | 0 | 0 |  | Reeves | Reeves | Tier 1 | 23RPG013 | 2023-05-11 | 2023-11-27 | 2024-01-09 | 38023, 38027, 38043, 38045, 38055 | Y |  |  |  | 77804 | 77803
77807A | Silverleaf 138kV station from TNMP submitted Cowpen/Silverleaf RPG | Construct TNMP Silverleaf 345kV-138kV BAAH substation. Install three 750 MVA 345kV-138kV transformers. Cut both Pecos to Cedarvale 138kV lines and Bone Springs Tap 138kV line into Silverleaf 138kV bus. Construct three 345kV tie lines from TNMP Silverleaf 345kV to Oncor Rock Draw 345kV Switching Station (PMCR # 78044). |  |  |  | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-15 |  | 138 | 4.05 | 0 | 0 |  | Ward | Ward | Tier 1 | 23RPG013 | 2023-05-11 | 2023-11-27 | 2024-01-09 | 38091, 38143, 38145, 38165 | Y |  |  |  | 77808 | 77807
81034 | Lamesa - Willow Valley 138 kV Line | Rebuild Lamesa to Willow Valley 138 kV line. |  | Lamesa Switch | Willow Valley Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8654 | 2026-12-15 |  | 138 | 0 | 32.1 | 0 |  | Borden | Dawson | Tier 3 | 25RPG019 | 2025-06-16 | 2025-07-08 |  | 1163, 1301, 1307, 1308 | Y |  |  |  | 81035 | 81034
81418 | Reiter to Yarbrough 138 kV Line Rebuild | Rebuild the existing138 kV line from Reiter to Yarbrough |  | Reiter | Yarbrough | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8527 | 2026-12-15 |  | 138 | 0 | 27.2 | 0 |  | Ector | Crane | Tier 3 | 25RPG008 |  |  |  | 10006, 11111, 18545 | Y |  |  |  | 81419 | 81418
78361A | Lake Creek - Rattlesnake Road 345 kV Line | Establish Lake Creek Switch - St Johns 345 kV Line, rebuild the Lake Creek Switch - Rattlesnake Road 345 kV Line, and install second circuit from Lake Creek Switch - Rattlesnake Road Switch |  | Lake Creek | Rattlesnake Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6276 | 2026-12-15 |  | 345 | 0 | 5.1 | 0 |  | McLennan | McLennan | Tier 3 | 23RPG022 | 2023-08-01 | 2023-09-01 |  | 3384, 3399, 3409 | Y |  |  |  | 81575 | 78361
76312 | Establish Ramhorn 138kV Switch | Establish Ramhorn 138kV Switch and Ramhorn -Dunham 138 kV Line |  | Ramhorn | Dunham | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5007 | 2026-12-15 |  | 138 | 19 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 568, 1570, 1840, 1842 | Y |  |  |  | 82052 | 76312
64239 | Vineyard Switch-Cypress Waters Switch 138 kV Line | Construct a new 138 kV circuit from Vineyard to Cypress Waters |  | Cypress Waters Switch | Vineyard Switch | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5320 | 2026-12-15 |  | 138 | 7.4 | 0 | 0 |  | Dallas | Tarrant | Tier 3 | 24RPG019 |  |  |  | 2017, 2022, 2386, 12012, 12013, 15030, 15031, 15035, 15040, 15041 | Y |  |  |  | 86787 | 64239
87413 | Establish Fallstown Switch – Pleasant Valley/Fisher Road 138 kV Double-Circuit Line and Fallstown Switch – Ceramic/Wichita Falls PPG 138 kV Double-Circuit Line | Establish Fallstown Switch – Pleasant Valley/Fisher Road 138 kV Double-Circuit Line and Fallstown Switch – Ceramic/Wichita Falls PPG 138 kV Double-Circuit Line |  | Fallstown Switch | Pleasant Valley/Fisher Road | Planned |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | R4024 | 2026-12-15 |  | 138 | 0 | 10.7 | 0 |  | Wichita | Wichita | Tier 4 |  |  |  |  | 1450, 1483, 1484, 1485, 1488, 17005 | Y |  |  |  | 87414 | 87413
87017 | Riverton - Sandlake 138 kV Line Conversion 345 kV and Riverton - Sandlake 138 kV Line | Convert Riverton – Sandlake 138 kV Line to 345 kV and Establish Riverton – Sandlake 138 kV Line |  | Riverton | Sandlake | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8793 | 2026-12-15 |  | 345 | 39.9 | 0 | 0 |  | Ward | Reeves | Tier 1 | 24RPG010 | 2024-03-18 |  |  | 1011, 11083, 11084, 11097, 11098 | Y |  |  |  | 87679 | 87017
87768 | Pintail 138 kV Capacitor Bank | Install a 110.4 MVAR Capacitor Bank at Pintail 138 kV Switch |  | Pintail | Pintail | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6346 | 2026-12-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Williamson | Williamson | Tier 4 |  |  |  |  | 3692 | Y |  |  |  | 87769 | 87768
87804 | Establish Notus 345 kV Switch | Establish Notus 345 kV Switch |  | Notus Switch | Notus Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6371 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 2255, 3376, 68091 | Y |  |  |  | 87805 | 87804
71910A | Rebuild the Hillsboro - Elm Mott 69 kV Line | Rebuild the Elm Mott Switch - West 69 kV Line Section |  | Elm Mott 69 kV Switch | West 69 kV Substation | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6221 | 2026-12-15 |  | 69 | 0 | 9 | 0 |  | McLennan | McLennan | Tier 3 |  |  |  |  | 3408, 3526, 3527, 3528, 3529, 13525 | Y |  |  |  | 91605 | 71910
91881A | Medallion 138 kV Switch | Adds Medallion138 kV Switch |  | Midland | Midland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8821 | 2026-12-15 |  | 138 | 0 | 0 | 0 | 0,110.4 | Midland | Midland | Tier 4 |  |  |  |  | 1172, 1200, 10124, 11145, 11179 | Y |  |  |  | 91882 | 91881
92655 | Jersey 138 kV Switch | Jersey 138 kV Switch |  | Jersey Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3343 | 2026-12-15 |  | 138 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1822, 1823, 2844 | Y |  |  |  | 92656 | 92655
92847 | Norwood 345 kV Terminal Equipment | Upgrade Norwood Switch 345 kV Terminal Equipment |  | Norwood |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4425 | 2026-12-15 |  | 345 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 1928, 2406 | Y |  |  |  | 92851 | 92847
99413 | Establish Pivot 138/69 kV Switch | Construct Pivot 138/69 kV Switch approved as part of 24RPG015 |  | Lamesa | Pivot | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8800 | 2026-12-15 |  | 69 | 0 | 2.1 | 0 |  | Dawson | Dawson | Tier 1 | 24RPG015 | 2024-05-02 |  |  | 1163, 1164, 1362, 1363, 1364, 1389, 1390, 1391, 9400, 11362, 18881, 18882, 18920 | Y |  |  |  | 99414 | 99413
87653 | Stoplight (fka Bluff Creek) - Union 138 kV Line Rebuild | Rebuild the existing Stoplight (fka Bluff Creek) - Union 138 kV Line Rebuild |  | Stoplight (fka Bluff Creek) | Union | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9002 | 2026-12-16 |  | 138 | 0 | 16 | 0 |  | Scurry | Scurry | Tier 3 | 26RPG014 | 2026-04-07 | 2026-05-04 |  | 1310, 10200, 18555 | Y |  |  |  | 87654 | 87653
78361B | Lake Creek - Rattlesnake Road 345 kV Line | Establish Possum Trot 345 kV Switch |  | Possum Trot | Possum Trot | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6276 | 2026-12-16 |  | 345 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 3 | 23RPG022 | 2023-08-01 | 2023-09-01 |  | 3384, 3399, 3402, 3403, 3405, 3409, 3410, 3412, 3741, 3791, 13402, 13405, 13410 | Y |  |  |  | 91985 | 78361
91457A | Establish Drane 345 kV Switch | Establish Drane 345 kV Switch |  | Drane 345 kV Switch | Drane 345 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6410 | 2026-12-16 |  | 345 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3295, 3376, 68091 | Y |  |  |  | 91458 | 91457
100689 | Install a 50MVAr Capacitor Bank at Hill Country Substation |  |  | 5210 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1040 | 2026-12-17 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5210 | Y |  |  |  | 100690 | 100689
100670 | Install a 50MVAr Capacitor Bank at Cagnon Substation |  |  | 5055 |  | Planned |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-1039 | 2026-12-17 |  | 138 | 0 | 0 | 0 | 0,50 | Bexar |  | Tier 2 | 24RPG004 |  | 2024-07-26 |  | 5055 | Y |  |  |  | 100671 | 100670
82714 | Rebuild of Airport of Substation | Atlas Substation will be replacing Airport Substation. |  | Filter Plant (BPUB), South Plant (BPUB), and Southmost (STEC) | Atlas (BPUB) | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2026-12-22 | 2026-03-02 | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5789, 59420, 59440, 59500 | Y | N |  |  | 82715 | 82714
104658B | Establish Pathfinder 345 kV Switch | Pathfinder 345 kV Switch Gen Tie |  | Pathfinder | Piedra Solar | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6364 | 2026-12-22 | 2026-05-14 | 345 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3815, 155783 | Y |  |  |  | 105761 | 104658
99453X | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Hillje equipment on Ckt.44 STP to Hillje to increase thermal limits as part of FRM2 upgrades. |  | STP | Hillje | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-30 |  | 345 | 0 | 0 | 0 |  | Matagorda | Wharton | Tier 4 |  |  |  |  | 5915, 9063, 44200 | Y | N |  |  | 102623 | 99453
68205 | GENRAL to Garden Villas Rebuild | Rebuild and Reconductor portion of Ckt.12B Bringhurst (GENRAL) to Garden Villas to prepare for future 138kV Conversion |  | GENRAL | Garden Villas | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-30 | 2025-09-11 | 69 | 0 | 9.91 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42690, 47540 | Y | N |  |  | 68206 | 68205
61394 | Portilla: Construct New Distribution Station | Construct new distribution station on the Lon Hill to Warburton 138 kV line | In-Service Date Update | Portilla |  | Under Construction |  | AEP TCC | Damian Raab mlforcum@aep.com 918-599-2674 | DP21X0008 | 2026-12-30 |  | 138 | 1.5 | 0 | 0 | 0,14.4 | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8020, 8027, 8046, 8920, 8924 | Y |  |  |  | 61395 | 61394
78485C | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade portions of Ckt.05E Bellaire to Sharpstown to Hillcroft to increase thermal limits. |  | Bellaire | Hillcroft | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 3.09 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 47015, 48145, 48343 | Y | N |  |  | 98949 | 78485
93127 | Lueders: Construct New Distribution Station | Construct new distribution station on the Fort Phantom to Paint Creek 138 kV line between California Creek and Fort Phantom |  | Lueders |  | Planned |  | AEP TNC | Nelson Carroll myturner@aep.com 918-599-2437 | DR23N0002 | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Shackelford |  | Tier 4 |  |  |  |  | 6165, 6200, 60070 | Y | N |  |  | 93128 | 93127
99427 | Luther - Bulldog 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L20I. Upgrade the existing Luther - Bulldog 138-kV line |  | Luther | Bulldog | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8553 | 2026-12-31 |  | 138 | 0 | 18.6 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 23831, 23832, 23833 | Y |  |  |  | 99428 | 99427
99596 | Add Mosquito Lake Gen POI |  |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38043, 38053, 38055 | Y |  |  |  | 99597 | 99596
99791B | Additional Facility Ratings Methodology Phase 2 (FRM2) Substation Upgrades. | Upgrade Ckt.79C BIGBAY to BAYOU to increase thermal limits as part of FRM2 upgrades. |  | BIGBAY | BAYOU | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42160, 42180 | Y | N |  |  | 99807 | 99791
100020 | 23RPG032: San Antonio South Reliability II: Rebuild Spruce to Pawnee into a double circuit | This project is phase 2 of the Spruce to Pawnee Double circuit rebuild. Phase 2 captures the CPS owned portion of the existing Spruce to Pawnee circuit 1 being upgraded. The remaining STEC owned portion will be upgraded/completed at a later date. |  | 5400 | 5725 | Under Construction | S-1067 | CPS/CPS, STEC | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0400 | 2026-12-31 |  | 345 | 45.83 | 45.83 | 0 |  | Bexar | Karnes | Tier 1 | 23RPG032 |  |  | 2024-04-23 | 5400, 5725 | Y |  |  |  | 100021 | 100020
91847B | Hornsby Load Power Transformer Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8186 | 2026-12-31 |  | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7045, 7047, 7341 | Y |  |  |  | 102392 | 91847
99453W | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade STP equipment on Ckt.44 STP to Hillje to increase thermal limits as part of FRM2 upgrades. |  | STP | Hillje | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Matagorda | Wharton | Tier 4 |  |  |  |  | 5915, 9063, 44200 | Y | N |  |  | 102603 | 99453
99453J | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.98A Bellaire to Smithers to increase thermal limits as part of FRM2 upgrades. |  | Bellaire | Smithers | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44650, 47000 | Y | N |  |  | 102610 | 99453
99453K | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.72A Jeanetta to WA Parish to increase thermal limits as part of FRM2 upgrades. |  | Jeanetta | WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44000, 47300 | Y | N |  |  | 102611 | 99453
75780A | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy BESS (26INR0250) | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. |  | Elmaton | STP /WA Parish | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 5915, 43990, 44000 | Y | N |  |  | 102654 | 75780
78485D | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Bellaire to Ulrich to Hillcroft to increase thermal limits. |  | Bellaire | Hillcroft | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 6.41 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 48146, 48378, 48512 | Y | N |  |  | 98950 | 78485
69888A | Deepwater to Clinton Ckts.33B-33C Line Upgrades | Fully reconductor Ckt.33B Deepwater to Texpet Switchrack to Harrisburg ahead of future 138kV conversions. |  | Deepwater | Harrisburg | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 69 | 0 | 3.82 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40470, 40800, 41560 | Y | N |  |  | 91910 | 69888
87429 | Reconductor Wickett to Staghorn 138kV line. |  |  | TNMP Wickett (37981) | TNMP Staghorn (37990) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 12.05 | 0 |  | Ward | Ward | Tier 4 |  |  |  |  | 37981, 37990 | Y |  |  |  | 87430 | 87429
87346 | Upgrade Ckt 25 Jeanetta to Westwood to increase thermal limits | Upgrade Ckt 25 Jeanetta to Westwood to increase thermal limits |  | Westwood | Jeanetta | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 | 2026-07-14 | 138 | 0 | 2.16 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47310, 48417 | Y | N |  |  | 87347 | 87346
80632 | Install Kilgore 35kV Distribution Substation. Loop on Ckt.86B to create new Ckt.86 CHEVRON to Kilgore to LANGSTON | Install Kilgore 35kV Distribution Substation. Loop on Ckt.86B to create new Ckt.86 CHEVRON to Kilgore to LANGSTON |  | Kilgore | CHEVRON/LANGSTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 5.12 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40300, 40775, 44830 | Y | N |  |  | 87179 | 80632
85973 | Georgetown - Rivery Transmission Line Upgrade | LCRA TSC will upgrade T597 Georgetown - Rivery 138-kV transmission line to achieve a higher operational rating. |  | Georgetown Substation |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-762-3658 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7343, 7347 | Y |  |  |  | 85974 | 85973 | 2023-SC17
85950 | Alford Substation Addition | This project will construct the new 138-kV Alford Substation. Alford will be near the existing Oncor Midkiff Substation and the planned Oncor Catclaw Switch. Alford will connect T594 Midkiff to Skywest and T611 Benedum to Midkiff and will provide two (2) 138-kV POIs for Oncor Catclaw Switch. | [5 empty] | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Upton | Upton | Tier 4 | 23RPG019 | 2023-08-03 | 2023-08-25 |  | 1210, 10058, 71210, 71211, 71213 | Y |  |  |  | 85951 | 85950 | 2023-FW8
81368 | Rio Pecos: Upgrade 138 kV Terminals | Upgrade the Soaptree and Whitebaker 138 kV terminals at the Rio Pecos 138 kV station |  | Rio Pecos |  | Planned | TP2023625 | AEP TNC | Jennifer Kates twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Crockett |  | Tier 4 |  |  |  |  | 6601, 38445 | Y | N |  |  | 81369 | 81368
103427 | Rebuild/reconductor Ckt.94C Metals Switchrack to METALS as a Hardening upgrade | Rebuild/reconductor portions of Ckt.35 Bellaire to Ulrich as a Hardening upgrade. |  | Bellaire | Ulrich | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 2.13 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 41051, 48361 | Y | N |  |  | 103428 | 103427
87637A | Install (2) new 100 MVA distribution transformers at Liberty substation to serve customer load. | Install (1) new 100 MVA distribution transformer on ckt.03 at Liberty substation to serve customer load. |  | Liberty-new distribution tap | White Oak/ Greens Bayou Plant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40715, 40965, 48210, 48212 | Y | N |  |  | 109548 | 87637
70628 | Japhet 138kV Distribution Sub and Upgrades | Upgrade portions of 69kV Ckt.12 Garden Villas to Bringhurst to Clinton. Install new 138kV Japhet distribution substation. Move 69kV Bringhurst substation load to new Japhet substation and retire Bringhurst substation. Retire portions of Ckt.12 and convert the remaining portions of Ckt.12 to 138kV service. Loop new Japhet substation to create new 138kV Ckt.13 University to Japhet to Clinton. |  | Japhet | University/Clinton | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 4.4 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40350, 40352, 42690, 45070, 47540, 47700, 47760, 48764 | Y | N |  |  | 111111 | 70628
59197 | Mason to Mason Switch: Rebuild 69 kV Line | Rehab the Mason to Mason Switch 69 kV Line | Company Contact Update | Mason | Mason Switch | Planned | 1126 - 1304 | AEP TNC | Carol Matheny myturner@aep.com 918-599-2437 | 1871 | 2026-12-31 |  | 69 | 0 | 10.3 | 0 |  | Mason | Mason | Tier 4 |  |  |  |  | 6393, 6394, 6396, 6407, 60458 | Y | N |  |  | 59198 | 59197
66366 | Rebuild Brazoria - Retrieve 138kV with bundled 795 ACSS | Planned ISD is Q4 2024, but project design currently under internal review. |  | TNMP Brazoria (bus # 39600) | CenterPoint Retrieve (bus # 43170) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2026-12-31 |  | 138 | 0 | 6.17 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 39600, 43170 | Y |  |  |  | 66367 | 66366
72268 | New Ingram Rd 138kV Substation | Install a new 138kV transmission loop in conjunction with the S-0978 QTS Ingram Rd Substation project. The substation will be looped into the Potranco to TCC/Crossroads transmission line and connected to (2) 138kV line terminals. |  | 5241 | 5102, 5346 | Under Construction | T-0354 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0978 | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Bexar |  | Tier 4 |  |  |  |  | 5102, 5241, 5346 | Y |  |  |  | 72269 | 72268
73362 | Uribe: Construct New Distribution Station | Construct new distribution station on the Molina to Zapata 138 kV line | In-Service Date Update | Uribe |  | Planned |  | AEP TCC | Alex Perkins jlsolis@aep.com 361-881-5574 |  | 2026-12-31 | 2958101 | 138 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 8299, 8646, 8985, 8993, 80230 | Y |  |  |  | 73363 | 73362
75786 | This project will create a POI Bus (station) named Skydancer to interconnect 23INR0295 | This project will create a POI Bus (station) named Skydancer to interconnect 23INR0295 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Bosque | Bosque | Tier 4 |  |  |  |  | 68055, 68080, 68090 | Y |  |  |  | 75787 | 75786
76669 | Eiland - Elbow 138 kV Line Rebuild | Add Permian Basin Reliability Plan Upgrade ID L20H. Upgrade the existing Eiland - Elbow 138-kV line |  | Elbow | Eiland | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8665 | 2026-12-31 |  | 138 | 0 | 18.5 | 0 |  | Howard | Howard | Tier 3 |  |  |  |  | 23834, 23853 | Y |  |  |  | 77043 | 76669
80482 | North McAllen: Construct New 138 kV Terminal | Interconnect Carambola BESS to the North McAllen 138 kV station | IN-SERVICE | North McAllen |  | In-Service | TP2023631 | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 |  | 2026-12-31 | 2026-03-17 | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8632 | Y |  |  |  | 80483 | 80482
72044B | Clute 138kV Switching Station |  |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  |  | 104729 | 72044
78455 | Oasis 345kV Substation / SOHO BESS II (25INR0162) | Install SOHO BESS II at Oasis 345kV substation… Connect at the same generator lead as SOHO BESS (SOHO BESS II - 25INR0162) |  | Oasis |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 43035, 113321, 113323 | Y | N |  |  | 78456 | 78455
87637B | Install (2) new 100 MVA distribution transformers at Liberty substation to serve customer load. | Install (1) new 100 MVA distribution transformer on ckt.21 at Liberty substation to serve customer load. |  | Liberty-new distribution tap | Northside/ Greens Bayou Plant | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40710, 40966, 48211, 48216 | Y | N |  | Cost included in other entry | 109549 | 87637
75780B | Loop new Elmaton substation into Ckt.39A to create new Ckt.39 STP to Elmaton to WA Parish. Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy BESS (26INR0250) | Install generator lead from Elmaton (ELM) substation to DUFFY (DUF) / Duffy BESS (26INR0250) |  | Elmaton | DUFFY | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43990, 114362 | Y | N |  |  | 102655 | 75780
73352C | PH Robinson Area 138kV Upgrades | Increase thermal limits through the application of 110% Emergency ratings for Ckt.79C BIGBAY to BAYOU. Request customers to approve the 110% Emergency rating of relevant equipment at Bigbay substation on the Ckt.79C line position. Bayou substation equipment has been upgraded and meets the Minimum ratings as of April 2025. |  | BIGBAY | BAYOU | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:02 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42160, 42180 | Y | N |  |  | 73355 | 73352
72044D | Clute 138kV Switching Station |  |  |  |  | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:03 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 22RPG038 | 2022-11-04 | 2022-12-01 | 2022-12-01 |  | Y | N |  |  | 104731 | 72044
80468 | Conoco: Construct New 138 kV Terminal | Interconnect Isaac Solar to the Conoco 138 kV station | Company Contact and In-Service Date Update | Conoco |  | Planned |  | AEP TCC | William Edwards deevans@aep.com 918-599-2938 |  | 2026-12-31 12:00 |  | 138 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 8114, 113651 | Y |  |  |  | 80469 | 80468
110445 | STEC Ammonia Plant Load Project Phase 1 | Construct Kemper Bluff substation to serve large load and connect to AEP’s 138-kV Dupont Switching station via a 138-kV transmission line, with normal and emergency ratings of at least 427 MVA and 478 MVA, respectively, which will require a new right of way (ROW), approximately 3.4-mile |  | Kemper Bluff | Dupont | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-12-31 12:15 |  | 138 | 3.4 |  | 0 |  | Victoria | Victoria | Tier 1 | 25RPG012 |  | 2026-01-13 |  |  | Y | N |  |  | 110446 | 110445

## CompletedTPIT100126NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2026
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
81726 | Mobile substation | Project is to add a mobile substation next to Airport Substation tapping into the Transmission line that is Filter Plant to Airport Substation. Then connecting lines South Plant to Southmost by passing Airport Substation. This is due to Airport Substation being decommissioned in April. |  | 59420 Filter Plant, 59500 South Plant | Mobile substation, 5789 Southmost | Planned |  | BPUB | Luis Martinez lugmartinez@brownsville-pub.com 956-983-6212 |  | 2024-04-15 | 2025-05-22 | 138 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5789, 5946, 59420, 59430, 59460, 59500 | Y |  |  |  | 81727 | 81726
82210 | PMCR for LEAGUE CITY STATION REBUILD | [6 empty] | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2024-05-31 | 2025-01-24 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 38920 | Y |  |  |  | 82211 | 82210
73368 | Grey Well Draw - Buffalo 138 kV Second Circuit | Add Grey Well Draw - Buffalo 138 kV Second Circuit |  | Grey Well Draw | Buffalo | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8692 | 2024-12-15 | 2025-01-01 | 138 | 6 | 26.2 | 0 |  | Midland | Midland | Tier 3 |  |  |  |  | 10061, 11390, 11396, 23837, 23858 | Y |  |  |  | 87790 | 73368
77074 | Buda to Turnersville Storm Hardening | Rebuild single circuit section of Buda to Turnersville and reconductor with bundled 795 ACSR Conductor, 439 MVA. |  | Buda | Turnersville | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2024-12-31 | 2025-01-09 | 138 | 0 | 3.8 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7500, 70498 | Y | N |  |  | 77075 | 77074
72053 | Oasis 345kV Substation Expansion for SOHO BESS (23INR0419) | Expand 345kV Oasis substation for SOHO BESS (23INR0419). Reposition existing Ckts. 18B and 27B Oasis to Dow and Ckt.99E Meadow to Oasis. |  | Oasis |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 | 2026-01-07 | 345 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 | [5 empty] | Y | N |  |  | 72054 | 72053
73352B | PH Robinson Area 138kV Upgrades | Upgrade Ckt.79F PH Robinson to Seabrook to HANNAH to HUNTER to increase thermal limits |  | PH Robinson | Seabrook | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2024-12-31 00:01 | 2025-01-09 | 138 | 0 | 0 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42780, 42830, 42852, 48282 | Y | N |  |  | 73354 | 73352
90790 | Palafox: Construct New 138 kV Temporary Tap | Construct new temporary tap on the North Laredo Switch to Reveille 138 kV line between Barrera and North Laredo Switch | IN-SERVICE |  |  | In-Service |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 | TP2024132 | 2025-01-18 | 2025-01-18 | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8108, 8909, 88000 | Y |  |  |  | 90791 | 90790
78167 | Add 2nd autotransformer at Trumbull | Add 2nd autotransformer at Trumbull |  | Trumbull | Trumbull | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-01-23 | 2025-02-20 | 69 | 0 | 0 | 40 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 221, 222 | Y |  |  |  | 78168 | 78167
76682 | Add Capacitor Bank at Savanna 138 kV Substation | Add Capacitor Bank at Savanna 138 kV Substation |  | Savanna |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8694 | 2025-01-31 | 2025-01-31 | 138 | 0 | 0 | 0 | 0,55.2 |  |  | Tier 4 |  |  |  |  | 10025, 23867, 23870 | Y |  |  |  | 81462 | 76682
73371F | BP24 Sub Upgrades | Upgrade Jeanetta to WA Parish Ckt.64A to increase thermal limits |  | Jeanetta | WA Parish | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-01-31 00:05 | 2025-06-05 | 138 | 0 | 0 | 0 |  | Harris | Fort Bend | Tier 4 |  |  |  |  | 44005, 47300 | Y | N |  |  | 89975 | 73371
73371H | BP24 Sub Upgrades | Upgrade White Oak to Jeanetta Ckt.72B to increase thermal limits |  | White Oak | Jeanetta | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-01-31 00:07 | 2025-02-11 | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 46600, 47300 | Y | N |  |  | 89977 | 73371
67919 | Avanzada: Construct New 345 kV Station | Interconnect Outpost Solar to the Lobo to Fowlerton 345 kV line | IN-SERVICE | Avanzada |  | In-Service |  | ETT | Zachary Lachiusa jlsolis@aep.com 361-881-5574 |  | 2025-02-14 | 2025-02-14 | 345 | 0.1 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 5709, 80219, 80235 | Y |  |  |  | 67920 | 67919
6216 | Bartlett Switch to Bartlett | Bartlett Switch to Bartlett |  | Bartlett Switch | Bartlett | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-02-14 12:00 | 2025-05-12 | 69 | 0 | 2.7 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 114, 118 | Y |  |  |  | 13941 | 6216
50725 | Lean Clay 138 kV Switch | Construct a new 138 kV switch |  | Culberson | Sand Lake | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8658 | 2025-02-15 | 2025-02-01 | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 1097, 11078, 11086 | Y |  |  |  | 82894 | 50725
81605 | Kolb Lake 138 kV POD | Establish Kolb Lake 138 kV POD |  | Kolb Lake POD | Kolb Lake POD | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6229 | 2025-02-15 | 2958101 | 138 | 0 | 0 | 0 |  | Angelina | Angelina | Tier 4 |  |  |  |  | 3307, 3340, 3346, 3347, 3747 | Y |  |  |  | 81606 | 81605
72876A | Provide 138 kV POD for Skybox at Teal Switch |  |  | Teal | Skybox | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6259 | 2025-02-15 | 2958101 | 138 | 0.2 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3362, 3371 | Y |  |  |  | 72877 | 72876
70223 | Mont - Pilot Grove Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 8-mile Mont ¿ Pilot Grove (T140) 138-kV transmission line. |  | Mont | Pilot Grove | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-02-17 | 2025-02-21 | 138 | 0 | 8 | 0 |  | Lavaca | Lavaca | Tier 4 |  |  |  |  | 7234, 7235, 7249 | Y | Y |  |  | 70224 | 70223
79683 | Add Branch between Padua and Sommers |  |  | 5395 | 170722 | Planned | S-0969, T-0327 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-02-18 | 2025-02-18 | 138 | 2.06 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5395, 170722 | Y |  |  |  | 79684 | 79683
54220 | Brazos' member will build McFarland substation, Brazos will install POI Picard | Brazos' member will build McFarland substation, Brazos will install POI Picard |  | Picard | Picard | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2025-02-23 | 2025-05-18 | 138 | 0 | 0 | 0 |  | Parker | Parker | Tier 4 |  |  |  |  | 483, 485, 486, 527 | Y |  |  |  | 54221 | 54220
76622 | Expand Peters 138kV substation for Walstrom BESS (22INR0540). | Expand Peters 138kV substation for Walstrom BESS (22INR0540). |  |  |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-02-28 | 2025-02-28 | 138 | 0 | 0 | 0 |  | Austin | Austin | Tier 4 |  |  |  |  | 46220, 171382 | Y | N |  |  | 76623 | 76622
78374 | Rockhound 345/138 kV Switch | Construct a new 345/138 kV Switch |  | Falcon Seaboard | Midland East | Under Construction |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8705 | 2025-03-01 | 2025-02-14 | 345 | 0 | 0 | 1200 |  | Midland | Martin | Tier 3 | 24RPG002 | 2024-01-11 |  |  | 1021, 1025, 10062, 10063, 10064, 10065, 11390, 23837, 23843, 23858 | Y |  |  |  | 78375 | 78374
61392 | Bergheim - Fair Oaks Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T238 Bergheim to Fair Oaks 138-kV and T656 Bergheim to Kendall 345-kV 4.1-mile double-circuit transmission line by replacing the aging conductor. |  | Bergheim | Fair Oaks Ranch/Kendall | Planned | 61406, 61358, 61350, 61234, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-03-12 | 2025-03-12 | 345 | 0 | 4.1 | 0 |  | Comal | Kendall | Tier 4 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7169, 7170, 7770 | Y | N |  |  | 61393 | 61392
45501 | Eldorado Live Oak to Sonora: Rebuild 69 kV line | Rehab Eldorado Live Oak to Sonora 69 kV line | IN-SERVICE | Eldorado Live Oak | Sonora | In-Service | 982 - 1160 | AEP TNC | David Baker twang1@aep.com 918-599-2635 | 2769 | 2025-03-12 01:00 | 2025-03-12 | 69 | 0 | 23.92 | 0 |  | Schleicher | Sutton | Tier 3 | 18RPG012 | 2018-12-18 | 2019-01-17 |  | 6054, 6498, 6503, 6505, 6509, 6510, 6513 | Y | N |  |  | 65530 | 45501
72500 | Rio Lago - New 138kV Substation | Loop new 138kV substation into the existing 138kV Bandera to Verde Creek line and install 40MVA distribution transformer. The new substation will be located approximately 1.64 miles from Bandera substation (23INR0078) |  | Bandera | Verde Creek | Planned |  | BEC | Jhonatan Guerrero Rivera j.rivera@banderaelectric. 830-612-0048 |  | 2025-03-17 | 2025-03-21 | 138 | 0.1 | 0 | 0 |  | Bandera | Bandera | Tier 4 |  |  |  |  | 7146, 7436, 7438 | Y | N |  |  | 72501 | 72500
47541 | Crane Circuit Breaker Addition | Provide transmission service to American Electric Power at Crane Substation. Adding one (1) breaker and associated equipment needed to connect the AEP-owned Crane to Kinnison 138-kV transmission line. |  | Crane Substation | Crane Substation | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2025-03-17 02:00 | 2025-02-26 | 138 | 0 | 0 | 0 |  | Crane | Crane | Tier 4 |  |  |  |  | 76615 | Y | N |  |  | 78402 | 47541
73895 | Sunglow Substation Addition | This project provides a point of interconnection for a new battery energy storage resource at a new 138-kV Sunglow Substation between LCRA TSC T627 and LCRA Rosita Creek Substation. |  | Sunglow |  | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-03-28 | 2025-03-12 | 138 | 0 | 0 | 0 |  | Maverick |  | Tier 4 |  |  |  |  | 8260, 78015, 78016 | Y | N |  |  | 73896 | 73895
69890 | Bailey 345kV Substation Expansion for Ray Gulf Wind (22INR0517) | Expand 345kV Bailey substation for Ray Gulf Wind generator interconnection (22INR0517) |  | Bailey |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-03-31 | 2025-07-08 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44040, 114215 | Y | N |  |  | 69891 | 69890
61234 | Antler - Bergheim Transmission Line Upgrade | This project will increase the reliability and capacity of transmission facilities on the T493 Antler to Bergheim 138-kV and T389 Bergheim to Hays Energy 345-kV 7.2-mile double-circuit transmission line by replacing the aging conductors from Antler to Bergheim substations. |  | Antler | Bergheim | Planned | 61406, 61358, 61392, 61350, 61362, 61356, 61400, 61402, 61404 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-04-01 | 2025-02-24 | 345 | 0 | 7.2 | 0 |  | Comal | Comal | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7043, 7170, 7171, 7770 | Y | N |  |  | 78331 | 61234
71982 | Upgrade Orange Grove station | Upgrade Orange Grove stationto ring bus |  | Orange Grove | Orange Grove | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-04-01 | 2025-04-01 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 | [5 empty] | Y |  |  |  | 71983 | 71982
81354 | GSEC_9452_Add_Snodgrass_Sub | Adding new Snodgrass sub to connect to AEP's Juncus Station. | Add New Load and Sub |  |  | In-Service |  | GSEC | John Vara jvara@gsec.coop 806-349-5228 |  | 2025-04-01 | 2025-04-01 | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 9452, 60002 | Y | Y |  |  | 81355 | 81354
71954 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 | Adds new Talitha substation and short line from Talitha to Orange Grove 138 |  | Orange Grove | Talitha | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-04-01 | 2025-04-01 | 138 | 0.73 | 0 | 0 |  | Jim Wells | Jim Wells | Tier 4 |  |  |  |  | 5660, 5661 | Y |  |  |  | 71955 | 71954
79990 | Add new Yellow Wolf station for 21INR0428 |  |  | Limestone | Gibbons Creek | Under Construction |  | CTT | Christina Minchew cminchew@lspower.com 636-698-8443 |  | 2025-04-08 | 2025-04-23 | 345 | 0 | 0 | 0 |  | Leon |  | Tier 4 |  |  |  |  | 967, 46020, 79007 | Y | N |  |  | 79991 | 79990
4323 | CPSE_Brooks_MLSE | Upgrade terminal at Brooks and ensure a rating of 2000 A (minimum) at both Braunig and Brooks terminals |  | Braunig | Brooks | In-Service |  | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0669 | 2025-04-10 | 2025-04-10 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5045, 5394 | Y | Y |  |  | 11875 | 4323
72576A | Lago Vista to Nameless Transmission Line Upgrade | Rebuild and upgrade Nameless to Lago Vista with double-circuit capable structures. Install 1 ckt with bundled 795 kcmil conductor (440 MVA). Final span of conductor and terminal equipment at Nameless will be upgraded to 440 MVA with ERCOT project #72576B. (Replaces ERCOT Project # 61277A) | 1/10/2023: Added information to clarify timing for final circuit rating upgrade. | Lago Vista | Nameless | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2025-04-15 | 2025-04-01 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70352, 70526 | Y | N |  |  | 72577 | 72576
70922 | Chief Brady - Georgetown Transmission Line Upgrade | LCRA TSC will upgrade T355 Chief Brady - Georgetown 138-kV transmission line to achieve a higher operational rating. |  | Chief Brady | Georgetown | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-04-18 | 2025-04-18 | 138 | 0 | 3 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 7343, 7366 | Y | N |  |  | 70923 | 70922 | 2023-SC17
71956 | Elgin Switch Substation Upgrade | LCRATSC will install a new three-breaker ring bus substation at Elgin Switch. Oncor will relocate its facilities from Elgin Switch to Brushy Creek. Install a temporary shoo-fly between T668 and T260 to maintain through-path during construction. |  | Elgin Switch |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-04-24 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 3541, 3650, 7321, 7324, 7338 | Y | N |  |  | 73564 | 71956
71930 | Upgrade RIOHONDO to BURNS line | Upgrade RIOHONDO to BURNS line to be 478MVA capable |  | Rio Hondo | Burns | Under Construction | 7192671928 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-05-01 | 2025-07-01 | 138 | 0 | 12.2 | 0 |  | Cameron | Cameron | Tier 4 |  |  |  |  | 5763, 8319 | Y |  |  |  | 71931 | 71930
81544 | GSEC_9466_Add_CampSprings_Sub | Add Big Country's Camp Springs Sub 9MW | ISD exceeds NMMS model load date |  |  | In-Service |  | GSEC | John Vara jvara@gsec.coop 806-349-5228 |  | 2025-05-01 | 2025-07-01 | 138 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 9466, 68012 | Y |  |  |  | 81545 | 81544
80753 | LST_Claytonville to Camp Springs 138 kV line additions | LST_Claytonville to Camp Springs 138 kV line additions |  | Claytonville 138 |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2025-05-01 | 2025-03-31 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68009, 68012 | Y |  |  |  | 80754 | 80753
69345 | Limmer Substation Addition | Construct a new LCRA TSC-owned Limmer Substation in the Hutto to Zorn 345 kV line approximately 3 miles east of Hutto. Limmer Substation will be installed initially as a five-breaker 345 kV breaker-and-a-half arrangement. |  | Zorn, Hutto | Limmer | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-01 | 2025-05-01 | 345 | 0 | 0 | 0 |  | Williamson | Travis | Tier 3 | 22RPG027 | 2022-08-29 | 2022-09-27 |  | 3696, 7042, 7340, 7341 | Y | Y |  |  | 78338 | 69345
89905 | Addition of facilities installed at OCI ALAMO 1 substation to install a Gen-Tie to Power Soportar Battery Energy Storage System (BESS). |  |  | 5007 | 171082 | Planned | S-1023, T-0363 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-01 | 2025-05-07 | 138 | 0.06 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 5007, 171082 | Y |  |  |  | 89906 | 89905
72588A | Trading Post to Cedar Valley Storm Hardening |  |  | Trading Post | Cedar Valley | Planned |  | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2025-05-05 | 2025-05-01 | 138 | 0 | 6.8 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70505, 70506 | Y | N |  |  | 72589 | 72588
67992D | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade | Upgrade Hamilton to Medical Center 138KV Line to 469MVA |  | 5187 | 5300 | In-Service |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-09 | 2025-04-16 | 138 | 0 | 1.02 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5187, 5300 | Y |  |  |  | 67994 | 67992
89984 | Kangaroo 345 kV Switch | Establish Kangaroo 345 kV Switch |  | Blackwater Draw Switch | Ogallala | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3030 | 2025-05-14 | 2025-06-12 | 345 | 0 | 0 | 0 |  | Castro | Castro | Tier 4 |  |  |  |  | 23912, 23915, 23920, 144842 | Y |  |  |  | 89985 | 89984
75889 | Add_Wellborn_Load |  |  | Wellborn |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-05-14 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Brazos |  | Tier 4 |  |  |  |  | 32895 | Y |  |  |  | 89951 | 75889
66569 | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch | Rebuild and reconfigure the existing Mulberry Creek 345 kV Switch |  | Mulberry Creek | Mulberry Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9022 | 2025-05-15 | 2025-05-15 | 345 | 0 | 0 | 0 |  | Jones | Jones | Tier 3 | 21RPG021 | 2021-12-17 | 2022-01-12 |  | 1435, 1459, 6235, 11420 | Y |  |  |  | 81422 | 66569
69552B | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 345 kV Switch, Autotransformers, and 345 kV Tie Lines to Limmer (LCRA) |  | Teal | Teal | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6165 | 2025-05-15 | 2025-05-30 | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 3696, 7341, 13363, 13364, 25090 | Y |  |  |  | 88554 | 69552
76578 | Upgrade the Temple Pecan - Temple Elm 138 kV Double-Circuit Line | Upgrade the 5-mile Temple Pecan - Temple Elm 138 kV Double-Circuit Line |  | Temple Pecan Creek | Temple Elm Creek | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6234 | 2025-05-15 | 2025-06-05 | 138 | 0 | 10 | 0 |  | Bell | Bell | Tier 1 | 24RPG001 |  |  |  | 3420, 13662 | Y |  |  |  | 76579 | 76578 | 2023-NC61
72007 | Ranger Camp 345/138/69 kV Switch | Construct a new 345/138/69 kV Switch to replace existing Morgan Creek Switch |  | Ranger Camp 345/138 kV Switch | Ranger Camp 345/138 kV Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3024 | 2025-05-15 | 2025-04-16 | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1025, 1030, 1032, 1033, 1064, 1189, 1190, 1348, 1378, 10049, 10050, 10051, 10052, 10134, 11004, 11035, 11332, 11342, 11393 | Y |  |  |  | 81363 | 72007
78365 | Fryers Creek 138/69 kV Switch | Construct the new Fryers Creek 138/69 kV Switch |  | Boggy Creek | Boggy Creek | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6295 | 2025-05-15 | 2958101 | 138 | 5 | 0 | 0 |  | Bell | Bell | Tier 1 |  |  |  |  | 132, 3415, 3493, 3496, 3607, 3643, 3644, 3645, 3689, 3726 | Y |  |  |  | 81558 | 78365
70538 | Pilot Grove - Yoakum Gartner Road Transmission Line Overhaul | Perform an overhaul on the 7.8 mile T614 Pilot Grove (structure #8/2) - Yoakum Gartner Road 138-kV transmission line. Structure #8/2 and the remaining portion of T614 will be overhauled as part of the FY23 Mont - Pilot Grove Transmission Line Overhaul project. |  | Pilot Grove | Yoakum Gartner | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-05-15 | 138 | 0 | 7.8 | 0 |  | Lavaca | DeWitt | Tier 4 |  |  |  |  | 7234, 7242 | Y | N |  |  | 70539 | 70538
70704A | Florence Substation Addition |  |  | Andice | Glasscock | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6320 | 2025-05-15 | 2025-05-15 | 138 | 0 | 0 | 0 |  | Williamson |  | Tier 4 |  |  |  |  | 7521, 7523, 70522 | Y | N |  |  | 70705 | 70704
73793 | McCarty Lane - Zorn Transmission Line Storm Hardening | Perform storm hardening on the 4.2 mile McCarty Lane - Zorn (T202) 138-kV transmission line. T202 is double-circuited with McCarty Lane - Beback - Zorn (T201) 138-kV transmission line. |  | McCarty Lane East | Zorn | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-05-01 | 138 | 0 | 8.58 | 0 |  | Hays | Guadalupe | Tier 4 |  |  |  |  | 7180, 7182, 7187 | Y | N |  |  | 73794 | 73793
73838 | Redwood - San Marcos Transmission Line Upgrade | LCRA TSC will upgrade T200 Redwood - San Marcos 138-kV transmission line to obtain a higher operational rating. |  | Redwood | San Marcos | Planned |  | LCRATSC | Dylan PReas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-05-13 | 138 | 0 | 2.5 | 0 |  | Hays | Hays | Tier 4 | 24RPG034 | 2024-11-07 | 2024-12-03 |  | 7188, 7192 | Y | N |  |  | 73839 | 73838
77041 | Leon Switch - Putnam Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 8.9-mile Leon Switch – Putnam (T727) 138-kV transmission line between Leon Switch existing structure #1/1 and Putnam existing structure #9/10. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Leon Switch | Putnam | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-05-21 | 138 | 0 | 8.95 | 0 |  | Eastland | Eastland | Tier 4 |  |  |  |  | 1624, 6310 | Y | Y |  |  | 77042 | 77041
85959 | San Marcos - Strahan Transmission Line Upgrade | LCRA TSC will upgrade T230 San Marcos - Strahan 138-kV transmission line to achieve a higher operational rating. |  | San Marcos (7192) | Strahan (7193) | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-04-30 | 138 | 0 | 1.25 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7192, 7193 | Y |  |  |  | 85960 | 85959
70704B | Florence Substation Addition | Fixes Florence bus disconnection issue by removing temporary equipment associated with FLORENCE substation cut-in |  |  |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6320 | 2025-05-15 | 2025-05-15 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7521, 7523, 70522 | Y |  |  |  | 90388 | 70704
72870 | Soda Lake Generator Circuit Breaker Addition | This project provides a point of interconnection for a new 202.99 MW Solar Energy at the 138-kV Soda Lake Substation by reconfiguring the Soda Lake Substation to breaker-and-a-half to add new 138-kV line terminal and one POI structure to accommodate the new interconnection. Update contingencies |  | Soda Lake |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-05-15 | 2025-06-09 | 138 | 0 | 0 | 0 |  | Crane |  | Tier 4 | [5 empty] | Y | N |  |  | 78298 | 72870
71199 | Yucca Drive - Moss 138 kV Line | Rebuild existing 138 kV line |  | Yucca Drive | Moss | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R9047 | 2025-05-15 | 2025-05-30 | 138 | 0 | 35.2 | 0 |  | Ector | Winkler | Tier 4 |  |  |  |  | 1009, 1019, 11015, 11128, 18663 | Y |  |  |  | 76384 | 71199
78371 | Richardson East Switch – Richardson Spring Creek 138 kV Line Section | Upgrade Richardson East Switch – Richardson Spring Creek 138 kV Line Section |  | Richardson East | Richardson Spring Creek | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4402 | 2025-05-15 | 2025-05-21 | 138 | 0 | 2.1 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2689, 2690 | Y |  |  |  | 78372 | 78371
78382 | Adds Capacitor Bank at White Dune | Adds Capacitor Bank at White Dune |  | White Dune |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8669 | 2025-05-15 | 2025-06-30 | 138 | 0 | 0 | 0 | 0,110.4 | Winkler | Winkler | Tier 4 |  |  |  |  | 18692 | Y |  |  |  | 80906 | 78382
81358A | Grindstone 138 kV Switch |  |  | Grindstone Switch | Grindstone Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1754 | 2025-05-15 | 2025-05-15 | 138 | 0 | 0 | 0 |  | Palo Pinto | Palo Pinto | Tier 4 |  |  |  |  | 1569, 1571, 1575, 1592, 1599, 154402 | Y |  |  |  | 81359 | 81358
82806 | Establish Long Hollow 345 kV Switch (POI for Pinnington Solar) | Establish Long Hollow 345 kV Switch (POI for Pinnington Solar) |  | Graham Plant Switch | Parker Switch | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3509 | 2025-05-15 | 2025-06-30 | 345 | 0 | 0 | 0 |  | Young | Parker | Tier 4 |  |  |  |  | 1430, 1436, 1506 | Y |  |  |  | 82807 | 82806
82808 | Stranger 345 kV Switch | Establish Stranger 345 kV Switch |  | Stranger Switch | Stranger Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6320 | 2025-05-15 | 2025-05-15 | 345 | 0 | 0 | 0 |  | Limestone | Limestone | Tier 4 |  |  |  |  | 3390, 3711, 3721, 154063 | Y |  |  |  | 82809 | 82808
82810A | Olympus 138 kV Switch | Establish Olympus 138 kV Switch |  | Olympus Switch | Olympus Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6330 | 2025-05-15 | 2025-05-08 | 138 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3125, 3127, 3454, 3466, 3723 | Y |  |  |  | 82811 | 82810
52247 | Marrs - Handley 69 kV Line Conversion to 138 kV | Convert the existing Marrs-Handley 69 kV line to 138 kV operation |  | Marrs SW | Handley | Under Construction |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5222 | 2025-05-15 | 2025-05-30 | 138 | 2.2 | 13 | 0 |  | Tarrant | Tarrant | Tier 4 |  |  |  |  | 1951, 1952, 1967, 1968, 1969, 2158, 2159, 2160, 2162, 11950, 11951, 11952, 11967 | Y |  |  |  | 86795 | 52247
87285 | Establish Stouts Creek 345 kV Switch | Establish Stouts Creek 345 kV Switch |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R984 | 2025-05-15 | 2025-06-13 | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1696, 2514, 12464, 120976 | Y |  |  |  | 87286 | 87285
87760 | Full House 138 kV Switch | Establish Full House 138 kV Switch for Lucky Bluff BESS |  | Full House | Full House | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6327 | 2025-05-15 | 2025-05-08 | 138 | 0 | 0 | 0 |  | Erath | Erath | Tier 4 |  |  |  |  | 1636, 1641, 1652, 153852 | Y |  |  |  | 87761 | 87760
89982 | Wrangler 345 kV Switch | Establish 345 Switch |  | Cottonwood | White River | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3032 | 2025-05-15 | 2025-05-16 | 345 | 0 | 0 | 0 |  | Motley | Motley | Tier 4 |  |  |  |  | 23919, 23922, 59904 | Y |  |  |  | 89983 | 89982
91060 | Establish Flying Tiger 138 kV Switch | Establish Flying Tiger 138 kV Switch |  | Flying Tiger 138 kV Switch |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3302 | 2025-05-15 | 2025-04-17 | 138 | 0 | 0 | 0 |  | Lamar | Lamar | Tier 4 |  |  |  |  | 1693, 1700, 2163 | Y |  |  |  | 91061 | 91060
91455 | Establish Dorsett 345 kV Switch |  |  | Dorsett 345 kV Switch | Dorsett 345 kV Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6323 | 2025-05-15 | 2025-05-08 | 345 | 0 | 0 | 0 |  | Rusk | Rusk | Tier 4 |  |  |  |  | 3100, 3105, 3339, 121043 | Y |  |  |  | 91529 | 91455
62666A | Upgrade and convert McGregor - Waco West Line | Rebuild and Upgrade McGregor Phillips - Waco West Switch 69 kV Line |  | Waco West | McGregor Phillips | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6172 | 2025-05-15 | 2025-12-15 | 69 | 0 | 17.5 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3370, 3437, 3584 | Y |  |  |  | 93105 | 62666
72004 | Cat Claw 138 kV Dynamic Reactive Device (formerly Midkiff) | Install a new Dynamic Reactive Device at Cat Claw (formerly Midkiff) |  | Cat Claw | Cat Claw | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8675 R8680 R8695 | 2025-05-15 | 2025-05-12 | 138 | 0 | 0 | 0 | -250250 | Upton | Upton | Tier 3 |  |  |  |  | 1210, 1217, 10058, 10059, 10060, 11218, 11345, 23870, 23871 | Y |  |  |  | 73345 | 72004
71980 | Watermill 345 kV Switch | Rebuild the existing Watermill 345 kV Switch |  | Watermill |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4012 | 2025-05-15 | 2958101 | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 | 23RPG017 |  |  |  | 2398, 2427, 2428, 2429, 2432, 2435, 2466, 2847, 2997, 3159, 12429 | Y |  |  |  | 76731 | 71980
81383 | Edwards Tap - Sandhills Tap 138 kV Line Rebuild | Edwards Tap - Sandhills Tap 138 kV Line Rebuild |  | Odessa EHV | Wolf | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8528 | 2025-05-15 | 2025-07-24 | 138 | 0 | 11.71 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 1102, 1103, 1110 | Y |  |  |  | 81384 | 81383
62068 | Lakeway - Marble Falls Transmission Line Storm Hardening | Increase the reliability of transmission facilities on the T497 Lakeway - Marble Falls 23-mile 138-kV transmission line. |  | Lakeway | Marble Falls | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2025-05-16 | 2025-05-16 | 138 | 0 | 23 | 0 |  | Travis | Burnet | Tier 4 | 22RPG031 | 2022-10-12 | 2022-11-03 |  | 7348, 7349, 7351, 7356, 7474, 7476, 7538, 7540 | Y | N | 22RPG031 reclassified as Tier 4 neutral by RPG review on 11/03/2022 |  | 62069 | 62068
66447 | Reforzar: Construct New 345 kV Station | Construct a new 345 kV station on the Lon Hill to North Edinburg 345 kV line | IN-SERVICE | Reforzar |  | Under Construction |  | AEP TCC | Chase Isaac jlsolis@aep.com 361-881-5574 | TP2022035 | 2025-05-16 | 2025-05-16 | 345 | 0 | 0 | 0 |  | Brooks |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 8455, 8905, 80078 | Y |  |  |  | 67317 | 66447
75887 | Add_SteepHollow_Load |  |  | Steep Hollow |  | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2025-05-19 | 2025-05-19 | 138 | 0 | 0 | 0 |  | Brazos | Brazos | Tier 4 | [5 empty] | Y |  |  |  | 91905 | 75887
72037A | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | New 345kV Seabreeze (SEB) substation for generator interconnection to Tanglewood Solar (23INR0054). Loop Ckt.27B into Seabreeze substation to create new Ckt.27 DOW to Seabreeze to Oasis. |  | Seabreeze | DOW/Oasis | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-21 | 2025-05-21 | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42110, 42500, 43020, 43035, 43150, 43300 | Y | N |  |  | 100208 | 72037
72037B | Seabreeze 345kV Substation for Tanglewood Solar (23INR0054) | Install generator lead from Seabreeze (SEB) substation to TANGLE (TNG) customer substation (23INR0054). |  | Seabreeze | TANGLE | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-21 00:01 | 2025-05-21 | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 43020, 113341, 113345 | Y | N |  | Cost included in main phase | 100209 | 72037
88063 | Valley South 345 kV Switch New POI (Platinum Storage) | Install new POI |  | Valley South |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3069 | 2025-05-22 | 2025-05-22 | 345 | 0 | 0 | 0 |  | Fannin |  | Tier 4 | [5 empty] | Y |  |  |  | 88064 | 88063
67992A | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade | Shepherd Rd to Valley Rd 138kV line Reconfiguration. |  | 5378, 5465 | 5320 | In-Service |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-29 | 2025-04-07 | 138 | 0.03 | 0 | 0 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5230, 5378, 5465 | Y |  |  |  | 72403 | 67992
67992C | CPSE_345KV_Howard_Switching_Station,CPSE_Hamilton_to_MedCtr_Upgrade | Looping of 345KV Howard Rd switching station into existing Cagnon to AVR and Cagnon to Spruce 34KV lies. The switching station will have 2 600MVA 345KV/138KV autotransformers. |  | 5056 | 5400 and 5475 | In-Service |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-05-29 | 2025-04-07 | 345 | 0.88 | 0 | 1200 |  | Bexar | Bexar | Tier 3 |  |  | 2021-12-16 |  | 5056, 5230, 5231, 5400, 5475 | Y |  |  |  | 67993 | 67992
6719B | Twelvemile Substation Addition | Cuts into the second circuit |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018769 | 2025-05-30 | 2025-06-17 | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 | 21RPG001 | 2021-02-21 | 2021-06-10 |  | 7053, 76008, 76015 | Y |  |  |  | 90722 | 6719
6719A | Twelvemile Substation Addition | Cuts into first circuit |  | Bakersfield | Schneeman Draw | In-Service |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 | 1018769 | 2025-05-30 | 2025-06-17 | 345 | 0 | 0 | 0 |  | Pecos | Crockett | Tier 4 | 21RPG001 | 2021-02-21 | 2021-06-10 |  | 7053, 76008, 76015 | Y | N |  |  | 58408 | 6719
78485A | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Westchase to Hayes to increase thermal limits. |  | Westchase | Britmoore | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-30 | 2025-02-07 | 138 | 0 | 6.21 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 48159, 48420 | Y | N |  |  | 90166 | 78485
78485E | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Westchase to Hayes to Britmoore to increase thermal limits. Upgrade Ckt.24 Bellaire equipment and relay limits. |  | Westchase | Britmoore | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 | 2025-06-03 | 138 | 0 | 6.21 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 44120, 48159 | Y | N |  |  | 90170 | 78485
66221L | Galena Park Area Conversion Project | De-energize Ckt.20 Greens Bayou to GYPSUM. |  | Greens Bayou | GYPSUM | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 | 2025-04-11 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40619, 40725, 40751, 48131 | Y | N |  |  | 98425 | 66221
69902A | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. Loop Ckt.18E into Mission substation to create new Ckt.18 Gibbons Creek to Mission to Zenith. (Ckt.18 Gibbons Creek to Mission tie-line). |  | MISSION | Gibbons Creek/Zenith | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 | 2025-05-07 | 345 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  |  | 967, 44900, 44920 | Y | N |  |  | 98392 | 69902
69902C | New 345kV Mission (MSS) substation for generator interconnection to Parliament Solar. | Install generator lead from Mission (MSS) substation to Parliament/Parliament Solar |  | MISSION | Parliament | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:01 | 2025-05-07 | 345 | 0 | 0 | 0 |  | Waller | Waller | Tier 4 |  |  |  |  | 44920, 113925 | Y | N |  |  | 98393 | 69902
73578K | Heights 138kV Loop Conversion | Convert Eureka to double-tap service. Tap Ckt.09D to create new Ckt.09D San Felipe to Eureka TR2/TR3 tap to White Oak. Reconductor Ckt.09D Eureka TR2/TR3 tap to White Oak to increase thermal limits. Upgrade San Felipe line relaying Ckt.09D San Felipe to White Oak. |  | San Felipe | White Oak | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:02 | 2025-05-14 | 138 | 0 | 1.57 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45750, 45752, 46615, 47382, 47685 | Y | N |  |  | 90929 | 73578
73578C | Heights 138kV Loop Conversion | Convert Eureka to double-tap service. Tap Ckt.81J to create new Ckt.81J White Oak to Eureka TR1 tap to Wirt. |  | Wirt | White Oak | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:02 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44656, 45750, 45751, 46615 | Y | N |  |  | 90928 | 73578
73578J | Heights 138kV Loop Conversion | Reconfigure Ckt.40A Dunlavy to HO Clarke with a temporary (BP25 to BP26) configuration. Remove the Dunlavy TR3 tap section from Ckt.40A and install tap section to Ckt.90A. |  | Dunlavy | HO Clarke | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:04 | 2025-05-08 | 69 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47160, 47850 | Y | N |  |  | 90927 | 73578
73578G | Heights 138kV Loop Conversion | Tap existing Ckt.90A Kirby to Garrott near Tower 34720 to serve Dunlavy transformer TR3 load. Create Ckt.90A Kirby tap to DN-TR3 tap to Garrott. |  | Kirby | Garrott | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-05-31 00:05 | 2025-05-08 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47580, 47593, 47660, 48363 | Y | N |  |  | 90930 | 73578
11TPIT0011 | East_Village138kV Substation | East_Village 138kV Substation |  | Techridge | East_Village SUB | In-Service |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-06-01 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9045, 9190, 9195 | Y |  |  |  | 13043 | 5357
70349 | Belknap to Fort Griffin: Rebuild 69 kV Line | Rehab Belknap to Fort Griffin 69 kV line | IN-SERVICE | Belknap | Fort Griffin | In-Service |  | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 |  | 2025-06-11 | 2025-06-11 | 69 | 0 | 23.6 | 0 |  | Jones | Shackelford | Tier 4 | 22RPG020 | 2022-06-27 | 2022-07-22 |  | 6178, 6210, 6214, 60398, 60409, 60445, 60466, 60471 | Y | N |  |  | 70350 | 70349
90353 | Establish Sandy Ranch 345 kV Switch | Establish Sandy Ranch 345 kV Switch |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3125 | 2025-06-20 | 2025-06-06 | 345 | 0 | 0 | 0 |  | Hopkins | Hopkins | Tier 4 |  |  |  |  | 1697, 2464, 2621, 121022 | Y |  |  |  | 90354 | 90353
72880 | Sisseton: Build 69 kV station | Build 69 kV switch station on the Aspermont to Hamlin 69 kV line | IN-SERVICE | Sisseton |  | In-Service |  | AEP TNC | Charles Burks twang1@aep.com 918-599-2635 | TP2022059 | 2025-06-25 | 2025-05-14 | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6073, 6156, 6184, 6185, 6186, 6187, 60068 | Y |  |  |  | 72881 | 72880
50900 | Mason to North Brady: Rebuild 69 kV line | Rehab Mason to North Brady 69 kV line | IN-SERVICE | Mason | North Brady | In-Service | 1046 - 1219 | AEP TNC | Chris Carroll twang1@aep.com 918-599-2635 | 2794 | 2025-06-25 | 2025-05-23 | 69 | 0 | 30.24 | 0 |  | Mason | McCulloch | Tier 3 | 19RPG019 | 2019-10-01 | 2019-11-01 |  | 6006, 6381, 6393, 6406, 60386 | Y | N |  |  | 65550 | 50900
76918 | Primavera 138 kV: Construct new station | New station to serve Tesla load | IN-SERVICE | Primavera |  | In-Service |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2023059 | 2025-06-25 | 2025-06-20 | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8003, 8518, 8749, 8921, 88747 | Y |  |  |  | 76919 | 76918
76574 | TexasAg Wind Interconnection | Interconnect TexasAg to the Brisita 345 kV station | IN-SERVICE | Brisita |  | In-Service |  | ETT | John Solis jlsolis@aep.com 361-881-5574 | TP2023129 | 2025-06-25 | 2025-05-14 | 345 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8383, 8574, 8693, 88693 | Y |  |  |  | 76575 | 76574
69467 | Dupont to Resnik: Rebuild 138 kV Line | Rebuild the Dupont to Resnik 138 kV line | IN-SERVICE / Dollars Update | Dupont | Resnik | In-Service |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2025-06-25 | 2025-05-15 | 138 |  | 0.83 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8422, 8580 | Y |  |  |  | 69468 | 69467
49574 | Tesla: Build 345 kV terminal | Interconnect Misae II solar farm at Tesla | IN-SERVICE | Tesla |  | In-Service | 1023 - 1201 | ETT | Raza Ansari twang1@aep.com 918-599-2635 | 2785 | 2025-06-25 | 2025-06-17 | 345 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 60501, 143964 | Y | N |  |  | 49575 | 49574
63924 | Quasar: Build New 345 kV Station | Interconnect Brass Fork Solar to the Clear Crossing to Coulomb 345 kV Line | In-Service | Quasar |  | Planned | 1138 - 1316 | ETT | Zach Lachiusa twang1@aep.com 918-599-2635 | 1883 | 2025-06-25 | 2025-06-27 | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60514, 60703, 60712 | Y | N |  |  | 63925 | 63924
67921 | Sisseton: Build 69 kV tap | Build new 69 kV tap on the Aspermont to Hamlin 69 kV line | IN-SERVICE | Sisseton |  | In-Service |  | AEP TNC | Charles Burks twang1@aep.com 918-599-2635 |  | 2025-06-25 | 2025-05-14 | 69 | 0 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6073, 6156, 6184, 6185, 6186, 6187, 60068 | Y |  |  |  | 67922 | 67921
48816 | Mulberry Creek: Rebuild 345 kV station | Rebuild Mulberry Creek 345 kV station and replace both autotransformers | IN-SERVICE | Mulberry Creek |  | Under Construction | 1015 - 1193 | AEP TNC | Forrest Farson twang1@aep.com 918-599-2635 | 2776 | 2025-06-25 01:00 | 2025-06-30 | 345 | 0 | 0 | 900 |  | Jones |  | Tier 4 | 21RPG021 | 2021-12-15 | 2022-01-13 |  | 1435, 1459, 6230, 6231, 6232, 6235, 11420, 60040, 60104, 60105, 60788, 60789 | Y | N |  |  | 65536 | 48816
45155 | Ollin: Build 138 kV station | Construct new Ollin 138 kV station | IN-SERVICE | Ollin |  | In-Service | 939 - 1117 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 2752 | 2025-06-26 01:00 | 2025-06-26 | 138 | 0.1 | 0 | 0 |  | Crane |  | Tier 4 | 19RPG013 |  |  |  | 6600, 6604, 6605, 6606, 6607, 6610, 6611, 6613, 6668, 6669, 60428, 60429, 60431, 60432, 60441, 76615 | Y | N |  |  | 45156 | 45155
70019 | Add 138kV Locust-Hickory line 700MVA |  |  | Locust | Hickory | Planned |  | DME | Mark Zimmerer 940-349-7169 |  | 2025-06-30 | 2025-06-30 | 138 | 0 | 1.85 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 922, 924 | Y | N |  |  | 70020 | 70019 | N/A
86043 | Saxet Substation Addition Phase 2 | This PMCR models the phase 2 cut-in of T437 Nueces Bay – Lon Hill with the second Saxet Hard Tap. LCRA TSC will add a temporary Tap on T437 |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-06-30 | 2025-06-06 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 8441, 8452, 78568 | Y |  |  |  | 86044 | 86043
5430O | Conversion to 138kV | Reconnect the 69kV Hickory - RD Wells to the 138kV Hickory and RD Wells substations. Line is already insulated for 138kV. |  | Hickory | RD Wells | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2025-07-01 | 2025-07-01 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 930 | Y | N | N/A |  | 55209 | 5430 | N/A
5430K | Conversion to 138kV | Construct new 138kV Hickory substation and terminate the existing Bonnie Brae - Hickory (which is already insulated for 138kV) at the new 138kV Hickory substation. |  | Bonnie Brae | Hickory | Planned | N/A | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2025-07-01 | 2025-07-01 | 138 | 0 | 0 | 0 |  | Denton | Denton | Tier 4 |  | 2015-11-10 |  | 2016-01-20 | 922, 931 | Y | N | N/A |  | 55205 | 5430 | N/A
64776 | Upgrade 138kV DentonWest-RDWells line to 700MVA (SUM2024) |  |  | RD Wells | Denton West | Planned |  | DME | Mark Zimmerer 940-349-7169 |  | 2025-07-01 | 2025-07-01 | 138 | 0 | 4.47 | 0 |  | Denton | Denton | Tier 4 | N/A |  |  |  | 930, 986 | Y | N |  |  | 64777 | 64776 | N/A
77648B | Establish Tiger Creek 345 kV Switch for Jaguar Solar/BESS | Tiger Creek Switch - Jaguar Solar/BESS 345 kV Line |  | Tiger Creek Switch | Jaguar Solar/BESS | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6223 | 2025-07-14 | 2025-10-16 | 345 | 0.5 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 3379, 153783 | Y |  |  |  | 87809 | 77648
82829 | New Furhman Substation | Adds New Furhman switching station on Rayburn - Vanderbilt line for generator interconnect |  | Rayburn | Vanderbilt | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-07-24 | 2025-08-04 | 138 | 0.84 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5502, 5506, 5584 | Y | N |  |  | 82830 | 82829
72882 | Lockhart - Luling 69-kV Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 15.8-mile Lockhart – Luling (T157) 69-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. |  | Lockhart | Luling | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-07-30 | 2025-06-27 | 69 | 0 | 15.83 | 0 |  | Caldwell | Caldwell | Tier 4 | 23RPG004 | 2023-02-24 | 2023-03-20 |  | 7215, 7218, 7220, 7223 | Y | N |  |  | 72883 | 72882
13TPIT0070 | Nash Creek Substation | Rebuild existing substation, and replace existing PWT with new 69kVx13.09 kV, new Control House, CSW, structures, containment foundations, bus, panels, etc |  | Nash Creek |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2025-07-30 | 2025-07-30 | 69 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 |  |  |  |  | 7596 | Y | N |  |  | 78324 | 3322
87389 | Friendswood Energy GENCO GT (24INR0456) | Friendswood Energy GENCO GT at HO Clarke substation. Utilize existing HO Clarke to Friendswood Energy generator lead. |  | HO Clarke |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-07-31 | 2025-07-25 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 47170, 111183 | Y | N |  |  | 87390 | 87389
64069 | Charger Solar Interconnection | Connect the Charger Interconnection to the Angstrom to STP 345 kV line | IN-SERVICE | Angstrom | STP | In-Service |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2021165 | 2025-07-31 | 2025-07-08 | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 5915, 8249, 8676, 8678 | Y |  |  |  | 64070 | 64069
76076 | Laredo VFT North to North Laredo Switch: Rebuild 138 kV Line | Rebuild Las Cruces to Milo 138 kV line | IN-SERVICE | Las Cruces | Milo | In-Service | 1116 - 1294 | AEP TCC/ETT | William Lovelace jlsolis@aep.com 361-881-5574 | TP2020072 3835 | 2025-08-15 | 2025-08-15 | 138 | 0 | 2.4 | 0 |  | Webb | Webb | Tier 4 |  |  |  |  | 8112, 8918 | Y |  |  |  | 76077 | 76076
77827 | Reconductor TNMP Cottonwood to Oncor Lean Clay |  |  | Oncor Lean Clay (11078) | TNMP Cottonwood (38099) | Under Construction |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-08-15 | 2025-02-21 | 138 | 0 | 0.33 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 11078, 38099, 38100 | Y |  |  |  | 87863 | 77827
72876B | Provide 138 kV POD for Skybox at Teal Switch |  |  | Teal | Skybox | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6259 | 2025-08-19 | 2958101 | 138 | 0.2 | 0 | 0 |  | Williamson | Williamson | Tier 4 |  |  |  |  | 3362, 3371 | Y |  |  |  | 99290 | 72876
69552C | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 345 kV Switch, Autotransformers, and 345 kV Tie Lines to Limmer (LCRA) |  | Teal | Teal | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6165 | 2025-08-20 | 2025-05-30 | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 3696, 7341, 13363, 13364, 25090 | Y |  |  |  | 99403 | 69552
78485B | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.09A Britmoore to Hayes to Alief to increase thermal limits. |  | Britmoore | Alief | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-08-30 | 2025-06-03 | 138 | 0 | 2 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 44020, 44120, 44310 | Y | N |  |  | 98948 | 78485
75835A | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Partial reconductor Ckt.66B Stone Lake to Tomball. Phase One of overall approved upgrades |  | Stone Lake | Tomball | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-08-30 | 2025-07-29 | 138 | 0 | 5.71 | 0 |  | Harris | Harris | Tier 3 | 23RPG012 | 2023-05-04 | 2023-05-26 | 2023-05-26 | 44840, 46510, 48348 | Y | N |  |  | 98429 | 75835
87846 | Bradberry 138 kV Switch | Bradberry 138 kV Switch |  | Bradberry |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4015 | 2025-08-30 | 2958101 | 138 | 0 | 0 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 3064, 3065, 3066 | Y |  |  |  | 87847 | 87846
6253 | AEN_New_Kramer_Lane_Substation |  |  | 9238 | 9276 | In-Service |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-09-04 | 2025-09-04 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9077, 9238, 9276 | Y |  |  |  | 13981 | 6253
66210 | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV | Upgrade and convert Lake Creek - Marlin 69 kV Line to 138 kV. Relocate the Lake Creek 138/69 kV Auto to Marlin. |  | Lake Creek | Marlin | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1743 | 2025-09-15 | 2025-12-01 | 138 | 0 | 13.7 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3410, 3411, 3416, 3418, 3694, 13401, 13639 | Y |  |  |  | 66211 | 66210
66202A | Upgrade Palestine-Crockett 69 kV Line | Rebuild the Palestine - Elkhart 69 kV Line |  | Palestine | Elkhart | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6182 | 2025-09-15 | 2025-08-06 | 69 | 0 | 9.8 | 0 |  | Anderson | Anderson | Tier 3 | 22RPG035 | 2022-10-15 | 2022-11-15 |  | 3273, 3285 | Y |  |  |  | 66203 | 66202
90786 | Establish Yarrelton 345 kV Switch | Establish Yarrelton 345 kV Switch for Hermes Solar and Storage |  | Yarrelton | Yarrelton | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6261 | 2025-09-29 | 2025-12-17 | 345 | 0 | 0 | 0 |  | Bell | Bell | Tier 4 |  |  |  |  | 3687, 3762, 3766, 154643 | Y |  |  |  | 90787 | 90786
76234 | Wormser Road: Construct New 138 kV Terminal | Interconnect Seven Flags BESS to the Wormser Road 138 kV station | IN-SERVICE | Wormser Road |  | Under Construction |  | AEP TCC | William Lovelace jlsolis@aep.com 361-881-5574 | TP2023311 | 2025-09-30 | 2025-09-15 | 138 |  |  |  |  | Webb |  | Tier 4 |  |  |  |  | 8295 | Y |  |  |  | 76235 | 76234
76686 | Hog Mountain 138 kV POD | Add Hog Mountain 138 kV POD |  | Quartz Sand | Hog Mountain POD | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8673 R8791 | 2025-09-30 | 2025-12-30 | 138 | 5.4 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 1229, 18552 | Y |  |  |  | 76687 | 76686
50878 | North Edinburg: 345 kV Reconfigure | Reconfigure the North Edinburg 345 kV station | In-Service | North Edinburg |  | In-Service | 1056 - 1229 | AEP TCC | Curtis Brown jlsolis@aep.com 361-881-5574 | 3786 | 2025-09-30 | 2025-11-24 | 345 | 0 | 0 | 0 | -100,0 | Hidalgo |  | Tier 4 |  |  |  |  | 8341, 8383 | Y | N |  |  | 50879 | 50878
71935 | Upgrade Hondo Creek to Castroville to 138kV | Upgrade Castroville sub to 138kV and line from Hondo creek to Castroville |  |  |  | In-Service | 71917 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-09-30 | 2025-12-08 | 138 | 0 | 0 | 0 |  |  |  | Tier 2 | 22RPG022 |  |  |  | 5804, 5807, 5808, 5810, 5819, 5821 | Y |  |  |  | 73097 | 71935
76705 | Prairieland 345/138 kV Switch and 138 kV Line | Establish Prairieland 345/138 kV Switch and Prairieland – Quartz Sand 138 kV Line |  | Prairieland | Quartz Sand | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8632 | 2025-09-30 | 2025-12-16 | 345 | 6 | 0 | 1200 |  | Glasscock | Glasscock | Tier 2 | 24RPG006 |  |  |  | 1030, 1058, 1229, 11387, 18548, 18549, 18550, 18551, 18552 | Y |  |  |  | 91943 | 76705
50847 | Sage: Expand 69 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | IN-SERVICE | Sage |  | In-Service | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2799 | 2025-10-06 | 2025-10-06 | 69 | 0 | 0 | 0 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-06-21 |  | 6604 | Y | N |  |  | 50848 | 50847
81358B | Grindstone 138 kV Switch |  |  | Grindstone | Black Springs BESS | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1754 | 2025-10-15 | 2025-10-10 | 138 | 0 | 0 | 0 |  | Palo Pinto | Palo Pinto | Tier 4 |  |  |  |  | 1569, 154402 | Y |  |  |  | 98712 | 81358
78414 | SW3379 Replacement | Replacing existing 1200 Amp switch and 1800 Amp bypass jumper with new 3000 Amp switch. |  |  |  | Planned |  | NBU | Jeff Morriss jmorriss@nbutexas.com 830-608-8881 |  | 2025-10-26 | 2025-09-15 | 138 | 0 | 0 | 0 |  | Comal |  | Tier 4 | [5 empty] | Y |  |  |  | 78417 | 78414
76721 | Winding Oaks 138 kV Switch (Rayburn POI) | Establish Winding Oaks POD 138 kV Switch |  |  |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3095 | 2025-10-30 | 2025-11-04 | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 1751, 2626, 12704 | Y |  |  |  | 76722 | 76721
73364 | New Omicron 138kV Substation | New Omicron 138kV Substation will be looped into the existing Cagnon to Rafter 138kV transmission line. |  | 5326 | 5055, 5355 | In-Service | T-350, S-0975 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-10-30 | 2025-10-30 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5055, 5326, 5355 | Y |  |  |  | 73365 | 73364
88046 | Rebuild the Omicron to Rafter transmission line | Rebuild the Omicron to Rafter 138kV transmission line with normal and emergency ratings of at least 570MVA in accordance with RPG Approval Letter. |  | 5326 | 5355 | In-Service |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-10-30 | 2025-10-30 | 138 | 0 | 1.7 | 0 |  | Bexar | Medina | Tier 2 | 24RPG004 | 2024-02-01 | 2024-07-26 |  | 5326, 5355 | Y |  |  |  | 88047 | 88046
78490B | Jeanetta Auto Upgrades | Replace existing 600 MVA Jeanetta Auto A3 with 800 MVA autotransformer |  | Jeanetta |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 | 2025-03-23 | 345 | 0 | 0 | 200 |  | Harris |  | Tier 3 | 23RPG031 | 2023-10-04 | 2023-10-26 |  | 47300, 47310, 49082 | Y | N |  |  | 79426 | 78490
78490A | Jeanetta Auto Upgrades | Replace existing 600 MVA Jeanetta Auto A1 with 800 MVA autotransformer |  | Jeanetta |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 | 2025-05-19 | 345 | 0 | 0 | 200 |  | Harris |  | Tier 3 | 23RPG031 | 2023-10-04 | 2023-10-26 |  | 47300, 47310, 49024 | Y | N |  |  | 79425 | 78490
75938 | Expand Zenith substation with addition of 35kV Distribution Facilities. Tap TR1 on Ckt.09J to create new Ckt.09J Zenith to Zenith TR1 tap to Fry Road tap. Tap TR2 on Ckt.76A to create new Ckt.76A Zenith to Zenith TR2 tap to Fry Road tap. | Expand Zenith substation with addition of 35kV Distribution Facilities. Tap TR1 on Ckt.09J to create new Ckt.09J Zenith to Zenith TR1 tap to Fry Road tap. Tap TR2 on Ckt.76A to create new Ckt.76A Zenith to Zenith TR2 tap to Fry Road tap. |  | Zenith | Fry Road | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 | 2025-03-05 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44910 | Y | N |  |  | 75939 | 75938
76274 | Hamilton Road: Construct New 138 kV Terminal | Interconnect Tierra Seca BESS to the Hamilton Road 138 kV station | In-Service | Hamilton Road |  | In-Service |  | AEP TCC/ETT | Robert Dougherty jlsolis@aep.com 361-881-5574 | TP2023133 | 2025-10-31 | 2025-10-29 | 138 | 0.1 | 0 | 0 |  | Val Verde |  | Tier 4 |  |  |  |  | 8255, 8684, 8687, 8688, 8690 | Y |  |  |  | 76275 | 76274
80486 | Loxley: Construct New 138 kV Station | Interconnect the Loxley load to the new Loxley 138 kV station on the Pleasanton to Trumbo 138 kV line | IN-SERVICE | Loxley |  | Planned |  | AEP TCC | Bill Edwards jlsolis@aep.com 361-881-5574 |  | 2025-10-31 | 2025-12-18 | 138 | 0.1 | 0 | 0 |  | Atascosa |  | Tier 4 |  |  |  |  | 5429, 8203, 80491 | Y |  |  |  | 80487 | 80486
72065 | Lake Jackson Distribution Substation Conversion to Low-Profile | Rebuild Lake Jackson 138/12kV distribution substation to low-profile |  | Lake Jackson |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 | 2025-09-24 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 42880, 43172 | Y | N |  |  | 72066 | 72065
76624 | WA Parish 345kV Substation Expansion for Crowned Heron Storage (24INR0405) | Expand 345kV WA Parish substation for Crowned Heron Storage (24INR0405) |  | WA Parish | HERON | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-10-31 00:01 | 2025-12-16 | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 44000, 114042 | Y | N |  |  | 93236 | 76624
70536 | New 138 kV Verde Circle Substation | New 138 kV Verde Circle Substation looping into existing 138 kV Westover Hills and VLSI line. |  | 5466 | 5467, 5488 | In-Service | T-0316 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0971 | 2025-11-20 | 2025-11-20 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5466, 5467, 5488 | Y |  |  |  | 70537 | 70536
77122 | Mulberry Creek: Construct New 345 kV Terminal | Interconnect the Lancium load to the Mulberry Creek 345 kV station | IN-SERVICE | Mulberry Creek |  | Planned | TP2023636 | AEP TNC | Forrest Farson myturner@aep.com 918-599-2437 |  | 2025-11-30 | 2025-12-31 | 345 | 2.25 | 0 | 0 |  | Jones |  | Tier 4 |  |  |  |  | 6235 | Y | N |  |  | 77123 | 77122
72566 | Cedar Valley to Friendship Storm Hardening | Rebuild single circuit section of Cedar Valley to Friendship and reconductor with bundled 795 ACSR Conductor, 440 MVA. Replaces Project ID 61268 |  | Cedar Valley | Friendship | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-11-30 | 2025-05-14 | 138 | 0 | 4.3 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70506, 70507 | Y | N |  |  | 72567 | 72566
78480A | Weinbrenner (WEI) 138kV CEHE Station for LONGPO (LNP) / Long Point Solar 19INR0042 | Loop new CEHE 138kV substation Weinbrenner (WEI) into Ckt.02J Burke to Eagle Nest to create new Ckt.02 Burke to Weinbrenner to Eagle Nest. |  | Weinbrenner | Burke/ Eagle Nest | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 | 2025-12-10 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42410, 42430, 42990 | Y | N |  |  | 100090 | 78480
66221K | Galena Park Area Conversion Project | Rebuild GYPSUM customer substation for 138kV loop-tap service. Tap new GYPSUM substation (Spear Stone) from Ckt.94 between TANKER and new Galena Park tap to create new Ckt.94M CITFIL to Normandy tap to Galena Park tap to Spear Stone to TANKER |  | CITFIL | Tanker | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 | 2025-11-07 | 138 | 4.31 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40590, 40612, 40630, 40731, 40739, 41172, 48130, 48261, 48402, 48613 | Y | N |  |  | 98664 | 66221
78480B | Weinbrenner (WEI) 138kV CEHE Station for LONGPO (LNP) / Long Point Solar 19INR0042 | Install one generator lead from CEHE 138kV substation Weinbrenner (WEI) to LONGPO (LNP) / Long Point Solar (19INR0042) |  | Weinbrenner | LONGPO | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 00:01 | 2025-12-10 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42990, 114583 | Y | N |  |  | 100091 | 78480
78471 | WA Parish 345kV Substation Expansion for Bypass Storage (23INR0336) | Expand 345kV WA Parish substation for Bypass Storage (23INR0336) |  | WA Parish | BYPASS | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 00:01 | 2025-10-30 | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 44000, 113803 | Y | N |  |  | 93237 | 78471
66221M | Galena Park Area Conversion Project | Reconfigure Galena Park by removing the temporary Ckt.94M Galena Park loop. Tap Galena Park transformer on Ckt.21K between Fidelity and Witter. |  | Fidelity | Witter | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-11-30 00:06 | 2025-11-07 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 21RPG020 | 2021-11-30 | 2021-12-22 | 2021-12-22 | 40590, 40611, 40612, 40619, 40630, 40751, 48402, 48610 | Y | N |  | Cost included in main entry | 98665 | 66221
92600A | John_Dumas_Circuit_Breaker_Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7999 | 2025-12-01 | 2025-12-22 | 345 | 0 | 0 | 0 |  | Caldwell | Caldwell | Tier 4 |  |  |  |  | 7041, 7042 | Y |  |  |  | 92601 | 92600
71937 | Caterpillar Substation | Add T6, 40 MVA. 138-26.08 kV PWT to Caterpillar Substation |  | Caterpillar |  | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.org |  | 2025-12-01 | 2026-01-12 | 138 | 0 | 0 | 0 |  | Guadalupe |  | Tier 4 | [5 empty] | Y | N |  |  | 71938 | 71937
92600B | John_Dumas_Circuit_Breaker_Addition |  |  |  |  | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7999 | 2025-12-01 | 2025-12-22 | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 7041, 7042, 7341 | Y |  |  |  | 100070 | 92600
70886 | Rebuild TinTop - Rio Colorado | Rebuild TinTop- Rio Colorado 795ACSR |  | Tin Top | Rio Colorado | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 | 2025-07-03 | 69 | 0 | 15.5 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5563, 5569 | Y |  |  |  | 70887 | 70886
55873 | Upgrade Moore to Hondo Creek 138 kV line | Replace the 336 ACSR with 1020 ACCC conductor while keeping the existing structures that still meet our standards. |  | Moore | Hondo Creek | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-12-01 | 2025-09-24 | 138 | 0 | 13.5 | 0 |  | Medina | Frio | Tier 2 | 19RPG021 | 2019-11-20 | 2020-05-21 |  | 5819, 5827 | Y | N | Field engineering is still occurring due to short timeline for this upgrade. Details may change. | Current plan is to upgrade the line using mostly existing structures. Detailed field engineering is underway and could change the plan. | 55874 | 55873
72588C | Trading Post to Cedar Valley Storm Hardening | Upgrading switch to bring line to full rating | [5 empty] | PEC | Charles Dewitt Charles.Dewitt@peci.com 830-868-5041 |  | 2025-12-01 | 2025-05-14 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 70505, 70506 | Y |  |  |  | 91746 | 72588
80913 | Sloan 138 kV Switch. | Establish Sloan 138 kV Switch |  | Midessa South Switch | Odessa/Midland East Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8659 | 2025-12-04 | 2025-05-14 | 138 | 0 | 0 | 0 |  | Midland | Midland | Tier 4 |  |  |  |  | 1059, 1124, 1138, 11137, 11138, 11143, 11165 | Y |  |  |  | 90314 | 80913
86633 | Dusty Road 345 kV Switch | Establish Dusty Road 345 kV Switch |  | Tonkawa | Graham | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8809 | 2025-12-04 | 2025-12-04 | 345 | 0 | 0 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  |  | 1048, 1430, 11050, 144787 | Y |  |  |  | 86634 | 86633
70900D | Roanoke Area Upgrades | Dunham 345 kV Switch and Ramhorn 345 kV Switch |  | Dunham Switch | Dunham Switch | In-Service |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5281 M5144 M5146 M5148 | 2025-12-14 | 2025-12-31 | 345 | 0 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 22RPG003 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 646, 1421, 1730, 1849, 2081, 21851, 31875, 33646 | Y | N |  |  | 102861 | 70900
62448 | Rebuild Marlin 69 kV Switch | Rebuild Marlin 69 kV Switch |  | Marlin | Marlin | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R1752 | 2025-12-15 | 2025-12-01 | 69 | 0 | 0 | 0 |  | Falls | Falls | Tier 4 |  |  |  |  | 3418, 3638, 13639 | Y |  |  |  | 62658 | 62448
72958 | Graham to Graham Switch 69 kV Line Rebuild | Graham to Graham Switch 69 kV Line Rebuild |  | Graham | Graham | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3001 | 2025-12-15 | 2025-12-31 | 69 | 0 | 2.6 | 0 |  | Young | Young | Tier 4 |  |  |  |  | 1597, 1602 | Y |  |  |  | 72959 | 72958
77174 | Rebuild Old Lake Sw - Ringgold Magnolia 69 kV line | Rebuild Old Lake Sw - Ringgold Magnolia 69 kV line |  | Old Lake Switch | Ringgold Magnolia | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3508 | 2025-12-15 | 2025-12-15 | 69 | 0 | 13 | 0 |  | Clay | Montague | Tier 4 |  |  |  |  | 1524, 11541, 11545 | Y |  |  |  | 77175 | 77174
87758 | Badger 345 kV Switch | Establish Badger 345 kV Switch for Sypert Branch Solar |  | Badger | Badger | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6317 | 2025-12-15 | 2025-12-05 | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3687, 3761, 13429, 171165 | Y |  |  |  | 87759 | 87758
87830 | Blue Mountain 138 kV Capactior Bank | Add 138 kV Capacitor Bank at Blue Mountain Switch |  |  |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8799 | 2025-12-15 | 2025-11-15 | 138 | 0 | 0 | 0 | 0,110.4 | Loving | Loving | Tier 4 |  |  |  |  | 18680 | Y |  |  |  | 87831 | 87830
90899 | Establish Woodbury 138 kV Switch | Establish Woodbury 138 kV Switch for Three W Solar |  | Woodbury | Woodbury | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6251 | 2025-12-15 | 2025-12-05 | 138 | 0 | 0 | 0 |  | Hill | Hill | Tier 4 |  |  |  |  | 237, 3522, 3781, 155482 | Y |  |  |  | 90900 | 90899
62666B | Upgrade and convert McGregor - Waco West Line | McGregor Phillips - Waco West 138 kV Operation |  | McGregor Phillips | Waco West | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6172 | 2025-12-15 | 2025-12-31 | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3370, 3372, 3436, 3437, 3440, 3441, 3446, 3562, 3584, 3585, 3594, 3596, 3793, 13436, 13438 | Y |  |  |  | 93100 | 62666
81060 | Riverton-Border-Quarry Field 138 kV Second Circuit | Add Permian Basin Reliability Plan Upgrade ID L1A and L1D Riverton-Border-Quarry Field 138 kV Second Circuit |  | Riverton | Quarry Field | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8733 | 2025-12-15 | 2025-12-01 | 138 | 29.7 | 0 | 0 |  | Reeves | Loving | Tier 4 |  |  |  |  | 11083, 11089 | Y |  |  |  | 98685 | 81060
100459 | Establish Token 138 kV POD |  |  | Token 138 kV |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3040 | 2025-12-15 | 2025-12-15 | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 968, 2181, 2477 | Y |  |  |  | 100460 | 100459
82810B | Olympus 138 kV Switch | Topology Correction: Add missing Olympus Switch - Kerens 138 kV Line Section |  | Olympus Switch | Kerens | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6330 | 2025-12-15 | 2025-05-08 | 138 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3125, 3466, 3723 | Y |  |  |  | 100595 | 82810
76135 | Hackberry Switch – DFW D-East 2 138 kV DCKT Line Section | Rebuild Hackberry Switch – DFW D-East 2 138 kV DCKT Line Section |  | Dallas | Dallas | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4347 M4357 | 2025-12-15 | 2025-12-31 | 138 | 0 | 12.2 | 0 |  | Dallas | Dallas | Tier 3 | 23RPG020 |  |  |  | 1996, 1997, 2001, 2010, 2388, 15020, 15021, 15025, 15026, 15045, 15046 | Y |  |  |  | 76136 | 76135 | 2022-NC6
78363 | Gunter 345/138 kV Switch | Establish Gunter 345/138 kV Switch |  | Gunter |  | In-Service |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com | M3301 | 2025-12-15 | 2026-03-31 | 345 | 0 | 0 | 600 | -75,0 | Collin |  | Tier 3 | 24RPG025 |  |  |  | 1730, 2235, 2236, 2373, 11735, 11757, 12235, 12468 | Y |  |  |  | 78364 | 78363
80546A | Upgrade the Hutto & Round Rock - Salado 138 kV Line | Increase the maximum operating temperature of the Hutto - Round Rock 138 kV Line and rebuild the Round Rock Westinghouse Tap - Round Rock Westinghouse 138 kV Line Section |  | Hutto Switch | Round Rock Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6203, R6202 | 2025-12-15 | 2026-01-06 | 138 | 0 | 8.8 | 0 |  | Williamson | Williamson | Tier 3 | 24RPG018, 25RPG006 | 2025-02-21 | 2025-03-17 |  | 3664, 3666, 3667, 3668, 3669, 3670 | Y |  |  |  | 81498 | 80546 | 2023-SC17
81389 | Sandhills Tap - Wolf 138 kV Line Rebuild | Sandhills Tap - Wolf 138 kV Line Rebuild |  | Odessa EHV | Wolf | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8528 | 2025-12-15 | 2025-12-15 | 138 | 0 | 14.2 | 0 |  | Ector | Ward | Tier 3 |  |  |  |  | 1013, 1103, 11018 | Y |  |  |  | 87113 | 81389
66289B | Tyler to Athens 138 kV line Conversion | Establish Foggle Switch, Establish Poynor POI, Echols to Athens 69 kV Line Upgrade |  | Athens | Echols | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6094 | 2025-12-15 | 2025-12-15 | 69 | 0 | 6.5 | 0 |  | Henderson | Henderson | Tier 3 | 22RPG015 | 2022-06-01 | 2022-07-01 |  | 3108, 3126, 3233, 3238, 3239, 3248, 3256, 3269, 3270, 3288, 3801, 6805 | Y |  |  |  | 92110 | 66289
81175 | Salt Flat Road 138 kV Switch and Salt Flat Road - Barr Ranch - Reiter 138 kV Second Circuit | Add Salt Flat Road 138 kV Switch and Salt Flat Road - Barr Ranch - Reiter 138 kV Second Circuit & De-energize auto at Odessa EHV |  | Reiter | Salt Flat Road | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8704 | 2025-12-15 | 2025-12-15 | 138 | 44 | 4.4 | 0 |  | Ector | Midland | Tier 3 | 25RPG007 |  |  |  | 1027, 1028, 1111, 1123, 1193, 1234, 1276, 1277, 11111, 11217, 11235, 11344, 18528, 18545, 18701, 23859 | Y |  |  |  | 93103 | 81175
72009 | Cattleman 345/138 kV Switch | Construct a new 345/138 kV Switch to replace existing Morgan Creek Switch |  | Cattleman | Cattleman | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8647 | 2025-12-15 | 2025-11-15 | 345 | 0 | 0 | 1200 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1030, 1032, 1058, 10053, 10054, 10055, 10056, 11395, 18548 | Y |  |  |  | 81376 | 72009
70900C | Roanoke Area Upgrades | Establish Exchange - Kingsridge 138 kV Double-Circuit Line |  | Exchange Switch | Kingsridge Switch | In-Service |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5281 M5144 M5146 M5148 | 2025-12-15 | 2025-12-15 | 138 | 3.4 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 22RPG003 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 12036, 12080, 12081, 112033 | Y | N |  |  | 102862 | 70900
5475 | Lufkin Switch - Redland Switch 345 kV Line | Construct a new 345 kV Line from Lufkin Switch to Redland Switch |  | Lufkin Switch | Redland Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6077 | 2025-12-15 | 2025-12-15 | 345 | 8.1 | 0 | 0 |  | Angelina | Angelina | Tier 2 | 20RPG019 | 2020-10-01 | 2022-04-01 |  | 3117, 3321 | Y | N |  |  | 13180 | 5475
72596C | PEC_MarshallFord_Paleface_StormHardening | Upgrade to terminal equipment and update to final circuit rating. Terminal end equipment update to be completed Fall 2024 based on original project schedule. (Replaces ERCOT Project # 61274C) | 1/10/2023: Changes to description based on final design. | Paleface | Marshall Ford | Planned |  | PEC/LCRATSC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2025-12-15 | 2025-11-01 | 138 | 0 | 11.5 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70477, 77356 | Y | N |  |  | 73445 | 72596
87477 | [5 empty] | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-12-16 | 2025-04-01 | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 3275, 3278, 6935, 6939 | Y |  |  |  | 87478 | 87477
76690 | Add Atchison POD | Add Atchison POD |  | Border Switch | Atchison | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8698 R8726 | 2025-12-16 | 2025-12-16 | 138 | 7 | 0 | 0 |  | Loving | Loving | Tier 4 |  |  |  |  | 11189, 11356, 18670, 18672, 18710 | Y |  |  |  | 98678 | 76690
68183 | Estes to Putnam: Rebuild 138 kV line | Rehab the Abilene South to Putnam 138 kV line | IN-SERVICE | Estes | Putnam | In-Service | 68150 | AEP TNC | Forrest Farson myturner@aep.com 918-599-2437 |  | 2025-12-16 | 2025-12-16 | 138 | 0 | 15 | 0 |  | Callahan | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6309, 60365, 61015 | Y | N |  |  | 68184 | 68183
99187 | This involves moving Harmony to a different bus/bay at Hill Country to alleviate the loading on HC auto 3 & 4. | Move Harmony - Hill Country from Auto 3&4 to Hill Country Auto 1&2. This involves moving Harmony to a different bus/bay at Hill Country to alleviate the loading on HC auto 3 & 4. |  | 5195 | 5210 | In-Service | S-1053a, T-0411 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2025-12-18 | 2025-12-18 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5195, 5208, 5210 | Y |  |  |  | 99188 | 99187
44946 | CPSE_New_Scenic_Loop_138kV_Load_Serving_Station | The new Scenic Loop 138 kV load serving station will be looped into existing Ranchtown to LCRA (Menger Creek) 138 kV transmission line. The substation should be located south west of the existing Fair Oaks Ranch and north east of the existing Ranchtown substation. |  | 5363 | 7665, 5358 | In-Service | S-0885 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0275 | 2025-12-18 20:00 | 2025-12-18 | 138 | 9 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5358, 5363, 7665 | Y |  |  |  | 44947 | 44946
81270 | Construct the new Prong Moss 345 kV switch | Construct a new 345 kV switch |  | Prong Moss | Prong Moss | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3025 | 2025-12-30 | 2025-12-31 | 345 | 0 | 0 | 0 |  | Howard | Howard | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 1025, 10049, 10057, 10062 | Y |  |  |  | 81271 | 81270
70665C | Danek (DNK) CEHE Substation for Remy Jade - 23INR0339 | Upgrade Ckt.03A PSARCO to BIGVUE to increase thermal limits. Transmission portion of upgrade. |  | PSARCO | BIGVUE | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 | 2026-01-12 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 40190, 40390, 40890, 41301, 48141, 113219 | Y | N |  |  | 98432 | 70665
73123 | Sim Gideon - Swiftex Transmission Line Upgrade | LCRA TSC will upgrade T608 Sim Gideon - Swiftex 138-kV transmission line to achieve a higher operational rating. |  | Sim Gideon | Swiftex | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2025-12-31 | 2025-12-31 | 138 | 0 | 10 | 0 |  | Bastrop | Bastrop | Tier 3 | 24RPG014 | 2024-05-02 | 2024-05-23 |  | 7310, 7319, 7326 | Y | N |  |  | 73124 | 73123 | 2023-SC15
72040A | Blueridge to WA Parish Ckt.02A Upgrades (22RPG041) | Upgrade portions of Ckt.02A Quail Valley tap to WA Parish and Ckt.02A DEWALT to Sienna tap as a Hardening upgrade. |  | DEWALT | Sienna | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 | 2025-01-29 | 138 | 0 | 6.14 | 0 |  | Harris | Fort Bend | Tier 4 | 22RPG041 | 2022-11-21 | 2022-12-15 | 2022-12-15 | 44180, 48302, 48335 | Y | N |  |  | 91115 | 72040
100667 | Oncor_MNE_100667_Cloud 138 kV POD | Establish Cloud 138 kV POD |  | Cloud 138 kV POD |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3309 | 2025-12-31 | 2025-12-31 | 138 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 2687, 2691, 12691 | Y |  |  |  | 100668 | 100667
90784 | Reconductor portions of Ckt.63C Moody to West Galveston as a Hardening project. |  |  | Moody | West Galveston | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 | 2025-10-31 | 138 | 0 | 2.78 | 0 |  | Galveston | Galveston | Tier 4 | 24RPG037 | 2024-12-06 | 2025-01-02 |  | 42950, 43400 | Y | N |  | Related to MOD Project 72063 | 90785 | 90784
99397 | Buffalo Creek BESS (26INR0405) at Cedar Creek 345kV CEHE Substation | Interconnect new generation facility for Buffalo Creek BESS (26INR0405) at Cedar Creek 345kV CEHE Substation. Utilize existing generator lead. Remove existing generator lead conductor and install new bundled 959ACSS conductor. |  | Cedar Creek | Buffalo Creek | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2025-12-31 | 2025-12-20 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 | [5 empty] | Y | N |  |  | 99398 | 99397
72647 | Add_Blue_Ridge_Load | Tapping the Blueridge substation and Climax Switching Station, and adding Blue Ridge load. |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2026-01-01 | 2025-08-01 | 69 | 0 | 0 | 0 |  | Collin | Collin | Tier 4 |  |  |  |  | 6803, 37240, 37245, 37280 | Y |  |  |  | 78600 | 72647
64063 | BRP Antlia BESS Interconnection | Connect BRP Antlia BESS to the Maxwell 138 kV station | IN-SERVICE | Maxwell | Antlia | In-Service |  | AEP TCC | Joseph Isaac mlforcum@aep.com 918-599-2674 |  | 2026-01-08 | 2025-01-31 | 138 | 0 | 0 | 0 |  | Val Verde | Val Verde | Tier 4 |  |  |  |  | 8998, 88999 | Y |  | TP2021260 |  | 64064 | 64063
50845 | Kinnison: Expand 138 kV station | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | IN-SERVICE | Kinnison |  | Under Construction | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2797 | 2026-01-08 | 2025-07-22 | 138 | 0 | 0 | 130 |  | Crane |  | Tier 3 |  | 2019-06-21 | 2019-07-22 |  | 6604, 6607, 6611, 60431 | Y | N |  |  | 65545 | 50845
73408 | Odysseus: Build new 345 kV station | Interconnect Ulysses Solar to the Odysseus 345 kV Station on the Bluff Creek to SA Red Creek 345 kV line | IN-SERVICE | Odysseus |  | Planned |  | AEP TNC | Zach Lachiusa twang1@aep.com 918-599-2635 |  | 2026-01-08 | 2025-12-31 | 345 | 0 | 0 | 0 |  | Coke |  | Tier 4 |  |  |  |  | 6444, 60040, 60072 | Y | N |  |  | 73409 | 73408
72935 | Saragosa: Install 2nd Bay | Install 2nd Bay at Saragosa Substation | IN-SERVICE | Saragosa |  | Planned |  | AEP TNC | Damian Raab twang1@aep.com 918-599-2635 |  | 2026-01-08 | 2025-05-30 | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60716 | Y | N |  |  | 72936 | 72935
51012 | Kinnison to Sage: Rebuild 69 kV line | Build Heron 138 kV station with a 138/69 kV auto, expand the Kinnison 138 kV station, expand the Sage 69 kV station, rebuild Heron to Ollin and convert to a 138 kV line, and rebuild Kinnison to Sage 69 kV line | IN-SERVICE | Kinnison | Sage | In-Service | 1048 - 1221 | AEP TNC | Gregory Crane twang1@aep.com 918-599-2635 | 2823 | 2026-01-08 01:00 | 2025-11-15 | 69 | 0 | 0.25 | 0 |  | Crane | Crane | Tier 3 |  | 2019-06-21 | 2019-07-17 |  | 6604, 60431 | Y | N |  |  | 65555 | 51012
45174 | Ollin to LCRA Crane: Partial Build, Partial Rebuild, and Conversion | Build new Ollin 138 kV station; partial build, rebuild, and conversion to 138 kV of Ollin to LCRA Crane; and rebuild McElroy to Sage | IN-SERVICE | Ollin | LCRA Crane | In-Service | 939 - 1117 | AEP TNC | Greg Crane twang1@aep.com 918-599-2635 | 2767 | 2026-01-08 01:00 | 2025-12-05 | 138 | 0.52 | 0 | 0 |  | Crane | Crane | Tier 4 | 19RPG013 |  |  |  | 6600, 6605, 6606, 6610, 6613, 6668, 6669, 60428, 60429, 60431, 60432, 60441, 76615 | Y | N |  |  | 65527 | 45174
76151 | Gas Pad Tap: Replace CTVT | Replace CTVT combination unit at Gas Pad station along the Lote Bush to Yucca Drive 138 kV line | IN-SERVICE | Gas Pad Tap |  | In-Service |  | AEP TNC | Bill Edwards twang1@aep.com 918-599-2635 |  | 2026-01-09 | 2025-05-02 | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 11245, 60397 | Y | N |  |  | 76152 | 76151
68252 | Lobo: Line settings | Interconnect Guajillo to the Lobo 345 kV station | IN-SERVICE | Lobo |  | Under Construction |  | ETT | Glen Reed gareed@aep.com 918-599-2664 |  | 2026-01-09 | 2025-04-14 | 345 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 80219, 163223 | Y |  |  |  | 68253 | 68252
70779 | Tortuga: Install Cap Bank | Install a 23.0 MVAR capacitor bank at the Tortuga 138 kV station | IN-SERVICE | Tortuga |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 | TP2022188 | 2026-01-09 | 2025-05-16 | 138 | 0 | 0 | 0 | 0,23 | Nueces |  | Tier 4 |  |  |  |  | 8697 | Y |  |  |  | 70780 | 70779
76214 | North Edinburg: 345 kV Reconfigure | Reconfigure North Edinburg 345 kV station: 2nd reactor | IN-SERVICE | North Edinburg |  | Planned |  | AEP TCC | Curtis Brown jlsolis@aep.com 361-881-5574 | TP2019168 | 2026-01-09 | 2025-11-24 | 345 | 0 | 0 | 0 | -50,0 | Hidalgo |  | Tier 4 |  |  |  |  | 5660, 8341, 8383, 8452, 8455, 8901, 8905 | Y |  |  |  | 76215 | 76214
50868 | Rosata - Structure 31/8: Line Rebuild | Coleto Creek - Kenedy SS: Line Rebuild | IN-SERVICE | Rosata | Kenedy SS | Planned | 1052 - 1225 | AEP TCC | Curtis Brown mlforcum@aep.com 918-599-2674 | 3780 | 2026-01-09 | 2025-05-15 | 138 | 0 | 15.5 | 0 |  | Goliad | Karnes | Tier 3 | 20RPG014 | 2020-08-19 | 2020-09-11 |  | 8153, 8186 | Y | N |  |  | 50869 | 50868
90004 | Juncus: Construct New 69 kV Temporary Tap | Interconnect the TEC Snodgrass load to the new Juncus 69 kV temporary tap on the Abilene South to Steamboat 69 kV line | IN-SERVICE | Juncus |  | Planned |  | AEP TNC | Bill Edwards twang1@aep.com 918-599-2635 | TP2023074 | 2026-01-10 | 2025-04-03 | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6326, 6328, 60133 | Y | Y |  |  | 91319 | 90004
4645 | Rebuild of Myra to Spring | Rebuild of Myra to Spring |  | Myra | Spring | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-01-12 | 2025-08-01 | 138 | 0 | 13.9 | 0 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 684, 690, 691 | Y |  |  |  | 12221 | 4645
71879 | Upgrade Metering CT | Upgrading the Metering CT for Elm Creek to Skyline Circuit 2. This upgrade will result in a rating increase for this transmission line. |  | 5133 | 5371 | In-Service |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0939b | 2026-01-22 | 2026-01-22 | 345 | 0 | 0 | 0 |  | Guadalupe | Bexar | Tier 4 |  |  |  |  | 5133, 5371 | Y |  |  |  | 71880 | 71879
80508 | Kilby: Construct New 345 kV Station | Interconnect Quantum Solar to the new Kilby 345 kV station on the Clear Crossing to Pendulo 345 kV line | IN-SERVICE | Kilby |  | In-Service | TP2023844 | ETT | Dave Goetz myturner@aep.com 918-599-2437 |  | 2026-01-27 | 2026-01-27 | 345 | 0 | 0 | 0 |  | Haskell |  | Tier 4 |  |  |  |  | 60089, 60507, 60514, 145568 | Y | N |  |  | 80509 | 80508
76350 | Install new TARGA 138kV customer substation as Ckt.86 Jordan to TARGA to CITIES. | Install new TARGA 138kV customer substation as Ckt.86 Jordan to TARGA to CITIES. |  | TARGA | Jordan/CITIES | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-30 | 2026-01-09 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40340, 40740, 40855, 40950 | Y | N |  |  | 103307 | 76350
69463 | Gulch: Construct new 345 kV Station | Interconnect Arroyo Solar to the new Gulch 345 kV station on the La Palma to Rio Hondo 345 kV line | IN-SERVICE | Gulch |  | Planned |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2026-01-30 | 2025-12-31 | 345 | 0.1 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8317, 8318, 8704, 8705 | Y |  |  |  | 70802 | 69463
76194 | Angstrom: Construct New 345 kV Terminal | Interconnect Pintail Pass BESS to the Angstrom 345 kV station | IN-SERVICE | Angstrom |  | In-Service |  | AEP TCC | Dave Goetz deevans@aep.com 918-599-2938 | TP2023132 | 2026-01-30 | 2026-01-30 | 345 | 0 | 0 | 0 |  | San Patricio |  | Tier 4 |  |  |  |  | 8249, 8956 | Y |  |  |  | 76195 | 76194
72063 | Moody to Stewart Ckt.63 Upgrades P1041 | Reconductor portions of Ckt.63 Stewart to West Galveston as a Hardening project |  | Stewart | West Galveston | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 | 2025-10-31 | 138 | 0 | 3.97 | 0 |  | Galveston | Galveston | Tier 4 |  |  |  |  | 42950, 42951 | Y | N |  |  | 72064 | 72063
66200D | Upgrade Taylor - Holland 69 kV Line | Rebuild the Granger - Taylor 69 kV Line |  | Taylor | Holland | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6173 | 2026-01-31 | 2026-01-16 | 69 | 0 | 5.9 | 0 |  | Williamson | Williamson | Tier 4 | 22RPG036 |  |  |  | 118, 3648, 3649, 13647 | Y |  |  |  | 71897 | 66200
80572 | Miel: Construct New 138 kV Station | Interconnect Nightfall Solar to the new Miel 138 kV station on the Razorback to Uvalde 138 kV line | IN-SERVICE | Miel |  | In-Service | TP2023841 | ETT | Zachary Lachiusa jlsolis@aep.com 361-881-5574 |  | 2026-01-31 | 2026-01-13 | 138 | 0 | 0 | 0 |  | Uvalde |  | Tier 4 |  |  |  |  | 8234, 8707, 8747 | Y | N |  |  | 80573 | 80572
72040B | Blueridge to WA Parish Ckt.02A Upgrades (22RPG041) | Upgrade portions of Ckt.02A Blueridge tap to DEWALT (P1048-3) as a Hardening upgrade. |  | Blueridge | DEWALT | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-01-31 | 2025-12-15 | 138 | 0 | 2.94 | 0 |  | Harris | Fort Bend | Tier 4 | 22RPG041 | 2022-11-21 | 2022-12-15 | 2022-12-15 | 44180, 48163 | Y | N |  | Cost included in main entry | 91116 | 72040
87905 | Hartring – Upland 138 kV Double Circuit Line | Construct new Hartring – Upland 138 kV Double Circuit Line |  | Ringo | LCRA Benedum | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8713 | 2026-01-31 12:00 | 2025-12-10 | 138 | 18 | 0 | 0 |  | Upton | Reagan | Tier 2 | 24RPG024 | 2024-08-09 |  |  | 18671, 18674, 18675, 18676 | Y |  |  |  | 93273 | 87905
68150 | Abilene South to Estes: Rebuild 138 kV Line | Rehab Abilene South to structure 33/7 | IN-SERVICE | Abilene South | Estes | In-Service |  | AEP TNC | Forrest Farson myturner@aep.com 918-599-2437 |  | 2026-02-28 | 2025-12-18 | 138 | 0 | 18.3 | 0 |  | Taylor | Callahan | Tier 4 |  | 2022-02-01 | 2022-03-01 | 2022-03-01 | 6260, 6313, 60063, 60336, 60355, 60365, 60773, 61015 | Y | N |  |  | 68151 | 68150
87344 | Addicks 345kV to White oak Ckt.71B Upgrades | Upgrade Ckt.71B Addicks to White Oak to increase thermal limits |  | Addicks | White Oak | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-02-28 | 2026-01-25 | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45600, 46600 | Y | N |  |  | 87345 | 87344
71926 | Upgrade BURNS to Heidelberg line | Upgrade BURNS to Heidelberg line to be 478MVA capable |  | Burns | Heidelberg | In-Service | 7192871930 | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-03-01 | 2026-04-02 | 138 | 0 | 10 | 0 |  | Cameron | Hidalgo | Tier 4 |  |  |  |  | 5763, 5765 | Y |  |  |  | 71927 | 71926
80384 |  | Reconductor Gibbons Creek to Greens Prairie Line |  | Gibbons Creek | Greens Pairie | Planned |  | BRYN | Clay Lindstrom clindstrom@btutilities.com 979-821-5763 |  | 2026-03-01 | 2026-03-13 | 138 | 0 | 12.9 | 0 |  | Grimes | Brazos | Tier 4 |  |  |  |  | 964, 32878 | Y |  |  |  | 80385 | 80384
78357 | Wilmer 345/138 kV Switch | Establish Wilmer 345/138 kV Switch |  | Wilmer |  | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4369 M4371 M4372 | 2026-03-02 | 2026-06-30 | 345 | 6 | 0 | 1200 | 0,220.8 | Dallas |  | Tier 1 | 24RPG022 | 2024-07-02 | 2024-07-29 |  | 2261, 2342, 2344, 2427, 2429, 2432, 2967, 3083, 3084, 3085, 13082, 23082 | Y |  |  |  | 78373 | 78357
66473 | Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line | Upgrade the Mesquite East Switch-Oates (GP&L)/Prairie Creek Switch 138 kV Double-Circuit Line |  | Mesquite East | Oates | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4137 | 2026-03-15 | 2026-05-31 | 138 | 0 | 17.5 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 831, 2742, 2747, 2756, 2764, 2765, 2766, 2767 | Y |  |  |  | 66475 | 66473
66188 | Cedar Crest - Dealey - West Levee 138 kV Line | Upgrade the existing 138 kV Line |  | Ceadr Crest | West Levee | In-Service |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4212 | 2026-03-15 | 2026-05-15 | 138 | 0 | 4.7 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2400, 2493, 2842 | Y |  |  |  | 66189 | 66188
61404 | Boerne Split-Welfare Transmission Line Upgrade | This project will Increase the reliability of transmission facilities on the T228 Boerne to Welfare 138-kV and T656 Bergheim to Kendall 345-kV 7.3-mile double-circuit transmission line by replacing the aging conductor. |  | Boerne, Bergheim | Welfare, Kendall | Planned | 61406, 61358, 61392, 61350, 61234, 61362, 61356, 61400, 61402 | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-03-15 | 2026-03-15 | 345 | 0 | 7.3 | 0 |  | Kendall | Kendall | Tier 3 | 22RPG005 | 2022-03-04 | 2022-09-09 |  | 7046, 7153, 7168, 7770 | Y | N |  |  | 78327 | 61404
87395 | Caldwell Substation Addition | LCRA TSC will build a new substation, Caldwell Substation, to manage 12 MW of load in the summer of 2024. This substation will be on the Cooks Point - Lyle Wolz 138-kV transmission line. The new substation will be approximately 5 miles south of Cooks Point substation. LCRA will install circuit breakers in a ring bus formation |  | Caldwell | Caldwell | Planned |  | LCRATSC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2026-03-16 01:00 | 2026-03-11 | 138 | 0 | 0 | 0 |  | Burleson | Burleson | Tier 4 |  |  |  |  | 7566, 7567, 7569 | Y | N |  |  | 87396 | 87395
87031 | Primavera: Construct New 138 kV Terminal | Interconnect Project Lynx Storage to the Primavera 138 kV station | IN-SERVICE / Dollars Update | Primavera |  | In-Service |  | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2024100 | 2026-03-19 | 2029-03-19 | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8003, 8749 | Y |  |  |  | 87032 | 87031
99453C | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.27 STP to Old Hickory (Elm Creek) to increase thermal limits as part of FRM2 upgrades. |  | STP | Old Hickory | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-03-30 | 2026-03-03 | 345 | 0 | 0 | 0 |  | Guadalupe | Matagorda | Tier 4 |  |  |  |  | 5133, 5915 | Y | N |  |  | 102607 | 99453
81274 | Ranger Camp – Cattleman 345 kV Double-Circuit Line | Construct a new 345 kV double-circuit line from Ranger Camp to Cattleman |  | Ranger Camp | Cattleman | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8648 | 2026-03-30 | 2026-06-01 | 345 | 6.8 | 0 | 0 |  | Mitchell | Mitchell | Tier 1 | 23RPG029 | 2023-09-29 |  |  | 10049, 10053 | Y |  |  |  | 81275 | 81274
65683 | To add Open Sky Station | To interconnect GINR 20INR0241 |  |  |  | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-03-31 | 2026-03-23 | 345 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 68001, 68004, 68014, 183452, 184183 | Y | N |  |  | 65684 | 65683
90157 | NRG THW GT at TH Wharton 345kV (24INR0482) | Install NRG THW GT at TH Wharton 345kV substation. Connect at the same generator lead as 05THWGEN |  | TH Wharton |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-03-31 | 2026-04-03 | 345 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 90159 | 90157
86015 | King Substation - Add 3rd Distribution Transformer | Install the third King distribution transformer. Tap on Ckt.86E to create new Ckt.86E Newport to King tap to Jonte. Updated for 26SSWG base case |  | King | Newport/Jonte | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-03-31 | 2026-03-06 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40912, 41150, 45660, 48182, 48187 | Y | N |  |  | 102954 | 86015
70880 | Rebuild Carancahua -TinTop | Rebuild Carancahua to TinTop with 795ACSR |  | Carancahua | Tin Top | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-04-01 | 2026-03-13 | 69 | 0 | 12.93 | 0 |  | Matagorda | Matagorda | Tier 4 |  |  |  |  | 5569, 5570, 5571, 5573 | Y |  |  |  | 70881 | 70880
104658A | Establish Pathfinder 345 kV Switch | Establish Pathfinder 345 kV Switch |  | Pathfinder | Pathfinder | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6364 | 2026-04-07 | 2026-05-14 | 345 | 0 | 0 | 0 |  | Freestone | Freestone | Tier 4 |  |  |  |  | 3815, 46020, 68091 | Y |  |  |  | 104659 | 104658
70186 | Buchanan CTEC - Kingsland 1 Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 6.2-mile Buchanan to Kingsland 2 to Kingsland 1 (T291) 69-kV transmission line. |  | Buchanan CTEC | Kingsland 1 | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 |  | 2026-04-07 | 2026-04-07 | 69 | 0 | 6.2 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7101, 7402, 7404 | Y | Y |  |  | 78419 | 70186
91911 | Establish Gristmill 345 kV Switch | Establish Gristmill 345 kV Switch for Yaupon Solar and Storage |  | Gristmill | Gristmill | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6232 | 2026-04-16 | 2026-06-01 | 345 | 0 | 0 | 0 |  | Milam | Milam | Tier 4 |  |  |  |  | 3706, 3765, 39950, 171843 | Y |  |  |  | 91912 | 91911
99744 | Laredo VFT North: 138 kV Breaker Addition | Install additional 138 kV breaker on the Lobo circuit #1 138 kV terminal at the Laredo VFT North 138 kV station | IN-SERVICE | Laredo VFT North |  | In-Service | TP2023630 | ETT | Remington Hajdik jlsolis@aep.com 361-881-5574 |  | 2026-04-30 | 2026-04-30 | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 | [5 empty] | Y |  |  |  | 99745 | 99744
99904 | Install a new 138kV transmission line approximately .1 miles long to connect the generator’s interconnection facilities to Leon Creek Switchyard. |  |  | 5260 | 171073 | In-Service | S-0977, T-0335 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-05-01 | 2026-01-20 | 138 | 0.13 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5260, 171073 | Y |  |  |  | 99905 | 99904
91847A | Hornsby Load Power Transformer Addition |  |  | Honrsby |  | Planned |  | LCRATSC | Dylan Preas Dylan.Preas@LCRA.ORG 512-578-4514 | PLC-8186 | 2026-05-08 | 2026-05-15 | 345 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 7047 | Y |  |  |  | 91956 | 91847
89986 | Mule Deer 345 kV Switch | Establish Mule Deer 345 kV Switch |  | Windmill | Wallaby | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R3031 | 2026-05-14 | 2026-06-30 | 345 | 0 | 0 | 0 |  | Deaf Smith | Deaf Smith | Tier 4 |  |  |  |  | 23909, 23910, 23921 | Y |  |  |  | 89987 | 89986
99185 | This involves moving Potranco to a different bus/bay at Cagnon to alleviate the loading on Cagnon auto 3 & 4. | Move Potranco - Cagnon from Auto 3 & 4 to Cagnon Auto 1 & 2. This involves moving Potranco to a different bus/bay at Cagnon to alleviate the loading on Cagnon auto 3 & 4. |  | 5346 | 5055 | In-Service | S-1053b, T-0412 | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 |  | 2026-05-15 | 2026-04-23 | 138 | 0 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5053, 5055, 5346 | Y |  |  |  | 99186 | 99185
70196 | Kingsland 1 - Sandy Creek Transmission Line Overhaul | LCRA TSC will perform an overhaul on the 7.3-mile Kingsland 1 ¿ Sandy Creek (T400) 69-kV transmission line. |  | Kingsland 1 | Sandy Creek | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 | 2026-04-07 | 69 | 0 | 7.3 | 0 |  | Llano | Llano | Tier 4 |  |  |  |  | 7121, 7400, 7404 | Y | Y |  |  | 70197 | 70196
70534 | Hueco Springs Substation Addition | NBU is constructing a new 138-kV substation to serve a new residential development. LCRA TSC will provide transmission service to the new load serving substation on the T235 Henne to Comal. |  | Henne | Comal | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 | 2026-05-08 | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7174, 7176, 7179 | Y | N |  |  | 70535 | 70534
78408 | Henne Substation Bus Upgrade | LCRA TSC intends to build a new 138 kV line from Henne to Kohlenberg and accommodate this line at Henne. Henne substation will be converted to a breaker and half configuration to improve reliability and support the project. |  | Henne | Henne | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 | 2026-05-10 | 138 | 0 | 0 | 0 |  | Comal | Comal | Tier 4 |  |  |  |  | 7172, 7173, 7174, 7176, 7182 | Y | N |  |  | 78411 | 78408
73106 | Lockhart - San Marcos Transmission Line Conversion | The five LCRA TSC-owned transmission line sections from Lockhart to San Marcos will be converted to 138-kV (T220 San Marcos to Camp Gary to Robert Brown Jr., T519 Robert Brown Jr. to Clear Fork, and T601 Clear Fork to Lockhart). |  | Lockhart | San Marcos | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 | 2026-05-13 | 138 | 0 | 0 | 0 |  | Caldwell | Hays | Tier 4 |  |  |  |  | 7188, 7191, 7192, 7194, 7195, 7196, 7215, 7216 | Y | N |  |  | 78513 | 73106 | 2023-SC11
92561 | LCRATSC_Colton_Elroy_Transmission_Line_Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. |  | 7208 | 7209 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org | PLC-6951 | 2026-05-15 | 2026-05-15 | 138 | 0 | 3.27 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7208, 7209 | Y |  |  |  | 92562 | 92561 | 2024-SC20
92575 | LCRATSC_Canyon_San_Marcos_Transmission_Line_Upgrade |  |  | 7192 | 7200 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org | PLC-7656 | 2026-05-15 | 2026-04-20 | 138 | 0 | 2.8 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7192, 7200, 70502 | Y |  |  |  | 92576 | 92575 | 2024-SC1
92598 | Bluebonnet - Wyldwood Transmission Line Overhaul | Overhaul transmission line structures per LCRA TSC standards and current NESC requirements. Replace existing conductor with bundled-Suwannee. |  | 7210 | 7556 | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org | PLC-6949 | 2026-05-15 | 2026-02-27 | 138 | 0 | 2.43 | 0 |  | Bastrop | Bastrop | Tier 4 |  |  |  |  | 7210, 7556 | Y |  |  |  | 92599 | 92598 | 2024-SC20
85963 | FPP Yard 2 - Lytton Springs Transmission Line Overhaul | LCRA TSC will overhaul FPP Yard #2 - Lytton Springs 345-kV transmission line T255 to ensure structural integrity of the circuit. Engineering will review this transmission circuit for scope including hardware/insulator integrity, structural load issues, need for containment (dead-ends) structures, and clearances at highway and railroad crossings. |  | FPP Yard 2 | Lytton Springs | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2026-05-15 | 2026-05-15 | 345 | 0 | 0 | 0 |  | Fayette | Caldwell | Tier 4 | 24RPG013 | 2024-04-11 | 2024-05-03 |  |  | Y |  |  |  | 85964 | 85963
91549 | Gabriel - Split Transmission Line Upgrade | LCRA TSC will upgrade T223 Gabriel to Georgetown East & T224 Gabriel to Jarrell 138-kV double-circuit transmission line from Gabriel to Split to obtain a higher operational rating. This 1.1-mile transmission line is owned by LCRA TSC. The remaining portions of T223 and T224 from Split to Georgetown East and from Split to Jarrell, respectively, are owned by Oncor. Line ratings and impedances being updated on ONCOR's PMCR 80546, phase #87647. | [5 empty] | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-7996 | 2026-05-15 | 2026-05-15 | 138 | 0 | 0 | 0 |  | Williamson | Williamson | Tier 4 | 25RPG006 |  |  |  |  | Y |  |  |  | 91550 | 91549
71130 | Centerville Switch - Lake Hubbard Switch 138 kV Double-Circuit Line | Upgrade the existing 138 kV Double-Circuit Line |  | Lake Hubbard | Centerville | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4126 | 2026-05-15 | 2026-05-15 | 138 | 0 | 13.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2401, 2402, 2439, 2450 | Y |  |  |  | 71131 | 71130
76652 | Line Termination at Cypress Waters | Vineyard Switch – Hackberry Switch 138 kV Line Termination at Cypress Waters 138 kV Switch |  | Cypress Waters |  | In-Service |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M5344 | 2026-05-15 | 2026-05-15 | 138 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2017, 2386, 2392 | Y |  |  |  | 76653 | 76652
88035 | Pastores 138 kV Switch | Construct a new 138 kV Switch |  | McDonald Road | Catclaw/Mudstone | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R8817 | 2026-05-15 | 2026-05-15 | 138 | 0 | 0 | 0 |  | Glasscock | Glasscock | Tier 4 |  |  |  |  | 1225, 1333, 10121, 11222 | Y |  |  |  | 88040 | 88035
91534A | Establish Glaze Lake 138 kV Switch | Establish Glaze Lake 138 kV Switch |  | Glaze Lake 138 kV Switch | Glaze Lake 138 kV Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6345 | 2026-05-15 | 2026-06-30 | 138 | 19.6 | 0 | 0 |  | Leon | Leon | Tier 4 |  |  |  |  | 3355, 3357, 3790 | Y |  |  |  | 91535 | 91534
92646 | Saddlewood 138 kV Switch | Saddlewood 138 kV Switch |  | Saddlewood |  | In-Service |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3242 | 2026-05-15 | 2026-05-15 | 138 | 0 | 0 | 0 |  | Hunt | Hunt | Tier 4 |  |  |  |  | 1815, 1819, 2843 | Y |  |  |  | 92647 | 92646
92680 | Stainback 345 kV Switch | Establish Stainback 345 kV Switch |  | Stainback 345 kV Switch |  | In-Service |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4383 | 2026-05-15 | 2026-05-15 | 345 | 0 | 0 | 0 |  | Dallas |  | Tier 4 |  |  |  |  | 2217, 2427, 2466, 3159 | Y |  |  |  | 92681 | 92680
92845 | Watermill to Reindeer 138 kV Line | Upgrade Watermill to Reindeer 138 kV Line |  | Watermill Switch | Reindeer | In-Service |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4430 | 2026-05-15 | 2026-05-15 | 138 | 0 | 2.6 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2429, 3065 | Y |  |  |  | 92846 | 92845
92870 | Bradberry Switch 138 kV Capacitors (Skybox Lancaster) | Bradberry Switch 138 kV Capacitors (Skybox Lancaster) |  | Bradberry Switch | Bradberry Switch | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4431 | 2026-05-15 | 2026-07-30 | 138 | 0 | 0 | 0 | 0,55.2 | Dallas |  | Tier 4 |  |  |  |  | 3064 | Y |  |  |  | 92871 | 92870
82810C | Olympus 138 kV Switch | Establish POI for Gaia Solar |  | Olympus | Gaia | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6330 | 2026-05-15 | 2025-05-08 | 138 | 0 | 0 | 0 |  | Navarro | Navarro | Tier 4 |  |  |  |  | 3723, 153963 | Y |  |  |  | 100066 | 82810
76650 | Establish Walleye Creek 345/138 kV Switch | Establish Walleye Creek 345/138 kV Switch |  | Walleye Creek | Walleye Creek | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6243 | 2026-05-15 | 2026-05-15 | 345 |  | 4.5 | 600 | 0,110.4 | Milam | Milam | Tier 3 | 23RPG030 | 2023-09-26 | 2023-10-25 |  | 116, 3541, 3712, 3713, 3714, 3715, 3716, 3717, 3742, 7040, 13429, 13430 | Y |  |  |  | 76651 | 76650
69552D | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 345 kV Switch, Autotransformers, and 345 kV Tie Lines to Limmer (LCRA) |  | Teal | Teal | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6165 | 2026-05-15 | 2025-05-30 | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 3696, 7341, 13363, 13364, 25090 | Y |  |  |  | 104539 | 69552
80921 | Downtown Kyle Substation Addition | Models the addition of a planned substation in Kyle area. |  | DOWNTOWN KYLE 70503 |  | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-05-15 | 2026-05-15 | 138 | 0 | 0 | 0 |  | Hays |  | Tier 4 |  |  |  |  | 70198, 70502, 70503 | Y |  |  |  | 80922 | 80921
67093 | New 138 kV station cut-in between Garfield and Hi-Cross | New 138 kV Easton Park Substation cut-in on CKT963 from Garfield to Hi-Cross substation to serve BBEC Load |  | 9143 | 9071, 9147 | In-Service |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2026-05-15 | 2026-05-14 | 138 | 0.43 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 9071, 9143, 9147 | Y |  |  |  | 67094 | 67093
71903 | Establish Launch Pad 138 kV Switch | Establish Launch Pad 138 kV Switch |  | Launch Pad | Launch Pad | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6156 | 2026-05-16 | 2026-05-15 | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3372, 3593, 3594, 3601, 3709 | Y |  |  |  | 71904 | 71903
80466 | Oleander: Construct New 138 kV Terminal | Interconnect Citrus Flatts BESS to the Oleander 138 kV station | IN-SERVICE | Oleander |  | In-Service |  | AEP TCC | Brooks Dow jlsolis@aep.com 361-881-5574 |  | 2026-05-16 | 2025-12-19 | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 80022, 164522 | Y |  |  |  | 80467 | 80466
64581A | New 138kV Waterfowl substation | Reconfigure existing Ckt.02F (move Seadoc/Seaway onto other circuit) resulting in Ckt.36 COPPER to Booster tap to Jones Creek. |  | COPPER | Jones Creek | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 | 2026-05-20 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 5568, 42195, 42199, 42215, 42540, 43211, 43212, 43221, 48006, 48007, 48039, 48333, 48334 | Y | N |  |  | 102644 | 64581
61552 | Matador to Turkey: Rebuild 69 kV Line | Rebuild 69 kV line from Matador to Turkey | IN-SERVICE | Matador | Turkey | In-Service | 1128 - 1306 | AEP TNC | Chris Carroll twang1@aep.com 918-599-2635 | 1873 | 2026-05-30 | 2026-05-30 | 69 | 0 | 26.9 | 0 |  | Motley | Hall | Tier 4 |  |  |  |  | 6020, 6024, 6039, 6041, 6044, 6140, 60351 | Y | N |  |  | 65596 | 61552
70898 | Flomot Tap: Rebuild 69 kV Line | Rehab Flomot Tap 69 kV Line | IN-SERVICE / Dollars update | Flomot Tap | Flomot | In-Service |  | AEP TNC | Chris Carroll myturner@aep.com 918-599-2437 |  | 2026-05-30 | 2026-05-30 | 69 | 0 | 7.06 | 0 |  | Motley | Motley | Tier 4 |  |  |  |  | 6041, 6042 | Y | N |  |  | 70899 | 70898
64581B | New 138kV Waterfowl substation | Install new CEHE-owned 138kV Waterfowl (WTR) substation. Reconfigure existing Ckt.02F and install new conductor to create new Ckt.54A Jones Creek to Waterfowl |  | Jones Creek | Waterfowl | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 00:01 | 2026-05-20 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 42540, 43470 | Y | N |  | Cost included in main entry | 102645 | 64581
64581C | New 138kV Waterfowl substation | Install new CEHE-owned 138kV Waterfowl (WTR) substation. Convert customer-owned Seadoc substation to loop service. Reconfigure existing Ckt.02F and reconnect Seadoc/Seaway to create new Ckt.02F Jones creek to Seadoc loop to Seaway tap to Waterfowl. |  | Jones Creek | Waterfowl | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 00:02 | 2026-05-20 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 42540, 43211, 43222, 43470, 48007 | Y | N |  | Cost included in main entry | 102646 | 64581
64581D | New 138kV Waterfowl substation | Install new CEHE-owned 138kV Waterfowl (WTR) substation. Remove existing Seaway Switchrack. Reconfigure existing Ckt.02F to create new Ckt.02L Waterfowl to Franklins Camp. |  | Waterfowl | Franklins Camp | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-30 00:03 | 2026-05-20 | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 | 21RPG009 | 2021-05-24 | 2021-06-16 |  | 5568, 43470 | Y | N |  | Cost included in main entry | 102647 | 64581
59959 | New Hickory 345kV Switchyard | Build a new New Hickory 345 switchyard to connect New Hickory Solar plant. This new Switchyard will loop into the existing Elm Creek to STP circuit 2 transmission line. |  | 5323 | 5133, 5915 | In-Service |  | CPS/NO | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0303; S-0940 | 2026-05-30 20:00 | 2026-05-16 | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5133, 5323, 5915 | Y |  |  |  | 59960 | 59959
71004A | Julia CEHE-Owned Sub for Melaza Solar (21INR0220) | Install new Julia (JUL) CEHE substation for generator interconnection to Maleza Solar. Loop Ckt.72 into Julia substation to create new Ckt.72 Hillje to Julia to Blue |  | Julia | Hillje/Blue | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-05-15 | 345 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 44060, 44200, 44220 | Y | N |  |  | 87171 | 71004
75835D | Upgrade Ckt.66B Stone Lake to Tomball to increase thermal limits. Install 40 MVAR cap bank at Hockley substation and tapped on Ckt.66B Hockley to Stone Lake. | Upgrade equipment to increase thermal limits. Phase Two of overall approved upgrades |  | Stone Lake | Tomball | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2025-12-10 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 3 | 23RPG012 | 2023-05-04 | 2023-05-26 | 2023-05-26 | 46510, 48348 | Y | N |  |  | 98431 | 75835
90130 | Install (2) new 100 MVA distribution transformers at Orchard substation. | Install two(2) new 100 MVA distribution transformers at Orchard substation. |  | Orchard | Beasly /MARICK | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-05-13 | 138 | 0 | 0 | 0 |  | Fort Bend |  | Tier 4 |  |  |  |  | 42420, 44521, 44540, 44541, 44545, 48441 | Y | N |  |  | 103882 | 90130
78427A | Bohemian (BOH) 138kV CEHE Substation for Destiny Storage (24INR0397) | Install new CEHE 138kV Bohemian (BOH) substation for generator interconnection to Destiny Storage. Loop Ckt.66K into substation to create new Ckt.66 Crosby to Bohemian to Eastgate. |  | Rhapsody | Crosby/ Eastgate | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-02-07 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40390, 40690 | Y | N |  |  | 103231 | 78427
99453L | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.97G Chambers to Jordan to increase thermal limits as part of FRM2 upgrades. |  | Chambers | Jordan | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-03-24 | 345 | 0 | 0 | 0 |  | Harris | Chambers | Tier 4 |  |  |  |  | 40255, 40850 | Y | N |  |  | 102617 | 99453
99453V | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.99 Limestone to Navarro to increase thermal limits as part of FRM2 upgrades. |  | Limestone | Navarro | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-05-08 | 345 | 0 | 0 | 0 |  | Navarro | Limestone | Tier 4 |  |  |  |  | 46020, 68091 | Y | N |  |  | 102614 | 99453
99453D | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.97A North Belt to TH Wharton to increase thermal limits as part of FRM2 upgrades. |  | North Belt | TH Wharton | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-02-16 | 345 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 45500, 46100 | Y | N |  |  | 102606 | 99453
99453A | Facility Ratings Methodology Phase 2 (FRM2) Upgrades | Upgrade Ckt.18 STP to Shaula (Elm Creek) to increase thermal limits as part of FRM2 upgrades. |  | STP | Shaula | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-02-25 | 345 | 0 | 0 | 0 |  | Guadalupe | Matagorda | Tier 4 |  |  |  |  | 5380, 5915 | Y | N |  |  | 102604 | 99453
63922 | Tiki Island Distribution Upgrades | Install double-tap distribution service to Tiki Island. Existing tap will remain on Ckt.63E La Marque to Stewart. Tap Ckt.93C La Marque to West Galveston for the new tap section to Tiki Island. |  | Tiki Island | LaMarque/West Galveston | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-05-14 | 138 | 0 | 0 | 0 |  | Galveston |  | Tier 4 |  |  |  |  | 42860, 43290, 43351, 43352, 43355, 43400, 48551, 48552, 48855 | Y | N |  |  | 91179 | 63922
87640 | New load customer interconnection RAOULT connecting on ckt 86 between DALTON and BRINE. | New load customer interconnection RAOULT connecting on ckt 86 between DALTON and BRINE. Expect transmission breakers in ring bus configuration for new RAOULT substation. |  | RAOULT | DALTON/ BRINE | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-04-29 | 138 | 0 | 0 | 0 |  | Chambers | Chambers | Tier 4 |  |  |  |  | 40220, 40740, 41740 | Y | N |  |  | 87641 | 87640
85970A | Athena (ATH) 138kV CEHE Station for RAVEN (RVN) / Raven Solar & Storage (24INR0209 & 24INR0210) | Loop new Athena CEHE 138kV substation into Ckt.65C East Bernard to Wallis to create new Ckt.65 East Bernard to Athena to Wallis. |  | Athena | East Bernard/Wallis | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 | 2026-05-04 | 138 | 0 | 0 | 0 |  | Wharton | Austin | Tier 4 |  |  |  |  | 44190, 44740, 46650 | Y | N |  |  | 87177 | 85970
6749 | Rosata: Build 138kV Substation | Build new Rosata 138 kV POD Switch on the Coleto Creek to Kenedy 138 kV line |  | Rosata |  | In-Service | 898 - 1076 | AEP TCC | Chase Stevens deevans@aep.com 918-599-2938 | 3682 | 2026-05-31 | 2026-05-31 | 138 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7241, 8153, 8162, 8186, 88153 | Y | Y |  |  | 14542 | 6749
90336 | DURZNO (DUR) 138kV Customer Substation | Install new customer-owned 138kV DURZNO (DUR) substation. Loop into Ckt.54 to create new Ckt.54 Jones Creek to DURZNO to Waterfowl. |  | DURAZNO | Jones Creek/ Waterfowl | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 | 2026-05-20 | 138 | 0.2 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42540, 43470, 43481 | Y | N |  |  | 90760 | 90336
78427B | Bohemian (BOH) 138kV CEHE Substation for Destiny Storage (24INR0397) | Install generator lead from Bohemian (BOH) substation to Rhapsody / RHAPSO (RHA) / Destiny Storage |  | Rhapsody | BOHEMI | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 00:01 | 2026-02-07 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40970, 113862 | Y | N |  |  | 103232 | 78427
102401 | LST_SamSwitch_Resiliency_(GTC)_Project | This project loops Helix to Navarro Circuit into LST Sam Switch station |  | Helix | Navarro | Planned |  | LST | Chenyan Guo Chenyan.guo@lonestar-transmission.com 305-972-0663 |  | 2026-06-01 | 2026-06-10 | 345 | 0 | 0 | 0 |  | Hill | Hill | Tier 3 | 25RPG031 |  |  |  | 68035, 68090, 68096 | Y |  |  |  | 102402 | 102401
87146 | GSEC_Tier4_9468_Add_Bull_Sub | New Substation Load out of 68001 Claytonville | Adding new 1400MW load with deposit and agreement. | Claytonville |  | In-Service |  | GSEC | John Vara jvara@gsec.coop 806-349-5228 |  | 2026-06-01 | 2026-05-01 | 345 | 0 | 0 | 0 |  | Fisher |  | Tier 4 |  |  |  |  | 9468, 68001 | Y |  |  |  | 87147 | 87146
76139 | Juncus: Construct New 69 kV Station | Interconnect the TEC Snodgrass load to the new Juncus 69 kV station on the Abilene South to Steamboat 69 kV line | IN-SERVICE | Juncus |  | In-Service |  | AEP TNC | Bill Edwards myturner@aep.com 918-599-2437 | TP2023074 | 2026-06-11 | 2026-07-22 | 69 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6326, 6328, 60002, 60133 | Y | Y |  |  | 76140 | 76139
69473 | Jaguar: Construct New Distribution Station | Construct new distribution station on the McGruder to Thomaston 138 kV line | IN-SERVICE | Jaguar |  | In-Service |  | AEP TCC | Will Simmons deevans@aep.com 918-599-2938 |  | 2026-06-11 | 2026-04-16 | 138 | 0 | 0 | 40 |  | Victoria |  | Tier 4 |  |  |  |  | 8183, 8194, 8724 | Y |  |  |  | 69474 | 69473
72942 | Bluff Creek: 138 kV Station Work | Replace fourteen (14) 138 kV Breakers and one (1) Circuit Switcher | IN-SERVICE | Bluff Creek |  | In-Service |  | AEP TNC | Remington Hajdik myturner@aep.com 918-599-2437 |  | 2026-06-11 | 2026-04-30 | 138 | 0 | 0 | 0 |  | Taylor |  | Tier 4 |  |  |  |  | 6216, 6260, 6351, 60040, 60043, 66216, 66217, 180455, 180463 | Y | N |  |  | 72943 | 72942
73359 | Vertrees: Construct New Distribution Station | Construct new distribution station on the Stewart Road to Weslaco Unit 138 kV line | IN-SERVICE | Vertrees |  | In-Service |  | AEP TCC | Jacob Pyle jlsolis@aep.com 361-881-5574 |  | 2026-06-11 | 2026-05-19 | 138 | 0 | 0 | 0 |  | Hidalgo |  | Tier 4 |  |  |  |  | 8348, 8662, 8737, 8951 | Y |  |  |  | 73360 | 73359
70900E | Roanoke Area Upgrades | Ramhorn Hill – Dunham 345 kV Double-Circuit Line |  | Dunham Switch | Ramhorn Switch | In-Service |  | ONCOR | Harsh Naik HARSH.NAIK@oncor.com 817-215-6771 | M5281 M5144 M5146 M5148 | 2026-06-15 | 2026-06-30 | 345 | 36.8 | 0 | 0 |  | Tarrant | Tarrant | Tier 1 | 22RPG003 | 2022-02-15 | 2022-03-15 | 2022-08-15 | 12067, 12068 | Y | N |  |  | 102863 | 70900
62643 | Rebuild Waco East 138 kV Switch | Rebuild Waco East 138 kV Switch |  | Waco East | Waco East | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6146 | 2026-06-24 | 2958101 | 138 | 0 | 0 | 0 |  | McLennan | McLennan | Tier 4 |  |  |  |  | 3434, 3438, 3439, 3443, 3452, 3481, 3482, 3551, 3559, 3708, 13438 | Y |  |  |  | 62664 | 62643
63956 | Clear Crossing: Build 345 kV terminal | Interconnect HODL Ranch II at Clear Crossing 345 kV station | IN-SERVICE | Clear Crossing | HODL Ranch II | In-Service | 1139 - 1317 | ETT/AEP TNC | Raza Ansari myturner@aep.com 918-599-2437 | 1884 | 2026-06-30 | 2026-06-30 | 345 | 0 | 0 | 0 |  | Haskell | Haskell | Tier 4 |  |  |  |  | 60017, 60515 | Y | N |  |  | 63957 | 63956
91402 | Buchanan_Burnet_TL_Overhaul | Perform an overhaul on the 11.4 mile T108 Buchanan - Burnet 69-kV (de-energized) transmission line |  | Buchanan | Burnet | Planned |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 | PLC-6943 | 2026-06-30 | 2026-06-25 | 138 | 0 | 11.4 | 0 |  | Burnet | Burnet | Tier 4 |  | 2025-06-03 | 2025-06-25 |  | 7087, 7092, 7093, 7097, 7100 | Y |  |  |  | 91403 | 91402 | 25RPG015
105347 | Adding back in Sharyland Kingfisher Station with a Planned ISD 05/31/2026 |  | Original modeling was delayed by other TSP | Palmito | Stewart Road | Under Construction |  | SLU | Charles Aleman caleman@huntutility.com 682-406-9656 |  | 2026-06-30 | 2026-06-30 | 345 | 0 | 0 | 0 |  | Cameron | Cameron | Tier 2 | 21RPG017 | 2020-09-20 | 2021-11-21 | 2021-12-21 | 8383, 79500, 79501, 80137 | Y |  |  |  | 105348 | 105347
90180B | Clodine Reconfiguration for Houston IV BESS (24INR0584) | Reposition Ckt.25B Clodine to Roark to the existing W670/W710 breaker position. |  | Clodine | Roark | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-06-30 | 2026-04-17 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | Y | N |  |  | 90182 | 90180
48774 | Fincas: Build new 138 kV distribution station | Construct new distribution station on the University to Wormser 138 kV line | IN-SERVICE | Fincas |  | In-Service | 1026 - 1204 | AEP TCC | Travis Coody jlsolis@aep.com 361-881-5574 | 3765 | 2026-06-30 | 2026-06-30 | 138 | 0 | 0 | 0 |  | Webb |  | Tier 4 |  |  |  |  | 8039, 8295, 8649, 8650, 8653 | Y | N |  |  | 81145 | 48774
73371B | BP24 Sub Upgrades | Upgrade Bellaire Auto A5 CTs to increase thermal limits |  | Bellaire |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-06-30 00:01 | 2026-06-23 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 47000, 47015, 49003 | Y | N |  |  | 89979 | 73371
90180A | Clodine Reconfiguration for Houston IV BESS (24INR0584) | Install one new generator lead at the existing Clodine W670/W680 breaker position for Houston IV BESS. |  | Clodine | Generator | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-06-30 00:01 | 2026-04-17 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 44140, 114523 | Y | N |  |  | 90181 | 90180
105583 | [5 empty] | Planned |  | DME | Mark Zimmerer Mark.Zimmerer@cityofdenton.com 940-349-7169 |  | 2026-07-01 | 2026-07-01 | 138 | 0.83 | 0 | 0 |  | Denton | Denton | Tier 4 |  |  |  |  | 901, 909, 910, 911, 912 | Y |  |  |  | 105584 | 105583
91534B | Establish Glaze Lake 138 kV Switch | Establish Glaze Lake 138 kV Switch Gen Tie |  | Glaze Lake 138 kV Switch | Leon Solar | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6345 | 2026-07-01 | 2026-05-15 | 138 | 0.28 | 0 | 0 |  | Leon | Leon | Tier 4 |  |  |  |  | 3790, 121175 | Y |  |  |  | 104654 | 91534
70882 | Rebuild Olivia - Carancahua | rebuild Olivia sw to Carancahua 795 ACSR |  | Olivia SW | Carancahua | In-Service |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2026-07-01 | 2026-07-15 | 69 | 0 | 8.71 | 0 |  | Jackson | Matagorda | Tier 4 |  |  |  |  | 5573, 5574 | Y |  |  |  | 70883 | 70882
72582C | Nameless to Leander Transmission Line Upgrade | Upgrade final span into Nameless, upgrade terminal equipment, and achieve circuit rating of 440 MVA. (Replaces ERCOT Project # 61279C) | 1/10/2023: Added information to clarify circuit rating. | Hero Way | Nameless | Planned |  | PEC | Joshua Rivers joshua.rivers@peci.com 830-330-4192 |  | 2026-07-01 | 2026-05-01 | 138 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 70526, 70536 | Y | N |  |  | 72585 | 72582
88867 | Rosita Creek Substation 138-kV T2 Power Transformer Addition. Replacing Committed project 57343 | Add second 138/13.09-kV power transformer bay with new 138-kV transmission switch and circuit switcher interconnected at LCRA Switch# 12669. New power transformer capacity will be 15/20/25 MVA. Replaces committed project 57343. | Site construction is complete. T2 ready for hot commissioning pending LCRA approval. | Rosita Creek | Rosita Creek | Planned |  | RGEC | Ruben Quiroga rquiroga@rgec.coop 830-291-4203 |  | 2026-07-24 | 2025-09-02 | 138 | 0 | 0 | 0 |  | Maverick | Maverick | Tier 4 |  |  |  |  | 78015 | Y |  |  |  | 88868 | 88867
79462 | Expand HO Clarke substation for Callisto II (22INR0558) | Expand HO Clarke substation for Callisto II (22INR0558) |  | HO Clarke |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-07-31 | 2026-05-15 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 | [5 empty] | Y | N |  |  | 109686 | 79462
85970B | Athena (ATH) 138kV CEHE Station for RAVEN (RVN) / Raven Solar & Storage (24INR0209 & 24INR0210) | Install one generator lead from Athena CEHE 138kV substation to RAVEN / Raven Solar & Storage (24INR0209 & 24INR0210). |  | Athena | RAVEN | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-07-31 00:01 | 2026-05-04 | 138 | 0 | 0 | 0 |  | Wharton |  | Tier 4 |  |  |  |  | 46650, 115092 | Y | N |  |  | 87178 | 85970
1275 | Hawkins to Gainesville | Hawkins to Gainesville |  | Hawkins | Gainesville | Planned |  | BEPC | Brian Hithersay bhithersay@brazoselectric.com 254-750-6795 |  | 2026-08-01 | 2026-11-01 | 69 | 0 | 6.72 | 80 |  | Cooke | Cooke | Tier 4 |  |  |  |  | 705, 706, 707, 726, 33705, 33706, 33726 | Y |  |  |  | 67891 | 1275
86011 | Snug 138kV Substation expansion for Cottonwood Bayou Storage (21INR0443) | Install Cottonwood Bayou Storage (21INR0443) at Snug 138kV substation. Connect at the same generator lead as Cottonwood Bayou Solar. |  | Snug |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 | 2025-05-23 | 138 | 0 | 0 | 0 |  | Brazoria |  | Tier 4 |  |  |  |  | 44890, 113435 | Y | N |  |  | 86012 | 86011
78485F | Britmoore to Bellaire Ckt.24B Upgrades | Upgrade Ckt.24B Hayes to Britmoore to increase thermal limits. |  | Hayes | Britmoore | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 | 2026-08-13 | 138 | 0 | 6.41 | 0 |  | Harris | Harris | Tier 3 | 23RPG025 | 2023-09-06 | 2023-09-28 | 2023-09-28 | 44120, 47014, 48159, 48512 | Y | N |  |  | 98951 | 78485
99399 | TH Wharton CB2 Cap Bank | Remove 120 MVAR CB1 cap bank from Velasco substation. Install removed CB1 cap bank at TH Wharton substation as replacement for THW CB2. |  | Velasco | TH Wharton | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 | 2025-09-30 | 138 | 0 | 0 | 0 |  | Harris |  | Tier 4 |  |  |  |  | 43360, 45515 | Y | N |  |  | 99400 | 99399
71106 | Dunlavy to HO Clarke Ckt.40A Partial Reconductor | Reconductor portions of Ckt.40A Dunlavy to HO Clarke ahead of future 138kV conversions |  | Dunlavy | HO Clarke | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 | 2026-07-09 | 69 | 0 | 4.41 | 0 |  | Harris | Harris | Tier 4 | 22RPG019 |  |  |  | 47015, 47160, 47320, 47580 | Y | N |  |  | 71107 | 71106
86009 | Expand ADLONG substation for XE Murat Storage (24INR0329) | Expand facilities at customer-owned ADLONG substation for XE Murat Storage (24INR0329). Utilize existing generator lead Eastgate to XE Murat Solar. |  | Eastgate | ADLONG | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-08-30 00:02 | 2025-03-06 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 40690, 113542 | Y | N |  |  | 98398 | 86009
69552E | Teal 345/138 kV Switch connected to LCRA POI (Limmer) | Teal 345 kV Switch, Autotransformers, and 345 kV Tie Lines to Limmer (LCRA) |  | Teal | Teal | In-Service |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | R6165 | 2026-09-15 | 2025-05-30 | 345 | 0 | 0 | 600 |  | Williamson | Williamson | Tier 3 | 22RPG027 | 2022-08-15 | 2022-09-15 |  | 3362, 3363, 3364, 3696, 7341, 13363, 13364 | Y |  |  |  | 111359 | 69552
86013 | Fairmont Distribution Reconfigurations with 4th Transformer | Install fourth Fairmont distribution transformer on Ckt.95F to create new Ckt.95F SOUTH to Fairmont TR4 tap to Clear Lake tap to Polaris tap to Kemah tap to PH Robinson 138kV North. Remove Fairmont TR3 from Ckt.95F and onto the Ckt.35A Fairmont line position. |  | Fairmont |  | In-Service |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-09-30 | 2026-07-31 | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 |  |  |  |  | 42614 | Y | N |  |  | 111428 | 86013

## CancelledTPIT100126NoCost
OCTOBER BASE FOR TRANSMISSION OWNER SUBMISSION FILE - TRANSMISSION PROJECT INFORMATION TRACKING (TPIT) FUTURE PROJECTS AS OF 10/1/2026
ERCOT Project Number | Project Title (text, please start with location name first) | Project Description (text) | Comments/Reasons for Delays/Changes/Speedup (text) (Optional) | Terminal "from" Location | Terminal "to" Location | Transmission Status "under construction, planned or conceptual" | Associated Projects (project number) (Optional) | Transmission Owner (text) | TSP/Company Contact | Transmission Owner Project Number (Optional) | Projected In-Service Date (Month/Yr) | Actual In-Service Date (Month/Yr) | Service Level kV | Trans Circuit Miles New | Trans Circuit Miles Rebuilt, Reconductored or Upgraded | Autotransformer Capacity (MVA) | Reactive Capability Added (Mvar ) (-Reactor, +Capacitor ) | County Location for Substation or Starting Point for a Line | County Location for Ending Point for a Line (Optional for Substation projects) | Planning Charter Tier | RPG Number | Date Submitted TO ERCOT for RPG Review (Month/Yr) | Date RPG Review Completed (Month/Yr) | Date ERCOT BOD Review Completed (Month/Yr) | SSWG Base Case Related Bus Numbers (If applicable) (CSV) | Is the project reflected in SSWG Base Cases? (Y/N) | Part of Interface (Y/N) | Requested Additional Information (Optional) | Other (Optional) | Phase Number | MOD Project Number | RTP Project Number
55603 | Big Foot to Pearsall: Rebuild 69 kV line | Rebuild 69 kV line from Big Foot to Dilley | Cancelled, incorrectly submitted prior to RPG submission. | Big Foot | Pearsall | Planned | 1104 - 1282 | AEP TCC | Bill Roberts bcogan@aep.com 918-599-2857 | 3821 | 2022-11-30 | 2025-05-12 | 69 | 0 | 14.79 | 0 |  | Frio | Frio | Tier 3 |  |  |  |  | 8216, 8218 | N |  |  |  | 65571 | 55603
3901 | Lobo to Freer: Rebuild 69 kV line | Rebuild Lobo to Freer 69 kV line with 795 ACSS | CANCELLED | Lobo | Freer | Planned | 677 - 0846 | AEP | Brandon Cogan bcogan@aep.com 918-599-2857 | 2596 | 2025-01-07 |  | 69 | 0 | 49.8 | 0 |  | Webb | Duval | Tier 3 |  |  |  |  | 8505, 80222 | N | N |  |  | 11371 | 3901 | 2013-R90
81573 | Oklaunion: Construct New 345 kV Terminal | Interconnect the Alpha load to the existing Oklaunion 345 kV station | CANCELLED | Oklaunion |  | Conceptual |  | AEP TNC/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-03-11 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6100 | N |  |  |  | 81574 | 81573
61467 | Merrilltown Substation Addition | New 138 kV station - Oncor load | [5 empty] | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2025-03-14 |  | 138 | 0 | 0 | 0 | 0,31.2 | Williamson | Williamson | Tier 4 |  |  |  |  | 9223, 9224, 9230, 9231 | N |  |  |  | 61468 | 61467
07TPIT0069 | Sterrett - Sardis 138 kV line | Upgrade existing 138 kV line |  | Sterrett | Sardis | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M361-E | 2025-05-15 |  | 138 | 0 | 2 | 0 |  | Ellis | Ellis | Tier 4 | [5 empty] | N | N |  |  | 10446 | 3102
61451 | La Vernia Substation | Replace T2, 20 MVA with a 40MVA dual high-dual low |  | La Vernia | La Vernia | Planned |  | GVEC | Rene A. Hernandez rhernandez@gvec.or |  | 2025-05-16 |  | 138 | 0 | 0 | 0 |  | Wilson | Wilson | Tier 4 |  |  |  |  | 7614 | N | N |  |  | 61452 | 61451
48854 | Adds Annova and Port South Bus and lines | Adds Annova and Port South buses, lines to connect Annova to Port South, line from HWY 511 to Port South, and reconnects line from S Carbide to HWY 511 into Port South |  | Annova LNG | Port South | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2025-06-01 |  | 138 | 22.1 | 0 | 0 | 0,120 | Cameron | Cameron | Tier 4 |  |  |  |  | 5767, 5775, 5776, 8337 | N | N |  |  | 48855 | 48854
70943 | Double circuit 138kV tie between Pyote and Coyanosa | Project resubmitted as PMCR ID # 77805 |  | Pyote (bus # 38001) | Coyanosa (bus # 38380) | Conceptual |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-06-01 |  | 138 | 15 | 0 | 0 |  | Ward | Reeves | Tier 2 |  |  |  |  | 38001, 38380 | N |  |  |  | 70944 | 70943
64021 | Texana Solar Interconnection | Connect the Texana Solar to the El Campo to Victoria 138 kV line | CANCELLED | El Campo | Victoria | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2020888 | 2025-06-24 |  | 138 | 0 | 0 | 0 |  | Wharton | Victoria | Tier 4 |  |  |  |  | 8099, 8102, 8117, 8192, 8675 | N |  |  |  | 64022 | 64021
65723 | Riedel: Build New Distribution Station | Construct new distribution station on the Magnolia Tap to Nixon 138 kV line | CANCELLED | Riedel |  |  | 1032 - 1210 | AEP TCC/LCRA | Michael Forcum mlforcum@aep.com 918-599-2674 | 3771 | 2025-06-24 |  | 138 | 0 | 0 | 0 |  | Karnes |  | Tier 4 |  |  |  |  | 8583 | N | Y |  |  | 65724 | 65723
69469 | Equinox Solar Project | Equinox Solar Project | CANCELLED | Cenizo | Del Sol |  |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 |  | 2025-06-25 |  | 345 | 0 | 0 | 0 |  | Starr | Starr | Tier 4 |  |  |  |  | 80355, 88355 | N |  |  |  | 69470 | 69469
76174 | Origin 138 kV Interconnection | Interconnect Callon Petroleum on the Saragosa to Solstice 138 kV line | CANCELLED | Origin |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2025-06-30 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60206, 60207, 60208, 60209, 60211, 60716 | N | N |  |  | 76175 | 76174
71136 | Waxahachie-Waxahachie OCF 69 kV Line Rebuild | Rebuild the existing Waxahachie-Waxahachie OCF 69 kV Line |  | Wilmer | Waxahachie | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4339 | 2025-07-01 |  | 69 | 0 | 0 | 0 |  | Dallas | Ellis | Tier 4 |  |  |  |  | 2335, 2343 | N |  |  |  | 71137 | 71136
92695 | Switchgrass station and Customer sub | Project cancelled by customer. |  |  |  | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2025-10-01 |  | 138 | 0 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 38069, 38070, 38071, 38294 | N |  |  |  | 94008 | 92695
78627 | RCEC_SherwoodShores_AddCap |  |  |  |  | Planned |  | RCEC | Stephen Geiger sgeiger@rayburnelectric.com 469-402-2112 |  | 2025-10-01 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 4 |  |  |  |  | 6806 | N |  |  |  | 78628 | 78627
76288 | Hecker to McCampbell: Rebuild 138 kV Line | Rebuild the Hecker to McCampbell 138 kV Line | CANCELLED | Hecker | McCampbell | Planned |  | AEP TCC | Glen Reed gareed@aep.com 918-599-2664 | TP2023507 | 2025-11-30 |  | 138 | 0 | 0 | 0 |  | San Patricio | San Patricio | Tier 4 |  |  |  |  | 8565, 80470 | N | N |  |  | 76289 | 76288
76280 | Reforzar: Build new 345 kV station - stage 2 | Build new 345 kV station on the Lon Hill to North Edinburg 345 kV line | CANCELLED | Reforzar |  | Planned |  | AEP TCC | Michael Forcum mlforcum@aep.com 918-599-2674 | TP2022035 | 2026-01-30 |  | 345 | 0 | 0 | 0 |  | Brooks |  | Tier 1 | 21RPG017 | 2020-09-15 | 2021-11-29 | 2021-12-10 | 80078 | N |  |  |  | 76281 | 76280
81146 | Southmayd 138 kV Switch | Establish Southmayd 138 kV Switch |  | Southmayd |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M4338 | 2026-05-15 |  | 138 | 0 | 0 | 0 |  | Grayson |  | Tier 4 |  |  |  |  | 1744, 2790, 11704 | N |  |  |  | 81147 | 81146
16TPIT0068 | Venus - Chaparral Steel Tap 138 kV Line | Upgrade existing line |  | Venus | Chaparral Steel Tap | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4113-E | 2026-05-15 |  | 138 | 0 | 5.5 | 0 |  | Ellis | Ellis | Tier 4 |  |  |  |  | 1908, 2300 | N | N |  |  | 10426 | 3082 | 2013-R50
16TPIT0064 | Simpson Stuart - Lancaster Witt 138 kV Line | Upgrade existing line |  | Simpson Stuart | Lancaster Witt | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4112-E | 2026-05-15 |  | 138 | 0 | 3 | 0 |  | Dallas | Dallas | Tier 4 |  |  |  |  | 2988, 3068 | N | N |  |  | 10416 | 3072 | 2013-R25
5496 | Forney Switch 345 kV Terminal Equipment | Upgrade the terminal equipment at Forney 345 kV Switch |  | Royse |  | Planned |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M3022 | 2026-05-15 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 4 |  |  |  |  | 2437, 2478 | N |  |  |  | 62442 | 5496
92865 | Oncor_ME_92865_Kirkland Park 138kV Capacitor Bank | Install capacitor banks at Kirkland Park |  | Kirkland Park | Kirkland Park | Planned | M4022 | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 |  | 2026-05-15 |  | 138 | 0 | 0 | 0 | 0,110 | Dallas |  | Tier 4 |  |  |  |  | 2457 | N |  |  |  | 92866 | 92865
99004 | Install 30MVAR cap bank at Fulshear distribution substation. |  |  | Fulshear |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-05-31 |  | 138 | 0 | 0 | 0 | 0,30 | Fort Bend |  | Tier 4 |  |  |  |  | 44750 | N | N |  |  | 99005 | 99004
81581 | Riley: Construct New 345 kV Terminal | Interconnect the Gamma load to the existing Riley 345 kV station | CANCEL | Riley |  | Conceptual |  | AEP TNC/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-06-30 |  | 345 | 0 | 0 | 0 |  | Wilbarger |  | Tier 4 |  |  |  |  | 6111 | N |  |  |  | 81582 | 81581
81647 | Dupont Switch to Sardinia: Construct New 138 kV Line | Interconnect the Epsilon load to the new Sardinia 138 kV station out of the existing Dupont Switch 138 kV station | CANCEL | Dupont Switch | Sardinia | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-06-30 |  | 138 | 2 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 8143, 81433 | N |  |  |  | 81648 | 81647
66122 | Tiempo: Build new 345 kV terminal | Interconnect Redonda Solar to the Tiempo 345 kV station |  | Tiempo |  | Under Construction |  | ETT | Aaron Fahey jlsolis@aep.com 361-881-5574 | TP2022009 | 2026-07-15 |  | 345 | 0.1 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 80224, 80232 | N |  |  |  | 66511 | 66122
70662 | Cobra: Build new 345 kV station | Interconnect Garcitas Solar to the new Cobra 345 kV station on the Radiant to Static 345 kV line | CANCEL | Cobra |  | Planned |  | AEP TCC | Zachary Lachiusa deevans@aep.com 918-599-2938 | TP2022750 | 2026-10-31 |  | 345 | 0 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5915, 8676, 8715, 8728 | N |  |  |  | 70663 | 70662
70305 | Camp Elizabeth: Build new 69 kV station | Construct new 69 kV box bay station with capacitor bank on the College Hills West to Sterling City 69 kV line | CANCELLED | Camp Elizabeth |  | Planned |  | AEP TNC | Bradley Case myturner@aep.com 918-599-2437 |  | 2026-11-30 |  | 69 | 0 | 0 | 0 | 0,7.7 | Sterling |  | Tier 4 |  |  |  |  | 6417, 6435, 6436, 6641, 11352 | N | N |  |  | 70306 | 70305
73621A | Hawkinsville (HAW) CNP-Owned 345kV Substation for Lavaca Bay Solar (23INR0084) | New 345kV Hawkinsville (HAW) substation for generator interconnection to Lavaca Bay Solar. Loop Ckt.27D into substation to create new Ckt.27 Jones Creek to Hawkinsville to Refuge. |  | Waterhole | BAILEY/Jones Creek | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 |  | 345 | 1.4 | 0 | 0 |  | Matagorda | Brazoria | Tier 4 |  |  |  |  | 42400, 42440, 42530 | N | N |  |  | 87138 | 73621
73621B | Hawkinsville (HAW) CNP-Owned 345kV Substation for Lavaca Bay Solar (23INR0084) | Install generator lead from Hawkinsville (HAW) substation to LAVACA / Lavaca Bay Solar. |  | Waterhole | PHOTON | Planned |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-11-30 00:01 |  | 345 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 | [5 empty] | N | N |  |  | 87139 | 73621
72029A | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ Solar (23INR0040) and Dori BQ BESS (24INR0196) | Loop new CEHE 138kV substation Ashville (ASH) into Ckt.06F Garden Villas to Holmes to create new Ckt.06 Garden Villas to Ashville to Holmes |  | Ashville | Garden Villas/ Holmes | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 90115 | 72029
81825 | Houdini: Construct New 345 kV Station | Interconnect the Xi load to the new Houdini 345 kV station on the STP to WAP 345 kV line | CANCEL | Houdini |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Matagorda |  | Tier 4 |  |  |  |  | 43990, 44000, 88800 | N |  |  |  | 81826 | 81825
81799 | Four Corners: Construct New 345 kV Station | Interconnect the Nu load to the new Four Corners 345 kV station on the Edith Clarke to Tesla 345 kV line | CANCEL | Four Corners |  | Conceptual |  | AEP TNC/ETT | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 |  | Hardeman |  | Tier 4 |  |  |  |  | 60501, 60505, 61616 | N | N |  |  | 81800 | 81799
81697 | Amber: Construct New 345 kV Station | Interconnect the Kappa load to the new Amber 345 kV station on the Blue Lacy to Reforzar and Blue Lacy to Nelson Sharpe 345 kV lines and add capacitors | CANCEL | Amber |  | Conceptual |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2026-12-31 |  | 345 | 0 | 0 | 0 | 0,523.6 | Nueces |  | Tier 3 |  |  |  |  | 80078, 84550, 84555, 85000 | N |  |  |  | 81698 | 81697
81657 | Verhalen: Construct New 138 kV Terminal | Interconnect the Eta load to the existing Verhalen 138 kV station | CANCEL | Verhalen |  | Conceptual |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 |  | 2026-12-31 |  | 138 | 0 | 0 | 0 |  | Reeves |  | Tier 4 |  |  |  |  | 60207 | N |  |  |  | 81658 | 81657
72029C | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ Solar (23INR0040) and Dori BQ BESS (24INR0196) | Install one generator lead from CEHE 138kV substation Ashville (ASH) to SUNLIT/Dori BQ BESS. Utilize same generator lead as Dori BQ Solar. |  | Ashville | SUNLIT | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 90117 | 72029
72029B | Ashville (ASH) 138kV CEHE Station for SUNLIT/Dori BQ Solar (23INR0040) and Dori BQ BESS (24INR0196) | Install one generator lead from CEHE 138kV substation Ashville (ASH) to SUNLIT/Dori BQ Solar. Utilize same generator lead as Dori BQ BESS. |  | Ashville | SUNLIT | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2026-12-31 00:01 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 90116 | 72029
90045 | Vanhagar to Collier: Construct New 138 kV Line | Interconnect the new Collier load station to the new Vanhagar 138 kV station on the Saragosa to Solstice 138 kV line between Hoef's Road and Verhalen | CANCEL | Vanhagar | Collier | Planned |  | AEP TNC | William Simmons twang1@aep.com 918-599-2635 | TP2024119 | 2027-02-28 |  | 138 | 1.5 | 0 | 0 |  | Reeves | Reeves | Tier 4 |  |  |  |  | 6077, 60127, 60128, 60808 | N | N |  |  | 90914 | 90045
78473A | Odin (ODI) 138kV CEHE Substation | (In terms of completed Waterfowl substation) Loop new CEHE 138kV substation Odin (ODI) into Ckt.36 to create new Ckt.36 COPPER to Odin to Booster tap to Jones Creek. |  | Odin | Brazosport/ Booster | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-04-30 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 |  |  |  |  | 42199, 42215, 42280 | N | N |  |  | 87133 | 78473
78473B | Odin (ODI) 138kV CEHE Substation | Install one generator lead from CEHE 138kV substation Odin (ODI) to VALHAL (VAL) / Valhalla Solar (26INR0042) |  | Odin | VALHAL | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-04-30 00:02 |  | 138 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 3 |  |  |  |  | 42280, 113811 | N | N |  |  | 87134 | 78473
76121 | Beeville Capacitor Addition | Add second 4.8 MVAR step at Beeville |  | Beeville |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-05-01 |  | 69 | 0 | 0 | 0 | 0,4.8 |  |  | Tier 4 |  |  |  |  | 5674 | N | N |  |  | 76122 | 76121
73540 | LCRATSC_Carlson_Substation_Addition | Substation addition to provide Point of Interconnection for Oncor Lund substation addition. |  | Carlson |  | Conceptual |  | LCRATSC | Dylan Preas dylan.preas@lcra.org |  | 2027-05-15 |  | 138 | 0 | 0 | 0 |  | Travis |  | Tier 4 |  |  |  |  | 3650, 7337, 7338 | N | N |  |  | 73541 | 73540
5525 | Forney - Lake Hubbard 345 kV Line | Construct new 345 kV line |  | Forney | Lake Hubbard | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4233 | 2027-05-15 |  | 345 | 0 | 7.5 | 0 |  | Kaufman | Dallas | Tier 2 |  |  |  |  | 2455, 2467 | N | N |  |  | 13252 | 5525
5522 | Lake Hubbard 345/138 kV Switching Station | Construct new 345/138 kV switching station |  | Lake Hubbard |  | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4139 | 2027-05-15 |  | 345 | 0 | 0 | 600 |  | Dallas |  | Tier 3 |  |  |  |  | 2401, 2402, 2455, 12455, 12456 | N | N |  |  | 13249 | 5522
81556 | Haber: Construct New 345 kV Terminal | Interconnect the Crunch load to the new Haber 345 kV station | CANCEL | Haber |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-05-30 |  | 345 | 1 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 81003, 81004 | N |  |  |  | 81557 | 81556
81548 | Haber: Construct New 345 kV Station | Interconnect the Theta load to the new Haber 345 kV station on the Cobra to Static 345 kV line | CANCEL | Haber |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-05-31 |  | 345 | 7 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 8676, 8728, 81003, 81006 | N |  |  |  | 81549 | 81548
81553 | Haber: Construct New 345 kV Terminal | Interconnect the Theta load to the new Haber 345 kV station | CANCEL | Haber |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-05-31 |  | 345 | 1 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 81003, 81005 | N |  |  |  | 81554 | 81553
90020 | Firerock: Install New 138/69 kV Autotransformer | Install new 138/69 kV autotransformer at the Firerock 138/69 kV station | CANCELLED | Firerock |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TP2022133 | 2027-05-31 |  | 138 | 0 | 0 | 130 |  | Coleman |  | Tier 4 | [5 empty] | N |  |  |  | 90021 | 90020
87029 | Parana: Construct New 138 kV Station | Interconnect Portside Energy Center Solar & Storage to the new Parana 138 kV station on the Big Three to Dupont SW 138 kV line | CANCEL | Parana |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | TP2024062 | 2027-05-31 |  | 138 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 80064 | N |  |  |  | 87030 | 87029
69479 | Radiant: Build new 345 kV Station | Interconnect Lunis Creek Solar to the new Radiant 345 kV station on the Cobra to STP 345 kV line | CANCEL | Radiant |  | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2027-05-31 |  | 345 | 0.2 | 0 | 0 |  | Jackson |  | Tier 4 |  |  |  |  | 5915, 8676, 8715 | N |  |  |  | 69480 | 69479
50282 | Adds new Jaguar sub near Twin Pines Switch | Adds new Jaguar sub between Twin Pines Switch and Highlands Sub. For AEP load. | AEP is looking at another location to serve the load. | Highlands Sub | Twin Pines Switch | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2027-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria | Victoria | Tier 4 |  |  |  |  | 5602, 5604, 5609 | N | N |  |  | 50283 | 50282
81655 | Candela: Construct New 345 kV Station | Interconnect the Zeta load to the new Candela 345 kV station | CANCEL | Candela |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2027-06-01 |  | 345 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8317, 8704, 8755 | N |  |  |  | 81656 | 81655
81746 | Calabaza: Construct New 138 kV Terminal | Interconnect the Lambda load to the new Calabaza 138 kV station | CANCEL | Calabaza |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-06-02 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 80380 | N | N |  |  | 81747 | 81746
90018 | Sand Crab: Construct New 138 kV Terminal | Interconnect Canvasback BESS to the Sand Crab 138 kV station | CANCEL | Sand Crab |  | Planned |  | AEP TCC | Brooks Dow deevans@aep.com 918-599-2938 |  | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Calhoun |  | Tier 4 | [5 empty] | N | N |  |  | 90019 | 90018
89993 | STP to Zoisite: Construct New 345 kV Line | Interconnect the HIF load to the new Zoisite 345 kV station on the STP to Zoisite 345 kV line | CANCEL | STP | Zoisite | Planned |  | AEP TCC | Douglas Evans deevans@aep.com 918-599-2938 |  | 2027-06-30 |  | 345 | 1.6 | 0 | 0 |  | Matagorda | Matagorda | Tier 4 | [5 empty] | N | N |  |  | 89994 | 89993
76916 | Snapdragon: Construct New 138 kV Station | Interconnect Desert Vine Solar to the new Snapdragon 138 kV station on the Revilla to Zapata 138 kV line | CANCELLED | Snapdragon |  | Planned |  | AEP TCC/ETT | Zachary Lachiusa jlsolis@aep.com 361-881-5574 | TP2023012 | 2027-06-30 |  | 138 | 0 | 0 | 0 |  | Zapata |  | Tier 4 |  |  |  |  | 8299, 8736, 8957 | N | Y |  |  | 76917 | 76916
44870 | Charlotte 69 kV Station | Charlotte 69 kV Station: Add Cap Bank |  | Charlotte | - | Planned | 976 - 1154 | AEP TCC | Michael Glueck bcogan@aep.com 918-599-2857 | 3734 | 2027-07-01 |  | 69 | 0 | 0 | 0 | 0,7.2 | Atascosa |  | Tier 3 | [5 empty] | N | N |  |  | 44871 | 44870
75810A | Install new 345kV Speedway substation for interconnection to Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. Install generator lead from Speedway to CRADLE solar | Install new 345kV Speedway (SPD) substation for generator interconnection to CRADLE/ Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. |  | Speedway | DOW/Oasis | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-08-30 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | N | N |  |  | 87165 | 75810
75810B | Install new 345kV Speedway substation for interconnection to Cradle Solar (23INR0150). Loop Ckt.18B into Speedway substation to create new Ckt.18 Oasis to Speedway to DOW. Install generator lead from Speedway to CRADLE solar | Install generator lead from Speedway (SPD) substation to CRADLE (CDL) customer substation (23INR0150). |  | Speedway | CRADLE | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-08-30 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | N | N |  |  | 87164 | 75810
87899 | Vaso: Construct New 138 kV Station | Interconnect the Alpha load to the new Vaso 138 kV station on the Cantwell to Citgo North Oak 138 kV line | CANCEL | Vaso |  | Conceptual |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 |  | 2027-08-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8466 | N |  |  |  | 87900 | 87899
4490 | LaPalma: Add 2nd 345/138 kV autotransformer | Add 345/138 kV autotransformer capacity at LaPalma | CANCELLED | LaPalma |  |  | 710 - 0880 | AEP TCC | Teresa Trotman bcogan@aep.com 918-599-2857 | 2904 | 2027-09-30 |  | 345 | 0 | 0 | 675 |  | Cameron |  | Tier 4 |  |  |  |  | 8314, 8317, 8356 | N | N |  |  | 12067 | 4490 | 2014-S15, S16
79456A | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072) | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072). Loop Ckt.18 into Huizache substation to create new Ckt.18 Speedway to Huizache to DOW. |  | Huizache | Speedway/DOW | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 |  |  |  |  | 42500, 43060, 46640 | N | N |  |  | 87175 | 79456
79456B | Install new 345kV Huizache (HUI) substation for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072) | Install generator lead from Huizache (HUI) substation to customer substation HIGHCH (HIC) for generator interconnection to High Chap Solar (25INR0068) & BESS (25INR0072). |  | Huizache | HIGHCH (High Chap) | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2027-12-31 00:01 |  | 345 | 0 | 0 | 0 |  | Brazoria | Brazoria | Tier 4 | [5 empty] | N | N |  |  | 87176 | 79456
72457 | AddKiowaToQuinlanLine | Add 138kV line from Kiowa to Quinlan |  | Kiowa | Quinlan | Planned |  | RCEC | Scott Donhamsdonham@rayburnelectric.com 469-402-2024 |  | 2028-01-01 | 2025-06-01 | 138 | 8 | 0 | 0 |  | Hunt | Hunt | Tier 2 |  |  |  |  | 6796, 6884 | N |  |  |  | 72458 | 72457
99132 | Expand Channelview 138kV substation for Brookview Road BESS (27INR0243) |  |  | Channelview |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Harris | Harris | Tier 4 | [5 empty] | N | N |  |  | 99133 | 99132
99800 | Marconi: Expand 138 kV Station | Interconnect Pajarita BESS to the existing Marconi 138 kV station | CANCELLED | Marconi |  | Planned |  | AEP TCC | Kymberly Cude jlsolis@aep.com 361-881-5574 | TP2025326 | 2028-02-28 |  | 138 | 0 | 0 | 0 |  | Cameron |  | Tier 4 |  |  |  |  | 8266 | N |  |  |  | 99801 | 99800
4834 | Cresson - Rocky Creek 138 kV Line | Construct new line | Project Deferral | Cresson | Rocky Creek | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M5228 | 2028-05-15 |  | 138 | 3 | 0 | 0 |  | Tarrant | Parker | Tier 2 |  |  |  |  | 1881, 2202 | N | N |  |  | 12436 | 4834
102546E | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.06L Plaza to Knight to Gulfgate to increase thermal limits. |  | Plaza | Gulfgate | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-30 |  | 138 | 0 | 9.03 | 0 |  | Chambers | Chambers | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111309 | 102546 | 24RPG028
102546G | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.79F PH Robinson to Seabrook to HANNA to HUNTER in order to increase thermal limits. |  | PH Robinson | HUNTER | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 9.97 | 0 |  |  |  | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111311 | 102546 | 24RPG028
102546C | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.03G Lyondell to Channelview (distribution) to Channelview (ring bus) in order to increase thermal limits. |  | Lyondell | Channelview | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 |  |  |  | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111318 | 102546 | 24RPG028
102546F | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.73B Britmoore to Woodcreek to Memorial to Westheimer in order to increase thermal limits. |  | Britmoore | Westheimer | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 7.19 | 0 |  |  |  | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111310 | 102546 | 24RPG028
102546H | Upgrades related to the Baytown Area Load Addition | Install (3) 7.2 MVAR distribution cap banks at Bayway substation. |  | Bayway |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,21.6 |  |  | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111312 | 102546 | 24RPG028
102546I | Upgrades related to the Baytown Area Load Addition | Install (1) 60 MVAR cap bank at Mykawa substation. |  | Mykawa |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,60 |  |  | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111313 | 102546 | 24RPG028
102546J | Upgrades related to the Baytown Area Load Addition | Install (1) 60 MVAR switchable cap bank at Humble substation. |  | Humble |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,60 |  |  | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111319 | 102546 | 24RPG028
102546K | Upgrades related to the Baytown Area Load Addition | Install (2) 14.4 MVAR distribution cap banks at Treaschwig substation. |  | Treaschwig |  | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0 | 0 | 0,28.8 |  |  | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111314 | 102546 | 24RPG028
102546D | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.08 Hermann to Grant to increase thermal limits. |  | Hermann | Grant | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 0.97 | 0 |  | Harris | Harris | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111316 | 102546 | 24RPG028
102546B | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.86 DALTON (to RAOULT) to BRINE to increase thermal limits. |  | DALTON | BRINE | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 3.39 | 0 |  | Chambers | Chambers | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111315 | 102546 | 24RPG028
102546A | Upgrades related to the Baytown Area Load Addition | Upgrade Ckt.84K HOPSON to WARVUE to increase thermal limits. |  | HOPSON | WARVUE | Conceptual |  | CNP | Wesley Woitt wesley.woitt@centerpointenergy.com 713-207-2760 |  | 2028-05-31 |  | 138 | 0 | 1.27 | 0 |  | Chambers | Chambers | Tier 1 |  | 2025-05-22 | 2025-09-12 | 2025-09-22 |  | N | N |  |  | 111317 | 102546 | 24RPG028
81588 | Chalybe: Expand 345 kV Station | Interconnect the Delta load to the Chalybe 345 kV station on the Chalybe to Kingfisher and Chalybe to Palmito 345 kV lines | CANCEL | Chalybe |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-06-01 |  | 345 | 46 | 0 | 1350 |  | Cameron |  | Tier 4 |  |  |  |  | 8735, 79500, 79501, 88337 | N | N |  |  | 81589 | 81588
90012 | Lumos: Construct New 345 kV Station | Interconnect Ross Solar & Storage to the new Lumos 345 kV station on the Angstrom to Static 345 kV line | CANCEL | Lumos |  | Planned |  | AEP TCC | Doug Evans deevans@aep.com 918-599-2938 | TP2024105 | 2028-06-30 |  | 345 | 0 | 0 | 0 |  | Refugio |  | Tier 4 |  |  |  |  | 8249, 8676, 80082 | N | N |  |  | 90013 | 90012
3818 | Rebuild Calallen to Robstown | Rebuild 4-0 ACSR 69 kV to higher rated and 138 kV capable line, as originally recommended in 2013 RTP. |  | Calallen | Robstown | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2028-12-01 |  | 69 | 0 | 6.26 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5626, 5634 | N | N |  |  | 11275 | 3818 | 2014-S2
87901 | Kallisto: Construct New 138 kV Station | Interconnect the Beta load to the new Kallisto 138 kV station on the Falfurrias to King Ranch Gas Plant 138 kV line | CANCELLED | Kallisto |  | Conceptual |  | AEP TCC | John Solis jlsolis@aep.com 361-881-5574 |  | 2028-12-31 |  | 138 | 0 | 0 | 0 |  | Kleberg |  | Tier 4 |  |  |  |  | 80228 | N |  |  |  | 87902 | 87901
81724 | Calabaza: Construct New 138 kV Station | Interconnect the Omicron load to the new Calabaza 138 kV station on the Gila to Tortuga and Nueces Bay to Saxet 138 kV lines | CANCELLED | Calabaza |  | Conceptual |  | AEP TCC/LCRA | Doug Evans deevans@aep.com 918-599-2938 |  | 2028-12-31 |  | 138 | 0 | 0 | 0 |  | Nueces |  | Tier 4 |  |  |  |  | 8168, 8441, 78568, 80260, 80380 | N |  |  |  | 81725 | 81724
76133 | West Childress: Station Rehab | Rehab the West Childress station | CANCELLED | West Childress |  | Planned |  | AEP TNC | Tong Wang twang1@aep.com 918-599-2635 | TA2020223 | 2029-01-31 |  | 138 | 0 | 0 | 0 |  | Childress |  | Tier 4 |  |  |  |  | 6030, 6135 | N | N |  |  | 76134 | 76133
92874 | Bear_Pen 345 kV Switch | Establish Bear pen 345 kV Switch |  | Bear Pen 345 kV Switch |  | Planned |  | ONCOR | Zagros Shahooei Zagros.Shahooei@oncor.com 817-215-5014 | M3063 | 2029-05-15 |  | 345 | 0 | 0 | 0 |  | Franklin | Franklin | Tier 4 |  |  |  |  | 1695, 2449, 11702 | N |  |  |  | 92875 | 92874
86273 | This project got canceled. | Autos to be upgraded to 672 MVAs. This project got canceled. |  | 7040 | 9328 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 345 | 0 | 0 | 0 |  | Travis | Travis | Tier 4 |  |  |  |  | 7040, 9328, 9329, 9330 | N |  |  |  | 86274 | 86273
6930 | New Paloma Substation | Adds new station and short line from Midstream |  | Midstream | Paloma | Planned |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2029-06-01 |  | 138 | 0.9 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 5643, 5644 | N | N |  |  | 14749 | 6930
86275 | DUNLAP auto already 672MVA. Delete this redundant project. | DUNLAP auto already 672MVA. Delete this redundant project. |  | 9044 | 9045 | Planned |  | AEN | Reza Ebrahimian reza.ebrahimian@austinenergy.com 512-322-6740 |  | 2029-06-01 |  | 345 | 0 | 0 | 672 |  | Travis | Travis | Tier 4 |  |  |  |  | 9044, 9045, 90001, 90007 | N |  |  |  | 86276 | 86275
6743 | Magellan Tank Farm: LCRA Interconnect | Add 138kV Tie Line between Navigation 138kV substation and Magellan's 138kV substation. Add Metering at Magellan's Substation. | Cancelled | Navigation | Magellan |  | 905 - 1083 | AEP TCC/LCRA | Michael Glueck bcogan@aep.com 918-599-2857 | 3689 | 2029-07-01 |  | 138 | 0 | 0 | 0 |  | Nueces | Nueces | Tier 4 |  |  |  |  | 78460 | N | Y |  |  | 14536 | 6743
65648 | Interconnects Faulkner Data Center | Project has been cancelled. |  | TNMP Faulkner (bus # 38124) | Customer substation (bus # 38125) | Planned |  | TNMP | Ross Cloninger Ross.Cloninger@tnmp.com 281-581-4733 |  | 2029-10-01 |  | 138 | 0.15 | 0 | 0 | 0,160 | Reeves | Reeves | Tier 4 |  |  |  |  | 38124, 38125 | N |  |  |  | 65649 | 65648
100165 | Gristmill_Substation_Addition | LCRA TSC will construct a new Gristmill Substation to provide transformation service to a PEC-member load |  |  |  | In-Service |  | LCRATSC | Dylan Preas dylan.preas@lcra.org 512-578-4514 |  | 2030-05-15 |  | 138 | 0 | 0 | 0 |  | Hays | Hays | Tier 4 |  |  |  |  | 7174, 7180, 7181, 7182 | N |  |  |  | 100259 | 100165
5524 | Royse South 345/138 kV Switching Station | Establish new 345/138 kV switching station |  | Royse | Forney | Conceptual |  | ONCOR | Jared Gurley Jared.Gurley@oncor.com 817-215-6079 | M4234 | 2030-05-15 12:00 |  | 345 | 0 | 0 | 0 |  | Rockwall |  | Tier 3 |  |  |  |  | 2437, 2467, 2469, 2470, 2471, 2472, 2474, 2478, 2485, 2702, 2710, 12471 | N | N |  |  | 49918 | 5524 | 2017-NC34
19TPIT0000 | Weser Substation | Replace 5.6 MVA with 69-13.09 kV, 20 MVA transformer |  | Weser |  | Planned |  | GVEC | Dylan Preas dylan.preas@LCRA.org 512-578-4514 |  | 2030-12-17 |  | 69 | 0 | 0 | 0 |  | Goliad |  | Tier 4 |  |  |  |  | 7239 | N | N |  |  | 10694 | 3336
5220 | Move Orange Grove load to 138 kV bus | Move load from the 69 KV to the 138 KV instead of replacing auto. 2015 RTP |  | Orange Grove |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 138 | 0 | 0 | 0 |  | Jim Wells |  | Tier 4 |  |  |  |  | 5660 | N | N |  |  | 12887 | 5220
3822 | San Miguel to Sigmor 138 kV line upgrade | Upgrade San Miguel to Sigmor 138 kV line as recommended in 2013 RTP. Will investigate re-conductoring on existing structures with ACCC and other high temperature conductors. |  | San Miguel | Sigmor | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 138 | 0 | 26.3 | 0 |  | Atascosa | Live Oak | Tier 3 |  |  |  |  | 5689, 5902, 8404 | N | N |  | Studies after the 2013 RTP have shown that AEP's approved project to rebuild the 69 kV Beeville to Three Rivers to 138 kV, TPIT 5166, reduces the loading on this line. STEC believes that rebuilding San Miguel to Sigmor is likely to be justified in the future by load growth and or generation additions. STEC recommends evaluating this project as an option when studies show the need for a project in this area of the transmission system. | 11279 | 3822 | 2013-R102
13TPIT0124 | Airport 69 kV Substation | Build new load serving station in the 69 kV line from Lone Tree to Twin Pines Switch. |  | Airport |  | Conceptual |  | STEC | Teddi Flessner tflessner@stec.org 361-485-6119 |  | 2031-06-01 |  | 69 | 0 | 0 | 0 |  | Victoria |  | Tier 4 |  |  |  |  | 5600, 5601, 5602 | N | N |  |  | 8729 | 1538
15TPIT0004 | Converse - New 138kV Substation | Loop new 138kV substation into future 138kV Martinez to Skyline transmission line |  | Converse | Martinez-Skyline | Planned | T-0177 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0601 | 2032-06-01 |  | 138 | 0.1 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5098, 5294, 5368 | N | N |  | There are no transformers associated with this project | 8143 | 967
12TPIT0009 | Masterson Rd - New 138kV Substation | Loop new 138kV substation into the existing 138kV Cagnon to Howard line. |  | Masterson Rd. | Cagnon-Howard | Planned | T-0910 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | S-0538 | 2032-06-05 |  | 138 | 8 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  |  |  |  | 5054, 5230, 5296 | N | N |  | There are no transformers associated with this project | 9466 | 2218
44963 | USAA Rebuild 138 kV Station | CPSE_USAA 138 kV Substation Rebuild and Line Reconfiguration. |  |  |  | Planned | S-0896 | CPS | Omer Mohammed omohammed@cpsenergy.com 210-353-2035 | T-0285 | 2032-07-01 |  | 138 | 0.6 | 0 | 0 |  | Bexar | Bexar | Tier 4 |  | 2019-01-10 |  |  | 5125, 5170, 5208, 5300, 5450, 5451, 5452, 5453 | N |  |  |  | 44964 | 44963

## RTPProjects
Project Number | Project Name | Transmission Owner | ERCOT Proposed in-service year | TSP MOD in-service year | Status of Project | Associated TPIT ERCOT Project Number(s) | Notes
2022-C1 | Cap bank Addition at AIRPRO Station | CNP | 2025 min
2016-N1 | Kiamichi Energy Facility (140077) 345-kV Reactor Addition | KIOWA POWER PARTNERS LLC (RE) | 2025 min
2021-N2 | City View (1483) – Ceramic (1485) 138-kV Line Terminal Equipment Upgrade | Oncor | 2024
2020-NC19 | Cedar Crest (2493) to Dealey (2842) to West Levee (2400) 138-kV Line Upgrades | Oncor | 2024
2021-NC9 | Sargant – Saint Augustine 138-kV Line Upgrade | Oncor | 2024
2022-NC1 | Waco Northeast Tap (3551) to Waco North (3552) 138-kV Line Upgrade | Oncor | 2024
2022-NC2 | Brand (827) to Ben Davis (968) 138-kV Line Upgrade | GPL | 2024 |  |  | 67170
2022-NC3 | Argyle - Corinth 138-kV Line Upgrade | ONCOR | 2024
2022-NC4 | Wilmer - Southside Filtration Tap East - Kleberg - Seagoville - Seagoville Switch 138-kV Line Upgrade | Oncor | 2024 |  |  | 71178
2022-NC5 | New International Airport Switch 345/138-kV Station | Oncor | 2024
2022-NC6 | Hackberry - DFW D-East 138-kV Line Upgrades | Oncor | 2024
2022-NC7 | Liggett Switch- DFW Area 138-kV Line Upgrades | Oncor | 2024
2022-NC8 | Lake Creek - Elm Mott 138-kV Line Upgrades | Oncor | 2024
2022-NC9 | Tin Roof 345-kV Expansion | Oncor | 2024
2022-NC10 | Randol Mill Tap East - Randol Mill 138-kV Line Upgrade | Oncor | 2024
2021-FW2 | Yucca Drive Switch - Wolfcamp - Courtney Creek 69-kV to 138-kV Line Conversion | Oncor | 2024
2021-FW4 | Rio Pecos - Rankin - Texon Tap - Atlantic Best Tap - Kemper Tap - Big Lake 69-kV to 138-kV Line Conversion | AEP | 2024
2021-FW5 | Caymus TNP - Gas Pad and Caymus TNP - Caymus Compressor TNP 138-kV Line Terminal Equipment Upgrade | TNMP, AEP | 2024
2021-FW6 | Monument Draw TNP to Monument Draw Gray Oak TNP 138-kV Line Terminal Equipment Upgrade | TNMP | 2027
2021-FW7 | TNMP Flat Top 138/25-kV Transformer Upgrade | TNMP | 2024
2021-FW8 | Wink TNP - California TNP 69-kV to 138-kV Line Conversion | TNMP | 2027
2021-FW12 | Moss Switch - Ector Harper - Red Lakes Switch - Penwell POD - Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2021-FW16 | 16th Street TNP - Fort Stockton TNP 69-kV Line Upgrade | TNMP | 2024
2021-FW19 | Morgan Creek SES - Longshore Switch 345-kV Line Upgrade | ONCOR | 2027
2021-FW20 | Lamesa - Key Sub - Gail Sub - Willow Valley Switch 138-kV Line Upgrade | Oncor | 2024
2021-FW23 | Big Spring West - Stanton East 138-kV Line Upgrade | Oncor | 2024
2021-FW24 | Adobe Meadow - Midland East 138-kV Line Upgrade | Oncor | 2025 min
2022-FW1 | Lynx - Tombstone - Fort Stockton Plant - Leon Creek TNP 138-kV Line Upgrade | AEP, TNMP | 2024
2022-FW2 | Cedarvale 345-kV Subtation Expansion | TNMP, Oncor | 2024
2022-FW3 | New Reiter 345/138-kV Substation and Quail East 345-kV Substation | Oncor | 2024
2022-FW4 | New Opyote to Pyote 138-kV Line Addition | TNMP, Oncor | 2024
2022-FW5 | New Load Bus 900012 - New Load Bus 900021 138-kV Line Addition | Oncor | 2024
2022-FW6 | Far West Reactive Power Support Device Additions | TNMP, Oncor, AEP | 2024 |  |  | 65648, 63661, 65642
2022-FW7 | Leon Creek TNP - Airport TNP 138-kV Line Limiting Element Upgrade | TNMP | 2024
2022-FW8 | New Load Bus 900080 - New Load Bus 900032 138-kV Line Addition | Oncor | 2024
2022-FW9 | Cholla 345/138-kV Station Addition | TNMP, Oncor | 2024
2022-FW10 | Dollarhide - Dollarhide Unocal 138-kV Line Upgrade | Oncor | 2024
2022-FW11 | Pecos TNP - Faulkner Toyah TNP 138-kV Line Addition | TNMP | 2024
2022-FW12 | Tarbush TNP - Pig Creek 138-kV Line Upgrade | TNMP, AEP | 2024
2022-FW13 | Yarbrough Sub - Pecos Trails POD - Monahans Tap 2 - Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2022-FW14 | Odessa EHV Switch - Rexall - General Tire Switch - Southwestern Portland Tap - Edwards Tap - Judkins - Sandhills Tap - Wolf Switching Station 138-kV Line Upgrade | Oncor | 2024
2022-FW15 | Holt Switch - Turnbaugh Corner Switch - Scharbauer POI - Oncor 900053 Tap - Notrees Southeast POI - Blockline POD - Amburguey - Yucca Drive Switch 138-kV Line Upgrade | Oncor | 2024
2022-FW16 | Moss Switch - Shin Oak POD - Yucca Drive Switch 138-kV Line Upgrade | Oncor | 2024
2022-FW17 | Moss Switch - Trigas Odessa Southwest - Big Three Odessa Tap 138-kV Line Upgrade | Oncor | 2024
2022-FW18 | Odessa EHV Switch - Trigas Odessa Tap 138-kV Line Upgrade | Oncor | 2024
2022-FW19 | Lamesa - Jim Payne POI - Paul D Tap 138-kV Line Upgrade | Oncor | 2024
2022-FW20 | Spraberry Switch - CRMWD 7 Tap - Meyers Draw - Dewey Lake Tap - Polecat Creek Switch 138-kV Line Upgrade | Oncor | 2025 min |  |  | 45640
2022-FW21 | Midland East – Midland County NW 345-kV Line Rebuild and Second Circuit Addition | Oncor | 2025 min
2022-FW22 | Midessa South 345/138-kV Transformer Upgrade and Second 345/138-kV Transformer Addition | Oncor | 2025 min
2022-FW23 | Consavvy South 345/138-kV Station Addition | Oncor | 2024
2022-FW24 | Faraday - Lamesa - Clearfork - Riverton 345-kV Double Circuit Line Addition | Oncor, WETT | 2024
2022-FW25 | Cedarvale Third 345/138-kV Transformer Addition | TNMP | 2024
2022-FW26 | Tarbush TNP - Leon Creek TNP and Woodward - Airport TNP - Leon Creek TNP 138-kV Line Additions | TNMP | 2024
2021-W1 | Cassava - San Angelo Concho 69-kV to 138-kV Line Conversion | AEP | 2025 min
2021-W2 | Morgan Creek - McDonald 138-kV Line Upgrade | Oncor | 2024
2021-W7 | San Angelo Highland Street - San Angelo South Tap - San Angelo Power Station 138-kV Line Upgrade | AEP | 2025
2021-W9 | San Angelo Paulann - San Angelo North 138-kV Line Upgrade | AEP | 2027
2021-W10 | San Angelo Red Creek - San Angelo Coke Street - Rusthill 138-kV Line Upgrade | AEP | 2025
2021-W12 | Cap Bank Addition at 138-kV Hargrove Substation | AEP | 2027
2022-W1 | China Grove - Getty Tap 138-kV Line Upgrade | ONCOR | 2028
2022-W2 | Morgan Creek SES - Tonkawa 345-kV Line Rebuild and Second Circuit Addition | ONCOR | 2025
2022-W3 | Colorado City - Plowboy 69-kV to 138-kV Line Conversion | ONCOR | 2025
2022-W4 | Abilene Northwest - Abilene Mulberry Creek - Abilene Industrial Park - Abilene Elmcreek 138-kV Line Upgrade | AEP | 2024
2022-W5 | Scurry Chevron - Kndrsacrc - New Load Bus 900041 Tap - Knapp 138-kV Line Upgrade | Oncor | 2027
2022-W6 | Morgan Creek - Westbrook - Latan Howard Tap 69-kV Line Upgrade | Oncor | 2024
2022-W7 | Knapp - Bluff Creek Switch - Exxon Sharon Ridge 138-kV Line Upgrade | Oncor | 2027
2021-WFW1 | Big Lake - Barnhart - Cassava 69-kV to 138-kV Line Conversion | AEP | 2027
2022-WFW1 | Twin Buttes - Hargrove - Pumpjack - Jerry - Russek Street - Big Lake 138-kV line Upgrade | AEP, LCRA TSC | 2024
2022-WFW2 | Midessa South SW - Consavvy - Longshore Switch - Morgan Creek SES 345-kV Line Upgrades | Oncor | 2025 min
2022-WFW3 | Morgan Creek SES - Falcon Seaboard - Midland East 345-kV Line Rebuild and Second Circuit Addition | Oncor | 2025 min
2022-SC1 | Sim Gideon - Bastrop City - Swiftex 138-KV Line Upgrade | LCRA TSC | 2027
2022-SC2 | San Marcos - Camp Gray - Robert Brown Jr - Clear Fork - Lockhart 69-kV to 138-kV Line Conversion | LCRA TSC | 2028
2022-SC3 | Pintail and Mallard 138-kV Substation and Line Additions | Oncor | 2025
2022-SC4 | Samsung 345-kV Substation and Line Addition | Oncor | 2028
2022-SC5 | Sandow Switch 345/138-kV Substation Expansion | Oncor | 2024
2022-SC6 | Howard - San Miguel 345-kV Double Circuit Line Addition and Beck Road 345/138-kV Substation Expansion | CPS, STEC | 2027
2022-SC7 | Decker 138-kV Bus Tie Breaker Upgrade | AEN | 2027
2022-SC8 | Lytton Substation 345/138-kV Transformer Addition | AEN | 2027
2022-S1 | Corpus Christi Sub 138/69-kV Transformer Addition and New 138-kV (8462) Substation and Line Additions | AEP, STEC | 2024
2022-S2 | Fannisub - Goliad 69-kV Line Upgrade | AEP, STEC | 2024
2022-S3 | Pearsall 138/69-kV Transformer Upgrade | STEC | 2027
2022-S4 | Cap Bank Addition at 138-kV Wormser Road Substation | AEP | 2025
2022-S5 | Reactor Addition at 345-kV NSub Substation | AEP | 2027
2022-S6 | San Diego - Freer 69-kV Line Upgrade | AEP | 2024
2022-S7 | Rincon - Gregory 69-kV Line Upgrade | AEP | 2024
2022-S8 | Rio Hondo - Burns - Heidelburg 138-kV Line Upgrade | STEC | 2024
2022-S9 | LA Palma – Haine Dr 138-kV Line Upgrade | AEP | 2025
2022-S10 | Wesmer - Pantera 138-kV Line Upgrade | AEP | 2024
2022-S11 | North Laredo- Unitec - Gateway West Tap 138-kV Line Upgrade | AEP | 2025

## TransmissionOwnerProjContac
TRANSMISSION OWNER | TPIT DISTRIBUTION | Primary Contact | Primary Email Address | Primary Phone | Secondary Contacts | Secondary Email Addresses | Secondary PHONE
AEP | Primary & Secondary | Cindy Miller | Camiller2@aep.com | Cindy Miller: 918 599 2891 | Glen Reed; Brandon Cogan; Mike Forcum; Jeff Ellis; Mina Turner; Lisa Kelso; | gareed@aep.com; bcogan@aep.com; mlforcum@aep.com; dnlyons@aep.com; jlellis@aep.com; myturner@aep.com; lokelso@aep.com; | Michael Forcum: 918 599 2674 Glen Reed: 918 599 2664 Brandon Cogan: 918 599 2857 Jeff Ellis: 918 599 3458
AUSTIN ENERGY | Primary & Secondary | Reza Ebrahimian | Reza.Ebrahimian@austinenergy.com; | Reza: (512) 322-6740 | Hunt, Dandy; Brion Ryan | dandy.hunt@austinenergy.com; Ryan, Brion <Brion.Ryan@austinenergy.com> | Reza:512 322 6740 Dandy:512 322 6748 Brion: 512-322-6879
BPUB | Primary | Luis Martinez | lugmartinez@brownsville-pub.com; | Luis: 956 983 6212 | Javier Martinez Jr. | jamartinez@brownsville-pub.com; | Javier: 956 983 6530
BEPC (BRAZOS ELECTRIC) | Primary & Secondary | Brian Hithersay | bhithersay@brazoselectric.com | Brian: 254-750-6795 | David Albers | dalbers@brazoselectric.com | David: 254 750 6358
BTU | Primary & Secondary | Edward Lopez | elopez@btutilities.com | Edward: 979 821 5697 | David Hering | dhering@btutilities.com | David: 979 821 5652
CNP | Primary & Secondary | Wesley Woitt | wesley.woitt@centerpointenergy.com | Wesley Woitt: 713-207-2760 | Samuel Whisler; Raja Sekhar Kakarla; Cody Mann | samuel.whisler@centerpointenergy.com; rajasekhar.kakarla@centerpointenergy.com; cody.mann@centerpointenergy.com | Samuel Whisler: 713-207-2767 Raja Sekhar Kakarla: 713-207-3614 Cody Mann: 713-207-3149
COCS | Primary | Glenn Gavit | ggavit@cstx.gov | Glenn: 979 764 3682 | Timothy Crabb, Stacy Engelmann | tcrabb@cstx.gov; sengelmann@cstx.gov; | Timothy Crabb 979 764 3439 Stacy Engelmann 979 764 3681
CPS | Primary & Secondary | William Robertson | wrobertson@cpsenergy.com | William: 210 353 4147 | Kenneth Bowen Marcos Terrazas Zuber Vohra Eduardo Olivarez | kbowen@cpsenergy.com; mterrazas1@cpsenergy.com; ZMVohra@cpsenergy.com; EJOlivarez@cpsenergy.com | Kenneth: 210 353 4142 Marcos: 210 353 2451 Zuber: 210 353 4262 Eduardo: 210 353 2357
CTT (Cross Texas Transmission) | Primary & Secondary | Christina Minchew | cminchew@lspower.com | Christina: 636:698:8443 | Ramya Nagarajan | RNagarajan@lspower.com | Ramya: 737-881-5008
DENTON | Primary & Secondary | Mark Zimmerer | Mark.Zimmerer@cityofdenton.com | Mark: 940 349 7169 | Cody Tenorio | Cody.Tenorio@cityofdenton.com | Cody: 940 349 7532
GARLAND | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | David Grubbs Kevin Sills | Dgrubbs@gpltexas.org; ksills@gpltexas.org | David: 972-205-2664 Kevin: 972-205-2603
Golden Spread EC | Primary & Secondary | Chris Koenig | ckoenig@gsec.coop | Chris: 806 349 5201 | Shane McMinn, Mark Reinart | smcminn@gsec.coop; mreinart@gsec.coop | Shane: 806 379 7766 Mark: 806 349 6562
LCRA TSC; BEC (Bandera); BBEC; CTEC; GVEC; NBU; SBEC; RGEC | Primary & Secondary | Dylan Preas | dylan.preas@lcra.org | Dylan: 512-578-4514 | Naved Khan | naved.khan@lcra.org | Naved: 512-578-4176
Lone Star | Primary & Secondary | Chenyan Guo | chenyan.guo@fpl.com | Chenyan: 561-304-5692 | Matt Gomes | Matthew.Gomes@LONESTAR-TRANSMISSION.COM | Matt - 512-236-3133
Oncor | Primary & Secondary | Jared Gurley | Jared.Gurley@oncor.com | Jared: 817-215-6079 | Zahra Jianpanah | Zahra.Jianpanah@oncor.com
PEC | Primary & Secondary | Charles DeWitt | charles.dewitt@peci.com | Charles: 830-225-0673 | Joshua Rivers | joshua.rivers@peci.com | Joshua: 830-330-4192
Rayburn | Primary | Stephen Geiger | sgeiger@rayburnelectric.com | Stephen: 469-402-2112 | Scott Donham | Sdonham@rayburnelectric.com | Scott: 469-402-2024
Sharyland Utilities | Primary & Secondary | Brad Schwarz | bschwarz@huntpower.com | Brad: 512-289-7425 | Mark Caskey | mcaskey@sharyland.com | Mark: 214 978 8243
STEC | Primary & Secondary | Teddi Flessner Long Tran | tflessner@stec.org long.tran@stec.org | Teddi: 361 485 6119 Long: 361 485 6318 | Paul Person Loretta Gonzalez | pperson@stec.org; lgonzalez@stec.org; | Paul: 361 485 6151 Loretta: 956 377 7120
TMPA | Primary & Secondary | Danh Huynh | Dhuynh@gpltexas.org | Danh: 972 205 3826 | Kevin Sills | Ksills@gpltexas.org | Kevin: 972-205-2603
TNMP | Primary & Secondary | Ross Cloninger | ross.cloninger@tnmp.com | Ross: 281-581-4733 | Xia, Tao Roberts, Vincent Gerety, Chris | Tao.Xia@tnmp.com; Vincent.Roberts@tnmp.com; Christopher.Gerety@tnmp.com; | Tao: 281-581-4764 Vincent:409-949-5608 Chris:409-949-5605
Wind Energy Texas Transmission (WETT) | Primary | Chris Ramirez | cramirez@wettllc.com | Chris: 737-218-4525 | Yang Zhang | yzhang@wettllc.com | Yang: 737-218-4542

## TSPResponsibility
Field Name | Required/ Optional
ERCOT Project Number | Required
RTP Project Number | Required if in RTP
RPG Project Number | Required for submitted Tier 1, 2, and 3 projects
Project Title | Required
Project Description | Optional
Comments/Reasons for Delays/Cancellations/Speedup | Optional
Terminal "from" Location | Optional
Terminal "to" Location | Optional
Transmission Status | Optional
Associated Projects (project number) | Optional
Transmission Owner | Required
TSP/Company Contact | Required
Transmission Owner Project Number | Optional
Projected In-Service Date (Month/Yr) | Required
Actual In-Service Date (Month/Yr) | Required once energized in the field
CONFIDENTIAL Total Project Estimated Cost | Required
Service Level kV | Required
Trans Circuit Miles New | Optional
Trans Circuit Miles Rebuilt or Upgraded | Optional
Autotransformer Capacity (MVA) | Optional
Reactive Capability Added | Optional
County Location for Substation or for a Line | Optional
County Location for Ending Point for a Line | Optional
Planning Charter Tier | Required
Date Submitted TO ERCOT for RPG Review | Required for submitted Tier 1, 2, and 3 projects
Date RPG Review Completed (Month/Yr) | Required for submitted Tier 1, 2, and 3 projects, if RPG review has been completed.
Date ERCOT BOD Review Completed | -Required for submitted Tier 1 projects, if ERCOT BOD review completed.
SSWG Base Case Related Bus Numbers | Required
Is the project reflected in SSWG Base Cases? | Required
Part of Interface (Y/N) | Required
Requested Additional Information | Optional

## Cost Summary Info
Net Effective Date | Actual In-Service Date | Tab | Cost Summary
past < effective < TPIT | past < actual < TPIT | Complete | Year Completed
past < effective < TPIT | TPIT < actual < future | Planned | Current Year Planned
past < effective < TPIT | actual == NULL | Planned | Current Year Planned
TPIT < effecitve < Current Year end | past < actual < future | Planned | Current Year Planned
TPIT < effecitve < Current Year end | actual == NULL | Planned | Current Year Planned
Current Year end < effective < future | past < actual < future | Future | Year
Current Year end < effective < future | actual == NULL | Future | Year