## Slide 1
Project Update
March 9, 2022
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2022 Release Targets
  In-Flight Strategic Projects
    Fast-Frequency Response (FFR) Advancement
    DGR/DESR Implementation
    BES Combo Model Implementation
  Securitization Update
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1096 – Require Sustained Two-Hour Capability for ECRS and Four-Hour Capability for Non-Spin
    SCR818 – Changes to Incorporate GIC Modeling Data into Existing Modeling Applications
  Technology Working Group
    Meeting held on 2/10/2022
    Next meeting planned for 3/31/2022
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 February Release – R1 – Various dates Complete
  NPRR1005 – Clarify Definition of Point of Interconnection (POI) and Add Definition Point of Interconnection Bus (POIB)
  NOGRR210 / RRGRR025 – Related to NPRR1005
  LPGRR068 – Add BUSLRG and BUSLRGDG Profile Types
  NPRR917 – Nodal Pricing for SODGs and SOTGs
  NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
  NPRR1065 – Implementation Adjustment for NPRR917
  NPRR1054 – Removal of Oklaunion Exemption Language (partial implementation)
2022 March Release – R2 – 3/29/2022-3/31/2022 4/5/2022-4/7/2022
  No revision requests
2022 May Release – R3 – 5/24/2022-5/26/2022 In Flight
  NPRR939 – Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions
  NPRR1093 – Load Resource Participation in Non-Spinning Reserve
  NPRR1101 – Create Non-Spin Deployment Groups made up of Generation Resources Providing Off-Line Non- Spinning Reserve and Load Resources that are Not Controllable Load Resources Providing Non-Spinning Reserve
  SCR800 – Addition of DC Tie Ramp to GTBD Calculation
  SCR809 – Changes to External Telemetry Validations in Resource Limit Calculator
  SCR814 – Point-to-Point (PTP) Obligation Bid Interval Limit
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.
2/1/2022
2/4/2022
2/10/2022-2/11/2022

## Slide 4: 2022 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Various Dates | April 4/5 – 4/7 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NOGRR210 RRGRR025 NPRR917 NPRR1052 NPRR1065 NPRR1073 NPRR1016 PGRR082 NOGRR212 | SCR814 | NPRR939 NPRR1093 NPRR1101 SCR800 SCR809 SCR814 | NPRR1108 | FFR Advancement (NPRR863 FFR) | TBD
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
E
E
E
E
E
E
ü
ü
ü
ü
Securitization Subchapter N March Go-Live
ECRS project started in 1/2022 with a go-live target prior to the EMS Freeze
1/1
EMS Freeze
Mid-2023 – Mid-2024
E
ü
ü
ü
ü
DGR/DESR
NPRR1054(a) – Portion of gray box
SCR789 Ph2
Late 2022
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 879, 885, 904, 918, 930, 935(b), 936, 941, 945, 962, 965, 1004, 1006, 1019, 1023, 1030, 1032, 1034, 1040, 1057 SCRs: 799, 805, 812 Market Guides: PGRR066, PGRR076 Other Binding Docs: OBDRR009
P
ü
ü
ü
ü

## Slide 5: In-Flight Strategic Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on 6/22/2021)
    Planned go-live for 2021-R6 (December 2021)
    NPRR863, NPRR1015, NPRR1079, NOGRR187
  PR354-01 DGR/DESR Implementation (successful go-live in early February)
    Target first new DGR in model in the April 2022 model load
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
  PR353-01 BES Combo Model Implementation – currently On Hold
    Target go-lives are TBD
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
ESR: Energy Storage Resource
DGR: Distributed Generation Resource
BES: Battery Energy Storage
The BES Combo Model project will be divided into multiple discreet efforts in order to increase the probability of moving forward on the most critical elements
Revised go-live target = 2022-R5
Orange text: 1/1/2022 go-live for DGR/DESR registration purposes

## Slide 6: Securitization Update
NPRR1103 Securitization – PURA Subchapter M Default Charges
  Approved by Board of Directors on 12/10/2021
  Approved by PUCT on 12/16/2021
NPRR1114 Securitization – PURA Subchapter N Uplift Charges
  Approved by PRS on 1/13/2022
  Approved by TAC on 1/31/2022
  Pending Board and PUCT consideration in March
Clarification NPRRs Posted
  NPRR1122 – Clarifications for Securitization Default Charges
  NPRR1123 – Clarifications for Securitization Uplift Charges
See 2/23/2022 TAC materials for latest update

## Slide 7: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1096 | Require Sustained Two-Hour Capability for ECRS and Four-Hour Capability for Non-Spin | 2022 | 2650 | $30k-$50k, 3-5 months Impacted Systems: NDCRC, EMS, Reporting Recommend alignment with NPRR863 Rank ECRS portion to be included in ECRS project Non-spin portion targeted for 2022 delivery
SCR818 | Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | 2023 | 3710 | $300k-$500k, 9-12 months Impacted Systems: Network Model Systems Likely approach: Deliver this project after completion of the in-flight SCR789 Phase 2 project
SCR820 | Operator Real-Time Messaging During Emergency | TBD | TBD | Additional time requested to complete IA Targeting IA for 4/14/2022 PRS meeting
PPL Rank Information
Next available 2022 Rank in Business Strategy = 3580
Next available Rank in Regulatory = 340
Options for…

## Slide 8: ERCOT Technology Working Group (TWG)
First meeting held on 2/10/2022 – Thank you to all who participated!
  Topics reviewed
    NPRR1093 XSD changes 2022-R3 target go-live
    FFRA / NPRR863 update 2022-R5 target go-live
    ECRS / NPRR863 update Release is TBD
    WAN refresh and encryption project update Encryption go-live by 4/30/2022
    NERC EMSWG update Q3 virtual conference
    MMS UI/OS UI IE support update
    MOTE enhancements
    SCR820 – Operator Real-Time Messaging IA underway
  Meetings docs posted on ERCOT.com
    https://www.ercot.com/calendar/event?id=1643307467620
Next meeting is 3/31/2022
  Agenda being formed over the coming days