## Slide 1
Projects with Interface Change Requirements
NPRR1093, FFRA, ECRS
Matt Mereness
March 31, 2022

## Slide 2: Outline
Purpose
Protocol Projects with Upcoming Market Facing Changes
  NPRR1093 Loads in Non-Spin
  NPRR863/FFRA delivery
  NPRR863/ECRS delivery
Discussion of Market Readiness concepts
Feedback for next TWG Meeting
Appendix
  NPRR1093 Details

## Slide 3: Reminder of purpose for interface change discussion
Leveraging the TWG forum to communicate future Protocol project changes where MPs will be required to change their ERCOT interfaces.
Target audience is Market Participant staff and/or vendors responsible for developing and deploying systems to adapt to market interface changes with ERCOT.
ERCOT plans to publish interface changes earlier in project process and use this forum to share technical details, listen to feedback, and provide estimated project dates including MOTE availability and Go-Live dates.
Note that this will not be the forum for project business details (will be in project readiness workshops).
3

## Slide 4: NPRR1093 Load Resource Participation in Non-Spinning Reserve
High-priority PUCT project
Expands procurement of Non-Spin to include Load Resources
  “Allow Load Resources that are not Controllable Load Resources to participate in Non-Spinning Reserve so that additional capacity is available to ERCOT Operators for the upcoming winter and summer 2022.” excerpt from NPRR
ERCOT just completed Business Requirements and planning for production 2022 Release 3 (late May 2022)
ERCOT worked to minimize interface changes
  Relatively minor changes to Market MMS XML submission
    Changes limited to new values with AS Self-Arrangement and AS Trades for Non-Spin from Load
    Backward compatible (traditional Non-Spin AS type remains the same)
  No changes to Telemetry/ICCP
  Changes to Reports

## Slide 5: Library of NPRR1093 Requirement Changes
Technical Specification Changes:
  Posted at last TWG (https://www.ercot.com/calendar/event?id=1643307467620)
    External_Web_Services_XSD_V1.22_NPRR1093
    EIP_External_Interfaces_Specification_v1_22
      Note the word doc leverages “gray boxed” language to capture multiple protocol changes.
    MarketSubmissionValidationRules_NP4-450-NPRR1093
Transaction Changes (more detail in Appendix):
  AS Trades (new type of Non-Spin, NSPNM)
  AS Self-Arrangement (new type of Non-Spin, NSPNM)
  Changes to market facing reports on next slide
Estimated Key Dates (will be in future Market Notices also):
  Project/Business workshop date: April 25, 2022 1-3pm
  MOTE availability date May 5, 2022
  Go-Live date: May 26, 2022

## Slide 6: Report Impact Summary – NPRR1093
Report | Change Summary
NP6-557-CD Group Assignments for NCLRs and Off-Line Generation Resources participating in NSRS | New Report - Daily Certified for QSEs Rpt ID: 21939
NP6-323-CD Real-Time ORDC and Reliability Deployment Price Adders and Reserves by SCED Interval | Report Modification Rpt ID: 13221 Change: Addition of new column ‘RTNCLRNSCAP’
NP6-792-ER Historical Real Time ORDC and Reliability Deployment Price Adders and Reserves | Report Modification Rpt ID: 13231 Change: Addition of new column ‘RTNCLRNSCAP’
NP8-385-ER Monthly Non-Spin NCLR Performance Report | New Report - Monthly Certified for QSEs Rpt ID: 22069
NP3-911 2-Day Ancillary Services Disclosure Output File: 2d_Self_Arranged_AS_NSPNM | Report Modification Rpt ID: 13057 Change: New CSV output file within the 2-Day Self-Arranged AS ‘2d_Self_Arranged_AS_NSPNM’ due to new NSPNM subtype
NP3-966-ER 60D DAM Disclosure Report Output file: 60-Day QSE-Specific Self-Arranged AS in DAM | Report Modification Rpt ID: 13051 Change: Current NSPIN Column to be split out to account for new subtype of NSPNM
NP3-965-ER 60D SCED Disclosure Report Output file: 60-Day QSE-Specific Self-Arranged AS in DAM | Report Modification Rpt ID: 13052 Change: Current NSPIN Column to be split out to account for new subtype of NSPNM

## Slide 7: FFRA (in NPRR863) Fast-Frequency Response Advancement Project
High-priority PUCT project
Incorporates Fast-Frequency Response into Response Reserves
Project scheduled for October 2022 Go-Live in R5
  Originally was planned for go-live Dec 2021
Project in re-planning stages
  Interface specifications previously published are still valid for FFRA changes
    See detailed content from 12/7/2021 workshop
    Creates 3 sub-types of RRS products
    Structural changes to XML and telemetry additions
    Changes affect all QSEs that schedule/sell/buy AS (not backward compatible)
  Planning for extending time in MOTE (time for QSE break/fix)
  ERCOT exploring technical market readiness options (measure MOTE success)
    Potentially discuss more at next TWG

## Slide 8: Library of FFRA Requirement Changes
Reminder of specs posted in library zip file at 12/7/2021 workshop
MarketSubmissionValidationRules_NP4-450
External Web Services XSD V1.21
EIP External Interfaces Specification v1.21 (FFR & DGR)
ERCOT_Nodal_ICCP_Communications_Handbook_v3_11_Change_Upd
Current Day Reports XSD v6.xx –Excerpt for workshop
Disclosure Reports Column Definitions Guide
Estimated Key Dates (will be in future Market Notices also):
  Project/Business workshop dates and cutover details: TBD
  MOTE availability dates: Aug-Sep 2022
  Go-Live date: October 2022

## Slide 9: ECRS (in NPRR863) ERCOT Contingency Reserve Service
High-priority PUCT project
Incorporates new 10-minute Ancillary Service (ERCOT Contingency Reserve Service).
Project recently initiated and targeting 2023 Go-Live in first half of year.
Project Impacts
  Similar to FFRA in terms of level of changes as this new Ancillary Service will impact all AS-related submissions and not be backward compatible.
ERCOT sharing high-level schedule and impacts so MPs can plan for development resources and budget as needed.

## Slide 10: Discussion of Confirming Market Readiness (FFRA/ECRS)
ERCOT is improving communication and the MP feedback loop for FFRA& ECRS implementations with 3 concepts below since both affect all Ancillary Service submissions (creates reliability risk if QSEs cannot submit AS transactions):
Concept of sending Confirmation email to all QSE Authorized Reps to confirm they are aware of the system impacts and are preparing for changes in Ancillary Service submissions for October 2022 delivery of FFRA project.
Concept of Longer MOTE Duration
Concept of Providing feedback loop on successful submissions by QSEs
  Weeks 1 & 2 - No submission summary published
  Weeks 3 & 4 - Publish submission summary by QSE (target 50% success)
  Weeks 5 & 6 - Publish submission summary by QSE (target 75% success)
  Week 7 - Publish submission summary by QSE (target 95% success)
Concepts will provide more communication and assurance for successful go-live.

## Slide 11: Feedback for next TWG Meeting
Current plan for next TWG meeting:
  Continue discuss of changes and/or additional details for:
    NPRR1093 (R3-May 2022 release)
    NPRR863/FFRA (R5-Oct 2022 release)
    NPRR863/ECRS (first half 2023 release)
    Discussion of Market Readiness concepts for FFRA & ECRS
    Any new projects on horizon
ERCOT open to feedback/questions for next TWG meeting
  Feedback in meeting, or can be directed to Matt.Mereness@ercot.com

## Slide 12: Appendix
NPRR 1093 Details

## Slide 13: NPRR 1093 XSD changes
External Web Services XSD V1.22_NPRR1093
ERCOTCommonTypes

## Slide 14: NPRR 1093 XSD changes
ERCOTCommonTypes

## Slide 15: NPRR 1093 Interface changes
EIP_External_Interface_Specifications_v1_22

## Slide 16: NPRR 1093 Interface changes
EIP_External_Interface_Specifications_v1_22

## Slide 17: NPRR 1093 Interface changes
EIP_External_Interface_Specifications_v1_22

## Slide 18: NPRR 1093 Interface changes
EIP_External_Interface_Specifications_v1_22

## Slide 19: NPRR 1093 Interface changes
EIP_External_Interface_Specifications_v1_22

## Slide 20: NPRR 1093 Market Validation Changes
MarketSubmissionValidationRules_NP4-450-NPRR1093