|  |  |  |  |
| --- | --- | --- | --- |
| NPRR Number | [1092](https://www.ercot.com/mktrules/issues/NPRR1092) | NPRR Title | Reduce RUC Offer Floor and Remove RUC Opt-Out Provision |
| Impact Analysis Date | | April 5, 2022 | |
| Estimated Cost/Budgetary Impact | | Phase 1:  Less than $5k O&M  Phase 2:  Between $50k and $75k | |
| Estimated Time Requirements | | Phase 1:  Changing the Reliability Unit Commitment (RUC) offer floor from its current value to a new value with units of dollars per MWh, through a parameter update.  No project required. Phase 1 of the NPRR can be implemented following Public Utility Commission of Texas (PUCT) approval.  Phase 2:  4 to 6 months  Changing the process by which a QSE can opt out of RUC Settlement for their Resource.  Phase 2 of the NPRR is dependent upon Public Utility Commission of Texas (PUCT) prioritization and approval. | |
| ERCOT Staffing Impacts (across all areas) | | Implementation Labor: 100% ERCOT; 0% Vendor  Ongoing Requirements: No impacts to ERCOT staffing. | |
| ERCOT Computer System Impacts | | The following ERCOT systems would be impacted:   * Market Operation Systems 100% | |
| ERCOT Business Function Impacts | | No impacts to ERCOT business functions. | |
| Grid Operations & Practices Impacts | | ERCOT will update grid operations and practices to implement this NPRR. | |

|  |
| --- |
| Evaluation of Interim Solutions or Alternatives for a More Efficient Implementation |
| None offered. |

|  |
| --- |
| Comments |
| None. |