## Slide 1
Project Update
April 14, 2022
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2022 Release Targets
  In-Flight Strategic Projects
    Fast-Frequency Response (FFR) Advancement
    DGR/DESR Implementation
    BES Combo Model Implementation
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1112 – Elimination of Unsecured Credit Limits
    NPRR1121 – Add Posting Requirement to Exceptional Fuel Cost Submission Process
  Technology Working Group
    Meeting held on 3/31/2022
    Next meeting tentatively planned for 5/12/2022
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 March Release – R2 –4/5/2022-4/7/2022 Complete
  No revision requests
2022 May Release – R3 – 5/24/2022-5/26/2022 In Flight
  NPRR939 – Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions
  NPRR1093 – Load Resource Participation in Non-Spinning Reserve
  NPRR1101 – Create Non-Spin Deployment Groups made up of Generation Resources Providing Off-Line Non- Spinning Reserve and Load Resources that are Not Controllable Load Resources Providing Non-Spinning Reserve
  Other RRs related to NPRR1093 – NOGRR232, OBDRR032, ODBRR033
  NPRR1113 – Clarification of Reg-Up Schedule for Controllable Load Resources in A/S Imbalance
  SCR800 – Addition of DC Tie Ramp to GTBD Calculation
  SCR809 – Changes to External Telemetry Validations in Resource Limit Calculator
  SCR814 – Point-to-Point (PTP) Obligation Bid Interval Limit
2022 July Release – R4 – 7/26/2022-7/28/2022 In Flight
  NPRR1108(a) – ERCOT Shall Approve or Deny All Resource Outage Requests
    Outage Scheduler portion in 2022-R4 release
    Reporting portion planned for 2022-R5
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2022 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Various Dates | April 4/5 – 4/7 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NOGRR210 RRGRR025 NPRR917 NPRR1052 NPRR1065 NPRR1073 NPRR1016 PGRR082 NOGRR212 |  | NPRR939 NPRR1093 NPRR1101 NPRR1113 NOGRR232 OBDRR032 OBDRR033 SCR800 SCR809 SCR814 | NPRR1108(a) | FFR Advancement (NPRR863 FFR) NPRR1108(b) | TBD
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
E
E
E
E
E
E
E
E
E
E
ü
ü
ü
ü
Securitization Subchapter N March Go-Live
ECRS project started in 1/2022 with a go-live target prior to the EMS Freeze
1/1
EMS Freeze
Mid-2023 – Mid-2024
E
P
ü
ü
ü
ü
DGR/DESR
NPRR1054(a) – Portion of gray box
NPRR1108(a) – Outage Scheduler changes
NPRR1108(b) – Reporting changes
SCR789 Ph2
Late 2022
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 879, 885, 904, 918, 930, 935(b), 936, 941, 945, 962, 965, 1004, 1006, 1019, 1023, 1030, 1032, 1034, 1040, 1057 SCRs: 799, 805, 812 Market Guides: PGRR066, PGRR076 Other Binding Docs: OBDRR009
P
ü
ü
ü
ü
NPRR1120 Firm Fuel Supply Service RFP
Issue no later than 8/1/2022
NPRR1093 Update
Workshop on 4/25/2022
MOTE available 5/5/2022
NPRR1120 Firm Fuel Supply Service
Contracts start in November

## Slide 5: In-Flight Strategic Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on 6/22/2021)
    Planned go-live for 2021-R6 (December 2021)
    NPRR863, NPRR1015, NPRR1079, NOGRR187
  PR354-01 DGR/DESR Implementation (successful go-live in early February)
    Target first new DGR in model in the April 2022 model load
    NPRR917 – Nodal Pricing for SODGs and SOTGs
    NPRR1016 – Clarify Requirements for DGRs and Distribution Energy Storage Resources
    NPRR1052 – Load Zone Pricing for Settlement Only Storage Prior to NPRR995
    NPRR1065 – Implementation Adjustment for NPRR917
    PGRR082 – Revise Section 5 and Establish Small Generation Interconnection Process
    Related RRs – NOGRR212, RRGRR026
  PR353-01 BES Combo Model Implementation – currently On Hold
    Target go-lives are TBD
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    Related RRs – NOGRR204, NOGRR208, OBDRR017, PGRR081, RRGRR023
ESR: Energy Storage Resource
DGR: Distributed Generation Resource
BES: Battery Energy Storage
The BES Combo Model project will be divided into multiple discreet efforts in order to increase the probability of moving forward on the most critical elements
Revised go-live target = 2022-R5
Orange text: 1/1/2022 go-live for DGR/DESR registration purposes

## Slide 6: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1121 | Add Posting Requirement to Exceptional Fuel Cost Submission Process | 2022 | 3590 | $25k-$45k, 3-5 months Impacted Systems: Reporting systems Other comments…
SCR820 | Operator Real-Time Messaging During Emergency | TBD | TBD | Additional time requested to complete IA Targeting IA for 5/12/2022 PRS meeting An additional month may be needed
PPL Rank Information
Next available 2022 Rank in Business Strategy = 3590
Next available Rank in Regulatory = 340
Options for…

## Slide 7: ERCOT Technology Working Group (TWG)
Chair: Venkat Tirupati, ERCOT
Vice-Chair: Kevin Bunch, EDF Energy NA
Meeting held on 03/31/2022 – Thank you to all the participants
Topics Reviewed
  NPRR1093 (May 2022)
  NPRR863 Phase 2 FFRA (Oct 2022)
  NPRR863/ECRS (Mid-2023)
  Public API and API improvements
  Extracts (CODE/MODE) posting timelines
  Retiring Legacy MIS public report functionality
  NERC EMSWG Update
  MMS/OS UI web browser
  MOTE enhancements
  Operator Real-Time Messaging SCR820
  CIM 16 upgrade
  TLS 1.0 and 1.1 deprecation
Next meeting is tentatively scheduled for 05/12/2022