## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2022-03-24
Agenda Item: | Decision / Resolution | Action Items :
January Meeting Notes
| Texas SET approved the February meeting notes. | The Texas SET Vice Chair will have the notes posted to the February meeting page key documents.
Retail Market Subcommittee (RMS) Update
RMGRR168, Modify ERCOT Responsibilities During the Mass Transition | The Texas SET Chair conducted a review of the Texas SET comments language as directed by RMS. ERCOT stated that they consulted the Public Utility Commission of Texas (PUCT) and stated that ERCOT did not receive a signoff from the PUCT on the new language. Texas SET discussed removing the language added for the Retail Market Guide (RMG) Section 7.11.3.2, (8), from the Texas SET comments; then adding different language to restate the CR requirements as a modified version of the Texas SET comments. The Centerpoint representative offered some language changes. | The Texas SET Chair will incorporate the modified language into the Texas SET comments; then send them to the working group for feedback to be given by Close of Business on March 30th; then send it on to ERCOT to post for the RMS April 5th meeting.
RMGRR168, Modify ERCOT Responsibilities During the Mass Transition--Texas SET Comments | See above
Draft NPRR to support RMGRR168, Modify ERCOT Responsibilities During the Mass Transition--Texas SET Comments | See above
ERCOT Update
Market Flight Test | ERCOT presented the flight update. The Flight Administrator shared a unique issue that occurred during the flight between one CR and TDSP involving a bank payment. ERCOT stated that the TDSP requested to allow the script to be delayed until next Monday to let the CR have the opportunity to correct the issue coming through the bank. The Centerpoint Energy representative asked ERCOT if they Texas Market Test Plan (TMTP) needs to be updated to cover ERCOT in situations like this. All agreed to let the scenario play out before determining what or if anything needs to be added to the TMTP.
Discussion Items
Other Business
Next Meeting--Face-to-face | 2022-04-20
Attendees F-T-F
Attendees Webex
Birdie Cobb Centerpoint Energy | Kathy Scott Centerpoint Energy
Carolyn Reed Centerpoint Energy | Kyle Patrick NRG
Dave Michaelson ERCOT | Melinca Earnest AEP
Deb Belin Earth Etch | Mark Pepdjonovic ESG
Diana Rehfeldt TNMP | Mark Ruane ERCOT
Eric Lotter GridMonitor | Paul Yockey ERCOT
Heather Falls ONCOR | Sam Pak ONCOR
Jeff Chen Centerpoint Energy | Sheri Wiegand Vistra
Jesse O Macias AEP Texas | Stephen Wilson TXU Energy
Jim Lee TEC | Steve Pliler Vistra
Jordan Troublefield ERCOT | Tyler Krueger BDE
Kathryn Thurman ERCOT