## Slide 1
Project Update
May 11, 2022
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2022 Release Targets
  In-Flight Strategic Projects
    Fast-Frequency Response (FFR) Advancement
    DGR/DESR Implementation
    BES Combo Model Implementation
  Priority/Rank Options for Revision Requests with Impacts
    RMGRR168 – Modify ERCOT’s Mass Transition Responsibilities
  Technology Working Group
    Next meeting scheduled for 5/19/2022
  “Not Started” Revision Request List
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 May Release – R3 – 5/24/2022-5/26/2022 In Flight
  NPRR939 – Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions
  NPRR1093 – Load Resource Participation in Non-Spinning Reserve
  Other RRs related to NPRR1093 – NOGRR232, OBDRR032, ODBRR033, OBDRR035
  NPRR1101 – Create Non-Spin Deployment Groups made up of Generation Resources Providing Off-Line Non- Spinning Reserve and Load Resources that are Not Controllable Load Resources Providing Non-Spinning Reserve
  NPRR1113 – Clarification of Reg-Up Schedule for Controllable Load Resources in A/S Imbalance
  SCR800 – Addition of DC Tie Ramp to GTBD Calculation
  SCR809 – Changes to External Telemetry Validations in Resource Limit Calculator
  SCR814 – Point-to-Point (PTP) Obligation Bid Interval Limit
2022 July Release – R4 – 7/26/2022-7/28/2022 In Flight
  NPRR1108 – ERCOT Shall Approve or Deny All Resource Outage Requests
    Correction to April PRS report: Outage Scheduler changes and related reporting will go-live in 2022-R4
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2022 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Various Dates | April 4/5 – 4/7 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NOGRR210 RRGRR025 NPRR917 NPRR1052 NPRR1065 NPRR1073 NPRR1016 PGRR082 NOGRR212 |  | NPRR939 NPRR1093 NPRR1101 NPRR1113 NOGRR232 OBDRR032 OBDRR033 OBDRR035 SCR800 SCR809 SCR814 MarkeTrak User Interface Refresh | NPRR1108 | FFR Advancement (NPRR863 FFR) NPRR1108(b) | TBD
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
E
E
E
E
E
E
E
E
E
E
E
ü
ü
ü
ü
Securitization Subchapter N March Go-Live
ECRS project started in 1/2022 with a go-live target prior to the EMS Freeze
1/1
EMS Freeze
Mid-2023 – Mid-2024
E
ü
ü
ü
ü
DGR/DESR
NPRR1054(a) – Portion of gray box
NPRR1108(a) – Outage Scheduler changes
NPRR1108(b) – Reporting changes
SCR789 Ph2
Late 2022
TBD Items | NPRRs: 484, 825(b), 826, 829, 841, 857, 879, 885, 904, 918, 930, 935(b), 936, 941, 945, 962, 965, 1004, 1006, 1019, 1023, 1030, 1032, 1034, 1040, 1057 SCRs: 799, 805, 812 Market Guides: PGRR066, PGRR076 Other Binding Docs: OBDRR009
P
ü
ü
ü
ü
NPRR1120 Firm Fuel Supply Service RFP
Issue no later than 8/1/2022
NPRR1093
Workshop 4/25/2022
MOTE 5/5/2022
MOTE Q&A 5/12/2022
NPRR1120 Firm Fuel Supply Service
Contracts start in November
6/4 – 6/6

## Slide 5: In-Flight Strategic Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on 6/22/2021)
    Planned go-live for 2021-R6 (December 2021)
    NPRR863, NPRR1015, NPRR1079, NOGRR187
  PR354-01 DGR/DESR Implementation (successful go-live in early February)
    Target first new DGR in model in the April 2022 model load
    NPRR917, NPRR1016, NPRR1052, NPRR1065, PGRR082, NOGRR212, RRGRR026
  PR353-01 BES Combo Model Implementation – decoupled into separate efforts below
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    TARGETING IMPLEMENTATION IN 2022
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    TARGETING IMPLEMENTATION IN 2022
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    POTENTIAL IMPLEMENTATION IN 2022
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    RUN IN PARALLEL WITH RARF REPLACEMENT – TARGET GO-LIVE 2023
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    EXPECTED IMPLEMENTATION AFTER ECRS IN 2023
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    IMPLEMENTATION TIMELINE TBD
ESR: Energy Storage Resource
DGR: Distributed Generation Resource
BES: Battery Energy Storage
Revised go-live target = 2022-R5
RELIABILITY
RELIABILITY
Project Complete!

## Slide 6: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
RMGRR168 | Modify ERCOT’s Mass Transition Responsibilities | 2022 | 3600 | $50k-$75k, 5-8 months Impacted Systems: Registration systems Work into project queue without disrupting other projects Discussed at 5/3/2022 RMS meeting
SCR820 | Operator Real-Time Messaging During Emergency | TBD | TBD | Additional time requested to complete IA Extra time has been needed due to: Outreach to other ISOs Time to research potential solutions (build vs. buy) Estimation team involved in critical in-flight projects Time to estimate takes longer when a new system is to being contemplated Targeting IA for June or July PRS meeting
PPL Rank Information
Next available 2022 Rank in Business Strategy = 3600
Next available Rank in Regulatory = 340
Options for…

## Slide 7: ERCOT Technology Working Group (TWG)
Next meeting is scheduled for 05/19/2022
Agenda still under development

## Slide 8: “Not Started” Revision Request List
A file with “Not Started” Revision Requests will be posted prior to the May PRS meeting
Preliminary comments will be included on some line items
ERCOT will be working on additional comments prior to June PRS
Primary discussion at May PRS will be the structure of the posted file to help everyone prepare for a more detailed discussion in June
Follow-up discussion to be held at the June/July PRS:
  Items that conflict with critical in-flight initiatives
  Items that may have a pathway to implementation in the next 6-12 months
  Market feedback on priority of the items in #2 above